## Projects
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects
Name | Start | Start | Finish | Finish | Time Now | Time Now | Baseline Start | Baseline Start | Baseline Finish | Baseline Finish | Activities | Activities | Budget Duration | Budget Duration | Actual Duration | Actual Duration | Remaining Duration | Remaining Duration | Total Duration | Total Duration | Budget Cost | Budget Cost | Actual Cost | Actual Cost | Remaining Cost | Remaining Cost | Total Cost | Total Cost
Large Test File |  | 2017-06-07 08:00 |  | 2028-09-29 08:00 |  | 2025-02-07 17:00 |  | 2017-06-07 08:00 |  | 2028-09-29 17:00 |  | 2125 |  | 4132.375 |  | 1945 |  | 928 |  | 2873 |  | 0 |  | 0 |  | 0 |  | 0
Large Test File2 | = | 2017-06-07 08:00 | p | 2029-04-20 09:39 | p | 2025-03-10 17:00 | = | 2017-06-07 08:00 | = | 2028-09-29 17:00 | q | 2124 | = | 4132.375 | p | 1965 | p | 1053 | p | 3018 | = | 0 | = | 0 | = | 0 | = | 0

## Activities
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Activities - 1 (0%) | Activities - 1 (0%) | Activities - 1 (0%) | Activities - 1 (0%) | Activities - 1 (0%) | Activities - 1 (0%) | Activities - 1 (0%) | Activities - 1 (0%) | Activities - 1 (0%) | Activities - 1 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2
1 | 5623 | fMG09RcSWYzXzGg7X0YP | Normal | 0 | 1.5.2.2.7.5 | 1.5.2.2.7.5 |  | P | O

## Relationships
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Relationships - 6 (0%) | Relationships - 6 (0%) | Relationships - 6 (0%) | Relationships - 6 (0%) | Relationships - 6 (0%) | Relationships - 6 (0%) | Relationships - 6 (0%) | Relationships - 6 (0%)
Predecessor ID | Predecessor | Predecessor Critical | Successor ID | Successor | Successor Critical | Large Test File | Large Test File2
5622 | Te1bYWNwZbtOSUo1ZQYQ | False | 5623 | fMG09RcSWYzXzGg7X0YP | False | FinishToStart (0) | O
5623 | fMG09RcSWYzXzGg7X0YP | False | 5624 | 3NrXrpICHYJmlcmaxOhN | False | FinishToStart (0) | O
630 | LI4Hnijrco4AuWNAKEW6 | False | 5447 | ijJ4zfbEfOInLYX7Vu9Z | False | StartToStart (0) | O
5446 | te2IySdiGAzR3DsuZCbz | False | 5447 | ijJ4zfbEfOInLYX7Vu9Z | False | FinishToStart (0) | O
1489 | pYq4lU1lCt1U75q3gu6M | False | 1490 | hF9FI1LNvFfgTTXhqPsR | False | FinishToStart (0) | O
5622 | Te1bYWNwZbtOSUo1ZQYQ | False | 5624 | 3NrXrpICHYJmlcmaxOhN | False | O | FinishToStart (0)

## Leads-Lags
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Leads/Lags - 6 (0%) | Leads/Lags - 6 (0%) | Leads/Lags - 6 (0%) | Leads/Lags - 6 (0%) | Leads/Lags - 6 (0%) | Leads/Lags - 6 (0%) | Leads/Lags - 6 (0%) | Leads/Lags - 6 (0%) | Leads/Lags - 6 (0%) | Leads/Lags - 6 (0%)
Predecessor ID | Predecessor | Predecessor Critical | Successor ID | Successor | Successor Critical | Large Test File Relationship Type | Large Test File2 Relationship Type | Large Test File Lead/Lag | Large Test File2 Lead/Lag
5622 | Te1bYWNwZbtOSUo1ZQYQ | False | 5623 | fMG09RcSWYzXzGg7X0YP | False | FinishToStart | O | 0 | O
5623 | fMG09RcSWYzXzGg7X0YP | False | 5624 | 3NrXrpICHYJmlcmaxOhN | False | FinishToStart | O | 0 | O
630 | LI4Hnijrco4AuWNAKEW6 | False | 5447 | ijJ4zfbEfOInLYX7Vu9Z | False | StartToStart | O | 0 | O
5446 | te2IySdiGAzR3DsuZCbz | False | 5447 | ijJ4zfbEfOInLYX7Vu9Z | False | FinishToStart | O | 0 | O
1489 | pYq4lU1lCt1U75q3gu6M | False | 1490 | hF9FI1LNvFfgTTXhqPsR | False | FinishToStart | O | 0 | O
5622 | Te1bYWNwZbtOSUo1ZQYQ | False | 5624 | 3NrXrpICHYJmlcmaxOhN | False | O | FinishToStart | O | 0

## Resources
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Resources - 4 (2%) | Resources - 4 (2%) | Resources - 4 (2%) | Resources - 4 (2%) | Resources - 4 (2%) | Resources - 4 (2%) | Resources - 4 (2%) | Resources - 4 (2%) | Resources - 4 (2%) | Resources - 4 (2%) | Resources - 4 (2%) | Resources - 4 (2%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Resource | Large Test File | Large Test File2 | Large Test File2
1 | 5334 | 5Bt8vyiG2PJ2FKCjQPP1 | Summary | 74 | 1.9.3.1.2 | 1.9.3.1.2 |  | 11 | 0.33609 | p | 0.50275
2 | 3776 | GHLE38QRMYNBeSYAGB18 | Normal | 32 | 1.7.1.2.6.3 | 1.7.1.2.6.3 |  | LaRC | 256 | p | 270.5167
3 | 3777 | YuGKQIQDxLVYRZzgUQjw | Normal | 9 | 1.7.1.2.6.4 | 1.7.1.2.6.4 |  | DYN | 72 | q | 65.15
4 | 5666 | lc2LPCzbTjVw9vZ8eS89 | Summary | 23 | 1.9.2.2 | 1.9.2.2 |  | MATL | 43987.4985 | p | 46441.0635

## Calendars
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Dynetics Standard
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Used for Microsoft Project 98 Baseline Calendar
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: 60 hour work week Dynetics Standard
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: 60 hour work week + Saturdays Dynetics Standard
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: 24 Hours
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Double Shift
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: 16 Hour Work Days
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: ZIN Project Calendar
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: ZIN Overtime Calendar
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: MFG-OT Calendar
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: 7 Day Work Wk
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: ZIN Overtime Calendar
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Used for Microsoft Project 98 Baseline Calendar1
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Used for Microsoft Project 98 Baseline Calendar2
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Used for Microsoft Project 98 Baseline Calendar11
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Night Shift
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Weekend Hours
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Overtime Calendar
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Overtime Schedule Calendar
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: ZIN_Holiday
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Drawing and MWO
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: SPACEDOC
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: SPACEDOC II
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: OT-2
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: OT-3 2019
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: OT - 47hr ZIN Project Calendar
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: ZIN Overtime Project Calendar
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: SPACE DOC
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: FCF Calendar
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: 7 days a wk work
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: ZIN Project Calendar - Overtime
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: EDU OT 6 days at 10 hours
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: ZIN Working Time
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: ZIN Working Time Expanded
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: OT 47hr ZIN Project Calendar
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Overtime Schedule Calendar
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Holiday and Vacation Time
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: ZBOT
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: SPACEDOC II
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: SCENIC Project Calendar
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: MFG-OT
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Copy of MFG-OT
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: ZIN Overtime Schedule Calendar
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: ASIT_REFERENCE
Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File | Large Test File |  |  | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00

## Calendar Exceptions
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Calendar: Standard1
Large Test File | Large Test File2
Calendar: Dynetics Standard
Large Test File | Large Test File2
2011-05-30 | 2011-05-30
2012-05-28 | 2012-05-28
2013-05-27 | 2013-05-27
2014-05-26 | 2014-05-26
2015-05-25 | 2015-05-25
2016-05-30 | 2016-05-30
2017-05-29 | 2017-05-29
2018-05-28 | 2018-05-28
2019-05-27 | 2019-05-27
2011-07-04 | 2011-07-04
2012-07-04 | 2012-07-04
2013-07-04 | 2013-07-04
2014-07-04 | 2014-07-04
2015-07-04 | 2015-07-04
2016-07-04 | 2016-07-04
2017-07-04 | 2017-07-04
2018-07-04 | 2018-07-04
2019-07-04 | 2019-07-04
2011-09-05 | 2011-09-05
2012-09-03 | 2012-09-03
2013-09-02 | 2013-09-02
2014-09-01 | 2014-09-01
2015-09-07 | 2015-09-07
2016-09-05 | 2016-09-05
2017-09-04 | 2017-09-04
2018-09-03 | 2018-09-03
2019-09-02 | 2019-09-02
2011-11-24 | 2011-11-24
2012-11-22 | 2012-11-22
2013-11-21 | 2013-11-21
2014-11-27 | 2014-11-27
2015-11-26 | 2015-11-26
2016-11-24 | 2016-11-24
2017-11-23 | 2017-11-23
2018-11-22 | 2018-11-22
2011-12-25 | 2011-12-25
2012-12-25 | 2012-12-25
2013-12-25 | 2013-12-25
2014-12-25 | 2014-12-25
2015-12-25 | 2015-12-25
2016-12-25 | 2016-12-25
2017-12-25 | 2017-12-25
2018-12-25 | 2018-12-25
2019-12-25 | 2019-12-25
2020-12-25 | 2020-12-25
2021-12-25 | 2021-12-25
2022-12-25 | 2022-12-25
2023-12-25 | 2023-12-25
2024-12-25 | 2024-12-25
2025-12-25 | 2025-12-25
2015-11-27 | 2015-11-27
2016-11-25 | 2016-11-25
2017-11-24 | 2017-11-24
2018-11-23 | 2018-11-23
2019-11-22 | 2019-11-22
2017-01-01 | 2017-01-01
2018-01-01 | 2018-01-01
2018-03-30 | 2018-03-30
2018-08-26 | 2018-08-26
2018-12-24 | 2018-12-24
2018-12-31 | 2018-12-31
2019-01-01 | 2019-01-01
2019-11-29 | 2019-11-29
2019-12-24 | 2019-12-24
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-05-25 | 2020-05-25
2020-07-06 | 2020-07-06
2020-09-07 | 2020-09-07
2020-11-26 | 2020-11-26
2021-01-18 | 2021-01-18
2021-05-31 | 2021-05-31
2021-07-05 | 2021-07-05
2021-09-06 | 2021-09-06
2021-11-25 | 2021-11-25
2021-12-24 | 2021-12-24
2021-12-31 | 2021-12-31
2022-01-17 | 2022-01-17
2022-05-30 | 2022-05-30
2022-07-04 | 2022-07-04
2022-09-05 | 2022-09-05
2022-11-24 | 2022-11-24
2022-12-26 | 2022-12-26
2023-01-02 | 2023-01-02
2023-01-16 | 2023-01-16
2023-05-29 | 2023-05-29
2023-07-04 | 2023-07-04
2023-09-04 | 2023-09-04
2023-11-23 | 2023-11-23
2024-01-01 | 2024-01-01
2024-01-15 | 2024-01-15
2024-05-27 | 2024-05-27
2024-07-04 | 2024-07-04
2024-09-02 | 2024-09-02
2024-11-28 | 2024-11-28
2024-11-29 | 2024-11-29
2025-01-01 | 2025-01-01
2025-01-20 | 2025-01-20
2025-02-17 | 2025-02-17
2025-05-26 | 2025-05-26
2025-06-19 | 2025-06-19
2025-07-04 | 2025-07-04
2025-09-01 | 2025-09-01
2025-10-13 | 2025-10-13
2025-11-11 | 2025-11-11
2025-11-27 | 2025-11-27
2026-01-01 | 2026-01-01
2026-01-19 | 2026-01-19
2026-02-16 | 2026-02-16
2026-05-25 | 2026-05-25
2026-06-19 | 2026-06-19
2026-07-03 | 2026-07-03
2026-09-07 | 2026-09-07
2026-10-12 | 2026-10-12
2026-11-11 | 2026-11-11
2026-11-26 | 2026-11-26
2026-12-25 | 2026-12-25
2027-01-01 | 2027-01-01
Calendar: Used for Microsoft Project 98 Baseline Calendar
Large Test File | Large Test File2
2011-01-17 | 2011-01-17
2012-01-16 | 2012-01-16
2013-01-14 | 2013-01-14
2014-01-20 | 2014-01-20
2015-01-19 | 2015-01-19
2016-01-18 | 2016-01-18
2017-01-16 | 2017-01-16
2018-01-15 | 2018-01-15
2019-01-14 | 2019-01-14
2020-01-20 | 2020-01-20
2021-01-18 | 2021-01-18
2022-01-17 | 2022-01-17
2023-01-16 | 2023-01-16
2024-01-15 | 2024-01-15
2011-04-22 | 2011-04-22
2011-05-30 | 2011-05-30
2012-05-28 | 2012-05-28
2013-05-27 | 2013-05-27
2014-05-26 | 2014-05-26
2015-05-25 | 2015-05-25
2016-05-30 | 2016-05-30
2017-05-29 | 2017-05-29
2018-05-28 | 2018-05-28
2019-05-27 | 2019-05-27
2020-05-25 | 2020-05-25
2021-05-31 | 2021-05-31
2022-05-30 | 2022-05-30
2023-05-29 | 2023-05-29
2024-05-27 | 2024-05-27
2025-05-26 | 2025-05-26
2011-07-04 | 2011-07-04
2012-07-04 | 2012-07-04
2013-07-04 | 2013-07-04
2014-07-04 | 2014-07-04
2015-07-04 | 2015-07-04
2016-07-04 | 2016-07-04
2017-07-04 | 2017-07-04
2018-07-04 | 2018-07-04
2019-07-04 | 2019-07-04
2020-07-04 | 2020-07-04
2021-07-04 | 2021-07-04
2022-07-04 | 2022-07-04
2023-07-04 | 2023-07-04
2024-07-04 | 2024-07-04
2025-07-04 | 2025-07-04
2011-09-05 | 2011-09-05
2012-09-03 | 2012-09-03
2013-09-02 | 2013-09-02
2014-09-01 | 2014-09-01
2015-09-07 | 2015-09-07
2016-09-05 | 2016-09-05
2017-09-04 | 2017-09-04
2018-09-03 | 2018-09-03
2019-09-02 | 2019-09-02
2020-09-07 | 2020-09-07
2021-09-06 | 2021-09-06
2022-09-05 | 2022-09-05
2023-09-04 | 2023-09-04
2024-09-02 | 2024-09-02
2025-09-01 | 2025-09-01
2011-11-24 | 2011-11-24
2012-11-22 | 2012-11-22
2013-11-21 | 2013-11-21
2014-11-27 | 2014-11-27
2015-11-26 | 2015-11-26
2016-11-24 | 2016-11-24
2017-11-23 | 2017-11-23
2018-11-22 | 2018-11-22
2019-11-21 | 2019-11-21
2020-11-26 | 2020-11-26
2021-11-25 | 2021-11-25
2022-11-24 | 2022-11-24
2023-11-23 | 2023-11-23
2024-11-21 | 2024-11-21
2011-11-25 | 2011-11-25
2012-11-23 | 2012-11-23
2011-12-23 | 2011-12-23
2011-12-25 | 2011-12-25
2012-12-25 | 2012-12-25
2013-12-25 | 2013-12-25
2014-12-25 | 2014-12-25
2015-12-25 | 2015-12-25
2016-12-25 | 2016-12-25
2017-12-25 | 2017-12-25
2018-12-25 | 2018-12-25
2019-12-25 | 2019-12-25
2020-12-25 | 2020-12-25
2021-12-25 | 2021-12-25
2022-12-25 | 2022-12-25
2023-12-25 | 2023-12-25
2024-12-25 | 2024-12-25
2025-12-25 | 2025-12-25
2011-12-26 | 2011-12-26
2012-01-01 | 2012-01-01
2012-01-02 | 2012-01-02
2012-04-06 | 2012-04-06
2012-12-24 | 2012-12-24
2012-12-31 | 2012-12-31
2013-01-01 | 2013-01-01
2013-11-29 | 2013-11-29
2013-12-24 | 2013-12-24
2013-12-26 | 2013-12-26
2014-01-01 | 2014-01-01
2015-01-01 | 2015-01-01
2016-01-01 | 2016-01-01
2017-01-01 | 2017-01-01
2018-01-01 | 2018-01-01
2019-01-01 | 2019-01-01
2020-01-01 | 2020-01-01
2021-01-01 | 2021-01-01
2022-01-01 | 2022-01-01
2015-11-27 | 2015-11-27
2016-11-25 | 2016-11-25
2017-11-24 | 2017-11-24
2018-11-23 | 2018-11-23
2019-11-22 | 2019-11-22
2014-12-26 | 2014-12-26
2015-01-02 | 2015-01-02
2015-07-03 | 2015-07-03
2015-12-24 | 2015-12-24
2015-12-31 | 2015-12-31
2016-12-26 | 2016-12-26
2016-12-27 | 2016-12-27
2017-01-02 | 2017-01-02
2017-04-14 | 2017-04-14
2017-12-26 | 2017-12-26
2018-03-30 | 2018-03-30
2018-12-24 | 2018-12-24
2018-12-31 | 2018-12-31
2019-11-29 | 2019-11-29
2019-12-24 | 2019-12-24
2019-12-26 | 2019-12-26
2020-07-03 | 2020-07-03
2020-11-27 | 2020-11-27
2020-12-24 | 2020-12-24
2020-12-31 | 2020-12-31
Calendar: 60 hour work week Dynetics Standard
Large Test File | Large Test File2
2011-04-22 | 2011-04-22
2011-05-30 | 2011-05-30
2012-05-28 | 2012-05-28
2013-05-27 | 2013-05-27
2014-05-26 | 2014-05-26
2015-05-25 | 2015-05-25
2016-05-30 | 2016-05-30
2017-05-29 | 2017-05-29
2018-05-28 | 2018-05-28
2019-05-27 | 2019-05-27
2020-05-25 | 2020-05-25
2021-05-31 | 2021-05-31
2022-05-30 | 2022-05-30
2011-07-04 | 2011-07-04
2012-07-04 | 2012-07-04
2013-07-04 | 2013-07-04
2014-07-04 | 2014-07-04
2015-07-04 | 2015-07-04
2016-07-04 | 2016-07-04
2017-07-04 | 2017-07-04
2018-07-04 | 2018-07-04
2019-07-04 | 2019-07-04
2020-07-04 | 2020-07-04
2021-07-04 | 2021-07-04
2022-07-04 | 2022-07-04
2011-09-05 | 2011-09-05
2012-09-03 | 2012-09-03
2013-09-02 | 2013-09-02
2014-09-01 | 2014-09-01
2015-09-07 | 2015-09-07
2016-09-05 | 2016-09-05
2017-09-04 | 2017-09-04
2018-09-03 | 2018-09-03
2019-09-02 | 2019-09-02
2020-09-07 | 2020-09-07
2021-09-06 | 2021-09-06
2022-09-05 | 2022-09-05
2011-11-24 | 2011-11-24
2012-11-22 | 2012-11-22
2013-11-21 | 2013-11-21
2014-11-27 | 2014-11-27
2015-11-26 | 2015-11-26
2016-11-24 | 2016-11-24
2017-11-23 | 2017-11-23
2018-11-22 | 2018-11-22
2019-11-21 | 2019-11-21
2020-11-26 | 2020-11-26
2021-11-25 | 2021-11-25
2011-11-25 | 2011-11-25
2012-11-23 | 2012-11-23
2011-12-23 | 2011-12-23
2011-12-25 | 2011-12-25
2012-12-25 | 2012-12-25
2013-12-25 | 2013-12-25
2014-12-25 | 2014-12-25
2015-12-25 | 2015-12-25
2016-12-25 | 2016-12-25
2017-12-25 | 2017-12-25
2018-12-25 | 2018-12-25
2019-12-25 | 2019-12-25
2020-12-25 | 2020-12-25
2021-12-25 | 2021-12-25
2022-12-25 | 2022-12-25
2023-12-25 | 2023-12-25
2024-12-25 | 2024-12-25
2025-12-25 | 2025-12-25
2011-12-26 | 2011-12-26
2012-01-01 | 2012-01-01
2012-01-02 | 2012-01-02
2012-04-06 | 2012-04-06
2012-12-24 | 2012-12-24
2012-12-31 | 2012-12-31
2013-01-01 | 2013-01-01
2013-11-29 | 2013-11-29
2013-12-24 | 2013-12-24
2013-12-26 | 2013-12-26
2014-01-01 | 2014-01-01
2015-01-01 | 2015-01-01
2016-01-01 | 2016-01-01
2017-01-01 | 2017-01-01
2018-01-01 | 2018-01-01
2019-01-01 | 2019-01-01
2020-01-01 | 2020-01-01
2021-01-01 | 2021-01-01
2022-01-01 | 2022-01-01
2015-11-27 | 2015-11-27
2016-11-25 | 2016-11-25
2017-11-24 | 2017-11-24
2018-11-23 | 2018-11-23
2019-11-22 | 2019-11-22
2014-12-26 | 2014-12-26
2015-01-02 | 2015-01-02
2015-07-03 | 2015-07-03
2015-12-24 | 2015-12-24
2015-12-31 | 2015-12-31
2016-12-26 | 2016-12-26
2016-12-27 | 2016-12-27
2017-01-02 | 2017-01-02
2017-04-14 | 2017-04-14
2017-12-26 | 2017-12-26
2018-03-30 | 2018-03-30
2018-08-26 | 2018-08-26
2018-12-24 | 2018-12-24
2018-12-31 | 2018-12-31
2019-11-29 | 2019-11-29
2019-12-24 | 2019-12-24
2019-12-26 | 2019-12-26
2020-01-20 | 2020-01-20
2020-07-03 | 2020-07-03
2020-11-27 | 2020-11-27
2020-12-24 | 2020-12-24
2020-12-31 | 2020-12-31
2021-01-18 | 2021-01-18
2022-01-17 | 2022-01-17
2023-01-02 | 2023-01-02
2023-01-16 | 2023-01-16
2023-05-29 | 2023-05-29
2023-07-04 | 2023-07-04
2023-09-04 | 2023-09-04
2023-11-23 | 2023-11-23
2024-01-01 | 2024-01-01
2024-01-15 | 2024-01-15
2024-05-27 | 2024-05-27
2024-07-04 | 2024-07-04
2024-09-02 | 2024-09-02
2024-11-28 | 2024-11-28
2025-01-01 | 2025-01-01
2025-01-20 | 2025-01-20
Calendar: 60 hour work week + Saturdays Dynetics Standard
Large Test File | Large Test File2
2011-04-22 | 2011-04-22
2011-05-30 | 2011-05-30
2012-05-28 | 2012-05-28
2013-05-27 | 2013-05-27
2014-05-26 | 2014-05-26
2015-05-25 | 2015-05-25
2016-05-30 | 2016-05-30
2017-05-29 | 2017-05-29
2018-05-28 | 2018-05-28
2019-05-27 | 2019-05-27
2020-05-25 | 2020-05-25
2021-05-31 | 2021-05-31
2022-05-30 | 2022-05-30
2011-07-04 | 2011-07-04
2012-07-04 | 2012-07-04
2013-07-04 | 2013-07-04
2014-07-04 | 2014-07-04
2015-07-04 | 2015-07-04
2016-07-04 | 2016-07-04
2017-07-04 | 2017-07-04
2018-07-04 | 2018-07-04
2019-07-04 | 2019-07-04
2020-07-04 | 2020-07-04
2021-07-04 | 2021-07-04
2022-07-04 | 2022-07-04
2011-09-05 | 2011-09-05
2012-09-03 | 2012-09-03
2013-09-02 | 2013-09-02
2014-09-01 | 2014-09-01
2015-09-07 | 2015-09-07
2016-09-05 | 2016-09-05
2017-09-04 | 2017-09-04
2018-09-03 | 2018-09-03
2019-09-02 | 2019-09-02
2020-09-07 | 2020-09-07
2021-09-06 | 2021-09-06
2022-09-05 | 2022-09-05
2011-11-24 | 2011-11-24
2012-11-22 | 2012-11-22
2013-11-21 | 2013-11-21
2014-11-27 | 2014-11-27
2015-11-26 | 2015-11-26
2016-11-24 | 2016-11-24
2017-11-23 | 2017-11-23
2018-11-22 | 2018-11-22
2019-11-21 | 2019-11-21
2020-11-26 | 2020-11-26
2021-11-25 | 2021-11-25
2011-11-25 | 2011-11-25
2012-11-23 | 2012-11-23
2011-12-23 | 2011-12-23
2011-12-25 | 2011-12-25
2012-12-25 | 2012-12-25
2013-12-25 | 2013-12-25
2014-12-25 | 2014-12-25
2015-12-25 | 2015-12-25
2016-12-25 | 2016-12-25
2017-12-25 | 2017-12-25
2018-12-25 | 2018-12-25
2019-12-25 | 2019-12-25
2020-12-25 | 2020-12-25
2021-12-25 | 2021-12-25
2022-12-25 | 2022-12-25
2023-12-25 | 2023-12-25
2024-12-25 | 2024-12-25
2025-12-25 | 2025-12-25
2011-12-26 | 2011-12-26
2012-01-01 | 2012-01-01
2012-01-02 | 2012-01-02
2012-04-06 | 2012-04-06
2012-12-24 | 2012-12-24
2012-12-31 | 2012-12-31
2013-01-01 | 2013-01-01
2013-11-29 | 2013-11-29
2013-12-24 | 2013-12-24
2013-12-26 | 2013-12-26
2014-01-01 | 2014-01-01
2015-01-01 | 2015-01-01
2016-01-01 | 2016-01-01
2017-01-01 | 2017-01-01
2018-01-01 | 2018-01-01
2019-01-01 | 2019-01-01
2020-01-01 | 2020-01-01
2021-01-01 | 2021-01-01
2022-01-01 | 2022-01-01
2015-11-27 | 2015-11-27
2016-11-25 | 2016-11-25
2017-11-24 | 2017-11-24
2018-11-23 | 2018-11-23
2019-11-22 | 2019-11-22
2014-12-26 | 2014-12-26
2015-01-02 | 2015-01-02
2015-07-03 | 2015-07-03
2015-12-24 | 2015-12-24
2015-12-31 | 2015-12-31
2016-12-26 | 2016-12-26
2016-12-27 | 2016-12-27
2017-01-02 | 2017-01-02
2017-04-14 | 2017-04-14
2017-12-26 | 2017-12-26
2018-03-30 | 2018-03-30
2018-08-26 | 2018-08-26
2018-12-24 | 2018-12-24
2018-12-31 | 2018-12-31
2019-11-29 | 2019-11-29
2019-12-24 | 2019-12-24
2019-12-26 | 2019-12-26
2020-01-20 | 2020-01-20
2020-07-03 | 2020-07-03
2020-11-27 | 2020-11-27
2020-12-24 | 2020-12-24
2020-12-31 | 2020-12-31
2021-01-18 | 2021-01-18
2022-01-17 | 2022-01-17
2023-01-16 | 2023-01-16
2024-01-15 | 2024-01-15
2025-01-20 | 2025-01-20
2022-11-25 | 2022-11-25
2022-11-26 | 2022-11-26
2022-12-23 | 2022-12-23
2022-12-24 | 2022-12-24
2022-12-26 | 2022-12-26
2023-01-02 | 2023-01-02
2023-05-29 | 2023-05-29
2023-07-04 | 2023-07-04
2023-09-04 | 2023-09-04
2023-11-23 | 2023-11-23
2024-01-01 | 2024-01-01
2024-05-27 | 2024-05-27
2024-07-04 | 2024-07-04
2024-09-02 | 2024-09-02
2024-11-28 | 2024-11-28
2025-01-01 | 2025-01-01
Calendar: 24 Hours
Large Test File | Large Test File2
Calendar: Double Shift
Large Test File | Large Test File2
2011-05-30 | 2011-05-30
2012-05-28 | 2012-05-28
2013-05-27 | 2013-05-27
2014-05-26 | 2014-05-26
2015-05-25 | 2015-05-25
2016-05-30 | 2016-05-30
2017-05-29 | 2017-05-29
2018-05-28 | 2018-05-28
2019-05-27 | 2019-05-27
2011-07-04 | 2011-07-04
2012-07-04 | 2012-07-04
2013-07-04 | 2013-07-04
2014-07-04 | 2014-07-04
2015-07-04 | 2015-07-04
2016-07-04 | 2016-07-04
2017-07-04 | 2017-07-04
2018-07-04 | 2018-07-04
2019-07-04 | 2019-07-04
2011-09-05 | 2011-09-05
2012-09-03 | 2012-09-03
2013-09-02 | 2013-09-02
2014-09-01 | 2014-09-01
2015-09-07 | 2015-09-07
2016-09-05 | 2016-09-05
2017-09-04 | 2017-09-04
2018-09-03 | 2018-09-03
2019-09-02 | 2019-09-02
2011-11-24 | 2011-11-24
2012-11-22 | 2012-11-22
2013-11-21 | 2013-11-21
2014-11-27 | 2014-11-27
2015-11-26 | 2015-11-26
2016-11-24 | 2016-11-24
2017-11-23 | 2017-11-23
2018-11-22 | 2018-11-22
2011-12-25 | 2011-12-25
2012-12-25 | 2012-12-25
2013-12-25 | 2013-12-25
2014-12-25 | 2014-12-25
2015-12-25 | 2015-12-25
2016-12-25 | 2016-12-25
2017-12-25 | 2017-12-25
2018-12-25 | 2018-12-25
2019-12-25 | 2019-12-25
2020-12-25 | 2020-12-25
2021-12-25 | 2021-12-25
2022-12-25 | 2022-12-25
2023-12-25 | 2023-12-25
2024-12-25 | 2024-12-25
2025-12-25 | 2025-12-25
2015-11-27 | 2015-11-27
2016-11-25 | 2016-11-25
2017-11-24 | 2017-11-24
2018-11-23 | 2018-11-23
2019-11-22 | 2019-11-22
2017-01-01 | 2017-01-01
2018-01-01 | 2018-01-01
2018-03-30 | 2018-03-30
2018-08-26 | 2018-08-26
2018-12-24 | 2018-12-24
2018-12-31 | 2018-12-31
2019-01-01 | 2019-01-01
2019-11-29 | 2019-11-29
2019-12-24 | 2019-12-24
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-05-25 | 2020-05-25
2020-07-06 | 2020-07-06
2020-09-07 | 2020-09-07
2020-11-26 | 2020-11-26
2021-01-18 | 2021-01-18
2021-05-31 | 2021-05-31
2021-07-05 | 2021-07-05
2021-09-06 | 2021-09-06
2021-11-25 | 2021-11-25
2021-12-24 | 2021-12-24
2021-12-31 | 2021-12-31
2022-01-17 | 2022-01-17
2022-05-30 | 2022-05-30
2022-07-04 | 2022-07-04
2022-09-05 | 2022-09-05
2022-11-24 | 2022-11-24
2022-12-26 | 2022-12-26
2023-01-02 | 2023-01-02
2023-01-16 | 2023-01-16
2023-05-29 | 2023-05-29
2023-07-04 | 2023-07-04
2023-09-04 | 2023-09-04
2023-11-23 | 2023-11-23
2024-01-01 | 2024-01-01
2024-01-15 | 2024-01-15
2024-05-27 | 2024-05-27
2024-07-04 | 2024-07-04
2024-09-02 | 2024-09-02
2024-11-28 | 2024-11-28
2025-01-01 | 2025-01-01
2025-01-20 | 2025-01-20
Calendar: 16 Hour Work Days
Large Test File | Large Test File2
2011-05-30 | 2011-05-30
2012-05-28 | 2012-05-28
2013-05-27 | 2013-05-27
2014-05-26 | 2014-05-26
2015-05-25 | 2015-05-25
2016-05-30 | 2016-05-30
2017-05-29 | 2017-05-29
2018-05-28 | 2018-05-28
2019-05-27 | 2019-05-27
2011-07-04 | 2011-07-04
2012-07-04 | 2012-07-04
2013-07-04 | 2013-07-04
2014-07-04 | 2014-07-04
2015-07-04 | 2015-07-04
2016-07-04 | 2016-07-04
2017-07-04 | 2017-07-04
2018-07-04 | 2018-07-04
2019-07-04 | 2019-07-04
2011-09-05 | 2011-09-05
2012-09-03 | 2012-09-03
2013-09-02 | 2013-09-02
2014-09-01 | 2014-09-01
2015-09-07 | 2015-09-07
2016-09-05 | 2016-09-05
2017-09-04 | 2017-09-04
2018-09-03 | 2018-09-03
2019-09-02 | 2019-09-02
2011-11-24 | 2011-11-24
2012-11-22 | 2012-11-22
2013-11-21 | 2013-11-21
2014-11-27 | 2014-11-27
2015-11-26 | 2015-11-26
2016-11-24 | 2016-11-24
2017-11-23 | 2017-11-23
2018-11-22 | 2018-11-22
2011-12-25 | 2011-12-25
2012-12-25 | 2012-12-25
2013-12-25 | 2013-12-25
2014-12-25 | 2014-12-25
2015-12-25 | 2015-12-25
2016-12-25 | 2016-12-25
2017-12-25 | 2017-12-25
2018-12-25 | 2018-12-25
2019-12-25 | 2019-12-25
2020-12-25 | 2020-12-25
2021-12-25 | 2021-12-25
2022-12-25 | 2022-12-25
2023-12-25 | 2023-12-25
2024-12-25 | 2024-12-25
2025-12-25 | 2025-12-25
2015-11-27 | 2015-11-27
2016-11-25 | 2016-11-25
2017-11-24 | 2017-11-24
2018-11-23 | 2018-11-23
2019-11-22 | 2019-11-22
2017-01-01 | 2017-01-01
2018-01-01 | 2018-01-01
2018-03-30 | 2018-03-30
2018-08-26 | 2018-08-26
2018-12-24 | 2018-12-24
2018-12-31 | 2018-12-31
2019-01-01 | 2019-01-01
2019-11-29 | 2019-11-29
2019-12-24 | 2019-12-24
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-05-25 | 2020-05-25
2020-07-06 | 2020-07-06
2020-09-07 | 2020-09-07
2020-11-26 | 2020-11-26
2021-01-18 | 2021-01-18
2021-05-31 | 2021-05-31
2021-07-05 | 2021-07-05
2021-09-06 | 2021-09-06
2021-11-25 | 2021-11-25
2021-12-24 | 2021-12-24
2021-12-31 | 2021-12-31
2022-01-17 | 2022-01-17
2022-05-30 | 2022-05-30
2022-07-04 | 2022-07-04
2022-09-05 | 2022-09-05
2022-11-24 | 2022-11-24
2022-12-26 | 2022-12-26
2023-01-02 | 2023-01-02
2023-01-16 | 2023-01-16
2023-05-29 | 2023-05-29
2023-07-04 | 2023-07-04
2023-09-04 | 2023-09-04
2023-11-23 | 2023-11-23
2024-01-01 | 2024-01-01
2024-01-15 | 2024-01-15
2024-05-27 | 2024-05-27
2024-07-04 | 2024-07-04
2024-09-02 | 2024-09-02
2024-11-28 | 2024-11-28
2025-01-01 | 2025-01-01
2025-01-20 | 2025-01-20
Calendar: ZIN Project Calendar
Large Test File | Large Test File2
2014-01-01 | 2014-01-01
2014-01-20 | 2014-01-20
2014-02-17 | 2014-02-17
2014-05-26 | 2014-05-26
2014-07-04 | 2014-07-04
2014-09-01 | 2014-09-01
2014-10-13 | 2014-10-13
2014-11-11 | 2014-11-11
2014-11-27 | 2014-11-27
2014-12-25 | 2014-12-25
2015-01-01 | 2015-01-01
2015-01-19 | 2015-01-19
2015-02-16 | 2015-02-16
2015-05-25 | 2015-05-25
2015-07-03 | 2015-07-03
2015-09-07 | 2015-09-07
2015-10-12 | 2015-10-12
2015-11-11 | 2015-11-11
2015-11-26 | 2015-11-26
2015-12-25 | 2015-12-25
2016-01-01 | 2016-01-01
2016-01-18 | 2016-01-18
2016-02-15 | 2016-02-15
2016-05-30 | 2016-05-30
2016-07-04 | 2016-07-04
2016-09-05 | 2016-09-05
2016-10-10 | 2016-10-10
2016-11-11 | 2016-11-11
2016-11-24 | 2016-11-24
2016-12-26 | 2016-12-26
2017-01-02 | 2017-01-02
2017-01-16 | 2017-01-16
2017-02-20 | 2017-02-20
2017-05-29 | 2017-05-29
2017-07-04 | 2017-07-04
2017-09-04 | 2017-09-04
2017-10-09 | 2017-10-09
2017-11-10 | 2017-11-10
2017-11-23 | 2017-11-23
2017-12-25 | 2017-12-25
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-11-26 | 2020-11-26
2020-12-25 | 2020-12-25
2021-01-01 | 2021-01-01
2021-01-18 | 2021-01-18
2021-02-15 | 2021-02-15
2021-05-31 | 2021-05-31
2021-07-05 | 2021-07-05
2021-09-06 | 2021-09-06
2021-10-11 | 2021-10-11
2021-11-11 | 2021-11-11
2021-11-25 | 2021-11-25
2021-12-24 | 2021-12-24
2021-12-31 | 2021-12-31
2022-01-17 | 2022-01-17
2022-02-21 | 2022-02-21
2022-05-30 | 2022-05-30
2022-07-04 | 2022-07-04
2022-09-05 | 2022-09-05
2022-10-10 | 2022-10-10
2022-11-11 | 2022-11-11
2022-11-24 | 2022-11-24
2022-12-26 | 2022-12-26
2023-01-02 | 2023-01-02
2023-01-16 | 2023-01-16
2023-02-20 | 2023-02-20
2023-05-29 | 2023-05-29
2023-07-04 | 2023-07-04
2023-09-04 | 2023-09-04
2023-10-09 | 2023-10-09
2023-11-10 | 2023-11-10
2023-11-23 | 2023-11-23
2023-12-25 | 2023-12-25
2024-01-01 | 2024-01-01
2024-01-15 | 2024-01-15
2024-02-19 | 2024-02-19
2024-05-27 | 2024-05-27
2024-07-04 | 2024-07-04
2024-09-02 | 2024-09-02
2024-10-14 | 2024-10-14
2024-11-11 | 2024-11-11
2024-11-28 | 2024-11-28
2024-12-25 | 2024-12-25
2025-01-01 | 2025-01-01
2025-01-20 | 2025-01-20
2025-02-17 | 2025-02-17
2025-05-26 | 2025-05-26
2025-07-04 | 2025-07-04
2025-09-01 | 2025-09-01
2025-10-13 | 2025-10-13
2025-11-11 | 2025-11-11
2025-11-27 | 2025-11-27
2025-12-25 | 2025-12-25
Calendar: ZIN Overtime Calendar
Large Test File | Large Test File2
2014-01-01 | 2014-01-01
2014-01-20 | 2014-01-20
2014-02-17 | 2014-02-17
2014-05-26 | 2014-05-26
2014-07-04 | 2014-07-04
2014-09-01 | 2014-09-01
2014-10-13 | 2014-10-13
2014-11-11 | 2014-11-11
2014-11-27 | 2014-11-27
2014-12-25 | 2014-12-25
2015-01-01 | 2015-01-01
2015-01-19 | 2015-01-19
2015-02-16 | 2015-02-16
2015-05-25 | 2015-05-25
2015-07-03 | 2015-07-03
2015-09-07 | 2015-09-07
2015-10-12 | 2015-10-12
2015-11-11 | 2015-11-11
2015-11-26 | 2015-11-26
2015-12-25 | 2015-12-25
2016-01-01 | 2016-01-01
2016-01-18 | 2016-01-18
2016-02-15 | 2016-02-15
2016-05-30 | 2016-05-30
2016-07-04 | 2016-07-04
2016-09-05 | 2016-09-05
2016-10-10 | 2016-10-10
2016-11-11 | 2016-11-11
2016-11-24 | 2016-11-24
2016-12-26 | 2016-12-26
2017-01-02 | 2017-01-02
2017-01-16 | 2017-01-16
2017-02-20 | 2017-02-20
2017-05-29 | 2017-05-29
2017-07-04 | 2017-07-04
2017-09-04 | 2017-09-04
2017-10-09 | 2017-10-09
2017-11-10 | 2017-11-10
2017-11-23 | 2017-11-23
2017-12-25 | 2017-12-25
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-11-26 | 2020-11-26
2020-12-25 | 2020-12-25
2021-01-01 | 2021-01-01
2021-01-18 | 2021-01-18
2021-02-15 | 2021-02-15
2021-05-31 | 2021-05-31
2021-07-05 | 2021-07-05
2021-09-06 | 2021-09-06
2021-10-11 | 2021-10-11
2021-11-11 | 2021-11-11
2021-11-25 | 2021-11-25
2021-12-24 | 2021-12-24
2021-12-31 | 2021-12-31
2022-01-17 | 2022-01-17
2022-02-21 | 2022-02-21
2022-05-30 | 2022-05-30
2022-07-04 | 2022-07-04
2022-09-05 | 2022-09-05
2022-10-10 | 2022-10-10
2022-11-11 | 2022-11-11
2022-11-24 | 2022-11-24
2022-12-26 | 2022-12-26
2023-01-02 | 2023-01-02
2023-01-16 | 2023-01-16
2023-02-20 | 2023-02-20
2023-05-29 | 2023-05-29
2023-07-04 | 2023-07-04
2023-09-04 | 2023-09-04
2023-10-09 | 2023-10-09
2023-11-10 | 2023-11-10
2023-11-23 | 2023-11-23
2023-12-25 | 2023-12-25
2024-01-01 | 2024-01-01
2024-01-15 | 2024-01-15
2024-02-19 | 2024-02-19
2024-05-27 | 2024-05-27
2024-07-04 | 2024-07-04
2024-09-02 | 2024-09-02
2024-10-14 | 2024-10-14
2024-11-11 | 2024-11-11
2024-11-28 | 2024-11-28
2024-12-25 | 2024-12-25
2025-01-01 | 2025-01-01
2025-01-20 | 2025-01-20
2025-02-17 | 2025-02-17
2025-05-26 | 2025-05-26
2025-07-04 | 2025-07-04
2025-09-01 | 2025-09-01
2025-10-13 | 2025-10-13
2025-11-11 | 2025-11-11
2025-11-27 | 2025-11-27
2025-12-25 | 2025-12-25
Calendar: MFG-OT Calendar
Large Test File | Large Test File2
2014-01-01 | 2014-01-01
2014-01-20 | 2014-01-20
2014-02-17 | 2014-02-17
2014-05-26 | 2014-05-26
2014-07-04 | 2014-07-04
2014-09-01 | 2014-09-01
2014-10-13 | 2014-10-13
2014-11-11 | 2014-11-11
2014-11-27 | 2014-11-27
2014-12-25 | 2014-12-25
2015-01-01 | 2015-01-01
2015-01-19 | 2015-01-19
2015-02-16 | 2015-02-16
2015-05-25 | 2015-05-25
2015-07-03 | 2015-07-03
2015-09-07 | 2015-09-07
2015-10-12 | 2015-10-12
2015-11-11 | 2015-11-11
2015-11-26 | 2015-11-26
2015-12-25 | 2015-12-25
2016-01-01 | 2016-01-01
2016-01-18 | 2016-01-18
2016-02-15 | 2016-02-15
2016-05-30 | 2016-05-30
2016-07-04 | 2016-07-04
2016-09-05 | 2016-09-05
2016-10-10 | 2016-10-10
2016-11-11 | 2016-11-11
2016-11-24 | 2016-11-24
2016-12-26 | 2016-12-26
2017-01-02 | 2017-01-02
2017-01-16 | 2017-01-16
2017-02-20 | 2017-02-20
2017-05-29 | 2017-05-29
2017-07-04 | 2017-07-04
2017-09-04 | 2017-09-04
2017-10-09 | 2017-10-09
2017-11-10 | 2017-11-10
2017-11-23 | 2017-11-23
2017-12-25 | 2017-12-25
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-11-26 | 2020-11-26
2020-12-25 | 2020-12-25
2021-01-01 | 2021-01-01
2021-01-18 | 2021-01-18
2021-02-15 | 2021-02-15
2021-05-31 | 2021-05-31
2021-07-05 | 2021-07-05
2021-09-06 | 2021-09-06
2021-10-11 | 2021-10-11
2021-11-11 | 2021-11-11
2021-11-25 | 2021-11-25
2021-12-24 | 2021-12-24
2021-12-31 | 2021-12-31
2022-01-17 | 2022-01-17
2022-02-21 | 2022-02-21
2022-05-30 | 2022-05-30
2022-07-04 | 2022-07-04
2022-09-05 | 2022-09-05
2022-10-10 | 2022-10-10
2022-11-11 | 2022-11-11
2022-11-24 | 2022-11-24
2022-12-26 | 2022-12-26
2023-01-02 | 2023-01-02
2023-01-16 | 2023-01-16
2023-02-20 | 2023-02-20
2023-05-29 | 2023-05-29
2023-07-04 | 2023-07-04
2023-09-04 | 2023-09-04
2023-10-09 | 2023-10-09
2023-11-10 | 2023-11-10
2023-11-23 | 2023-11-23
2023-12-25 | 2023-12-25
2024-01-01 | 2024-01-01
2024-01-15 | 2024-01-15
2024-02-19 | 2024-02-19
2024-05-27 | 2024-05-27
2024-07-04 | 2024-07-04
2024-09-02 | 2024-09-02
2024-10-14 | 2024-10-14
2024-11-11 | 2024-11-11
2024-11-28 | 2024-11-28
2024-12-25 | 2024-12-25
2025-01-01 | 2025-01-01
2025-01-20 | 2025-01-20
2025-02-17 | 2025-02-17
2025-05-26 | 2025-05-26
2025-07-04 | 2025-07-04
2025-09-01 | 2025-09-01
2025-10-13 | 2025-10-13
2025-11-11 | 2025-11-11
2025-11-27 | 2025-11-27
2025-12-25 | 2025-12-25
Calendar: 7 Day Work Wk
Large Test File | Large Test File2
2017-07-04 | 2017-07-04
2017-09-04 | 2017-09-04
2017-10-09 | 2017-10-09
2017-11-10 | 2017-11-10
2017-11-23 | 2017-11-23
2017-12-25 | 2017-12-25
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-11-26 | 2020-11-26
2020-12-25 | 2020-12-25
2021-01-01 | 2021-01-01
2021-01-18 | 2021-01-18
2021-02-15 | 2021-02-15
2021-05-31 | 2021-05-31
2021-07-05 | 2021-07-05
2021-09-06 | 2021-09-06
2021-10-11 | 2021-10-11
2021-11-11 | 2021-11-11
2021-11-25 | 2021-11-25
2021-12-24 | 2021-12-24
2021-12-31 | 2021-12-31
2022-01-17 | 2022-01-17
2022-02-21 | 2022-02-21
2022-05-30 | 2022-05-30
2022-07-04 | 2022-07-04
2022-09-05 | 2022-09-05
2022-10-10 | 2022-10-10
2022-11-11 | 2022-11-11
2022-11-24 | 2022-11-24
2022-12-26 | 2022-12-26
2023-01-02 | 2023-01-02
2023-01-16 | 2023-01-16
2023-02-20 | 2023-02-20
2023-05-29 | 2023-05-29
2023-07-04 | 2023-07-04
2023-09-04 | 2023-09-04
2023-10-09 | 2023-10-09
2023-11-10 | 2023-11-10
2023-11-23 | 2023-11-23
2023-12-25 | 2023-12-25
2024-01-01 | 2024-01-01
2024-01-15 | 2024-01-15
2024-02-19 | 2024-02-19
2024-05-27 | 2024-05-27
2024-07-04 | 2024-07-04
2024-09-02 | 2024-09-02
2024-10-14 | 2024-10-14
2024-11-11 | 2024-11-11
2024-11-28 | 2024-11-28
2024-12-25 | 2024-12-25
2025-01-01 | 2025-01-01
2025-01-20 | 2025-01-20
2025-02-17 | 2025-02-17
2025-05-26 | 2025-05-26
2025-07-04 | 2025-07-04
2025-09-01 | 2025-09-01
2025-10-13 | 2025-10-13
2025-11-11 | 2025-11-11
2025-11-27 | 2025-11-27
2025-12-25 | 2025-12-25
Calendar: ZIN Overtime Calendar
Large Test File | Large Test File2
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-11-26 | 2020-11-26
2020-12-25 | 2020-12-25
Calendar: Used for Microsoft Project 98 Baseline Calendar1
Large Test File | Large Test File2
2014-01-01 | 2014-01-01
2014-01-20 | 2014-01-20
2014-02-17 | 2014-02-17
2014-05-26 | 2014-05-26
2014-07-04 | 2014-07-04
2014-09-01 | 2014-09-01
2014-10-13 | 2014-10-13
2014-11-11 | 2014-11-11
2014-11-27 | 2014-11-27
2014-12-25 | 2014-12-25
Calendar: Used for Microsoft Project 98 Baseline Calendar2
Large Test File | Large Test File2
2014-01-01 | 2014-01-01
2014-01-20 | 2014-01-20
2014-02-17 | 2014-02-17
2014-05-26 | 2014-05-26
2014-07-04 | 2014-07-04
2014-09-01 | 2014-09-01
2014-10-13 | 2014-10-13
2014-11-11 | 2014-11-11
2014-11-27 | 2014-11-27
2014-12-25 | 2014-12-25
Calendar: Used for Microsoft Project 98 Baseline Calendar11
Large Test File | Large Test File2
2014-01-01 | 2014-01-01
2014-01-20 | 2014-01-20
2014-02-17 | 2014-02-17
2014-05-26 | 2014-05-26
2014-07-04 | 2014-07-04
2014-09-01 | 2014-09-01
2014-10-13 | 2014-10-13
2014-11-11 | 2014-11-11
2014-11-27 | 2014-11-27
2014-12-25 | 2014-12-25
Calendar: Night Shift
Large Test File | Large Test File2
Calendar: Weekend Hours
Large Test File | Large Test File2
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-27 | 2020-05-27
2020-07-04 | 2020-07-04
Calendar: Overtime Calendar
Large Test File | Large Test File2
2017-11-10 | 2017-11-10
2017-11-23 | 2017-11-23
2017-12-25 | 2017-12-25
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
Calendar: Overtime Schedule Calendar
Large Test File | Large Test File2
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-11-26 | 2020-11-26
2020-12-25 | 2020-12-25
Calendar: ZIN_Holiday
Large Test File | Large Test File2
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-11-26 | 2020-11-26
2020-12-25 | 2020-12-25
Calendar: Drawing and MWO
Large Test File | Large Test File2
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-11-26 | 2020-11-26
2020-12-25 | 2020-12-25
2021-01-01 | 2021-01-01
2021-01-18 | 2021-01-18
2021-02-15 | 2021-02-15
2021-05-31 | 2021-05-31
2021-07-05 | 2021-07-05
2021-09-06 | 2021-09-06
2021-10-11 | 2021-10-11
2021-11-11 | 2021-11-11
2021-11-25 | 2021-11-25
2021-12-24 | 2021-12-24
2021-12-31 | 2021-12-31
2022-01-17 | 2022-01-17
2022-02-21 | 2022-02-21
2022-05-30 | 2022-05-30
2022-07-04 | 2022-07-04
2022-09-05 | 2022-09-05
2022-10-10 | 2022-10-10
2022-11-11 | 2022-11-11
2022-11-24 | 2022-11-24
2022-12-26 | 2022-12-26
Calendar: SPACEDOC
Large Test File | Large Test File2
2012-01-01 | 2012-01-01
2013-01-01 | 2013-01-01
2014-01-01 | 2014-01-01
2015-01-01 | 2015-01-01
2016-01-01 | 2016-01-01
2017-01-01 | 2017-01-01
2018-01-01 | 2018-01-01
2019-01-01 | 2019-01-01
2020-01-01 | 2020-01-01
2021-01-01 | 2021-01-01
2012-01-16 | 2012-01-16
2013-01-14 | 2013-01-14
2014-01-20 | 2014-01-20
2015-01-19 | 2015-01-19
2016-01-18 | 2016-01-18
2017-01-16 | 2017-01-16
2018-01-15 | 2018-01-15
2019-01-14 | 2019-01-14
2020-01-20 | 2020-01-20
2021-01-18 | 2021-01-18
2012-02-20 | 2012-02-20
2013-02-18 | 2013-02-18
2014-02-17 | 2014-02-17
2015-02-16 | 2015-02-16
2016-02-15 | 2016-02-15
2017-02-20 | 2017-02-20
2018-02-19 | 2018-02-19
2019-02-18 | 2019-02-18
2020-02-17 | 2020-02-17
2021-02-15 | 2021-02-15
2013-05-27 | 2013-05-27
2014-05-26 | 2014-05-26
2015-05-25 | 2015-05-25
2016-05-23 | 2016-05-23
2017-05-22 | 2017-05-22
2018-05-21 | 2018-05-21
2019-05-27 | 2019-05-27
2020-05-25 | 2020-05-25
2021-05-24 | 2021-05-24
2022-05-23 | 2022-05-23
2012-07-04 | 2012-07-04
2013-07-04 | 2013-07-04
2014-07-04 | 2014-07-04
2015-07-04 | 2015-07-04
2016-07-04 | 2016-07-04
2017-07-04 | 2017-07-04
2018-07-04 | 2018-07-04
2019-07-04 | 2019-07-04
2020-07-04 | 2020-07-04
2021-07-04 | 2021-07-04
2012-09-03 | 2012-09-03
2013-09-02 | 2013-09-02
2014-09-01 | 2014-09-01
2015-09-07 | 2015-09-07
2016-09-05 | 2016-09-05
2017-09-04 | 2017-09-04
2018-09-03 | 2018-09-03
2019-09-02 | 2019-09-02
2020-09-07 | 2020-09-07
2021-09-06 | 2021-09-06
2012-10-15 | 2012-10-15
2013-10-14 | 2013-10-14
2014-10-20 | 2014-10-20
2015-10-19 | 2015-10-19
2016-10-17 | 2016-10-17
2017-10-16 | 2017-10-16
2018-10-15 | 2018-10-15
2019-10-14 | 2019-10-14
2020-10-19 | 2020-10-19
2012-11-11 | 2012-11-11
2013-11-11 | 2013-11-11
2014-11-11 | 2014-11-11
2015-11-11 | 2015-11-11
2016-11-11 | 2016-11-11
2017-11-11 | 2017-11-11
2018-11-11 | 2018-11-11
2019-11-11 | 2019-11-11
2020-11-11 | 2020-11-11
2021-11-11 | 2021-11-11
2012-11-22 | 2012-11-22
2013-11-21 | 2013-11-21
2014-11-27 | 2014-11-27
2015-11-26 | 2015-11-26
2016-11-24 | 2016-11-24
2017-11-23 | 2017-11-23
2018-11-22 | 2018-11-22
2019-11-21 | 2019-11-21
2020-11-26 | 2020-11-26
2021-11-25 | 2021-11-25
2012-12-25 | 2012-12-25
2013-12-25 | 2013-12-25
2014-12-25 | 2014-12-25
2015-12-25 | 2015-12-25
2016-12-25 | 2016-12-25
2017-12-25 | 2017-12-25
2018-12-25 | 2018-12-25
2019-12-25 | 2019-12-25
2020-12-25 | 2020-12-25
Calendar: SPACEDOC II
Large Test File | Large Test File2
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
Calendar: OT-2
Large Test File | Large Test File2
2017-11-10 | 2017-11-10
2017-11-23 | 2017-11-23
2017-12-25 | 2017-12-25
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
Calendar: OT-3 2019
Large Test File | Large Test File2
2017-11-10 | 2017-11-10
2017-11-23 | 2017-11-23
2017-12-25 | 2017-12-25
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
Calendar: OT - 47hr ZIN Project Calendar
Large Test File | Large Test File2
2017-11-10 | 2017-11-10
2017-11-23 | 2017-11-23
2017-12-25 | 2017-12-25
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
Calendar: ZIN Overtime Project Calendar
Large Test File | Large Test File2
2017-12-25 | 2017-12-25
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-11-26 | 2020-11-26
2020-12-25 | 2020-12-25
2021-01-01 | 2021-01-01
2021-01-18 | 2021-01-18
2021-02-15 | 2021-02-15
2021-05-31 | 2021-05-31
2021-07-05 | 2021-07-05
2021-09-06 | 2021-09-06
2021-10-11 | 2021-10-11
2021-11-11 | 2021-11-11
2021-11-25 | 2021-11-25
2021-12-24 | 2021-12-24
2021-12-31 | 2021-12-31
2022-01-17 | 2022-01-17
2022-02-21 | 2022-02-21
2022-05-30 | 2022-05-30
2022-07-04 | 2022-07-04
2022-09-05 | 2022-09-05
2022-10-10 | 2022-10-10
2022-11-11 | 2022-11-11
2022-11-24 | 2022-11-24
2022-12-26 | 2022-12-26
Calendar: SPACE DOC
Large Test File | Large Test File2
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
Calendar: FCF Calendar
Large Test File | Large Test File2
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-11-26 | 2020-11-26
2020-12-25 | 2020-12-25
2021-01-01 | 2021-01-01
Calendar: 7 days a wk work
Large Test File | Large Test File2
2017-07-04 | 2017-07-04
2017-09-04 | 2017-09-04
2017-10-09 | 2017-10-09
2017-11-10 | 2017-11-10
2017-11-23 | 2017-11-23
2017-12-25 | 2017-12-25
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-11-26 | 2020-11-26
2020-12-25 | 2020-12-25
2021-01-01 | 2021-01-01
2021-01-18 | 2021-01-18
2021-02-15 | 2021-02-15
2021-05-31 | 2021-05-31
2021-07-05 | 2021-07-05
2021-09-06 | 2021-09-06
2021-10-11 | 2021-10-11
2021-11-11 | 2021-11-11
2021-11-25 | 2021-11-25
2021-12-24 | 2021-12-24
2021-12-31 | 2021-12-31
2022-01-17 | 2022-01-17
2022-02-21 | 2022-02-21
2022-05-30 | 2022-05-30
2022-07-04 | 2022-07-04
2022-09-05 | 2022-09-05
2022-10-10 | 2022-10-10
2022-11-11 | 2022-11-11
2022-11-24 | 2022-11-24
2022-12-26 | 2022-12-26
2023-01-02 | 2023-01-02
2023-01-16 | 2023-01-16
2023-02-20 | 2023-02-20
2023-05-29 | 2023-05-29
2023-07-04 | 2023-07-04
2023-09-04 | 2023-09-04
2023-10-09 | 2023-10-09
2023-11-10 | 2023-11-10
2023-11-23 | 2023-11-23
2023-12-25 | 2023-12-25
2024-01-01 | 2024-01-01
2024-01-15 | 2024-01-15
2024-02-19 | 2024-02-19
2024-05-27 | 2024-05-27
2024-07-04 | 2024-07-04
2024-09-02 | 2024-09-02
2024-10-14 | 2024-10-14
2024-11-11 | 2024-11-11
2024-11-28 | 2024-11-28
2024-12-25 | 2024-12-25
2025-01-01 | 2025-01-01
2025-01-20 | 2025-01-20
2025-02-17 | 2025-02-17
2025-05-26 | 2025-05-26
2025-07-04 | 2025-07-04
2025-09-01 | 2025-09-01
2025-10-13 | 2025-10-13
2025-11-11 | 2025-11-11
2025-11-27 | 2025-11-27
2025-12-25 | 2025-12-25
Calendar: ZIN Project Calendar - Overtime
Large Test File | Large Test File2
2014-01-01 | 2014-01-01
2014-01-20 | 2014-01-20
2014-02-17 | 2014-02-17
2014-05-26 | 2014-05-26
2014-07-04 | 2014-07-04
2014-09-01 | 2014-09-01
2014-10-13 | 2014-10-13
2014-11-11 | 2014-11-11
2014-11-27 | 2014-11-27
2014-12-25 | 2014-12-25
2015-01-01 | 2015-01-01
2015-01-19 | 2015-01-19
2015-02-16 | 2015-02-16
2015-05-25 | 2015-05-25
2015-07-03 | 2015-07-03
2015-09-07 | 2015-09-07
2015-10-12 | 2015-10-12
2015-11-11 | 2015-11-11
2015-11-26 | 2015-11-26
2015-12-25 | 2015-12-25
2016-01-01 | 2016-01-01
2016-01-18 | 2016-01-18
2016-02-15 | 2016-02-15
2016-05-30 | 2016-05-30
2016-07-04 | 2016-07-04
2016-09-05 | 2016-09-05
2016-10-10 | 2016-10-10
2016-11-11 | 2016-11-11
2016-11-24 | 2016-11-24
2016-12-26 | 2016-12-26
2017-01-02 | 2017-01-02
2017-01-16 | 2017-01-16
2017-02-20 | 2017-02-20
2017-05-29 | 2017-05-29
2017-07-04 | 2017-07-04
2017-09-04 | 2017-09-04
2017-10-09 | 2017-10-09
2017-11-10 | 2017-11-10
2017-11-23 | 2017-11-23
2017-12-25 | 2017-12-25
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-11-26 | 2020-11-26
2020-12-25 | 2020-12-25
2021-01-01 | 2021-01-01
2021-01-18 | 2021-01-18
2021-02-15 | 2021-02-15
2021-05-31 | 2021-05-31
2021-07-05 | 2021-07-05
2021-09-06 | 2021-09-06
2021-10-11 | 2021-10-11
2021-11-11 | 2021-11-11
2021-11-25 | 2021-11-25
2021-12-24 | 2021-12-24
2021-12-31 | 2021-12-31
2022-01-17 | 2022-01-17
2022-02-21 | 2022-02-21
2022-05-30 | 2022-05-30
2022-07-04 | 2022-07-04
2022-09-05 | 2022-09-05
2022-10-10 | 2022-10-10
2022-11-11 | 2022-11-11
2022-11-24 | 2022-11-24
2022-12-26 | 2022-12-26
2023-01-02 | 2023-01-02
2023-01-16 | 2023-01-16
2023-02-20 | 2023-02-20
2023-05-29 | 2023-05-29
2023-07-04 | 2023-07-04
2023-09-04 | 2023-09-04
2023-10-09 | 2023-10-09
2023-11-10 | 2023-11-10
2023-11-23 | 2023-11-23
2023-12-25 | 2023-12-25
2024-01-01 | 2024-01-01
2024-01-15 | 2024-01-15
2024-02-19 | 2024-02-19
2024-05-27 | 2024-05-27
2024-07-04 | 2024-07-04
2024-09-02 | 2024-09-02
2024-10-14 | 2024-10-14
2024-11-11 | 2024-11-11
2024-11-28 | 2024-11-28
2024-12-25 | 2024-12-25
2025-01-01 | 2025-01-01
2025-01-20 | 2025-01-20
2025-02-17 | 2025-02-17
2025-05-26 | 2025-05-26
2025-07-04 | 2025-07-04
2025-09-01 | 2025-09-01
2025-10-13 | 2025-10-13
2025-11-11 | 2025-11-11
2025-11-27 | 2025-11-27
2025-12-25 | 2025-12-25
Calendar: EDU OT 6 days at 10 hours
Large Test File | Large Test File2
2014-01-01 | 2014-01-01
2014-01-20 | 2014-01-20
2014-02-17 | 2014-02-17
2014-05-26 | 2014-05-26
2014-07-04 | 2014-07-04
2014-09-01 | 2014-09-01
2014-10-13 | 2014-10-13
2014-11-11 | 2014-11-11
2014-11-27 | 2014-11-27
2014-12-25 | 2014-12-25
2015-01-01 | 2015-01-01
2015-01-19 | 2015-01-19
2015-02-16 | 2015-02-16
2015-05-25 | 2015-05-25
2015-07-03 | 2015-07-03
2015-09-07 | 2015-09-07
2015-10-12 | 2015-10-12
2015-11-11 | 2015-11-11
2015-11-26 | 2015-11-26
2015-12-25 | 2015-12-25
2016-01-01 | 2016-01-01
2016-01-18 | 2016-01-18
2016-02-15 | 2016-02-15
2016-05-30 | 2016-05-30
2016-07-04 | 2016-07-04
2016-09-05 | 2016-09-05
2016-10-10 | 2016-10-10
2016-11-11 | 2016-11-11
2016-11-24 | 2016-11-24
2016-12-26 | 2016-12-26
2017-01-02 | 2017-01-02
2017-01-16 | 2017-01-16
2017-02-20 | 2017-02-20
2017-05-29 | 2017-05-29
2017-07-04 | 2017-07-04
2017-09-04 | 2017-09-04
2017-10-09 | 2017-10-09
2017-11-10 | 2017-11-10
2017-11-23 | 2017-11-23
2017-12-25 | 2017-12-25
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-11-26 | 2020-11-26
2020-12-25 | 2020-12-25
2021-01-01 | 2021-01-01
2021-01-18 | 2021-01-18
2021-02-15 | 2021-02-15
2021-05-31 | 2021-05-31
2021-07-05 | 2021-07-05
2021-09-06 | 2021-09-06
2021-10-11 | 2021-10-11
2021-11-11 | 2021-11-11
2021-11-25 | 2021-11-25
2021-12-24 | 2021-12-24
2021-12-31 | 2021-12-31
2022-01-17 | 2022-01-17
2022-02-21 | 2022-02-21
2022-05-30 | 2022-05-30
2022-07-04 | 2022-07-04
2022-09-05 | 2022-09-05
2022-10-10 | 2022-10-10
2022-11-11 | 2022-11-11
2022-11-24 | 2022-11-24
2022-12-26 | 2022-12-26
2023-01-02 | 2023-01-02
2023-01-16 | 2023-01-16
2023-02-20 | 2023-02-20
2023-05-29 | 2023-05-29
2023-07-04 | 2023-07-04
2023-09-04 | 2023-09-04
2023-10-09 | 2023-10-09
2023-11-10 | 2023-11-10
2023-11-23 | 2023-11-23
2023-12-25 | 2023-12-25
2024-01-01 | 2024-01-01
2024-01-15 | 2024-01-15
2024-02-19 | 2024-02-19
2024-05-27 | 2024-05-27
2024-07-04 | 2024-07-04
2024-09-02 | 2024-09-02
2024-10-14 | 2024-10-14
2024-11-11 | 2024-11-11
2024-11-28 | 2024-11-28
2024-12-25 | 2024-12-25
2025-01-01 | 2025-01-01
2025-01-20 | 2025-01-20
2025-02-17 | 2025-02-17
2025-05-26 | 2025-05-26
2025-07-04 | 2025-07-04
2025-09-01 | 2025-09-01
2025-10-13 | 2025-10-13
2025-11-11 | 2025-11-11
2025-11-27 | 2025-11-27
2025-12-25 | 2025-12-25
Calendar: ZIN Working Time
Large Test File | Large Test File2
2016-09-05 | 2016-09-05
2016-10-10 | 2016-10-10
2016-11-11 | 2016-11-11
2016-11-24 | 2016-11-24
2016-12-26 | 2016-12-26
2017-01-02 | 2017-01-02
2017-01-16 | 2017-01-16
2017-02-20 | 2017-02-20
2017-05-29 | 2017-05-29
2017-07-04 | 2017-07-04
2017-09-04 | 2017-09-04
2017-10-09 | 2017-10-09
2017-11-10 | 2017-11-10
2017-11-23 | 2017-11-23
2017-12-25 | 2017-12-25
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-21 | 2018-05-21
Calendar: ZIN Working Time Expanded
Large Test File | Large Test File2
2016-09-05 | 2016-09-05
2017-09-04 | 2017-09-04
2018-09-03 | 2018-09-03
2019-09-02 | 2019-09-02
2020-09-07 | 2020-09-07
2021-09-06 | 2021-09-06
2022-09-05 | 2022-09-05
2023-09-04 | 2023-09-04
2024-09-02 | 2024-09-02
2016-10-10 | 2016-10-10
2016-11-11 | 2016-11-11
2016-11-24 | 2016-11-24
2017-11-23 | 2017-11-23
2018-11-22 | 2018-11-22
2019-11-21 | 2019-11-21
2020-11-26 | 2020-11-26
2021-11-25 | 2021-11-25
2022-11-24 | 2022-11-24
2023-11-23 | 2023-11-23
2024-11-21 | 2024-11-21
2025-11-27 | 2025-11-27
2026-11-26 | 2026-11-26
2027-11-25 | 2027-11-25
2028-11-23 | 2028-11-23
2029-11-22 | 2029-11-22
2016-12-26 | 2016-12-26
2017-01-02 | 2017-01-02
2017-01-16 | 2017-01-16
2017-02-20 | 2017-02-20
2017-05-29 | 2017-05-29
2017-07-04 | 2017-07-04
2017-10-09 | 2017-10-09
2017-11-10 | 2017-11-10
2017-12-25 | 2017-12-25
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-21 | 2018-05-21
2018-07-04 | 2018-07-04
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-12-25 | 2020-12-25
Calendar: OT 47hr ZIN Project Calendar
Large Test File | Large Test File2
2012-01-01 | 2012-01-01
2013-01-01 | 2013-01-01
2014-01-01 | 2014-01-01
2015-01-01 | 2015-01-01
2016-01-01 | 2016-01-01
2017-01-01 | 2017-01-01
2018-01-01 | 2018-01-01
2019-01-01 | 2019-01-01
2020-01-01 | 2020-01-01
2021-01-01 | 2021-01-01
2012-01-16 | 2012-01-16
2013-01-14 | 2013-01-14
2014-01-20 | 2014-01-20
2015-01-19 | 2015-01-19
2016-01-18 | 2016-01-18
2017-01-16 | 2017-01-16
2018-01-15 | 2018-01-15
2019-01-14 | 2019-01-14
2020-01-20 | 2020-01-20
2021-01-18 | 2021-01-18
2012-02-20 | 2012-02-20
2013-02-18 | 2013-02-18
2014-02-17 | 2014-02-17
2015-02-16 | 2015-02-16
2016-02-15 | 2016-02-15
2017-02-20 | 2017-02-20
2018-02-19 | 2018-02-19
2019-02-18 | 2019-02-18
2020-02-17 | 2020-02-17
2021-02-15 | 2021-02-15
2013-05-27 | 2013-05-27
2014-05-26 | 2014-05-26
2015-05-25 | 2015-05-25
2016-05-23 | 2016-05-23
2017-05-22 | 2017-05-22
2018-05-21 | 2018-05-21
2019-05-27 | 2019-05-27
2020-05-25 | 2020-05-25
2021-05-24 | 2021-05-24
2022-05-23 | 2022-05-23
2012-07-04 | 2012-07-04
2013-07-04 | 2013-07-04
2014-07-04 | 2014-07-04
2015-07-04 | 2015-07-04
2016-07-04 | 2016-07-04
2017-07-04 | 2017-07-04
2018-07-04 | 2018-07-04
2019-07-04 | 2019-07-04
2020-07-04 | 2020-07-04
2021-07-04 | 2021-07-04
2012-09-03 | 2012-09-03
2013-09-02 | 2013-09-02
2014-09-01 | 2014-09-01
2015-09-07 | 2015-09-07
2016-09-05 | 2016-09-05
2017-09-04 | 2017-09-04
2018-09-03 | 2018-09-03
2019-09-02 | 2019-09-02
2020-09-07 | 2020-09-07
2021-09-06 | 2021-09-06
2012-10-15 | 2012-10-15
2013-10-14 | 2013-10-14
2014-10-20 | 2014-10-20
2015-10-19 | 2015-10-19
2016-10-17 | 2016-10-17
2017-10-16 | 2017-10-16
2018-10-15 | 2018-10-15
2019-10-14 | 2019-10-14
2020-10-19 | 2020-10-19
2012-11-11 | 2012-11-11
2013-11-11 | 2013-11-11
2014-11-11 | 2014-11-11
2015-11-11 | 2015-11-11
2016-11-11 | 2016-11-11
2017-11-11 | 2017-11-11
2018-11-11 | 2018-11-11
2019-11-11 | 2019-11-11
2020-11-11 | 2020-11-11
2021-11-11 | 2021-11-11
2012-11-22 | 2012-11-22
2013-11-21 | 2013-11-21
2014-11-27 | 2014-11-27
2015-11-26 | 2015-11-26
2016-11-24 | 2016-11-24
2017-11-23 | 2017-11-23
2018-11-22 | 2018-11-22
2019-11-21 | 2019-11-21
2020-11-26 | 2020-11-26
2021-11-25 | 2021-11-25
2012-12-25 | 2012-12-25
2013-12-25 | 2013-12-25
2014-12-25 | 2014-12-25
2015-12-25 | 2015-12-25
2016-12-25 | 2016-12-25
2017-12-25 | 2017-12-25
2018-12-25 | 2018-12-25
2019-12-25 | 2019-12-25
2020-12-25 | 2020-12-25
Calendar: Overtime Schedule Calendar
Large Test File | Large Test File2
2017-09-04 | 2017-09-04
2017-10-09 | 2017-10-09
2017-11-10 | 2017-11-10
2017-11-23 | 2017-11-23
2017-12-25 | 2017-12-25
2018-01-01 | 2018-01-01
2018-01-15 | 2018-01-15
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
Calendar: Holiday and Vacation Time
Large Test File | Large Test File2
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
Calendar: ZBOT
Large Test File | Large Test File2
2011-10-10 | 2011-10-10
Calendar: SPACEDOC II
Large Test File | Large Test File2
2018-02-19 | 2018-02-19
2018-05-28 | 2018-05-28
2018-07-04 | 2018-07-04
2018-09-03 | 2018-09-03
2018-10-08 | 2018-10-08
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
Calendar: SCENIC Project Calendar
Large Test File | Large Test File2
2018-10-08 | 2018-10-08
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
Calendar: MFG-OT
Large Test File | Large Test File2
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-11-26 | 2020-11-26
2020-12-25 | 2020-12-25
Calendar: Copy of MFG-OT
Large Test File | Large Test File2
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
Calendar: ZIN Overtime Schedule Calendar
Large Test File | Large Test File2
2018-11-12 | 2018-11-12
2018-11-22 | 2018-11-22
2018-12-25 | 2018-12-25
2019-01-01 | 2019-01-01
2019-01-21 | 2019-01-21
2019-02-18 | 2019-02-18
2019-05-27 | 2019-05-27
2019-07-04 | 2019-07-04
2019-09-02 | 2019-09-02
2019-10-14 | 2019-10-14
2019-11-11 | 2019-11-11
2019-11-28 | 2019-11-28
2019-12-25 | 2019-12-25
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-02-17 | 2020-02-17
2020-05-25 | 2020-05-25
2020-07-03 | 2020-07-03
2020-09-07 | 2020-09-07
2020-10-12 | 2020-10-12
2020-11-11 | 2020-11-11
2020-11-26 | 2020-11-26
2020-12-25 | 2020-12-25
Calendar: ASIT_REFERENCE
Large Test File | Large Test File2

## ID
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2

## Description
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2

## Activity-Type
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2

## Baseline-Duration
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2

## Original-Duration
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Original Duration - 756 (36%) | Original Duration - 756 (36%) | Original Duration - 756 (36%) | Original Duration - 756 (36%) | Original Duration - 756 (36%) | Original Duration - 756 (36%) | Original Duration - 756 (36%) | Original Duration - 756 (36%) | Original Duration - 756 (36%) | Original Duration - 756 (36%) | Original Duration - 756 (36%) | Original Duration - 756 (36%) | Original Duration - 756 (36%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 1249 | v1zgYyoO7UpynPZXt29g | Summary | 611 | 1 | 1 |  | 2874 | p | 145 | -5% | 3019
2 | 147 | DEZpxiHWY7fkyvQEaEGc | Summary | 1132 | 1.2 | 1.2 |  | 2874 | p | 145 | -5% | 3019
3 | 158 | D5C8AUNeoI4YKF3PggKx | Summary | 255 | 1.2.7 | 1.2.7 |  | 655 | p | 438 | -67% | 1093
4 | 6636 | 3J1qFTgnrSSZVnoYdTv5 | Summary | 140 | 1.2.7.3 | 1.2.7.3 |  | 389 | p | 12 | -3% | 401
5 | 6338 | whnkqeDzsaW1H7xphaZA | Normal | 49 | 1.2.7.3.4 | 1.2.7.3.4 |  | 49 | p | 3 | -6% | 52
6 | 6673 | sIWmvaXMX3ZF9ctRNm7s | Normal | 34 | 1.2.7.3.3 | 1.2.7.3.3 |  | 112 | q | -1 | (-1%) | 111
7 | 160 | gFTVv5U5XORyz5ZEYbdN | Summary | 703 | 1.2.8 | 1.2.8 |  | 703 | q | -1 | 0% | 702
8 | 172 | EY5PMcgR4N5ReAIF6NHn | Summary | 582 | 1.2.9 | 1.2.9 |  | 582 | p | 22 | -4% | 604
9 | 179 | jSOjvYE1qiHOKdcV2ixu | Summary | 554 | 1.2.10 | 1.2.10 |  | 739 | p | 69 | -9% | 808
10 | 195 | jWoM7YMyhsN7uWtVDNIl | Summary | 276 | 1.2.11 | 1.2.11 |  | 276 | p | 596 | -216% | 872
11 | 4180 | LxVAz76PSOUu8y7B8sy3 | Summary | 218 | 1.3 | 1.3 |  | 1186 | p | 12 | -1% | 1198
12 | 384 | GE3w1SHplCQZN7aYDVw8 | Summary | 34 | 1.3.3 | 1.3.3 |  | 1136 | p | 12 | -1% | 1148
13 | 429 | Pbs0MxOqvHazWgB8fpDs | Summary | 41 | 1.3.3.2 | 1.3.3.2 |  | 1041 | p | 9 | -1% | 1050
14 | 436 | OGXVzK31PKUn8DxCdn94 | Normal | 33 | 1.3.3.2.10 | 1.3.3.2.10 |  | 33 | p | 1 | -3% | 34
15 | 437 | kEyeaq7ebxWRSvBqGkHC | Summary | 19 | 1.3.3.1 | 1.3.3.1 |  | 998 | p | 20 | -2% | 1018
16 | 438 | QjVW4dYK4boDcUrG7MUx | Summary | 23 | 1.3.3.1.2 | 1.3.3.1.2 |  | 390 | p | 20 | -5% | 410
17 | 445 | cIIfBfMFMZUbJxswwNzj | Summary | 28 | 1.3.3.1.2.4 | 1.3.3.1.2.4 |  | 378 | p | 20 | -5% | 398
18 | 5768 | 9l9o7D6Il8vKVgGgZRMW | Summary | 197 | 1.3.3.4 | 1.3.3.4 |  | 394 | p | 12 | -3% | 406
19 | 6289 | NknbxY1EWobhbJ98SVRq | Summary | 270 | 1.3.2 | 1.3.2 |  | 737 | p | 12 | -2% | 749
20 | 3848 | g0gBmZeXCCPZTY4kkYs8 | Summary | 210 | 1.3.2.1 | 1.3.2.1 |  | 737 | p | 10 | -1% | 747
21 | 3849 | PKYN5IsyqbTocjyswPFM | Normal | 17 | 1.3.2.1.1 | 1.3.2.1.1 |  | 482 | q | -4 | (-1%) | 478
22 | 3850 | sk2pEdmn2KeVBRyrQzgn | Summary | 233 | 1.3.2.1.2 | 1.3.2.1.2 |  | 441 | p | 10 | -2% | 451
23 | 3857 | FObPKa3HJ5KI4gFmAx2r | Summary | 210 | 1.3.2.1.2.2 | 1.3.2.1.2.2 |  | 277 | p | 29 | -10% | 306
24 | 3858 | pWvg9Owxac1jXAINT5hs | Normal | 24 | 1.3.2.1.2.2.1 | 1.3.2.1.2.2.1 |  | 79 | q | -5 | (-6%) | 74
25 | 3859 | xrpLG6wlwOL4sRwHPU5B | Normal | 28 | 1.3.2.1.2.2.2 | 1.3.2.1.2.2.2 |  | 28 | p | 1 | -4% | 29
26 | 3861 | rvfyADOJtzNcPT3VL85f | Normal | 100 | 1.3.2.1.2.2.3 | 1.3.2.1.2.2.3 |  | 100 | p | 21 | -21% | 121
27 | 3862 | FUtleP4nAJHYxzLOWKZH | Normal | 20 | 1.3.2.1.2.2.4 | 1.3.2.1.2.2.4 |  | 20 | q | -1 | (-5%) | 19
28 | 3863 | WaF24jcpD2qzV3M05hSl | Summary | 178 | 1.3.2.1.2.3 | 1.3.2.1.2.3 |  | 374 | p | 9 | -2% | 383
29 | 3864 | kkmwKYrSq6DehQmbGkxo | Summary | 90 | 1.3.2.1.2.3.2 | 1.3.2.1.2.3.2 |  | 90 | q | -3 | (-3%) | 87
30 | 3865 | ZK3GDclfde20Vh8DU71K | Normal | 30 | 1.3.2.1.2.3.2.1 | 1.3.2.1.2.3.2.1 |  | 30 | p | 2 | -7% | 32
31 | 3866 | 8Zrc7ItBhrTjO1TWxqmf | Normal | 20 | 1.3.2.1.2.3.2.2 | 1.3.2.1.2.3.2.2 |  | 20 | q | -4 | (-20%) | 16
32 | 3868 | NCkZSbtMfUxIg95lxXXn | Normal | 10 | 1.3.2.1.2.3.2.6 | 1.3.2.1.2.3.2.6 |  | 10 | q | -1 | (-10%) | 9
33 | 6563 | 7FPcbor42GN7O6Ym4IZM | Normal | 10 | 1.3.2.1.2.3.2.4 | 1.3.2.1.2.3.2.4 |  | 10 | p | 1 | -10% | 11
34 | 7186 | ttl1FahPn0WwOuyGdmk6 | Summary | 138 | 1.3.2.3 | 1.3.2.3 |  | 276 | p | 15 | -5% | 291
35 | 7188 | yn5QOVI2BZ7jor10JaQN | Summary | 55 | 1.3.2.3.2 | 1.3.2.3.2 |  | 144 | q | -1 | (-1%) | 143
36 | 7189 | jup7puBG1dNvbV8jB14f | Summary | 69 | 1.3.2.3.2.1 | 1.3.2.3.2.1 |  | 144 | q | -10 | (-7%) | 134
37 | 7190 | Ob13piboJI4zFNOVPzZD | Summary | 50 | 1.3.2.3.2.1.1 | 1.3.2.3.2.1.1 |  | 95 | q | -16 | (-17%) | 79
38 | 7192 | rcBSOCAYFUxP7jsyoqGw | Normal | 11 | 1.3.2.3.2.1.1.2 | 1.3.2.3.2.1.1.2 |  | 11 | q | -2 | (-18%) | 9
39 | 7193 | hzdeRXxytBFeNJPq5eHn | Summary | 50 | 1.3.2.3.2.1.2 | 1.3.2.3.2.1.2 |  | 74 | q | -22 | (-30%) | 52
40 | 7194 | mB0uoGZ1D1fuFzk350Kb | Normal | 30 | 1.3.2.3.2.1.2.1 | 1.3.2.3.2.1.2.1 |  | 30 | q | -7 | (-23%) | 23
41 | 7196 | fFBpC2vR2qp5KXHLtypR | Summary | 23 | 1.3.2.3.2.1.3 | 1.3.2.3.2.1.3 |  | 95 | p | 20 | -21% | 115
42 | 7205 | 688LmElxek6WZQ34zEgD | Summary | 40 | 1.3.2.3.2.2 | 1.3.2.3.2.2 |  | 81 | p | 19 | -23% | 100
43 | 7206 | bMXBNIC1fF7AjliDPdfr | Normal | 25 | 1.3.2.3.2.2.1 | 1.3.2.3.2.2.1 |  | 60 | q | -1 | (-2%) | 59
44 | 7207 | 51ZGrscW6XrNzeOMbLyw | Normal | 5 | 1.3.2.3.2.2.2 | 1.3.2.3.2.2.2 |  | 5 | q | -1 | (-20%) | 4
45 | 7210 | 5vpOUfvEpSU2AKPwltv0 | Summary | 14 | 1.3.2.3.2.3 | 1.3.2.3.2.3 |  | 89 | q | -2 | (-2%) | 87
46 | 7212 | IA5BwO4PzPuXs5yI3XzH | Normal | 5 | 1.3.2.3.2.3.2 | 1.3.2.3.2.3.2 |  | 5 | q | -2 | (-40%) | 3
47 | 7215 | a8OJFGtOVEyM75c9puYK | Summary | 34 | 1.3.2.3.2.4 | 1.3.2.3.2.4 |  | 71 | p | 7 | -10% | 78
48 | 7220 | nvywSXdnd0LSUGSiB3or | Normal | 10 | 1.3.2.3.2.4.5 | 1.3.2.3.2.4.5 |  | 10 | p | 2 | -20% | 12
49 | 7221 | PYoR7OoHLcblZDJJ1hTC | Normal | 20 | 1.3.2.3.2.4.6 | 1.3.2.3.2.4.6 |  | 20 | p | 5 | -25% | 25
50 | 7223 | 2cLCJpvBPh4ccgbvKrEi | Summary | 38 | 1.3.2.3.2.5 | 1.3.2.3.2.5 |  | 115 | p | 28 | -24% | 143
51 | 7227 | QiFvht1v2EB9ODLdNK6M | Normal | 25 | 1.3.2.3.2.5.4 | 1.3.2.3.2.5.4 |  | 30 | p | 6 | -20% | 36
52 | 7228 | SSqxRWtJ8NkhLwkx3Zp5 | Normal | 15 | 1.3.2.3.2.5.5 | 1.3.2.3.2.5.5 |  | 15 | p | 2 | -13% | 17
53 | 7514 | 4jhJaLUHxegkfPxUyChC | Normal | 15 | 1.3.2.3.2.5.9 | 1.3.2.3.2.5.9 |  | 15 | q | -1 | (-7%) | 14
54 | 7236 | OqdHv6QLhEyFdmarh5Mg | Normal | 5 | 1.3.2.3.3.1.4 | 1.3.2.3.3.1.4 |  | 5 | p | 1 | -20% | 6
55 | 7237 | xLl9f1S8pVLgozw4LZw4 | Normal | 10 | 1.3.2.3.3.1.5 | 1.3.2.3.3.1.5 |  | 10 | q | -1 | (-10%) | 9
56 | 7243 | nppwsC1hz1MTRepHit5q | Normal | 3 | 1.3.2.3.3.2.3 | 1.3.2.3.3.2.3 |  | 3 | p | 1 | -33% | 4
57 | 7244 | FpvbIzqyAjmrguHRtjoA | Summary | 68 | 1.3.2.3.4 | 1.3.2.3.4 |  | 68 | p | 3 | -4% | 71
58 | 7245 | ysJ2Wz17vAaH50NFOd3r | Normal | 2 | 1.3.2.3.4.1 | 1.3.2.3.4.1 |  | 2 | p | 1 | -50% | 3
59 | 7246 | w8OYvCOBO1azAOar59yv | Normal | 3 | 1.3.2.3.4.2 | 1.3.2.3.4.2 |  | 3 | q | -1 | (-33%) | 2
60 | 7248 | nqyBToLUXvLl91VDFcK9 | Summary | 20 | 1.3.2.3.4.4 | 1.3.2.3.4.4 |  | 20 | p | 2 | -10% | 22
61 | 7250 | G5mdz8DmOa8TGNlmxmOk | Normal | 20 | 1.3.2.3.4.4.2 | 1.3.2.3.4.4.2 |  | 20 | p | 2 | -10% | 22
62 | 7251 | p2IEwFFq1YxDgQwaqReT | Summary | 48 | 1.3.2.3.4.5 | 1.3.2.3.4.5 |  | 48 | p | 1 | -2% | 49
63 | 7252 | R4hlQqYwslHcXudIUORM | Normal | 20 | 1.3.2.3.4.5.1 | 1.3.2.3.4.5.1 |  | 20 | p | 2 | -10% | 22
64 | 7257 | EmkT3sq6aGy3vx96JSsX | Normal | 3 | 1.3.2.3.4.5.6 | 1.3.2.3.4.5.6 |  | 3 | q | -1 | (-33%) | 2
65 | 6269 | tUCxonMalaI13D6hsUSU | Summary | 99 | 1.5 | 1.5 |  | 1240 | p | 12 | -1% | 1252
66 | 6278 | SNMcp7h74WVvBiN3lPNB | Summary | 66 | 1.5.6 | 1.5.6 |  | 1230 | p | 22 | -2% | 1252
67 | 605 | HP2TrbmUH5Qc4V2P2k1T | Normal | 14 | 1.5.6.1 | 1.5.6.1 |  | 838 | p | 3 | 0% | 841
68 | 620 | q8advjPa5PEndSFXJ05j | Summary | 158 | 1.5.6.6 | 1.5.6.6 |  | 756 | p | 22 | -3% | 778
69 | 622 | Q48N5ZSDLesB1Bsda2wx | Summary | 156 | 1.5.6.6.2 | 1.5.6.6.2 |  | 478 | p | 19 | -4% | 497
70 | 633 | FgJ5XjjThZN85XQOJ0nJ | Normal | 21 | 1.5.6.6.2.10 | 1.5.6.6.2.10 |  | 21 | q | -1 | (-5%) | 20
71 | 635 | ztvy5zkS4z9HirKgvHGY | Normal | 20 | 1.5.6.6.2.11 | 1.5.6.6.2.11 |  | 20 | q | -2 | (-10%) | 18
72 | 636 | ZpIfqMwIaczq2BqznW2q | Normal | 6 | 1.5.6.6.2.12 | 1.5.6.6.2.12 |  | 6 | p | 2 | -33% | 8
73 | 640 | 10AmMHkCz4b8n0xqbyCt | Normal | 5 | 1.5.6.6.2.16 | 1.5.6.6.2.16 |  | 5 | q | -1 | (-20%) | 4
74 | 641 | KUqcSNVxncHPLVJNV5ca | Normal | 2 | 1.5.6.6.2.17 | 1.5.6.6.2.17 |  | 2 | q | -1 | (-50%) | 1
75 | 646 | Haue3rYYySw3jbXWnBeq | Normal | 3 | 1.5.6.6.3 | 1.5.6.6.3 |  | 3 | p | 1 | -33% | 4
76 | 648 | 6WPgljRre9DjhHGVsVUH | Summary | 120 | 1.5.6.6.5 | 1.5.6.6.5 |  | 426 | p | 22 | -5% | 448
77 | 657 | nePaKBbqDo6OltylvukE | Summary | 14 | 1.5.6.6.5.4 | 1.5.6.6.5.4 |  | 14 | q | -1 | (-7%) | 13
78 | 658 | PyBKEPMZMe2YeOC66yut | Normal | 11 | 1.5.6.6.5.4.1 | 1.5.6.6.5.4.1 |  | 11 | q | -1 | (-9%) | 10
79 | 666 | OcAHNnZWZgiwxfUiheGU | Normal | 5 | 1.5.6.6.5.6 | 1.5.6.6.5.6 |  | 5 | q | -1 | (-20%) | 4
80 | 667 | HPj21Hyun1nWvxJOQMhf | Normal | 28 | 1.5.6.6.5.7 | 1.5.6.6.5.7 |  | 28 | p | 3 | -11% | 31
81 | 670 | zBtIFoyMK1KgXAv407C9 | Summary | 29 | 1.5.6.5 | 1.5.6.5 |  | 239 | p | 20 | -8% | 259
82 | 6281 | RYPcKAyzQapOQ3GupQll | Summary | 104 | 1.5.5 | 1.5.5 |  | 415 | p | 19 | -5% | 434
83 | 1466 | LmBGiI2jXQ3lZF0l79sj | Summary | 104 | 1.5.5.1 | 1.5.5.1 |  | 415 | p | 19 | -5% | 434
84 | 1471 | FsiT4ZMTOq9hGqZQQdYf | Normal | 11 | 1.5.5.1.9 | 1.5.5.1.9 |  | 11 | p | 3 | -27% | 14
85 | 1472 | KG0YDAdikr58WjA79FVb | Normal | 9 | 1.5.5.1.10 | 1.5.5.1.10 |  | 9 | q | -1 | (-11%) | 8
86 | 6292 | 1Cm9NXihvfL2WEnYcHvT | Summary | 42 | 1.5.4 | 1.5.4 |  | 845 | p | 27 | -3% | 872
87 | 3944 | HRTLaCTjRjqysGxmE6ve | Normal | 36 | 1.5.4.2 | 1.5.4.2 |  | 418 | p | 2 | 0% | 420
88 | 3949 | knRWxUZkgPmXKgij09tb | Summary | 25 | 1.5.4.5 | 1.5.4.5 |  | 419 | p | 27 | -6% | 446
89 | 3950 | NJx1RMKdqhuNKRLGMSBQ | Summary | 27 | 1.5.4.5.1 | 1.5.4.5.1 |  | 336 | p | 27 | -8% | 363
90 | 3951 | BNWJw3sHADBJTHA2Ybu0 | Normal | 16 | 1.5.4.5.1.1 | 1.5.4.5.1.1 |  | 291 | p | 1 | 0% | 292
91 | 3964 | ZzcX1hV2BTbfmTYJl5AE | Summary | 19 | 1.5.4.5.4 | 1.5.4.5.4 |  | 401 | p | 26 | -6% | 427
92 | 3967 | BaECEBO5p44IeRhOgeK2 | Normal | 19 | 1.5.4.5.4.3 | 1.5.4.5.4.3 |  | 134 | p | 6 | -4% | 140
93 | 5996 | M6DLFbZyZKXroBVfXncj | Summary | 19 | 1.5.4.4 | 1.5.4.4 |  | 396 | p | 20 | -5% | 416
94 | 3948 | 6ze4BjeYc1B5uifD0Fqa | Normal | 10 | 1.5.4.4.9 | 1.5.4.4.9 |  | 196 | q | -1 | (-1%) | 195
95 | 6605 | Qtljmhuq3GHp8HrV3pPP | Normal | 6 | 1.5.4.4.7 | 1.5.4.4.7 |  | 48 | p | 1 | -2% | 49
96 | 6299 | JvNaxkj9UdrgV7BcBski | Summary | 134 | 1.5.1 | 1.5.1 |  | 735 | p | 22 | -3% | 757
97 | 4213 | pNBoUl9px0n4wFhfXXqQ | Summary | 90 | 1.5.1.1 | 1.5.1.1 |  | 591 | p | 22 | -4% | 613
98 | 6444 | XymP4MvJgra2aDdoc9vw | Normal | 46 | 1.5.1.1.2 | 1.5.1.1.2 |  | 546 | q | -7 | (-1%) | 539
99 | 6445 | Wo6GLLiu9tXQyZ8t43hX | Normal | 43 | 1.5.1.1.3 | 1.5.1.1.3 |  | 43 | p | 9 | -21% | 52
100 | 6674 | 3EUoGYyEaAia67bx8maJ | Summary | 69 | 1.5.1.3 | 1.5.1.3 |  | 248 | q | -1 | 0% | 247
101 | 6680 | ttlvn3uwilh7nqgbHtE7 | Normal | 37 | 1.5.1.3.7 | 1.5.1.3.7 |  | 110 | p | 2 | -2% | 112
102 | 6681 | NHiN8b86HRxpkLb9JGGD | Normal | 10 | 1.5.1.3.9 | 1.5.1.3.9 |  | 10 | p | 2 | -20% | 12
103 | 6308 | 9d1kbrq4aHbr7FOmo76u | Summary | 27 | 1.5.2 | 1.5.2 |  | 975 | q | -4 | 0% | 971
104 | 5611 | e3AOkT5PZcArPsKmcVqB | Summary | 48 | 1.5.2.2 | 1.5.2.2 |  | 777 | q | -4 | (-1%) | 773
105 | 5614 | COTl0owSvMhEdF9iuXCz | Normal | 0 | 1.5.2.2.10.2 | 1.5.2.2.10.2 |  | 0 | p | 1 |  | 1
106 | 5627 | s0vjJX7zGlVyBdE0eigo | Summary | 15 | 1.5.2.2.8 | 1.5.2.2.8 |  | 15 | q | -1 | (-7%) | 14
107 | 5629 | ghMhRqrbgVxCQv51dU2T | Normal | 0 | 1.5.2.2.8.2 | 1.5.2.2.8.2 |  | 0 | p | 1 |  | 1
108 | 5633 | 2UPBwQymcCOUpuUjnBTe | Normal | 3 | 1.5.2.2.8.6 | 1.5.2.2.8.6 |  | 3 | q | -1 | (-33%) | 2
109 | 5635 | ZYzv9KOmVdYL2d3ZPb8b | Summary | 0 | 1.5.2.2.9 | 1.5.2.2.9 |  | 18 | p | 1 | -6% | 19
110 | 5638 | jBSFjjY1RfmWgqa8tOlO | Normal | 0 | 1.5.2.2.9.3 | 1.5.2.2.9.3 |  | 11 | p | 1 | -9% | 12
111 | 5641 | QjWOhv4eRSTZWx0ATAUl | Normal | 23 | 1.5.2.2.11 | 1.5.2.2.11 |  | 23 | q | -3 | (-13%) | 20
112 | 6309 | taNk8S9bKnlDToaFycS6 | Summary | 37 | 1.5.3 | 1.5.3 |  | 311 | p | 19 | -6% | 330
113 | 5443 | L0xk8h495fvdhlwnri8N | Summary | 37 | 1.5.3.1 | 1.5.3.1 |  | 311 | p | 19 | -6% | 330
114 | 5445 | 95pLIsxhFDdrMJGVBrpQ | Summary | 35 | 1.5.3.1.2 | 1.5.3.1.2 |  | 43 | p | 19 | -44% | 62
115 | 5447 | ijJ4zfbEfOInLYX7Vu9Z | Normal | 6 | 1.5.3.1.2.2 | 1.5.3.1.2.2 |  | 6 | q | -1 | (-17%) | 5
116 | 5449 | 6It4K5O7iZJhLoLO2jyi | Normal | 6 | 1.5.3.1.2.4 | 1.5.3.1.2.4 |  | 6 | q | -1 | (-17%) | 5
117 | 7381 | Ao7wteklS85dOuCCMM3I | Normal | 124 | 1.5.1 | 1.5.1 |  | 124 | q | -13 | (-10%) | 111
118 | 6270 | Wwp4MRWhcV55WleZhe1f | Summary | 288 | 1.4 | 1.4 |  | 975 | p | 21 | -2% | 996
119 | 6290 | VuOK0YK760zOpXaJ9U7h | Summary | 140 | 1.4.3 | 1.4.3 |  | 915 | p | 8 | -1% | 923
120 | 4537 | FhESv2GOKRYErv6rS2Ko | Summary | 140 | 1.4.3.1 | 1.4.3.1 |  | 915 | p | 8 | -1% | 923
121 | 4536 | zU98x2LHVd7UXovDFMXu | Normal | 14 | 1.4.3.1.1 | 1.4.3.1.1 |  | 511 | p | 3 | -1% | 514
122 | 5854 | 2kqOvhRPajU4Q0ZPsUnx | Normal | 8 | 1.4.3.1.4 | 1.4.3.1.4 |  | 8 | p | 1 | -12% | 9
123 | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Normal | 49 | 1.4.3.1.5 | 1.4.3.1.5 |  | 49 | p | 8 | -16% | 57
124 | 6291 | 7X6NK9qir9GRz5m7bXmK | Summary | 297 | 1.4.1 | 1.4.1 |  | 860 | p | 21 | -2% | 881
125 | 3891 | VQVEpj4HfOnKALplb4t9 | Summary | 43 | 1.4.1.1 | 1.4.1.1 |  | 366 | p | 18 | -5% | 384
126 | 3897 | cqWsQsQWdy7etYVMNQBf | Summary | 53 | 1.4.1.1.2 | 1.4.1.1.2 |  | 325 | p | 18 | -6% | 343
127 | 3900 | fYbjIfZDvkbYu7p7dq3N | Normal | 14 | 1.4.1.1.2.3 | 1.4.1.1.2.3 |  | 53 | q | -2 | (-4%) | 51
128 | 3902 | FL4HGNxujC5zK4lN6AVO | Summary | 30 | 1.4.1.2 | 1.4.1.2 |  | 440 | q | -16 | (-4%) | 424
129 | 3903 | e0nMZ5CLCmjCURLrKpol | Summary | 30 | 1.4.1.2.1 | 1.4.1.2.1 |  | 440 | q | -16 | (-4%) | 424
130 | 3907 | pFYLZycbgH4KMn6pLhBU | Summary | 272 | 1.4.1.3 | 1.4.1.3 |  | 272 | p | 71 | -26% | 343
131 | 3910 | pNRX5rV0uvvHnR27z1AO | Normal | 8 | 1.4.1.3.3 | 1.4.1.3.3 |  | 8 | q | -1 | (-12%) | 7
132 | 3911 | R3AK39H17lCC16PE9DkR | Normal | 10 | 1.4.1.3.4 | 1.4.1.3.4 |  | 10 | q | -2 | (-20%) | 8
133 | 3912 | BSEXS69UjCPQ6j2zF47p | Normal | 15 | 1.4.1.3.5 | 1.4.1.3.5 |  | 15 | q | -2 | (-13%) | 13
134 | 3913 | nUmJBAacPI2xORV8OCED | Normal | 20 | 1.4.1.3.6 | 1.4.1.3.6 |  | 20 | p | 3 | -15% | 23
135 | 3914 | e7efPn2W4IFyilt2hNai | Normal | 30 | 1.4.1.3.7 | 1.4.1.3.7 |  | 30 | q | -5 | (-17%) | 25
136 | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Normal | 5 | 1.4.1.3.8 | 1.4.1.3.8 |  | 5 | p | 1 | -20% | 6
137 | 3917 | hmttcJptV92JIo4OpANW | Normal | 5 | 1.4.1.3.10 | 1.4.1.3.10 |  | 5 | p | 1 | -20% | 6
138 | 3922 | yD55zWPn8USsNa4i8nCC | Normal | 5 | 1.4.1.4.4 | 1.4.1.4.4 |  | 5 | p | 2 | -40% | 7
139 | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Normal | 15 | 1.4.1.4.5 | 1.4.1.4.5 |  | 15 | p | 7 | -47% | 22
140 | 3924 | N1CigBiMQE2J41ZAMkt0 | Normal | 20 | 1.4.1.4.6 | 1.4.1.4.6 |  | 20 | p | 2 | -10% | 22
141 | 3925 | hSr4t1vn7GiB6Kp7YK0M | Normal | 5 | 1.4.1.4.7 | 1.4.1.4.7 |  | 5 | q | -1 | (-20%) | 4
142 | 3926 | vGJMK6sejFbKR6Gom2up | Normal | 5 | 1.4.1.4.8 | 1.4.1.4.8 |  | 5 | p | 2 | -40% | 7
143 | 3927 | 3RLmiC17tI4E2ggNuRe0 | Normal | 5 | 1.4.1.4.9 | 1.4.1.4.9 |  | 5 | p | 1 | -20% | 6
144 | 6318 | cM5VCGnPiK1mfNJo8YLF | Summary | 309 | 1.4.2 | 1.4.2 |  | 972 | p | 3 | 0% | 975
145 | 5213 | 6YmlQVHNVjUNryBHQf8a | Summary | 61 | 1.4.2.2.3 | 1.4.2.2.3 |  | 61 | q | -4 | (-7%) | 57
146 | 5215 | KawuX1icbWQB8WlKVKy9 | Normal | 60 | 1.4.2.2.3.2 | 1.4.2.2.3.2 |  | 60 | q | -5 | (-8%) | 55
147 | 5217 | e116DivbRDCkLiH2zNhl | Summary | 61 | 1.4.2.2.4 | 1.4.2.2.4 |  | 61 | p | 2 | -3% | 63
148 | 5219 | Uz3hspiJXkYJElXZ00I5 | Normal | 60 | 1.4.2.2.4.2 | 1.4.2.2.4.2 |  | 60 | p | 2 | -3% | 62
149 | 5221 | iTaWceiQKMF6gUaF3DCB | Summary | 61 | 1.4.2.2.5 | 1.4.2.2.5 |  | 61 | q | -1 | (-2%) | 60
150 | 5223 | 3nEJb4lsc7akFmF6ULw7 | Normal | 60 | 1.4.2.2.5.2 | 1.4.2.2.5.2 |  | 60 | q | -1 | (-2%) | 59
151 | 5277 | TgmqG1sR4A60sNmMtPcE | Summary | 193 | 1.4.2.2.7 | 1.4.2.2.7 |  | 193 | p | 11 | -6% | 204
152 | 5278 | OmCdw3tKtVsW24V2aNqQ | Normal | 8 | 1.4.2.2.7.1 | 1.4.2.2.7.1 |  | 8 | p | 2 | -25% | 10
153 | 5279 | htHZ3VhuaadgfKg1VQls | Summary | 47 | 1.4.2.2.7.11 | 1.4.2.2.7.11 |  | 47 | p | 10 | -21% | 57
154 | 5282 | qBzS7vPbhPVzs7sVXgmM | Normal | 5 | 1.4.2.2.7.11.3 | 1.4.2.2.7.11.3 |  | 5 | q | -2 | (-40%) | 3
155 | 5283 | fU0pzeQGz2MN3lZmznFh | Normal | 5 | 1.4.2.2.7.11.4 | 1.4.2.2.7.11.4 |  | 5 | p | 1 | -20% | 6
156 | 5285 | ffNcVsnPBySsZbQiEShc | Normal | 10 | 1.4.2.2.7.11.6 | 1.4.2.2.7.11.6 |  | 10 | p | 1 | -10% | 11
157 | 6457 | PFYaNHtSBj97Eh5ysTvH | Normal | 7 | 1.4.2.2.7.2 | 1.4.2.2.7.2 |  | 7 | q | -2 | (-29%) | 5
158 | 6459 | ylmwXTiOnCLJpwlHTaRg | Normal | 10 | 1.4.2.2.7.4 | 1.4.2.2.7.4 |  | 10 | p | 2 | -20% | 12
159 | 6461 | 7ypQo0ZyAHzCHmFRlywg | Normal | 10 | 1.4.2.2.7.6 | 1.4.2.2.7.6 |  | 10 | p | 2 | -20% | 12
160 | 6464 | McSTYqZ3LCfaYSSmZoTn | Normal | 7 | 1.4.2.2.7.9 | 1.4.2.2.7.9 |  | 7 | q | -1 | (-14%) | 6
161 | 5226 | R9JO9mOSGmg0eoDimoJT | Summary | 71 | 1.4.2.1 | 1.4.2.1 |  | 653 | q | -23 | (-4%) | 630
162 | 5240 | NSmZbDTp76mGzDSQ7Ceh | Summary | 56 | 1.4.2.1.3 | 1.4.2.1.3 |  | 56 | p | 144 | -257% | 200
163 | 5241 | v6EKIZLcnDHW8CXOrD7y | Normal | 21 | 1.4.2.1.3.1 | 1.4.2.1.3.1 |  | 21 | q | -1 | (-5%) | 20
164 | 5242 | JYCfpao49G3jD8M94S66 | Normal | 10 | 1.4.2.1.3.2 | 1.4.2.1.3.2 |  | 10 | p | 1 | -10% | 11
165 | 5244 | Nwqnc6xsOuQ8oMDbKNfv | Normal | 15 | 1.4.2.1.3.4 | 1.4.2.1.3.4 |  | 15 | p | 1 | -7% | 16
166 | 5262 | PI0DE6xTKT4gLnHpqgjE | Summary | 137 | 1.4.2.1.6 | 1.4.2.1.6 |  | 361 | q | -23 | (-6%) | 338
167 | 5263 | URhzXaXmWu6rBPIMitrn | Normal | 30 | 1.4.2.1.6.1 | 1.4.2.1.6.1 |  | 224 | p | 1 | 0% | 225
168 | 5265 | ATYnDTN93dB3aTXfzslo | Normal | 6 | 1.4.2.1.6.2 | 1.4.2.1.6.2 |  | 6 | q | -1 | (-17%) | 5
169 | 5266 | G5H4IlBy3M3Zxs38gcIH | Normal | 10 | 1.4.2.1.6.3 | 1.4.2.1.6.3 |  | 10 | p | 1 | -10% | 11
170 | 5267 | 3RI5G3ymKjaLn96cfboa | Normal | 11 | 1.4.2.1.6.4 | 1.4.2.1.6.4 |  | 11 | p | 2 | -18% | 13
171 | 5268 | fG9nayiE82fFlNFtuyfN | Normal | 8 | 1.4.2.1.6.5 | 1.4.2.1.6.5 |  | 8 | p | 9 | -112% | 17
172 | 5269 | UP8sWsDXCDMiwOqWz3ib | Normal | 5 | 1.4.2.1.6.6 | 1.4.2.1.6.6 |  | 5 | p | 1 | -20% | 6
173 | 5270 | 0UA65kBzwzHULCayr1Gq | Normal | 8 | 1.4.2.1.6.7 | 1.4.2.1.6.7 |  | 8 | q | -1 | (-12%) | 7
174 | 5271 | mtztJWmm2OBnfmSsuoGt | Normal | 10 | 1.4.2.1.6.8 | 1.4.2.1.6.8 |  | 10 | p | 1 | -10% | 11
175 | 5272 | kvS9pO69DNwaLvofAQcb | Normal | 11 | 1.4.2.1.6.9 | 1.4.2.1.6.9 |  | 11 | p | 5 | -45% | 16
176 | 5289 | tqKGxL2oceRufkd47wnf | Summary | 319 | 1.4.2.3 | 1.4.2.3 |  | 319 | p | 26 | -8% | 345
177 | 5313 | 3y8KKUl940HiJi7UFKFT | Summary | 106 | 1.4.2.3.3 | 1.4.2.3.3 |  | 106 | p | 4 | -4% | 110
178 | 5316 | LCfcLPfxTjnSY0dCrjlE | Normal | 10 | 1.4.2.3.3.2 | 1.4.2.3.3.2 |  | 10 | q | -1 | (-10%) | 9
179 | 5317 | pw6YyMXR7oeqsrtIHdqo | Normal | 9 | 1.4.2.3.3.3 | 1.4.2.3.3.3 |  | 9 | p | 1 | -11% | 10
180 | 5318 | KMG5hXAC4X2MZPfyVOSc | Normal | 5 | 1.4.2.3.3.8 | 1.4.2.3.3.8 |  | 5 | p | 1 | -20% | 6
181 | 5319 | mDGXCmTQB2ITo8MYwlYq | Normal | 5 | 1.4.2.3.3.9 | 1.4.2.3.3.9 |  | 5 | p | 1 | -20% | 6
182 | 5322 | oNpYocgOFdrRcJiQE0H5 | Normal | 5 | 1.4.2.3.3.12 | 1.4.2.3.3.12 |  | 5 | p | 1 | -20% | 6
183 | 5326 | esDa5lJIA5zg0nP58cRd | Summary | 32 | 1.4.2.3.4 | 1.4.2.3.4 |  | 32 | q | -3 | (-9%) | 29
184 | 5327 | iRZmxts3rKQ38tplQw52 | Normal | 30 | 1.4.2.3.4.1 | 1.4.2.3.4.1 |  | 30 | q | -3 | (-10%) | 27
185 | 6321 | KAyzIHlSkkFZqIIdJ9JD | Summary | 144 | 1.4.2.3.2 | 1.4.2.3.2 |  | 144 | q | -24 | (-17%) | 120
186 | 5298 | c4SSanbHhynqs8RkqT3I | Normal | 3 | 1.4.2.3.2.2 | 1.4.2.3.2.2 |  | 3 | p | 1 | -33% | 4
187 | 5299 | HB5wL9z8KlZFeAas0WUQ | Normal | 11 | 1.4.2.3.2.3 | 1.4.2.3.2.3 |  | 11 | q | -1 | (-9%) | 10
188 | 5302 | 2rc67Y2hzAhRvE7YihWA | Normal | 10 | 1.4.2.3.2.1 | 1.4.2.3.2.1 |  | 10 | q | -1 | (-10%) | 9
189 | 5306 | yar7ts7ASIpTQqyvnwQd | Normal | 5 | 1.4.2.3.2.13 | 1.4.2.3.2.13 |  | 5 | p | 1 | -20% | 6
190 | 5307 | yRByGMPgEQcCecr5HzAA | Normal | 2 | 1.4.2.3.2.15 | 1.4.2.3.2.15 |  | 2 | p | 2 | -100% | 4
191 | 5308 | JBAsTSNPb9OQmIAmtadV | Normal | 20 | 1.4.2.3.2.17 | 1.4.2.3.2.17 |  | 20 | p | 9 | -45% | 29
192 | 6271 | Q6QswYSvhipRUbZBXuiu | Summary | 315 | 1.6 | 1.6 |  | 1928 | p | 68 | -4% | 1996
193 | 6277 | moVS9Ou3GclDwNSW1OnS | Summary | 264 | 1.6.7 | 1.6.7 |  | 1134 | p | 69 | -6% | 1203
194 | 700 | PZaQwD8fp0dlxZIxEZEd | Normal | 279 | 1.6.7.10 | 1.6.7.10 |  | 779 | p | 45 | -6% | 824
195 | 728 | 4dRz6TQj3FOK8lstTqZK | Summary | 396 | 1.6.7.9 | 1.6.7.9 |  | 636 | p | 52 | -8% | 688
196 | 741 | cktDjgZ5bp36SrQnCM1w | Summary | 458 | 1.6.7.9.3 | 1.6.7.9.3 |  | 511 | p | 52 | -10% | 563
197 | 751 | AADJzuTGAb4gWytj7CQi | Normal | 18 | 1.6.7.9.3.8 | 1.6.7.9.3.8 |  | 18 | q | -1 | (-6%) | 17
198 | 752 | r0c0rFS4EkOGynasmiCG | Normal | 36 | 1.6.7.9.3.7 | 1.6.7.9.3.7 |  | 36 | p | 1 | -3% | 37
199 | 759 | cZuo3MY7iyDrOJC1qVJx | Normal | 5 | 1.6.7.9.3.9 | 1.6.7.9.3.9 |  | 5 | q | -1 | (-20%) | 4
200 | 6323 | aU24Z8SrLl20SyyllZuy | Summary | 80 | 1.6.7.9.3.5 | 1.6.7.9.3.5 |  | 220 | q | -3 | (-1%) | 217
201 | 745 | aO52oWR4hBrrP5GVCo2a | Normal | 11 | 1.6.7.9.3.5.2 | 1.6.7.9.3.5.2 |  | 11 | q | -3 | (-27%) | 8
202 | 746 | qMC0J8brk1dsdpzlKrk7 | Normal | 12 | 1.6.7.9.3.5.3 | 1.6.7.9.3.5.3 |  | 12 | q | -1 | (-8%) | 11
203 | 6324 | gthK0FxwJBk3laTELp8O | Summary | 45 | 1.6.7.9.3.6 | 1.6.7.9.3.6 |  | 45 | q | -1 | (-2%) | 44
204 | 749 | Q6UXOpf9Kvzek7IGY0vp | Normal | 11 | 1.6.7.9.3.6.3 | 1.6.7.9.3.6.3 |  | 11 | q | -2 | (-18%) | 9
205 | 750 | lsyrPytnmjLTpXFywa7Z | Normal | 11 | 1.6.7.9.3.6.4 | 1.6.7.9.3.6.4 |  | 11 | p | 1 | -9% | 12
206 | 6325 | SeCXD5wMvkrEekc1PKVb | Summary | 48 | 1.6.7.9.3.10 | 1.6.7.9.3.10 |  | 48 | p | 58 | -121% | 106
207 | 753 | 8158sxzbHZvZEVAAqewP | Normal | 47 | 1.6.7.9.3.10.1 | 1.6.7.9.3.10.1 |  | 47 | p | 22 | -47% | 69
208 | 754 | hfPeDXfQSV7Nx9zb2rD7 | Normal | 8 | 1.6.7.9.3.10.2 | 1.6.7.9.3.10.2 |  | 8 | q | -2 | (-25%) | 6
209 | 5782 | EYY3j1SjnoLUV06T0QHs | Normal | 5 | 1.6.7.9.3.10.7 | 1.6.7.9.3.10.7 |  | 5 | q | -2 | (-40%) | 3
210 | 6326 | F4s3MnfyyA74WCIympSi | Summary | 75 | 1.6.7.9.3.11 | 1.6.7.9.3.11 |  | 75 | p | 38 | -51% | 113
211 | 760 | 7IpOsslq7gyebnCTulxX | Normal | 66 | 1.6.7.9.3.11.1 | 1.6.7.9.3.11.1 |  | 66 | q | -1 | (-2%) | 65
212 | 762 | nRInnITHYgcDsU5KDg6m | Normal | 8 | 1.6.7.9.3.11.3 | 1.6.7.9.3.11.3 |  | 8 | q | -2 | (-25%) | 6
213 | 6327 | dOJS0LaWQU970ssSiqsz | Summary | 59 | 1.6.7.9.3.12 | 1.6.7.9.3.12 |  | 59 | p | 5 | -8% | 64
214 | 763 | hLK2cdXSS7IhOZR53PgI | Normal | 6 | 1.6.7.9.3.12.1 | 1.6.7.9.3.12.1 |  | 6 | q | -1 | (-17%) | 5
215 | 764 | wTf98lLeHiXAkWj17mAH | Normal | 53 | 1.6.7.9.3.12.2 | 1.6.7.9.3.12.2 |  | 53 | p | 6 | -11% | 59
216 | 770 | cHAOkWrFbu094CNd9eCk | Summary | 91 | 1.6.7.8 | 1.6.7.8 |  | 527 | p | 17 | -3% | 544
217 | 6434 | cc8WGEqtonq4zOxPHtWc | Normal | 65 | 1.6.7.8.4 | 1.6.7.8.4 |  | 94 | q | -3 | (-3%) | 91
218 | 5785 | xIbBdattr1YLWDiqGWPC | Summary | 126 | 1.6.7.11 | 1.6.7.11 |  | 126 | p | 10 | -8% | 136
219 | 6435 | Ql00ScpYzqtI9PQP57zu | Normal | 122 | 1.6.7.11.2 | 1.6.7.11.2 |  | 122 | p | 11 | -9% | 133
220 | 6284 | T6s1mlIi1Lu4cscBpq9h | Summary | 273 | 1.6.6 | 1.6.6 |  | 447 | p | 7 | -2% | 454
221 | 1519 | Ig6aeqJATmPNbReGQrzj | Summary | 273 | 1.6.6.1 | 1.6.6.1 |  | 447 | p | 7 | -2% | 454
222 | 1464 | VN7GLU7alOC9oD3kkW9q | Normal | 30 | 1.6.6.1.4 | 1.6.6.1.4 |  | 30 | p | 8 | -27% | 38
223 | 1475 | suCYO4gIoCSrnZchT6aQ | Normal | 3 | 1.6.6.1.6 | 1.6.6.1.6 |  | 3 | p | 1 | -33% | 4
224 | 1476 | gbuDNYIgLq2nB3WERl4p | Normal | 30 | 1.6.6.1.7 | 1.6.6.1.7 |  | 30 | p | 7 | -23% | 37
225 | 1478 | UR7xa7LgN3sMlpzxRjvW | Normal | 3 | 1.6.6.1.9 | 1.6.6.1.9 |  | 3 | q | -1 | (-33%) | 2
226 | 6293 | WhUcOZjaj9TDZe74ojmh | Summary | 172 | 1.6.4 | 1.6.4 |  | 823 | p | 68 | -8% | 891
227 | 3929 | GkmiaraCbWdBUaRv136y | Summary | 19 | 1.6.4.15 | 1.6.4.15 |  | 315 | p | 29 | -9% | 344
228 | 3938 | 2iJ091mlhEkJyqoddB4L | Normal | 14 | 1.6.4.15.1 | 1.6.4.15.1 |  | 295 | q | -6 | (-2%) | 289
229 | 3931 | GleHIX38gd9vOXaUQYVA | Normal | 33 | 1.6.4.11 | 1.6.4.11 |  | 350 | q | -4 | (-1%) | 346
230 | 3933 | FbGZSJQTtuDZR2p8qmxq | Normal | 33 | 1.6.4.13 | 1.6.4.13 |  | 350 | p | 6 | -2% | 356
231 | 3935 | IRdaiLeeauelAg4QWklz | Normal | 33 | 1.6.4.12 | 1.6.4.12 |  | 350 | q | -1 | 0% | 349
232 | 3939 | cuQ4HC0Kn3S6GTvqv7QE | Normal | 33 | 1.6.4.14 | 1.6.4.14 |  | 350 | p | 9 | -3% | 359
233 | 3971 | mB1p68eekBqQhgV8es2U | Summary | 19 | 1.6.4.7 | 1.6.4.7 |  | 243 | p | 25 | -10% | 268
234 | 3981 | YTm9sByrDxPUc7AlWXh1 | Normal | 15 | 1.6.4.7.2 | 1.6.4.7.2 |  | 199 | q | -1 | (-1%) | 198
235 | 3980 | po54OWwjtqomy5uOkFBU | Normal | 40 | 1.6.4.4 | 1.6.4.4 |  | 318 | p | 5 | -2% | 323
236 | 3991 | kc0LQmDrjfLGJeMU4QIH | Summary | 70 | 1.6.4.17 | 1.6.4.17 |  | 440 | p | 26 | -6% | 466
237 | 3992 | cy141kwlo0X5isTqv3ku | Summary | 25 | 1.6.4.17.4 | 1.6.4.17.4 |  | 25 | p | 3 | -12% | 28
238 | 3993 | LBRozXrRhpq69SKlxnDb | Normal | 10 | 1.6.4.17.4.1 | 1.6.4.17.4.1 |  | 10 | p | 3 | -30% | 13
239 | 3994 | DvOjAQ6C9aXKnpaAVD1H | Normal | 5 | 1.6.4.17.4.2 | 1.6.4.17.4.2 |  | 5 | p | 1 | -20% | 6
240 | 3998 | 5UhDwyM7phAycUkk1Nye | Normal | 10 | 1.6.4.17.3.1 | 1.6.4.17.3.1 |  | 10 | p | 1 | -10% | 11
241 | 4000 | Y3aJp60cYMHromf8xgAE | Normal | 5 | 1.6.4.17.3.3 | 1.6.4.17.3.3 |  | 5 | q | -1 | (-20%) | 4
242 | 4002 | nJzh0eFJGsqvOmQRJzHn | Summary | 27 | 1.6.4.17.2 | 1.6.4.17.2 |  | 265 | p | 23 | -9% | 288
243 | 4003 | gjf3v6NdOQannovTvAoE | Normal | 19 | 1.6.4.17.2.1 | 1.6.4.17.2.1 |  | 257 | p | 1 | 0% | 258
244 | 4005 | NxZ8rMz5ZnJaz6z1SXKM | Normal | 3 | 1.6.4.17.2.3 | 1.6.4.17.2.3 |  | 3 | p | 1 | -33% | 4
245 | 4006 | fOTuJvqH3OcilXcZuEM5 | Normal | 4 | 1.6.4.17.2.4 | 1.6.4.17.2.4 |  | 4 | p | 1 | -25% | 5
246 | 4012 | A4Ck0Reyqf4cLzrM8uUY | Summary | 206 | 1.6.4.19 | 1.6.4.19 |  | 583 | q | -169 | (-29%) | 414
247 | 6168 | BHtkkzlMW8757DY2qb23 | Summary | 143 | 1.6.4.19.3 | 1.6.4.19.3 |  | 143 | p | 5 | -3% | 148
248 | 6169 | gdW3U4pURjb9iKkAVexH | Summary | 60 | 1.6.4.19.3.1 | 1.6.4.19.3.1 |  | 60 | p | 4 | -7% | 64
249 | 6170 | AwYLgXY6Mo1DqCbUEhPQ | Summary | 30 | 1.6.4.19.3.1.1 | 1.6.4.19.3.1.1 |  | 30 | p | 3 | -10% | 33
250 | 6172 | QgFskomqU31VYtYzB2O0 | Normal | 15 | 1.6.4.19.3.1.1.2 | 1.6.4.19.3.1.1.2 |  | 15 | p | 2 | -13% | 17
251 | 6174 | dvLkHNDhuFTU7AO5XWky | Normal | 15 | 1.6.4.19.3.1.3 | 1.6.4.19.3.1.3 |  | 15 | p | 2 | -13% | 17
252 | 6175 | IEttja5qNJ6P760Cd9De | Summary | 40 | 1.6.4.19.3.2 | 1.6.4.19.3.2 |  | 40 | p | 2 | -5% | 42
253 | 6176 | B6x3R7fnpOwupecmo90D | Normal | 10 | 1.6.4.19.3.2.1 | 1.6.4.19.3.2.1 |  | 10 | p | 1 | -10% | 11
254 | 6179 | xksMzlhYjvKZ4p1XJwSB | Normal | 10 | 1.6.4.19.3.2.4 | 1.6.4.19.3.2.4 |  | 10 | p | 1 | -10% | 11
255 | 6182 | JQHbjwkPqIslt5thIOgQ | Normal | 5 | 1.6.4.19.3.5 | 1.6.4.19.3.5 |  | 5 | q | -1 | (-20%) | 4
256 | 4037 | hMBnPD0NfYpjSqEpRMYY | Summary | 554 | 1.6.4.20 | 1.6.4.20 |  | 571 | p | 68 | -12% | 639
257 | 4038 | VkrURyJwsSkEVRV6WcXe | Summary | 411 | 1.6.4.20.1 | 1.6.4.20.1 |  | 432 | p | 51 | -12% | 483
258 | 4040 | g5zNgGHP8U11wPTJKhcB | Normal | 20 | 1.6.4.20.1.3 | 1.6.4.20.1.3 |  | 20 | q | -4 | (-20%) | 16
259 | 4041 | f0PORH3GhEIXFjYfGbTd | Normal | 97 | 1.6.4.20.1.6 | 1.6.4.20.1.6 |  | 97 | p | 22 | -23% | 119
260 | 4042 | SyfMayqY4a7i0nZLPz6Y | Normal | 129 | 1.6.4.20.1.7 | 1.6.4.20.1.7 |  | 129 | q | -4 | (-3%) | 125
261 | 6622 | EmEy5gJckBYofEEYNXFv | Normal | 20 | 1.6.4.20.1.4 | 1.6.4.20.1.4 |  | 20 | p | 2 | -10% | 22
262 | 6623 | BVU87KMg9Rhzc6j5yKVh | Normal | 20 | 1.6.4.20.1.5 | 1.6.4.20.1.5 |  | 20 | q | -1 | (-5%) | 19
263 | 4043 | XbXkjxtfHUxhg4CK1elt | Summary | 127 | 1.6.4.20.2 | 1.6.4.20.2 |  | 127 | p | 18 | -14% | 145
264 | 4045 | mDphgqAAxA2RnvA52x8A | Normal | 20 | 1.6.4.20.2.1 | 1.6.4.20.2.1 |  | 20 | p | 4 | -20% | 24
265 | 4046 | 5HyQBVwuqRdeW1HhaSOP | Normal | 10 | 1.6.4.20.2.2 | 1.6.4.20.2.2 |  | 10 | p | 1 | -10% | 11
266 | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Normal | 72 | 1.6.4.20.2.3 | 1.6.4.20.2.3 |  | 72 | p | 8 | -11% | 80
267 | 4048 | ybbKhm9jdtNbVzABGZ8L | Normal | 20 | 1.6.4.20.2.4 | 1.6.4.20.2.4 |  | 20 | p | 5 | -25% | 25
268 | 4049 | kP1jeiEwkYg4HRpUjG4p | Normal | 5 | 1.6.4.20.2.5 | 1.6.4.20.2.5 |  | 5 | q | -1 | (-20%) | 4
269 | 4050 | jQIHIDf5FTnJxQysEvnn | Summary | 37 | 1.6.4.20.3 | 1.6.4.20.3 |  | 37 | p | 3 | -8% | 40
270 | 4052 | JSSXcLTdD9VQNM766DgK | Normal | 20 | 1.6.4.20.3.1.1 | 1.6.4.20.3.1.1 |  | 20 | p | 1 | -5% | 21
271 | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Normal | 12 | 1.6.4.20.3.1.2 | 1.6.4.20.3.1.2 |  | 12 | q | -1 | (-8%) | 11
272 | 4059 | sH9kz6O2EFda2hu4x8Kx | Summary | 12 | 1.6.4.20.3.3 | 1.6.4.20.3.3 |  | 12 | q | -1 | (-8%) | 11
273 | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Normal | 3 | 1.6.4.20.3.3.1 | 1.6.4.20.3.3.1 |  | 3 | q | -1 | (-33%) | 2
274 | 5748 | cHP8KcDQZp8MvOi5a8Wj | Summary | 64 | 1.6.4.18 | 1.6.4.18 |  | 387 | p | 3 | -1% | 390
275 | 6701 | vwWJ3SVwW3tYdDDMDgOK | Summary | 60 | 1.6.4.18.3 | 1.6.4.18.3 |  | 217 | p | 3 | -1% | 220
276 | 6713 | JQXHTZXJblKyiNyxM0eT | Summary | 78 | 1.6.4.18.3.3 | 1.6.4.18.3.3 |  | 207 | p | 3 | -1% | 210
277 | 6727 | 5BlmDU3ct4fwjT54EODG | Summary | 21 | 1.6.4.18.3.3.2 | 1.6.4.18.3.3.2 |  | 94 | q | -1 | (-1%) | 93
278 | 7271 | 7ZvC3KC1rMxIYvbhicKJ | Normal | 10 | 1.6.4.18.3.3.2.7 | 1.6.4.18.3.3.2.7 |  | 10 | q | -1 | (-10%) | 9
279 | 7007 | 9uputDeZmGdSlUY8oN4J | Summary | 64 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 114 | p | 3 | -3% | 117
280 | 7010 | l7MAqMN94R7DBQRgok6z | Normal | 5 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 5 | q | -1 | (-20%) | 4
281 | 7301 | mVBynbXAicTgOFud0Dl3 | Normal | 5 | 1.6.4.18.3.3.7.6 | 1.6.4.18.3.3.7.6 |  | 5 | p | 1 | -20% | 6
282 | 7302 | 6S1rSJxqNAmNyzjZVL7L | Normal | 5 | 1.6.4.18.3.3.7.8 | 1.6.4.18.3.3.7.8 |  | 5 | q | -1 | (-20%) | 4
283 | 7279 | uD2jpviUMAewZ4YhDj8P | Summary | 32 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 72 | q | -6 | (-8%) | 66
284 | 7286 | weppsWRcwILLbxkFpraK | Summary | 39 | 1.6.4.18.3.3.5 | 1.6.4.18.3.3.5 |  | 57 | p | 1 | -2% | 58
285 | 7289 | YNbMTserJcwdDTx8O6lt | Normal | 5 | 1.6.4.18.3.3.5.3 | 1.6.4.18.3.3.5.3 |  | 5 | p | 1 | -20% | 6
286 | 7292 | 6vEOHVPLFOaXnW1xcDp6 | Normal | 10 | 1.6.4.18.3.3.5.6 | 1.6.4.18.3.3.5.6 |  | 10 | q | -1 | (-10%) | 9
287 | 7293 | ep0qwejNT11UOlW5WmY0 | Summary | 28 | 1.6.4.18.3.3.6 | 1.6.4.18.3.3.6 |  | 48 | p | 4 | -8% | 52
288 | 7296 | PnFVdPiNKahDkradYWdd | Normal | 5 | 1.6.4.18.3.3.6.3 | 1.6.4.18.3.3.6.3 |  | 5 | p | 2 | -40% | 7
289 | 7299 | ymtRqRQZa4AjGraGOZVd | Normal | 10 | 1.6.4.18.3.3.6.6 | 1.6.4.18.3.3.6.6 |  | 10 | p | 2 | -20% | 12
290 | 6297 | AqdIsKbIPOfZJkjKYjnG | Summary | 118 | 1.6.1 | 1.6.1 |  | 928 | q | -256 | (-28%) | 672
291 | 4200 | YSdvLAa6ztbhOKei71CV | Summary | 108 | 1.6.1.1 | 1.6.1.1 |  | 648 | p | 23 | -4% | 671
292 | 4202 | N5DTU5adYVhKR5So2Uvc | Normal | 88 | 1.6.1.1.3 | 1.6.1.1.3 |  | 469 | p | 2 | 0% | 471
293 | 4204 | CRzwy8942pbCOpcOMW2v | Normal | 20 | 1.6.1.1.4 | 1.6.1.1.4 |  | 20 | p | 1 | -5% | 21
294 | 4209 | 0Ck6gz1ZilLs9fM0b7nU | Summary | 46 | 1.6.1.3 | 1.6.1.3 |  | 547 | p | 11 | -2% | 558
295 | 4212 | yktUOUuzQyzOVBFBfL42 | Normal | 46 | 1.6.1.3.1 | 1.6.1.3.1 |  | 547 | q | -9 | (-2%) | 538
296 | 6311 | tQdu1pFxVkY2bj5IQjxI | Summary | 77 | 1.6.3 | 1.6.3 |  | 1594 | p | 109 | -7% | 1703
297 | 5452 | u9nFTwEoKsBrgeg8njOT | Normal | 5 | 1.6.3.1 | 1.6.3.1 |  | 711 | p | 185 | -26% | 896
298 | 5457 | kGunJCROCjWQWqBfRKBZ | Summary | 1 | 1.6.3.2 | 1.6.3.2 |  | 748 | p | 16 | -2% | 764
299 | 5458 | DngVHB2HpHpsOjFWu5hu | Summary | 1 | 1.6.3.2.1 | 1.6.3.2.1 |  | 748 | p | 16 | -2% | 764
300 | 5506 | wLM81Xdu8B5geOMMQz6m | Summary | 119 | 1.6.3.3 | 1.6.3.3 |  | 259 | p | 109 | -42% | 368
301 | 5508 | wHSntGHJkj4aA0wA3fA2 | Normal | 14 | 1.6.3.3.3 | 1.6.3.3.3 |  | 14 | p | 1 | -7% | 15
302 | 5509 | 1FHP32ReWIveKb3JOWEG | Summary | 44 | 1.6.3.3.4 | 1.6.3.3.4 |  | 44 | p | 5 | -11% | 49
303 | 5510 | LTFwTsrnxYhrGNFUv7CM | Normal | 12 | 1.6.3.3.4.1 | 1.6.3.3.4.1 |  | 12 | p | 3 | -25% | 15
304 | 5511 | Od3mMFxB7LjrJLF1slz4 | Normal | 11 | 1.6.3.3.4.2 | 1.6.3.3.4.2 |  | 11 | p | 1 | -9% | 12
305 | 5512 | Des2hDKSMjcJndTJRzoQ | Normal | 11 | 1.6.3.3.4.3 | 1.6.3.3.4.3 |  | 11 | p | 1 | -9% | 12
306 | 6890 | QKIolSsTnUWZiIhR6M5v | Normal | 40 | 1.6.3.3.1 | 1.6.3.3.1 |  | 165 | q | -10 | (-6%) | 155
307 | 6359 | hvfa0617w1FgmEnjjKwJ | Summary | 26 | 1.7.2.16 | 1.7.2.16 |  | 189 | p | 1 | -1% | 190
308 | 6360 | DMXbIVCeMtVR5pi4d5UN | Summary | 26 | 1.7.2.16.1 | 1.7.2.16.1 |  | 189 | p | 1 | -1% | 190
309 | 6361 | VEKeY9azNIVSZDSjYyKy | Summary | 33 | 1.7.2.16.1.3 | 1.7.2.16.1.3 |  | 189 | p | 1 | -1% | 190
310 | 7303 | fpLHmKjlfpy4s4tap5Xw | Summary | 39 | 1.6.3.11.1.3.4 | 1.6.3.11.1.3.4 |  | 72 | q | -6 | (-8%) | 66
311 | 7307 | eye8r8DevGvPITcdrMUe | Normal | 6 | 1.6.3.11.1.3.4.4 | 1.6.3.11.1.3.4.4 |  | 6 | q | -1 | (-17%) | 5
312 | 7309 | 19skeJKmh3pRSfTF3DDB | Summary | 30 | 1.6.3.11.1.3.5 | 1.6.3.11.1.3.5 |  | 64 | p | 1 | -2% | 65
313 | 7313 | boaUnlKi0h6sKdwgAbmA | Normal | 5 | 1.6.3.11.1.3.5.4 | 1.6.3.11.1.3.5.4 |  | 5 | p | 1 | -20% | 6
314 | 7315 | 9LywAxRsXdHsCrCcjGKV | Summary | 27 | 1.6.3.11.1.3.6 | 1.6.3.11.1.3.6 |  | 64 | p | 1 | -2% | 65
315 | 7318 | vWglY3BMmZCigDWMEMyY | Normal | 3 | 1.6.3.11.1.3.6.3 | 1.6.3.11.1.3.6.3 |  | 3 | p | 1 | -33% | 4
316 | 6273 | ljz6i2ltFwqcRU3btDx0 | Summary | 552 | 1.8 | 1.8 |  | 800 | p | 410 | -51% | 1210
317 | 1639 | mkPE1mMWzawwUBF3KKzV | Summary | 277 | 1.8.2 | 1.8.2 |  | 800 | p | 410 | -51% | 1210
318 | 6074 | fkBL64dyW7paLwgGr0ue | Normal | 212 | 1.8.2.3 | 1.8.2.3 |  | 594 | q | -2 | 0% | 592
319 | 6075 | pe2nScqRc5pgTwGaT5Zd | Normal | 193 | 1.8.2.2 | 1.8.2.2 |  | 575 | p | 13 | -2% | 588
320 | 6295 | uPS9GNqRLP4065SnBhEr | Summary | 387 | 1.8.5 | 1.8.5 |  | 417 | p | 258 | -62% | 675
321 | 3679 | 1KDcwGZKgevw1MizqBh0 | Summary | 387 | 1.8.5.1 | 1.8.5.1 |  | 417 | p | 258 | -62% | 675
322 | 3680 | E8qsx9NjEz7vaL5H7EFb | Summary | 189 | 1.8.5.1.1 | 1.8.5.1.1 |  | 189 | p | 6 | -3% | 195
323 | 3681 | wdhUrQuIMTMPn1LoqO1m | Normal | 24 | 1.8.5.1.1.1 | 1.8.5.1.1.1 |  | 24 | q | -7 | (-29%) | 17
324 | 3682 | 38PSIqFGHzjKldiudT82 | Summary | 25 | 1.8.5.1.1.4 | 1.8.5.1.1.4 |  | 25 | p | 3 | -12% | 28
325 | 3683 | JW3LUw009FZ7ddD6CdLX | Normal | 20 | 1.8.5.1.1.4.1 | 1.8.5.1.1.4.1 |  | 20 | p | 2 | -10% | 22
326 | 3684 | g3f8U3i4iakOhylueut6 | Normal | 5 | 1.8.5.1.1.4.2 | 1.8.5.1.1.4.2 |  | 5 | p | 2 | -40% | 7
327 | 3685 | eStRoX3vnaDmRLAWk58C | Summary | 40 | 1.8.5.1.1.5 | 1.8.5.1.1.5 |  | 40 | p | 6 | -15% | 46
328 | 3686 | 7zhxjkpiLTAH9tiW1eYy | Normal | 20 | 1.8.5.1.1.5.1 | 1.8.5.1.1.5.1 |  | 20 | p | 4 | -20% | 24
329 | 3690 | 8YDpqEvemQaMsfVmGpF8 | Normal | 5 | 1.8.5.1.1.5.5 | 1.8.5.1.1.5.5 |  | 5 | p | 1 | -20% | 6
330 | 3691 | ofZrlktbiXkVpuhhIeO5 | Summary | 25 | 1.8.5.1.1.6 | 1.8.5.1.1.6 |  | 25 | p | 1 | -4% | 26
331 | 3692 | xRsKOxB8zGAnVTXugcHQ | Normal | 20 | 1.8.5.1.1.6.1 | 1.8.5.1.1.6.1 |  | 20 | p | 1 | -5% | 21
332 | 3694 | 4tipOydrC0LTNincaMDW | Summary | 35 | 1.8.5.1.1.7 | 1.8.5.1.1.7 |  | 35 | p | 12 | -34% | 47
333 | 3695 | lT6NpgfSYqKHtVYFLSzF | Normal | 20 | 1.8.5.1.1.7.1 | 1.8.5.1.1.7.1 |  | 20 | p | 8 | -40% | 28
334 | 3696 | gijouZuJR1ZVcSfHKSTf | Normal | 5 | 1.8.5.1.1.7.2 | 1.8.5.1.1.7.2 |  | 5 | p | 1 | -20% | 6
335 | 3697 | 1158ttL4JEmZYV6RmdcS | Normal | 5 | 1.8.5.1.1.7.3 | 1.8.5.1.1.7.3 |  | 5 | p | 1 | -20% | 6
336 | 3698 | AKCwPpEPQi4iH3XDRpiM | Normal | 5 | 1.8.5.1.1.7.4 | 1.8.5.1.1.7.4 |  | 5 | p | 1 | -20% | 6
337 | 3700 | WE9bFDn3y5M7oiID5UPj | Normal | 20 | 1.8.5.1.1.8.1 | 1.8.5.1.1.8.1 |  | 20 | q | -2 | (-10%) | 18
338 | 3702 | sTuPByKbZEfSXxt0Z2G9 | Normal | 5 | 1.8.5.1.1.8.3 | 1.8.5.1.1.8.3 |  | 5 | p | 1 | -20% | 6
339 | 3703 | WHZRJAK4v6S9Zk2EBeP3 | Summary | 40 | 1.8.5.1.1.9 | 1.8.5.1.1.9 |  | 40 | q | -7 | (-18%) | 33
340 | 3704 | 3CXbrhXJooXd98jlpAkg | Normal | 20 | 1.8.5.1.1.9.1 | 1.8.5.1.1.9.1 |  | 20 | q | -6 | (-30%) | 14
341 | 3705 | RO9RShNcg0h7x9fD24Zk | Normal | 5 | 1.8.5.1.1.9.2 | 1.8.5.1.1.9.2 |  | 5 | q | -2 | (-40%) | 3
342 | 3706 | w8MhGnhxyXFIHvJdw6bc | Normal | 5 | 1.8.5.1.1.9.3 | 1.8.5.1.1.9.3 |  | 5 | p | 1 | -20% | 6
343 | 3707 | dJNKgtiJ1M8pNoPOlZcZ | Normal | 5 | 1.8.5.1.1.9.4 | 1.8.5.1.1.9.4 |  | 5 | p | 1 | -20% | 6
344 | 3709 | gpO5WcJkYid7jZAXZwbn | Summary | 40 | 1.8.5.1.1.10 | 1.8.5.1.1.10 |  | 40 | p | 4 | -10% | 44
345 | 3710 | KOKaQwRJEoC6vlU3mKjm | Normal | 20 | 1.8.5.1.1.10.1 | 1.8.5.1.1.10.1 |  | 20 | p | 1 | -5% | 21
346 | 3712 | sZwrgRbHYjKWcIa9rVK3 | Normal | 5 | 1.8.5.1.1.10.3 | 1.8.5.1.1.10.3 |  | 5 | p | 1 | -20% | 6
347 | 3713 | 4NbryuRKpmrExDEDqArG | Normal | 5 | 1.8.5.1.1.10.4 | 1.8.5.1.1.10.4 |  | 5 | q | -1 | (-20%) | 4
348 | 3714 | Fbm1iHrhCX8z8SNRXJuq | Normal | 5 | 1.8.5.1.1.10.5 | 1.8.5.1.1.10.5 |  | 5 | p | 2 | -40% | 7
349 | 6647 | hWzCSsDre5WTTpryk1b0 | Normal | 5 | 1.8.5.1.1.3 | 1.8.5.1.1.3 |  | 5 | p | 1 | -20% | 6
350 | 3715 | V6i7uYjEJBRYHjhIimqJ | Summary | 50 | 1.8.5.1.2 | 1.8.5.1.2 |  | 50 | q | -4 | (-8%) | 46
351 | 3716 | bdy5zVX59rD935sK6M5v | Normal | 20 | 1.8.5.1.2.1 | 1.8.5.1.2.1 |  | 20 | q | -1 | (-5%) | 19
352 | 3717 | 5PdqCAMtbYgi5VsFO6ls | Normal | 20 | 1.8.5.1.2.4 | 1.8.5.1.2.4 |  | 20 | q | -2 | (-10%) | 18
353 | 6671 | 0oTh3tmNX3iVSaVNVmGK | Normal | 5 | 1.8.5.1.2.2 | 1.8.5.1.2.2 |  | 5 | p | 1 | -20% | 6
354 | 6672 | BKyGOzVPyPwKpI9CyseJ | Normal | 5 | 1.8.5.1.2.3 | 1.8.5.1.2.3 |  | 5 | q | -2 | (-40%) | 3
355 | 3718 | vTyTgxcbRSz6H6lqDAEf | Summary | 20 | 1.8.5.1.3 | 1.8.5.1.3 |  | 20 | q | -9 | (-45%) | 11
356 | 3719 | B9ymEBZ7zimHMMqNS20Q | Normal | 20 | 1.8.5.1.3.1 | 1.8.5.1.3.1 |  | 20 | q | -9 | (-45%) | 11
357 | 3720 | rPRo0RE1uNkj9oG127hu | Summary | 109 | 1.8.5.1.4 | 1.8.5.1.4 |  | 109 | q | -10 | (-9%) | 99
358 | 3722 | hYa6Ppkzu6veYWmxHffd | Normal | 27 | 1.8.5.1.4.2 | 1.8.5.1.4.2 |  | 27 | q | -1 | (-4%) | 26
359 | 6650 | FvuNLI4Jaew3VjPpwL3e | Normal | 28 | 1.8.5.1.4.4 | 1.8.5.1.4.4 |  | 28 | q | -7 | (-25%) | 21
360 | 6652 | 0afM7N7hGdWHQjlFenVR | Normal | 10 | 1.8.5.1.4.6 | 1.8.5.1.4.6 |  | 10 | q | -2 | (-20%) | 8
361 | 3723 | 4qmbzAmtSx0gvDVaBsYe | Summary | 239 | 1.8.5.1.5 | 1.8.5.1.5 |  | 330 | p | 11 | -3% | 341
362 | 3724 | ZCOxRRLLrh9Pa7VnBAyk | Normal | 27 | 1.8.5.1.5.1 | 1.8.5.1.5.1 |  | 27 | q | -3 | (-11%) | 24
363 | 3725 | 8cgOIQk4rBKvjXdBm8mF | Normal | 91 | 1.8.5.1.5.9 | 1.8.5.1.5.9 |  | 200 | q | -24 | (-12%) | 176
364 | 6663 | LVExlIxeJ6XB3yqm0Dzs | Normal | 28 | 1.8.5.1.5.4 | 1.8.5.1.5.4 |  | 28 | q | -1 | (-4%) | 27
365 | 6664 | Io9oZ1dPqEE9GDlMTPxh | Normal | 28 | 1.8.5.1.5.5 | 1.8.5.1.5.5 |  | 28 | p | 1 | -4% | 29
366 | 6665 | ycT0qtEFjd4p02S4Ehf1 | Normal | 28 | 1.8.5.1.5.6 | 1.8.5.1.5.6 |  | 28 | q | -2 | (-7%) | 26
367 | 6666 | sX3PHseynvzwKI9my2AH | Normal | 15 | 1.8.5.1.5.7 | 1.8.5.1.5.7 |  | 15 | p | 7 | -47% | 22
368 | 6667 | 0dYk2X7XWh2rSSHkHo2L | Normal | 10 | 1.8.5.1.5.8 | 1.8.5.1.5.8 |  | 10 | q | -3 | (-30%) | 7
369 | 3726 | 5hjTNIk7WmpZNtmCLhPN | Summary | 96 | 1.8.5.1.6 | 1.8.5.1.6 |  | 96 | p | 13 | -14% | 109
370 | 3727 | rGcF2XgkgPtqRDM3KJ2D | Normal | 28 | 1.8.5.1.6.1 | 1.8.5.1.6.1 |  | 28 | p | 4 | -14% | 32
371 | 3728 | Hgqc9wbzS3SDikBm20zt | Normal | 28 | 1.8.5.1.6.3 | 1.8.5.1.6.3 |  | 28 | p | 7 | -25% | 35
372 | 6654 | MMK0qYycfTMCrFAZcf8J | Normal | 15 | 1.8.5.1.6.4 | 1.8.5.1.6.4 |  | 15 | p | 1 | -7% | 16
373 | 3729 | Y6b5KP0DE9c4tlFzqxp3 | Summary | 81 | 1.8.5.1.7 | 1.8.5.1.7 |  | 81 | q | -3 | (-4%) | 78
374 | 3730 | TswICWhG0Mjj1DenbPW5 | Normal | 28 | 1.8.5.1.7.1 | 1.8.5.1.7.1 |  | 28 | p | 2 | -7% | 30
375 | 6626 | 9d2gtkuh8SmNZwArNzpn | Normal | 10 | 1.8.5.1.7.4 | 1.8.5.1.7.4 |  | 10 | q | -2 | (-20%) | 8
376 | 6627 | QBgG0JxqOymB6vyjKsRZ | Normal | 28 | 1.8.5.1.7.2 | 1.8.5.1.7.2 |  | 28 | q | -1 | (-4%) | 27
377 | 6628 | PAI9VZBMaYriaY1wvhOi | Normal | 15 | 1.8.5.1.7.3 | 1.8.5.1.7.3 |  | 15 | q | -2 | (-13%) | 13
378 | 3733 | ufu7SWDoeBfTzZW24BQU | Summary | 189 | 1.8.5.1.9 | 1.8.5.1.9 |  | 189 | p | 423 | -224% | 612
379 | 3735 | rgqtw8hyurrfag2amXLA | Normal | 109 | 1.8.5.1.9.2 | 1.8.5.1.9.2 |  | 109 | q | -2 | (-2%) | 107
380 | 3736 | eIMYQUSTObIc5Lp6kKBE | Normal | 40 | 1.8.5.1.9.3 | 1.8.5.1.9.3 |  | 40 | q | -13 | (-32%) | 27
381 | 3737 | z19Wnme0hJcfEI4IfIQR | Normal | 25 | 1.8.5.1.9.4 | 1.8.5.1.9.4 |  | 25 | q | -3 | (-12%) | 22
382 | 6657 | uq5fluI8KT8LkPx57ktn | Normal | 10 | 1.8.5.1.9.5 | 1.8.5.1.9.5 |  | 10 | p | 2 | -20% | 12
383 | 6658 | ktg0XNnAmjjc1caqICt2 | Normal | 5 | 1.8.5.1.9.6 | 1.8.5.1.9.6 |  | 5 | p | 1 | -20% | 6
384 | 3739 | Ba23bBwg4xGpRd3Ht4kS | Normal | 24 | 1.8.5.1.10.1 | 1.8.5.1.10.1 |  | 24 | q | -3 | (-12%) | 21
385 | 3740 | lRtbtcrLyr1QGd0laoJi | Normal | 25 | 1.8.5.1.10.2 | 1.8.5.1.10.2 |  | 25 | p | 1 | -4% | 26
386 | 3741 | V05WnFKB5t2LuixhoKHO | Normal | 25 | 1.8.5.1.10.3 | 1.8.5.1.10.3 |  | 25 | p | 4 | -16% | 29
387 | 3742 | LRjVz0hoZuIRlQgcLYzs | Normal | 25 | 1.8.5.1.10.6 | 1.8.5.1.10.6 |  | 25 | p | 3 | -12% | 28
388 | 6648 | Z5T3n0GGVz8PB0IY5TXC | Normal | 10 | 1.8.5.1.10.5 | 1.8.5.1.10.5 |  | 10 | q | -2 | (-20%) | 8
389 | 6656 | tqprQgHoroqT051BXug3 | Normal | 15 | 1.8.5.1.10.4 | 1.8.5.1.10.4 |  | 15 | q | -2 | (-13%) | 13
390 | 6659 | NN3Qiea1foOxv05JqXnT | Normal | 10 | 1.8.5.1.10.7 | 1.8.5.1.10.7 |  | 10 | q | -1 | (-10%) | 9
391 | 6642 | A7Bd82G8YCk8VjEZkcvi | Summary | 135 | 1.8.5.1.8 | 1.8.5.1.8 |  | 135 | p | 340 | -252% | 475
392 | 3731 | 02LiOyWN4DF8GOeNSP5s | Normal | 20 | 1.8.5.1.8.1 | 1.8.5.1.8.1 |  | 20 | q | -4 | (-20%) | 16
393 | 3732 | x85AkT9s5HT2a4U2goND | Normal | 20 | 1.8.5.1.8.8 | 1.8.5.1.8.8 |  | 20 | p | 4 | -20% | 24
394 | 6629 | n59ds33sZr9JNOobmYWE | Normal | 30 | 1.8.5.1.8.2 | 1.8.5.1.8.2 |  | 30 | q | -10 | (-33%) | 20
395 | 6632 | 5y36mClzGR7vkSsODb4C | Normal | 15 | 1.8.5.1.8.5 | 1.8.5.1.8.5 |  | 15 | q | -4 | (-27%) | 11
396 | 6633 | uS272glxjETpDiVeJyGv | Normal | 20 | 1.8.5.1.8.6 | 1.8.5.1.8.6 |  | 20 | p | 2 | -10% | 22
397 | 6634 | 65ghvPiwU0AxSKrC11rG | Normal | 20 | 1.8.5.1.8.7 | 1.8.5.1.8.7 |  | 20 | p | 8 | -40% | 28
398 | 6643 | sKnPCsxlq51dE8cz52fo | Normal | 10 | 1.8.5.1.8.9 | 1.8.5.1.8.9 |  | 10 | q | -1 | (-10%) | 9
399 | 6313 | 8HYxn50EKf1DU0fX0MF7 | Summary | 391 | 1.8.4 | 1.8.4 |  | 391 | p | 819 | -209% | 1210
400 | 5516 | dd6fm1lW4tBXPtNV5RGW | Summary | 391 | 1.8.4.1 | 1.8.4.1 |  | 391 | p | 819 | -209% | 1210
401 | 5517 | IHfroMkwx3TZoTXYbBOK | Normal | 40 | 1.8.4.1.1 | 1.8.4.1.1 |  | 40 | q | -13 | (-32%) | 27
402 | 5518 | V0a5XEJ0jxIkhnpEDg8e | Normal | 40 | 1.8.4.1.2 | 1.8.4.1.2 |  | 40 | p | 8 | -20% | 48
403 | 5519 | D5sl3M5NpO77EU7TPYT0 | Normal | 40 | 1.8.4.1.3 | 1.8.4.1.3 |  | 40 | q | -3 | (-8%) | 37
404 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 1454 | p | 1565 | -108% | 3019
405 | 5331 | emM9tIPUc6I6BRQdDkUj | Summary | 325 | 1.9.3 | 1.9.3 |  | 325 | q | -21 | (-6%) | 304
406 | 5332 | Jas5wmBgln6JvMRLtRUk | Summary | 110 | 1.9.3.1 | 1.9.3.1 |  | 110 | p | 1 | -1% | 111
407 | 5334 | 5Bt8vyiG2PJ2FKCjQPP1 | Summary | 74 | 1.9.3.1.2 | 1.9.3.1.2 |  | 74 | p | 3 | -4% | 77
408 | 6472 | j0VQ7fJsNHb1HpOVRoJN | Normal | 7 | 1.9.3.1.2.2 | 1.9.3.1.2.2 |  | 7 | p | 1 | -14% | 8
409 | 6473 | FN1N5cBOnOQJN0lvtY6J | Normal | 5 | 1.9.3.1.2.3 | 1.9.3.1.2.3 |  | 5 | p | 1 | -20% | 6
410 | 6475 | TkBVMCiZTEhYxjcnMNRI | Normal | 8 | 1.9.3.1.2.5 | 1.9.3.1.2.5 |  | 8 | q | -2 | (-25%) | 6
411 | 6476 | HdsfOo0UbW7iVGjY7L1O | Normal | 10 | 1.9.3.1.2.6 | 1.9.3.1.2.6 |  | 10 | p | 3 | -30% | 13
412 | 6478 | ZDDqpCGw2ELQiAxZVJFo | Normal | 7 | 1.9.3.1.2.8 | 1.9.3.1.2.8 |  | 7 | q | -1 | (-14%) | 6
413 | 6479 | i51TyrBkECB0t7wKJruE | Normal | 7 | 1.9.3.1.2.9 | 1.9.3.1.2.9 |  | 7 | p | 1 | -14% | 8
414 | 5335 | fBEkx0xCtVpw1OeE4jLB | Summary | 25 | 1.9.3.1.3 | 1.9.3.1.3 |  | 25 | q | -2 | (-8%) | 23
415 | 5336 | FIhKbBOHnlTp0loBBfvV | Normal | 3 | 1.9.3.1.3.1 | 1.9.3.1.3.1 |  | 3 | p | 1 | -33% | 4
416 | 5337 | TPAbtCx4KhMQiN0iVD1F | Normal | 0 | 1.9.3.1.3.2 | 1.9.3.1.3.2 |  | 0 | p | 1 |  | 1
417 | 5340 | lQJTDBnvPE8mTPnPre3v | Normal | 10 | 1.9.3.1.3.5 | 1.9.3.1.3.5 |  | 10 | q | -2 | (-20%) | 8
418 | 5341 | nevxwfefPkBzu42CDbNd | Normal | 10 | 1.9.3.1.3.6 | 1.9.3.1.3.6 |  | 10 | q | -3 | (-30%) | 7
419 | 5342 | s0JiBiXDLP6oybWmkZ43 | Normal | 6 | 1.9.3.1.4 | 1.9.3.1.4 |  | 6 | q | -1 | (-17%) | 5
420 | 6275 | OL3lkJGtK3tkk0d4SBRn | Summary | 288 | 1.9.9 | 1.9.9 |  | 1390 | p | 659 | -47% | 2049
421 | 845 | U1v5hScHSOPPxa5ohjfI | Summary | 189 | 1.9.9.7 | 1.9.9.7 |  | 1180 | p | 17 | -1% | 1197
422 | 847 | JilJNxxBcx7QrT5PcKLM | Summary | 189 | 1.9.9.7.2 | 1.9.9.7.2 |  | 1160 | p | 17 | -1% | 1177
423 | 869 | 8QCM3LZ8SN5y0jCLtGNh | Summary | 129 | 1.9.9.7.2.7 | 1.9.9.7.2.7 |  | 129 | q | -1 | (-1%) | 128
424 | 6419 | NORPsF566zq8VZyN1UzF | Normal | 10 | 1.9.9.7.2.7.1 | 1.9.9.7.2.7.1 |  | 10 | p | 1 | -10% | 11
425 | 6420 | 043wOhyyEd8vJkuUBkFf | Normal | 40 | 1.9.9.7.2.7.2 | 1.9.9.7.2.7.2 |  | 40 | q | -3 | (-8%) | 37
426 | 6421 | JZROXyECnTBG3SBjYZJ8 | Normal | 79 | 1.9.9.7.2.7.3 | 1.9.9.7.2.7.3 |  | 79 | p | 2 | -3% | 81
427 | 6418 | W9pbV5i9WFkdVEGtW75H | Normal | 45 | 1.9.9.7.2.5 | 1.9.9.7.2.5 |  | 50 | q | -2 | (-4%) | 48
428 | 870 | m3oEXpasu7ssfpw9dqLv | Summary | 267 | 1.9.9.14 | 1.9.9.14 |  | 802 | p | 658 | -82% | 1460
429 | 4667 | gXRr1908PexMoLIDosFv | Normal | 100 | 1.9.9.14.3 | 1.9.9.14.3 |  | 100 | q | -8 | (-8%) | 92
430 | 4669 | aeClBbTsJ3qrKHWqQ1Rw | Normal | 40 | 1.9.9.14.5 | 1.9.9.14.5 |  | 40 | q | -4 | (-10%) | 36
431 | 4679 | rpzkOhA603pApmNdMeVE | Normal | 0 | 1.9.9.14.6 | 1.9.9.14.6 |  | 0 | p | 1 |  | 1
432 | 5787 | r6JEZEKCpBbNZRe1W7Ef | Normal | 91 | 1.9.9.14.2 | 1.9.9.14.2 |  | 91 | p | 22 | -24% | 113
433 | 899 | w1GWQdUx9oG06oopRYZx | Summary | 24 | 1.9.9.15 | 1.9.9.15 |  | 24 | q | -2 | (-8%) | 22
434 | 901 | HcFqHITfVdYMyzVb3S8v | Normal | 18 | 1.9.9.15.2 | 1.9.9.15.2 |  | 18 | p | 2 | -11% | 20
435 | 903 | UDGopgZ2sb1QsQEooZ9G | Normal | 8 | 1.9.9.15.4 | 1.9.9.15.4 |  | 8 | q | -1 | (-12%) | 7
436 | 905 | MxRWNVEH6ZVBPqNnA2hI | Normal | 8 | 1.9.9.15.6 | 1.9.9.15.6 |  | 8 | q | -2 | (-25%) | 6
437 | 914 | q0UeyWaeMXFoeUDjjzhX | Summary | 18 | 1.9.9.5 | 1.9.9.5 |  | 18 | p | 3 | -17% | 21
438 | 915 | jxzEE3EBeGWt1nE3uHcj | Summary | 18 | 1.9.9.5.1 | 1.9.9.5.1 |  | 18 | p | 3 | -17% | 21
439 | 916 | d4bxhxtQW3GaLrDrUlf9 | Normal | 17 | 1.9.9.5.1.1 | 1.9.9.5.1.1 |  | 17 | p | 2 | -12% | 19
440 | 4538 | aTyUglf0WPX6H8Zd17Iq | Summary | 71 | 1.9.9.16 | 1.9.9.16 |  | 71 | q | -3 | (-4%) | 68
441 | 6509 | sp3XFaPtGgzrVeC1wvvV | Normal | 10 | 1.9.9.16.3 | 1.9.9.16.3 |  | 10 | q | -3 | (-30%) | 7
442 | 6510 | dar9hgzhSUYJxC1MeoTS | Normal | 10 | 1.9.9.16.4 | 1.9.9.16.4 |  | 10 | p | 2 | -20% | 12
443 | 6513 | IG8fHoH3vjERJ6iSB3Rj | Normal | 36 | 1.9.9.16.5 | 1.9.9.16.5 |  | 36 | q | -2 | (-6%) | 34
444 | 6686 | IDiuvzfQRXyu7MCMX1jW | Normal | 5 | 1.9.9.11 | 1.9.9.11 |  | 158 | q | -1 | (-1%) | 157
445 | 7388 | subTjNOw9tjXphx2xXzW | Summary | 324 | 1.9.9.13 | 1.9.9.13 |  | 324 | p | 9 | -3% | 333
446 | 7389 | xTfJP5JFEqXIDmLDdKVZ | Summary | 43 | 1.9.9.13.1 | 1.9.9.13.1 |  | 43 | p | 7 | -16% | 50
447 | 7390 | GV26YG775A5KHHrrMIRV | Summary | 32 | 1.9.9.13.1.1 | 1.9.9.13.1.1 |  | 32 | p | 7 | -22% | 39
448 | 7392 | ylVP19AJuwY485wgDJEG | Normal | 10 | 1.9.9.13.1.1.2 | 1.9.9.13.1.1.2 |  | 10 | q | -2 | (-20%) | 8
449 | 7394 | zHoRZ9fggWfe9FGnA954 | Normal | 10 | 1.9.9.13.1.1.4 | 1.9.9.13.1.1.4 |  | 10 | q | -1 | (-10%) | 9
450 | 7396 | gQKdIVV4LZyvHUAfFFFg | Normal | 10 | 1.9.9.13.1.1.6 | 1.9.9.13.1.1.6 |  | 10 | q | -1 | (-10%) | 9
451 | 7397 | gmOEJCOmO6SQ6HMlGXfq | Summary | 12 | 1.9.9.13.1.2 | 1.9.9.13.1.2 |  | 12 | p | 8 | -67% | 20
452 | 7400 | VGtguPWpaIPmF0Ojsz8a | Summary | 176 | 1.9.9.13.2 | 1.9.9.13.2 |  | 176 | p | 4 | -2% | 180
453 | 7403 | pHZBXvaYVwug2p7gN6jp | Summary | 17 | 1.9.9.13.2.3 | 1.9.9.13.2.3 |  | 17 | q | -1 | (-6%) | 16
454 | 7405 | 5GpI6xkgfIoVOnU9egD8 | Normal | 12 | 1.9.9.13.2.3.2 | 1.9.9.13.2.3.2 |  | 12 | q | -1 | (-8%) | 11
455 | 7406 | WxzG2sAIbVYYiem4v3mk | Normal | 12 | 1.9.9.13.2.3.3 | 1.9.9.13.2.3.3 |  | 12 | q | -2 | (-17%) | 10
456 | 7408 | uKngouP2QMMQmu6HFm0I | Normal | 11 | 1.9.9.13.2.4.1 | 1.9.9.13.2.4.1 |  | 11 | q | -1 | (-9%) | 10
457 | 7409 | C7eZzAQkBbKewE4wmmOD | Normal | 11 | 1.9.9.13.2.4.2 | 1.9.9.13.2.4.2 |  | 11 | q | -1 | (-9%) | 10
458 | 7411 | OzHccTXr25Mf4pmiIMuT | Normal | 11 | 1.9.9.13.2.4.4 | 1.9.9.13.2.4.4 |  | 11 | p | 2 | -18% | 13
459 | 7412 | obz02flxb00pYjKUpMNx | Normal | 12 | 1.9.9.13.2.5 | 1.9.9.13.2.5 |  | 12 | p | 1 | -8% | 13
460 | 7413 | xazO1XwNp5eROWJmaREL | Summary | 36 | 1.9.9.13.2.6 | 1.9.9.13.2.6 |  | 36 | p | 5 | -14% | 41
461 | 7415 | RsULMViXRZoYahxlMUQ4 | Normal | 20 | 1.9.9.13.2.6.2 | 1.9.9.13.2.6.2 |  | 20 | p | 4 | -20% | 24
462 | 7417 | yrCdbpyUp4mqkbXiv5Nc | Normal | 6 | 1.9.9.13.2.6.4 | 1.9.9.13.2.6.4 |  | 6 | q | -1 | (-17%) | 5
463 | 7418 | Iw5sTi596kP8d52cBWYm | Normal | 5 | 1.9.9.13.2.6.5 | 1.9.9.13.2.6.5 |  | 5 | p | 1 | -20% | 6
464 | 7420 | ia01m1zWF4qAvVLVg5It | Summary | 54 | 1.9.9.13.2.8 | 1.9.9.13.2.8 |  | 54 | q | -2 | (-4%) | 52
465 | 7423 | hs9Gt4WgG9pENnEIaC7X | Normal | 14 | 1.9.9.13.2.8.3 | 1.9.9.13.2.8.3 |  | 14 | p | 1 | -7% | 15
466 | 7424 | WqCakGr8mHgCENNWHHjW | Normal | 5 | 1.9.9.13.2.8.4 | 1.9.9.13.2.8.4 |  | 5 | p | 1 | -20% | 6
467 | 7425 | Pv27HXd826jlfuUJmTLH | Normal | 20 | 1.9.9.13.2.8.5 | 1.9.9.13.2.8.5 |  | 20 | q | -2 | (-10%) | 18
468 | 7426 | UjcYgNHyPV73fWy2GGNA | Normal | 5 | 1.9.9.13.2.8.6 | 1.9.9.13.2.8.6 |  | 5 | p | 1 | -20% | 6
469 | 7428 | C3roUkJ3GEdxAvfnxnUE | Normal | 6 | 1.9.9.13.2.8.8 | 1.9.9.13.2.8.8 |  | 6 | p | 1 | -17% | 7
470 | 7429 | GMfJSktlv5oUXA5LFNgA | Normal | 6 | 1.9.9.13.2.8.9 | 1.9.9.13.2.8.9 |  | 6 | q | -2 | (-33%) | 4
471 | 7430 | AjX0fOJfuCWTWcoFWrZe | Summary | 11 | 1.9.9.13.2.9 | 1.9.9.13.2.9 |  | 11 | p | 2 | -18% | 13
472 | 7433 | FxBsJSw4ZNEIyIQA8bL9 | Normal | 8 | 1.9.9.13.2.9.3 | 1.9.9.13.2.9.3 |  | 8 | p | 2 | -25% | 10
473 | 7435 | nSo6tYchIu2Aw4YtE45u | Summary | 44 | 1.9.9.13.4 | 1.9.9.13.4 |  | 44 | p | 2 | -5% | 46
474 | 7436 | Y83lvWkQwfsc3dMGwfVN | Summary | 30 | 1.9.9.13.4.1 | 1.9.9.13.4.1 |  | 30 | p | 2 | -7% | 32
475 | 7437 | E8EwVgjFQaEPGP66WsCb | Summary | 30 | 1.9.9.13.4.1.1 | 1.9.9.13.4.1.1 |  | 30 | q | -5 | (-17%) | 25
476 | 7438 | y2P0mgWq1uFkM4aVxtQJ | Normal | 15 | 1.9.9.13.4.1.1.1 | 1.9.9.13.4.1.1.1 |  | 15 | q | -3 | (-20%) | 12
477 | 7440 | 3ZzL4TktDwncii0hY2dA | Normal | 10 | 1.9.9.13.4.1.1.3 | 1.9.9.13.4.1.1.3 |  | 10 | q | -2 | (-20%) | 8
478 | 7441 | IcgrxiRjEYJLwuugm8N7 | Summary | 30 | 1.9.9.13.4.1.2 | 1.9.9.13.4.1.2 |  | 30 | p | 2 | -7% | 32
479 | 7442 | B8zfbswYxyRxHa21jaE6 | Normal | 15 | 1.9.9.13.4.1.2.1 | 1.9.9.13.4.1.2.1 |  | 15 | p | 1 | -7% | 16
480 | 7443 | lvFKaF8Jtq8DkkB0s9nv | Normal | 15 | 1.9.9.13.4.1.2.2 | 1.9.9.13.4.1.2.2 |  | 15 | p | 2 | -13% | 17
481 | 7444 | 419IszMaZW6XNIQptprk | Normal | 20 | 1.9.9.13.4.1.3 | 1.9.9.13.4.1.3 |  | 20 | p | 5 | -25% | 25
482 | 7445 | oNfFp4VAwKEpoSujTbHZ | Normal | 10 | 1.9.9.13.4.1.4 | 1.9.9.13.4.1.4 |  | 10 | p | 2 | -20% | 12
483 | 7450 | F3vtt1T8lz7mQWFPgUKT | Normal | 2 | 1.9.9.13.4.3 | 1.9.9.13.4.3 |  | 2 | q | -1 | (-50%) | 1
484 | 7513 | NbiRgc4Tdvxa900kw7Xq | Normal | 8 | 1.7.10.27 | 1.7.10.27 |  | 8 | q | -1 | (-12%) | 7
485 | 7542 | E3YdLEfamF0eZCISJiqw | Normal | 10 | 1.7.10.11 | 1.7.10.11 |  | 10 | q | -1 | (-10%) | 9
486 | 6279 | p7EJXT1muDSglD2OZLFH | Summary | 274 | 1.9.7 | 1.9.7 |  | 1144 | p | 1862 | -163% | 3006
487 | 1484 | 6ARiGRg3KLswRpJLOmGD | Summary | 229 | 1.9.7.18 | 1.9.7.18 |  | 513 | p | 1465 | -286% | 1978
488 | 1485 | R0QJsNVi0JzXq4FadBdS | Normal | 20 | 1.9.7.18.4 | 1.9.7.18.4 |  | 20 | p | 2 | -10% | 22
489 | 1486 | 9VYbXOz4xuMas0igEBkB | Summary | 56 | 1.9.7.18.6 | 1.9.7.18.6 |  | 56 | p | 1 | -2% | 57
490 | 6540 | BF294XdCZHw2CEg81bOs | Normal | 19 | 1.9.7.18.6.1 | 1.9.7.18.6.1 |  | 19 | q | -1 | (-5%) | 18
491 | 6541 | X8phwYugZBkIbn0OysQW | Normal | 19 | 1.9.7.18.6.2 | 1.9.7.18.6.2 |  | 19 | p | 2 | -11% | 21
492 | 1489 | pYq4lU1lCt1U75q3gu6M | Normal | 11 | 1.9.7.18.1 | 1.9.7.18.1 |  | 229 | p | 1 | 0% | 230
493 | 1490 | hF9FI1LNvFfgTTXhqPsR | Normal | 77 | 1.9.7.18.2 | 1.9.7.18.2 |  | 77 | p | 1 | -1% | 78
494 | 4587 | 5uS9ktvplxYkrLheR3Q9 | Normal | 20 | 1.9.7.18.5 | 1.9.7.18.5 |  | 20 | p | 3 | -15% | 23
495 | 1496 | 5t2MhilpkZRDQA3VTcGS | Normal | 48 | 1.9.7.7 | 1.9.7.7 |  | 48 | p | 2 | -4% | 50
496 | 1505 | 4c3z8pWafVxAWNC1MpC9 | Normal | 106 | 1.9.7.8 | 1.9.7.8 |  | 106 | q | -3 | (-3%) | 103
497 | 1508 | SDZ1pqYbdynEzXZrWujj | Normal | 30 | 1.9.7.6 | 1.9.7.6 |  | 304 | q | -3 | (-1%) | 301
498 | 1529 | WOa3B8SPUOSM5ThLE2Jo | Summary | 69 | 1.9.7.14 | 1.9.7.14 |  | 262 | p | 10 | -4% | 272
499 | 1534 | SuchbNnj1ndABAEPQlrb | Normal | 10 | 1.9.7.14.6 | 1.9.7.14.6 |  | 10 | p | 1 | -10% | 11
500 | 1535 | vIOpwJGhGrQ4pKl5nahR | Summary | 61 | 1.9.7.15 | 1.9.7.15 |  | 417 | p | 22 | -5% | 439
501 | 1538 | 1Xm6i4dPIyAKJzF1jRtD | Normal | 45 | 1.9.7.15.3 | 1.9.7.15.3 |  | 45 | p | 2 | -4% | 47
502 | 1542 | VmFPpoMfVfLEXeRBF7Um | Normal | 9 | 1.9.7.15.8 | 1.9.7.15.8 |  | 9 | q | -1 | (-11%) | 8
503 | 1543 | P2oxmSB7jXG6Ib9VEZ89 | Normal | 9 | 1.9.7.15.9 | 1.9.7.15.9 |  | 9 | p | 2 | -22% | 11
504 | 4585 | Z4QB23UBk58Dyd3318zD | Normal | 10 | 1.9.7.15.6 | 1.9.7.15.6 |  | 10 | q | -3 | (-30%) | 7
505 | 1544 | dYtuUpkdltDWUtvWJGdC | Summary | 80 | 1.9.7.16 | 1.9.7.16 |  | 384 | q | -5 | (-1%) | 379
506 | 1549 | s8gTUDwRZFDpCO4enZqk | Normal | 15 | 1.9.7.16.6 | 1.9.7.16.6 |  | 15 | p | 302 | -2013% | 317
507 | 1550 | UoQFPyMNVa9QPyq2kgrl | Normal | 9 | 1.9.7.16.7 | 1.9.7.16.7 |  | 9 | q | -1 | (-11%) | 8
508 | 1551 | FTwSjNJQyZH6RsSSqWG9 | Summary | 78 | 1.9.7.19 | 1.9.7.19 |  | 813 | p | 1 | 0% | 814
509 | 1561 | 8BMHpFsmSFY1BvBQKfdD | Normal | 10 | 1.9.7.19.11 | 1.9.7.19.11 |  | 10 | p | 2 | -20% | 12
510 | 4574 | z7UYZlhr663oN8lfFWmH | Summary | 29 | 1.9.7.11 | 1.9.7.11 |  | 396 | q | -19 | (-5%) | 377
511 | 4578 | kBeLaux8MTugqoi5KPvZ | Summary | 74 | 1.9.7.13 | 1.9.7.13 |  | 74 | p | 14 | -19% | 88
512 | 4581 | FxGRGf2kppDMdfFrZkS4 | Normal | 36 | 1.9.7.12 | 1.9.7.12 |  | 42 | q | -7 | (-17%) | 35
513 | 4588 | L1kgBhMEjlIJ4HNHh1TQ | Summary | 141 | 1.9.7.20 | 1.9.7.20 |  | 141 | q | -3 | (-2%) | 138
514 | 1566 | KFj0hxHWvExDoqTqgDeg | Normal | 118 | 1.9.7.20.1 | 1.9.7.20.1 |  | 118 | q | -2 | (-2%) | 116
515 | 1567 | GV5or0ucuouXZiqAkH0N | Normal | 10 | 1.9.7.20.2 | 1.9.7.20.2 |  | 10 | p | 2 | -20% | 12
516 | 1568 | JI4xSRBKV4FYnRXdw7Wz | Normal | 9 | 1.9.7.20.3 | 1.9.7.20.3 |  | 9 | q | -1 | (-11%) | 8
517 | 1569 | DVuFJt4FGQSIgeZkA41d | Normal | 4 | 1.9.7.20.4 | 1.9.7.20.4 |  | 4 | q | -1 | (-25%) | 3
518 | 6439 | JoFd6fDKN7NWznuQx6gK | Normal | 56 | 1.9.7.10 | 1.9.7.10 |  | 56 | q | -4 | (-7%) | 52
519 | 7323 | p8rF5Tk8321hO30p5zSy | Summary | 79 | 1.7.8.18 | 1.7.8.18 |  | 105 | p | 9 | -9% | 114
520 | 7455 | hQlezwT73UjuGPZkyuVr | Normal | 9 | 1.7.8.18.2 | 1.7.8.18.2 |  | 9 | q | -1 | (-11%) | 8
521 | 7456 | 3cfjdZ38xGBNf8roD7He | Normal | 9 | 1.7.8.18.3 | 1.7.8.18.3 |  | 9 | q | -1 | (-11%) | 8
522 | 7458 | cMhUMuxC0sax27543As7 | Normal | 24 | 1.7.8.18.5 | 1.7.8.18.5 |  | 24 | p | 2 | -8% | 26
523 | 7459 | xf7OMyoiQ38QdcweBYiq | Normal | 20 | 1.7.8.18.6 | 1.7.8.18.6 |  | 20 | p | 4 | -20% | 24
524 | 7382 | GJk3wpkfagyrb21gVciV | Summary | 288 | 1.9.7.22 | 1.9.7.22 |  | 288 | p | 1051 | -365% | 1339
525 | 7384 | xn1TRUhUfNd3ygHlAMk1 | Normal | 16 | 1.9.7.22.2 | 1.9.7.22.2 |  | 16 | q | -4 | (-25%) | 12
526 | 6285 | 0inPdnysTnfuJeCJJEwo | Summary | 131 | 1.9.1 | 1.9.1 |  | 566 | p | 15 | -3% | 581
527 | 4593 | XK8YU5H8vMrR7jBOr6fS | Normal | 99 | 1.9.1.1 | 1.9.1.1 |  | 100 | q | -8 | (-8%) | 92
528 | 4605 | jXRAJqcdCYbTQqzq5oVG | Normal | 14 | 1.7.3.2 | 1.7.3.2 |  | 235 | p | 1 | 0% | 236
529 | 4607 | 9Rf8xh1sYqA0mX8AIEgx | Summary | 52 | 1.7.3.5 | 1.7.3.5 |  | 52 | q | -4 | (-8%) | 48
530 | 4608 | tlJeJHdE7OwhwWyVvZ8P | Normal | 5 | 1.7.3.5.1 | 1.7.3.5.1 |  | 5 | q | -1 | (-20%) | 4
531 | 4613 | z0DGpsje53b33zXA5t1P | Normal | 20 | 1.7.3.5.6 | 1.7.3.5.6 |  | 20 | q | -3 | (-15%) | 17
532 | 4615 | Io6EVgFdyRjG7CB2g0Wy | Summary | 98 | 1.7.3.4 | 1.7.3.4 |  | 351 | p | 25 | -7% | 376
533 | 4618 | mRqsjEijsp2iSp4l7aof | Normal | 5 | 1.7.3.4.3 | 1.7.3.4.3 |  | 5 | p | 2 | -40% | 7
534 | 4619 | 8asUr7UOO8nabPagFvw9 | Normal | 40 | 1.7.3.4.4 | 1.7.3.4.4 |  | 40 | q | -2 | (-5%) | 38
535 | 4620 | UWR5akRFo4eKiDyQVnYr | Normal | 23 | 1.7.3.4.5 | 1.7.3.4.5 |  | 23 | q | -6 | (-26%) | 17
536 | 4622 | Bm2ajkWBwO6Cvc6RoPdK | Normal | 5 | 1.7.3.4.7 | 1.7.3.4.7 |  | 5 | p | 2 | -40% | 7
537 | 4623 | sDTQ4X48dvup817zb0Do | Normal | 20 | 1.7.3.4.8 | 1.7.3.4.8 |  | 20 | p | 1 | -5% | 21
538 | 4624 | 3CGv61AS00FFpM5LrRat | Normal | 20 | 1.7.3.4.9 | 1.7.3.4.9 |  | 20 | q | -1 | (-5%) | 19
539 | 4626 | 92oajspBBxTpnlNQO91I | Summary | 90 | 1.7.3.6 | 1.7.3.6 |  | 425 | p | 15 | -4% | 440
540 | 4630 | pjdWghPSPBEOfTIZFZhV | Normal | 5 | 1.7.3.6.4 | 1.7.3.6.4 |  | 144 | q | -1 | (-1%) | 143
541 | 4633 | STHfhyBuM5qFiEzHSgws | Normal | 19 | 1.7.3.6.7 | 1.7.3.6.7 |  | 19 | q | -3 | (-16%) | 16
542 | 4637 | ohQUE8EwZLGEmkE5FTpA | Summary | 8 | 1.7.3.7 | 1.7.3.7 |  | 318 | p | 19 | -6% | 337
543 | 6608 | ifCvUSq9UjUAw7FKKXTR | Normal | 14 | 1.7.3.7.3 | 1.7.3.7.3 |  | 242 | q | -1 | 0% | 241
544 | 7259 | Dcjo2uskRMoBajU90pQq | Normal | 60 | 1.7.1.4 | 1.7.1.4 |  | 60 | p | 2 | -3% | 62
545 | 6294 | Jtjxi70STISSeVqV8OJy | Summary | 163 | 1.9.6 | 1.9.6 |  | 931 | p | 583 | -63% | 1514
546 | 3745 | D0mR64Wbk6oru5hoL4DG | Summary | 62 | 1.7.1.2 | 1.7.1.2 |  | 423 | p | 21 | -5% | 444
547 | 3773 | jfB1zdAbu7JeWEH3ijwy | Summary | 73 | 1.7.1.2.6 | 1.7.1.2.6 |  | 240 | p | 21 | -9% | 261
548 | 3776 | GHLE38QRMYNBeSYAGB18 | Normal | 32 | 1.7.1.2.6.3 | 1.7.1.2.6.3 |  | 37 | p | 2 | -5% | 39
549 | 3777 | YuGKQIQDxLVYRZzgUQjw | Normal | 9 | 1.7.1.2.6.4 | 1.7.1.2.6.4 |  | 9 | q | -1 | (-11%) | 8
550 | 3783 | FcDlmkxQNUOM36qP0M0H | Summary | 58 | 1.7.1.3 | 1.7.1.3 |  | 461 | p | 22 | -5% | 483
551 | 3790 | Om0YwWoKF5usOVLnDccR | Summary | 13 | 1.7.1.3.4 | 1.7.1.3.4 |  | 396 | p | 22 | -6% | 418
552 | 6977 | F0juzsyqTnJm6sTJe4ff | Normal | 14 | 1.7.1.3.4.7 | 1.7.1.3.4.7 |  | 163 | p | 2 | -1% | 165
553 | 6138 | EvFVoaLHb5OgszmS4Hdy | Summary | 44 | 1.7.1.3.9 | 1.7.1.3.9 |  | 44 | p | 1 | -2% | 45
554 | 6139 | VECMPYMi2oWf71g3eai1 | Normal | 29 | 1.7.1.3.9.1 | 1.7.1.3.9.1 |  | 29 | q | -2 | (-7%) | 27
555 | 6140 | mO0F0FFUdRVKYlb84WcT | Normal | 15 | 1.7.1.3.9.2 | 1.7.1.3.9.2 |  | 15 | p | 3 | -20% | 18
556 | 6978 | z4sj2SQJw3pdZet8Am0U | Normal | 9 | 1.7.1.3.5 | 1.7.1.3.5 |  | 9 | p | 2 | -22% | 11
557 | 6983 | PcmQnh6ym2R5IAKzFgwu | Summary | 141 | 1.7.1.3.7 | 1.7.1.3.7 |  | 159 | p | 21 | -13% | 180
558 | 6990 | K8cvVDryBsyahUujiNmr | Summary | 22 | 1.7.1.3.8 | 1.7.1.3.8 |  | 22 | p | 41 | -186% | 63
559 | 6982 | E06yVWmTg8kRS6Gv9kOV | Summary | 6 | 1.7.1.3.8.3 | 1.7.1.3.8.3 |  | 6 | p | 3 | -50% | 9
560 | 6991 | RAhO7UtYgqwLkhTknwrO | Normal | 6 | 1.7.1.3.8.1 | 1.7.1.3.8.1 |  | 6 | q | -1 | (-17%) | 5
561 | 3803 | vx1oFVBFPqydBxZJ7V4g | Summary | 112 | 1.7.1.5 | 1.7.1.5 |  | 445 | p | 35 | -8% | 480
562 | 3808 | mNtnU9AYiACOeBrTPE9f | Summary | 29 | 1.7.1.5.3 | 1.7.1.5.3 |  | 212 | p | 17 | -8% | 229
563 | 3809 | ukioB4iHiwrfEXpseTiK | Normal | 15 | 1.7.1.5.3.1 | 1.7.1.5.3.1 |  | 198 | p | 1 | -1% | 199
564 | 3810 | CJxWy7PnZPcI4EPHEeme | Normal | 9 | 1.7.1.5.3.2 | 1.7.1.5.3.2 |  | 9 | q | -2 | (-22%) | 7
565 | 3811 | wGtgxCT3lCK6u2EOL8xN | Normal | 5 | 1.7.1.5.3.3 | 1.7.1.5.3.3 |  | 5 | q | -2 | (-40%) | 3
566 | 3813 | sYeTNUsya13QYMbMJg21 | Normal | 25 | 1.7.1.5.7 | 1.7.1.5.7 |  | 25 | p | 1 | -4% | 26
567 | 3816 | 6MWmVgC0FSCF3lMoTGjJ | Summary | 40 | 1.7.1.5.10 | 1.7.1.5.10 |  | 40 | p | 14 | -35% | 54
568 | 3819 | FSVjbKFfUmqE2fpbGGPv | Normal | 3 | 1.7.1.5.10.3 | 1.7.1.5.10.3 |  | 3 | q | -1 | (-33%) | 2
569 | 3820 | FhKtXXrOwkDfPm4RFzRW | Normal | 10 | 1.7.1.5.10.4 | 1.7.1.5.10.4 |  | 10 | p | 1 | -10% | 11
570 | 3821 | cHjYAw102skS4vR6DXqX | Normal | 20 | 1.7.1.5.10.5 | 1.7.1.5.10.5 |  | 20 | p | 4 | -20% | 24
571 | 6147 | BUcWclFVChflBnUDJ9UM | Normal | 40 | 1.7.1.5.4 | 1.7.1.5.4 |  | 87 | p | 17 | -20% | 104
572 | 6148 | V03eKqopjAXoUvRodLvQ | Normal | 13 | 1.7.1.5.6 | 1.7.1.5.6 |  | 27 | p | 1 | -4% | 28
573 | 4078 | ybbKeBChK3D60QzH8ONZ | Normal | 76 | 1.9.6.5 | 1.9.6.5 |  | 177 | q | -3 | (-2%) | 174
574 | 4129 | G6dPcJRrq5zqLYx4Vr0R | Summary | 475 | 1.9.6.10 | 1.9.6.10 |  | 706 | p | 657 | -93% | 1363
575 | 4131 | 3WZTLr4e3INGux4LMgj0 | Summary | 146 | 1.9.6.10.2 | 1.9.6.10.2 |  | 146 | q | -42 | (-29%) | 104
576 | 5861 | adMwYb1cwVT0ja23ZKPV | Normal | 10 | 1.9.6.10.2.5 | 1.9.6.10.2.5 |  | 10 | q | -1 | (-10%) | 9
577 | 5862 | rkVKH7eSVnkv5Rz0hIbo | Normal | 25 | 1.9.6.10.2.6 | 1.9.6.10.2.6 |  | 25 | p | 3 | -12% | 28
578 | 5863 | axx1H8vuWtNbWz6aJYpW | Normal | 20 | 1.9.6.10.2.7 | 1.9.6.10.2.7 |  | 20 | p | 3 | -15% | 23
579 | 5864 | ZuXAUp7kzm7PDgs0Clm4 | Normal | 20 | 1.9.6.10.2.8 | 1.9.6.10.2.8 |  | 20 | q | -3 | (-15%) | 17
580 | 5867 | 6vMprMC9ZRYTg9c055cw | Normal | 3 | 1.9.6.10.2.11 | 1.9.6.10.2.11 |  | 3 | q | -1 | (-33%) | 2
581 | 5870 | rLlKwDBGmyMe6lxLtymf | Summary | 59 | 1.9.6.10.3 | 1.9.6.10.3 |  | 59 | p | 6 | -10% | 65
582 | 5871 | owx5unCKcaLauhH4kWyj | Normal | 5 | 1.9.6.10.3.1 | 1.9.6.10.3.1 |  | 5 | p | 1 | -20% | 6
583 | 5872 | qImIYF1Y50rp0FNnsaoS | Normal | 10 | 1.9.6.10.3.2 | 1.9.6.10.3.2 |  | 10 | p | 2 | -20% | 12
584 | 5873 | FfFQqcMQ2fY5X0GvK0Xd | Normal | 20 | 1.9.6.10.3.3 | 1.9.6.10.3.3 |  | 20 | p | 5 | -25% | 25
585 | 6624 | sVpbcWAee9M5eeft5sdO | Normal | 15 | 1.9.6.10.3.4 | 1.9.6.10.3.4 |  | 15 | q | -2 | (-13%) | 13
586 | 6625 | it5qGsWYKIf8fEL1a2TB | Normal | 5 | 1.9.6.10.3.5 | 1.9.6.10.3.5 |  | 5 | p | 1 | -20% | 6
587 | 5877 | 8uIO0L3CbsjXfYIL70ur | Summary | 162 | 1.9.6.10.4 | 1.9.6.10.4 |  | 162 | p | 56 | -35% | 218
588 | 5878 | eKJmpIIS7eePXp789pq5 | Summary | 60 | 1.9.6.10.4.1 | 1.9.6.10.4.1 |  | 60 | p | 1 | -2% | 61
589 | 5880 | z8rht75g90pc62Jd1j8e | Normal | 15 | 1.9.6.10.4.1.1.1 | 1.9.6.10.4.1.1.1 |  | 15 | q | -2 | (-13%) | 13
590 | 5881 | ZPPJV7wrbqyTumtl84NX | Normal | 15 | 1.9.6.10.4.1.1.2 | 1.9.6.10.4.1.1.2 |  | 15 | p | 1 | -7% | 16
591 | 5882 | PdfqDNDAaUS1Z9tfvPSB | Normal | 15 | 1.9.6.10.4.1.2 | 1.9.6.10.4.1.2 |  | 15 | q | -1 | (-7%) | 14
592 | 5883 | 3J3dFKPf8v7HKW1lSal4 | Normal | 15 | 1.9.6.10.4.1.3 | 1.9.6.10.4.1.3 |  | 15 | p | 2 | -13% | 17
593 | 5884 | J3ZDJxR9DKKi4JquRb3Q | Summary | 20 | 1.9.6.10.4.2 | 1.9.6.10.4.2 |  | 20 | p | 2 | -10% | 22
594 | 5887 | xjL6okqGZuFc1ChaUzA0 | Normal | 5 | 1.9.6.10.4.2.3 | 1.9.6.10.4.2.3 |  | 5 | p | 1 | -20% | 6
595 | 4134 | 86JmjjOtZxj7XQRp3CQF | Summary | 466 | 1.9.6.11 | 1.9.6.11 |  | 760 | p | 458 | -60% | 1218
596 | 4135 | 0voiyAtBe9AzaXfs8cVF | Summary | 322 | 1.9.6.11.1 | 1.9.6.11.1 |  | 712 | p | 457 | -64% | 1169
597 | 4138 | 75WgU7H7MCC8DDgOcnsD | Normal | 30 | 1.9.6.11.1.3 | 1.9.6.11.1.3 |  | 30 | q | -2 | (-7%) | 28
598 | 4139 | 9SKpfzivi43NDDuHUq0B | Normal | 5 | 1.9.6.11.1.4 | 1.9.6.11.1.4 |  | 5 | q | -1 | (-20%) | 4
599 | 4140 | Lk7gef35zB3WaxM8Xyxe | Summary | 48 | 1.9.6.11.2 | 1.9.6.11.2 |  | 48 | p | 1 | -2% | 49
600 | 4141 | HGo5Ep3pqhcsiM5K4QjA | Summary | 23 | 1.9.6.11.2.1 | 1.9.6.11.2.1 |  | 23 | p | 2 | -9% | 25
601 | 4142 | VTqJrDLpWuaSlvRQajcM | Normal | 12 | 1.9.6.11.2.1.1 | 1.9.6.11.2.1.1 |  | 12 | p | 1 | -8% | 13
602 | 4143 | UwGhtpl5Mnq9WQrcrXRR | Normal | 11 | 1.9.6.11.2.1.2 | 1.9.6.11.2.1.2 |  | 11 | p | 1 | -9% | 12
603 | 4144 | zaFQ6K5wegGvKt6DGuoz | Summary | 25 | 1.9.6.11.2.2 | 1.9.6.11.2.2 |  | 25 | q | -1 | (-4%) | 24
604 | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Normal | 10 | 1.9.6.11.2.2.1 | 1.9.6.11.2.2.1 |  | 10 | q | -1 | (-10%) | 9
605 | 4146 | rTeXGnIwGPt6ES3ynSHq | Normal | 5 | 1.9.6.11.2.2.2 | 1.9.6.11.2.2.2 |  | 5 | q | -1 | (-20%) | 4
606 | 4147 | hQaW5HIstT5bbsPEBxyQ | Normal | 10 | 1.9.6.11.2.2.3 | 1.9.6.11.2.2.3 |  | 10 | p | 1 | -10% | 11
607 | 5753 | ZptYdARXANY2IOcoHhB1 | Summary | 78 | 1.9.6.1 | 1.9.6.1 |  | 499 | p | 629 | -126% | 1128
608 | 5999 | hTF24jclc5ogfsrVWXZd | Normal | 40 | 1.9.6.1.7.1 | 1.9.6.1.7.1 |  | 40 | p | 1 | -2% | 41
609 | 6004 | xOhJcEwgSz1TAvNHU4tB | Normal | 40 | 1.9.6.1.8.1 | 1.9.6.1.8.1 |  | 40 | q | -12 | (-30%) | 28
610 | 6008 | Ph5VFx7Ghit4AwZEFBXT | Summary | 50 | 1.9.6.1.6 | 1.9.6.1.6 |  | 50 | q | -1 | (-2%) | 49
611 | 6009 | NVgukc0KZBShUa0wIlyx | Normal | 30 | 1.9.6.1.6.1 | 1.9.6.1.6.1 |  | 30 | p | 2 | -7% | 32
612 | 6010 | tIYqVtlT4yOF2YQ2FRYY | Normal | 10 | 1.9.6.1.6.2 | 1.9.6.1.6.2 |  | 10 | q | -1 | (-10%) | 9
613 | 6012 | Z1jpWQx4GyFcVoEVg0i0 | Normal | 5 | 1.9.6.1.6.4 | 1.9.6.1.6.4 |  | 5 | q | -1 | (-20%) | 4
614 | 6013 | y2dxMv99iLhGOXikZGuK | Summary | 34 | 1.9.6.1.5 | 1.9.6.1.5 |  | 34 | q | -2 | (-6%) | 32
615 | 6014 | hYHiAVYfHXdDTdWEk9J8 | Normal | 15 | 1.9.6.1.5.1 | 1.9.6.1.5.1 |  | 15 | q | -1 | (-7%) | 14
616 | 6016 | gwhB80Lv7eu4PoYwev8o | Normal | 5 | 1.9.6.1.5.3 | 1.9.6.1.5.3 |  | 5 | q | -1 | (-20%) | 4
617 | 6957 | ar01N24L63iczVEh1mVo | Summary | 24 | 1.9.6.1.4 | 1.9.6.1.4 |  | 24 | q | -2 | (-8%) | 22
618 | 6958 | 6Ul4V6iAcnpVqewOp14Y | Normal | 4 | 1.9.6.1.4.1 | 1.9.6.1.4.1 |  | 4 | q | -1 | (-25%) | 3
619 | 6959 | w9Vvv79ftt4PUqInNFyD | Normal | 5 | 1.9.6.1.4.2 | 1.9.6.1.4.2 |  | 5 | q | -1 | (-20%) | 4
620 | 6961 | NOksVV7sTymsgwMrnh6x | Normal | 10 | 1.9.6.1.4.4 | 1.9.6.1.4.4 |  | 10 | q | -1 | (-10%) | 9
621 | 5762 | BY50RWHTB6QfyvgvJksd | Summary | 36 | 1.9.6.9 | 1.9.6.9 |  | 420 | p | 20 | -5% | 440
622 | 6424 | xU9ngPKik2IYPonksYTK | Summary | 24 | 1.7.1.8 | 1.7.1.8 |  | 71 | q | -69 | (-97%) | 2
623 | 6296 | SlR21lje1Tex9DLMlAM1 | Summary | 222 | 1.9.8 | 1.9.8 |  | 1198 | p | 659 | -55% | 1857
624 | 4192 | vUDAXlHZqbmK6WAsX9hH | Summary | 139 | 1.9.8.1 | 1.9.8.1 |  | 940 | q | -12 | (-1%) | 928
625 | 4196 | 2ZwOzHGH45ywtPvfASSG | Normal | 5 | 1.9.8.1.5 | 1.9.8.1.5 |  | 5 | p | 1 | -20% | 6
626 | 4197 | 4xVk2zrTd9sJnt9BJFir | Summary | 36 | 1.9.8.1.6 | 1.9.8.1.6 |  | 253 | q | -25 | (-10%) | 228
627 | 4198 | k6X8NWhjfeQOPZdDpmna | Normal | 20 | 1.9.8.1.9 | 1.9.8.1.9 |  | 295 | p | 1 | 0% | 296
628 | 5985 | AUKn3E7aViOsULw8HdKV | Normal | 131 | 1.9.8.1.12 | 1.9.8.1.12 |  | 131 | q | -34 | (-26%) | 97
629 | 4222 | uotgqiCu1xVBvHdpBC3E | Summary | 97 | 1.9.8.2 | 1.9.8.2 |  | 564 | q | -8 | (-1%) | 556
630 | 4235 | QiaATNQSPId7svzcuO8r | Normal | 91 | 1.9.8.2.7 | 1.9.8.2.7 |  | 91 | q | -30 | (-33%) | 61
631 | 4238 | ReJqSs3gutB053iVY5c7 | Summary | 76 | 1.9.8.4 | 1.9.8.4 |  | 548 | p | 29 | -5% | 577
632 | 4242 | RIVyyga7UReDeuixs5m9 | Normal | 66 | 1.9.8.4.4 | 1.9.8.4.4 |  | 346 | p | 10 | -3% | 356
633 | 4246 | ANAzXnUTz1PCb3xsov4Y | Normal | 10 | 1.9.8.4.7 | 1.9.8.4.7 |  | 10 | q | -1 | (-10%) | 9
634 | 4256 | G2pYfP7dsnHVTgqQD6mD | Summary | 82 | 1.9.8.10 | 1.9.8.10 |  | 82 | p | 3 | -4% | 85
635 | 4258 | GzQkXlTiYJMdE6nBDVeb | Normal | 6 | 1.9.8.10.1 | 1.9.8.10.1 |  | 6 | q | -1 | (-17%) | 5
636 | 6090 | LkexiRQNUDyJAwm8EPYV | Normal | 32 | 1.9.8.10.7 | 1.9.8.10.7 |  | 32 | p | 4 | -12% | 36
637 | 6430 | IYyY3jK4t9QuDyuxqyQ5 | Normal | 15 | 1.9.8.10.2 | 1.9.8.10.2 |  | 15 | q | -2 | (-13%) | 13
638 | 6431 | mXx66gQ5BZWpD3idmZgM | Normal | 10 | 1.9.8.10.3 | 1.9.8.10.3 |  | 10 | p | 2 | -20% | 12
639 | 6432 | vMoeJo3Rc30lMwFim6rn | Normal | 10 | 1.9.8.10.4 | 1.9.8.10.4 |  | 10 | p | 1 | -10% | 11
640 | 6314 | PaZTrKFuMaJQzXHDclW5 | Summary | 34 | 1.9.2 | 1.9.2 |  | 467 | p | 19 | -4% | 486
641 | 5666 | lc2LPCzbTjVw9vZ8eS89 | Summary | 23 | 1.9.2.2 | 1.9.2.2 |  | 395 | p | 18 | -5% | 413
642 | 5667 | chBvra0KGhqU3lfHBAI4 | Summary | 23 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 395 | p | 18 | -5% | 413
643 | 5669 | bBSx7g3AuM8uxZcIYlIi | Normal | 20 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 108 | p | 18 | -17% | 126
644 | 5672 | 2GDxhVAL0LbO4lfSMjXo | Summary | 47 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 467 | p | 19 | -4% | 486
645 | 5690 | jLB7gq1wR8egZrMIoAc7 | Summary | 24 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 24 | q | -2 | (-8%) | 22
646 | 5691 | glUuWw43f2R9t2hl6VHO | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 10 | q | -3 | (-30%) | 7
647 | 5693 | VdKRFLdSc60knizSqFXc | Normal | 14 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 14 | p | 1 | -7% | 15
648 | 5694 | Gb0taOZcQ8l0cdHliY6j | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 10 | p | 2 | -20% | 12
649 | 5697 | 4nIBzBv3LSP60HeOLv0f | Normal | 5 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 5 | p | 1 | -20% | 6
650 | 6315 | 2iW64uJmzViIcLEo0dMn | Summary | 181 | 1.9.5 | 1.9.5 |  | 1248 | p | 661 | -53% | 1909
651 | 5532 | NHN4dwEEPEqCDqA4Rwlr | Summary | 74 | 1.9.5.1 | 1.9.5.1 |  | 332 | p | 39 | -12% | 371
652 | 5535 | XVk7S0ldLHQUWflKhMBn | Normal | 11 | 1.9.5.1.2 | 1.9.5.1.2 |  | 66 | q | -2 | (-3%) | 64
653 | 5536 | cYU0DBZylLxVRoLEp7Bc | Normal | 40 | 1.9.5.1.4 | 1.9.5.1.4 |  | 40 | p | 14 | -35% | 54
654 | 5537 | 9xVQhmyTVkChMoMOy91g | Summary | 193 | 1.9.5.2 | 1.9.5.2 |  | 551 | p | 663 | -120% | 1214
655 | 5539 | kRsO3PSMDsMxji3dmdNc | Normal | 5 | 1.9.5.2.2 | 1.9.5.2.2 |  | 375 | p | 623 | -166% | 998
656 | 5540 | GKx3XnA1BSbhTsgdKbqP | Normal | 14 | 1.9.5.2.8 | 1.9.5.2.8 |  | 116 | p | 4 | -3% | 120
657 | 5542 | 4ivItsonCrTGke19i41Z | Normal | 15 | 1.9.5.2.6 | 1.9.5.2.6 |  | 154 | p | 1 | -1% | 155
658 | 5543 | XaHBDo6QUBfyTg5ESk7j | Normal | 15 | 1.9.5.2.9 | 1.9.5.2.9 |  | 153 | p | 5 | -3% | 158
659 | 5544 | cIc3ARzcdrbXv6maHllr | Summary | 129 | 1.9.5.2.13 | 1.9.5.2.13 |  | 129 | p | 636 | -493% | 765
660 | 5545 | 7UVU8IboY6NG7sqZCrUC | Normal | 7 | 1.9.5.2.13.2 | 1.9.5.2.13.2 |  | 7 | q | -1 | (-14%) | 6
661 | 5546 | Shs5wuYOFSkTF1YslX8w | Normal | 6 | 1.9.5.2.13.5 | 1.9.5.2.13.5 |  | 6 | p | 1 | -17% | 7
662 | 5548 | Zfzda0CfmpiN8ZL93G3t | Normal | 5 | 1.9.5.2.13.9 | 1.9.5.2.13.9 |  | 5 | p | 1 | -20% | 6
663 | 5556 | fOMVaiOa0jnHOJyDUdVQ | Normal | 25 | 1.9.5.2.13.11 | 1.9.5.2.13.11 |  | 25 | p | 1 | -4% | 26
664 | 7000 | yP1oDcnUQTy3g68ZLgu0 | Normal | 8 | 1.9.5.2.13.1 | 1.9.5.2.13.1 |  | 8 | q | -2 | (-25%) | 6
665 | 5557 | U376LwOjKfNZoVLUlmMD | Summary | 113 | 1.9.5.2.12 | 1.9.5.2.12 |  | 113 | p | 636 | -563% | 749
666 | 5558 | RXAxJx3BHWNVdWFPfZ2a | Normal | 13 | 1.9.5.2.12.2 | 1.9.5.2.12.2 |  | 13 | p | 1 | -8% | 14
667 | 5561 | Vb2zzMF18WNANxlCzGiz | Normal | 5 | 1.9.5.2.12.9 | 1.9.5.2.12.9 |  | 5 | q | -1 | (-20%) | 4
668 | 5569 | 35aiC9HLOSrIl2OBwDvd | Normal | 25 | 1.9.5.2.12.11 | 1.9.5.2.12.11 |  | 25 | p | 3 | -12% | 28
669 | 5734 | iq9bjqBZvH9Bj6912271 | Normal | 6 | 1.9.5.2.12.3 | 1.9.5.2.12.3 |  | 6 | p | 1 | -17% | 7
670 | 5737 | iDzIA8f8DQgg2wVNkaUu | Normal | 7 | 1.9.5.2.12.7 | 1.9.5.2.12.7 |  | 7 | p | 1 | -14% | 8
671 | 7001 | WpRQh8HvPfyDha8FH5FR | Normal | 9 | 1.9.5.2.12.1 | 1.9.5.2.12.1 |  | 9 | p | 1 | -11% | 10
672 | 5570 | MuDwSgsBJjDxwFkSMWYJ | Summary | 116 | 1.9.5.2.11 | 1.9.5.2.11 |  | 174 | p | 645 | -371% | 819
673 | 5571 | lfRAbO0c5jl7NaC6s7pm | Normal | 21 | 1.9.5.2.11.2 | 1.9.5.2.11.2 |  | 21 | p | 1 | -5% | 22
674 | 5572 | jk3Vm36iIGViuk9dpLfQ | Normal | 8 | 1.9.5.2.11.5 | 1.9.5.2.11.5 |  | 8 | q | -3 | (-38%) | 5
675 | 5574 | 3iKE3riinMPRUpVpTfwx | Normal | 5 | 1.9.5.2.11.9 | 1.9.5.2.11.9 |  | 5 | p | 1 | -20% | 6
676 | 5582 | 6tLu8emqwotxTkeBbEpy | Normal | 26 | 1.9.5.2.11.11 | 1.9.5.2.11.11 |  | 26 | q | -5 | (-19%) | 21
677 | 5583 | gkFBoXdv1oJb2jtBcO5M | Summary | 147 | 1.9.5.2.14 | 1.9.5.2.14 |  | 147 | p | 643 | -437% | 790
678 | 5587 | OXOUsYDejGVlgqn4Z1vl | Normal | 5 | 1.9.5.2.14.9 | 1.9.5.2.14.9 |  | 5 | p | 1 | -20% | 6
679 | 5595 | REFTk0AP9RBTibJWVhuH | Normal | 26 | 1.9.5.2.14.11 | 1.9.5.2.14.11 |  | 26 | p | 5 | -19% | 31
680 | 5742 | 88bEv4EMiOL2y8w1ttIM | Normal | 4 | 1.9.5.2.14.3 | 1.9.5.2.14.3 |  | 4 | p | 1 | -25% | 5
681 | 5744 | cSBfnbrbVLLFYTMEfBKA | Normal | 6 | 1.9.5.2.14.6 | 1.9.5.2.14.6 |  | 6 | p | 1 | -17% | 7
682 | 5745 | ZY99Y6JX4jBylnfeedvo | Normal | 6 | 1.9.5.2.14.7 | 1.9.5.2.14.7 |  | 6 | q | -1 | (-17%) | 5
683 | 6446 | XvbStahAymwCoqNIbMJG | Summary | 32 | 1.9.5.2.4 | 1.9.5.2.4 |  | 32 | q | -2 | (-6%) | 30
684 | 6532 | 15e7xcLR1b1jSikaz0S2 | Normal | 32 | 1.9.5.2.4.2 | 1.9.5.2.4.2 |  | 32 | q | -3 | (-9%) | 29
685 | 6533 | b0mutjzKj8FRw4zkbb8K | Normal | 32 | 1.9.5.2.4.1 | 1.9.5.2.4.1 |  | 32 | q | -2 | (-6%) | 30
686 | 6534 | 8Gl2bk4Fxxo2fsClDJqG | Normal | 32 | 1.9.5.2.4.3 | 1.9.5.2.4.3 |  | 32 | q | -4 | (-12%) | 28
687 | 6535 | dWze9AnK8NrEMD9LOEyU | Normal | 32 | 1.9.5.2.4.4 | 1.9.5.2.4.4 |  | 32 | q | -4 | (-12%) | 28
688 | 6528 | LROLnQke0gWnMONa67YB | Summary | 50 | 1.9.5.2.5 | 1.9.5.2.5 |  | 119 | p | 21 | -18% | 140
689 | 6531 | iX155TL3hNg9Ca4Bsb4A | Normal | 35 | 1.9.5.2.5.2 | 1.9.5.2.5.2 |  | 64 | p | 1 | -2% | 65
690 | 6955 | CPACk87DS0kpO7pXcdwS | Normal | 10 | 1.9.5.2.10 | 1.9.5.2.10 |  | 10 | p | 1 | -10% | 11
691 | 6997 | MBGoTUikAECGvIHYk1uV | Normal | 24 | 1.9.5.2.3 | 1.9.5.2.3 |  | 49 | q | -1 | (-2%) | 48
692 | 5596 | upn4QoZvaKBmBMoyhnq5 | Summary | 90 | 1.9.5.3 | 1.9.5.3 |  | 90 | p | 7 | -8% | 97
693 | 5597 | zKJsJYNcPRFZ7wBjvprv | Normal | 18 | 1.9.5.3.1 | 1.9.5.3.1 |  | 18 | q | -1 | (-6%) | 17
694 | 5598 | zvvzNQqIPXzcVRwy0N44 | Summary | 52 | 1.9.5.3.2 | 1.9.5.3.2 |  | 52 | p | 6 | -12% | 58
695 | 5599 | T0Oh47cWIVU9y2MKPB0U | Normal | 12 | 1.9.5.3.2.1 | 1.9.5.3.2.1 |  | 12 | p | 1 | -8% | 13
696 | 5600 | oTkX6bjokLXQ590hdeFy | Normal | 12 | 1.9.5.3.2.2 | 1.9.5.3.2.2 |  | 12 | p | 4 | -33% | 16
697 | 5601 | xa7cRxeKgQxZnuHNAYMQ | Normal | 12 | 1.9.5.3.2.3 | 1.9.5.3.2.3 |  | 12 | q | -3 | (-25%) | 9
698 | 5602 | QlxDegibloFbHrPNJwyW | Normal | 12 | 1.9.5.3.2.4 | 1.9.5.3.2.4 |  | 12 | p | 2 | -17% | 14
699 | 6189 | OaskfHPb0rGXxqxmUlvr | Summary | 69 | 1.7.2.7 | 1.7.2.7 |  | 1096 | p | 29 | -3% | 1125
700 | 6248 | DGpV8AP7Q4dyYuiDaoIl | Summary | 56 | 1.7.2.7.2 | 1.7.2.7.2 |  | 399 | p | 29 | -7% | 428
701 | 6251 | Ha7ZmVRhPp4EjAGEFQOQ | Normal | 56 | 1.7.2.7.2.3 | 1.7.2.7.2.3 |  | 193 | p | 9 | -5% | 202
702 | 6252 | FwTW8u2nmxBgH6wyvtoz | Summary | 56 | 1.7.2.7.3 | 1.7.2.7.3 |  | 399 | p | 21 | -5% | 420
703 | 6255 | 6Rcxv4eHz2WhxfD2wxtd | Normal | 56 | 1.7.2.7.3.3 | 1.7.2.7.3.3 |  | 193 | p | 1 | -1% | 194
704 | 6256 | TcRehVKUpIeirJTvWiO5 | Summary | 14 | 1.7.2.7.4 | 1.7.2.7.4 |  | 357 | p | 21 | -6% | 378
705 | 6259 | q6ww59eaDtL5Df1J4lsR | Normal | 14 | 1.7.2.7.4.3 | 1.7.2.7.4.3 |  | 151 | p | 1 | -1% | 152
706 | 6260 | nYwGXpoj6WqcdUPfZoTk | Summary | 14 | 1.7.2.7.5 | 1.7.2.7.5 |  | 357 | p | 23 | -6% | 380
707 | 6263 | aKytB1b2oD2t1WVaznUP | Normal | 14 | 1.7.2.7.5.3 | 1.7.2.7.5.3 |  | 151 | p | 3 | -2% | 154
708 | 6317 | NzqiT3qChWGoVO5Oxj9C | Summary | 111 | 1.9.4 | 1.9.4 |  | 1040 | p | 272 | -26% | 1312
709 | 5355 | lohINUHwZqjP23W1PYQO | Summary | 26 | 1.9.4.1 | 1.9.4.1 |  | 913 | q | -1 | 0% | 912
710 | 5360 | ARncD9Nx3De5DONPy9Bs | Normal | 3 | 1.9.4.1.4 | 1.9.4.1.4 |  | 3 | q | -1 | (-33%) | 2
711 | 7262 | dH18W6KApKWC8TAOWb50 | Normal | 36 | 1.7.4.1.4 | 1.7.4.1.4 |  | 36 | p | 3 | -8% | 39
712 | 5362 | 4bsxfawvV6TKTvCq9VoB | Summary | 6 | 1.9.4.2 | 1.9.4.2 |  | 899 | p | 341 | -38% | 1240
713 | 7260 | DPsh83rHAyIaiD8XYnO0 | Normal | 6 | 1.7.4.2.4 | 1.7.4.2.4 |  | 36 | p | 323 | -897% | 359
714 | 5375 | zkXPpJkHw8DPAtspwcmA | Summary | 124 | 1.9.4.4 | 1.9.4.4 |  | 481 | p | 319 | -66% | 800
715 | 5376 | zSTdFwWI5FOaluV37lYS | Normal | 63 | 1.9.4.4.1 | 1.9.4.4.1 |  | 245 | q | -7 | (-3%) | 238
716 | 5377 | Wv5w7NMYDRM71nE6dVi0 | Summary | 58 | 1.9.4.5 | 1.9.4.5 |  | 170 | p | 3 | -2% | 173
717 | 5383 | u1aficyBQ2O9A8MnpdfZ | Normal | 20 | 1.9.4.5.6 | 1.9.4.5.6 |  | 20 | p | 5 | -25% | 25
718 | 5385 | ohwsmv9qOoV0RNzIdjJI | Normal | 15 | 1.9.4.5.8 | 1.9.4.5.8 |  | 15 | p | 2 | -13% | 17
719 | 5386 | tSuemAovBYAaHNhFiwaF | Normal | 15 | 1.9.4.5.9 | 1.9.4.5.9 |  | 15 | q | -3 | (-20%) | 12
720 | 5387 | 9gTKo9vjb1rQAbWcTOOW | Summary | 58 | 1.9.4.6 | 1.9.4.6 |  | 170 | q | -5 | (-3%) | 165
721 | 5392 | TRJmldmXNRf3NwsZhgng | Normal | 20 | 1.9.4.6.5 | 1.9.4.6.5 |  | 20 | q | -2 | (-10%) | 18
722 | 5394 | ungpeNo64cspVo3BuO9g | Normal | 10 | 1.9.4.6.7 | 1.9.4.6.7 |  | 10 | p | 1 | -10% | 11
723 | 5395 | KZXvYFda88KgX9w7a3ES | Normal | 15 | 1.9.4.6.8 | 1.9.4.6.8 |  | 15 | q | -1 | (-7%) | 14
724 | 5396 | FNjsTUKVT29tBcVlvaM6 | Normal | 15 | 1.9.4.6.9 | 1.9.4.6.9 |  | 15 | q | -2 | (-13%) | 13
725 | 5397 | KGrMeH5y6HH9dj1tr8uB | Summary | 53 | 1.9.4.7 | 1.9.4.7 |  | 53 | p | 4 | -8% | 57
726 | 5398 | EMMfZLgDhvN5O0lAfznQ | Normal | 15 | 1.9.4.7.1 | 1.9.4.7.1 |  | 15 | p | 1 | -7% | 16
727 | 5401 | WWZjxA63YxH38hnYmVKG | Normal | 8 | 1.9.4.7.4 | 1.9.4.7.4 |  | 8 | p | 3 | -38% | 11
728 | 5402 | zDUD70mdAG3rcozejCwk | Summary | 15 | 1.9.4.8 | 1.9.4.8 |  | 15 | p | 264 | -1760% | 279
729 | 5403 | wP2WbhW6upJb7JmdzCw1 | Normal | 9 | 1.9.4.8.1 | 1.9.4.8.1 |  | 9 | p | 1 | -11% | 10
730 | 5404 | UrewlDJ3J2c8Ueci7p9E | Normal | 6 | 1.9.4.8.2 | 1.9.4.8.2 |  | 6 | q | -1 | (-17%) | 5
731 | 7265 | uNFJkQaxxZ7oOYaM8QxX | Normal | 13 | 1.7.4.3.6.1 | 1.7.4.3.6.1 |  | 13 | p | 1 | -8% | 14
732 | 7266 | y7TR6NxR4uOKxinxsnEt | Normal | 13 | 1.7.4.3.6.2 | 1.7.4.3.6.2 |  | 13 | q | -1 | (-8%) | 12
733 | 7267 | f0BUmD79ZhKqjjzrwXUq | Normal | 13 | 1.7.4.3.6.3 | 1.7.4.3.6.3 |  | 13 | p | 1 | -8% | 14
734 | 7322 | XsHCl5GkwKVP3xy7r0jT | Summary | 85 | 1.7.5 | 1.7.5 |  | 85 | p | 5 | -6% | 90
735 | 7528 | 8SnF5zCB4rJyZyQZLLZc | Normal | 8 | 1.7.5.1 | 1.7.5.1 |  | 8 | p | 3 | -38% | 11
736 | 7531 | WsQS39Ko43y2ykuRUNnk | Normal | 8 | 1.7.5.4 | 1.7.5.4 |  | 8 | p | 2 | -25% | 10
737 | 7532 | tNKjUDGuH9lZvW14y0xJ | Normal | 22 | 1.7.5.5 | 1.7.5.5 |  | 22 | p | 1 | -5% | 23
738 | 7533 | HKUUjAeDBFLcgj42uw3c | Normal | 19 | 1.7.5.6 | 1.7.5.6 |  | 19 | p | 2 | -11% | 21
739 | 7534 | s7VTtgJqjYjf9pbLYcYj | Normal | 8 | 1.7.5.7 | 1.7.5.7 |  | 8 | q | -1 | (-12%) | 7
740 | 7535 | uGgP1gHCy12zlVFcLeTG | Normal | 6 | 1.7.5.8 | 1.7.5.8 |  | 6 | q | -1 | (-17%) | 5
741 | 7536 | kbIucnV7qsI0ZjxbK1cH | Normal | 6 | 1.7.5.9 | 1.7.5.9 |  | 6 | p | 1 | -17% | 7
742 | 6688 | aKOlgm9Tw9oPXF0YCFLp | Summary | 911 | 1.11 | 1.11 |  | 2873 | q | -421 | (-15%) | 2452
743 | 6689 | fEYxMDiPOAwjjU8zha5c | Normal | 396 | 1.11.1 | 1.11.1 |  | 569 | q | -102 | (-18%) | 467
744 | 6690 | bopLkaAZbmZjIM9EGI6L | Normal | 532 | 1.11.2 | 1.11.2 |  | 532 | p | 63 | -12% | 595
745 | 6691 | xLErpFHjPEH3ifHRbBMY | Normal | 396 | 1.11.3 | 1.11.3 |  | 569 | p | 90 | -16% | 659
746 | 6692 | g8WcEZ6I6SGdlePHrYPP | Normal | 248 | 1.11.4 | 1.11.4 |  | 421 | p | 24 | -6% | 445
747 | 6695 | Bx0BPJ0BcPw49QEL7Psq | Normal | 313 | 1.11.8 | 1.11.8 |  | 570 | q | -68 | (-12%) | 502
748 | 6696 | XbFIp383UbA72xJPH4hJ | Normal | 101 | 1.11.9 | 1.11.9 |  | 274 | q | -1 | 0% | 273
749 | 6697 | gpkN7vTMpz4ZZxhDAmeL | Normal | 126 | 1.11.10 | 1.11.10 |  | 131 | p | 1 | -1% | 132
750 | 6698 | eRsel9yyFaDkcYLZgvjC | Normal | 142 | 1.11.11 | 1.11.11 |  | 399 | p | 10 | -3% | 409
751 | 6699 | k8943lu4TS9ZW2TcUvha | Normal | 256 | 1.11.12 | 1.11.12 |  | 398 | p | 33 | -8% | 431
752 | 7376 | FfEUU5kpALOu6FlmjosD | Normal | 396 | 1.10.3 | 1.10.3 |  | 1874 | p | 22 | -1% | 1896
753 | 7378 | YjoFZZooPnFRzsk2Ba2E | Normal | 288 | 1.10.6 | 1.10.6 |  | 1776 | p | 75 | -4% | 1851
754 | 7379 | 7GajZBAFakrGWC1WlgE6 | Normal | 142 | 1.10.14 | 1.10.14 |  | 1047 | q | -37 | (-4%) | 1010
755 | 7380 | wkyoOF6gHS9pA0Dm9pZY | Normal | 140 | 1.10.17 | 1.10.17 |  | 736 | q | -20 | (-3%) | 716
756 | 7131 | XTX9Wl5SzTxAD1rtsh9U | Summary | 0 | 1.10 | 1.10 |  | 808 | p | 1824 | -226% | 2632

## Actual-Duration
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Actual Duration - 193 (9%) | Actual Duration - 193 (9%) | Actual Duration - 193 (9%) | Actual Duration - 193 (9%) | Actual Duration - 193 (9%) | Actual Duration - 193 (9%) | Actual Duration - 193 (9%) | Actual Duration - 193 (9%) | Actual Duration - 193 (9%) | Actual Duration - 193 (9%) | Actual Duration - 193 (9%) | Actual Duration - 193 (9%) | Actual Duration - 193 (9%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 1249 | v1zgYyoO7UpynPZXt29g | Summary | 611 | 1 | 1 |  | 2263 | p | 67 | -3% | 2330
2 | 147 | DEZpxiHWY7fkyvQEaEGc | Summary | 1132 | 1.2 | 1.2 |  | 1742 | p | 76 | -4% | 1818
3 | 158 | D5C8AUNeoI4YKF3PggKx | Summary | 255 | 1.2.7 | 1.2.7 |  | 400 | p | 261 | -65% | 661
4 | 6636 | 3J1qFTgnrSSZVnoYdTv5 | Summary | 140 | 1.2.7.3 | 1.2.7.3 |  | 249 | p | 5 | -2% | 254
5 | 179 | jSOjvYE1qiHOKdcV2ixu | Summary | 554 | 1.2.10 | 1.2.10 |  | 185 | p | 26 | -14% | 211
6 | 4180 | LxVAz76PSOUu8y7B8sy3 | Summary | 218 | 1.3 | 1.3 |  | 968 | p | 10 | -1% | 978
7 | 384 | GE3w1SHplCQZN7aYDVw8 | Summary | 34 | 1.3.3 | 1.3.3 |  | 1102 | p | 11 | -1% | 1113
8 | 429 | Pbs0MxOqvHazWgB8fpDs | Summary | 41 | 1.3.3.2 | 1.3.3.2 |  | 1000 | p | 7 | -1% | 1007
9 | 437 | kEyeaq7ebxWRSvBqGkHC | Summary | 19 | 1.3.3.1 | 1.3.3.1 |  | 979 | p | 19 | -2% | 998
10 | 438 | QjVW4dYK4boDcUrG7MUx | Summary | 23 | 1.3.3.1.2 | 1.3.3.1.2 |  | 367 | p | 18 | -5% | 385
11 | 445 | cIIfBfMFMZUbJxswwNzj | Summary | 28 | 1.3.3.1.2.4 | 1.3.3.1.2.4 |  | 350 | p | 19 | -5% | 369
12 | 5768 | 9l9o7D6Il8vKVgGgZRMW | Summary | 197 | 1.3.3.4 | 1.3.3.4 |  | 197 | p | 13 | -7% | 210
13 | 6289 | NknbxY1EWobhbJ98SVRq | Summary | 270 | 1.3.2 | 1.3.2 |  | 467 | p | 10 | -2% | 477
14 | 3848 | g0gBmZeXCCPZTY4kkYs8 | Summary | 210 | 1.3.2.1 | 1.3.2.1 |  | 527 | p | 2 | 0% | 529
15 | 3850 | sk2pEdmn2KeVBRyrQzgn | Summary | 233 | 1.3.2.1.2 | 1.3.2.1.2 |  | 208 | q | -1 | 0% | 207
16 | 3857 | FObPKa3HJ5KI4gFmAx2r | Summary | 210 | 1.3.2.1.2.2 | 1.3.2.1.2.2 |  | 67 | p | 2 | -3% | 69
17 | 3863 | WaF24jcpD2qzV3M05hSl | Summary | 178 | 1.3.2.1.2.3 | 1.3.2.1.2.3 |  | 196 | p | 8 | -4% | 204
18 | 7186 | ttl1FahPn0WwOuyGdmk6 | Summary | 138 | 1.3.2.3 | 1.3.2.3 |  | 138 | p | 12 | -9% | 150
19 | 7188 | yn5QOVI2BZ7jor10JaQN | Summary | 55 | 1.3.2.3.2 | 1.3.2.3.2 |  | 89 | p | 2 | -2% | 91
20 | 7189 | jup7puBG1dNvbV8jB14f | Summary | 69 | 1.3.2.3.2.1 | 1.3.2.3.2.1 |  | 75 | q | -2 | (-3%) | 73
21 | 7190 | Ob13piboJI4zFNOVPzZD | Summary | 50 | 1.3.2.3.2.1.1 | 1.3.2.3.2.1.1 |  | 45 | q | -4 | (-9%) | 41
22 | 7193 | hzdeRXxytBFeNJPq5eHn | Summary | 50 | 1.3.2.3.2.1.2 | 1.3.2.3.2.1.2 |  | 24 | q | -5 | (-21%) | 19
23 | 7196 | fFBpC2vR2qp5KXHLtypR | Summary | 23 | 1.3.2.3.2.1.3 | 1.3.2.3.2.1.3 |  | 72 | p | 15 | -21% | 87
24 | 7205 | 688LmElxek6WZQ34zEgD | Summary | 40 | 1.3.2.3.2.2 | 1.3.2.3.2.2 |  | 41 | p | 11 | -27% | 52
25 | 7210 | 5vpOUfvEpSU2AKPwltv0 | Summary | 14 | 1.3.2.3.2.3 | 1.3.2.3.2.3 |  | 75 | p | 5 | -7% | 80
26 | 7211 | wSDYMNBcPlclxMN6Hc8V | Normal | 5 | 1.3.2.3.2.3.1 | 1.3.2.3.2.3.1 |  | 75 | p | 5 | -7% | 80
27 | 7215 | a8OJFGtOVEyM75c9puYK | Summary | 34 | 1.3.2.3.2.4 | 1.3.2.3.2.4 |  | 37 | p | 3 | -8% | 40
28 | 7218 | 5fSpBiSdaCD1mvMsYs0j | Normal | 2 | 1.3.2.3.2.4.3 | 1.3.2.3.2.4.3 |  | 6 | p | 2 | -33% | 8
29 | 7219 | tMHxEODKuKminmE9Mjg5 | Normal | 1 | 1.3.2.3.2.4.4 | 1.3.2.3.2.4.4 |  | 0 | p | 1 |  | 1
30 | 7223 | 2cLCJpvBPh4ccgbvKrEi | Summary | 38 | 1.3.2.3.2.5 | 1.3.2.3.2.5 |  | 77 | p | 20 | -26% | 97
31 | 7226 | fsyu9CvTMAXTCK7e04ez | Normal | 1 | 1.3.2.3.2.5.3 | 1.3.2.3.2.5.3 |  | 23 | p | 1 | -4% | 24
32 | 7515 | jdxLrBmn54gbF5MbPNVU | Normal | 5 | 1.3.2.3.2.5.8 | 1.3.2.3.2.5.8 |  | 5 | p | 5 | -100% | 10
33 | 6269 | tUCxonMalaI13D6hsUSU | Summary | 99 | 1.5 | 1.5 |  | 1141 | p | 9 | -1% | 1150
34 | 6278 | SNMcp7h74WVvBiN3lPNB | Summary | 66 | 1.5.6 | 1.5.6 |  | 1164 | p | 22 | -2% | 1186
35 | 620 | q8advjPa5PEndSFXJ05j | Summary | 158 | 1.5.6.6 | 1.5.6.6 |  | 598 | p | 19 | -3% | 617
36 | 622 | Q48N5ZSDLesB1Bsda2wx | Summary | 156 | 1.5.6.6.2 | 1.5.6.6.2 |  | 321 | p | 19 | -6% | 340
37 | 631 | jjFU6HpNq2otAi9zmRWR | Normal | 2 | 1.5.6.6.2.7 | 1.5.6.6.2.7 |  | 4 | p | 2 | -50% | 6
38 | 648 | 6WPgljRre9DjhHGVsVUH | Summary | 120 | 1.5.6.6.5 | 1.5.6.6.5 |  | 306 | p | 14 | -5% | 320
39 | 670 | zBtIFoyMK1KgXAv407C9 | Summary | 29 | 1.5.6.5 | 1.5.6.5 |  | 210 | p | 33 | -16% | 243
40 | 6141 | PCEOtJROHHMKXYkoR4rp | Normal | 3 | 1.5.6.5.1 | 1.5.6.5.1 |  | 43 | p | 3 | -7% | 46
41 | 6281 | RYPcKAyzQapOQ3GupQll | Summary | 104 | 1.5.5 | 1.5.5 |  | 311 | p | 13 | -4% | 324
42 | 1466 | LmBGiI2jXQ3lZF0l79sj | Summary | 104 | 1.5.5.1 | 1.5.5.1 |  | 311 | p | 13 | -4% | 324
43 | 1457 | W1XQ7yoZAeSgm7UftoXN | Normal | 1 | 1.5.5.1.2 | 1.5.5.1.2 |  | 0 | p | 1 |  | 1
44 | 6292 | 1Cm9NXihvfL2WEnYcHvT | Summary | 42 | 1.5.4 | 1.5.4 |  | 803 | p | 21 | -3% | 824
45 | 3949 | knRWxUZkgPmXKgij09tb | Summary | 25 | 1.5.4.5 | 1.5.4.5 |  | 394 | p | 21 | -5% | 415
46 | 3950 | NJx1RMKdqhuNKRLGMSBQ | Summary | 27 | 1.5.4.5.1 | 1.5.4.5.1 |  | 309 | p | 23 | -7% | 332
47 | 3964 | ZzcX1hV2BTbfmTYJl5AE | Summary | 19 | 1.5.4.5.4 | 1.5.4.5.4 |  | 382 | p | 19 | -5% | 401
48 | 5996 | M6DLFbZyZKXroBVfXncj | Summary | 19 | 1.5.4.4 | 1.5.4.4 |  | 377 | p | 18 | -5% | 395
49 | 6299 | JvNaxkj9UdrgV7BcBski | Summary | 134 | 1.5.1 | 1.5.1 |  | 601 | p | 13 | -2% | 614
50 | 4213 | pNBoUl9px0n4wFhfXXqQ | Summary | 90 | 1.5.1.1 | 1.5.1.1 |  | 501 | p | 17 | -3% | 518
51 | 6674 | 3EUoGYyEaAia67bx8maJ | Summary | 69 | 1.5.1.3 | 1.5.1.3 |  | 179 | q | -4 | (-2%) | 175
52 | 6308 | 9d1kbrq4aHbr7FOmo76u | Summary | 27 | 1.5.2 | 1.5.2 |  | 948 | q | -10 | (-1%) | 938
53 | 5611 | e3AOkT5PZcArPsKmcVqB | Summary | 48 | 1.5.2.2 | 1.5.2.2 |  | 729 | q | -14 | (-2%) | 715
54 | 5627 | s0vjJX7zGlVyBdE0eigo | Summary | 15 | 1.5.2.2.8 | 1.5.2.2.8 |  | 0 | p | 5 |  | 5
55 | 7545 | 65jUkOPqlMfpoMROhJ4O | Normal | 5 | 1.5.3.2.9.1 | 1.5.3.2.9.1 |  | 0 | p | 5 |  | 5
56 | 5635 | ZYzv9KOmVdYL2d3ZPb8b | Summary | 0 | 1.5.2.2.9 | 1.5.2.2.9 |  | 18 | q | -17 | (-94%) | 1
57 | 5638 | jBSFjjY1RfmWgqa8tOlO | Normal | 0 | 1.5.2.2.9.3 | 1.5.2.2.9.3 |  | 11 | q | -11 | (-100%) | 0
58 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | 5 | q | -5 | (-100%) | 0
59 | 6309 | taNk8S9bKnlDToaFycS6 | Summary | 37 | 1.5.3 | 1.5.3 |  | 274 | p | 20 | -7% | 294
60 | 5443 | L0xk8h495fvdhlwnri8N | Summary | 37 | 1.5.3.1 | 1.5.3.1 |  | 274 | p | 20 | -7% | 294
61 | 5445 | 95pLIsxhFDdrMJGVBrpQ | Summary | 35 | 1.5.3.1.2 | 1.5.3.1.2 |  | 8 | p | 5 | -62% | 13
62 | 6270 | Wwp4MRWhcV55WleZhe1f | Summary | 288 | 1.4 | 1.4 |  | 687 | p | 5 | -1% | 692
63 | 6290 | VuOK0YK760zOpXaJ9U7h | Summary | 140 | 1.4.3 | 1.4.3 |  | 775 | q | -10 | (-1%) | 765
64 | 4537 | FhESv2GOKRYErv6rS2Ko | Summary | 140 | 1.4.3.1 | 1.4.3.1 |  | 775 | q | -10 | (-1%) | 765
65 | 6291 | 7X6NK9qir9GRz5m7bXmK | Summary | 297 | 1.4.1 | 1.4.1 |  | 563 | p | 8 | -1% | 571
66 | 3891 | VQVEpj4HfOnKALplb4t9 | Summary | 43 | 1.4.1.1 | 1.4.1.1 |  | 323 | p | 20 | -6% | 343
67 | 3897 | cqWsQsQWdy7etYVMNQBf | Summary | 53 | 1.4.1.1.2 | 1.4.1.1.2 |  | 272 | p | 20 | -7% | 292
68 | 3902 | FL4HGNxujC5zK4lN6AVO | Summary | 30 | 1.4.1.2 | 1.4.1.2 |  | 410 | q | -15 | (-4%) | 395
69 | 3903 | e0nMZ5CLCmjCURLrKpol | Summary | 30 | 1.4.1.2.1 | 1.4.1.2.1 |  | 410 | q | -15 | (-4%) | 395
70 | 6318 | cM5VCGnPiK1mfNJo8YLF | Summary | 309 | 1.4.2 | 1.4.2 |  | 663 | q | -8 | (-1%) | 655
71 | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Summary | 707 | 1.4.2.2 | 1.4.2.2 |  | 148 | q | -1 | (-1%) | 147
72 | 5226 | R9JO9mOSGmg0eoDimoJT | Summary | 71 | 1.4.2.1 | 1.4.2.1 |  | 582 | q | -27 | (-5%) | 555
73 | 5262 | PI0DE6xTKT4gLnHpqgjE | Summary | 137 | 1.4.2.1.6 | 1.4.2.1.6 |  | 224 | q | -25 | (-11%) | 199
74 | 6271 | Q6QswYSvhipRUbZBXuiu | Summary | 315 | 1.6 | 1.6 |  | 1613 | p | 22 | -1% | 1635
75 | 6277 | moVS9Ou3GclDwNSW1OnS | Summary | 264 | 1.6.7 | 1.6.7 |  | 870 | p | 36 | -4% | 906
76 | 728 | 4dRz6TQj3FOK8lstTqZK | Summary | 396 | 1.6.7.9 | 1.6.7.9 |  | 240 | p | 13 | -5% | 253
77 | 741 | cktDjgZ5bp36SrQnCM1w | Summary | 458 | 1.6.7.9.3 | 1.6.7.9.3 |  | 53 | p | 3 | -6% | 56
78 | 6323 | aU24Z8SrLl20SyyllZuy | Summary | 80 | 1.6.7.9.3.5 | 1.6.7.9.3.5 |  | 140 | p | 6 | -4% | 146
79 | 770 | cHAOkWrFbu094CNd9eCk | Summary | 91 | 1.6.7.8 | 1.6.7.8 |  | 436 | p | 18 | -4% | 454
80 | 6284 | T6s1mlIi1Lu4cscBpq9h | Summary | 273 | 1.6.6 | 1.6.6 |  | 174 | q | -14 | (-8%) | 160
81 | 1519 | Ig6aeqJATmPNbReGQrzj | Summary | 273 | 1.6.6.1 | 1.6.6.1 |  | 174 | q | -14 | (-8%) | 160
82 | 1463 | IQX94tuow2VKmVJTuhEN | Normal | 1 | 1.6.6.1.3 | 1.6.6.1.3 |  | 0 | p | 1 |  | 1
83 | 6293 | WhUcOZjaj9TDZe74ojmh | Summary | 172 | 1.6.4 | 1.6.4 |  | 651 | p | 49 | -8% | 700
84 | 3929 | GkmiaraCbWdBUaRv136y | Summary | 19 | 1.6.4.15 | 1.6.4.15 |  | 296 | p | 33 | -11% | 329
85 | 3971 | mB1p68eekBqQhgV8es2U | Summary | 19 | 1.6.4.7 | 1.6.4.7 |  | 224 | p | 24 | -11% | 248
86 | 3973 | 00qHhBlTe8pinGtKpu3n | Normal | 4 | 1.6.4.6 | 1.6.4.6 |  | 381 | p | 4 | -1% | 385
87 | 3991 | kc0LQmDrjfLGJeMU4QIH | Summary | 70 | 1.6.4.17 | 1.6.4.17 |  | 370 | p | 17 | -5% | 387
88 | 4002 | nJzh0eFJGsqvOmQRJzHn | Summary | 27 | 1.6.4.17.2 | 1.6.4.17.2 |  | 238 | p | 18 | -8% | 256
89 | 4012 | A4Ck0Reyqf4cLzrM8uUY | Summary | 206 | 1.6.4.19 | 1.6.4.19 |  | 377 | q | -112 | (-30%) | 265
90 | 4037 | hMBnPD0NfYpjSqEpRMYY | Summary | 554 | 1.6.4.20 | 1.6.4.20 |  | 17 | p | 1 | -6% | 18
91 | 4038 | VkrURyJwsSkEVRV6WcXe | Summary | 411 | 1.6.4.20.1 | 1.6.4.20.1 |  | 21 | p | 1 | -5% | 22
92 | 5748 | cHP8KcDQZp8MvOi5a8Wj | Summary | 64 | 1.6.4.18 | 1.6.4.18 |  | 323 | p | 9 | -3% | 332
93 | 6701 | vwWJ3SVwW3tYdDDMDgOK | Summary | 60 | 1.6.4.18.3 | 1.6.4.18.3 |  | 157 | p | 8 | -5% | 165
94 | 6713 | JQXHTZXJblKyiNyxM0eT | Summary | 78 | 1.6.4.18.3.3 | 1.6.4.18.3.3 |  | 129 | p | 10 | -8% | 139
95 | 6727 | 5BlmDU3ct4fwjT54EODG | Summary | 21 | 1.6.4.18.3.3.2 | 1.6.4.18.3.3.2 |  | 73 | p | 6 | -8% | 79
96 | 6738 | XB1ZMgqMWvDJpnRGKTB3 | Normal | 3 | 1.6.4.18.3.3.2.10 | 1.6.4.18.3.3.2.10 |  | 0 | p | 3 |  | 3
97 | 7003 | XfnOKCk0EbakXF7t35fN | Normal | 1 | 1.6.4.18.3.3.2.9 | 1.6.4.18.3.3.2.9 |  | 34 | p | 1 | -3% | 35
98 | 7007 | 9uputDeZmGdSlUY8oN4J | Summary | 64 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 50 | p | 15 | -30% | 65
99 | 7277 | hIopgQViPH34dy6jPgEs | Normal | 6 | 1.6.4.18.3.3.7.5 | 1.6.4.18.3.3.7.5 |  | 0 | p | 6 |  | 6
100 | 7279 | uD2jpviUMAewZ4YhDj8P | Summary | 32 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 40 | q | -3 | (-8%) | 37
101 | 7293 | ep0qwejNT11UOlW5WmY0 | Summary | 28 | 1.6.4.18.3.3.6 | 1.6.4.18.3.3.6 |  | 20 | p | 2 | -10% | 22
102 | 7295 | tyaakhlAtuOpVSt7bVvo | Normal | 1 | 1.6.4.18.3.3.6.2 | 1.6.4.18.3.3.6.2 |  | 0 | p | 1 |  | 1
103 | 6297 | AqdIsKbIPOfZJkjKYjnG | Summary | 118 | 1.6.1 | 1.6.1 |  | 810 | q | -220 | (-27%) | 590
104 | 4200 | YSdvLAa6ztbhOKei71CV | Summary | 108 | 1.6.1.1 | 1.6.1.1 |  | 540 | p | 17 | -3% | 557
105 | 4209 | 0Ck6gz1ZilLs9fM0b7nU | Summary | 46 | 1.6.1.3 | 1.6.1.3 |  | 501 | p | 19 | -4% | 520
106 | 6311 | tQdu1pFxVkY2bj5IQjxI | Summary | 77 | 1.6.3 | 1.6.3 |  | 1517 | p | 6 | 0% | 1523
107 | 5457 | kGunJCROCjWQWqBfRKBZ | Summary | 1 | 1.6.3.2 | 1.6.3.2 |  | 747 | p | 16 | -2% | 763
108 | 5458 | DngVHB2HpHpsOjFWu5hu | Summary | 1 | 1.6.3.2.1 | 1.6.3.2.1 |  | 747 | p | 16 | -2% | 763
109 | 5506 | wLM81Xdu8B5geOMMQz6m | Summary | 119 | 1.6.3.3 | 1.6.3.3 |  | 140 | p | 63 | -45% | 203
110 | 6359 | hvfa0617w1FgmEnjjKwJ | Summary | 26 | 1.7.2.16 | 1.7.2.16 |  | 163 | p | 2 | -1% | 165
111 | 6360 | DMXbIVCeMtVR5pi4d5UN | Summary | 26 | 1.7.2.16.1 | 1.7.2.16.1 |  | 163 | p | 2 | -1% | 165
112 | 6361 | VEKeY9azNIVSZDSjYyKy | Summary | 33 | 1.7.2.16.1.3 | 1.7.2.16.1.3 |  | 156 | p | 3 | -2% | 159
113 | 7303 | fpLHmKjlfpy4s4tap5Xw | Summary | 39 | 1.6.3.11.1.3.4 | 1.6.3.11.1.3.4 |  | 33 | q | -1 | (-3%) | 32
114 | 7309 | 19skeJKmh3pRSfTF3DDB | Summary | 30 | 1.6.3.11.1.3.5 | 1.6.3.11.1.3.5 |  | 34 | p | 6 | -18% | 40
115 | 7312 | ZHpaj2955bjmxPKFBEf2 | Normal | 2 | 1.6.3.11.1.3.5.3 | 1.6.3.11.1.3.5.3 |  | 0 | p | 2 |  | 2
116 | 7315 | 9LywAxRsXdHsCrCcjGKV | Summary | 27 | 1.6.3.11.1.3.6 | 1.6.3.11.1.3.6 |  | 37 | q | -1 | (-3%) | 36
117 | 6273 | ljz6i2ltFwqcRU3btDx0 | Summary | 552 | 1.8 | 1.8 |  | 248 | p | 132 | -53% | 380
118 | 1639 | mkPE1mMWzawwUBF3KKzV | Summary | 277 | 1.8.2 | 1.8.2 |  | 523 | p | 260 | -50% | 783
119 | 6295 | uPS9GNqRLP4065SnBhEr | Summary | 387 | 1.8.5 | 1.8.5 |  | 30 | p | 20 | -67% | 50
120 | 3679 | 1KDcwGZKgevw1MizqBh0 | Summary | 387 | 1.8.5.1 | 1.8.5.1 |  | 30 | p | 20 | -67% | 50
121 | 3723 | 4qmbzAmtSx0gvDVaBsYe | Summary | 239 | 1.8.5.1.5 | 1.8.5.1.5 |  | 91 | p | 9 | -10% | 100
122 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 1191 | p | 1194 | -100% | 2385
123 | 6275 | OL3lkJGtK3tkk0d4SBRn | Summary | 288 | 1.9.9 | 1.9.9 |  | 1103 | p | 518 | -47% | 1621
124 | 845 | U1v5hScHSOPPxa5ohjfI | Summary | 189 | 1.9.9.7 | 1.9.9.7 |  | 991 | p | 16 | -2% | 1007
125 | 847 | JilJNxxBcx7QrT5PcKLM | Summary | 189 | 1.9.9.7.2 | 1.9.9.7.2 |  | 971 | p | 17 | -2% | 988
126 | 870 | m3oEXpasu7ssfpw9dqLv | Summary | 267 | 1.9.9.14 | 1.9.9.14 |  | 536 | p | 425 | -79% | 961
127 | 6128 | 7jXaekqqhUCDWSDfnxzo | Summary | 28 | 1.7.4.2 | 1.7.4.2 |  | 184 | q | -1 | (-1%) | 183
128 | 6279 | p7EJXT1muDSglD2OZLFH | Summary | 274 | 1.9.7 | 1.9.7 |  | 870 | p | 1261 | -145% | 2131
129 | 1484 | 6ARiGRg3KLswRpJLOmGD | Summary | 229 | 1.9.7.18 | 1.9.7.18 |  | 284 | p | 791 | -279% | 1075
130 | 1529 | WOa3B8SPUOSM5ThLE2Jo | Summary | 69 | 1.9.7.14 | 1.9.7.14 |  | 193 | p | 6 | -3% | 199
131 | 1535 | vIOpwJGhGrQ4pKl5nahR | Summary | 61 | 1.9.7.15 | 1.9.7.15 |  | 356 | p | 21 | -6% | 377
132 | 1539 | ySsQ3GXU4tpHt4hn7HeO | Normal | 2 | 1.9.7.15.4 | 1.9.7.15.4 |  | 204 | p | 2 | -1% | 206
133 | 1540 | GIXHFfgJ4jA0lgUlb0GT | Normal | 1 | 1.9.7.15.5 | 1.9.7.15.5 |  | 0 | p | 1 |  | 1
134 | 1544 | dYtuUpkdltDWUtvWJGdC | Summary | 80 | 1.9.7.16 | 1.9.7.16 |  | 304 | q | -212 | (-70%) | 92
135 | 1551 | FTwSjNJQyZH6RsSSqWG9 | Summary | 78 | 1.9.7.19 | 1.9.7.19 |  | 735 | p | 1 | 0% | 736
136 | 1560 | fBOtciokyA85OuE15WSO | Normal | 1 | 1.9.7.19.10 | 1.9.7.19.10 |  | 142 | p | 1 | -1% | 143
137 | 4574 | z7UYZlhr663oN8lfFWmH | Summary | 29 | 1.9.7.11 | 1.9.7.11 |  | 367 | q | -21 | (-6%) | 346
138 | 7323 | p8rF5Tk8321hO30p5zSy | Summary | 79 | 1.7.8.18 | 1.7.8.18 |  | 26 | p | 1 | -4% | 27
139 | 6285 | 0inPdnysTnfuJeCJJEwo | Summary | 131 | 1.9.1 | 1.9.1 |  | 435 | p | 16 | -4% | 451
140 | 4615 | Io6EVgFdyRjG7CB2g0Wy | Summary | 98 | 1.7.3.4 | 1.7.3.4 |  | 253 | p | 21 | -8% | 274
141 | 4626 | 92oajspBBxTpnlNQO91I | Summary | 90 | 1.7.3.6 | 1.7.3.6 |  | 335 | p | 16 | -5% | 351
142 | 4637 | ohQUE8EwZLGEmkE5FTpA | Summary | 8 | 1.7.3.7 | 1.7.3.7 |  | 310 | p | 19 | -6% | 329
143 | 6294 | Jtjxi70STISSeVqV8OJy | Summary | 163 | 1.9.6 | 1.9.6 |  | 768 | p | 484 | -63% | 1252
144 | 3745 | D0mR64Wbk6oru5hoL4DG | Summary | 62 | 1.7.1.2 | 1.7.1.2 |  | 361 | p | 17 | -5% | 378
145 | 3773 | jfB1zdAbu7JeWEH3ijwy | Summary | 73 | 1.7.1.2.6 | 1.7.1.2.6 |  | 167 | p | 13 | -8% | 180
146 | 3783 | FcDlmkxQNUOM36qP0M0H | Summary | 58 | 1.7.1.3 | 1.7.1.3 |  | 403 | p | 18 | -4% | 421
147 | 3790 | Om0YwWoKF5usOVLnDccR | Summary | 13 | 1.7.1.3.4 | 1.7.1.3.4 |  | 383 | p | 20 | -5% | 403
148 | 6983 | PcmQnh6ym2R5IAKzFgwu | Summary | 141 | 1.7.1.3.7 | 1.7.1.3.7 |  | 18 | p | 2 | -11% | 20
149 | 3803 | vx1oFVBFPqydBxZJ7V4g | Summary | 112 | 1.7.1.5 | 1.7.1.5 |  | 333 | p | 14 | -4% | 347
150 | 3808 | mNtnU9AYiACOeBrTPE9f | Summary | 29 | 1.7.1.5.3 | 1.7.1.5.3 |  | 183 | p | 18 | -10% | 201
151 | 4129 | G6dPcJRrq5zqLYx4Vr0R | Summary | 475 | 1.9.6.10 | 1.9.6.10 |  | 230 | p | 205 | -89% | 435
152 | 4134 | 86JmjjOtZxj7XQRp3CQF | Summary | 466 | 1.9.6.11 | 1.9.6.11 |  | 294 | p | 180 | -61% | 474
153 | 4135 | 0voiyAtBe9AzaXfs8cVF | Summary | 322 | 1.9.6.11.1 | 1.9.6.11.1 |  | 390 | p | 264 | -68% | 654
154 | 5753 | ZptYdARXANY2IOcoHhB1 | Summary | 78 | 1.9.6.1 | 1.9.6.1 |  | 421 | p | 559 | -133% | 980
155 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | 0 | p | 20 |  | 20
156 | 5762 | BY50RWHTB6QfyvgvJksd | Summary | 36 | 1.9.6.9 | 1.9.6.9 |  | 384 | p | 18 | -5% | 402
157 | 6424 | xU9ngPKik2IYPonksYTK | Summary | 24 | 1.7.1.8 | 1.7.1.8 |  | 47 | q | -46 | (-98%) | 1
158 | 6296 | SlR21lje1Tex9DLMlAM1 | Summary | 222 | 1.9.8 | 1.9.8 |  | 977 | p | 571 | -58% | 1548
159 | 4192 | vUDAXlHZqbmK6WAsX9hH | Summary | 139 | 1.9.8.1 | 1.9.8.1 |  | 801 | p | 14 | -2% | 815
160 | 4197 | 4xVk2zrTd9sJnt9BJFir | Summary | 36 | 1.9.8.1.6 | 1.9.8.1.6 |  | 217 | q | -33 | (-15%) | 184
161 | 4222 | uotgqiCu1xVBvHdpBC3E | Summary | 97 | 1.9.8.2 | 1.9.8.2 |  | 467 | p | 22 | -5% | 489
162 | 4238 | ReJqSs3gutB053iVY5c7 | Summary | 76 | 1.9.8.4 | 1.9.8.4 |  | 472 | p | 17 | -4% | 489
163 | 6314 | PaZTrKFuMaJQzXHDclW5 | Summary | 34 | 1.9.2 | 1.9.2 |  | 433 | p | 8 | -2% | 441
164 | 5666 | lc2LPCzbTjVw9vZ8eS89 | Summary | 23 | 1.9.2.2 | 1.9.2.2 |  | 372 | q | -2 | (-1%) | 370
165 | 5667 | chBvra0KGhqU3lfHBAI4 | Summary | 23 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 372 | q | -2 | (-1%) | 370
166 | 5672 | 2GDxhVAL0LbO4lfSMjXo | Summary | 47 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 420 | p | 16 | -4% | 436
167 | 6315 | 2iW64uJmzViIcLEo0dMn | Summary | 181 | 1.9.5 | 1.9.5 |  | 1067 | p | 421 | -39% | 1488
168 | 5532 | NHN4dwEEPEqCDqA4Rwlr | Summary | 74 | 1.9.5.1 | 1.9.5.1 |  | 258 | p | 57 | -22% | 315
169 | 5533 | g1oQNBzKk6OrBukgGH7R | Normal | 40 | 1.9.5.1.3 | 1.9.5.1.3 |  | 0 | p | 40 |  | 40
170 | 5537 | 9xVQhmyTVkChMoMOy91g | Summary | 193 | 1.9.5.2 | 1.9.5.2 |  | 358 | p | 220 | -61% | 578
171 | 5570 | MuDwSgsBJjDxwFkSMWYJ | Summary | 116 | 1.9.5.2.11 | 1.9.5.2.11 |  | 58 | p | 227 | -391% | 285
172 | 6528 | LROLnQke0gWnMONa67YB | Summary | 50 | 1.9.5.2.5 | 1.9.5.2.5 |  | 69 | p | 11 | -16% | 80
173 | 6189 | OaskfHPb0rGXxqxmUlvr | Summary | 69 | 1.7.2.7 | 1.7.2.7 |  | 1027 | p | 20 | -2% | 1047
174 | 6248 | DGpV8AP7Q4dyYuiDaoIl | Summary | 56 | 1.7.2.7.2 | 1.7.2.7.2 |  | 343 | p | 17 | -5% | 360
175 | 6252 | FwTW8u2nmxBgH6wyvtoz | Summary | 56 | 1.7.2.7.3 | 1.7.2.7.3 |  | 343 | p | 17 | -5% | 360
176 | 6256 | TcRehVKUpIeirJTvWiO5 | Summary | 14 | 1.7.2.7.4 | 1.7.2.7.4 |  | 343 | p | 19 | -6% | 362
177 | 6260 | nYwGXpoj6WqcdUPfZoTk | Summary | 14 | 1.7.2.7.5 | 1.7.2.7.5 |  | 343 | p | 19 | -6% | 362
178 | 6317 | NzqiT3qChWGoVO5Oxj9C | Summary | 111 | 1.9.4 | 1.9.4 |  | 929 | p | 169 | -18% | 1098
179 | 5355 | lohINUHwZqjP23W1PYQO | Summary | 26 | 1.9.4.1 | 1.9.4.1 |  | 887 | p | 23 | -3% | 910
180 | 5358 | Tenn83cNUrlWZNLgXJG2 | Normal | 2 | 1.9.4.1.2 | 1.9.4.1.2 |  | 382 | p | 2 | -1% | 384
181 | 5359 | VhUQP0fhGYyFZ67e4nln | Normal | 2 | 1.9.4.1.3 | 1.9.4.1.3 |  | 382 | p | 2 | -1% | 384
182 | 7262 | dH18W6KApKWC8TAOWb50 | Normal | 36 | 1.7.4.1.4 | 1.7.4.1.4 |  | 0 | p | 39 |  | 39
183 | 5362 | 4bsxfawvV6TKTvCq9VoB | Summary | 6 | 1.9.4.2 | 1.9.4.2 |  | 893 | p | 111 | -12% | 1004
184 | 5375 | zkXPpJkHw8DPAtspwcmA | Summary | 124 | 1.9.4.4 | 1.9.4.4 |  | 357 | p | 254 | -71% | 611
185 | 5377 | Wv5w7NMYDRM71nE6dVi0 | Summary | 58 | 1.9.4.5 | 1.9.4.5 |  | 112 | p | 5 | -4% | 117
186 | 5379 | 7aIIakNe0KPRF0TCK1un | Normal | 2 | 1.9.4.5.2 | 1.9.4.5.2 |  | 76 | p | 2 | -3% | 78
187 | 5381 | HgkAkSCruVdxdZyXC7sW | Normal | 4 | 1.9.4.5.4 | 1.9.4.5.4 |  | 15 | p | 4 | -27% | 19
188 | 5387 | 9gTKo9vjb1rQAbWcTOOW | Summary | 58 | 1.9.4.6 | 1.9.4.6 |  | 112 | p | 3 | -3% | 115
189 | 5389 | 0FrUudkzBjpolAMz4tT0 | Normal | 2 | 1.9.4.6.2 | 1.9.4.6.2 |  | 76 | p | 2 | -3% | 78
190 | 5391 | rUGJjnqPCImSizDtYOdy | Normal | 4 | 1.9.4.6.4 | 1.9.4.6.4 |  | 15 | p | 4 | -27% | 19
191 | 6688 | aKOlgm9Tw9oPXF0YCFLp | Summary | 911 | 1.11 | 1.11 |  | 1962 | q | -301 | (-15%) | 1661
192 | 7551 | G4afE8kOleATkD8qyqeP | Normal | 1 | 1.10.19 | 1.10.19 |  | 0 | p | 1 |  | 1
193 | 7131 | XTX9Wl5SzTxAD1rtsh9U | Summary | 0 | 1.10 | 1.10 |  | 808 | p | 1824 | -226% | 2632

## Remaining-Duration
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Remaining Duration - 780 (37%) | Remaining Duration - 780 (37%) | Remaining Duration - 780 (37%) | Remaining Duration - 780 (37%) | Remaining Duration - 780 (37%) | Remaining Duration - 780 (37%) | Remaining Duration - 780 (37%) | Remaining Duration - 780 (37%) | Remaining Duration - 780 (37%) | Remaining Duration - 780 (37%) | Remaining Duration - 780 (37%) | Remaining Duration - 780 (37%) | Remaining Duration - 780 (37%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 1249 | v1zgYyoO7UpynPZXt29g | Summary | 611 | 1 | 1 |  | 611 | p | 79 | -13% | 690
2 | 147 | DEZpxiHWY7fkyvQEaEGc | Summary | 1132 | 1.2 | 1.2 |  | 1132 | p | 69 | -6% | 1201
3 | 158 | D5C8AUNeoI4YKF3PggKx | Summary | 255 | 1.2.7 | 1.2.7 |  | 255 | p | 176 | -69% | 431
4 | 6636 | 3J1qFTgnrSSZVnoYdTv5 | Summary | 140 | 1.2.7.3 | 1.2.7.3 |  | 140 | p | 6 | -4% | 146
5 | 6338 | whnkqeDzsaW1H7xphaZA | Normal | 49 | 1.2.7.3.4 | 1.2.7.3.4 |  | 49 | p | 3 | -6% | 52
6 | 6673 | sIWmvaXMX3ZF9ctRNm7s | Normal | 34 | 1.2.7.3.3 | 1.2.7.3.3 |  | 34 | q | -1 | (-3%) | 33
7 | 160 | gFTVv5U5XORyz5ZEYbdN | Summary | 703 | 1.2.8 | 1.2.8 |  | 703 | q | -1 | 0% | 702
8 | 172 | EY5PMcgR4N5ReAIF6NHn | Summary | 582 | 1.2.9 | 1.2.9 |  | 582 | p | 22 | -4% | 604
9 | 179 | jSOjvYE1qiHOKdcV2ixu | Summary | 554 | 1.2.10 | 1.2.10 |  | 554 | p | 43 | -8% | 597
10 | 195 | jWoM7YMyhsN7uWtVDNIl | Summary | 276 | 1.2.11 | 1.2.11 |  | 276 | p | 596 | -216% | 872
11 | 4180 | LxVAz76PSOUu8y7B8sy3 | Summary | 218 | 1.3 | 1.3 |  | 218 | p | 2 | -1% | 220
12 | 384 | GE3w1SHplCQZN7aYDVw8 | Summary | 34 | 1.3.3 | 1.3.3 |  | 34 | p | 1 | -3% | 35
13 | 429 | Pbs0MxOqvHazWgB8fpDs | Summary | 41 | 1.3.3.2 | 1.3.3.2 |  | 41 | p | 2 | -5% | 43
14 | 436 | OGXVzK31PKUn8DxCdn94 | Normal | 33 | 1.3.3.2.10 | 1.3.3.2.10 |  | 33 | p | 1 | -3% | 34
15 | 437 | kEyeaq7ebxWRSvBqGkHC | Summary | 19 | 1.3.3.1 | 1.3.3.1 |  | 19 | p | 1 | -5% | 20
16 | 438 | QjVW4dYK4boDcUrG7MUx | Summary | 23 | 1.3.3.1.2 | 1.3.3.1.2 |  | 23 | p | 2 | -9% | 25
17 | 445 | cIIfBfMFMZUbJxswwNzj | Summary | 28 | 1.3.3.1.2.4 | 1.3.3.1.2.4 |  | 28 | p | 2 | -7% | 30
18 | 5768 | 9l9o7D6Il8vKVgGgZRMW | Summary | 197 | 1.3.3.4 | 1.3.3.4 |  | 197 | q | -1 | (-1%) | 196
19 | 6289 | NknbxY1EWobhbJ98SVRq | Summary | 270 | 1.3.2 | 1.3.2 |  | 270 | p | 2 | -1% | 272
20 | 3848 | g0gBmZeXCCPZTY4kkYs8 | Summary | 210 | 1.3.2.1 | 1.3.2.1 |  | 210 | p | 8 | -4% | 218
21 | 3849 | PKYN5IsyqbTocjyswPFM | Normal | 17 | 1.3.2.1.1 | 1.3.2.1.1 |  | 17 | q | -4 | (-24%) | 13
22 | 3850 | sk2pEdmn2KeVBRyrQzgn | Summary | 233 | 1.3.2.1.2 | 1.3.2.1.2 |  | 233 | p | 11 | -5% | 244
23 | 3857 | FObPKa3HJ5KI4gFmAx2r | Summary | 210 | 1.3.2.1.2.2 | 1.3.2.1.2.2 |  | 210 | p | 27 | -13% | 237
24 | 3858 | pWvg9Owxac1jXAINT5hs | Normal | 24 | 1.3.2.1.2.2.1 | 1.3.2.1.2.2.1 |  | 24 | q | -5 | (-21%) | 19
25 | 3859 | xrpLG6wlwOL4sRwHPU5B | Normal | 28 | 1.3.2.1.2.2.2 | 1.3.2.1.2.2.2 |  | 28 | p | 1 | -4% | 29
26 | 3861 | rvfyADOJtzNcPT3VL85f | Normal | 100 | 1.3.2.1.2.2.3 | 1.3.2.1.2.2.3 |  | 100 | p | 21 | -21% | 121
27 | 3862 | FUtleP4nAJHYxzLOWKZH | Normal | 20 | 1.3.2.1.2.2.4 | 1.3.2.1.2.2.4 |  | 20 | q | -1 | (-5%) | 19
28 | 3863 | WaF24jcpD2qzV3M05hSl | Summary | 178 | 1.3.2.1.2.3 | 1.3.2.1.2.3 |  | 178 | p | 1 | -1% | 179
29 | 3864 | kkmwKYrSq6DehQmbGkxo | Summary | 90 | 1.3.2.1.2.3.2 | 1.3.2.1.2.3.2 |  | 90 | q | -3 | (-3%) | 87
30 | 3865 | ZK3GDclfde20Vh8DU71K | Normal | 30 | 1.3.2.1.2.3.2.1 | 1.3.2.1.2.3.2.1 |  | 30 | p | 2 | -7% | 32
31 | 3866 | 8Zrc7ItBhrTjO1TWxqmf | Normal | 20 | 1.3.2.1.2.3.2.2 | 1.3.2.1.2.3.2.2 |  | 20 | q | -4 | (-20%) | 16
32 | 3868 | NCkZSbtMfUxIg95lxXXn | Normal | 10 | 1.3.2.1.2.3.2.6 | 1.3.2.1.2.3.2.6 |  | 10 | q | -1 | (-10%) | 9
33 | 6563 | 7FPcbor42GN7O6Ym4IZM | Normal | 10 | 1.3.2.1.2.3.2.4 | 1.3.2.1.2.3.2.4 |  | 10 | p | 1 | -10% | 11
34 | 7186 | ttl1FahPn0WwOuyGdmk6 | Summary | 138 | 1.3.2.3 | 1.3.2.3 |  | 138 | p | 3 | -2% | 141
35 | 7188 | yn5QOVI2BZ7jor10JaQN | Summary | 55 | 1.3.2.3.2 | 1.3.2.3.2 |  | 55 | q | -3 | (-5%) | 52
36 | 7189 | jup7puBG1dNvbV8jB14f | Summary | 69 | 1.3.2.3.2.1 | 1.3.2.3.2.1 |  | 69 | q | -8 | (-12%) | 61
37 | 7190 | Ob13piboJI4zFNOVPzZD | Summary | 50 | 1.3.2.3.2.1.1 | 1.3.2.3.2.1.1 |  | 50 | q | -12 | (-24%) | 38
38 | 7192 | rcBSOCAYFUxP7jsyoqGw | Normal | 11 | 1.3.2.3.2.1.1.2 | 1.3.2.3.2.1.1.2 |  | 11 | q | -2 | (-18%) | 9
39 | 7193 | hzdeRXxytBFeNJPq5eHn | Summary | 50 | 1.3.2.3.2.1.2 | 1.3.2.3.2.1.2 |  | 50 | q | -18 | (-36%) | 32
40 | 7194 | mB0uoGZ1D1fuFzk350Kb | Normal | 30 | 1.3.2.3.2.1.2.1 | 1.3.2.3.2.1.2.1 |  | 30 | q | -7 | (-23%) | 23
41 | 7196 | fFBpC2vR2qp5KXHLtypR | Summary | 23 | 1.3.2.3.2.1.3 | 1.3.2.3.2.1.3 |  | 23 | p | 5 | -22% | 28
42 | 7205 | 688LmElxek6WZQ34zEgD | Summary | 40 | 1.3.2.3.2.2 | 1.3.2.3.2.2 |  | 40 | p | 8 | -20% | 48
43 | 7206 | bMXBNIC1fF7AjliDPdfr | Normal | 25 | 1.3.2.3.2.2.1 | 1.3.2.3.2.2.1 |  | 25 | q | -1 | (-4%) | 24
44 | 7207 | 51ZGrscW6XrNzeOMbLyw | Normal | 5 | 1.3.2.3.2.2.2 | 1.3.2.3.2.2.2 |  | 5 | q | -1 | (-20%) | 4
45 | 7210 | 5vpOUfvEpSU2AKPwltv0 | Summary | 14 | 1.3.2.3.2.3 | 1.3.2.3.2.3 |  | 14 | q | -7 | (-50%) | 7
46 | 7211 | wSDYMNBcPlclxMN6Hc8V | Normal | 5 | 1.3.2.3.2.3.1 | 1.3.2.3.2.3.1 |  | 5 | q | -5 | (-100%) | 0
47 | 7212 | IA5BwO4PzPuXs5yI3XzH | Normal | 5 | 1.3.2.3.2.3.2 | 1.3.2.3.2.3.2 |  | 5 | q | -2 | (-40%) | 3
48 | 7215 | a8OJFGtOVEyM75c9puYK | Summary | 34 | 1.3.2.3.2.4 | 1.3.2.3.2.4 |  | 34 | p | 4 | -12% | 38
49 | 7218 | 5fSpBiSdaCD1mvMsYs0j | Normal | 2 | 1.3.2.3.2.4.3 | 1.3.2.3.2.4.3 |  | 2 | q | -2 | (-100%) | 0
50 | 7219 | tMHxEODKuKminmE9Mjg5 | Normal | 1 | 1.3.2.3.2.4.4 | 1.3.2.3.2.4.4 |  | 1 | q | -1 | (-100%) | 0
51 | 7220 | nvywSXdnd0LSUGSiB3or | Normal | 10 | 1.3.2.3.2.4.5 | 1.3.2.3.2.4.5 |  | 10 | p | 2 | -20% | 12
52 | 7221 | PYoR7OoHLcblZDJJ1hTC | Normal | 20 | 1.3.2.3.2.4.6 | 1.3.2.3.2.4.6 |  | 20 | p | 5 | -25% | 25
53 | 7223 | 2cLCJpvBPh4ccgbvKrEi | Summary | 38 | 1.3.2.3.2.5 | 1.3.2.3.2.5 |  | 38 | p | 8 | -21% | 46
54 | 7226 | fsyu9CvTMAXTCK7e04ez | Normal | 1 | 1.3.2.3.2.5.3 | 1.3.2.3.2.5.3 |  | 1 | q | -1 | (-100%) | 0
55 | 7227 | QiFvht1v2EB9ODLdNK6M | Normal | 25 | 1.3.2.3.2.5.4 | 1.3.2.3.2.5.4 |  | 25 | p | 6 | -24% | 31
56 | 7228 | SSqxRWtJ8NkhLwkx3Zp5 | Normal | 15 | 1.3.2.3.2.5.5 | 1.3.2.3.2.5.5 |  | 15 | p | 2 | -13% | 17
57 | 7514 | 4jhJaLUHxegkfPxUyChC | Normal | 15 | 1.3.2.3.2.5.9 | 1.3.2.3.2.5.9 |  | 15 | q | -1 | (-7%) | 14
58 | 7515 | jdxLrBmn54gbF5MbPNVU | Normal | 5 | 1.3.2.3.2.5.8 | 1.3.2.3.2.5.8 |  | 5 | q | -5 | (-100%) | 0
59 | 7236 | OqdHv6QLhEyFdmarh5Mg | Normal | 5 | 1.3.2.3.3.1.4 | 1.3.2.3.3.1.4 |  | 5 | p | 1 | -20% | 6
60 | 7237 | xLl9f1S8pVLgozw4LZw4 | Normal | 10 | 1.3.2.3.3.1.5 | 1.3.2.3.3.1.5 |  | 10 | q | -1 | (-10%) | 9
61 | 7243 | nppwsC1hz1MTRepHit5q | Normal | 3 | 1.3.2.3.3.2.3 | 1.3.2.3.3.2.3 |  | 3 | p | 1 | -33% | 4
62 | 7244 | FpvbIzqyAjmrguHRtjoA | Summary | 68 | 1.3.2.3.4 | 1.3.2.3.4 |  | 68 | p | 3 | -4% | 71
63 | 7245 | ysJ2Wz17vAaH50NFOd3r | Normal | 2 | 1.3.2.3.4.1 | 1.3.2.3.4.1 |  | 2 | p | 1 | -50% | 3
64 | 7246 | w8OYvCOBO1azAOar59yv | Normal | 3 | 1.3.2.3.4.2 | 1.3.2.3.4.2 |  | 3 | q | -1 | (-33%) | 2
65 | 7248 | nqyBToLUXvLl91VDFcK9 | Summary | 20 | 1.3.2.3.4.4 | 1.3.2.3.4.4 |  | 20 | p | 2 | -10% | 22
66 | 7250 | G5mdz8DmOa8TGNlmxmOk | Normal | 20 | 1.3.2.3.4.4.2 | 1.3.2.3.4.4.2 |  | 20 | p | 2 | -10% | 22
67 | 7251 | p2IEwFFq1YxDgQwaqReT | Summary | 48 | 1.3.2.3.4.5 | 1.3.2.3.4.5 |  | 48 | p | 1 | -2% | 49
68 | 7252 | R4hlQqYwslHcXudIUORM | Normal | 20 | 1.3.2.3.4.5.1 | 1.3.2.3.4.5.1 |  | 20 | p | 2 | -10% | 22
69 | 7257 | EmkT3sq6aGy3vx96JSsX | Normal | 3 | 1.3.2.3.4.5.6 | 1.3.2.3.4.5.6 |  | 3 | q | -1 | (-33%) | 2
70 | 6269 | tUCxonMalaI13D6hsUSU | Summary | 99 | 1.5 | 1.5 |  | 99 | p | 3 | -3% | 102
71 | 605 | HP2TrbmUH5Qc4V2P2k1T | Normal | 14 | 1.5.6.1 | 1.5.6.1 |  | 14 | p | 3 | -21% | 17
72 | 620 | q8advjPa5PEndSFXJ05j | Summary | 158 | 1.5.6.6 | 1.5.6.6 |  | 158 | p | 3 | -2% | 161
73 | 622 | Q48N5ZSDLesB1Bsda2wx | Summary | 156 | 1.5.6.6.2 | 1.5.6.6.2 |  | 156 | p | 1 | -1% | 157
74 | 631 | jjFU6HpNq2otAi9zmRWR | Normal | 2 | 1.5.6.6.2.7 | 1.5.6.6.2.7 |  | 2 | q | -2 | (-100%) | 0
75 | 633 | FgJ5XjjThZN85XQOJ0nJ | Normal | 21 | 1.5.6.6.2.10 | 1.5.6.6.2.10 |  | 21 | q | -1 | (-5%) | 20
76 | 635 | ztvy5zkS4z9HirKgvHGY | Normal | 20 | 1.5.6.6.2.11 | 1.5.6.6.2.11 |  | 20 | q | -2 | (-10%) | 18
77 | 636 | ZpIfqMwIaczq2BqznW2q | Normal | 6 | 1.5.6.6.2.12 | 1.5.6.6.2.12 |  | 6 | p | 2 | -33% | 8
78 | 640 | 10AmMHkCz4b8n0xqbyCt | Normal | 5 | 1.5.6.6.2.16 | 1.5.6.6.2.16 |  | 5 | q | -1 | (-20%) | 4
79 | 641 | KUqcSNVxncHPLVJNV5ca | Normal | 2 | 1.5.6.6.2.17 | 1.5.6.6.2.17 |  | 2 | q | -1 | (-50%) | 1
80 | 646 | Haue3rYYySw3jbXWnBeq | Normal | 3 | 1.5.6.6.3 | 1.5.6.6.3 |  | 3 | p | 1 | -33% | 4
81 | 648 | 6WPgljRre9DjhHGVsVUH | Summary | 120 | 1.5.6.6.5 | 1.5.6.6.5 |  | 120 | p | 8 | -7% | 128
82 | 657 | nePaKBbqDo6OltylvukE | Summary | 14 | 1.5.6.6.5.4 | 1.5.6.6.5.4 |  | 14 | q | -1 | (-7%) | 13
83 | 658 | PyBKEPMZMe2YeOC66yut | Normal | 11 | 1.5.6.6.5.4.1 | 1.5.6.6.5.4.1 |  | 11 | q | -1 | (-9%) | 10
84 | 666 | OcAHNnZWZgiwxfUiheGU | Normal | 5 | 1.5.6.6.5.6 | 1.5.6.6.5.6 |  | 5 | q | -1 | (-20%) | 4
85 | 667 | HPj21Hyun1nWvxJOQMhf | Normal | 28 | 1.5.6.6.5.7 | 1.5.6.6.5.7 |  | 28 | p | 3 | -11% | 31
86 | 670 | zBtIFoyMK1KgXAv407C9 | Summary | 29 | 1.5.6.5 | 1.5.6.5 |  | 29 | q | -13 | (-45%) | 16
87 | 6141 | PCEOtJROHHMKXYkoR4rp | Normal | 3 | 1.5.6.5.1 | 1.5.6.5.1 |  | 3 | q | -3 | (-100%) | 0
88 | 6281 | RYPcKAyzQapOQ3GupQll | Summary | 104 | 1.5.5 | 1.5.5 |  | 104 | p | 6 | -6% | 110
89 | 1466 | LmBGiI2jXQ3lZF0l79sj | Summary | 104 | 1.5.5.1 | 1.5.5.1 |  | 104 | p | 6 | -6% | 110
90 | 1457 | W1XQ7yoZAeSgm7UftoXN | Normal | 1 | 1.5.5.1.2 | 1.5.5.1.2 |  | 1 | q | -1 | (-100%) | 0
91 | 1471 | FsiT4ZMTOq9hGqZQQdYf | Normal | 11 | 1.5.5.1.9 | 1.5.5.1.9 |  | 11 | p | 3 | -27% | 14
92 | 1472 | KG0YDAdikr58WjA79FVb | Normal | 9 | 1.5.5.1.10 | 1.5.5.1.10 |  | 9 | q | -1 | (-11%) | 8
93 | 6292 | 1Cm9NXihvfL2WEnYcHvT | Summary | 42 | 1.5.4 | 1.5.4 |  | 42 | p | 6 | -14% | 48
94 | 3944 | HRTLaCTjRjqysGxmE6ve | Normal | 36 | 1.5.4.2 | 1.5.4.2 |  | 36 | p | 2 | -6% | 38
95 | 3949 | knRWxUZkgPmXKgij09tb | Summary | 25 | 1.5.4.5 | 1.5.4.5 |  | 25 | p | 6 | -24% | 31
96 | 3950 | NJx1RMKdqhuNKRLGMSBQ | Summary | 27 | 1.5.4.5.1 | 1.5.4.5.1 |  | 27 | p | 4 | -15% | 31
97 | 3951 | BNWJw3sHADBJTHA2Ybu0 | Normal | 16 | 1.5.4.5.1.1 | 1.5.4.5.1.1 |  | 16 | p | 1 | -6% | 17
98 | 3964 | ZzcX1hV2BTbfmTYJl5AE | Summary | 19 | 1.5.4.5.4 | 1.5.4.5.4 |  | 19 | p | 7 | -37% | 26
99 | 3967 | BaECEBO5p44IeRhOgeK2 | Normal | 19 | 1.5.4.5.4.3 | 1.5.4.5.4.3 |  | 19 | p | 6 | -32% | 25
100 | 5996 | M6DLFbZyZKXroBVfXncj | Summary | 19 | 1.5.4.4 | 1.5.4.4 |  | 19 | p | 1 | -5% | 20
101 | 3948 | 6ze4BjeYc1B5uifD0Fqa | Normal | 10 | 1.5.4.4.9 | 1.5.4.4.9 |  | 10 | q | -1 | (-10%) | 9
102 | 6605 | Qtljmhuq3GHp8HrV3pPP | Normal | 6 | 1.5.4.4.7 | 1.5.4.4.7 |  | 6 | p | 1 | -17% | 7
103 | 6299 | JvNaxkj9UdrgV7BcBski | Summary | 134 | 1.5.1 | 1.5.1 |  | 134 | p | 9 | -7% | 143
104 | 4213 | pNBoUl9px0n4wFhfXXqQ | Summary | 90 | 1.5.1.1 | 1.5.1.1 |  | 90 | p | 5 | -6% | 95
105 | 6444 | XymP4MvJgra2aDdoc9vw | Normal | 46 | 1.5.1.1.2 | 1.5.1.1.2 |  | 46 | q | -7 | (-15%) | 39
106 | 6445 | Wo6GLLiu9tXQyZ8t43hX | Normal | 43 | 1.5.1.1.3 | 1.5.1.1.3 |  | 43 | p | 9 | -21% | 52
107 | 6674 | 3EUoGYyEaAia67bx8maJ | Summary | 69 | 1.5.1.3 | 1.5.1.3 |  | 69 | p | 4 | -6% | 73
108 | 6680 | ttlvn3uwilh7nqgbHtE7 | Normal | 37 | 1.5.1.3.7 | 1.5.1.3.7 |  | 37 | p | 2 | -5% | 39
109 | 6681 | NHiN8b86HRxpkLb9JGGD | Normal | 10 | 1.5.1.3.9 | 1.5.1.3.9 |  | 10 | p | 2 | -20% | 12
110 | 6308 | 9d1kbrq4aHbr7FOmo76u | Summary | 27 | 1.5.2 | 1.5.2 |  | 27 | p | 6 | -22% | 33
111 | 5611 | e3AOkT5PZcArPsKmcVqB | Summary | 48 | 1.5.2.2 | 1.5.2.2 |  | 48 | p | 10 | -21% | 58
112 | 5614 | COTl0owSvMhEdF9iuXCz | Normal | 0 | 1.5.2.2.10.2 | 1.5.2.2.10.2 |  | 0 | p | 1 |  | 1
113 | 5627 | s0vjJX7zGlVyBdE0eigo | Summary | 15 | 1.5.2.2.8 | 1.5.2.2.8 |  | 15 | q | -6 | (-40%) | 9
114 | 5629 | ghMhRqrbgVxCQv51dU2T | Normal | 0 | 1.5.2.2.8.2 | 1.5.2.2.8.2 |  | 0 | p | 1 |  | 1
115 | 5633 | 2UPBwQymcCOUpuUjnBTe | Normal | 3 | 1.5.2.2.8.6 | 1.5.2.2.8.6 |  | 3 | q | -1 | (-33%) | 2
116 | 7545 | 65jUkOPqlMfpoMROhJ4O | Normal | 5 | 1.5.3.2.9.1 | 1.5.3.2.9.1 |  | 5 | q | -5 | (-100%) | 0
117 | 5635 | ZYzv9KOmVdYL2d3ZPb8b | Summary | 0 | 1.5.2.2.9 | 1.5.2.2.9 |  | 0 | p | 18 |  | 18
118 | 5638 | jBSFjjY1RfmWgqa8tOlO | Normal | 0 | 1.5.2.2.9.3 | 1.5.2.2.9.3 |  | 0 | p | 12 |  | 12
119 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | 0 | p | 5 |  | 5
120 | 5641 | QjWOhv4eRSTZWx0ATAUl | Normal | 23 | 1.5.2.2.11 | 1.5.2.2.11 |  | 23 | q | -3 | (-13%) | 20
121 | 6309 | taNk8S9bKnlDToaFycS6 | Summary | 37 | 1.5.3 | 1.5.3 |  | 37 | q | -1 | (-3%) | 36
122 | 5443 | L0xk8h495fvdhlwnri8N | Summary | 37 | 1.5.3.1 | 1.5.3.1 |  | 37 | q | -1 | (-3%) | 36
123 | 5445 | 95pLIsxhFDdrMJGVBrpQ | Summary | 35 | 1.5.3.1.2 | 1.5.3.1.2 |  | 35 | p | 15 | -43% | 50
124 | 5447 | ijJ4zfbEfOInLYX7Vu9Z | Normal | 6 | 1.5.3.1.2.2 | 1.5.3.1.2.2 |  | 6 | q | -1 | (-17%) | 5
125 | 5449 | 6It4K5O7iZJhLoLO2jyi | Normal | 6 | 1.5.3.1.2.4 | 1.5.3.1.2.4 |  | 6 | q | -1 | (-17%) | 5
126 | 7381 | Ao7wteklS85dOuCCMM3I | Normal | 124 | 1.5.1 | 1.5.1 |  | 124 | q | -13 | (-10%) | 111
127 | 6270 | Wwp4MRWhcV55WleZhe1f | Summary | 288 | 1.4 | 1.4 |  | 288 | p | 16 | -6% | 304
128 | 6290 | VuOK0YK760zOpXaJ9U7h | Summary | 140 | 1.4.3 | 1.4.3 |  | 140 | p | 18 | -13% | 158
129 | 4537 | FhESv2GOKRYErv6rS2Ko | Summary | 140 | 1.4.3.1 | 1.4.3.1 |  | 140 | p | 18 | -13% | 158
130 | 4536 | zU98x2LHVd7UXovDFMXu | Normal | 14 | 1.4.3.1.1 | 1.4.3.1.1 |  | 14 | p | 3 | -21% | 17
131 | 5854 | 2kqOvhRPajU4Q0ZPsUnx | Normal | 8 | 1.4.3.1.4 | 1.4.3.1.4 |  | 8 | p | 1 | -12% | 9
132 | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Normal | 49 | 1.4.3.1.5 | 1.4.3.1.5 |  | 49 | p | 8 | -16% | 57
133 | 6291 | 7X6NK9qir9GRz5m7bXmK | Summary | 297 | 1.4.1 | 1.4.1 |  | 297 | p | 13 | -4% | 310
134 | 3891 | VQVEpj4HfOnKALplb4t9 | Summary | 43 | 1.4.1.1 | 1.4.1.1 |  | 43 | q | -2 | (-5%) | 41
135 | 3897 | cqWsQsQWdy7etYVMNQBf | Summary | 53 | 1.4.1.1.2 | 1.4.1.1.2 |  | 53 | q | -2 | (-4%) | 51
136 | 3900 | fYbjIfZDvkbYu7p7dq3N | Normal | 14 | 1.4.1.1.2.3 | 1.4.1.1.2.3 |  | 14 | q | -2 | (-14%) | 12
137 | 3902 | FL4HGNxujC5zK4lN6AVO | Summary | 30 | 1.4.1.2 | 1.4.1.2 |  | 30 | q | -1 | (-3%) | 29
138 | 3903 | e0nMZ5CLCmjCURLrKpol | Summary | 30 | 1.4.1.2.1 | 1.4.1.2.1 |  | 30 | q | -1 | (-3%) | 29
139 | 3907 | pFYLZycbgH4KMn6pLhBU | Summary | 272 | 1.4.1.3 | 1.4.1.3 |  | 272 | p | 71 | -26% | 343
140 | 3910 | pNRX5rV0uvvHnR27z1AO | Normal | 8 | 1.4.1.3.3 | 1.4.1.3.3 |  | 8 | q | -1 | (-12%) | 7
141 | 3911 | R3AK39H17lCC16PE9DkR | Normal | 10 | 1.4.1.3.4 | 1.4.1.3.4 |  | 10 | q | -2 | (-20%) | 8
142 | 3912 | BSEXS69UjCPQ6j2zF47p | Normal | 15 | 1.4.1.3.5 | 1.4.1.3.5 |  | 15 | q | -2 | (-13%) | 13
143 | 3913 | nUmJBAacPI2xORV8OCED | Normal | 20 | 1.4.1.3.6 | 1.4.1.3.6 |  | 20 | p | 3 | -15% | 23
144 | 3914 | e7efPn2W4IFyilt2hNai | Normal | 30 | 1.4.1.3.7 | 1.4.1.3.7 |  | 30 | q | -5 | (-17%) | 25
145 | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Normal | 5 | 1.4.1.3.8 | 1.4.1.3.8 |  | 5 | p | 1 | -20% | 6
146 | 3917 | hmttcJptV92JIo4OpANW | Normal | 5 | 1.4.1.3.10 | 1.4.1.3.10 |  | 5 | p | 1 | -20% | 6
147 | 3922 | yD55zWPn8USsNa4i8nCC | Normal | 5 | 1.4.1.4.4 | 1.4.1.4.4 |  | 5 | p | 2 | -40% | 7
148 | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Normal | 15 | 1.4.1.4.5 | 1.4.1.4.5 |  | 15 | p | 7 | -47% | 22
149 | 3924 | N1CigBiMQE2J41ZAMkt0 | Normal | 20 | 1.4.1.4.6 | 1.4.1.4.6 |  | 20 | p | 2 | -10% | 22
150 | 3925 | hSr4t1vn7GiB6Kp7YK0M | Normal | 5 | 1.4.1.4.7 | 1.4.1.4.7 |  | 5 | q | -1 | (-20%) | 4
151 | 3926 | vGJMK6sejFbKR6Gom2up | Normal | 5 | 1.4.1.4.8 | 1.4.1.4.8 |  | 5 | p | 2 | -40% | 7
152 | 3927 | 3RLmiC17tI4E2ggNuRe0 | Normal | 5 | 1.4.1.4.9 | 1.4.1.4.9 |  | 5 | p | 1 | -20% | 6
153 | 6318 | cM5VCGnPiK1mfNJo8YLF | Summary | 309 | 1.4.2 | 1.4.2 |  | 309 | p | 11 | -4% | 320
154 | 5213 | 6YmlQVHNVjUNryBHQf8a | Summary | 61 | 1.4.2.2.3 | 1.4.2.2.3 |  | 61 | q | -4 | (-7%) | 57
155 | 5215 | KawuX1icbWQB8WlKVKy9 | Normal | 60 | 1.4.2.2.3.2 | 1.4.2.2.3.2 |  | 60 | q | -5 | (-8%) | 55
156 | 5217 | e116DivbRDCkLiH2zNhl | Summary | 61 | 1.4.2.2.4 | 1.4.2.2.4 |  | 61 | p | 2 | -3% | 63
157 | 5219 | Uz3hspiJXkYJElXZ00I5 | Normal | 60 | 1.4.2.2.4.2 | 1.4.2.2.4.2 |  | 60 | p | 2 | -3% | 62
158 | 5221 | iTaWceiQKMF6gUaF3DCB | Summary | 61 | 1.4.2.2.5 | 1.4.2.2.5 |  | 61 | q | -1 | (-2%) | 60
159 | 5223 | 3nEJb4lsc7akFmF6ULw7 | Normal | 60 | 1.4.2.2.5.2 | 1.4.2.2.5.2 |  | 60 | q | -1 | (-2%) | 59
160 | 5277 | TgmqG1sR4A60sNmMtPcE | Summary | 193 | 1.4.2.2.7 | 1.4.2.2.7 |  | 193 | p | 11 | -6% | 204
161 | 5278 | OmCdw3tKtVsW24V2aNqQ | Normal | 8 | 1.4.2.2.7.1 | 1.4.2.2.7.1 |  | 8 | p | 2 | -25% | 10
162 | 5279 | htHZ3VhuaadgfKg1VQls | Summary | 47 | 1.4.2.2.7.11 | 1.4.2.2.7.11 |  | 47 | p | 10 | -21% | 57
163 | 5282 | qBzS7vPbhPVzs7sVXgmM | Normal | 5 | 1.4.2.2.7.11.3 | 1.4.2.2.7.11.3 |  | 5 | q | -2 | (-40%) | 3
164 | 5283 | fU0pzeQGz2MN3lZmznFh | Normal | 5 | 1.4.2.2.7.11.4 | 1.4.2.2.7.11.4 |  | 5 | p | 1 | -20% | 6
165 | 5285 | ffNcVsnPBySsZbQiEShc | Normal | 10 | 1.4.2.2.7.11.6 | 1.4.2.2.7.11.6 |  | 10 | p | 1 | -10% | 11
166 | 6457 | PFYaNHtSBj97Eh5ysTvH | Normal | 7 | 1.4.2.2.7.2 | 1.4.2.2.7.2 |  | 7 | q | -2 | (-29%) | 5
167 | 6459 | ylmwXTiOnCLJpwlHTaRg | Normal | 10 | 1.4.2.2.7.4 | 1.4.2.2.7.4 |  | 10 | p | 2 | -20% | 12
168 | 6461 | 7ypQo0ZyAHzCHmFRlywg | Normal | 10 | 1.4.2.2.7.6 | 1.4.2.2.7.6 |  | 10 | p | 2 | -20% | 12
169 | 6464 | McSTYqZ3LCfaYSSmZoTn | Normal | 7 | 1.4.2.2.7.9 | 1.4.2.2.7.9 |  | 7 | q | -1 | (-14%) | 6
170 | 5226 | R9JO9mOSGmg0eoDimoJT | Summary | 71 | 1.4.2.1 | 1.4.2.1 |  | 71 | p | 4 | -6% | 75
171 | 5240 | NSmZbDTp76mGzDSQ7Ceh | Summary | 56 | 1.4.2.1.3 | 1.4.2.1.3 |  | 56 | p | 144 | -257% | 200
172 | 5241 | v6EKIZLcnDHW8CXOrD7y | Normal | 21 | 1.4.2.1.3.1 | 1.4.2.1.3.1 |  | 21 | q | -1 | (-5%) | 20
173 | 5242 | JYCfpao49G3jD8M94S66 | Normal | 10 | 1.4.2.1.3.2 | 1.4.2.1.3.2 |  | 10 | p | 1 | -10% | 11
174 | 5244 | Nwqnc6xsOuQ8oMDbKNfv | Normal | 15 | 1.4.2.1.3.4 | 1.4.2.1.3.4 |  | 15 | p | 1 | -7% | 16
175 | 5262 | PI0DE6xTKT4gLnHpqgjE | Summary | 137 | 1.4.2.1.6 | 1.4.2.1.6 |  | 137 | p | 2 | -1% | 139
176 | 5263 | URhzXaXmWu6rBPIMitrn | Normal | 30 | 1.4.2.1.6.1 | 1.4.2.1.6.1 |  | 30 | p | 1 | -3% | 31
177 | 5265 | ATYnDTN93dB3aTXfzslo | Normal | 6 | 1.4.2.1.6.2 | 1.4.2.1.6.2 |  | 6 | q | -1 | (-17%) | 5
178 | 5266 | G5H4IlBy3M3Zxs38gcIH | Normal | 10 | 1.4.2.1.6.3 | 1.4.2.1.6.3 |  | 10 | p | 1 | -10% | 11
179 | 5267 | 3RI5G3ymKjaLn96cfboa | Normal | 11 | 1.4.2.1.6.4 | 1.4.2.1.6.4 |  | 11 | p | 2 | -18% | 13
180 | 5268 | fG9nayiE82fFlNFtuyfN | Normal | 8 | 1.4.2.1.6.5 | 1.4.2.1.6.5 |  | 8 | p | 9 | -112% | 17
181 | 5269 | UP8sWsDXCDMiwOqWz3ib | Normal | 5 | 1.4.2.1.6.6 | 1.4.2.1.6.6 |  | 5 | p | 1 | -20% | 6
182 | 5270 | 0UA65kBzwzHULCayr1Gq | Normal | 8 | 1.4.2.1.6.7 | 1.4.2.1.6.7 |  | 8 | q | -1 | (-12%) | 7
183 | 5271 | mtztJWmm2OBnfmSsuoGt | Normal | 10 | 1.4.2.1.6.8 | 1.4.2.1.6.8 |  | 10 | p | 1 | -10% | 11
184 | 5272 | kvS9pO69DNwaLvofAQcb | Normal | 11 | 1.4.2.1.6.9 | 1.4.2.1.6.9 |  | 11 | p | 5 | -45% | 16
185 | 5289 | tqKGxL2oceRufkd47wnf | Summary | 319 | 1.4.2.3 | 1.4.2.3 |  | 319 | p | 26 | -8% | 345
186 | 5313 | 3y8KKUl940HiJi7UFKFT | Summary | 106 | 1.4.2.3.3 | 1.4.2.3.3 |  | 106 | p | 4 | -4% | 110
187 | 5316 | LCfcLPfxTjnSY0dCrjlE | Normal | 10 | 1.4.2.3.3.2 | 1.4.2.3.3.2 |  | 10 | q | -1 | (-10%) | 9
188 | 5317 | pw6YyMXR7oeqsrtIHdqo | Normal | 9 | 1.4.2.3.3.3 | 1.4.2.3.3.3 |  | 9 | p | 1 | -11% | 10
189 | 5318 | KMG5hXAC4X2MZPfyVOSc | Normal | 5 | 1.4.2.3.3.8 | 1.4.2.3.3.8 |  | 5 | p | 1 | -20% | 6
190 | 5319 | mDGXCmTQB2ITo8MYwlYq | Normal | 5 | 1.4.2.3.3.9 | 1.4.2.3.3.9 |  | 5 | p | 1 | -20% | 6
191 | 5322 | oNpYocgOFdrRcJiQE0H5 | Normal | 5 | 1.4.2.3.3.12 | 1.4.2.3.3.12 |  | 5 | p | 1 | -20% | 6
192 | 5326 | esDa5lJIA5zg0nP58cRd | Summary | 32 | 1.4.2.3.4 | 1.4.2.3.4 |  | 32 | q | -3 | (-9%) | 29
193 | 5327 | iRZmxts3rKQ38tplQw52 | Normal | 30 | 1.4.2.3.4.1 | 1.4.2.3.4.1 |  | 30 | q | -3 | (-10%) | 27
194 | 6321 | KAyzIHlSkkFZqIIdJ9JD | Summary | 144 | 1.4.2.3.2 | 1.4.2.3.2 |  | 144 | q | -24 | (-17%) | 120
195 | 5298 | c4SSanbHhynqs8RkqT3I | Normal | 3 | 1.4.2.3.2.2 | 1.4.2.3.2.2 |  | 3 | p | 1 | -33% | 4
196 | 5299 | HB5wL9z8KlZFeAas0WUQ | Normal | 11 | 1.4.2.3.2.3 | 1.4.2.3.2.3 |  | 11 | q | -1 | (-9%) | 10
197 | 5302 | 2rc67Y2hzAhRvE7YihWA | Normal | 10 | 1.4.2.3.2.1 | 1.4.2.3.2.1 |  | 10 | q | -1 | (-10%) | 9
198 | 5306 | yar7ts7ASIpTQqyvnwQd | Normal | 5 | 1.4.2.3.2.13 | 1.4.2.3.2.13 |  | 5 | p | 1 | -20% | 6
199 | 5307 | yRByGMPgEQcCecr5HzAA | Normal | 2 | 1.4.2.3.2.15 | 1.4.2.3.2.15 |  | 2 | p | 2 | -100% | 4
200 | 5308 | JBAsTSNPb9OQmIAmtadV | Normal | 20 | 1.4.2.3.2.17 | 1.4.2.3.2.17 |  | 20 | p | 9 | -45% | 29
201 | 6271 | Q6QswYSvhipRUbZBXuiu | Summary | 315 | 1.6 | 1.6 |  | 315 | p | 46 | -15% | 361
202 | 6277 | moVS9Ou3GclDwNSW1OnS | Summary | 264 | 1.6.7 | 1.6.7 |  | 264 | p | 33 | -12% | 297
203 | 700 | PZaQwD8fp0dlxZIxEZEd | Normal | 279 | 1.6.7.10 | 1.6.7.10 |  | 279 | p | 45 | -16% | 324
204 | 728 | 4dRz6TQj3FOK8lstTqZK | Summary | 396 | 1.6.7.9 | 1.6.7.9 |  | 396 | p | 39 | -10% | 435
205 | 741 | cktDjgZ5bp36SrQnCM1w | Summary | 458 | 1.6.7.9.3 | 1.6.7.9.3 |  | 458 | p | 50 | -11% | 508
206 | 751 | AADJzuTGAb4gWytj7CQi | Normal | 18 | 1.6.7.9.3.8 | 1.6.7.9.3.8 |  | 18 | q | -1 | (-6%) | 17
207 | 752 | r0c0rFS4EkOGynasmiCG | Normal | 36 | 1.6.7.9.3.7 | 1.6.7.9.3.7 |  | 36 | p | 1 | -3% | 37
208 | 759 | cZuo3MY7iyDrOJC1qVJx | Normal | 5 | 1.6.7.9.3.9 | 1.6.7.9.3.9 |  | 5 | q | -1 | (-20%) | 4
209 | 6323 | aU24Z8SrLl20SyyllZuy | Summary | 80 | 1.6.7.9.3.5 | 1.6.7.9.3.5 |  | 80 | q | -10 | (-12%) | 70
210 | 745 | aO52oWR4hBrrP5GVCo2a | Normal | 11 | 1.6.7.9.3.5.2 | 1.6.7.9.3.5.2 |  | 11 | q | -3 | (-27%) | 8
211 | 746 | qMC0J8brk1dsdpzlKrk7 | Normal | 12 | 1.6.7.9.3.5.3 | 1.6.7.9.3.5.3 |  | 12 | q | -1 | (-8%) | 11
212 | 6324 | gthK0FxwJBk3laTELp8O | Summary | 45 | 1.6.7.9.3.6 | 1.6.7.9.3.6 |  | 45 | q | -1 | (-2%) | 44
213 | 749 | Q6UXOpf9Kvzek7IGY0vp | Normal | 11 | 1.6.7.9.3.6.3 | 1.6.7.9.3.6.3 |  | 11 | q | -2 | (-18%) | 9
214 | 750 | lsyrPytnmjLTpXFywa7Z | Normal | 11 | 1.6.7.9.3.6.4 | 1.6.7.9.3.6.4 |  | 11 | p | 1 | -9% | 12
215 | 6325 | SeCXD5wMvkrEekc1PKVb | Summary | 48 | 1.6.7.9.3.10 | 1.6.7.9.3.10 |  | 48 | p | 58 | -121% | 106
216 | 753 | 8158sxzbHZvZEVAAqewP | Normal | 47 | 1.6.7.9.3.10.1 | 1.6.7.9.3.10.1 |  | 47 | p | 22 | -47% | 69
217 | 754 | hfPeDXfQSV7Nx9zb2rD7 | Normal | 8 | 1.6.7.9.3.10.2 | 1.6.7.9.3.10.2 |  | 8 | q | -2 | (-25%) | 6
218 | 5782 | EYY3j1SjnoLUV06T0QHs | Normal | 5 | 1.6.7.9.3.10.7 | 1.6.7.9.3.10.7 |  | 5 | q | -2 | (-40%) | 3
219 | 6326 | F4s3MnfyyA74WCIympSi | Summary | 75 | 1.6.7.9.3.11 | 1.6.7.9.3.11 |  | 75 | p | 38 | -51% | 113
220 | 760 | 7IpOsslq7gyebnCTulxX | Normal | 66 | 1.6.7.9.3.11.1 | 1.6.7.9.3.11.1 |  | 66 | q | -1 | (-2%) | 65
221 | 762 | nRInnITHYgcDsU5KDg6m | Normal | 8 | 1.6.7.9.3.11.3 | 1.6.7.9.3.11.3 |  | 8 | q | -2 | (-25%) | 6
222 | 6327 | dOJS0LaWQU970ssSiqsz | Summary | 59 | 1.6.7.9.3.12 | 1.6.7.9.3.12 |  | 59 | p | 5 | -8% | 64
223 | 763 | hLK2cdXSS7IhOZR53PgI | Normal | 6 | 1.6.7.9.3.12.1 | 1.6.7.9.3.12.1 |  | 6 | q | -1 | (-17%) | 5
224 | 764 | wTf98lLeHiXAkWj17mAH | Normal | 53 | 1.6.7.9.3.12.2 | 1.6.7.9.3.12.2 |  | 53 | p | 6 | -11% | 59
225 | 770 | cHAOkWrFbu094CNd9eCk | Summary | 91 | 1.6.7.8 | 1.6.7.8 |  | 91 | q | -1 | (-1%) | 90
226 | 6434 | cc8WGEqtonq4zOxPHtWc | Normal | 65 | 1.6.7.8.4 | 1.6.7.8.4 |  | 65 | q | -3 | (-5%) | 62
227 | 5785 | xIbBdattr1YLWDiqGWPC | Summary | 126 | 1.6.7.11 | 1.6.7.11 |  | 126 | p | 10 | -8% | 136
228 | 6435 | Ql00ScpYzqtI9PQP57zu | Normal | 122 | 1.6.7.11.2 | 1.6.7.11.2 |  | 122 | p | 11 | -9% | 133
229 | 6284 | T6s1mlIi1Lu4cscBpq9h | Summary | 273 | 1.6.6 | 1.6.6 |  | 273 | p | 21 | -8% | 294
230 | 1519 | Ig6aeqJATmPNbReGQrzj | Summary | 273 | 1.6.6.1 | 1.6.6.1 |  | 273 | p | 21 | -8% | 294
231 | 1463 | IQX94tuow2VKmVJTuhEN | Normal | 1 | 1.6.6.1.3 | 1.6.6.1.3 |  | 1 | q | -1 | (-100%) | 0
232 | 1464 | VN7GLU7alOC9oD3kkW9q | Normal | 30 | 1.6.6.1.4 | 1.6.6.1.4 |  | 30 | p | 8 | -27% | 38
233 | 1475 | suCYO4gIoCSrnZchT6aQ | Normal | 3 | 1.6.6.1.6 | 1.6.6.1.6 |  | 3 | p | 1 | -33% | 4
234 | 1476 | gbuDNYIgLq2nB3WERl4p | Normal | 30 | 1.6.6.1.7 | 1.6.6.1.7 |  | 30 | p | 7 | -23% | 37
235 | 1478 | UR7xa7LgN3sMlpzxRjvW | Normal | 3 | 1.6.6.1.9 | 1.6.6.1.9 |  | 3 | q | -1 | (-33%) | 2
236 | 6293 | WhUcOZjaj9TDZe74ojmh | Summary | 172 | 1.6.4 | 1.6.4 |  | 172 | p | 19 | -11% | 191
237 | 3929 | GkmiaraCbWdBUaRv136y | Summary | 19 | 1.6.4.15 | 1.6.4.15 |  | 19 | q | -4 | (-21%) | 15
238 | 3938 | 2iJ091mlhEkJyqoddB4L | Normal | 14 | 1.6.4.15.1 | 1.6.4.15.1 |  | 14 | q | -6 | (-43%) | 8
239 | 3931 | GleHIX38gd9vOXaUQYVA | Normal | 33 | 1.6.4.11 | 1.6.4.11 |  | 33 | q | -4 | (-12%) | 29
240 | 3933 | FbGZSJQTtuDZR2p8qmxq | Normal | 33 | 1.6.4.13 | 1.6.4.13 |  | 33 | p | 6 | -18% | 39
241 | 3935 | IRdaiLeeauelAg4QWklz | Normal | 33 | 1.6.4.12 | 1.6.4.12 |  | 33 | q | -1 | (-3%) | 32
242 | 3939 | cuQ4HC0Kn3S6GTvqv7QE | Normal | 33 | 1.6.4.14 | 1.6.4.14 |  | 33 | p | 9 | -27% | 42
243 | 3971 | mB1p68eekBqQhgV8es2U | Summary | 19 | 1.6.4.7 | 1.6.4.7 |  | 19 | p | 2 | -11% | 21
244 | 3981 | YTm9sByrDxPUc7AlWXh1 | Normal | 15 | 1.6.4.7.2 | 1.6.4.7.2 |  | 15 | q | -1 | (-7%) | 14
245 | 3973 | 00qHhBlTe8pinGtKpu3n | Normal | 4 | 1.6.4.6 | 1.6.4.6 |  | 4 | q | -4 | (-100%) | 0
246 | 3980 | po54OWwjtqomy5uOkFBU | Normal | 40 | 1.6.4.4 | 1.6.4.4 |  | 40 | p | 5 | -12% | 45
247 | 3991 | kc0LQmDrjfLGJeMU4QIH | Summary | 70 | 1.6.4.17 | 1.6.4.17 |  | 70 | p | 10 | -14% | 80
248 | 3992 | cy141kwlo0X5isTqv3ku | Summary | 25 | 1.6.4.17.4 | 1.6.4.17.4 |  | 25 | p | 3 | -12% | 28
249 | 3993 | LBRozXrRhpq69SKlxnDb | Normal | 10 | 1.6.4.17.4.1 | 1.6.4.17.4.1 |  | 10 | p | 3 | -30% | 13
250 | 3994 | DvOjAQ6C9aXKnpaAVD1H | Normal | 5 | 1.6.4.17.4.2 | 1.6.4.17.4.2 |  | 5 | p | 1 | -20% | 6
251 | 3998 | 5UhDwyM7phAycUkk1Nye | Normal | 10 | 1.6.4.17.3.1 | 1.6.4.17.3.1 |  | 10 | p | 1 | -10% | 11
252 | 4000 | Y3aJp60cYMHromf8xgAE | Normal | 5 | 1.6.4.17.3.3 | 1.6.4.17.3.3 |  | 5 | q | -1 | (-20%) | 4
253 | 4002 | nJzh0eFJGsqvOmQRJzHn | Summary | 27 | 1.6.4.17.2 | 1.6.4.17.2 |  | 27 | p | 5 | -19% | 32
254 | 4003 | gjf3v6NdOQannovTvAoE | Normal | 19 | 1.6.4.17.2.1 | 1.6.4.17.2.1 |  | 19 | p | 1 | -5% | 20
255 | 4005 | NxZ8rMz5ZnJaz6z1SXKM | Normal | 3 | 1.6.4.17.2.3 | 1.6.4.17.2.3 |  | 3 | p | 1 | -33% | 4
256 | 4006 | fOTuJvqH3OcilXcZuEM5 | Normal | 4 | 1.6.4.17.2.4 | 1.6.4.17.2.4 |  | 4 | p | 1 | -25% | 5
257 | 4012 | A4Ck0Reyqf4cLzrM8uUY | Summary | 206 | 1.6.4.19 | 1.6.4.19 |  | 206 | q | -56 | (-27%) | 150
258 | 6168 | BHtkkzlMW8757DY2qb23 | Summary | 143 | 1.6.4.19.3 | 1.6.4.19.3 |  | 143 | p | 5 | -3% | 148
259 | 6169 | gdW3U4pURjb9iKkAVexH | Summary | 60 | 1.6.4.19.3.1 | 1.6.4.19.3.1 |  | 60 | p | 4 | -7% | 64
260 | 6170 | AwYLgXY6Mo1DqCbUEhPQ | Summary | 30 | 1.6.4.19.3.1.1 | 1.6.4.19.3.1.1 |  | 30 | p | 3 | -10% | 33
261 | 6172 | QgFskomqU31VYtYzB2O0 | Normal | 15 | 1.6.4.19.3.1.1.2 | 1.6.4.19.3.1.1.2 |  | 15 | p | 2 | -13% | 17
262 | 6174 | dvLkHNDhuFTU7AO5XWky | Normal | 15 | 1.6.4.19.3.1.3 | 1.6.4.19.3.1.3 |  | 15 | p | 2 | -13% | 17
263 | 6175 | IEttja5qNJ6P760Cd9De | Summary | 40 | 1.6.4.19.3.2 | 1.6.4.19.3.2 |  | 40 | p | 2 | -5% | 42
264 | 6176 | B6x3R7fnpOwupecmo90D | Normal | 10 | 1.6.4.19.3.2.1 | 1.6.4.19.3.2.1 |  | 10 | p | 1 | -10% | 11
265 | 6179 | xksMzlhYjvKZ4p1XJwSB | Normal | 10 | 1.6.4.19.3.2.4 | 1.6.4.19.3.2.4 |  | 10 | p | 1 | -10% | 11
266 | 6182 | JQHbjwkPqIslt5thIOgQ | Normal | 5 | 1.6.4.19.3.5 | 1.6.4.19.3.5 |  | 5 | q | -1 | (-20%) | 4
267 | 4037 | hMBnPD0NfYpjSqEpRMYY | Summary | 554 | 1.6.4.20 | 1.6.4.20 |  | 554 | p | 67 | -12% | 621
268 | 4038 | VkrURyJwsSkEVRV6WcXe | Summary | 411 | 1.6.4.20.1 | 1.6.4.20.1 |  | 411 | p | 51 | -12% | 462
269 | 4040 | g5zNgGHP8U11wPTJKhcB | Normal | 20 | 1.6.4.20.1.3 | 1.6.4.20.1.3 |  | 20 | q | -4 | (-20%) | 16
270 | 4041 | f0PORH3GhEIXFjYfGbTd | Normal | 97 | 1.6.4.20.1.6 | 1.6.4.20.1.6 |  | 97 | p | 22 | -23% | 119
271 | 4042 | SyfMayqY4a7i0nZLPz6Y | Normal | 129 | 1.6.4.20.1.7 | 1.6.4.20.1.7 |  | 129 | q | -4 | (-3%) | 125
272 | 6622 | EmEy5gJckBYofEEYNXFv | Normal | 20 | 1.6.4.20.1.4 | 1.6.4.20.1.4 |  | 20 | p | 2 | -10% | 22
273 | 6623 | BVU87KMg9Rhzc6j5yKVh | Normal | 20 | 1.6.4.20.1.5 | 1.6.4.20.1.5 |  | 20 | q | -1 | (-5%) | 19
274 | 4043 | XbXkjxtfHUxhg4CK1elt | Summary | 127 | 1.6.4.20.2 | 1.6.4.20.2 |  | 127 | p | 18 | -14% | 145
275 | 4045 | mDphgqAAxA2RnvA52x8A | Normal | 20 | 1.6.4.20.2.1 | 1.6.4.20.2.1 |  | 20 | p | 4 | -20% | 24
276 | 4046 | 5HyQBVwuqRdeW1HhaSOP | Normal | 10 | 1.6.4.20.2.2 | 1.6.4.20.2.2 |  | 10 | p | 1 | -10% | 11
277 | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Normal | 72 | 1.6.4.20.2.3 | 1.6.4.20.2.3 |  | 72 | p | 8 | -11% | 80
278 | 4048 | ybbKhm9jdtNbVzABGZ8L | Normal | 20 | 1.6.4.20.2.4 | 1.6.4.20.2.4 |  | 20 | p | 5 | -25% | 25
279 | 4049 | kP1jeiEwkYg4HRpUjG4p | Normal | 5 | 1.6.4.20.2.5 | 1.6.4.20.2.5 |  | 5 | q | -1 | (-20%) | 4
280 | 4050 | jQIHIDf5FTnJxQysEvnn | Summary | 37 | 1.6.4.20.3 | 1.6.4.20.3 |  | 37 | p | 3 | -8% | 40
281 | 4052 | JSSXcLTdD9VQNM766DgK | Normal | 20 | 1.6.4.20.3.1.1 | 1.6.4.20.3.1.1 |  | 20 | p | 1 | -5% | 21
282 | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Normal | 12 | 1.6.4.20.3.1.2 | 1.6.4.20.3.1.2 |  | 12 | q | -1 | (-8%) | 11
283 | 4059 | sH9kz6O2EFda2hu4x8Kx | Summary | 12 | 1.6.4.20.3.3 | 1.6.4.20.3.3 |  | 12 | q | -1 | (-8%) | 11
284 | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Normal | 3 | 1.6.4.20.3.3.1 | 1.6.4.20.3.3.1 |  | 3 | q | -1 | (-33%) | 2
285 | 5748 | cHP8KcDQZp8MvOi5a8Wj | Summary | 64 | 1.6.4.18 | 1.6.4.18 |  | 64 | q | -6 | (-9%) | 58
286 | 6701 | vwWJ3SVwW3tYdDDMDgOK | Summary | 60 | 1.6.4.18.3 | 1.6.4.18.3 |  | 60 | q | -5 | (-8%) | 55
287 | 6713 | JQXHTZXJblKyiNyxM0eT | Summary | 78 | 1.6.4.18.3.3 | 1.6.4.18.3.3 |  | 78 | q | -7 | (-9%) | 71
288 | 6727 | 5BlmDU3ct4fwjT54EODG | Summary | 21 | 1.6.4.18.3.3.2 | 1.6.4.18.3.3.2 |  | 21 | q | -7 | (-33%) | 14
289 | 6738 | XB1ZMgqMWvDJpnRGKTB3 | Normal | 3 | 1.6.4.18.3.3.2.10 | 1.6.4.18.3.3.2.10 |  | 3 | q | -3 | (-100%) | 0
290 | 7003 | XfnOKCk0EbakXF7t35fN | Normal | 1 | 1.6.4.18.3.3.2.9 | 1.6.4.18.3.3.2.9 |  | 1 | q | -1 | (-100%) | 0
291 | 7271 | 7ZvC3KC1rMxIYvbhicKJ | Normal | 10 | 1.6.4.18.3.3.2.7 | 1.6.4.18.3.3.2.7 |  | 10 | q | -1 | (-10%) | 9
292 | 7007 | 9uputDeZmGdSlUY8oN4J | Summary | 64 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 64 | q | -12 | (-19%) | 52
293 | 7010 | l7MAqMN94R7DBQRgok6z | Normal | 5 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 5 | q | -1 | (-20%) | 4
294 | 7277 | hIopgQViPH34dy6jPgEs | Normal | 6 | 1.6.4.18.3.3.7.5 | 1.6.4.18.3.3.7.5 |  | 6 | q | -6 | (-100%) | 0
295 | 7301 | mVBynbXAicTgOFud0Dl3 | Normal | 5 | 1.6.4.18.3.3.7.6 | 1.6.4.18.3.3.7.6 |  | 5 | p | 1 | -20% | 6
296 | 7302 | 6S1rSJxqNAmNyzjZVL7L | Normal | 5 | 1.6.4.18.3.3.7.8 | 1.6.4.18.3.3.7.8 |  | 5 | q | -1 | (-20%) | 4
297 | 7279 | uD2jpviUMAewZ4YhDj8P | Summary | 32 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 32 | q | -3 | (-9%) | 29
298 | 7286 | weppsWRcwILLbxkFpraK | Summary | 39 | 1.6.4.18.3.3.5 | 1.6.4.18.3.3.5 |  | 39 | p | 1 | -3% | 40
299 | 7289 | YNbMTserJcwdDTx8O6lt | Normal | 5 | 1.6.4.18.3.3.5.3 | 1.6.4.18.3.3.5.3 |  | 5 | p | 1 | -20% | 6
300 | 7292 | 6vEOHVPLFOaXnW1xcDp6 | Normal | 10 | 1.6.4.18.3.3.5.6 | 1.6.4.18.3.3.5.6 |  | 10 | q | -1 | (-10%) | 9
301 | 7293 | ep0qwejNT11UOlW5WmY0 | Summary | 28 | 1.6.4.18.3.3.6 | 1.6.4.18.3.3.6 |  | 28 | p | 3 | -11% | 31
302 | 7295 | tyaakhlAtuOpVSt7bVvo | Normal | 1 | 1.6.4.18.3.3.6.2 | 1.6.4.18.3.3.6.2 |  | 1 | q | -1 | (-100%) | 0
303 | 7296 | PnFVdPiNKahDkradYWdd | Normal | 5 | 1.6.4.18.3.3.6.3 | 1.6.4.18.3.3.6.3 |  | 5 | p | 2 | -40% | 7
304 | 7299 | ymtRqRQZa4AjGraGOZVd | Normal | 10 | 1.6.4.18.3.3.6.6 | 1.6.4.18.3.3.6.6 |  | 10 | p | 2 | -20% | 12
305 | 6297 | AqdIsKbIPOfZJkjKYjnG | Summary | 118 | 1.6.1 | 1.6.1 |  | 118 | q | -36 | (-31%) | 82
306 | 4200 | YSdvLAa6ztbhOKei71CV | Summary | 108 | 1.6.1.1 | 1.6.1.1 |  | 108 | p | 6 | -6% | 114
307 | 4202 | N5DTU5adYVhKR5So2Uvc | Normal | 88 | 1.6.1.1.3 | 1.6.1.1.3 |  | 88 | p | 2 | -2% | 90
308 | 4204 | CRzwy8942pbCOpcOMW2v | Normal | 20 | 1.6.1.1.4 | 1.6.1.1.4 |  | 20 | p | 1 | -5% | 21
309 | 4209 | 0Ck6gz1ZilLs9fM0b7nU | Summary | 46 | 1.6.1.3 | 1.6.1.3 |  | 46 | q | -7 | (-15%) | 39
310 | 4212 | yktUOUuzQyzOVBFBfL42 | Normal | 46 | 1.6.1.3.1 | 1.6.1.3.1 |  | 46 | q | -9 | (-20%) | 37
311 | 6311 | tQdu1pFxVkY2bj5IQjxI | Summary | 77 | 1.6.3 | 1.6.3 |  | 77 | p | 103 | -134% | 180
312 | 5452 | u9nFTwEoKsBrgeg8njOT | Normal | 5 | 1.6.3.1 | 1.6.3.1 |  | 5 | p | 185 | -3700% | 190
313 | 5506 | wLM81Xdu8B5geOMMQz6m | Summary | 119 | 1.6.3.3 | 1.6.3.3 |  | 119 | p | 46 | -39% | 165
314 | 5508 | wHSntGHJkj4aA0wA3fA2 | Normal | 14 | 1.6.3.3.3 | 1.6.3.3.3 |  | 14 | p | 1 | -7% | 15
315 | 5509 | 1FHP32ReWIveKb3JOWEG | Summary | 44 | 1.6.3.3.4 | 1.6.3.3.4 |  | 44 | p | 5 | -11% | 49
316 | 5510 | LTFwTsrnxYhrGNFUv7CM | Normal | 12 | 1.6.3.3.4.1 | 1.6.3.3.4.1 |  | 12 | p | 3 | -25% | 15
317 | 5511 | Od3mMFxB7LjrJLF1slz4 | Normal | 11 | 1.6.3.3.4.2 | 1.6.3.3.4.2 |  | 11 | p | 1 | -9% | 12
318 | 5512 | Des2hDKSMjcJndTJRzoQ | Normal | 11 | 1.6.3.3.4.3 | 1.6.3.3.4.3 |  | 11 | p | 1 | -9% | 12
319 | 6890 | QKIolSsTnUWZiIhR6M5v | Normal | 40 | 1.6.3.3.1 | 1.6.3.3.1 |  | 40 | q | -10 | (-25%) | 30
320 | 6359 | hvfa0617w1FgmEnjjKwJ | Summary | 26 | 1.7.2.16 | 1.7.2.16 |  | 26 | q | -1 | (-4%) | 25
321 | 6360 | DMXbIVCeMtVR5pi4d5UN | Summary | 26 | 1.7.2.16.1 | 1.7.2.16.1 |  | 26 | q | -1 | (-4%) | 25
322 | 6361 | VEKeY9azNIVSZDSjYyKy | Summary | 33 | 1.7.2.16.1.3 | 1.7.2.16.1.3 |  | 33 | q | -2 | (-6%) | 31
323 | 7303 | fpLHmKjlfpy4s4tap5Xw | Summary | 39 | 1.6.3.11.1.3.4 | 1.6.3.11.1.3.4 |  | 39 | q | -5 | (-13%) | 34
324 | 7307 | eye8r8DevGvPITcdrMUe | Normal | 6 | 1.6.3.11.1.3.4.4 | 1.6.3.11.1.3.4.4 |  | 6 | q | -1 | (-17%) | 5
325 | 7309 | 19skeJKmh3pRSfTF3DDB | Summary | 30 | 1.6.3.11.1.3.5 | 1.6.3.11.1.3.5 |  | 30 | q | -5 | (-17%) | 25
326 | 7312 | ZHpaj2955bjmxPKFBEf2 | Normal | 2 | 1.6.3.11.1.3.5.3 | 1.6.3.11.1.3.5.3 |  | 2 | q | -2 | (-100%) | 0
327 | 7313 | boaUnlKi0h6sKdwgAbmA | Normal | 5 | 1.6.3.11.1.3.5.4 | 1.6.3.11.1.3.5.4 |  | 5 | p | 1 | -20% | 6
328 | 7315 | 9LywAxRsXdHsCrCcjGKV | Summary | 27 | 1.6.3.11.1.3.6 | 1.6.3.11.1.3.6 |  | 27 | p | 2 | -7% | 29
329 | 7318 | vWglY3BMmZCigDWMEMyY | Normal | 3 | 1.6.3.11.1.3.6.3 | 1.6.3.11.1.3.6.3 |  | 3 | p | 1 | -33% | 4
330 | 6273 | ljz6i2ltFwqcRU3btDx0 | Summary | 552 | 1.8 | 1.8 |  | 552 | p | 277 | -50% | 829
331 | 1639 | mkPE1mMWzawwUBF3KKzV | Summary | 277 | 1.8.2 | 1.8.2 |  | 277 | p | 149 | -54% | 426
332 | 6074 | fkBL64dyW7paLwgGr0ue | Normal | 212 | 1.8.2.3 | 1.8.2.3 |  | 212 | q | -2 | (-1%) | 210
333 | 6075 | pe2nScqRc5pgTwGaT5Zd | Normal | 193 | 1.8.2.2 | 1.8.2.2 |  | 193 | p | 13 | -7% | 206
334 | 6295 | uPS9GNqRLP4065SnBhEr | Summary | 387 | 1.8.5 | 1.8.5 |  | 387 | p | 239 | -62% | 626
335 | 3679 | 1KDcwGZKgevw1MizqBh0 | Summary | 387 | 1.8.5.1 | 1.8.5.1 |  | 387 | p | 239 | -62% | 626
336 | 3680 | E8qsx9NjEz7vaL5H7EFb | Summary | 189 | 1.8.5.1.1 | 1.8.5.1.1 |  | 189 | p | 6 | -3% | 195
337 | 3681 | wdhUrQuIMTMPn1LoqO1m | Normal | 24 | 1.8.5.1.1.1 | 1.8.5.1.1.1 |  | 24 | q | -7 | (-29%) | 17
338 | 3682 | 38PSIqFGHzjKldiudT82 | Summary | 25 | 1.8.5.1.1.4 | 1.8.5.1.1.4 |  | 25 | p | 3 | -12% | 28
339 | 3683 | JW3LUw009FZ7ddD6CdLX | Normal | 20 | 1.8.5.1.1.4.1 | 1.8.5.1.1.4.1 |  | 20 | p | 2 | -10% | 22
340 | 3684 | g3f8U3i4iakOhylueut6 | Normal | 5 | 1.8.5.1.1.4.2 | 1.8.5.1.1.4.2 |  | 5 | p | 2 | -40% | 7
341 | 3685 | eStRoX3vnaDmRLAWk58C | Summary | 40 | 1.8.5.1.1.5 | 1.8.5.1.1.5 |  | 40 | p | 6 | -15% | 46
342 | 3686 | 7zhxjkpiLTAH9tiW1eYy | Normal | 20 | 1.8.5.1.1.5.1 | 1.8.5.1.1.5.1 |  | 20 | p | 4 | -20% | 24
343 | 3690 | 8YDpqEvemQaMsfVmGpF8 | Normal | 5 | 1.8.5.1.1.5.5 | 1.8.5.1.1.5.5 |  | 5 | p | 1 | -20% | 6
344 | 3691 | ofZrlktbiXkVpuhhIeO5 | Summary | 25 | 1.8.5.1.1.6 | 1.8.5.1.1.6 |  | 25 | p | 1 | -4% | 26
345 | 3692 | xRsKOxB8zGAnVTXugcHQ | Normal | 20 | 1.8.5.1.1.6.1 | 1.8.5.1.1.6.1 |  | 20 | p | 1 | -5% | 21
346 | 3694 | 4tipOydrC0LTNincaMDW | Summary | 35 | 1.8.5.1.1.7 | 1.8.5.1.1.7 |  | 35 | p | 12 | -34% | 47
347 | 3695 | lT6NpgfSYqKHtVYFLSzF | Normal | 20 | 1.8.5.1.1.7.1 | 1.8.5.1.1.7.1 |  | 20 | p | 8 | -40% | 28
348 | 3696 | gijouZuJR1ZVcSfHKSTf | Normal | 5 | 1.8.5.1.1.7.2 | 1.8.5.1.1.7.2 |  | 5 | p | 1 | -20% | 6
349 | 3697 | 1158ttL4JEmZYV6RmdcS | Normal | 5 | 1.8.5.1.1.7.3 | 1.8.5.1.1.7.3 |  | 5 | p | 1 | -20% | 6
350 | 3698 | AKCwPpEPQi4iH3XDRpiM | Normal | 5 | 1.8.5.1.1.7.4 | 1.8.5.1.1.7.4 |  | 5 | p | 1 | -20% | 6
351 | 3700 | WE9bFDn3y5M7oiID5UPj | Normal | 20 | 1.8.5.1.1.8.1 | 1.8.5.1.1.8.1 |  | 20 | q | -2 | (-10%) | 18
352 | 3702 | sTuPByKbZEfSXxt0Z2G9 | Normal | 5 | 1.8.5.1.1.8.3 | 1.8.5.1.1.8.3 |  | 5 | p | 1 | -20% | 6
353 | 3703 | WHZRJAK4v6S9Zk2EBeP3 | Summary | 40 | 1.8.5.1.1.9 | 1.8.5.1.1.9 |  | 40 | q | -7 | (-18%) | 33
354 | 3704 | 3CXbrhXJooXd98jlpAkg | Normal | 20 | 1.8.5.1.1.9.1 | 1.8.5.1.1.9.1 |  | 20 | q | -6 | (-30%) | 14
355 | 3705 | RO9RShNcg0h7x9fD24Zk | Normal | 5 | 1.8.5.1.1.9.2 | 1.8.5.1.1.9.2 |  | 5 | q | -2 | (-40%) | 3
356 | 3706 | w8MhGnhxyXFIHvJdw6bc | Normal | 5 | 1.8.5.1.1.9.3 | 1.8.5.1.1.9.3 |  | 5 | p | 1 | -20% | 6
357 | 3707 | dJNKgtiJ1M8pNoPOlZcZ | Normal | 5 | 1.8.5.1.1.9.4 | 1.8.5.1.1.9.4 |  | 5 | p | 1 | -20% | 6
358 | 3709 | gpO5WcJkYid7jZAXZwbn | Summary | 40 | 1.8.5.1.1.10 | 1.8.5.1.1.10 |  | 40 | p | 4 | -10% | 44
359 | 3710 | KOKaQwRJEoC6vlU3mKjm | Normal | 20 | 1.8.5.1.1.10.1 | 1.8.5.1.1.10.1 |  | 20 | p | 1 | -5% | 21
360 | 3712 | sZwrgRbHYjKWcIa9rVK3 | Normal | 5 | 1.8.5.1.1.10.3 | 1.8.5.1.1.10.3 |  | 5 | p | 1 | -20% | 6
361 | 3713 | 4NbryuRKpmrExDEDqArG | Normal | 5 | 1.8.5.1.1.10.4 | 1.8.5.1.1.10.4 |  | 5 | q | -1 | (-20%) | 4
362 | 3714 | Fbm1iHrhCX8z8SNRXJuq | Normal | 5 | 1.8.5.1.1.10.5 | 1.8.5.1.1.10.5 |  | 5 | p | 2 | -40% | 7
363 | 6647 | hWzCSsDre5WTTpryk1b0 | Normal | 5 | 1.8.5.1.1.3 | 1.8.5.1.1.3 |  | 5 | p | 1 | -20% | 6
364 | 3715 | V6i7uYjEJBRYHjhIimqJ | Summary | 50 | 1.8.5.1.2 | 1.8.5.1.2 |  | 50 | q | -4 | (-8%) | 46
365 | 3716 | bdy5zVX59rD935sK6M5v | Normal | 20 | 1.8.5.1.2.1 | 1.8.5.1.2.1 |  | 20 | q | -1 | (-5%) | 19
366 | 3717 | 5PdqCAMtbYgi5VsFO6ls | Normal | 20 | 1.8.5.1.2.4 | 1.8.5.1.2.4 |  | 20 | q | -2 | (-10%) | 18
367 | 6671 | 0oTh3tmNX3iVSaVNVmGK | Normal | 5 | 1.8.5.1.2.2 | 1.8.5.1.2.2 |  | 5 | p | 1 | -20% | 6
368 | 6672 | BKyGOzVPyPwKpI9CyseJ | Normal | 5 | 1.8.5.1.2.3 | 1.8.5.1.2.3 |  | 5 | q | -2 | (-40%) | 3
369 | 3718 | vTyTgxcbRSz6H6lqDAEf | Summary | 20 | 1.8.5.1.3 | 1.8.5.1.3 |  | 20 | q | -9 | (-45%) | 11
370 | 3719 | B9ymEBZ7zimHMMqNS20Q | Normal | 20 | 1.8.5.1.3.1 | 1.8.5.1.3.1 |  | 20 | q | -9 | (-45%) | 11
371 | 3720 | rPRo0RE1uNkj9oG127hu | Summary | 109 | 1.8.5.1.4 | 1.8.5.1.4 |  | 109 | q | -10 | (-9%) | 99
372 | 3722 | hYa6Ppkzu6veYWmxHffd | Normal | 27 | 1.8.5.1.4.2 | 1.8.5.1.4.2 |  | 27 | q | -1 | (-4%) | 26
373 | 6650 | FvuNLI4Jaew3VjPpwL3e | Normal | 28 | 1.8.5.1.4.4 | 1.8.5.1.4.4 |  | 28 | q | -7 | (-25%) | 21
374 | 6652 | 0afM7N7hGdWHQjlFenVR | Normal | 10 | 1.8.5.1.4.6 | 1.8.5.1.4.6 |  | 10 | q | -2 | (-20%) | 8
375 | 3723 | 4qmbzAmtSx0gvDVaBsYe | Summary | 239 | 1.8.5.1.5 | 1.8.5.1.5 |  | 239 | p | 2 | -1% | 241
376 | 3724 | ZCOxRRLLrh9Pa7VnBAyk | Normal | 27 | 1.8.5.1.5.1 | 1.8.5.1.5.1 |  | 27 | q | -3 | (-11%) | 24
377 | 3725 | 8cgOIQk4rBKvjXdBm8mF | Normal | 91 | 1.8.5.1.5.9 | 1.8.5.1.5.9 |  | 91 | q | -24 | (-26%) | 67
378 | 6663 | LVExlIxeJ6XB3yqm0Dzs | Normal | 28 | 1.8.5.1.5.4 | 1.8.5.1.5.4 |  | 28 | q | -1 | (-4%) | 27
379 | 6664 | Io9oZ1dPqEE9GDlMTPxh | Normal | 28 | 1.8.5.1.5.5 | 1.8.5.1.5.5 |  | 28 | p | 1 | -4% | 29
380 | 6665 | ycT0qtEFjd4p02S4Ehf1 | Normal | 28 | 1.8.5.1.5.6 | 1.8.5.1.5.6 |  | 28 | q | -2 | (-7%) | 26
381 | 6666 | sX3PHseynvzwKI9my2AH | Normal | 15 | 1.8.5.1.5.7 | 1.8.5.1.5.7 |  | 15 | p | 7 | -47% | 22
382 | 6667 | 0dYk2X7XWh2rSSHkHo2L | Normal | 10 | 1.8.5.1.5.8 | 1.8.5.1.5.8 |  | 10 | q | -3 | (-30%) | 7
383 | 3726 | 5hjTNIk7WmpZNtmCLhPN | Summary | 96 | 1.8.5.1.6 | 1.8.5.1.6 |  | 96 | p | 13 | -14% | 109
384 | 3727 | rGcF2XgkgPtqRDM3KJ2D | Normal | 28 | 1.8.5.1.6.1 | 1.8.5.1.6.1 |  | 28 | p | 4 | -14% | 32
385 | 3728 | Hgqc9wbzS3SDikBm20zt | Normal | 28 | 1.8.5.1.6.3 | 1.8.5.1.6.3 |  | 28 | p | 7 | -25% | 35
386 | 6654 | MMK0qYycfTMCrFAZcf8J | Normal | 15 | 1.8.5.1.6.4 | 1.8.5.1.6.4 |  | 15 | p | 1 | -7% | 16
387 | 3729 | Y6b5KP0DE9c4tlFzqxp3 | Summary | 81 | 1.8.5.1.7 | 1.8.5.1.7 |  | 81 | q | -3 | (-4%) | 78
388 | 3730 | TswICWhG0Mjj1DenbPW5 | Normal | 28 | 1.8.5.1.7.1 | 1.8.5.1.7.1 |  | 28 | p | 2 | -7% | 30
389 | 6626 | 9d2gtkuh8SmNZwArNzpn | Normal | 10 | 1.8.5.1.7.4 | 1.8.5.1.7.4 |  | 10 | q | -2 | (-20%) | 8
390 | 6627 | QBgG0JxqOymB6vyjKsRZ | Normal | 28 | 1.8.5.1.7.2 | 1.8.5.1.7.2 |  | 28 | q | -1 | (-4%) | 27
391 | 6628 | PAI9VZBMaYriaY1wvhOi | Normal | 15 | 1.8.5.1.7.3 | 1.8.5.1.7.3 |  | 15 | q | -2 | (-13%) | 13
392 | 3733 | ufu7SWDoeBfTzZW24BQU | Summary | 189 | 1.8.5.1.9 | 1.8.5.1.9 |  | 189 | p | 423 | -224% | 612
393 | 3735 | rgqtw8hyurrfag2amXLA | Normal | 109 | 1.8.5.1.9.2 | 1.8.5.1.9.2 |  | 109 | q | -2 | (-2%) | 107
394 | 3736 | eIMYQUSTObIc5Lp6kKBE | Normal | 40 | 1.8.5.1.9.3 | 1.8.5.1.9.3 |  | 40 | q | -13 | (-32%) | 27
395 | 3737 | z19Wnme0hJcfEI4IfIQR | Normal | 25 | 1.8.5.1.9.4 | 1.8.5.1.9.4 |  | 25 | q | -3 | (-12%) | 22
396 | 6657 | uq5fluI8KT8LkPx57ktn | Normal | 10 | 1.8.5.1.9.5 | 1.8.5.1.9.5 |  | 10 | p | 2 | -20% | 12
397 | 6658 | ktg0XNnAmjjc1caqICt2 | Normal | 5 | 1.8.5.1.9.6 | 1.8.5.1.9.6 |  | 5 | p | 1 | -20% | 6
398 | 3739 | Ba23bBwg4xGpRd3Ht4kS | Normal | 24 | 1.8.5.1.10.1 | 1.8.5.1.10.1 |  | 24 | q | -3 | (-12%) | 21
399 | 3740 | lRtbtcrLyr1QGd0laoJi | Normal | 25 | 1.8.5.1.10.2 | 1.8.5.1.10.2 |  | 25 | p | 1 | -4% | 26
400 | 3741 | V05WnFKB5t2LuixhoKHO | Normal | 25 | 1.8.5.1.10.3 | 1.8.5.1.10.3 |  | 25 | p | 4 | -16% | 29
401 | 3742 | LRjVz0hoZuIRlQgcLYzs | Normal | 25 | 1.8.5.1.10.6 | 1.8.5.1.10.6 |  | 25 | p | 3 | -12% | 28
402 | 6648 | Z5T3n0GGVz8PB0IY5TXC | Normal | 10 | 1.8.5.1.10.5 | 1.8.5.1.10.5 |  | 10 | q | -2 | (-20%) | 8
403 | 6656 | tqprQgHoroqT051BXug3 | Normal | 15 | 1.8.5.1.10.4 | 1.8.5.1.10.4 |  | 15 | q | -2 | (-13%) | 13
404 | 6659 | NN3Qiea1foOxv05JqXnT | Normal | 10 | 1.8.5.1.10.7 | 1.8.5.1.10.7 |  | 10 | q | -1 | (-10%) | 9
405 | 6642 | A7Bd82G8YCk8VjEZkcvi | Summary | 135 | 1.8.5.1.8 | 1.8.5.1.8 |  | 135 | p | 340 | -252% | 475
406 | 3731 | 02LiOyWN4DF8GOeNSP5s | Normal | 20 | 1.8.5.1.8.1 | 1.8.5.1.8.1 |  | 20 | q | -4 | (-20%) | 16
407 | 3732 | x85AkT9s5HT2a4U2goND | Normal | 20 | 1.8.5.1.8.8 | 1.8.5.1.8.8 |  | 20 | p | 4 | -20% | 24
408 | 6629 | n59ds33sZr9JNOobmYWE | Normal | 30 | 1.8.5.1.8.2 | 1.8.5.1.8.2 |  | 30 | q | -10 | (-33%) | 20
409 | 6632 | 5y36mClzGR7vkSsODb4C | Normal | 15 | 1.8.5.1.8.5 | 1.8.5.1.8.5 |  | 15 | q | -4 | (-27%) | 11
410 | 6633 | uS272glxjETpDiVeJyGv | Normal | 20 | 1.8.5.1.8.6 | 1.8.5.1.8.6 |  | 20 | p | 2 | -10% | 22
411 | 6634 | 65ghvPiwU0AxSKrC11rG | Normal | 20 | 1.8.5.1.8.7 | 1.8.5.1.8.7 |  | 20 | p | 8 | -40% | 28
412 | 6643 | sKnPCsxlq51dE8cz52fo | Normal | 10 | 1.8.5.1.8.9 | 1.8.5.1.8.9 |  | 10 | q | -1 | (-10%) | 9
413 | 6313 | 8HYxn50EKf1DU0fX0MF7 | Summary | 391 | 1.8.4 | 1.8.4 |  | 391 | p | 819 | -209% | 1210
414 | 5516 | dd6fm1lW4tBXPtNV5RGW | Summary | 391 | 1.8.4.1 | 1.8.4.1 |  | 391 | p | 819 | -209% | 1210
415 | 5517 | IHfroMkwx3TZoTXYbBOK | Normal | 40 | 1.8.4.1.1 | 1.8.4.1.1 |  | 40 | q | -13 | (-32%) | 27
416 | 5518 | V0a5XEJ0jxIkhnpEDg8e | Normal | 40 | 1.8.4.1.2 | 1.8.4.1.2 |  | 40 | p | 8 | -20% | 48
417 | 5519 | D5sl3M5NpO77EU7TPYT0 | Normal | 40 | 1.8.4.1.3 | 1.8.4.1.3 |  | 40 | q | -3 | (-8%) | 37
418 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 263 | p | 371 | -141% | 634
419 | 5331 | emM9tIPUc6I6BRQdDkUj | Summary | 325 | 1.9.3 | 1.9.3 |  | 325 | q | -21 | (-6%) | 304
420 | 5332 | Jas5wmBgln6JvMRLtRUk | Summary | 110 | 1.9.3.1 | 1.9.3.1 |  | 110 | p | 1 | -1% | 111
421 | 5334 | 5Bt8vyiG2PJ2FKCjQPP1 | Summary | 74 | 1.9.3.1.2 | 1.9.3.1.2 |  | 74 | p | 3 | -4% | 77
422 | 6472 | j0VQ7fJsNHb1HpOVRoJN | Normal | 7 | 1.9.3.1.2.2 | 1.9.3.1.2.2 |  | 7 | p | 1 | -14% | 8
423 | 6473 | FN1N5cBOnOQJN0lvtY6J | Normal | 5 | 1.9.3.1.2.3 | 1.9.3.1.2.3 |  | 5 | p | 1 | -20% | 6
424 | 6475 | TkBVMCiZTEhYxjcnMNRI | Normal | 8 | 1.9.3.1.2.5 | 1.9.3.1.2.5 |  | 8 | q | -2 | (-25%) | 6
425 | 6476 | HdsfOo0UbW7iVGjY7L1O | Normal | 10 | 1.9.3.1.2.6 | 1.9.3.1.2.6 |  | 10 | p | 3 | -30% | 13
426 | 6478 | ZDDqpCGw2ELQiAxZVJFo | Normal | 7 | 1.9.3.1.2.8 | 1.9.3.1.2.8 |  | 7 | q | -1 | (-14%) | 6
427 | 6479 | i51TyrBkECB0t7wKJruE | Normal | 7 | 1.9.3.1.2.9 | 1.9.3.1.2.9 |  | 7 | p | 1 | -14% | 8
428 | 5335 | fBEkx0xCtVpw1OeE4jLB | Summary | 25 | 1.9.3.1.3 | 1.9.3.1.3 |  | 25 | q | -2 | (-8%) | 23
429 | 5336 | FIhKbBOHnlTp0loBBfvV | Normal | 3 | 1.9.3.1.3.1 | 1.9.3.1.3.1 |  | 3 | p | 1 | -33% | 4
430 | 5337 | TPAbtCx4KhMQiN0iVD1F | Normal | 0 | 1.9.3.1.3.2 | 1.9.3.1.3.2 |  | 0 | p | 1 |  | 1
431 | 5340 | lQJTDBnvPE8mTPnPre3v | Normal | 10 | 1.9.3.1.3.5 | 1.9.3.1.3.5 |  | 10 | q | -2 | (-20%) | 8
432 | 5341 | nevxwfefPkBzu42CDbNd | Normal | 10 | 1.9.3.1.3.6 | 1.9.3.1.3.6 |  | 10 | q | -3 | (-30%) | 7
433 | 5342 | s0JiBiXDLP6oybWmkZ43 | Normal | 6 | 1.9.3.1.4 | 1.9.3.1.4 |  | 6 | q | -1 | (-17%) | 5
434 | 6275 | OL3lkJGtK3tkk0d4SBRn | Summary | 288 | 1.9.9 | 1.9.9 |  | 288 | p | 140 | -49% | 428
435 | 845 | U1v5hScHSOPPxa5ohjfI | Summary | 189 | 1.9.9.7 | 1.9.9.7 |  | 189 | p | 1 | -1% | 190
436 | 869 | 8QCM3LZ8SN5y0jCLtGNh | Summary | 129 | 1.9.9.7.2.7 | 1.9.9.7.2.7 |  | 129 | q | -1 | (-1%) | 128
437 | 6419 | NORPsF566zq8VZyN1UzF | Normal | 10 | 1.9.9.7.2.7.1 | 1.9.9.7.2.7.1 |  | 10 | p | 1 | -10% | 11
438 | 6420 | 043wOhyyEd8vJkuUBkFf | Normal | 40 | 1.9.9.7.2.7.2 | 1.9.9.7.2.7.2 |  | 40 | q | -3 | (-8%) | 37
439 | 6421 | JZROXyECnTBG3SBjYZJ8 | Normal | 79 | 1.9.9.7.2.7.3 | 1.9.9.7.2.7.3 |  | 79 | p | 2 | -3% | 81
440 | 6418 | W9pbV5i9WFkdVEGtW75H | Normal | 45 | 1.9.9.7.2.5 | 1.9.9.7.2.5 |  | 45 | q | -2 | (-4%) | 43
441 | 870 | m3oEXpasu7ssfpw9dqLv | Summary | 267 | 1.9.9.14 | 1.9.9.14 |  | 267 | p | 231 | -87% | 498
442 | 4667 | gXRr1908PexMoLIDosFv | Normal | 100 | 1.9.9.14.3 | 1.9.9.14.3 |  | 100 | q | -8 | (-8%) | 92
443 | 4669 | aeClBbTsJ3qrKHWqQ1Rw | Normal | 40 | 1.9.9.14.5 | 1.9.9.14.5 |  | 40 | q | -4 | (-10%) | 36
444 | 4679 | rpzkOhA603pApmNdMeVE | Normal | 0 | 1.9.9.14.6 | 1.9.9.14.6 |  | 0 | p | 1 |  | 1
445 | 5787 | r6JEZEKCpBbNZRe1W7Ef | Normal | 91 | 1.9.9.14.2 | 1.9.9.14.2 |  | 91 | p | 22 | -24% | 113
446 | 899 | w1GWQdUx9oG06oopRYZx | Summary | 24 | 1.9.9.15 | 1.9.9.15 |  | 24 | q | -2 | (-8%) | 22
447 | 901 | HcFqHITfVdYMyzVb3S8v | Normal | 18 | 1.9.9.15.2 | 1.9.9.15.2 |  | 18 | p | 2 | -11% | 20
448 | 903 | UDGopgZ2sb1QsQEooZ9G | Normal | 8 | 1.9.9.15.4 | 1.9.9.15.4 |  | 8 | q | -1 | (-12%) | 7
449 | 905 | MxRWNVEH6ZVBPqNnA2hI | Normal | 8 | 1.9.9.15.6 | 1.9.9.15.6 |  | 8 | q | -2 | (-25%) | 6
450 | 914 | q0UeyWaeMXFoeUDjjzhX | Summary | 18 | 1.9.9.5 | 1.9.9.5 |  | 18 | p | 3 | -17% | 21
451 | 915 | jxzEE3EBeGWt1nE3uHcj | Summary | 18 | 1.9.9.5.1 | 1.9.9.5.1 |  | 18 | p | 3 | -17% | 21
452 | 916 | d4bxhxtQW3GaLrDrUlf9 | Normal | 17 | 1.9.9.5.1.1 | 1.9.9.5.1.1 |  | 17 | p | 2 | -12% | 19
453 | 4538 | aTyUglf0WPX6H8Zd17Iq | Summary | 71 | 1.9.9.16 | 1.9.9.16 |  | 71 | q | -3 | (-4%) | 68
454 | 6509 | sp3XFaPtGgzrVeC1wvvV | Normal | 10 | 1.9.9.16.3 | 1.9.9.16.3 |  | 10 | q | -3 | (-30%) | 7
455 | 6510 | dar9hgzhSUYJxC1MeoTS | Normal | 10 | 1.9.9.16.4 | 1.9.9.16.4 |  | 10 | p | 2 | -20% | 12
456 | 6513 | IG8fHoH3vjERJ6iSB3Rj | Normal | 36 | 1.9.9.16.5 | 1.9.9.16.5 |  | 36 | q | -2 | (-6%) | 34
457 | 6128 | 7jXaekqqhUCDWSDfnxzo | Summary | 28 | 1.7.4.2 | 1.7.4.2 |  | 28 | p | 1 | -4% | 29
458 | 6686 | IDiuvzfQRXyu7MCMX1jW | Normal | 5 | 1.9.9.11 | 1.9.9.11 |  | 5 | q | -1 | (-20%) | 4
459 | 7388 | subTjNOw9tjXphx2xXzW | Summary | 324 | 1.9.9.13 | 1.9.9.13 |  | 324 | p | 9 | -3% | 333
460 | 7389 | xTfJP5JFEqXIDmLDdKVZ | Summary | 43 | 1.9.9.13.1 | 1.9.9.13.1 |  | 43 | p | 7 | -16% | 50
461 | 7390 | GV26YG775A5KHHrrMIRV | Summary | 32 | 1.9.9.13.1.1 | 1.9.9.13.1.1 |  | 32 | p | 7 | -22% | 39
462 | 7392 | ylVP19AJuwY485wgDJEG | Normal | 10 | 1.9.9.13.1.1.2 | 1.9.9.13.1.1.2 |  | 10 | q | -2 | (-20%) | 8
463 | 7394 | zHoRZ9fggWfe9FGnA954 | Normal | 10 | 1.9.9.13.1.1.4 | 1.9.9.13.1.1.4 |  | 10 | q | -1 | (-10%) | 9
464 | 7396 | gQKdIVV4LZyvHUAfFFFg | Normal | 10 | 1.9.9.13.1.1.6 | 1.9.9.13.1.1.6 |  | 10 | q | -1 | (-10%) | 9
465 | 7397 | gmOEJCOmO6SQ6HMlGXfq | Summary | 12 | 1.9.9.13.1.2 | 1.9.9.13.1.2 |  | 12 | p | 8 | -67% | 20
466 | 7400 | VGtguPWpaIPmF0Ojsz8a | Summary | 176 | 1.9.9.13.2 | 1.9.9.13.2 |  | 176 | p | 4 | -2% | 180
467 | 7403 | pHZBXvaYVwug2p7gN6jp | Summary | 17 | 1.9.9.13.2.3 | 1.9.9.13.2.3 |  | 17 | q | -1 | (-6%) | 16
468 | 7405 | 5GpI6xkgfIoVOnU9egD8 | Normal | 12 | 1.9.9.13.2.3.2 | 1.9.9.13.2.3.2 |  | 12 | q | -1 | (-8%) | 11
469 | 7406 | WxzG2sAIbVYYiem4v3mk | Normal | 12 | 1.9.9.13.2.3.3 | 1.9.9.13.2.3.3 |  | 12 | q | -2 | (-17%) | 10
470 | 7408 | uKngouP2QMMQmu6HFm0I | Normal | 11 | 1.9.9.13.2.4.1 | 1.9.9.13.2.4.1 |  | 11 | q | -1 | (-9%) | 10
471 | 7409 | C7eZzAQkBbKewE4wmmOD | Normal | 11 | 1.9.9.13.2.4.2 | 1.9.9.13.2.4.2 |  | 11 | q | -1 | (-9%) | 10
472 | 7411 | OzHccTXr25Mf4pmiIMuT | Normal | 11 | 1.9.9.13.2.4.4 | 1.9.9.13.2.4.4 |  | 11 | p | 2 | -18% | 13
473 | 7412 | obz02flxb00pYjKUpMNx | Normal | 12 | 1.9.9.13.2.5 | 1.9.9.13.2.5 |  | 12 | p | 1 | -8% | 13
474 | 7413 | xazO1XwNp5eROWJmaREL | Summary | 36 | 1.9.9.13.2.6 | 1.9.9.13.2.6 |  | 36 | p | 5 | -14% | 41
475 | 7415 | RsULMViXRZoYahxlMUQ4 | Normal | 20 | 1.9.9.13.2.6.2 | 1.9.9.13.2.6.2 |  | 20 | p | 4 | -20% | 24
476 | 7417 | yrCdbpyUp4mqkbXiv5Nc | Normal | 6 | 1.9.9.13.2.6.4 | 1.9.9.13.2.6.4 |  | 6 | q | -1 | (-17%) | 5
477 | 7418 | Iw5sTi596kP8d52cBWYm | Normal | 5 | 1.9.9.13.2.6.5 | 1.9.9.13.2.6.5 |  | 5 | p | 1 | -20% | 6
478 | 7420 | ia01m1zWF4qAvVLVg5It | Summary | 54 | 1.9.9.13.2.8 | 1.9.9.13.2.8 |  | 54 | q | -2 | (-4%) | 52
479 | 7423 | hs9Gt4WgG9pENnEIaC7X | Normal | 14 | 1.9.9.13.2.8.3 | 1.9.9.13.2.8.3 |  | 14 | p | 1 | -7% | 15
480 | 7424 | WqCakGr8mHgCENNWHHjW | Normal | 5 | 1.9.9.13.2.8.4 | 1.9.9.13.2.8.4 |  | 5 | p | 1 | -20% | 6
481 | 7425 | Pv27HXd826jlfuUJmTLH | Normal | 20 | 1.9.9.13.2.8.5 | 1.9.9.13.2.8.5 |  | 20 | q | -2 | (-10%) | 18
482 | 7426 | UjcYgNHyPV73fWy2GGNA | Normal | 5 | 1.9.9.13.2.8.6 | 1.9.9.13.2.8.6 |  | 5 | p | 1 | -20% | 6
483 | 7428 | C3roUkJ3GEdxAvfnxnUE | Normal | 6 | 1.9.9.13.2.8.8 | 1.9.9.13.2.8.8 |  | 6 | p | 1 | -17% | 7
484 | 7429 | GMfJSktlv5oUXA5LFNgA | Normal | 6 | 1.9.9.13.2.8.9 | 1.9.9.13.2.8.9 |  | 6 | q | -2 | (-33%) | 4
485 | 7430 | AjX0fOJfuCWTWcoFWrZe | Summary | 11 | 1.9.9.13.2.9 | 1.9.9.13.2.9 |  | 11 | p | 2 | -18% | 13
486 | 7433 | FxBsJSw4ZNEIyIQA8bL9 | Normal | 8 | 1.9.9.13.2.9.3 | 1.9.9.13.2.9.3 |  | 8 | p | 2 | -25% | 10
487 | 7435 | nSo6tYchIu2Aw4YtE45u | Summary | 44 | 1.9.9.13.4 | 1.9.9.13.4 |  | 44 | p | 2 | -5% | 46
488 | 7436 | Y83lvWkQwfsc3dMGwfVN | Summary | 30 | 1.9.9.13.4.1 | 1.9.9.13.4.1 |  | 30 | p | 2 | -7% | 32
489 | 7437 | E8EwVgjFQaEPGP66WsCb | Summary | 30 | 1.9.9.13.4.1.1 | 1.9.9.13.4.1.1 |  | 30 | q | -5 | (-17%) | 25
490 | 7438 | y2P0mgWq1uFkM4aVxtQJ | Normal | 15 | 1.9.9.13.4.1.1.1 | 1.9.9.13.4.1.1.1 |  | 15 | q | -3 | (-20%) | 12
491 | 7440 | 3ZzL4TktDwncii0hY2dA | Normal | 10 | 1.9.9.13.4.1.1.3 | 1.9.9.13.4.1.1.3 |  | 10 | q | -2 | (-20%) | 8
492 | 7441 | IcgrxiRjEYJLwuugm8N7 | Summary | 30 | 1.9.9.13.4.1.2 | 1.9.9.13.4.1.2 |  | 30 | p | 2 | -7% | 32
493 | 7442 | B8zfbswYxyRxHa21jaE6 | Normal | 15 | 1.9.9.13.4.1.2.1 | 1.9.9.13.4.1.2.1 |  | 15 | p | 1 | -7% | 16
494 | 7443 | lvFKaF8Jtq8DkkB0s9nv | Normal | 15 | 1.9.9.13.4.1.2.2 | 1.9.9.13.4.1.2.2 |  | 15 | p | 2 | -13% | 17
495 | 7444 | 419IszMaZW6XNIQptprk | Normal | 20 | 1.9.9.13.4.1.3 | 1.9.9.13.4.1.3 |  | 20 | p | 5 | -25% | 25
496 | 7445 | oNfFp4VAwKEpoSujTbHZ | Normal | 10 | 1.9.9.13.4.1.4 | 1.9.9.13.4.1.4 |  | 10 | p | 2 | -20% | 12
497 | 7450 | F3vtt1T8lz7mQWFPgUKT | Normal | 2 | 1.9.9.13.4.3 | 1.9.9.13.4.3 |  | 2 | q | -1 | (-50%) | 1
498 | 7513 | NbiRgc4Tdvxa900kw7Xq | Normal | 8 | 1.7.10.27 | 1.7.10.27 |  | 8 | q | -1 | (-12%) | 7
499 | 7542 | E3YdLEfamF0eZCISJiqw | Normal | 10 | 1.7.10.11 | 1.7.10.11 |  | 10 | q | -1 | (-10%) | 9
500 | 6279 | p7EJXT1muDSglD2OZLFH | Summary | 274 | 1.9.7 | 1.9.7 |  | 274 | p | 602 | -220% | 876
501 | 1484 | 6ARiGRg3KLswRpJLOmGD | Summary | 229 | 1.9.7.18 | 1.9.7.18 |  | 229 | p | 675 | -295% | 904
502 | 1485 | R0QJsNVi0JzXq4FadBdS | Normal | 20 | 1.9.7.18.4 | 1.9.7.18.4 |  | 20 | p | 2 | -10% | 22
503 | 1486 | 9VYbXOz4xuMas0igEBkB | Summary | 56 | 1.9.7.18.6 | 1.9.7.18.6 |  | 56 | p | 1 | -2% | 57
504 | 6540 | BF294XdCZHw2CEg81bOs | Normal | 19 | 1.9.7.18.6.1 | 1.9.7.18.6.1 |  | 19 | q | -1 | (-5%) | 18
505 | 6541 | X8phwYugZBkIbn0OysQW | Normal | 19 | 1.9.7.18.6.2 | 1.9.7.18.6.2 |  | 19 | p | 2 | -11% | 21
506 | 1489 | pYq4lU1lCt1U75q3gu6M | Normal | 11 | 1.9.7.18.1 | 1.9.7.18.1 |  | 11 | p | 1 | -9% | 12
507 | 1490 | hF9FI1LNvFfgTTXhqPsR | Normal | 77 | 1.9.7.18.2 | 1.9.7.18.2 |  | 77 | p | 1 | -1% | 78
508 | 4587 | 5uS9ktvplxYkrLheR3Q9 | Normal | 20 | 1.9.7.18.5 | 1.9.7.18.5 |  | 20 | p | 3 | -15% | 23
509 | 1496 | 5t2MhilpkZRDQA3VTcGS | Normal | 48 | 1.9.7.7 | 1.9.7.7 |  | 48 | p | 2 | -4% | 50
510 | 1505 | 4c3z8pWafVxAWNC1MpC9 | Normal | 106 | 1.9.7.8 | 1.9.7.8 |  | 106 | q | -3 | (-3%) | 103
511 | 1508 | SDZ1pqYbdynEzXZrWujj | Normal | 30 | 1.9.7.6 | 1.9.7.6 |  | 30 | q | -3 | (-10%) | 27
512 | 1529 | WOa3B8SPUOSM5ThLE2Jo | Summary | 69 | 1.9.7.14 | 1.9.7.14 |  | 69 | p | 4 | -6% | 73
513 | 1534 | SuchbNnj1ndABAEPQlrb | Normal | 10 | 1.9.7.14.6 | 1.9.7.14.6 |  | 10 | p | 1 | -10% | 11
514 | 1535 | vIOpwJGhGrQ4pKl5nahR | Summary | 61 | 1.9.7.15 | 1.9.7.15 |  | 61 | p | 1 | -2% | 62
515 | 1538 | 1Xm6i4dPIyAKJzF1jRtD | Normal | 45 | 1.9.7.15.3 | 1.9.7.15.3 |  | 45 | p | 2 | -4% | 47
516 | 1539 | ySsQ3GXU4tpHt4hn7HeO | Normal | 2 | 1.9.7.15.4 | 1.9.7.15.4 |  | 2 | q | -2 | (-100%) | 0
517 | 1540 | GIXHFfgJ4jA0lgUlb0GT | Normal | 1 | 1.9.7.15.5 | 1.9.7.15.5 |  | 1 | q | -1 | (-100%) | 0
518 | 1542 | VmFPpoMfVfLEXeRBF7Um | Normal | 9 | 1.9.7.15.8 | 1.9.7.15.8 |  | 9 | q | -1 | (-11%) | 8
519 | 1543 | P2oxmSB7jXG6Ib9VEZ89 | Normal | 9 | 1.9.7.15.9 | 1.9.7.15.9 |  | 9 | p | 2 | -22% | 11
520 | 4585 | Z4QB23UBk58Dyd3318zD | Normal | 10 | 1.9.7.15.6 | 1.9.7.15.6 |  | 10 | q | -3 | (-30%) | 7
521 | 1544 | dYtuUpkdltDWUtvWJGdC | Summary | 80 | 1.9.7.16 | 1.9.7.16 |  | 80 | p | 207 | -259% | 287
522 | 1549 | s8gTUDwRZFDpCO4enZqk | Normal | 15 | 1.9.7.16.6 | 1.9.7.16.6 |  | 15 | p | 302 | -2013% | 317
523 | 1550 | UoQFPyMNVa9QPyq2kgrl | Normal | 9 | 1.9.7.16.7 | 1.9.7.16.7 |  | 9 | q | -1 | (-11%) | 8
524 | 1560 | fBOtciokyA85OuE15WSO | Normal | 1 | 1.9.7.19.10 | 1.9.7.19.10 |  | 1 | q | -1 | (-100%) | 0
525 | 1561 | 8BMHpFsmSFY1BvBQKfdD | Normal | 10 | 1.9.7.19.11 | 1.9.7.19.11 |  | 10 | p | 2 | -20% | 12
526 | 4574 | z7UYZlhr663oN8lfFWmH | Summary | 29 | 1.9.7.11 | 1.9.7.11 |  | 29 | p | 3 | -10% | 32
527 | 4578 | kBeLaux8MTugqoi5KPvZ | Summary | 74 | 1.9.7.13 | 1.9.7.13 |  | 74 | p | 14 | -19% | 88
528 | 4581 | FxGRGf2kppDMdfFrZkS4 | Normal | 36 | 1.9.7.12 | 1.9.7.12 |  | 36 | q | -7 | (-19%) | 29
529 | 4588 | L1kgBhMEjlIJ4HNHh1TQ | Summary | 141 | 1.9.7.20 | 1.9.7.20 |  | 141 | q | -3 | (-2%) | 138
530 | 1566 | KFj0hxHWvExDoqTqgDeg | Normal | 118 | 1.9.7.20.1 | 1.9.7.20.1 |  | 118 | q | -2 | (-2%) | 116
531 | 1567 | GV5or0ucuouXZiqAkH0N | Normal | 10 | 1.9.7.20.2 | 1.9.7.20.2 |  | 10 | p | 2 | -20% | 12
532 | 1568 | JI4xSRBKV4FYnRXdw7Wz | Normal | 9 | 1.9.7.20.3 | 1.9.7.20.3 |  | 9 | q | -1 | (-11%) | 8
533 | 1569 | DVuFJt4FGQSIgeZkA41d | Normal | 4 | 1.9.7.20.4 | 1.9.7.20.4 |  | 4 | q | -1 | (-25%) | 3
534 | 6439 | JoFd6fDKN7NWznuQx6gK | Normal | 56 | 1.9.7.10 | 1.9.7.10 |  | 56 | q | -4 | (-7%) | 52
535 | 7323 | p8rF5Tk8321hO30p5zSy | Summary | 79 | 1.7.8.18 | 1.7.8.18 |  | 79 | p | 8 | -10% | 87
536 | 7455 | hQlezwT73UjuGPZkyuVr | Normal | 9 | 1.7.8.18.2 | 1.7.8.18.2 |  | 9 | q | -1 | (-11%) | 8
537 | 7456 | 3cfjdZ38xGBNf8roD7He | Normal | 9 | 1.7.8.18.3 | 1.7.8.18.3 |  | 9 | q | -1 | (-11%) | 8
538 | 7458 | cMhUMuxC0sax27543As7 | Normal | 24 | 1.7.8.18.5 | 1.7.8.18.5 |  | 24 | p | 2 | -8% | 26
539 | 7459 | xf7OMyoiQ38QdcweBYiq | Normal | 20 | 1.7.8.18.6 | 1.7.8.18.6 |  | 20 | p | 4 | -20% | 24
540 | 7382 | GJk3wpkfagyrb21gVciV | Summary | 288 | 1.9.7.22 | 1.9.7.22 |  | 288 | p | 1051 | -365% | 1339
541 | 7384 | xn1TRUhUfNd3ygHlAMk1 | Normal | 16 | 1.9.7.22.2 | 1.9.7.22.2 |  | 16 | q | -4 | (-25%) | 12
542 | 6285 | 0inPdnysTnfuJeCJJEwo | Summary | 131 | 1.9.1 | 1.9.1 |  | 131 | q | -1 | (-1%) | 130
543 | 4593 | XK8YU5H8vMrR7jBOr6fS | Normal | 99 | 1.9.1.1 | 1.9.1.1 |  | 99 | q | -8 | (-8%) | 91
544 | 4605 | jXRAJqcdCYbTQqzq5oVG | Normal | 14 | 1.7.3.2 | 1.7.3.2 |  | 14 | p | 1 | -7% | 15
545 | 4607 | 9Rf8xh1sYqA0mX8AIEgx | Summary | 52 | 1.7.3.5 | 1.7.3.5 |  | 52 | q | -4 | (-8%) | 48
546 | 4608 | tlJeJHdE7OwhwWyVvZ8P | Normal | 5 | 1.7.3.5.1 | 1.7.3.5.1 |  | 5 | q | -1 | (-20%) | 4
547 | 4613 | z0DGpsje53b33zXA5t1P | Normal | 20 | 1.7.3.5.6 | 1.7.3.5.6 |  | 20 | q | -3 | (-15%) | 17
548 | 4615 | Io6EVgFdyRjG7CB2g0Wy | Summary | 98 | 1.7.3.4 | 1.7.3.4 |  | 98 | p | 4 | -4% | 102
549 | 4616 | FR5tuVwQGmPNYmz6BeMP | Normal | 2 | 1.7.3.4.1 | 1.7.3.4.1 |  | 2 | q | -1 | (-50%) | 1
550 | 4618 | mRqsjEijsp2iSp4l7aof | Normal | 5 | 1.7.3.4.3 | 1.7.3.4.3 |  | 5 | p | 2 | -40% | 7
551 | 4619 | 8asUr7UOO8nabPagFvw9 | Normal | 40 | 1.7.3.4.4 | 1.7.3.4.4 |  | 40 | q | -2 | (-5%) | 38
552 | 4620 | UWR5akRFo4eKiDyQVnYr | Normal | 23 | 1.7.3.4.5 | 1.7.3.4.5 |  | 23 | q | -6 | (-26%) | 17
553 | 4622 | Bm2ajkWBwO6Cvc6RoPdK | Normal | 5 | 1.7.3.4.7 | 1.7.3.4.7 |  | 5 | p | 2 | -40% | 7
554 | 4623 | sDTQ4X48dvup817zb0Do | Normal | 20 | 1.7.3.4.8 | 1.7.3.4.8 |  | 20 | p | 1 | -5% | 21
555 | 4624 | 3CGv61AS00FFpM5LrRat | Normal | 20 | 1.7.3.4.9 | 1.7.3.4.9 |  | 20 | q | -1 | (-5%) | 19
556 | 4626 | 92oajspBBxTpnlNQO91I | Summary | 90 | 1.7.3.6 | 1.7.3.6 |  | 90 | q | -1 | (-1%) | 89
557 | 4630 | pjdWghPSPBEOfTIZFZhV | Normal | 5 | 1.7.3.6.4 | 1.7.3.6.4 |  | 5 | q | -1 | (-20%) | 4
558 | 4633 | STHfhyBuM5qFiEzHSgws | Normal | 19 | 1.7.3.6.7 | 1.7.3.6.7 |  | 19 | q | -3 | (-16%) | 16
559 | 6608 | ifCvUSq9UjUAw7FKKXTR | Normal | 14 | 1.7.3.7.3 | 1.7.3.7.3 |  | 14 | q | -1 | (-7%) | 13
560 | 7259 | Dcjo2uskRMoBajU90pQq | Normal | 60 | 1.7.1.4 | 1.7.1.4 |  | 60 | p | 2 | -3% | 62
561 | 6294 | Jtjxi70STISSeVqV8OJy | Summary | 163 | 1.9.6 | 1.9.6 |  | 163 | p | 99 | -61% | 262
562 | 3745 | D0mR64Wbk6oru5hoL4DG | Summary | 62 | 1.7.1.2 | 1.7.1.2 |  | 62 | p | 4 | -6% | 66
563 | 3773 | jfB1zdAbu7JeWEH3ijwy | Summary | 73 | 1.7.1.2.6 | 1.7.1.2.6 |  | 73 | p | 8 | -11% | 81
564 | 3776 | GHLE38QRMYNBeSYAGB18 | Normal | 32 | 1.7.1.2.6.3 | 1.7.1.2.6.3 |  | 32 | p | 2 | -6% | 34
565 | 3777 | YuGKQIQDxLVYRZzgUQjw | Normal | 9 | 1.7.1.2.6.4 | 1.7.1.2.6.4 |  | 9 | q | -1 | (-11%) | 8
566 | 3783 | FcDlmkxQNUOM36qP0M0H | Summary | 58 | 1.7.1.3 | 1.7.1.3 |  | 58 | p | 5 | -9% | 63
567 | 3790 | Om0YwWoKF5usOVLnDccR | Summary | 13 | 1.7.1.3.4 | 1.7.1.3.4 |  | 13 | p | 2 | -15% | 15
568 | 6977 | F0juzsyqTnJm6sTJe4ff | Normal | 14 | 1.7.1.3.4.7 | 1.7.1.3.4.7 |  | 14 | p | 2 | -14% | 16
569 | 6138 | EvFVoaLHb5OgszmS4Hdy | Summary | 44 | 1.7.1.3.9 | 1.7.1.3.9 |  | 44 | p | 1 | -2% | 45
570 | 6139 | VECMPYMi2oWf71g3eai1 | Normal | 29 | 1.7.1.3.9.1 | 1.7.1.3.9.1 |  | 29 | q | -2 | (-7%) | 27
571 | 6140 | mO0F0FFUdRVKYlb84WcT | Normal | 15 | 1.7.1.3.9.2 | 1.7.1.3.9.2 |  | 15 | p | 3 | -20% | 18
572 | 6978 | z4sj2SQJw3pdZet8Am0U | Normal | 9 | 1.7.1.3.5 | 1.7.1.3.5 |  | 9 | p | 2 | -22% | 11
573 | 6983 | PcmQnh6ym2R5IAKzFgwu | Summary | 141 | 1.7.1.3.7 | 1.7.1.3.7 |  | 141 | p | 19 | -13% | 160
574 | 6990 | K8cvVDryBsyahUujiNmr | Summary | 22 | 1.7.1.3.8 | 1.7.1.3.8 |  | 22 | p | 41 | -186% | 63
575 | 6982 | E06yVWmTg8kRS6Gv9kOV | Summary | 6 | 1.7.1.3.8.3 | 1.7.1.3.8.3 |  | 6 | p | 3 | -50% | 9
576 | 6991 | RAhO7UtYgqwLkhTknwrO | Normal | 6 | 1.7.1.3.8.1 | 1.7.1.3.8.1 |  | 6 | q | -1 | (-17%) | 5
577 | 3803 | vx1oFVBFPqydBxZJ7V4g | Summary | 112 | 1.7.1.5 | 1.7.1.5 |  | 112 | p | 21 | -19% | 133
578 | 3808 | mNtnU9AYiACOeBrTPE9f | Summary | 29 | 1.7.1.5.3 | 1.7.1.5.3 |  | 29 | q | -1 | (-3%) | 28
579 | 3809 | ukioB4iHiwrfEXpseTiK | Normal | 15 | 1.7.1.5.3.1 | 1.7.1.5.3.1 |  | 15 | p | 1 | -7% | 16
580 | 3810 | CJxWy7PnZPcI4EPHEeme | Normal | 9 | 1.7.1.5.3.2 | 1.7.1.5.3.2 |  | 9 | q | -2 | (-22%) | 7
581 | 3811 | wGtgxCT3lCK6u2EOL8xN | Normal | 5 | 1.7.1.5.3.3 | 1.7.1.5.3.3 |  | 5 | q | -2 | (-40%) | 3
582 | 3813 | sYeTNUsya13QYMbMJg21 | Normal | 25 | 1.7.1.5.7 | 1.7.1.5.7 |  | 25 | p | 1 | -4% | 26
583 | 3816 | 6MWmVgC0FSCF3lMoTGjJ | Summary | 40 | 1.7.1.5.10 | 1.7.1.5.10 |  | 40 | p | 14 | -35% | 54
584 | 3819 | FSVjbKFfUmqE2fpbGGPv | Normal | 3 | 1.7.1.5.10.3 | 1.7.1.5.10.3 |  | 3 | q | -1 | (-33%) | 2
585 | 3820 | FhKtXXrOwkDfPm4RFzRW | Normal | 10 | 1.7.1.5.10.4 | 1.7.1.5.10.4 |  | 10 | p | 1 | -10% | 11
586 | 3821 | cHjYAw102skS4vR6DXqX | Normal | 20 | 1.7.1.5.10.5 | 1.7.1.5.10.5 |  | 20 | p | 4 | -20% | 24
587 | 6147 | BUcWclFVChflBnUDJ9UM | Normal | 40 | 1.7.1.5.4 | 1.7.1.5.4 |  | 40 | p | 17 | -42% | 57
588 | 6148 | V03eKqopjAXoUvRodLvQ | Normal | 13 | 1.7.1.5.6 | 1.7.1.5.6 |  | 13 | p | 1 | -8% | 14
589 | 4078 | ybbKeBChK3D60QzH8ONZ | Normal | 76 | 1.9.6.5 | 1.9.6.5 |  | 76 | q | -3 | (-4%) | 73
590 | 4129 | G6dPcJRrq5zqLYx4Vr0R | Summary | 475 | 1.9.6.10 | 1.9.6.10 |  | 475 | p | 453 | -95% | 928
591 | 4131 | 3WZTLr4e3INGux4LMgj0 | Summary | 146 | 1.9.6.10.2 | 1.9.6.10.2 |  | 146 | q | -42 | (-29%) | 104
592 | 5861 | adMwYb1cwVT0ja23ZKPV | Normal | 10 | 1.9.6.10.2.5 | 1.9.6.10.2.5 |  | 10 | q | -1 | (-10%) | 9
593 | 5862 | rkVKH7eSVnkv5Rz0hIbo | Normal | 25 | 1.9.6.10.2.6 | 1.9.6.10.2.6 |  | 25 | p | 3 | -12% | 28
594 | 5863 | axx1H8vuWtNbWz6aJYpW | Normal | 20 | 1.9.6.10.2.7 | 1.9.6.10.2.7 |  | 20 | p | 3 | -15% | 23
595 | 5864 | ZuXAUp7kzm7PDgs0Clm4 | Normal | 20 | 1.9.6.10.2.8 | 1.9.6.10.2.8 |  | 20 | q | -3 | (-15%) | 17
596 | 5867 | 6vMprMC9ZRYTg9c055cw | Normal | 3 | 1.9.6.10.2.11 | 1.9.6.10.2.11 |  | 3 | q | -1 | (-33%) | 2
597 | 5870 | rLlKwDBGmyMe6lxLtymf | Summary | 59 | 1.9.6.10.3 | 1.9.6.10.3 |  | 59 | p | 6 | -10% | 65
598 | 5871 | owx5unCKcaLauhH4kWyj | Normal | 5 | 1.9.6.10.3.1 | 1.9.6.10.3.1 |  | 5 | p | 1 | -20% | 6
599 | 5872 | qImIYF1Y50rp0FNnsaoS | Normal | 10 | 1.9.6.10.3.2 | 1.9.6.10.3.2 |  | 10 | p | 2 | -20% | 12
600 | 5873 | FfFQqcMQ2fY5X0GvK0Xd | Normal | 20 | 1.9.6.10.3.3 | 1.9.6.10.3.3 |  | 20 | p | 5 | -25% | 25
601 | 6624 | sVpbcWAee9M5eeft5sdO | Normal | 15 | 1.9.6.10.3.4 | 1.9.6.10.3.4 |  | 15 | q | -2 | (-13%) | 13
602 | 6625 | it5qGsWYKIf8fEL1a2TB | Normal | 5 | 1.9.6.10.3.5 | 1.9.6.10.3.5 |  | 5 | p | 1 | -20% | 6
603 | 5877 | 8uIO0L3CbsjXfYIL70ur | Summary | 162 | 1.9.6.10.4 | 1.9.6.10.4 |  | 162 | p | 56 | -35% | 218
604 | 5878 | eKJmpIIS7eePXp789pq5 | Summary | 60 | 1.9.6.10.4.1 | 1.9.6.10.4.1 |  | 60 | p | 1 | -2% | 61
605 | 5880 | z8rht75g90pc62Jd1j8e | Normal | 15 | 1.9.6.10.4.1.1.1 | 1.9.6.10.4.1.1.1 |  | 15 | q | -2 | (-13%) | 13
606 | 5881 | ZPPJV7wrbqyTumtl84NX | Normal | 15 | 1.9.6.10.4.1.1.2 | 1.9.6.10.4.1.1.2 |  | 15 | p | 1 | -7% | 16
607 | 5882 | PdfqDNDAaUS1Z9tfvPSB | Normal | 15 | 1.9.6.10.4.1.2 | 1.9.6.10.4.1.2 |  | 15 | q | -1 | (-7%) | 14
608 | 5883 | 3J3dFKPf8v7HKW1lSal4 | Normal | 15 | 1.9.6.10.4.1.3 | 1.9.6.10.4.1.3 |  | 15 | p | 2 | -13% | 17
609 | 5884 | J3ZDJxR9DKKi4JquRb3Q | Summary | 20 | 1.9.6.10.4.2 | 1.9.6.10.4.2 |  | 20 | p | 2 | -10% | 22
610 | 5887 | xjL6okqGZuFc1ChaUzA0 | Normal | 5 | 1.9.6.10.4.2.3 | 1.9.6.10.4.2.3 |  | 5 | p | 1 | -20% | 6
611 | 4134 | 86JmjjOtZxj7XQRp3CQF | Summary | 466 | 1.9.6.11 | 1.9.6.11 |  | 466 | p | 277 | -59% | 743
612 | 4135 | 0voiyAtBe9AzaXfs8cVF | Summary | 322 | 1.9.6.11.1 | 1.9.6.11.1 |  | 322 | p | 192 | -60% | 514
613 | 4138 | 75WgU7H7MCC8DDgOcnsD | Normal | 30 | 1.9.6.11.1.3 | 1.9.6.11.1.3 |  | 30 | q | -2 | (-7%) | 28
614 | 4139 | 9SKpfzivi43NDDuHUq0B | Normal | 5 | 1.9.6.11.1.4 | 1.9.6.11.1.4 |  | 5 | q | -1 | (-20%) | 4
615 | 4140 | Lk7gef35zB3WaxM8Xyxe | Summary | 48 | 1.9.6.11.2 | 1.9.6.11.2 |  | 48 | p | 1 | -2% | 49
616 | 4141 | HGo5Ep3pqhcsiM5K4QjA | Summary | 23 | 1.9.6.11.2.1 | 1.9.6.11.2.1 |  | 23 | p | 2 | -9% | 25
617 | 4142 | VTqJrDLpWuaSlvRQajcM | Normal | 12 | 1.9.6.11.2.1.1 | 1.9.6.11.2.1.1 |  | 12 | p | 1 | -8% | 13
618 | 4143 | UwGhtpl5Mnq9WQrcrXRR | Normal | 11 | 1.9.6.11.2.1.2 | 1.9.6.11.2.1.2 |  | 11 | p | 1 | -9% | 12
619 | 4144 | zaFQ6K5wegGvKt6DGuoz | Summary | 25 | 1.9.6.11.2.2 | 1.9.6.11.2.2 |  | 25 | q | -1 | (-4%) | 24
620 | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Normal | 10 | 1.9.6.11.2.2.1 | 1.9.6.11.2.2.1 |  | 10 | q | -1 | (-10%) | 9
621 | 4146 | rTeXGnIwGPt6ES3ynSHq | Normal | 5 | 1.9.6.11.2.2.2 | 1.9.6.11.2.2.2 |  | 5 | q | -1 | (-20%) | 4
622 | 4147 | hQaW5HIstT5bbsPEBxyQ | Normal | 10 | 1.9.6.11.2.2.3 | 1.9.6.11.2.2.3 |  | 10 | p | 1 | -10% | 11
623 | 5753 | ZptYdARXANY2IOcoHhB1 | Summary | 78 | 1.9.6.1 | 1.9.6.1 |  | 78 | p | 70 | -90% | 148
624 | 5999 | hTF24jclc5ogfsrVWXZd | Normal | 40 | 1.9.6.1.7.1 | 1.9.6.1.7.1 |  | 40 | p | 1 | -2% | 41
625 | 6004 | xOhJcEwgSz1TAvNHU4tB | Normal | 40 | 1.9.6.1.8.1 | 1.9.6.1.8.1 |  | 40 | q | -12 | (-30%) | 28
626 | 6008 | Ph5VFx7Ghit4AwZEFBXT | Summary | 50 | 1.9.6.1.6 | 1.9.6.1.6 |  | 50 | q | -1 | (-2%) | 49
627 | 6009 | NVgukc0KZBShUa0wIlyx | Normal | 30 | 1.9.6.1.6.1 | 1.9.6.1.6.1 |  | 30 | p | 2 | -7% | 32
628 | 6010 | tIYqVtlT4yOF2YQ2FRYY | Normal | 10 | 1.9.6.1.6.2 | 1.9.6.1.6.2 |  | 10 | q | -1 | (-10%) | 9
629 | 6012 | Z1jpWQx4GyFcVoEVg0i0 | Normal | 5 | 1.9.6.1.6.4 | 1.9.6.1.6.4 |  | 5 | q | -1 | (-20%) | 4
630 | 6013 | y2dxMv99iLhGOXikZGuK | Summary | 34 | 1.9.6.1.5 | 1.9.6.1.5 |  | 34 | q | -2 | (-6%) | 32
631 | 6014 | hYHiAVYfHXdDTdWEk9J8 | Normal | 15 | 1.9.6.1.5.1 | 1.9.6.1.5.1 |  | 15 | q | -1 | (-7%) | 14
632 | 6016 | gwhB80Lv7eu4PoYwev8o | Normal | 5 | 1.9.6.1.5.3 | 1.9.6.1.5.3 |  | 5 | q | -1 | (-20%) | 4
633 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | 20 | q | -20 | (-100%) | 0
634 | 6957 | ar01N24L63iczVEh1mVo | Summary | 24 | 1.9.6.1.4 | 1.9.6.1.4 |  | 24 | q | -2 | (-8%) | 22
635 | 6958 | 6Ul4V6iAcnpVqewOp14Y | Normal | 4 | 1.9.6.1.4.1 | 1.9.6.1.4.1 |  | 4 | q | -1 | (-25%) | 3
636 | 6959 | w9Vvv79ftt4PUqInNFyD | Normal | 5 | 1.9.6.1.4.2 | 1.9.6.1.4.2 |  | 5 | q | -1 | (-20%) | 4
637 | 6961 | NOksVV7sTymsgwMrnh6x | Normal | 10 | 1.9.6.1.4.4 | 1.9.6.1.4.4 |  | 10 | q | -1 | (-10%) | 9
638 | 5762 | BY50RWHTB6QfyvgvJksd | Summary | 36 | 1.9.6.9 | 1.9.6.9 |  | 36 | p | 2 | -6% | 38
639 | 6424 | xU9ngPKik2IYPonksYTK | Summary | 24 | 1.7.1.8 | 1.7.1.8 |  | 24 | q | -23 | (-96%) | 1
640 | 6296 | SlR21lje1Tex9DLMlAM1 | Summary | 222 | 1.9.8 | 1.9.8 |  | 222 | p | 87 | -39% | 309
641 | 4192 | vUDAXlHZqbmK6WAsX9hH | Summary | 139 | 1.9.8.1 | 1.9.8.1 |  | 139 | q | -26 | (-19%) | 113
642 | 4196 | 2ZwOzHGH45ywtPvfASSG | Normal | 5 | 1.9.8.1.5 | 1.9.8.1.5 |  | 5 | p | 1 | -20% | 6
643 | 4197 | 4xVk2zrTd9sJnt9BJFir | Summary | 36 | 1.9.8.1.6 | 1.9.8.1.6 |  | 36 | p | 8 | -22% | 44
644 | 4198 | k6X8NWhjfeQOPZdDpmna | Normal | 20 | 1.9.8.1.9 | 1.9.8.1.9 |  | 20 | p | 1 | -5% | 21
645 | 5985 | AUKn3E7aViOsULw8HdKV | Normal | 131 | 1.9.8.1.12 | 1.9.8.1.12 |  | 131 | q | -34 | (-26%) | 97
646 | 4222 | uotgqiCu1xVBvHdpBC3E | Summary | 97 | 1.9.8.2 | 1.9.8.2 |  | 97 | q | -29 | (-30%) | 68
647 | 4235 | QiaATNQSPId7svzcuO8r | Normal | 91 | 1.9.8.2.7 | 1.9.8.2.7 |  | 91 | q | -30 | (-33%) | 61
648 | 4238 | ReJqSs3gutB053iVY5c7 | Summary | 76 | 1.9.8.4 | 1.9.8.4 |  | 76 | p | 12 | -16% | 88
649 | 4242 | RIVyyga7UReDeuixs5m9 | Normal | 66 | 1.9.8.4.4 | 1.9.8.4.4 |  | 66 | p | 10 | -15% | 76
650 | 4246 | ANAzXnUTz1PCb3xsov4Y | Normal | 10 | 1.9.8.4.7 | 1.9.8.4.7 |  | 10 | q | -1 | (-10%) | 9
651 | 4256 | G2pYfP7dsnHVTgqQD6mD | Summary | 82 | 1.9.8.10 | 1.9.8.10 |  | 82 | p | 3 | -4% | 85
652 | 4258 | GzQkXlTiYJMdE6nBDVeb | Normal | 6 | 1.9.8.10.1 | 1.9.8.10.1 |  | 6 | q | -1 | (-17%) | 5
653 | 6090 | LkexiRQNUDyJAwm8EPYV | Normal | 32 | 1.9.8.10.7 | 1.9.8.10.7 |  | 32 | p | 4 | -12% | 36
654 | 6430 | IYyY3jK4t9QuDyuxqyQ5 | Normal | 15 | 1.9.8.10.2 | 1.9.8.10.2 |  | 15 | q | -2 | (-13%) | 13
655 | 6431 | mXx66gQ5BZWpD3idmZgM | Normal | 10 | 1.9.8.10.3 | 1.9.8.10.3 |  | 10 | p | 2 | -20% | 12
656 | 6432 | vMoeJo3Rc30lMwFim6rn | Normal | 10 | 1.9.8.10.4 | 1.9.8.10.4 |  | 10 | p | 1 | -10% | 11
657 | 6314 | PaZTrKFuMaJQzXHDclW5 | Summary | 34 | 1.9.2 | 1.9.2 |  | 34 | p | 11 | -32% | 45
658 | 5666 | lc2LPCzbTjVw9vZ8eS89 | Summary | 23 | 1.9.2.2 | 1.9.2.2 |  | 23 | p | 19 | -83% | 42
659 | 5667 | chBvra0KGhqU3lfHBAI4 | Summary | 23 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 23 | p | 19 | -83% | 42
660 | 5669 | bBSx7g3AuM8uxZcIYlIi | Normal | 20 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 20 | p | 18 | -90% | 38
661 | 5672 | 2GDxhVAL0LbO4lfSMjXo | Summary | 47 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 47 | p | 4 | -9% | 51
662 | 5690 | jLB7gq1wR8egZrMIoAc7 | Summary | 24 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 24 | q | -2 | (-8%) | 22
663 | 5691 | glUuWw43f2R9t2hl6VHO | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 10 | q | -3 | (-30%) | 7
664 | 5693 | VdKRFLdSc60knizSqFXc | Normal | 14 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 14 | p | 1 | -7% | 15
665 | 5694 | Gb0taOZcQ8l0cdHliY6j | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 10 | p | 2 | -20% | 12
666 | 5697 | 4nIBzBv3LSP60HeOLv0f | Normal | 5 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 5 | p | 1 | -20% | 6
667 | 6315 | 2iW64uJmzViIcLEo0dMn | Summary | 181 | 1.9.5 | 1.9.5 |  | 181 | p | 241 | -133% | 422
668 | 5532 | NHN4dwEEPEqCDqA4Rwlr | Summary | 74 | 1.9.5.1 | 1.9.5.1 |  | 74 | q | -18 | (-24%) | 56
669 | 5533 | g1oQNBzKk6OrBukgGH7R | Normal | 40 | 1.9.5.1.3 | 1.9.5.1.3 |  | 40 | q | -40 | (-100%) | 0
670 | 5535 | XVk7S0ldLHQUWflKhMBn | Normal | 11 | 1.9.5.1.2 | 1.9.5.1.2 |  | 11 | q | -2 | (-18%) | 9
671 | 5536 | cYU0DBZylLxVRoLEp7Bc | Normal | 40 | 1.9.5.1.4 | 1.9.5.1.4 |  | 40 | p | 14 | -35% | 54
672 | 5537 | 9xVQhmyTVkChMoMOy91g | Summary | 193 | 1.9.5.2 | 1.9.5.2 |  | 193 | p | 444 | -230% | 637
673 | 5539 | kRsO3PSMDsMxji3dmdNc | Normal | 5 | 1.9.5.2.2 | 1.9.5.2.2 |  | 5 | p | 623 | -12460% | 628
674 | 5540 | GKx3XnA1BSbhTsgdKbqP | Normal | 14 | 1.9.5.2.8 | 1.9.5.2.8 |  | 14 | p | 4 | -29% | 18
675 | 5542 | 4ivItsonCrTGke19i41Z | Normal | 15 | 1.9.5.2.6 | 1.9.5.2.6 |  | 15 | p | 1 | -7% | 16
676 | 5543 | XaHBDo6QUBfyTg5ESk7j | Normal | 15 | 1.9.5.2.9 | 1.9.5.2.9 |  | 15 | p | 5 | -33% | 20
677 | 5544 | cIc3ARzcdrbXv6maHllr | Summary | 129 | 1.9.5.2.13 | 1.9.5.2.13 |  | 129 | p | 636 | -493% | 765
678 | 5545 | 7UVU8IboY6NG7sqZCrUC | Normal | 7 | 1.9.5.2.13.2 | 1.9.5.2.13.2 |  | 7 | q | -1 | (-14%) | 6
679 | 5546 | Shs5wuYOFSkTF1YslX8w | Normal | 6 | 1.9.5.2.13.5 | 1.9.5.2.13.5 |  | 6 | p | 1 | -17% | 7
680 | 5548 | Zfzda0CfmpiN8ZL93G3t | Normal | 5 | 1.9.5.2.13.9 | 1.9.5.2.13.9 |  | 5 | p | 1 | -20% | 6
681 | 5556 | fOMVaiOa0jnHOJyDUdVQ | Normal | 25 | 1.9.5.2.13.11 | 1.9.5.2.13.11 |  | 25 | p | 1 | -4% | 26
682 | 7000 | yP1oDcnUQTy3g68ZLgu0 | Normal | 8 | 1.9.5.2.13.1 | 1.9.5.2.13.1 |  | 8 | q | -2 | (-25%) | 6
683 | 5557 | U376LwOjKfNZoVLUlmMD | Summary | 113 | 1.9.5.2.12 | 1.9.5.2.12 |  | 113 | p | 636 | -563% | 749
684 | 5558 | RXAxJx3BHWNVdWFPfZ2a | Normal | 13 | 1.9.5.2.12.2 | 1.9.5.2.12.2 |  | 13 | p | 1 | -8% | 14
685 | 5561 | Vb2zzMF18WNANxlCzGiz | Normal | 5 | 1.9.5.2.12.9 | 1.9.5.2.12.9 |  | 5 | q | -1 | (-20%) | 4
686 | 5569 | 35aiC9HLOSrIl2OBwDvd | Normal | 25 | 1.9.5.2.12.11 | 1.9.5.2.12.11 |  | 25 | p | 3 | -12% | 28
687 | 5734 | iq9bjqBZvH9Bj6912271 | Normal | 6 | 1.9.5.2.12.3 | 1.9.5.2.12.3 |  | 6 | p | 1 | -17% | 7
688 | 5737 | iDzIA8f8DQgg2wVNkaUu | Normal | 7 | 1.9.5.2.12.7 | 1.9.5.2.12.7 |  | 7 | p | 1 | -14% | 8
689 | 7001 | WpRQh8HvPfyDha8FH5FR | Normal | 9 | 1.9.5.2.12.1 | 1.9.5.2.12.1 |  | 9 | p | 1 | -11% | 10
690 | 5570 | MuDwSgsBJjDxwFkSMWYJ | Summary | 116 | 1.9.5.2.11 | 1.9.5.2.11 |  | 116 | p | 418 | -360% | 534
691 | 5571 | lfRAbO0c5jl7NaC6s7pm | Normal | 21 | 1.9.5.2.11.2 | 1.9.5.2.11.2 |  | 21 | p | 1 | -5% | 22
692 | 5572 | jk3Vm36iIGViuk9dpLfQ | Normal | 8 | 1.9.5.2.11.5 | 1.9.5.2.11.5 |  | 8 | q | -3 | (-38%) | 5
693 | 5574 | 3iKE3riinMPRUpVpTfwx | Normal | 5 | 1.9.5.2.11.9 | 1.9.5.2.11.9 |  | 5 | p | 1 | -20% | 6
694 | 5582 | 6tLu8emqwotxTkeBbEpy | Normal | 26 | 1.9.5.2.11.11 | 1.9.5.2.11.11 |  | 26 | q | -5 | (-19%) | 21
695 | 5583 | gkFBoXdv1oJb2jtBcO5M | Summary | 147 | 1.9.5.2.14 | 1.9.5.2.14 |  | 147 | p | 643 | -437% | 790
696 | 5587 | OXOUsYDejGVlgqn4Z1vl | Normal | 5 | 1.9.5.2.14.9 | 1.9.5.2.14.9 |  | 5 | p | 1 | -20% | 6
697 | 5595 | REFTk0AP9RBTibJWVhuH | Normal | 26 | 1.9.5.2.14.11 | 1.9.5.2.14.11 |  | 26 | p | 5 | -19% | 31
698 | 5742 | 88bEv4EMiOL2y8w1ttIM | Normal | 4 | 1.9.5.2.14.3 | 1.9.5.2.14.3 |  | 4 | p | 1 | -25% | 5
699 | 5744 | cSBfnbrbVLLFYTMEfBKA | Normal | 6 | 1.9.5.2.14.6 | 1.9.5.2.14.6 |  | 6 | p | 1 | -17% | 7
700 | 5745 | ZY99Y6JX4jBylnfeedvo | Normal | 6 | 1.9.5.2.14.7 | 1.9.5.2.14.7 |  | 6 | q | -1 | (-17%) | 5
701 | 6446 | XvbStahAymwCoqNIbMJG | Summary | 32 | 1.9.5.2.4 | 1.9.5.2.4 |  | 32 | q | -2 | (-6%) | 30
702 | 6532 | 15e7xcLR1b1jSikaz0S2 | Normal | 32 | 1.9.5.2.4.2 | 1.9.5.2.4.2 |  | 32 | q | -3 | (-9%) | 29
703 | 6533 | b0mutjzKj8FRw4zkbb8K | Normal | 32 | 1.9.5.2.4.1 | 1.9.5.2.4.1 |  | 32 | q | -2 | (-6%) | 30
704 | 6534 | 8Gl2bk4Fxxo2fsClDJqG | Normal | 32 | 1.9.5.2.4.3 | 1.9.5.2.4.3 |  | 32 | q | -4 | (-12%) | 28
705 | 6535 | dWze9AnK8NrEMD9LOEyU | Normal | 32 | 1.9.5.2.4.4 | 1.9.5.2.4.4 |  | 32 | q | -4 | (-12%) | 28
706 | 6528 | LROLnQke0gWnMONa67YB | Summary | 50 | 1.9.5.2.5 | 1.9.5.2.5 |  | 50 | p | 11 | -22% | 61
707 | 6531 | iX155TL3hNg9Ca4Bsb4A | Normal | 35 | 1.9.5.2.5.2 | 1.9.5.2.5.2 |  | 35 | p | 1 | -3% | 36
708 | 6955 | CPACk87DS0kpO7pXcdwS | Normal | 10 | 1.9.5.2.10 | 1.9.5.2.10 |  | 10 | p | 1 | -10% | 11
709 | 6997 | MBGoTUikAECGvIHYk1uV | Normal | 24 | 1.9.5.2.3 | 1.9.5.2.3 |  | 24 | q | -1 | (-4%) | 23
710 | 5596 | upn4QoZvaKBmBMoyhnq5 | Summary | 90 | 1.9.5.3 | 1.9.5.3 |  | 90 | p | 7 | -8% | 97
711 | 5597 | zKJsJYNcPRFZ7wBjvprv | Normal | 18 | 1.9.5.3.1 | 1.9.5.3.1 |  | 18 | q | -1 | (-6%) | 17
712 | 5598 | zvvzNQqIPXzcVRwy0N44 | Summary | 52 | 1.9.5.3.2 | 1.9.5.3.2 |  | 52 | p | 6 | -12% | 58
713 | 5599 | T0Oh47cWIVU9y2MKPB0U | Normal | 12 | 1.9.5.3.2.1 | 1.9.5.3.2.1 |  | 12 | p | 1 | -8% | 13
714 | 5600 | oTkX6bjokLXQ590hdeFy | Normal | 12 | 1.9.5.3.2.2 | 1.9.5.3.2.2 |  | 12 | p | 4 | -33% | 16
715 | 5601 | xa7cRxeKgQxZnuHNAYMQ | Normal | 12 | 1.9.5.3.2.3 | 1.9.5.3.2.3 |  | 12 | q | -3 | (-25%) | 9
716 | 5602 | QlxDegibloFbHrPNJwyW | Normal | 12 | 1.9.5.3.2.4 | 1.9.5.3.2.4 |  | 12 | p | 2 | -17% | 14
717 | 6189 | OaskfHPb0rGXxqxmUlvr | Summary | 69 | 1.7.2.7 | 1.7.2.7 |  | 69 | p | 9 | -13% | 78
718 | 6248 | DGpV8AP7Q4dyYuiDaoIl | Summary | 56 | 1.7.2.7.2 | 1.7.2.7.2 |  | 56 | p | 12 | -21% | 68
719 | 6251 | Ha7ZmVRhPp4EjAGEFQOQ | Normal | 56 | 1.7.2.7.2.3 | 1.7.2.7.2.3 |  | 56 | p | 9 | -16% | 65
720 | 6252 | FwTW8u2nmxBgH6wyvtoz | Summary | 56 | 1.7.2.7.3 | 1.7.2.7.3 |  | 56 | p | 4 | -7% | 60
721 | 6255 | 6Rcxv4eHz2WhxfD2wxtd | Normal | 56 | 1.7.2.7.3.3 | 1.7.2.7.3.3 |  | 56 | p | 1 | -2% | 57
722 | 6256 | TcRehVKUpIeirJTvWiO5 | Summary | 14 | 1.7.2.7.4 | 1.7.2.7.4 |  | 14 | p | 2 | -14% | 16
723 | 6259 | q6ww59eaDtL5Df1J4lsR | Normal | 14 | 1.7.2.7.4.3 | 1.7.2.7.4.3 |  | 14 | p | 1 | -7% | 15
724 | 6260 | nYwGXpoj6WqcdUPfZoTk | Summary | 14 | 1.7.2.7.5 | 1.7.2.7.5 |  | 14 | p | 4 | -29% | 18
725 | 6263 | aKytB1b2oD2t1WVaznUP | Normal | 14 | 1.7.2.7.5.3 | 1.7.2.7.5.3 |  | 14 | p | 3 | -21% | 17
726 | 6317 | NzqiT3qChWGoVO5Oxj9C | Summary | 111 | 1.9.4 | 1.9.4 |  | 111 | p | 102 | -92% | 213
727 | 5355 | lohINUHwZqjP23W1PYQO | Summary | 26 | 1.9.4.1 | 1.9.4.1 |  | 26 | q | -24 | (-92%) | 2
728 | 5358 | Tenn83cNUrlWZNLgXJG2 | Normal | 2 | 1.9.4.1.2 | 1.9.4.1.2 |  | 2 | q | -2 | (-100%) | 0
729 | 5359 | VhUQP0fhGYyFZ67e4nln | Normal | 2 | 1.9.4.1.3 | 1.9.4.1.3 |  | 2 | q | -2 | (-100%) | 0
730 | 5360 | ARncD9Nx3De5DONPy9Bs | Normal | 3 | 1.9.4.1.4 | 1.9.4.1.4 |  | 3 | q | -1 | (-33%) | 2
731 | 7262 | dH18W6KApKWC8TAOWb50 | Normal | 36 | 1.7.4.1.4 | 1.7.4.1.4 |  | 36 | q | -36 | (-100%) | 0
732 | 5362 | 4bsxfawvV6TKTvCq9VoB | Summary | 6 | 1.9.4.2 | 1.9.4.2 |  | 6 | p | 230 | -3833% | 236
733 | 7260 | DPsh83rHAyIaiD8XYnO0 | Normal | 6 | 1.7.4.2.4 | 1.7.4.2.4 |  | 6 | p | 323 | -5383% | 329
734 | 5375 | zkXPpJkHw8DPAtspwcmA | Summary | 124 | 1.9.4.4 | 1.9.4.4 |  | 124 | p | 66 | -53% | 190
735 | 5376 | zSTdFwWI5FOaluV37lYS | Normal | 63 | 1.9.4.4.1 | 1.9.4.4.1 |  | 63 | q | -7 | (-11%) | 56
736 | 5377 | Wv5w7NMYDRM71nE6dVi0 | Summary | 58 | 1.9.4.5 | 1.9.4.5 |  | 58 | q | -2 | (-3%) | 56
737 | 5379 | 7aIIakNe0KPRF0TCK1un | Normal | 2 | 1.9.4.5.2 | 1.9.4.5.2 |  | 2 | q | -2 | (-100%) | 0
738 | 5381 | HgkAkSCruVdxdZyXC7sW | Normal | 4 | 1.9.4.5.4 | 1.9.4.5.4 |  | 4 | q | -4 | (-100%) | 0
739 | 5383 | u1aficyBQ2O9A8MnpdfZ | Normal | 20 | 1.9.4.5.6 | 1.9.4.5.6 |  | 20 | p | 5 | -25% | 25
740 | 5385 | ohwsmv9qOoV0RNzIdjJI | Normal | 15 | 1.9.4.5.8 | 1.9.4.5.8 |  | 15 | p | 2 | -13% | 17
741 | 5386 | tSuemAovBYAaHNhFiwaF | Normal | 15 | 1.9.4.5.9 | 1.9.4.5.9 |  | 15 | q | -3 | (-20%) | 12
742 | 5387 | 9gTKo9vjb1rQAbWcTOOW | Summary | 58 | 1.9.4.6 | 1.9.4.6 |  | 58 | q | -8 | (-14%) | 50
743 | 5389 | 0FrUudkzBjpolAMz4tT0 | Normal | 2 | 1.9.4.6.2 | 1.9.4.6.2 |  | 2 | q | -2 | (-100%) | 0
744 | 5391 | rUGJjnqPCImSizDtYOdy | Normal | 4 | 1.9.4.6.4 | 1.9.4.6.4 |  | 4 | q | -4 | (-100%) | 0
745 | 5392 | TRJmldmXNRf3NwsZhgng | Normal | 20 | 1.9.4.6.5 | 1.9.4.6.5 |  | 20 | q | -2 | (-10%) | 18
746 | 5394 | ungpeNo64cspVo3BuO9g | Normal | 10 | 1.9.4.6.7 | 1.9.4.6.7 |  | 10 | p | 1 | -10% | 11
747 | 5395 | KZXvYFda88KgX9w7a3ES | Normal | 15 | 1.9.4.6.8 | 1.9.4.6.8 |  | 15 | q | -1 | (-7%) | 14
748 | 5396 | FNjsTUKVT29tBcVlvaM6 | Normal | 15 | 1.9.4.6.9 | 1.9.4.6.9 |  | 15 | q | -2 | (-13%) | 13
749 | 5397 | KGrMeH5y6HH9dj1tr8uB | Summary | 53 | 1.9.4.7 | 1.9.4.7 |  | 53 | p | 4 | -8% | 57
750 | 5398 | EMMfZLgDhvN5O0lAfznQ | Normal | 15 | 1.9.4.7.1 | 1.9.4.7.1 |  | 15 | p | 1 | -7% | 16
751 | 5401 | WWZjxA63YxH38hnYmVKG | Normal | 8 | 1.9.4.7.4 | 1.9.4.7.4 |  | 8 | p | 3 | -38% | 11
752 | 5402 | zDUD70mdAG3rcozejCwk | Summary | 15 | 1.9.4.8 | 1.9.4.8 |  | 15 | p | 264 | -1760% | 279
753 | 5403 | wP2WbhW6upJb7JmdzCw1 | Normal | 9 | 1.9.4.8.1 | 1.9.4.8.1 |  | 9 | p | 1 | -11% | 10
754 | 5404 | UrewlDJ3J2c8Ueci7p9E | Normal | 6 | 1.9.4.8.2 | 1.9.4.8.2 |  | 6 | q | -1 | (-17%) | 5
755 | 7265 | uNFJkQaxxZ7oOYaM8QxX | Normal | 13 | 1.7.4.3.6.1 | 1.7.4.3.6.1 |  | 13 | p | 1 | -8% | 14
756 | 7266 | y7TR6NxR4uOKxinxsnEt | Normal | 13 | 1.7.4.3.6.2 | 1.7.4.3.6.2 |  | 13 | q | -1 | (-8%) | 12
757 | 7267 | f0BUmD79ZhKqjjzrwXUq | Normal | 13 | 1.7.4.3.6.3 | 1.7.4.3.6.3 |  | 13 | p | 1 | -8% | 14
758 | 7322 | XsHCl5GkwKVP3xy7r0jT | Summary | 85 | 1.7.5 | 1.7.5 |  | 85 | p | 5 | -6% | 90
759 | 7528 | 8SnF5zCB4rJyZyQZLLZc | Normal | 8 | 1.7.5.1 | 1.7.5.1 |  | 8 | p | 3 | -38% | 11
760 | 7531 | WsQS39Ko43y2ykuRUNnk | Normal | 8 | 1.7.5.4 | 1.7.5.4 |  | 8 | p | 2 | -25% | 10
761 | 7532 | tNKjUDGuH9lZvW14y0xJ | Normal | 22 | 1.7.5.5 | 1.7.5.5 |  | 22 | p | 1 | -5% | 23
762 | 7533 | HKUUjAeDBFLcgj42uw3c | Normal | 19 | 1.7.5.6 | 1.7.5.6 |  | 19 | p | 2 | -11% | 21
763 | 7534 | s7VTtgJqjYjf9pbLYcYj | Normal | 8 | 1.7.5.7 | 1.7.5.7 |  | 8 | q | -1 | (-12%) | 7
764 | 7535 | uGgP1gHCy12zlVFcLeTG | Normal | 6 | 1.7.5.8 | 1.7.5.8 |  | 6 | q | -1 | (-17%) | 5
765 | 7536 | kbIucnV7qsI0ZjxbK1cH | Normal | 6 | 1.7.5.9 | 1.7.5.9 |  | 6 | p | 1 | -17% | 7
766 | 6688 | aKOlgm9Tw9oPXF0YCFLp | Summary | 911 | 1.11 | 1.11 |  | 911 | q | -119 | (-13%) | 792
767 | 6689 | fEYxMDiPOAwjjU8zha5c | Normal | 396 | 1.11.1 | 1.11.1 |  | 396 | q | -102 | (-26%) | 294
768 | 6690 | bopLkaAZbmZjIM9EGI6L | Normal | 532 | 1.11.2 | 1.11.2 |  | 532 | p | 63 | -12% | 595
769 | 6691 | xLErpFHjPEH3ifHRbBMY | Normal | 396 | 1.11.3 | 1.11.3 |  | 396 | p | 90 | -23% | 486
770 | 6692 | g8WcEZ6I6SGdlePHrYPP | Normal | 248 | 1.11.4 | 1.11.4 |  | 248 | p | 24 | -10% | 272
771 | 6695 | Bx0BPJ0BcPw49QEL7Psq | Normal | 313 | 1.11.8 | 1.11.8 |  | 313 | q | -68 | (-22%) | 245
772 | 6696 | XbFIp383UbA72xJPH4hJ | Normal | 101 | 1.11.9 | 1.11.9 |  | 101 | q | -1 | (-1%) | 100
773 | 6697 | gpkN7vTMpz4ZZxhDAmeL | Normal | 126 | 1.11.10 | 1.11.10 |  | 126 | p | 1 | -1% | 127
774 | 6698 | eRsel9yyFaDkcYLZgvjC | Normal | 142 | 1.11.11 | 1.11.11 |  | 142 | p | 10 | -7% | 152
775 | 6699 | k8943lu4TS9ZW2TcUvha | Normal | 256 | 1.11.12 | 1.11.12 |  | 256 | p | 33 | -13% | 289
776 | 7376 | FfEUU5kpALOu6FlmjosD | Normal | 396 | 1.10.3 | 1.10.3 |  | 396 | p | 22 | -6% | 418
777 | 7378 | YjoFZZooPnFRzsk2Ba2E | Normal | 288 | 1.10.6 | 1.10.6 |  | 288 | p | 75 | -26% | 363
778 | 7379 | 7GajZBAFakrGWC1WlgE6 | Normal | 142 | 1.10.14 | 1.10.14 |  | 142 | q | -37 | (-26%) | 105
779 | 7380 | wkyoOF6gHS9pA0Dm9pZY | Normal | 140 | 1.10.17 | 1.10.17 |  | 140 | q | -20 | (-14%) | 120
780 | 7551 | G4afE8kOleATkD8qyqeP | Normal | 1 | 1.10.19 | 1.10.19 |  | 1 | q | -1 | (-100%) | 0

## Total-Float
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Total Float - 1303 (61%) | Total Float - 1303 (61%) | Total Float - 1303 (61%) | Total Float - 1303 (61%) | Total Float - 1303 (61%) | Total Float - 1303 (61%) | Total Float - 1303 (61%) | Total Float - 1303 (61%) | Total Float - 1303 (61%) | Total Float - 1303 (61%) | Total Float - 1303 (61%) | Total Float - 1303 (61%) | Total Float - 1303 (61%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 152 | QJ29ZvAvtEjBcpqHDer1 | Milestone | 0 | 1.2.3 | 1.2.3 |  | 514 | q | -514 | (-100%) | 0
2 | 158 | D5C8AUNeoI4YKF3PggKx | Summary | 255 | 1.2.7 | 1.2.7 |  | 510 | q | -292 | (-57%) | 218
3 | 155 | 1yu6CrDX9QU5hWE1UWMV | Milestone | 0 | 1.2.7.11 | 1.2.7.11 |  | 510 | q | -292 | (-57%) | 218
4 | 166 | KkWbk0R1FXz2L56lHFvV | Normal | 2 | 1.2.7.4 | 1.2.7.4 |  | 37 | p | 20 | -54% | 57
5 | 6618 | LspmB73Oe2b9O1GVbm64 | Milestone | 0 | 1.2.7.2 | 1.2.7.2 |  | 488 | p | 117 | -24% | 605
6 | 6636 | 3J1qFTgnrSSZVnoYdTv5 | Summary | 140 | 1.2.7.3 | 1.2.7.3 |  | 37 | p | 20 | -54% | 57
7 | 6338 | whnkqeDzsaW1H7xphaZA | Normal | 49 | 1.2.7.3.4 | 1.2.7.3.4 |  | 37 | p | 20 | -54% | 57
8 | 6640 | QUv6m7GotPkUb98mhJX7 | Normal | 14 | 1.2.7.3.6 | 1.2.7.3.6 |  | 37 | p | 20 | -54% | 57
9 | 6673 | sIWmvaXMX3ZF9ctRNm7s | Normal | 34 | 1.2.7.3.3 | 1.2.7.3.3 |  | 68 | p | 10 | -15% | 78
10 | 6872 | SjyWialEYK436pEnV5Nr | Normal | 1 | 1.2.7.5 | 1.2.7.5 |  | 121 | q | -35 | (-29%) | 86
11 | 6874 | 1XFpbhK6U752FQe8voXZ | Normal | 1 | 1.2.7.6 | 1.2.7.6 |  | 23 | q | -45 | (-196%) | -22
12 | 6878 | VU7w4voCV7rMMsz4AnPW | Normal | 1 | 1.2.7.10 | 1.2.7.10 |  | 316 | p | 1 | 0% | 317
13 | 6879 | Vbp0cBOXY9azJeyTE4S4 | Normal | 3 | 1.2.7.7 | 1.2.7.7 |  | 11 | q | -47 | (-427%) | -36
14 | 6880 | ZuauWvCPNW7n2NMscMO2 | Normal | 4 | 1.2.7.8 | 1.2.7.8 |  | -26 | q | -8 | -31% | -34
15 | 6881 | XekYY8n1P4vELtk4BUks | Normal | 1 | 1.2.7.9 | 1.2.7.9 |  | 19 | p | 1 | -5% | 20
16 | 7185 | 9DFzvUnK8UE41lq7OD40 | Milestone | 0 | 1.2.7.1 | 1.2.7.1 |  | 488 | p | 131 | -27% | 619
17 | 7550 | fUEnUBwdI1z3bgOngjaQ | Milestone | 0 | 1.2.7.5 | 1.2.7.5 |  | 0 | p | 57 |  | 57
18 | 160 | gFTVv5U5XORyz5ZEYbdN | Summary | 703 | 1.2.8 | 1.2.8 |  | 19 | p | 1 | -5% | 20
19 | 168 | MT1CsCIMkhjJER6f3fjG | Milestone | 0 | 1.2.8.4 | 1.2.8.4 |  | 19 | p | 1 | -5% | 20
20 | 5294 | A0MDYkkQxesjEWQub0UM | Milestone | 0 | 1.2.8.3 | 1.2.8.3 |  | 37 | p | 20 | -54% | 57
21 | 172 | EY5PMcgR4N5ReAIF6NHn | Summary | 582 | 1.2.9 | 1.2.9 |  | 158 | q | -22 | (-14%) | 136
22 | 173 | vJHK0TlIBzGpfYqdt8YI | Milestone | 0 | 1.2.9.4 | 1.2.9.4 |  | 158 | q | -22 | (-14%) | 136
23 | 177 | V4ys3lAm8KEbtjGqLAuR | Milestone | 0 | 1.2.9.2 | 1.2.9.2 |  | 216 | q | -19 | (-9%) | 197
24 | 178 | Cncpm0GACo0ppNIEy1Gp | Milestone | 0 | 1.2.9.3 | 1.2.9.3 |  | 212 | q | -20 | (-9%) | 192
25 | 179 | jSOjvYE1qiHOKdcV2ixu | Summary | 554 | 1.2.10 | 1.2.10 |  | 512 | p | 76 | -15% | 588
26 | 180 | 9Vp3PBZnh9TpV8TGBWRG | Milestone | 0 | 1.2.10.14 | 1.2.10.14 |  | 512 | p | 76 | -15% | 588
27 | 193 | nJh7oj8wCJYW8hyepdLI | Milestone | 0 | 1.2.10.12 | 1.2.10.12 |  | 652 | p | 126 | -19% | 778
28 | 194 | wTcNF86mfD2cPQPmQB1c | Milestone | 0 | 1.2.10.13 | 1.2.10.13 |  | 512 | p | 76 | -15% | 588
29 | 7132 | osdxrWYmqQZxyGZXe9Pr | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 515 | p | 150 | -29% | 665
30 | 7546 | tdocr3pqURBYHZWcAyMG | Normal | 1 | 1.2.10.12 | 1.2.10.12 |  | 511 | p | 191 | -37% | 702
31 | 7547 | 2p5uMAQ0v8mT9pq4KeWp | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 522 | p | 183 | -35% | 705
32 | 7548 | TdNnLE8G4vf1vBjggzLw | Normal | 1 | 1.2.10.15 | 1.2.10.15 |  | 524 | p | 178 | -34% | 702
33 | 7549 | yUAt6Fi3Vichq9Ai1DSh | Normal | 1 | 1.2.10.13 | 1.2.10.13 |  | 535 | p | 167 | -31% | 702
34 | 195 | jWoM7YMyhsN7uWtVDNIl | Summary | 276 | 1.2.11 | 1.2.11 |  | 514 | q | -506 | (-98%) | 8
35 | 196 | kzYOxx4jS6vhIcTyxNFn | Milestone | 0 | 1.2.11.11 | 1.2.11.11 |  | 514 | q | -506 | (-98%) | 8
36 | 197 | LZAvhCOF77OBkAngJSDi | Milestone | 0 | 1.2.11.1 | 1.2.11.1 |  | 516 | q | -505 | (-98%) | 11
37 | 198 | X7Nxs9NuQXJ5Bf6aQwVp | Milestone | 0 | 1.2.11.2 | 1.2.11.2 |  | 516 | q | -512 | (-99%) | 4
38 | 199 | TiaYdQ98Ovd3qBAfSAyG | Milestone | 0 | 1.2.11.3 | 1.2.11.3 |  | 515 | q | -513 | (-100%) | 2
39 | 200 | yynHcCtrZd0Ye6iQJb2E | Milestone | 0 | 1.2.11.4 | 1.2.11.4 |  | 522 | q | -513 | (-98%) | 9
40 | 202 | mjF0YLun5LIdlxtu3zFl | Milestone | 0 | 1.2.11.5 | 1.2.11.5 |  | 699 | p | 132 | -19% | 831
41 | 203 | 2a1x42QofxcVsgjcXtkr | Milestone | 0 | 1.2.11.6 | 1.2.11.6 |  | 516 | q | -505 | (-98%) | 11
42 | 204 | 8T22gllTunmLl2jY7IMk | Milestone | 0 | 1.2.11.7 | 1.2.11.7 |  | 516 | q | -512 | (-99%) | 4
43 | 205 | dm3U5Xjvi5rN2LqWegXW | Milestone | 0 | 1.2.11.8 | 1.2.11.8 |  | 515 | q | -513 | (-100%) | 2
44 | 206 | ZOAcdJHtChBG5MUjo5uw | Milestone | 0 | 1.2.11.9 | 1.2.11.9 |  | 522 | q | -513 | (-98%) | 9
45 | 209 | 0FNuAiL5ZzPZSZ3dZfoV | Milestone | 0 | 1.2.11.10 | 1.2.11.10 |  | 539 | q | -512 | (-95%) | 27
46 | 7015 | U0mup1noPd6mH1CxWGtr | Milestone | 0 | 1.2.5 | 1.2.5 |  | 454 | q | -454 | (-100%) | 0
47 | 7016 | pVOP21cemlwRUbhUeRME | Milestone | 0 | 1.2.4 | 1.2.4 |  | 450 | q | -232 | (-52%) | 218
48 | 150 | 7cu6yvdJV8ndF0CYMHk8 | Milestone | 0 | 1.1 | 1.1 |  | 514 | q | -514 | (-100%) | 0
49 | 4180 | LxVAz76PSOUu8y7B8sy3 | Summary | 218 | 1.3 | 1.3 |  | 188 | q | -12 | (-6%) | 176
50 | 384 | GE3w1SHplCQZN7aYDVw8 | Summary | 34 | 1.3.3 | 1.3.3 |  | 37 | p | 20 | -54% | 57
51 | 429 | Pbs0MxOqvHazWgB8fpDs | Summary | 41 | 1.3.3.2 | 1.3.3.2 |  | 37 | p | 20 | -54% | 57
52 | 436 | OGXVzK31PKUn8DxCdn94 | Normal | 33 | 1.3.3.2.10 | 1.3.3.2.10 |  | 37 | p | 20 | -54% | 57
53 | 437 | kEyeaq7ebxWRSvBqGkHC | Summary | 19 | 1.3.3.1 | 1.3.3.1 |  | 53 | p | 8 | -15% | 61
54 | 438 | QjVW4dYK4boDcUrG7MUx | Summary | 23 | 1.3.3.1.2 | 1.3.3.1.2 |  | 53 | p | 8 | -15% | 61
55 | 445 | cIIfBfMFMZUbJxswwNzj | Summary | 28 | 1.3.3.1.2.4 | 1.3.3.1.2.4 |  | 53 | p | 8 | -15% | 61
56 | 6438 | sSGfho0IWOHZYw1Z8jLl | Normal | 16 | 1.3.3.1.2.4.5 | 1.3.3.1.2.4.5 |  | 53 | p | 8 | -15% | 61
57 | 5768 | 9l9o7D6Il8vKVgGgZRMW | Summary | 197 | 1.3.3.4 | 1.3.3.4 |  | 37 | p | 20 | -54% | 57
58 | 428 | pxWL5EoMWeaDmapfAV7m | Normal | 2 | 1.3.3.4.2 | 1.3.3.4.2 |  | 37 | p | 20 | -54% | 57
59 | 6289 | NknbxY1EWobhbJ98SVRq | Summary | 270 | 1.3.2 | 1.3.2 |  | 188 | q | -12 | (-6%) | 176
60 | 3848 | g0gBmZeXCCPZTY4kkYs8 | Summary | 210 | 1.3.2.1 | 1.3.2.1 |  | 188 | q | -10 | (-5%) | 178
61 | 3849 | PKYN5IsyqbTocjyswPFM | Normal | 17 | 1.3.2.1.1 | 1.3.2.1.1 |  | 45 | p | 12 | -27% | 57
62 | 3850 | sk2pEdmn2KeVBRyrQzgn | Summary | 233 | 1.3.2.1.2 | 1.3.2.1.2 |  | 188 | q | -10 | (-5%) | 178
63 | 3857 | FObPKa3HJ5KI4gFmAx2r | Summary | 210 | 1.3.2.1.2.2 | 1.3.2.1.2.2 |  | 207 | q | -29 | (-14%) | 178
64 | 3858 | pWvg9Owxac1jXAINT5hs | Normal | 24 | 1.3.2.1.2.2.1 | 1.3.2.1.2.2.1 |  | 45 | p | 13 | -29% | 58
65 | 3859 | xrpLG6wlwOL4sRwHPU5B | Normal | 28 | 1.3.2.1.2.2.2 | 1.3.2.1.2.2.2 |  | 220 | q | -36 | (-16%) | 184
66 | 3861 | rvfyADOJtzNcPT3VL85f | Normal | 100 | 1.3.2.1.2.2.3 | 1.3.2.1.2.2.3 |  | 207 | q | -29 | (-14%) | 178
67 | 3862 | FUtleP4nAJHYxzLOWKZH | Normal | 20 | 1.3.2.1.2.2.4 | 1.3.2.1.2.2.4 |  | 207 | q | -29 | (-14%) | 178
68 | 3863 | WaF24jcpD2qzV3M05hSl | Summary | 178 | 1.3.2.1.2.3 | 1.3.2.1.2.3 |  | 188 | q | -9 | (-5%) | 179
69 | 3864 | kkmwKYrSq6DehQmbGkxo | Summary | 90 | 1.3.2.1.2.3.2 | 1.3.2.1.2.3.2 |  | 188 | q | -9 | (-5%) | 179
70 | 3865 | ZK3GDclfde20Vh8DU71K | Normal | 30 | 1.3.2.1.2.3.2.1 | 1.3.2.1.2.3.2.1 |  | 188 | q | -9 | (-5%) | 179
71 | 3866 | 8Zrc7ItBhrTjO1TWxqmf | Normal | 20 | 1.3.2.1.2.3.2.2 | 1.3.2.1.2.3.2.2 |  | 188 | q | -9 | (-5%) | 179
72 | 3867 | l8TRHVr9p6bfQBwzbTty | Normal | 5 | 1.3.2.1.2.3.2.5 | 1.3.2.1.2.3.2.5 |  | 188 | q | -9 | (-5%) | 179
73 | 3868 | NCkZSbtMfUxIg95lxXXn | Normal | 10 | 1.3.2.1.2.3.2.6 | 1.3.2.1.2.3.2.6 |  | 188 | q | -9 | (-5%) | 179
74 | 3869 | wbVbYxDNomEEsv0XDKnQ | Normal | 5 | 1.3.2.1.2.3.2.7 | 1.3.2.1.2.3.2.7 |  | 188 | q | -9 | (-5%) | 179
75 | 6562 | Z3AfJmLBpOLyJb1GhvwC | Normal | 10 | 1.3.2.1.2.3.2.3 | 1.3.2.1.2.3.2.3 |  | 188 | q | -9 | (-5%) | 179
76 | 6563 | 7FPcbor42GN7O6Ym4IZM | Normal | 10 | 1.3.2.1.2.3.2.4 | 1.3.2.1.2.3.2.4 |  | 188 | q | -9 | (-5%) | 179
77 | 7186 | ttl1FahPn0WwOuyGdmk6 | Summary | 138 | 1.3.2.3 | 1.3.2.3 |  | 181 | q | -16 | (-9%) | 165
78 | 7188 | yn5QOVI2BZ7jor10JaQN | Summary | 55 | 1.3.2.3.2 | 1.3.2.3.2 |  | 106 | p | 32 | -30% | 138
79 | 7189 | jup7puBG1dNvbV8jB14f | Summary | 69 | 1.3.2.3.2.1 | 1.3.2.3.2.1 |  | 94 | p | 42 | -45% | 136
80 | 7190 | Ob13piboJI4zFNOVPzZD | Summary | 50 | 1.3.2.3.2.1.1 | 1.3.2.3.2.1.1 |  | 94 | p | 54 | -57% | 148
81 | 7192 | rcBSOCAYFUxP7jsyoqGw | Normal | 11 | 1.3.2.3.2.1.1.2 | 1.3.2.3.2.1.1.2 |  | 94 | p | 54 | -57% | 148
82 | 7193 | hzdeRXxytBFeNJPq5eHn | Summary | 50 | 1.3.2.3.2.1.2 | 1.3.2.3.2.1.2 |  | 94 | p | 54 | -57% | 148
83 | 7194 | mB0uoGZ1D1fuFzk350Kb | Normal | 30 | 1.3.2.3.2.1.2.1 | 1.3.2.3.2.1.2.1 |  | 94 | p | 54 | -57% | 148
84 | 7196 | fFBpC2vR2qp5KXHLtypR | Summary | 23 | 1.3.2.3.2.1.3 | 1.3.2.3.2.1.3 |  | 124 | p | 12 | -10% | 136
85 | 7199 | G7LfPy6euQCIQjteO0x8 | Normal | 20 | 1.3.2.3.2.1.3.3 | 1.3.2.3.2.1.3.3 |  | 124 | p | 12 | -10% | 136
86 | 7200 | 7Va2LPPEsZrLZmgpV2qc | Summary | 19 | 1.3.2.3.2.1.4 | 1.3.2.3.2.1.4 |  | 94 | p | 42 | -45% | 136
87 | 7201 | UKbpgMkpfrIPVoEOJEeO | Normal | 10 | 1.3.2.3.2.1.4.1 | 1.3.2.3.2.1.4.1 |  | 94 | p | 42 | -45% | 136
88 | 7202 | vy1jnuopIHJe5PhTsUNw | Normal | 5 | 1.3.2.3.2.1.4.2 | 1.3.2.3.2.1.4.2 |  | 94 | p | 42 | -45% | 136
89 | 7203 | KqVHIBvrHNAu5GlarotD | Normal | 3 | 1.3.2.3.2.1.4.3 | 1.3.2.3.2.1.4.3 |  | 94 | p | 42 | -45% | 136
90 | 7204 | BUAmcwglNtP3GEkJsPLR | Normal | 1 | 1.3.2.3.2.1.4.4 | 1.3.2.3.2.1.4.4 |  | 94 | p | 42 | -45% | 136
91 | 7205 | 688LmElxek6WZQ34zEgD | Summary | 40 | 1.3.2.3.2.2 | 1.3.2.3.2.2 |  | 129 | p | 13 | -10% | 142
92 | 7206 | bMXBNIC1fF7AjliDPdfr | Normal | 25 | 1.3.2.3.2.2.1 | 1.3.2.3.2.2.1 |  | 129 | p | 13 | -10% | 142
93 | 7207 | 51ZGrscW6XrNzeOMbLyw | Normal | 5 | 1.3.2.3.2.2.2 | 1.3.2.3.2.2.2 |  | 129 | p | 13 | -10% | 142
94 | 7208 | 5Vu53Z23NG8K3uSzUcYA | Normal | 3 | 1.3.2.3.2.2.3 | 1.3.2.3.2.2.3 |  | 129 | p | 13 | -10% | 142
95 | 7209 | r8OmtZddpdGbVxNEynIO | Normal | 1 | 1.3.2.3.2.2.4 | 1.3.2.3.2.2.4 |  | 129 | p | 13 | -10% | 142
96 | 7210 | 5vpOUfvEpSU2AKPwltv0 | Summary | 14 | 1.3.2.3.2.3 | 1.3.2.3.2.3 |  | 134 | p | 31 | -23% | 165
97 | 7211 | wSDYMNBcPlclxMN6Hc8V | Normal | 5 | 1.3.2.3.2.3.1 | 1.3.2.3.2.3.1 |  | 134 | q | -134 | (-100%) | 0
98 | 7212 | IA5BwO4PzPuXs5yI3XzH | Normal | 5 | 1.3.2.3.2.3.2 | 1.3.2.3.2.3.2 |  | 134 | p | 31 | -23% | 165
99 | 7213 | GkAhONTSL0EMIVzc5bXh | Normal | 3 | 1.3.2.3.2.3.3 | 1.3.2.3.2.3.3 |  | 134 | p | 31 | -23% | 165
100 | 7214 | ysGFXohNyFRFQ06jmkjW | Normal | 1 | 1.3.2.3.2.3.4 | 1.3.2.3.2.3.4 |  | 134 | p | 31 | -23% | 165
101 | 7215 | a8OJFGtOVEyM75c9puYK | Summary | 34 | 1.3.2.3.2.4 | 1.3.2.3.2.4 |  | 129 | p | 24 | -19% | 153
102 | 7218 | 5fSpBiSdaCD1mvMsYs0j | Normal | 2 | 1.3.2.3.2.4.3 | 1.3.2.3.2.4.3 |  | 129 | q | -129 | (-100%) | 0
103 | 7219 | tMHxEODKuKminmE9Mjg5 | Normal | 1 | 1.3.2.3.2.4.4 | 1.3.2.3.2.4.4 |  | 129 | q | -129 | (-100%) | 0
104 | 7220 | nvywSXdnd0LSUGSiB3or | Normal | 10 | 1.3.2.3.2.4.5 | 1.3.2.3.2.4.5 |  | 129 | p | 24 | -19% | 153
105 | 7221 | PYoR7OoHLcblZDJJ1hTC | Normal | 20 | 1.3.2.3.2.4.6 | 1.3.2.3.2.4.6 |  | 129 | p | 24 | -19% | 153
106 | 7222 | W1KVKgORO9KqmU1uQFqG | Normal | 1 | 1.3.2.3.2.4.7 | 1.3.2.3.2.4.7 |  | 129 | p | 24 | -19% | 153
107 | 7223 | 2cLCJpvBPh4ccgbvKrEi | Summary | 38 | 1.3.2.3.2.5 | 1.3.2.3.2.5 |  | 135 | p | 3 | -2% | 138
108 | 7226 | fsyu9CvTMAXTCK7e04ez | Normal | 1 | 1.3.2.3.2.5.3 | 1.3.2.3.2.5.3 |  | 147 | q | -147 | (-100%) | 0
109 | 7227 | QiFvht1v2EB9ODLdNK6M | Normal | 25 | 1.3.2.3.2.5.4 | 1.3.2.3.2.5.4 |  | 123 | p | 3 | -2% | 126
110 | 7228 | SSqxRWtJ8NkhLwkx3Zp5 | Normal | 15 | 1.3.2.3.2.5.5 | 1.3.2.3.2.5.5 |  | 123 | p | 3 | -2% | 126
111 | 7514 | 4jhJaLUHxegkfPxUyChC | Normal | 15 | 1.3.2.3.2.5.9 | 1.3.2.3.2.5.9 |  | 155 | p | 33 | -21% | 188
112 | 7515 | jdxLrBmn54gbF5MbPNVU | Normal | 5 | 1.3.2.3.2.5.8 | 1.3.2.3.2.5.8 |  | 155 | q | -155 | (-100%) | 0
113 | 7231 | Kz2H44CrN943Xn6RI0Et | Summary | 19 | 1.3.2.3.3 | 1.3.2.3.3 |  | 37 | p | 20 | -54% | 57
114 | 7232 | cCMYeGs7uzTIiiDhvAui | Summary | 12 | 1.3.2.3.3.1 | 1.3.2.3.3.1 |  | 37 | p | 20 | -54% | 57
115 | 7233 | rgerXXfH5cOVWHlSbXtk | Normal | 2 | 1.3.2.3.3.1.1 | 1.3.2.3.3.1.1 |  | 45 | p | 20 | -44% | 65
116 | 7234 | 4Nk8AWONEAABjENRSl4s | Normal | 3 | 1.3.2.3.3.1.2 | 1.3.2.3.3.1.2 |  | 44 | p | 19 | -43% | 63
117 | 7235 | uR7e5eYUOS8ur8CkZgir | Normal | 2 | 1.3.2.3.3.1.3 | 1.3.2.3.3.1.3 |  | 44 | p | 19 | -43% | 63
118 | 7236 | OqdHv6QLhEyFdmarh5Mg | Normal | 5 | 1.3.2.3.3.1.4 | 1.3.2.3.3.1.4 |  | 44 | p | 19 | -43% | 63
119 | 7237 | xLl9f1S8pVLgozw4LZw4 | Normal | 10 | 1.3.2.3.3.1.5 | 1.3.2.3.3.1.5 |  | 37 | p | 21 | -57% | 58
120 | 7238 | hj0QAuvemNr4BSx0wqCM | Normal | 10 | 1.3.2.3.3.1.6 | 1.3.2.3.3.1.6 |  | 37 | p | 20 | -54% | 57
121 | 7239 | sGRMuNmZsu5Ap3rRR6Ja | Normal | 2 | 1.3.2.3.3.1.7 | 1.3.2.3.3.1.7 |  | 37 | p | 20 | -54% | 57
122 | 7240 | jJgg05qz3M4QbDAQ4nmn | Summary | 7 | 1.3.2.3.3.2 | 1.3.2.3.3.2 |  | 37 | p | 20 | -54% | 57
123 | 7241 | RP09WyAKLetAyeWXIWbd | Normal | 1 | 1.3.2.3.3.2.1 | 1.3.2.3.3.2.1 |  | 37 | p | 20 | -54% | 57
124 | 7242 | PNiOufePi0cnwKsaAHa8 | Normal | 3 | 1.3.2.3.3.2.2 | 1.3.2.3.3.2.2 |  | 37 | p | 20 | -54% | 57
125 | 7243 | nppwsC1hz1MTRepHit5q | Normal | 3 | 1.3.2.3.3.2.3 | 1.3.2.3.3.2.3 |  | 37 | p | 20 | -54% | 57
126 | 7244 | FpvbIzqyAjmrguHRtjoA | Summary | 68 | 1.3.2.3.4 | 1.3.2.3.4 |  | 37 | p | 20 | -54% | 57
127 | 7245 | ysJ2Wz17vAaH50NFOd3r | Normal | 2 | 1.3.2.3.4.1 | 1.3.2.3.4.1 |  | 38 | p | 19 | -50% | 57
128 | 7246 | w8OYvCOBO1azAOar59yv | Normal | 3 | 1.3.2.3.4.2 | 1.3.2.3.4.2 |  | 37 | p | 20 | -54% | 57
129 | 7247 | QmLDbLdk9YgltF6FQxKi | Normal | 2 | 1.3.2.3.4.3 | 1.3.2.3.4.3 |  | 37 | p | 20 | -54% | 57
130 | 7248 | nqyBToLUXvLl91VDFcK9 | Summary | 20 | 1.3.2.3.4.4 | 1.3.2.3.4.4 |  | 181 | q | -16 | (-9%) | 165
131 | 7249 | T3rEQsXy5TFYVzdnmRkQ | Normal | 20 | 1.3.2.3.4.4.1 | 1.3.2.3.4.4.1 |  | 181 | q | -14 | (-8%) | 167
132 | 7250 | G5mdz8DmOa8TGNlmxmOk | Normal | 20 | 1.3.2.3.4.4.2 | 1.3.2.3.4.4.2 |  | 181 | q | -16 | (-9%) | 165
133 | 7251 | p2IEwFFq1YxDgQwaqReT | Summary | 48 | 1.3.2.3.4.5 | 1.3.2.3.4.5 |  | 181 | q | -16 | (-9%) | 165
134 | 7252 | R4hlQqYwslHcXudIUORM | Normal | 20 | 1.3.2.3.4.5.1 | 1.3.2.3.4.5.1 |  | 181 | q | -16 | (-9%) | 165
135 | 7253 | 5Q6OCjUddDwnqpg2shNG | Normal | 5 | 1.3.2.3.4.5.2 | 1.3.2.3.4.5.2 |  | 181 | q | -16 | (-9%) | 165
136 | 7254 | aZsc8OQGYCtOtLNUDl4p | Normal | 7 | 1.3.2.3.4.5.3 | 1.3.2.3.4.5.3 |  | 181 | q | -16 | (-9%) | 165
137 | 7255 | GiGIxdlKVFOGW1rlVkpg | Normal | 5 | 1.3.2.3.4.5.4 | 1.3.2.3.4.5.4 |  | 181 | q | -16 | (-9%) | 165
138 | 7256 | ZTFxKau19KKCcFlUDIYg | Normal | 7 | 1.3.2.3.4.5.5 | 1.3.2.3.4.5.5 |  | 181 | q | -16 | (-9%) | 165
139 | 7257 | EmkT3sq6aGy3vx96JSsX | Normal | 3 | 1.3.2.3.4.5.6 | 1.3.2.3.4.5.6 |  | 181 | q | -16 | (-9%) | 165
140 | 7258 | PBxke5bv0Yk6xXbQcvVe | Normal | 1 | 1.3.2.3.4.5.7 | 1.3.2.3.4.5.7 |  | 181 | q | -16 | (-9%) | 165
141 | 6269 | tUCxonMalaI13D6hsUSU | Summary | 99 | 1.5 | 1.5 |  | 148 | q | -12 | (-8%) | 136
142 | 6278 | SNMcp7h74WVvBiN3lPNB | Summary | 66 | 1.5.6 | 1.5.6 |  | 10 | q | -43 | (-430%) | -33
143 | 605 | HP2TrbmUH5Qc4V2P2k1T | Normal | 14 | 1.5.6.1 | 1.5.6.1 |  | 155 | q | -45 | (-29%) | 110
144 | 620 | q8advjPa5PEndSFXJ05j | Summary | 158 | 1.5.6.6 | 1.5.6.6 |  | 10 | q | -43 | (-430%) | -33
145 | 622 | Q48N5ZSDLesB1Bsda2wx | Summary | 156 | 1.5.6.6.2 | 1.5.6.6.2 |  | 10 | q | -43 | (-430%) | -33
146 | 631 | jjFU6HpNq2otAi9zmRWR | Normal | 2 | 1.5.6.6.2.7 | 1.5.6.6.2.7 |  | 87 | q | -87 | (-100%) | 0
147 | 632 | tuv9OmQcJHKkVCVrbrrv | Normal | 6 | 1.5.6.6.2.8 | 1.5.6.6.2.8 |  | 87 | q | -20 | (-23%) | 67
148 | 633 | FgJ5XjjThZN85XQOJ0nJ | Normal | 21 | 1.5.6.6.2.10 | 1.5.6.6.2.10 |  | 10 | q | -43 | (-430%) | -33
149 | 634 | o4DRQRcsScdVmCSXNbxF | Normal | 10 | 1.5.6.6.2.9 | 1.5.6.6.2.9 |  | 10 | q | -43 | (-430%) | -33
150 | 635 | ztvy5zkS4z9HirKgvHGY | Normal | 20 | 1.5.6.6.2.11 | 1.5.6.6.2.11 |  | 10 | q | -43 | (-430%) | -33
151 | 636 | ZpIfqMwIaczq2BqznW2q | Normal | 6 | 1.5.6.6.2.12 | 1.5.6.6.2.12 |  | 10 | q | -43 | (-430%) | -33
152 | 637 | 3VAZwvp2NS6usl0wrvOM | Normal | 7 | 1.5.6.6.2.13 | 1.5.6.6.2.13 |  | 10 | q | -43 | (-430%) | -33
153 | 638 | 34zoFClD9RS7gLTCPZs0 | Normal | 5 | 1.5.6.6.2.14 | 1.5.6.6.2.14 |  | 10 | q | -43 | (-430%) | -33
154 | 640 | 10AmMHkCz4b8n0xqbyCt | Normal | 5 | 1.5.6.6.2.16 | 1.5.6.6.2.16 |  | 10 | q | -43 | (-430%) | -33
155 | 641 | KUqcSNVxncHPLVJNV5ca | Normal | 2 | 1.5.6.6.2.17 | 1.5.6.6.2.17 |  | 10 | q | -43 | (-430%) | -33
156 | 642 | chCwawHUqn0ea2ArCnKB | Normal | 0 | 1.5.6.6.2.18 | 1.5.6.6.2.18 |  | 10 | q | -43 | (-430%) | -33
157 | 643 | xZBRzE3QVYmQCjnzxLQv | Normal | 4 | 1.5.6.6.2.19 | 1.5.6.6.2.19 |  | 10 | q | -43 | (-430%) | -33
158 | 644 | tUTeQ74YpmkuuOiouSXU | Normal | 5 | 1.5.6.6.2.20 | 1.5.6.6.2.20 |  | 10 | q | -43 | (-430%) | -33
159 | 645 | mSrjcTZmK12EdJmOEYFi | Normal | 1 | 1.5.6.6.2.21 | 1.5.6.6.2.21 |  | 10 | q | -43 | (-430%) | -33
160 | 646 | Haue3rYYySw3jbXWnBeq | Normal | 3 | 1.5.6.6.3 | 1.5.6.6.3 |  | 10 | q | -43 | (-430%) | -33
161 | 647 | 6jlP0Y4QQ5KPQWxvolLg | Normal | 1 | 1.5.6.6.4 | 1.5.6.6.4 |  | 10 | q | -43 | (-430%) | -33
162 | 648 | 6WPgljRre9DjhHGVsVUH | Summary | 120 | 1.5.6.6.5 | 1.5.6.6.5 |  | 10 | q | -43 | (-430%) | -33
163 | 656 | lzPFAx9Fh8cDxyQ3uxFX | Normal | 1 | 1.5.6.6.5.3 | 1.5.6.6.5.3 |  | 10 | q | -43 | (-430%) | -33
164 | 657 | nePaKBbqDo6OltylvukE | Summary | 14 | 1.5.6.6.5.4 | 1.5.6.6.5.4 |  | 10 | q | -43 | (-430%) | -33
165 | 658 | PyBKEPMZMe2YeOC66yut | Normal | 11 | 1.5.6.6.5.4.1 | 1.5.6.6.5.4.1 |  | 10 | q | -43 | (-430%) | -33
166 | 664 | H1KB0K8mM12Opvc4oDP1 | Normal | 3 | 1.5.6.6.5.4.2 | 1.5.6.6.5.4.2 |  | 10 | q | -43 | (-430%) | -33
167 | 665 | FIEbexlYHnOcZkEBs7WM | Normal | 5 | 1.5.6.6.5.5 | 1.5.6.6.5.5 |  | 10 | q | -43 | (-430%) | -33
168 | 666 | OcAHNnZWZgiwxfUiheGU | Normal | 5 | 1.5.6.6.5.6 | 1.5.6.6.5.6 |  | 10 | q | -43 | (-430%) | -33
169 | 667 | HPj21Hyun1nWvxJOQMhf | Normal | 28 | 1.5.6.6.5.7 | 1.5.6.6.5.7 |  | 10 | q | -43 | (-430%) | -33
170 | 670 | zBtIFoyMK1KgXAv407C9 | Summary | 29 | 1.5.6.5 | 1.5.6.5 |  | 10 | q | -43 | (-430%) | -33
171 | 671 | ZM52W2kHJJCM7052Da3J | Normal | 2 | 1.5.6.5.2 | 1.5.6.5.2 |  | 24 | q | -43 | (-179%) | -19
172 | 672 | AcRvLPQ7WrNfvcLBOWzV | Normal | 1 | 1.5.6.5.3 | 1.5.6.5.3 |  | 10 | q | -43 | (-430%) | -33
173 | 6141 | PCEOtJROHHMKXYkoR4rp | Normal | 3 | 1.5.6.5.1 | 1.5.6.5.1 |  | 200 | q | -200 | (-100%) | 0
174 | 6281 | RYPcKAyzQapOQ3GupQll | Summary | 104 | 1.5.5 | 1.5.5 |  | 352 | q | -19 | (-5%) | 333
175 | 1466 | LmBGiI2jXQ3lZF0l79sj | Summary | 104 | 1.5.5.1 | 1.5.5.1 |  | 352 | q | -19 | (-5%) | 333
176 | 1457 | W1XQ7yoZAeSgm7UftoXN | Normal | 1 | 1.5.5.1.2 | 1.5.5.1.2 |  | 352 | q | -352 | (-100%) | 0
177 | 1458 | W2l89btZYbaZZjxZTUR4 | Normal | 12 | 1.5.5.1.3 | 1.5.5.1.3 |  | 352 | q | -3 | (-1%) | 349
178 | 1459 | MxsNofofvf6CR0hsGInx | Normal | 1 | 1.5.5.1.4 | 1.5.5.1.4 |  | 352 | q | -3 | (-1%) | 349
179 | 1468 | 8e77YoSi4abIbMILI8hH | Normal | 5 | 1.5.5.1.5 | 1.5.5.1.5 |  | 355 | q | -22 | (-6%) | 333
180 | 1469 | MZooHRTMNCHrNy0nPaCQ | Normal | 1 | 1.5.5.1.6 | 1.5.5.1.6 |  | 355 | q | -22 | (-6%) | 333
181 | 1470 | PdTqfNwd2IKBXe26tWkB | Normal | 1 | 1.5.5.1.8 | 1.5.5.1.8 |  | 352 | q | -19 | (-5%) | 333
182 | 1471 | FsiT4ZMTOq9hGqZQQdYf | Normal | 11 | 1.5.5.1.9 | 1.5.5.1.9 |  | 352 | q | -19 | (-5%) | 333
183 | 1472 | KG0YDAdikr58WjA79FVb | Normal | 9 | 1.5.5.1.10 | 1.5.5.1.10 |  | 352 | q | -19 | (-5%) | 333
184 | 4584 | H2uIo7s6dGmX6mrjT7jd | Normal | 9 | 1.5.5.1.7 | 1.5.5.1.7 |  | 355 | q | -22 | (-6%) | 333
185 | 6292 | 1Cm9NXihvfL2WEnYcHvT | Summary | 42 | 1.5.4 | 1.5.4 |  | 132 | q | -49 | (-37%) | 83
186 | 3944 | HRTLaCTjRjqysGxmE6ve | Normal | 36 | 1.5.4.2 | 1.5.4.2 |  | 63 | q | -44 | (-70%) | 19
187 | 3945 | bJfaWXH8yBacWp0eqnXx | Normal | 1 | 1.5.4.3 | 1.5.4.3 |  | 63 | q | -44 | (-70%) | 19
188 | 3949 | knRWxUZkgPmXKgij09tb | Summary | 25 | 1.5.4.5 | 1.5.4.5 |  | 120 | q | -49 | (-41%) | 71
189 | 3950 | NJx1RMKdqhuNKRLGMSBQ | Summary | 27 | 1.5.4.5.1 | 1.5.4.5.1 |  | 120 | q | -49 | (-41%) | 71
190 | 3951 | BNWJw3sHADBJTHA2Ybu0 | Normal | 16 | 1.5.4.5.1.1 | 1.5.4.5.1.1 |  | 120 | q | -49 | (-41%) | 71
191 | 3952 | HkhDGF3pWO8GORFQnyh9 | Normal | 5 | 1.5.4.5.1.2 | 1.5.4.5.1.2 |  | 120 | q | -49 | (-41%) | 71
192 | 3953 | dYr7YcYkpYYUeESNUSkl | Normal | 2 | 1.5.4.5.1.3 | 1.5.4.5.1.3 |  | 120 | q | -49 | (-41%) | 71
193 | 3954 | r37KEs6OIDoMKT5Yz5nA | Normal | 1 | 1.5.4.5.1.4 | 1.5.4.5.1.4 |  | 120 | q | -49 | (-41%) | 71
194 | 3964 | ZzcX1hV2BTbfmTYJl5AE | Summary | 19 | 1.5.4.5.4 | 1.5.4.5.4 |  | 120 | q | -49 | (-41%) | 71
195 | 3967 | BaECEBO5p44IeRhOgeK2 | Normal | 19 | 1.5.4.5.4.3 | 1.5.4.5.4.3 |  | 120 | q | -49 | (-41%) | 71
196 | 5996 | M6DLFbZyZKXroBVfXncj | Summary | 19 | 1.5.4.4 | 1.5.4.4 |  | 155 | q | -42 | (-27%) | 113
197 | 3948 | 6ze4BjeYc1B5uifD0Fqa | Normal | 10 | 1.5.4.4.9 | 1.5.4.4.9 |  | 66 | q | -40 | (-61%) | 26
198 | 6202 | X3XRH6pSpuIgaacqwHSp | Normal | 14 | 1.5.4.4.10 | 1.5.4.4.10 |  | 155 | q | -42 | (-27%) | 113
199 | 6605 | Qtljmhuq3GHp8HrV3pPP | Normal | 6 | 1.5.4.4.7 | 1.5.4.4.7 |  | 66 | q | -40 | (-61%) | 26
200 | 6606 | pKonEcYtBOhP3mqLQIUx | Normal | 5 | 1.5.4.4.8 | 1.5.4.4.8 |  | 66 | q | -40 | (-61%) | 26
201 | 6299 | JvNaxkj9UdrgV7BcBski | Summary | 134 | 1.5.1 | 1.5.1 |  | 158 | q | -22 | (-14%) | 136
202 | 4213 | pNBoUl9px0n4wFhfXXqQ | Summary | 90 | 1.5.1.1 | 1.5.1.1 |  | 10 | q | -43 | (-430%) | -33
203 | 4215 | I07WrBLpDQufO3mvIdSu | Normal | 1 | 1.5.1.1.4 | 1.5.1.1.4 |  | 10 | q | -43 | (-430%) | -33
204 | 6444 | XymP4MvJgra2aDdoc9vw | Normal | 46 | 1.5.1.1.2 | 1.5.1.1.2 |  | 10 | q | -43 | (-430%) | -33
205 | 6445 | Wo6GLLiu9tXQyZ8t43hX | Normal | 43 | 1.5.1.1.3 | 1.5.1.1.3 |  | 10 | q | -43 | (-430%) | -33
206 | 6081 | VjHQD510O4fPJGbP9Knq | Normal | 1 | 1.5.1.2 | 1.5.1.2 |  | 158 | q | -22 | (-14%) | 136
207 | 6674 | 3EUoGYyEaAia67bx8maJ | Summary | 69 | 1.5.1.3 | 1.5.1.3 |  | 316 | p | 1 | 0% | 317
208 | 6680 | ttlvn3uwilh7nqgbHtE7 | Normal | 37 | 1.5.1.3.7 | 1.5.1.3.7 |  | 341 | q | -24 | (-7%) | 317
209 | 6681 | NHiN8b86HRxpkLb9JGGD | Normal | 10 | 1.5.1.3.9 | 1.5.1.3.9 |  | 341 | q | -24 | (-7%) | 317
210 | 6682 | 695WEwNqpcHeAbXSBRci | Normal | 2 | 1.5.1.3.10 | 1.5.1.3.10 |  | 316 | p | 1 | 0% | 317
211 | 6684 | TL3Mtv3QlGNejnoXktH7 | Normal | 1 | 1.5.1.3.8 | 1.5.1.3.8 |  | 341 | q | -24 | (-7%) | 317
212 | 6308 | 9d1kbrq4aHbr7FOmo76u | Summary | 27 | 1.5.2 | 1.5.2 |  | 349 | p | 4 | -1% | 353
213 | 5611 | e3AOkT5PZcArPsKmcVqB | Summary | 48 | 1.5.2.2 | 1.5.2.2 |  | 349 | p | 4 | -1% | 353
214 | 5612 | JBIAfh9fImNsEXfXoHCz | Summary | 5 | 1.5.2.2.10 | 1.5.2.2.10 |  | 349 | p | 4 | -1% | 353
215 | 5613 | cc9QdsdOkkgaQ8ateKZX | Normal | 1 | 1.5.2.2.10.1 | 1.5.2.2.10.1 |  | 349 | p | 4 | -1% | 353
216 | 5614 | COTl0owSvMhEdF9iuXCz | Normal | 0 | 1.5.2.2.10.2 | 1.5.2.2.10.2 |  | 349 | p | 4 | -1% | 353
217 | 5615 | 0lLRNnxfg3utwoPLwt26 | Normal | 2 | 1.5.2.2.10.3 | 1.5.2.2.10.3 |  | 349 | p | 4 | -1% | 353
218 | 5616 | 5Z54Ad8GhuwKLjQHaz2Y | Normal | 1 | 1.5.2.2.10.4 | 1.5.2.2.10.4 |  | 349 | p | 4 | -1% | 353
219 | 5617 | fALGtnsfw381gf0W53Ia | Normal | 0 | 1.5.2.2.10.5 | 1.5.2.2.10.5 |  | 349 | p | 4 | -1% | 353
220 | 5627 | s0vjJX7zGlVyBdE0eigo | Summary | 15 | 1.5.2.2.8 | 1.5.2.2.8 |  | 349 | p | 4 | -1% | 353
221 | 5628 | JolyrZVyKy7n75ZL5gZI | Normal | 2 | 1.5.2.2.8.1 | 1.5.2.2.8.1 |  | 349 | p | 4 | -1% | 353
222 | 5629 | ghMhRqrbgVxCQv51dU2T | Normal | 0 | 1.5.2.2.8.2 | 1.5.2.2.8.2 |  | 349 | p | 4 | -1% | 353
223 | 5630 | eU3bwvC6wgraOvc5hiLt | Milestone | 0 | 1.5.2.2.8.3 | 1.5.2.2.8.3 |  | 349 | p | 4 | -1% | 353
224 | 5631 | gvTQVNdftDRXYXclyMFo | Normal | 3 | 1.5.2.2.8.4 | 1.5.2.2.8.4 |  | 349 | p | 4 | -1% | 353
225 | 5632 | DfRDIp64TG1m6LE7SSYQ | Milestone | 0 | 1.5.2.2.8.5 | 1.5.2.2.8.5 |  | 349 | p | 4 | -1% | 353
226 | 5633 | 2UPBwQymcCOUpuUjnBTe | Normal | 3 | 1.5.2.2.8.6 | 1.5.2.2.8.6 |  | 349 | p | 4 | -1% | 353
227 | 5634 | gm5pLWvICR0pU7aShOGD | Normal | 1 | 1.5.2.2.8.7 | 1.5.2.2.8.7 |  | 349 | p | 4 | -1% | 353
228 | 7545 | 65jUkOPqlMfpoMROhJ4O | Normal | 5 | 1.5.3.2.9.1 | 1.5.3.2.9.1 |  | 349 | q | -349 | (-100%) | 0
229 | 5635 | ZYzv9KOmVdYL2d3ZPb8b | Summary | 0 | 1.5.2.2.9 | 1.5.2.2.9 |  | 0 | p | 370 |  | 370
230 | 5637 | agdOsAK6kuG5dvRDXVyv | Milestone | 0 | 1.5.2.2.9.2 | 1.5.2.2.9.2 |  | 0 | p | 370 |  | 370
231 | 5638 | jBSFjjY1RfmWgqa8tOlO | Normal | 0 | 1.5.2.2.9.3 | 1.5.2.2.9.3 |  | 0 | p | 370 |  | 370
232 | 5639 | ymvGdGMdlU958QTwMU9V | Normal | 0 | 1.5.2.2.9.4 | 1.5.2.2.9.4 |  | 0 | p | 370 |  | 370
233 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | 0 | p | 370 |  | 370
234 | 5641 | QjWOhv4eRSTZWx0ATAUl | Normal | 23 | 1.5.2.2.11 | 1.5.2.2.11 |  | 349 | p | 4 | -1% | 353
235 | 6309 | taNk8S9bKnlDToaFycS6 | Summary | 37 | 1.5.3 | 1.5.3 |  | 66 | q | -40 | (-61%) | 26
236 | 5443 | L0xk8h495fvdhlwnri8N | Summary | 37 | 1.5.3.1 | 1.5.3.1 |  | 66 | q | -40 | (-61%) | 26
237 | 5445 | 95pLIsxhFDdrMJGVBrpQ | Summary | 35 | 1.5.3.1.2 | 1.5.3.1.2 |  | 66 | q | -40 | (-61%) | 26
238 | 5447 | ijJ4zfbEfOInLYX7Vu9Z | Normal | 6 | 1.5.3.1.2.2 | 1.5.3.1.2.2 |  | 66 | q | -40 | (-61%) | 26
239 | 5448 | cS9oDqhLQ00Df4o4XStO | Normal | 6 | 1.5.3.1.2.3 | 1.5.3.1.2.3 |  | 66 | q | -40 | (-61%) | 26
240 | 5449 | 6It4K5O7iZJhLoLO2jyi | Normal | 6 | 1.5.3.1.2.4 | 1.5.3.1.2.4 |  | 66 | q | -40 | (-61%) | 26
241 | 5450 | maMtUzorvxHWuMFIlXlq | Normal | 5 | 1.5.3.1.3 | 1.5.3.1.3 |  | 66 | q | -40 | (-61%) | 26
242 | 7381 | Ao7wteklS85dOuCCMM3I | Normal | 124 | 1.5.1 | 1.5.1 |  | 148 | q | -9 | (-6%) | 139
243 | 6270 | Wwp4MRWhcV55WleZhe1f | Summary | 288 | 1.4 | 1.4 |  | 450 | p | 124 | -28% | 574
244 | 6290 | VuOK0YK760zOpXaJ9U7h | Summary | 140 | 1.4.3 | 1.4.3 |  | -26 | q | -8 | -31% | -34
245 | 4537 | FhESv2GOKRYErv6rS2Ko | Summary | 140 | 1.4.3.1 | 1.4.3.1 |  | -26 | q | -8 | -31% | -34
246 | 576 | m8O5CFAYfVbtxxZI5qQW | Normal | 15 | 1.4.3.1.2 | 1.4.3.1.2 |  | 65 | p | 2 | -3% | 67
247 | 4536 | zU98x2LHVd7UXovDFMXu | Normal | 14 | 1.4.3.1.1 | 1.4.3.1.1 |  | 258 | q | -46 | (-18%) | 212
248 | 5854 | 2kqOvhRPajU4Q0ZPsUnx | Normal | 8 | 1.4.3.1.4 | 1.4.3.1.4 |  | 11 | q | -46 | (-418%) | -35
249 | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Normal | 49 | 1.4.3.1.5 | 1.4.3.1.5 |  | -26 | q | -8 | -31% | -34
250 | 6607 | IhYDHpDNbof6PVOjQ9lw | Normal | 4 | 1.4.3.1.3 | 1.4.3.1.3 |  | 16 | q | -47 | (-294%) | -31
251 | 6291 | 7X6NK9qir9GRz5m7bXmK | Summary | 297 | 1.4.1 | 1.4.1 |  | 450 | p | 124 | -28% | 574
252 | 3891 | VQVEpj4HfOnKALplb4t9 | Summary | 43 | 1.4.1.1 | 1.4.1.1 |  | 238 | q | -41 | (-17%) | 197
253 | 3897 | cqWsQsQWdy7etYVMNQBf | Summary | 53 | 1.4.1.1.2 | 1.4.1.1.2 |  | 238 | q | -41 | (-17%) | 197
254 | 3900 | fYbjIfZDvkbYu7p7dq3N | Normal | 14 | 1.4.1.1.2.3 | 1.4.1.1.2.3 |  | 238 | q | -41 | (-17%) | 197
255 | 3901 | Jj1toL1YzUk95oK7OfgU | Normal | 4 | 1.4.1.1.2.4 | 1.4.1.1.2.4 |  | 238 | q | -41 | (-17%) | 197
256 | 3902 | FL4HGNxujC5zK4lN6AVO | Summary | 30 | 1.4.1.2 | 1.4.1.2 |  | 216 | p | 21 | -10% | 237
257 | 3903 | e0nMZ5CLCmjCURLrKpol | Summary | 30 | 1.4.1.2.1 | 1.4.1.2.1 |  | 216 | p | 21 | -10% | 237
258 | 6565 | XyBOyY3JpPW2h1I7PEur | Normal | 21 | 1.4.1.2.1.5 | 1.4.1.2.1.5 |  | 216 | p | 21 | -10% | 237
259 | 6566 | gAyE6SkFHV1MNEAJitQ7 | Normal | 1 | 1.4.1.2.1.6 | 1.4.1.2.1.6 |  | 216 | p | 21 | -10% | 237
260 | 3907 | pFYLZycbgH4KMn6pLhBU | Summary | 272 | 1.4.1.3 | 1.4.1.3 |  | 24 | q | -17 | (-71%) | 7
261 | 3908 | y9tKov3jCEzWGyA9B1wJ | Normal | 5 | 1.4.1.3.1 | 1.4.1.3.1 |  | 178 | p | 59 | -33% | 237
262 | 3909 | VvjZ0oHXTTG06m5XlL1B | Normal | 10 | 1.4.1.3.2 | 1.4.1.3.2 |  | 178 | p | 59 | -33% | 237
263 | 3910 | pNRX5rV0uvvHnR27z1AO | Normal | 8 | 1.4.1.3.3 | 1.4.1.3.3 |  | 24 | q | -17 | (-71%) | 7
264 | 3911 | R3AK39H17lCC16PE9DkR | Normal | 10 | 1.4.1.3.4 | 1.4.1.3.4 |  | 24 | q | -17 | (-71%) | 7
265 | 3912 | BSEXS69UjCPQ6j2zF47p | Normal | 15 | 1.4.1.3.5 | 1.4.1.3.5 |  | 24 | q | -17 | (-71%) | 7
266 | 3913 | nUmJBAacPI2xORV8OCED | Normal | 20 | 1.4.1.3.6 | 1.4.1.3.6 |  | 24 | q | -17 | (-71%) | 7
267 | 3914 | e7efPn2W4IFyilt2hNai | Normal | 30 | 1.4.1.3.7 | 1.4.1.3.7 |  | 24 | q | -17 | (-71%) | 7
268 | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Normal | 5 | 1.4.1.3.8 | 1.4.1.3.8 |  | 24 | q | -17 | (-71%) | 7
269 | 3916 | xcLTkuiw0V5a2mOSGmcP | Normal | 10 | 1.4.1.3.9 | 1.4.1.3.9 |  | 24 | q | -17 | (-71%) | 7
270 | 3917 | hmttcJptV92JIo4OpANW | Normal | 5 | 1.4.1.3.10 | 1.4.1.3.10 |  | 24 | q | -17 | (-71%) | 7
271 | 3918 | VKkEEklTkhlAtqntT93x | Summary | 160 | 1.4.1.4 | 1.4.1.4 |  | 450 | p | 124 | -28% | 574
272 | 3919 | 70MdVf3krr3KZdDhEaoj | Normal | 1 | 1.4.1.4.1 | 1.4.1.4.1 |  | 537 | p | 111 | -21% | 648
273 | 3920 | mBVNyTIN7rvKyNQxzyxZ | Normal | 9 | 1.4.1.4.2 | 1.4.1.4.2 |  | 537 | p | 111 | -21% | 648
274 | 3921 | jEuseC90wYhkn0V4svXs | Normal | 3 | 1.4.1.4.3 | 1.4.1.4.3 |  | 496 | p | 133 | -27% | 629
275 | 3922 | yD55zWPn8USsNa4i8nCC | Normal | 5 | 1.4.1.4.4 | 1.4.1.4.4 |  | 450 | p | 124 | -28% | 574
276 | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Normal | 15 | 1.4.1.4.5 | 1.4.1.4.5 |  | 450 | p | 124 | -28% | 574
277 | 3924 | N1CigBiMQE2J41ZAMkt0 | Normal | 20 | 1.4.1.4.6 | 1.4.1.4.6 |  | 450 | p | 124 | -28% | 574
278 | 3925 | hSr4t1vn7GiB6Kp7YK0M | Normal | 5 | 1.4.1.4.7 | 1.4.1.4.7 |  | 450 | p | 124 | -28% | 574
279 | 3926 | vGJMK6sejFbKR6Gom2up | Normal | 5 | 1.4.1.4.8 | 1.4.1.4.8 |  | 450 | p | 124 | -28% | 574
280 | 3927 | 3RLmiC17tI4E2ggNuRe0 | Normal | 5 | 1.4.1.4.9 | 1.4.1.4.9 |  | 450 | p | 124 | -28% | 574
281 | 3928 | hCBFci3gUopMkWW2dQQj | Normal | 5 | 1.4.1.4.10 | 1.4.1.4.10 |  | 450 | p | 124 | -28% | 574
282 | 6318 | cM5VCGnPiK1mfNJo8YLF | Summary | 309 | 1.4.2 | 1.4.2 |  | 455 | p | 142 | -31% | 597
283 | 5217 | e116DivbRDCkLiH2zNhl | Summary | 61 | 1.4.2.2.4 | 1.4.2.2.4 |  | 85 | q | -8 | (-9%) | 77
284 | 5218 | 8GMyARBjPLtiSR4txAaa | Milestone | 0 | 1.4.2.2.4.1 | 1.4.2.2.4.1 |  | 85 | q | -8 | (-9%) | 77
285 | 5219 | Uz3hspiJXkYJElXZ00I5 | Normal | 60 | 1.4.2.2.4.2 | 1.4.2.2.4.2 |  | 85 | q | -8 | (-9%) | 77
286 | 5220 | QAqXx5k5ldQJaugZyYbR | Normal | 1 | 1.4.2.2.4.3 | 1.4.2.2.4.3 |  | 85 | q | -8 | (-9%) | 77
287 | 5221 | iTaWceiQKMF6gUaF3DCB | Summary | 61 | 1.4.2.2.5 | 1.4.2.2.5 |  | 117 | q | -4 | (-3%) | 113
288 | 5222 | 4u5ocGGr0fcTRpzuglXZ | Milestone | 0 | 1.4.2.2.5.1 | 1.4.2.2.5.1 |  | 117 | q | -4 | (-3%) | 113
289 | 5223 | 3nEJb4lsc7akFmF6ULw7 | Normal | 60 | 1.4.2.2.5.2 | 1.4.2.2.5.2 |  | 117 | q | -4 | (-3%) | 113
290 | 5224 | PvORb6t1pqf23aOFbh3S | Normal | 1 | 1.4.2.2.5.3 | 1.4.2.2.5.3 |  | 117 | q | -4 | (-3%) | 113
291 | 5277 | TgmqG1sR4A60sNmMtPcE | Summary | 193 | 1.4.2.2.7 | 1.4.2.2.7 |  | -28 | p | 3 | (-11%) | -25
292 | 5278 | OmCdw3tKtVsW24V2aNqQ | Normal | 8 | 1.4.2.2.7.1 | 1.4.2.2.7.1 |  | -28 | p | 3 | (-11%) | -25
293 | 5279 | htHZ3VhuaadgfKg1VQls | Summary | 47 | 1.4.2.2.7.11 | 1.4.2.2.7.11 |  | -28 | p | 4 | (-14%) | -24
294 | 5280 | q0a2rl5NSMPQe2o4IYAd | Normal | 3 | 1.4.2.2.7.11.1 | 1.4.2.2.7.11.1 |  | -28 | p | 10 | (-36%) | -18
295 | 5281 | 3GO4XZOZrW4CEje40UJT | Normal | 5 | 1.4.2.2.7.11.2 | 1.4.2.2.7.11.2 |  | -6 | p | 1 | (-17%) | -5
296 | 5282 | qBzS7vPbhPVzs7sVXgmM | Normal | 5 | 1.4.2.2.7.11.3 | 1.4.2.2.7.11.3 |  | -11 | q | -12 | -109% | -23
297 | 5283 | fU0pzeQGz2MN3lZmznFh | Normal | 5 | 1.4.2.2.7.11.4 | 1.4.2.2.7.11.4 |  | -16 | p | 16 | (-100%) | 0
298 | 5284 | epM0xPGW4QTSpblHVWYc | Normal | 10 | 1.4.2.2.7.11.5 | 1.4.2.2.7.11.5 |  | -28 | p | 5 | (-18%) | -23
299 | 5285 | ffNcVsnPBySsZbQiEShc | Normal | 10 | 1.4.2.2.7.11.6 | 1.4.2.2.7.11.6 |  | -28 | p | 4 | (-14%) | -24
300 | 5286 | Yb8sH9U5B9gBzfVjcJKN | Normal | 6 | 1.4.2.2.7.12 | 1.4.2.2.7.12 |  | -28 | p | 4 | (-14%) | -24
301 | 5287 | bhDhrVJ9ZVKMNyReuPKm | Normal | 5 | 1.4.2.2.7.13 | 1.4.2.2.7.13 |  | -28 | p | 4 | (-14%) | -24
302 | 5288 | RIVzpLwElpoiAIgfwKiL | Milestone | 0 | 1.4.2.2.7.14 | 1.4.2.2.7.14 |  | -28 | p | 4 | (-14%) | -24
303 | 6457 | PFYaNHtSBj97Eh5ysTvH | Normal | 7 | 1.4.2.2.7.2 | 1.4.2.2.7.2 |  | -28 | p | 3 | (-11%) | -25
304 | 6458 | pDFztlVdvvSj2i4Cz5Z9 | Normal | 5 | 1.4.2.2.7.3 | 1.4.2.2.7.3 |  | -28 | p | 3 | (-11%) | -25
305 | 6459 | ylmwXTiOnCLJpwlHTaRg | Normal | 10 | 1.4.2.2.7.4 | 1.4.2.2.7.4 |  | -28 | p | 3 | (-11%) | -25
306 | 6460 | CystLMJtc4xxgICiEMDQ | Normal | 8 | 1.4.2.2.7.5 | 1.4.2.2.7.5 |  | -28 | p | 3 | (-11%) | -25
307 | 6461 | 7ypQo0ZyAHzCHmFRlywg | Normal | 10 | 1.4.2.2.7.6 | 1.4.2.2.7.6 |  | -28 | p | 3 | (-11%) | -25
308 | 6462 | BWDOi71UCejcEb1fgeoY | Normal | 7 | 1.4.2.2.7.7 | 1.4.2.2.7.7 |  | -28 | p | 3 | (-11%) | -25
309 | 6463 | OelD6citgJccZhV0UyvH | Normal | 7 | 1.4.2.2.7.8 | 1.4.2.2.7.8 |  | -28 | p | 3 | (-11%) | -25
310 | 6464 | McSTYqZ3LCfaYSSmZoTn | Normal | 7 | 1.4.2.2.7.9 | 1.4.2.2.7.9 |  | -28 | p | 3 | (-11%) | -25
311 | 6465 | WAyiiuxKOgY7bZWYUV9d | Normal | 5 | 1.4.2.2.7.10 | 1.4.2.2.7.10 |  | -28 | p | 3 | (-11%) | -25
312 | 5226 | R9JO9mOSGmg0eoDimoJT | Summary | 71 | 1.4.2.1 | 1.4.2.1 |  | 773 | p | 168 | -22% | 941
313 | 5240 | NSmZbDTp76mGzDSQ7Ceh | Summary | 56 | 1.4.2.1.3 | 1.4.2.1.3 |  | 10 | q | -1 | (-10%) | 9
314 | 5241 | v6EKIZLcnDHW8CXOrD7y | Normal | 21 | 1.4.2.1.3.1 | 1.4.2.1.3.1 |  | 10 | p | 122 | -1220% | 132
315 | 5242 | JYCfpao49G3jD8M94S66 | Normal | 10 | 1.4.2.1.3.2 | 1.4.2.1.3.2 |  | 10 | p | 88 | -880% | 98
316 | 5243 | 0XN39P602kPVdw6rXYZi | Normal | 10 | 1.4.2.1.3.3 | 1.4.2.1.3.3 |  | 10 | q | -1 | (-10%) | 9
317 | 5244 | Nwqnc6xsOuQ8oMDbKNfv | Normal | 15 | 1.4.2.1.3.4 | 1.4.2.1.3.4 |  | 10 | q | -1 | (-10%) | 9
318 | 5262 | PI0DE6xTKT4gLnHpqgjE | Summary | 137 | 1.4.2.1.6 | 1.4.2.1.6 |  | -28 | p | 4 | (-14%) | -24
319 | 5263 | URhzXaXmWu6rBPIMitrn | Normal | 30 | 1.4.2.1.6.1 | 1.4.2.1.6.1 |  | -28 | p | 4 | (-14%) | -24
320 | 5265 | ATYnDTN93dB3aTXfzslo | Normal | 6 | 1.4.2.1.6.2 | 1.4.2.1.6.2 |  | -28 | p | 4 | (-14%) | -24
321 | 5266 | G5H4IlBy3M3Zxs38gcIH | Normal | 10 | 1.4.2.1.6.3 | 1.4.2.1.6.3 |  | -28 | p | 4 | (-14%) | -24
322 | 5267 | 3RI5G3ymKjaLn96cfboa | Normal | 11 | 1.4.2.1.6.4 | 1.4.2.1.6.4 |  | -28 | p | 4 | (-14%) | -24
323 | 5268 | fG9nayiE82fFlNFtuyfN | Normal | 8 | 1.4.2.1.6.5 | 1.4.2.1.6.5 |  | 52 | q | -33 | (-63%) | 19
324 | 5269 | UP8sWsDXCDMiwOqWz3ib | Normal | 5 | 1.4.2.1.6.6 | 1.4.2.1.6.6 |  | -28 | p | 4 | (-14%) | -24
325 | 5270 | 0UA65kBzwzHULCayr1Gq | Normal | 8 | 1.4.2.1.6.7 | 1.4.2.1.6.7 |  | -28 | p | 4 | (-14%) | -24
326 | 5271 | mtztJWmm2OBnfmSsuoGt | Normal | 10 | 1.4.2.1.6.8 | 1.4.2.1.6.8 |  | -28 | p | 4 | (-14%) | -24
327 | 5272 | kvS9pO69DNwaLvofAQcb | Normal | 11 | 1.4.2.1.6.9 | 1.4.2.1.6.9 |  | -28 | p | 4 | (-14%) | -24
328 | 5273 | fGHKYfAaAseAkWqOpGpv | Normal | 10 | 1.4.2.1.6.10 | 1.4.2.1.6.10 |  | -28 | p | 4 | (-14%) | -24
329 | 5274 | zjsmmZ1Zvuz0mxAk4wzH | Normal | 10 | 1.4.2.1.6.11 | 1.4.2.1.6.11 |  | -28 | p | 4 | (-14%) | -24
330 | 5275 | lBTJLZ8EG6vqarjSz7m6 | Milestone | 0 | 1.4.2.1.6.12 | 1.4.2.1.6.12 |  | -28 | p | 4 | (-14%) | -24
331 | 5264 | 2BYRPY9ftrCpjg2j3vxJ | Milestone | 0 | 1.4.2.1.8 | 1.4.2.1.8 |  | 932 | p | 369 | -40% | 1301
332 | 5276 | yja2Gk0YbNXya3vsxrwh | Milestone | 0 | 1.4.2.1.7 | 1.4.2.1.7 |  | -28 | p | 4 | (-14%) | -24
333 | 5290 | NEvSl0zKCrGJ6lqshTZO | Milestone | 0 | 1.4.2.3.1 | 1.4.2.3.1 |  | 117 | q | -4 | (-3%) | 113
334 | 5313 | 3y8KKUl940HiJi7UFKFT | Summary | 106 | 1.4.2.3.3 | 1.4.2.3.3 |  | 455 | p | 142 | -31% | 597
335 | 5314 | SRtjKDi8lC5PBWdNdIAU | Normal | 10 | 1.4.2.3.3.1 | 1.4.2.3.3.1 |  | 463 | p | 142 | -31% | 605
336 | 5316 | LCfcLPfxTjnSY0dCrjlE | Normal | 10 | 1.4.2.3.3.2 | 1.4.2.3.3.2 |  | 455 | p | 142 | -31% | 597
337 | 5317 | pw6YyMXR7oeqsrtIHdqo | Normal | 9 | 1.4.2.3.3.3 | 1.4.2.3.3.3 |  | 455 | p | 142 | -31% | 597
338 | 5318 | KMG5hXAC4X2MZPfyVOSc | Normal | 5 | 1.4.2.3.3.8 | 1.4.2.3.3.8 |  | 455 | p | 142 | -31% | 597
339 | 5319 | mDGXCmTQB2ITo8MYwlYq | Normal | 5 | 1.4.2.3.3.9 | 1.4.2.3.3.9 |  | 455 | p | 142 | -31% | 597
340 | 5320 | hu6UActfLD0rLfdNqC55 | Normal | 5 | 1.4.2.3.3.10 | 1.4.2.3.3.10 |  | 455 | p | 142 | -31% | 597
341 | 5321 | pG9QTaeiPcJe7Bm3iI1s | Normal | 5 | 1.4.2.3.3.11 | 1.4.2.3.3.11 |  | 455 | p | 142 | -31% | 597
342 | 5322 | oNpYocgOFdrRcJiQE0H5 | Normal | 5 | 1.4.2.3.3.12 | 1.4.2.3.3.12 |  | 455 | p | 142 | -31% | 597
343 | 5323 | Tt5dEbDabBigq84Eat5c | Normal | 5 | 1.4.2.3.3.13 | 1.4.2.3.3.13 |  | 455 | p | 142 | -31% | 597
344 | 5324 | INz2wzhVzgQCZLXqwTZc | Normal | 5 | 1.4.2.3.3.14 | 1.4.2.3.3.14 |  | 455 | p | 142 | -31% | 597
345 | 5325 | D5c4JntP5EU4thbOE4hi | Normal | 1 | 1.4.2.3.3.15 | 1.4.2.3.3.15 |  | 455 | p | 142 | -31% | 597
346 | 6467 | n3qEWBmgcrCNzbacKk03 | Normal | 5 | 1.4.2.3.3.4 | 1.4.2.3.3.4 |  | 455 | p | 142 | -31% | 597
347 | 6468 | BqsEZH5IWCI59bWKml0D | Normal | 5 | 1.4.2.3.3.5 | 1.4.2.3.3.5 |  | 455 | p | 142 | -31% | 597
348 | 6469 | TtC6fzAb8zClFAVfKkP8 | Normal | 5 | 1.4.2.3.3.6 | 1.4.2.3.3.6 |  | 455 | p | 142 | -31% | 597
349 | 6470 | UrgnPc0HjVwpN7twGsWX | Normal | 5 | 1.4.2.3.3.7 | 1.4.2.3.3.7 |  | 455 | p | 142 | -31% | 597
350 | 5326 | esDa5lJIA5zg0nP58cRd | Summary | 32 | 1.4.2.3.4 | 1.4.2.3.4 |  | 201 | p | 25 | -12% | 226
351 | 5327 | iRZmxts3rKQ38tplQw52 | Normal | 30 | 1.4.2.3.4.1 | 1.4.2.3.4.1 |  | 201 | p | 25 | -12% | 226
352 | 5328 | ngeJL3ilFttQtHxnOEwX | Normal | 1 | 1.4.2.3.4.2 | 1.4.2.3.4.2 |  | 201 | p | 25 | -12% | 226
353 | 5329 | GYUaK0PI1fV4kag2egD8 | Normal | 1 | 1.4.2.3.4.3 | 1.4.2.3.4.3 |  | 742 | p | 171 | -23% | 913
354 | 6321 | KAyzIHlSkkFZqIIdJ9JD | Summary | 144 | 1.4.2.3.2 | 1.4.2.3.2 |  | 11 | q | -47 | (-427%) | -36
355 | 5298 | c4SSanbHhynqs8RkqT3I | Normal | 3 | 1.4.2.3.2.2 | 1.4.2.3.2.2 |  | 11 | q | -47 | (-427%) | -36
356 | 5299 | HB5wL9z8KlZFeAas0WUQ | Normal | 11 | 1.4.2.3.2.3 | 1.4.2.3.2.3 |  | 11 | q | -47 | (-427%) | -36
357 | 5301 | hHw9byxBfgMW8zXuSsdj | Milestone | 0 | 1.4.2.3.2.12 | 1.4.2.3.2.12 |  | 11 | q | -47 | (-427%) | -36
358 | 5302 | 2rc67Y2hzAhRvE7YihWA | Normal | 10 | 1.4.2.3.2.1 | 1.4.2.3.2.1 |  | 11 | q | -47 | (-427%) | -36
359 | 5303 | SgeIRg4ykwxbNqD9urWV | Normal | 2 | 1.4.2.3.2.8 | 1.4.2.3.2.8 |  | 11 | q | -47 | (-427%) | -36
360 | 5304 | KRXQrBZsFBKS9k4FvAsp | Normal | 3 | 1.4.2.3.2.9 | 1.4.2.3.2.9 |  | 11 | q | -47 | (-427%) | -36
361 | 5305 | TyGQYH0bANBrFjXmh15D | Normal | 2 | 1.4.2.3.2.10 | 1.4.2.3.2.10 |  | 11 | q | -47 | (-427%) | -36
362 | 5306 | yar7ts7ASIpTQqyvnwQd | Normal | 5 | 1.4.2.3.2.13 | 1.4.2.3.2.13 |  | 11 | q | -47 | (-427%) | -36
363 | 5307 | yRByGMPgEQcCecr5HzAA | Normal | 2 | 1.4.2.3.2.15 | 1.4.2.3.2.15 |  | 11 | q | -47 | (-427%) | -36
364 | 5308 | JBAsTSNPb9OQmIAmtadV | Normal | 20 | 1.4.2.3.2.17 | 1.4.2.3.2.17 |  | 8 | q | -44 | (-550%) | -36
365 | 5309 | xRRT514kq8kwyv7njrs5 | Normal | 5 | 1.4.2.3.2.19 | 1.4.2.3.2.19 |  | -28 | q | -8 | -29% | -36
366 | 5311 | BowxNbb4uXSnAk8z8ZkC | Normal | 2 | 1.4.2.3.2.22 | 1.4.2.3.2.22 |  | -28 | q | -8 | -29% | -36
367 | 5312 | mmXMEY1kphvE51vXPbq6 | Milestone | 0 | 1.4.2.3.2.25 | 1.4.2.3.2.25 |  | 19 | p | 1 | -5% | 20
368 | 6516 | qmbk7ROGAo4AwJOySAlG | Normal | 4 | 1.4.2.3.2.4 | 1.4.2.3.2.4 |  | 11 | q | -47 | (-427%) | -36
369 | 6517 | YGaikKlMVGc6fqtUBZ7h | Normal | 5 | 1.4.2.3.2.5 | 1.4.2.3.2.5 |  | 11 | q | -47 | (-427%) | -36
370 | 6518 | 0rDsNLFYCabTnyCcopAQ | Normal | 8 | 1.4.2.3.2.6 | 1.4.2.3.2.6 |  | 11 | q | -47 | (-427%) | -36
371 | 6519 | UldK3RoYRJH5Hsfv02Lh | Normal | 2 | 1.4.2.3.2.7 | 1.4.2.3.2.7 |  | 11 | q | -47 | (-427%) | -36
372 | 6520 | UaqqB30tdDFCsCHRRpeh | Normal | 2 | 1.4.2.3.2.11 | 1.4.2.3.2.11 |  | 11 | q | -47 | (-427%) | -36
373 | 6521 | LDY9CVOjImzsQ4NE65Qz | Normal | 1 | 1.4.2.3.2.16 | 1.4.2.3.2.16 |  | 11 | q | -47 | (-427%) | -36
374 | 6522 | WYJvDx3FrKALT2lj4FIo | Normal | 2 | 1.4.2.3.2.18 | 1.4.2.3.2.18 |  | 8 | q | -44 | (-550%) | -36
375 | 6523 | TvM5XBX3OaVljTSOZ4e2 | Normal | 2 | 1.4.2.3.2.21 | 1.4.2.3.2.21 |  | -28 | q | -8 | -29% | -36
376 | 6524 | cvaJgvK8KpGYV8ykH12h | Normal | 2 | 1.4.2.3.2.23 | 1.4.2.3.2.23 |  | -28 | q | -8 | -29% | -36
377 | 6525 | GtEwLNkefPtnncnl90X4 | Normal | 3 | 1.4.2.3.2.24 | 1.4.2.3.2.24 |  | -27 | q | -9 | -33% | -36
378 | 6873 | gSZIbC6fsU6IM6McOJy8 | Normal | 1 | 1.4.2.3.2.14 | 1.4.2.3.2.14 |  | 11 | q | -47 | (-427%) | -36
379 | 6271 | Q6QswYSvhipRUbZBXuiu | Summary | 315 | 1.6 | 1.6 |  | 488 | p | 77 | -16% | 565
380 | 6277 | moVS9Ou3GclDwNSW1OnS | Summary | 264 | 1.6.7 | 1.6.7 |  | 512 | p | 76 | -15% | 588
381 | 678 | N57z7OkXN935WcKbC4jO | Normal | 1 | 1.6.7.2 | 1.6.7.2 |  | 512 | p | 83 | -16% | 595
382 | 700 | PZaQwD8fp0dlxZIxEZEd | Normal | 279 | 1.6.7.10 | 1.6.7.10 |  | 510 | p | 64 | -13% | 574
383 | 728 | 4dRz6TQj3FOK8lstTqZK | Summary | 396 | 1.6.7.9 | 1.6.7.9 |  | 512 | p | 83 | -16% | 595
384 | 741 | cktDjgZ5bp36SrQnCM1w | Summary | 458 | 1.6.7.9.3 | 1.6.7.9.3 |  | 512 | p | 83 | -16% | 595
385 | 751 | AADJzuTGAb4gWytj7CQi | Normal | 18 | 1.6.7.9.3.8 | 1.6.7.9.3.8 |  | 488 | p | 117 | -24% | 605
386 | 752 | r0c0rFS4EkOGynasmiCG | Normal | 36 | 1.6.7.9.3.7 | 1.6.7.9.3.7 |  | 510 | p | 106 | -21% | 616
387 | 759 | cZuo3MY7iyDrOJC1qVJx | Normal | 5 | 1.6.7.9.3.9 | 1.6.7.9.3.9 |  | 488 | p | 117 | -24% | 605
388 | 765 | qOEfFivvitnF8cw9csOP | Normal | 1 | 1.6.7.9.3.13 | 1.6.7.9.3.13 |  | 512 | p | 83 | -16% | 595
389 | 5773 | OCcI80TDGF8LlIXj66uV | Normal | 3 | 1.6.7.9.3.14 | 1.6.7.9.3.14 |  | 512 | p | 83 | -16% | 595
390 | 6323 | aU24Z8SrLl20SyyllZuy | Summary | 80 | 1.6.7.9.3.5 | 1.6.7.9.3.5 |  | 498 | p | 133 | -27% | 631
391 | 745 | aO52oWR4hBrrP5GVCo2a | Normal | 11 | 1.6.7.9.3.5.2 | 1.6.7.9.3.5.2 |  | 488 | p | 131 | -27% | 619
392 | 746 | qMC0J8brk1dsdpzlKrk7 | Normal | 12 | 1.6.7.9.3.5.3 | 1.6.7.9.3.5.3 |  | 498 | p | 133 | -27% | 631
393 | 6324 | gthK0FxwJBk3laTELp8O | Summary | 45 | 1.6.7.9.3.6 | 1.6.7.9.3.6 |  | 488 | p | 117 | -24% | 605
394 | 747 | nul8vpOEtI2Q6W5Q0Qo9 | Normal | 12 | 1.6.7.9.3.6.1 | 1.6.7.9.3.6.1 |  | 488 | p | 117 | -24% | 605
395 | 748 | M1HHh2K01o23jS8vpDxS | Normal | 11 | 1.6.7.9.3.6.2 | 1.6.7.9.3.6.2 |  | 488 | p | 117 | -24% | 605
396 | 749 | Q6UXOpf9Kvzek7IGY0vp | Normal | 11 | 1.6.7.9.3.6.3 | 1.6.7.9.3.6.3 |  | 488 | p | 117 | -24% | 605
397 | 750 | lsyrPytnmjLTpXFywa7Z | Normal | 11 | 1.6.7.9.3.6.4 | 1.6.7.9.3.6.4 |  | 488 | p | 117 | -24% | 605
398 | 6325 | SeCXD5wMvkrEekc1PKVb | Summary | 48 | 1.6.7.9.3.10 | 1.6.7.9.3.10 |  | 506 | p | 72 | -14% | 578
399 | 753 | 8158sxzbHZvZEVAAqewP | Normal | 47 | 1.6.7.9.3.10.1 | 1.6.7.9.3.10.1 |  | 522 | p | 92 | -18% | 614
400 | 754 | hfPeDXfQSV7Nx9zb2rD7 | Normal | 8 | 1.6.7.9.3.10.2 | 1.6.7.9.3.10.2 |  | 506 | p | 59 | -12% | 565
401 | 755 | DQUdswbbJv1Qpkj0EGFX | Normal | 8 | 1.6.7.9.3.10.3 | 1.6.7.9.3.10.3 |  | 506 | p | 59 | -12% | 565
402 | 756 | ae3T3d3nFoXZXK7gqkAr | Normal | 20 | 1.6.7.9.3.10.4 | 1.6.7.9.3.10.4 |  | 506 | p | 59 | -12% | 565
403 | 757 | wbc1AZ0GUhXzQk6SoWIe | Normal | 6 | 1.6.7.9.3.10.6 | 1.6.7.9.3.10.6 |  | 506 | p | 59 | -12% | 565
404 | 758 | FbN1rrQYTlsz1haWZnFy | Normal | 6 | 1.6.7.9.3.10.8 | 1.6.7.9.3.10.8 |  | 506 | p | 59 | -12% | 565
405 | 5780 | XCMvjmTKbAUuCZwuNlSF | Normal | 6 | 1.6.7.9.3.10.5 | 1.6.7.9.3.10.5 |  | 520 | p | 59 | -11% | 579
406 | 5782 | EYY3j1SjnoLUV06T0QHs | Normal | 5 | 1.6.7.9.3.10.7 | 1.6.7.9.3.10.7 |  | 513 | p | 61 | -12% | 574
407 | 6326 | F4s3MnfyyA74WCIympSi | Summary | 75 | 1.6.7.9.3.11 | 1.6.7.9.3.11 |  | 488 | p | 77 | -16% | 565
408 | 760 | 7IpOsslq7gyebnCTulxX | Normal | 66 | 1.6.7.9.3.11.1 | 1.6.7.9.3.11.1 |  | 488 | p | 117 | -24% | 605
409 | 761 | x6fNhJzs4uMW9trtiNEW | Normal | 1 | 1.6.7.9.3.11.2 | 1.6.7.9.3.11.2 |  | 488 | p | 77 | -16% | 565
410 | 762 | nRInnITHYgcDsU5KDg6m | Normal | 8 | 1.6.7.9.3.11.3 | 1.6.7.9.3.11.3 |  | 488 | p | 77 | -16% | 565
411 | 6327 | dOJS0LaWQU970ssSiqsz | Summary | 59 | 1.6.7.9.3.12 | 1.6.7.9.3.12 |  | 488 | p | 77 | -16% | 565
412 | 763 | hLK2cdXSS7IhOZR53PgI | Normal | 6 | 1.6.7.9.3.12.1 | 1.6.7.9.3.12.1 |  | 488 | p | 77 | -16% | 565
413 | 764 | wTf98lLeHiXAkWj17mAH | Normal | 53 | 1.6.7.9.3.12.2 | 1.6.7.9.3.12.2 |  | 488 | p | 77 | -16% | 565
414 | 770 | cHAOkWrFbu094CNd9eCk | Summary | 91 | 1.6.7.8 | 1.6.7.8 |  | 650 | p | 106 | -16% | 756
415 | 786 | 5RJIBxVgSA4dodMzOCsx | Normal | 1 | 1.6.7.8.5 | 1.6.7.8.5 |  | 650 | p | 106 | -16% | 756
416 | 6434 | cc8WGEqtonq4zOxPHtWc | Normal | 65 | 1.6.7.8.4 | 1.6.7.8.4 |  | 650 | p | 106 | -16% | 756
417 | 5785 | xIbBdattr1YLWDiqGWPC | Summary | 126 | 1.6.7.11 | 1.6.7.11 |  | 512 | p | 76 | -15% | 588
418 | 5774 | Dvlkt7hdSzdJ7ChIr4xD | Normal | 2 | 1.6.7.11.1 | 1.6.7.11.1 |  | 512 | p | 76 | -15% | 588
419 | 5775 | D3NIdGcGrWNhiaQ0dYbY | Normal | 2 | 1.6.7.11.3 | 1.6.7.11.3 |  | 512 | p | 76 | -15% | 588
420 | 6435 | Ql00ScpYzqtI9PQP57zu | Normal | 122 | 1.6.7.11.2 | 1.6.7.11.2 |  | 512 | p | 76 | -15% | 588
421 | 6284 | T6s1mlIi1Lu4cscBpq9h | Summary | 273 | 1.6.6 | 1.6.6 |  | 616 | p | 141 | -23% | 757
422 | 1519 | Ig6aeqJATmPNbReGQrzj | Summary | 273 | 1.6.6.1 | 1.6.6.1 |  | 616 | p | 141 | -23% | 757
423 | 1463 | IQX94tuow2VKmVJTuhEN | Normal | 1 | 1.6.6.1.3 | 1.6.6.1.3 |  | 122 | q | -122 | (-100%) | 0
424 | 1464 | VN7GLU7alOC9oD3kkW9q | Normal | 30 | 1.6.6.1.4 | 1.6.6.1.4 |  | 122 | q | -31 | (-25%) | 91
425 | 1465 | i7zbkIpCuBMJlMsq6ma0 | Normal | 1 | 1.6.6.1.5 | 1.6.6.1.5 |  | 122 | q | -31 | (-25%) | 91
426 | 1475 | suCYO4gIoCSrnZchT6aQ | Normal | 3 | 1.6.6.1.6 | 1.6.6.1.6 |  | 598 | p | 119 | -20% | 717
427 | 1476 | gbuDNYIgLq2nB3WERl4p | Normal | 30 | 1.6.6.1.7 | 1.6.6.1.7 |  | 598 | p | 119 | -20% | 717
428 | 1477 | BC1NYB3fqAlfckX7ECXI | Normal | 1 | 1.6.6.1.8 | 1.6.6.1.8 |  | 598 | p | 119 | -20% | 717
429 | 1478 | UR7xa7LgN3sMlpzxRjvW | Normal | 3 | 1.6.6.1.9 | 1.6.6.1.9 |  | 616 | p | 141 | -23% | 757
430 | 6293 | WhUcOZjaj9TDZe74ojmh | Summary | 172 | 1.6.4 | 1.6.4 |  | 488 | p | 77 | -16% | 565
431 | 3929 | GkmiaraCbWdBUaRv136y | Summary | 19 | 1.6.4.15 | 1.6.4.15 |  | 630 | p | 113 | -18% | 743
432 | 3932 | RKLg9Drqo40Q82TFH1VL | Normal | 1 | 1.6.4.15.2 | 1.6.4.15.2 |  | 494 | p | 111 | -22% | 605
433 | 3934 | 10Oh1H5M5HjeoWxU1u0w | Normal | 1 | 1.6.4.15.4 | 1.6.4.15.4 |  | 630 | p | 116 | -18% | 746
434 | 3936 | hwXDQy0MWIQ4jzjNT4oM | Normal | 1 | 1.6.4.15.3 | 1.6.4.15.3 |  | 630 | p | 124 | -20% | 754
435 | 3938 | 2iJ091mlhEkJyqoddB4L | Normal | 14 | 1.6.4.15.1 | 1.6.4.15.1 |  | 650 | p | 128 | -20% | 778
436 | 3940 | 8UqvtHTIMRT16eupajKq | Normal | 1 | 1.6.4.15.5 | 1.6.4.15.5 |  | 630 | p | 113 | -18% | 743
437 | 3931 | GleHIX38gd9vOXaUQYVA | Normal | 33 | 1.6.4.11 | 1.6.4.11 |  | 494 | p | 111 | -22% | 605
438 | 3933 | FbGZSJQTtuDZR2p8qmxq | Normal | 33 | 1.6.4.13 | 1.6.4.13 |  | 630 | p | 116 | -18% | 746
439 | 3935 | IRdaiLeeauelAg4QWklz | Normal | 33 | 1.6.4.12 | 1.6.4.12 |  | 630 | p | 124 | -20% | 754
440 | 3939 | cuQ4HC0Kn3S6GTvqv7QE | Normal | 33 | 1.6.4.14 | 1.6.4.14 |  | 630 | p | 113 | -18% | 743
441 | 3971 | mB1p68eekBqQhgV8es2U | Summary | 19 | 1.6.4.7 | 1.6.4.7 |  | 655 | p | 101 | -15% | 756
442 | 3974 | xzlIrgrrtbLscLWLbbQq | Normal | 1 | 1.6.4.7.1 | 1.6.4.7.1 |  | 607 | p | 128 | -21% | 735
443 | 3981 | YTm9sByrDxPUc7AlWXh1 | Normal | 15 | 1.6.4.7.2 | 1.6.4.7.2 |  | 655 | p | 101 | -15% | 756
444 | 3973 | 00qHhBlTe8pinGtKpu3n | Normal | 4 | 1.6.4.6 | 1.6.4.6 |  | 607 | q | -607 | (-100%) | 0
445 | 3980 | po54OWwjtqomy5uOkFBU | Normal | 40 | 1.6.4.4 | 1.6.4.4 |  | 655 | p | 101 | -15% | 756
446 | 3991 | kc0LQmDrjfLGJeMU4QIH | Summary | 70 | 1.6.4.17 | 1.6.4.17 |  | 315 | q | -26 | (-8%) | 289
447 | 3992 | cy141kwlo0X5isTqv3ku | Summary | 25 | 1.6.4.17.4 | 1.6.4.17.4 |  | 315 | q | -26 | (-8%) | 289
448 | 3993 | LBRozXrRhpq69SKlxnDb | Normal | 10 | 1.6.4.17.4.1 | 1.6.4.17.4.1 |  | 315 | q | -26 | (-8%) | 289
449 | 3994 | DvOjAQ6C9aXKnpaAVD1H | Normal | 5 | 1.6.4.17.4.2 | 1.6.4.17.4.2 |  | 315 | q | -26 | (-8%) | 289
450 | 3995 | AUkl27NW1i9i5huez8Rg | Normal | 5 | 1.6.4.17.4.3 | 1.6.4.17.4.3 |  | 315 | q | -26 | (-8%) | 289
451 | 3996 | Bw8X4DjnSuQgBiA6BEKp | Normal | 5 | 1.6.4.17.4.4 | 1.6.4.17.4.4 |  | 315 | q | -26 | (-8%) | 289
452 | 3997 | KJPP8ivswwWTIeIfPXEM | Summary | 25 | 1.6.4.17.3 | 1.6.4.17.3 |  | 315 | q | -26 | (-8%) | 289
453 | 3998 | 5UhDwyM7phAycUkk1Nye | Normal | 10 | 1.6.4.17.3.1 | 1.6.4.17.3.1 |  | 315 | q | -26 | (-8%) | 289
454 | 3999 | v6kjlf8aEDhSJHzOK2Uo | Normal | 5 | 1.6.4.17.3.2 | 1.6.4.17.3.2 |  | 315 | q | -26 | (-8%) | 289
455 | 4000 | Y3aJp60cYMHromf8xgAE | Normal | 5 | 1.6.4.17.3.3 | 1.6.4.17.3.3 |  | 315 | q | -26 | (-8%) | 289
456 | 4001 | Cjtbc2cmKWchyZlcOxo3 | Normal | 5 | 1.6.4.17.3.4 | 1.6.4.17.3.4 |  | 315 | q | -26 | (-8%) | 289
457 | 4002 | nJzh0eFJGsqvOmQRJzHn | Summary | 27 | 1.6.4.17.2 | 1.6.4.17.2 |  | 315 | q | -26 | (-8%) | 289
458 | 4003 | gjf3v6NdOQannovTvAoE | Normal | 19 | 1.6.4.17.2.1 | 1.6.4.17.2.1 |  | 315 | q | -26 | (-8%) | 289
459 | 4004 | fF1Y54WMybWnXZsBJgYM | Normal | 1 | 1.6.4.17.2.2 | 1.6.4.17.2.2 |  | 315 | q | -26 | (-8%) | 289
460 | 4005 | NxZ8rMz5ZnJaz6z1SXKM | Normal | 3 | 1.6.4.17.2.3 | 1.6.4.17.2.3 |  | 315 | q | -26 | (-8%) | 289
461 | 4006 | fOTuJvqH3OcilXcZuEM5 | Normal | 4 | 1.6.4.17.2.4 | 1.6.4.17.2.4 |  | 315 | q | -26 | (-8%) | 289
462 | 4012 | A4Ck0Reyqf4cLzrM8uUY | Summary | 206 | 1.6.4.19 | 1.6.4.19 |  | 191 | p | 169 | -88% | 360
463 | 6168 | BHtkkzlMW8757DY2qb23 | Summary | 143 | 1.6.4.19.3 | 1.6.4.19.3 |  | 191 | p | 169 | -88% | 360
464 | 6169 | gdW3U4pURjb9iKkAVexH | Summary | 60 | 1.6.4.19.3.1 | 1.6.4.19.3.1 |  | 191 | p | 169 | -88% | 360
465 | 6170 | AwYLgXY6Mo1DqCbUEhPQ | Summary | 30 | 1.6.4.19.3.1.1 | 1.6.4.19.3.1.1 |  | 191 | p | 169 | -88% | 360
466 | 6171 | ZR4zae2ZYhCMcZhj7T05 | Normal | 15 | 1.6.4.19.3.1.1.1 | 1.6.4.19.3.1.1.1 |  | 191 | p | 169 | -88% | 360
467 | 6172 | QgFskomqU31VYtYzB2O0 | Normal | 15 | 1.6.4.19.3.1.1.2 | 1.6.4.19.3.1.1.2 |  | 191 | p | 169 | -88% | 360
468 | 6173 | nRc7GqDGMG4VP1O5IlEd | Normal | 15 | 1.6.4.19.3.1.2 | 1.6.4.19.3.1.2 |  | 191 | p | 169 | -88% | 360
469 | 6174 | dvLkHNDhuFTU7AO5XWky | Normal | 15 | 1.6.4.19.3.1.3 | 1.6.4.19.3.1.3 |  | 191 | p | 169 | -88% | 360
470 | 6175 | IEttja5qNJ6P760Cd9De | Summary | 40 | 1.6.4.19.3.2 | 1.6.4.19.3.2 |  | 191 | p | 169 | -88% | 360
471 | 6176 | B6x3R7fnpOwupecmo90D | Normal | 10 | 1.6.4.19.3.2.1 | 1.6.4.19.3.2.1 |  | 191 | p | 169 | -88% | 360
472 | 6177 | vkZhJMfsZWiMPLTjgcam | Normal | 10 | 1.6.4.19.3.2.2 | 1.6.4.19.3.2.2 |  | 191 | p | 169 | -88% | 360
473 | 6178 | XEU5rnQh2VnDpMl1eT0o | Normal | 10 | 1.6.4.19.3.2.3 | 1.6.4.19.3.2.3 |  | 191 | p | 169 | -88% | 360
474 | 6179 | xksMzlhYjvKZ4p1XJwSB | Normal | 10 | 1.6.4.19.3.2.4 | 1.6.4.19.3.2.4 |  | 191 | p | 169 | -88% | 360
475 | 6180 | oR7r0RquVFe2h8pCK9HY | Normal | 10 | 1.6.4.19.3.3 | 1.6.4.19.3.3 |  | 191 | p | 169 | -88% | 360
476 | 6181 | UJ3hrxCJ5NslZjdDLEyu | Normal | 20 | 1.6.4.19.3.4 | 1.6.4.19.3.4 |  | 191 | p | 169 | -88% | 360
477 | 6182 | JQHbjwkPqIslt5thIOgQ | Normal | 5 | 1.6.4.19.3.5 | 1.6.4.19.3.5 |  | 191 | p | 169 | -88% | 360
478 | 6183 | 5NqxhAyIl3JXTpWWvSnV | Normal | 2 | 1.6.4.19.3.6 | 1.6.4.19.3.6 |  | 191 | p | 169 | -88% | 360
479 | 6184 | vx8CoW16lw8uEEVKaVp7 | Normal | 5 | 1.6.4.19.3.7 | 1.6.4.19.3.7 |  | 191 | p | 169 | -88% | 360
480 | 6185 | A91LND4pEy61zvjvAsaQ | Normal | 1 | 1.6.4.19.3.8 | 1.6.4.19.3.8 |  | 191 | p | 169 | -88% | 360
481 | 4037 | hMBnPD0NfYpjSqEpRMYY | Summary | 554 | 1.6.4.20 | 1.6.4.20 |  | 488 | p | 77 | -16% | 565
482 | 4038 | VkrURyJwsSkEVRV6WcXe | Summary | 411 | 1.6.4.20.1 | 1.6.4.20.1 |  | 488 | p | 77 | -16% | 565
483 | 4040 | g5zNgGHP8U11wPTJKhcB | Normal | 20 | 1.6.4.20.1.3 | 1.6.4.20.1.3 |  | 656 | p | 305 | -46% | 961
484 | 4041 | f0PORH3GhEIXFjYfGbTd | Normal | 97 | 1.6.4.20.1.6 | 1.6.4.20.1.6 |  | 619 | p | 280 | -45% | 899
485 | 4042 | SyfMayqY4a7i0nZLPz6Y | Normal | 129 | 1.6.4.20.1.7 | 1.6.4.20.1.7 |  | 510 | p | 64 | -13% | 574
486 | 6621 | pXe0ZxltUhDf1quSL5q2 | Normal | 15 | 1.6.4.20.1.2 | 1.6.4.20.1.2 |  | 191 | p | 169 | -88% | 360
487 | 6622 | EmEy5gJckBYofEEYNXFv | Normal | 20 | 1.6.4.20.1.4 | 1.6.4.20.1.4 |  | 488 | p | 77 | -16% | 565
488 | 6623 | BVU87KMg9Rhzc6j5yKVh | Normal | 20 | 1.6.4.20.1.5 | 1.6.4.20.1.5 |  | 488 | p | 77 | -16% | 565
489 | 4043 | XbXkjxtfHUxhg4CK1elt | Summary | 127 | 1.6.4.20.2 | 1.6.4.20.2 |  | 488 | p | 77 | -16% | 565
490 | 4045 | mDphgqAAxA2RnvA52x8A | Normal | 20 | 1.6.4.20.2.1 | 1.6.4.20.2.1 |  | 488 | p | 77 | -16% | 565
491 | 4046 | 5HyQBVwuqRdeW1HhaSOP | Normal | 10 | 1.6.4.20.2.2 | 1.6.4.20.2.2 |  | 488 | p | 77 | -16% | 565
492 | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Normal | 72 | 1.6.4.20.2.3 | 1.6.4.20.2.3 |  | 488 | p | 77 | -16% | 565
493 | 4048 | ybbKhm9jdtNbVzABGZ8L | Normal | 20 | 1.6.4.20.2.4 | 1.6.4.20.2.4 |  | 488 | p | 77 | -16% | 565
494 | 4049 | kP1jeiEwkYg4HRpUjG4p | Normal | 5 | 1.6.4.20.2.5 | 1.6.4.20.2.5 |  | 488 | p | 77 | -16% | 565
495 | 4050 | jQIHIDf5FTnJxQysEvnn | Summary | 37 | 1.6.4.20.3 | 1.6.4.20.3 |  | 488 | p | 77 | -16% | 565
496 | 4051 | bizigDTezGi1mMHxJ1gi | Summary | 32 | 1.6.4.20.3.1 | 1.6.4.20.3.1 |  | 488 | p | 80 | -16% | 568
497 | 4052 | JSSXcLTdD9VQNM766DgK | Normal | 20 | 1.6.4.20.3.1.1 | 1.6.4.20.3.1.1 |  | 488 | p | 80 | -16% | 568
498 | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Normal | 12 | 1.6.4.20.3.1.2 | 1.6.4.20.3.1.2 |  | 488 | p | 80 | -16% | 568
499 | 4054 | WhXMUGkGRid5sulqMW8S | Summary | 5 | 1.6.4.20.3.2 | 1.6.4.20.3.2 |  | 488 | p | 80 | -16% | 568
500 | 4055 | dWrJCmOwv1i72p29KBXE | Normal | 2 | 1.6.4.20.3.2.1 | 1.6.4.20.3.2.1 |  | 488 | p | 80 | -16% | 568
501 | 4056 | a1SRK7UWhIIMlkKKriy9 | Normal | 1 | 1.6.4.20.3.2.2 | 1.6.4.20.3.2.2 |  | 488 | p | 80 | -16% | 568
502 | 4057 | NKnvgqAHKv63TOKudyZQ | Normal | 1 | 1.6.4.20.3.2.3 | 1.6.4.20.3.2.3 |  | 488 | p | 80 | -16% | 568
503 | 4058 | cbANjhwCBqAluf1RM04K | Normal | 1 | 1.6.4.20.3.2.4 | 1.6.4.20.3.2.4 |  | 488 | p | 80 | -16% | 568
504 | 4059 | sH9kz6O2EFda2hu4x8Kx | Summary | 12 | 1.6.4.20.3.3 | 1.6.4.20.3.3 |  | 488 | p | 77 | -16% | 565
505 | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Normal | 3 | 1.6.4.20.3.3.1 | 1.6.4.20.3.3.1 |  | 488 | p | 77 | -16% | 565
506 | 4061 | ViM2psfxppAdWr3IoYdq | Normal | 3 | 1.6.4.20.3.3.2 | 1.6.4.20.3.3.2 |  | 488 | p | 77 | -16% | 565
507 | 4062 | RvsEFsErXikPrAOovPaZ | Normal | 1 | 1.6.4.20.3.3.3 | 1.6.4.20.3.3.3 |  | 488 | p | 77 | -16% | 565
508 | 4063 | ma6GKJ3GzeKmeF4AshaM | Normal | 4 | 1.6.4.20.3.3.4 | 1.6.4.20.3.3.4 |  | 488 | p | 77 | -16% | 565
509 | 4064 | OALhjNOvEaqSDAmsS5Il | Normal | 1 | 1.6.4.20.3.3.5 | 1.6.4.20.3.3.5 |  | 488 | p | 77 | -16% | 565
510 | 5748 | cHP8KcDQZp8MvOi5a8Wj | Summary | 64 | 1.6.4.18 | 1.6.4.18 |  | 501 | p | 126 | -25% | 627
511 | 6701 | vwWJ3SVwW3tYdDDMDgOK | Summary | 60 | 1.6.4.18.3 | 1.6.4.18.3 |  | 501 | p | 126 | -25% | 627
512 | 6713 | JQXHTZXJblKyiNyxM0eT | Summary | 78 | 1.6.4.18.3.3 | 1.6.4.18.3.3 |  | 501 | p | 126 | -25% | 627
513 | 6727 | 5BlmDU3ct4fwjT54EODG | Summary | 21 | 1.6.4.18.3.3.2 | 1.6.4.18.3.3.2 |  | 521 | p | 130 | -25% | 651
514 | 6738 | XB1ZMgqMWvDJpnRGKTB3 | Normal | 3 | 1.6.4.18.3.3.2.10 | 1.6.4.18.3.3.2.10 |  | 521 | q | -521 | (-100%) | 0
515 | 7003 | XfnOKCk0EbakXF7t35fN | Normal | 1 | 1.6.4.18.3.3.2.9 | 1.6.4.18.3.3.2.9 |  | 521 | q | -521 | (-100%) | 0
516 | 7270 | 3AlavOi01JfJwLM1b81K | Milestone | 0 | 1.6.4.18.3.3.2.6 | 1.6.4.18.3.3.2.6 |  | 521 | q | -521 | (-100%) | 0
517 | 7271 | 7ZvC3KC1rMxIYvbhicKJ | Normal | 10 | 1.6.4.18.3.3.2.7 | 1.6.4.18.3.3.2.7 |  | 521 | p | 130 | -25% | 651
518 | 7007 | 9uputDeZmGdSlUY8oN4J | Summary | 64 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 501 | p | 126 | -25% | 627
519 | 7010 | l7MAqMN94R7DBQRgok6z | Normal | 5 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 501 | p | 126 | -25% | 627
520 | 7277 | hIopgQViPH34dy6jPgEs | Normal | 6 | 1.6.4.18.3.3.7.5 | 1.6.4.18.3.3.7.5 |  | 488 | q | -488 | (-100%) | 0
521 | 7278 | 4Ma7Z2LiPmWBC9UI6vyb | Normal | 5 | 1.6.4.18.3.3.7.7 | 1.6.4.18.3.3.7.7 |  | 501 | p | 130 | -26% | 631
522 | 7300 | JMkMoXIhBdn9ICcOd798 | Normal | 5 | 1.6.4.18.3.3.7.4 | 1.6.4.18.3.3.7.4 |  | 521 | p | 130 | -25% | 651
523 | 7301 | mVBynbXAicTgOFud0Dl3 | Normal | 5 | 1.6.4.18.3.3.7.6 | 1.6.4.18.3.3.7.6 |  | 501 | p | 130 | -26% | 631
524 | 7302 | 6S1rSJxqNAmNyzjZVL7L | Normal | 5 | 1.6.4.18.3.3.7.8 | 1.6.4.18.3.3.7.8 |  | 501 | p | 126 | -25% | 627
525 | 7279 | uD2jpviUMAewZ4YhDj8P | Summary | 32 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 503 | p | 136 | -27% | 639
526 | 7282 | sTVLhyKAe9uIrxTuOSsB | Normal | 2 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 503 | p | 136 | -27% | 639
527 | 7283 | GyFcZSlU29ifaVubQEBd | Normal | 2 | 1.6.4.18.3.3.4.4 | 1.6.4.18.3.3.4.4 |  | 503 | p | 136 | -27% | 639
528 | 7284 | AoDPK2hmzwZjnwdc6ENo | Normal | 1 | 1.6.4.18.3.3.4.5 | 1.6.4.18.3.3.4.5 |  | 503 | p | 136 | -27% | 639
529 | 7285 | UP4KQN3vFTNJJtYiVHhd | Normal | 10 | 1.6.4.18.3.3.4.6 | 1.6.4.18.3.3.4.6 |  | 503 | p | 136 | -27% | 639
530 | 7286 | weppsWRcwILLbxkFpraK | Summary | 39 | 1.6.4.18.3.3.5 | 1.6.4.18.3.3.5 |  | 504 | p | 130 | -26% | 634
531 | 7289 | YNbMTserJcwdDTx8O6lt | Normal | 5 | 1.6.4.18.3.3.5.3 | 1.6.4.18.3.3.5.3 |  | 504 | p | 130 | -26% | 634
532 | 7290 | rpRUKocvSOF2GnoJsxWr | Normal | 2 | 1.6.4.18.3.3.5.4 | 1.6.4.18.3.3.5.4 |  | 504 | p | 130 | -26% | 634
533 | 7291 | ThxkR8uStFOgKr5Kajlm | Normal | 1 | 1.6.4.18.3.3.5.5 | 1.6.4.18.3.3.5.5 |  | 504 | p | 130 | -26% | 634
534 | 7292 | 6vEOHVPLFOaXnW1xcDp6 | Normal | 10 | 1.6.4.18.3.3.5.6 | 1.6.4.18.3.3.5.6 |  | 504 | p | 130 | -26% | 634
535 | 7293 | ep0qwejNT11UOlW5WmY0 | Summary | 28 | 1.6.4.18.3.3.6 | 1.6.4.18.3.3.6 |  | 501 | p | 126 | -25% | 627
536 | 7295 | tyaakhlAtuOpVSt7bVvo | Normal | 1 | 1.6.4.18.3.3.6.2 | 1.6.4.18.3.3.6.2 |  | 507 | q | -507 | (-100%) | 0
537 | 7296 | PnFVdPiNKahDkradYWdd | Normal | 5 | 1.6.4.18.3.3.6.3 | 1.6.4.18.3.3.6.3 |  | 501 | p | 126 | -25% | 627
538 | 7297 | JA5LCeR4tD4Vqq2Jfy9o | Normal | 2 | 1.6.4.18.3.3.6.4 | 1.6.4.18.3.3.6.4 |  | 501 | p | 126 | -25% | 627
539 | 7298 | uHK4wyA8DzlXgqm5UKoq | Normal | 1 | 1.6.4.18.3.3.6.5 | 1.6.4.18.3.3.6.5 |  | 501 | p | 126 | -25% | 627
540 | 7299 | ymtRqRQZa4AjGraGOZVd | Normal | 10 | 1.6.4.18.3.3.6.6 | 1.6.4.18.3.3.6.6 |  | 501 | p | 126 | -25% | 627
541 | 6297 | AqdIsKbIPOfZJkjKYjnG | Summary | 118 | 1.6.1 | 1.6.1 |  | 539 | p | 402 | -75% | 941
542 | 4200 | YSdvLAa6ztbhOKei71CV | Summary | 108 | 1.6.1.1 | 1.6.1.1 |  | 532 | p | 153 | -29% | 685
543 | 4202 | N5DTU5adYVhKR5So2Uvc | Normal | 88 | 1.6.1.1.3 | 1.6.1.1.3 |  | 302 | q | -22 | (-7%) | 280
544 | 4204 | CRzwy8942pbCOpcOMW2v | Normal | 20 | 1.6.1.1.4 | 1.6.1.1.4 |  | 532 | p | 153 | -29% | 685
545 | 4209 | 0Ck6gz1ZilLs9fM0b7nU | Summary | 46 | 1.6.1.3 | 1.6.1.3 |  | 566 | p | 117 | -21% | 683
546 | 4212 | yktUOUuzQyzOVBFBfL42 | Normal | 46 | 1.6.1.3.1 | 1.6.1.3.1 |  | 566 | p | 117 | -21% | 683
547 | 4218 | T5g2El1CSAmFZNlboxQh | Normal | 1 | 1.6.1.4 | 1.6.1.4 |  | 532 | p | 153 | -29% | 685
548 | 6080 | jFrzSNmYyPDtKSvRlBw2 | Normal | 1 | 1.6.1.6 | 1.6.1.6 |  | 539 | p | 914 | -170% | 1453
549 | 6311 | tQdu1pFxVkY2bj5IQjxI | Summary | 77 | 1.6.3 | 1.6.3 |  | 547 | p | 18 | -3% | 565
550 | 5452 | u9nFTwEoKsBrgeg8njOT | Normal | 5 | 1.6.3.1 | 1.6.3.1 |  | 643 | q | -78 | (-12%) | 565
551 | 5457 | kGunJCROCjWQWqBfRKBZ | Summary | 1 | 1.6.3.2 | 1.6.3.2 |  | 643 | p | 111 | -17% | 754
552 | 5458 | DngVHB2HpHpsOjFWu5hu | Summary | 1 | 1.6.3.2.1 | 1.6.3.2.1 |  | 643 | p | 111 | -17% | 754
553 | 5505 | nVzBMSNTKKq9KPWblsw1 | Normal | 1 | 1.6.3.2.1.9 | 1.6.3.2.1.9 |  | 643 | p | 111 | -17% | 754
554 | 5506 | wLM81Xdu8B5geOMMQz6m | Summary | 119 | 1.6.3.3 | 1.6.3.3 |  | 547 | p | 18 | -3% | 565
555 | 5507 | 1r4d5DbY2YIgMhg8HKuO | Normal | 3 | 1.6.3.3.2 | 1.6.3.3.2 |  | 488 | p | 117 | -24% | 605
556 | 5508 | wHSntGHJkj4aA0wA3fA2 | Normal | 14 | 1.6.3.3.3 | 1.6.3.3.3 |  | 488 | p | 117 | -24% | 605
557 | 5509 | 1FHP32ReWIveKb3JOWEG | Summary | 44 | 1.6.3.3.4 | 1.6.3.3.4 |  | 511 | p | 105 | -21% | 616
558 | 5510 | LTFwTsrnxYhrGNFUv7CM | Normal | 12 | 1.6.3.3.4.1 | 1.6.3.3.4.1 |  | 512 | p | 104 | -20% | 616
559 | 5511 | Od3mMFxB7LjrJLF1slz4 | Normal | 11 | 1.6.3.3.4.2 | 1.6.3.3.4.2 |  | 511 | p | 105 | -21% | 616
560 | 5512 | Des2hDKSMjcJndTJRzoQ | Normal | 11 | 1.6.3.3.4.3 | 1.6.3.3.4.3 |  | 511 | p | 105 | -21% | 616
561 | 5513 | z1vb48lrGwUUDjKbD3gr | Normal | 10 | 1.6.3.3.4.4 | 1.6.3.3.4.4 |  | 511 | p | 105 | -21% | 616
562 | 5514 | leNXdZKmybH4tpy20cQU | Normal | 5 | 1.6.3.3.5 | 1.6.3.3.5 |  | 547 | p | 18 | -3% | 565
563 | 6890 | QKIolSsTnUWZiIhR6M5v | Normal | 40 | 1.6.3.3.1 | 1.6.3.3.1 |  | 488 | p | 117 | -24% | 605
564 | 6359 | hvfa0617w1FgmEnjjKwJ | Summary | 26 | 1.7.2.16 | 1.7.2.16 |  | 501 | p | 126 | -25% | 627
565 | 6360 | DMXbIVCeMtVR5pi4d5UN | Summary | 26 | 1.7.2.16.1 | 1.7.2.16.1 |  | 501 | p | 126 | -25% | 627
566 | 6361 | VEKeY9azNIVSZDSjYyKy | Summary | 33 | 1.7.2.16.1.3 | 1.7.2.16.1.3 |  | 501 | p | 126 | -25% | 627
567 | 7303 | fpLHmKjlfpy4s4tap5Xw | Summary | 39 | 1.6.3.11.1.3.4 | 1.6.3.11.1.3.4 |  | 503 | p | 136 | -27% | 639
568 | 7307 | eye8r8DevGvPITcdrMUe | Normal | 6 | 1.6.3.11.1.3.4.4 | 1.6.3.11.1.3.4.4 |  | 503 | p | 136 | -27% | 639
569 | 7308 | BXoPyB4GmzJwvFdrkJ7b | Normal | 1 | 1.6.3.11.1.3.4.5 | 1.6.3.11.1.3.4.5 |  | 503 | p | 136 | -27% | 639
570 | 7309 | 19skeJKmh3pRSfTF3DDB | Summary | 30 | 1.6.3.11.1.3.5 | 1.6.3.11.1.3.5 |  | 504 | p | 130 | -26% | 634
571 | 7312 | ZHpaj2955bjmxPKFBEf2 | Normal | 2 | 1.6.3.11.1.3.5.3 | 1.6.3.11.1.3.5.3 |  | 501 | q | -501 | (-100%) | 0
572 | 7313 | boaUnlKi0h6sKdwgAbmA | Normal | 5 | 1.6.3.11.1.3.5.4 | 1.6.3.11.1.3.5.4 |  | 501 | p | 126 | -25% | 627
573 | 7314 | zaliCdoIQDW2tx8wBQyt | Normal | 1 | 1.6.3.11.1.3.5.5 | 1.6.3.11.1.3.5.5 |  | 504 | p | 130 | -26% | 634
574 | 7315 | 9LywAxRsXdHsCrCcjGKV | Summary | 27 | 1.6.3.11.1.3.6 | 1.6.3.11.1.3.6 |  | 501 | p | 126 | -25% | 627
575 | 7318 | vWglY3BMmZCigDWMEMyY | Normal | 3 | 1.6.3.11.1.3.6.3 | 1.6.3.11.1.3.6.3 |  | 501 | p | 126 | -25% | 627
576 | 7319 | Fr6VbOwwg75s6X3Xcfql | Normal | 5 | 1.6.3.11.1.3.6.4 | 1.6.3.11.1.3.6.4 |  | 501 | p | 126 | -25% | 627
577 | 7320 | MRmQHJYBr9cc2OfLUSYd | Normal | 1 | 1.6.3.11.1.3.6.5 | 1.6.3.11.1.3.6.5 |  | 501 | p | 126 | -25% | 627
578 | 6273 | ljz6i2ltFwqcRU3btDx0 | Summary | 552 | 1.8 | 1.8 |  | 510 | q | -265 | (-52%) | 245
579 | 1639 | mkPE1mMWzawwUBF3KKzV | Summary | 277 | 1.8.2 | 1.8.2 |  | -26 | q | -410 | -1577% | -436
580 | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Milestone | 0 | 1.8.2.1 | 1.8.2.1 |  | -26 | q | -410 | -1577% | -436
581 | 6074 | fkBL64dyW7paLwgGr0ue | Normal | 212 | 1.8.2.3 | 1.8.2.3 |  | 180 | q | -18 | (-10%) | 162
582 | 6075 | pe2nScqRc5pgTwGaT5Zd | Normal | 193 | 1.8.2.2 | 1.8.2.2 |  | 199 | q | -33 | (-17%) | 166
583 | 6295 | uPS9GNqRLP4065SnBhEr | Summary | 387 | 1.8.5 | 1.8.5 |  | 84 | p | 15 | -18% | 99
584 | 3679 | 1KDcwGZKgevw1MizqBh0 | Summary | 387 | 1.8.5.1 | 1.8.5.1 |  | 84 | p | 15 | -18% | 99
585 | 3680 | E8qsx9NjEz7vaL5H7EFb | Summary | 189 | 1.8.5.1.1 | 1.8.5.1.1 |  | 104 | q | -5 | (-5%) | 99
586 | 3681 | wdhUrQuIMTMPn1LoqO1m | Normal | 24 | 1.8.5.1.1.1 | 1.8.5.1.1.1 |  | 104 | q | -5 | (-5%) | 99
587 | 3682 | 38PSIqFGHzjKldiudT82 | Summary | 25 | 1.8.5.1.1.4 | 1.8.5.1.1.4 |  | 104 | q | -5 | (-5%) | 99
588 | 3683 | JW3LUw009FZ7ddD6CdLX | Normal | 20 | 1.8.5.1.1.4.1 | 1.8.5.1.1.4.1 |  | 104 | q | -5 | (-5%) | 99
589 | 3684 | g3f8U3i4iakOhylueut6 | Normal | 5 | 1.8.5.1.1.4.2 | 1.8.5.1.1.4.2 |  | 104 | q | -5 | (-5%) | 99
590 | 3685 | eStRoX3vnaDmRLAWk58C | Summary | 40 | 1.8.5.1.1.5 | 1.8.5.1.1.5 |  | 104 | q | -5 | (-5%) | 99
591 | 3686 | 7zhxjkpiLTAH9tiW1eYy | Normal | 20 | 1.8.5.1.1.5.1 | 1.8.5.1.1.5.1 |  | 104 | q | -5 | (-5%) | 99
592 | 3687 | 0zzWvesUS18qEUfjK5NH | Normal | 5 | 1.8.5.1.1.5.2 | 1.8.5.1.1.5.2 |  | 204 | q | -2 | (-1%) | 202
593 | 3688 | zSUYYsBrfiOGi6qJakS6 | Normal | 5 | 1.8.5.1.1.5.3 | 1.8.5.1.1.5.3 |  | 204 | q | -2 | (-1%) | 202
594 | 3689 | X7sWUqInOJZ9zcVzmfT1 | Normal | 5 | 1.8.5.1.1.5.4 | 1.8.5.1.1.5.4 |  | 204 | q | -2 | (-1%) | 202
595 | 3690 | 8YDpqEvemQaMsfVmGpF8 | Normal | 5 | 1.8.5.1.1.5.5 | 1.8.5.1.1.5.5 |  | 204 | q | -2 | (-1%) | 202
596 | 3691 | ofZrlktbiXkVpuhhIeO5 | Summary | 25 | 1.8.5.1.1.6 | 1.8.5.1.1.6 |  | 104 | q | -5 | (-5%) | 99
597 | 3692 | xRsKOxB8zGAnVTXugcHQ | Normal | 20 | 1.8.5.1.1.6.1 | 1.8.5.1.1.6.1 |  | 104 | q | -5 | (-5%) | 99
598 | 3693 | Hn8rBaTvxeP9Vb10zF48 | Normal | 5 | 1.8.5.1.1.6.2 | 1.8.5.1.1.6.2 |  | 199 | q | -2 | (-1%) | 197
599 | 3694 | 4tipOydrC0LTNincaMDW | Summary | 35 | 1.8.5.1.1.7 | 1.8.5.1.1.7 |  | 104 | q | -5 | (-5%) | 99
600 | 3695 | lT6NpgfSYqKHtVYFLSzF | Normal | 20 | 1.8.5.1.1.7.1 | 1.8.5.1.1.7.1 |  | 104 | q | -5 | (-5%) | 99
601 | 3696 | gijouZuJR1ZVcSfHKSTf | Normal | 5 | 1.8.5.1.1.7.2 | 1.8.5.1.1.7.2 |  | 169 | q | -13 | (-8%) | 156
602 | 3697 | 1158ttL4JEmZYV6RmdcS | Normal | 5 | 1.8.5.1.1.7.3 | 1.8.5.1.1.7.3 |  | 169 | q | -13 | (-8%) | 156
603 | 3698 | AKCwPpEPQi4iH3XDRpiM | Normal | 5 | 1.8.5.1.1.7.4 | 1.8.5.1.1.7.4 |  | 169 | q | -13 | (-8%) | 156
604 | 3699 | AYANEA6OuC5b95kp3uyI | Summary | 30 | 1.8.5.1.1.8 | 1.8.5.1.1.8 |  | 104 | q | -5 | (-5%) | 99
605 | 3700 | WE9bFDn3y5M7oiID5UPj | Normal | 20 | 1.8.5.1.1.8.1 | 1.8.5.1.1.8.1 |  | 104 | q | -5 | (-5%) | 99
606 | 3701 | CXSHp4tESy2S0nMNpo3C | Normal | 5 | 1.8.5.1.1.8.2 | 1.8.5.1.1.8.2 |  | 184 | q | -22 | (-12%) | 162
607 | 3702 | sTuPByKbZEfSXxt0Z2G9 | Normal | 5 | 1.8.5.1.1.8.3 | 1.8.5.1.1.8.3 |  | 184 | q | -22 | (-12%) | 162
608 | 3703 | WHZRJAK4v6S9Zk2EBeP3 | Summary | 40 | 1.8.5.1.1.9 | 1.8.5.1.1.9 |  | 104 | q | -5 | (-5%) | 99
609 | 3704 | 3CXbrhXJooXd98jlpAkg | Normal | 20 | 1.8.5.1.1.9.1 | 1.8.5.1.1.9.1 |  | 104 | q | -5 | (-5%) | 99
610 | 3705 | RO9RShNcg0h7x9fD24Zk | Normal | 5 | 1.8.5.1.1.9.2 | 1.8.5.1.1.9.2 |  | 124 | q | -2 | (-2%) | 122
611 | 3706 | w8MhGnhxyXFIHvJdw6bc | Normal | 5 | 1.8.5.1.1.9.3 | 1.8.5.1.1.9.3 |  | 124 | q | -2 | (-2%) | 122
612 | 3707 | dJNKgtiJ1M8pNoPOlZcZ | Normal | 5 | 1.8.5.1.1.9.4 | 1.8.5.1.1.9.4 |  | 124 | q | -2 | (-2%) | 122
613 | 3708 | 84VtM14FQkMGurZDdBLv | Normal | 5 | 1.8.5.1.1.9.5 | 1.8.5.1.1.9.5 |  | 124 | q | -2 | (-2%) | 122
614 | 3709 | gpO5WcJkYid7jZAXZwbn | Summary | 40 | 1.8.5.1.1.10 | 1.8.5.1.1.10 |  | 104 | q | -5 | (-5%) | 99
615 | 3710 | KOKaQwRJEoC6vlU3mKjm | Normal | 20 | 1.8.5.1.1.10.1 | 1.8.5.1.1.10.1 |  | 104 | q | -5 | (-5%) | 99
616 | 3711 | XXu8BmtFqx4o2r8a6o98 | Normal | 5 | 1.8.5.1.1.10.2 | 1.8.5.1.1.10.2 |  | 104 | q | -5 | (-5%) | 99
617 | 3712 | sZwrgRbHYjKWcIa9rVK3 | Normal | 5 | 1.8.5.1.1.10.3 | 1.8.5.1.1.10.3 |  | 104 | q | -5 | (-5%) | 99
618 | 3713 | 4NbryuRKpmrExDEDqArG | Normal | 5 | 1.8.5.1.1.10.4 | 1.8.5.1.1.10.4 |  | 104 | q | -5 | (-5%) | 99
619 | 3714 | Fbm1iHrhCX8z8SNRXJuq | Normal | 5 | 1.8.5.1.1.10.5 | 1.8.5.1.1.10.5 |  | 104 | q | -5 | (-5%) | 99
620 | 6646 | CmmxWTpZgFyyAwkQnNh3 | Normal | 10 | 1.8.5.1.1.2 | 1.8.5.1.1.2 |  | 324 | q | -6 | (-2%) | 318
621 | 6647 | hWzCSsDre5WTTpryk1b0 | Normal | 5 | 1.8.5.1.1.3 | 1.8.5.1.1.3 |  | 324 | q | -6 | (-2%) | 318
622 | 3715 | V6i7uYjEJBRYHjhIimqJ | Summary | 50 | 1.8.5.1.2 | 1.8.5.1.2 |  | 104 | q | -5 | (-5%) | 99
623 | 3716 | bdy5zVX59rD935sK6M5v | Normal | 20 | 1.8.5.1.2.1 | 1.8.5.1.2.1 |  | 104 | q | -5 | (-5%) | 99
624 | 3717 | 5PdqCAMtbYgi5VsFO6ls | Normal | 20 | 1.8.5.1.2.4 | 1.8.5.1.2.4 |  | 104 | q | -5 | (-5%) | 99
625 | 6671 | 0oTh3tmNX3iVSaVNVmGK | Normal | 5 | 1.8.5.1.2.2 | 1.8.5.1.2.2 |  | 104 | q | -5 | (-5%) | 99
626 | 6672 | BKyGOzVPyPwKpI9CyseJ | Normal | 5 | 1.8.5.1.2.3 | 1.8.5.1.2.3 |  | 104 | q | -5 | (-5%) | 99
627 | 3718 | vTyTgxcbRSz6H6lqDAEf | Summary | 20 | 1.8.5.1.3 | 1.8.5.1.3 |  | 104 | q | -5 | (-5%) | 99
628 | 3719 | B9ymEBZ7zimHMMqNS20Q | Normal | 20 | 1.8.5.1.3.1 | 1.8.5.1.3.1 |  | 104 | q | -5 | (-5%) | 99
629 | 3720 | rPRo0RE1uNkj9oG127hu | Summary | 109 | 1.8.5.1.4 | 1.8.5.1.4 |  | 107 | p | 415 | -388% | 522
630 | 3721 | 45j7fpB55qVEeWfRBgCv | Normal | 1 | 1.8.5.1.4.1 | 1.8.5.1.4.1 |  | 107 | p | 415 | -388% | 522
631 | 3722 | hYa6Ppkzu6veYWmxHffd | Normal | 27 | 1.8.5.1.4.2 | 1.8.5.1.4.2 |  | 257 | p | 418 | -163% | 675
632 | 6649 | TeFWDZJ3h8q4yVNptUYE | Normal | 28 | 1.8.5.1.4.3 | 1.8.5.1.4.3 |  | 257 | p | 418 | -163% | 675
633 | 6650 | FvuNLI4Jaew3VjPpwL3e | Normal | 28 | 1.8.5.1.4.4 | 1.8.5.1.4.4 |  | 257 | p | 418 | -163% | 675
634 | 6651 | T3J0AzovT4qFTLJ7Lgki | Normal | 15 | 1.8.5.1.4.5 | 1.8.5.1.4.5 |  | 257 | p | 418 | -163% | 675
635 | 6652 | 0afM7N7hGdWHQjlFenVR | Normal | 10 | 1.8.5.1.4.6 | 1.8.5.1.4.6 |  | 257 | p | 418 | -163% | 675
636 | 3723 | 4qmbzAmtSx0gvDVaBsYe | Summary | 239 | 1.8.5.1.5 | 1.8.5.1.5 |  | 171 | q | -11 | (-6%) | 160
637 | 3724 | ZCOxRRLLrh9Pa7VnBAyk | Normal | 27 | 1.8.5.1.5.1 | 1.8.5.1.5.1 |  | 104 | q | -5 | (-5%) | 99
638 | 3725 | 8cgOIQk4rBKvjXdBm8mF | Normal | 91 | 1.8.5.1.5.9 | 1.8.5.1.5.9 |  | 298 | p | 4 | -1% | 302
639 | 6661 | bQxmmL7mcUsEGpKkQTDo | Normal | 28 | 1.8.5.1.5.2 | 1.8.5.1.5.2 |  | 171 | q | -11 | (-6%) | 160
640 | 6662 | CVNpv9CNU8XhfLmVwl8x | Normal | 28 | 1.8.5.1.5.3 | 1.8.5.1.5.3 |  | 171 | q | -11 | (-6%) | 160
641 | 6663 | LVExlIxeJ6XB3yqm0Dzs | Normal | 28 | 1.8.5.1.5.4 | 1.8.5.1.5.4 |  | 171 | q | -11 | (-6%) | 160
642 | 6664 | Io9oZ1dPqEE9GDlMTPxh | Normal | 28 | 1.8.5.1.5.5 | 1.8.5.1.5.5 |  | 171 | q | -11 | (-6%) | 160
643 | 6665 | ycT0qtEFjd4p02S4Ehf1 | Normal | 28 | 1.8.5.1.5.6 | 1.8.5.1.5.6 |  | 171 | q | -11 | (-6%) | 160
644 | 6666 | sX3PHseynvzwKI9my2AH | Normal | 15 | 1.8.5.1.5.7 | 1.8.5.1.5.7 |  | 171 | q | -11 | (-6%) | 160
645 | 6667 | 0dYk2X7XWh2rSSHkHo2L | Normal | 10 | 1.8.5.1.5.8 | 1.8.5.1.5.8 |  | 171 | q | -11 | (-6%) | 160
646 | 6668 | NGuTznXCCG5yuIi6lGQO | Normal | 1 | 1.8.5.1.5.10 | 1.8.5.1.5.10 |  | 298 | p | 4 | -1% | 302
647 | 6669 | t8MCocRefa6DhiQNsJVn | Normal | 1 | 1.8.5.1.5.11 | 1.8.5.1.5.11 |  | 298 | p | 4 | -1% | 302
648 | 6670 | vWxPVjk5e7KHTev8998h | Normal | 1 | 1.8.5.1.5.12 | 1.8.5.1.5.12 |  | 298 | p | 4 | -1% | 302
649 | 3726 | 5hjTNIk7WmpZNtmCLhPN | Summary | 96 | 1.8.5.1.6 | 1.8.5.1.6 |  | 234 | p | 118 | -50% | 352
650 | 3727 | rGcF2XgkgPtqRDM3KJ2D | Normal | 28 | 1.8.5.1.6.1 | 1.8.5.1.6.1 |  | 234 | p | 118 | -50% | 352
651 | 3728 | Hgqc9wbzS3SDikBm20zt | Normal | 28 | 1.8.5.1.6.3 | 1.8.5.1.6.3 |  | 234 | p | 118 | -50% | 352
652 | 6653 | K0AYRckqpyO0HzRrxXG6 | Normal | 15 | 1.8.5.1.6.2 | 1.8.5.1.6.2 |  | 234 | p | 118 | -50% | 352
653 | 6654 | MMK0qYycfTMCrFAZcf8J | Normal | 15 | 1.8.5.1.6.4 | 1.8.5.1.6.4 |  | 234 | p | 118 | -50% | 352
654 | 6655 | gl8c5oVG5KfrLbsQSFL4 | Normal | 10 | 1.8.5.1.6.5 | 1.8.5.1.6.5 |  | 234 | p | 118 | -50% | 352
655 | 3729 | Y6b5KP0DE9c4tlFzqxp3 | Summary | 81 | 1.8.5.1.7 | 1.8.5.1.7 |  | 291 | p | 405 | -139% | 696
656 | 3730 | TswICWhG0Mjj1DenbPW5 | Normal | 28 | 1.8.5.1.7.1 | 1.8.5.1.7.1 |  | 291 | p | 405 | -139% | 696
657 | 6626 | 9d2gtkuh8SmNZwArNzpn | Normal | 10 | 1.8.5.1.7.4 | 1.8.5.1.7.4 |  | 291 | p | 405 | -139% | 696
658 | 6627 | QBgG0JxqOymB6vyjKsRZ | Normal | 28 | 1.8.5.1.7.2 | 1.8.5.1.7.2 |  | 291 | p | 405 | -139% | 696
659 | 6628 | PAI9VZBMaYriaY1wvhOi | Normal | 15 | 1.8.5.1.7.3 | 1.8.5.1.7.3 |  | 291 | p | 405 | -139% | 696
660 | 3733 | ufu7SWDoeBfTzZW24BQU | Summary | 189 | 1.8.5.1.9 | 1.8.5.1.9 |  | 84 | p | 78 | -93% | 162
661 | 3734 | cAszcoDUs4YPdXAiXa4B | Milestone | 0 | 1.8.5.1.9.1 | 1.8.5.1.9.1 |  | 84 | p | 428 | -510% | 512
662 | 3735 | rgqtw8hyurrfag2amXLA | Normal | 109 | 1.8.5.1.9.2 | 1.8.5.1.9.2 |  | 84 | p | 428 | -510% | 512
663 | 3736 | eIMYQUSTObIc5Lp6kKBE | Normal | 40 | 1.8.5.1.9.3 | 1.8.5.1.9.3 |  | 84 | p | 428 | -510% | 512
664 | 3737 | z19Wnme0hJcfEI4IfIQR | Normal | 25 | 1.8.5.1.9.4 | 1.8.5.1.9.4 |  | 179 | q | -17 | (-9%) | 162
665 | 6657 | uq5fluI8KT8LkPx57ktn | Normal | 10 | 1.8.5.1.9.5 | 1.8.5.1.9.5 |  | 179 | q | -17 | (-9%) | 162
666 | 6658 | ktg0XNnAmjjc1caqICt2 | Normal | 5 | 1.8.5.1.9.6 | 1.8.5.1.9.6 |  | 179 | q | -17 | (-9%) | 162
667 | 3738 | bohrZqwOTsvUL4DEUnjh | Summary | 139 | 1.8.5.1.10 | 1.8.5.1.10 |  | 109 | p | 413 | -379% | 522
668 | 3739 | Ba23bBwg4xGpRd3Ht4kS | Normal | 24 | 1.8.5.1.10.1 | 1.8.5.1.10.1 |  | 109 | p | 413 | -379% | 522
669 | 3740 | lRtbtcrLyr1QGd0laoJi | Normal | 25 | 1.8.5.1.10.2 | 1.8.5.1.10.2 |  | 229 | p | 406 | -177% | 635
670 | 3741 | V05WnFKB5t2LuixhoKHO | Normal | 25 | 1.8.5.1.10.3 | 1.8.5.1.10.3 |  | 229 | p | 406 | -177% | 635
671 | 3742 | LRjVz0hoZuIRlQgcLYzs | Normal | 25 | 1.8.5.1.10.6 | 1.8.5.1.10.6 |  | 229 | p | 406 | -177% | 635
672 | 6648 | Z5T3n0GGVz8PB0IY5TXC | Normal | 10 | 1.8.5.1.10.5 | 1.8.5.1.10.5 |  | 229 | p | 406 | -177% | 635
673 | 6656 | tqprQgHoroqT051BXug3 | Normal | 15 | 1.8.5.1.10.4 | 1.8.5.1.10.4 |  | 229 | p | 406 | -177% | 635
674 | 6659 | NN3Qiea1foOxv05JqXnT | Normal | 10 | 1.8.5.1.10.7 | 1.8.5.1.10.7 |  | 229 | p | 406 | -177% | 635
675 | 6660 | pWIs4hM6SgH2pFjSQ3qo | Normal | 5 | 1.8.5.1.10.8 | 1.8.5.1.10.8 |  | 229 | p | 406 | -177% | 635
676 | 6642 | A7Bd82G8YCk8VjEZkcvi | Summary | 135 | 1.8.5.1.8 | 1.8.5.1.8 |  | 84 | p | 81 | -96% | 165
677 | 3731 | 02LiOyWN4DF8GOeNSP5s | Normal | 20 | 1.8.5.1.8.1 | 1.8.5.1.8.1 |  | 84 | p | 428 | -510% | 512
678 | 3732 | x85AkT9s5HT2a4U2goND | Normal | 20 | 1.8.5.1.8.8 | 1.8.5.1.8.8 |  | 159 | p | 421 | -265% | 580
679 | 6629 | n59ds33sZr9JNOobmYWE | Normal | 30 | 1.8.5.1.8.2 | 1.8.5.1.8.2 |  | 84 | p | 428 | -510% | 512
680 | 6630 | y36QmeQSyS7BZflkeM7e | Normal | 10 | 1.8.5.1.8.3 | 1.8.5.1.8.3 |  | 84 | p | 428 | -510% | 512
681 | 6631 | Ghk1eKq5exIyUH3hdAeR | Normal | 20 | 1.8.5.1.8.4 | 1.8.5.1.8.4 |  | 84 | p | 428 | -510% | 512
682 | 6632 | 5y36mClzGR7vkSsODb4C | Normal | 15 | 1.8.5.1.8.5 | 1.8.5.1.8.5 |  | 84 | p | 428 | -510% | 512
683 | 6633 | uS272glxjETpDiVeJyGv | Normal | 20 | 1.8.5.1.8.6 | 1.8.5.1.8.6 |  | 84 | p | 428 | -510% | 512
684 | 6634 | 65ghvPiwU0AxSKrC11rG | Normal | 20 | 1.8.5.1.8.7 | 1.8.5.1.8.7 |  | 84 | p | 428 | -510% | 512
685 | 6643 | sKnPCsxlq51dE8cz52fo | Normal | 10 | 1.8.5.1.8.9 | 1.8.5.1.8.9 |  | 159 | p | 421 | -265% | 580
686 | 6644 | 0NVu6ABxwy3imKaZ2MTJ | Normal | 10 | 1.8.5.1.8.10 | 1.8.5.1.8.10 |  | 159 | p | 6 | -4% | 165
687 | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Summary | 1 | 1.8.1 | 1.8.1 |  | 510 | q | -265 | (-52%) | 245
688 | 6082 | YsSSuERf5VIDKO5m8eZo | Normal | 1 | 1.8.1.1 | 1.8.1.1 |  | 510 | q | -265 | (-52%) | 245
689 | 6313 | 8HYxn50EKf1DU0fX0MF7 | Summary | 391 | 1.8.4 | 1.8.4 |  | 325 | q | -80 | (-25%) | 245
690 | 5516 | dd6fm1lW4tBXPtNV5RGW | Summary | 391 | 1.8.4.1 | 1.8.4.1 |  | 325 | q | -80 | (-25%) | 245
691 | 5517 | IHfroMkwx3TZoTXYbBOK | Normal | 40 | 1.8.4.1.1 | 1.8.4.1.1 |  | 325 | p | 422 | -130% | 747
692 | 5518 | V0a5XEJ0jxIkhnpEDg8e | Normal | 40 | 1.8.4.1.2 | 1.8.4.1.2 |  | 325 | p | 401 | -123% | 726
693 | 5519 | D5sl3M5NpO77EU7TPYT0 | Normal | 40 | 1.8.4.1.3 | 1.8.4.1.3 |  | 325 | p | 412 | -127% | 737
694 | 5523 | APkwTVep7mUhgmcCl4NB | Milestone | 0 | 1.8.4.1.4 | 1.8.4.1.4 |  | 510 | q | -265 | (-52%) | 245
695 | 5527 | Mw5Re8SivA42laH7UhJE | Milestone | 0 | 1.8.4.1.5 | 1.8.4.1.5 |  | 510 | q | -265 | (-52%) | 245
696 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 514 | q | -514 | (-100%) | 0
697 | 5331 | emM9tIPUc6I6BRQdDkUj | Summary | 325 | 1.9.3 | 1.9.3 |  | 620 | p | 171 | -28% | 791
698 | 5332 | Jas5wmBgln6JvMRLtRUk | Summary | 110 | 1.9.3.1 | 1.9.3.1 |  | 620 | p | 171 | -28% | 791
699 | 5333 | NEZJUiuEFBeqDBEbXbzQ | Milestone | 0 | 1.9.3.1.1 | 1.9.3.1.1 |  | 620 | p | 171 | -28% | 791
700 | 5334 | 5Bt8vyiG2PJ2FKCjQPP1 | Summary | 74 | 1.9.3.1.2 | 1.9.3.1.2 |  | 620 | p | 171 | -28% | 791
701 | 6471 | xmZvSzAhf2D9ir29atKO | Normal | 8 | 1.9.3.1.2.1 | 1.9.3.1.2.1 |  | 620 | p | 171 | -28% | 791
702 | 6472 | j0VQ7fJsNHb1HpOVRoJN | Normal | 7 | 1.9.3.1.2.2 | 1.9.3.1.2.2 |  | 620 | p | 171 | -28% | 791
703 | 6473 | FN1N5cBOnOQJN0lvtY6J | Normal | 5 | 1.9.3.1.2.3 | 1.9.3.1.2.3 |  | 620 | p | 171 | -28% | 791
704 | 6474 | k77H7bJ7aRKhBrZeZFzu | Normal | 10 | 1.9.3.1.2.4 | 1.9.3.1.2.4 |  | 620 | p | 171 | -28% | 791
705 | 6475 | TkBVMCiZTEhYxjcnMNRI | Normal | 8 | 1.9.3.1.2.5 | 1.9.3.1.2.5 |  | 620 | p | 171 | -28% | 791
706 | 6476 | HdsfOo0UbW7iVGjY7L1O | Normal | 10 | 1.9.3.1.2.6 | 1.9.3.1.2.6 |  | 620 | p | 171 | -28% | 791
707 | 6477 | m1G8PrmdvRxZwBbLlVUQ | Normal | 7 | 1.9.3.1.2.7 | 1.9.3.1.2.7 |  | 620 | p | 171 | -28% | 791
708 | 6478 | ZDDqpCGw2ELQiAxZVJFo | Normal | 7 | 1.9.3.1.2.8 | 1.9.3.1.2.8 |  | 620 | p | 171 | -28% | 791
709 | 6479 | i51TyrBkECB0t7wKJruE | Normal | 7 | 1.9.3.1.2.9 | 1.9.3.1.2.9 |  | 620 | p | 171 | -28% | 791
710 | 6480 | XeKgBzwPereNdZmXnTFt | Normal | 5 | 1.9.3.1.2.10 | 1.9.3.1.2.10 |  | 620 | p | 171 | -28% | 791
711 | 5335 | fBEkx0xCtVpw1OeE4jLB | Summary | 25 | 1.9.3.1.3 | 1.9.3.1.3 |  | 620 | p | 171 | -28% | 791
712 | 5336 | FIhKbBOHnlTp0loBBfvV | Normal | 3 | 1.9.3.1.3.1 | 1.9.3.1.3.1 |  | 622 | p | 171 | -27% | 793
713 | 5337 | TPAbtCx4KhMQiN0iVD1F | Normal | 0 | 1.9.3.1.3.2 | 1.9.3.1.3.2 |  | 624 | p | 172 | -28% | 796
714 | 5338 | NXWa8B3rzsUFws6lYttF | Normal | 5 | 1.9.3.1.3.3 | 1.9.3.1.3.3 |  | 620 | p | 171 | -28% | 791
715 | 5339 | o98eRuEZGwoxxa1Byl7H | Normal | 5 | 1.9.3.1.3.4 | 1.9.3.1.3.4 |  | 620 | p | 171 | -28% | 791
716 | 5340 | lQJTDBnvPE8mTPnPre3v | Normal | 10 | 1.9.3.1.3.5 | 1.9.3.1.3.5 |  | 620 | p | 171 | -28% | 791
717 | 5341 | nevxwfefPkBzu42CDbNd | Normal | 10 | 1.9.3.1.3.6 | 1.9.3.1.3.6 |  | 620 | p | 171 | -28% | 791
718 | 5342 | s0JiBiXDLP6oybWmkZ43 | Normal | 6 | 1.9.3.1.4 | 1.9.3.1.4 |  | 620 | p | 171 | -28% | 791
719 | 5343 | NROXqcLUoQ0RLz64rMVc | Normal | 5 | 1.9.3.1.5 | 1.9.3.1.5 |  | 620 | p | 171 | -28% | 791
720 | 5344 | Kw3Fj6kwk5uOl7tQyqrL | Milestone | 0 | 1.9.3.1.6 | 1.9.3.1.6 |  | 620 | p | 171 | -28% | 791
721 | 6275 | OL3lkJGtK3tkk0d4SBRn | Summary | 288 | 1.9.9 | 1.9.9 |  | 514 | q | -514 | (-100%) | 0
722 | 795 | 85yV4lhIxXIziyB5R2QA | Normal | 1 | 1.9.9.1 | 1.9.9.1 |  | 524 | q | -513 | (-98%) | 11
723 | 844 | 1qfp8o9PQxr9vZvO7S5k | Normal | 1 | 1.9.9.4 | 1.9.9.4 |  | 514 | q | -514 | (-100%) | 0
724 | 845 | U1v5hScHSOPPxa5ohjfI | Summary | 189 | 1.9.9.7 | 1.9.9.7 |  | 586 | p | 130 | -22% | 716
725 | 847 | JilJNxxBcx7QrT5PcKLM | Summary | 189 | 1.9.9.7.2 | 1.9.9.7.2 |  | 586 | p | 130 | -22% | 716
726 | 866 | 0rLFG0X22Uukcn0axQTO | Normal | 50 | 1.9.9.7.2.6 | 1.9.9.7.2.6 |  | 586 | p | 130 | -22% | 716
727 | 869 | 8QCM3LZ8SN5y0jCLtGNh | Summary | 129 | 1.9.9.7.2.7 | 1.9.9.7.2.7 |  | 586 | p | 130 | -22% | 716
728 | 6419 | NORPsF566zq8VZyN1UzF | Normal | 10 | 1.9.9.7.2.7.1 | 1.9.9.7.2.7.1 |  | 586 | p | 130 | -22% | 716
729 | 6420 | 043wOhyyEd8vJkuUBkFf | Normal | 40 | 1.9.9.7.2.7.2 | 1.9.9.7.2.7.2 |  | 586 | p | 130 | -22% | 716
730 | 6421 | JZROXyECnTBG3SBjYZJ8 | Normal | 79 | 1.9.9.7.2.7.3 | 1.9.9.7.2.7.3 |  | 586 | p | 130 | -22% | 716
731 | 6418 | W9pbV5i9WFkdVEGtW75H | Normal | 45 | 1.9.9.7.2.5 | 1.9.9.7.2.5 |  | 586 | p | 130 | -22% | 716
732 | 870 | m3oEXpasu7ssfpw9dqLv | Summary | 267 | 1.9.9.14 | 1.9.9.14 |  | 514 | q | -514 | (-100%) | 0
733 | 4667 | gXRr1908PexMoLIDosFv | Normal | 100 | 1.9.9.14.3 | 1.9.9.14.3 |  | 598 | p | 113 | -19% | 711
734 | 4668 | G3SLCzd88WLMRnAF5Et7 | Normal | 0 | 1.9.9.14.4 | 1.9.9.14.4 |  | 536 | q | -516 | (-96%) | 20
735 | 4669 | aeClBbTsJ3qrKHWqQ1Rw | Normal | 40 | 1.9.9.14.5 | 1.9.9.14.5 |  | 598 | p | 113 | -19% | 711
736 | 4679 | rpzkOhA603pApmNdMeVE | Normal | 0 | 1.9.9.14.6 | 1.9.9.14.6 |  | 514 | q | -514 | (-100%) | 0
737 | 5786 | d3N6cqydEgoPO1XBMSTu | Normal | 7 | 1.9.9.14.1 | 1.9.9.14.1 |  | 598 | p | 113 | -19% | 711
738 | 5787 | r6JEZEKCpBbNZRe1W7Ef | Normal | 91 | 1.9.9.14.2 | 1.9.9.14.2 |  | 598 | p | 113 | -19% | 711
739 | 899 | w1GWQdUx9oG06oopRYZx | Summary | 24 | 1.9.9.15 | 1.9.9.15 |  | 514 | q | -514 | (-100%) | 0
740 | 900 | ANUK0HdVlI2Jd5hSzs0f | Milestone | 0 | 1.9.9.15.1 | 1.9.9.15.1 |  | 514 | q | -514 | (-100%) | 0
741 | 901 | HcFqHITfVdYMyzVb3S8v | Normal | 18 | 1.9.9.15.2 | 1.9.9.15.2 |  | 519 | q | -514 | (-99%) | 5
742 | 902 | nIjAIVHCOoi1ijXym0cI | Normal | 3 | 1.9.9.15.3 | 1.9.9.15.3 |  | 514 | q | -514 | (-100%) | 0
743 | 903 | UDGopgZ2sb1QsQEooZ9G | Normal | 8 | 1.9.9.15.4 | 1.9.9.15.4 |  | 514 | q | -514 | (-100%) | 0
744 | 904 | 4CH3NSJx1luiHbrrAEJg | Normal | 2 | 1.9.9.15.5 | 1.9.9.15.5 |  | 519 | q | -514 | (-99%) | 5
745 | 905 | MxRWNVEH6ZVBPqNnA2hI | Normal | 8 | 1.9.9.15.6 | 1.9.9.15.6 |  | 514 | q | -514 | (-100%) | 0
746 | 906 | PL0zn2U2NPPXQqakkHLb | Normal | 5 | 1.9.9.15.7 | 1.9.9.15.7 |  | 514 | q | -514 | (-100%) | 0
747 | 907 | 5mTVpVcHzmsYLVY8xpKs | Normal | 5 | 1.9.9.15.8 | 1.9.9.15.8 |  | 514 | q | -514 | (-100%) | 0
748 | 914 | q0UeyWaeMXFoeUDjjzhX | Summary | 18 | 1.9.9.5 | 1.9.9.5 |  | 782 | q | -510 | (-65%) | 272
749 | 915 | jxzEE3EBeGWt1nE3uHcj | Summary | 18 | 1.9.9.5.1 | 1.9.9.5.1 |  | 782 | q | -510 | (-65%) | 272
750 | 916 | d4bxhxtQW3GaLrDrUlf9 | Normal | 17 | 1.9.9.5.1.1 | 1.9.9.5.1.1 |  | 782 | q | -510 | (-65%) | 272
751 | 917 | mbDdHZHm9OoYye329Ue6 | Normal | 1 | 1.9.9.5.1.2 | 1.9.9.5.1.2 |  | 782 | q | -510 | (-65%) | 272
752 | 4538 | aTyUglf0WPX6H8Zd17Iq | Summary | 71 | 1.9.9.16 | 1.9.9.16 |  | 514 | q | -514 | (-100%) | 0
753 | 6509 | sp3XFaPtGgzrVeC1wvvV | Normal | 10 | 1.9.9.16.3 | 1.9.9.16.3 |  | 514 | q | -509 | (-99%) | 5
754 | 6510 | dar9hgzhSUYJxC1MeoTS | Normal | 10 | 1.9.9.16.4 | 1.9.9.16.4 |  | 514 | q | -514 | (-100%) | 0
755 | 6513 | IG8fHoH3vjERJ6iSB3Rj | Normal | 36 | 1.9.9.16.5 | 1.9.9.16.5 |  | 514 | q | -514 | (-100%) | 0
756 | 6514 | imV319lPgBwI8oLVT5sB | Normal | 1 | 1.9.9.16.2 | 1.9.9.16.2 |  | 514 | q | -514 | (-100%) | 0
757 | 6515 | a8Kdm3F6uLeIN4SEhwX9 | Normal | 1 | 1.9.9.16.1 | 1.9.9.16.1 |  | 536 | q | -516 | (-96%) | 20
758 | 5783 | BOvEGIzyTacp1vvD9v7M | Normal | 1 | 1.9.9.2 | 1.9.9.2 |  | 586 | p | 130 | -22% | 716
759 | 6128 | 7jXaekqqhUCDWSDfnxzo | Summary | 28 | 1.7.4.2 | 1.7.4.2 |  | 113 | p | 6 | -5% | 119
760 | 6130 | 3AAePL8Vt5bI7qDxsaDX | Normal | 20 | 1.7.4.2.3 | 1.7.4.2.3 |  | 113 | p | 6 | -5% | 119
761 | 6685 | 2nkdQcaVv7LgM8d4dFld | Summary | 1 | 1.9.9.12 | 1.9.9.12 |  | 743 | p | 266 | -36% | 1009
762 | 6687 | RiyOBd4mBIE5Cq6C0A4h | Normal | 1 | 1.9.9.12.1 | 1.9.9.12.1 |  | 743 | p | 266 | -36% | 1009
763 | 6686 | IDiuvzfQRXyu7MCMX1jW | Normal | 5 | 1.9.9.11 | 1.9.9.11 |  | 878 | p | 131 | -15% | 1009
764 | 7388 | subTjNOw9tjXphx2xXzW | Summary | 324 | 1.9.9.13 | 1.9.9.13 |  | 514 | q | -514 | (-100%) | 0
765 | 7389 | xTfJP5JFEqXIDmLDdKVZ | Summary | 43 | 1.9.9.13.1 | 1.9.9.13.1 |  | 514 | q | -514 | (-100%) | 0
766 | 7390 | GV26YG775A5KHHrrMIRV | Summary | 32 | 1.9.9.13.1.1 | 1.9.9.13.1.1 |  | 514 | q | -512 | (-100%) | 2
767 | 7391 | UumEMUqxjwvZXtHBx1rg | Normal | 3 | 1.9.9.13.1.1.1 | 1.9.9.13.1.1.1 |  | 514 | q | -506 | (-98%) | 8
768 | 7392 | ylVP19AJuwY485wgDJEG | Normal | 10 | 1.9.9.13.1.1.2 | 1.9.9.13.1.1.2 |  | 516 | q | -505 | (-98%) | 11
769 | 7393 | RzIyrLZKRoqlWdOJYpGf | Normal | 3 | 1.9.9.13.1.1.3 | 1.9.9.13.1.1.3 |  | 514 | q | -506 | (-98%) | 8
770 | 7394 | zHoRZ9fggWfe9FGnA954 | Normal | 10 | 1.9.9.13.1.1.4 | 1.9.9.13.1.1.4 |  | 516 | q | -512 | (-99%) | 4
771 | 7395 | PMjQe1vYJ6mxUbNABucF | Normal | 3 | 1.9.9.13.1.1.5 | 1.9.9.13.1.1.5 |  | 514 | q | -506 | (-98%) | 8
772 | 7396 | gQKdIVV4LZyvHUAfFFFg | Normal | 10 | 1.9.9.13.1.1.6 | 1.9.9.13.1.1.6 |  | 515 | q | -513 | (-100%) | 2
773 | 7397 | gmOEJCOmO6SQ6HMlGXfq | Summary | 12 | 1.9.9.13.1.2 | 1.9.9.13.1.2 |  | 514 | q | -514 | (-100%) | 0
774 | 7398 | ItOQSxoXEYWD5clVNK0n | Normal | 3 | 1.9.9.13.1.2.1 | 1.9.9.13.1.2.1 |  | 514 | q | -506 | (-98%) | 8
775 | 7399 | cXpFrNuZR7O8wPV6KZK3 | Normal | 9 | 1.9.9.13.1.2.2 | 1.9.9.13.1.2.2 |  | 514 | q | -514 | (-100%) | 0
776 | 7400 | VGtguPWpaIPmF0Ojsz8a | Summary | 176 | 1.9.9.13.2 | 1.9.9.13.2 |  | 522 | q | -513 | (-98%) | 9
777 | 7401 | H3MyBOTVJ4MGxcXcavMD | Normal | 2 | 1.9.9.13.2.1 | 1.9.9.13.2.1 |  | 522 | q | -513 | (-98%) | 9
778 | 7402 | pMiEhGou1QDK96DPu7Q8 | Normal | 1 | 1.9.9.13.2.2 | 1.9.9.13.2.2 |  | 514 | q | -514 | (-100%) | 0
779 | 7403 | pHZBXvaYVwug2p7gN6jp | Summary | 17 | 1.9.9.13.2.3 | 1.9.9.13.2.3 |  | 514 | q | -514 | (-100%) | 0
780 | 7404 | EvHLT3cR3tYYGwcq6SC1 | Normal | 5 | 1.9.9.13.2.3.1 | 1.9.9.13.2.3.1 |  | 514 | q | -514 | (-100%) | 0
781 | 7405 | 5GpI6xkgfIoVOnU9egD8 | Normal | 12 | 1.9.9.13.2.3.2 | 1.9.9.13.2.3.2 |  | 514 | q | -514 | (-100%) | 0
782 | 7406 | WxzG2sAIbVYYiem4v3mk | Normal | 12 | 1.9.9.13.2.3.3 | 1.9.9.13.2.3.3 |  | 514 | q | -513 | (-100%) | 1
783 | 7407 | 0eiyRK1I5mgUCdtpXpqY | Summary | 44 | 1.9.9.13.2.4 | 1.9.9.13.2.4 |  | 514 | q | -514 | (-100%) | 0
784 | 7408 | uKngouP2QMMQmu6HFm0I | Normal | 11 | 1.9.9.13.2.4.1 | 1.9.9.13.2.4.1 |  | 514 | q | -514 | (-100%) | 0
785 | 7409 | C7eZzAQkBbKewE4wmmOD | Normal | 11 | 1.9.9.13.2.4.2 | 1.9.9.13.2.4.2 |  | 514 | q | -514 | (-100%) | 0
786 | 7410 | VCdEPtbQjRcgNUnNprkZ | Normal | 11 | 1.9.9.13.2.4.3 | 1.9.9.13.2.4.3 |  | 514 | q | -514 | (-100%) | 0
787 | 7411 | OzHccTXr25Mf4pmiIMuT | Normal | 11 | 1.9.9.13.2.4.4 | 1.9.9.13.2.4.4 |  | 514 | q | -514 | (-100%) | 0
788 | 7412 | obz02flxb00pYjKUpMNx | Normal | 12 | 1.9.9.13.2.5 | 1.9.9.13.2.5 |  | 532 | q | -505 | (-95%) | 27
789 | 7413 | xazO1XwNp5eROWJmaREL | Summary | 36 | 1.9.9.13.2.6 | 1.9.9.13.2.6 |  | 514 | q | -514 | (-100%) | 0
790 | 7414 | DrM34eAIT9imz4vRHbHm | Normal | 2 | 1.9.9.13.2.6.1 | 1.9.9.13.2.6.1 |  | 514 | q | -514 | (-100%) | 0
791 | 7415 | RsULMViXRZoYahxlMUQ4 | Normal | 20 | 1.9.9.13.2.6.2 | 1.9.9.13.2.6.2 |  | 514 | q | -514 | (-100%) | 0
792 | 7416 | U8irVJqpjJwQWU5FcpMo | Normal | 3 | 1.9.9.13.2.6.3 | 1.9.9.13.2.6.3 |  | 514 | q | -514 | (-100%) | 0
793 | 7417 | yrCdbpyUp4mqkbXiv5Nc | Normal | 6 | 1.9.9.13.2.6.4 | 1.9.9.13.2.6.4 |  | 514 | q | -514 | (-100%) | 0
794 | 7418 | Iw5sTi596kP8d52cBWYm | Normal | 5 | 1.9.9.13.2.6.5 | 1.9.9.13.2.6.5 |  | 514 | q | -514 | (-100%) | 0
795 | 7419 | s9reBpLseCBnslseiKA6 | Normal | 2 | 1.9.9.13.2.7 | 1.9.9.13.2.7 |  | 514 | q | -514 | (-100%) | 0
796 | 7420 | ia01m1zWF4qAvVLVg5It | Summary | 54 | 1.9.9.13.2.8 | 1.9.9.13.2.8 |  | 514 | q | -514 | (-100%) | 0
797 | 7421 | 5PvQN5TGe8y7KbK2rRhO | Normal | 8 | 1.9.9.13.2.8.1 | 1.9.9.13.2.8.1 |  | 514 | q | -514 | (-100%) | 0
798 | 7422 | fj19MvsSAfWHeVGXiA1H | Normal | 5 | 1.9.9.13.2.8.2 | 1.9.9.13.2.8.2 |  | 540 | q | -515 | (-95%) | 25
799 | 7423 | hs9Gt4WgG9pENnEIaC7X | Normal | 14 | 1.9.9.13.2.8.3 | 1.9.9.13.2.8.3 |  | 514 | q | -514 | (-100%) | 0
800 | 7424 | WqCakGr8mHgCENNWHHjW | Normal | 5 | 1.9.9.13.2.8.4 | 1.9.9.13.2.8.4 |  | 538 | q | -517 | (-96%) | 21
801 | 7425 | Pv27HXd826jlfuUJmTLH | Normal | 20 | 1.9.9.13.2.8.5 | 1.9.9.13.2.8.5 |  | 514 | q | -514 | (-100%) | 0
802 | 7426 | UjcYgNHyPV73fWy2GGNA | Normal | 5 | 1.9.9.13.2.8.6 | 1.9.9.13.2.8.6 |  | 528 | q | -516 | (-98%) | 12
803 | 7427 | 5QMAV8W19uO0knxuRgYc | Normal | 6 | 1.9.9.13.2.8.7 | 1.9.9.13.2.8.7 |  | 514 | q | -514 | (-100%) | 0
804 | 7428 | C3roUkJ3GEdxAvfnxnUE | Normal | 6 | 1.9.9.13.2.8.8 | 1.9.9.13.2.8.8 |  | 514 | q | -514 | (-100%) | 0
805 | 7429 | GMfJSktlv5oUXA5LFNgA | Normal | 6 | 1.9.9.13.2.8.9 | 1.9.9.13.2.8.9 |  | 514 | q | -514 | (-100%) | 0
806 | 7430 | AjX0fOJfuCWTWcoFWrZe | Summary | 11 | 1.9.9.13.2.9 | 1.9.9.13.2.9 |  | 514 | q | -514 | (-100%) | 0
807 | 7431 | YKkcKAxBNBkRs3Gs0cxp | Normal | 7 | 1.9.9.13.2.9.1 | 1.9.9.13.2.9.1 |  | 538 | q | -510 | (-95%) | 28
808 | 7432 | HbmHLQTrqR87hE03VIdq | Normal | 3 | 1.9.9.13.2.9.2 | 1.9.9.13.2.9.2 |  | 514 | q | -514 | (-100%) | 0
809 | 7433 | FxBsJSw4ZNEIyIQA8bL9 | Normal | 8 | 1.9.9.13.2.9.3 | 1.9.9.13.2.9.3 |  | 514 | q | -514 | (-100%) | 0
810 | 7434 | MkjgnYEnwrIrITdXMEl9 | Milestone | 0 | 1.9.9.13.3 | 1.9.9.13.3 |  | 514 | q | -514 | (-100%) | 0
811 | 7435 | nSo6tYchIu2Aw4YtE45u | Summary | 44 | 1.9.9.13.4 | 1.9.9.13.4 |  | 514 | q | -514 | (-100%) | 0
812 | 7436 | Y83lvWkQwfsc3dMGwfVN | Summary | 30 | 1.9.9.13.4.1 | 1.9.9.13.4.1 |  | 514 | q | -514 | (-100%) | 0
813 | 7437 | E8EwVgjFQaEPGP66WsCb | Summary | 30 | 1.9.9.13.4.1.1 | 1.9.9.13.4.1.1 |  | 514 | q | -506 | (-98%) | 8
814 | 7438 | y2P0mgWq1uFkM4aVxtQJ | Normal | 15 | 1.9.9.13.4.1.1.1 | 1.9.9.13.4.1.1.1 |  | 514 | q | -506 | (-98%) | 8
815 | 7439 | nsJKxwZOWJc3LdYsNOwr | Normal | 5 | 1.9.9.13.4.1.1.2 | 1.9.9.13.4.1.1.2 |  | 514 | q | -506 | (-98%) | 8
816 | 7440 | 3ZzL4TktDwncii0hY2dA | Normal | 10 | 1.9.9.13.4.1.1.3 | 1.9.9.13.4.1.1.3 |  | 514 | q | -506 | (-98%) | 8
817 | 7441 | IcgrxiRjEYJLwuugm8N7 | Summary | 30 | 1.9.9.13.4.1.2 | 1.9.9.13.4.1.2 |  | 514 | q | -514 | (-100%) | 0
818 | 7442 | B8zfbswYxyRxHa21jaE6 | Normal | 15 | 1.9.9.13.4.1.2.1 | 1.9.9.13.4.1.2.1 |  | 514 | q | -514 | (-100%) | 0
819 | 7443 | lvFKaF8Jtq8DkkB0s9nv | Normal | 15 | 1.9.9.13.4.1.2.2 | 1.9.9.13.4.1.2.2 |  | 514 | q | -514 | (-100%) | 0
820 | 7444 | 419IszMaZW6XNIQptprk | Normal | 20 | 1.9.9.13.4.1.3 | 1.9.9.13.4.1.3 |  | 524 | q | -517 | (-99%) | 7
821 | 7445 | oNfFp4VAwKEpoSujTbHZ | Normal | 10 | 1.9.9.13.4.1.4 | 1.9.9.13.4.1.4 |  | 534 | q | -513 | (-96%) | 21
822 | 7446 | NnBZUSVumxDXwVdCLN8g | Summary | 12 | 1.9.9.13.4.2 | 1.9.9.13.4.2 |  | 514 | q | -514 | (-100%) | 0
823 | 7447 | CAsJ3atkVCS14hehUB9Y | Normal | 4 | 1.9.9.13.4.2.1 | 1.9.9.13.4.2.1 |  | 514 | q | -513 | (-100%) | 1
824 | 7448 | 8tMCh2h8AwE53TPPkfEv | Normal | 3 | 1.9.9.13.4.2.2 | 1.9.9.13.4.2.2 |  | 514 | q | -514 | (-100%) | 0
825 | 7449 | LaZxXVdUnGzqswRGUiV5 | Normal | 7 | 1.9.9.13.4.2.3 | 1.9.9.13.4.2.3 |  | 514 | q | -514 | (-100%) | 0
826 | 7450 | F3vtt1T8lz7mQWFPgUKT | Normal | 2 | 1.9.9.13.4.3 | 1.9.9.13.4.3 |  | 514 | q | -514 | (-100%) | 0
827 | 7451 | nShmtMdGhMi3SzNeAZjW | Milestone | 0 | 1.9.9.13.4.4 | 1.9.9.13.4.4 |  | 514 | q | -514 | (-100%) | 0
828 | 7510 | 4i5VLTIa98HteWhFzYjv | Normal | 3 | 1.7.10.24 | 1.7.10.24 |  | 514 | q | -506 | (-98%) | 8
829 | 7511 | tHPdmsBqm9kHM69dtq3h | Normal | 7 | 1.7.10.25 | 1.7.10.25 |  | 514 | q | -506 | (-98%) | 8
830 | 7512 | hmOTDv9qQbSDcHudIm9x | Normal | 7 | 1.7.10.26 | 1.7.10.26 |  | 514 | q | -506 | (-98%) | 8
831 | 7513 | NbiRgc4Tdvxa900kw7Xq | Normal | 8 | 1.7.10.27 | 1.7.10.27 |  | 514 | q | -506 | (-98%) | 8
832 | 7539 | ROucR7pug9aGzObG8pvW | Normal | 1 | 1.7.10.8 | 1.7.10.8 |  | 580 | p | 537 | -93% | 1117
833 | 7540 | njszlznNRnCyRW2hgoMI | Normal | 10 | 1.7.10.9 | 1.7.10.9 |  | 580 | p | 537 | -93% | 1117
834 | 7541 | R63tw5xkvmDGiWpIPQRa | Normal | 1 | 1.7.10.10 | 1.7.10.10 |  | 568 | p | 559 | -98% | 1127
835 | 7542 | E3YdLEfamF0eZCISJiqw | Normal | 10 | 1.7.10.11 | 1.7.10.11 |  | 550 | p | 569 | -103% | 1119
836 | 7543 | nhpJxewK7uClQLzGXJQJ | Normal | 1 | 1.7.10.12 | 1.7.10.12 |  | 526 | p | 601 | -114% | 1127
837 | 7544 | cfuUTFyz3WOPAOOiNQOb | Normal | 1 | 1.7.10.13 | 1.7.10.13 |  | 526 | p | 602 | -114% | 1128
838 | 6279 | p7EJXT1muDSglD2OZLFH | Summary | 274 | 1.9.7 | 1.9.7 |  | 526 | q | -513 | (-98%) | 13
839 | 1484 | 6ARiGRg3KLswRpJLOmGD | Summary | 229 | 1.9.7.18 | 1.9.7.18 |  | 648 | p | 393 | -61% | 1041
840 | 1485 | R0QJsNVi0JzXq4FadBdS | Normal | 20 | 1.9.7.18.4 | 1.9.7.18.4 |  | 206 | p | 1951 | -947% | 2157
841 | 1486 | 9VYbXOz4xuMas0igEBkB | Summary | 56 | 1.9.7.18.6 | 1.9.7.18.6 |  | 206 | p | 1951 | -947% | 2157
842 | 6540 | BF294XdCZHw2CEg81bOs | Normal | 19 | 1.9.7.18.6.1 | 1.9.7.18.6.1 |  | 206 | p | 1951 | -947% | 2157
843 | 6541 | X8phwYugZBkIbn0OysQW | Normal | 19 | 1.9.7.18.6.2 | 1.9.7.18.6.2 |  | 206 | p | 1951 | -947% | 2157
844 | 6542 | fphO3nZhiS43G9CLfKfB | Normal | 18 | 1.9.7.18.6.3 | 1.9.7.18.6.3 |  | 206 | p | 1951 | -947% | 2157
845 | 1489 | pYq4lU1lCt1U75q3gu6M | Normal | 11 | 1.9.7.18.1 | 1.9.7.18.1 |  | 206 | p | 835 | -405% | 1041
846 | 1490 | hF9FI1LNvFfgTTXhqPsR | Normal | 77 | 1.9.7.18.2 | 1.9.7.18.2 |  | 206 | p | 1951 | -947% | 2157
847 | 1491 | XpTPefWn9TT3C06gw8rA | Normal | 1 | 1.9.7.18.3 | 1.9.7.18.3 |  | 206 | p | 1951 | -947% | 2157
848 | 1495 | 0kid3Dd3U5gCQNrt2pwY | Normal | 1 | 1.9.7.18.8 | 1.9.7.18.8 |  | 822 | p | 158 | -19% | 980
849 | 1504 | ndaml8HRsqEWzWIKrI7h | Normal | 5 | 1.9.7.18.10 | 1.9.7.18.10 |  | 760 | p | 162 | -21% | 922
850 | 4587 | 5uS9ktvplxYkrLheR3Q9 | Normal | 20 | 1.9.7.18.5 | 1.9.7.18.5 |  | 206 | p | 1951 | -947% | 2157
851 | 1496 | 5t2MhilpkZRDQA3VTcGS | Normal | 48 | 1.9.7.7 | 1.9.7.7 |  | 822 | p | 158 | -19% | 980
852 | 1505 | 4c3z8pWafVxAWNC1MpC9 | Normal | 106 | 1.9.7.8 | 1.9.7.8 |  | 760 | p | 162 | -21% | 922
853 | 1508 | SDZ1pqYbdynEzXZrWujj | Normal | 30 | 1.9.7.6 | 1.9.7.6 |  | 852 | p | 126 | -15% | 978
854 | 1529 | WOa3B8SPUOSM5ThLE2Jo | Summary | 69 | 1.9.7.14 | 1.9.7.14 |  | 818 | p | 135 | -17% | 953
855 | 1531 | KX1eD2ASIZaZBZuqoVp4 | Normal | 1 | 1.9.7.14.2 | 1.9.7.14.2 |  | 842 | p | 277 | -33% | 1119
856 | 1532 | fQ3wcWF8uEWMRGpUCxEA | Normal | 1 | 1.9.7.14.4 | 1.9.7.14.4 |  | 840 | p | 157 | -19% | 997
857 | 1533 | juvdtwZkjArAkPOzLrhN | Normal | 15 | 1.9.7.14.5 | 1.9.7.14.5 |  | 818 | p | 135 | -17% | 953
858 | 1534 | SuchbNnj1ndABAEPQlrb | Normal | 10 | 1.9.7.14.6 | 1.9.7.14.6 |  | 818 | p | 135 | -17% | 953
859 | 4583 | QzcCl72pVAI4zSVR8VAE | Normal | 1 | 1.9.7.14.3 | 1.9.7.14.3 |  | 842 | p | 277 | -33% | 1119
860 | 1535 | vIOpwJGhGrQ4pKl5nahR | Summary | 61 | 1.9.7.15 | 1.9.7.15 |  | 322 | q | -22 | (-7%) | 300
861 | 1537 | HoYmSEeaxBfAYgcISNXh | Normal | 5 | 1.9.7.15.2 | 1.9.7.15.2 |  | 322 | q | -22 | (-7%) | 300
862 | 1538 | 1Xm6i4dPIyAKJzF1jRtD | Normal | 45 | 1.9.7.15.3 | 1.9.7.15.3 |  | 322 | q | -22 | (-7%) | 300
863 | 1539 | ySsQ3GXU4tpHt4hn7HeO | Normal | 2 | 1.9.7.15.4 | 1.9.7.15.4 |  | 359 | q | -359 | (-100%) | 0
864 | 1540 | GIXHFfgJ4jA0lgUlb0GT | Normal | 1 | 1.9.7.15.5 | 1.9.7.15.5 |  | 359 | q | -359 | (-100%) | 0
865 | 1541 | ss8yD9dhZfTIp9UxqHnG | Normal | 1 | 1.9.7.15.7 | 1.9.7.15.7 |  | 322 | q | -22 | (-7%) | 300
866 | 1542 | VmFPpoMfVfLEXeRBF7Um | Normal | 9 | 1.9.7.15.8 | 1.9.7.15.8 |  | 322 | q | -22 | (-7%) | 300
867 | 1543 | P2oxmSB7jXG6Ib9VEZ89 | Normal | 9 | 1.9.7.15.9 | 1.9.7.15.9 |  | 322 | q | -22 | (-7%) | 300
868 | 4585 | Z4QB23UBk58Dyd3318zD | Normal | 10 | 1.9.7.15.6 | 1.9.7.15.6 |  | 359 | p | 2 | -1% | 361
869 | 1544 | dYtuUpkdltDWUtvWJGdC | Summary | 80 | 1.9.7.16 | 1.9.7.16 |  | 355 | p | 4 | -1% | 359
870 | 1547 | K0gsOWDMqaySswr72BAQ | Normal | 1 | 1.9.7.16.3 | 1.9.7.16.3 |  | 355 | p | 6 | -2% | 361
871 | 1548 | 4jCrHn72KCapTPEI9TzQ | Normal | 2 | 1.9.7.16.5 | 1.9.7.16.5 |  | 355 | p | 6 | -2% | 361
872 | 1549 | s8gTUDwRZFDpCO4enZqk | Normal | 15 | 1.9.7.16.6 | 1.9.7.16.6 |  | 355 | p | 84 | -24% | 439
873 | 1550 | UoQFPyMNVa9QPyq2kgrl | Normal | 9 | 1.9.7.16.7 | 1.9.7.16.7 |  | 355 | p | 4 | -1% | 359
874 | 4586 | kRWFuIGKur6ToFmAr9JC | Normal | 1 | 1.9.7.16.4 | 1.9.7.16.4 |  | 355 | p | 6 | -2% | 361
875 | 1551 | FTwSjNJQyZH6RsSSqWG9 | Summary | 78 | 1.9.7.19 | 1.9.7.19 |  | 322 | q | -1 | 0% | 321
876 | 1560 | fBOtciokyA85OuE15WSO | Normal | 1 | 1.9.7.19.10 | 1.9.7.19.10 |  | 322 | q | -322 | (-100%) | 0
877 | 1561 | 8BMHpFsmSFY1BvBQKfdD | Normal | 10 | 1.9.7.19.11 | 1.9.7.19.11 |  | 322 | q | -1 | 0% | 321
878 | 1562 | lBuCdKTmKHrCdvS4FVbB | Normal | 40 | 1.9.7.19.12 | 1.9.7.19.12 |  | 322 | q | -1 | 0% | 321
879 | 1563 | TUxQ6kz9ittb2zcmlLCL | Normal | 10 | 1.9.7.19.13 | 1.9.7.19.13 |  | 322 | q | -1 | 0% | 321
880 | 1564 | OkMyUpJo7fqJaif9Jvyb | Normal | 5 | 1.9.7.19.14 | 1.9.7.19.14 |  | 322 | q | -1 | 0% | 321
881 | 1565 | 9BGxipQLCi4kED7E7faW | Normal | 4 | 1.9.7.19.15 | 1.9.7.19.15 |  | 322 | q | -1 | 0% | 321
882 | 4571 | grLKm3VpZ98OhRQH2gBq | Normal | 29 | 1.9.7.1 | 1.9.7.1 |  | 872 | p | 125 | -14% | 997
883 | 4572 | 5hxJeLGqqaIlIue4XwRC | Normal | 1 | 1.9.7.2 | 1.9.7.2 |  | 872 | p | 125 | -14% | 997
884 | 4574 | z7UYZlhr663oN8lfFWmH | Summary | 29 | 1.9.7.11 | 1.9.7.11 |  | 760 | p | 162 | -21% | 922
885 | 1497 | q56IdotBOPeXlK3605d6 | Normal | 1 | 1.9.7.11.4 | 1.9.7.11.4 |  | 822 | p | 158 | -19% | 980
886 | 1506 | zNKWNUMZ7wFR6LBQ8bZ2 | Normal | 1 | 1.9.7.11.5 | 1.9.7.11.5 |  | 760 | p | 162 | -21% | 922
887 | 1509 | xdWSZU8MxGE52WBHNu6X | Normal | 1 | 1.9.7.11.3 | 1.9.7.11.3 |  | 852 | p | 126 | -15% | 978
888 | 6440 | u5F2XJPKXxmZ5m99Yx5A | Normal | 1 | 1.9.7.11.7 | 1.9.7.11.7 |  | 826 | p | 147 | -18% | 973
889 | 4575 | nPe6rBdPLk408ntp39jn | Normal | 1 | 1.9.7.3 | 1.9.7.3 |  | 800 | p | 608 | -76% | 1408
890 | 4578 | kBeLaux8MTugqoi5KPvZ | Summary | 74 | 1.9.7.13 | 1.9.7.13 |  | 355 | p | 4 | -1% | 359
891 | 1462 | 2Cc6AJ3gtv1XGHwG4F9W | Normal | 1 | 1.9.7.13.3 | 1.9.7.13.3 |  | 352 | q | -19 | (-5%) | 333
892 | 1518 | qXbL36bdYftxHm1TCntK | Normal | 1 | 1.9.7.13.4 | 1.9.7.13.4 |  | 818 | p | 135 | -17% | 953
893 | 4579 | xoTCeJS6YwjvMvm1YAvH | Normal | 1 | 1.9.7.13.2 | 1.9.7.13.2 |  | 322 | q | -22 | (-7%) | 300
894 | 4580 | llDwDvQQbSyeeXMs3M2a | Normal | 1 | 1.9.7.13.1 | 1.9.7.13.1 |  | 355 | p | 4 | -1% | 359
895 | 4581 | FxGRGf2kppDMdfFrZkS4 | Normal | 36 | 1.9.7.12 | 1.9.7.12 |  | 706 | p | 134 | -19% | 840
896 | 4588 | L1kgBhMEjlIJ4HNHh1TQ | Summary | 141 | 1.9.7.20 | 1.9.7.20 |  | 672 | p | 145 | -22% | 817
897 | 1566 | KFj0hxHWvExDoqTqgDeg | Normal | 118 | 1.9.7.20.1 | 1.9.7.20.1 |  | 672 | p | 145 | -22% | 817
898 | 1567 | GV5or0ucuouXZiqAkH0N | Normal | 10 | 1.9.7.20.2 | 1.9.7.20.2 |  | 672 | p | 145 | -22% | 817
899 | 1568 | JI4xSRBKV4FYnRXdw7Wz | Normal | 9 | 1.9.7.20.3 | 1.9.7.20.3 |  | 672 | p | 145 | -22% | 817
900 | 1569 | DVuFJt4FGQSIgeZkA41d | Normal | 4 | 1.9.7.20.4 | 1.9.7.20.4 |  | 672 | p | 145 | -22% | 817
901 | 4590 | 21lrGsmJiPqRYOd4yY3H | Summary | 2 | 1.9.7.21 | 1.9.7.21 |  | 514 | q | -514 | (-100%) | 0
902 | 1570 | 9hmrS48cr19KgrseY4yN | Normal | 2 | 1.9.7.21.1 | 1.9.7.21.1 |  | 514 | q | -514 | (-100%) | 0
903 | 6439 | JoFd6fDKN7NWznuQx6gK | Normal | 56 | 1.9.7.10 | 1.9.7.10 |  | 826 | p | 147 | -18% | 973
904 | 7323 | p8rF5Tk8321hO30p5zSy | Summary | 79 | 1.7.8.18 | 1.7.8.18 |  | 818 | p | 135 | -17% | 953
905 | 7454 | JYERhD3wllXGZEgPk4Fl | Normal | 5 | 1.7.8.18.1 | 1.7.8.18.1 |  | 833 | p | 120 | -14% | 953
906 | 7455 | hQlezwT73UjuGPZkyuVr | Normal | 9 | 1.7.8.18.2 | 1.7.8.18.2 |  | 833 | p | 120 | -14% | 953
907 | 7456 | 3cfjdZ38xGBNf8roD7He | Normal | 9 | 1.7.8.18.3 | 1.7.8.18.3 |  | 833 | p | 120 | -14% | 953
908 | 7457 | abNwDWOnFoe0xwhiRueS | Normal | 1 | 1.7.8.18.4 | 1.7.8.18.4 |  | 830 | p | 123 | -15% | 953
909 | 7458 | cMhUMuxC0sax27543As7 | Normal | 24 | 1.7.8.18.5 | 1.7.8.18.5 |  | 818 | p | 135 | -17% | 953
910 | 7459 | xf7OMyoiQ38QdcweBYiq | Normal | 20 | 1.7.8.18.6 | 1.7.8.18.6 |  | 818 | p | 135 | -17% | 953
911 | 7324 | GVXYroUMjcAFUHa4B19H | Normal | 1 | 1.7.8.19 | 1.7.8.19 |  | 823 | p | 523 | -64% | 1346
912 | 7325 | wl82vK5NXqnnsHIySTFp | Normal | 1 | 1.7.8.20 | 1.7.8.20 |  | 818 | p | 135 | -17% | 953
913 | 7382 | GJk3wpkfagyrb21gVciV | Summary | 288 | 1.9.7.22 | 1.9.7.22 |  | 538 | q | -510 | (-95%) | 28
914 | 7383 | chM988R4AoJxJINOHhOy | Normal | 1 | 1.9.7.22.1 | 1.9.7.22.1 |  | 796 | p | 546 | -69% | 1342
915 | 7384 | xn1TRUhUfNd3ygHlAMk1 | Normal | 16 | 1.9.7.22.2 | 1.9.7.22.2 |  | 796 | p | 546 | -69% | 1342
916 | 7385 | cYlWo9e2zkkP7jtt7iLZ | Normal | 1 | 1.9.7.22.3 | 1.9.7.22.3 |  | 796 | p | 546 | -69% | 1342
917 | 7386 | F9n9tFj3S3xXbwXNgAjU | Normal | 5 | 1.9.7.22.4 | 1.9.7.22.4 |  | 538 | q | -510 | (-95%) | 28
918 | 6285 | 0inPdnysTnfuJeCJJEwo | Summary | 131 | 1.9.1 | 1.9.1 |  | 190 | q | -15 | (-8%) | 175
919 | 4593 | XK8YU5H8vMrR7jBOr6fS | Normal | 99 | 1.9.1.1 | 1.9.1.1 |  | 248 | q | -8 | (-3%) | 240
920 | 4594 | EUFkYGsAZWO3vgZroOTA | Normal | 1 | 1.9.1.2 | 1.9.1.2 |  | 248 | q | -8 | (-3%) | 240
921 | 4595 | 0i30zTvKTrSo3R9n999e | Normal | 2 | 1.9.1.3 | 1.9.1.3 |  | 248 | q | -8 | (-3%) | 240
922 | 4605 | jXRAJqcdCYbTQqzq5oVG | Normal | 14 | 1.7.3.2 | 1.7.3.2 |  | 219 | q | -20 | (-9%) | 199
923 | 4606 | e1c7TqZJ2saEXqSPx9Ca | Normal | 1 | 1.7.3.3 | 1.7.3.3 |  | 219 | q | -20 | (-9%) | 199
924 | 4607 | 9Rf8xh1sYqA0mX8AIEgx | Summary | 52 | 1.7.3.5 | 1.7.3.5 |  | 219 | q | -20 | (-9%) | 199
925 | 4608 | tlJeJHdE7OwhwWyVvZ8P | Normal | 5 | 1.7.3.5.1 | 1.7.3.5.1 |  | 219 | q | -20 | (-9%) | 199
926 | 4609 | PoeQu0I6Io83IRbk7WtS | Normal | 5 | 1.7.3.5.2 | 1.7.3.5.2 |  | 219 | q | -20 | (-9%) | 199
927 | 4610 | UGUZlny6Ut8S0mLRTL2X | Normal | 1 | 1.7.3.5.3 | 1.7.3.5.3 |  | 219 | q | -20 | (-9%) | 199
928 | 4611 | 1TZOFiOcsBCmkfhi03Iw | Normal | 5 | 1.7.3.5.4 | 1.7.3.5.4 |  | 219 | q | -20 | (-9%) | 199
929 | 4612 | ZwEXlYv6PrV1t0gzfqom | Normal | 10 | 1.7.3.5.5 | 1.7.3.5.5 |  | 219 | q | -20 | (-9%) | 199
930 | 4613 | z0DGpsje53b33zXA5t1P | Normal | 20 | 1.7.3.5.6 | 1.7.3.5.6 |  | 219 | q | -20 | (-9%) | 199
931 | 4614 | cqs4HA7sR83mroZvcBiw | Normal | 1 | 1.7.3.5.7 | 1.7.3.5.7 |  | 219 | q | -20 | (-9%) | 199
932 | 4615 | Io6EVgFdyRjG7CB2g0Wy | Summary | 98 | 1.7.3.4 | 1.7.3.4 |  | 269 | q | -25 | (-9%) | 244
933 | 4616 | FR5tuVwQGmPNYmz6BeMP | Normal | 2 | 1.7.3.4.1 | 1.7.3.4.1 |  | 266 | q | -7 | (-3%) | 259
934 | 4617 | OziRB3N5b7cM46iEETGg | Normal | 5 | 1.7.3.4.2 | 1.7.3.4.2 |  | 250 | q | -16 | (-6%) | 234
935 | 4618 | mRqsjEijsp2iSp4l7aof | Normal | 5 | 1.7.3.4.3 | 1.7.3.4.3 |  | 284 | q | -20 | (-7%) | 264
936 | 4619 | 8asUr7UOO8nabPagFvw9 | Normal | 40 | 1.7.3.4.4 | 1.7.3.4.4 |  | 250 | q | -16 | (-6%) | 234
937 | 4620 | UWR5akRFo4eKiDyQVnYr | Normal | 23 | 1.7.3.4.5 | 1.7.3.4.5 |  | 266 | q | -7 | (-3%) | 259
938 | 4621 | pGB9dynKUfIMuzj3AWVv | Normal | 1 | 1.7.3.4.6 | 1.7.3.4.6 |  | 219 | q | -20 | (-9%) | 199
939 | 4622 | Bm2ajkWBwO6Cvc6RoPdK | Normal | 5 | 1.7.3.4.7 | 1.7.3.4.7 |  | 219 | q | -20 | (-9%) | 199
940 | 4623 | sDTQ4X48dvup817zb0Do | Normal | 20 | 1.7.3.4.8 | 1.7.3.4.8 |  | 219 | q | -20 | (-9%) | 199
941 | 4624 | 3CGv61AS00FFpM5LrRat | Normal | 20 | 1.7.3.4.9 | 1.7.3.4.9 |  | 219 | q | -20 | (-9%) | 199
942 | 4625 | NkJyZ342jkgJkVCalD4F | Normal | 2 | 1.7.3.4.10 | 1.7.3.4.10 |  | 269 | q | -25 | (-9%) | 244
943 | 4626 | 92oajspBBxTpnlNQO91I | Summary | 90 | 1.7.3.6 | 1.7.3.6 |  | 190 | q | -15 | (-8%) | 175
944 | 4630 | pjdWghPSPBEOfTIZFZhV | Normal | 5 | 1.7.3.6.4 | 1.7.3.6.4 |  | 341 | q | -17 | (-5%) | 324
945 | 4631 | EXJQS9o5Eq3lGkaYsCap | Normal | 1 | 1.7.3.6.5 | 1.7.3.6.5 |  | 341 | q | -17 | (-5%) | 324
946 | 4632 | VGp2Ji3lCAas2O4B01f5 | Normal | 1 | 1.7.3.6.6 | 1.7.3.6.6 |  | 341 | q | -17 | (-5%) | 324
947 | 4633 | STHfhyBuM5qFiEzHSgws | Normal | 19 | 1.7.3.6.7 | 1.7.3.6.7 |  | 341 | q | -17 | (-5%) | 324
948 | 4634 | cbBLoWE0dwfwOCS04ga7 | Normal | 15 | 1.7.3.6.8 | 1.7.3.6.8 |  | 341 | q | -17 | (-5%) | 324
949 | 4635 | vrd0V7BeylNxhzgI26F9 | Normal | 8 | 1.7.3.6.11 | 1.7.3.6.11 |  | 341 | q | -17 | (-5%) | 324
950 | 4636 | DgPDbwa39NNm3em6lmtZ | Normal | 1 | 1.7.3.6.12 | 1.7.3.6.12 |  | 190 | q | -15 | (-8%) | 175
951 | 4663 | X9pjxOrdX8ZwQAfQziSu | Normal | 1 | 1.7.3.6.9 | 1.7.3.6.9 |  | 341 | q | -17 | (-5%) | 324
952 | 4664 | DAxARpEpHAwipBCK81bc | Normal | 8 | 1.7.3.6.10 | 1.7.3.6.10 |  | 341 | q | -16 | (-5%) | 325
953 | 4637 | ohQUE8EwZLGEmkE5FTpA | Summary | 8 | 1.7.3.7 | 1.7.3.7 |  | 219 | q | -18 | (-8%) | 201
954 | 6608 | ifCvUSq9UjUAw7FKKXTR | Normal | 14 | 1.7.3.7.3 | 1.7.3.7.3 |  | 219 | q | -18 | (-8%) | 201
955 | 7259 | Dcjo2uskRMoBajU90pQq | Normal | 60 | 1.7.1.4 | 1.7.1.4 |  | 219 | q | -20 | (-9%) | 199
956 | 6294 | Jtjxi70STISSeVqV8OJy | Summary | 163 | 1.9.6 | 1.9.6 |  | 530 | q | -437 | (-82%) | 93
957 | 3745 | D0mR64Wbk6oru5hoL4DG | Summary | 62 | 1.7.1.2 | 1.7.1.2 |  | 351 | q | -21 | (-6%) | 330
958 | 3773 | jfB1zdAbu7JeWEH3ijwy | Summary | 73 | 1.7.1.2.6 | 1.7.1.2.6 |  | 351 | q | -21 | (-6%) | 330
959 | 3776 | GHLE38QRMYNBeSYAGB18 | Normal | 32 | 1.7.1.2.6.3 | 1.7.1.2.6.3 |  | 351 | q | -21 | (-6%) | 330
960 | 3777 | YuGKQIQDxLVYRZzgUQjw | Normal | 9 | 1.7.1.2.6.4 | 1.7.1.2.6.4 |  | 351 | q | -21 | (-6%) | 330
961 | 3783 | FcDlmkxQNUOM36qP0M0H | Summary | 58 | 1.7.1.3 | 1.7.1.3 |  | 313 | q | -22 | (-7%) | 291
962 | 3790 | Om0YwWoKF5usOVLnDccR | Summary | 13 | 1.7.1.3.4 | 1.7.1.3.4 |  | 313 | q | -22 | (-7%) | 291
963 | 6977 | F0juzsyqTnJm6sTJe4ff | Normal | 14 | 1.7.1.3.4.7 | 1.7.1.3.4.7 |  | 313 | q | -22 | (-7%) | 291
964 | 6138 | EvFVoaLHb5OgszmS4Hdy | Summary | 44 | 1.7.1.3.9 | 1.7.1.3.9 |  | 313 | q | -22 | (-7%) | 291
965 | 6139 | VECMPYMi2oWf71g3eai1 | Normal | 29 | 1.7.1.3.9.1 | 1.7.1.3.9.1 |  | 313 | q | -22 | (-7%) | 291
966 | 6140 | mO0F0FFUdRVKYlb84WcT | Normal | 15 | 1.7.1.3.9.2 | 1.7.1.3.9.2 |  | 313 | q | -22 | (-7%) | 291
967 | 6978 | z4sj2SQJw3pdZet8Am0U | Normal | 9 | 1.7.1.3.5 | 1.7.1.3.5 |  | 346 | q | -21 | (-6%) | 325
968 | 6983 | PcmQnh6ym2R5IAKzFgwu | Summary | 141 | 1.7.1.3.7 | 1.7.1.3.7 |  | 313 | q | -22 | (-7%) | 291
969 | 6985 | eGeEyEDP9xa0SwHKf7WR | Normal | 7 | 1.7.1.3.7.4 | 1.7.1.3.7.4 |  | 313 | q | -22 | (-7%) | 291
970 | 6986 | 31qYZ6wVIReV9ZOAqgem | Summary | 9 | 1.7.1.3.7.5 | 1.7.1.3.7.5 |  | 313 | q | -22 | (-7%) | 291
971 | 6987 | 50so1NYgvDTnEeNkdrjv | Normal | 3 | 1.7.1.3.7.5.1 | 1.7.1.3.7.5.1 |  | 313 | q | -22 | (-7%) | 291
972 | 6988 | bmsC3uFxKZ3RPA57Ivjb | Normal | 3 | 1.7.1.3.7.5.2 | 1.7.1.3.7.5.2 |  | 313 | q | -22 | (-7%) | 291
973 | 6989 | okOYULy0nclsZMYhl4sg | Normal | 3 | 1.7.1.3.7.5.3 | 1.7.1.3.7.5.3 |  | 313 | q | -22 | (-7%) | 291
974 | 7184 | gKjyagqR1BEsAZjZk4l5 | Milestone | 0 | 1.7.1.3.7.3 | 1.7.1.3.7.3 |  | 314 | p | 19 | -6% | 333
975 | 6990 | K8cvVDryBsyahUujiNmr | Summary | 22 | 1.7.1.3.8 | 1.7.1.3.8 |  | 330 | q | -12 | (-4%) | 318
976 | 6136 | bVRB0EhNo1xoyHBU8R0I | Normal | 1 | 1.7.1.3.8.2 | 1.7.1.3.8.2 |  | 346 | q | -21 | (-6%) | 325
977 | 6982 | E06yVWmTg8kRS6Gv9kOV | Summary | 6 | 1.7.1.3.8.3 | 1.7.1.3.8.3 |  | 314 | q | -19 | (-6%) | 295
978 | 6137 | gagQpjsDXV4QnJ1bUthb | Normal | 2 | 1.7.1.3.8.3.1 | 1.7.1.3.8.3.1 |  | 346 | q | -21 | (-6%) | 325
979 | 6979 | ZYA6dvbLVog9FL6DNJRb | Normal | 5 | 1.7.1.3.8.3.2 | 1.7.1.3.8.3.2 |  | 313 | q | -22 | (-7%) | 291
980 | 6991 | RAhO7UtYgqwLkhTknwrO | Normal | 6 | 1.7.1.3.8.1 | 1.7.1.3.8.1 |  | 346 | p | 16 | -5% | 362
981 | 3803 | vx1oFVBFPqydBxZJ7V4g | Summary | 112 | 1.7.1.5 | 1.7.1.5 |  | 311 | q | -35 | (-11%) | 276
982 | 3808 | mNtnU9AYiACOeBrTPE9f | Summary | 29 | 1.7.1.5.3 | 1.7.1.5.3 |  | 330 | q | -22 | (-7%) | 308
983 | 3809 | ukioB4iHiwrfEXpseTiK | Normal | 15 | 1.7.1.5.3.1 | 1.7.1.5.3.1 |  | 330 | q | -22 | (-7%) | 308
984 | 3810 | CJxWy7PnZPcI4EPHEeme | Normal | 9 | 1.7.1.5.3.2 | 1.7.1.5.3.2 |  | 330 | q | -22 | (-7%) | 308
985 | 3811 | wGtgxCT3lCK6u2EOL8xN | Normal | 5 | 1.7.1.5.3.3 | 1.7.1.5.3.3 |  | 330 | q | -22 | (-7%) | 308
986 | 3813 | sYeTNUsya13QYMbMJg21 | Normal | 25 | 1.7.1.5.7 | 1.7.1.5.7 |  | 311 | q | -26 | (-8%) | 285
987 | 3814 | c3HTuVFoRVefrW72mxSE | Normal | 3 | 1.7.1.5.8 | 1.7.1.5.8 |  | 319 | q | -43 | (-13%) | 276
988 | 3815 | nJJAkVwt0aHLNZMMtbkw | Normal | 3 | 1.7.1.5.9 | 1.7.1.5.9 |  | 311 | q | -26 | (-8%) | 285
989 | 3816 | 6MWmVgC0FSCF3lMoTGjJ | Summary | 40 | 1.7.1.5.10 | 1.7.1.5.10 |  | 311 | q | -35 | (-11%) | 276
990 | 3817 | LqjKPVRVNU7j1iAlkL3t | Normal | 2 | 1.7.1.5.10.1 | 1.7.1.5.10.1 |  | 311 | q | -26 | (-8%) | 285
991 | 3818 | Cmm1EfLtBPedDjXV8dAv | Normal | 5 | 1.7.1.5.10.2 | 1.7.1.5.10.2 |  | 311 | q | -26 | (-8%) | 285
992 | 3819 | FSVjbKFfUmqE2fpbGGPv | Normal | 3 | 1.7.1.5.10.3 | 1.7.1.5.10.3 |  | 311 | q | -26 | (-8%) | 285
993 | 3820 | FhKtXXrOwkDfPm4RFzRW | Normal | 10 | 1.7.1.5.10.4 | 1.7.1.5.10.4 |  | 311 | q | -35 | (-11%) | 276
994 | 3821 | cHjYAw102skS4vR6DXqX | Normal | 20 | 1.7.1.5.10.5 | 1.7.1.5.10.5 |  | 311 | q | -35 | (-11%) | 276
995 | 6147 | BUcWclFVChflBnUDJ9UM | Normal | 40 | 1.7.1.5.4 | 1.7.1.5.4 |  | 319 | q | -43 | (-13%) | 276
996 | 6148 | V03eKqopjAXoUvRodLvQ | Normal | 13 | 1.7.1.5.6 | 1.7.1.5.6 |  | 311 | q | -26 | (-8%) | 285
997 | 4078 | ybbKeBChK3D60QzH8ONZ | Normal | 76 | 1.9.6.5 | 1.9.6.5 |  | 718 | p | 130 | -18% | 848
998 | 4129 | G6dPcJRrq5zqLYx4Vr0R | Summary | 475 | 1.9.6.10 | 1.9.6.10 |  | 514 | q | -509 | (-99%) | 5
999 | 4131 | 3WZTLr4e3INGux4LMgj0 | Summary | 146 | 1.9.6.10.2 | 1.9.6.10.2 |  | 172 | q | -608 | (-353%) | -436
1000 | 5857 | g9TizAnooUcHoXglcd4n | Milestone | 0 | 1.9.6.10.2.1 | 1.9.6.10.2.1 |  | 203 | q | -634 | (-312%) | -431
1001 | 5858 | 9N3N0HBhBeb82jbbU7Vx | Milestone | 0 | 1.9.6.10.2.2 | 1.9.6.10.2.2 |  | 215 | q | -651 | (-303%) | -436
1002 | 5859 | RMhsXtyk4773BtipN2HO | Normal | 1 | 1.9.6.10.2.3 | 1.9.6.10.2.3 |  | 215 | q | -651 | (-303%) | -436
1003 | 5860 | AMUT2hrMeOWSIoK5dO6S | Normal | 10 | 1.9.6.10.2.4 | 1.9.6.10.2.4 |  | 172 | q | -608 | (-353%) | -436
1004 | 5861 | adMwYb1cwVT0ja23ZKPV | Normal | 10 | 1.9.6.10.2.5 | 1.9.6.10.2.5 |  | 172 | q | -608 | (-353%) | -436
1005 | 5862 | rkVKH7eSVnkv5Rz0hIbo | Normal | 25 | 1.9.6.10.2.6 | 1.9.6.10.2.6 |  | 172 | q | -608 | (-353%) | -436
1006 | 5863 | axx1H8vuWtNbWz6aJYpW | Normal | 20 | 1.9.6.10.2.7 | 1.9.6.10.2.7 |  | 172 | q | -608 | (-353%) | -436
1007 | 5864 | ZuXAUp7kzm7PDgs0Clm4 | Normal | 20 | 1.9.6.10.2.8 | 1.9.6.10.2.8 |  | 172 | q | -608 | (-353%) | -436
1008 | 5865 | pfx92tyIHO0nDV8Eg4vj | Normal | 3 | 1.9.6.10.2.9 | 1.9.6.10.2.9 |  | 172 | q | -608 | (-353%) | -436
1009 | 5866 | qnFTkxNSvGIYOwHhqElS | Normal | 5 | 1.9.6.10.2.10 | 1.9.6.10.2.10 |  | 172 | q | -608 | (-353%) | -436
1010 | 5867 | 6vMprMC9ZRYTg9c055cw | Normal | 3 | 1.9.6.10.2.11 | 1.9.6.10.2.11 |  | 172 | q | -608 | (-353%) | -436
1011 | 5868 | qP5P60WlJm98gR28uFOw | Normal | 1 | 1.9.6.10.2.12 | 1.9.6.10.2.12 |  | 172 | q | -608 | (-353%) | -436
1012 | 5869 | 5FBVtcv48JlyNzpes7ps | Normal | 5 | 1.9.6.10.2.13 | 1.9.6.10.2.13 |  | 172 | q | -608 | (-353%) | -436
1013 | 5870 | rLlKwDBGmyMe6lxLtymf | Summary | 59 | 1.9.6.10.3 | 1.9.6.10.3 |  | 172 | q | -608 | (-353%) | -436
1014 | 5871 | owx5unCKcaLauhH4kWyj | Normal | 5 | 1.9.6.10.3.1 | 1.9.6.10.3.1 |  | 172 | q | -608 | (-353%) | -436
1015 | 5872 | qImIYF1Y50rp0FNnsaoS | Normal | 10 | 1.9.6.10.3.2 | 1.9.6.10.3.2 |  | 172 | q | -608 | (-353%) | -436
1016 | 5873 | FfFQqcMQ2fY5X0GvK0Xd | Normal | 20 | 1.9.6.10.3.3 | 1.9.6.10.3.3 |  | 172 | q | -608 | (-353%) | -436
1017 | 5874 | fHTDjpnY2Gm0gViXPiAD | Normal | 2 | 1.9.6.10.3.6 | 1.9.6.10.3.6 |  | 172 | q | -608 | (-353%) | -436
1018 | 5875 | TQZary26m4SvJkpuQUlv | Normal | 1 | 1.9.6.10.3.7 | 1.9.6.10.3.7 |  | 172 | q | -608 | (-353%) | -436
1019 | 5876 | 5ZRJqmbhPGswffOWtWat | Normal | 1 | 1.9.6.10.3.8 | 1.9.6.10.3.8 |  | 172 | q | -608 | (-353%) | -436
1020 | 6624 | sVpbcWAee9M5eeft5sdO | Normal | 15 | 1.9.6.10.3.4 | 1.9.6.10.3.4 |  | 172 | q | -608 | (-353%) | -436
1021 | 6625 | it5qGsWYKIf8fEL1a2TB | Normal | 5 | 1.9.6.10.3.5 | 1.9.6.10.3.5 |  | 172 | q | -608 | (-353%) | -436
1022 | 5877 | 8uIO0L3CbsjXfYIL70ur | Summary | 162 | 1.9.6.10.4 | 1.9.6.10.4 |  | 514 | q | -509 | (-99%) | 5
1023 | 5878 | eKJmpIIS7eePXp789pq5 | Summary | 60 | 1.9.6.10.4.1 | 1.9.6.10.4.1 |  | 615 | q | -454 | (-74%) | 161
1024 | 5879 | CJrwB1y6NRnYYg7kpaRv | Summary | 30 | 1.9.6.10.4.1.1 | 1.9.6.10.4.1.1 |  | 615 | q | -454 | (-74%) | 161
1025 | 5880 | z8rht75g90pc62Jd1j8e | Normal | 15 | 1.9.6.10.4.1.1.1 | 1.9.6.10.4.1.1.1 |  | 615 | q | -454 | (-74%) | 161
1026 | 5881 | ZPPJV7wrbqyTumtl84NX | Normal | 15 | 1.9.6.10.4.1.1.2 | 1.9.6.10.4.1.1.2 |  | 615 | q | -454 | (-74%) | 161
1027 | 5882 | PdfqDNDAaUS1Z9tfvPSB | Normal | 15 | 1.9.6.10.4.1.2 | 1.9.6.10.4.1.2 |  | 615 | q | -454 | (-74%) | 161
1028 | 5883 | 3J3dFKPf8v7HKW1lSal4 | Normal | 15 | 1.9.6.10.4.1.3 | 1.9.6.10.4.1.3 |  | 615 | q | -454 | (-74%) | 161
1029 | 5884 | J3ZDJxR9DKKi4JquRb3Q | Summary | 20 | 1.9.6.10.4.2 | 1.9.6.10.4.2 |  | 644 | q | -454 | (-70%) | 190
1030 | 5885 | p0UOLQYQkw5raD9Hf7AI | Normal | 5 | 1.9.6.10.4.2.1 | 1.9.6.10.4.2.1 |  | 644 | q | -454 | (-70%) | 190
1031 | 5886 | mfBVa7VrtMT45ZcRp9ur | Normal | 5 | 1.9.6.10.4.2.2 | 1.9.6.10.4.2.2 |  | 644 | q | -454 | (-70%) | 190
1032 | 5887 | xjL6okqGZuFc1ChaUzA0 | Normal | 5 | 1.9.6.10.4.2.3 | 1.9.6.10.4.2.3 |  | 644 | q | -454 | (-70%) | 190
1033 | 5888 | 0NLdruhvCSk61FiIPSJA | Normal | 5 | 1.9.6.10.4.2.4 | 1.9.6.10.4.2.4 |  | 644 | q | -454 | (-70%) | 190
1034 | 5889 | vcqfMiWzgD0sBRK91JrP | Normal | 3 | 1.9.6.10.4.3 | 1.9.6.10.4.3 |  | 644 | q | -454 | (-70%) | 190
1035 | 5890 | r7iAplKyl5D3dW7yC0Jk | Normal | 5 | 1.9.6.10.4.4 | 1.9.6.10.4.4 |  | 644 | q | -454 | (-70%) | 190
1036 | 5891 | 55B0pL3dU2GPDxU6IZLg | Normal | 1 | 1.9.6.10.4.5 | 1.9.6.10.4.5 |  | 644 | q | -454 | (-70%) | 190
1037 | 5892 | zyPP7s8BBmPhydQ5fB2g | Normal | 1 | 1.9.6.10.4.8 | 1.9.6.10.4.8 |  | 514 | q | -509 | (-99%) | 5
1038 | 5893 | JSBvauC3wpirasqwMrC9 | Normal | 1 | 1.9.6.10.4.6 | 1.9.6.10.4.6 |  | 644 | q | -454 | (-70%) | 190
1039 | 5894 | AO4SgiivKvvxQJupi2GS | Normal | 1 | 1.9.6.10.4.7 | 1.9.6.10.4.7 |  | 644 | q | -454 | (-70%) | 190
1040 | 4134 | 86JmjjOtZxj7XQRp3CQF | Summary | 466 | 1.9.6.11 | 1.9.6.11 |  | 530 | q | -312 | (-59%) | 218
1041 | 4135 | 0voiyAtBe9AzaXfs8cVF | Summary | 322 | 1.9.6.11.1 | 1.9.6.11.1 |  | 530 | q | -312 | (-59%) | 218
1042 | 4136 | bllhlvXmXgF1yFG9Nwfe | Normal | 16 | 1.9.6.11.1.1 | 1.9.6.11.1.1 |  | 530 | q | -312 | (-59%) | 218
1043 | 4137 | rnRXxVdKdR5NUADIB31n | Normal | 1 | 1.9.6.11.1.2 | 1.9.6.11.1.2 |  | 530 | q | -312 | (-59%) | 218
1044 | 4138 | 75WgU7H7MCC8DDgOcnsD | Normal | 30 | 1.9.6.11.1.3 | 1.9.6.11.1.3 |  | 530 | q | -312 | (-59%) | 218
1045 | 4139 | 9SKpfzivi43NDDuHUq0B | Normal | 5 | 1.9.6.11.1.4 | 1.9.6.11.1.4 |  | 530 | q | -312 | (-59%) | 218
1046 | 4140 | Lk7gef35zB3WaxM8Xyxe | Summary | 48 | 1.9.6.11.2 | 1.9.6.11.2 |  | 530 | q | -312 | (-59%) | 218
1047 | 4141 | HGo5Ep3pqhcsiM5K4QjA | Summary | 23 | 1.9.6.11.2.1 | 1.9.6.11.2.1 |  | 530 | q | -312 | (-59%) | 218
1048 | 4142 | VTqJrDLpWuaSlvRQajcM | Normal | 12 | 1.9.6.11.2.1.1 | 1.9.6.11.2.1.1 |  | 530 | q | -312 | (-59%) | 218
1049 | 4143 | UwGhtpl5Mnq9WQrcrXRR | Normal | 11 | 1.9.6.11.2.1.2 | 1.9.6.11.2.1.2 |  | 530 | q | -312 | (-59%) | 218
1050 | 4144 | zaFQ6K5wegGvKt6DGuoz | Summary | 25 | 1.9.6.11.2.2 | 1.9.6.11.2.2 |  | 530 | q | -312 | (-59%) | 218
1051 | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Normal | 10 | 1.9.6.11.2.2.1 | 1.9.6.11.2.2.1 |  | 530 | q | -312 | (-59%) | 218
1052 | 4146 | rTeXGnIwGPt6ES3ynSHq | Normal | 5 | 1.9.6.11.2.2.2 | 1.9.6.11.2.2.2 |  | 530 | q | -312 | (-59%) | 218
1053 | 4147 | hQaW5HIstT5bbsPEBxyQ | Normal | 10 | 1.9.6.11.2.2.3 | 1.9.6.11.2.2.3 |  | 530 | q | -312 | (-59%) | 218
1054 | 5753 | ZptYdARXANY2IOcoHhB1 | Summary | 78 | 1.9.6.1 | 1.9.6.1 |  | 275 | q | -355 | (-129%) | -80
1055 | 5998 | aRBXPvE6pbVbcbhlDtu4 | Summary | 47 | 1.9.6.1.7 | 1.9.6.1.7 |  | 203 | q | -634 | (-312%) | -431
1056 | 5999 | hTF24jclc5ogfsrVWXZd | Normal | 40 | 1.9.6.1.7.1 | 1.9.6.1.7.1 |  | 203 | q | -634 | (-312%) | -431
1057 | 6000 | dvNXA0SZWky1SGhKE7td | Normal | 5 | 1.9.6.1.7.2 | 1.9.6.1.7.2 |  | 203 | q | -634 | (-312%) | -431
1058 | 6001 | z8HVZ6SyP3QpkaT54VAm | Normal | 1 | 1.9.6.1.7.3 | 1.9.6.1.7.3 |  | 203 | q | -634 | (-312%) | -431
1059 | 6002 | rmlzSal3Nkh8gQGzhscw | Normal | 1 | 1.9.6.1.7.4 | 1.9.6.1.7.4 |  | 203 | q | -634 | (-312%) | -431
1060 | 6003 | zkyCYMQIHOywdkyzbjbi | Summary | 48 | 1.9.6.1.8 | 1.9.6.1.8 |  | 275 | q | -629 | (-229%) | -354
1061 | 6004 | xOhJcEwgSz1TAvNHU4tB | Normal | 40 | 1.9.6.1.8.1 | 1.9.6.1.8.1 |  | 276 | q | -616 | (-223%) | -340
1062 | 6005 | gw3ZFSF3nzLqLqYBiqR7 | Normal | 5 | 1.9.6.1.8.2 | 1.9.6.1.8.2 |  | 276 | q | -616 | (-223%) | -340
1063 | 6006 | HEKaqqmbwSXnCRXB6fED | Normal | 1 | 1.9.6.1.8.3 | 1.9.6.1.8.3 |  | 276 | q | -616 | (-223%) | -340
1064 | 6007 | vdBzwsumrXxpXNAKvnKh | Normal | 1 | 1.9.6.1.8.4 | 1.9.6.1.8.4 |  | 275 | q | -629 | (-229%) | -354
1065 | 6008 | Ph5VFx7Ghit4AwZEFBXT | Summary | 50 | 1.9.6.1.6 | 1.9.6.1.6 |  | 203 | q | -634 | (-312%) | -431
1066 | 6009 | NVgukc0KZBShUa0wIlyx | Normal | 30 | 1.9.6.1.6.1 | 1.9.6.1.6.1 |  | 203 | q | -634 | (-312%) | -431
1067 | 6010 | tIYqVtlT4yOF2YQ2FRYY | Normal | 10 | 1.9.6.1.6.2 | 1.9.6.1.6.2 |  | 229 | q | -631 | (-276%) | -402
1068 | 6011 | 9Y3pHbqvwzl2AwHfvrBG | Normal | 5 | 1.9.6.1.6.3 | 1.9.6.1.6.3 |  | 229 | q | -631 | (-276%) | -402
1069 | 6012 | Z1jpWQx4GyFcVoEVg0i0 | Normal | 5 | 1.9.6.1.6.4 | 1.9.6.1.6.4 |  | 229 | q | -631 | (-276%) | -402
1070 | 6013 | y2dxMv99iLhGOXikZGuK | Summary | 34 | 1.9.6.1.5 | 1.9.6.1.5 |  | 203 | q | -26 | (-13%) | 177
1071 | 6014 | hYHiAVYfHXdDTdWEk9J8 | Normal | 15 | 1.9.6.1.5.1 | 1.9.6.1.5.1 |  | 203 | q | -26 | (-13%) | 177
1072 | 6015 | MXdxqc8Y6tIByFeEqluF | Normal | 10 | 1.9.6.1.5.2 | 1.9.6.1.5.2 |  | 260 | q | -23 | (-9%) | 237
1073 | 6016 | gwhB80Lv7eu4PoYwev8o | Normal | 5 | 1.9.6.1.5.3 | 1.9.6.1.5.3 |  | 260 | q | -23 | (-9%) | 237
1074 | 6017 | VCyTBN0y7V3erCRNMvm4 | Normal | 4 | 1.9.6.1.5.4 | 1.9.6.1.5.4 |  | 260 | q | -23 | (-9%) | 237
1075 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | 217 | q | -217 | (-100%) | 0
1076 | 6957 | ar01N24L63iczVEh1mVo | Summary | 24 | 1.9.6.1.4 | 1.9.6.1.4 |  | 203 | q | -26 | (-13%) | 177
1077 | 6958 | 6Ul4V6iAcnpVqewOp14Y | Normal | 4 | 1.9.6.1.4.1 | 1.9.6.1.4.1 |  | 203 | q | -26 | (-13%) | 177
1078 | 6959 | w9Vvv79ftt4PUqInNFyD | Normal | 5 | 1.9.6.1.4.2 | 1.9.6.1.4.2 |  | 203 | q | -26 | (-13%) | 177
1079 | 6960 | xIgpHAurEQ244gHa2T5q | Normal | 5 | 1.9.6.1.4.3 | 1.9.6.1.4.3 |  | 275 | q | -24 | (-9%) | 251
1080 | 6961 | NOksVV7sTymsgwMrnh6x | Normal | 10 | 1.9.6.1.4.4 | 1.9.6.1.4.4 |  | 275 | q | -24 | (-9%) | 251
1081 | 5762 | BY50RWHTB6QfyvgvJksd | Summary | 36 | 1.9.6.9 | 1.9.6.9 |  | 696 | p | 126 | -18% | 822
1082 | 4074 | H2vE7zxiBRw3YTdo2zSW | Normal | 35 | 1.9.6.9.2 | 1.9.6.9.2 |  | 696 | p | 126 | -18% | 822
1083 | 4075 | dGbNHsOLhslKk8CjhyjE | Normal | 1 | 1.9.6.9.3 | 1.9.6.9.3 |  | 696 | p | 126 | -18% | 822
1084 | 6424 | xU9ngPKik2IYPonksYTK | Summary | 24 | 1.7.1.8 | 1.7.1.8 |  | 903 | p | 214 | -24% | 1117
1085 | 6427 | NeAxFJaqSLize8VPNJ6N | Normal | 1 | 1.7.1.8.3 | 1.7.1.8.3 |  | 903 | p | 214 | -24% | 1117
1086 | 6296 | SlR21lje1Tex9DLMlAM1 | Summary | 222 | 1.9.8 | 1.9.8 |  | 514 | q | -514 | (-100%) | 0
1087 | 4192 | vUDAXlHZqbmK6WAsX9hH | Summary | 139 | 1.9.8.1 | 1.9.8.1 |  | 638 | p | 159 | -25% | 797
1088 | 4196 | 2ZwOzHGH45ywtPvfASSG | Normal | 5 | 1.9.8.1.5 | 1.9.8.1.5 |  | 638 | p | 159 | -25% | 797
1089 | 4197 | 4xVk2zrTd9sJnt9BJFir | Summary | 36 | 1.9.8.1.6 | 1.9.8.1.6 |  | 782 | p | 171 | -22% | 953
1090 | 5974 | cJ7VeFZezCBnvYlHxCmb | Normal | 1 | 1.9.8.1.6.7 | 1.9.8.1.6.7 |  | 782 | p | 226 | -29% | 1008
1091 | 4198 | k6X8NWhjfeQOPZdDpmna | Normal | 20 | 1.9.8.1.9 | 1.9.8.1.9 |  | 113 | q | -14 | (-12%) | 99
1092 | 5985 | AUKn3E7aViOsULw8HdKV | Normal | 131 | 1.9.8.1.12 | 1.9.8.1.12 |  | 638 | p | 159 | -25% | 797
1093 | 4222 | uotgqiCu1xVBvHdpBC3E | Summary | 97 | 1.9.8.2 | 1.9.8.2 |  | 532 | p | 153 | -29% | 685
1094 | 4231 | 8h0WH2qeIC7tfvcerCPa | Normal | 1 | 1.9.8.2.3 | 1.9.8.2.3 |  | 548 | p | 300 | -55% | 848
1095 | 4235 | QiaATNQSPId7svzcuO8r | Normal | 91 | 1.9.8.2.7 | 1.9.8.2.7 |  | 532 | p | 153 | -29% | 685
1096 | 4238 | ReJqSs3gutB053iVY5c7 | Summary | 76 | 1.9.8.4 | 1.9.8.4 |  | 314 | q | -29 | (-9%) | 285
1097 | 4242 | RIVyyga7UReDeuixs5m9 | Normal | 66 | 1.9.8.4.4 | 1.9.8.4.4 |  | 314 | q | -29 | (-9%) | 285
1098 | 4243 | LpPx7AWOh1V8dzWVWc6j | Normal | 1 | 1.9.8.4.5 | 1.9.8.4.5 |  | 314 | p | 247 | -79% | 561
1099 | 4246 | ANAzXnUTz1PCb3xsov4Y | Normal | 10 | 1.9.8.4.7 | 1.9.8.4.7 |  | 314 | q | -29 | (-9%) | 285
1100 | 4248 | E1RJwJWM8qrsKP3o7Toy | Normal | 1 | 1.9.8.7 | 1.9.8.7 |  | 268 | p | 12 | -4% | 280
1101 | 4251 | IBg36OMMKUy3vwEnRNF0 | Normal | 1 | 1.9.8.6 | 1.9.8.6 |  | 309 | p | 463 | -150% | 772
1102 | 4253 | hnujWIe1JDNg9VHs3TWw | Normal | 1 | 1.9.8.8 | 1.9.8.8 |  | 264 | p | 16 | -6% | 280
1103 | 4255 | TAfq40Sin0H6Q2YT0OS5 | Milestone | 0 | 1.9.8.3 | 1.9.8.3 |  | 532 | p | 153 | -29% | 685
1104 | 4256 | G2pYfP7dsnHVTgqQD6mD | Summary | 82 | 1.9.8.10 | 1.9.8.10 |  | 151 | p | 538 | -356% | 689
1105 | 4258 | GzQkXlTiYJMdE6nBDVeb | Normal | 6 | 1.9.8.10.1 | 1.9.8.10.1 |  | 151 | p | 538 | -356% | 689
1106 | 6090 | LkexiRQNUDyJAwm8EPYV | Normal | 32 | 1.9.8.10.7 | 1.9.8.10.7 |  | 151 | p | 538 | -356% | 689
1107 | 6187 | kIPGiItVAbHq2ks8DK41 | Normal | 5 | 1.9.8.10.6 | 1.9.8.10.6 |  | 151 | p | 538 | -356% | 689
1108 | 6430 | IYyY3jK4t9QuDyuxqyQ5 | Normal | 15 | 1.9.8.10.2 | 1.9.8.10.2 |  | 151 | p | 538 | -356% | 689
1109 | 6431 | mXx66gQ5BZWpD3idmZgM | Normal | 10 | 1.9.8.10.3 | 1.9.8.10.3 |  | 151 | p | 538 | -356% | 689
1110 | 6432 | vMoeJo3Rc30lMwFim6rn | Normal | 10 | 1.9.8.10.4 | 1.9.8.10.4 |  | 151 | p | 538 | -356% | 689
1111 | 6433 | zONKYXhH5yZJE26xvIWD | Normal | 4 | 1.9.8.10.5 | 1.9.8.10.5 |  | 151 | p | 538 | -356% | 689
1112 | 6083 | 3dsblDK1X9ztc27EZU3v | Normal | 1 | 1.9.8.5 | 1.9.8.5 |  | 625 | q | -503 | (-80%) | 122
1113 | 6084 | deZM0xh115wln716GUoI | Normal | 1 | 1.9.8.9 | 1.9.8.9 |  | 514 | q | -514 | (-100%) | 0
1114 | 7321 | CTokiQfH6gyOyeZJGrxP | Normal | 1 | 1.7.9.11 | 1.7.9.11 |  | 313 | p | 459 | -147% | 772
1115 | 6314 | PaZTrKFuMaJQzXHDclW5 | Summary | 34 | 1.9.2 | 1.9.2 |  | 712 | p | 129 | -18% | 841
1116 | 5666 | lc2LPCzbTjVw9vZ8eS89 | Summary | 23 | 1.9.2.2 | 1.9.2.2 |  | 712 | p | 129 | -18% | 841
1117 | 5667 | chBvra0KGhqU3lfHBAI4 | Summary | 23 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 712 | p | 129 | -18% | 841
1118 | 5669 | bBSx7g3AuM8uxZcIYlIi | Normal | 20 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 712 | p | 129 | -18% | 841
1119 | 5672 | 2GDxhVAL0LbO4lfSMjXo | Summary | 47 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 712 | p | 129 | -18% | 841
1120 | 5690 | jLB7gq1wR8egZrMIoAc7 | Summary | 24 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 712 | p | 129 | -18% | 841
1121 | 5691 | glUuWw43f2R9t2hl6VHO | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 712 | p | 129 | -18% | 841
1122 | 5692 | KeXnvnZRx0KMyut3yw5s | Milestone | 0 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 712 | p | 129 | -18% | 841
1123 | 5693 | VdKRFLdSc60knizSqFXc | Normal | 14 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 712 | p | 129 | -18% | 841
1124 | 5694 | Gb0taOZcQ8l0cdHliY6j | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 712 | p | 129 | -18% | 841
1125 | 5695 | ePp2idADlztrdEpItyCc | Milestone | 0 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 712 | p | 129 | -18% | 841
1126 | 5696 | npE0RnxADwI7cDPG1fDa | Normal | 4 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 712 | p | 129 | -18% | 841
1127 | 5697 | 4nIBzBv3LSP60HeOLv0f | Normal | 5 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 712 | p | 129 | -18% | 841
1128 | 6315 | 2iW64uJmzViIcLEo0dMn | Summary | 181 | 1.9.5 | 1.9.5 |  | 538 | q | -514 | (-96%) | 24
1129 | 5532 | NHN4dwEEPEqCDqA4Rwlr | Summary | 74 | 1.9.5.1 | 1.9.5.1 |  | 638 | p | 105 | -16% | 743
1130 | 5533 | g1oQNBzKk6OrBukgGH7R | Normal | 40 | 1.9.5.1.3 | 1.9.5.1.3 |  | 570 | q | -570 | (-100%) | 0
1131 | 5535 | XVk7S0ldLHQUWflKhMBn | Normal | 11 | 1.9.5.1.2 | 1.9.5.1.2 |  | 682 | p | 126 | -18% | 808
1132 | 5536 | cYU0DBZylLxVRoLEp7Bc | Normal | 40 | 1.9.5.1.4 | 1.9.5.1.4 |  | 550 | p | 113 | -21% | 663
1133 | 5537 | 9xVQhmyTVkChMoMOy91g | Summary | 193 | 1.9.5.2 | 1.9.5.2 |  | 538 | q | -514 | (-96%) | 24
1134 | 5539 | kRsO3PSMDsMxji3dmdNc | Normal | 5 | 1.9.5.2.2 | 1.9.5.2.2 |  | 215 | q | -651 | (-303%) | -436
1135 | 5540 | GKx3XnA1BSbhTsgdKbqP | Normal | 14 | 1.9.5.2.8 | 1.9.5.2.8 |  | 284 | q | -28 | (-10%) | 256
1136 | 5541 | LhqIvyBzzdwllIHwrPz2 | Normal | 5 | 1.9.5.2.7 | 1.9.5.2.7 |  | 207 | q | -26 | (-13%) | 181
1137 | 5542 | 4ivItsonCrTGke19i41Z | Normal | 15 | 1.9.5.2.6 | 1.9.5.2.6 |  | 203 | q | -26 | (-13%) | 177
1138 | 5543 | XaHBDo6QUBfyTg5ESk7j | Normal | 15 | 1.9.5.2.9 | 1.9.5.2.9 |  | 289 | q | -29 | (-10%) | 260
1139 | 5544 | cIc3ARzcdrbXv6maHllr | Summary | 129 | 1.9.5.2.13 | 1.9.5.2.13 |  | 538 | q | -514 | (-96%) | 24
1140 | 5545 | 7UVU8IboY6NG7sqZCrUC | Normal | 7 | 1.9.5.2.13.2 | 1.9.5.2.13.2 |  | 514 | q | -514 | (-100%) | 0
1141 | 5546 | Shs5wuYOFSkTF1YslX8w | Normal | 6 | 1.9.5.2.13.5 | 1.9.5.2.13.5 |  | 515 | q | -513 | (-100%) | 2
1142 | 5547 | KglXvc5QwlHEboIvY96Q | Normal | 4 | 1.9.5.2.13.8 | 1.9.5.2.13.8 |  | 515 | q | -513 | (-100%) | 2
1143 | 5548 | Zfzda0CfmpiN8ZL93G3t | Normal | 5 | 1.9.5.2.13.9 | 1.9.5.2.13.9 |  | 515 | q | -513 | (-100%) | 2
1144 | 5549 | PgYJem7PJFdGgV04ojeL | Normal | 1 | 1.4.17 | 1.4.17 |  | 515 | q | -513 | (-100%) | 2
1145 | 5556 | fOMVaiOa0jnHOJyDUdVQ | Normal | 25 | 1.9.5.2.13.11 | 1.9.5.2.13.11 |  | 538 | q | -514 | (-96%) | 24
1146 | 5730 | ypyrsmMFJqJ9aPla6UhQ | Normal | 4 | 1.9.5.2.13.3 | 1.9.5.2.13.3 |  | 514 | q | -514 | (-100%) | 0
1147 | 5731 | uQF6Ff0bc2cqy3b37ZQc | Normal | 1 | 1.9.5.2.13.4 | 1.9.5.2.13.4 |  | 514 | q | -514 | (-100%) | 0
1148 | 5732 | OQKwpwUgImWCC2Fp5G0Q | Normal | 7 | 1.9.5.2.13.6 | 1.9.5.2.13.6 |  | 515 | q | -513 | (-100%) | 2
1149 | 5733 | wyOxVAS94HubPKo2yHJm | Normal | 7 | 1.9.5.2.13.7 | 1.9.5.2.13.7 |  | 515 | q | -513 | (-100%) | 2
1150 | 7000 | yP1oDcnUQTy3g68ZLgu0 | Normal | 8 | 1.9.5.2.13.1 | 1.9.5.2.13.1 |  | 552 | p | 122 | -22% | 674
1151 | 5557 | U376LwOjKfNZoVLUlmMD | Summary | 113 | 1.9.5.2.12 | 1.9.5.2.12 |  | 538 | q | -514 | (-96%) | 24
1152 | 5558 | RXAxJx3BHWNVdWFPfZ2a | Normal | 13 | 1.9.5.2.12.2 | 1.9.5.2.12.2 |  | 514 | q | -514 | (-100%) | 0
1153 | 5559 | jJoy8dUJMWD3ZuNw52D0 | Normal | 8 | 1.9.5.2.12.5 | 1.9.5.2.12.5 |  | 516 | q | -512 | (-99%) | 4
1154 | 5560 | wu3sL1wqoiodUr5mG52N | Normal | 4 | 1.9.5.2.12.8 | 1.9.5.2.12.8 |  | 516 | q | -512 | (-99%) | 4
1155 | 5561 | Vb2zzMF18WNANxlCzGiz | Normal | 5 | 1.9.5.2.12.9 | 1.9.5.2.12.9 |  | 516 | q | -512 | (-99%) | 4
1156 | 5562 | vp7j6GBYm2dAMLvxEFuE | Normal | 1 | 1.4.20 | 1.4.20 |  | 516 | q | -512 | (-99%) | 4
1157 | 5569 | 35aiC9HLOSrIl2OBwDvd | Normal | 25 | 1.9.5.2.12.11 | 1.9.5.2.12.11 |  | 538 | q | -514 | (-96%) | 24
1158 | 5734 | iq9bjqBZvH9Bj6912271 | Normal | 6 | 1.9.5.2.12.3 | 1.9.5.2.12.3 |  | 514 | q | -514 | (-100%) | 0
1159 | 5735 | Z8zFgfwvHK2hwW2AW8Qa | Normal | 1 | 1.9.5.2.12.4 | 1.9.5.2.12.4 |  | 514 | q | -514 | (-100%) | 0
1160 | 5736 | QgUmTWGvxjzq3xqrWPJK | Normal | 7 | 1.9.5.2.12.6 | 1.9.5.2.12.6 |  | 516 | q | -512 | (-99%) | 4
1161 | 5737 | iDzIA8f8DQgg2wVNkaUu | Normal | 7 | 1.9.5.2.12.7 | 1.9.5.2.12.7 |  | 516 | q | -512 | (-99%) | 4
1162 | 7001 | WpRQh8HvPfyDha8FH5FR | Normal | 9 | 1.9.5.2.12.1 | 1.9.5.2.12.1 |  | 540 | p | 117 | -22% | 657
1163 | 5570 | MuDwSgsBJjDxwFkSMWYJ | Summary | 116 | 1.9.5.2.11 | 1.9.5.2.11 |  | 548 | q | -503 | (-92%) | 45
1164 | 5571 | lfRAbO0c5jl7NaC6s7pm | Normal | 21 | 1.9.5.2.11.2 | 1.9.5.2.11.2 |  | 514 | q | -514 | (-100%) | 0
1165 | 5572 | jk3Vm36iIGViuk9dpLfQ | Normal | 8 | 1.9.5.2.11.5 | 1.9.5.2.11.5 |  | 514 | q | -506 | (-98%) | 8
1166 | 5573 | u3MfiduPa05JsS2ly7WD | Normal | 4 | 1.9.5.2.11.8 | 1.9.5.2.11.8 |  | 514 | q | -506 | (-98%) | 8
1167 | 5574 | 3iKE3riinMPRUpVpTfwx | Normal | 5 | 1.9.5.2.11.9 | 1.9.5.2.11.9 |  | 516 | q | -505 | (-98%) | 11
1168 | 5575 | 48yotl4pDzxbk5y0VDbK | Normal | 1 | 1.4.23 | 1.4.23 |  | 516 | q | -505 | (-98%) | 11
1169 | 5582 | 6tLu8emqwotxTkeBbEpy | Normal | 26 | 1.9.5.2.11.11 | 1.9.5.2.11.11 |  | 548 | q | -503 | (-92%) | 45
1170 | 5738 | ME2oX9BwgLu5cggaunhg | Normal | 5 | 1.9.5.2.11.3 | 1.9.5.2.11.3 |  | 514 | q | -514 | (-100%) | 0
1171 | 5739 | IivOSmNLtmlF9JKFLUrl | Normal | 1 | 1.9.5.2.11.4 | 1.9.5.2.11.4 |  | 514 | q | -514 | (-100%) | 0
1172 | 5740 | eRxCjL3dV2CpHvAG84r7 | Normal | 12 | 1.9.5.2.11.6 | 1.9.5.2.11.6 |  | 514 | q | -506 | (-98%) | 8
1173 | 5741 | 8Y4jq7dOt4lN4NYBT6r1 | Normal | 12 | 1.9.5.2.11.7 | 1.9.5.2.11.7 |  | 514 | q | -506 | (-98%) | 8
1174 | 6998 | CyWehBzIvIWKBi1qju4z | Normal | 15 | 1.9.5.2.11.1 | 1.9.5.2.11.1 |  | 522 | p | 117 | -22% | 639
1175 | 5583 | gkFBoXdv1oJb2jtBcO5M | Summary | 147 | 1.9.5.2.14 | 1.9.5.2.14 |  | 538 | q | -514 | (-96%) | 24
1176 | 5584 | 6WMzJdzS7tY0wFFuXnrc | Normal | 7 | 1.9.5.2.14.2 | 1.9.5.2.14.2 |  | 514 | q | -514 | (-100%) | 0
1177 | 5585 | KljMWvDEBGSuBTW4zQhZ | Normal | 7 | 1.9.5.2.14.5 | 1.9.5.2.14.5 |  | 514 | q | -514 | (-100%) | 0
1178 | 5586 | Z3ZWpIsgJCSKUX161hV0 | Normal | 4 | 1.9.5.2.14.8 | 1.9.5.2.14.8 |  | 514 | q | -514 | (-100%) | 0
1179 | 5587 | OXOUsYDejGVlgqn4Z1vl | Normal | 5 | 1.9.5.2.14.9 | 1.9.5.2.14.9 |  | 514 | q | -514 | (-100%) | 0
1180 | 5588 | MFjHKzinVVI0Ndx8qx0B | Normal | 1 | 1.4.26 | 1.4.26 |  | 514 | q | -514 | (-100%) | 0
1181 | 5595 | REFTk0AP9RBTibJWVhuH | Normal | 26 | 1.9.5.2.14.11 | 1.9.5.2.14.11 |  | 538 | q | -514 | (-96%) | 24
1182 | 5742 | 88bEv4EMiOL2y8w1ttIM | Normal | 4 | 1.9.5.2.14.3 | 1.9.5.2.14.3 |  | 514 | q | -514 | (-100%) | 0
1183 | 5743 | 0Uz4krHDVCdAlMd5aRwh | Normal | 1 | 1.9.5.2.14.4 | 1.9.5.2.14.4 |  | 514 | q | -514 | (-100%) | 0
1184 | 5744 | cSBfnbrbVLLFYTMEfBKA | Normal | 6 | 1.9.5.2.14.6 | 1.9.5.2.14.6 |  | 514 | q | -514 | (-100%) | 0
1185 | 5745 | ZY99Y6JX4jBylnfeedvo | Normal | 6 | 1.9.5.2.14.7 | 1.9.5.2.14.7 |  | 514 | q | -514 | (-100%) | 0
1186 | 6999 | AnycnugTW971av3hMZXE | Normal | 8 | 1.9.5.2.14.1 | 1.9.5.2.14.1 |  | 556 | p | 121 | -22% | 677
1187 | 6446 | XvbStahAymwCoqNIbMJG | Summary | 32 | 1.9.5.2.4 | 1.9.5.2.4 |  | 526 | p | 396 | -75% | 922
1188 | 6532 | 15e7xcLR1b1jSikaz0S2 | Normal | 32 | 1.9.5.2.4.2 | 1.9.5.2.4.2 |  | 548 | p | 398 | -73% | 946
1189 | 6533 | b0mutjzKj8FRw4zkbb8K | Normal | 32 | 1.9.5.2.4.1 | 1.9.5.2.4.1 |  | 526 | p | 396 | -75% | 922
1190 | 6534 | 8Gl2bk4Fxxo2fsClDJqG | Normal | 32 | 1.9.5.2.4.3 | 1.9.5.2.4.3 |  | 558 | p | 396 | -71% | 954
1191 | 6535 | dWze9AnK8NrEMD9LOEyU | Normal | 32 | 1.9.5.2.4.4 | 1.9.5.2.4.4 |  | 570 | p | 396 | -69% | 966
1192 | 6528 | LROLnQke0gWnMONa67YB | Summary | 50 | 1.9.5.2.5 | 1.9.5.2.5 |  | 524 | p | 117 | -22% | 641
1193 | 6531 | iX155TL3hNg9Ca4Bsb4A | Normal | 35 | 1.9.5.2.5.2 | 1.9.5.2.5.2 |  | 524 | p | 117 | -22% | 641
1194 | 6955 | CPACk87DS0kpO7pXcdwS | Normal | 10 | 1.9.5.2.10 | 1.9.5.2.10 |  | 215 | q | -651 | (-303%) | -436
1195 | 6997 | MBGoTUikAECGvIHYk1uV | Normal | 24 | 1.9.5.2.3 | 1.9.5.2.3 |  | 514 | q | -514 | (-100%) | 0
1196 | 5596 | upn4QoZvaKBmBMoyhnq5 | Summary | 90 | 1.9.5.3 | 1.9.5.3 |  | 538 | q | -514 | (-96%) | 24
1197 | 5597 | zKJsJYNcPRFZ7wBjvprv | Normal | 18 | 1.9.5.3.1 | 1.9.5.3.1 |  | 558 | q | -510 | (-91%) | 48
1198 | 5598 | zvvzNQqIPXzcVRwy0N44 | Summary | 52 | 1.9.5.3.2 | 1.9.5.3.2 |  | 538 | q | -514 | (-96%) | 24
1199 | 5599 | T0Oh47cWIVU9y2MKPB0U | Normal | 12 | 1.9.5.3.2.1 | 1.9.5.3.2.1 |  | 542 | q | -511 | (-94%) | 31
1200 | 5600 | oTkX6bjokLXQ590hdeFy | Normal | 12 | 1.9.5.3.2.2 | 1.9.5.3.2.2 |  | 542 | q | -511 | (-94%) | 31
1201 | 5601 | xa7cRxeKgQxZnuHNAYMQ | Normal | 12 | 1.9.5.3.2.3 | 1.9.5.3.2.3 |  | 538 | q | -514 | (-96%) | 24
1202 | 5602 | QlxDegibloFbHrPNJwyW | Normal | 12 | 1.9.5.3.2.4 | 1.9.5.3.2.4 |  | 538 | q | -514 | (-96%) | 24
1203 | 5603 | dwMYG7lg76TqxtTxZNCR | Normal | 5 | 1.9.5.3.3 | 1.9.5.3.3 |  | 538 | q | -514 | (-96%) | 24
1204 | 6189 | OaskfHPb0rGXxqxmUlvr | Summary | 69 | 1.7.2.7 | 1.7.2.7 |  | 336 | q | -29 | (-9%) | 307
1205 | 6248 | DGpV8AP7Q4dyYuiDaoIl | Summary | 56 | 1.7.2.7.2 | 1.7.2.7.2 |  | 336 | q | -29 | (-9%) | 307
1206 | 6251 | Ha7ZmVRhPp4EjAGEFQOQ | Normal | 56 | 1.7.2.7.2.3 | 1.7.2.7.2.3 |  | 336 | q | -29 | (-9%) | 307
1207 | 6252 | FwTW8u2nmxBgH6wyvtoz | Summary | 56 | 1.7.2.7.3 | 1.7.2.7.3 |  | 336 | q | -21 | (-6%) | 315
1208 | 6255 | 6Rcxv4eHz2WhxfD2wxtd | Normal | 56 | 1.7.2.7.3.3 | 1.7.2.7.3.3 |  | 336 | q | -21 | (-6%) | 315
1209 | 6256 | TcRehVKUpIeirJTvWiO5 | Summary | 14 | 1.7.2.7.4 | 1.7.2.7.4 |  | 378 | q | -21 | (-6%) | 357
1210 | 6259 | q6ww59eaDtL5Df1J4lsR | Normal | 14 | 1.7.2.7.4.3 | 1.7.2.7.4.3 |  | 378 | q | -21 | (-6%) | 357
1211 | 6260 | nYwGXpoj6WqcdUPfZoTk | Summary | 14 | 1.7.2.7.5 | 1.7.2.7.5 |  | 378 | q | -23 | (-6%) | 355
1212 | 6263 | aKytB1b2oD2t1WVaznUP | Normal | 14 | 1.7.2.7.5.3 | 1.7.2.7.5.3 |  | 378 | q | -23 | (-6%) | 355
1213 | 6317 | NzqiT3qChWGoVO5Oxj9C | Summary | 111 | 1.9.4 | 1.9.4 |  | 776 | q | -298 | (-38%) | 478
1214 | 5355 | lohINUHwZqjP23W1PYQO | Summary | 26 | 1.9.4.1 | 1.9.4.1 |  | 650 | p | 147 | -23% | 797
1215 | 5358 | Tenn83cNUrlWZNLgXJG2 | Normal | 2 | 1.9.4.1.2 | 1.9.4.1.2 |  | 690 | q | -690 | (-100%) | 0
1216 | 5359 | VhUQP0fhGYyFZ67e4nln | Normal | 2 | 1.9.4.1.3 | 1.9.4.1.3 |  | 650 | q | -650 | (-100%) | 0
1217 | 5360 | ARncD9Nx3De5DONPy9Bs | Normal | 3 | 1.9.4.1.4 | 1.9.4.1.4 |  | 650 | p | 147 | -23% | 797
1218 | 7262 | dH18W6KApKWC8TAOWb50 | Normal | 36 | 1.7.4.1.4 | 1.7.4.1.4 |  | 650 | q | -650 | (-100%) | 0
1219 | 7263 | mjGxmWsUF3dJi6MlhQpM | Normal | 1 | 1.7.4.1.5 | 1.7.4.1.5 |  | 650 | p | 147 | -23% | 797
1220 | 5362 | 4bsxfawvV6TKTvCq9VoB | Summary | 6 | 1.9.4.2 | 1.9.4.2 |  | 684 | q | -194 | (-28%) | 490
1221 | 5368 | NKJL1ZJN3KgUArkbA4qS | Normal | 3 | 1.9.4.2.4 | 1.9.4.2.4 |  | 684 | q | -194 | (-28%) | 490
1222 | 7260 | DPsh83rHAyIaiD8XYnO0 | Normal | 6 | 1.7.4.2.4 | 1.7.4.2.4 |  | 684 | q | -194 | (-28%) | 490
1223 | 7261 | isfym7y8CMuc9Vq3Mbcl | Normal | 1 | 1.7.4.2.5 | 1.7.4.2.5 |  | 684 | q | -194 | (-28%) | 490
1224 | 5375 | zkXPpJkHw8DPAtspwcmA | Summary | 124 | 1.9.4.4 | 1.9.4.4 |  | 650 | q | -172 | (-26%) | 478
1225 | 5376 | zSTdFwWI5FOaluV37lYS | Normal | 63 | 1.9.4.4.1 | 1.9.4.4.1 |  | 650 | q | -172 | (-26%) | 478
1226 | 5377 | Wv5w7NMYDRM71nE6dVi0 | Summary | 58 | 1.9.4.5 | 1.9.4.5 |  | 844 | q | -102 | (-12%) | 742
1227 | 5379 | 7aIIakNe0KPRF0TCK1un | Normal | 2 | 1.9.4.5.2 | 1.9.4.5.2 |  | 926 | q | -926 | (-100%) | 0
1228 | 5381 | HgkAkSCruVdxdZyXC7sW | Normal | 4 | 1.9.4.5.4 | 1.9.4.5.4 |  | 602 | q | -602 | (-100%) | 0
1229 | 5382 | VlX4WunUzdS7Nqvh5ftn | Normal | 20 | 1.9.4.5.5 | 1.9.4.5.5 |  | 602 | p | 140 | -23% | 742
1230 | 5383 | u1aficyBQ2O9A8MnpdfZ | Normal | 20 | 1.9.4.5.6 | 1.9.4.5.6 |  | 602 | p | 140 | -23% | 742
1231 | 5384 | d8i6C63YfOF3EovUl19W | Normal | 10 | 1.9.4.5.7 | 1.9.4.5.7 |  | 602 | p | 140 | -23% | 742
1232 | 5385 | ohwsmv9qOoV0RNzIdjJI | Normal | 15 | 1.9.4.5.8 | 1.9.4.5.8 |  | 602 | p | 140 | -23% | 742
1233 | 5386 | tSuemAovBYAaHNhFiwaF | Normal | 15 | 1.9.4.5.9 | 1.9.4.5.9 |  | 602 | p | 140 | -23% | 742
1234 | 5387 | 9gTKo9vjb1rQAbWcTOOW | Summary | 58 | 1.9.4.6 | 1.9.4.6 |  | 844 | q | -94 | (-11%) | 750
1235 | 5389 | 0FrUudkzBjpolAMz4tT0 | Normal | 2 | 1.9.4.6.2 | 1.9.4.6.2 |  | 926 | q | -926 | (-100%) | 0
1236 | 5391 | rUGJjnqPCImSizDtYOdy | Normal | 4 | 1.9.4.6.4 | 1.9.4.6.4 |  | 602 | q | -602 | (-100%) | 0
1237 | 5392 | TRJmldmXNRf3NwsZhgng | Normal | 20 | 1.9.4.6.5 | 1.9.4.6.5 |  | 602 | p | 148 | -25% | 750
1238 | 5393 | 3qvg7di25vdBD8UUvM1a | Normal | 20 | 1.9.4.6.6 | 1.9.4.6.6 |  | 602 | p | 148 | -25% | 750
1239 | 5394 | ungpeNo64cspVo3BuO9g | Normal | 10 | 1.9.4.6.7 | 1.9.4.6.7 |  | 602 | p | 148 | -25% | 750
1240 | 5395 | KZXvYFda88KgX9w7a3ES | Normal | 15 | 1.9.4.6.8 | 1.9.4.6.8 |  | 602 | p | 148 | -25% | 750
1241 | 5396 | FNjsTUKVT29tBcVlvaM6 | Normal | 15 | 1.9.4.6.9 | 1.9.4.6.9 |  | 602 | p | 148 | -25% | 750
1242 | 5397 | KGrMeH5y6HH9dj1tr8uB | Summary | 53 | 1.9.4.7 | 1.9.4.7 |  | 602 | p | 140 | -23% | 742
1243 | 5398 | EMMfZLgDhvN5O0lAfznQ | Normal | 15 | 1.9.4.7.1 | 1.9.4.7.1 |  | 602 | p | 140 | -23% | 742
1244 | 5399 | 5K7jeUOrZ3wka9S2O1Dn | Normal | 15 | 1.9.4.7.2 | 1.9.4.7.2 |  | 602 | p | 140 | -23% | 742
1245 | 5400 | I2IZFfCcy2hUSTtihPWq | Normal | 15 | 1.9.4.7.3 | 1.9.4.7.3 |  | 602 | p | 140 | -23% | 742
1246 | 5401 | WWZjxA63YxH38hnYmVKG | Normal | 8 | 1.9.4.7.4 | 1.9.4.7.4 |  | 602 | p | 140 | -23% | 742
1247 | 5402 | zDUD70mdAG3rcozejCwk | Summary | 15 | 1.9.4.8 | 1.9.4.8 |  | 602 | q | -124 | (-21%) | 478
1248 | 5403 | wP2WbhW6upJb7JmdzCw1 | Normal | 9 | 1.9.4.8.1 | 1.9.4.8.1 |  | 602 | p | 140 | -23% | 742
1249 | 5404 | UrewlDJ3J2c8Ueci7p9E | Normal | 6 | 1.9.4.8.2 | 1.9.4.8.2 |  | 602 | q | -124 | (-21%) | 478
1250 | 7264 | vNqQNKJIEgg8BiBzdWeI | Summary | 57 | 1.7.4.3.6 | 1.7.4.3.6 |  | 650 | q | -160 | (-25%) | 490
1251 | 7265 | uNFJkQaxxZ7oOYaM8QxX | Normal | 13 | 1.7.4.3.6.1 | 1.7.4.3.6.1 |  | 650 | q | -160 | (-25%) | 490
1252 | 7266 | y7TR6NxR4uOKxinxsnEt | Normal | 13 | 1.7.4.3.6.2 | 1.7.4.3.6.2 |  | 650 | q | -160 | (-25%) | 490
1253 | 7267 | f0BUmD79ZhKqjjzrwXUq | Normal | 13 | 1.7.4.3.6.3 | 1.7.4.3.6.3 |  | 650 | q | -160 | (-25%) | 490
1254 | 7268 | sP1zO7OhzT9CUKqdzecJ | Normal | 12 | 1.7.4.3.6.4 | 1.7.4.3.6.4 |  | 650 | q | -160 | (-25%) | 490
1255 | 7269 | 7v5GPnNw6yREyKfoeMiZ | Normal | 5 | 1.7.4.3.6.5 | 1.7.4.3.6.5 |  | 650 | q | -160 | (-25%) | 490
1256 | 7322 | XsHCl5GkwKVP3xy7r0jT | Summary | 85 | 1.7.5 | 1.7.5 |  | 293 | p | 391 | -133% | 684
1257 | 7528 | 8SnF5zCB4rJyZyQZLLZc | Normal | 8 | 1.7.5.1 | 1.7.5.1 |  | 293 | p | 391 | -133% | 684
1258 | 7529 | ugdLGMeRoSNQZE98ehwR | Normal | 8 | 1.7.5.2 | 1.7.5.2 |  | 293 | p | 394 | -134% | 687
1259 | 7530 | tZgNvNsEFqNHmYVKXpMu | Normal | 7 | 1.7.5.3 | 1.7.5.3 |  | 293 | p | 391 | -133% | 684
1260 | 7531 | WsQS39Ko43y2ykuRUNnk | Normal | 8 | 1.7.5.4 | 1.7.5.4 |  | 293 | p | 391 | -133% | 684
1261 | 7532 | tNKjUDGuH9lZvW14y0xJ | Normal | 22 | 1.7.5.5 | 1.7.5.5 |  | 293 | p | 391 | -133% | 684
1262 | 7533 | HKUUjAeDBFLcgj42uw3c | Normal | 19 | 1.7.5.6 | 1.7.5.6 |  | 293 | p | 391 | -133% | 684
1263 | 7534 | s7VTtgJqjYjf9pbLYcYj | Normal | 8 | 1.7.5.7 | 1.7.5.7 |  | 293 | p | 391 | -133% | 684
1264 | 7535 | uGgP1gHCy12zlVFcLeTG | Normal | 6 | 1.7.5.8 | 1.7.5.8 |  | 293 | p | 391 | -133% | 684
1265 | 7536 | kbIucnV7qsI0ZjxbK1cH | Normal | 6 | 1.7.5.9 | 1.7.5.9 |  | 293 | p | 391 | -133% | 684
1266 | 7537 | ZiOXL4e3BgetRuJ4aYKK | Normal | 1 | 1.7.5.10 | 1.7.5.10 |  | 293 | p | 391 | -133% | 684
1267 | 6688 | aKOlgm9Tw9oPXF0YCFLp | Summary | 911 | 1.11 | 1.11 |  | 1 | p | 566 | -56600% | 567
1268 | 6689 | fEYxMDiPOAwjjU8zha5c | Normal | 396 | 1.11.1 | 1.11.1 |  | 532 | p | 227 | -43% | 759
1269 | 6690 | bopLkaAZbmZjIM9EGI6L | Normal | 532 | 1.11.2 | 1.11.2 |  | 1 | p | 859 | -85900% | 860
1270 | 6691 | xLErpFHjPEH3ifHRbBMY | Normal | 396 | 1.11.3 | 1.11.3 |  | 532 | p | 35 | -7% | 567
1271 | 6692 | g8WcEZ6I6SGdlePHrYPP | Normal | 248 | 1.11.4 | 1.11.4 |  | 636 | p | 106 | -17% | 742
1272 | 6695 | Bx0BPJ0BcPw49QEL7Psq | Normal | 313 | 1.11.8 | 1.11.8 |  | 614 | p | 193 | -31% | 807
1273 | 6696 | XbFIp383UbA72xJPH4hJ | Normal | 101 | 1.11.9 | 1.11.9 |  | 783 | p | 131 | -17% | 914
1274 | 6697 | gpkN7vTMpz4ZZxhDAmeL | Normal | 126 | 1.11.10 | 1.11.10 |  | 758 | p | 129 | -17% | 887
1275 | 6698 | eRsel9yyFaDkcYLZgvjC | Normal | 142 | 1.11.11 | 1.11.11 |  | 785 | p | 116 | -15% | 901
1276 | 6699 | k8943lu4TS9ZW2TcUvha | Normal | 256 | 1.11.12 | 1.11.12 |  | 672 | p | 92 | -14% | 764
1277 | 7376 | FfEUU5kpALOu6FlmjosD | Normal | 396 | 1.10.3 | 1.10.3 |  | 532 | p | 103 | -19% | 635
1278 | 7378 | YjoFZZooPnFRzsk2Ba2E | Normal | 288 | 1.10.6 | 1.10.6 |  | 639 | p | 50 | -8% | 689
1279 | 7379 | 7GajZBAFakrGWC1WlgE6 | Normal | 142 | 1.10.14 | 1.10.14 |  | 785 | p | 162 | -21% | 947
1280 | 7380 | wkyoOF6gHS9pA0Dm9pZY | Normal | 140 | 1.10.17 | 1.10.17 |  | 787 | p | 145 | -18% | 932
1281 | 7551 | G4afE8kOleATkD8qyqeP | Normal | 1 | 1.10.19 | 1.10.19 |  | 2873 | q | -2873 | (-100%) | 0
1282 | 7131 | XTX9Wl5SzTxAD1rtsh9U | Summary | 0 | 1.10 | 1.10 |  | 454 | q | -209 | (-46%) | 245
1283 | 156 | 0RXSkgYJdrs7AeQvgU3w | Milestone | 0 | 1.10.24 | 1.10.24 |  | -26 | q | -410 | -1577% | -436
1284 | 157 | DYCfhHgWVvjY4WPSrw6q | Milestone | 0 | 1.10.25 | 1.10.25 |  | -26 | q | -410 | -1577% | -436
1285 | 7107 | fjlRoMsMUGjOnNWoUkGJ | Milestone | 0 | 1.10.16 | 1.10.16 |  | 454 | p | 143 | -31% | 597
1286 | 7108 | wFwSqsIrP0eolc7owrIn | Milestone | 0 | 1.10.3 | 1.10.3 |  | 349 | p | 4 | -1% | 353
1287 | 7110 | fycPVr34q6lr2y2bEJNl | Milestone | 0 | 1.10.9 | 1.10.9 |  | 269 | q | -25 | (-9%) | 244
1288 | 7111 | gs1r9nT3BBBdW42nHT47 | Milestone | 0 | 1.10.13 | 1.10.13 |  | 219 | q | -20 | (-9%) | 199
1289 | 7112 | a270fhhuENq55tFKO8IB | Milestone | 0 | 1.10.10 | 1.10.10 |  | 190 | q | -15 | (-8%) | 175
1290 | 7114 | pZqvbi91bBhqyjB86evl | Milestone | 0 | 1.10.2 | 1.10.2 |  | 124 | q | -14 | (-11%) | 110
1291 | 7115 | mxRJVREYCLlOZtWGohdT | Milestone | 0 | 1.10.8 | 1.10.8 |  | 104 | q | -5 | (-5%) | 99
1292 | 7116 | 4gFjRlWXKNF16b9sFMXr | Milestone | 0 | 1.10.11 | 1.10.11 |  | 234 | p | 118 | -50% | 352
1293 | 7117 | zFlqKdf38AVahGy9Q9X8 | Milestone | 0 | 1.10.12 | 1.10.12 |  | 159 | p | 6 | -4% | 165
1294 | 7118 | 6jNHf85fMsjQD6qn9QnY | Milestone | 0 | 1.10.14 | 1.10.14 |  | 179 | q | -17 | (-9%) | 162
1295 | 7119 | OQnmDeJwrgb4ibYKrZjo | Milestone | 0 | 1.10.15 | 1.10.15 |  | 229 | p | 406 | -177% | 635
1296 | 7120 | ewfCDE69jjk4Zb5M5CES | Milestone | 0 | 1.10.4 | 1.10.4 |  | 355 | p | 4 | -1% | 359
1297 | 7121 | V4W6CQQo6lTjRlhYdPDq | Milestone | 0 | 1.10.5 | 1.10.5 |  | 322 | q | -22 | (-7%) | 300
1298 | 7122 | ZQwX0qpiGy3bERfpXjQ0 | Milestone | 0 | 1.10.6 | 1.10.6 |  | 352 | q | -19 | (-5%) | 333
1299 | 7123 | 0fpNMQTy9Zfk1YAC7GK2 | Milestone | 0 | 1.10.7 | 1.10.7 |  | 356 | p | 5 | -1% | 361
1300 | 7124 | yYQOOagkBr46kWICPuG6 | Milestone | 0 | 1.10.17 | 1.10.17 |  | 243 | p | 1953 | -804% | 2196
1301 | 7125 | a4xeGKWGk9YyWLffVRQZ | Milestone | 0 | 1.10.18 | 1.10.18 |  | 224 | p | 1951 | -871% | 2175
1302 | 7126 | XIH51zzlt2AXqf8IkYxf | Milestone | 0 | 1.10.19 | 1.10.19 |  | 206 | p | 1951 | -947% | 2157
1303 | 7129 | kvNY0frGkARL99AbSHw0 | Milestone | 0 | 1.10.22 | 1.10.22 |  | 322 | q | -1 | 0% | 321

## Free-Float
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Free Float - 550 (26%) | Free Float - 550 (26%) | Free Float - 550 (26%) | Free Float - 550 (26%) | Free Float - 550 (26%) | Free Float - 550 (26%) | Free Float - 550 (26%) | Free Float - 550 (26%) | Free Float - 550 (26%) | Free Float - 550 (26%) | Free Float - 550 (26%) | Free Float - 550 (26%) | Free Float - 550 (26%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 158 | D5C8AUNeoI4YKF3PggKx | Summary | 255 | 1.2.7 | 1.2.7 |  | 510 | q | -292 | (-57%) | 218
2 | 155 | 1yu6CrDX9QU5hWE1UWMV | Milestone | 0 | 1.2.7.11 | 1.2.7.11 |  | 60 | q | -60 | (-100%) | 0
3 | 166 | KkWbk0R1FXz2L56lHFvV | Normal | 2 | 1.2.7.4 | 1.2.7.4 |  | 37 | q | -37 | (-100%) | 0
4 | 6636 | 3J1qFTgnrSSZVnoYdTv5 | Summary | 140 | 1.2.7.3 | 1.2.7.3 |  | 37 | p | 20 | -54% | 57
5 | 6673 | sIWmvaXMX3ZF9ctRNm7s | Normal | 34 | 1.2.7.3.3 | 1.2.7.3.3 |  | 31 | q | -10 | (-32%) | 21
6 | 6872 | SjyWialEYK436pEnV5Nr | Normal | 1 | 1.2.7.5 | 1.2.7.5 |  | 110 | q | -24 | (-22%) | 86
7 | 6874 | 1XFpbhK6U752FQe8voXZ | Normal | 1 | 1.2.7.6 | 1.2.7.6 |  | 12 | q | -12 | (-100%) | 0
8 | 6878 | VU7w4voCV7rMMsz4AnPW | Normal | 1 | 1.2.7.10 | 1.2.7.10 |  | 316 | p | 1 | 0% | 317
9 | 160 | gFTVv5U5XORyz5ZEYbdN | Summary | 703 | 1.2.8 | 1.2.8 |  | 19 | p | 1 | -5% | 20
10 | 168 | MT1CsCIMkhjJER6f3fjG | Milestone | 0 | 1.2.8.4 | 1.2.8.4 |  | 19 | p | 1 | -5% | 20
11 | 172 | EY5PMcgR4N5ReAIF6NHn | Summary | 582 | 1.2.9 | 1.2.9 |  | 158 | q | -22 | (-14%) | 136
12 | 173 | vJHK0TlIBzGpfYqdt8YI | Milestone | 0 | 1.2.9.4 | 1.2.9.4 |  | 158 | q | -22 | (-14%) | 136
13 | 177 | V4ys3lAm8KEbtjGqLAuR | Milestone | 0 | 1.2.9.2 | 1.2.9.2 |  | 4 | p | 1 | -25% | 5
14 | 178 | Cncpm0GACo0ppNIEy1Gp | Milestone | 0 | 1.2.9.3 | 1.2.9.3 |  | 54 | p | 2 | -4% | 56
15 | 179 | jSOjvYE1qiHOKdcV2ixu | Summary | 554 | 1.2.10 | 1.2.10 |  | 512 | p | 76 | -15% | 588
16 | 193 | nJh7oj8wCJYW8hyepdLI | Milestone | 0 | 1.2.10.12 | 1.2.10.12 |  | 140 | p | 50 | -36% | 190
17 | 7132 | osdxrWYmqQZxyGZXe9Pr | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 27 | p | 33 | -122% | 60
18 | 7546 | tdocr3pqURBYHZWcAyMG | Normal | 1 | 1.2.10.12 | 1.2.10.12 |  | 23 | p | 74 | -322% | 97
19 | 7547 | 2p5uMAQ0v8mT9pq4KeWp | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 34 | p | 66 | -194% | 100
20 | 7548 | TdNnLE8G4vf1vBjggzLw | Normal | 1 | 1.2.10.15 | 1.2.10.15 |  | 13 | q | -13 | (-100%) | 0
21 | 7549 | yUAt6Fi3Vichq9Ai1DSh | Normal | 1 | 1.2.10.13 | 1.2.10.13 |  | 11 | q | -11 | (-100%) | 0
22 | 195 | jWoM7YMyhsN7uWtVDNIl | Summary | 276 | 1.2.11 | 1.2.11 |  | 514 | q | -506 | (-98%) | 8
23 | 202 | mjF0YLun5LIdlxtu3zFl | Milestone | 0 | 1.2.11.5 | 1.2.11.5 |  | 160 | p | 644 | -402% | 804
24 | 209 | 0FNuAiL5ZzPZSZ3dZfoV | Milestone | 0 | 1.2.11.10 | 1.2.11.10 |  | 26 | q | -4 | (-15%) | 22
25 | 7015 | U0mup1noPd6mH1CxWGtr | Milestone | 0 | 1.2.5 | 1.2.5 |  | 454 | q | -454 | (-100%) | 0
26 | 7016 | pVOP21cemlwRUbhUeRME | Milestone | 0 | 1.2.4 | 1.2.4 |  | 450 | q | -232 | (-52%) | 218
27 | 4180 | LxVAz76PSOUu8y7B8sy3 | Summary | 218 | 1.3 | 1.3 |  | 188 | q | -12 | (-6%) | 176
28 | 384 | GE3w1SHplCQZN7aYDVw8 | Summary | 34 | 1.3.3 | 1.3.3 |  | 37 | p | 20 | -54% | 57
29 | 429 | Pbs0MxOqvHazWgB8fpDs | Summary | 41 | 1.3.3.2 | 1.3.3.2 |  | 37 | p | 20 | -54% | 57
30 | 437 | kEyeaq7ebxWRSvBqGkHC | Summary | 19 | 1.3.3.1 | 1.3.3.1 |  | 53 | p | 8 | -15% | 61
31 | 438 | QjVW4dYK4boDcUrG7MUx | Summary | 23 | 1.3.3.1.2 | 1.3.3.1.2 |  | 53 | p | 8 | -15% | 61
32 | 445 | cIIfBfMFMZUbJxswwNzj | Summary | 28 | 1.3.3.1.2.4 | 1.3.3.1.2.4 |  | 53 | p | 8 | -15% | 61
33 | 6438 | sSGfho0IWOHZYw1Z8jLl | Normal | 16 | 1.3.3.1.2.4.5 | 1.3.3.1.2.4.5 |  | 8 | q | -5 | (-62%) | 3
34 | 5768 | 9l9o7D6Il8vKVgGgZRMW | Summary | 197 | 1.3.3.4 | 1.3.3.4 |  | 37 | p | 20 | -54% | 57
35 | 6289 | NknbxY1EWobhbJ98SVRq | Summary | 270 | 1.3.2 | 1.3.2 |  | 188 | q | -12 | (-6%) | 176
36 | 3848 | g0gBmZeXCCPZTY4kkYs8 | Summary | 210 | 1.3.2.1 | 1.3.2.1 |  | 188 | q | -10 | (-5%) | 178
37 | 3849 | PKYN5IsyqbTocjyswPFM | Normal | 17 | 1.3.2.1.1 | 1.3.2.1.1 |  | 8 | q | -8 | (-100%) | 0
38 | 3850 | sk2pEdmn2KeVBRyrQzgn | Summary | 233 | 1.3.2.1.2 | 1.3.2.1.2 |  | 188 | q | -10 | (-5%) | 178
39 | 3857 | FObPKa3HJ5KI4gFmAx2r | Summary | 210 | 1.3.2.1.2.2 | 1.3.2.1.2.2 |  | 207 | q | -29 | (-14%) | 178
40 | 3859 | xrpLG6wlwOL4sRwHPU5B | Normal | 28 | 1.3.2.1.2.2.2 | 1.3.2.1.2.2.2 |  | 13 | q | -7 | (-54%) | 6
41 | 3862 | FUtleP4nAJHYxzLOWKZH | Normal | 20 | 1.3.2.1.2.2.4 | 1.3.2.1.2.2.4 |  | 207 | q | -29 | (-14%) | 178
42 | 3863 | WaF24jcpD2qzV3M05hSl | Summary | 178 | 1.3.2.1.2.3 | 1.3.2.1.2.3 |  | 188 | q | -9 | (-5%) | 179
43 | 3864 | kkmwKYrSq6DehQmbGkxo | Summary | 90 | 1.3.2.1.2.3.2 | 1.3.2.1.2.3.2 |  | 188 | q | -9 | (-5%) | 179
44 | 3869 | wbVbYxDNomEEsv0XDKnQ | Normal | 5 | 1.3.2.1.2.3.2.7 | 1.3.2.1.2.3.2.7 |  | 188 | q | -9 | (-5%) | 179
45 | 7186 | ttl1FahPn0WwOuyGdmk6 | Summary | 138 | 1.3.2.3 | 1.3.2.3 |  | 181 | q | -16 | (-9%) | 165
46 | 7188 | yn5QOVI2BZ7jor10JaQN | Summary | 55 | 1.3.2.3.2 | 1.3.2.3.2 |  | 106 | p | 32 | -30% | 138
47 | 7189 | jup7puBG1dNvbV8jB14f | Summary | 69 | 1.3.2.3.2.1 | 1.3.2.3.2.1 |  | 94 | p | 42 | -45% | 136
48 | 7190 | Ob13piboJI4zFNOVPzZD | Summary | 50 | 1.3.2.3.2.1.1 | 1.3.2.3.2.1.1 |  | 94 | p | 54 | -57% | 148
49 | 7193 | hzdeRXxytBFeNJPq5eHn | Summary | 50 | 1.3.2.3.2.1.2 | 1.3.2.3.2.1.2 |  | 94 | p | 54 | -57% | 148
50 | 7194 | mB0uoGZ1D1fuFzk350Kb | Normal | 30 | 1.3.2.3.2.1.2.1 | 1.3.2.3.2.1.2.1 |  | 0 | p | 12 |  | 12
51 | 7196 | fFBpC2vR2qp5KXHLtypR | Summary | 23 | 1.3.2.3.2.1.3 | 1.3.2.3.2.1.3 |  | 124 | p | 12 | -10% | 136
52 | 7200 | 7Va2LPPEsZrLZmgpV2qc | Summary | 19 | 1.3.2.3.2.1.4 | 1.3.2.3.2.1.4 |  | 94 | p | 42 | -45% | 136
53 | 7204 | BUAmcwglNtP3GEkJsPLR | Normal | 1 | 1.3.2.3.2.1.4.4 | 1.3.2.3.2.1.4.4 |  | 57 | p | 21 | -37% | 78
54 | 7205 | 688LmElxek6WZQ34zEgD | Summary | 40 | 1.3.2.3.2.2 | 1.3.2.3.2.2 |  | 129 | p | 13 | -10% | 142
55 | 7209 | r8OmtZddpdGbVxNEynIO | Normal | 1 | 1.3.2.3.2.2.4 | 1.3.2.3.2.2.4 |  | 92 | q | -8 | (-9%) | 84
56 | 7210 | 5vpOUfvEpSU2AKPwltv0 | Summary | 14 | 1.3.2.3.2.3 | 1.3.2.3.2.3 |  | 134 | p | 31 | -23% | 165
57 | 7214 | ysGFXohNyFRFQ06jmkjW | Normal | 1 | 1.3.2.3.2.3.4 | 1.3.2.3.2.3.4 |  | 6 | p | 22 | -367% | 28
58 | 7215 | a8OJFGtOVEyM75c9puYK | Summary | 34 | 1.3.2.3.2.4 | 1.3.2.3.2.4 |  | 129 | p | 24 | -19% | 153
59 | 7222 | W1KVKgORO9KqmU1uQFqG | Normal | 1 | 1.3.2.3.2.4.7 | 1.3.2.3.2.4.7 |  | 92 | p | 4 | -4% | 96
60 | 7223 | 2cLCJpvBPh4ccgbvKrEi | Summary | 38 | 1.3.2.3.2.5 | 1.3.2.3.2.5 |  | 135 | p | 3 | -2% | 138
61 | 7226 | fsyu9CvTMAXTCK7e04ez | Normal | 1 | 1.3.2.3.2.5.3 | 1.3.2.3.2.5.3 |  | 24 | q | -24 | (-100%) | 0
62 | 7228 | SSqxRWtJ8NkhLwkx3Zp5 | Normal | 15 | 1.3.2.3.2.5.5 | 1.3.2.3.2.5.5 |  | 86 | q | -17 | (-20%) | 69
63 | 7514 | 4jhJaLUHxegkfPxUyChC | Normal | 15 | 1.3.2.3.2.5.9 | 1.3.2.3.2.5.9 |  | 118 | p | 13 | -11% | 131
64 | 7231 | Kz2H44CrN943Xn6RI0Et | Summary | 19 | 1.3.2.3.3 | 1.3.2.3.3 |  | 37 | p | 20 | -54% | 57
65 | 7232 | cCMYeGs7uzTIiiDhvAui | Summary | 12 | 1.3.2.3.3.1 | 1.3.2.3.3.1 |  | 37 | p | 20 | -54% | 57
66 | 7236 | OqdHv6QLhEyFdmarh5Mg | Normal | 5 | 1.3.2.3.3.1.4 | 1.3.2.3.3.1.4 |  | 7 | q | -1 | (-14%) | 6
67 | 7237 | xLl9f1S8pVLgozw4LZw4 | Normal | 10 | 1.3.2.3.3.1.5 | 1.3.2.3.3.1.5 |  | 0 | p | 1 |  | 1
68 | 7240 | jJgg05qz3M4QbDAQ4nmn | Summary | 7 | 1.3.2.3.3.2 | 1.3.2.3.3.2 |  | 37 | p | 20 | -54% | 57
69 | 7244 | FpvbIzqyAjmrguHRtjoA | Summary | 68 | 1.3.2.3.4 | 1.3.2.3.4 |  | 37 | p | 20 | -54% | 57
70 | 7245 | ysJ2Wz17vAaH50NFOd3r | Normal | 2 | 1.3.2.3.4.1 | 1.3.2.3.4.1 |  | 1 | q | -1 | (-100%) | 0
71 | 7248 | nqyBToLUXvLl91VDFcK9 | Summary | 20 | 1.3.2.3.4.4 | 1.3.2.3.4.4 |  | 181 | q | -16 | (-9%) | 165
72 | 7249 | T3rEQsXy5TFYVzdnmRkQ | Normal | 20 | 1.3.2.3.4.4.1 | 1.3.2.3.4.4.1 |  | 0 | p | 2 |  | 2
73 | 7251 | p2IEwFFq1YxDgQwaqReT | Summary | 48 | 1.3.2.3.4.5 | 1.3.2.3.4.5 |  | 181 | q | -16 | (-9%) | 165
74 | 6269 | tUCxonMalaI13D6hsUSU | Summary | 99 | 1.5 | 1.5 |  | 148 | q | -12 | (-8%) | 136
75 | 6278 | SNMcp7h74WVvBiN3lPNB | Summary | 66 | 1.5.6 | 1.5.6 |  | 10 | q | -10 | (-100%) | 0
76 | 605 | HP2TrbmUH5Qc4V2P2k1T | Normal | 14 | 1.5.6.1 | 1.5.6.1 |  | 144 | q | -34 | (-24%) | 110
77 | 620 | q8advjPa5PEndSFXJ05j | Summary | 158 | 1.5.6.6 | 1.5.6.6 |  | 10 | q | -10 | (-100%) | 0
78 | 622 | Q48N5ZSDLesB1Bsda2wx | Summary | 156 | 1.5.6.6.2 | 1.5.6.6.2 |  | 10 | q | -10 | (-100%) | 0
79 | 632 | tuv9OmQcJHKkVCVrbrrv | Normal | 6 | 1.5.6.6.2.8 | 1.5.6.6.2.8 |  | 21 | p | 20 | -95% | 41
80 | 648 | 6WPgljRre9DjhHGVsVUH | Summary | 120 | 1.5.6.6.5 | 1.5.6.6.5 |  | 10 | q | -10 | (-100%) | 0
81 | 657 | nePaKBbqDo6OltylvukE | Summary | 14 | 1.5.6.6.5.4 | 1.5.6.6.5.4 |  | 10 | q | -10 | (-100%) | 0
82 | 670 | zBtIFoyMK1KgXAv407C9 | Summary | 29 | 1.5.6.5 | 1.5.6.5 |  | 10 | q | -10 | (-100%) | 0
83 | 671 | ZM52W2kHJJCM7052Da3J | Normal | 2 | 1.5.6.5.2 | 1.5.6.5.2 |  | 14 | q | -14 | (-100%) | 0
84 | 6141 | PCEOtJROHHMKXYkoR4rp | Normal | 3 | 1.5.6.5.1 | 1.5.6.5.1 |  | 176 | q | -176 | (-100%) | 0
85 | 6281 | RYPcKAyzQapOQ3GupQll | Summary | 104 | 1.5.5 | 1.5.5 |  | 352 | q | -19 | (-5%) | 333
86 | 1466 | LmBGiI2jXQ3lZF0l79sj | Summary | 104 | 1.5.5.1 | 1.5.5.1 |  | 352 | q | -19 | (-5%) | 333
87 | 1459 | MxsNofofvf6CR0hsGInx | Normal | 1 | 1.5.5.1.4 | 1.5.5.1.4 |  | 0 | p | 17 |  | 17
88 | 4584 | H2uIo7s6dGmX6mrjT7jd | Normal | 9 | 1.5.5.1.7 | 1.5.5.1.7 |  | 3 | q | -3 | (-100%) | 0
89 | 6292 | 1Cm9NXihvfL2WEnYcHvT | Summary | 42 | 1.5.4 | 1.5.4 |  | 132 | q | -49 | (-37%) | 83
90 | 3945 | bJfaWXH8yBacWp0eqnXx | Normal | 1 | 1.5.4.3 | 1.5.4.3 |  | 53 | q | -34 | (-64%) | 19
91 | 3949 | knRWxUZkgPmXKgij09tb | Summary | 25 | 1.5.4.5 | 1.5.4.5 |  | 120 | q | -49 | (-41%) | 71
92 | 3950 | NJx1RMKdqhuNKRLGMSBQ | Summary | 27 | 1.5.4.5.1 | 1.5.4.5.1 |  | 120 | q | -49 | (-41%) | 71
93 | 3954 | r37KEs6OIDoMKT5Yz5nA | Normal | 1 | 1.5.4.5.1.4 | 1.5.4.5.1.4 |  | 110 | q | -39 | (-35%) | 71
94 | 3964 | ZzcX1hV2BTbfmTYJl5AE | Summary | 19 | 1.5.4.5.4 | 1.5.4.5.4 |  | 120 | q | -49 | (-41%) | 71
95 | 5996 | M6DLFbZyZKXroBVfXncj | Summary | 19 | 1.5.4.4 | 1.5.4.4 |  | 155 | q | -42 | (-27%) | 113
96 | 6202 | X3XRH6pSpuIgaacqwHSp | Normal | 14 | 1.5.4.4.10 | 1.5.4.4.10 |  | 144 | q | -31 | (-22%) | 113
97 | 6299 | JvNaxkj9UdrgV7BcBski | Summary | 134 | 1.5.1 | 1.5.1 |  | 158 | q | -22 | (-14%) | 136
98 | 4213 | pNBoUl9px0n4wFhfXXqQ | Summary | 90 | 1.5.1.1 | 1.5.1.1 |  | 10 | q | -10 | (-100%) | 0
99 | 6081 | VjHQD510O4fPJGbP9Knq | Normal | 1 | 1.5.1.2 | 1.5.1.2 |  | 158 | q | -22 | (-14%) | 136
100 | 6674 | 3EUoGYyEaAia67bx8maJ | Summary | 69 | 1.5.1.3 | 1.5.1.3 |  | 316 | p | 1 | 0% | 317
101 | 6681 | NHiN8b86HRxpkLb9JGGD | Normal | 10 | 1.5.1.3.9 | 1.5.1.3.9 |  | 25 | q | -25 | (-100%) | 0
102 | 6308 | 9d1kbrq4aHbr7FOmo76u | Summary | 27 | 1.5.2 | 1.5.2 |  | 349 | p | 4 | -1% | 353
103 | 5611 | e3AOkT5PZcArPsKmcVqB | Summary | 48 | 1.5.2.2 | 1.5.2.2 |  | 349 | p | 4 | -1% | 353
104 | 5612 | JBIAfh9fImNsEXfXoHCz | Summary | 5 | 1.5.2.2.10 | 1.5.2.2.10 |  | 349 | p | 4 | -1% | 353
105 | 5627 | s0vjJX7zGlVyBdE0eigo | Summary | 15 | 1.5.2.2.8 | 1.5.2.2.8 |  | 349 | p | 4 | -1% | 353
106 | 5635 | ZYzv9KOmVdYL2d3ZPb8b | Summary | 0 | 1.5.2.2.9 | 1.5.2.2.9 |  | 0 | p | 370 |  | 370
107 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | 0 | p | 17 |  | 17
108 | 6309 | taNk8S9bKnlDToaFycS6 | Summary | 37 | 1.5.3 | 1.5.3 |  | 66 | q | -40 | (-61%) | 26
109 | 5443 | L0xk8h495fvdhlwnri8N | Summary | 37 | 1.5.3.1 | 1.5.3.1 |  | 66 | q | -40 | (-61%) | 26
110 | 5445 | 95pLIsxhFDdrMJGVBrpQ | Summary | 35 | 1.5.3.1.2 | 1.5.3.1.2 |  | 66 | q | -40 | (-61%) | 26
111 | 5450 | maMtUzorvxHWuMFIlXlq | Normal | 5 | 1.5.3.1.3 | 1.5.3.1.3 |  | 56 | q | -30 | (-54%) | 26
112 | 7381 | Ao7wteklS85dOuCCMM3I | Normal | 124 | 1.5.1 | 1.5.1 |  | 148 | q | -9 | (-6%) | 139
113 | 6270 | Wwp4MRWhcV55WleZhe1f | Summary | 288 | 1.4 | 1.4 |  | 450 | p | 124 | -28% | 574
114 | 576 | m8O5CFAYfVbtxxZI5qQW | Normal | 15 | 1.4.3.1.2 | 1.4.3.1.2 |  | 50 | p | 17 | -34% | 67
115 | 4536 | zU98x2LHVd7UXovDFMXu | Normal | 14 | 1.4.3.1.1 | 1.4.3.1.1 |  | 242 | q | -30 | (-12%) | 212
116 | 6607 | IhYDHpDNbof6PVOjQ9lw | Normal | 4 | 1.4.3.1.3 | 1.4.3.1.3 |  | 5 | q | -5 | (-100%) | 0
117 | 6291 | 7X6NK9qir9GRz5m7bXmK | Summary | 297 | 1.4.1 | 1.4.1 |  | 450 | p | 124 | -28% | 574
118 | 3891 | VQVEpj4HfOnKALplb4t9 | Summary | 43 | 1.4.1.1 | 1.4.1.1 |  | 238 | q | -41 | (-17%) | 197
119 | 3897 | cqWsQsQWdy7etYVMNQBf | Summary | 53 | 1.4.1.1.2 | 1.4.1.1.2 |  | 238 | q | -41 | (-17%) | 197
120 | 3901 | Jj1toL1YzUk95oK7OfgU | Normal | 4 | 1.4.1.1.2.4 | 1.4.1.1.2.4 |  | 173 | q | -43 | (-25%) | 130
121 | 3902 | FL4HGNxujC5zK4lN6AVO | Summary | 30 | 1.4.1.2 | 1.4.1.2 |  | 216 | p | 21 | -10% | 237
122 | 3903 | e0nMZ5CLCmjCURLrKpol | Summary | 30 | 1.4.1.2.1 | 1.4.1.2.1 |  | 216 | p | 21 | -10% | 237
123 | 6566 | gAyE6SkFHV1MNEAJitQ7 | Normal | 1 | 1.4.1.2.1.6 | 1.4.1.2.1.6 |  | 38 | q | -38 | (-100%) | 0
124 | 3907 | pFYLZycbgH4KMn6pLhBU | Summary | 272 | 1.4.1.3 | 1.4.1.3 |  | 24 | q | -17 | (-71%) | 7
125 | 3909 | VvjZ0oHXTTG06m5XlL1B | Normal | 10 | 1.4.1.3.2 | 1.4.1.3.2 |  | 154 | p | 76 | -49% | 230
126 | 3917 | hmttcJptV92JIo4OpANW | Normal | 5 | 1.4.1.3.10 | 1.4.1.3.10 |  | 24 | q | -17 | (-71%) | 7
127 | 3918 | VKkEEklTkhlAtqntT93x | Summary | 160 | 1.4.1.4 | 1.4.1.4 |  | 450 | p | 124 | -28% | 574
128 | 3920 | mBVNyTIN7rvKyNQxzyxZ | Normal | 9 | 1.4.1.4.2 | 1.4.1.4.2 |  | 41 | q | -22 | (-54%) | 19
129 | 3921 | jEuseC90wYhkn0V4svXs | Normal | 3 | 1.4.1.4.3 | 1.4.1.4.3 |  | 46 | p | 9 | -20% | 55
130 | 3928 | hCBFci3gUopMkWW2dQQj | Normal | 5 | 1.4.1.4.10 | 1.4.1.4.10 |  | 0 | p | 356 |  | 356
131 | 6318 | cM5VCGnPiK1mfNJo8YLF | Summary | 309 | 1.4.2 | 1.4.2 |  | 455 | p | 142 | -31% | 597
132 | 5216 | xOecB4tLtQXauOnWGD4l | Normal | 1 | 1.4.2.2.3.3 | 1.4.2.2.3.3 |  | 0 | p | 3 |  | 3
133 | 5217 | e116DivbRDCkLiH2zNhl | Summary | 61 | 1.4.2.2.4 | 1.4.2.2.4 |  | 85 | q | -8 | (-9%) | 77
134 | 5220 | QAqXx5k5ldQJaugZyYbR | Normal | 1 | 1.4.2.2.4.3 | 1.4.2.2.4.3 |  | 74 | p | 3 | -4% | 77
135 | 5221 | iTaWceiQKMF6gUaF3DCB | Summary | 61 | 1.4.2.2.5 | 1.4.2.2.5 |  | 117 | q | -4 | (-3%) | 113
136 | 5226 | R9JO9mOSGmg0eoDimoJT | Summary | 71 | 1.4.2.1 | 1.4.2.1 |  | 773 | p | 168 | -22% | 941
137 | 5240 | NSmZbDTp76mGzDSQ7Ceh | Summary | 56 | 1.4.2.1.3 | 1.4.2.1.3 |  | 10 | q | -1 | (-10%) | 9
138 | 5241 | v6EKIZLcnDHW8CXOrD7y | Normal | 21 | 1.4.2.1.3.1 | 1.4.2.1.3.1 |  | 0 | p | 34 |  | 34
139 | 5242 | JYCfpao49G3jD8M94S66 | Normal | 10 | 1.4.2.1.3.2 | 1.4.2.1.3.2 |  | 0 | p | 89 |  | 89
140 | 5268 | fG9nayiE82fFlNFtuyfN | Normal | 8 | 1.4.2.1.6.5 | 1.4.2.1.6.5 |  | 52 | q | -33 | (-63%) | 19
141 | 5264 | 2BYRPY9ftrCpjg2j3vxJ | Milestone | 0 | 1.4.2.1.8 | 1.4.2.1.8 |  | 414 | p | 887 | -214% | 1301
142 | 5290 | NEvSl0zKCrGJ6lqshTZO | Milestone | 0 | 1.4.2.3.1 | 1.4.2.3.1 |  | 106 | p | 7 | -7% | 113
143 | 5313 | 3y8KKUl940HiJi7UFKFT | Summary | 106 | 1.4.2.3.3 | 1.4.2.3.3 |  | 455 | p | 142 | -31% | 597
144 | 5326 | esDa5lJIA5zg0nP58cRd | Summary | 32 | 1.4.2.3.4 | 1.4.2.3.4 |  | 250 | q | -1 | 0% | 249
145 | 5329 | GYUaK0PI1fV4kag2egD8 | Normal | 1 | 1.4.2.3.4.3 | 1.4.2.3.4.3 |  | 227 | p | 468 | -206% | 695
146 | 6321 | KAyzIHlSkkFZqIIdJ9JD | Summary | 144 | 1.4.2.3.2 | 1.4.2.3.2 |  | 11 | q | -11 | (-100%) | 0
147 | 6521 | LDY9CVOjImzsQ4NE65Qz | Normal | 1 | 1.4.2.3.2.16 | 1.4.2.3.2.16 |  | 3 | q | -3 | (-100%) | 0
148 | 6522 | WYJvDx3FrKALT2lj4FIo | Normal | 2 | 1.4.2.3.2.18 | 1.4.2.3.2.18 |  | 8 | q | -8 | (-100%) | 0
149 | 6271 | Q6QswYSvhipRUbZBXuiu | Summary | 315 | 1.6 | 1.6 |  | 488 | p | 77 | -16% | 565
150 | 6277 | moVS9Ou3GclDwNSW1OnS | Summary | 264 | 1.6.7 | 1.6.7 |  | 512 | p | 76 | -15% | 588
151 | 728 | 4dRz6TQj3FOK8lstTqZK | Summary | 396 | 1.6.7.9 | 1.6.7.9 |  | 512 | p | 83 | -16% | 595
152 | 741 | cktDjgZ5bp36SrQnCM1w | Summary | 458 | 1.6.7.9.3 | 1.6.7.9.3 |  | 512 | p | 83 | -16% | 595
153 | 5773 | OCcI80TDGF8LlIXj66uV | Normal | 3 | 1.6.7.9.3.14 | 1.6.7.9.3.14 |  | 0 | p | 6 |  | 6
154 | 6323 | aU24Z8SrLl20SyyllZuy | Summary | 80 | 1.6.7.9.3.5 | 1.6.7.9.3.5 |  | 498 | p | 133 | -27% | 631
155 | 746 | qMC0J8brk1dsdpzlKrk7 | Normal | 12 | 1.6.7.9.3.5.3 | 1.6.7.9.3.5.3 |  | 10 | p | 15 | -150% | 25
156 | 6324 | gthK0FxwJBk3laTELp8O | Summary | 45 | 1.6.7.9.3.6 | 1.6.7.9.3.6 |  | 488 | p | 117 | -24% | 605
157 | 6325 | SeCXD5wMvkrEekc1PKVb | Summary | 48 | 1.6.7.9.3.10 | 1.6.7.9.3.10 |  | 506 | p | 72 | -14% | 578
158 | 753 | 8158sxzbHZvZEVAAqewP | Normal | 47 | 1.6.7.9.3.10.1 | 1.6.7.9.3.10.1 |  | 34 | p | 15 | -44% | 49
159 | 758 | FbN1rrQYTlsz1haWZnFy | Normal | 6 | 1.6.7.9.3.10.8 | 1.6.7.9.3.10.8 |  | 18 | q | -18 | (-100%) | 0
160 | 5782 | EYY3j1SjnoLUV06T0QHs | Normal | 5 | 1.6.7.9.3.10.7 | 1.6.7.9.3.10.7 |  | 25 | q | -16 | (-64%) | 9
161 | 6326 | F4s3MnfyyA74WCIympSi | Summary | 75 | 1.6.7.9.3.11 | 1.6.7.9.3.11 |  | 488 | p | 77 | -16% | 565
162 | 6327 | dOJS0LaWQU970ssSiqsz | Summary | 59 | 1.6.7.9.3.12 | 1.6.7.9.3.12 |  | 488 | p | 77 | -16% | 565
163 | 770 | cHAOkWrFbu094CNd9eCk | Summary | 91 | 1.6.7.8 | 1.6.7.8 |  | 650 | p | 106 | -16% | 756
164 | 786 | 5RJIBxVgSA4dodMzOCsx | Normal | 1 | 1.6.7.8.5 | 1.6.7.8.5 |  | 162 | p | 29 | -18% | 191
165 | 5785 | xIbBdattr1YLWDiqGWPC | Summary | 126 | 1.6.7.11 | 1.6.7.11 |  | 512 | p | 76 | -15% | 588
166 | 5775 | D3NIdGcGrWNhiaQ0dYbY | Normal | 2 | 1.6.7.11.3 | 1.6.7.11.3 |  | 24 | q | -4 | (-17%) | 20
167 | 6284 | T6s1mlIi1Lu4cscBpq9h | Summary | 273 | 1.6.6 | 1.6.6 |  | 616 | p | 141 | -23% | 757
168 | 1519 | Ig6aeqJATmPNbReGQrzj | Summary | 273 | 1.6.6.1 | 1.6.6.1 |  | 616 | p | 141 | -23% | 757
169 | 1465 | i7zbkIpCuBMJlMsq6ma0 | Normal | 1 | 1.6.6.1.5 | 1.6.6.1.5 |  | 112 | q | -21 | (-19%) | 91
170 | 1477 | BC1NYB3fqAlfckX7ECXI | Normal | 1 | 1.6.6.1.8 | 1.6.6.1.8 |  | 110 | p | 2 | -2% | 112
171 | 1478 | UR7xa7LgN3sMlpzxRjvW | Normal | 3 | 1.6.6.1.9 | 1.6.6.1.9 |  | 78 | p | 651 | -835% | 729
172 | 6293 | WhUcOZjaj9TDZe74ojmh | Summary | 172 | 1.6.4 | 1.6.4 |  | 488 | p | 77 | -16% | 565
173 | 3929 | GkmiaraCbWdBUaRv136y | Summary | 19 | 1.6.4.15 | 1.6.4.15 |  | 630 | p | 113 | -18% | 743
174 | 3932 | RKLg9Drqo40Q82TFH1VL | Normal | 1 | 1.6.4.15.2 | 1.6.4.15.2 |  | 6 | q | -6 | (-100%) | 0
175 | 3934 | 10Oh1H5M5HjeoWxU1u0w | Normal | 1 | 1.6.4.15.4 | 1.6.4.15.4 |  | 117 | p | 629 | -538% | 746
176 | 3936 | hwXDQy0MWIQ4jzjNT4oM | Normal | 1 | 1.6.4.15.3 | 1.6.4.15.3 |  | 117 | p | 637 | -544% | 754
177 | 3938 | 2iJ091mlhEkJyqoddB4L | Normal | 14 | 1.6.4.15.1 | 1.6.4.15.1 |  | 137 | p | 641 | -468% | 778
178 | 3940 | 8UqvtHTIMRT16eupajKq | Normal | 1 | 1.6.4.15.5 | 1.6.4.15.5 |  | 117 | p | 626 | -535% | 743
179 | 3971 | mB1p68eekBqQhgV8es2U | Summary | 19 | 1.6.4.7 | 1.6.4.7 |  | 655 | p | 101 | -15% | 756
180 | 3974 | xzlIrgrrtbLscLWLbbQq | Normal | 1 | 1.6.4.7.1 | 1.6.4.7.1 |  | 119 | p | 10 | -8% | 129
181 | 3981 | YTm9sByrDxPUc7AlWXh1 | Normal | 15 | 1.6.4.7.2 | 1.6.4.7.2 |  | 149 | p | 42 | -28% | 191
182 | 3991 | kc0LQmDrjfLGJeMU4QIH | Summary | 70 | 1.6.4.17 | 1.6.4.17 |  | 315 | q | -26 | (-8%) | 289
183 | 3992 | cy141kwlo0X5isTqv3ku | Summary | 25 | 1.6.4.17.4 | 1.6.4.17.4 |  | 315 | q | -26 | (-8%) | 289
184 | 3996 | Bw8X4DjnSuQgBiA6BEKp | Normal | 5 | 1.6.4.17.4.4 | 1.6.4.17.4.4 |  | 25 | q | -11 | (-44%) | 14
185 | 3997 | KJPP8ivswwWTIeIfPXEM | Summary | 25 | 1.6.4.17.3 | 1.6.4.17.3 |  | 315 | q | -26 | (-8%) | 289
186 | 4002 | nJzh0eFJGsqvOmQRJzHn | Summary | 27 | 1.6.4.17.2 | 1.6.4.17.2 |  | 315 | q | -26 | (-8%) | 289
187 | 4012 | A4Ck0Reyqf4cLzrM8uUY | Summary | 206 | 1.6.4.19 | 1.6.4.19 |  | 191 | p | 169 | -88% | 360
188 | 6168 | BHtkkzlMW8757DY2qb23 | Summary | 143 | 1.6.4.19.3 | 1.6.4.19.3 |  | 191 | p | 169 | -88% | 360
189 | 6169 | gdW3U4pURjb9iKkAVexH | Summary | 60 | 1.6.4.19.3.1 | 1.6.4.19.3.1 |  | 191 | p | 169 | -88% | 360
190 | 6170 | AwYLgXY6Mo1DqCbUEhPQ | Summary | 30 | 1.6.4.19.3.1.1 | 1.6.4.19.3.1.1 |  | 191 | p | 169 | -88% | 360
191 | 6175 | IEttja5qNJ6P760Cd9De | Summary | 40 | 1.6.4.19.3.2 | 1.6.4.19.3.2 |  | 191 | p | 169 | -88% | 360
192 | 6185 | A91LND4pEy61zvjvAsaQ | Normal | 1 | 1.6.4.19.3.8 | 1.6.4.19.3.8 |  | 120 | p | 225 | -188% | 345
193 | 4037 | hMBnPD0NfYpjSqEpRMYY | Summary | 554 | 1.6.4.20 | 1.6.4.20 |  | 488 | p | 77 | -16% | 565
194 | 4038 | VkrURyJwsSkEVRV6WcXe | Summary | 411 | 1.6.4.20.1 | 1.6.4.20.1 |  | 488 | p | 77 | -16% | 565
195 | 4040 | g5zNgGHP8U11wPTJKhcB | Normal | 20 | 1.6.4.20.1.3 | 1.6.4.20.1.3 |  | 168 | p | 228 | -136% | 396
196 | 4041 | f0PORH3GhEIXFjYfGbTd | Normal | 97 | 1.6.4.20.1.6 | 1.6.4.20.1.6 |  | 131 | p | 203 | -155% | 334
197 | 4042 | SyfMayqY4a7i0nZLPz6Y | Normal | 129 | 1.6.4.20.1.7 | 1.6.4.20.1.7 |  | 8 | q | -6 | (-75%) | 2
198 | 4043 | XbXkjxtfHUxhg4CK1elt | Summary | 127 | 1.6.4.20.2 | 1.6.4.20.2 |  | 488 | p | 77 | -16% | 565
199 | 4050 | jQIHIDf5FTnJxQysEvnn | Summary | 37 | 1.6.4.20.3 | 1.6.4.20.3 |  | 488 | p | 77 | -16% | 565
200 | 4051 | bizigDTezGi1mMHxJ1gi | Summary | 32 | 1.6.4.20.3.1 | 1.6.4.20.3.1 |  | 488 | p | 80 | -16% | 568
201 | 4054 | WhXMUGkGRid5sulqMW8S | Summary | 5 | 1.6.4.20.3.2 | 1.6.4.20.3.2 |  | 488 | p | 80 | -16% | 568
202 | 4058 | cbANjhwCBqAluf1RM04K | Normal | 1 | 1.6.4.20.3.2.4 | 1.6.4.20.3.2.4 |  | 38 | p | 313 | -824% | 351
203 | 4059 | sH9kz6O2EFda2hu4x8Kx | Summary | 12 | 1.6.4.20.3.3 | 1.6.4.20.3.3 |  | 488 | p | 77 | -16% | 565
204 | 4064 | OALhjNOvEaqSDAmsS5Il | Normal | 1 | 1.6.4.20.3.3.5 | 1.6.4.20.3.3.5 |  | 38 | p | 309 | -813% | 347
205 | 5748 | cHP8KcDQZp8MvOi5a8Wj | Summary | 64 | 1.6.4.18 | 1.6.4.18 |  | 501 | p | 126 | -25% | 627
206 | 6701 | vwWJ3SVwW3tYdDDMDgOK | Summary | 60 | 1.6.4.18.3 | 1.6.4.18.3 |  | 501 | p | 126 | -25% | 627
207 | 6713 | JQXHTZXJblKyiNyxM0eT | Summary | 78 | 1.6.4.18.3.3 | 1.6.4.18.3.3 |  | 501 | p | 126 | -25% | 627
208 | 6727 | 5BlmDU3ct4fwjT54EODG | Summary | 21 | 1.6.4.18.3.3.2 | 1.6.4.18.3.3.2 |  | 521 | p | 130 | -25% | 651
209 | 7007 | 9uputDeZmGdSlUY8oN4J | Summary | 64 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 501 | p | 126 | -25% | 627
210 | 7010 | l7MAqMN94R7DBQRgok6z | Normal | 5 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 13 | p | 9 | -69% | 22
211 | 7278 | 4Ma7Z2LiPmWBC9UI6vyb | Normal | 5 | 1.6.4.18.3.3.7.7 | 1.6.4.18.3.3.7.7 |  | 0 | p | 4 |  | 4
212 | 7300 | JMkMoXIhBdn9ICcOd798 | Normal | 5 | 1.6.4.18.3.3.7.4 | 1.6.4.18.3.3.7.4 |  | 20 | p | 4 | -20% | 24
213 | 7279 | uD2jpviUMAewZ4YhDj8P | Summary | 32 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 503 | p | 136 | -27% | 639
214 | 7285 | UP4KQN3vFTNJJtYiVHhd | Normal | 10 | 1.6.4.18.3.3.4.6 | 1.6.4.18.3.3.4.6 |  | 2 | p | 6 | -300% | 8
215 | 7286 | weppsWRcwILLbxkFpraK | Summary | 39 | 1.6.4.18.3.3.5 | 1.6.4.18.3.3.5 |  | 504 | p | 130 | -26% | 634
216 | 7292 | 6vEOHVPLFOaXnW1xcDp6 | Normal | 10 | 1.6.4.18.3.3.5.6 | 1.6.4.18.3.3.5.6 |  | 3 | q | -1 | (-33%) | 2
217 | 7293 | ep0qwejNT11UOlW5WmY0 | Summary | 28 | 1.6.4.18.3.3.6 | 1.6.4.18.3.3.6 |  | 501 | p | 126 | -25% | 627
218 | 7295 | tyaakhlAtuOpVSt7bVvo | Normal | 1 | 1.6.4.18.3.3.6.2 | 1.6.4.18.3.3.6.2 |  | 6 | q | -6 | (-100%) | 0
219 | 6297 | AqdIsKbIPOfZJkjKYjnG | Summary | 118 | 1.6.1 | 1.6.1 |  | 539 | p | 402 | -75% | 941
220 | 4200 | YSdvLAa6ztbhOKei71CV | Summary | 108 | 1.6.1.1 | 1.6.1.1 |  | 532 | p | 153 | -29% | 685
221 | 4209 | 0Ck6gz1ZilLs9fM0b7nU | Summary | 46 | 1.6.1.3 | 1.6.1.3 |  | 566 | p | 117 | -21% | 683
222 | 4212 | yktUOUuzQyzOVBFBfL42 | Normal | 46 | 1.6.1.3.1 | 1.6.1.3.1 |  | 78 | q | -1 | (-1%) | 77
223 | 6080 | jFrzSNmYyPDtKSvRlBw2 | Normal | 1 | 1.6.1.6 | 1.6.1.6 |  | 26 | p | 1427 | -5488% | 1453
224 | 6311 | tQdu1pFxVkY2bj5IQjxI | Summary | 77 | 1.6.3 | 1.6.3 |  | 547 | p | 18 | -3% | 565
225 | 5452 | u9nFTwEoKsBrgeg8njOT | Normal | 5 | 1.6.3.1 | 1.6.3.1 |  | 96 | q | -96 | (-100%) | 0
226 | 5457 | kGunJCROCjWQWqBfRKBZ | Summary | 1 | 1.6.3.2 | 1.6.3.2 |  | 643 | p | 111 | -17% | 754
227 | 5458 | DngVHB2HpHpsOjFWu5hu | Summary | 1 | 1.6.3.2.1 | 1.6.3.2.1 |  | 643 | p | 111 | -17% | 754
228 | 5505 | nVzBMSNTKKq9KPWblsw1 | Normal | 1 | 1.6.3.2.1.9 | 1.6.3.2.1.9 |  | 0 | p | 189 |  | 189
229 | 5506 | wLM81Xdu8B5geOMMQz6m | Summary | 119 | 1.6.3.3 | 1.6.3.3 |  | 547 | p | 18 | -3% | 565
230 | 5509 | 1FHP32ReWIveKb3JOWEG | Summary | 44 | 1.6.3.3.4 | 1.6.3.3.4 |  | 511 | p | 105 | -21% | 616
231 | 5514 | leNXdZKmybH4tpy20cQU | Normal | 5 | 1.6.3.3.5 | 1.6.3.3.5 |  | 41 | q | -41 | (-100%) | 0
232 | 6359 | hvfa0617w1FgmEnjjKwJ | Summary | 26 | 1.7.2.16 | 1.7.2.16 |  | 501 | p | 126 | -25% | 627
233 | 6360 | DMXbIVCeMtVR5pi4d5UN | Summary | 26 | 1.7.2.16.1 | 1.7.2.16.1 |  | 501 | p | 126 | -25% | 627
234 | 6361 | VEKeY9azNIVSZDSjYyKy | Summary | 33 | 1.7.2.16.1.3 | 1.7.2.16.1.3 |  | 501 | p | 126 | -25% | 627
235 | 7303 | fpLHmKjlfpy4s4tap5Xw | Summary | 39 | 1.6.3.11.1.3.4 | 1.6.3.11.1.3.4 |  | 503 | p | 136 | -27% | 639
236 | 7309 | 19skeJKmh3pRSfTF3DDB | Summary | 30 | 1.6.3.11.1.3.5 | 1.6.3.11.1.3.5 |  | 504 | p | 130 | -26% | 634
237 | 7315 | 9LywAxRsXdHsCrCcjGKV | Summary | 27 | 1.6.3.11.1.3.6 | 1.6.3.11.1.3.6 |  | 501 | p | 126 | -25% | 627
238 | 6273 | ljz6i2ltFwqcRU3btDx0 | Summary | 552 | 1.8 | 1.8 |  | 510 | q | -265 | (-52%) | 245
239 | 6074 | fkBL64dyW7paLwgGr0ue | Normal | 212 | 1.8.2.3 | 1.8.2.3 |  | 180 | q | -18 | (-10%) | 162
240 | 6075 | pe2nScqRc5pgTwGaT5Zd | Normal | 193 | 1.8.2.2 | 1.8.2.2 |  | 199 | q | -33 | (-17%) | 166
241 | 6295 | uPS9GNqRLP4065SnBhEr | Summary | 387 | 1.8.5 | 1.8.5 |  | 84 | p | 15 | -18% | 99
242 | 3679 | 1KDcwGZKgevw1MizqBh0 | Summary | 387 | 1.8.5.1 | 1.8.5.1 |  | 84 | p | 15 | -18% | 99
243 | 3680 | E8qsx9NjEz7vaL5H7EFb | Summary | 189 | 1.8.5.1.1 | 1.8.5.1.1 |  | 104 | q | -5 | (-5%) | 99
244 | 3682 | 38PSIqFGHzjKldiudT82 | Summary | 25 | 1.8.5.1.1.4 | 1.8.5.1.1.4 |  | 104 | q | -5 | (-5%) | 99
245 | 3685 | eStRoX3vnaDmRLAWk58C | Summary | 40 | 1.8.5.1.1.5 | 1.8.5.1.1.5 |  | 104 | q | -5 | (-5%) | 99
246 | 3690 | 8YDpqEvemQaMsfVmGpF8 | Normal | 5 | 1.8.5.1.1.5.5 | 1.8.5.1.1.5.5 |  | 100 | p | 4 | -4% | 104
247 | 3691 | ofZrlktbiXkVpuhhIeO5 | Summary | 25 | 1.8.5.1.1.6 | 1.8.5.1.1.6 |  | 104 | q | -5 | (-5%) | 99
248 | 3693 | Hn8rBaTvxeP9Vb10zF48 | Normal | 5 | 1.8.5.1.1.6.2 | 1.8.5.1.1.6.2 |  | 95 | p | 4 | -4% | 99
249 | 3694 | 4tipOydrC0LTNincaMDW | Summary | 35 | 1.8.5.1.1.7 | 1.8.5.1.1.7 |  | 104 | q | -5 | (-5%) | 99
250 | 3698 | AKCwPpEPQi4iH3XDRpiM | Normal | 5 | 1.8.5.1.1.7.4 | 1.8.5.1.1.7.4 |  | 65 | q | -8 | (-12%) | 57
251 | 3699 | AYANEA6OuC5b95kp3uyI | Summary | 30 | 1.8.5.1.1.8 | 1.8.5.1.1.8 |  | 104 | q | -5 | (-5%) | 99
252 | 3702 | sTuPByKbZEfSXxt0Z2G9 | Normal | 5 | 1.8.5.1.1.8.3 | 1.8.5.1.1.8.3 |  | 5 | q | -5 | (-100%) | 0
253 | 3703 | WHZRJAK4v6S9Zk2EBeP3 | Summary | 40 | 1.8.5.1.1.9 | 1.8.5.1.1.9 |  | 104 | q | -5 | (-5%) | 99
254 | 3708 | 84VtM14FQkMGurZDdBLv | Normal | 5 | 1.8.5.1.1.9.5 | 1.8.5.1.1.9.5 |  | 20 | p | 4 | -20% | 24
255 | 3709 | gpO5WcJkYid7jZAXZwbn | Summary | 40 | 1.8.5.1.1.10 | 1.8.5.1.1.10 |  | 104 | q | -5 | (-5%) | 99
256 | 6647 | hWzCSsDre5WTTpryk1b0 | Normal | 5 | 1.8.5.1.1.3 | 1.8.5.1.1.3 |  | 324 | q | -6 | (-2%) | 318
257 | 3715 | V6i7uYjEJBRYHjhIimqJ | Summary | 50 | 1.8.5.1.2 | 1.8.5.1.2 |  | 104 | q | -5 | (-5%) | 99
258 | 3718 | vTyTgxcbRSz6H6lqDAEf | Summary | 20 | 1.8.5.1.3 | 1.8.5.1.3 |  | 104 | q | -5 | (-5%) | 99
259 | 3720 | rPRo0RE1uNkj9oG127hu | Summary | 109 | 1.8.5.1.4 | 1.8.5.1.4 |  | 107 | p | 415 | -388% | 522
260 | 6652 | 0afM7N7hGdWHQjlFenVR | Normal | 10 | 1.8.5.1.4.6 | 1.8.5.1.4.6 |  | 257 | p | 418 | -163% | 675
261 | 3723 | 4qmbzAmtSx0gvDVaBsYe | Summary | 239 | 1.8.5.1.5 | 1.8.5.1.5 |  | 171 | q | -11 | (-6%) | 160
262 | 6667 | 0dYk2X7XWh2rSSHkHo2L | Normal | 10 | 1.8.5.1.5.8 | 1.8.5.1.5.8 |  | 171 | q | -11 | (-6%) | 160
263 | 6670 | vWxPVjk5e7KHTev8998h | Normal | 1 | 1.8.5.1.5.12 | 1.8.5.1.5.12 |  | 298 | p | 4 | -1% | 302
264 | 3726 | 5hjTNIk7WmpZNtmCLhPN | Summary | 96 | 1.8.5.1.6 | 1.8.5.1.6 |  | 234 | p | 118 | -50% | 352
265 | 3729 | Y6b5KP0DE9c4tlFzqxp3 | Summary | 81 | 1.8.5.1.7 | 1.8.5.1.7 |  | 291 | p | 405 | -139% | 696
266 | 6626 | 9d2gtkuh8SmNZwArNzpn | Normal | 10 | 1.8.5.1.7.4 | 1.8.5.1.7.4 |  | 291 | p | 405 | -139% | 696
267 | 3733 | ufu7SWDoeBfTzZW24BQU | Summary | 189 | 1.8.5.1.9 | 1.8.5.1.9 |  | 84 | p | 78 | -93% | 162
268 | 3738 | bohrZqwOTsvUL4DEUnjh | Summary | 139 | 1.8.5.1.10 | 1.8.5.1.10 |  | 109 | p | 413 | -379% | 522
269 | 6642 | A7Bd82G8YCk8VjEZkcvi | Summary | 135 | 1.8.5.1.8 | 1.8.5.1.8 |  | 84 | p | 81 | -96% | 165
270 | 6634 | 65ghvPiwU0AxSKrC11rG | Normal | 20 | 1.8.5.1.8.7 | 1.8.5.1.8.7 |  | 84 | p | 428 | -510% | 512
271 | 6643 | sKnPCsxlq51dE8cz52fo | Normal | 10 | 1.8.5.1.8.9 | 1.8.5.1.8.9 |  | 0 | p | 415 |  | 415
272 | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Summary | 1 | 1.8.1 | 1.8.1 |  | 510 | q | -265 | (-52%) | 245
273 | 6082 | YsSSuERf5VIDKO5m8eZo | Normal | 1 | 1.8.1.1 | 1.8.1.1 |  | 0 | p | 28 |  | 28
274 | 6313 | 8HYxn50EKf1DU0fX0MF7 | Summary | 391 | 1.8.4 | 1.8.4 |  | 325 | q | -80 | (-25%) | 245
275 | 5516 | dd6fm1lW4tBXPtNV5RGW | Summary | 391 | 1.8.4.1 | 1.8.4.1 |  | 325 | q | -80 | (-25%) | 245
276 | 5517 | IHfroMkwx3TZoTXYbBOK | Normal | 40 | 1.8.4.1.1 | 1.8.4.1.1 |  | 325 | p | 422 | -130% | 747
277 | 5518 | V0a5XEJ0jxIkhnpEDg8e | Normal | 40 | 1.8.4.1.2 | 1.8.4.1.2 |  | 325 | p | 401 | -123% | 726
278 | 5519 | D5sl3M5NpO77EU7TPYT0 | Normal | 40 | 1.8.4.1.3 | 1.8.4.1.3 |  | 325 | p | 412 | -127% | 737
279 | 5523 | APkwTVep7mUhgmcCl4NB | Milestone | 0 | 1.8.4.1.4 | 1.8.4.1.4 |  | 0 | p | 28 |  | 28
280 | 5527 | Mw5Re8SivA42laH7UhJE | Milestone | 0 | 1.8.4.1.5 | 1.8.4.1.5 |  | 0 | p | 28 |  | 28
281 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 514 | q | -514 | (-100%) | 0
282 | 5331 | emM9tIPUc6I6BRQdDkUj | Summary | 325 | 1.9.3 | 1.9.3 |  | 620 | p | 171 | -28% | 791
283 | 5332 | Jas5wmBgln6JvMRLtRUk | Summary | 110 | 1.9.3.1 | 1.9.3.1 |  | 620 | p | 171 | -28% | 791
284 | 5334 | 5Bt8vyiG2PJ2FKCjQPP1 | Summary | 74 | 1.9.3.1.2 | 1.9.3.1.2 |  | 620 | p | 171 | -28% | 791
285 | 5335 | fBEkx0xCtVpw1OeE4jLB | Summary | 25 | 1.9.3.1.3 | 1.9.3.1.3 |  | 620 | p | 171 | -28% | 791
286 | 5344 | Kw3Fj6kwk5uOl7tQyqrL | Milestone | 0 | 1.9.3.1.6 | 1.9.3.1.6 |  | 99 | p | 685 | -692% | 784
287 | 6275 | OL3lkJGtK3tkk0d4SBRn | Summary | 288 | 1.9.9 | 1.9.9 |  | 514 | q | -514 | (-100%) | 0
288 | 844 | 1qfp8o9PQxr9vZvO7S5k | Normal | 1 | 1.9.9.4 | 1.9.9.4 |  | 60 | q | -60 | (-100%) | 0
289 | 845 | U1v5hScHSOPPxa5ohjfI | Summary | 189 | 1.9.9.7 | 1.9.9.7 |  | 586 | p | 130 | -22% | 716
290 | 847 | JilJNxxBcx7QrT5PcKLM | Summary | 189 | 1.9.9.7.2 | 1.9.9.7.2 |  | 586 | p | 130 | -22% | 716
291 | 869 | 8QCM3LZ8SN5y0jCLtGNh | Summary | 129 | 1.9.9.7.2.7 | 1.9.9.7.2.7 |  | 586 | p | 130 | -22% | 716
292 | 870 | m3oEXpasu7ssfpw9dqLv | Summary | 267 | 1.9.9.14 | 1.9.9.14 |  | 514 | q | -514 | (-100%) | 0
293 | 4669 | aeClBbTsJ3qrKHWqQ1Rw | Normal | 40 | 1.9.9.14.5 | 1.9.9.14.5 |  | 84 | p | 627 | -746% | 711
294 | 899 | w1GWQdUx9oG06oopRYZx | Summary | 24 | 1.9.9.15 | 1.9.9.15 |  | 514 | q | -514 | (-100%) | 0
295 | 904 | 4CH3NSJx1luiHbrrAEJg | Normal | 2 | 1.9.9.15.5 | 1.9.9.15.5 |  | 6 | q | -6 | (-100%) | 0
296 | 914 | q0UeyWaeMXFoeUDjjzhX | Summary | 18 | 1.9.9.5 | 1.9.9.5 |  | 782 | q | -510 | (-65%) | 272
297 | 915 | jxzEE3EBeGWt1nE3uHcj | Summary | 18 | 1.9.9.5.1 | 1.9.9.5.1 |  | 782 | q | -510 | (-65%) | 272
298 | 917 | mbDdHZHm9OoYye329Ue6 | Normal | 1 | 1.9.9.5.1.2 | 1.9.9.5.1.2 |  | 268 | p | 4 | -1% | 272
299 | 4538 | aTyUglf0WPX6H8Zd17Iq | Summary | 71 | 1.9.9.16 | 1.9.9.16 |  | 514 | q | -514 | (-100%) | 0
300 | 6509 | sp3XFaPtGgzrVeC1wvvV | Normal | 10 | 1.9.9.16.3 | 1.9.9.16.3 |  | 0 | p | 5 |  | 5
301 | 6515 | a8Kdm3F6uLeIN4SEhwX9 | Normal | 1 | 1.9.9.16.1 | 1.9.9.16.1 |  | 23 | q | -3 | (-13%) | 20
302 | 5783 | BOvEGIzyTacp1vvD9v7M | Normal | 1 | 1.9.9.2 | 1.9.9.2 |  | 73 | p | 643 | -881% | 716
303 | 6128 | 7jXaekqqhUCDWSDfnxzo | Summary | 28 | 1.7.4.2 | 1.7.4.2 |  | 113 | p | 6 | -5% | 119
304 | 6130 | 3AAePL8Vt5bI7qDxsaDX | Normal | 20 | 1.7.4.2.3 | 1.7.4.2.3 |  | 0 | p | 21 |  | 21
305 | 6685 | 2nkdQcaVv7LgM8d4dFld | Summary | 1 | 1.9.9.12 | 1.9.9.12 |  | 743 | p | 266 | -36% | 1009
306 | 6687 | RiyOBd4mBIE5Cq6C0A4h | Normal | 1 | 1.9.9.12.1 | 1.9.9.12.1 |  | 228 | p | 773 | -339% | 1001
307 | 6686 | IDiuvzfQRXyu7MCMX1jW | Normal | 5 | 1.9.9.11 | 1.9.9.11 |  | 135 | q | -135 | (-100%) | 0
308 | 7388 | subTjNOw9tjXphx2xXzW | Summary | 324 | 1.9.9.13 | 1.9.9.13 |  | 514 | q | -514 | (-100%) | 0
309 | 7389 | xTfJP5JFEqXIDmLDdKVZ | Summary | 43 | 1.9.9.13.1 | 1.9.9.13.1 |  | 514 | q | -514 | (-100%) | 0
310 | 7390 | GV26YG775A5KHHrrMIRV | Summary | 32 | 1.9.9.13.1.1 | 1.9.9.13.1.1 |  | 514 | q | -512 | (-100%) | 2
311 | 7392 | ylVP19AJuwY485wgDJEG | Normal | 10 | 1.9.9.13.1.1.2 | 1.9.9.13.1.1.2 |  | 0 | p | 7 |  | 7
312 | 7394 | zHoRZ9fggWfe9FGnA954 | Normal | 10 | 1.9.9.13.1.1.4 | 1.9.9.13.1.1.4 |  | 0 | p | 2 |  | 2
313 | 7397 | gmOEJCOmO6SQ6HMlGXfq | Summary | 12 | 1.9.9.13.1.2 | 1.9.9.13.1.2 |  | 514 | q | -514 | (-100%) | 0
314 | 7398 | ItOQSxoXEYWD5clVNK0n | Normal | 3 | 1.9.9.13.1.2.1 | 1.9.9.13.1.2.1 |  | 0 | p | 8 |  | 8
315 | 7400 | VGtguPWpaIPmF0Ojsz8a | Summary | 176 | 1.9.9.13.2 | 1.9.9.13.2 |  | 522 | q | -513 | (-98%) | 9
316 | 7403 | pHZBXvaYVwug2p7gN6jp | Summary | 17 | 1.9.9.13.2.3 | 1.9.9.13.2.3 |  | 514 | q | -514 | (-100%) | 0
317 | 7406 | WxzG2sAIbVYYiem4v3mk | Normal | 12 | 1.9.9.13.2.3.3 | 1.9.9.13.2.3.3 |  | 0 | p | 1 |  | 1
318 | 7407 | 0eiyRK1I5mgUCdtpXpqY | Summary | 44 | 1.9.9.13.2.4 | 1.9.9.13.2.4 |  | 514 | q | -514 | (-100%) | 0
319 | 7413 | xazO1XwNp5eROWJmaREL | Summary | 36 | 1.9.9.13.2.6 | 1.9.9.13.2.6 |  | 514 | q | -514 | (-100%) | 0
320 | 7420 | ia01m1zWF4qAvVLVg5It | Summary | 54 | 1.9.9.13.2.8 | 1.9.9.13.2.8 |  | 514 | q | -514 | (-100%) | 0
321 | 7422 | fj19MvsSAfWHeVGXiA1H | Normal | 5 | 1.9.9.13.2.8.2 | 1.9.9.13.2.8.2 |  | 3 | p | 1 | -33% | 4
322 | 7426 | UjcYgNHyPV73fWy2GGNA | Normal | 5 | 1.9.9.13.2.8.6 | 1.9.9.13.2.8.6 |  | 15 | q | -3 | (-20%) | 12
323 | 7430 | AjX0fOJfuCWTWcoFWrZe | Summary | 11 | 1.9.9.13.2.9 | 1.9.9.13.2.9 |  | 514 | q | -514 | (-100%) | 0
324 | 7435 | nSo6tYchIu2Aw4YtE45u | Summary | 44 | 1.9.9.13.4 | 1.9.9.13.4 |  | 514 | q | -514 | (-100%) | 0
325 | 7436 | Y83lvWkQwfsc3dMGwfVN | Summary | 30 | 1.9.9.13.4.1 | 1.9.9.13.4.1 |  | 514 | q | -514 | (-100%) | 0
326 | 7437 | E8EwVgjFQaEPGP66WsCb | Summary | 30 | 1.9.9.13.4.1.1 | 1.9.9.13.4.1.1 |  | 514 | q | -506 | (-98%) | 8
327 | 7440 | 3ZzL4TktDwncii0hY2dA | Normal | 10 | 1.9.9.13.4.1.1.3 | 1.9.9.13.4.1.1.3 |  | 0 | p | 7 |  | 7
328 | 7441 | IcgrxiRjEYJLwuugm8N7 | Summary | 30 | 1.9.9.13.4.1.2 | 1.9.9.13.4.1.2 |  | 514 | q | -514 | (-100%) | 0
329 | 7444 | 419IszMaZW6XNIQptprk | Normal | 20 | 1.9.9.13.4.1.3 | 1.9.9.13.4.1.3 |  | 10 | q | -3 | (-30%) | 7
330 | 7446 | NnBZUSVumxDXwVdCLN8g | Summary | 12 | 1.9.9.13.4.2 | 1.9.9.13.4.2 |  | 514 | q | -514 | (-100%) | 0
331 | 7540 | njszlznNRnCyRW2hgoMI | Normal | 10 | 1.7.10.9 | 1.7.10.9 |  | 66 | p | 1044 | -1582% | 1110
332 | 7541 | R63tw5xkvmDGiWpIPQRa | Normal | 1 | 1.7.10.10 | 1.7.10.10 |  | 55 | p | 1065 | -1936% | 1120
333 | 7542 | E3YdLEfamF0eZCISJiqw | Normal | 10 | 1.7.10.11 | 1.7.10.11 |  | 36 | p | 1076 | -2989% | 1112
334 | 7543 | nhpJxewK7uClQLzGXJQJ | Normal | 1 | 1.7.10.12 | 1.7.10.12 |  | 12 | p | 1108 | -9233% | 1120
335 | 7544 | cfuUTFyz3WOPAOOiNQOb | Normal | 1 | 1.7.10.13 | 1.7.10.13 |  | 12 | p | 1108 | -9233% | 1120
336 | 6279 | p7EJXT1muDSglD2OZLFH | Summary | 274 | 1.9.7 | 1.9.7 |  | 526 | q | -513 | (-98%) | 13
337 | 1484 | 6ARiGRg3KLswRpJLOmGD | Summary | 229 | 1.9.7.18 | 1.9.7.18 |  | 648 | p | 393 | -61% | 1041
338 | 1486 | 9VYbXOz4xuMas0igEBkB | Summary | 56 | 1.9.7.18.6 | 1.9.7.18.6 |  | 206 | p | 1951 | -947% | 2157
339 | 1489 | pYq4lU1lCt1U75q3gu6M | Normal | 11 | 1.9.7.18.1 | 1.9.7.18.1 |  | 0 | p | 1041 |  | 1041
340 | 1529 | WOa3B8SPUOSM5ThLE2Jo | Summary | 69 | 1.9.7.14 | 1.9.7.14 |  | 818 | p | 135 | -17% | 953
341 | 1532 | fQ3wcWF8uEWMRGpUCxEA | Normal | 1 | 1.9.7.14.4 | 1.9.7.14.4 |  | 22 | p | 21 | -95% | 43
342 | 4583 | QzcCl72pVAI4zSVR8VAE | Normal | 1 | 1.9.7.14.3 | 1.9.7.14.3 |  | 2 | p | 120 | -6000% | 122
343 | 1535 | vIOpwJGhGrQ4pKl5nahR | Summary | 61 | 1.9.7.15 | 1.9.7.15 |  | 322 | q | -22 | (-7%) | 300
344 | 4585 | Z4QB23UBk58Dyd3318zD | Normal | 10 | 1.9.7.15.6 | 1.9.7.15.6 |  | 37 | p | 24 | -65% | 61
345 | 1544 | dYtuUpkdltDWUtvWJGdC | Summary | 80 | 1.9.7.16 | 1.9.7.16 |  | 355 | p | 4 | -1% | 359
346 | 1551 | FTwSjNJQyZH6RsSSqWG9 | Summary | 78 | 1.9.7.19 | 1.9.7.19 |  | 322 | q | -1 | 0% | 321
347 | 4572 | 5hxJeLGqqaIlIue4XwRC | Normal | 1 | 1.9.7.2 | 1.9.7.2 |  | 32 | q | -32 | (-100%) | 0
348 | 4574 | z7UYZlhr663oN8lfFWmH | Summary | 29 | 1.9.7.11 | 1.9.7.11 |  | 760 | p | 162 | -21% | 922
349 | 1497 | q56IdotBOPeXlK3605d6 | Normal | 1 | 1.9.7.11.4 | 1.9.7.11.4 |  | 0 | p | 2 |  | 2
350 | 1506 | zNKWNUMZ7wFR6LBQ8bZ2 | Normal | 1 | 1.9.7.11.5 | 1.9.7.11.5 |  | 246 | p | 676 | -275% | 922
351 | 1509 | xdWSZU8MxGE52WBHNu6X | Normal | 1 | 1.9.7.11.3 | 1.9.7.11.3 |  | 338 | p | 640 | -189% | 978
352 | 6440 | u5F2XJPKXxmZ5m99Yx5A | Normal | 1 | 1.9.7.11.7 | 1.9.7.11.7 |  | 312 | p | 661 | -212% | 973
353 | 4575 | nPe6rBdPLk408ntp39jn | Normal | 1 | 1.9.7.3 | 1.9.7.3 |  | 286 | p | 1122 | -392% | 1408
354 | 4578 | kBeLaux8MTugqoi5KPvZ | Summary | 74 | 1.9.7.13 | 1.9.7.13 |  | 355 | p | 4 | -1% | 359
355 | 1518 | qXbL36bdYftxHm1TCntK | Normal | 1 | 1.9.7.13.4 | 1.9.7.13.4 |  | 308 | p | 428 | -139% | 736
356 | 4581 | FxGRGf2kppDMdfFrZkS4 | Normal | 36 | 1.9.7.12 | 1.9.7.12 |  | 34 | q | -11 | (-32%) | 23
357 | 4588 | L1kgBhMEjlIJ4HNHh1TQ | Summary | 141 | 1.9.7.20 | 1.9.7.20 |  | 672 | p | 145 | -22% | 817
358 | 1569 | DVuFJt4FGQSIgeZkA41d | Normal | 4 | 1.9.7.20.4 | 1.9.7.20.4 |  | 158 | p | 659 | -417% | 817
359 | 4590 | 21lrGsmJiPqRYOd4yY3H | Summary | 2 | 1.9.7.21 | 1.9.7.21 |  | 514 | q | -514 | (-100%) | 0
360 | 7323 | p8rF5Tk8321hO30p5zSy | Summary | 79 | 1.7.8.18 | 1.7.8.18 |  | 818 | p | 135 | -17% | 953
361 | 7456 | 3cfjdZ38xGBNf8roD7He | Normal | 9 | 1.7.8.18.3 | 1.7.8.18.3 |  | 3 | q | -3 | (-100%) | 0
362 | 7457 | abNwDWOnFoe0xwhiRueS | Normal | 1 | 1.7.8.18.4 | 1.7.8.18.4 |  | 12 | q | -12 | (-100%) | 0
363 | 7324 | GVXYroUMjcAFUHa4B19H | Normal | 1 | 1.7.8.19 | 1.7.8.19 |  | 5 | p | 388 | -7760% | 393
364 | 7382 | GJk3wpkfagyrb21gVciV | Summary | 288 | 1.9.7.22 | 1.9.7.22 |  | 538 | q | -510 | (-95%) | 28
365 | 7385 | cYlWo9e2zkkP7jtt7iLZ | Normal | 1 | 1.9.7.22.3 | 1.9.7.22.3 |  | 258 | p | 1056 | -409% | 1314
366 | 7386 | F9n9tFj3S3xXbwXNgAjU | Normal | 5 | 1.9.7.22.4 | 1.9.7.22.4 |  | 24 | q | -1 | (-4%) | 23
367 | 6285 | 0inPdnysTnfuJeCJJEwo | Summary | 131 | 1.9.1 | 1.9.1 |  | 190 | q | -15 | (-8%) | 175
368 | 4595 | 0i30zTvKTrSo3R9n999e | Normal | 2 | 1.9.1.3 | 1.9.1.3 |  | 29 | p | 12 | -41% | 41
369 | 4607 | 9Rf8xh1sYqA0mX8AIEgx | Summary | 52 | 1.7.3.5 | 1.7.3.5 |  | 219 | q | -20 | (-9%) | 199
370 | 4615 | Io6EVgFdyRjG7CB2g0Wy | Summary | 98 | 1.7.3.4 | 1.7.3.4 |  | 269 | q | -25 | (-9%) | 244
371 | 4618 | mRqsjEijsp2iSp4l7aof | Normal | 5 | 1.7.3.4.3 | 1.7.3.4.3 |  | 65 | p | 1 | -2% | 66
372 | 4619 | 8asUr7UOO8nabPagFvw9 | Normal | 40 | 1.7.3.4.4 | 1.7.3.4.4 |  | 31 | p | 5 | -16% | 36
373 | 4620 | UWR5akRFo4eKiDyQVnYr | Normal | 23 | 1.7.3.4.5 | 1.7.3.4.5 |  | 47 | p | 13 | -28% | 60
374 | 4626 | 92oajspBBxTpnlNQO91I | Summary | 90 | 1.7.3.6 | 1.7.3.6 |  | 190 | q | -15 | (-8%) | 175
375 | 4635 | vrd0V7BeylNxhzgI26F9 | Normal | 8 | 1.7.3.6.11 | 1.7.3.6.11 |  | 151 | q | -1 | (-1%) | 150
376 | 4664 | DAxARpEpHAwipBCK81bc | Normal | 8 | 1.7.3.6.10 | 1.7.3.6.10 |  | 151 | q | -1 | (-1%) | 150
377 | 4637 | ohQUE8EwZLGEmkE5FTpA | Summary | 8 | 1.7.3.7 | 1.7.3.7 |  | 219 | q | -18 | (-8%) | 201
378 | 6608 | ifCvUSq9UjUAw7FKKXTR | Normal | 14 | 1.7.3.7.3 | 1.7.3.7.3 |  | 0 | p | 2 |  | 2
379 | 6294 | Jtjxi70STISSeVqV8OJy | Summary | 163 | 1.9.6 | 1.9.6 |  | 530 | q | -437 | (-82%) | 93
380 | 3745 | D0mR64Wbk6oru5hoL4DG | Summary | 62 | 1.7.1.2 | 1.7.1.2 |  | 351 | q | -21 | (-6%) | 330
381 | 3773 | jfB1zdAbu7JeWEH3ijwy | Summary | 73 | 1.7.1.2.6 | 1.7.1.2.6 |  | 351 | q | -21 | (-6%) | 330
382 | 3777 | YuGKQIQDxLVYRZzgUQjw | Normal | 9 | 1.7.1.2.6.4 | 1.7.1.2.6.4 |  | 351 | q | -21 | (-6%) | 330
383 | 3783 | FcDlmkxQNUOM36qP0M0H | Summary | 58 | 1.7.1.3 | 1.7.1.3 |  | 313 | q | -22 | (-7%) | 291
384 | 3790 | Om0YwWoKF5usOVLnDccR | Summary | 13 | 1.7.1.3.4 | 1.7.1.3.4 |  | 313 | q | -22 | (-7%) | 291
385 | 6138 | EvFVoaLHb5OgszmS4Hdy | Summary | 44 | 1.7.1.3.9 | 1.7.1.3.9 |  | 313 | q | -22 | (-7%) | 291
386 | 6140 | mO0F0FFUdRVKYlb84WcT | Normal | 15 | 1.7.1.3.9.2 | 1.7.1.3.9.2 |  | 313 | q | -22 | (-7%) | 291
387 | 6983 | PcmQnh6ym2R5IAKzFgwu | Summary | 141 | 1.7.1.3.7 | 1.7.1.3.7 |  | 313 | q | -22 | (-7%) | 291
388 | 6986 | 31qYZ6wVIReV9ZOAqgem | Summary | 9 | 1.7.1.3.7.5 | 1.7.1.3.7.5 |  | 313 | q | -22 | (-7%) | 291
389 | 6990 | K8cvVDryBsyahUujiNmr | Summary | 22 | 1.7.1.3.8 | 1.7.1.3.8 |  | 330 | q | -12 | (-4%) | 318
390 | 6982 | E06yVWmTg8kRS6Gv9kOV | Summary | 6 | 1.7.1.3.8.3 | 1.7.1.3.8.3 |  | 314 | q | -19 | (-6%) | 295
391 | 6137 | gagQpjsDXV4QnJ1bUthb | Normal | 2 | 1.7.1.3.8.3.1 | 1.7.1.3.8.3.1 |  | 33 | p | 1 | -3% | 34
392 | 6991 | RAhO7UtYgqwLkhTknwrO | Normal | 6 | 1.7.1.3.8.1 | 1.7.1.3.8.1 |  | 0 | p | 38 |  | 38
393 | 3803 | vx1oFVBFPqydBxZJ7V4g | Summary | 112 | 1.7.1.5 | 1.7.1.5 |  | 311 | q | -35 | (-11%) | 276
394 | 3808 | mNtnU9AYiACOeBrTPE9f | Summary | 29 | 1.7.1.5.3 | 1.7.1.5.3 |  | 330 | q | -22 | (-7%) | 308
395 | 3811 | wGtgxCT3lCK6u2EOL8xN | Normal | 5 | 1.7.1.5.3.3 | 1.7.1.5.3.3 |  | 11 | p | 12 | -109% | 23
396 | 3814 | c3HTuVFoRVefrW72mxSE | Normal | 3 | 1.7.1.5.8 | 1.7.1.5.8 |  | 8 | q | -8 | (-100%) | 0
397 | 3816 | 6MWmVgC0FSCF3lMoTGjJ | Summary | 40 | 1.7.1.5.10 | 1.7.1.5.10 |  | 311 | q | -35 | (-11%) | 276
398 | 3819 | FSVjbKFfUmqE2fpbGGPv | Normal | 3 | 1.7.1.5.10.3 | 1.7.1.5.10.3 |  | 0 | p | 9 |  | 9
399 | 3821 | cHjYAw102skS4vR6DXqX | Normal | 20 | 1.7.1.5.10.5 | 1.7.1.5.10.5 |  | 311 | q | -35 | (-11%) | 276
400 | 4078 | ybbKeBChK3D60QzH8ONZ | Normal | 76 | 1.9.6.5 | 1.9.6.5 |  | 205 | p | 643 | -314% | 848
401 | 4129 | G6dPcJRrq5zqLYx4Vr0R | Summary | 475 | 1.9.6.10 | 1.9.6.10 |  | 514 | q | -509 | (-99%) | 5
402 | 4131 | 3WZTLr4e3INGux4LMgj0 | Summary | 146 | 1.9.6.10.2 | 1.9.6.10.2 |  | 172 | q | -172 | (-100%) | 0
403 | 5857 | g9TizAnooUcHoXglcd4n | Milestone | 0 | 1.9.6.10.2.1 | 1.9.6.10.2.1 |  | 31 | q | -31 | (-100%) | 0
404 | 5859 | RMhsXtyk4773BtipN2HO | Normal | 1 | 1.9.6.10.2.3 | 1.9.6.10.2.3 |  | 43 | q | -43 | (-100%) | 0
405 | 5870 | rLlKwDBGmyMe6lxLtymf | Summary | 59 | 1.9.6.10.3 | 1.9.6.10.3 |  | 172 | q | -172 | (-100%) | 0
406 | 5876 | 5ZRJqmbhPGswffOWtWat | Normal | 1 | 1.9.6.10.3.8 | 1.9.6.10.3.8 |  | 172 | q | -172 | (-100%) | 0
407 | 5877 | 8uIO0L3CbsjXfYIL70ur | Summary | 162 | 1.9.6.10.4 | 1.9.6.10.4 |  | 514 | q | -509 | (-99%) | 5
408 | 5878 | eKJmpIIS7eePXp789pq5 | Summary | 60 | 1.9.6.10.4.1 | 1.9.6.10.4.1 |  | 615 | q | -454 | (-74%) | 161
409 | 5879 | CJrwB1y6NRnYYg7kpaRv | Summary | 30 | 1.9.6.10.4.1.1 | 1.9.6.10.4.1.1 |  | 615 | q | -454 | (-74%) | 161
410 | 5883 | 3J3dFKPf8v7HKW1lSal4 | Normal | 15 | 1.9.6.10.4.1.3 | 1.9.6.10.4.1.3 |  | 102 | p | 55 | -54% | 157
411 | 5884 | J3ZDJxR9DKKi4JquRb3Q | Summary | 20 | 1.9.6.10.4.2 | 1.9.6.10.4.2 |  | 644 | q | -454 | (-70%) | 190
412 | 5894 | AO4SgiivKvvxQJupi2GS | Normal | 1 | 1.9.6.10.4.7 | 1.9.6.10.4.7 |  | 130 | p | 55 | -42% | 185
413 | 4134 | 86JmjjOtZxj7XQRp3CQF | Summary | 466 | 1.9.6.11 | 1.9.6.11 |  | 530 | q | -312 | (-59%) | 218
414 | 4135 | 0voiyAtBe9AzaXfs8cVF | Summary | 322 | 1.9.6.11.1 | 1.9.6.11.1 |  | 530 | q | -312 | (-59%) | 218
415 | 4140 | Lk7gef35zB3WaxM8Xyxe | Summary | 48 | 1.9.6.11.2 | 1.9.6.11.2 |  | 530 | q | -312 | (-59%) | 218
416 | 4141 | HGo5Ep3pqhcsiM5K4QjA | Summary | 23 | 1.9.6.11.2.1 | 1.9.6.11.2.1 |  | 530 | q | -312 | (-59%) | 218
417 | 4144 | zaFQ6K5wegGvKt6DGuoz | Summary | 25 | 1.9.6.11.2.2 | 1.9.6.11.2.2 |  | 530 | q | -312 | (-59%) | 218
418 | 4147 | hQaW5HIstT5bbsPEBxyQ | Normal | 10 | 1.9.6.11.2.2.3 | 1.9.6.11.2.2.3 |  | 20 | q | -20 | (-100%) | 0
419 | 5753 | ZptYdARXANY2IOcoHhB1 | Summary | 78 | 1.9.6.1 | 1.9.6.1 |  | 275 | q | -275 | (-100%) | 0
420 | 5998 | aRBXPvE6pbVbcbhlDtu4 | Summary | 47 | 1.9.6.1.7 | 1.9.6.1.7 |  | 203 | q | -203 | (-100%) | 0
421 | 6003 | zkyCYMQIHOywdkyzbjbi | Summary | 48 | 1.9.6.1.8 | 1.9.6.1.8 |  | 275 | q | -275 | (-100%) | 0
422 | 6006 | HEKaqqmbwSXnCRXB6fED | Normal | 1 | 1.9.6.1.8.3 | 1.9.6.1.8.3 |  | 1 | q | -1 | (-100%) | 0
423 | 6007 | vdBzwsumrXxpXNAKvnKh | Normal | 1 | 1.9.6.1.8.4 | 1.9.6.1.8.4 |  | 275 | q | -275 | (-100%) | 0
424 | 6008 | Ph5VFx7Ghit4AwZEFBXT | Summary | 50 | 1.9.6.1.6 | 1.9.6.1.6 |  | 203 | q | -203 | (-100%) | 0
425 | 6012 | Z1jpWQx4GyFcVoEVg0i0 | Normal | 5 | 1.9.6.1.6.4 | 1.9.6.1.6.4 |  | 26 | q | -26 | (-100%) | 0
426 | 6013 | y2dxMv99iLhGOXikZGuK | Summary | 34 | 1.9.6.1.5 | 1.9.6.1.5 |  | 203 | q | -26 | (-13%) | 177
427 | 6017 | VCyTBN0y7V3erCRNMvm4 | Normal | 4 | 1.9.6.1.5.4 | 1.9.6.1.5.4 |  | 57 | p | 180 | -316% | 237
428 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | 14 | q | -14 | (-100%) | 0
429 | 6957 | ar01N24L63iczVEh1mVo | Summary | 24 | 1.9.6.1.4 | 1.9.6.1.4 |  | 203 | q | -26 | (-13%) | 177
430 | 6961 | NOksVV7sTymsgwMrnh6x | Normal | 10 | 1.9.6.1.4.4 | 1.9.6.1.4.4 |  | 15 | q | -1 | (-7%) | 14
431 | 5762 | BY50RWHTB6QfyvgvJksd | Summary | 36 | 1.9.6.9 | 1.9.6.9 |  | 696 | p | 126 | -18% | 822
432 | 4075 | dGbNHsOLhslKk8CjhyjE | Normal | 1 | 1.9.6.9.3 | 1.9.6.9.3 |  | 164 | p | 630 | -384% | 794
433 | 6424 | xU9ngPKik2IYPonksYTK | Summary | 24 | 1.7.1.8 | 1.7.1.8 |  | 903 | p | 214 | -24% | 1117
434 | 6427 | NeAxFJaqSLize8VPNJ6N | Normal | 1 | 1.7.1.8.3 | 1.7.1.8.3 |  | 390 | p | 727 | -186% | 1117
435 | 6296 | SlR21lje1Tex9DLMlAM1 | Summary | 222 | 1.9.8 | 1.9.8 |  | 514 | q | -514 | (-100%) | 0
436 | 4192 | vUDAXlHZqbmK6WAsX9hH | Summary | 139 | 1.9.8.1 | 1.9.8.1 |  | 638 | p | 159 | -25% | 797
437 | 4196 | 2ZwOzHGH45ywtPvfASSG | Normal | 5 | 1.9.8.1.5 | 1.9.8.1.5 |  | 125 | p | 672 | -538% | 797
438 | 4197 | 4xVk2zrTd9sJnt9BJFir | Summary | 36 | 1.9.8.1.6 | 1.9.8.1.6 |  | 782 | p | 171 | -22% | 953
439 | 5974 | cJ7VeFZezCBnvYlHxCmb | Normal | 1 | 1.9.8.1.6.7 | 1.9.8.1.6.7 |  | 268 | p | 740 | -276% | 1008
440 | 4222 | uotgqiCu1xVBvHdpBC3E | Summary | 97 | 1.9.8.2 | 1.9.8.2 |  | 532 | p | 153 | -29% | 685
441 | 4231 | 8h0WH2qeIC7tfvcerCPa | Normal | 1 | 1.9.8.2.3 | 1.9.8.2.3 |  | 15 | p | 148 | -987% | 163
442 | 4238 | ReJqSs3gutB053iVY5c7 | Summary | 76 | 1.9.8.4 | 1.9.8.4 |  | 314 | q | -29 | (-9%) | 285
443 | 4243 | LpPx7AWOh1V8dzWVWc6j | Normal | 1 | 1.9.8.4.5 | 1.9.8.4.5 |  | 0 | p | 277 |  | 277
444 | 4246 | ANAzXnUTz1PCb3xsov4Y | Normal | 10 | 1.9.8.4.7 | 1.9.8.4.7 |  | 46 | q | -41 | (-89%) | 5
445 | 4248 | E1RJwJWM8qrsKP3o7Toy | Normal | 1 | 1.9.8.7 | 1.9.8.7 |  | 4 | q | -4 | (-100%) | 0
446 | 4251 | IBg36OMMKUy3vwEnRNF0 | Normal | 1 | 1.9.8.6 | 1.9.8.6 |  | 45 | p | 447 | -993% | 492
447 | 4253 | hnujWIe1JDNg9VHs3TWw | Normal | 1 | 1.9.8.8 | 1.9.8.8 |  | 264 | p | 16 | -6% | 280
448 | 4255 | TAfq40Sin0H6Q2YT0OS5 | Milestone | 0 | 1.9.8.3 | 1.9.8.3 |  | 0 | p | 658 |  | 658
449 | 4256 | G2pYfP7dsnHVTgqQD6mD | Summary | 82 | 1.9.8.10 | 1.9.8.10 |  | 151 | p | 538 | -356% | 689
450 | 6090 | LkexiRQNUDyJAwm8EPYV | Normal | 32 | 1.9.8.10.7 | 1.9.8.10.7 |  | 151 | p | 538 | -356% | 689
451 | 6083 | 3dsblDK1X9ztc27EZU3v | Normal | 1 | 1.9.8.5 | 1.9.8.5 |  | 112 | p | 6 | -5% | 118
452 | 6084 | deZM0xh115wln716GUoI | Normal | 1 | 1.9.8.9 | 1.9.8.9 |  | 514 | q | -514 | (-100%) | 0
453 | 7321 | CTokiQfH6gyOyeZJGrxP | Normal | 1 | 1.7.9.11 | 1.7.9.11 |  | 49 | p | 443 | -904% | 492
454 | 6314 | PaZTrKFuMaJQzXHDclW5 | Summary | 34 | 1.9.2 | 1.9.2 |  | 712 | p | 129 | -18% | 841
455 | 5666 | lc2LPCzbTjVw9vZ8eS89 | Summary | 23 | 1.9.2.2 | 1.9.2.2 |  | 712 | p | 129 | -18% | 841
456 | 5667 | chBvra0KGhqU3lfHBAI4 | Summary | 23 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 712 | p | 129 | -18% | 841
457 | 5672 | 2GDxhVAL0LbO4lfSMjXo | Summary | 47 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 712 | p | 129 | -18% | 841
458 | 5690 | jLB7gq1wR8egZrMIoAc7 | Summary | 24 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 712 | p | 129 | -18% | 841
459 | 5697 | 4nIBzBv3LSP60HeOLv0f | Normal | 5 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 199 | p | 642 | -323% | 841
460 | 6315 | 2iW64uJmzViIcLEo0dMn | Summary | 181 | 1.9.5 | 1.9.5 |  | 538 | q | -514 | (-96%) | 24
461 | 5532 | NHN4dwEEPEqCDqA4Rwlr | Summary | 74 | 1.9.5.1 | 1.9.5.1 |  | 638 | p | 105 | -16% | 743
462 | 5533 | g1oQNBzKk6OrBukgGH7R | Normal | 40 | 1.9.5.1.3 | 1.9.5.1.3 |  | 56 | q | -56 | (-100%) | 0
463 | 5535 | XVk7S0ldLHQUWflKhMBn | Normal | 11 | 1.9.5.1.2 | 1.9.5.1.2 |  | 79 | p | 651 | -824% | 730
464 | 5536 | cYU0DBZylLxVRoLEp7Bc | Normal | 40 | 1.9.5.1.4 | 1.9.5.1.4 |  | 36 | p | 627 | -1742% | 663
465 | 5537 | 9xVQhmyTVkChMoMOy91g | Summary | 193 | 1.9.5.2 | 1.9.5.2 |  | 538 | q | -514 | (-96%) | 24
466 | 5540 | GKx3XnA1BSbhTsgdKbqP | Normal | 14 | 1.9.5.2.8 | 1.9.5.2.8 |  | 0 | p | 1 |  | 1
467 | 5544 | cIc3ARzcdrbXv6maHllr | Summary | 129 | 1.9.5.2.13 | 1.9.5.2.13 |  | 538 | q | -514 | (-96%) | 24
468 | 5557 | U376LwOjKfNZoVLUlmMD | Summary | 113 | 1.9.5.2.12 | 1.9.5.2.12 |  | 538 | q | -514 | (-96%) | 24
469 | 5570 | MuDwSgsBJjDxwFkSMWYJ | Summary | 116 | 1.9.5.2.11 | 1.9.5.2.11 |  | 548 | q | -503 | (-92%) | 45
470 | 5582 | 6tLu8emqwotxTkeBbEpy | Normal | 26 | 1.9.5.2.11.11 | 1.9.5.2.11.11 |  | 9 | p | 13 | -144% | 22
471 | 5583 | gkFBoXdv1oJb2jtBcO5M | Summary | 147 | 1.9.5.2.14 | 1.9.5.2.14 |  | 538 | q | -514 | (-96%) | 24
472 | 6999 | AnycnugTW971av3hMZXE | Normal | 8 | 1.9.5.2.14.1 | 1.9.5.2.14.1 |  | 43 | p | 634 | -1474% | 677
473 | 6446 | XvbStahAymwCoqNIbMJG | Summary | 32 | 1.9.5.2.4 | 1.9.5.2.4 |  | 526 | p | 396 | -75% | 922
474 | 6532 | 15e7xcLR1b1jSikaz0S2 | Normal | 32 | 1.9.5.2.4.2 | 1.9.5.2.4.2 |  | 33 | p | 909 | -2755% | 942
475 | 6533 | b0mutjzKj8FRw4zkbb8K | Normal | 32 | 1.9.5.2.4.1 | 1.9.5.2.4.1 |  | 13 | p | 902 | -6938% | 915
476 | 6534 | 8Gl2bk4Fxxo2fsClDJqG | Normal | 32 | 1.9.5.2.4.3 | 1.9.5.2.4.3 |  | 43 | p | 909 | -2114% | 952
477 | 6535 | dWze9AnK8NrEMD9LOEyU | Normal | 32 | 1.9.5.2.4.4 | 1.9.5.2.4.4 |  | 56 | p | 910 | -1625% | 966
478 | 6528 | LROLnQke0gWnMONa67YB | Summary | 50 | 1.9.5.2.5 | 1.9.5.2.5 |  | 524 | p | 117 | -22% | 641
479 | 6531 | iX155TL3hNg9Ca4Bsb4A | Normal | 35 | 1.9.5.2.5.2 | 1.9.5.2.5.2 |  | 10 | p | 631 | -6310% | 641
480 | 5596 | upn4QoZvaKBmBMoyhnq5 | Summary | 90 | 1.9.5.3 | 1.9.5.3 |  | 538 | q | -514 | (-96%) | 24
481 | 5597 | zKJsJYNcPRFZ7wBjvprv | Normal | 18 | 1.9.5.3.1 | 1.9.5.3.1 |  | 15 | p | 2 | -13% | 17
482 | 5598 | zvvzNQqIPXzcVRwy0N44 | Summary | 52 | 1.9.5.3.2 | 1.9.5.3.2 |  | 538 | q | -514 | (-96%) | 24
483 | 5600 | oTkX6bjokLXQ590hdeFy | Normal | 12 | 1.9.5.3.2.2 | 1.9.5.3.2.2 |  | 4 | p | 3 | -75% | 7
484 | 5603 | dwMYG7lg76TqxtTxZNCR | Normal | 5 | 1.9.5.3.3 | 1.9.5.3.3 |  | 25 | q | -1 | (-4%) | 24
485 | 6189 | OaskfHPb0rGXxqxmUlvr | Summary | 69 | 1.7.2.7 | 1.7.2.7 |  | 336 | q | -29 | (-9%) | 307
486 | 6248 | DGpV8AP7Q4dyYuiDaoIl | Summary | 56 | 1.7.2.7.2 | 1.7.2.7.2 |  | 336 | q | -29 | (-9%) | 307
487 | 6251 | Ha7ZmVRhPp4EjAGEFQOQ | Normal | 56 | 1.7.2.7.2.3 | 1.7.2.7.2.3 |  | 336 | q | -29 | (-9%) | 307
488 | 6252 | FwTW8u2nmxBgH6wyvtoz | Summary | 56 | 1.7.2.7.3 | 1.7.2.7.3 |  | 336 | q | -21 | (-6%) | 315
489 | 6255 | 6Rcxv4eHz2WhxfD2wxtd | Normal | 56 | 1.7.2.7.3.3 | 1.7.2.7.3.3 |  | 336 | q | -21 | (-6%) | 315
490 | 6256 | TcRehVKUpIeirJTvWiO5 | Summary | 14 | 1.7.2.7.4 | 1.7.2.7.4 |  | 378 | q | -21 | (-6%) | 357
491 | 6259 | q6ww59eaDtL5Df1J4lsR | Normal | 14 | 1.7.2.7.4.3 | 1.7.2.7.4.3 |  | 378 | q | -21 | (-6%) | 357
492 | 6260 | nYwGXpoj6WqcdUPfZoTk | Summary | 14 | 1.7.2.7.5 | 1.7.2.7.5 |  | 378 | q | -23 | (-6%) | 355
493 | 6263 | aKytB1b2oD2t1WVaznUP | Normal | 14 | 1.7.2.7.5.3 | 1.7.2.7.5.3 |  | 378 | q | -23 | (-6%) | 355
494 | 6317 | NzqiT3qChWGoVO5Oxj9C | Summary | 111 | 1.9.4 | 1.9.4 |  | 776 | q | -298 | (-38%) | 478
495 | 5355 | lohINUHwZqjP23W1PYQO | Summary | 26 | 1.9.4.1 | 1.9.4.1 |  | 650 | p | 147 | -23% | 797
496 | 5358 | Tenn83cNUrlWZNLgXJG2 | Normal | 2 | 1.9.4.1.2 | 1.9.4.1.2 |  | 40 | q | -40 | (-100%) | 0
497 | 5360 | ARncD9Nx3De5DONPy9Bs | Normal | 3 | 1.9.4.1.4 | 1.9.4.1.4 |  | 0 | p | 307 |  | 307
498 | 5362 | 4bsxfawvV6TKTvCq9VoB | Summary | 6 | 1.9.4.2 | 1.9.4.2 |  | 684 | q | -194 | (-28%) | 490
499 | 5368 | NKJL1ZJN3KgUArkbA4qS | Normal | 3 | 1.9.4.2.4 | 1.9.4.2.4 |  | 34 | q | -34 | (-100%) | 0
500 | 5375 | zkXPpJkHw8DPAtspwcmA | Summary | 124 | 1.9.4.4 | 1.9.4.4 |  | 650 | q | -172 | (-26%) | 478
501 | 5376 | zSTdFwWI5FOaluV37lYS | Normal | 63 | 1.9.4.4.1 | 1.9.4.4.1 |  | 47 | q | -47 | (-100%) | 0
502 | 5377 | Wv5w7NMYDRM71nE6dVi0 | Summary | 58 | 1.9.4.5 | 1.9.4.5 |  | 844 | q | -102 | (-12%) | 742
503 | 5379 | 7aIIakNe0KPRF0TCK1un | Normal | 2 | 1.9.4.5.2 | 1.9.4.5.2 |  | 926 | q | -926 | (-100%) | 0
504 | 5387 | 9gTKo9vjb1rQAbWcTOOW | Summary | 58 | 1.9.4.6 | 1.9.4.6 |  | 844 | q | -94 | (-11%) | 750
505 | 5389 | 0FrUudkzBjpolAMz4tT0 | Normal | 2 | 1.9.4.6.2 | 1.9.4.6.2 |  | 926 | q | -926 | (-100%) | 0
506 | 5396 | FNjsTUKVT29tBcVlvaM6 | Normal | 15 | 1.9.4.6.9 | 1.9.4.6.9 |  | 0 | p | 8 |  | 8
507 | 5397 | KGrMeH5y6HH9dj1tr8uB | Summary | 53 | 1.9.4.7 | 1.9.4.7 |  | 602 | p | 140 | -23% | 742
508 | 5402 | zDUD70mdAG3rcozejCwk | Summary | 15 | 1.9.4.8 | 1.9.4.8 |  | 602 | q | -124 | (-21%) | 478
509 | 5403 | wP2WbhW6upJb7JmdzCw1 | Normal | 9 | 1.9.4.8.1 | 1.9.4.8.1 |  | 0 | p | 264 |  | 264
510 | 5404 | UrewlDJ3J2c8Ueci7p9E | Normal | 6 | 1.9.4.8.2 | 1.9.4.8.2 |  | 89 | p | 389 | -437% | 478
511 | 7264 | vNqQNKJIEgg8BiBzdWeI | Summary | 57 | 1.7.4.3.6 | 1.7.4.3.6 |  | 650 | q | -160 | (-25%) | 490
512 | 7269 | 7v5GPnNw6yREyKfoeMiZ | Normal | 5 | 1.7.4.3.6.5 | 1.7.4.3.6.5 |  | 0 | p | 12 |  | 12
513 | 7322 | XsHCl5GkwKVP3xy7r0jT | Summary | 85 | 1.7.5 | 1.7.5 |  | 293 | p | 391 | -133% | 684
514 | 7529 | ugdLGMeRoSNQZE98ehwR | Normal | 8 | 1.7.5.2 | 1.7.5.2 |  | 0 | p | 3 |  | 3
515 | 7537 | ZiOXL4e3BgetRuJ4aYKK | Normal | 1 | 1.7.5.10 | 1.7.5.10 |  | 38 | p | 398 | -1047% | 436
516 | 6688 | aKOlgm9Tw9oPXF0YCFLp | Summary | 911 | 1.11 | 1.11 |  | 1 | p | 566 | -56600% | 567
517 | 6689 | fEYxMDiPOAwjjU8zha5c | Normal | 396 | 1.11.1 | 1.11.1 |  | 78 | p | 681 | -873% | 759
518 | 6690 | bopLkaAZbmZjIM9EGI6L | Normal | 532 | 1.11.2 | 1.11.2 |  | 1 | p | 859 | -85900% | 860
519 | 6691 | xLErpFHjPEH3ifHRbBMY | Normal | 396 | 1.11.3 | 1.11.3 |  | 78 | p | 489 | -627% | 567
520 | 6692 | g8WcEZ6I6SGdlePHrYPP | Normal | 248 | 1.11.4 | 1.11.4 |  | 122 | p | 613 | -502% | 735
521 | 6695 | Bx0BPJ0BcPw49QEL7Psq | Normal | 313 | 1.11.8 | 1.11.8 |  | 100 | p | 707 | -707% | 807
522 | 6696 | XbFIp383UbA72xJPH4hJ | Normal | 101 | 1.11.9 | 1.11.9 |  | 268 | p | 638 | -238% | 906
523 | 6697 | gpkN7vTMpz4ZZxhDAmeL | Normal | 126 | 1.11.10 | 1.11.10 |  | 244 | p | 635 | -260% | 879
524 | 6698 | eRsel9yyFaDkcYLZgvjC | Normal | 142 | 1.11.11 | 1.11.11 |  | 272 | p | 629 | -231% | 901
525 | 6699 | k8943lu4TS9ZW2TcUvha | Normal | 256 | 1.11.12 | 1.11.12 |  | 218 | p | 546 | -250% | 764
526 | 7376 | FfEUU5kpALOu6FlmjosD | Normal | 396 | 1.10.3 | 1.10.3 |  | 82 | p | 336 | -410% | 418
527 | 7378 | YjoFZZooPnFRzsk2Ba2E | Normal | 288 | 1.10.6 | 1.10.6 |  | 126 | p | 563 | -447% | 689
528 | 7379 | 7GajZBAFakrGWC1WlgE6 | Normal | 142 | 1.10.14 | 1.10.14 |  | 272 | p | 675 | -248% | 947
529 | 7380 | wkyoOF6gHS9pA0Dm9pZY | Normal | 140 | 1.10.17 | 1.10.17 |  | 274 | p | 658 | -240% | 932
530 | 7551 | G4afE8kOleATkD8qyqeP | Normal | 1 | 1.10.19 | 1.10.19 |  | 2873 | q | -2873 | (-100%) | 0
531 | 7131 | XTX9Wl5SzTxAD1rtsh9U | Summary | 0 | 1.10 | 1.10 |  | 454 | q | -209 | (-46%) | 245
532 | 7107 | fjlRoMsMUGjOnNWoUkGJ | Milestone | 0 | 1.10.16 | 1.10.16 |  | 0 | p | 597 |  | 597
533 | 7108 | wFwSqsIrP0eolc7owrIn | Milestone | 0 | 1.10.3 | 1.10.3 |  | 349 | p | 4 | -1% | 353
534 | 7110 | fycPVr34q6lr2y2bEJNl | Milestone | 0 | 1.10.9 | 1.10.9 |  | 269 | q | -25 | (-9%) | 244
535 | 7111 | gs1r9nT3BBBdW42nHT47 | Milestone | 0 | 1.10.13 | 1.10.13 |  | 219 | q | -20 | (-9%) | 199
536 | 7112 | a270fhhuENq55tFKO8IB | Milestone | 0 | 1.10.10 | 1.10.10 |  | 190 | q | -15 | (-8%) | 175
537 | 7114 | pZqvbi91bBhqyjB86evl | Milestone | 0 | 1.10.2 | 1.10.2 |  | 124 | q | -14 | (-11%) | 110
538 | 7115 | mxRJVREYCLlOZtWGohdT | Milestone | 0 | 1.10.8 | 1.10.8 |  | 104 | q | -5 | (-5%) | 99
539 | 7116 | 4gFjRlWXKNF16b9sFMXr | Milestone | 0 | 1.10.11 | 1.10.11 |  | 234 | p | 118 | -50% | 352
540 | 7117 | zFlqKdf38AVahGy9Q9X8 | Milestone | 0 | 1.10.12 | 1.10.12 |  | 159 | p | 6 | -4% | 165
541 | 7118 | 6jNHf85fMsjQD6qn9QnY | Milestone | 0 | 1.10.14 | 1.10.14 |  | 179 | q | -17 | (-9%) | 162
542 | 7119 | OQnmDeJwrgb4ibYKrZjo | Milestone | 0 | 1.10.15 | 1.10.15 |  | 229 | p | 406 | -177% | 635
543 | 7120 | ewfCDE69jjk4Zb5M5CES | Milestone | 0 | 1.10.4 | 1.10.4 |  | 355 | p | 4 | -1% | 359
544 | 7121 | V4W6CQQo6lTjRlhYdPDq | Milestone | 0 | 1.10.5 | 1.10.5 |  | 322 | q | -22 | (-7%) | 300
545 | 7122 | ZQwX0qpiGy3bERfpXjQ0 | Milestone | 0 | 1.10.6 | 1.10.6 |  | 352 | q | -19 | (-5%) | 333
546 | 7123 | 0fpNMQTy9Zfk1YAC7GK2 | Milestone | 0 | 1.10.7 | 1.10.7 |  | 356 | p | 5 | -1% | 361
547 | 7124 | yYQOOagkBr46kWICPuG6 | Milestone | 0 | 1.10.17 | 1.10.17 |  | 243 | p | 1953 | -804% | 2196
548 | 7125 | a4xeGKWGk9YyWLffVRQZ | Milestone | 0 | 1.10.18 | 1.10.18 |  | 224 | p | 1951 | -871% | 2175
549 | 7126 | XIH51zzlt2AXqf8IkYxf | Milestone | 0 | 1.10.19 | 1.10.19 |  | 206 | p | 1951 | -947% | 2157
550 | 7129 | kvNY0frGkARL99AbSHw0 | Milestone | 0 | 1.10.22 | 1.10.22 |  | 322 | q | -1 | 0% | 321

## Calendar
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2

## Start
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Start - 1010 (48%) | Start - 1010 (48%) | Start - 1010 (48%) | Start - 1010 (48%) | Start - 1010 (48%) | Start - 1010 (48%) | Start - 1010 (48%) | Start - 1010 (48%) | Start - 1010 (48%) | Start - 1010 (48%) | Start - 1010 (48%) | Start - 1010 (48%) | Start - 1010 (48%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 152 | QJ29ZvAvtEjBcpqHDer1 | Milestone | 0 | 1.2.3 | 1.2.3 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
2 | 155 | 1yu6CrDX9QU5hWE1UWMV | Milestone | 0 | 1.2.7.11 | 1.2.7.11 |  | 2026-10-08 16:58 | p | 620 |  | 2028-06-20 14:26
3 | 166 | KkWbk0R1FXz2L56lHFvV | Normal | 2 | 1.2.7.4 | 1.2.7.4 |  | 2025-09-17 08:00 | p | 15 |  | 2025-10-02 14:07
4 | 6618 | LspmB73Oe2b9O1GVbm64 | Milestone | 0 | 1.2.7.2 | 1.2.7.2 |  | 2025-04-30 17:00 | p | 15 |  | 2025-05-16 13:13
5 | 6338 | whnkqeDzsaW1H7xphaZA | Normal | 49 | 1.2.7.3.4 | 1.2.7.3.4 |  | 2025-05-13 08:00 | p | 14 |  | 2025-05-27 08:33
6 | 6640 | QUv6m7GotPkUb98mhJX7 | Normal | 14 | 1.2.7.3.6 | 1.2.7.3.6 |  | 2025-08-27 08:00 | p | 16 |  | 2025-09-12 09:49
7 | 6872 | SjyWialEYK436pEnV5Nr | Normal | 1 | 1.2.7.5 | 1.2.7.5 |  | 2025-09-19 08:00 | p | 17 |  | 2025-10-06 13:01
8 | 6874 | 1XFpbhK6U752FQe8voXZ | Normal | 1 | 1.2.7.6 | 1.2.7.6 |  | 2026-01-29 15:00 | p | 33 |  | 2026-03-03 15:34
9 | 6878 | VU7w4voCV7rMMsz4AnPW | Normal | 1 | 1.2.7.10 | 1.2.7.10 |  | 2025-05-28 08:00 | q | 0 |  | 2025-05-27 08:17
10 | 6879 | Vbp0cBOXY9azJeyTE4S4 | Normal | 3 | 1.2.7.7 | 1.2.7.7 |  | 2026-03-17 15:00 | p | 30 |  | 2026-04-17 09:06
11 | 6880 | ZuauWvCPNW7n2NMscMO2 | Normal | 4 | 1.2.7.8 | 1.2.7.8 |  | 2026-07-24 16:58 | q | 0 |  | 2026-07-24 15:08
12 | 6881 | XekYY8n1P4vELtk4BUks | Normal | 1 | 1.2.7.9 | 1.2.7.9 |  | 2026-08-04 16:58 | q | 0 |  | 2026-08-04 11:54
13 | 7550 | fUEnUBwdI1z3bgOngjaQ | Milestone | 0 | 1.2.7.5 | 1.2.7.5 |  | 2025-11-13 08:00 | q | -37 |  | 2025-10-06 15:42
14 | 168 | MT1CsCIMkhjJER6f3fjG | Milestone | 0 | 1.2.8.4 | 1.2.8.4 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
15 | 5294 | A0MDYkkQxesjEWQub0UM | Milestone | 0 | 1.2.8.3 | 1.2.8.3 |  | 2025-09-18 17:00 | p | 17 |  | 2025-10-06 13:01
16 | 173 | vJHK0TlIBzGpfYqdt8YI | Milestone | 0 | 1.2.9.4 | 1.2.9.4 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
17 | 177 | V4ys3lAm8KEbtjGqLAuR | Milestone | 0 | 1.2.9.2 | 1.2.9.2 |  | 2025-10-21 12:00 | p | 28 |  | 2025-11-19 09:32
18 | 178 | Cncpm0GACo0ppNIEy1Gp | Milestone | 0 | 1.2.9.3 | 1.2.9.3 |  | 2025-10-27 12:00 | p | 29 |  | 2025-11-25 16:19
19 | 180 | 9Vp3PBZnh9TpV8TGBWRG | Milestone | 0 | 1.2.10.14 | 1.2.10.14 |  | 2026-09-25 17:00 | p | 104 |  | 2027-01-08 08:25
20 | 193 | nJh7oj8wCJYW8hyepdLI | Milestone | 0 | 1.2.10.12 | 1.2.10.12 |  | 2025-09-09 17:00 | p | 12 |  | 2025-09-22 16:40
21 | 194 | wTcNF86mfD2cPQPmQB1c | Milestone | 0 | 1.2.10.13 | 1.2.10.13 |  | 2026-04-02 17:00 | p | 84 |  | 2026-06-26 11:47
22 | 7132 | osdxrWYmqQZxyGZXe9Pr | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 2025-03-24 17:00 | q | -31 |  | 2025-02-21 16:57
23 | 7546 | tdocr3pqURBYHZWcAyMG | Normal | 1 | 1.2.10.12 | 1.2.10.12 |  | 2025-03-28 08:00 | q | -90 |  | 2024-12-27 08:56
24 | 7547 | 2p5uMAQ0v8mT9pq4KeWp | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 2025-03-14 08:00 | q | -80 |  | 2024-12-23 17:00
25 | 7548 | TdNnLE8G4vf1vBjggzLw | Normal | 1 | 1.2.10.15 | 1.2.10.15 |  | 2025-03-10 08:00 | q | -73 |  | 2024-12-26 08:22
26 | 7549 | yUAt6Fi3Vichq9Ai1DSh | Normal | 1 | 1.2.10.13 | 1.2.10.13 |  | 2025-02-20 08:00 | q | -58 |  | 2024-12-24 08:00
27 | 195 | jWoM7YMyhsN7uWtVDNIl | Summary | 276 | 1.2.11 | 1.2.11 |  | 2025-06-23 17:00 | p | 87 |  | 2025-09-19 09:47
28 | 196 | kzYOxx4jS6vhIcTyxNFn | Milestone | 0 | 1.2.11.11 | 1.2.11.11 |  | 2026-07-31 12:00 | p | 929 |  | 2029-02-14 13:47
29 | 197 | LZAvhCOF77OBkAngJSDi | Milestone | 0 | 1.2.11.1 | 1.2.11.1 |  | 2025-06-23 17:00 | p | 933 |  | 2028-01-13 14:31
30 | 198 | X7Nxs9NuQXJ5Bf6aQwVp | Milestone | 0 | 1.2.11.2 | 1.2.11.2 |  | 2025-07-08 17:00 | p | 939 |  | 2028-02-03 15:25
31 | 199 | TiaYdQ98Ovd3qBAfSAyG | Milestone | 0 | 1.2.11.3 | 1.2.11.3 |  | 2025-07-22 17:00 | p | 940 |  | 2028-02-18 16:01
32 | 200 | yynHcCtrZd0Ye6iQJb2E | Milestone | 0 | 1.2.11.4 | 1.2.11.4 |  | 2025-08-06 17:00 | p | 942 |  | 2028-03-06 16:52
33 | 202 | mjF0YLun5LIdlxtu3zFl | Milestone | 0 | 1.2.11.5 | 1.2.11.5 |  | 2025-08-26 17:00 | p | 23 |  | 2025-09-19 09:47
34 | 203 | 2a1x42QofxcVsgjcXtkr | Milestone | 0 | 1.2.11.6 | 1.2.11.6 |  | 2025-06-23 17:00 | p | 933 |  | 2028-01-13 14:31
35 | 204 | 8T22gllTunmLl2jY7IMk | Milestone | 0 | 1.2.11.7 | 1.2.11.7 |  | 2025-07-08 17:00 | p | 939 |  | 2028-02-03 15:25
36 | 205 | dm3U5Xjvi5rN2LqWegXW | Milestone | 0 | 1.2.11.8 | 1.2.11.8 |  | 2025-07-22 17:00 | p | 940 |  | 2028-02-18 16:01
37 | 206 | ZOAcdJHtChBG5MUjo5uw | Milestone | 0 | 1.2.11.9 | 1.2.11.9 |  | 2025-08-06 17:00 | p | 942 |  | 2028-03-06 16:52
38 | 209 | 0FNuAiL5ZzPZSZ3dZfoV | Milestone | 0 | 1.2.11.10 | 1.2.11.10 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
39 | 6077 | 9YjbRTuPDmKPhAucMUDE | Milestone | 0 | 1.2.6 | 1.2.6 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
40 | 7015 | U0mup1noPd6mH1CxWGtr | Milestone | 0 | 1.2.5 | 1.2.5 |  | 2027-01-01 08:05 | p | 840 |  | 2029-04-20 09:27
41 | 7016 | pVOP21cemlwRUbhUeRME | Milestone | 0 | 1.2.4 | 1.2.4 |  | 2027-01-07 16:58 | p | 529 |  | 2028-06-20 14:26
42 | 150 | 7cu6yvdJV8ndF0CYMHk8 | Milestone | 0 | 1.1 | 1.1 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
43 | 436 | OGXVzK31PKUn8DxCdn94 | Normal | 33 | 1.3.3.2.10 | 1.3.3.2.10 |  | 2025-03-27 08:00 | p | 11 |  | 2025-04-07 16:46
44 | 428 | pxWL5EoMWeaDmapfAV7m | Normal | 2 | 1.3.3.4.2 | 1.3.3.4.2 |  | 2025-09-17 08:00 | p | 15 |  | 2025-10-02 14:07
45 | 3859 | xrpLG6wlwOL4sRwHPU5B | Normal | 28 | 1.3.2.1.2.2.2 | 1.3.2.1.2.2.2 |  | 2025-03-17 08:00 | p | 21 |  | 2025-04-07 08:26
46 | 3861 | rvfyADOJtzNcPT3VL85f | Normal | 100 | 1.3.2.1.2.2.3 | 1.3.2.1.2.2.3 |  | 2025-05-13 08:00 | p | 14 |  | 2025-05-27 08:33
47 | 3862 | FUtleP4nAJHYxzLOWKZH | Normal | 20 | 1.3.2.1.2.2.4 | 1.3.2.1.2.2.4 |  | 2025-10-06 08:00 | p | 44 |  | 2025-11-19 09:25
48 | 3864 | kkmwKYrSq6DehQmbGkxo | Summary | 90 | 1.3.2.1.2.3.2 | 1.3.2.1.2.3.2 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
49 | 3865 | ZK3GDclfde20Vh8DU71K | Normal | 30 | 1.3.2.1.2.3.2.1 | 1.3.2.1.2.3.2.1 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
50 | 3866 | 8Zrc7ItBhrTjO1TWxqmf | Normal | 20 | 1.3.2.1.2.3.2.2 | 1.3.2.1.2.3.2.2 |  | 2025-09-05 08:00 | p | 19 |  | 2025-09-24 11:48
51 | 3867 | l8TRHVr9p6bfQBwzbTty | Normal | 5 | 1.3.2.1.2.3.2.5 | 1.3.2.1.2.3.2.5 |  | 2025-11-03 08:00 | p | 14 |  | 2025-11-17 16:33
52 | 3868 | NCkZSbtMfUxIg95lxXXn | Normal | 10 | 1.3.2.1.2.3.2.6 | 1.3.2.1.2.3.2.6 |  | 2025-11-10 08:00 | p | 15 |  | 2025-11-25 09:06
53 | 3869 | wbVbYxDNomEEsv0XDKnQ | Normal | 5 | 1.3.2.1.2.3.2.7 | 1.3.2.1.2.3.2.7 |  | 2025-11-25 08:00 | p | 13 |  | 2025-12-08 14:21
54 | 6562 | Z3AfJmLBpOLyJb1GhvwC | Normal | 10 | 1.3.2.1.2.3.2.3 | 1.3.2.1.2.3.2.3 |  | 2025-10-03 08:00 | p | 14 |  | 2025-10-17 08:06
55 | 6563 | 7FPcbor42GN7O6Ym4IZM | Normal | 10 | 1.3.2.1.2.3.2.4 | 1.3.2.1.2.3.2.4 |  | 2025-10-20 08:00 | p | 10 |  | 2025-10-30 14:23
56 | 7192 | rcBSOCAYFUxP7jsyoqGw | Normal | 11 | 1.3.2.3.2.1.1.2 | 1.3.2.3.2.1.1.2 |  | 2025-02-24 08:00 | q | -21 |  | 2025-02-03 08:00
57 | 7194 | mB0uoGZ1D1fuFzk350Kb | Normal | 30 | 1.3.2.3.2.1.2.1 | 1.3.2.3.2.1.2.1 |  | 2025-03-11 08:00 | q | -24 |  | 2025-02-14 10:33
58 | 7200 | 7Va2LPPEsZrLZmgpV2qc | Summary | 19 | 1.3.2.3.2.1.4 | 1.3.2.3.2.1.4 |  | 2025-04-22 08:00 | q | -14 |  | 2025-04-07 15:15
59 | 7201 | UKbpgMkpfrIPVoEOJEeO | Normal | 10 | 1.3.2.3.2.1.4.1 | 1.3.2.3.2.1.4.1 |  | 2025-04-22 08:00 | q | -14 |  | 2025-04-07 15:15
60 | 7202 | vy1jnuopIHJe5PhTsUNw | Normal | 5 | 1.3.2.3.2.1.4.2 | 1.3.2.3.2.1.4.2 |  | 2025-05-06 08:00 | q | -14 |  | 2025-04-21 10:40
61 | 7203 | KqVHIBvrHNAu5GlarotD | Normal | 3 | 1.3.2.3.2.1.4.3 | 1.3.2.3.2.1.4.3 |  | 2025-05-13 08:00 | q | -14 |  | 2025-04-28 14:19
62 | 7204 | BUAmcwglNtP3GEkJsPLR | Normal | 1 | 1.3.2.3.2.1.4.4 | 1.3.2.3.2.1.4.4 |  | 2025-05-16 08:00 | q | -14 |  | 2025-05-01 15:00
63 | 7207 | 51ZGrscW6XrNzeOMbLyw | Normal | 5 | 1.3.2.3.2.2.2 | 1.3.2.3.2.2.2 |  | 2025-03-18 08:00 | p | 27 |  | 2025-04-14 15:15
64 | 7208 | 5Vu53Z23NG8K3uSzUcYA | Normal | 3 | 1.3.2.3.2.2.3 | 1.3.2.3.2.2.3 |  | 2025-03-25 08:00 | p | 24 |  | 2025-04-18 11:26
65 | 7209 | r8OmtZddpdGbVxNEynIO | Normal | 1 | 1.3.2.3.2.2.4 | 1.3.2.3.2.2.4 |  | 2025-03-28 08:00 | p | 26 |  | 2025-04-23 15:28
66 | 7213 | GkAhONTSL0EMIVzc5bXh | Normal | 3 | 1.3.2.3.2.3.3 | 1.3.2.3.2.3.3 |  | 2025-02-25 08:00 | q | -3 |  | 2025-02-21 09:11
67 | 7214 | ysGFXohNyFRFQ06jmkjW | Normal | 1 | 1.3.2.3.2.3.4 | 1.3.2.3.2.3.4 |  | 2025-02-28 08:00 | q | -1 |  | 2025-02-26 09:58
68 | 7221 | PYoR7OoHLcblZDJJ1hTC | Normal | 20 | 1.3.2.3.2.4.6 | 1.3.2.3.2.4.6 |  | 2025-02-28 08:00 | p | 3 |  | 2025-03-03 15:22
69 | 7222 | W1KVKgORO9KqmU1uQFqG | Normal | 1 | 1.3.2.3.2.4.7 | 1.3.2.3.2.4.7 |  | 2025-03-28 08:00 | p | 11 |  | 2025-04-08 09:39
70 | 7228 | SSqxRWtJ8NkhLwkx3Zp5 | Normal | 15 | 1.3.2.3.2.5.5 | 1.3.2.3.2.5.5 |  | 2025-03-18 08:00 | p | 35 |  | 2025-04-22 16:25
71 | 7231 | Kz2H44CrN943Xn6RI0Et | Summary | 19 | 1.3.2.3.3 | 1.3.2.3.3 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
72 | 7232 | cCMYeGs7uzTIiiDhvAui | Summary | 12 | 1.3.2.3.3.1 | 1.3.2.3.3.1 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
73 | 7233 | rgerXXfH5cOVWHlSbXtk | Normal | 2 | 1.3.2.3.3.1.1 | 1.3.2.3.3.1.1 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
74 | 7234 | 4Nk8AWONEAABjENRSl4s | Normal | 3 | 1.3.2.3.3.1.2 | 1.3.2.3.3.1.2 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
75 | 7235 | uR7e5eYUOS8ur8CkZgir | Normal | 2 | 1.3.2.3.3.1.3 | 1.3.2.3.3.1.3 |  | 2025-07-29 08:00 | p | 15 |  | 2025-08-13 16:17
76 | 7236 | OqdHv6QLhEyFdmarh5Mg | Normal | 5 | 1.3.2.3.3.1.4 | 1.3.2.3.3.1.4 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
77 | 7237 | xLl9f1S8pVLgozw4LZw4 | Normal | 10 | 1.3.2.3.3.1.5 | 1.3.2.3.3.1.5 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
78 | 7238 | hj0QAuvemNr4BSx0wqCM | Normal | 10 | 1.3.2.3.3.1.6 | 1.3.2.3.3.1.6 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
79 | 7239 | sGRMuNmZsu5Ap3rRR6Ja | Normal | 2 | 1.3.2.3.3.1.7 | 1.3.2.3.3.1.7 |  | 2025-08-07 08:00 | p | 15 |  | 2025-08-22 13:46
80 | 7240 | jJgg05qz3M4QbDAQ4nmn | Summary | 7 | 1.3.2.3.3.2 | 1.3.2.3.3.2 |  | 2025-08-11 08:00 | p | 15 |  | 2025-08-26 10:04
81 | 7241 | RP09WyAKLetAyeWXIWbd | Normal | 1 | 1.3.2.3.3.2.1 | 1.3.2.3.3.2.1 |  | 2025-08-11 08:00 | p | 15 |  | 2025-08-26 10:04
82 | 7242 | PNiOufePi0cnwKsaAHa8 | Normal | 3 | 1.3.2.3.3.2.2 | 1.3.2.3.3.2.2 |  | 2025-08-12 08:00 | p | 15 |  | 2025-08-27 11:29
83 | 7243 | nppwsC1hz1MTRepHit5q | Normal | 3 | 1.3.2.3.3.2.3 | 1.3.2.3.3.2.3 |  | 2025-08-15 08:00 | p | 18 |  | 2025-09-02 09:31
84 | 7244 | FpvbIzqyAjmrguHRtjoA | Summary | 68 | 1.3.2.3.4 | 1.3.2.3.4 |  | 2025-08-20 08:00 | p | 16 |  | 2025-09-05 14:36
85 | 7245 | ysJ2Wz17vAaH50NFOd3r | Normal | 2 | 1.3.2.3.4.1 | 1.3.2.3.4.1 |  | 2025-08-20 08:00 | p | 16 |  | 2025-09-05 14:36
86 | 7246 | w8OYvCOBO1azAOar59yv | Normal | 3 | 1.3.2.3.4.2 | 1.3.2.3.4.2 |  | 2025-08-20 08:00 | p | 16 |  | 2025-09-05 14:36
87 | 7247 | QmLDbLdk9YgltF6FQxKi | Normal | 2 | 1.3.2.3.4.3 | 1.3.2.3.4.3 |  | 2025-08-25 08:00 | p | 16 |  | 2025-09-10 10:05
88 | 7248 | nqyBToLUXvLl91VDFcK9 | Summary | 20 | 1.3.2.3.4.4 | 1.3.2.3.4.4 |  | 2025-08-20 08:00 | p | 16 |  | 2025-09-05 14:36
89 | 7249 | T3rEQsXy5TFYVzdnmRkQ | Normal | 20 | 1.3.2.3.4.4.1 | 1.3.2.3.4.4.1 |  | 2025-08-20 08:00 | p | 16 |  | 2025-09-05 14:36
90 | 7250 | G5mdz8DmOa8TGNlmxmOk | Normal | 20 | 1.3.2.3.4.4.2 | 1.3.2.3.4.4.2 |  | 2025-08-20 08:00 | p | 16 |  | 2025-09-05 14:36
91 | 7251 | p2IEwFFq1YxDgQwaqReT | Summary | 48 | 1.3.2.3.4.5 | 1.3.2.3.4.5 |  | 2025-09-18 08:00 | p | 19 |  | 2025-10-07 14:40
92 | 7252 | R4hlQqYwslHcXudIUORM | Normal | 20 | 1.3.2.3.4.5.1 | 1.3.2.3.4.5.1 |  | 2025-09-18 08:00 | p | 19 |  | 2025-10-07 14:40
93 | 7253 | 5Q6OCjUddDwnqpg2shNG | Normal | 5 | 1.3.2.3.4.5.2 | 1.3.2.3.4.5.2 |  | 2025-10-17 08:00 | p | 24 |  | 2025-11-10 09:00
94 | 7254 | aZsc8OQGYCtOtLNUDl4p | Normal | 7 | 1.3.2.3.4.5.3 | 1.3.2.3.4.5.3 |  | 2025-10-24 08:00 | p | 25 |  | 2025-11-18 09:39
95 | 7255 | GiGIxdlKVFOGW1rlVkpg | Normal | 5 | 1.3.2.3.4.5.4 | 1.3.2.3.4.5.4 |  | 2025-11-04 08:00 | p | 22 |  | 2025-11-26 15:22
96 | 7256 | ZTFxKau19KKCcFlUDIYg | Normal | 7 | 1.3.2.3.4.5.5 | 1.3.2.3.4.5.5 |  | 2025-11-12 08:00 | p | 22 |  | 2025-12-04 15:27
97 | 7257 | EmkT3sq6aGy3vx96JSsX | Normal | 3 | 1.3.2.3.4.5.6 | 1.3.2.3.4.5.6 |  | 2025-11-21 08:00 | p | 25 |  | 2025-12-16 08:47
98 | 7258 | PBxke5bv0Yk6xXbQcvVe | Normal | 1 | 1.3.2.3.4.5.7 | 1.3.2.3.4.5.7 |  | 2025-11-26 08:00 | p | 22 |  | 2025-12-18 10:41
99 | 633 | FgJ5XjjThZN85XQOJ0nJ | Normal | 21 | 1.5.6.6.2.10 | 1.5.6.6.2.10 |  | 2025-06-18 08:00 | p | 33 |  | 2025-07-21 15:45
100 | 634 | o4DRQRcsScdVmCSXNbxF | Normal | 10 | 1.5.6.6.2.9 | 1.5.6.6.2.9 |  | 2025-07-21 08:00 | p | 28 |  | 2025-08-18 13:19
101 | 635 | ztvy5zkS4z9HirKgvHGY | Normal | 20 | 1.5.6.6.2.11 | 1.5.6.6.2.11 |  | 2025-08-01 13:00 | p | 32 |  | 2025-09-02 15:12
102 | 636 | ZpIfqMwIaczq2BqznW2q | Normal | 6 | 1.5.6.6.2.12 | 1.5.6.6.2.12 |  | 2025-08-29 13:00 | p | 27 |  | 2025-09-26 11:01
103 | 637 | 3VAZwvp2NS6usl0wrvOM | Normal | 7 | 1.5.6.6.2.13 | 1.5.6.6.2.13 |  | 2025-09-09 13:00 | p | 28 |  | 2025-10-08 09:26
104 | 638 | 34zoFClD9RS7gLTCPZs0 | Normal | 5 | 1.5.6.6.2.14 | 1.5.6.6.2.14 |  | 2025-09-18 13:00 | p | 31 |  | 2025-10-20 11:33
105 | 640 | 10AmMHkCz4b8n0xqbyCt | Normal | 5 | 1.5.6.6.2.16 | 1.5.6.6.2.16 |  | 2025-09-25 13:00 | p | 31 |  | 2025-10-27 11:29
106 | 641 | KUqcSNVxncHPLVJNV5ca | Normal | 2 | 1.5.6.6.2.17 | 1.5.6.6.2.17 |  | 2025-10-02 13:00 | p | 29 |  | 2025-10-31 16:23
107 | 642 | chCwawHUqn0ea2ArCnKB | Normal | 0 | 1.5.6.6.2.18 | 1.5.6.6.2.18 |  | 2025-10-06 08:00 | p | 29 |  | 2025-11-04 08:38
108 | 643 | xZBRzE3QVYmQCjnzxLQv | Normal | 4 | 1.5.6.6.2.19 | 1.5.6.6.2.19 |  | 2025-10-06 13:00 | p | 29 |  | 2025-11-04 13:00
109 | 644 | tUTeQ74YpmkuuOiouSXU | Normal | 5 | 1.5.6.6.2.20 | 1.5.6.6.2.20 |  | 2025-10-10 13:00 | p | 31 |  | 2025-11-10 15:13
110 | 645 | mSrjcTZmK12EdJmOEYFi | Normal | 1 | 1.5.6.6.2.21 | 1.5.6.6.2.21 |  | 2025-10-20 13:00 | p | 28 |  | 2025-11-18 10:28
111 | 646 | Haue3rYYySw3jbXWnBeq | Normal | 3 | 1.5.6.6.3 | 1.5.6.6.3 |  | 2025-10-21 13:00 | p | 28 |  | 2025-11-19 09:32
112 | 647 | 6jlP0Y4QQ5KPQWxvolLg | Normal | 1 | 1.5.6.6.4 | 1.5.6.6.4 |  | 2025-10-24 13:00 | p | 31 |  | 2025-11-24 16:06
113 | 656 | lzPFAx9Fh8cDxyQ3uxFX | Normal | 1 | 1.5.6.6.5.3 | 1.5.6.6.5.3 |  | 2025-10-27 13:00 | p | 29 |  | 2025-11-25 16:19
114 | 657 | nePaKBbqDo6OltylvukE | Summary | 14 | 1.5.6.6.5.4 | 1.5.6.6.5.4 |  | 2025-10-28 15:00 | p | 30 |  | 2025-11-28 09:44
115 | 658 | PyBKEPMZMe2YeOC66yut | Normal | 11 | 1.5.6.6.5.4.1 | 1.5.6.6.5.4.1 |  | 2025-10-28 15:00 | p | 30 |  | 2025-11-28 09:44
116 | 664 | H1KB0K8mM12Opvc4oDP1 | Normal | 3 | 1.5.6.6.5.4.2 | 1.5.6.6.5.4.2 |  | 2025-11-13 15:00 | p | 28 |  | 2025-12-12 13:16
117 | 665 | FIEbexlYHnOcZkEBs7WM | Normal | 5 | 1.5.6.6.5.5 | 1.5.6.6.5.5 |  | 2025-11-19 15:00 | p | 29 |  | 2025-12-18 16:45
118 | 666 | OcAHNnZWZgiwxfUiheGU | Normal | 5 | 1.5.6.6.5.6 | 1.5.6.6.5.6 |  | 2025-11-26 15:00 | p | 30 |  | 2025-12-26 15:53
119 | 667 | HPj21Hyun1nWvxJOQMhf | Normal | 28 | 1.5.6.6.5.7 | 1.5.6.6.5.7 |  | 2025-12-04 15:00 | p | 28 |  | 2026-01-02 14:34
120 | 671 | ZM52W2kHJJCM7052Da3J | Normal | 2 | 1.5.6.5.2 | 1.5.6.5.2 |  | 2025-10-24 13:00 | p | 31 |  | 2025-11-24 16:06
121 | 672 | AcRvLPQ7WrNfvcLBOWzV | Normal | 1 | 1.5.6.5.3 | 1.5.6.5.3 |  | 2025-11-18 15:00 | p | 28 |  | 2025-12-17 14:16
122 | 1459 | MxsNofofvf6CR0hsGInx | Normal | 1 | 1.5.5.1.4 | 1.5.5.1.4 |  | 2025-03-06 08:00 | p | 0 |  | 2025-03-06 09:25
123 | 1469 | MZooHRTMNCHrNy0nPaCQ | Normal | 1 | 1.5.5.1.6 | 1.5.5.1.6 |  | 2025-02-18 08:00 | p | 27 |  | 2025-03-17 15:37
124 | 1470 | PdTqfNwd2IKBXe26tWkB | Normal | 1 | 1.5.5.1.8 | 1.5.5.1.8 |  | 2025-03-07 08:00 | p | 24 |  | 2025-03-31 15:24
125 | 1471 | FsiT4ZMTOq9hGqZQQdYf | Normal | 11 | 1.5.5.1.9 | 1.5.5.1.9 |  | 2025-03-10 08:00 | p | 23 |  | 2025-04-02 10:21
126 | 1472 | KG0YDAdikr58WjA79FVb | Normal | 9 | 1.5.5.1.10 | 1.5.5.1.10 |  | 2025-03-25 08:00 | p | 27 |  | 2025-04-21 16:39
127 | 4584 | H2uIo7s6dGmX6mrjT7jd | Normal | 9 | 1.5.5.1.7 | 1.5.5.1.7 |  | 2025-02-19 08:00 | p | 27 |  | 2025-03-18 16:39
128 | 3945 | bJfaWXH8yBacWp0eqnXx | Normal | 1 | 1.5.4.3 | 1.5.4.3 |  | 2025-04-02 08:00 | p | 30 |  | 2025-05-02 11:55
129 | 3952 | HkhDGF3pWO8GORFQnyh9 | Normal | 5 | 1.5.4.5.1.2 | 1.5.4.5.1.2 |  | 2025-03-24 08:00 | p | 36 |  | 2025-04-29 09:11
130 | 3953 | dYr7YcYkpYYUeESNUSkl | Normal | 2 | 1.5.4.5.1.3 | 1.5.4.5.1.3 |  | 2025-03-31 08:00 | p | 36 |  | 2025-05-06 10:35
131 | 3954 | r37KEs6OIDoMKT5Yz5nA | Normal | 1 | 1.5.4.5.1.4 | 1.5.4.5.1.4 |  | 2025-04-02 08:00 | p | 36 |  | 2025-05-08 11:53
132 | 6606 | pKonEcYtBOhP3mqLQIUx | Normal | 5 | 1.5.4.4.8 | 1.5.4.4.8 |  | 2025-02-19 08:00 | p | 29 |  | 2025-03-20 10:14
133 | 4215 | I07WrBLpDQufO3mvIdSu | Normal | 1 | 1.5.1.1.4 | 1.5.1.1.4 |  | 2025-06-17 08:00 | p | 31 |  | 2025-07-18 16:22
134 | 6445 | Wo6GLLiu9tXQyZ8t43hX | Normal | 43 | 1.5.1.1.3 | 1.5.1.1.3 |  | 2025-04-16 08:00 | p | 19 |  | 2025-05-05 08:35
135 | 6081 | VjHQD510O4fPJGbP9Knq | Normal | 1 | 1.5.1.2 | 1.5.1.2 |  | 2026-01-14 15:00 | p | 34 |  | 2026-02-17 15:29
136 | 6681 | NHiN8b86HRxpkLb9JGGD | Normal | 10 | 1.5.1.3.9 | 1.5.1.3.9 |  | 2025-04-04 08:00 | p | 32 |  | 2025-05-06 13:11
137 | 6682 | 695WEwNqpcHeAbXSBRci | Normal | 2 | 1.5.1.3.10 | 1.5.1.3.10 |  | 2025-05-23 08:00 | q | 0 |  | 2025-05-22 09:52
138 | 6684 | TL3Mtv3QlGNejnoXktH7 | Normal | 1 | 1.5.1.3.8 | 1.5.1.3.8 |  | 2025-04-03 08:00 | p | 32 |  | 2025-05-05 10:33
139 | 5612 | JBIAfh9fImNsEXfXoHCz | Summary | 5 | 1.5.2.2.10 | 1.5.2.2.10 |  | 2025-03-03 17:00 | q | 0 |  | 2025-03-03 08:55
140 | 5613 | cc9QdsdOkkgaQ8ateKZX | Normal | 1 | 1.5.2.2.10.1 | 1.5.2.2.10.1 |  | 2025-03-03 17:00 | q | 0 |  | 2025-03-03 08:55
141 | 5614 | COTl0owSvMhEdF9iuXCz | Normal | 0 | 1.5.2.2.10.2 | 1.5.2.2.10.2 |  | 2025-03-05 09:36 | q | 0 |  | 2025-03-04 10:46
142 | 5615 | 0lLRNnxfg3utwoPLwt26 | Normal | 2 | 1.5.2.2.10.3 | 1.5.2.2.10.3 |  | 2025-03-05 14:36 | q | 0 |  | 2025-03-04 16:11
143 | 5616 | 5Z54Ad8GhuwKLjQHaz2Y | Normal | 1 | 1.5.2.2.10.4 | 1.5.2.2.10.4 |  | 2025-03-07 14:36 | q | 0 |  | 2025-03-06 16:11
144 | 5617 | fALGtnsfw381gf0W53Ia | Normal | 0 | 1.5.2.2.10.5 | 1.5.2.2.10.5 |  | 2025-03-10 14:36 | q | -2 |  | 2025-03-07 16:45
145 | 5629 | ghMhRqrbgVxCQv51dU2T | Normal | 0 | 1.5.2.2.8.2 | 1.5.2.2.8.2 |  | 2025-02-20 13:00 | q | 0 |  | 2025-02-20 11:50
146 | 5630 | eU3bwvC6wgraOvc5hiLt | Milestone | 0 | 1.5.2.2.8.3 | 1.5.2.2.8.3 |  | 2025-02-20 17:00 | p | 0 |  | 2025-02-21 08:01
147 | 5631 | gvTQVNdftDRXYXclyMFo | Normal | 3 | 1.5.2.2.8.4 | 1.5.2.2.8.4 |  | 2025-02-21 08:00 | p | 0 |  | 2025-02-21 08:01
148 | 5632 | DfRDIp64TG1m6LE7SSYQ | Milestone | 0 | 1.5.2.2.8.5 | 1.5.2.2.8.5 |  | 2025-02-25 17:00 | q | 0 |  | 2025-02-25 15:53
149 | 5633 | 2UPBwQymcCOUpuUjnBTe | Normal | 3 | 1.5.2.2.8.6 | 1.5.2.2.8.6 |  | 2025-02-26 08:00 | q | 0 |  | 2025-02-25 15:53
150 | 5634 | gm5pLWvICR0pU7aShOGD | Normal | 1 | 1.5.2.2.8.7 | 1.5.2.2.8.7 |  | 2025-03-03 08:00 | q | -2 |  | 2025-02-28 08:37
151 | 5639 | ymvGdGMdlU958QTwMU9V | Normal | 0 | 1.5.2.2.9.4 | 1.5.2.2.9.4 |  | 2025-01-27 08:00 | p | 1 |  | 2025-01-28 10:34
152 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | 2025-01-27 13:00 | p | 1 |  | 2025-01-28 15:01
153 | 5641 | QjWOhv4eRSTZWx0ATAUl | Normal | 23 | 1.5.2.2.11 | 1.5.2.2.11 |  | 2025-03-11 08:00 | q | 0 |  | 2025-03-10 10:07
154 | 5447 | ijJ4zfbEfOInLYX7Vu9Z | Normal | 6 | 1.5.3.1.2.2 | 1.5.3.1.2.2 |  | 2025-02-26 08:00 | p | 29 |  | 2025-03-27 11:44
155 | 5448 | cS9oDqhLQ00Df4o4XStO | Normal | 6 | 1.5.3.1.2.3 | 1.5.3.1.2.3 |  | 2025-03-06 08:00 | p | 28 |  | 2025-04-03 13:50
156 | 5449 | 6It4K5O7iZJhLoLO2jyi | Normal | 6 | 1.5.3.1.2.4 | 1.5.3.1.2.4 |  | 2025-03-14 08:00 | p | 28 |  | 2025-04-11 09:26
157 | 5450 | maMtUzorvxHWuMFIlXlq | Normal | 5 | 1.5.3.1.3 | 1.5.3.1.3 |  | 2025-03-24 08:00 | p | 25 |  | 2025-04-18 10:47
158 | 7381 | Ao7wteklS85dOuCCMM3I | Normal | 124 | 1.5.1 | 1.5.1 |  | 2025-08-01 13:00 | p | 32 |  | 2025-09-02 15:12
159 | 576 | m8O5CFAYfVbtxxZI5qQW | Normal | 15 | 1.4.3.1.2 | 1.4.3.1.2 |  | 2025-11-13 08:00 | q | -37 |  | 2025-10-06 15:42
160 | 5854 | 2kqOvhRPajU4Q0ZPsUnx | Normal | 8 | 1.4.3.1.4 | 1.4.3.1.4 |  | 2026-03-03 15:00 | p | 30 |  | 2026-04-03 13:41
161 | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Normal | 49 | 1.4.3.1.5 | 1.4.3.1.5 |  | 2026-07-30 16:58 | q | 0 |  | 2026-07-30 10:58
162 | 6607 | IhYDHpDNbof6PVOjQ9lw | Normal | 4 | 1.4.3.1.3 | 1.4.3.1.3 |  | 2026-02-18 15:00 | p | 33 |  | 2026-03-24 09:15
163 | 3901 | Jj1toL1YzUk95oK7OfgU | Normal | 4 | 1.4.1.1.2.4 | 1.4.1.1.2.4 |  | 2025-03-03 08:00 | p | 23 |  | 2025-03-26 16:16
164 | 6566 | gAyE6SkFHV1MNEAJitQ7 | Normal | 1 | 1.4.1.2.1.6 | 1.4.1.2.1.6 |  | 2025-05-01 08:00 | q | -21 |  | 2025-04-09 11:48
165 | 3907 | pFYLZycbgH4KMn6pLhBU | Summary | 272 | 1.4.1.3 | 1.4.1.3 |  | 2025-06-27 08:00 | q | -77 |  | 2025-04-10 11:58
166 | 3908 | y9tKov3jCEzWGyA9B1wJ | Normal | 5 | 1.4.1.3.1 | 1.4.1.3.1 |  | 2025-06-27 08:00 | q | -77 |  | 2025-04-10 11:58
167 | 3909 | VvjZ0oHXTTG06m5XlL1B | Normal | 10 | 1.4.1.3.2 | 1.4.1.3.2 |  | 2025-07-07 08:00 | q | -80 |  | 2025-04-17 14:24
168 | 3910 | pNRX5rV0uvvHnR27z1AO | Normal | 8 | 1.4.1.3.3 | 1.4.1.3.3 |  | 2026-03-03 15:00 | p | 30 |  | 2026-04-03 13:41
169 | 3911 | R3AK39H17lCC16PE9DkR | Normal | 10 | 1.4.1.3.4 | 1.4.1.3.4 |  | 2026-03-13 15:00 | p | 32 |  | 2026-04-14 16:59
170 | 3912 | BSEXS69UjCPQ6j2zF47p | Normal | 15 | 1.4.1.3.5 | 1.4.1.3.5 |  | 2026-03-27 15:00 | p | 28 |  | 2026-04-24 15:54
171 | 3913 | nUmJBAacPI2xORV8OCED | Normal | 20 | 1.4.1.3.6 | 1.4.1.3.6 |  | 2026-04-17 15:00 | p | 26 |  | 2026-05-14 09:13
172 | 3914 | e7efPn2W4IFyilt2hNai | Normal | 30 | 1.4.1.3.7 | 1.4.1.3.7 |  | 2026-05-15 15:00 | p | 32 |  | 2026-06-16 16:59
173 | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Normal | 5 | 1.4.1.3.8 | 1.4.1.3.8 |  | 2026-06-30 15:00 | p | 23 |  | 2026-07-24 08:09
174 | 3916 | xcLTkuiw0V5a2mOSGmcP | Normal | 10 | 1.4.1.3.9 | 1.4.1.3.9 |  | 2026-07-08 15:00 | p | 25 |  | 2026-08-03 08:38
175 | 3917 | hmttcJptV92JIo4OpANW | Normal | 5 | 1.4.1.3.10 | 1.4.1.3.10 |  | 2026-07-22 15:00 | p | 22 |  | 2026-08-14 14:20
176 | 3918 | VKkEEklTkhlAtqntT93x | Summary | 160 | 1.4.1.4 | 1.4.1.4 |  | 2026-05-15 15:00 | p | 32 |  | 2026-06-16 16:59
177 | 3919 | 70MdVf3krr3KZdDhEaoj | Normal | 1 | 1.4.1.4.1 | 1.4.1.4.1 |  | 2026-05-15 15:00 | p | 32 |  | 2026-06-16 16:59
178 | 3920 | mBVNyTIN7rvKyNQxzyxZ | Normal | 9 | 1.4.1.4.2 | 1.4.1.4.2 |  | 2026-05-18 15:00 | p | 30 |  | 2026-06-18 09:43
179 | 3921 | jEuseC90wYhkn0V4svXs | Normal | 3 | 1.4.1.4.3 | 1.4.1.4.3 |  | 2026-07-30 16:58 | q | 0 |  | 2026-07-30 10:58
180 | 3922 | yD55zWPn8USsNa4i8nCC | Normal | 5 | 1.4.1.4.4 | 1.4.1.4.4 |  | 2026-10-08 16:58 | p | 12 |  | 2026-10-21 15:39
181 | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Normal | 15 | 1.4.1.4.5 | 1.4.1.4.5 |  | 2026-10-16 16:58 | p | 13 |  | 2026-10-30 14:41
182 | 3924 | N1CigBiMQE2J41ZAMkt0 | Normal | 20 | 1.4.1.4.6 | 1.4.1.4.6 |  | 2026-11-06 16:58 | p | 26 |  | 2026-12-03 15:30
183 | 3925 | hSr4t1vn7GiB6Kp7YK0M | Normal | 5 | 1.4.1.4.7 | 1.4.1.4.7 |  | 2026-12-08 16:58 | p | 28 |  | 2027-01-06 15:40
184 | 3926 | vGJMK6sejFbKR6Gom2up | Normal | 5 | 1.4.1.4.8 | 1.4.1.4.8 |  | 2026-12-15 16:58 | p | 27 |  | 2027-01-12 15:02
185 | 3927 | 3RLmiC17tI4E2ggNuRe0 | Normal | 5 | 1.4.1.4.9 | 1.4.1.4.9 |  | 2026-12-22 16:58 | p | 29 |  | 2027-01-21 14:26
186 | 3928 | hCBFci3gUopMkWW2dQQj | Normal | 5 | 1.4.1.4.10 | 1.4.1.4.10 |  | 2026-12-30 16:58 | p | 29 |  | 2027-01-29 15:28
187 | 5213 | 6YmlQVHNVjUNryBHQf8a | Summary | 61 | 1.4.2.2.3 | 1.4.2.2.3 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
188 | 5214 | KnSim1DOJ7A0BYyW8QOP | Milestone | 0 | 1.4.2.2.3.1 | 1.4.2.2.3.1 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
189 | 5215 | KawuX1icbWQB8WlKVKy9 | Normal | 60 | 1.4.2.2.3.2 | 1.4.2.2.3.2 |  | 2025-08-13 08:00 | q | -26 |  | 2025-07-17 16:02
190 | 5216 | xOecB4tLtQXauOnWGD4l | Normal | 1 | 1.4.2.2.3.3 | 1.4.2.2.3.3 |  | 2025-11-07 08:00 | q | -34 |  | 2025-10-03 16:30
191 | 5217 | e116DivbRDCkLiH2zNhl | Summary | 61 | 1.4.2.2.4 | 1.4.2.2.4 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
192 | 5218 | 8GMyARBjPLtiSR4txAaa | Milestone | 0 | 1.4.2.2.4.1 | 1.4.2.2.4.1 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
193 | 5219 | Uz3hspiJXkYJElXZ00I5 | Normal | 60 | 1.4.2.2.4.2 | 1.4.2.2.4.2 |  | 2025-08-13 08:00 | q | -26 |  | 2025-07-17 16:02
194 | 5220 | QAqXx5k5ldQJaugZyYbR | Normal | 1 | 1.4.2.2.4.3 | 1.4.2.2.4.3 |  | 2025-11-07 08:00 | q | -21 |  | 2025-10-16 09:10
195 | 5221 | iTaWceiQKMF6gUaF3DCB | Summary | 61 | 1.4.2.2.5 | 1.4.2.2.5 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
196 | 5222 | 4u5ocGGr0fcTRpzuglXZ | Milestone | 0 | 1.4.2.2.5.1 | 1.4.2.2.5.1 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
197 | 5223 | 3nEJb4lsc7akFmF6ULw7 | Normal | 60 | 1.4.2.2.5.2 | 1.4.2.2.5.2 |  | 2025-08-13 08:00 | q | -26 |  | 2025-07-17 16:02
198 | 5224 | PvORb6t1pqf23aOFbh3S | Normal | 1 | 1.4.2.2.5.3 | 1.4.2.2.5.3 |  | 2025-11-07 08:00 | q | -28 |  | 2025-10-09 15:42
199 | 5225 | b44Ij1WE7Qrra8bO7ZTN | Normal | 1 | 1.4.2.2.6 | 1.4.2.2.6 |  | 2026-07-20 16:58 | q | 0 |  | 2026-07-20 11:30
200 | 5277 | TgmqG1sR4A60sNmMtPcE | Summary | 193 | 1.4.2.2.7 | 1.4.2.2.7 |  | 2025-10-07 16:09 | q | -32 |  | 2025-09-04 16:24
201 | 5278 | OmCdw3tKtVsW24V2aNqQ | Normal | 8 | 1.4.2.2.7.1 | 1.4.2.2.7.1 |  | 2025-10-07 16:09 | q | -32 |  | 2025-09-04 16:24
202 | 5279 | htHZ3VhuaadgfKg1VQls | Summary | 47 | 1.4.2.2.7.11 | 1.4.2.2.7.11 |  | 2026-04-21 08:01 | q | -31 |  | 2026-03-20 13:20
203 | 5280 | q0a2rl5NSMPQe2o4IYAd | Normal | 3 | 1.4.2.2.7.11.1 | 1.4.2.2.7.11.1 |  | 2026-05-12 15:05 | q | -35 |  | 2026-04-07 14:50
204 | 5281 | 3GO4XZOZrW4CEje40UJT | Normal | 5 | 1.4.2.2.7.11.2 | 1.4.2.2.7.11.2 |  | 2026-04-21 08:01 | q | -21 |  | 2026-03-30 09:44
205 | 5282 | qBzS7vPbhPVzs7sVXgmM | Normal | 5 | 1.4.2.2.7.11.3 | 1.4.2.2.7.11.3 |  | 2026-04-28 08:01 | q | -21 |  | 2026-04-06 10:47
206 | 5283 | fU0pzeQGz2MN3lZmznFh | Normal | 5 | 1.4.2.2.7.11.4 | 1.4.2.2.7.11.4 |  | 2026-05-05 08:01 | q | -45 |  | 2026-03-20 13:20
207 | 5284 | epM0xPGW4QTSpblHVWYc | Normal | 10 | 1.4.2.2.7.11.5 | 1.4.2.2.7.11.5 |  | 2026-05-28 08:58 | q | -28 |  | 2026-04-29 11:35
208 | 5285 | ffNcVsnPBySsZbQiEShc | Normal | 10 | 1.4.2.2.7.11.6 | 1.4.2.2.7.11.6 |  | 2026-06-11 08:58 | q | -19 |  | 2026-05-22 15:08
209 | 5286 | Yb8sH9U5B9gBzfVjcJKN | Normal | 6 | 1.4.2.2.7.12 | 1.4.2.2.7.12 |  | 2026-06-25 08:58 | q | -16 |  | 2026-06-09 08:48
210 | 5287 | bhDhrVJ9ZVKMNyReuPKm | Normal | 5 | 1.4.2.2.7.13 | 1.4.2.2.7.13 |  | 2026-07-02 16:58 | q | -16 |  | 2026-06-16 16:30
211 | 5288 | RIVzpLwElpoiAIgfwKiL | Milestone | 0 | 1.4.2.2.7.14 | 1.4.2.2.7.14 |  | 2026-07-09 16:58 | q | -16 |  | 2026-06-23 15:58
212 | 6457 | PFYaNHtSBj97Eh5ysTvH | Normal | 7 | 1.4.2.2.7.2 | 1.4.2.2.7.2 |  | 2026-01-19 08:01 | q | -33 |  | 2025-12-16 08:32
213 | 6458 | pDFztlVdvvSj2i4Cz5Z9 | Normal | 5 | 1.4.2.2.7.3 | 1.4.2.2.7.3 |  | 2026-01-28 08:01 | q | -35 |  | 2025-12-23 11:39
214 | 6459 | ylmwXTiOnCLJpwlHTaRg | Normal | 10 | 1.4.2.2.7.4 | 1.4.2.2.7.4 |  | 2026-02-04 08:01 | q | -34 |  | 2025-12-31 11:37
215 | 6460 | CystLMJtc4xxgICiEMDQ | Normal | 8 | 1.4.2.2.7.5 | 1.4.2.2.7.5 |  | 2026-02-18 08:01 | q | -32 |  | 2026-01-16 09:43
216 | 6461 | 7ypQo0ZyAHzCHmFRlywg | Normal | 10 | 1.4.2.2.7.6 | 1.4.2.2.7.6 |  | 2026-03-02 08:01 | q | -32 |  | 2026-01-28 08:58
217 | 6462 | BWDOi71UCejcEb1fgeoY | Normal | 7 | 1.4.2.2.7.7 | 1.4.2.2.7.7 |  | 2026-03-16 08:01 | q | -30 |  | 2026-02-13 08:15
218 | 6463 | OelD6citgJccZhV0UyvH | Normal | 7 | 1.4.2.2.7.8 | 1.4.2.2.7.8 |  | 2026-03-25 08:01 | q | -29 |  | 2026-02-23 15:14
219 | 6464 | McSTYqZ3LCfaYSSmZoTn | Normal | 7 | 1.4.2.2.7.9 | 1.4.2.2.7.9 |  | 2026-04-03 08:01 | q | -28 |  | 2026-03-05 08:27
220 | 6465 | WAyiiuxKOgY7bZWYUV9d | Normal | 5 | 1.4.2.2.7.10 | 1.4.2.2.7.10 |  | 2026-04-14 08:01 | q | -31 |  | 2026-03-13 10:58
221 | 5240 | NSmZbDTp76mGzDSQ7Ceh | Summary | 56 | 1.4.2.1.3 | 1.4.2.1.3 |  | 2025-05-23 08:00 | q | -235 |  | 2024-09-30 08:00
222 | 5241 | v6EKIZLcnDHW8CXOrD7y | Normal | 21 | 1.4.2.1.3.1 | 1.4.2.1.3.1 |  | 2025-05-23 08:00 | q | -235 |  | 2024-09-30 08:00
223 | 5242 | JYCfpao49G3jD8M94S66 | Normal | 10 | 1.4.2.1.3.2 | 1.4.2.1.3.2 |  | 2025-06-24 08:00 | q | -188 |  | 2024-12-18 08:00
224 | 5243 | 0XN39P602kPVdw6rXYZi | Normal | 10 | 1.4.2.1.3.3 | 1.4.2.1.3.3 |  | 2025-07-09 08:00 | q | -56 |  | 2025-05-13 10:18
225 | 5244 | Nwqnc6xsOuQ8oMDbKNfv | Normal | 15 | 1.4.2.1.3.4 | 1.4.2.1.3.4 |  | 2025-07-23 08:00 | q | -27 |  | 2025-06-25 08:52
226 | 5265 | ATYnDTN93dB3aTXfzslo | Normal | 6 | 1.4.2.1.6.2 | 1.4.2.1.6.2 |  | 2025-03-25 14:00 | p | 28 |  | 2025-04-22 14:42
227 | 5266 | G5H4IlBy3M3Zxs38gcIH | Normal | 10 | 1.4.2.1.6.3 | 1.4.2.1.6.3 |  | 2025-04-15 11:00 | p | 27 |  | 2025-05-13 10:18
228 | 5267 | 3RI5G3ymKjaLn96cfboa | Normal | 11 | 1.4.2.1.6.4 | 1.4.2.1.6.4 |  | 2025-04-15 11:00 | p | 27 |  | 2025-05-13 10:18
229 | 5268 | fG9nayiE82fFlNFtuyfN | Normal | 8 | 1.4.2.1.6.5 | 1.4.2.1.6.5 |  | 2025-06-03 08:00 | q | 0 |  | 2025-06-02 15:18
230 | 5269 | UP8sWsDXCDMiwOqWz3ib | Normal | 5 | 1.4.2.1.6.6 | 1.4.2.1.6.6 |  | 2025-05-13 14:00 | p | 20 |  | 2025-06-02 15:18
231 | 5270 | 0UA65kBzwzHULCayr1Gq | Normal | 8 | 1.4.2.1.6.7 | 1.4.2.1.6.7 |  | 2025-07-25 09:00 | q | -38 |  | 2025-06-16 11:06
232 | 5271 | mtztJWmm2OBnfmSsuoGt | Normal | 10 | 1.4.2.1.6.8 | 1.4.2.1.6.8 |  | 2025-08-08 08:30 | q | -38 |  | 2025-06-30 09:21
233 | 5272 | kvS9pO69DNwaLvofAQcb | Normal | 11 | 1.4.2.1.6.9 | 1.4.2.1.6.9 |  | 2025-08-22 08:30 | q | -36 |  | 2025-07-16 08:39
234 | 5273 | fGHKYfAaAseAkWqOpGpv | Normal | 10 | 1.4.2.1.6.10 | 1.4.2.1.6.10 |  | 2025-09-09 08:30 | q | -33 |  | 2025-08-06 13:53
235 | 5274 | zjsmmZ1Zvuz0mxAk4wzH | Normal | 10 | 1.4.2.1.6.11 | 1.4.2.1.6.11 |  | 2025-09-23 08:30 | q | -33 |  | 2025-08-20 11:00
236 | 5275 | lBTJLZ8EG6vqarjSz7m6 | Milestone | 0 | 1.4.2.1.6.12 | 1.4.2.1.6.12 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
237 | 5264 | 2BYRPY9ftrCpjg2j3vxJ | Milestone | 0 | 1.4.2.1.8 | 1.4.2.1.8 |  | 2025-02-21 08:00 | q | -328 |  | 2024-03-29 17:00
238 | 5276 | yja2Gk0YbNXya3vsxrwh | Milestone | 0 | 1.4.2.1.7 | 1.4.2.1.7 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
239 | 5289 | tqKGxL2oceRufkd47wnf | Summary | 319 | 1.4.2.3 | 1.4.2.3 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
240 | 5290 | NEvSl0zKCrGJ6lqshTZO | Milestone | 0 | 1.4.2.3.1 | 1.4.2.3.1 |  | 2025-11-07 17:00 | q | -28 |  | 2025-10-10 15:45
241 | 5313 | 3y8KKUl940HiJi7UFKFT | Summary | 106 | 1.4.2.3.3 | 1.4.2.3.3 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
242 | 5314 | SRtjKDi8lC5PBWdNdIAU | Normal | 10 | 1.4.2.3.3.1 | 1.4.2.3.3.1 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
243 | 5316 | LCfcLPfxTjnSY0dCrjlE | Normal | 10 | 1.4.2.3.3.2 | 1.4.2.3.3.2 |  | 2026-08-19 16:59 | q | 0 |  | 2026-08-19 15:33
244 | 5317 | pw6YyMXR7oeqsrtIHdqo | Normal | 9 | 1.4.2.3.3.3 | 1.4.2.3.3.3 |  | 2026-09-16 11:59 | p | 0 |  | 2026-09-16 13:30
245 | 5318 | KMG5hXAC4X2MZPfyVOSc | Normal | 5 | 1.4.2.3.3.8 | 1.4.2.3.3.8 |  | 2026-11-06 10:08 | p | 0 |  | 2026-11-06 15:15
246 | 5319 | mDGXCmTQB2ITo8MYwlYq | Normal | 5 | 1.4.2.3.3.9 | 1.4.2.3.3.9 |  | 2026-11-13 10:08 | p | 3 |  | 2026-11-16 11:36
247 | 5320 | hu6UActfLD0rLfdNqC55 | Normal | 5 | 1.4.2.3.3.10 | 1.4.2.3.3.10 |  | 2026-11-20 10:08 | p | 3 |  | 2026-11-24 08:25
248 | 5321 | pG9QTaeiPcJe7Bm3iI1s | Normal | 5 | 1.4.2.3.3.11 | 1.4.2.3.3.11 |  | 2026-11-27 10:08 | p | 3 |  | 2026-12-01 08:22
249 | 5322 | oNpYocgOFdrRcJiQE0H5 | Normal | 5 | 1.4.2.3.3.12 | 1.4.2.3.3.12 |  | 2026-12-04 10:08 | p | 4 |  | 2026-12-08 11:18
250 | 5323 | Tt5dEbDabBigq84Eat5c | Normal | 5 | 1.4.2.3.3.13 | 1.4.2.3.3.13 |  | 2026-12-11 10:08 | p | 4 |  | 2026-12-16 08:59
251 | 5324 | INz2wzhVzgQCZLXqwTZc | Normal | 5 | 1.4.2.3.3.14 | 1.4.2.3.3.14 |  | 2026-12-18 13:39 | p | 5 |  | 2026-12-23 13:51
252 | 5325 | D5c4JntP5EU4thbOE4hi | Normal | 1 | 1.4.2.3.3.15 | 1.4.2.3.3.15 |  | 2026-12-31 08:05 | p | 5 |  | 2027-01-05 08:10
253 | 6467 | n3qEWBmgcrCNzbacKk03 | Normal | 5 | 1.4.2.3.3.4 | 1.4.2.3.3.4 |  | 2026-10-09 10:08 | p | 0 |  | 2026-10-09 11:37
254 | 6468 | BqsEZH5IWCI59bWKml0D | Normal | 5 | 1.4.2.3.3.5 | 1.4.2.3.3.5 |  | 2026-10-16 10:08 | p | 0 |  | 2026-10-16 11:31
255 | 6469 | TtC6fzAb8zClFAVfKkP8 | Normal | 5 | 1.4.2.3.3.6 | 1.4.2.3.3.6 |  | 2026-10-23 10:08 | p | 0 |  | 2026-10-23 15:39
256 | 6470 | UrgnPc0HjVwpN7twGsWX | Normal | 5 | 1.4.2.3.3.7 | 1.4.2.3.3.7 |  | 2026-10-30 10:08 | p | 0 |  | 2026-10-30 15:11
257 | 5326 | esDa5lJIA5zg0nP58cRd | Summary | 32 | 1.4.2.3.4 | 1.4.2.3.4 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
258 | 5327 | iRZmxts3rKQ38tplQw52 | Normal | 30 | 1.4.2.3.4.1 | 1.4.2.3.4.1 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
259 | 5328 | ngeJL3ilFttQtHxnOEwX | Normal | 1 | 1.4.2.3.4.2 | 1.4.2.3.4.2 |  | 2025-11-20 08:30 | q | -36 |  | 2025-10-14 11:56
260 | 5329 | GYUaK0PI1fV4kag2egD8 | Normal | 1 | 1.4.2.3.4.3 | 1.4.2.3.4.3 |  | 2025-11-21 08:30 | q | -36 |  | 2025-10-15 13:36
261 | 6321 | KAyzIHlSkkFZqIIdJ9JD | Summary | 144 | 1.4.2.3.2 | 1.4.2.3.2 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
262 | 5298 | c4SSanbHhynqs8RkqT3I | Normal | 3 | 1.4.2.3.2.2 | 1.4.2.3.2.2 |  | 2026-01-29 15:00 | p | 33 |  | 2026-03-03 15:34
263 | 5299 | HB5wL9z8KlZFeAas0WUQ | Normal | 11 | 1.4.2.3.2.3 | 1.4.2.3.2.3 |  | 2026-02-03 15:00 | p | 33 |  | 2026-03-09 14:34
264 | 5301 | hHw9byxBfgMW8zXuSsdj | Milestone | 0 | 1.4.2.3.2.12 | 1.4.2.3.2.12 |  | 2026-04-02 15:00 | p | 33 |  | 2026-05-05 15:37
265 | 5302 | 2rc67Y2hzAhRvE7YihWA | Normal | 10 | 1.4.2.3.2.1 | 1.4.2.3.2.1 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
266 | 5303 | SgeIRg4ykwxbNqD9urWV | Normal | 2 | 1.4.2.3.2.8 | 1.4.2.3.2.8 |  | 2026-03-20 15:00 | p | 32 |  | 2026-04-22 11:45
267 | 5304 | KRXQrBZsFBKS9k4FvAsp | Normal | 3 | 1.4.2.3.2.9 | 1.4.2.3.2.9 |  | 2026-03-24 15:00 | p | 30 |  | 2026-04-24 14:59
268 | 5305 | TyGQYH0bANBrFjXmh15D | Normal | 2 | 1.4.2.3.2.10 | 1.4.2.3.2.10 |  | 2026-03-27 15:00 | p | 33 |  | 2026-04-29 15:04
269 | 5306 | yar7ts7ASIpTQqyvnwQd | Normal | 5 | 1.4.2.3.2.13 | 1.4.2.3.2.13 |  | 2026-04-02 15:00 | p | 33 |  | 2026-05-05 15:37
270 | 5307 | yRByGMPgEQcCecr5HzAA | Normal | 2 | 1.4.2.3.2.15 | 1.4.2.3.2.15 |  | 2026-04-10 15:00 | p | 34 |  | 2026-05-15 09:22
271 | 5308 | JBAsTSNPb9OQmIAmtadV | Normal | 20 | 1.4.2.3.2.17 | 1.4.2.3.2.17 |  | 2026-04-21 08:01 | p | 34 |  | 2026-05-25 16:19
272 | 5309 | xRRT514kq8kwyv7njrs5 | Normal | 5 | 1.4.2.3.2.19 | 1.4.2.3.2.19 |  | 2026-07-09 16:58 | q | 0 |  | 2026-07-09 10:39
273 | 5310 | RMnJ5j2lLGlokfxLAfSa | Normal | 2 | 1.4.2.3.2.20 | 1.4.2.3.2.20 |  | 2026-07-16 16:58 | q | 0 |  | 2026-07-16 10:39
274 | 5311 | BowxNbb4uXSnAk8z8ZkC | Normal | 2 | 1.4.2.3.2.22 | 1.4.2.3.2.22 |  | 2026-07-20 16:58 | q | 0 |  | 2026-07-20 14:13
275 | 5312 | mmXMEY1kphvE51vXPbq6 | Milestone | 0 | 1.4.2.3.2.25 | 1.4.2.3.2.25 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
276 | 6516 | qmbk7ROGAo4AwJOySAlG | Normal | 4 | 1.4.2.3.2.4 | 1.4.2.3.2.4 |  | 2026-02-18 15:00 | p | 33 |  | 2026-03-24 09:15
277 | 6517 | YGaikKlMVGc6fqtUBZ7h | Normal | 5 | 1.4.2.3.2.5 | 1.4.2.3.2.5 |  | 2026-02-24 15:00 | p | 31 |  | 2026-03-27 16:17
278 | 6518 | 0rDsNLFYCabTnyCcopAQ | Normal | 8 | 1.4.2.3.2.6 | 1.4.2.3.2.6 |  | 2026-03-03 15:00 | p | 30 |  | 2026-04-03 13:41
279 | 6519 | UldK3RoYRJH5Hsfv02Lh | Normal | 2 | 1.4.2.3.2.7 | 1.4.2.3.2.7 |  | 2026-03-13 15:00 | p | 32 |  | 2026-04-15 13:51
280 | 6520 | UaqqB30tdDFCsCHRRpeh | Normal | 2 | 1.4.2.3.2.11 | 1.4.2.3.2.11 |  | 2026-03-31 15:00 | p | 31 |  | 2026-05-01 16:04
281 | 6521 | LDY9CVOjImzsQ4NE65Qz | Normal | 1 | 1.4.2.3.2.16 | 1.4.2.3.2.16 |  | 2026-04-14 15:00 | p | 38 |  | 2026-05-22 15:08
282 | 6522 | WYJvDx3FrKALT2lj4FIo | Normal | 2 | 1.4.2.3.2.18 | 1.4.2.3.2.18 |  | 2026-05-19 08:01 | p | 49 |  | 2026-07-07 09:10
283 | 6523 | TvM5XBX3OaVljTSOZ4e2 | Normal | 2 | 1.4.2.3.2.21 | 1.4.2.3.2.21 |  | 2026-07-16 16:58 | q | 0 |  | 2026-07-16 10:39
284 | 6524 | cvaJgvK8KpGYV8ykH12h | Normal | 2 | 1.4.2.3.2.23 | 1.4.2.3.2.23 |  | 2026-07-22 16:58 | q | 0 |  | 2026-07-22 14:13
285 | 6525 | GtEwLNkefPtnncnl90X4 | Normal | 3 | 1.4.2.3.2.24 | 1.4.2.3.2.24 |  | 2026-07-30 16:58 | q | 0 |  | 2026-07-30 10:58
286 | 6873 | gSZIbC6fsU6IM6McOJy8 | Normal | 1 | 1.4.2.3.2.14 | 1.4.2.3.2.14 |  | 2026-04-09 15:00 | p | 34 |  | 2026-05-14 08:39
287 | 678 | N57z7OkXN935WcKbC4jO | Normal | 1 | 1.6.7.2 | 1.6.7.2 |  | 2026-03-26 08:00 | p | 75 |  | 2026-06-09 09:07
288 | 751 | AADJzuTGAb4gWytj7CQi | Normal | 18 | 1.6.7.9.3.8 | 1.6.7.9.3.8 |  | 2025-08-07 08:00 | p | 14 |  | 2025-08-21 13:22
289 | 752 | r0c0rFS4EkOGynasmiCG | Normal | 36 | 1.6.7.9.3.7 | 1.6.7.9.3.7 |  | 2025-07-08 08:00 | p | 21 |  | 2025-07-29 09:13
290 | 759 | cZuo3MY7iyDrOJC1qVJx | Normal | 5 | 1.6.7.9.3.9 | 1.6.7.9.3.9 |  | 2025-09-03 08:00 | p | 13 |  | 2025-09-16 11:56
291 | 765 | qOEfFivvitnF8cw9csOP | Normal | 1 | 1.6.7.9.3.13 | 1.6.7.9.3.13 |  | 2026-03-26 08:00 | p | 75 |  | 2026-06-09 09:07
292 | 5773 | OCcI80TDGF8LlIXj66uV | Normal | 3 | 1.6.7.9.3.14 | 1.6.7.9.3.14 |  | 2026-03-27 08:00 | p | 75 |  | 2026-06-10 09:42
293 | 746 | qMC0J8brk1dsdpzlKrk7 | Normal | 12 | 1.6.7.9.3.5.3 | 1.6.7.9.3.5.3 |  | 2025-04-01 08:00 | q | -4 |  | 2025-03-27 10:10
294 | 6324 | gthK0FxwJBk3laTELp8O | Summary | 45 | 1.6.7.9.3.6 | 1.6.7.9.3.6 |  | 2025-05-01 08:00 | p | 15 |  | 2025-05-16 13:13
295 | 747 | nul8vpOEtI2Q6W5Q0Qo9 | Normal | 12 | 1.6.7.9.3.6.1 | 1.6.7.9.3.6.1 |  | 2025-05-01 08:00 | p | 15 |  | 2025-05-16 13:13
296 | 748 | M1HHh2K01o23jS8vpDxS | Normal | 11 | 1.6.7.9.3.6.2 | 1.6.7.9.3.6.2 |  | 2025-05-19 08:00 | p | 16 |  | 2025-06-04 15:23
297 | 749 | Q6UXOpf9Kvzek7IGY0vp | Normal | 11 | 1.6.7.9.3.6.3 | 1.6.7.9.3.6.3 |  | 2025-06-04 08:00 | p | 16 |  | 2025-06-20 14:07
298 | 750 | lsyrPytnmjLTpXFywa7Z | Normal | 11 | 1.6.7.9.3.6.4 | 1.6.7.9.3.6.4 |  | 2025-06-20 08:00 | p | 13 |  | 2025-07-03 16:35
299 | 6325 | SeCXD5wMvkrEekc1PKVb | Summary | 48 | 1.6.7.9.3.10 | 1.6.7.9.3.10 |  | 2025-09-10 08:00 | p | 12 |  | 2025-09-22 16:40
300 | 753 | 8158sxzbHZvZEVAAqewP | Normal | 47 | 1.6.7.9.3.10.1 | 1.6.7.9.3.10.1 |  | 2025-09-10 08:00 | p | 12 |  | 2025-09-22 16:40
301 | 754 | hfPeDXfQSV7Nx9zb2rD7 | Normal | 8 | 1.6.7.9.3.10.2 | 1.6.7.9.3.10.2 |  | 2025-09-10 08:00 | p | 99 |  | 2025-12-18 08:10
302 | 755 | DQUdswbbJv1Qpkj0EGFX | Normal | 8 | 1.6.7.9.3.10.3 | 1.6.7.9.3.10.3 |  | 2025-09-22 08:00 | p | 98 |  | 2025-12-29 11:51
303 | 756 | ae3T3d3nFoXZXK7gqkAr | Normal | 20 | 1.6.7.9.3.10.4 | 1.6.7.9.3.10.4 |  | 2025-10-02 08:00 | p | 99 |  | 2026-01-09 10:16
304 | 757 | wbc1AZ0GUhXzQk6SoWIe | Normal | 6 | 1.6.7.9.3.10.6 | 1.6.7.9.3.10.6 |  | 2025-10-31 08:00 | p | 101 |  | 2026-02-09 11:31
305 | 758 | FbN1rrQYTlsz1haWZnFy | Normal | 6 | 1.6.7.9.3.10.8 | 1.6.7.9.3.10.8 |  | 2025-11-10 08:00 | p | 100 |  | 2026-02-18 15:32
306 | 5780 | XCMvjmTKbAUuCZwuNlSF | Normal | 6 | 1.6.7.9.3.10.5 | 1.6.7.9.3.10.5 |  | 2025-10-02 08:00 | p | 99 |  | 2026-01-09 10:16
307 | 5782 | EYY3j1SjnoLUV06T0QHs | Normal | 5 | 1.6.7.9.3.10.7 | 1.6.7.9.3.10.7 |  | 2025-10-31 08:00 | p | 101 |  | 2026-02-09 11:31
308 | 6326 | F4s3MnfyyA74WCIympSi | Summary | 75 | 1.6.7.9.3.11 | 1.6.7.9.3.11 |  | 2025-09-10 08:00 | p | 12 |  | 2025-09-22 16:40
309 | 760 | 7IpOsslq7gyebnCTulxX | Normal | 66 | 1.6.7.9.3.11.1 | 1.6.7.9.3.11.1 |  | 2025-09-10 08:00 | p | 12 |  | 2025-09-22 16:40
310 | 761 | x6fNhJzs4uMW9trtiNEW | Normal | 1 | 1.6.7.9.3.11.2 | 1.6.7.9.3.11.2 |  | 2025-12-16 08:00 | p | 72 |  | 2026-02-26 13:37
311 | 762 | nRInnITHYgcDsU5KDg6m | Normal | 8 | 1.6.7.9.3.11.3 | 1.6.7.9.3.11.3 |  | 2025-12-17 08:00 | p | 72 |  | 2026-02-27 13:36
312 | 6327 | dOJS0LaWQU970ssSiqsz | Summary | 59 | 1.6.7.9.3.12 | 1.6.7.9.3.12 |  | 2025-12-30 08:00 | p | 69 |  | 2026-03-09 16:30
313 | 763 | hLK2cdXSS7IhOZR53PgI | Normal | 6 | 1.6.7.9.3.12.1 | 1.6.7.9.3.12.1 |  | 2025-12-30 08:00 | p | 69 |  | 2026-03-09 16:30
314 | 764 | wTf98lLeHiXAkWj17mAH | Normal | 53 | 1.6.7.9.3.12.2 | 1.6.7.9.3.12.2 |  | 2026-01-08 08:00 | p | 68 |  | 2026-03-17 09:11
315 | 786 | 5RJIBxVgSA4dodMzOCsx | Normal | 1 | 1.6.7.8.5 | 1.6.7.8.5 |  | 2025-05-13 08:00 | p | 24 |  | 2025-06-06 08:25
316 | 5785 | xIbBdattr1YLWDiqGWPC | Summary | 126 | 1.6.7.11 | 1.6.7.11 |  | 2026-04-01 08:00 | p | 84 |  | 2026-06-24 13:57
317 | 5774 | Dvlkt7hdSzdJ7ChIr4xD | Normal | 2 | 1.6.7.11.1 | 1.6.7.11.1 |  | 2026-04-01 08:00 | p | 84 |  | 2026-06-24 13:57
318 | 5775 | D3NIdGcGrWNhiaQ0dYbY | Normal | 2 | 1.6.7.11.3 | 1.6.7.11.3 |  | 2026-09-28 08:00 | p | 102 |  | 2027-01-08 08:25
319 | 6435 | Ql00ScpYzqtI9PQP57zu | Normal | 122 | 1.6.7.11.2 | 1.6.7.11.2 |  | 2026-04-03 08:00 | p | 84 |  | 2026-06-26 11:47
320 | 1465 | i7zbkIpCuBMJlMsq6ma0 | Normal | 1 | 1.6.6.1.5 | 1.6.6.1.5 |  | 2025-03-31 08:00 | p | 10 |  | 2025-04-10 08:56
321 | 1476 | gbuDNYIgLq2nB3WERl4p | Normal | 30 | 1.6.6.1.7 | 1.6.6.1.7 |  | 2025-02-19 08:00 | p | 0 |  | 2025-02-19 14:02
322 | 1477 | BC1NYB3fqAlfckX7ECXI | Normal | 1 | 1.6.6.1.8 | 1.6.6.1.8 |  | 2025-04-02 08:00 | p | 9 |  | 2025-04-11 13:03
323 | 1478 | UR7xa7LgN3sMlpzxRjvW | Normal | 3 | 1.6.6.1.9 | 1.6.6.1.9 |  | 2025-12-16 08:00 | p | 13 |  | 2025-12-29 08:26
324 | 3932 | RKLg9Drqo40Q82TFH1VL | Normal | 1 | 1.6.4.15.2 | 1.6.4.15.2 |  | 2025-03-28 08:00 | p | 21 |  | 2025-04-18 16:49
325 | 3934 | 10Oh1H5M5HjeoWxU1u0w | Normal | 1 | 1.6.4.15.4 | 1.6.4.15.4 |  | 2025-03-28 08:00 | p | 38 |  | 2025-05-05 11:02
326 | 3936 | hwXDQy0MWIQ4jzjNT4oM | Normal | 1 | 1.6.4.15.3 | 1.6.4.15.3 |  | 2025-03-28 08:00 | p | 26 |  | 2025-04-23 14:13
327 | 3940 | 8UqvtHTIMRT16eupajKq | Normal | 1 | 1.6.4.15.5 | 1.6.4.15.5 |  | 2025-03-28 08:00 | p | 41 |  | 2025-05-08 08:55
328 | 3992 | cy141kwlo0X5isTqv3ku | Summary | 25 | 1.6.4.17.4 | 1.6.4.17.4 |  | 2025-04-24 08:00 | p | 34 |  | 2025-05-28 09:23
329 | 3993 | LBRozXrRhpq69SKlxnDb | Normal | 10 | 1.6.4.17.4.1 | 1.6.4.17.4.1 |  | 2025-04-24 08:00 | p | 34 |  | 2025-05-28 09:23
330 | 3994 | DvOjAQ6C9aXKnpaAVD1H | Normal | 5 | 1.6.4.17.4.2 | 1.6.4.17.4.2 |  | 2025-05-08 08:00 | p | 36 |  | 2025-06-13 15:55
331 | 3995 | AUkl27NW1i9i5huez8Rg | Normal | 5 | 1.6.4.17.4.3 | 1.6.4.17.4.3 |  | 2025-05-15 08:00 | p | 40 |  | 2025-06-24 13:47
332 | 3996 | Bw8X4DjnSuQgBiA6BEKp | Normal | 5 | 1.6.4.17.4.4 | 1.6.4.17.4.4 |  | 2025-05-22 08:00 | p | 40 |  | 2025-07-01 13:18
333 | 3997 | KJPP8ivswwWTIeIfPXEM | Summary | 25 | 1.6.4.17.3 | 1.6.4.17.3 |  | 2025-03-20 08:00 | p | 32 |  | 2025-04-21 16:12
334 | 3998 | 5UhDwyM7phAycUkk1Nye | Normal | 10 | 1.6.4.17.3.1 | 1.6.4.17.3.1 |  | 2025-03-20 08:00 | p | 32 |  | 2025-04-21 16:12
335 | 3999 | v6kjlf8aEDhSJHzOK2Uo | Normal | 5 | 1.6.4.17.3.2 | 1.6.4.17.3.2 |  | 2025-04-03 08:00 | p | 33 |  | 2025-05-06 13:19
336 | 4000 | Y3aJp60cYMHromf8xgAE | Normal | 5 | 1.6.4.17.3.3 | 1.6.4.17.3.3 |  | 2025-04-10 08:00 | p | 33 |  | 2025-05-13 13:44
337 | 4001 | Cjtbc2cmKWchyZlcOxo3 | Normal | 5 | 1.6.4.17.3.4 | 1.6.4.17.3.4 |  | 2025-04-17 08:00 | p | 32 |  | 2025-05-19 16:26
338 | 4004 | fF1Y54WMybWnXZsBJgYM | Normal | 1 | 1.6.4.17.2.2 | 1.6.4.17.2.2 |  | 2025-03-10 08:00 | p | 28 |  | 2025-04-07 16:11
339 | 4005 | NxZ8rMz5ZnJaz6z1SXKM | Normal | 3 | 1.6.4.17.2.3 | 1.6.4.17.2.3 |  | 2025-03-11 08:00 | p | 29 |  | 2025-04-09 08:26
340 | 4006 | fOTuJvqH3OcilXcZuEM5 | Normal | 4 | 1.6.4.17.2.4 | 1.6.4.17.2.4 |  | 2025-03-14 08:00 | p | 31 |  | 2025-04-14 15:27
341 | 6168 | BHtkkzlMW8757DY2qb23 | Summary | 143 | 1.6.4.19.3 | 1.6.4.19.3 |  | 2025-05-02 08:00 | q | -253 |  | 2024-08-22 08:00
342 | 6169 | gdW3U4pURjb9iKkAVexH | Summary | 60 | 1.6.4.19.3.1 | 1.6.4.19.3.1 |  | 2025-05-02 08:00 | q | -253 |  | 2024-08-22 08:00
343 | 6170 | AwYLgXY6Mo1DqCbUEhPQ | Summary | 30 | 1.6.4.19.3.1.1 | 1.6.4.19.3.1.1 |  | 2025-05-02 08:00 | q | -253 |  | 2024-08-22 08:00
344 | 6171 | ZR4zae2ZYhCMcZhj7T05 | Normal | 15 | 1.6.4.19.3.1.1.1 | 1.6.4.19.3.1.1.1 |  | 2025-05-02 08:00 | q | -253 |  | 2024-08-22 08:00
345 | 6172 | QgFskomqU31VYtYzB2O0 | Normal | 15 | 1.6.4.19.3.1.1.2 | 1.6.4.19.3.1.1.2 |  | 2025-05-23 08:00 | q | -251 |  | 2024-09-13 08:51
346 | 6173 | nRc7GqDGMG4VP1O5IlEd | Normal | 15 | 1.6.4.19.3.1.2 | 1.6.4.19.3.1.2 |  | 2025-06-16 08:00 | q | -250 |  | 2024-10-08 13:09
347 | 6174 | dvLkHNDhuFTU7AO5XWky | Normal | 15 | 1.6.4.19.3.1.3 | 1.6.4.19.3.1.3 |  | 2025-07-09 08:00 | q | -252 |  | 2024-10-29 13:56
348 | 6175 | IEttja5qNJ6P760Cd9De | Summary | 40 | 1.6.4.19.3.2 | 1.6.4.19.3.2 |  | 2025-07-30 08:00 | q | -250 |  | 2024-11-21 11:58
349 | 6176 | B6x3R7fnpOwupecmo90D | Normal | 10 | 1.6.4.19.3.2.1 | 1.6.4.19.3.2.1 |  | 2025-07-30 08:00 | q | -250 |  | 2024-11-21 11:58
350 | 6177 | vkZhJMfsZWiMPLTjgcam | Normal | 10 | 1.6.4.19.3.2.2 | 1.6.4.19.3.2.2 |  | 2025-08-13 08:00 | q | -245 |  | 2024-12-10 13:52
351 | 6178 | XEU5rnQh2VnDpMl1eT0o | Normal | 10 | 1.6.4.19.3.2.3 | 1.6.4.19.3.2.3 |  | 2025-08-27 08:00 | q | -245 |  | 2024-12-24 10:02
352 | 6179 | xksMzlhYjvKZ4p1XJwSB | Normal | 10 | 1.6.4.19.3.2.4 | 1.6.4.19.3.2.4 |  | 2025-09-11 08:00 | q | -244 |  | 2025-01-09 11:14
353 | 6180 | oR7r0RquVFe2h8pCK9HY | Normal | 10 | 1.6.4.19.3.3 | 1.6.4.19.3.3 |  | 2025-09-25 08:00 | q | -240 |  | 2025-01-27 13:26
354 | 6181 | UJ3hrxCJ5NslZjdDLEyu | Normal | 20 | 1.6.4.19.3.4 | 1.6.4.19.3.4 |  | 2025-10-09 08:00 | q | -240 |  | 2025-02-10 14:35
355 | 6182 | JQHbjwkPqIslt5thIOgQ | Normal | 5 | 1.6.4.19.3.5 | 1.6.4.19.3.5 |  | 2025-11-07 08:00 | q | -240 |  | 2025-03-11 14:19
356 | 6183 | 5NqxhAyIl3JXTpWWvSnV | Normal | 2 | 1.6.4.19.3.6 | 1.6.4.19.3.6 |  | 2025-11-17 08:00 | q | -244 |  | 2025-03-17 15:31
357 | 6184 | vx8CoW16lw8uEEVKaVp7 | Normal | 5 | 1.6.4.19.3.7 | 1.6.4.19.3.7 |  | 2025-11-19 08:00 | q | -244 |  | 2025-03-19 11:26
358 | 6185 | A91LND4pEy61zvjvAsaQ | Normal | 1 | 1.6.4.19.3.8 | 1.6.4.19.3.8 |  | 2025-11-26 08:00 | q | -244 |  | 2025-03-26 10:08
359 | 4040 | g5zNgGHP8U11wPTJKhcB | Normal | 20 | 1.6.4.20.1.3 | 1.6.4.20.1.3 |  | 2025-05-23 08:00 | q | -251 |  | 2024-09-13 10:10
360 | 4041 | f0PORH3GhEIXFjYfGbTd | Normal | 97 | 1.6.4.20.1.6 | 1.6.4.20.1.6 |  | 2025-05-23 08:00 | q | -251 |  | 2024-09-13 10:10
361 | 4042 | SyfMayqY4a7i0nZLPz6Y | Normal | 129 | 1.6.4.20.1.7 | 1.6.4.20.1.7 |  | 2025-09-15 08:00 | p | 99 |  | 2025-12-23 14:42
362 | 6621 | pXe0ZxltUhDf1quSL5q2 | Normal | 15 | 1.6.4.20.1.2 | 1.6.4.20.1.2 |  | 2025-05-02 08:00 | q | -253 |  | 2024-08-22 08:00
363 | 6622 | EmEy5gJckBYofEEYNXFv | Normal | 20 | 1.6.4.20.1.4 | 1.6.4.20.1.4 |  | 2026-02-26 08:00 | p | 69 |  | 2026-05-06 14:45
364 | 6623 | BVU87KMg9Rhzc6j5yKVh | Normal | 20 | 1.6.4.20.1.5 | 1.6.4.20.1.5 |  | 2026-03-26 08:00 | p | 75 |  | 2026-06-09 09:07
365 | 4043 | XbXkjxtfHUxhg4CK1elt | Summary | 127 | 1.6.4.20.2 | 1.6.4.20.2 |  | 2026-04-23 08:00 | p | 76 |  | 2026-07-08 11:24
366 | 4045 | mDphgqAAxA2RnvA52x8A | Normal | 20 | 1.6.4.20.2.1 | 1.6.4.20.2.1 |  | 2026-04-23 08:00 | p | 76 |  | 2026-07-08 11:24
367 | 4046 | 5HyQBVwuqRdeW1HhaSOP | Normal | 10 | 1.6.4.20.2.2 | 1.6.4.20.2.2 |  | 2026-05-21 08:00 | p | 82 |  | 2026-08-11 16:05
368 | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Normal | 72 | 1.6.4.20.2.3 | 1.6.4.20.2.3 |  | 2026-06-05 08:00 | p | 83 |  | 2026-08-27 10:41
369 | 4048 | ybbKhm9jdtNbVzABGZ8L | Normal | 20 | 1.6.4.20.2.4 | 1.6.4.20.2.4 |  | 2026-09-18 08:00 | p | 96 |  | 2026-12-23 10:38
370 | 4049 | kP1jeiEwkYg4HRpUjG4p | Normal | 5 | 1.6.4.20.2.5 | 1.6.4.20.2.5 |  | 2026-10-19 08:00 | p | 102 |  | 2027-01-29 09:24
371 | 4050 | jQIHIDf5FTnJxQysEvnn | Summary | 37 | 1.6.4.20.3 | 1.6.4.20.3 |  | 2026-09-18 08:00 | p | 96 |  | 2026-12-23 10:38
372 | 4051 | bizigDTezGi1mMHxJ1gi | Summary | 32 | 1.6.4.20.3.1 | 1.6.4.20.3.1 |  | 2026-09-18 08:00 | p | 96 |  | 2026-12-23 10:38
373 | 4052 | JSSXcLTdD9VQNM766DgK | Normal | 20 | 1.6.4.20.3.1.1 | 1.6.4.20.3.1.1 |  | 2026-09-18 08:00 | p | 96 |  | 2026-12-23 10:38
374 | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Normal | 12 | 1.6.4.20.3.1.2 | 1.6.4.20.3.1.2 |  | 2026-10-19 08:00 | p | 95 |  | 2027-01-22 15:39
375 | 4054 | WhXMUGkGRid5sulqMW8S | Summary | 5 | 1.6.4.20.3.2 | 1.6.4.20.3.2 |  | 2026-11-04 08:00 | p | 97 |  | 2027-02-09 08:06
376 | 4055 | dWrJCmOwv1i72p29KBXE | Normal | 2 | 1.6.4.20.3.2.1 | 1.6.4.20.3.2.1 |  | 2026-11-04 08:00 | p | 97 |  | 2027-02-09 08:06
377 | 4056 | a1SRK7UWhIIMlkKKriy9 | Normal | 1 | 1.6.4.20.3.2.2 | 1.6.4.20.3.2.2 |  | 2026-11-06 08:00 | p | 96 |  | 2027-02-10 16:11
378 | 4057 | NKnvgqAHKv63TOKudyZQ | Normal | 1 | 1.6.4.20.3.2.3 | 1.6.4.20.3.2.3 |  | 2026-11-09 08:00 | p | 94 |  | 2027-02-11 16:13
379 | 4058 | cbANjhwCBqAluf1RM04K | Normal | 1 | 1.6.4.20.3.2.4 | 1.6.4.20.3.2.4 |  | 2026-11-10 08:00 | p | 94 |  | 2027-02-12 15:25
380 | 4059 | sH9kz6O2EFda2hu4x8Kx | Summary | 12 | 1.6.4.20.3.3 | 1.6.4.20.3.3 |  | 2026-10-26 08:00 | p | 101 |  | 2027-02-04 09:16
381 | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Normal | 3 | 1.6.4.20.3.3.1 | 1.6.4.20.3.3.1 |  | 2026-10-26 08:00 | p | 101 |  | 2027-02-04 09:16
382 | 4061 | ViM2psfxppAdWr3IoYdq | Normal | 3 | 1.6.4.20.3.3.2 | 1.6.4.20.3.3.2 |  | 2026-10-29 08:00 | p | 102 |  | 2027-02-08 13:21
383 | 4062 | RvsEFsErXikPrAOovPaZ | Normal | 1 | 1.6.4.20.3.3.3 | 1.6.4.20.3.3.3 |  | 2026-11-03 08:00 | p | 100 |  | 2027-02-11 14:06
384 | 4063 | ma6GKJ3GzeKmeF4AshaM | Normal | 4 | 1.6.4.20.3.3.4 | 1.6.4.20.3.3.4 |  | 2026-11-04 08:00 | p | 100 |  | 2027-02-12 10:03
385 | 4064 | OALhjNOvEaqSDAmsS5Il | Normal | 1 | 1.6.4.20.3.3.5 | 1.6.4.20.3.3.5 |  | 2026-11-10 08:00 | p | 100 |  | 2027-02-18 09:34
386 | 7010 | l7MAqMN94R7DBQRgok6z | Normal | 5 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 2025-04-07 08:00 | p | 3 |  | 2025-04-10 13:11
387 | 7278 | 4Ma7Z2LiPmWBC9UI6vyb | Normal | 5 | 1.6.4.18.3.3.7.7 | 1.6.4.18.3.3.7.7 |  | 2025-03-24 08:00 | p | 0 |  | 2025-03-24 13:52
388 | 7300 | JMkMoXIhBdn9ICcOd798 | Normal | 5 | 1.6.4.18.3.3.7.4 | 1.6.4.18.3.3.7.4 |  | 2025-03-03 08:00 | q | -2 |  | 2025-02-28 08:19
389 | 7302 | 6S1rSJxqNAmNyzjZVL7L | Normal | 5 | 1.6.4.18.3.3.7.8 | 1.6.4.18.3.3.7.8 |  | 2025-03-31 08:00 | p | 4 |  | 2025-04-04 11:17
390 | 7282 | sTVLhyKAe9uIrxTuOSsB | Normal | 2 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 2025-02-20 08:00 | q | -8 |  | 2025-02-11 10:23
391 | 7283 | GyFcZSlU29ifaVubQEBd | Normal | 2 | 1.6.4.18.3.3.4.4 | 1.6.4.18.3.3.4.4 |  | 2025-02-24 08:00 | q | -10 |  | 2025-02-13 10:49
392 | 7284 | AoDPK2hmzwZjnwdc6ENo | Normal | 1 | 1.6.4.18.3.3.4.5 | 1.6.4.18.3.3.4.5 |  | 2025-02-26 08:00 | q | -7 |  | 2025-02-18 09:49
393 | 7285 | UP4KQN3vFTNJJtYiVHhd | Normal | 10 | 1.6.4.18.3.3.4.6 | 1.6.4.18.3.3.4.6 |  | 2025-02-27 08:00 | q | -7 |  | 2025-02-19 08:43
394 | 7289 | YNbMTserJcwdDTx8O6lt | Normal | 5 | 1.6.4.18.3.3.5.3 | 1.6.4.18.3.3.5.3 |  | 2025-02-21 08:00 | p | 0 |  | 2025-02-21 16:57
395 | 7290 | rpRUKocvSOF2GnoJsxWr | Normal | 2 | 1.6.4.18.3.3.5.4 | 1.6.4.18.3.3.5.4 |  | 2025-02-28 08:00 | p | 4 |  | 2025-03-04 09:58
396 | 7291 | ThxkR8uStFOgKr5Kajlm | Normal | 1 | 1.6.4.18.3.3.5.5 | 1.6.4.18.3.3.5.5 |  | 2025-03-04 08:00 | p | 2 |  | 2025-03-06 09:58
397 | 7292 | 6vEOHVPLFOaXnW1xcDp6 | Normal | 10 | 1.6.4.18.3.3.5.6 | 1.6.4.18.3.3.5.6 |  | 2025-03-05 08:00 | p | 2 |  | 2025-03-07 09:02
398 | 7296 | PnFVdPiNKahDkradYWdd | Normal | 5 | 1.6.4.18.3.3.6.3 | 1.6.4.18.3.3.6.3 |  | 2025-03-05 08:00 | p | 1 |  | 2025-03-06 11:06
399 | 7297 | JA5LCeR4tD4Vqq2Jfy9o | Normal | 2 | 1.6.4.18.3.3.6.4 | 1.6.4.18.3.3.6.4 |  | 2025-03-12 08:00 | p | 5 |  | 2025-03-17 09:24
400 | 7298 | uHK4wyA8DzlXgqm5UKoq | Normal | 1 | 1.6.4.18.3.3.6.5 | 1.6.4.18.3.3.6.5 |  | 2025-03-14 08:00 | p | 4 |  | 2025-03-18 16:05
401 | 7299 | ymtRqRQZa4AjGraGOZVd | Normal | 10 | 1.6.4.18.3.3.6.6 | 1.6.4.18.3.3.6.6 |  | 2025-03-17 08:00 | p | 2 |  | 2025-03-19 14:52
402 | 4204 | CRzwy8942pbCOpcOMW2v | Normal | 20 | 1.6.1.1.4 | 1.6.1.1.4 |  | 2025-06-16 08:00 | p | 32 |  | 2025-07-18 08:03
403 | 4218 | T5g2El1CSAmFZNlboxQh | Normal | 1 | 1.6.1.4 | 1.6.1.4 |  | 2025-07-16 08:00 | p | 30 |  | 2025-08-15 13:39
404 | 6080 | jFrzSNmYyPDtKSvRlBw2 | Normal | 1 | 1.6.1.6 | 1.6.1.6 |  | 2026-08-26 08:00 | q | -1115 |  | 2023-08-07 08:00
405 | 5507 | 1r4d5DbY2YIgMhg8HKuO | Normal | 3 | 1.6.3.3.2 | 1.6.3.3.2 |  | 2025-04-08 08:00 | p | 14 |  | 2025-04-22 10:47
406 | 5508 | wHSntGHJkj4aA0wA3fA2 | Normal | 14 | 1.6.3.3.3 | 1.6.3.3.3 |  | 2025-04-11 08:00 | p | 14 |  | 2025-04-25 15:13
407 | 5509 | 1FHP32ReWIveKb3JOWEG | Summary | 44 | 1.6.3.3.4 | 1.6.3.3.4 |  | 2025-05-01 08:00 | p | 15 |  | 2025-05-16 13:13
408 | 5510 | LTFwTsrnxYhrGNFUv7CM | Normal | 12 | 1.6.3.3.4.1 | 1.6.3.3.4.1 |  | 2025-05-01 08:00 | p | 15 |  | 2025-05-16 13:13
409 | 5511 | Od3mMFxB7LjrJLF1slz4 | Normal | 11 | 1.6.3.3.4.2 | 1.6.3.3.4.2 |  | 2025-05-19 08:00 | p | 21 |  | 2025-06-09 13:11
410 | 5512 | Des2hDKSMjcJndTJRzoQ | Normal | 11 | 1.6.3.3.4.3 | 1.6.3.3.4.3 |  | 2025-06-04 08:00 | p | 22 |  | 2025-06-26 15:16
411 | 5513 | z1vb48lrGwUUDjKbD3gr | Normal | 10 | 1.6.3.3.4.4 | 1.6.3.3.4.4 |  | 2025-06-20 08:00 | p | 25 |  | 2025-07-15 10:49
412 | 5514 | leNXdZKmybH4tpy20cQU | Normal | 5 | 1.6.3.3.5 | 1.6.3.3.5 |  | 2025-07-07 08:00 | p | 156 |  | 2025-12-10 16:55
413 | 7307 | eye8r8DevGvPITcdrMUe | Normal | 6 | 1.6.3.11.1.3.4.4 | 1.6.3.11.1.3.4.4 |  | 2025-02-10 08:00 | q | -7 |  | 2025-02-03 08:00
414 | 7308 | BXoPyB4GmzJwvFdrkJ7b | Normal | 1 | 1.6.3.11.1.3.4.5 | 1.6.3.11.1.3.4.5 |  | 2025-02-19 08:00 | q | -8 |  | 2025-02-10 11:28
415 | 7314 | zaliCdoIQDW2tx8wBQyt | Normal | 1 | 1.6.3.11.1.3.5.5 | 1.6.3.11.1.3.5.5 |  | 2025-02-20 08:00 | p | 0 |  | 2025-02-20 15:12
416 | 7318 | vWglY3BMmZCigDWMEMyY | Normal | 3 | 1.6.3.11.1.3.6.3 | 1.6.3.11.1.3.6.3 |  | 2025-02-20 08:00 | p | 0 |  | 2025-02-20 15:12
417 | 7319 | Fr6VbOwwg75s6X3Xcfql | Normal | 5 | 1.6.3.11.1.3.6.4 | 1.6.3.11.1.3.6.4 |  | 2025-02-25 08:00 | p | 1 |  | 2025-02-26 15:34
418 | 7320 | MRmQHJYBr9cc2OfLUSYd | Normal | 1 | 1.6.3.11.1.3.6.5 | 1.6.3.11.1.3.6.5 |  | 2025-03-04 08:00 | p | 1 |  | 2025-03-05 13:53
419 | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Milestone | 0 | 1.8.2.1 | 1.8.2.1 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
420 | 6295 | uPS9GNqRLP4065SnBhEr | Summary | 387 | 1.8.5 | 1.8.5 |  | 2024-09-03 08:00 | q | -393 |  | 2023-08-07 08:00
421 | 3679 | 1KDcwGZKgevw1MizqBh0 | Summary | 387 | 1.8.5.1 | 1.8.5.1 |  | 2024-09-03 08:00 | q | -393 |  | 2023-08-07 08:00
422 | 3680 | E8qsx9NjEz7vaL5H7EFb | Summary | 189 | 1.8.5.1.1 | 1.8.5.1.1 |  | 2025-03-24 08:00 | p | 16 |  | 2025-04-09 09:57
423 | 3681 | wdhUrQuIMTMPn1LoqO1m | Normal | 24 | 1.8.5.1.1.1 | 1.8.5.1.1.1 |  | 2025-03-24 08:00 | p | 16 |  | 2025-04-09 09:57
424 | 3682 | 38PSIqFGHzjKldiudT82 | Summary | 25 | 1.8.5.1.1.4 | 1.8.5.1.1.4 |  | 2025-04-25 08:00 | p | 7 |  | 2025-05-02 09:24
425 | 3683 | JW3LUw009FZ7ddD6CdLX | Normal | 20 | 1.8.5.1.1.4.1 | 1.8.5.1.1.4.1 |  | 2025-04-25 08:00 | p | 7 |  | 2025-05-02 09:24
426 | 3684 | g3f8U3i4iakOhylueut6 | Normal | 5 | 1.8.5.1.1.4.2 | 1.8.5.1.1.4.2 |  | 2025-05-23 08:00 | p | 11 |  | 2025-06-03 16:26
427 | 3685 | eStRoX3vnaDmRLAWk58C | Summary | 40 | 1.8.5.1.1.5 | 1.8.5.1.1.5 |  | 2025-06-02 08:00 | p | 10 |  | 2025-06-12 11:53
428 | 3686 | 7zhxjkpiLTAH9tiW1eYy | Normal | 20 | 1.8.5.1.1.5.1 | 1.8.5.1.1.5.1 |  | 2025-06-02 08:00 | p | 10 |  | 2025-06-12 11:53
429 | 3687 | 0zzWvesUS18qEUfjK5NH | Normal | 5 | 1.8.5.1.1.5.2 | 1.8.5.1.1.5.2 |  | 2025-07-01 08:00 | p | 17 |  | 2025-07-18 15:02
430 | 3688 | zSUYYsBrfiOGi6qJakS6 | Normal | 5 | 1.8.5.1.1.5.3 | 1.8.5.1.1.5.3 |  | 2025-07-09 08:00 | p | 16 |  | 2025-07-25 16:44
431 | 3689 | X7sWUqInOJZ9zcVzmfT1 | Normal | 5 | 1.8.5.1.1.5.4 | 1.8.5.1.1.5.4 |  | 2025-07-16 08:00 | p | 19 |  | 2025-08-04 10:03
432 | 3690 | 8YDpqEvemQaMsfVmGpF8 | Normal | 5 | 1.8.5.1.1.5.5 | 1.8.5.1.1.5.5 |  | 2025-07-23 08:00 | p | 19 |  | 2025-08-11 11:02
433 | 3691 | ofZrlktbiXkVpuhhIeO5 | Summary | 25 | 1.8.5.1.1.6 | 1.8.5.1.1.6 |  | 2025-07-01 08:00 | p | 17 |  | 2025-07-18 15:02
434 | 3692 | xRsKOxB8zGAnVTXugcHQ | Normal | 20 | 1.8.5.1.1.6.1 | 1.8.5.1.1.6.1 |  | 2025-07-01 08:00 | p | 17 |  | 2025-07-18 15:02
435 | 3693 | Hn8rBaTvxeP9Vb10zF48 | Normal | 5 | 1.8.5.1.1.6.2 | 1.8.5.1.1.6.2 |  | 2025-07-30 08:00 | p | 19 |  | 2025-08-18 16:30
436 | 3694 | 4tipOydrC0LTNincaMDW | Summary | 35 | 1.8.5.1.1.7 | 1.8.5.1.1.7 |  | 2025-07-30 08:00 | p | 19 |  | 2025-08-18 16:30
437 | 3695 | lT6NpgfSYqKHtVYFLSzF | Normal | 20 | 1.8.5.1.1.7.1 | 1.8.5.1.1.7.1 |  | 2025-07-30 08:00 | p | 19 |  | 2025-08-18 16:30
438 | 3696 | gijouZuJR1ZVcSfHKSTf | Normal | 5 | 1.8.5.1.1.7.2 | 1.8.5.1.1.7.2 |  | 2025-08-27 08:00 | p | 33 |  | 2025-09-29 09:56
439 | 3697 | 1158ttL4JEmZYV6RmdcS | Normal | 5 | 1.8.5.1.1.7.3 | 1.8.5.1.1.7.3 |  | 2025-09-04 08:00 | p | 33 |  | 2025-10-07 10:03
440 | 3698 | AKCwPpEPQi4iH3XDRpiM | Normal | 5 | 1.8.5.1.1.7.4 | 1.8.5.1.1.7.4 |  | 2025-09-11 08:00 | p | 35 |  | 2025-10-16 08:57
441 | 3699 | AYANEA6OuC5b95kp3uyI | Summary | 30 | 1.8.5.1.1.8 | 1.8.5.1.1.8 |  | 2025-08-27 08:00 | p | 33 |  | 2025-09-29 09:56
442 | 3700 | WE9bFDn3y5M7oiID5UPj | Normal | 20 | 1.8.5.1.1.8.1 | 1.8.5.1.1.8.1 |  | 2025-08-27 08:00 | p | 33 |  | 2025-09-29 09:56
443 | 3701 | CXSHp4tESy2S0nMNpo3C | Normal | 5 | 1.8.5.1.1.8.2 | 1.8.5.1.1.8.2 |  | 2025-09-25 08:00 | p | 29 |  | 2025-10-24 13:58
444 | 3702 | sTuPByKbZEfSXxt0Z2G9 | Normal | 5 | 1.8.5.1.1.8.3 | 1.8.5.1.1.8.3 |  | 2025-10-02 08:00 | p | 29 |  | 2025-10-31 16:47
445 | 3703 | WHZRJAK4v6S9Zk2EBeP3 | Summary | 40 | 1.8.5.1.1.9 | 1.8.5.1.1.9 |  | 2025-09-25 08:00 | p | 29 |  | 2025-10-24 13:58
446 | 3704 | 3CXbrhXJooXd98jlpAkg | Normal | 20 | 1.8.5.1.1.9.1 | 1.8.5.1.1.9.1 |  | 2025-09-25 08:00 | p | 29 |  | 2025-10-24 13:58
447 | 3705 | RO9RShNcg0h7x9fD24Zk | Normal | 5 | 1.8.5.1.1.9.2 | 1.8.5.1.1.9.2 |  | 2025-10-24 08:00 | p | 21 |  | 2025-11-14 10:21
448 | 3706 | w8MhGnhxyXFIHvJdw6bc | Normal | 5 | 1.8.5.1.1.9.3 | 1.8.5.1.1.9.3 |  | 2025-10-31 08:00 | p | 19 |  | 2025-11-19 13:23
449 | 3707 | dJNKgtiJ1M8pNoPOlZcZ | Normal | 5 | 1.8.5.1.1.9.4 | 1.8.5.1.1.9.4 |  | 2025-11-07 08:00 | p | 21 |  | 2025-11-28 11:01
450 | 3708 | 84VtM14FQkMGurZDdBLv | Normal | 5 | 1.8.5.1.1.9.5 | 1.8.5.1.1.9.5 |  | 2025-11-17 08:00 | p | 21 |  | 2025-12-08 08:35
451 | 3709 | gpO5WcJkYid7jZAXZwbn | Summary | 40 | 1.8.5.1.1.10 | 1.8.5.1.1.10 |  | 2025-10-24 08:00 | p | 21 |  | 2025-11-14 10:21
452 | 3710 | KOKaQwRJEoC6vlU3mKjm | Normal | 20 | 1.8.5.1.1.10.1 | 1.8.5.1.1.10.1 |  | 2025-10-24 08:00 | p | 21 |  | 2025-11-14 10:21
453 | 3711 | XXu8BmtFqx4o2r8a6o98 | Normal | 5 | 1.8.5.1.1.10.2 | 1.8.5.1.1.10.2 |  | 2025-11-24 08:00 | p | 22 |  | 2025-12-16 13:41
454 | 3712 | sZwrgRbHYjKWcIa9rVK3 | Normal | 5 | 1.8.5.1.1.10.3 | 1.8.5.1.1.10.3 |  | 2025-12-02 08:00 | p | 22 |  | 2025-12-24 08:37
455 | 3713 | 4NbryuRKpmrExDEDqArG | Normal | 5 | 1.8.5.1.1.10.4 | 1.8.5.1.1.10.4 |  | 2025-12-09 08:00 | p | 24 |  | 2026-01-02 15:25
456 | 3714 | Fbm1iHrhCX8z8SNRXJuq | Normal | 5 | 1.8.5.1.1.10.5 | 1.8.5.1.1.10.5 |  | 2025-12-16 08:00 | p | 24 |  | 2026-01-09 09:53
457 | 6646 | CmmxWTpZgFyyAwkQnNh3 | Normal | 10 | 1.8.5.1.1.2 | 1.8.5.1.1.2 |  | 2025-04-25 08:00 | p | 7 |  | 2025-05-02 09:24
458 | 6647 | hWzCSsDre5WTTpryk1b0 | Normal | 5 | 1.8.5.1.1.3 | 1.8.5.1.1.3 |  | 2025-05-09 08:00 | p | 6 |  | 2025-05-15 15:57
459 | 3715 | V6i7uYjEJBRYHjhIimqJ | Summary | 50 | 1.8.5.1.2 | 1.8.5.1.2 |  | 2025-12-23 08:00 | p | 28 |  | 2026-01-20 16:54
460 | 3716 | bdy5zVX59rD935sK6M5v | Normal | 20 | 1.8.5.1.2.1 | 1.8.5.1.2.1 |  | 2025-12-23 08:00 | p | 28 |  | 2026-01-20 16:54
461 | 3717 | 5PdqCAMtbYgi5VsFO6ls | Normal | 20 | 1.8.5.1.2.4 | 1.8.5.1.2.4 |  | 2026-02-06 08:00 | p | 25 |  | 2026-03-03 10:48
462 | 6671 | 0oTh3tmNX3iVSaVNVmGK | Normal | 5 | 1.8.5.1.2.2 | 1.8.5.1.2.2 |  | 2026-01-23 08:00 | p | 26 |  | 2026-02-18 09:11
463 | 6672 | BKyGOzVPyPwKpI9CyseJ | Normal | 5 | 1.8.5.1.2.3 | 1.8.5.1.2.3 |  | 2026-01-30 08:00 | p | 27 |  | 2026-02-26 09:38
464 | 3718 | vTyTgxcbRSz6H6lqDAEf | Summary | 20 | 1.8.5.1.3 | 1.8.5.1.3 |  | 2026-03-09 08:00 | p | 18 |  | 2026-03-27 11:53
465 | 3719 | B9ymEBZ7zimHMMqNS20Q | Normal | 20 | 1.8.5.1.3.1 | 1.8.5.1.3.1 |  | 2026-03-09 08:00 | p | 18 |  | 2026-03-27 11:53
466 | 3720 | rPRo0RE1uNkj9oG127hu | Summary | 109 | 1.8.5.1.4 | 1.8.5.1.4 |  | 2025-03-19 08:00 | q | -590 |  | 2023-08-07 08:00
467 | 3721 | 45j7fpB55qVEeWfRBgCv | Normal | 1 | 1.8.5.1.4.1 | 1.8.5.1.4.1 |  | 2025-03-19 08:00 | q | -590 |  | 2023-08-07 08:00
468 | 3722 | hYa6Ppkzu6veYWmxHffd | Normal | 27 | 1.8.5.1.4.2 | 1.8.5.1.4.2 |  | 2025-03-20 08:00 | q | -590 |  | 2023-08-07 16:59
469 | 6649 | TeFWDZJ3h8q4yVNptUYE | Normal | 28 | 1.8.5.1.4.3 | 1.8.5.1.4.3 |  | 2025-04-28 08:00 | q | -591 |  | 2023-09-14 10:45
470 | 6650 | FvuNLI4Jaew3VjPpwL3e | Normal | 28 | 1.8.5.1.4.4 | 1.8.5.1.4.4 |  | 2025-06-06 08:00 | q | -590 |  | 2023-10-24 11:20
471 | 6651 | T3J0AzovT4qFTLJ7Lgki | Normal | 15 | 1.8.5.1.4.5 | 1.8.5.1.4.5 |  | 2025-07-18 08:00 | q | -603 |  | 2023-11-22 11:54
472 | 6652 | 0afM7N7hGdWHQjlFenVR | Normal | 10 | 1.8.5.1.4.6 | 1.8.5.1.4.6 |  | 2025-08-08 08:00 | q | -602 |  | 2023-12-14 08:10
473 | 3724 | ZCOxRRLLrh9Pa7VnBAyk | Normal | 27 | 1.8.5.1.5.1 | 1.8.5.1.5.1 |  | 2025-03-24 08:00 | p | 16 |  | 2025-04-09 09:57
474 | 6661 | bQxmmL7mcUsEGpKkQTDo | Normal | 28 | 1.8.5.1.5.2 | 1.8.5.1.5.2 |  | 2025-04-30 08:00 | p | 12 |  | 2025-05-12 16:01
475 | 6662 | CVNpv9CNU8XhfLmVwl8x | Normal | 28 | 1.8.5.1.5.3 | 1.8.5.1.5.3 |  | 2025-06-10 08:00 | p | 14 |  | 2025-06-24 09:50
476 | 6663 | LVExlIxeJ6XB3yqm0Dzs | Normal | 28 | 1.8.5.1.5.4 | 1.8.5.1.5.4 |  | 2025-07-22 08:00 | p | 13 |  | 2025-08-04 10:00
477 | 6664 | Io9oZ1dPqEE9GDlMTPxh | Normal | 28 | 1.8.5.1.5.5 | 1.8.5.1.5.5 |  | 2025-08-29 08:00 | p | 13 |  | 2025-09-11 10:43
478 | 6665 | ycT0qtEFjd4p02S4Ehf1 | Normal | 28 | 1.8.5.1.5.6 | 1.8.5.1.5.6 |  | 2025-10-09 08:00 | p | 13 |  | 2025-10-22 16:20
479 | 6666 | sX3PHseynvzwKI9my2AH | Normal | 15 | 1.8.5.1.5.7 | 1.8.5.1.5.7 |  | 2025-11-20 08:00 | p | 11 |  | 2025-12-01 13:30
480 | 6667 | 0dYk2X7XWh2rSSHkHo2L | Normal | 10 | 1.8.5.1.5.8 | 1.8.5.1.5.8 |  | 2025-12-12 08:00 | p | 21 |  | 2026-01-02 13:43
481 | 6668 | NGuTznXCCG5yuIi6lGQO | Normal | 1 | 1.8.5.1.5.10 | 1.8.5.1.5.10 |  | 2025-06-20 08:00 | q | -7 |  | 2025-06-12 16:22
482 | 6669 | t8MCocRefa6DhiQNsJVn | Normal | 1 | 1.8.5.1.5.11 | 1.8.5.1.5.11 |  | 2025-06-23 08:00 | q | -6 |  | 2025-06-16 09:10
483 | 6670 | vWxPVjk5e7KHTev8998h | Normal | 1 | 1.8.5.1.5.12 | 1.8.5.1.5.12 |  | 2025-06-24 08:00 | q | -6 |  | 2025-06-17 10:26
484 | 3726 | 5hjTNIk7WmpZNtmCLhPN | Summary | 96 | 1.8.5.1.6 | 1.8.5.1.6 |  | 2025-05-08 08:00 | q | -191 |  | 2024-10-29 08:00
485 | 3727 | rGcF2XgkgPtqRDM3KJ2D | Normal | 28 | 1.8.5.1.6.1 | 1.8.5.1.6.1 |  | 2025-05-08 08:00 | q | -191 |  | 2024-10-29 08:00
486 | 3728 | Hgqc9wbzS3SDikBm20zt | Normal | 28 | 1.8.5.1.6.3 | 1.8.5.1.6.3 |  | 2025-07-11 08:00 | q | -183 |  | 2025-01-08 13:33
487 | 6653 | K0AYRckqpyO0HzRrxXG6 | Normal | 15 | 1.8.5.1.6.2 | 1.8.5.1.6.2 |  | 2025-06-18 08:00 | q | -183 |  | 2024-12-16 08:38
488 | 6654 | MMK0qYycfTMCrFAZcf8J | Normal | 15 | 1.8.5.1.6.4 | 1.8.5.1.6.4 |  | 2025-08-20 08:00 | q | -172 |  | 2025-02-28 09:27
489 | 6655 | gl8c5oVG5KfrLbsQSFL4 | Normal | 10 | 1.8.5.1.6.5 | 1.8.5.1.6.5 |  | 2025-09-11 08:00 | q | -170 |  | 2025-03-24 14:21
490 | 3729 | Y6b5KP0DE9c4tlFzqxp3 | Summary | 81 | 1.8.5.1.7 | 1.8.5.1.7 |  | 2025-03-11 08:00 | q | -582 |  | 2023-08-07 08:00
491 | 3730 | TswICWhG0Mjj1DenbPW5 | Normal | 28 | 1.8.5.1.7.1 | 1.8.5.1.7.1 |  | 2025-03-11 08:00 | q | -582 |  | 2023-08-07 08:00
492 | 6626 | 9d2gtkuh8SmNZwArNzpn | Normal | 10 | 1.8.5.1.7.4 | 1.8.5.1.7.4 |  | 2025-06-20 08:00 | q | -583 |  | 2023-11-14 08:25
493 | 6627 | QBgG0JxqOymB6vyjKsRZ | Normal | 28 | 1.8.5.1.7.2 | 1.8.5.1.7.2 |  | 2025-04-18 08:00 | q | -577 |  | 2023-09-18 16:36
494 | 6628 | PAI9VZBMaYriaY1wvhOi | Normal | 15 | 1.8.5.1.7.3 | 1.8.5.1.7.3 |  | 2025-05-29 08:00 | q | -581 |  | 2023-10-25 15:22
495 | 3733 | ufu7SWDoeBfTzZW24BQU | Summary | 189 | 1.8.5.1.9 | 1.8.5.1.9 |  | 2025-03-17 08:00 | q | -588 |  | 2023-08-07 08:00
496 | 3734 | cAszcoDUs4YPdXAiXa4B | Milestone | 0 | 1.8.5.1.9.1 | 1.8.5.1.9.1 |  | 2025-03-17 08:00 | q | -588 |  | 2023-08-07 08:00
497 | 3735 | rgqtw8hyurrfag2amXLA | Normal | 109 | 1.8.5.1.9.2 | 1.8.5.1.9.2 |  | 2025-03-17 08:00 | q | -588 |  | 2023-08-07 08:00
498 | 3736 | eIMYQUSTObIc5Lp6kKBE | Normal | 40 | 1.8.5.1.9.3 | 1.8.5.1.9.3 |  | 2025-08-20 08:00 | q | -588 |  | 2024-01-09 09:41
499 | 3737 | z19Wnme0hJcfEI4IfIQR | Normal | 25 | 1.8.5.1.9.4 | 1.8.5.1.9.4 |  | 2025-10-17 08:00 | p | 26 |  | 2025-11-12 10:27
500 | 6657 | uq5fluI8KT8LkPx57ktn | Normal | 10 | 1.8.5.1.9.5 | 1.8.5.1.9.5 |  | 2025-11-24 08:00 | p | 21 |  | 2025-12-15 14:16
501 | 6658 | ktg0XNnAmjjc1caqICt2 | Normal | 5 | 1.8.5.1.9.6 | 1.8.5.1.9.6 |  | 2025-12-09 08:00 | p | 24 |  | 2026-01-02 09:26
502 | 3738 | bohrZqwOTsvUL4DEUnjh | Summary | 139 | 1.8.5.1.10 | 1.8.5.1.10 |  | 2025-03-17 08:00 | q | -588 |  | 2023-08-07 08:00
503 | 3739 | Ba23bBwg4xGpRd3Ht4kS | Normal | 24 | 1.8.5.1.10.1 | 1.8.5.1.10.1 |  | 2025-03-17 08:00 | q | -588 |  | 2023-08-07 08:00
504 | 3740 | lRtbtcrLyr1QGd0laoJi | Normal | 25 | 1.8.5.1.10.2 | 1.8.5.1.10.2 |  | 2025-04-18 08:00 | q | -589 |  | 2023-09-06 09:53
505 | 3741 | V05WnFKB5t2LuixhoKHO | Normal | 25 | 1.8.5.1.10.3 | 1.8.5.1.10.3 |  | 2025-05-23 08:00 | q | -588 |  | 2023-10-12 14:10
506 | 3742 | LRjVz0hoZuIRlQgcLYzs | Normal | 25 | 1.8.5.1.10.6 | 1.8.5.1.10.6 |  | 2025-08-06 08:00 | q | -592 |  | 2023-12-22 13:47
507 | 6648 | Z5T3n0GGVz8PB0IY5TXC | Normal | 10 | 1.8.5.1.10.5 | 1.8.5.1.10.5 |  | 2025-07-23 08:00 | q | -588 |  | 2023-12-12 14:39
508 | 6656 | tqprQgHoroqT051BXug3 | Normal | 15 | 1.8.5.1.10.4 | 1.8.5.1.10.4 |  | 2025-07-01 08:00 | q | -586 |  | 2023-11-22 14:32
509 | 6659 | NN3Qiea1foOxv05JqXnT | Normal | 10 | 1.8.5.1.10.7 | 1.8.5.1.10.7 |  | 2025-09-11 08:00 | q | -583 |  | 2024-02-05 11:06
510 | 6660 | pWIs4hM6SgH2pFjSQ3qo | Normal | 5 | 1.8.5.1.10.8 | 1.8.5.1.10.8 |  | 2025-09-25 08:00 | q | -586 |  | 2024-02-16 09:31
511 | 6642 | A7Bd82G8YCk8VjEZkcvi | Summary | 135 | 1.8.5.1.8 | 1.8.5.1.8 |  | 2025-10-17 08:00 | q | -608 |  | 2024-02-16 08:12
512 | 3731 | 02LiOyWN4DF8GOeNSP5s | Normal | 20 | 1.8.5.1.8.1 | 1.8.5.1.8.1 |  | 2025-10-17 08:00 | q | -608 |  | 2024-02-16 08:12
513 | 3732 | x85AkT9s5HT2a4U2goND | Normal | 20 | 1.8.5.1.8.8 | 1.8.5.1.8.8 |  | 2025-11-17 08:00 | q | -615 |  | 2024-03-11 09:57
514 | 6629 | n59ds33sZr9JNOobmYWE | Normal | 30 | 1.8.5.1.8.2 | 1.8.5.1.8.2 |  | 2025-11-17 08:00 | q | -615 |  | 2024-03-11 09:57
515 | 6630 | y36QmeQSyS7BZflkeM7e | Normal | 10 | 1.8.5.1.8.3 | 1.8.5.1.8.3 |  | 2025-12-31 08:00 | q | -631 |  | 2024-04-08 11:05
516 | 6631 | Ghk1eKq5exIyUH3hdAeR | Normal | 20 | 1.8.5.1.8.4 | 1.8.5.1.8.4 |  | 2026-01-15 08:00 | q | -632 |  | 2024-04-22 15:09
517 | 6632 | 5y36mClzGR7vkSsODb4C | Normal | 15 | 1.8.5.1.8.5 | 1.8.5.1.8.5 |  | 2026-02-13 08:00 | q | -632 |  | 2024-05-21 08:31
518 | 6633 | uS272glxjETpDiVeJyGv | Normal | 20 | 1.8.5.1.8.6 | 1.8.5.1.8.6 |  | 2026-03-09 08:00 | q | -640 |  | 2024-06-06 13:24
519 | 6634 | 65ghvPiwU0AxSKrC11rG | Normal | 20 | 1.8.5.1.8.7 | 1.8.5.1.8.7 |  | 2026-04-06 08:00 | q | -635 |  | 2024-07-09 11:38
520 | 6643 | sKnPCsxlq51dE8cz52fo | Normal | 10 | 1.8.5.1.8.9 | 1.8.5.1.8.9 |  | 2025-12-16 08:00 | q | -612 |  | 2024-04-12 08:54
521 | 6644 | 0NVu6ABxwy3imKaZ2MTJ | Normal | 10 | 1.8.5.1.8.10 | 1.8.5.1.8.10 |  | 2025-12-31 08:00 | q | -11 |  | 2025-12-19 09:31
522 | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Summary | 1 | 1.8.1 | 1.8.1 |  | 2026-10-07 16:58 | p | 580 |  | 2028-05-10 13:40
523 | 6082 | YsSSuERf5VIDKO5m8eZo | Normal | 1 | 1.8.1.1 | 1.8.1.1 |  | 2026-10-07 16:58 | p | 580 |  | 2028-05-10 13:40
524 | 6313 | 8HYxn50EKf1DU0fX0MF7 | Summary | 391 | 1.8.4 | 1.8.4 |  | 2025-03-20 08:00 | q | -591 |  | 2023-08-07 08:00
525 | 5516 | dd6fm1lW4tBXPtNV5RGW | Summary | 391 | 1.8.4.1 | 1.8.4.1 |  | 2025-03-20 08:00 | q | -591 |  | 2023-08-07 08:00
526 | 5517 | IHfroMkwx3TZoTXYbBOK | Normal | 40 | 1.8.4.1.1 | 1.8.4.1.1 |  | 2025-03-20 08:00 | q | -591 |  | 2023-08-07 08:00
527 | 5518 | V0a5XEJ0jxIkhnpEDg8e | Normal | 40 | 1.8.4.1.2 | 1.8.4.1.2 |  | 2025-03-20 08:00 | q | -591 |  | 2023-08-07 08:00
528 | 5519 | D5sl3M5NpO77EU7TPYT0 | Normal | 40 | 1.8.4.1.3 | 1.8.4.1.3 |  | 2025-03-20 08:00 | q | -591 |  | 2023-08-07 08:00
529 | 5523 | APkwTVep7mUhgmcCl4NB | Milestone | 0 | 1.8.4.1.4 | 1.8.4.1.4 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
530 | 5527 | Mw5Re8SivA42laH7UhJE | Milestone | 0 | 1.8.4.1.5 | 1.8.4.1.5 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
531 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 2021-01-04 08:00 | q | -1307 |  | 2017-06-07 08:00
532 | 5332 | Jas5wmBgln6JvMRLtRUk | Summary | 110 | 1.9.3.1 | 1.9.3.1 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
533 | 5333 | NEZJUiuEFBeqDBEbXbzQ | Milestone | 0 | 1.9.3.1.1 | 1.9.3.1.1 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
534 | 5334 | 5Bt8vyiG2PJ2FKCjQPP1 | Summary | 74 | 1.9.3.1.2 | 1.9.3.1.2 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
535 | 6471 | xmZvSzAhf2D9ir29atKO | Normal | 8 | 1.9.3.1.2.1 | 1.9.3.1.2.1 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
536 | 6472 | j0VQ7fJsNHb1HpOVRoJN | Normal | 7 | 1.9.3.1.2.2 | 1.9.3.1.2.2 |  | 2025-10-20 08:30 | q | -33 |  | 2025-09-16 10:33
537 | 6473 | FN1N5cBOnOQJN0lvtY6J | Normal | 5 | 1.9.3.1.2.3 | 1.9.3.1.2.3 |  | 2025-10-29 08:30 | q | -32 |  | 2025-09-26 09:27
538 | 6474 | k77H7bJ7aRKhBrZeZFzu | Normal | 10 | 1.9.3.1.2.4 | 1.9.3.1.2.4 |  | 2025-11-05 08:30 | q | -32 |  | 2025-10-03 14:29
539 | 6475 | TkBVMCiZTEhYxjcnMNRI | Normal | 8 | 1.9.3.1.2.5 | 1.9.3.1.2.5 |  | 2025-11-20 08:30 | q | -30 |  | 2025-10-20 14:59
540 | 6476 | HdsfOo0UbW7iVGjY7L1O | Normal | 10 | 1.9.3.1.2.6 | 1.9.3.1.2.6 |  | 2025-12-03 08:30 | q | -35 |  | 2025-10-28 16:00
541 | 6477 | m1G8PrmdvRxZwBbLlVUQ | Normal | 7 | 1.9.3.1.2.7 | 1.9.3.1.2.7 |  | 2025-12-17 08:30 | q | -29 |  | 2025-11-17 14:43
542 | 6478 | ZDDqpCGw2ELQiAxZVJFo | Normal | 7 | 1.9.3.1.2.8 | 1.9.3.1.2.8 |  | 2025-12-29 08:30 | q | -32 |  | 2025-11-26 14:19
543 | 6479 | i51TyrBkECB0t7wKJruE | Normal | 7 | 1.9.3.1.2.9 | 1.9.3.1.2.9 |  | 2026-01-07 08:30 | q | -29 |  | 2025-12-08 08:48
544 | 6480 | XeKgBzwPereNdZmXnTFt | Normal | 5 | 1.9.3.1.2.10 | 1.9.3.1.2.10 |  | 2026-01-16 08:30 | q | -28 |  | 2025-12-18 11:40
545 | 5335 | fBEkx0xCtVpw1OeE4jLB | Summary | 25 | 1.9.3.1.3 | 1.9.3.1.3 |  | 2026-01-23 08:30 | q | -27 |  | 2025-12-26 11:55
546 | 5336 | FIhKbBOHnlTp0loBBfvV | Normal | 3 | 1.9.3.1.3.1 | 1.9.3.1.3.1 |  | 2026-01-23 08:30 | q | -27 |  | 2025-12-26 11:55
547 | 5337 | TPAbtCx4KhMQiN0iVD1F | Normal | 0 | 1.9.3.1.3.2 | 1.9.3.1.3.2 |  | 2026-01-23 08:30 | q | -27 |  | 2025-12-26 11:55
548 | 5338 | NXWa8B3rzsUFws6lYttF | Normal | 5 | 1.9.3.1.3.3 | 1.9.3.1.3.3 |  | 2026-01-23 08:30 | q | -27 |  | 2025-12-26 11:55
549 | 5339 | o98eRuEZGwoxxa1Byl7H | Normal | 5 | 1.9.3.1.3.4 | 1.9.3.1.3.4 |  | 2026-01-23 08:30 | q | -27 |  | 2025-12-26 11:55
550 | 5340 | lQJTDBnvPE8mTPnPre3v | Normal | 10 | 1.9.3.1.3.5 | 1.9.3.1.3.5 |  | 2026-01-30 08:30 | q | -27 |  | 2026-01-02 14:46
551 | 5341 | nevxwfefPkBzu42CDbNd | Normal | 10 | 1.9.3.1.3.6 | 1.9.3.1.3.6 |  | 2026-02-13 08:30 | q | -29 |  | 2026-01-14 13:07
552 | 5342 | s0JiBiXDLP6oybWmkZ43 | Normal | 6 | 1.9.3.1.4 | 1.9.3.1.4 |  | 2026-02-27 08:30 | q | -28 |  | 2026-01-29 08:33
553 | 5343 | NROXqcLUoQ0RLz64rMVc | Normal | 5 | 1.9.3.1.5 | 1.9.3.1.5 |  | 2026-03-09 08:30 | q | -31 |  | 2026-02-05 15:31
554 | 5344 | Kw3Fj6kwk5uOl7tQyqrL | Milestone | 0 | 1.9.3.1.6 | 1.9.3.1.6 |  | 2026-03-16 08:30 | q | -31 |  | 2026-02-12 16:16
555 | 795 | 85yV4lhIxXIziyB5R2QA | Normal | 1 | 1.9.9.1 | 1.9.9.1 |  | 2026-09-16 13:00 | p | 929 |  | 2029-04-03 11:47
556 | 844 | 1qfp8o9PQxr9vZvO7S5k | Normal | 1 | 1.9.9.4 | 1.9.9.4 |  | 2026-10-02 13:00 | p | 929 |  | 2029-04-19 10:06
557 | 866 | 0rLFG0X22Uukcn0axQTO | Normal | 50 | 1.9.9.7.2.6 | 1.9.9.7.2.6 |  | 2025-04-15 08:00 | p | 23 |  | 2025-05-08 13:10
558 | 869 | 8QCM3LZ8SN5y0jCLtGNh | Summary | 129 | 1.9.9.7.2.7 | 1.9.9.7.2.7 |  | 2025-06-26 08:00 | p | 26 |  | 2025-07-22 15:07
559 | 6419 | NORPsF566zq8VZyN1UzF | Normal | 10 | 1.9.9.7.2.7.1 | 1.9.9.7.2.7.1 |  | 2025-06-26 08:00 | p | 26 |  | 2025-07-22 15:07
560 | 6420 | 043wOhyyEd8vJkuUBkFf | Normal | 40 | 1.9.9.7.2.7.2 | 1.9.9.7.2.7.2 |  | 2025-07-11 08:00 | p | 26 |  | 2025-08-06 11:19
561 | 6421 | JZROXyECnTBG3SBjYZJ8 | Normal | 79 | 1.9.9.7.2.7.3 | 1.9.9.7.2.7.3 |  | 2025-09-08 08:00 | p | 21 |  | 2025-09-29 08:24
562 | 4667 | gXRr1908PexMoLIDosFv | Normal | 100 | 1.9.9.14.3 | 1.9.9.14.3 |  | 2025-07-01 08:00 | p | 58 |  | 2025-08-28 14:51
563 | 4668 | G3SLCzd88WLMRnAF5Et7 | Normal | 0 | 1.9.9.14.4 | 1.9.9.14.4 |  | 2026-04-20 08:00 | p | 935 |  | 2028-11-10 11:17
564 | 4669 | aeClBbTsJ3qrKHWqQ1Rw | Normal | 40 | 1.9.9.14.5 | 1.9.9.14.5 |  | 2025-11-24 08:00 | p | 51 |  | 2026-01-14 08:57
565 | 4679 | rpzkOhA603pApmNdMeVE | Normal | 0 | 1.9.9.14.6 | 1.9.9.14.6 |  | 2026-05-22 08:00 | p | 934 |  | 2028-12-11 08:48
566 | 5787 | r6JEZEKCpBbNZRe1W7Ef | Normal | 91 | 1.9.9.14.2 | 1.9.9.14.2 |  | 2025-02-20 08:00 | p | 28 |  | 2025-03-20 08:03
567 | 899 | w1GWQdUx9oG06oopRYZx | Summary | 24 | 1.9.9.15 | 1.9.9.15 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
568 | 900 | ANUK0HdVlI2Jd5hSzs0f | Milestone | 0 | 1.9.9.15.1 | 1.9.9.15.1 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
569 | 901 | HcFqHITfVdYMyzVb3S8v | Normal | 18 | 1.9.9.15.2 | 1.9.9.15.2 |  | 2026-04-20 08:00 | p | 935 |  | 2028-11-10 11:17
570 | 902 | nIjAIVHCOoi1ijXym0cI | Normal | 3 | 1.9.9.15.3 | 1.9.9.15.3 |  | 2026-04-20 08:00 | p | 935 |  | 2028-11-10 11:17
571 | 903 | UDGopgZ2sb1QsQEooZ9G | Normal | 8 | 1.9.9.15.4 | 1.9.9.15.4 |  | 2026-04-23 08:00 | p | 937 |  | 2028-11-15 11:13
572 | 904 | 4CH3NSJx1luiHbrrAEJg | Normal | 2 | 1.9.9.15.5 | 1.9.9.15.5 |  | 2026-05-14 08:00 | p | 939 |  | 2028-12-08 16:02
573 | 905 | MxRWNVEH6ZVBPqNnA2hI | Normal | 8 | 1.9.9.15.6 | 1.9.9.15.6 |  | 2026-05-05 08:00 | p | 934 |  | 2028-11-24 11:14
574 | 906 | PL0zn2U2NPPXQqakkHLb | Normal | 5 | 1.9.9.15.7 | 1.9.9.15.7 |  | 2026-05-15 08:00 | p | 934 |  | 2028-12-04 09:48
575 | 907 | 5mTVpVcHzmsYLVY8xpKs | Normal | 5 | 1.9.9.15.8 | 1.9.9.15.8 |  | 2026-05-15 08:00 | p | 934 |  | 2028-12-04 09:48
576 | 914 | q0UeyWaeMXFoeUDjjzhX | Summary | 18 | 1.9.9.5 | 1.9.9.5 |  | 2025-08-12 08:00 | p | 937 |  | 2028-03-06 16:52
577 | 915 | jxzEE3EBeGWt1nE3uHcj | Summary | 18 | 1.9.9.5.1 | 1.9.9.5.1 |  | 2025-08-12 08:00 | p | 937 |  | 2028-03-06 16:52
578 | 916 | d4bxhxtQW3GaLrDrUlf9 | Normal | 17 | 1.9.9.5.1.1 | 1.9.9.5.1.1 |  | 2025-08-12 08:00 | p | 937 |  | 2028-03-06 16:52
579 | 917 | mbDdHZHm9OoYye329Ue6 | Normal | 1 | 1.9.9.5.1.2 | 1.9.9.5.1.2 |  | 2025-09-05 08:00 | p | 941 |  | 2028-04-03 11:32
580 | 4538 | aTyUglf0WPX6H8Zd17Iq | Summary | 71 | 1.9.9.16 | 1.9.9.16 |  | 2026-04-20 13:00 | p | 935 |  | 2028-11-10 15:58
581 | 6509 | sp3XFaPtGgzrVeC1wvvV | Normal | 10 | 1.9.9.16.3 | 1.9.9.16.3 |  | 2026-05-26 13:00 | p | 931 |  | 2028-12-12 15:12
582 | 6510 | dar9hgzhSUYJxC1MeoTS | Normal | 10 | 1.9.9.16.4 | 1.9.9.16.4 |  | 2026-05-26 13:00 | p | 931 |  | 2028-12-12 13:13
583 | 6513 | IG8fHoH3vjERJ6iSB3Rj | Normal | 36 | 1.9.9.16.5 | 1.9.9.16.5 |  | 2026-06-09 13:00 | p | 933 |  | 2028-12-28 15:13
584 | 6514 | imV319lPgBwI8oLVT5sB | Normal | 1 | 1.9.9.16.2 | 1.9.9.16.2 |  | 2026-05-22 13:00 | p | 934 |  | 2028-12-11 13:54
585 | 6515 | a8Kdm3F6uLeIN4SEhwX9 | Normal | 1 | 1.9.9.16.1 | 1.9.9.16.1 |  | 2026-04-20 13:00 | p | 935 |  | 2028-11-10 15:58
586 | 5783 | BOvEGIzyTacp1vvD9v7M | Normal | 1 | 1.9.9.2 | 1.9.9.2 |  | 2026-01-02 08:00 | p | 26 |  | 2026-01-28 08:39
587 | 6685 | 2nkdQcaVv7LgM8d4dFld | Summary | 1 | 1.9.9.12 | 1.9.9.12 |  | 2025-08-29 08:00 | q | -164 |  | 2025-03-17 11:08
588 | 6687 | RiyOBd4mBIE5Cq6C0A4h | Normal | 1 | 1.9.9.12.1 | 1.9.9.12.1 |  | 2025-08-29 08:00 | q | -164 |  | 2025-03-17 11:08
589 | 7388 | subTjNOw9tjXphx2xXzW | Summary | 324 | 1.9.9.13 | 1.9.9.13 |  | 2025-06-18 08:00 | p | 933 |  | 2028-01-07 16:28
590 | 7389 | xTfJP5JFEqXIDmLDdKVZ | Summary | 43 | 1.9.9.13.1 | 1.9.9.13.1 |  | 2025-06-18 08:00 | p | 933 |  | 2028-01-07 16:28
591 | 7390 | GV26YG775A5KHHrrMIRV | Summary | 32 | 1.9.9.13.1.1 | 1.9.9.13.1.1 |  | 2025-06-18 08:00 | p | 933 |  | 2028-01-07 16:28
592 | 7391 | UumEMUqxjwvZXtHBx1rg | Normal | 3 | 1.9.9.13.1.1.1 | 1.9.9.13.1.1.1 |  | 2025-06-18 08:00 | p | 933 |  | 2028-01-07 16:28
593 | 7392 | ylVP19AJuwY485wgDJEG | Normal | 10 | 1.9.9.13.1.1.2 | 1.9.9.13.1.1.2 |  | 2025-06-24 08:00 | p | 933 |  | 2028-01-13 14:31
594 | 7393 | RzIyrLZKRoqlWdOJYpGf | Normal | 3 | 1.9.9.13.1.1.3 | 1.9.9.13.1.1.3 |  | 2025-07-03 08:00 | p | 935 |  | 2028-01-24 08:24
595 | 7394 | zHoRZ9fggWfe9FGnA954 | Normal | 10 | 1.9.9.13.1.1.4 | 1.9.9.13.1.1.4 |  | 2025-07-09 08:00 | p | 939 |  | 2028-02-03 15:25
596 | 7395 | PMjQe1vYJ6mxUbNABucF | Normal | 3 | 1.9.9.13.1.1.5 | 1.9.9.13.1.1.5 |  | 2025-07-18 08:00 | p | 934 |  | 2028-02-07 14:23
597 | 7396 | gQKdIVV4LZyvHUAfFFFg | Normal | 10 | 1.9.9.13.1.1.6 | 1.9.9.13.1.1.6 |  | 2025-07-23 08:00 | p | 940 |  | 2028-02-18 16:01
598 | 7397 | gmOEJCOmO6SQ6HMlGXfq | Summary | 12 | 1.9.9.13.1.2 | 1.9.9.13.1.2 |  | 2025-08-04 08:00 | p | 931 |  | 2028-02-21 11:14
599 | 7398 | ItOQSxoXEYWD5clVNK0n | Normal | 3 | 1.9.9.13.1.2.1 | 1.9.9.13.1.2.1 |  | 2025-08-04 08:00 | p | 931 |  | 2028-02-21 11:14
600 | 7399 | cXpFrNuZR7O8wPV6KZK3 | Normal | 9 | 1.9.9.13.1.2.2 | 1.9.9.13.1.2.2 |  | 2025-08-07 08:00 | p | 942 |  | 2028-03-06 16:52
601 | 7400 | VGtguPWpaIPmF0Ojsz8a | Summary | 176 | 1.9.9.13.2 | 1.9.9.13.2 |  | 2025-08-05 13:00 | p | 940 |  | 2028-03-03 08:58
602 | 7401 | H3MyBOTVJ4MGxcXcavMD | Normal | 2 | 1.9.9.13.2.1 | 1.9.9.13.2.1 |  | 2025-08-05 13:00 | p | 940 |  | 2028-03-03 08:58
603 | 7402 | pMiEhGou1QDK96DPu7Q8 | Normal | 1 | 1.9.9.13.2.2 | 1.9.9.13.2.2 |  | 2025-08-20 08:00 | p | 943 |  | 2028-03-20 09:05
604 | 7403 | pHZBXvaYVwug2p7gN6jp | Summary | 17 | 1.9.9.13.2.3 | 1.9.9.13.2.3 |  | 2025-08-21 08:00 | p | 943 |  | 2028-03-21 09:16
605 | 7404 | EvHLT3cR3tYYGwcq6SC1 | Normal | 5 | 1.9.9.13.2.3.1 | 1.9.9.13.2.3.1 |  | 2025-08-21 08:00 | p | 943 |  | 2028-03-21 09:16
606 | 7405 | 5GpI6xkgfIoVOnU9egD8 | Normal | 12 | 1.9.9.13.2.3.2 | 1.9.9.13.2.3.2 |  | 2025-08-28 08:00 | p | 943 |  | 2028-03-28 09:50
607 | 7406 | WxzG2sAIbVYYiem4v3mk | Normal | 12 | 1.9.9.13.2.3.3 | 1.9.9.13.2.3.3 |  | 2025-08-28 08:00 | p | 943 |  | 2028-03-28 09:50
608 | 7407 | 0eiyRK1I5mgUCdtpXpqY | Summary | 44 | 1.9.9.13.2.4 | 1.9.9.13.2.4 |  | 2025-09-16 08:00 | p | 939 |  | 2028-04-12 13:04
609 | 7408 | uKngouP2QMMQmu6HFm0I | Normal | 11 | 1.9.9.13.2.4.1 | 1.9.9.13.2.4.1 |  | 2025-09-16 08:00 | p | 939 |  | 2028-04-12 13:04
610 | 7409 | C7eZzAQkBbKewE4wmmOD | Normal | 11 | 1.9.9.13.2.4.2 | 1.9.9.13.2.4.2 |  | 2025-10-01 08:00 | p | 938 |  | 2028-04-26 11:31
611 | 7410 | VCdEPtbQjRcgNUnNprkZ | Normal | 11 | 1.9.9.13.2.4.3 | 1.9.9.13.2.4.3 |  | 2025-10-17 08:00 | p | 936 |  | 2028-05-10 14:48
612 | 7411 | OzHccTXr25Mf4pmiIMuT | Normal | 11 | 1.9.9.13.2.4.4 | 1.9.9.13.2.4.4 |  | 2025-11-03 08:00 | p | 934 |  | 2028-05-25 13:17
613 | 7412 | obz02flxb00pYjKUpMNx | Normal | 12 | 1.9.9.13.2.5 | 1.9.9.13.2.5 |  | 2025-11-26 08:00 | p | 930 |  | 2028-06-13 08:48
614 | 7413 | xazO1XwNp5eROWJmaREL | Summary | 36 | 1.9.9.13.2.6 | 1.9.9.13.2.6 |  | 2025-11-19 08:00 | p | 937 |  | 2028-06-13 08:48
615 | 7414 | DrM34eAIT9imz4vRHbHm | Normal | 2 | 1.9.9.13.2.6.1 | 1.9.9.13.2.6.1 |  | 2025-11-19 08:00 | p | 937 |  | 2028-06-13 08:48
616 | 7415 | RsULMViXRZoYahxlMUQ4 | Normal | 20 | 1.9.9.13.2.6.2 | 1.9.9.13.2.6.2 |  | 2025-11-21 08:00 | p | 937 |  | 2028-06-15 09:53
617 | 7416 | U8irVJqpjJwQWU5FcpMo | Normal | 3 | 1.9.9.13.2.6.3 | 1.9.9.13.2.6.3 |  | 2025-12-22 08:00 | p | 940 |  | 2028-07-19 11:22
618 | 7417 | yrCdbpyUp4mqkbXiv5Nc | Normal | 6 | 1.9.9.13.2.6.4 | 1.9.9.13.2.6.4 |  | 2025-12-26 08:00 | p | 941 |  | 2028-07-24 15:52
619 | 7418 | Iw5sTi596kP8d52cBWYm | Normal | 5 | 1.9.9.13.2.6.5 | 1.9.9.13.2.6.5 |  | 2026-01-06 08:00 | p | 938 |  | 2028-08-01 09:30
620 | 7419 | s9reBpLseCBnslseiKA6 | Normal | 2 | 1.9.9.13.2.7 | 1.9.9.13.2.7 |  | 2026-01-13 08:00 | p | 938 |  | 2028-08-08 14:51
621 | 7420 | ia01m1zWF4qAvVLVg5It | Summary | 54 | 1.9.9.13.2.8 | 1.9.9.13.2.8 |  | 2026-01-15 08:00 | p | 939 |  | 2028-08-11 09:38
622 | 7421 | 5PvQN5TGe8y7KbK2rRhO | Normal | 8 | 1.9.9.13.2.8.1 | 1.9.9.13.2.8.1 |  | 2026-01-15 08:00 | p | 939 |  | 2028-08-11 09:38
623 | 7422 | fj19MvsSAfWHeVGXiA1H | Normal | 5 | 1.9.9.13.2.8.2 | 1.9.9.13.2.8.2 |  | 2026-01-15 08:00 | p | 939 |  | 2028-08-11 09:38
624 | 7423 | hs9Gt4WgG9pENnEIaC7X | Normal | 14 | 1.9.9.13.2.8.3 | 1.9.9.13.2.8.3 |  | 2026-01-28 08:00 | p | 938 |  | 2028-08-23 13:49
625 | 7424 | WqCakGr8mHgCENNWHHjW | Normal | 5 | 1.9.9.13.2.8.4 | 1.9.9.13.2.8.4 |  | 2026-01-28 08:00 | p | 938 |  | 2028-08-23 13:49
626 | 7425 | Pv27HXd826jlfuUJmTLH | Normal | 20 | 1.9.9.13.2.8.5 | 1.9.9.13.2.8.5 |  | 2026-02-18 08:00 | p | 938 |  | 2028-09-13 10:12
627 | 7426 | UjcYgNHyPV73fWy2GGNA | Normal | 5 | 1.9.9.13.2.8.6 | 1.9.9.13.2.8.6 |  | 2026-02-18 08:00 | p | 938 |  | 2028-09-13 10:12
628 | 7427 | 5QMAV8W19uO0knxuRgYc | Normal | 6 | 1.9.9.13.2.8.7 | 1.9.9.13.2.8.7 |  | 2026-03-18 08:00 | p | 936 |  | 2028-10-09 10:02
629 | 7428 | C3roUkJ3GEdxAvfnxnUE | Normal | 6 | 1.9.9.13.2.8.8 | 1.9.9.13.2.8.8 |  | 2026-03-18 08:00 | p | 936 |  | 2028-10-09 10:02
630 | 7429 | GMfJSktlv5oUXA5LFNgA | Normal | 6 | 1.9.9.13.2.8.9 | 1.9.9.13.2.8.9 |  | 2026-03-26 08:00 | p | 937 |  | 2028-10-18 08:20
631 | 7430 | AjX0fOJfuCWTWcoFWrZe | Summary | 11 | 1.9.9.13.2.9 | 1.9.9.13.2.9 |  | 2026-04-03 08:00 | p | 935 |  | 2028-10-24 13:16
632 | 7431 | YKkcKAxBNBkRs3Gs0cxp | Normal | 7 | 1.9.9.13.2.9.1 | 1.9.9.13.2.9.1 |  | 2026-04-03 08:00 | p | 935 |  | 2028-10-24 13:16
633 | 7432 | HbmHLQTrqR87hE03VIdq | Normal | 3 | 1.9.9.13.2.9.2 | 1.9.9.13.2.9.2 |  | 2026-04-03 08:00 | p | 935 |  | 2028-10-24 13:16
634 | 7433 | FxBsJSw4ZNEIyIQA8bL9 | Normal | 8 | 1.9.9.13.2.9.3 | 1.9.9.13.2.9.3 |  | 2026-04-08 08:00 | p | 933 |  | 2028-10-27 11:33
635 | 7434 | MkjgnYEnwrIrITdXMEl9 | Milestone | 0 | 1.9.9.13.3 | 1.9.9.13.3 |  | 2026-07-31 12:00 | p | 929 |  | 2029-02-14 13:47
636 | 7435 | nSo6tYchIu2Aw4YtE45u | Summary | 44 | 1.9.9.13.4 | 1.9.9.13.4 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
637 | 7436 | Y83lvWkQwfsc3dMGwfVN | Summary | 30 | 1.9.9.13.4.1 | 1.9.9.13.4.1 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
638 | 7437 | E8EwVgjFQaEPGP66WsCb | Summary | 30 | 1.9.9.13.4.1.1 | 1.9.9.13.4.1.1 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
639 | 7438 | y2P0mgWq1uFkM4aVxtQJ | Normal | 15 | 1.9.9.13.4.1.1.1 | 1.9.9.13.4.1.1.1 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
640 | 7439 | nsJKxwZOWJc3LdYsNOwr | Normal | 5 | 1.9.9.13.4.1.1.2 | 1.9.9.13.4.1.1.2 |  | 2026-08-21 13:00 | p | 926 |  | 2029-03-05 08:26
641 | 7440 | 3ZzL4TktDwncii0hY2dA | Normal | 10 | 1.9.9.13.4.1.1.3 | 1.9.9.13.4.1.1.3 |  | 2026-08-28 13:00 | p | 924 |  | 2029-03-09 14:27
642 | 7441 | IcgrxiRjEYJLwuugm8N7 | Summary | 30 | 1.9.9.13.4.1.2 | 1.9.9.13.4.1.2 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
643 | 7442 | B8zfbswYxyRxHa21jaE6 | Normal | 15 | 1.9.9.13.4.1.2.1 | 1.9.9.13.4.1.2.1 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
644 | 7443 | lvFKaF8Jtq8DkkB0s9nv | Normal | 15 | 1.9.9.13.4.1.2.2 | 1.9.9.13.4.1.2.2 |  | 2026-08-21 13:00 | p | 929 |  | 2029-03-08 09:14
645 | 7444 | 419IszMaZW6XNIQptprk | Normal | 20 | 1.9.9.13.4.1.3 | 1.9.9.13.4.1.3 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
646 | 7445 | oNfFp4VAwKEpoSujTbHZ | Normal | 10 | 1.9.9.13.4.1.4 | 1.9.9.13.4.1.4 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
647 | 7446 | NnBZUSVumxDXwVdCLN8g | Summary | 12 | 1.9.9.13.4.2 | 1.9.9.13.4.2 |  | 2026-09-14 13:00 | p | 928 |  | 2029-03-30 14:22
648 | 7447 | CAsJ3atkVCS14hehUB9Y | Normal | 4 | 1.9.9.13.4.2.1 | 1.9.9.13.4.2.1 |  | 2026-09-14 13:00 | p | 928 |  | 2029-03-30 14:22
649 | 7448 | 8tMCh2h8AwE53TPPkfEv | Normal | 3 | 1.9.9.13.4.2.2 | 1.9.9.13.4.2.2 |  | 2026-09-16 13:00 | p | 929 |  | 2029-04-03 11:47
650 | 7449 | LaZxXVdUnGzqswRGUiV5 | Normal | 7 | 1.9.9.13.4.2.3 | 1.9.9.13.4.2.3 |  | 2026-09-21 13:00 | p | 928 |  | 2029-04-06 13:07
651 | 7450 | F3vtt1T8lz7mQWFPgUKT | Normal | 2 | 1.9.9.13.4.3 | 1.9.9.13.4.3 |  | 2026-09-30 13:00 | p | 930 |  | 2029-04-17 15:30
652 | 7451 | nShmtMdGhMi3SzNeAZjW | Milestone | 0 | 1.9.9.13.4.4 | 1.9.9.13.4.4 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
653 | 7510 | 4i5VLTIa98HteWhFzYjv | Normal | 3 | 1.7.10.24 | 1.7.10.24 |  | 2025-06-13 08:00 | p | 936 |  | 2028-01-05 08:46
654 | 7511 | tHPdmsBqm9kHM69dtq3h | Normal | 7 | 1.7.10.25 | 1.7.10.25 |  | 2025-06-24 08:00 | p | 933 |  | 2028-01-13 08:07
655 | 7512 | hmOTDv9qQbSDcHudIm9x | Normal | 7 | 1.7.10.26 | 1.7.10.26 |  | 2025-07-09 08:00 | p | 932 |  | 2028-01-27 11:46
656 | 7513 | NbiRgc4Tdvxa900kw7Xq | Normal | 8 | 1.7.10.27 | 1.7.10.27 |  | 2025-07-23 08:00 | p | 932 |  | 2028-02-10 13:38
657 | 7539 | ROucR7pug9aGzObG8pvW | Normal | 1 | 1.7.10.8 | 1.7.10.8 |  | 2025-02-28 08:00 | q | -571 |  | 2023-08-07 08:00
658 | 7540 | njszlznNRnCyRW2hgoMI | Normal | 10 | 1.7.10.9 | 1.7.10.9 |  | 2025-03-03 08:00 | q | -572 |  | 2023-08-08 08:37
659 | 7541 | R63tw5xkvmDGiWpIPQRa | Normal | 1 | 1.7.10.10 | 1.7.10.10 |  | 2025-03-31 08:00 | q | -602 |  | 2023-08-07 08:00
660 | 7542 | E3YdLEfamF0eZCISJiqw | Normal | 10 | 1.7.10.11 | 1.7.10.11 |  | 2025-04-14 08:00 | q | -616 |  | 2023-08-07 08:00
661 | 7543 | nhpJxewK7uClQLzGXJQJ | Normal | 1 | 1.7.10.12 | 1.7.10.12 |  | 2025-05-30 08:00 | q | -662 |  | 2023-08-07 08:00
662 | 7544 | cfuUTFyz3WOPAOOiNQOb | Normal | 1 | 1.7.10.13 | 1.7.10.13 |  | 2025-05-30 08:00 | q | -662 |  | 2023-08-07 08:00
663 | 6279 | p7EJXT1muDSglD2OZLFH | Summary | 274 | 1.9.7 | 1.9.7 |  | 2022-03-07 08:00 | q | -1734 |  | 2017-06-07 08:00
664 | 1484 | 6ARiGRg3KLswRpJLOmGD | Summary | 229 | 1.9.7.18 | 1.9.7.18 |  | 2023-10-24 08:00 | q | -2330 |  | 2017-06-07 08:00
665 | 1485 | R0QJsNVi0JzXq4FadBdS | Normal | 20 | 1.9.7.18.4 | 1.9.7.18.4 |  | 2025-06-18 08:00 | q | -2819 |  | 2017-09-28 08:18
666 | 1486 | 9VYbXOz4xuMas0igEBkB | Summary | 56 | 1.9.7.18.6 | 1.9.7.18.6 |  | 2025-08-15 08:00 | q | -2810 |  | 2017-12-04 08:30
667 | 6540 | BF294XdCZHw2CEg81bOs | Normal | 19 | 1.9.7.18.6.1 | 1.9.7.18.6.1 |  | 2025-08-15 08:00 | q | -2810 |  | 2017-12-04 08:30
668 | 6541 | X8phwYugZBkIbn0OysQW | Normal | 19 | 1.9.7.18.6.2 | 1.9.7.18.6.2 |  | 2025-09-12 08:00 | q | -2814 |  | 2017-12-28 16:20
669 | 6542 | fphO3nZhiS43G9CLfKfB | Normal | 18 | 1.9.7.18.6.3 | 1.9.7.18.6.3 |  | 2025-10-09 08:00 | q | -2809 |  | 2018-01-29 14:01
670 | 1490 | hF9FI1LNvFfgTTXhqPsR | Normal | 77 | 1.9.7.18.2 | 1.9.7.18.2 |  | 2025-02-27 08:00 | q | -2822 |  | 2017-06-07 08:00
671 | 1491 | XpTPefWn9TT3C06gw8rA | Normal | 1 | 1.9.7.18.3 | 1.9.7.18.3 |  | 2025-06-17 08:00 | q | -2820 |  | 2017-09-26 16:07
672 | 1495 | 0kid3Dd3U5gCQNrt2pwY | Normal | 1 | 1.9.7.18.8 | 1.9.7.18.8 |  | 2025-02-26 08:00 | q | -23 |  | 2025-02-03 08:00
673 | 1504 | ndaml8HRsqEWzWIKrI7h | Normal | 5 | 1.9.7.18.10 | 1.9.7.18.10 |  | 2025-02-26 08:00 | q | -23 |  | 2025-02-03 08:00
674 | 4587 | 5uS9ktvplxYkrLheR3Q9 | Normal | 20 | 1.9.7.18.5 | 1.9.7.18.5 |  | 2025-07-18 08:00 | q | -2820 |  | 2017-10-27 15:51
675 | 1496 | 5t2MhilpkZRDQA3VTcGS | Normal | 48 | 1.9.7.7 | 1.9.7.7 |  | 2025-02-27 08:00 | q | -22 |  | 2025-02-04 08:47
676 | 1505 | 4c3z8pWafVxAWNC1MpC9 | Normal | 106 | 1.9.7.8 | 1.9.7.8 |  | 2025-03-05 08:00 | q | -22 |  | 2025-02-10 11:29
677 | 1531 | KX1eD2ASIZaZBZuqoVp4 | Normal | 1 | 1.9.7.14.2 | 1.9.7.14.2 |  | 2025-05-01 08:00 | q | -192 |  | 2024-10-21 08:00
678 | 1532 | fQ3wcWF8uEWMRGpUCxEA | Normal | 1 | 1.9.7.14.4 | 1.9.7.14.4 |  | 2025-05-07 08:00 | q | -18 |  | 2025-04-18 16:03
679 | 1533 | juvdtwZkjArAkPOzLrhN | Normal | 15 | 1.9.7.14.5 | 1.9.7.14.5 |  | 2025-06-10 08:00 | p | 13 |  | 2025-06-23 16:18
680 | 1534 | SuchbNnj1ndABAEPQlrb | Normal | 10 | 1.9.7.14.6 | 1.9.7.14.6 |  | 2025-07-02 08:00 | p | 14 |  | 2025-07-16 10:48
681 | 4583 | QzcCl72pVAI4zSVR8VAE | Normal | 1 | 1.9.7.14.3 | 1.9.7.14.3 |  | 2025-05-02 08:00 | q | -191 |  | 2024-10-22 08:07
682 | 1538 | 1Xm6i4dPIyAKJzF1jRtD | Normal | 45 | 1.9.7.15.3 | 1.9.7.15.3 |  | 2025-02-18 08:00 | p | 27 |  | 2025-03-17 16:37
683 | 1541 | ss8yD9dhZfTIp9UxqHnG | Normal | 1 | 1.9.7.15.7 | 1.9.7.15.7 |  | 2025-04-22 08:00 | p | 29 |  | 2025-05-21 11:41
684 | 1542 | VmFPpoMfVfLEXeRBF7Um | Normal | 9 | 1.9.7.15.8 | 1.9.7.15.8 |  | 2025-04-23 08:00 | p | 29 |  | 2025-05-22 10:13
685 | 1543 | P2oxmSB7jXG6Ib9VEZ89 | Normal | 9 | 1.9.7.15.9 | 1.9.7.15.9 |  | 2025-05-06 08:00 | p | 29 |  | 2025-06-04 09:43
686 | 1547 | K0gsOWDMqaySswr72BAQ | Normal | 1 | 1.9.7.16.3 | 1.9.7.16.3 |  | 2025-02-21 08:00 | q | -361 |  | 2024-02-26 08:00
687 | 1548 | 4jCrHn72KCapTPEI9TzQ | Normal | 2 | 1.9.7.16.5 | 1.9.7.16.5 |  | 2025-02-25 08:00 | q | -362 |  | 2024-02-28 08:10
688 | 1549 | s8gTUDwRZFDpCO4enZqk | Normal | 15 | 1.9.7.16.6 | 1.9.7.16.6 |  | 2025-02-27 08:00 | q | -362 |  | 2024-03-01 08:50
689 | 1550 | UoQFPyMNVa9QPyq2kgrl | Normal | 9 | 1.9.7.16.7 | 1.9.7.16.7 |  | 2025-03-20 08:00 | q | -5 |  | 2025-03-14 09:48
690 | 4586 | kRWFuIGKur6ToFmAr9JC | Normal | 1 | 1.9.7.16.4 | 1.9.7.16.4 |  | 2025-02-24 08:00 | q | -362 |  | 2024-02-27 08:41
691 | 1562 | lBuCdKTmKHrCdvS4FVbB | Normal | 40 | 1.9.7.19.12 | 1.9.7.19.12 |  | 2025-02-26 08:00 | p | 1 |  | 2025-02-27 13:07
692 | 1563 | TUxQ6kz9ittb2zcmlLCL | Normal | 10 | 1.9.7.19.13 | 1.9.7.19.13 |  | 2025-04-23 08:00 | p | 1 |  | 2025-04-24 15:44
693 | 1564 | OkMyUpJo7fqJaif9Jvyb | Normal | 5 | 1.9.7.19.14 | 1.9.7.19.14 |  | 2025-05-07 08:00 | p | 1 |  | 2025-05-08 11:23
694 | 1565 | 9BGxipQLCi4kED7E7faW | Normal | 4 | 1.9.7.19.15 | 1.9.7.19.15 |  | 2025-05-14 08:00 | p | 1 |  | 2025-05-15 09:42
695 | 4572 | 5hxJeLGqqaIlIue4XwRC | Normal | 1 | 1.9.7.2 | 1.9.7.2 |  | 2025-03-21 08:00 | p | 27 |  | 2025-04-17 16:18
696 | 1497 | q56IdotBOPeXlK3605d6 | Normal | 1 | 1.9.7.11.4 | 1.9.7.11.4 |  | 2025-05-06 08:00 | q | -20 |  | 2025-04-15 16:33
697 | 1506 | zNKWNUMZ7wFR6LBQ8bZ2 | Normal | 1 | 1.9.7.11.5 | 1.9.7.11.5 |  | 2025-08-05 08:00 | q | -27 |  | 2025-07-08 16:49
698 | 1509 | xdWSZU8MxGE52WBHNu6X | Normal | 1 | 1.9.7.11.3 | 1.9.7.11.3 |  | 2025-03-25 08:00 | p | 23 |  | 2025-04-17 10:54
699 | 6440 | u5F2XJPKXxmZ5m99Yx5A | Normal | 1 | 1.9.7.11.7 | 1.9.7.11.7 |  | 2025-04-30 08:00 | q | -5 |  | 2025-04-24 11:28
700 | 4575 | nPe6rBdPLk408ntp39jn | Normal | 1 | 1.9.7.3 | 1.9.7.3 |  | 2025-06-06 08:00 | q | -669 |  | 2023-08-07 08:00
701 | 4578 | kBeLaux8MTugqoi5KPvZ | Summary | 74 | 1.9.7.13 | 1.9.7.13 |  | 2025-04-02 08:00 | q | -6 |  | 2025-03-26 11:36
702 | 1462 | 2Cc6AJ3gtv1XGHwG4F9W | Normal | 1 | 1.9.7.13.3 | 1.9.7.13.3 |  | 2025-04-07 08:00 | p | 24 |  | 2025-05-01 16:08
703 | 1518 | qXbL36bdYftxHm1TCntK | Normal | 1 | 1.9.7.13.4 | 1.9.7.13.4 |  | 2025-07-17 08:00 | p | 13 |  | 2025-07-30 16:47
704 | 4579 | xoTCeJS6YwjvMvm1YAvH | Normal | 1 | 1.9.7.13.2 | 1.9.7.13.2 |  | 2025-05-19 08:00 | p | 32 |  | 2025-06-20 10:23
705 | 4580 | llDwDvQQbSyeeXMs3M2a | Normal | 1 | 1.9.7.13.1 | 1.9.7.13.1 |  | 2025-04-02 08:00 | q | -6 |  | 2025-03-26 11:36
706 | 4588 | L1kgBhMEjlIJ4HNHh1TQ | Summary | 141 | 1.9.7.20 | 1.9.7.20 |  | 2025-05-20 08:00 | p | 1 |  | 2025-05-21 11:08
707 | 1566 | KFj0hxHWvExDoqTqgDeg | Normal | 118 | 1.9.7.20.1 | 1.9.7.20.1 |  | 2025-05-20 08:00 | p | 1 |  | 2025-05-21 11:08
708 | 1567 | GV5or0ucuouXZiqAkH0N | Normal | 10 | 1.9.7.20.2 | 1.9.7.20.2 |  | 2025-11-07 08:00 | q | 0 |  | 2025-11-06 08:08
709 | 1568 | JI4xSRBKV4FYnRXdw7Wz | Normal | 9 | 1.9.7.20.3 | 1.9.7.20.3 |  | 2025-11-24 08:00 | p | 0 |  | 2025-11-24 13:31
710 | 1569 | DVuFJt4FGQSIgeZkA41d | Normal | 4 | 1.9.7.20.4 | 1.9.7.20.4 |  | 2025-12-08 08:00 | q | -2 |  | 2025-12-05 10:32
711 | 4590 | 21lrGsmJiPqRYOd4yY3H | Summary | 2 | 1.9.7.21 | 1.9.7.21 |  | 2026-09-14 13:00 | p | 928 |  | 2029-03-30 14:22
712 | 1570 | 9hmrS48cr19KgrseY4yN | Normal | 2 | 1.9.7.21.1 | 1.9.7.21.1 |  | 2026-09-14 13:00 | p | 928 |  | 2029-03-30 14:22
713 | 7455 | hQlezwT73UjuGPZkyuVr | Normal | 9 | 1.7.8.18.2 | 1.7.8.18.2 |  | 2025-02-18 08:00 | p | 28 |  | 2025-03-18 09:56
714 | 7456 | 3cfjdZ38xGBNf8roD7He | Normal | 9 | 1.7.8.18.3 | 1.7.8.18.3 |  | 2025-03-03 08:00 | p | 25 |  | 2025-03-28 10:02
715 | 7457 | abNwDWOnFoe0xwhiRueS | Normal | 1 | 1.7.8.18.4 | 1.7.8.18.4 |  | 2025-03-19 08:00 | p | 21 |  | 2025-04-09 14:59
716 | 7458 | cMhUMuxC0sax27543As7 | Normal | 24 | 1.7.8.18.5 | 1.7.8.18.5 |  | 2025-04-07 08:00 | p | 3 |  | 2025-04-10 14:30
717 | 7459 | xf7OMyoiQ38QdcweBYiq | Normal | 20 | 1.7.8.18.6 | 1.7.8.18.6 |  | 2025-05-09 08:00 | p | 7 |  | 2025-05-16 10:07
718 | 7324 | GVXYroUMjcAFUHa4B19H | Normal | 1 | 1.7.8.19 | 1.7.8.19 |  | 2025-03-28 08:00 | q | -555 |  | 2023-09-20 08:00
719 | 7325 | wl82vK5NXqnnsHIySTFp | Normal | 1 | 1.7.8.20 | 1.7.8.20 |  | 2025-06-09 08:00 | p | 11 |  | 2025-06-20 15:38
720 | 7382 | GJk3wpkfagyrb21gVciV | Summary | 288 | 1.9.7.22 | 1.9.7.22 |  | 2025-02-26 08:00 | q | -569 |  | 2023-08-07 08:00
721 | 7383 | chM988R4AoJxJINOHhOy | Normal | 1 | 1.9.7.22.1 | 1.9.7.22.1 |  | 2025-02-26 08:00 | q | -569 |  | 2023-08-07 08:00
722 | 7384 | xn1TRUhUfNd3ygHlAMk1 | Normal | 16 | 1.9.7.22.2 | 1.9.7.22.2 |  | 2025-02-27 08:00 | q | -569 |  | 2023-08-07 16:42
723 | 7385 | cYlWo9e2zkkP7jtt7iLZ | Normal | 1 | 1.9.7.22.3 | 1.9.7.22.3 |  | 2025-03-21 08:00 | q | -575 |  | 2023-08-23 16:37
724 | 7386 | F9n9tFj3S3xXbwXNgAjU | Normal | 5 | 1.9.7.22.4 | 1.9.7.22.4 |  | 2026-04-14 08:00 | p | 933 |  | 2028-11-02 14:33
725 | 4594 | EUFkYGsAZWO3vgZroOTA | Normal | 1 | 1.9.1.2 | 1.9.1.2 |  | 2025-07-02 08:00 | p | 19 |  | 2025-07-21 08:37
726 | 4595 | 0i30zTvKTrSo3R9n999e | Normal | 2 | 1.9.1.3 | 1.9.1.3 |  | 2025-07-03 08:00 | p | 19 |  | 2025-07-22 08:41
727 | 4606 | e1c7TqZJ2saEXqSPx9Ca | Normal | 1 | 1.7.3.3 | 1.7.3.3 |  | 2025-05-27 08:00 | p | 31 |  | 2025-06-27 15:19
728 | 4607 | 9Rf8xh1sYqA0mX8AIEgx | Summary | 52 | 1.7.3.5 | 1.7.3.5 |  | 2025-08-04 08:00 | p | 35 |  | 2025-09-08 13:07
729 | 4608 | tlJeJHdE7OwhwWyVvZ8P | Normal | 5 | 1.7.3.5.1 | 1.7.3.5.1 |  | 2025-08-04 08:00 | p | 35 |  | 2025-09-08 13:07
730 | 4609 | PoeQu0I6Io83IRbk7WtS | Normal | 5 | 1.7.3.5.2 | 1.7.3.5.2 |  | 2025-08-11 08:00 | p | 32 |  | 2025-09-12 13:59
731 | 4610 | UGUZlny6Ut8S0mLRTL2X | Normal | 1 | 1.7.3.5.3 | 1.7.3.5.3 |  | 2025-08-18 08:00 | p | 32 |  | 2025-09-19 14:20
732 | 4611 | 1TZOFiOcsBCmkfhi03Iw | Normal | 5 | 1.7.3.5.4 | 1.7.3.5.4 |  | 2025-08-26 08:00 | p | 34 |  | 2025-09-29 13:08
733 | 4612 | ZwEXlYv6PrV1t0gzfqom | Normal | 10 | 1.7.3.5.5 | 1.7.3.5.5 |  | 2025-09-03 08:00 | p | 33 |  | 2025-10-06 11:44
734 | 4613 | z0DGpsje53b33zXA5t1P | Normal | 20 | 1.7.3.5.6 | 1.7.3.5.6 |  | 2025-09-17 08:00 | p | 34 |  | 2025-10-21 10:58
735 | 4614 | cqs4HA7sR83mroZvcBiw | Normal | 1 | 1.7.3.5.7 | 1.7.3.5.7 |  | 2025-10-16 08:00 | p | 29 |  | 2025-11-14 09:46
736 | 4618 | mRqsjEijsp2iSp4l7aof | Normal | 5 | 1.7.3.4.3 | 1.7.3.4.3 |  | 2025-02-18 08:00 | p | 28 |  | 2025-03-18 11:06
737 | 4619 | 8asUr7UOO8nabPagFvw9 | Normal | 40 | 1.7.3.4.4 | 1.7.3.4.4 |  | 2025-02-18 08:00 | p | 28 |  | 2025-03-18 11:06
738 | 4620 | UWR5akRFo4eKiDyQVnYr | Normal | 23 | 1.7.3.4.5 | 1.7.3.4.5 |  | 2025-02-18 08:00 | p | 22 |  | 2025-03-12 11:53
739 | 4621 | pGB9dynKUfIMuzj3AWVv | Normal | 1 | 1.7.3.4.6 | 1.7.3.4.6 |  | 2025-05-28 08:00 | p | 33 |  | 2025-06-30 15:35
740 | 4622 | Bm2ajkWBwO6Cvc6RoPdK | Normal | 5 | 1.7.3.4.7 | 1.7.3.4.7 |  | 2025-05-29 08:00 | p | 33 |  | 2025-07-01 14:45
741 | 4623 | sDTQ4X48dvup817zb0Do | Normal | 20 | 1.7.3.4.8 | 1.7.3.4.8 |  | 2025-06-05 08:00 | p | 36 |  | 2025-07-11 16:20
742 | 4624 | 3CGv61AS00FFpM5LrRat | Normal | 20 | 1.7.3.4.9 | 1.7.3.4.9 |  | 2025-07-07 08:00 | p | 35 |  | 2025-08-11 16:17
743 | 4625 | NkJyZ342jkgJkVCalD4F | Normal | 2 | 1.7.3.4.10 | 1.7.3.4.10 |  | 2025-08-04 08:00 | p | 35 |  | 2025-09-08 13:07
744 | 4631 | EXJQS9o5Eq3lGkaYsCap | Normal | 1 | 1.7.3.6.5 | 1.7.3.6.5 |  | 2025-02-18 08:00 | p | 27 |  | 2025-03-17 08:01
745 | 4632 | VGp2Ji3lCAas2O4B01f5 | Normal | 1 | 1.7.3.6.6 | 1.7.3.6.6 |  | 2025-02-19 08:00 | p | 26 |  | 2025-03-17 16:23
746 | 4633 | STHfhyBuM5qFiEzHSgws | Normal | 19 | 1.7.3.6.7 | 1.7.3.6.7 |  | 2025-02-20 08:00 | p | 26 |  | 2025-03-18 16:09
747 | 4634 | cbBLoWE0dwfwOCS04ga7 | Normal | 15 | 1.7.3.6.8 | 1.7.3.6.8 |  | 2025-03-19 08:00 | p | 22 |  | 2025-04-10 09:43
748 | 4635 | vrd0V7BeylNxhzgI26F9 | Normal | 8 | 1.7.3.6.11 | 1.7.3.6.11 |  | 2025-04-10 08:00 | p | 22 |  | 2025-05-02 09:31
749 | 4636 | DgPDbwa39NNm3em6lmtZ | Normal | 1 | 1.7.3.6.12 | 1.7.3.6.12 |  | 2025-11-28 08:00 | p | 21 |  | 2025-12-19 09:31
750 | 4663 | X9pjxOrdX8ZwQAfQziSu | Normal | 1 | 1.7.3.6.9 | 1.7.3.6.9 |  | 2025-04-09 08:00 | p | 22 |  | 2025-05-01 09:46
751 | 4664 | DAxARpEpHAwipBCK81bc | Normal | 8 | 1.7.3.6.10 | 1.7.3.6.10 |  | 2025-04-10 08:00 | p | 22 |  | 2025-05-02 09:31
752 | 7259 | Dcjo2uskRMoBajU90pQq | Normal | 60 | 1.7.1.4 | 1.7.1.4 |  | 2025-03-03 08:00 | p | 29 |  | 2025-04-01 09:25
753 | 3777 | YuGKQIQDxLVYRZzgUQjw | Normal | 9 | 1.7.1.2.6.4 | 1.7.1.2.6.4 |  | 2025-03-27 08:00 | p | 29 |  | 2025-04-25 15:31
754 | 6138 | EvFVoaLHb5OgszmS4Hdy | Summary | 44 | 1.7.1.3.9 | 1.7.1.3.9 |  | 2025-04-01 08:00 | p | 28 |  | 2025-04-29 15:49
755 | 6139 | VECMPYMi2oWf71g3eai1 | Normal | 29 | 1.7.1.3.9.1 | 1.7.1.3.9.1 |  | 2025-04-01 08:00 | p | 28 |  | 2025-04-29 15:49
756 | 6140 | mO0F0FFUdRVKYlb84WcT | Normal | 15 | 1.7.1.3.9.2 | 1.7.1.3.9.2 |  | 2025-05-12 08:00 | p | 25 |  | 2025-06-06 16:23
757 | 6978 | z4sj2SQJw3pdZet8Am0U | Normal | 9 | 1.7.1.3.5 | 1.7.1.3.5 |  | 2025-03-10 08:00 | p | 22 |  | 2025-04-01 13:07
758 | 6985 | eGeEyEDP9xa0SwHKf7WR | Normal | 7 | 1.7.1.3.7.4 | 1.7.1.3.7.4 |  | 2025-03-03 08:00 | p | 29 |  | 2025-04-01 13:07
759 | 6986 | 31qYZ6wVIReV9ZOAqgem | Summary | 9 | 1.7.1.3.7.5 | 1.7.1.3.7.5 |  | 2025-03-12 08:00 | p | 29 |  | 2025-04-10 09:59
760 | 6987 | 50so1NYgvDTnEeNkdrjv | Normal | 3 | 1.7.1.3.7.5.1 | 1.7.1.3.7.5.1 |  | 2025-03-12 08:00 | p | 29 |  | 2025-04-10 09:59
761 | 6988 | bmsC3uFxKZ3RPA57Ivjb | Normal | 3 | 1.7.1.3.7.5.2 | 1.7.1.3.7.5.2 |  | 2025-03-17 08:00 | p | 28 |  | 2025-04-14 16:39
762 | 6989 | okOYULy0nclsZMYhl4sg | Normal | 3 | 1.7.1.3.7.5.3 | 1.7.1.3.7.5.3 |  | 2025-03-20 08:00 | p | 29 |  | 2025-04-18 11:00
763 | 7184 | gKjyagqR1BEsAZjZk4l5 | Milestone | 0 | 1.7.1.3.7.3 | 1.7.1.3.7.3 |  | 2025-02-28 08:00 | q | -29 |  | 2025-01-30 08:00
764 | 6990 | K8cvVDryBsyahUujiNmr | Summary | 22 | 1.7.1.3.8 | 1.7.1.3.8 |  | 2025-02-28 08:00 | q | -29 |  | 2025-01-30 08:00
765 | 6136 | bVRB0EhNo1xoyHBU8R0I | Normal | 1 | 1.7.1.3.8.2 | 1.7.1.3.8.2 |  | 2025-03-21 08:00 | p | 26 |  | 2025-04-16 09:22
766 | 6982 | E06yVWmTg8kRS6Gv9kOV | Summary | 6 | 1.7.1.3.8.3 | 1.7.1.3.8.3 |  | 2025-03-24 08:00 | p | 24 |  | 2025-04-17 09:11
767 | 6137 | gagQpjsDXV4QnJ1bUthb | Normal | 2 | 1.7.1.3.8.3.1 | 1.7.1.3.8.3.1 |  | 2025-03-24 08:00 | p | 24 |  | 2025-04-17 09:11
768 | 6979 | ZYA6dvbLVog9FL6DNJRb | Normal | 5 | 1.7.1.3.8.3.2 | 1.7.1.3.8.3.2 |  | 2025-03-25 08:00 | p | 29 |  | 2025-04-23 10:16
769 | 6991 | RAhO7UtYgqwLkhTknwrO | Normal | 6 | 1.7.1.3.8.1 | 1.7.1.3.8.1 |  | 2025-02-28 08:00 | q | -29 |  | 2025-01-30 08:00
770 | 3810 | CJxWy7PnZPcI4EPHEeme | Normal | 9 | 1.7.1.5.3.2 | 1.7.1.5.3.2 |  | 2025-03-04 08:00 | p | 28 |  | 2025-04-01 15:07
771 | 3811 | wGtgxCT3lCK6u2EOL8xN | Normal | 5 | 1.7.1.5.3.3 | 1.7.1.5.3.3 |  | 2025-03-17 08:00 | p | 24 |  | 2025-04-10 11:21
772 | 3813 | sYeTNUsya13QYMbMJg21 | Normal | 25 | 1.7.1.5.7 | 1.7.1.5.7 |  | 2025-02-28 08:00 | p | 28 |  | 2025-03-28 13:11
773 | 3814 | c3HTuVFoRVefrW72mxSE | Normal | 3 | 1.7.1.5.8 | 1.7.1.5.8 |  | 2025-04-08 08:00 | p | 52 |  | 2025-05-30 10:39
774 | 3815 | nJJAkVwt0aHLNZMMtbkw | Normal | 3 | 1.7.1.5.9 | 1.7.1.5.9 |  | 2025-04-04 08:00 | p | 31 |  | 2025-05-05 11:31
775 | 3816 | 6MWmVgC0FSCF3lMoTGjJ | Summary | 40 | 1.7.1.5.10 | 1.7.1.5.10 |  | 2025-04-09 08:00 | p | 29 |  | 2025-05-08 08:56
776 | 3817 | LqjKPVRVNU7j1iAlkL3t | Normal | 2 | 1.7.1.5.10.1 | 1.7.1.5.10.1 |  | 2025-04-09 08:00 | p | 29 |  | 2025-05-08 08:56
777 | 3818 | Cmm1EfLtBPedDjXV8dAv | Normal | 5 | 1.7.1.5.10.2 | 1.7.1.5.10.2 |  | 2025-04-11 08:00 | p | 31 |  | 2025-05-12 09:26
778 | 3819 | FSVjbKFfUmqE2fpbGGPv | Normal | 3 | 1.7.1.5.10.3 | 1.7.1.5.10.3 |  | 2025-04-18 08:00 | p | 31 |  | 2025-05-19 08:29
779 | 3820 | FhKtXXrOwkDfPm4RFzRW | Normal | 10 | 1.7.1.5.10.4 | 1.7.1.5.10.4 |  | 2025-04-23 08:00 | p | 42 |  | 2025-06-04 10:07
780 | 3821 | cHjYAw102skS4vR6DXqX | Normal | 20 | 1.7.1.5.10.5 | 1.7.1.5.10.5 |  | 2025-05-07 08:00 | p | 44 |  | 2025-06-20 10:34
781 | 4131 | 3WZTLr4e3INGux4LMgj0 | Summary | 146 | 1.9.6.10.2 | 1.9.6.10.2 |  | 2025-03-03 17:00 | p | 927 |  | 2027-09-17 14:49
782 | 5857 | g9TizAnooUcHoXglcd4n | Milestone | 0 | 1.9.6.10.2.1 | 1.9.6.10.2.1 |  | 2025-07-25 17:00 | p | 906 |  | 2028-01-18 08:48
783 | 5858 | 9N3N0HBhBeb82jbbU7Vx | Milestone | 0 | 1.9.6.10.2.2 | 1.9.6.10.2.2 |  | 2025-03-03 17:00 | p | 927 |  | 2027-09-17 14:49
784 | 5859 | RMhsXtyk4773BtipN2HO | Normal | 1 | 1.9.6.10.2.3 | 1.9.6.10.2.3 |  | 2025-03-04 08:00 | p | 927 |  | 2027-09-17 14:49
785 | 5860 | AMUT2hrMeOWSIoK5dO6S | Normal | 10 | 1.9.6.10.2.4 | 1.9.6.10.2.4 |  | 2025-05-05 08:00 | p | 868 |  | 2027-09-20 14:29
786 | 5861 | adMwYb1cwVT0ja23ZKPV | Normal | 10 | 1.9.6.10.2.5 | 1.9.6.10.2.5 |  | 2025-05-19 08:00 | p | 868 |  | 2027-10-04 10:58
787 | 5862 | rkVKH7eSVnkv5Rz0hIbo | Normal | 25 | 1.9.6.10.2.6 | 1.9.6.10.2.6 |  | 2025-06-03 08:00 | p | 864 |  | 2027-10-15 15:33
788 | 5863 | axx1H8vuWtNbWz6aJYpW | Normal | 20 | 1.9.6.10.2.7 | 1.9.6.10.2.7 |  | 2025-07-10 08:00 | p | 868 |  | 2027-11-25 10:07
789 | 5864 | ZuXAUp7kzm7PDgs0Clm4 | Normal | 20 | 1.9.6.10.2.8 | 1.9.6.10.2.8 |  | 2025-08-07 08:00 | p | 873 |  | 2027-12-28 09:23
790 | 5865 | pfx92tyIHO0nDV8Eg4vj | Normal | 3 | 1.9.6.10.2.9 | 1.9.6.10.2.9 |  | 2025-09-05 08:00 | p | 866 |  | 2028-01-19 16:30
791 | 5866 | qnFTkxNSvGIYOwHhqElS | Normal | 5 | 1.9.6.10.2.10 | 1.9.6.10.2.10 |  | 2025-09-10 08:00 | p | 866 |  | 2028-01-24 14:23
792 | 5867 | 6vMprMC9ZRYTg9c055cw | Normal | 3 | 1.9.6.10.2.11 | 1.9.6.10.2.11 |  | 2025-09-17 08:00 | p | 866 |  | 2028-01-31 13:50
793 | 5868 | qP5P60WlJm98gR28uFOw | Normal | 1 | 1.9.6.10.2.12 | 1.9.6.10.2.12 |  | 2025-09-22 08:00 | p | 863 |  | 2028-02-02 13:03
794 | 5869 | 5FBVtcv48JlyNzpes7ps | Normal | 5 | 1.9.6.10.2.13 | 1.9.6.10.2.13 |  | 2025-09-23 08:00 | p | 863 |  | 2028-02-03 11:32
795 | 5870 | rLlKwDBGmyMe6lxLtymf | Summary | 59 | 1.9.6.10.3 | 1.9.6.10.3 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
796 | 5871 | owx5unCKcaLauhH4kWyj | Normal | 5 | 1.9.6.10.3.1 | 1.9.6.10.3.1 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
797 | 5872 | qImIYF1Y50rp0FNnsaoS | Normal | 10 | 1.9.6.10.3.2 | 1.9.6.10.3.2 |  | 2025-10-07 08:00 | p | 864 |  | 2028-02-18 13:09
798 | 5873 | FfFQqcMQ2fY5X0GvK0Xd | Normal | 20 | 1.9.6.10.3.3 | 1.9.6.10.3.3 |  | 2025-10-22 08:00 | p | 867 |  | 2028-03-07 11:58
799 | 5874 | fHTDjpnY2Gm0gViXPiAD | Normal | 2 | 1.9.6.10.3.6 | 1.9.6.10.3.6 |  | 2025-12-19 08:00 | p | 871 |  | 2028-05-08 10:44
800 | 5875 | TQZary26m4SvJkpuQUlv | Normal | 1 | 1.9.6.10.3.7 | 1.9.6.10.3.7 |  | 2025-12-23 08:00 | p | 869 |  | 2028-05-10 09:09
801 | 5876 | 5ZRJqmbhPGswffOWtWat | Normal | 1 | 1.9.6.10.3.8 | 1.9.6.10.3.8 |  | 2025-12-24 08:00 | p | 868 |  | 2028-05-10 16:29
802 | 6624 | sVpbcWAee9M5eeft5sdO | Normal | 15 | 1.9.6.10.3.4 | 1.9.6.10.3.4 |  | 2025-11-20 08:00 | p | 873 |  | 2028-04-11 11:46
803 | 6625 | it5qGsWYKIf8fEL1a2TB | Normal | 5 | 1.9.6.10.3.5 | 1.9.6.10.3.5 |  | 2025-12-12 08:00 | p | 868 |  | 2028-04-28 14:05
804 | 5877 | 8uIO0L3CbsjXfYIL70ur | Summary | 162 | 1.9.6.10.4 | 1.9.6.10.4 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
805 | 5878 | eKJmpIIS7eePXp789pq5 | Summary | 60 | 1.9.6.10.4.1 | 1.9.6.10.4.1 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
806 | 5879 | CJrwB1y6NRnYYg7kpaRv | Summary | 30 | 1.9.6.10.4.1.1 | 1.9.6.10.4.1.1 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
807 | 5880 | z8rht75g90pc62Jd1j8e | Normal | 15 | 1.9.6.10.4.1.1.1 | 1.9.6.10.4.1.1.1 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
808 | 5881 | ZPPJV7wrbqyTumtl84NX | Normal | 15 | 1.9.6.10.4.1.1.2 | 1.9.6.10.4.1.1.2 |  | 2025-10-22 08:00 | p | 860 |  | 2028-02-29 13:49
809 | 5882 | PdfqDNDAaUS1Z9tfvPSB | Normal | 15 | 1.9.6.10.4.1.2 | 1.9.6.10.4.1.2 |  | 2025-11-13 08:00 | p | 860 |  | 2028-03-22 15:58
810 | 5883 | 3J3dFKPf8v7HKW1lSal4 | Normal | 15 | 1.9.6.10.4.1.3 | 1.9.6.10.4.1.3 |  | 2025-12-05 08:00 | p | 858 |  | 2028-04-11 16:56
811 | 5884 | J3ZDJxR9DKKi4JquRb3Q | Summary | 20 | 1.9.6.10.4.2 | 1.9.6.10.4.2 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
812 | 5885 | p0UOLQYQkw5raD9Hf7AI | Normal | 5 | 1.9.6.10.4.2.1 | 1.9.6.10.4.2.1 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
813 | 5886 | mfBVa7VrtMT45ZcRp9ur | Normal | 5 | 1.9.6.10.4.2.2 | 1.9.6.10.4.2.2 |  | 2025-10-07 08:00 | p | 863 |  | 2028-02-17 11:18
814 | 5887 | xjL6okqGZuFc1ChaUzA0 | Normal | 5 | 1.9.6.10.4.2.3 | 1.9.6.10.4.2.3 |  | 2025-10-15 08:00 | p | 862 |  | 2028-02-24 11:50
815 | 5888 | 0NLdruhvCSk61FiIPSJA | Normal | 5 | 1.9.6.10.4.2.4 | 1.9.6.10.4.2.4 |  | 2025-10-22 08:00 | p | 863 |  | 2028-03-03 15:24
816 | 5889 | vcqfMiWzgD0sBRK91JrP | Normal | 3 | 1.9.6.10.4.3 | 1.9.6.10.4.3 |  | 2025-10-29 08:00 | p | 866 |  | 2028-03-13 08:09
817 | 5890 | r7iAplKyl5D3dW7yC0Jk | Normal | 5 | 1.9.6.10.4.4 | 1.9.6.10.4.4 |  | 2025-11-03 08:00 | p | 863 |  | 2028-03-15 15:38
818 | 5891 | 55B0pL3dU2GPDxU6IZLg | Normal | 1 | 1.9.6.10.4.5 | 1.9.6.10.4.5 |  | 2025-11-10 08:00 | p | 863 |  | 2028-03-22 15:32
819 | 5892 | zyPP7s8BBmPhydQ5fB2g | Normal | 1 | 1.9.6.10.4.8 | 1.9.6.10.4.8 |  | 2026-05-22 13:00 | p | 934 |  | 2028-12-11 13:54
820 | 5893 | JSBvauC3wpirasqwMrC9 | Normal | 1 | 1.9.6.10.4.6 | 1.9.6.10.4.6 |  | 2025-11-12 08:00 | p | 862 |  | 2028-03-23 13:30
821 | 5894 | AO4SgiivKvvxQJupi2GS | Normal | 1 | 1.9.6.10.4.7 | 1.9.6.10.4.7 |  | 2025-11-13 08:00 | p | 862 |  | 2028-03-24 13:34
822 | 4137 | rnRXxVdKdR5NUADIB31n | Normal | 1 | 1.9.6.11.1.2 | 1.9.6.11.1.2 |  | 2026-05-12 08:00 | p | 654 |  | 2028-02-25 10:36
823 | 4138 | 75WgU7H7MCC8DDgOcnsD | Normal | 30 | 1.9.6.11.1.3 | 1.9.6.11.1.3 |  | 2026-05-13 08:00 | p | 656 |  | 2028-02-28 11:51
824 | 4139 | 9SKpfzivi43NDDuHUq0B | Normal | 5 | 1.9.6.11.1.4 | 1.9.6.11.1.4 |  | 2026-06-26 08:00 | p | 650 |  | 2028-04-06 09:05
825 | 4140 | Lk7gef35zB3WaxM8Xyxe | Summary | 48 | 1.9.6.11.2 | 1.9.6.11.2 |  | 2026-07-06 08:00 | p | 646 |  | 2028-04-12 13:02
826 | 4141 | HGo5Ep3pqhcsiM5K4QjA | Summary | 23 | 1.9.6.11.2.1 | 1.9.6.11.2.1 |  | 2026-07-06 08:00 | p | 646 |  | 2028-04-12 13:02
827 | 4142 | VTqJrDLpWuaSlvRQajcM | Normal | 12 | 1.9.6.11.2.1.1 | 1.9.6.11.2.1.1 |  | 2026-07-06 08:00 | p | 646 |  | 2028-04-12 13:02
828 | 4143 | UwGhtpl5Mnq9WQrcrXRR | Normal | 11 | 1.9.6.11.2.1.2 | 1.9.6.11.2.1.2 |  | 2026-07-22 08:00 | p | 649 |  | 2028-05-01 15:56
829 | 4144 | zaFQ6K5wegGvKt6DGuoz | Summary | 25 | 1.9.6.11.2.2 | 1.9.6.11.2.2 |  | 2026-08-06 08:00 | p | 650 |  | 2028-05-17 11:22
830 | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Normal | 10 | 1.9.6.11.2.2.1 | 1.9.6.11.2.2.1 |  | 2026-08-06 08:00 | p | 650 |  | 2028-05-17 11:22
831 | 4146 | rTeXGnIwGPt6ES3ynSHq | Normal | 5 | 1.9.6.11.2.2.2 | 1.9.6.11.2.2.2 |  | 2026-08-20 08:00 | p | 649 |  | 2028-05-30 13:43
832 | 4147 | hQaW5HIstT5bbsPEBxyQ | Normal | 10 | 1.9.6.11.2.2.3 | 1.9.6.11.2.2.3 |  | 2026-08-27 08:00 | p | 648 |  | 2028-06-05 15:25
833 | 5998 | aRBXPvE6pbVbcbhlDtu4 | Summary | 47 | 1.9.6.1.7 | 1.9.6.1.7 |  | 2025-05-19 08:00 | p | 906 |  | 2027-11-11 13:59
834 | 5999 | hTF24jclc5ogfsrVWXZd | Normal | 40 | 1.9.6.1.7.1 | 1.9.6.1.7.1 |  | 2025-05-19 08:00 | p | 906 |  | 2027-11-11 13:59
835 | 6000 | dvNXA0SZWky1SGhKE7td | Normal | 5 | 1.9.6.1.7.2 | 1.9.6.1.7.2 |  | 2025-07-17 08:00 | p | 904 |  | 2028-01-07 09:53
836 | 6001 | z8HVZ6SyP3QpkaT54VAm | Normal | 1 | 1.9.6.1.7.3 | 1.9.6.1.7.3 |  | 2025-07-24 08:00 | p | 904 |  | 2028-01-14 10:43
837 | 6002 | rmlzSal3Nkh8gQGzhscw | Normal | 1 | 1.9.6.1.7.4 | 1.9.6.1.7.4 |  | 2025-07-25 08:00 | p | 906 |  | 2028-01-17 10:37
838 | 6003 | zkyCYMQIHOywdkyzbjbi | Summary | 48 | 1.9.6.1.8 | 1.9.6.1.8 |  | 2025-05-19 08:00 | p | 906 |  | 2027-11-11 13:59
839 | 6004 | xOhJcEwgSz1TAvNHU4tB | Normal | 40 | 1.9.6.1.8.1 | 1.9.6.1.8.1 |  | 2025-05-19 08:00 | p | 906 |  | 2027-11-11 13:59
840 | 6005 | gw3ZFSF3nzLqLqYBiqR7 | Normal | 5 | 1.9.6.1.8.2 | 1.9.6.1.8.2 |  | 2025-07-17 08:00 | p | 887 |  | 2027-12-21 11:00
841 | 6006 | HEKaqqmbwSXnCRXB6fED | Normal | 1 | 1.9.6.1.8.3 | 1.9.6.1.8.3 |  | 2025-07-24 08:00 | p | 887 |  | 2027-12-28 10:31
842 | 6007 | vdBzwsumrXxpXNAKvnKh | Normal | 1 | 1.9.6.1.8.4 | 1.9.6.1.8.4 |  | 2025-07-28 08:00 | p | 904 |  | 2028-01-18 08:48
843 | 6008 | Ph5VFx7Ghit4AwZEFBXT | Summary | 50 | 1.9.6.1.6 | 1.9.6.1.6 |  | 2025-04-07 08:00 | p | 905 |  | 2027-09-29 08:00
844 | 6009 | NVgukc0KZBShUa0wIlyx | Normal | 30 | 1.9.6.1.6.1 | 1.9.6.1.6.1 |  | 2025-04-07 08:00 | p | 905 |  | 2027-09-29 08:00
845 | 6010 | tIYqVtlT4yOF2YQ2FRYY | Normal | 10 | 1.9.6.1.6.2 | 1.9.6.1.6.2 |  | 2025-05-19 08:00 | p | 906 |  | 2027-11-11 13:59
846 | 6011 | 9Y3pHbqvwzl2AwHfvrBG | Normal | 5 | 1.9.6.1.6.3 | 1.9.6.1.6.3 |  | 2025-06-03 08:00 | p | 904 |  | 2027-11-24 11:11
847 | 6012 | Z1jpWQx4GyFcVoEVg0i0 | Normal | 5 | 1.9.6.1.6.4 | 1.9.6.1.6.4 |  | 2025-06-10 08:00 | p | 904 |  | 2027-12-01 10:24
848 | 6013 | y2dxMv99iLhGOXikZGuK | Summary | 34 | 1.9.6.1.5 | 1.9.6.1.5 |  | 2025-03-17 08:00 | p | 25 |  | 2025-04-11 15:34
849 | 6014 | hYHiAVYfHXdDTdWEk9J8 | Normal | 15 | 1.9.6.1.5.1 | 1.9.6.1.5.1 |  | 2025-03-17 08:00 | p | 25 |  | 2025-04-11 15:34
850 | 6015 | MXdxqc8Y6tIByFeEqluF | Normal | 10 | 1.9.6.1.5.2 | 1.9.6.1.5.2 |  | 2025-04-07 08:00 | p | 24 |  | 2025-05-01 14:39
851 | 6016 | gwhB80Lv7eu4PoYwev8o | Normal | 5 | 1.9.6.1.5.3 | 1.9.6.1.5.3 |  | 2025-04-21 08:00 | p | 24 |  | 2025-05-15 14:44
852 | 6017 | VCyTBN0y7V3erCRNMvm4 | Normal | 4 | 1.9.6.1.5.4 | 1.9.6.1.5.4 |  | 2025-04-28 08:00 | p | 23 |  | 2025-05-21 13:41
853 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | 2025-02-18 08:00 | p | 925 |  | 2027-09-01 08:00
854 | 6957 | ar01N24L63iczVEh1mVo | Summary | 24 | 1.9.6.1.4 | 1.9.6.1.4 |  | 2025-03-04 08:00 | p | 29 |  | 2025-04-02 09:07
855 | 6958 | 6Ul4V6iAcnpVqewOp14Y | Normal | 4 | 1.9.6.1.4.1 | 1.9.6.1.4.1 |  | 2025-03-04 08:00 | p | 29 |  | 2025-04-02 09:07
856 | 6959 | w9Vvv79ftt4PUqInNFyD | Normal | 5 | 1.9.6.1.4.2 | 1.9.6.1.4.2 |  | 2025-03-10 08:00 | p | 28 |  | 2025-04-07 13:43
857 | 6960 | xIgpHAurEQ244gHa2T5q | Normal | 5 | 1.9.6.1.4.3 | 1.9.6.1.4.3 |  | 2025-03-17 08:00 | p | 25 |  | 2025-04-11 15:34
858 | 6961 | NOksVV7sTymsgwMrnh6x | Normal | 10 | 1.9.6.1.4.4 | 1.9.6.1.4.4 |  | 2025-03-24 08:00 | p | 25 |  | 2025-04-18 14:07
859 | 4075 | dGbNHsOLhslKk8CjhyjE | Normal | 1 | 1.9.6.9.3 | 1.9.6.9.3 |  | 2025-04-01 08:00 | p | 27 |  | 2025-04-28 13:41
860 | 6427 | NeAxFJaqSLize8VPNJ6N | Normal | 1 | 1.7.1.8.3 | 1.7.1.8.3 |  | 2025-03-14 08:00 | q | -101 |  | 2024-12-03 08:00
861 | 4196 | 2ZwOzHGH45ywtPvfASSG | Normal | 5 | 1.9.8.1.5 | 1.9.8.1.5 |  | 2025-09-16 08:00 | q | -20 |  | 2025-08-26 15:35
862 | 5974 | cJ7VeFZezCBnvYlHxCmb | Normal | 1 | 1.9.8.1.6.7 | 1.9.8.1.6.7 |  | 2025-02-27 08:00 | q | -120 |  | 2024-10-30 08:00
863 | 5985 | AUKn3E7aViOsULw8HdKV | Normal | 131 | 1.9.8.1.12 | 1.9.8.1.12 |  | 2025-03-11 08:00 | p | 29 |  | 2025-04-09 09:57
864 | 4231 | 8h0WH2qeIC7tfvcerCPa | Normal | 1 | 1.9.8.2.3 | 1.9.8.2.3 |  | 2025-06-24 08:00 | q | -183 |  | 2024-12-23 08:00
865 | 4235 | QiaATNQSPId7svzcuO8r | Normal | 91 | 1.9.8.2.7 | 1.9.8.2.7 |  | 2025-07-17 08:00 | p | 32 |  | 2025-08-18 14:35
866 | 4243 | LpPx7AWOh1V8dzWVWc6j | Normal | 1 | 1.9.8.4.5 | 1.9.8.4.5 |  | 2025-05-13 08:00 | q | -357 |  | 2024-05-21 08:00
867 | 4246 | ANAzXnUTz1PCb3xsov4Y | Normal | 10 | 1.9.8.4.7 | 1.9.8.4.7 |  | 2025-05-14 08:00 | p | 44 |  | 2025-06-27 11:52
868 | 4248 | E1RJwJWM8qrsKP3o7Toy | Normal | 1 | 1.9.8.7 | 1.9.8.7 |  | 2025-08-05 08:00 | q | -17 |  | 2025-07-18 08:03
869 | 4251 | IBg36OMMKUy3vwEnRNF0 | Normal | 1 | 1.9.8.6 | 1.9.8.6 |  | 2025-06-05 08:00 | q | -668 |  | 2023-08-07 08:00
870 | 4253 | hnujWIe1JDNg9VHs3TWw | Normal | 1 | 1.9.8.8 | 1.9.8.8 |  | 2025-08-12 08:00 | q | -24 |  | 2025-07-18 16:27
871 | 4255 | TAfq40Sin0H6Q2YT0OS5 | Milestone | 0 | 1.9.8.3 | 1.9.8.3 |  | 2025-11-25 17:00 | q | -11 |  | 2025-11-14 11:45
872 | 4256 | G2pYfP7dsnHVTgqQD6mD | Summary | 82 | 1.9.8.10 | 1.9.8.10 |  | 2025-09-26 08:00 | q | -781 |  | 2023-08-07 08:00
873 | 4258 | GzQkXlTiYJMdE6nBDVeb | Normal | 6 | 1.9.8.10.1 | 1.9.8.10.1 |  | 2025-09-26 08:00 | q | -781 |  | 2023-08-07 08:00
874 | 6090 | LkexiRQNUDyJAwm8EPYV | Normal | 32 | 1.9.8.10.7 | 1.9.8.10.7 |  | 2025-12-10 08:00 | q | -788 |  | 2023-10-13 16:14
875 | 6187 | kIPGiItVAbHq2ks8DK41 | Normal | 5 | 1.9.8.10.6 | 1.9.8.10.6 |  | 2025-12-03 08:00 | q | -785 |  | 2023-10-09 09:37
876 | 6430 | IYyY3jK4t9QuDyuxqyQ5 | Normal | 15 | 1.9.8.10.2 | 1.9.8.10.2 |  | 2025-10-06 08:00 | q | -786 |  | 2023-08-11 16:09
877 | 6431 | mXx66gQ5BZWpD3idmZgM | Normal | 10 | 1.9.8.10.3 | 1.9.8.10.3 |  | 2025-10-28 08:00 | q | -789 |  | 2023-08-30 13:04
878 | 6432 | vMoeJo3Rc30lMwFim6rn | Normal | 10 | 1.9.8.10.4 | 1.9.8.10.4 |  | 2025-11-12 08:00 | q | -785 |  | 2023-09-18 11:27
879 | 6433 | zONKYXhH5yZJE26xvIWD | Normal | 4 | 1.9.8.10.5 | 1.9.8.10.5 |  | 2025-11-26 08:00 | q | -784 |  | 2023-10-03 11:25
880 | 6083 | 3dsblDK1X9ztc27EZU3v | Normal | 1 | 1.9.8.5 | 1.9.8.5 |  | 2025-12-12 08:00 | p | 930 |  | 2028-06-29 10:44
881 | 6084 | deZM0xh115wln716GUoI | Normal | 1 | 1.9.8.9 | 1.9.8.9 |  | 2026-10-02 13:00 | p | 929 |  | 2029-04-19 10:06
882 | 7321 | CTokiQfH6gyOyeZJGrxP | Normal | 1 | 1.7.9.11 | 1.7.9.11 |  | 2025-05-30 08:00 | q | -662 |  | 2023-08-07 08:00
883 | 5690 | jLB7gq1wR8egZrMIoAc7 | Summary | 24 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-02-27 17:00 | p | 25 |  | 2025-03-25 16:29
884 | 5691 | glUuWw43f2R9t2hl6VHO | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-02-27 17:00 | p | 25 |  | 2025-03-25 16:29
885 | 5692 | KeXnvnZRx0KMyut3yw5s | Milestone | 0 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-03-13 17:00 | p | 21 |  | 2025-04-04 10:19
886 | 5693 | VdKRFLdSc60knizSqFXc | Normal | 14 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-03-13 17:00 | p | 21 |  | 2025-04-04 10:19
887 | 5694 | Gb0taOZcQ8l0cdHliY6j | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-02 17:00 | p | 22 |  | 2025-04-25 09:18
888 | 5695 | ePp2idADlztrdEpItyCc | Milestone | 0 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-16 17:00 | p | 25 |  | 2025-05-12 15:52
889 | 5696 | npE0RnxADwI7cDPG1fDa | Normal | 4 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-16 17:00 | p | 25 |  | 2025-05-12 15:52
890 | 5697 | 4nIBzBv3LSP60HeOLv0f | Normal | 5 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-23 08:00 | p | 26 |  | 2025-05-19 10:36
891 | 5536 | cYU0DBZylLxVRoLEp7Bc | Normal | 40 | 1.9.5.1.4 | 1.9.5.1.4 |  | 2025-03-04 08:00 | p | 34 |  | 2025-04-07 16:10
892 | 5544 | cIc3ARzcdrbXv6maHllr | Summary | 129 | 1.9.5.2.13 | 1.9.5.2.13 |  | 2025-03-17 08:00 | p | 29 |  | 2025-04-15 16:20
893 | 5545 | 7UVU8IboY6NG7sqZCrUC | Normal | 7 | 1.9.5.2.13.2 | 1.9.5.2.13.2 |  | 2025-05-21 08:00 | p | 944 |  | 2027-12-21 13:16
894 | 5546 | Shs5wuYOFSkTF1YslX8w | Normal | 6 | 1.9.5.2.13.5 | 1.9.5.2.13.5 |  | 2025-06-09 08:00 | p | 940 |  | 2028-01-05 14:48
895 | 5547 | KglXvc5QwlHEboIvY96Q | Normal | 4 | 1.9.5.2.13.8 | 1.9.5.2.13.8 |  | 2025-07-09 08:00 | p | 939 |  | 2028-02-03 13:14
896 | 5548 | Zfzda0CfmpiN8ZL93G3t | Normal | 5 | 1.9.5.2.13.9 | 1.9.5.2.13.9 |  | 2025-07-15 08:00 | p | 939 |  | 2028-02-09 13:14
897 | 5549 | PgYJem7PJFdGgV04ojeL | Normal | 1 | 1.4.17 | 1.4.17 |  | 2025-07-22 08:00 | p | 940 |  | 2028-02-17 13:18
898 | 5556 | fOMVaiOa0jnHOJyDUdVQ | Normal | 25 | 1.9.5.2.13.11 | 1.9.5.2.13.11 |  | 2025-08-13 08:00 | p | 944 |  | 2028-03-14 13:46
899 | 5730 | ypyrsmMFJqJ9aPla6UhQ | Normal | 4 | 1.9.5.2.13.3 | 1.9.5.2.13.3 |  | 2025-06-02 08:00 | p | 940 |  | 2027-12-29 16:29
900 | 5731 | uQF6Ff0bc2cqy3b37ZQc | Normal | 1 | 1.9.5.2.13.4 | 1.9.5.2.13.4 |  | 2025-06-06 08:00 | p | 942 |  | 2028-01-04 15:46
901 | 5732 | OQKwpwUgImWCC2Fp5G0Q | Normal | 7 | 1.9.5.2.13.6 | 1.9.5.2.13.6 |  | 2025-06-17 08:00 | p | 941 |  | 2028-01-14 10:46
902 | 5733 | wyOxVAS94HubPKo2yHJm | Normal | 7 | 1.9.5.2.13.7 | 1.9.5.2.13.7 |  | 2025-06-27 08:00 | p | 942 |  | 2028-01-25 11:46
903 | 7000 | yP1oDcnUQTy3g68ZLgu0 | Normal | 8 | 1.9.5.2.13.1 | 1.9.5.2.13.1 |  | 2025-03-17 08:00 | p | 29 |  | 2025-04-15 16:20
904 | 5557 | U376LwOjKfNZoVLUlmMD | Summary | 113 | 1.9.5.2.12 | 1.9.5.2.12 |  | 2025-03-04 08:00 | p | 29 |  | 2025-04-02 09:07
905 | 5558 | RXAxJx3BHWNVdWFPfZ2a | Normal | 13 | 1.9.5.2.12.2 | 1.9.5.2.12.2 |  | 2025-04-23 08:00 | p | 940 |  | 2027-11-19 08:41
906 | 5559 | jJoy8dUJMWD3ZuNw52D0 | Normal | 8 | 1.9.5.2.12.5 | 1.9.5.2.12.5 |  | 2025-05-21 08:00 | p | 944 |  | 2027-12-21 13:16
907 | 5560 | wu3sL1wqoiodUr5mG52N | Normal | 4 | 1.9.5.2.12.8 | 1.9.5.2.12.8 |  | 2025-06-24 08:00 | p | 941 |  | 2028-01-21 13:29
908 | 5561 | Vb2zzMF18WNANxlCzGiz | Normal | 5 | 1.9.5.2.12.9 | 1.9.5.2.12.9 |  | 2025-06-30 08:00 | p | 941 |  | 2028-01-27 11:57
909 | 5562 | vp7j6GBYm2dAMLvxEFuE | Normal | 1 | 1.4.20 | 1.4.20 |  | 2025-07-08 08:00 | p | 939 |  | 2028-02-02 14:54
910 | 5569 | 35aiC9HLOSrIl2OBwDvd | Normal | 25 | 1.9.5.2.12.11 | 1.9.5.2.12.11 |  | 2025-07-09 08:00 | p | 939 |  | 2028-02-03 15:25
911 | 5734 | iq9bjqBZvH9Bj6912271 | Normal | 6 | 1.9.5.2.12.3 | 1.9.5.2.12.3 |  | 2025-05-12 08:00 | p | 941 |  | 2027-12-09 10:24
912 | 5735 | Z8zFgfwvHK2hwW2AW8Qa | Normal | 1 | 1.9.5.2.12.4 | 1.9.5.2.12.4 |  | 2025-05-20 08:00 | p | 944 |  | 2027-12-20 13:06
913 | 5736 | QgUmTWGvxjzq3xqrWPJK | Normal | 7 | 1.9.5.2.12.6 | 1.9.5.2.12.6 |  | 2025-06-03 08:00 | p | 941 |  | 2027-12-31 14:10
914 | 5737 | iDzIA8f8DQgg2wVNkaUu | Normal | 7 | 1.9.5.2.12.7 | 1.9.5.2.12.7 |  | 2025-06-12 08:00 | p | 943 |  | 2028-01-11 10:01
915 | 7001 | WpRQh8HvPfyDha8FH5FR | Normal | 9 | 1.9.5.2.12.1 | 1.9.5.2.12.1 |  | 2025-03-04 08:00 | p | 29 |  | 2025-04-02 09:07
916 | 5571 | lfRAbO0c5jl7NaC6s7pm | Normal | 21 | 1.9.5.2.11.2 | 1.9.5.2.11.2 |  | 2025-03-17 08:00 | p | 939 |  | 2027-10-12 11:58
917 | 5572 | jk3Vm36iIGViuk9dpLfQ | Normal | 8 | 1.9.5.2.11.5 | 1.9.5.2.11.5 |  | 2025-04-23 08:00 | p | 940 |  | 2027-11-19 08:41
918 | 5573 | u3MfiduPa05JsS2ly7WD | Normal | 4 | 1.9.5.2.11.8 | 1.9.5.2.11.8 |  | 2025-06-09 08:00 | p | 933 |  | 2027-12-29 16:03
919 | 5574 | 3iKE3riinMPRUpVpTfwx | Normal | 5 | 1.9.5.2.11.9 | 1.9.5.2.11.9 |  | 2025-06-13 08:00 | p | 936 |  | 2028-01-05 08:46
920 | 5575 | 48yotl4pDzxbk5y0VDbK | Normal | 1 | 1.4.23 | 1.4.23 |  | 2025-06-23 08:00 | p | 933 |  | 2028-01-12 14:00
921 | 5582 | 6tLu8emqwotxTkeBbEpy | Normal | 26 | 1.9.5.2.11.11 | 1.9.5.2.11.11 |  | 2025-06-24 08:00 | p | 933 |  | 2028-01-13 14:31
922 | 5738 | ME2oX9BwgLu5cggaunhg | Normal | 5 | 1.9.5.2.11.3 | 1.9.5.2.11.3 |  | 2025-04-15 08:00 | p | 940 |  | 2027-11-11 09:42
923 | 5739 | IivOSmNLtmlF9JKFLUrl | Normal | 1 | 1.9.5.2.11.4 | 1.9.5.2.11.4 |  | 2025-04-22 08:00 | p | 940 |  | 2027-11-18 09:40
924 | 5740 | eRxCjL3dV2CpHvAG84r7 | Normal | 12 | 1.9.5.2.11.6 | 1.9.5.2.11.6 |  | 2025-05-05 08:00 | p | 935 |  | 2027-11-26 08:06
925 | 5741 | 8Y4jq7dOt4lN4NYBT6r1 | Normal | 12 | 1.9.5.2.11.7 | 1.9.5.2.11.7 |  | 2025-05-21 08:00 | p | 936 |  | 2027-12-13 15:36
926 | 5583 | gkFBoXdv1oJb2jtBcO5M | Summary | 147 | 1.9.5.2.14 | 1.9.5.2.14 |  | 2025-03-27 08:00 | p | 27 |  | 2025-04-23 16:51
927 | 5584 | 6WMzJdzS7tY0wFFuXnrc | Normal | 7 | 1.9.5.2.14.2 | 1.9.5.2.14.2 |  | 2025-06-09 08:00 | p | 940 |  | 2028-01-05 14:48
928 | 5585 | KljMWvDEBGSuBTW4zQhZ | Normal | 7 | 1.9.5.2.14.5 | 1.9.5.2.14.5 |  | 2025-06-26 08:00 | p | 943 |  | 2028-01-25 09:57
929 | 5586 | Z3ZWpIsgJCSKUX161hV0 | Normal | 4 | 1.9.5.2.14.8 | 1.9.5.2.14.8 |  | 2025-07-24 08:00 | p | 939 |  | 2028-02-18 14:37
930 | 5587 | OXOUsYDejGVlgqn4Z1vl | Normal | 5 | 1.9.5.2.14.9 | 1.9.5.2.14.9 |  | 2025-07-30 08:00 | p | 939 |  | 2028-02-24 11:24
931 | 5588 | MFjHKzinVVI0Ndx8qx0B | Normal | 1 | 1.4.26 | 1.4.26 |  | 2025-08-06 08:00 | p | 940 |  | 2028-03-03 15:26
932 | 5595 | REFTk0AP9RBTibJWVhuH | Normal | 26 | 1.9.5.2.14.11 | 1.9.5.2.14.11 |  | 2025-09-18 08:00 | p | 944 |  | 2028-04-19 10:01
933 | 5742 | 88bEv4EMiOL2y8w1ttIM | Normal | 4 | 1.9.5.2.14.3 | 1.9.5.2.14.3 |  | 2025-06-18 08:00 | p | 940 |  | 2028-01-14 16:57
934 | 5743 | 0Uz4krHDVCdAlMd5aRwh | Normal | 1 | 1.9.5.2.14.4 | 1.9.5.2.14.4 |  | 2025-06-25 08:00 | p | 940 |  | 2028-01-21 16:37
935 | 5744 | cSBfnbrbVLLFYTMEfBKA | Normal | 6 | 1.9.5.2.14.6 | 1.9.5.2.14.6 |  | 2025-07-08 08:00 | p | 939 |  | 2028-02-02 15:52
936 | 5745 | ZY99Y6JX4jBylnfeedvo | Normal | 6 | 1.9.5.2.14.7 | 1.9.5.2.14.7 |  | 2025-07-16 08:00 | p | 943 |  | 2028-02-14 09:20
937 | 6999 | AnycnugTW971av3hMZXE | Normal | 8 | 1.9.5.2.14.1 | 1.9.5.2.14.1 |  | 2025-03-27 08:00 | p | 27 |  | 2025-04-23 16:51
938 | 6446 | XvbStahAymwCoqNIbMJG | Summary | 32 | 1.9.5.2.4 | 1.9.5.2.4 |  | 2025-03-03 08:00 | q | -364 |  | 2024-03-04 08:00
939 | 6532 | 15e7xcLR1b1jSikaz0S2 | Normal | 32 | 1.9.5.2.4.2 | 1.9.5.2.4.2 |  | 2025-03-03 08:00 | q | -364 |  | 2024-03-04 08:00
940 | 6533 | b0mutjzKj8FRw4zkbb8K | Normal | 32 | 1.9.5.2.4.1 | 1.9.5.2.4.1 |  | 2025-03-03 08:00 | q | -364 |  | 2024-03-04 08:00
941 | 6534 | 8Gl2bk4Fxxo2fsClDJqG | Normal | 32 | 1.9.5.2.4.3 | 1.9.5.2.4.3 |  | 2025-03-03 08:00 | q | -364 |  | 2024-03-04 08:00
942 | 6535 | dWze9AnK8NrEMD9LOEyU | Normal | 32 | 1.9.5.2.4.4 | 1.9.5.2.4.4 |  | 2025-03-03 08:00 | q | -364 |  | 2024-03-04 08:00
943 | 6955 | CPACk87DS0kpO7pXcdwS | Normal | 10 | 1.9.5.2.10 | 1.9.5.2.10 |  | 2025-02-18 08:00 | p | 926 |  | 2027-09-02 13:26
944 | 5596 | upn4QoZvaKBmBMoyhnq5 | Summary | 90 | 1.9.5.3 | 1.9.5.3 |  | 2025-07-30 08:00 | p | 939 |  | 2028-02-24 11:24
945 | 5597 | zKJsJYNcPRFZ7wBjvprv | Normal | 18 | 1.9.5.3.1 | 1.9.5.3.1 |  | 2025-07-30 08:00 | p | 939 |  | 2028-02-24 11:24
946 | 5598 | zvvzNQqIPXzcVRwy0N44 | Summary | 52 | 1.9.5.3.2 | 1.9.5.3.2 |  | 2025-09-16 08:00 | p | 939 |  | 2028-04-12 13:04
947 | 5599 | T0Oh47cWIVU9y2MKPB0U | Normal | 12 | 1.9.5.3.2.1 | 1.9.5.3.2.1 |  | 2025-09-16 08:00 | p | 939 |  | 2028-04-12 13:04
948 | 5600 | oTkX6bjokLXQ590hdeFy | Normal | 12 | 1.9.5.3.2.2 | 1.9.5.3.2.2 |  | 2025-10-02 08:00 | p | 942 |  | 2028-05-01 15:11
949 | 5601 | xa7cRxeKgQxZnuHNAYMQ | Normal | 12 | 1.9.5.3.2.3 | 1.9.5.3.2.3 |  | 2025-10-27 08:00 | p | 948 |  | 2028-06-01 10:32
950 | 5602 | QlxDegibloFbHrPNJwyW | Normal | 12 | 1.9.5.3.2.4 | 1.9.5.3.2.4 |  | 2025-11-13 08:00 | p | 944 |  | 2028-06-14 08:04
951 | 5603 | dwMYG7lg76TqxtTxZNCR | Normal | 5 | 1.9.5.3.3 | 1.9.5.3.3 |  | 2025-12-02 08:00 | p | 944 |  | 2028-07-03 15:24
952 | 5360 | ARncD9Nx3De5DONPy9Bs | Normal | 3 | 1.9.4.1.4 | 1.9.4.1.4 |  | 2025-04-10 08:00 | q | 0 |  | 2025-04-09 16:48
953 | 5368 | NKJL1ZJN3KgUArkbA4qS | Normal | 3 | 1.9.4.2.4 | 1.9.4.2.4 |  | 2025-02-21 08:00 | p | 496 |  | 2026-07-02 11:08
954 | 7261 | isfym7y8CMuc9Vq3Mbcl | Normal | 1 | 1.7.4.2.5 | 1.7.4.2.5 |  | 2025-02-20 08:00 | p | 496 |  | 2026-07-01 13:56
955 | 5383 | u1aficyBQ2O9A8MnpdfZ | Normal | 20 | 1.9.4.5.6 | 1.9.4.5.6 |  | 2025-03-17 08:00 | p | 0 |  | 2025-03-17 08:25
956 | 5384 | d8i6C63YfOF3EovUl19W | Normal | 10 | 1.9.4.5.7 | 1.9.4.5.7 |  | 2025-04-14 08:00 | p | 4 |  | 2025-04-18 13:59
957 | 5385 | ohwsmv9qOoV0RNzIdjJI | Normal | 15 | 1.9.4.5.8 | 1.9.4.5.8 |  | 2025-04-28 08:00 | p | 4 |  | 2025-05-02 14:06
958 | 5386 | tSuemAovBYAaHNhFiwaF | Normal | 15 | 1.9.4.5.9 | 1.9.4.5.9 |  | 2025-05-19 08:00 | p | 9 |  | 2025-05-28 10:53
959 | 5393 | 3qvg7di25vdBD8UUvM1a | Normal | 20 | 1.9.4.6.6 | 1.9.4.6.6 |  | 2025-03-17 08:00 | q | -4 |  | 2025-03-12 13:55
960 | 5394 | ungpeNo64cspVo3BuO9g | Normal | 10 | 1.9.4.6.7 | 1.9.4.6.7 |  | 2025-04-14 08:00 | q | -4 |  | 2025-04-09 13:03
961 | 5395 | KZXvYFda88KgX9w7a3ES | Normal | 15 | 1.9.4.6.8 | 1.9.4.6.8 |  | 2025-04-28 08:00 | q | -3 |  | 2025-04-24 13:29
962 | 5396 | FNjsTUKVT29tBcVlvaM6 | Normal | 15 | 1.9.4.6.9 | 1.9.4.6.9 |  | 2025-05-19 08:00 | q | -4 |  | 2025-05-14 14:24
963 | 5397 | KGrMeH5y6HH9dj1tr8uB | Summary | 53 | 1.9.4.7 | 1.9.4.7 |  | 2025-06-10 08:00 | p | 3 |  | 2025-06-13 10:42
964 | 5398 | EMMfZLgDhvN5O0lAfznQ | Normal | 15 | 1.9.4.7.1 | 1.9.4.7.1 |  | 2025-06-10 08:00 | p | 3 |  | 2025-06-13 10:42
965 | 5399 | 5K7jeUOrZ3wka9S2O1Dn | Normal | 15 | 1.9.4.7.2 | 1.9.4.7.2 |  | 2025-07-02 08:00 | p | 7 |  | 2025-07-09 13:26
966 | 5400 | I2IZFfCcy2hUSTtihPWq | Normal | 15 | 1.9.4.7.3 | 1.9.4.7.3 |  | 2025-07-24 08:00 | p | 6 |  | 2025-07-30 13:24
967 | 5401 | WWZjxA63YxH38hnYmVKG | Normal | 8 | 1.9.4.7.4 | 1.9.4.7.4 |  | 2025-08-14 08:00 | p | 6 |  | 2025-08-20 11:13
968 | 5402 | zDUD70mdAG3rcozejCwk | Summary | 15 | 1.9.4.8 | 1.9.4.8 |  | 2025-08-26 08:00 | p | 10 |  | 2025-09-05 13:16
969 | 5403 | wP2WbhW6upJb7JmdzCw1 | Normal | 9 | 1.9.4.8.1 | 1.9.4.8.1 |  | 2025-08-26 08:00 | p | 10 |  | 2025-09-05 13:16
970 | 5404 | UrewlDJ3J2c8Ueci7p9E | Normal | 6 | 1.9.4.8.2 | 1.9.4.8.2 |  | 2025-09-09 08:00 | p | 395 |  | 2026-10-09 11:51
971 | 7264 | vNqQNKJIEgg8BiBzdWeI | Summary | 57 | 1.7.4.3.6 | 1.7.4.3.6 |  | 2025-04-10 08:00 | p | 448 |  | 2026-07-02 11:08
972 | 7265 | uNFJkQaxxZ7oOYaM8QxX | Normal | 13 | 1.7.4.3.6.1 | 1.7.4.3.6.1 |  | 2025-04-10 08:00 | p | 448 |  | 2026-07-02 11:08
973 | 7266 | y7TR6NxR4uOKxinxsnEt | Normal | 13 | 1.7.4.3.6.2 | 1.7.4.3.6.2 |  | 2025-04-30 08:00 | p | 449 |  | 2026-07-23 15:35
974 | 7267 | f0BUmD79ZhKqjjzrwXUq | Normal | 13 | 1.7.4.3.6.3 | 1.7.4.3.6.3 |  | 2025-05-19 08:00 | p | 449 |  | 2026-08-11 09:18
975 | 7268 | sP1zO7OhzT9CUKqdzecJ | Normal | 12 | 1.7.4.3.6.4 | 1.7.4.3.6.4 |  | 2025-06-06 08:00 | p | 448 |  | 2026-08-28 16:14
976 | 7269 | 7v5GPnNw6yREyKfoeMiZ | Normal | 5 | 1.7.4.3.6.5 | 1.7.4.3.6.5 |  | 2025-06-25 08:00 | p | 448 |  | 2026-09-16 15:45
977 | 7322 | XsHCl5GkwKVP3xy7r0jT | Summary | 85 | 1.7.5 | 1.7.5 |  | 2025-03-03 08:00 | q | -574 |  | 2023-08-07 08:00
978 | 7528 | 8SnF5zCB4rJyZyQZLLZc | Normal | 8 | 1.7.5.1 | 1.7.5.1 |  | 2025-03-03 08:00 | q | -574 |  | 2023-08-07 08:00
979 | 7529 | ugdLGMeRoSNQZE98ehwR | Normal | 8 | 1.7.5.2 | 1.7.5.2 |  | 2025-03-03 08:00 | q | -574 |  | 2023-08-07 08:00
980 | 7530 | tZgNvNsEFqNHmYVKXpMu | Normal | 7 | 1.7.5.3 | 1.7.5.3 |  | 2025-03-13 08:00 | q | -569 |  | 2023-08-21 13:24
981 | 7531 | WsQS39Ko43y2ykuRUNnk | Normal | 8 | 1.7.5.4 | 1.7.5.4 |  | 2025-03-24 08:00 | q | -571 |  | 2023-08-30 10:14
982 | 7532 | tNKjUDGuH9lZvW14y0xJ | Normal | 22 | 1.7.5.5 | 1.7.5.5 |  | 2025-04-03 08:00 | q | -566 |  | 2023-09-14 09:50
983 | 7533 | HKUUjAeDBFLcgj42uw3c | Normal | 19 | 1.7.5.6 | 1.7.5.6 |  | 2025-05-05 08:00 | q | -565 |  | 2023-10-17 11:23
984 | 7534 | s7VTtgJqjYjf9pbLYcYj | Normal | 8 | 1.7.5.7 | 1.7.5.7 |  | 2025-06-02 08:00 | q | -564 |  | 2023-11-15 13:09
985 | 7535 | uGgP1gHCy12zlVFcLeTG | Normal | 6 | 1.7.5.8 | 1.7.5.8 |  | 2025-06-12 08:00 | q | -562 |  | 2023-11-27 10:34
986 | 7536 | kbIucnV7qsI0ZjxbK1cH | Normal | 6 | 1.7.5.9 | 1.7.5.9 |  | 2025-06-23 08:00 | q | -569 |  | 2023-12-01 16:48
987 | 7537 | ZiOXL4e3BgetRuJ4aYKK | Normal | 1 | 1.7.5.10 | 1.7.5.10 |  | 2025-07-01 08:00 | q | -566 |  | 2023-12-12 13:17
988 | 6690 | bopLkaAZbmZjIM9EGI6L | Normal | 532 | 1.11.2 | 1.11.2 |  | 2026-09-08 08:00 | q | -1128 |  | 2023-08-07 08:00
989 | 7131 | XTX9Wl5SzTxAD1rtsh9U | Summary | 0 | 1.10 | 1.10 |  | 2023-10-12 17:00 | q | -2114 |  | 2017-12-28 16:20
990 | 156 | 0RXSkgYJdrs7AeQvgU3w | Milestone | 0 | 1.10.24 | 1.10.24 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
991 | 157 | DYCfhHgWVvjY4WPSrw6q | Milestone | 0 | 1.10.25 | 1.10.25 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
992 | 7107 | fjlRoMsMUGjOnNWoUkGJ | Milestone | 0 | 1.10.16 | 1.10.16 |  | 2027-01-01 08:05 | p | 5 |  | 2027-01-06 08:12
993 | 7108 | wFwSqsIrP0eolc7owrIn | Milestone | 0 | 1.10.3 | 1.10.3 |  | 2025-04-10 17:00 | q | -3 |  | 2025-04-07 10:08
994 | 7110 | fycPVr34q6lr2y2bEJNl | Milestone | 0 | 1.10.9 | 1.10.9 |  | 2025-08-05 17:00 | p | 35 |  | 2025-09-10 14:26
995 | 7111 | gs1r9nT3BBBdW42nHT47 | Milestone | 0 | 1.10.13 | 1.10.13 |  | 2025-10-16 17:00 | p | 31 |  | 2025-11-17 09:47
996 | 7112 | a270fhhuENq55tFKO8IB | Milestone | 0 | 1.10.10 | 1.10.10 |  | 2025-11-28 17:00 | p | 23 |  | 2025-12-22 09:42
997 | 7114 | pZqvbi91bBhqyjB86evl | Milestone | 0 | 1.10.2 | 1.10.2 |  | 2026-03-06 17:00 | p | 20 |  | 2026-03-27 11:53
998 | 7115 | mxRJVREYCLlOZtWGohdT | Milestone | 0 | 1.10.8 | 1.10.8 |  | 2026-04-03 17:00 | p | 9 |  | 2026-04-13 11:49
999 | 7116 | 4gFjRlWXKNF16b9sFMXr | Milestone | 0 | 1.10.11 | 1.10.11 |  | 2025-09-24 17:00 | q | -170 |  | 2025-04-07 15:53
1000 | 7117 | zFlqKdf38AVahGy9Q9X8 | Milestone | 0 | 1.10.12 | 1.10.12 |  | 2026-01-14 17:00 | q | -8 |  | 2026-01-06 13:47
1001 | 7118 | 6jNHf85fMsjQD6qn9QnY | Milestone | 0 | 1.10.14 | 1.10.14 |  | 2025-12-15 17:00 | p | 27 |  | 2026-01-12 08:25
1002 | 7119 | OQnmDeJwrgb4ibYKrZjo | Milestone | 0 | 1.10.15 | 1.10.15 |  | 2025-10-01 17:00 | q | -586 |  | 2024-02-23 09:07
1003 | 7120 | ewfCDE69jjk4Zb5M5CES | Milestone | 0 | 1.10.4 | 1.10.4 |  | 2025-04-02 17:00 | q | -6 |  | 2025-03-27 13:16
1004 | 7121 | V4W6CQQo6lTjRlhYdPDq | Milestone | 0 | 1.10.5 | 1.10.5 |  | 2025-05-19 17:00 | p | 34 |  | 2025-06-23 10:29
1005 | 7122 | ZQwX0qpiGy3bERfpXjQ0 | Milestone | 0 | 1.10.6 | 1.10.6 |  | 2025-04-07 17:00 | p | 27 |  | 2025-05-05 10:48
1006 | 7123 | 0fpNMQTy9Zfk1YAC7GK2 | Milestone | 0 | 1.10.7 | 1.10.7 |  | 2025-04-01 17:00 | q | -6 |  | 2025-03-26 11:36
1007 | 7124 | yYQOOagkBr46kWICPuG6 | Milestone | 0 | 1.10.17 | 1.10.17 |  | 2025-09-11 17:00 | q | -2814 |  | 2017-12-28 16:20
1008 | 7125 | a4xeGKWGk9YyWLffVRQZ | Milestone | 0 | 1.10.18 | 1.10.18 |  | 2025-10-08 17:00 | q | -2809 |  | 2018-01-29 14:01
1009 | 7126 | XIH51zzlt2AXqf8IkYxf | Milestone | 0 | 1.10.19 | 1.10.19 |  | 2025-11-04 17:00 | q | -2812 |  | 2018-02-22 16:01
1010 | 7129 | kvNY0frGkARL99AbSHw0 | Milestone | 0 | 1.10.22 | 1.10.22 |  | 2025-05-19 17:00 | p | 1 |  | 2025-05-21 11:08

## Finish
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Finish - 1283 (60%) | Finish - 1283 (60%) | Finish - 1283 (60%) | Finish - 1283 (60%) | Finish - 1283 (60%) | Finish - 1283 (60%) | Finish - 1283 (60%) | Finish - 1283 (60%) | Finish - 1283 (60%) | Finish - 1283 (60%) | Finish - 1283 (60%) | Finish - 1283 (60%) | Finish - 1283 (60%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 1249 | v1zgYyoO7UpynPZXt29g | Summary | 611 | 1 | 1 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
2 | 147 | DEZpxiHWY7fkyvQEaEGc | Summary | 1132 | 1.2 | 1.2 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
3 | 152 | QJ29ZvAvtEjBcpqHDer1 | Milestone | 0 | 1.2.3 | 1.2.3 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
4 | 158 | D5C8AUNeoI4YKF3PggKx | Summary | 255 | 1.2.7 | 1.2.7 |  | 2026-10-08 16:58 | p | 620 |  | 2028-06-20 14:26
5 | 155 | 1yu6CrDX9QU5hWE1UWMV | Milestone | 0 | 1.2.7.11 | 1.2.7.11 |  | 2026-10-08 16:58 | p | 620 |  | 2028-06-20 14:26
6 | 166 | KkWbk0R1FXz2L56lHFvV | Normal | 2 | 1.2.7.4 | 1.2.7.4 |  | 2025-09-18 17:00 | p | 17 |  | 2025-10-06 15:42
7 | 6618 | LspmB73Oe2b9O1GVbm64 | Milestone | 0 | 1.2.7.2 | 1.2.7.2 |  | 2025-04-30 17:00 | p | 15 |  | 2025-05-16 13:13
8 | 6636 | 3J1qFTgnrSSZVnoYdTv5 | Summary | 140 | 1.2.7.3 | 1.2.7.3 |  | 2025-09-16 17:00 | p | 15 |  | 2025-10-02 14:07
9 | 6338 | whnkqeDzsaW1H7xphaZA | Normal | 49 | 1.2.7.3.4 | 1.2.7.3.4 |  | 2025-07-23 17:00 | p | 15 |  | 2025-08-08 14:24
10 | 6640 | QUv6m7GotPkUb98mhJX7 | Normal | 14 | 1.2.7.3.6 | 1.2.7.3.6 |  | 2025-09-16 17:00 | p | 15 |  | 2025-10-02 14:07
11 | 6673 | sIWmvaXMX3ZF9ctRNm7s | Normal | 34 | 1.2.7.3.3 | 1.2.7.3.3 |  | 2025-03-28 17:00 | p | 26 |  | 2025-04-24 15:12
12 | 6872 | SjyWialEYK436pEnV5Nr | Normal | 1 | 1.2.7.5 | 1.2.7.5 |  | 2025-09-19 17:00 | p | 17 |  | 2025-10-07 13:03
13 | 6874 | 1XFpbhK6U752FQe8voXZ | Normal | 1 | 1.2.7.6 | 1.2.7.6 |  | 2026-01-30 15:00 | p | 33 |  | 2026-03-04 16:32
14 | 6878 | VU7w4voCV7rMMsz4AnPW | Normal | 1 | 1.2.7.10 | 1.2.7.10 |  | 2025-05-28 17:00 | q | 0 |  | 2025-05-28 09:06
15 | 6879 | Vbp0cBOXY9azJeyTE4S4 | Normal | 3 | 1.2.7.7 | 1.2.7.7 |  | 2026-03-20 15:00 | p | 32 |  | 2026-04-22 11:45
16 | 6880 | ZuauWvCPNW7n2NMscMO2 | Normal | 4 | 1.2.7.8 | 1.2.7.8 |  | 2026-07-30 16:58 | q | 0 |  | 2026-07-30 10:58
17 | 6881 | XekYY8n1P4vELtk4BUks | Normal | 1 | 1.2.7.9 | 1.2.7.9 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
18 | 7550 | fUEnUBwdI1z3bgOngjaQ | Milestone | 0 | 1.2.7.5 | 1.2.7.5 |  | 2025-11-13 08:00 | q | -37 |  | 2025-10-06 15:42
19 | 160 | gFTVv5U5XORyz5ZEYbdN | Summary | 703 | 1.2.8 | 1.2.8 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
20 | 168 | MT1CsCIMkhjJER6f3fjG | Milestone | 0 | 1.2.8.4 | 1.2.8.4 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
21 | 5294 | A0MDYkkQxesjEWQub0UM | Milestone | 0 | 1.2.8.3 | 1.2.8.3 |  | 2025-09-18 17:00 | p | 17 |  | 2025-10-06 13:01
22 | 172 | EY5PMcgR4N5ReAIF6NHn | Summary | 582 | 1.2.9 | 1.2.9 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
23 | 173 | vJHK0TlIBzGpfYqdt8YI | Milestone | 0 | 1.2.9.4 | 1.2.9.4 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
24 | 177 | V4ys3lAm8KEbtjGqLAuR | Milestone | 0 | 1.2.9.2 | 1.2.9.2 |  | 2025-10-21 12:00 | p | 28 |  | 2025-11-19 09:32
25 | 178 | Cncpm0GACo0ppNIEy1Gp | Milestone | 0 | 1.2.9.3 | 1.2.9.3 |  | 2025-10-27 12:00 | p | 29 |  | 2025-11-25 16:19
26 | 179 | jSOjvYE1qiHOKdcV2ixu | Summary | 554 | 1.2.10 | 1.2.10 |  | 2026-09-25 17:00 | p | 104 |  | 2027-01-08 08:25
27 | 180 | 9Vp3PBZnh9TpV8TGBWRG | Milestone | 0 | 1.2.10.14 | 1.2.10.14 |  | 2026-09-25 17:00 | p | 104 |  | 2027-01-08 08:25
28 | 193 | nJh7oj8wCJYW8hyepdLI | Milestone | 0 | 1.2.10.12 | 1.2.10.12 |  | 2025-09-09 17:00 | p | 12 |  | 2025-09-22 16:40
29 | 194 | wTcNF86mfD2cPQPmQB1c | Milestone | 0 | 1.2.10.13 | 1.2.10.13 |  | 2026-04-02 17:00 | p | 84 |  | 2026-06-26 11:47
30 | 7132 | osdxrWYmqQZxyGZXe9Pr | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 2025-03-24 17:00 | q | -31 |  | 2025-02-21 16:57
31 | 7546 | tdocr3pqURBYHZWcAyMG | Normal | 1 | 1.2.10.12 | 1.2.10.12 |  | 2025-03-28 17:00 | q | -91 |  | 2024-12-27 15:38
32 | 7547 | 2p5uMAQ0v8mT9pq4KeWp | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 2025-03-14 08:00 | q | -80 |  | 2024-12-23 17:00
33 | 7548 | TdNnLE8G4vf1vBjggzLw | Normal | 1 | 1.2.10.15 | 1.2.10.15 |  | 2025-03-10 17:00 | q | -73 |  | 2024-12-27 08:56
34 | 7549 | yUAt6Fi3Vichq9Ai1DSh | Normal | 1 | 1.2.10.13 | 1.2.10.13 |  | 2025-02-20 17:00 | q | -56 |  | 2024-12-26 08:22
35 | 195 | jWoM7YMyhsN7uWtVDNIl | Summary | 276 | 1.2.11 | 1.2.11 |  | 2026-07-31 12:00 | p | 929 |  | 2029-02-14 13:47
36 | 196 | kzYOxx4jS6vhIcTyxNFn | Milestone | 0 | 1.2.11.11 | 1.2.11.11 |  | 2026-07-31 12:00 | p | 929 |  | 2029-02-14 13:47
37 | 197 | LZAvhCOF77OBkAngJSDi | Milestone | 0 | 1.2.11.1 | 1.2.11.1 |  | 2025-06-23 17:00 | p | 933 |  | 2028-01-13 14:31
38 | 198 | X7Nxs9NuQXJ5Bf6aQwVp | Milestone | 0 | 1.2.11.2 | 1.2.11.2 |  | 2025-07-08 17:00 | p | 939 |  | 2028-02-03 15:25
39 | 199 | TiaYdQ98Ovd3qBAfSAyG | Milestone | 0 | 1.2.11.3 | 1.2.11.3 |  | 2025-07-22 17:00 | p | 940 |  | 2028-02-18 16:01
40 | 200 | yynHcCtrZd0Ye6iQJb2E | Milestone | 0 | 1.2.11.4 | 1.2.11.4 |  | 2025-08-06 17:00 | p | 942 |  | 2028-03-06 16:52
41 | 202 | mjF0YLun5LIdlxtu3zFl | Milestone | 0 | 1.2.11.5 | 1.2.11.5 |  | 2025-08-26 17:00 | p | 23 |  | 2025-09-19 09:47
42 | 203 | 2a1x42QofxcVsgjcXtkr | Milestone | 0 | 1.2.11.6 | 1.2.11.6 |  | 2025-06-23 17:00 | p | 933 |  | 2028-01-13 14:31
43 | 204 | 8T22gllTunmLl2jY7IMk | Milestone | 0 | 1.2.11.7 | 1.2.11.7 |  | 2025-07-08 17:00 | p | 939 |  | 2028-02-03 15:25
44 | 205 | dm3U5Xjvi5rN2LqWegXW | Milestone | 0 | 1.2.11.8 | 1.2.11.8 |  | 2025-07-22 17:00 | p | 940 |  | 2028-02-18 16:01
45 | 206 | ZOAcdJHtChBG5MUjo5uw | Milestone | 0 | 1.2.11.9 | 1.2.11.9 |  | 2025-08-06 17:00 | p | 942 |  | 2028-03-06 16:52
46 | 209 | 0FNuAiL5ZzPZSZ3dZfoV | Milestone | 0 | 1.2.11.10 | 1.2.11.10 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
47 | 6077 | 9YjbRTuPDmKPhAucMUDE | Milestone | 0 | 1.2.6 | 1.2.6 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
48 | 7015 | U0mup1noPd6mH1CxWGtr | Milestone | 0 | 1.2.5 | 1.2.5 |  | 2027-01-01 08:05 | p | 840 |  | 2029-04-20 09:27
49 | 7016 | pVOP21cemlwRUbhUeRME | Milestone | 0 | 1.2.4 | 1.2.4 |  | 2027-01-07 16:58 | p | 529 |  | 2028-06-20 14:26
50 | 150 | 7cu6yvdJV8ndF0CYMHk8 | Milestone | 0 | 1.1 | 1.1 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
51 | 4180 | LxVAz76PSOUu8y7B8sy3 | Summary | 218 | 1.3 | 1.3 |  | 2025-12-02 17:00 | p | 16 |  | 2025-12-19 09:31
52 | 384 | GE3w1SHplCQZN7aYDVw8 | Summary | 34 | 1.3.3 | 1.3.3 |  | 2025-09-18 17:00 | p | 17 |  | 2025-10-06 13:01
53 | 429 | Pbs0MxOqvHazWgB8fpDs | Summary | 41 | 1.3.3.2 | 1.3.3.2 |  | 2025-05-12 17:00 | p | 14 |  | 2025-05-27 08:33
54 | 436 | OGXVzK31PKUn8DxCdn94 | Normal | 33 | 1.3.3.2.10 | 1.3.3.2.10 |  | 2025-05-12 17:00 | p | 14 |  | 2025-05-27 08:33
55 | 437 | kEyeaq7ebxWRSvBqGkHC | Summary | 19 | 1.3.3.1 | 1.3.3.1 |  | 2025-03-04 17:00 | p | 28 |  | 2025-04-02 11:41
56 | 438 | QjVW4dYK4boDcUrG7MUx | Summary | 23 | 1.3.3.1.2 | 1.3.3.1.2 |  | 2025-03-04 17:00 | p | 28 |  | 2025-04-02 11:41
57 | 445 | cIIfBfMFMZUbJxswwNzj | Summary | 28 | 1.3.3.1.2.4 | 1.3.3.1.2.4 |  | 2025-03-04 17:00 | p | 28 |  | 2025-04-02 11:41
58 | 6438 | sSGfho0IWOHZYw1Z8jLl | Normal | 16 | 1.3.3.1.2.4.5 | 1.3.3.1.2.4.5 |  | 2025-03-04 17:00 | p | 28 |  | 2025-04-02 11:41
59 | 5768 | 9l9o7D6Il8vKVgGgZRMW | Summary | 197 | 1.3.3.4 | 1.3.3.4 |  | 2025-09-18 17:00 | p | 17 |  | 2025-10-06 13:01
60 | 428 | pxWL5EoMWeaDmapfAV7m | Normal | 2 | 1.3.3.4.2 | 1.3.3.4.2 |  | 2025-09-18 17:00 | p | 17 |  | 2025-10-06 13:01
61 | 6289 | NknbxY1EWobhbJ98SVRq | Summary | 270 | 1.3.2 | 1.3.2 |  | 2025-12-02 17:00 | p | 16 |  | 2025-12-19 09:31
62 | 3848 | g0gBmZeXCCPZTY4kkYs8 | Summary | 210 | 1.3.2.1 | 1.3.2.1 |  | 2025-12-02 17:00 | p | 14 |  | 2025-12-17 08:23
63 | 3849 | PKYN5IsyqbTocjyswPFM | Normal | 17 | 1.3.2.1.1 | 1.3.2.1.1 |  | 2025-03-14 17:00 | p | 23 |  | 2025-04-07 16:46
64 | 3850 | sk2pEdmn2KeVBRyrQzgn | Summary | 233 | 1.3.2.1.2 | 1.3.2.1.2 |  | 2025-12-02 17:00 | p | 14 |  | 2025-12-17 08:23
65 | 3857 | FObPKa3HJ5KI4gFmAx2r | Summary | 210 | 1.3.2.1.2.2 | 1.3.2.1.2.2 |  | 2025-11-03 17:00 | p | 43 |  | 2025-12-17 08:23
66 | 3858 | pWvg9Owxac1jXAINT5hs | Normal | 24 | 1.3.2.1.2.2.1 | 1.3.2.1.2.2.1 |  | 2025-03-14 17:00 | p | 23 |  | 2025-04-07 08:26
67 | 3859 | xrpLG6wlwOL4sRwHPU5B | Normal | 28 | 1.3.2.1.2.2.2 | 1.3.2.1.2.2.2 |  | 2025-04-23 17:00 | p | 21 |  | 2025-05-15 16:03
68 | 3861 | rvfyADOJtzNcPT3VL85f | Normal | 100 | 1.3.2.1.2.2.3 | 1.3.2.1.2.2.3 |  | 2025-10-03 17:00 | p | 46 |  | 2025-11-19 09:25
69 | 3862 | FUtleP4nAJHYxzLOWKZH | Normal | 20 | 1.3.2.1.2.2.4 | 1.3.2.1.2.2.4 |  | 2025-11-03 17:00 | p | 43 |  | 2025-12-17 08:23
70 | 3863 | WaF24jcpD2qzV3M05hSl | Summary | 178 | 1.3.2.1.2.3 | 1.3.2.1.2.3 |  | 2025-12-02 17:00 | p | 12 |  | 2025-12-15 14:11
71 | 3864 | kkmwKYrSq6DehQmbGkxo | Summary | 90 | 1.3.2.1.2.3.2 | 1.3.2.1.2.3.2 |  | 2025-12-02 17:00 | p | 12 |  | 2025-12-15 14:11
72 | 3865 | ZK3GDclfde20Vh8DU71K | Normal | 30 | 1.3.2.1.2.3.2.1 | 1.3.2.1.2.3.2.1 |  | 2025-09-04 17:00 | p | 19 |  | 2025-09-24 11:48
73 | 3866 | 8Zrc7ItBhrTjO1TWxqmf | Normal | 20 | 1.3.2.1.2.3.2.2 | 1.3.2.1.2.3.2.2 |  | 2025-10-02 17:00 | p | 14 |  | 2025-10-17 08:06
74 | 3867 | l8TRHVr9p6bfQBwzbTty | Normal | 5 | 1.3.2.1.2.3.2.5 | 1.3.2.1.2.3.2.5 |  | 2025-11-07 17:00 | p | 17 |  | 2025-11-25 09:06
75 | 3868 | NCkZSbtMfUxIg95lxXXn | Normal | 10 | 1.3.2.1.2.3.2.6 | 1.3.2.1.2.3.2.6 |  | 2025-11-24 17:00 | p | 13 |  | 2025-12-08 14:21
76 | 3869 | wbVbYxDNomEEsv0XDKnQ | Normal | 5 | 1.3.2.1.2.3.2.7 | 1.3.2.1.2.3.2.7 |  | 2025-12-02 17:00 | p | 12 |  | 2025-12-15 14:11
77 | 6562 | Z3AfJmLBpOLyJb1GhvwC | Normal | 10 | 1.3.2.1.2.3.2.3 | 1.3.2.1.2.3.2.3 |  | 2025-10-17 17:00 | p | 12 |  | 2025-10-30 14:23
78 | 6563 | 7FPcbor42GN7O6Ym4IZM | Normal | 10 | 1.3.2.1.2.3.2.4 | 1.3.2.1.2.3.2.4 |  | 2025-10-31 17:00 | p | 16 |  | 2025-11-17 16:33
79 | 7186 | ttl1FahPn0WwOuyGdmk6 | Summary | 138 | 1.3.2.3 | 1.3.2.3 |  | 2025-11-26 17:00 | p | 22 |  | 2025-12-19 09:31
80 | 7188 | yn5QOVI2BZ7jor10JaQN | Summary | 55 | 1.3.2.3.2 | 1.3.2.3.2 |  | 2025-05-16 17:00 | q | 0 |  | 2025-05-16 10:05
81 | 7189 | jup7puBG1dNvbV8jB14f | Summary | 69 | 1.3.2.3.2.1 | 1.3.2.3.2.1 |  | 2025-05-16 17:00 | q | -14 |  | 2025-05-02 15:39
82 | 7190 | Ob13piboJI4zFNOVPzZD | Summary | 50 | 1.3.2.3.2.1.1 | 1.3.2.3.2.1.1 |  | 2025-03-10 17:00 | q | -24 |  | 2025-02-14 10:33
83 | 7192 | rcBSOCAYFUxP7jsyoqGw | Normal | 11 | 1.3.2.3.2.1.1.2 | 1.3.2.3.2.1.1.2 |  | 2025-03-10 17:00 | q | -24 |  | 2025-02-14 10:33
84 | 7193 | hzdeRXxytBFeNJPq5eHn | Summary | 50 | 1.3.2.3.2.1.2 | 1.3.2.3.2.1.2 |  | 2025-04-21 17:00 | q | -32 |  | 2025-03-20 13:33
85 | 7194 | mB0uoGZ1D1fuFzk350Kb | Normal | 30 | 1.3.2.3.2.1.2.1 | 1.3.2.3.2.1.2.1 |  | 2025-04-21 17:00 | q | -32 |  | 2025-03-20 13:33
86 | 7196 | fFBpC2vR2qp5KXHLtypR | Summary | 23 | 1.3.2.3.2.1.3 | 1.3.2.3.2.1.3 |  | 2025-03-10 17:00 | p | 27 |  | 2025-04-07 15:15
87 | 7199 | G7LfPy6euQCIQjteO0x8 | Normal | 20 | 1.3.2.3.2.1.3.3 | 1.3.2.3.2.1.3.3 |  | 2025-03-10 17:00 | p | 27 |  | 2025-04-07 15:15
88 | 7200 | 7Va2LPPEsZrLZmgpV2qc | Summary | 19 | 1.3.2.3.2.1.4 | 1.3.2.3.2.1.4 |  | 2025-05-16 17:00 | q | -14 |  | 2025-05-02 15:39
89 | 7201 | UKbpgMkpfrIPVoEOJEeO | Normal | 10 | 1.3.2.3.2.1.4.1 | 1.3.2.3.2.1.4.1 |  | 2025-05-05 17:00 | q | -14 |  | 2025-04-21 10:40
90 | 7202 | vy1jnuopIHJe5PhTsUNw | Normal | 5 | 1.3.2.3.2.1.4.2 | 1.3.2.3.2.1.4.2 |  | 2025-05-12 17:00 | q | -14 |  | 2025-04-28 14:19
91 | 7203 | KqVHIBvrHNAu5GlarotD | Normal | 3 | 1.3.2.3.2.1.4.3 | 1.3.2.3.2.1.4.3 |  | 2025-05-15 17:00 | q | -14 |  | 2025-05-01 15:00
92 | 7204 | BUAmcwglNtP3GEkJsPLR | Normal | 1 | 1.3.2.3.2.1.4.4 | 1.3.2.3.2.1.4.4 |  | 2025-05-16 17:00 | q | -14 |  | 2025-05-02 15:39
93 | 7205 | 688LmElxek6WZQ34zEgD | Summary | 40 | 1.3.2.3.2.2 | 1.3.2.3.2.2 |  | 2025-03-28 17:00 | p | 26 |  | 2025-04-24 15:38
94 | 7206 | bMXBNIC1fF7AjliDPdfr | Normal | 25 | 1.3.2.3.2.2.1 | 1.3.2.3.2.2.1 |  | 2025-03-17 17:00 | p | 27 |  | 2025-04-14 15:15
95 | 7207 | 51ZGrscW6XrNzeOMbLyw | Normal | 5 | 1.3.2.3.2.2.2 | 1.3.2.3.2.2.2 |  | 2025-03-24 17:00 | p | 24 |  | 2025-04-18 11:26
96 | 7208 | 5Vu53Z23NG8K3uSzUcYA | Normal | 3 | 1.3.2.3.2.2.3 | 1.3.2.3.2.2.3 |  | 2025-03-27 17:00 | p | 26 |  | 2025-04-23 15:28
97 | 7209 | r8OmtZddpdGbVxNEynIO | Normal | 1 | 1.3.2.3.2.2.4 | 1.3.2.3.2.2.4 |  | 2025-03-28 17:00 | p | 26 |  | 2025-04-24 15:38
98 | 7210 | 5vpOUfvEpSU2AKPwltv0 | Summary | 14 | 1.3.2.3.2.3 | 1.3.2.3.2.3 |  | 2025-02-28 17:00 | q | -1 |  | 2025-02-27 10:09
99 | 7212 | IA5BwO4PzPuXs5yI3XzH | Normal | 5 | 1.3.2.3.2.3.2 | 1.3.2.3.2.3.2 |  | 2025-02-24 17:00 | q | -3 |  | 2025-02-21 09:11
100 | 7213 | GkAhONTSL0EMIVzc5bXh | Normal | 3 | 1.3.2.3.2.3.3 | 1.3.2.3.2.3.3 |  | 2025-02-27 17:00 | q | -1 |  | 2025-02-26 09:58
101 | 7214 | ysGFXohNyFRFQ06jmkjW | Normal | 1 | 1.3.2.3.2.3.4 | 1.3.2.3.2.3.4 |  | 2025-02-28 17:00 | q | -1 |  | 2025-02-27 10:09
102 | 7215 | a8OJFGtOVEyM75c9puYK | Summary | 34 | 1.3.2.3.2.4 | 1.3.2.3.2.4 |  | 2025-03-28 17:00 | p | 11 |  | 2025-04-09 09:47
103 | 7220 | nvywSXdnd0LSUGSiB3or | Normal | 10 | 1.3.2.3.2.4.5 | 1.3.2.3.2.4.5 |  | 2025-02-27 17:00 | p | 3 |  | 2025-03-03 15:22
104 | 7221 | PYoR7OoHLcblZDJJ1hTC | Normal | 20 | 1.3.2.3.2.4.6 | 1.3.2.3.2.4.6 |  | 2025-03-27 17:00 | p | 11 |  | 2025-04-08 09:39
105 | 7222 | W1KVKgORO9KqmU1uQFqG | Normal | 1 | 1.3.2.3.2.4.7 | 1.3.2.3.2.4.7 |  | 2025-03-28 17:00 | p | 11 |  | 2025-04-09 09:47
106 | 7223 | 2cLCJpvBPh4ccgbvKrEi | Summary | 38 | 1.3.2.3.2.5 | 1.3.2.3.2.5 |  | 2025-04-07 17:00 | p | 38 |  | 2025-05-16 10:05
107 | 7227 | QiFvht1v2EB9ODLdNK6M | Normal | 25 | 1.3.2.3.2.5.4 | 1.3.2.3.2.5.4 |  | 2025-03-17 17:00 | p | 35 |  | 2025-04-22 16:25
108 | 7228 | SSqxRWtJ8NkhLwkx3Zp5 | Normal | 15 | 1.3.2.3.2.5.5 | 1.3.2.3.2.5.5 |  | 2025-04-07 17:00 | p | 38 |  | 2025-05-16 10:05
109 | 7514 | 4jhJaLUHxegkfPxUyChC | Normal | 15 | 1.3.2.3.2.5.9 | 1.3.2.3.2.5.9 |  | 2025-03-10 17:00 | q | -3 |  | 2025-03-07 14:10
110 | 7231 | Kz2H44CrN943Xn6RI0Et | Summary | 19 | 1.3.2.3.3 | 1.3.2.3.3 |  | 2025-08-19 17:00 | p | 16 |  | 2025-09-05 14:36
111 | 7232 | cCMYeGs7uzTIiiDhvAui | Summary | 12 | 1.3.2.3.3.1 | 1.3.2.3.3.1 |  | 2025-08-08 17:00 | p | 17 |  | 2025-08-26 10:04
112 | 7233 | rgerXXfH5cOVWHlSbXtk | Normal | 2 | 1.3.2.3.3.1.1 | 1.3.2.3.3.1.1 |  | 2025-07-25 17:00 | p | 17 |  | 2025-08-12 11:23
113 | 7234 | 4Nk8AWONEAABjENRSl4s | Normal | 3 | 1.3.2.3.3.1.2 | 1.3.2.3.3.1.2 |  | 2025-07-28 17:00 | p | 15 |  | 2025-08-13 16:17
114 | 7235 | uR7e5eYUOS8ur8CkZgir | Normal | 2 | 1.3.2.3.3.1.3 | 1.3.2.3.3.1.3 |  | 2025-07-30 17:00 | p | 18 |  | 2025-08-18 09:29
115 | 7236 | OqdHv6QLhEyFdmarh5Mg | Normal | 5 | 1.3.2.3.3.1.4 | 1.3.2.3.3.1.4 |  | 2025-07-30 17:00 | p | 18 |  | 2025-08-18 13:54
116 | 7237 | xLl9f1S8pVLgozw4LZw4 | Normal | 10 | 1.3.2.3.3.1.5 | 1.3.2.3.3.1.5 |  | 2025-08-06 17:00 | p | 14 |  | 2025-08-21 10:04
117 | 7238 | hj0QAuvemNr4BSx0wqCM | Normal | 10 | 1.3.2.3.3.1.6 | 1.3.2.3.3.1.6 |  | 2025-08-06 17:00 | p | 15 |  | 2025-08-22 13:46
118 | 7239 | sGRMuNmZsu5Ap3rRR6Ja | Normal | 2 | 1.3.2.3.3.1.7 | 1.3.2.3.3.1.7 |  | 2025-08-08 17:00 | p | 17 |  | 2025-08-26 10:04
119 | 7240 | jJgg05qz3M4QbDAQ4nmn | Summary | 7 | 1.3.2.3.3.2 | 1.3.2.3.3.2 |  | 2025-08-19 17:00 | p | 16 |  | 2025-09-05 14:36
120 | 7241 | RP09WyAKLetAyeWXIWbd | Normal | 1 | 1.3.2.3.3.2.1 | 1.3.2.3.3.2.1 |  | 2025-08-11 17:00 | p | 15 |  | 2025-08-27 11:29
121 | 7242 | PNiOufePi0cnwKsaAHa8 | Normal | 3 | 1.3.2.3.3.2.2 | 1.3.2.3.3.2.2 |  | 2025-08-14 17:00 | p | 18 |  | 2025-09-02 09:31
122 | 7243 | nppwsC1hz1MTRepHit5q | Normal | 3 | 1.3.2.3.3.2.3 | 1.3.2.3.3.2.3 |  | 2025-08-19 17:00 | p | 16 |  | 2025-09-05 14:36
123 | 7244 | FpvbIzqyAjmrguHRtjoA | Summary | 68 | 1.3.2.3.4 | 1.3.2.3.4 |  | 2025-11-26 17:00 | p | 22 |  | 2025-12-19 09:31
124 | 7245 | ysJ2Wz17vAaH50NFOd3r | Normal | 2 | 1.3.2.3.4.1 | 1.3.2.3.4.1 |  | 2025-08-21 17:00 | p | 19 |  | 2025-09-10 10:05
125 | 7246 | w8OYvCOBO1azAOar59yv | Normal | 3 | 1.3.2.3.4.2 | 1.3.2.3.4.2 |  | 2025-08-22 17:00 | p | 18 |  | 2025-09-10 09:32
126 | 7247 | QmLDbLdk9YgltF6FQxKi | Normal | 2 | 1.3.2.3.4.3 | 1.3.2.3.4.3 |  | 2025-08-26 17:00 | p | 16 |  | 2025-09-12 09:49
127 | 7248 | nqyBToLUXvLl91VDFcK9 | Summary | 20 | 1.3.2.3.4.4 | 1.3.2.3.4.4 |  | 2025-09-17 17:00 | p | 19 |  | 2025-10-07 14:40
128 | 7249 | T3rEQsXy5TFYVzdnmRkQ | Normal | 20 | 1.3.2.3.4.4.1 | 1.3.2.3.4.4.1 |  | 2025-09-17 17:00 | p | 15 |  | 2025-10-03 15:17
129 | 7250 | G5mdz8DmOa8TGNlmxmOk | Normal | 20 | 1.3.2.3.4.4.2 | 1.3.2.3.4.4.2 |  | 2025-09-17 17:00 | p | 19 |  | 2025-10-07 14:40
130 | 7251 | p2IEwFFq1YxDgQwaqReT | Summary | 48 | 1.3.2.3.4.5 | 1.3.2.3.4.5 |  | 2025-11-26 17:00 | p | 22 |  | 2025-12-19 09:31
131 | 7252 | R4hlQqYwslHcXudIUORM | Normal | 20 | 1.3.2.3.4.5.1 | 1.3.2.3.4.5.1 |  | 2025-10-16 17:00 | p | 24 |  | 2025-11-10 09:00
132 | 7253 | 5Q6OCjUddDwnqpg2shNG | Normal | 5 | 1.3.2.3.4.5.2 | 1.3.2.3.4.5.2 |  | 2025-10-23 17:00 | p | 25 |  | 2025-11-18 09:39
133 | 7254 | aZsc8OQGYCtOtLNUDl4p | Normal | 7 | 1.3.2.3.4.5.3 | 1.3.2.3.4.5.3 |  | 2025-11-03 17:00 | p | 22 |  | 2025-11-26 15:22
134 | 7255 | GiGIxdlKVFOGW1rlVkpg | Normal | 5 | 1.3.2.3.4.5.4 | 1.3.2.3.4.5.4 |  | 2025-11-10 17:00 | p | 23 |  | 2025-12-04 15:27
135 | 7256 | ZTFxKau19KKCcFlUDIYg | Normal | 7 | 1.3.2.3.4.5.5 | 1.3.2.3.4.5.5 |  | 2025-11-20 17:00 | p | 25 |  | 2025-12-16 08:47
136 | 7257 | EmkT3sq6aGy3vx96JSsX | Normal | 3 | 1.3.2.3.4.5.6 | 1.3.2.3.4.5.6 |  | 2025-11-25 17:00 | p | 22 |  | 2025-12-18 10:41
137 | 7258 | PBxke5bv0Yk6xXbQcvVe | Normal | 1 | 1.3.2.3.4.5.7 | 1.3.2.3.4.5.7 |  | 2025-11-26 17:00 | p | 22 |  | 2025-12-19 09:31
138 | 6269 | tUCxonMalaI13D6hsUSU | Summary | 99 | 1.5 | 1.5 |  | 2026-02-02 12:00 | p | 16 |  | 2026-02-18 15:29
139 | 6278 | SNMcp7h74WVvBiN3lPNB | Summary | 66 | 1.5.6 | 1.5.6 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
140 | 605 | HP2TrbmUH5Qc4V2P2k1T | Normal | 14 | 1.5.6.1 | 1.5.6.1 |  | 2025-02-28 17:00 | p | 33 |  | 2025-04-03 08:33
141 | 620 | q8advjPa5PEndSFXJ05j | Summary | 158 | 1.5.6.6 | 1.5.6.6 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
142 | 622 | Q48N5ZSDLesB1Bsda2wx | Summary | 156 | 1.5.6.6.2 | 1.5.6.6.2 |  | 2025-10-21 12:00 | p | 28 |  | 2025-11-19 09:32
143 | 632 | tuv9OmQcJHKkVCVrbrrv | Normal | 6 | 1.5.6.6.2.8 | 1.5.6.6.2.8 |  | 2025-02-20 17:00 | p | 0 |  | 2025-02-21 10:54
144 | 633 | FgJ5XjjThZN85XQOJ0nJ | Normal | 21 | 1.5.6.6.2.10 | 1.5.6.6.2.10 |  | 2025-07-18 17:00 | p | 30 |  | 2025-08-18 13:19
145 | 634 | o4DRQRcsScdVmCSXNbxF | Normal | 10 | 1.5.6.6.2.9 | 1.5.6.6.2.9 |  | 2025-08-01 12:00 | p | 32 |  | 2025-09-02 15:12
146 | 635 | ztvy5zkS4z9HirKgvHGY | Normal | 20 | 1.5.6.6.2.11 | 1.5.6.6.2.11 |  | 2025-08-29 12:00 | p | 27 |  | 2025-09-26 11:01
147 | 636 | ZpIfqMwIaczq2BqznW2q | Normal | 6 | 1.5.6.6.2.12 | 1.5.6.6.2.12 |  | 2025-09-09 12:00 | p | 28 |  | 2025-10-08 09:26
148 | 637 | 3VAZwvp2NS6usl0wrvOM | Normal | 7 | 1.5.6.6.2.13 | 1.5.6.6.2.13 |  | 2025-09-18 12:00 | p | 31 |  | 2025-10-20 11:33
149 | 638 | 34zoFClD9RS7gLTCPZs0 | Normal | 5 | 1.5.6.6.2.14 | 1.5.6.6.2.14 |  | 2025-09-25 12:00 | p | 31 |  | 2025-10-27 11:29
150 | 640 | 10AmMHkCz4b8n0xqbyCt | Normal | 5 | 1.5.6.6.2.16 | 1.5.6.6.2.16 |  | 2025-10-02 12:00 | p | 29 |  | 2025-10-31 16:23
151 | 641 | KUqcSNVxncHPLVJNV5ca | Normal | 2 | 1.5.6.6.2.17 | 1.5.6.6.2.17 |  | 2025-10-03 17:00 | p | 31 |  | 2025-11-04 08:38
152 | 642 | chCwawHUqn0ea2ArCnKB | Normal | 0 | 1.5.6.6.2.18 | 1.5.6.6.2.18 |  | 2025-10-06 12:00 | p | 29 |  | 2025-11-04 12:00
153 | 643 | xZBRzE3QVYmQCjnzxLQv | Normal | 4 | 1.5.6.6.2.19 | 1.5.6.6.2.19 |  | 2025-10-10 12:00 | p | 31 |  | 2025-11-10 15:13
154 | 644 | tUTeQ74YpmkuuOiouSXU | Normal | 5 | 1.5.6.6.2.20 | 1.5.6.6.2.20 |  | 2025-10-20 12:00 | p | 28 |  | 2025-11-18 10:28
155 | 645 | mSrjcTZmK12EdJmOEYFi | Normal | 1 | 1.5.6.6.2.21 | 1.5.6.6.2.21 |  | 2025-10-21 12:00 | p | 28 |  | 2025-11-19 09:32
156 | 646 | Haue3rYYySw3jbXWnBeq | Normal | 3 | 1.5.6.6.3 | 1.5.6.6.3 |  | 2025-10-24 12:00 | p | 31 |  | 2025-11-24 16:06
157 | 647 | 6jlP0Y4QQ5KPQWxvolLg | Normal | 1 | 1.5.6.6.4 | 1.5.6.6.4 |  | 2025-10-27 12:00 | p | 29 |  | 2025-11-25 16:19
158 | 648 | 6WPgljRre9DjhHGVsVUH | Summary | 120 | 1.5.6.6.5 | 1.5.6.6.5 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
159 | 656 | lzPFAx9Fh8cDxyQ3uxFX | Normal | 1 | 1.5.6.6.5.3 | 1.5.6.6.5.3 |  | 2025-10-28 15:00 | p | 30 |  | 2025-11-28 09:44
160 | 657 | nePaKBbqDo6OltylvukE | Summary | 14 | 1.5.6.6.5.4 | 1.5.6.6.5.4 |  | 2025-11-18 15:00 | p | 28 |  | 2025-12-17 14:16
161 | 658 | PyBKEPMZMe2YeOC66yut | Normal | 11 | 1.5.6.6.5.4.1 | 1.5.6.6.5.4.1 |  | 2025-11-13 15:00 | p | 28 |  | 2025-12-12 13:16
162 | 664 | H1KB0K8mM12Opvc4oDP1 | Normal | 3 | 1.5.6.6.5.4.2 | 1.5.6.6.5.4.2 |  | 2025-11-18 15:00 | p | 28 |  | 2025-12-17 14:16
163 | 665 | FIEbexlYHnOcZkEBs7WM | Normal | 5 | 1.5.6.6.5.5 | 1.5.6.6.5.5 |  | 2025-11-26 15:00 | p | 30 |  | 2025-12-26 15:53
164 | 666 | OcAHNnZWZgiwxfUiheGU | Normal | 5 | 1.5.6.6.5.6 | 1.5.6.6.5.6 |  | 2025-12-04 15:00 | p | 28 |  | 2026-01-02 14:34
165 | 667 | HPj21Hyun1nWvxJOQMhf | Normal | 28 | 1.5.6.6.5.7 | 1.5.6.6.5.7 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
166 | 670 | zBtIFoyMK1KgXAv407C9 | Summary | 29 | 1.5.6.5 | 1.5.6.5 |  | 2025-11-19 15:00 | p | 29 |  | 2025-12-18 16:45
167 | 671 | ZM52W2kHJJCM7052Da3J | Normal | 2 | 1.5.6.5.2 | 1.5.6.5.2 |  | 2025-10-28 12:00 | p | 29 |  | 2025-11-26 13:52
168 | 672 | AcRvLPQ7WrNfvcLBOWzV | Normal | 1 | 1.5.6.5.3 | 1.5.6.5.3 |  | 2025-11-19 15:00 | p | 29 |  | 2025-12-18 16:45
169 | 6281 | RYPcKAyzQapOQ3GupQll | Summary | 104 | 1.5.5 | 1.5.5 |  | 2025-04-04 17:00 | p | 26 |  | 2025-05-01 16:08
170 | 1466 | LmBGiI2jXQ3lZF0l79sj | Summary | 104 | 1.5.5.1 | 1.5.5.1 |  | 2025-04-04 17:00 | p | 26 |  | 2025-05-01 16:08
171 | 1458 | W2l89btZYbaZZjxZTUR4 | Normal | 12 | 1.5.5.1.3 | 1.5.5.1.3 |  | 2025-03-05 17:00 | p | 0 |  | 2025-03-06 09:25
172 | 1459 | MxsNofofvf6CR0hsGInx | Normal | 1 | 1.5.5.1.4 | 1.5.5.1.4 |  | 2025-03-06 17:00 | p | 0 |  | 2025-03-07 09:07
173 | 1468 | 8e77YoSi4abIbMILI8hH | Normal | 5 | 1.5.5.1.5 | 1.5.5.1.5 |  | 2025-02-14 17:00 | p | 30 |  | 2025-03-17 15:37
174 | 1469 | MZooHRTMNCHrNy0nPaCQ | Normal | 1 | 1.5.5.1.6 | 1.5.5.1.6 |  | 2025-02-18 17:00 | p | 27 |  | 2025-03-18 16:39
175 | 1470 | PdTqfNwd2IKBXe26tWkB | Normal | 1 | 1.5.5.1.8 | 1.5.5.1.8 |  | 2025-03-07 17:00 | p | 25 |  | 2025-04-02 10:21
176 | 1471 | FsiT4ZMTOq9hGqZQQdYf | Normal | 11 | 1.5.5.1.9 | 1.5.5.1.9 |  | 2025-03-24 17:00 | p | 27 |  | 2025-04-21 16:39
177 | 1472 | KG0YDAdikr58WjA79FVb | Normal | 9 | 1.5.5.1.10 | 1.5.5.1.10 |  | 2025-04-04 17:00 | p | 26 |  | 2025-05-01 16:08
178 | 4584 | H2uIo7s6dGmX6mrjT7jd | Normal | 9 | 1.5.5.1.7 | 1.5.5.1.7 |  | 2025-03-03 17:00 | p | 27 |  | 2025-03-31 15:24
179 | 6292 | 1Cm9NXihvfL2WEnYcHvT | Summary | 42 | 1.5.4 | 1.5.4 |  | 2025-04-02 17:00 | p | 36 |  | 2025-05-09 13:29
180 | 3944 | HRTLaCTjRjqysGxmE6ve | Normal | 36 | 1.5.4.2 | 1.5.4.2 |  | 2025-04-01 17:00 | p | 30 |  | 2025-05-02 11:55
181 | 3945 | bJfaWXH8yBacWp0eqnXx | Normal | 1 | 1.5.4.3 | 1.5.4.3 |  | 2025-04-02 17:00 | p | 32 |  | 2025-05-05 14:25
182 | 3949 | knRWxUZkgPmXKgij09tb | Summary | 25 | 1.5.4.5 | 1.5.4.5 |  | 2025-04-02 17:00 | p | 36 |  | 2025-05-09 13:29
183 | 3950 | NJx1RMKdqhuNKRLGMSBQ | Summary | 27 | 1.5.4.5.1 | 1.5.4.5.1 |  | 2025-04-02 17:00 | p | 36 |  | 2025-05-09 13:29
184 | 3951 | BNWJw3sHADBJTHA2Ybu0 | Normal | 16 | 1.5.4.5.1.1 | 1.5.4.5.1.1 |  | 2025-03-21 17:00 | p | 38 |  | 2025-04-29 09:11
185 | 3952 | HkhDGF3pWO8GORFQnyh9 | Normal | 5 | 1.5.4.5.1.2 | 1.5.4.5.1.2 |  | 2025-03-28 17:00 | p | 38 |  | 2025-05-06 10:35
186 | 3953 | dYr7YcYkpYYUeESNUSkl | Normal | 2 | 1.5.4.5.1.3 | 1.5.4.5.1.3 |  | 2025-04-01 17:00 | p | 36 |  | 2025-05-08 11:53
187 | 3954 | r37KEs6OIDoMKT5Yz5nA | Normal | 1 | 1.5.4.5.1.4 | 1.5.4.5.1.4 |  | 2025-04-02 17:00 | p | 36 |  | 2025-05-09 13:29
188 | 3964 | ZzcX1hV2BTbfmTYJl5AE | Summary | 19 | 1.5.4.5.4 | 1.5.4.5.4 |  | 2025-03-07 17:00 | p | 38 |  | 2025-04-15 09:11
189 | 3967 | BaECEBO5p44IeRhOgeK2 | Normal | 19 | 1.5.4.5.4.3 | 1.5.4.5.4.3 |  | 2025-03-07 17:00 | p | 38 |  | 2025-04-15 09:11
190 | 5996 | M6DLFbZyZKXroBVfXncj | Summary | 19 | 1.5.4.4 | 1.5.4.4 |  | 2025-02-28 17:00 | p | 27 |  | 2025-03-28 14:33
191 | 3948 | 6ze4BjeYc1B5uifD0Fqa | Normal | 10 | 1.5.4.4.9 | 1.5.4.4.9 |  | 2025-02-25 17:00 | p | 29 |  | 2025-03-27 11:44
192 | 6202 | X3XRH6pSpuIgaacqwHSp | Normal | 14 | 1.5.4.4.10 | 1.5.4.4.10 |  | 2025-02-28 17:00 | p | 27 |  | 2025-03-28 14:33
193 | 6605 | Qtljmhuq3GHp8HrV3pPP | Normal | 6 | 1.5.4.4.7 | 1.5.4.4.7 |  | 2025-02-18 17:00 | p | 29 |  | 2025-03-20 10:14
194 | 6606 | pKonEcYtBOhP3mqLQIUx | Normal | 5 | 1.5.4.4.8 | 1.5.4.4.8 |  | 2025-02-25 17:00 | p | 29 |  | 2025-03-27 11:44
195 | 6299 | JvNaxkj9UdrgV7BcBski | Summary | 134 | 1.5.1 | 1.5.1 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
196 | 4213 | pNBoUl9px0n4wFhfXXqQ | Summary | 90 | 1.5.1.1 | 1.5.1.1 |  | 2025-06-17 17:00 | p | 33 |  | 2025-07-21 15:45
197 | 4215 | I07WrBLpDQufO3mvIdSu | Normal | 1 | 1.5.1.1.4 | 1.5.1.1.4 |  | 2025-06-17 17:00 | p | 33 |  | 2025-07-21 15:45
198 | 6444 | XymP4MvJgra2aDdoc9vw | Normal | 46 | 1.5.1.1.2 | 1.5.1.1.2 |  | 2025-04-15 17:00 | p | 19 |  | 2025-05-05 08:35
199 | 6445 | Wo6GLLiu9tXQyZ8t43hX | Normal | 43 | 1.5.1.1.3 | 1.5.1.1.3 |  | 2025-06-16 17:00 | p | 31 |  | 2025-07-18 16:22
200 | 6081 | VjHQD510O4fPJGbP9Knq | Normal | 1 | 1.5.1.2 | 1.5.1.2 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
201 | 6674 | 3EUoGYyEaAia67bx8maJ | Summary | 69 | 1.5.1.3 | 1.5.1.3 |  | 2025-05-27 17:00 | q | 0 |  | 2025-05-27 08:17
202 | 6680 | ttlvn3uwilh7nqgbHtE7 | Normal | 37 | 1.5.1.3.7 | 1.5.1.3.7 |  | 2025-04-02 17:00 | p | 32 |  | 2025-05-05 10:33
203 | 6681 | NHiN8b86HRxpkLb9JGGD | Normal | 10 | 1.5.1.3.9 | 1.5.1.3.9 |  | 2025-04-17 17:00 | p | 34 |  | 2025-05-22 09:52
204 | 6682 | 695WEwNqpcHeAbXSBRci | Normal | 2 | 1.5.1.3.10 | 1.5.1.3.10 |  | 2025-05-27 17:00 | q | 0 |  | 2025-05-27 08:17
205 | 6684 | TL3Mtv3QlGNejnoXktH7 | Normal | 1 | 1.5.1.3.8 | 1.5.1.3.8 |  | 2025-04-03 17:00 | p | 32 |  | 2025-05-06 13:11
206 | 6308 | 9d1kbrq4aHbr7FOmo76u | Summary | 27 | 1.5.2 | 1.5.2 |  | 2025-04-10 17:00 | q | -3 |  | 2025-04-07 10:08
207 | 5611 | e3AOkT5PZcArPsKmcVqB | Summary | 48 | 1.5.2.2 | 1.5.2.2 |  | 2025-04-10 17:00 | q | -3 |  | 2025-04-07 10:08
208 | 5612 | JBIAfh9fImNsEXfXoHCz | Summary | 5 | 1.5.2.2.10 | 1.5.2.2.10 |  | 2025-03-10 17:00 | q | 0 |  | 2025-03-10 10:07
209 | 5613 | cc9QdsdOkkgaQ8ateKZX | Normal | 1 | 1.5.2.2.10.1 | 1.5.2.2.10.1 |  | 2025-03-05 09:36 | q | 0 |  | 2025-03-04 10:46
210 | 5614 | COTl0owSvMhEdF9iuXCz | Normal | 0 | 1.5.2.2.10.2 | 1.5.2.2.10.2 |  | 2025-03-05 14:36 | q | 0 |  | 2025-03-04 16:11
211 | 5615 | 0lLRNnxfg3utwoPLwt26 | Normal | 2 | 1.5.2.2.10.3 | 1.5.2.2.10.3 |  | 2025-03-07 14:36 | q | 0 |  | 2025-03-06 16:11
212 | 5616 | 5Z54Ad8GhuwKLjQHaz2Y | Normal | 1 | 1.5.2.2.10.4 | 1.5.2.2.10.4 |  | 2025-03-10 14:36 | q | -2 |  | 2025-03-07 16:45
213 | 5617 | fALGtnsfw381gf0W53Ia | Normal | 0 | 1.5.2.2.10.5 | 1.5.2.2.10.5 |  | 2025-03-10 17:00 | q | 0 |  | 2025-03-10 10:07
214 | 5627 | s0vjJX7zGlVyBdE0eigo | Summary | 15 | 1.5.2.2.8 | 1.5.2.2.8 |  | 2025-03-03 17:00 | q | 0 |  | 2025-03-03 08:55
215 | 5628 | JolyrZVyKy7n75ZL5gZI | Normal | 2 | 1.5.2.2.8.1 | 1.5.2.2.8.1 |  | 2025-02-20 12:00 | q | 0 |  | 2025-02-20 11:50
216 | 5629 | ghMhRqrbgVxCQv51dU2T | Normal | 0 | 1.5.2.2.8.2 | 1.5.2.2.8.2 |  | 2025-02-20 17:00 | p | 0 |  | 2025-02-21 08:01
217 | 5630 | eU3bwvC6wgraOvc5hiLt | Milestone | 0 | 1.5.2.2.8.3 | 1.5.2.2.8.3 |  | 2025-02-20 17:00 | p | 0 |  | 2025-02-21 08:01
218 | 5631 | gvTQVNdftDRXYXclyMFo | Normal | 3 | 1.5.2.2.8.4 | 1.5.2.2.8.4 |  | 2025-02-25 17:00 | q | 0 |  | 2025-02-25 15:53
219 | 5632 | DfRDIp64TG1m6LE7SSYQ | Milestone | 0 | 1.5.2.2.8.5 | 1.5.2.2.8.5 |  | 2025-02-25 17:00 | q | 0 |  | 2025-02-25 15:53
220 | 5633 | 2UPBwQymcCOUpuUjnBTe | Normal | 3 | 1.5.2.2.8.6 | 1.5.2.2.8.6 |  | 2025-02-28 17:00 | q | 0 |  | 2025-02-28 08:37
221 | 5634 | gm5pLWvICR0pU7aShOGD | Normal | 1 | 1.5.2.2.8.7 | 1.5.2.2.8.7 |  | 2025-03-03 17:00 | q | 0 |  | 2025-03-03 08:55
222 | 5635 | ZYzv9KOmVdYL2d3ZPb8b | Summary | 0 | 1.5.2.2.9 | 1.5.2.2.9 |  | 2025-02-03 12:00 | p | 1 |  | 2025-02-04 16:37
223 | 5638 | jBSFjjY1RfmWgqa8tOlO | Normal | 0 | 1.5.2.2.9.3 | 1.5.2.2.9.3 |  | 2025-01-24 17:00 | p | 3 |  | 2025-01-28 10:34
224 | 5639 | ymvGdGMdlU958QTwMU9V | Normal | 0 | 1.5.2.2.9.4 | 1.5.2.2.9.4 |  | 2025-01-27 12:00 | p | 1 |  | 2025-01-28 15:01
225 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | 2025-02-03 12:00 | p | 1 |  | 2025-02-04 16:37
226 | 5641 | QjWOhv4eRSTZWx0ATAUl | Normal | 23 | 1.5.2.2.11 | 1.5.2.2.11 |  | 2025-04-10 17:00 | q | -3 |  | 2025-04-07 10:08
227 | 6309 | taNk8S9bKnlDToaFycS6 | Summary | 37 | 1.5.3 | 1.5.3 |  | 2025-03-28 17:00 | p | 27 |  | 2025-04-25 11:28
228 | 5443 | L0xk8h495fvdhlwnri8N | Summary | 37 | 1.5.3.1 | 1.5.3.1 |  | 2025-03-28 17:00 | p | 27 |  | 2025-04-25 11:28
229 | 5445 | 95pLIsxhFDdrMJGVBrpQ | Summary | 35 | 1.5.3.1.2 | 1.5.3.1.2 |  | 2025-03-21 17:00 | p | 27 |  | 2025-04-18 10:47
230 | 5447 | ijJ4zfbEfOInLYX7Vu9Z | Normal | 6 | 1.5.3.1.2.2 | 1.5.3.1.2.2 |  | 2025-03-05 17:00 | p | 28 |  | 2025-04-03 13:50
231 | 5448 | cS9oDqhLQ00Df4o4XStO | Normal | 6 | 1.5.3.1.2.3 | 1.5.3.1.2.3 |  | 2025-03-13 17:00 | p | 28 |  | 2025-04-11 09:26
232 | 5449 | 6It4K5O7iZJhLoLO2jyi | Normal | 6 | 1.5.3.1.2.4 | 1.5.3.1.2.4 |  | 2025-03-21 17:00 | p | 27 |  | 2025-04-18 10:47
233 | 5450 | maMtUzorvxHWuMFIlXlq | Normal | 5 | 1.5.3.1.3 | 1.5.3.1.3 |  | 2025-03-28 17:00 | p | 27 |  | 2025-04-25 11:28
234 | 7381 | Ao7wteklS85dOuCCMM3I | Normal | 124 | 1.5.1 | 1.5.1 |  | 2026-02-02 12:00 | p | 10 |  | 2026-02-12 16:14
235 | 6270 | Wwp4MRWhcV55WleZhe1f | Summary | 288 | 1.4 | 1.4 |  | 2027-01-07 16:58 | p | 31 |  | 2027-02-08 09:57
236 | 6290 | VuOK0YK760zOpXaJ9U7h | Summary | 140 | 1.4.3 | 1.4.3 |  | 2026-10-08 16:58 | p | 12 |  | 2026-10-21 15:39
237 | 4537 | FhESv2GOKRYErv6rS2Ko | Summary | 140 | 1.4.3.1 | 1.4.3.1 |  | 2026-10-08 16:58 | p | 12 |  | 2026-10-21 15:39
238 | 576 | m8O5CFAYfVbtxxZI5qQW | Normal | 15 | 1.4.3.1.2 | 1.4.3.1.2 |  | 2025-12-04 17:00 | q | -37 |  | 2025-10-28 13:56
239 | 4536 | zU98x2LHVd7UXovDFMXu | Normal | 14 | 1.4.3.1.1 | 1.4.3.1.1 |  | 2025-02-28 17:00 | p | 32 |  | 2025-04-02 14:38
240 | 5854 | 2kqOvhRPajU4Q0ZPsUnx | Normal | 8 | 1.4.3.1.4 | 1.4.3.1.4 |  | 2026-03-13 15:00 | p | 33 |  | 2026-04-16 14:51
241 | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Normal | 49 | 1.4.3.1.5 | 1.4.3.1.5 |  | 2026-10-08 16:58 | p | 12 |  | 2026-10-21 15:39
242 | 6607 | IhYDHpDNbof6PVOjQ9lw | Normal | 4 | 1.4.3.1.3 | 1.4.3.1.3 |  | 2026-02-24 15:00 | p | 33 |  | 2026-03-30 11:05
243 | 6291 | 7X6NK9qir9GRz5m7bXmK | Summary | 297 | 1.4.1 | 1.4.1 |  | 2027-01-07 16:58 | p | 31 |  | 2027-02-08 09:57
244 | 3891 | VQVEpj4HfOnKALplb4t9 | Summary | 43 | 1.4.1.1 | 1.4.1.1 |  | 2025-03-06 17:00 | p | 26 |  | 2025-04-02 09:46
245 | 3897 | cqWsQsQWdy7etYVMNQBf | Summary | 53 | 1.4.1.1.2 | 1.4.1.1.2 |  | 2025-03-06 17:00 | p | 26 |  | 2025-04-02 09:46
246 | 3900 | fYbjIfZDvkbYu7p7dq3N | Normal | 14 | 1.4.1.1.2.3 | 1.4.1.1.2.3 |  | 2025-02-28 17:00 | p | 25 |  | 2025-03-26 16:16
247 | 3901 | Jj1toL1YzUk95oK7OfgU | Normal | 4 | 1.4.1.1.2.4 | 1.4.1.1.2.4 |  | 2025-03-06 17:00 | p | 26 |  | 2025-04-02 09:46
248 | 3902 | FL4HGNxujC5zK4lN6AVO | Summary | 30 | 1.4.1.2 | 1.4.1.2 |  | 2025-05-01 17:00 | q | -21 |  | 2025-04-10 11:58
249 | 3903 | e0nMZ5CLCmjCURLrKpol | Summary | 30 | 1.4.1.2.1 | 1.4.1.2.1 |  | 2025-05-01 17:00 | q | -21 |  | 2025-04-10 11:58
250 | 6565 | XyBOyY3JpPW2h1I7PEur | Normal | 21 | 1.4.1.2.1.5 | 1.4.1.2.1.5 |  | 2025-04-30 17:00 | q | -21 |  | 2025-04-09 11:48
251 | 6566 | gAyE6SkFHV1MNEAJitQ7 | Normal | 1 | 1.4.1.2.1.6 | 1.4.1.2.1.6 |  | 2025-05-01 17:00 | q | -21 |  | 2025-04-10 11:58
252 | 3907 | pFYLZycbgH4KMn6pLhBU | Summary | 272 | 1.4.1.3 | 1.4.1.3 |  | 2026-07-29 15:00 | p | 25 |  | 2026-08-24 10:42
253 | 3908 | y9tKov3jCEzWGyA9B1wJ | Normal | 5 | 1.4.1.3.1 | 1.4.1.3.1 |  | 2025-07-03 17:00 | q | -77 |  | 2025-04-17 14:24
254 | 3909 | VvjZ0oHXTTG06m5XlL1B | Normal | 10 | 1.4.1.3.2 | 1.4.1.3.2 |  | 2025-07-18 17:00 | q | -78 |  | 2025-05-01 14:14
255 | 3910 | pNRX5rV0uvvHnR27z1AO | Normal | 8 | 1.4.1.3.3 | 1.4.1.3.3 |  | 2026-03-13 15:00 | p | 32 |  | 2026-04-14 16:59
256 | 3911 | R3AK39H17lCC16PE9DkR | Normal | 10 | 1.4.1.3.4 | 1.4.1.3.4 |  | 2026-03-27 15:00 | p | 28 |  | 2026-04-24 15:54
257 | 3912 | BSEXS69UjCPQ6j2zF47p | Normal | 15 | 1.4.1.3.5 | 1.4.1.3.5 |  | 2026-04-17 15:00 | p | 26 |  | 2026-05-14 09:13
258 | 3913 | nUmJBAacPI2xORV8OCED | Normal | 20 | 1.4.1.3.6 | 1.4.1.3.6 |  | 2026-05-15 15:00 | p | 32 |  | 2026-06-16 16:59
259 | 3914 | e7efPn2W4IFyilt2hNai | Normal | 30 | 1.4.1.3.7 | 1.4.1.3.7 |  | 2026-06-30 15:00 | p | 23 |  | 2026-07-24 08:09
260 | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Normal | 5 | 1.4.1.3.8 | 1.4.1.3.8 |  | 2026-07-08 15:00 | p | 25 |  | 2026-08-03 08:38
261 | 3916 | xcLTkuiw0V5a2mOSGmcP | Normal | 10 | 1.4.1.3.9 | 1.4.1.3.9 |  | 2026-07-22 15:00 | p | 22 |  | 2026-08-14 14:20
262 | 3917 | hmttcJptV92JIo4OpANW | Normal | 5 | 1.4.1.3.10 | 1.4.1.3.10 |  | 2026-07-29 15:00 | p | 25 |  | 2026-08-24 10:42
263 | 3918 | VKkEEklTkhlAtqntT93x | Summary | 160 | 1.4.1.4 | 1.4.1.4 |  | 2027-01-07 16:58 | p | 31 |  | 2027-02-08 09:57
264 | 3919 | 70MdVf3krr3KZdDhEaoj | Normal | 1 | 1.4.1.4.1 | 1.4.1.4.1 |  | 2026-05-18 15:00 | p | 30 |  | 2026-06-18 09:43
265 | 3920 | mBVNyTIN7rvKyNQxzyxZ | Normal | 9 | 1.4.1.4.2 | 1.4.1.4.2 |  | 2026-06-01 15:00 | p | 30 |  | 2026-07-01 16:36
266 | 3921 | jEuseC90wYhkn0V4svXs | Normal | 3 | 1.4.1.4.3 | 1.4.1.4.3 |  | 2026-08-04 16:58 | q | 0 |  | 2026-08-04 09:54
267 | 3922 | yD55zWPn8USsNa4i8nCC | Normal | 5 | 1.4.1.4.4 | 1.4.1.4.4 |  | 2026-10-16 16:58 | p | 13 |  | 2026-10-30 14:41
268 | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Normal | 15 | 1.4.1.4.5 | 1.4.1.4.5 |  | 2026-11-06 16:58 | p | 26 |  | 2026-12-03 15:30
269 | 3924 | N1CigBiMQE2J41ZAMkt0 | Normal | 20 | 1.4.1.4.6 | 1.4.1.4.6 |  | 2026-12-08 16:58 | p | 28 |  | 2027-01-06 15:40
270 | 3925 | hSr4t1vn7GiB6Kp7YK0M | Normal | 5 | 1.4.1.4.7 | 1.4.1.4.7 |  | 2026-12-15 16:58 | p | 27 |  | 2027-01-12 15:02
271 | 3926 | vGJMK6sejFbKR6Gom2up | Normal | 5 | 1.4.1.4.8 | 1.4.1.4.8 |  | 2026-12-22 16:58 | p | 29 |  | 2027-01-21 14:26
272 | 3927 | 3RLmiC17tI4E2ggNuRe0 | Normal | 5 | 1.4.1.4.9 | 1.4.1.4.9 |  | 2026-12-30 16:58 | p | 29 |  | 2027-01-29 15:28
273 | 3928 | hCBFci3gUopMkWW2dQQj | Normal | 5 | 1.4.1.4.10 | 1.4.1.4.10 |  | 2027-01-07 16:58 | p | 31 |  | 2027-02-08 09:57
274 | 6318 | cM5VCGnPiK1mfNJo8YLF | Summary | 309 | 1.4.2 | 1.4.2 |  | 2027-01-01 08:05 | p | 5 |  | 2027-01-06 08:12
275 | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Summary | 707 | 1.4.2.2 | 1.4.2.2 |  | 2026-07-21 16:58 | q | 0 |  | 2026-07-21 13:25
276 | 5213 | 6YmlQVHNVjUNryBHQf8a | Summary | 61 | 1.4.2.2.3 | 1.4.2.2.3 |  | 2025-11-07 17:00 | q | -31 |  | 2025-10-07 11:20
277 | 5214 | KnSim1DOJ7A0BYyW8QOP | Milestone | 0 | 1.4.2.2.3.1 | 1.4.2.2.3.1 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
278 | 5215 | KawuX1icbWQB8WlKVKy9 | Normal | 60 | 1.4.2.2.3.2 | 1.4.2.2.3.2 |  | 2025-11-06 17:00 | q | -34 |  | 2025-10-03 16:30
279 | 5216 | xOecB4tLtQXauOnWGD4l | Normal | 1 | 1.4.2.2.3.3 | 1.4.2.2.3.3 |  | 2025-11-07 17:00 | q | -31 |  | 2025-10-07 11:20
280 | 5217 | e116DivbRDCkLiH2zNhl | Summary | 61 | 1.4.2.2.4 | 1.4.2.2.4 |  | 2025-11-07 17:00 | q | -21 |  | 2025-10-17 08:36
281 | 5218 | 8GMyARBjPLtiSR4txAaa | Milestone | 0 | 1.4.2.2.4.1 | 1.4.2.2.4.1 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
282 | 5219 | Uz3hspiJXkYJElXZ00I5 | Normal | 60 | 1.4.2.2.4.2 | 1.4.2.2.4.2 |  | 2025-11-06 17:00 | q | -21 |  | 2025-10-16 09:10
283 | 5220 | QAqXx5k5ldQJaugZyYbR | Normal | 1 | 1.4.2.2.4.3 | 1.4.2.2.4.3 |  | 2025-11-07 17:00 | q | -21 |  | 2025-10-17 08:36
284 | 5221 | iTaWceiQKMF6gUaF3DCB | Summary | 61 | 1.4.2.2.5 | 1.4.2.2.5 |  | 2025-11-07 17:00 | q | -28 |  | 2025-10-10 15:45
285 | 5222 | 4u5ocGGr0fcTRpzuglXZ | Milestone | 0 | 1.4.2.2.5.1 | 1.4.2.2.5.1 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
286 | 5223 | 3nEJb4lsc7akFmF6ULw7 | Normal | 60 | 1.4.2.2.5.2 | 1.4.2.2.5.2 |  | 2025-11-06 17:00 | q | -28 |  | 2025-10-09 15:42
287 | 5224 | PvORb6t1pqf23aOFbh3S | Normal | 1 | 1.4.2.2.5.3 | 1.4.2.2.5.3 |  | 2025-11-07 17:00 | q | -28 |  | 2025-10-10 15:45
288 | 5225 | b44Ij1WE7Qrra8bO7ZTN | Normal | 1 | 1.4.2.2.6 | 1.4.2.2.6 |  | 2026-07-21 16:58 | q | 0 |  | 2026-07-21 13:25
289 | 5277 | TgmqG1sR4A60sNmMtPcE | Summary | 193 | 1.4.2.2.7 | 1.4.2.2.7 |  | 2026-07-09 16:58 | q | -16 |  | 2026-06-23 15:58
290 | 5278 | OmCdw3tKtVsW24V2aNqQ | Normal | 8 | 1.4.2.2.7.1 | 1.4.2.2.7.1 |  | 2026-01-19 08:01 | q | -33 |  | 2025-12-16 08:32
291 | 5279 | htHZ3VhuaadgfKg1VQls | Summary | 47 | 1.4.2.2.7.11 | 1.4.2.2.7.11 |  | 2026-06-25 08:58 | q | -16 |  | 2026-06-09 08:39
292 | 5280 | q0a2rl5NSMPQe2o4IYAd | Normal | 3 | 1.4.2.2.7.11.1 | 1.4.2.2.7.11.1 |  | 2026-05-28 08:58 | q | -34 |  | 2026-04-23 09:05
293 | 5281 | 3GO4XZOZrW4CEje40UJT | Normal | 5 | 1.4.2.2.7.11.2 | 1.4.2.2.7.11.2 |  | 2026-04-28 08:01 | q | -21 |  | 2026-04-06 08:30
294 | 5282 | qBzS7vPbhPVzs7sVXgmM | Normal | 5 | 1.4.2.2.7.11.3 | 1.4.2.2.7.11.3 |  | 2026-05-05 08:01 | q | -5 |  | 2026-04-29 11:35
295 | 5283 | fU0pzeQGz2MN3lZmznFh | Normal | 5 | 1.4.2.2.7.11.4 | 1.4.2.2.7.11.4 |  | 2026-05-12 08:01 | q | -42 |  | 2026-03-30 09:44
296 | 5284 | epM0xPGW4QTSpblHVWYc | Normal | 10 | 1.4.2.2.7.11.5 | 1.4.2.2.7.11.5 |  | 2026-06-11 08:58 | q | -21 |  | 2026-05-20 13:10
297 | 5285 | ffNcVsnPBySsZbQiEShc | Normal | 10 | 1.4.2.2.7.11.6 | 1.4.2.2.7.11.6 |  | 2026-06-25 08:58 | q | -16 |  | 2026-06-09 08:39
298 | 5286 | Yb8sH9U5B9gBzfVjcJKN | Normal | 6 | 1.4.2.2.7.12 | 1.4.2.2.7.12 |  | 2026-07-02 16:58 | q | -16 |  | 2026-06-16 16:30
299 | 5287 | bhDhrVJ9ZVKMNyReuPKm | Normal | 5 | 1.4.2.2.7.13 | 1.4.2.2.7.13 |  | 2026-07-09 16:58 | q | -16 |  | 2026-06-23 15:58
300 | 5288 | RIVzpLwElpoiAIgfwKiL | Milestone | 0 | 1.4.2.2.7.14 | 1.4.2.2.7.14 |  | 2026-07-09 16:58 | q | -16 |  | 2026-06-23 15:58
301 | 6457 | PFYaNHtSBj97Eh5ysTvH | Normal | 7 | 1.4.2.2.7.2 | 1.4.2.2.7.2 |  | 2026-01-28 08:01 | q | -35 |  | 2025-12-23 11:39
302 | 6458 | pDFztlVdvvSj2i4Cz5Z9 | Normal | 5 | 1.4.2.2.7.3 | 1.4.2.2.7.3 |  | 2026-02-04 08:01 | q | -34 |  | 2025-12-31 11:37
303 | 6459 | ylmwXTiOnCLJpwlHTaRg | Normal | 10 | 1.4.2.2.7.4 | 1.4.2.2.7.4 |  | 2026-02-18 08:01 | q | -32 |  | 2026-01-16 09:43
304 | 6460 | CystLMJtc4xxgICiEMDQ | Normal | 8 | 1.4.2.2.7.5 | 1.4.2.2.7.5 |  | 2026-03-02 08:01 | q | -32 |  | 2026-01-28 08:58
305 | 6461 | 7ypQo0ZyAHzCHmFRlywg | Normal | 10 | 1.4.2.2.7.6 | 1.4.2.2.7.6 |  | 2026-03-16 08:01 | q | -30 |  | 2026-02-13 08:15
306 | 6462 | BWDOi71UCejcEb1fgeoY | Normal | 7 | 1.4.2.2.7.7 | 1.4.2.2.7.7 |  | 2026-03-25 08:01 | q | -29 |  | 2026-02-23 15:14
307 | 6463 | OelD6citgJccZhV0UyvH | Normal | 7 | 1.4.2.2.7.8 | 1.4.2.2.7.8 |  | 2026-04-03 08:01 | q | -28 |  | 2026-03-05 08:27
308 | 6464 | McSTYqZ3LCfaYSSmZoTn | Normal | 7 | 1.4.2.2.7.9 | 1.4.2.2.7.9 |  | 2026-04-14 08:01 | q | -31 |  | 2026-03-13 10:58
309 | 6465 | WAyiiuxKOgY7bZWYUV9d | Normal | 5 | 1.4.2.2.7.10 | 1.4.2.2.7.10 |  | 2026-04-21 08:01 | q | -31 |  | 2026-03-20 13:20
310 | 5226 | R9JO9mOSGmg0eoDimoJT | Summary | 71 | 1.4.2.1 | 1.4.2.1 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
311 | 5240 | NSmZbDTp76mGzDSQ7Ceh | Summary | 56 | 1.4.2.1.3 | 1.4.2.1.3 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
312 | 5241 | v6EKIZLcnDHW8CXOrD7y | Normal | 21 | 1.4.2.1.3.1 | 1.4.2.1.3.1 |  | 2025-06-23 17:00 | q | -237 |  | 2024-10-29 11:37
313 | 5242 | JYCfpao49G3jD8M94S66 | Normal | 10 | 1.4.2.1.3.2 | 1.4.2.1.3.2 |  | 2025-07-08 17:00 | q | -183 |  | 2025-01-06 08:46
314 | 5243 | 0XN39P602kPVdw6rXYZi | Normal | 10 | 1.4.2.1.3.3 | 1.4.2.1.3.3 |  | 2025-07-22 17:00 | q | -27 |  | 2025-06-25 08:52
315 | 5244 | Nwqnc6xsOuQ8oMDbKNfv | Normal | 15 | 1.4.2.1.3.4 | 1.4.2.1.3.4 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
316 | 5262 | PI0DE6xTKT4gLnHpqgjE | Summary | 137 | 1.4.2.1.6 | 1.4.2.1.6 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
317 | 5263 | URhzXaXmWu6rBPIMitrn | Normal | 30 | 1.4.2.1.6.1 | 1.4.2.1.6.1 |  | 2025-03-24 17:00 | p | 28 |  | 2025-04-22 14:42
318 | 5265 | ATYnDTN93dB3aTXfzslo | Normal | 6 | 1.4.2.1.6.2 | 1.4.2.1.6.2 |  | 2025-04-15 11:00 | p | 27 |  | 2025-05-13 10:18
319 | 5266 | G5H4IlBy3M3Zxs38gcIH | Normal | 10 | 1.4.2.1.6.3 | 1.4.2.1.6.3 |  | 2025-04-29 14:00 | p | 29 |  | 2025-05-29 10:56
320 | 5267 | 3RI5G3ymKjaLn96cfboa | Normal | 11 | 1.4.2.1.6.4 | 1.4.2.1.6.4 |  | 2025-05-13 14:00 | p | 20 |  | 2025-06-02 15:18
321 | 5268 | fG9nayiE82fFlNFtuyfN | Normal | 8 | 1.4.2.1.6.5 | 1.4.2.1.6.5 |  | 2025-06-12 17:00 | p | 20 |  | 2025-07-03 08:50
322 | 5269 | UP8sWsDXCDMiwOqWz3ib | Normal | 5 | 1.4.2.1.6.6 | 1.4.2.1.6.6 |  | 2025-07-25 09:00 | q | -38 |  | 2025-06-16 11:06
323 | 5270 | 0UA65kBzwzHULCayr1Gq | Normal | 8 | 1.4.2.1.6.7 | 1.4.2.1.6.7 |  | 2025-08-08 08:30 | q | -38 |  | 2025-06-30 09:21
324 | 5271 | mtztJWmm2OBnfmSsuoGt | Normal | 10 | 1.4.2.1.6.8 | 1.4.2.1.6.8 |  | 2025-08-22 08:30 | q | -36 |  | 2025-07-16 08:39
325 | 5272 | kvS9pO69DNwaLvofAQcb | Normal | 11 | 1.4.2.1.6.9 | 1.4.2.1.6.9 |  | 2025-09-09 08:30 | q | -33 |  | 2025-08-06 13:53
326 | 5273 | fGHKYfAaAseAkWqOpGpv | Normal | 10 | 1.4.2.1.6.10 | 1.4.2.1.6.10 |  | 2025-09-23 08:30 | q | -33 |  | 2025-08-20 11:00
327 | 5274 | zjsmmZ1Zvuz0mxAk4wzH | Normal | 10 | 1.4.2.1.6.11 | 1.4.2.1.6.11 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
328 | 5275 | lBTJLZ8EG6vqarjSz7m6 | Milestone | 0 | 1.4.2.1.6.12 | 1.4.2.1.6.12 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
329 | 5264 | 2BYRPY9ftrCpjg2j3vxJ | Milestone | 0 | 1.4.2.1.8 | 1.4.2.1.8 |  | 2025-02-21 08:00 | q | -328 |  | 2024-03-29 17:00
330 | 5276 | yja2Gk0YbNXya3vsxrwh | Milestone | 0 | 1.4.2.1.7 | 1.4.2.1.7 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
331 | 5289 | tqKGxL2oceRufkd47wnf | Summary | 319 | 1.4.2.3 | 1.4.2.3 |  | 2027-01-01 08:05 | p | 5 |  | 2027-01-06 08:12
332 | 5290 | NEvSl0zKCrGJ6lqshTZO | Milestone | 0 | 1.4.2.3.1 | 1.4.2.3.1 |  | 2025-11-07 17:00 | q | -28 |  | 2025-10-10 15:45
333 | 5313 | 3y8KKUl940HiJi7UFKFT | Summary | 106 | 1.4.2.3.3 | 1.4.2.3.3 |  | 2027-01-01 08:05 | p | 5 |  | 2027-01-06 08:12
334 | 5314 | SRtjKDi8lC5PBWdNdIAU | Normal | 10 | 1.4.2.3.3.1 | 1.4.2.3.3.1 |  | 2026-08-19 16:58 | q | 0 |  | 2026-08-19 13:44
335 | 5316 | LCfcLPfxTjnSY0dCrjlE | Normal | 10 | 1.4.2.3.3.2 | 1.4.2.3.3.2 |  | 2026-09-16 11:59 | q | 0 |  | 2026-09-16 10:06
336 | 5317 | pw6YyMXR7oeqsrtIHdqo | Normal | 9 | 1.4.2.3.3.3 | 1.4.2.3.3.3 |  | 2026-10-09 10:08 | p | 0 |  | 2026-10-09 11:37
337 | 5318 | KMG5hXAC4X2MZPfyVOSc | Normal | 5 | 1.4.2.3.3.8 | 1.4.2.3.3.8 |  | 2026-11-13 10:08 | p | 3 |  | 2026-11-16 11:36
338 | 5319 | mDGXCmTQB2ITo8MYwlYq | Normal | 5 | 1.4.2.3.3.9 | 1.4.2.3.3.9 |  | 2026-11-20 10:08 | p | 3 |  | 2026-11-24 08:25
339 | 5320 | hu6UActfLD0rLfdNqC55 | Normal | 5 | 1.4.2.3.3.10 | 1.4.2.3.3.10 |  | 2026-11-27 10:08 | p | 3 |  | 2026-12-01 08:22
340 | 5321 | pG9QTaeiPcJe7Bm3iI1s | Normal | 5 | 1.4.2.3.3.11 | 1.4.2.3.3.11 |  | 2026-12-04 10:08 | p | 4 |  | 2026-12-08 11:18
341 | 5322 | oNpYocgOFdrRcJiQE0H5 | Normal | 5 | 1.4.2.3.3.12 | 1.4.2.3.3.12 |  | 2026-12-11 10:08 | p | 4 |  | 2026-12-16 08:59
342 | 5323 | Tt5dEbDabBigq84Eat5c | Normal | 5 | 1.4.2.3.3.13 | 1.4.2.3.3.13 |  | 2026-12-18 10:08 | p | 5 |  | 2026-12-23 10:18
343 | 5324 | INz2wzhVzgQCZLXqwTZc | Normal | 5 | 1.4.2.3.3.14 | 1.4.2.3.3.14 |  | 2026-12-31 08:05 | p | 5 |  | 2027-01-05 08:10
344 | 5325 | D5c4JntP5EU4thbOE4hi | Normal | 1 | 1.4.2.3.3.15 | 1.4.2.3.3.15 |  | 2027-01-01 08:05 | p | 5 |  | 2027-01-06 08:12
345 | 6467 | n3qEWBmgcrCNzbacKk03 | Normal | 5 | 1.4.2.3.3.4 | 1.4.2.3.3.4 |  | 2026-10-16 10:08 | p | 0 |  | 2026-10-16 11:31
346 | 6468 | BqsEZH5IWCI59bWKml0D | Normal | 5 | 1.4.2.3.3.5 | 1.4.2.3.3.5 |  | 2026-10-23 10:08 | p | 0 |  | 2026-10-23 15:39
347 | 6469 | TtC6fzAb8zClFAVfKkP8 | Normal | 5 | 1.4.2.3.3.6 | 1.4.2.3.3.6 |  | 2026-10-30 10:08 | p | 0 |  | 2026-10-30 15:11
348 | 6470 | UrgnPc0HjVwpN7twGsWX | Normal | 5 | 1.4.2.3.3.7 | 1.4.2.3.3.7 |  | 2026-11-06 10:08 | p | 0 |  | 2026-11-06 15:15
349 | 5326 | esDa5lJIA5zg0nP58cRd | Summary | 32 | 1.4.2.3.4 | 1.4.2.3.4 |  | 2025-11-24 08:30 | q | -38 |  | 2025-10-16 13:50
350 | 5327 | iRZmxts3rKQ38tplQw52 | Normal | 30 | 1.4.2.3.4.1 | 1.4.2.3.4.1 |  | 2025-11-20 08:30 | q | -36 |  | 2025-10-14 11:56
351 | 5328 | ngeJL3ilFttQtHxnOEwX | Normal | 1 | 1.4.2.3.4.2 | 1.4.2.3.4.2 |  | 2025-11-21 08:30 | q | -36 |  | 2025-10-15 13:36
352 | 5329 | GYUaK0PI1fV4kag2egD8 | Normal | 1 | 1.4.2.3.4.3 | 1.4.2.3.4.3 |  | 2025-11-24 08:30 | q | -38 |  | 2025-10-16 13:50
353 | 6321 | KAyzIHlSkkFZqIIdJ9JD | Summary | 144 | 1.4.2.3.2 | 1.4.2.3.2 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
354 | 5298 | c4SSanbHhynqs8RkqT3I | Normal | 3 | 1.4.2.3.2.2 | 1.4.2.3.2.2 |  | 2026-02-03 15:00 | p | 33 |  | 2026-03-09 14:34
355 | 5299 | HB5wL9z8KlZFeAas0WUQ | Normal | 11 | 1.4.2.3.2.3 | 1.4.2.3.2.3 |  | 2026-02-18 15:00 | p | 33 |  | 2026-03-24 09:15
356 | 5301 | hHw9byxBfgMW8zXuSsdj | Milestone | 0 | 1.4.2.3.2.12 | 1.4.2.3.2.12 |  | 2026-04-02 15:00 | p | 33 |  | 2026-05-05 15:37
357 | 5302 | 2rc67Y2hzAhRvE7YihWA | Normal | 10 | 1.4.2.3.2.1 | 1.4.2.3.2.1 |  | 2026-01-29 15:00 | p | 33 |  | 2026-03-03 15:34
358 | 5303 | SgeIRg4ykwxbNqD9urWV | Normal | 2 | 1.4.2.3.2.8 | 1.4.2.3.2.8 |  | 2026-03-24 15:00 | p | 30 |  | 2026-04-24 14:59
359 | 5304 | KRXQrBZsFBKS9k4FvAsp | Normal | 3 | 1.4.2.3.2.9 | 1.4.2.3.2.9 |  | 2026-03-27 15:00 | p | 33 |  | 2026-04-29 15:04
360 | 5305 | TyGQYH0bANBrFjXmh15D | Normal | 2 | 1.4.2.3.2.10 | 1.4.2.3.2.10 |  | 2026-03-31 15:00 | p | 31 |  | 2026-05-01 16:04
361 | 5306 | yar7ts7ASIpTQqyvnwQd | Normal | 5 | 1.4.2.3.2.13 | 1.4.2.3.2.13 |  | 2026-04-09 15:00 | p | 34 |  | 2026-05-14 08:39
362 | 5307 | yRByGMPgEQcCecr5HzAA | Normal | 2 | 1.4.2.3.2.15 | 1.4.2.3.2.15 |  | 2026-04-14 15:00 | p | 38 |  | 2026-05-22 15:08
363 | 5308 | JBAsTSNPb9OQmIAmtadV | Normal | 20 | 1.4.2.3.2.17 | 1.4.2.3.2.17 |  | 2026-05-19 08:01 | p | 49 |  | 2026-07-07 09:10
364 | 5309 | xRRT514kq8kwyv7njrs5 | Normal | 5 | 1.4.2.3.2.19 | 1.4.2.3.2.19 |  | 2026-07-16 16:58 | q | 0 |  | 2026-07-16 10:39
365 | 5310 | RMnJ5j2lLGlokfxLAfSa | Normal | 2 | 1.4.2.3.2.20 | 1.4.2.3.2.20 |  | 2026-07-20 16:58 | q | 0 |  | 2026-07-20 11:30
366 | 5311 | BowxNbb4uXSnAk8z8ZkC | Normal | 2 | 1.4.2.3.2.22 | 1.4.2.3.2.22 |  | 2026-07-22 16:58 | q | 0 |  | 2026-07-22 14:13
367 | 5312 | mmXMEY1kphvE51vXPbq6 | Milestone | 0 | 1.4.2.3.2.25 | 1.4.2.3.2.25 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
368 | 6516 | qmbk7ROGAo4AwJOySAlG | Normal | 4 | 1.4.2.3.2.4 | 1.4.2.3.2.4 |  | 2026-02-24 15:00 | p | 31 |  | 2026-03-27 16:17
369 | 6517 | YGaikKlMVGc6fqtUBZ7h | Normal | 5 | 1.4.2.3.2.5 | 1.4.2.3.2.5 |  | 2026-03-03 15:00 | p | 30 |  | 2026-04-03 13:41
370 | 6518 | 0rDsNLFYCabTnyCcopAQ | Normal | 8 | 1.4.2.3.2.6 | 1.4.2.3.2.6 |  | 2026-03-13 15:00 | p | 32 |  | 2026-04-15 13:51
371 | 6519 | UldK3RoYRJH5Hsfv02Lh | Normal | 2 | 1.4.2.3.2.7 | 1.4.2.3.2.7 |  | 2026-03-17 15:00 | p | 30 |  | 2026-04-17 09:06
372 | 6520 | UaqqB30tdDFCsCHRRpeh | Normal | 2 | 1.4.2.3.2.11 | 1.4.2.3.2.11 |  | 2026-04-02 15:00 | p | 33 |  | 2026-05-05 15:37
373 | 6521 | LDY9CVOjImzsQ4NE65Qz | Normal | 1 | 1.4.2.3.2.16 | 1.4.2.3.2.16 |  | 2026-04-15 15:00 | p | 40 |  | 2026-05-25 16:19
374 | 6522 | WYJvDx3FrKALT2lj4FIo | Normal | 2 | 1.4.2.3.2.18 | 1.4.2.3.2.18 |  | 2026-05-21 08:01 | p | 49 |  | 2026-07-09 10:39
375 | 6523 | TvM5XBX3OaVljTSOZ4e2 | Normal | 2 | 1.4.2.3.2.21 | 1.4.2.3.2.21 |  | 2026-07-20 16:58 | q | 0 |  | 2026-07-20 14:13
376 | 6524 | cvaJgvK8KpGYV8ykH12h | Normal | 2 | 1.4.2.3.2.23 | 1.4.2.3.2.23 |  | 2026-07-24 16:58 | q | 0 |  | 2026-07-24 15:08
377 | 6525 | GtEwLNkefPtnncnl90X4 | Normal | 3 | 1.4.2.3.2.24 | 1.4.2.3.2.24 |  | 2026-08-04 16:58 | q | 0 |  | 2026-08-04 11:54
378 | 6873 | gSZIbC6fsU6IM6McOJy8 | Normal | 1 | 1.4.2.3.2.14 | 1.4.2.3.2.14 |  | 2026-04-10 15:00 | p | 34 |  | 2026-05-15 09:22
379 | 6271 | Q6QswYSvhipRUbZBXuiu | Summary | 315 | 1.6 | 1.6 |  | 2026-11-10 17:00 | p | 100 |  | 2027-02-19 10:11
380 | 6277 | moVS9Ou3GclDwNSW1OnS | Summary | 264 | 1.6.7 | 1.6.7 |  | 2026-09-29 17:00 | p | 104 |  | 2027-01-12 08:36
381 | 678 | N57z7OkXN935WcKbC4jO | Normal | 1 | 1.6.7.2 | 1.6.7.2 |  | 2026-03-26 17:00 | p | 75 |  | 2026-06-10 09:28
382 | 700 | PZaQwD8fp0dlxZIxEZEd | Normal | 279 | 1.6.7.10 | 1.6.7.10 |  | 2026-03-23 17:00 | p | 92 |  | 2026-06-24 13:57
383 | 728 | 4dRz6TQj3FOK8lstTqZK | Summary | 396 | 1.6.7.9 | 1.6.7.9 |  | 2026-03-31 17:00 | p | 75 |  | 2026-06-15 09:17
384 | 741 | cktDjgZ5bp36SrQnCM1w | Summary | 458 | 1.6.7.9.3 | 1.6.7.9.3 |  | 2026-03-31 17:00 | p | 75 |  | 2026-06-15 09:17
385 | 751 | AADJzuTGAb4gWytj7CQi | Normal | 18 | 1.6.7.9.3.8 | 1.6.7.9.3.8 |  | 2025-09-02 17:00 | p | 13 |  | 2025-09-16 11:56
386 | 752 | r0c0rFS4EkOGynasmiCG | Normal | 36 | 1.6.7.9.3.7 | 1.6.7.9.3.7 |  | 2025-08-26 17:00 | p | 23 |  | 2025-09-19 09:47
387 | 759 | cZuo3MY7iyDrOJC1qVJx | Normal | 5 | 1.6.7.9.3.9 | 1.6.7.9.3.9 |  | 2025-09-09 17:00 | p | 12 |  | 2025-09-22 16:40
388 | 765 | qOEfFivvitnF8cw9csOP | Normal | 1 | 1.6.7.9.3.13 | 1.6.7.9.3.13 |  | 2026-03-26 17:00 | p | 75 |  | 2026-06-10 09:42
389 | 5773 | OCcI80TDGF8LlIXj66uV | Normal | 3 | 1.6.7.9.3.14 | 1.6.7.9.3.14 |  | 2026-03-31 17:00 | p | 75 |  | 2026-06-15 09:17
390 | 6323 | aU24Z8SrLl20SyyllZuy | Summary | 80 | 1.6.7.9.3.5 | 1.6.7.9.3.5 |  | 2025-04-16 17:00 | q | -5 |  | 2025-04-11 09:33
391 | 745 | aO52oWR4hBrrP5GVCo2a | Normal | 11 | 1.6.7.9.3.5.2 | 1.6.7.9.3.5.2 |  | 2025-03-31 17:00 | q | -4 |  | 2025-03-27 10:10
392 | 746 | qMC0J8brk1dsdpzlKrk7 | Normal | 12 | 1.6.7.9.3.5.3 | 1.6.7.9.3.5.3 |  | 2025-04-16 17:00 | q | -5 |  | 2025-04-11 09:33
393 | 6324 | gthK0FxwJBk3laTELp8O | Summary | 45 | 1.6.7.9.3.6 | 1.6.7.9.3.6 |  | 2025-07-07 17:00 | p | 14 |  | 2025-07-22 13:22
394 | 747 | nul8vpOEtI2Q6W5Q0Qo9 | Normal | 12 | 1.6.7.9.3.6.1 | 1.6.7.9.3.6.1 |  | 2025-05-16 17:00 | p | 18 |  | 2025-06-04 15:23
395 | 748 | M1HHh2K01o23jS8vpDxS | Normal | 11 | 1.6.7.9.3.6.2 | 1.6.7.9.3.6.2 |  | 2025-06-03 17:00 | p | 16 |  | 2025-06-20 14:07
396 | 749 | Q6UXOpf9Kvzek7IGY0vp | Normal | 11 | 1.6.7.9.3.6.3 | 1.6.7.9.3.6.3 |  | 2025-06-18 17:00 | p | 14 |  | 2025-07-03 16:35
397 | 750 | lsyrPytnmjLTpXFywa7Z | Normal | 11 | 1.6.7.9.3.6.4 | 1.6.7.9.3.6.4 |  | 2025-07-07 17:00 | p | 14 |  | 2025-07-22 13:22
398 | 6325 | SeCXD5wMvkrEekc1PKVb | Summary | 48 | 1.6.7.9.3.10 | 1.6.7.9.3.10 |  | 2025-11-18 17:00 | p | 99 |  | 2026-02-26 13:37
399 | 753 | 8158sxzbHZvZEVAAqewP | Normal | 47 | 1.6.7.9.3.10.1 | 1.6.7.9.3.10.1 |  | 2025-11-17 17:00 | p | 48 |  | 2026-01-05 10:21
400 | 754 | hfPeDXfQSV7Nx9zb2rD7 | Normal | 8 | 1.6.7.9.3.10.2 | 1.6.7.9.3.10.2 |  | 2025-09-19 17:00 | p | 100 |  | 2025-12-29 11:51
401 | 755 | DQUdswbbJv1Qpkj0EGFX | Normal | 8 | 1.6.7.9.3.10.3 | 1.6.7.9.3.10.3 |  | 2025-10-01 17:00 | p | 99 |  | 2026-01-09 10:16
402 | 756 | ae3T3d3nFoXZXK7gqkAr | Normal | 20 | 1.6.7.9.3.10.4 | 1.6.7.9.3.10.4 |  | 2025-10-30 17:00 | p | 101 |  | 2026-02-09 11:31
403 | 757 | wbc1AZ0GUhXzQk6SoWIe | Normal | 6 | 1.6.7.9.3.10.6 | 1.6.7.9.3.10.6 |  | 2025-11-07 17:00 | p | 102 |  | 2026-02-18 15:32
404 | 758 | FbN1rrQYTlsz1haWZnFy | Normal | 6 | 1.6.7.9.3.10.8 | 1.6.7.9.3.10.8 |  | 2025-11-18 17:00 | p | 99 |  | 2026-02-26 13:37
405 | 5780 | XCMvjmTKbAUuCZwuNlSF | Normal | 6 | 1.6.7.9.3.10.5 | 1.6.7.9.3.10.5 |  | 2025-10-09 17:00 | p | 102 |  | 2026-01-20 09:43
406 | 5782 | EYY3j1SjnoLUV06T0QHs | Normal | 5 | 1.6.7.9.3.10.7 | 1.6.7.9.3.10.7 |  | 2025-11-06 17:00 | p | 97 |  | 2026-02-12 15:16
407 | 6326 | F4s3MnfyyA74WCIympSi | Summary | 75 | 1.6.7.9.3.11 | 1.6.7.9.3.11 |  | 2025-12-29 17:00 | p | 69 |  | 2026-03-09 16:30
408 | 760 | 7IpOsslq7gyebnCTulxX | Normal | 66 | 1.6.7.9.3.11.1 | 1.6.7.9.3.11.1 |  | 2025-12-15 17:00 | p | 13 |  | 2025-12-29 08:26
409 | 761 | x6fNhJzs4uMW9trtiNEW | Normal | 1 | 1.6.7.9.3.11.2 | 1.6.7.9.3.11.2 |  | 2025-12-16 17:00 | p | 72 |  | 2026-02-27 13:36
410 | 762 | nRInnITHYgcDsU5KDg6m | Normal | 8 | 1.6.7.9.3.11.3 | 1.6.7.9.3.11.3 |  | 2025-12-29 17:00 | p | 69 |  | 2026-03-09 16:30
411 | 6327 | dOJS0LaWQU970ssSiqsz | Summary | 59 | 1.6.7.9.3.12 | 1.6.7.9.3.12 |  | 2026-03-25 17:00 | p | 75 |  | 2026-06-09 09:07
412 | 763 | hLK2cdXSS7IhOZR53PgI | Normal | 6 | 1.6.7.9.3.12.1 | 1.6.7.9.3.12.1 |  | 2026-01-07 17:00 | p | 68 |  | 2026-03-17 09:11
413 | 764 | wTf98lLeHiXAkWj17mAH | Normal | 53 | 1.6.7.9.3.12.2 | 1.6.7.9.3.12.2 |  | 2026-03-25 17:00 | p | 75 |  | 2026-06-09 09:07
414 | 770 | cHAOkWrFbu094CNd9eCk | Summary | 91 | 1.6.7.8 | 1.6.7.8 |  | 2025-05-13 17:00 | p | 26 |  | 2025-06-09 09:54
415 | 786 | 5RJIBxVgSA4dodMzOCsx | Normal | 1 | 1.6.7.8.5 | 1.6.7.8.5 |  | 2025-05-13 17:00 | p | 26 |  | 2025-06-09 09:54
416 | 6434 | cc8WGEqtonq4zOxPHtWc | Normal | 65 | 1.6.7.8.4 | 1.6.7.8.4 |  | 2025-05-12 17:00 | p | 24 |  | 2025-06-06 08:25
417 | 5785 | xIbBdattr1YLWDiqGWPC | Summary | 126 | 1.6.7.11 | 1.6.7.11 |  | 2026-09-29 17:00 | p | 104 |  | 2027-01-12 08:36
418 | 5774 | Dvlkt7hdSzdJ7ChIr4xD | Normal | 2 | 1.6.7.11.1 | 1.6.7.11.1 |  | 2026-04-02 17:00 | p | 84 |  | 2026-06-26 11:47
419 | 5775 | D3NIdGcGrWNhiaQ0dYbY | Normal | 2 | 1.6.7.11.3 | 1.6.7.11.3 |  | 2026-09-29 17:00 | p | 104 |  | 2027-01-12 08:36
420 | 6435 | Ql00ScpYzqtI9PQP57zu | Normal | 122 | 1.6.7.11.2 | 1.6.7.11.2 |  | 2026-09-25 17:00 | p | 104 |  | 2027-01-08 08:25
421 | 6284 | T6s1mlIi1Lu4cscBpq9h | Summary | 273 | 1.6.6 | 1.6.6 |  | 2025-12-18 17:00 | p | 12 |  | 2025-12-31 11:08
422 | 1519 | Ig6aeqJATmPNbReGQrzj | Summary | 273 | 1.6.6.1 | 1.6.6.1 |  | 2025-12-18 17:00 | p | 12 |  | 2025-12-31 11:08
423 | 1464 | VN7GLU7alOC9oD3kkW9q | Normal | 30 | 1.6.6.1.4 | 1.6.6.1.4 |  | 2025-03-28 17:00 | p | 12 |  | 2025-04-10 08:56
424 | 1465 | i7zbkIpCuBMJlMsq6ma0 | Normal | 1 | 1.6.6.1.5 | 1.6.6.1.5 |  | 2025-03-31 17:00 | p | 10 |  | 2025-04-11 08:54
425 | 1475 | suCYO4gIoCSrnZchT6aQ | Normal | 3 | 1.6.6.1.6 | 1.6.6.1.6 |  | 2025-02-18 17:00 | p | 0 |  | 2025-02-19 14:02
426 | 1476 | gbuDNYIgLq2nB3WERl4p | Normal | 30 | 1.6.6.1.7 | 1.6.6.1.7 |  | 2025-04-01 17:00 | p | 9 |  | 2025-04-11 13:03
427 | 1477 | BC1NYB3fqAlfckX7ECXI | Normal | 1 | 1.6.6.1.8 | 1.6.6.1.8 |  | 2025-04-02 17:00 | p | 11 |  | 2025-04-14 09:35
428 | 1478 | UR7xa7LgN3sMlpzxRjvW | Normal | 3 | 1.6.6.1.9 | 1.6.6.1.9 |  | 2025-12-18 17:00 | p | 12 |  | 2025-12-31 11:08
429 | 6293 | WhUcOZjaj9TDZe74ojmh | Summary | 172 | 1.6.4 | 1.6.4 |  | 2026-11-10 17:00 | p | 100 |  | 2027-02-19 10:11
430 | 3929 | GkmiaraCbWdBUaRv136y | Summary | 19 | 1.6.4.15 | 1.6.4.15 |  | 2025-03-28 17:00 | p | 41 |  | 2025-05-09 09:49
431 | 3932 | RKLg9Drqo40Q82TFH1VL | Normal | 1 | 1.6.4.15.2 | 1.6.4.15.2 |  | 2025-03-28 17:00 | p | 24 |  | 2025-04-22 10:47
432 | 3934 | 10Oh1H5M5HjeoWxU1u0w | Normal | 1 | 1.6.4.15.4 | 1.6.4.15.4 |  | 2025-03-28 17:00 | p | 38 |  | 2025-05-06 13:01
433 | 3936 | hwXDQy0MWIQ4jzjNT4oM | Normal | 1 | 1.6.4.15.3 | 1.6.4.15.3 |  | 2025-03-28 17:00 | p | 26 |  | 2025-04-24 14:24
434 | 3938 | 2iJ091mlhEkJyqoddB4L | Normal | 14 | 1.6.4.15.1 | 1.6.4.15.1 |  | 2025-02-28 17:00 | p | 20 |  | 2025-03-21 09:14
435 | 3940 | 8UqvtHTIMRT16eupajKq | Normal | 1 | 1.6.4.15.5 | 1.6.4.15.5 |  | 2025-03-28 17:00 | p | 41 |  | 2025-05-09 09:49
436 | 3931 | GleHIX38gd9vOXaUQYVA | Normal | 33 | 1.6.4.11 | 1.6.4.11 |  | 2025-03-27 17:00 | p | 21 |  | 2025-04-18 16:49
437 | 3933 | FbGZSJQTtuDZR2p8qmxq | Normal | 33 | 1.6.4.13 | 1.6.4.13 |  | 2025-03-27 17:00 | p | 38 |  | 2025-05-05 11:02
438 | 3935 | IRdaiLeeauelAg4QWklz | Normal | 33 | 1.6.4.12 | 1.6.4.12 |  | 2025-03-27 17:00 | p | 26 |  | 2025-04-23 14:13
439 | 3939 | cuQ4HC0Kn3S6GTvqv7QE | Normal | 33 | 1.6.4.14 | 1.6.4.14 |  | 2025-03-27 17:00 | p | 41 |  | 2025-05-08 08:55
440 | 3971 | mB1p68eekBqQhgV8es2U | Summary | 19 | 1.6.4.7 | 1.6.4.7 |  | 2025-04-07 17:00 | p | 35 |  | 2025-05-13 09:38
441 | 3974 | xzlIrgrrtbLscLWLbbQq | Normal | 1 | 1.6.4.7.1 | 1.6.4.7.1 |  | 2025-02-14 17:00 | p | 3 |  | 2025-02-18 08:40
442 | 3981 | YTm9sByrDxPUc7AlWXh1 | Normal | 15 | 1.6.4.7.2 | 1.6.4.7.2 |  | 2025-04-07 17:00 | p | 35 |  | 2025-05-13 09:38
443 | 3980 | po54OWwjtqomy5uOkFBU | Normal | 40 | 1.6.4.4 | 1.6.4.4 |  | 2025-04-07 17:00 | p | 35 |  | 2025-05-13 09:38
444 | 3991 | kc0LQmDrjfLGJeMU4QIH | Summary | 70 | 1.6.4.17 | 1.6.4.17 |  | 2025-05-29 17:00 | p | 40 |  | 2025-07-09 11:49
445 | 3992 | cy141kwlo0X5isTqv3ku | Summary | 25 | 1.6.4.17.4 | 1.6.4.17.4 |  | 2025-05-29 17:00 | p | 40 |  | 2025-07-09 11:49
446 | 3993 | LBRozXrRhpq69SKlxnDb | Normal | 10 | 1.6.4.17.4.1 | 1.6.4.17.4.1 |  | 2025-05-07 17:00 | p | 36 |  | 2025-06-13 15:55
447 | 3994 | DvOjAQ6C9aXKnpaAVD1H | Normal | 5 | 1.6.4.17.4.2 | 1.6.4.17.4.2 |  | 2025-05-14 17:00 | p | 40 |  | 2025-06-24 13:47
448 | 3995 | AUkl27NW1i9i5huez8Rg | Normal | 5 | 1.6.4.17.4.3 | 1.6.4.17.4.3 |  | 2025-05-21 17:00 | p | 40 |  | 2025-07-01 13:18
449 | 3996 | Bw8X4DjnSuQgBiA6BEKp | Normal | 5 | 1.6.4.17.4.4 | 1.6.4.17.4.4 |  | 2025-05-29 17:00 | p | 40 |  | 2025-07-09 11:49
450 | 3997 | KJPP8ivswwWTIeIfPXEM | Summary | 25 | 1.6.4.17.3 | 1.6.4.17.3 |  | 2025-04-23 17:00 | p | 34 |  | 2025-05-28 09:23
451 | 3998 | 5UhDwyM7phAycUkk1Nye | Normal | 10 | 1.6.4.17.3.1 | 1.6.4.17.3.1 |  | 2025-04-02 17:00 | p | 33 |  | 2025-05-06 13:19
452 | 3999 | v6kjlf8aEDhSJHzOK2Uo | Normal | 5 | 1.6.4.17.3.2 | 1.6.4.17.3.2 |  | 2025-04-09 17:00 | p | 33 |  | 2025-05-13 13:44
453 | 4000 | Y3aJp60cYMHromf8xgAE | Normal | 5 | 1.6.4.17.3.3 | 1.6.4.17.3.3 |  | 2025-04-16 17:00 | p | 32 |  | 2025-05-19 16:26
454 | 4001 | Cjtbc2cmKWchyZlcOxo3 | Normal | 5 | 1.6.4.17.3.4 | 1.6.4.17.3.4 |  | 2025-04-23 17:00 | p | 34 |  | 2025-05-28 09:23
455 | 4002 | nJzh0eFJGsqvOmQRJzHn | Summary | 27 | 1.6.4.17.2 | 1.6.4.17.2 |  | 2025-03-19 17:00 | p | 32 |  | 2025-04-21 16:12
456 | 4003 | gjf3v6NdOQannovTvAoE | Normal | 19 | 1.6.4.17.2.1 | 1.6.4.17.2.1 |  | 2025-03-07 17:00 | p | 30 |  | 2025-04-07 16:11
457 | 4004 | fF1Y54WMybWnXZsBJgYM | Normal | 1 | 1.6.4.17.2.2 | 1.6.4.17.2.2 |  | 2025-03-10 17:00 | p | 29 |  | 2025-04-09 08:26
458 | 4005 | NxZ8rMz5ZnJaz6z1SXKM | Normal | 3 | 1.6.4.17.2.3 | 1.6.4.17.2.3 |  | 2025-03-13 17:00 | p | 31 |  | 2025-04-14 15:27
459 | 4006 | fOTuJvqH3OcilXcZuEM5 | Normal | 4 | 1.6.4.17.2.4 | 1.6.4.17.2.4 |  | 2025-03-19 17:00 | p | 32 |  | 2025-04-21 16:12
460 | 4012 | A4Ck0Reyqf4cLzrM8uUY | Summary | 206 | 1.6.4.19 | 1.6.4.19 |  | 2025-11-26 17:00 | q | -244 |  | 2025-03-27 10:14
461 | 6168 | BHtkkzlMW8757DY2qb23 | Summary | 143 | 1.6.4.19.3 | 1.6.4.19.3 |  | 2025-11-26 17:00 | q | -244 |  | 2025-03-27 10:14
462 | 6169 | gdW3U4pURjb9iKkAVexH | Summary | 60 | 1.6.4.19.3.1 | 1.6.4.19.3.1 |  | 2025-07-29 17:00 | q | -250 |  | 2024-11-21 11:58
463 | 6170 | AwYLgXY6Mo1DqCbUEhPQ | Summary | 30 | 1.6.4.19.3.1.1 | 1.6.4.19.3.1.1 |  | 2025-06-13 17:00 | q | -248 |  | 2024-10-08 13:09
464 | 6171 | ZR4zae2ZYhCMcZhj7T05 | Normal | 15 | 1.6.4.19.3.1.1.1 | 1.6.4.19.3.1.1.1 |  | 2025-05-22 17:00 | q | -251 |  | 2024-09-13 08:51
465 | 6172 | QgFskomqU31VYtYzB2O0 | Normal | 15 | 1.6.4.19.3.1.1.2 | 1.6.4.19.3.1.1.2 |  | 2025-06-13 17:00 | q | -248 |  | 2024-10-08 13:09
466 | 6173 | nRc7GqDGMG4VP1O5IlEd | Normal | 15 | 1.6.4.19.3.1.2 | 1.6.4.19.3.1.2 |  | 2025-07-08 17:00 | q | -252 |  | 2024-10-29 13:56
467 | 6174 | dvLkHNDhuFTU7AO5XWky | Normal | 15 | 1.6.4.19.3.1.3 | 1.6.4.19.3.1.3 |  | 2025-07-29 17:00 | q | -250 |  | 2024-11-21 11:58
468 | 6175 | IEttja5qNJ6P760Cd9De | Summary | 40 | 1.6.4.19.3.2 | 1.6.4.19.3.2 |  | 2025-09-24 17:00 | q | -240 |  | 2025-01-27 13:26
469 | 6176 | B6x3R7fnpOwupecmo90D | Normal | 10 | 1.6.4.19.3.2.1 | 1.6.4.19.3.2.1 |  | 2025-08-12 17:00 | q | -245 |  | 2024-12-10 13:52
470 | 6177 | vkZhJMfsZWiMPLTjgcam | Normal | 10 | 1.6.4.19.3.2.2 | 1.6.4.19.3.2.2 |  | 2025-08-26 17:00 | q | -245 |  | 2024-12-24 10:02
471 | 6178 | XEU5rnQh2VnDpMl1eT0o | Normal | 10 | 1.6.4.19.3.2.3 | 1.6.4.19.3.2.3 |  | 2025-09-10 17:00 | q | -244 |  | 2025-01-09 11:14
472 | 6179 | xksMzlhYjvKZ4p1XJwSB | Normal | 10 | 1.6.4.19.3.2.4 | 1.6.4.19.3.2.4 |  | 2025-09-24 17:00 | q | -240 |  | 2025-01-27 13:26
473 | 6180 | oR7r0RquVFe2h8pCK9HY | Normal | 10 | 1.6.4.19.3.3 | 1.6.4.19.3.3 |  | 2025-10-08 17:00 | q | -240 |  | 2025-02-10 14:35
474 | 6181 | UJ3hrxCJ5NslZjdDLEyu | Normal | 20 | 1.6.4.19.3.4 | 1.6.4.19.3.4 |  | 2025-11-06 17:00 | q | -240 |  | 2025-03-11 14:19
475 | 6182 | JQHbjwkPqIslt5thIOgQ | Normal | 5 | 1.6.4.19.3.5 | 1.6.4.19.3.5 |  | 2025-11-14 17:00 | q | -242 |  | 2025-03-17 15:31
476 | 6183 | 5NqxhAyIl3JXTpWWvSnV | Normal | 2 | 1.6.4.19.3.6 | 1.6.4.19.3.6 |  | 2025-11-18 17:00 | q | -244 |  | 2025-03-19 11:26
477 | 6184 | vx8CoW16lw8uEEVKaVp7 | Normal | 5 | 1.6.4.19.3.7 | 1.6.4.19.3.7 |  | 2025-11-25 17:00 | q | -244 |  | 2025-03-26 10:08
478 | 6185 | A91LND4pEy61zvjvAsaQ | Normal | 1 | 1.6.4.19.3.8 | 1.6.4.19.3.8 |  | 2025-11-26 17:00 | q | -244 |  | 2025-03-27 10:14
479 | 4037 | hMBnPD0NfYpjSqEpRMYY | Summary | 554 | 1.6.4.20 | 1.6.4.20 |  | 2026-11-10 17:00 | p | 100 |  | 2027-02-19 10:11
480 | 4038 | VkrURyJwsSkEVRV6WcXe | Summary | 411 | 1.6.4.20.1 | 1.6.4.20.1 |  | 2026-04-22 17:00 | p | 76 |  | 2026-07-08 11:24
481 | 4040 | g5zNgGHP8U11wPTJKhcB | Normal | 20 | 1.6.4.20.1.3 | 1.6.4.20.1.3 |  | 2025-06-23 17:00 | q | -262 |  | 2024-10-04 16:18
482 | 4041 | f0PORH3GhEIXFjYfGbTd | Normal | 97 | 1.6.4.20.1.6 | 1.6.4.20.1.6 |  | 2025-10-10 17:00 | q | -217 |  | 2025-03-07 08:15
483 | 4042 | SyfMayqY4a7i0nZLPz6Y | Normal | 129 | 1.6.4.20.1.7 | 1.6.4.20.1.7 |  | 2026-03-23 17:00 | p | 92 |  | 2026-06-24 13:57
484 | 6621 | pXe0ZxltUhDf1quSL5q2 | Normal | 15 | 1.6.4.20.1.2 | 1.6.4.20.1.2 |  | 2025-05-22 17:00 | q | -251 |  | 2024-09-13 10:10
485 | 6622 | EmEy5gJckBYofEEYNXFv | Normal | 20 | 1.6.4.20.1.4 | 1.6.4.20.1.4 |  | 2026-03-25 17:00 | p | 75 |  | 2026-06-09 09:07
486 | 6623 | BVU87KMg9Rhzc6j5yKVh | Normal | 20 | 1.6.4.20.1.5 | 1.6.4.20.1.5 |  | 2026-04-22 17:00 | p | 76 |  | 2026-07-08 11:24
487 | 4043 | XbXkjxtfHUxhg4CK1elt | Summary | 127 | 1.6.4.20.2 | 1.6.4.20.2 |  | 2026-10-23 17:00 | p | 103 |  | 2027-02-04 09:16
488 | 4045 | mDphgqAAxA2RnvA52x8A | Normal | 20 | 1.6.4.20.2.1 | 1.6.4.20.2.1 |  | 2026-05-20 17:00 | p | 82 |  | 2026-08-11 16:05
489 | 4046 | 5HyQBVwuqRdeW1HhaSOP | Normal | 10 | 1.6.4.20.2.2 | 1.6.4.20.2.2 |  | 2026-06-04 17:00 | p | 83 |  | 2026-08-27 10:41
490 | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Normal | 72 | 1.6.4.20.2.3 | 1.6.4.20.2.3 |  | 2026-09-17 17:00 | p | 96 |  | 2026-12-23 10:38
491 | 4048 | ybbKhm9jdtNbVzABGZ8L | Normal | 20 | 1.6.4.20.2.4 | 1.6.4.20.2.4 |  | 2026-10-16 17:00 | p | 104 |  | 2027-01-29 09:24
492 | 4049 | kP1jeiEwkYg4HRpUjG4p | Normal | 5 | 1.6.4.20.2.5 | 1.6.4.20.2.5 |  | 2026-10-23 17:00 | p | 103 |  | 2027-02-04 09:16
493 | 4050 | jQIHIDf5FTnJxQysEvnn | Summary | 37 | 1.6.4.20.3 | 1.6.4.20.3 |  | 2026-11-10 17:00 | p | 100 |  | 2027-02-19 10:11
494 | 4051 | bizigDTezGi1mMHxJ1gi | Summary | 32 | 1.6.4.20.3.1 | 1.6.4.20.3.1 |  | 2026-11-03 17:00 | p | 97 |  | 2027-02-09 08:06
495 | 4052 | JSSXcLTdD9VQNM766DgK | Normal | 20 | 1.6.4.20.3.1.1 | 1.6.4.20.3.1.1 |  | 2026-10-16 17:00 | p | 97 |  | 2027-01-22 15:39
496 | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Normal | 12 | 1.6.4.20.3.1.2 | 1.6.4.20.3.1.2 |  | 2026-11-03 17:00 | p | 97 |  | 2027-02-09 08:06
497 | 4054 | WhXMUGkGRid5sulqMW8S | Summary | 5 | 1.6.4.20.3.2 | 1.6.4.20.3.2 |  | 2026-11-10 17:00 | p | 96 |  | 2027-02-15 15:07
498 | 4055 | dWrJCmOwv1i72p29KBXE | Normal | 2 | 1.6.4.20.3.2.1 | 1.6.4.20.3.2.1 |  | 2026-11-05 17:00 | p | 96 |  | 2027-02-10 16:11
499 | 4056 | a1SRK7UWhIIMlkKKriy9 | Normal | 1 | 1.6.4.20.3.2.2 | 1.6.4.20.3.2.2 |  | 2026-11-06 17:00 | p | 96 |  | 2027-02-11 16:13
500 | 4057 | NKnvgqAHKv63TOKudyZQ | Normal | 1 | 1.6.4.20.3.2.3 | 1.6.4.20.3.2.3 |  | 2026-11-09 17:00 | p | 94 |  | 2027-02-12 15:25
501 | 4058 | cbANjhwCBqAluf1RM04K | Normal | 1 | 1.6.4.20.3.2.4 | 1.6.4.20.3.2.4 |  | 2026-11-10 17:00 | p | 96 |  | 2027-02-15 15:07
502 | 4059 | sH9kz6O2EFda2hu4x8Kx | Summary | 12 | 1.6.4.20.3.3 | 1.6.4.20.3.3 |  | 2026-11-10 17:00 | p | 100 |  | 2027-02-19 10:11
503 | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Normal | 3 | 1.6.4.20.3.3.1 | 1.6.4.20.3.3.1 |  | 2026-10-28 17:00 | p | 102 |  | 2027-02-08 13:21
504 | 4061 | ViM2psfxppAdWr3IoYdq | Normal | 3 | 1.6.4.20.3.3.2 | 1.6.4.20.3.3.2 |  | 2026-11-02 17:00 | p | 100 |  | 2027-02-11 14:06
505 | 4062 | RvsEFsErXikPrAOovPaZ | Normal | 1 | 1.6.4.20.3.3.3 | 1.6.4.20.3.3.3 |  | 2026-11-03 17:00 | p | 100 |  | 2027-02-12 10:03
506 | 4063 | ma6GKJ3GzeKmeF4AshaM | Normal | 4 | 1.6.4.20.3.3.4 | 1.6.4.20.3.3.4 |  | 2026-11-09 17:00 | p | 100 |  | 2027-02-18 09:34
507 | 4064 | OALhjNOvEaqSDAmsS5Il | Normal | 1 | 1.6.4.20.3.3.5 | 1.6.4.20.3.3.5 |  | 2026-11-10 17:00 | p | 100 |  | 2027-02-19 10:11
508 | 5748 | cHP8KcDQZp8MvOi5a8Wj | Summary | 64 | 1.6.4.18 | 1.6.4.18 |  | 2025-04-11 17:00 | p | 4 |  | 2025-04-16 15:51
509 | 6701 | vwWJ3SVwW3tYdDDMDgOK | Summary | 60 | 1.6.4.18.3 | 1.6.4.18.3 |  | 2025-04-11 17:00 | p | 4 |  | 2025-04-16 15:51
510 | 6713 | JQXHTZXJblKyiNyxM0eT | Summary | 78 | 1.6.4.18.3.3 | 1.6.4.18.3.3 |  | 2025-04-11 17:00 | p | 4 |  | 2025-04-16 15:51
511 | 6727 | 5BlmDU3ct4fwjT54EODG | Summary | 21 | 1.6.4.18.3.3.2 | 1.6.4.18.3.3.2 |  | 2025-02-28 17:00 | q | 0 |  | 2025-02-28 08:19
512 | 7271 | 7ZvC3KC1rMxIYvbhicKJ | Normal | 10 | 1.6.4.18.3.3.2.7 | 1.6.4.18.3.3.2.7 |  | 2025-02-28 17:00 | q | 0 |  | 2025-02-28 08:19
513 | 7007 | 9uputDeZmGdSlUY8oN4J | Summary | 64 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 2025-04-11 17:00 | p | 4 |  | 2025-04-16 15:51
514 | 7010 | l7MAqMN94R7DBQRgok6z | Normal | 5 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 2025-04-11 17:00 | p | 4 |  | 2025-04-16 15:51
515 | 7278 | 4Ma7Z2LiPmWBC9UI6vyb | Normal | 5 | 1.6.4.18.3.3.7.7 | 1.6.4.18.3.3.7.7 |  | 2025-03-28 17:00 | p | 2 |  | 2025-03-31 11:26
516 | 7300 | JMkMoXIhBdn9ICcOd798 | Normal | 5 | 1.6.4.18.3.3.7.4 | 1.6.4.18.3.3.7.4 |  | 2025-03-07 17:00 | q | 0 |  | 2025-03-07 11:52
517 | 7301 | mVBynbXAicTgOFud0Dl3 | Normal | 5 | 1.6.4.18.3.3.7.6 | 1.6.4.18.3.3.7.6 |  | 2025-03-21 17:00 | p | 2 |  | 2025-03-24 13:52
518 | 7302 | 6S1rSJxqNAmNyzjZVL7L | Normal | 5 | 1.6.4.18.3.3.7.8 | 1.6.4.18.3.3.7.8 |  | 2025-04-04 17:00 | p | 5 |  | 2025-04-10 13:11
519 | 7279 | uD2jpviUMAewZ4YhDj8P | Summary | 32 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 2025-03-12 17:00 | q | -7 |  | 2025-03-05 08:36
520 | 7282 | sTVLhyKAe9uIrxTuOSsB | Normal | 2 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 2025-02-21 17:00 | q | -8 |  | 2025-02-13 10:49
521 | 7283 | GyFcZSlU29ifaVubQEBd | Normal | 2 | 1.6.4.18.3.3.4.4 | 1.6.4.18.3.3.4.4 |  | 2025-02-25 17:00 | q | -7 |  | 2025-02-18 09:49
522 | 7284 | AoDPK2hmzwZjnwdc6ENo | Normal | 1 | 1.6.4.18.3.3.4.5 | 1.6.4.18.3.3.4.5 |  | 2025-02-26 17:00 | q | -7 |  | 2025-02-19 08:43
523 | 7285 | UP4KQN3vFTNJJtYiVHhd | Normal | 10 | 1.6.4.18.3.3.4.6 | 1.6.4.18.3.3.4.6 |  | 2025-03-12 17:00 | q | -7 |  | 2025-03-05 08:36
524 | 7286 | weppsWRcwILLbxkFpraK | Summary | 39 | 1.6.4.18.3.3.5 | 1.6.4.18.3.3.5 |  | 2025-03-18 17:00 | p | 1 |  | 2025-03-20 09:30
525 | 7289 | YNbMTserJcwdDTx8O6lt | Normal | 5 | 1.6.4.18.3.3.5.3 | 1.6.4.18.3.3.5.3 |  | 2025-02-27 17:00 | p | 4 |  | 2025-03-04 09:58
526 | 7290 | rpRUKocvSOF2GnoJsxWr | Normal | 2 | 1.6.4.18.3.3.5.4 | 1.6.4.18.3.3.5.4 |  | 2025-03-03 17:00 | p | 2 |  | 2025-03-06 09:58
527 | 7291 | ThxkR8uStFOgKr5Kajlm | Normal | 1 | 1.6.4.18.3.3.5.5 | 1.6.4.18.3.3.5.5 |  | 2025-03-04 17:00 | p | 2 |  | 2025-03-07 09:02
528 | 7292 | 6vEOHVPLFOaXnW1xcDp6 | Normal | 10 | 1.6.4.18.3.3.5.6 | 1.6.4.18.3.3.5.6 |  | 2025-03-18 17:00 | p | 1 |  | 2025-03-20 09:30
529 | 7293 | ep0qwejNT11UOlW5WmY0 | Summary | 28 | 1.6.4.18.3.3.6 | 1.6.4.18.3.3.6 |  | 2025-03-28 17:00 | p | 6 |  | 2025-04-04 11:17
530 | 7296 | PnFVdPiNKahDkradYWdd | Normal | 5 | 1.6.4.18.3.3.6.3 | 1.6.4.18.3.3.6.3 |  | 2025-03-11 17:00 | p | 5 |  | 2025-03-17 09:24
531 | 7297 | JA5LCeR4tD4Vqq2Jfy9o | Normal | 2 | 1.6.4.18.3.3.6.4 | 1.6.4.18.3.3.6.4 |  | 2025-03-13 17:00 | p | 4 |  | 2025-03-18 16:05
532 | 7298 | uHK4wyA8DzlXgqm5UKoq | Normal | 1 | 1.6.4.18.3.3.6.5 | 1.6.4.18.3.3.6.5 |  | 2025-03-14 17:00 | p | 4 |  | 2025-03-19 14:52
533 | 7299 | ymtRqRQZa4AjGraGOZVd | Normal | 10 | 1.6.4.18.3.3.6.6 | 1.6.4.18.3.3.6.6 |  | 2025-03-28 17:00 | p | 6 |  | 2025-04-04 11:17
534 | 6297 | AqdIsKbIPOfZJkjKYjnG | Summary | 118 | 1.6.1 | 1.6.1 |  | 2026-08-26 17:00 | q | -373 |  | 2025-08-18 14:35
535 | 4200 | YSdvLAa6ztbhOKei71CV | Summary | 108 | 1.6.1.1 | 1.6.1.1 |  | 2025-07-15 17:00 | p | 30 |  | 2025-08-15 13:39
536 | 4202 | N5DTU5adYVhKR5So2Uvc | Normal | 88 | 1.6.1.1.3 | 1.6.1.1.3 |  | 2025-06-13 17:00 | p | 34 |  | 2025-07-18 08:03
537 | 4204 | CRzwy8942pbCOpcOMW2v | Normal | 20 | 1.6.1.1.4 | 1.6.1.1.4 |  | 2025-07-15 17:00 | p | 30 |  | 2025-08-15 13:39
538 | 4209 | 0Ck6gz1ZilLs9fM0b7nU | Summary | 46 | 1.6.1.3 | 1.6.1.3 |  | 2025-04-15 17:00 | p | 15 |  | 2025-05-01 09:01
539 | 4212 | yktUOUuzQyzOVBFBfL42 | Normal | 46 | 1.6.1.3.1 | 1.6.1.3.1 |  | 2025-04-15 17:00 | p | 15 |  | 2025-05-01 09:01
540 | 4218 | T5g2El1CSAmFZNlboxQh | Normal | 1 | 1.6.1.4 | 1.6.1.4 |  | 2025-07-16 17:00 | p | 32 |  | 2025-08-18 14:35
541 | 6080 | jFrzSNmYyPDtKSvRlBw2 | Normal | 1 | 1.6.1.6 | 1.6.1.6 |  | 2026-08-26 17:00 | q | -1115 |  | 2023-08-07 16:17
542 | 6311 | tQdu1pFxVkY2bj5IQjxI | Summary | 77 | 1.6.3 | 1.6.3 |  | 2025-07-11 17:00 | p | 159 |  | 2025-12-18 08:10
543 | 5452 | u9nFTwEoKsBrgeg8njOT | Normal | 5 | 1.6.3.1 | 1.6.3.1 |  | 2025-02-14 17:00 | p | 298 |  | 2025-12-10 16:55
544 | 5457 | kGunJCROCjWQWqBfRKBZ | Summary | 1 | 1.6.3.2 | 1.6.3.2 |  | 2025-02-14 17:00 | p | 25 |  | 2025-03-12 09:58
545 | 5458 | DngVHB2HpHpsOjFWu5hu | Summary | 1 | 1.6.3.2.1 | 1.6.3.2.1 |  | 2025-02-14 17:00 | p | 25 |  | 2025-03-12 09:58
546 | 5505 | nVzBMSNTKKq9KPWblsw1 | Normal | 1 | 1.6.3.2.1.9 | 1.6.3.2.1.9 |  | 2025-02-14 17:00 | p | 25 |  | 2025-03-12 09:58
547 | 5506 | wLM81Xdu8B5geOMMQz6m | Summary | 119 | 1.6.3.3 | 1.6.3.3 |  | 2025-07-11 17:00 | p | 159 |  | 2025-12-18 08:10
548 | 5507 | 1r4d5DbY2YIgMhg8HKuO | Normal | 3 | 1.6.3.3.2 | 1.6.3.3.2 |  | 2025-04-10 17:00 | p | 14 |  | 2025-04-25 15:13
549 | 5508 | wHSntGHJkj4aA0wA3fA2 | Normal | 14 | 1.6.3.3.3 | 1.6.3.3.3 |  | 2025-04-30 17:00 | p | 15 |  | 2025-05-16 13:13
550 | 5509 | 1FHP32ReWIveKb3JOWEG | Summary | 44 | 1.6.3.3.4 | 1.6.3.3.4 |  | 2025-07-03 17:00 | p | 25 |  | 2025-07-29 09:13
551 | 5510 | LTFwTsrnxYhrGNFUv7CM | Normal | 12 | 1.6.3.3.4.1 | 1.6.3.3.4.1 |  | 2025-05-16 12:00 | p | 24 |  | 2025-06-09 13:11
552 | 5511 | Od3mMFxB7LjrJLF1slz4 | Normal | 11 | 1.6.3.3.4.2 | 1.6.3.3.4.2 |  | 2025-06-03 17:00 | p | 22 |  | 2025-06-26 15:16
553 | 5512 | Des2hDKSMjcJndTJRzoQ | Normal | 11 | 1.6.3.3.4.3 | 1.6.3.3.4.3 |  | 2025-06-18 17:00 | p | 26 |  | 2025-07-15 10:49
554 | 5513 | z1vb48lrGwUUDjKbD3gr | Normal | 10 | 1.6.3.3.4.4 | 1.6.3.3.4.4 |  | 2025-07-03 17:00 | p | 25 |  | 2025-07-29 09:13
555 | 5514 | leNXdZKmybH4tpy20cQU | Normal | 5 | 1.6.3.3.5 | 1.6.3.3.5 |  | 2025-07-11 17:00 | p | 159 |  | 2025-12-18 08:10
556 | 6890 | QKIolSsTnUWZiIhR6M5v | Normal | 40 | 1.6.3.3.1 | 1.6.3.3.1 |  | 2025-04-07 17:00 | p | 14 |  | 2025-04-22 10:47
557 | 6359 | hvfa0617w1FgmEnjjKwJ | Summary | 26 | 1.7.2.16 | 1.7.2.16 |  | 2025-03-04 17:00 | p | 1 |  | 2025-03-06 11:06
558 | 6360 | DMXbIVCeMtVR5pi4d5UN | Summary | 26 | 1.7.2.16.1 | 1.7.2.16.1 |  | 2025-03-04 17:00 | p | 1 |  | 2025-03-06 11:06
559 | 6361 | VEKeY9azNIVSZDSjYyKy | Summary | 33 | 1.7.2.16.1.3 | 1.7.2.16.1.3 |  | 2025-03-04 17:00 | p | 1 |  | 2025-03-06 11:06
560 | 7303 | fpLHmKjlfpy4s4tap5Xw | Summary | 39 | 1.6.3.11.1.3.4 | 1.6.3.11.1.3.4 |  | 2025-02-19 17:00 | q | -8 |  | 2025-02-11 10:23
561 | 7307 | eye8r8DevGvPITcdrMUe | Normal | 6 | 1.6.3.11.1.3.4.4 | 1.6.3.11.1.3.4.4 |  | 2025-02-18 17:00 | q | -8 |  | 2025-02-10 11:28
562 | 7308 | BXoPyB4GmzJwvFdrkJ7b | Normal | 1 | 1.6.3.11.1.3.4.5 | 1.6.3.11.1.3.4.5 |  | 2025-02-19 17:00 | q | -8 |  | 2025-02-11 10:23
563 | 7309 | 19skeJKmh3pRSfTF3DDB | Summary | 30 | 1.6.3.11.1.3.5 | 1.6.3.11.1.3.5 |  | 2025-02-20 17:00 | p | 0 |  | 2025-02-21 16:57
564 | 7313 | boaUnlKi0h6sKdwgAbmA | Normal | 5 | 1.6.3.11.1.3.5.4 | 1.6.3.11.1.3.5.4 |  | 2025-02-19 17:00 | p | 0 |  | 2025-02-20 15:12
565 | 7314 | zaliCdoIQDW2tx8wBQyt | Normal | 1 | 1.6.3.11.1.3.5.5 | 1.6.3.11.1.3.5.5 |  | 2025-02-20 17:00 | p | 0 |  | 2025-02-21 16:57
566 | 7315 | 9LywAxRsXdHsCrCcjGKV | Summary | 27 | 1.6.3.11.1.3.6 | 1.6.3.11.1.3.6 |  | 2025-03-04 17:00 | p | 1 |  | 2025-03-06 11:06
567 | 7318 | vWglY3BMmZCigDWMEMyY | Normal | 3 | 1.6.3.11.1.3.6.3 | 1.6.3.11.1.3.6.3 |  | 2025-02-24 17:00 | p | 1 |  | 2025-02-26 15:34
568 | 7319 | Fr6VbOwwg75s6X3Xcfql | Normal | 5 | 1.6.3.11.1.3.6.4 | 1.6.3.11.1.3.6.4 |  | 2025-03-03 17:00 | p | 1 |  | 2025-03-05 13:53
569 | 7320 | MRmQHJYBr9cc2OfLUSYd | Normal | 1 | 1.6.3.11.1.3.6.5 | 1.6.3.11.1.3.6.5 |  | 2025-03-04 17:00 | p | 1 |  | 2025-03-06 11:06
570 | 6273 | ljz6i2ltFwqcRU3btDx0 | Summary | 552 | 1.8 | 1.8 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
571 | 1639 | mkPE1mMWzawwUBF3KKzV | Summary | 277 | 1.8.2 | 1.8.2 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
572 | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Milestone | 0 | 1.8.2.1 | 1.8.2.1 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
573 | 6074 | fkBL64dyW7paLwgGr0ue | Normal | 212 | 1.8.2.3 | 1.8.2.3 |  | 2025-12-12 17:00 | p | 27 |  | 2026-01-09 16:28
574 | 6075 | pe2nScqRc5pgTwGaT5Zd | Normal | 193 | 1.8.2.2 | 1.8.2.2 |  | 2025-11-14 17:00 | p | 51 |  | 2026-01-05 15:20
575 | 6295 | uPS9GNqRLP4065SnBhEr | Summary | 387 | 1.8.5 | 1.8.5 |  | 2026-05-01 17:00 | q | -18 |  | 2026-04-13 11:49
576 | 3679 | 1KDcwGZKgevw1MizqBh0 | Summary | 387 | 1.8.5.1 | 1.8.5.1 |  | 2026-05-01 17:00 | q | -18 |  | 2026-04-13 11:49
577 | 3680 | E8qsx9NjEz7vaL5H7EFb | Summary | 189 | 1.8.5.1.1 | 1.8.5.1.1 |  | 2025-12-22 17:00 | p | 28 |  | 2026-01-20 16:54
578 | 3681 | wdhUrQuIMTMPn1LoqO1m | Normal | 24 | 1.8.5.1.1.1 | 1.8.5.1.1.1 |  | 2025-04-24 17:00 | p | 7 |  | 2025-05-02 09:24
579 | 3682 | 38PSIqFGHzjKldiudT82 | Summary | 25 | 1.8.5.1.1.4 | 1.8.5.1.1.4 |  | 2025-05-30 17:00 | p | 12 |  | 2025-06-12 11:53
580 | 3683 | JW3LUw009FZ7ddD6CdLX | Normal | 20 | 1.8.5.1.1.4.1 | 1.8.5.1.1.4.1 |  | 2025-05-22 17:00 | p | 11 |  | 2025-06-03 16:26
581 | 3684 | g3f8U3i4iakOhylueut6 | Normal | 5 | 1.8.5.1.1.4.2 | 1.8.5.1.1.4.2 |  | 2025-05-30 17:00 | p | 12 |  | 2025-06-12 11:53
582 | 3685 | eStRoX3vnaDmRLAWk58C | Summary | 40 | 1.8.5.1.1.5 | 1.8.5.1.1.5 |  | 2025-07-29 17:00 | p | 20 |  | 2025-08-19 08:33
583 | 3686 | 7zhxjkpiLTAH9tiW1eYy | Normal | 20 | 1.8.5.1.1.5.1 | 1.8.5.1.1.5.1 |  | 2025-06-30 17:00 | p | 17 |  | 2025-07-18 15:02
584 | 3687 | 0zzWvesUS18qEUfjK5NH | Normal | 5 | 1.8.5.1.1.5.2 | 1.8.5.1.1.5.2 |  | 2025-07-08 17:00 | p | 16 |  | 2025-07-25 16:44
585 | 3688 | zSUYYsBrfiOGi6qJakS6 | Normal | 5 | 1.8.5.1.1.5.3 | 1.8.5.1.1.5.3 |  | 2025-07-15 17:00 | p | 19 |  | 2025-08-04 10:03
586 | 3689 | X7sWUqInOJZ9zcVzmfT1 | Normal | 5 | 1.8.5.1.1.5.4 | 1.8.5.1.1.5.4 |  | 2025-07-22 17:00 | p | 19 |  | 2025-08-11 11:02
587 | 3690 | 8YDpqEvemQaMsfVmGpF8 | Normal | 5 | 1.8.5.1.1.5.5 | 1.8.5.1.1.5.5 |  | 2025-07-29 17:00 | p | 20 |  | 2025-08-19 08:33
588 | 3691 | ofZrlktbiXkVpuhhIeO5 | Summary | 25 | 1.8.5.1.1.6 | 1.8.5.1.1.6 |  | 2025-08-05 17:00 | p | 20 |  | 2025-08-26 08:33
589 | 3692 | xRsKOxB8zGAnVTXugcHQ | Normal | 20 | 1.8.5.1.1.6.1 | 1.8.5.1.1.6.1 |  | 2025-07-29 17:00 | p | 19 |  | 2025-08-18 16:30
590 | 3693 | Hn8rBaTvxeP9Vb10zF48 | Normal | 5 | 1.8.5.1.1.6.2 | 1.8.5.1.1.6.2 |  | 2025-08-05 17:00 | p | 20 |  | 2025-08-26 08:33
591 | 3694 | 4tipOydrC0LTNincaMDW | Summary | 35 | 1.8.5.1.1.7 | 1.8.5.1.1.7 |  | 2025-09-17 17:00 | p | 36 |  | 2025-10-24 13:49
592 | 3695 | lT6NpgfSYqKHtVYFLSzF | Normal | 20 | 1.8.5.1.1.7.1 | 1.8.5.1.1.7.1 |  | 2025-08-26 17:00 | p | 33 |  | 2025-09-29 09:56
593 | 3696 | gijouZuJR1ZVcSfHKSTf | Normal | 5 | 1.8.5.1.1.7.2 | 1.8.5.1.1.7.2 |  | 2025-09-03 17:00 | p | 33 |  | 2025-10-07 10:03
594 | 3697 | 1158ttL4JEmZYV6RmdcS | Normal | 5 | 1.8.5.1.1.7.3 | 1.8.5.1.1.7.3 |  | 2025-09-10 17:00 | p | 35 |  | 2025-10-16 08:57
595 | 3698 | AKCwPpEPQi4iH3XDRpiM | Normal | 5 | 1.8.5.1.1.7.4 | 1.8.5.1.1.7.4 |  | 2025-09-17 17:00 | p | 36 |  | 2025-10-24 13:49
596 | 3699 | AYANEA6OuC5b95kp3uyI | Summary | 30 | 1.8.5.1.1.8 | 1.8.5.1.1.8 |  | 2025-10-08 17:00 | p | 34 |  | 2025-11-12 10:27
597 | 3700 | WE9bFDn3y5M7oiID5UPj | Normal | 20 | 1.8.5.1.1.8.1 | 1.8.5.1.1.8.1 |  | 2025-09-24 17:00 | p | 29 |  | 2025-10-24 13:58
598 | 3701 | CXSHp4tESy2S0nMNpo3C | Normal | 5 | 1.8.5.1.1.8.2 | 1.8.5.1.1.8.2 |  | 2025-10-01 17:00 | p | 29 |  | 2025-10-31 16:47
599 | 3702 | sTuPByKbZEfSXxt0Z2G9 | Normal | 5 | 1.8.5.1.1.8.3 | 1.8.5.1.1.8.3 |  | 2025-10-08 17:00 | p | 34 |  | 2025-11-12 10:27
600 | 3703 | WHZRJAK4v6S9Zk2EBeP3 | Summary | 40 | 1.8.5.1.1.9 | 1.8.5.1.1.9 |  | 2025-11-21 17:00 | p | 23 |  | 2025-12-15 08:23
601 | 3704 | 3CXbrhXJooXd98jlpAkg | Normal | 20 | 1.8.5.1.1.9.1 | 1.8.5.1.1.9.1 |  | 2025-10-23 17:00 | p | 21 |  | 2025-11-14 10:21
602 | 3705 | RO9RShNcg0h7x9fD24Zk | Normal | 5 | 1.8.5.1.1.9.2 | 1.8.5.1.1.9.2 |  | 2025-10-30 17:00 | p | 19 |  | 2025-11-19 13:23
603 | 3706 | w8MhGnhxyXFIHvJdw6bc | Normal | 5 | 1.8.5.1.1.9.3 | 1.8.5.1.1.9.3 |  | 2025-11-06 17:00 | p | 21 |  | 2025-11-28 11:01
604 | 3707 | dJNKgtiJ1M8pNoPOlZcZ | Normal | 5 | 1.8.5.1.1.9.4 | 1.8.5.1.1.9.4 |  | 2025-11-14 17:00 | p | 23 |  | 2025-12-08 08:35
605 | 3708 | 84VtM14FQkMGurZDdBLv | Normal | 5 | 1.8.5.1.1.9.5 | 1.8.5.1.1.9.5 |  | 2025-11-21 17:00 | p | 23 |  | 2025-12-15 08:23
606 | 3709 | gpO5WcJkYid7jZAXZwbn | Summary | 40 | 1.8.5.1.1.10 | 1.8.5.1.1.10 |  | 2025-12-22 17:00 | p | 28 |  | 2026-01-20 16:54
607 | 3710 | KOKaQwRJEoC6vlU3mKjm | Normal | 20 | 1.8.5.1.1.10.1 | 1.8.5.1.1.10.1 |  | 2025-11-21 17:00 | p | 24 |  | 2025-12-16 13:41
608 | 3711 | XXu8BmtFqx4o2r8a6o98 | Normal | 5 | 1.8.5.1.1.10.2 | 1.8.5.1.1.10.2 |  | 2025-12-01 17:00 | p | 22 |  | 2025-12-24 08:37
609 | 3712 | sZwrgRbHYjKWcIa9rVK3 | Normal | 5 | 1.8.5.1.1.10.3 | 1.8.5.1.1.10.3 |  | 2025-12-08 17:00 | p | 24 |  | 2026-01-02 15:25
610 | 3713 | 4NbryuRKpmrExDEDqArG | Normal | 5 | 1.8.5.1.1.10.4 | 1.8.5.1.1.10.4 |  | 2025-12-15 17:00 | p | 24 |  | 2026-01-09 09:53
611 | 3714 | Fbm1iHrhCX8z8SNRXJuq | Normal | 5 | 1.8.5.1.1.10.5 | 1.8.5.1.1.10.5 |  | 2025-12-22 17:00 | p | 28 |  | 2026-01-20 16:54
612 | 6646 | CmmxWTpZgFyyAwkQnNh3 | Normal | 10 | 1.8.5.1.1.2 | 1.8.5.1.1.2 |  | 2025-05-08 17:00 | p | 6 |  | 2025-05-15 15:57
613 | 6647 | hWzCSsDre5WTTpryk1b0 | Normal | 5 | 1.8.5.1.1.3 | 1.8.5.1.1.3 |  | 2025-05-15 17:00 | p | 7 |  | 2025-05-23 15:38
614 | 3715 | V6i7uYjEJBRYHjhIimqJ | Summary | 50 | 1.8.5.1.2 | 1.8.5.1.2 |  | 2026-03-06 17:00 | p | 20 |  | 2026-03-27 11:53
615 | 3716 | bdy5zVX59rD935sK6M5v | Normal | 20 | 1.8.5.1.2.1 | 1.8.5.1.2.1 |  | 2026-01-22 17:00 | p | 26 |  | 2026-02-18 09:11
616 | 3717 | 5PdqCAMtbYgi5VsFO6ls | Normal | 20 | 1.8.5.1.2.4 | 1.8.5.1.2.4 |  | 2026-03-06 17:00 | p | 20 |  | 2026-03-27 11:53
617 | 6671 | 0oTh3tmNX3iVSaVNVmGK | Normal | 5 | 1.8.5.1.2.2 | 1.8.5.1.2.2 |  | 2026-01-29 17:00 | p | 27 |  | 2026-02-26 09:38
618 | 6672 | BKyGOzVPyPwKpI9CyseJ | Normal | 5 | 1.8.5.1.2.3 | 1.8.5.1.2.3 |  | 2026-02-05 17:00 | p | 25 |  | 2026-03-03 10:48
619 | 3718 | vTyTgxcbRSz6H6lqDAEf | Summary | 20 | 1.8.5.1.3 | 1.8.5.1.3 |  | 2026-04-03 17:00 | p | 9 |  | 2026-04-13 11:49
620 | 3719 | B9ymEBZ7zimHMMqNS20Q | Normal | 20 | 1.8.5.1.3.1 | 1.8.5.1.3.1 |  | 2026-04-03 17:00 | p | 9 |  | 2026-04-13 11:49
621 | 3720 | rPRo0RE1uNkj9oG127hu | Summary | 109 | 1.8.5.1.4 | 1.8.5.1.4 |  | 2025-08-21 17:00 | q | -603 |  | 2023-12-27 10:48
622 | 3721 | 45j7fpB55qVEeWfRBgCv | Normal | 1 | 1.8.5.1.4.1 | 1.8.5.1.4.1 |  | 2025-03-19 17:00 | q | -590 |  | 2023-08-07 16:59
623 | 3722 | hYa6Ppkzu6veYWmxHffd | Normal | 27 | 1.8.5.1.4.2 | 1.8.5.1.4.2 |  | 2025-04-25 17:00 | q | -589 |  | 2023-09-14 10:45
624 | 6649 | TeFWDZJ3h8q4yVNptUYE | Normal | 28 | 1.8.5.1.4.3 | 1.8.5.1.4.3 |  | 2025-06-05 17:00 | q | -590 |  | 2023-10-24 11:20
625 | 6650 | FvuNLI4Jaew3VjPpwL3e | Normal | 28 | 1.8.5.1.4.4 | 1.8.5.1.4.4 |  | 2025-07-17 17:00 | q | -603 |  | 2023-11-22 11:54
626 | 6651 | T3J0AzovT4qFTLJ7Lgki | Normal | 15 | 1.8.5.1.4.5 | 1.8.5.1.4.5 |  | 2025-08-07 17:00 | q | -602 |  | 2023-12-14 08:10
627 | 6652 | 0afM7N7hGdWHQjlFenVR | Normal | 10 | 1.8.5.1.4.6 | 1.8.5.1.4.6 |  | 2025-08-21 17:00 | q | -603 |  | 2023-12-27 10:48
628 | 3723 | 4qmbzAmtSx0gvDVaBsYe | Summary | 239 | 1.8.5.1.5 | 1.8.5.1.5 |  | 2025-12-26 17:00 | p | 18 |  | 2026-01-14 08:31
629 | 3724 | ZCOxRRLLrh9Pa7VnBAyk | Normal | 27 | 1.8.5.1.5.1 | 1.8.5.1.5.1 |  | 2025-04-29 17:00 | p | 12 |  | 2025-05-12 16:01
630 | 3725 | 8cgOIQk4rBKvjXdBm8mF | Normal | 91 | 1.8.5.1.5.9 | 1.8.5.1.5.9 |  | 2025-06-18 17:00 | q | -6 |  | 2025-06-12 16:22
631 | 6661 | bQxmmL7mcUsEGpKkQTDo | Normal | 28 | 1.8.5.1.5.2 | 1.8.5.1.5.2 |  | 2025-06-09 17:00 | p | 14 |  | 2025-06-24 09:50
632 | 6662 | CVNpv9CNU8XhfLmVwl8x | Normal | 28 | 1.8.5.1.5.3 | 1.8.5.1.5.3 |  | 2025-07-21 17:00 | p | 13 |  | 2025-08-04 10:00
633 | 6663 | LVExlIxeJ6XB3yqm0Dzs | Normal | 28 | 1.8.5.1.5.4 | 1.8.5.1.5.4 |  | 2025-08-28 17:00 | p | 13 |  | 2025-09-11 10:43
634 | 6664 | Io9oZ1dPqEE9GDlMTPxh | Normal | 28 | 1.8.5.1.5.5 | 1.8.5.1.5.5 |  | 2025-10-08 17:00 | p | 13 |  | 2025-10-22 16:20
635 | 6665 | ycT0qtEFjd4p02S4Ehf1 | Normal | 28 | 1.8.5.1.5.6 | 1.8.5.1.5.6 |  | 2025-11-19 17:00 | p | 11 |  | 2025-12-01 13:30
636 | 6666 | sX3PHseynvzwKI9my2AH | Normal | 15 | 1.8.5.1.5.7 | 1.8.5.1.5.7 |  | 2025-12-11 17:00 | p | 21 |  | 2026-01-02 13:43
637 | 6667 | 0dYk2X7XWh2rSSHkHo2L | Normal | 10 | 1.8.5.1.5.8 | 1.8.5.1.5.8 |  | 2025-12-26 17:00 | p | 18 |  | 2026-01-14 08:31
638 | 6668 | NGuTznXCCG5yuIi6lGQO | Normal | 1 | 1.8.5.1.5.10 | 1.8.5.1.5.10 |  | 2025-06-20 17:00 | q | -4 |  | 2025-06-16 09:10
639 | 6669 | t8MCocRefa6DhiQNsJVn | Normal | 1 | 1.8.5.1.5.11 | 1.8.5.1.5.11 |  | 2025-06-23 17:00 | q | -6 |  | 2025-06-17 10:26
640 | 6670 | vWxPVjk5e7KHTev8998h | Normal | 1 | 1.8.5.1.5.12 | 1.8.5.1.5.12 |  | 2025-06-24 17:00 | q | -6 |  | 2025-06-18 11:53
641 | 3726 | 5hjTNIk7WmpZNtmCLhPN | Summary | 96 | 1.8.5.1.6 | 1.8.5.1.6 |  | 2025-09-24 17:00 | q | -170 |  | 2025-04-07 15:53
642 | 3727 | rGcF2XgkgPtqRDM3KJ2D | Normal | 28 | 1.8.5.1.6.1 | 1.8.5.1.6.1 |  | 2025-06-17 17:00 | q | -183 |  | 2024-12-16 08:38
643 | 3728 | Hgqc9wbzS3SDikBm20zt | Normal | 28 | 1.8.5.1.6.3 | 1.8.5.1.6.3 |  | 2025-08-19 17:00 | q | -172 |  | 2025-02-28 09:27
644 | 6653 | K0AYRckqpyO0HzRrxXG6 | Normal | 15 | 1.8.5.1.6.2 | 1.8.5.1.6.2 |  | 2025-07-10 17:00 | q | -183 |  | 2025-01-08 13:33
645 | 6654 | MMK0qYycfTMCrFAZcf8J | Normal | 15 | 1.8.5.1.6.4 | 1.8.5.1.6.4 |  | 2025-09-10 17:00 | q | -170 |  | 2025-03-24 14:21
646 | 6655 | gl8c5oVG5KfrLbsQSFL4 | Normal | 10 | 1.8.5.1.6.5 | 1.8.5.1.6.5 |  | 2025-09-24 17:00 | q | -170 |  | 2025-04-07 15:53
647 | 3729 | Y6b5KP0DE9c4tlFzqxp3 | Summary | 81 | 1.8.5.1.7 | 1.8.5.1.7 |  | 2025-07-03 17:00 | q | -584 |  | 2023-11-27 11:06
648 | 3730 | TswICWhG0Mjj1DenbPW5 | Normal | 28 | 1.8.5.1.7.1 | 1.8.5.1.7.1 |  | 2025-04-17 17:00 | q | -577 |  | 2023-09-18 16:36
649 | 6626 | 9d2gtkuh8SmNZwArNzpn | Normal | 10 | 1.8.5.1.7.4 | 1.8.5.1.7.4 |  | 2025-07-03 17:00 | q | -584 |  | 2023-11-27 11:06
650 | 6627 | QBgG0JxqOymB6vyjKsRZ | Normal | 28 | 1.8.5.1.7.2 | 1.8.5.1.7.2 |  | 2025-05-28 17:00 | q | -581 |  | 2023-10-25 15:22
651 | 6628 | PAI9VZBMaYriaY1wvhOi | Normal | 15 | 1.8.5.1.7.3 | 1.8.5.1.7.3 |  | 2025-06-18 17:00 | q | -582 |  | 2023-11-14 08:25
652 | 3733 | ufu7SWDoeBfTzZW24BQU | Summary | 189 | 1.8.5.1.9 | 1.8.5.1.9 |  | 2025-12-15 17:00 | p | 27 |  | 2026-01-12 08:25
653 | 3734 | cAszcoDUs4YPdXAiXa4B | Milestone | 0 | 1.8.5.1.9.1 | 1.8.5.1.9.1 |  | 2025-03-17 08:00 | q | -588 |  | 2023-08-07 08:00
654 | 3735 | rgqtw8hyurrfag2amXLA | Normal | 109 | 1.8.5.1.9.2 | 1.8.5.1.9.2 |  | 2025-08-19 17:00 | q | -588 |  | 2024-01-09 09:41
655 | 3736 | eIMYQUSTObIc5Lp6kKBE | Normal | 40 | 1.8.5.1.9.3 | 1.8.5.1.9.3 |  | 2025-10-16 17:00 | q | -608 |  | 2024-02-16 08:12
656 | 3737 | z19Wnme0hJcfEI4IfIQR | Normal | 25 | 1.8.5.1.9.4 | 1.8.5.1.9.4 |  | 2025-11-21 17:00 | p | 23 |  | 2025-12-15 14:16
657 | 6657 | uq5fluI8KT8LkPx57ktn | Normal | 10 | 1.8.5.1.9.5 | 1.8.5.1.9.5 |  | 2025-12-08 17:00 | p | 24 |  | 2026-01-02 09:26
658 | 6658 | ktg0XNnAmjjc1caqICt2 | Normal | 5 | 1.8.5.1.9.6 | 1.8.5.1.9.6 |  | 2025-12-15 17:00 | p | 27 |  | 2026-01-12 08:25
659 | 3738 | bohrZqwOTsvUL4DEUnjh | Summary | 139 | 1.8.5.1.10 | 1.8.5.1.10 |  | 2025-10-01 17:00 | q | -586 |  | 2024-02-23 09:07
660 | 3739 | Ba23bBwg4xGpRd3Ht4kS | Normal | 24 | 1.8.5.1.10.1 | 1.8.5.1.10.1 |  | 2025-04-17 17:00 | q | -589 |  | 2023-09-06 09:53
661 | 3740 | lRtbtcrLyr1QGd0laoJi | Normal | 25 | 1.8.5.1.10.2 | 1.8.5.1.10.2 |  | 2025-05-22 17:00 | q | -588 |  | 2023-10-12 14:10
662 | 3741 | V05WnFKB5t2LuixhoKHO | Normal | 25 | 1.8.5.1.10.3 | 1.8.5.1.10.3 |  | 2025-06-30 17:00 | q | -586 |  | 2023-11-22 14:32
663 | 3742 | LRjVz0hoZuIRlQgcLYzs | Normal | 25 | 1.8.5.1.10.6 | 1.8.5.1.10.6 |  | 2025-09-10 17:00 | q | -583 |  | 2024-02-05 11:06
664 | 6648 | Z5T3n0GGVz8PB0IY5TXC | Normal | 10 | 1.8.5.1.10.5 | 1.8.5.1.10.5 |  | 2025-08-05 17:00 | q | -592 |  | 2023-12-22 13:47
665 | 6656 | tqprQgHoroqT051BXug3 | Normal | 15 | 1.8.5.1.10.4 | 1.8.5.1.10.4 |  | 2025-07-22 17:00 | q | -588 |  | 2023-12-12 14:39
666 | 6659 | NN3Qiea1foOxv05JqXnT | Normal | 10 | 1.8.5.1.10.7 | 1.8.5.1.10.7 |  | 2025-09-24 17:00 | q | -586 |  | 2024-02-16 09:31
667 | 6660 | pWIs4hM6SgH2pFjSQ3qo | Normal | 5 | 1.8.5.1.10.8 | 1.8.5.1.10.8 |  | 2025-10-01 17:00 | q | -586 |  | 2024-02-23 09:07
668 | 6642 | A7Bd82G8YCk8VjEZkcvi | Summary | 135 | 1.8.5.1.8 | 1.8.5.1.8 |  | 2026-05-01 17:00 | q | -115 |  | 2026-01-06 13:47
669 | 3731 | 02LiOyWN4DF8GOeNSP5s | Normal | 20 | 1.8.5.1.8.1 | 1.8.5.1.8.1 |  | 2025-11-14 17:00 | q | -613 |  | 2024-03-11 09:57
670 | 3732 | x85AkT9s5HT2a4U2goND | Normal | 20 | 1.8.5.1.8.8 | 1.8.5.1.8.8 |  | 2025-12-15 17:00 | q | -612 |  | 2024-04-12 08:54
671 | 6629 | n59ds33sZr9JNOobmYWE | Normal | 30 | 1.8.5.1.8.2 | 1.8.5.1.8.2 |  | 2025-12-30 17:00 | q | -631 |  | 2024-04-08 11:05
672 | 6630 | y36QmeQSyS7BZflkeM7e | Normal | 10 | 1.8.5.1.8.3 | 1.8.5.1.8.3 |  | 2026-01-14 17:00 | q | -632 |  | 2024-04-22 15:09
673 | 6631 | Ghk1eKq5exIyUH3hdAeR | Normal | 20 | 1.8.5.1.8.4 | 1.8.5.1.8.4 |  | 2026-02-12 17:00 | q | -632 |  | 2024-05-21 08:31
674 | 6632 | 5y36mClzGR7vkSsODb4C | Normal | 15 | 1.8.5.1.8.5 | 1.8.5.1.8.5 |  | 2026-03-06 17:00 | q | -638 |  | 2024-06-06 13:24
675 | 6633 | uS272glxjETpDiVeJyGv | Normal | 20 | 1.8.5.1.8.6 | 1.8.5.1.8.6 |  | 2026-04-03 17:00 | q | -633 |  | 2024-07-09 11:38
676 | 6634 | 65ghvPiwU0AxSKrC11rG | Normal | 20 | 1.8.5.1.8.7 | 1.8.5.1.8.7 |  | 2026-05-01 17:00 | q | -623 |  | 2024-08-16 10:21
677 | 6643 | sKnPCsxlq51dE8cz52fo | Normal | 10 | 1.8.5.1.8.9 | 1.8.5.1.8.9 |  | 2025-12-30 17:00 | q | -614 |  | 2024-04-25 11:25
678 | 6644 | 0NVu6ABxwy3imKaZ2MTJ | Normal | 10 | 1.8.5.1.8.10 | 1.8.5.1.8.10 |  | 2026-01-14 17:00 | q | -8 |  | 2026-01-06 13:47
679 | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Summary | 1 | 1.8.1 | 1.8.1 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
680 | 6082 | YsSSuERf5VIDKO5m8eZo | Normal | 1 | 1.8.1.1 | 1.8.1.1 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
681 | 6313 | 8HYxn50EKf1DU0fX0MF7 | Summary | 391 | 1.8.4 | 1.8.4 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
682 | 5516 | dd6fm1lW4tBXPtNV5RGW | Summary | 391 | 1.8.4.1 | 1.8.4.1 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
683 | 5517 | IHfroMkwx3TZoTXYbBOK | Normal | 40 | 1.8.4.1.1 | 1.8.4.1.1 |  | 2025-05-14 17:00 | q | -609 |  | 2023-09-13 16:06
684 | 5518 | V0a5XEJ0jxIkhnpEDg8e | Normal | 40 | 1.8.4.1.2 | 1.8.4.1.2 |  | 2025-05-14 17:00 | q | -579 |  | 2023-10-13 08:50
685 | 5519 | D5sl3M5NpO77EU7TPYT0 | Normal | 40 | 1.8.4.1.3 | 1.8.4.1.3 |  | 2025-05-14 17:00 | q | -594 |  | 2023-09-28 09:53
686 | 5523 | APkwTVep7mUhgmcCl4NB | Milestone | 0 | 1.8.4.1.4 | 1.8.4.1.4 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
687 | 5527 | Mw5Re8SivA42laH7UhJE | Milestone | 0 | 1.8.4.1.5 | 1.8.4.1.5 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
688 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 2026-10-05 12:00 | p | 927 |  | 2029-04-20 09:39
689 | 5331 | emM9tIPUc6I6BRQdDkUj | Summary | 325 | 1.9.3 | 1.9.3 |  | 2026-03-16 08:30 | q | -31 |  | 2026-02-12 16:16
690 | 5332 | Jas5wmBgln6JvMRLtRUk | Summary | 110 | 1.9.3.1 | 1.9.3.1 |  | 2026-03-16 08:30 | q | -31 |  | 2026-02-12 16:16
691 | 5333 | NEZJUiuEFBeqDBEbXbzQ | Milestone | 0 | 1.9.3.1.1 | 1.9.3.1.1 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
692 | 5334 | 5Bt8vyiG2PJ2FKCjQPP1 | Summary | 74 | 1.9.3.1.2 | 1.9.3.1.2 |  | 2026-01-23 08:30 | q | -27 |  | 2025-12-26 11:55
693 | 6471 | xmZvSzAhf2D9ir29atKO | Normal | 8 | 1.9.3.1.2.1 | 1.9.3.1.2.1 |  | 2025-10-20 08:30 | q | -33 |  | 2025-09-16 10:33
694 | 6472 | j0VQ7fJsNHb1HpOVRoJN | Normal | 7 | 1.9.3.1.2.2 | 1.9.3.1.2.2 |  | 2025-10-29 08:30 | q | -32 |  | 2025-09-26 09:27
695 | 6473 | FN1N5cBOnOQJN0lvtY6J | Normal | 5 | 1.9.3.1.2.3 | 1.9.3.1.2.3 |  | 2025-11-05 08:30 | q | -32 |  | 2025-10-03 14:29
696 | 6474 | k77H7bJ7aRKhBrZeZFzu | Normal | 10 | 1.9.3.1.2.4 | 1.9.3.1.2.4 |  | 2025-11-20 08:30 | q | -30 |  | 2025-10-20 14:59
697 | 6475 | TkBVMCiZTEhYxjcnMNRI | Normal | 8 | 1.9.3.1.2.5 | 1.9.3.1.2.5 |  | 2025-12-03 08:30 | q | -35 |  | 2025-10-28 16:00
698 | 6476 | HdsfOo0UbW7iVGjY7L1O | Normal | 10 | 1.9.3.1.2.6 | 1.9.3.1.2.6 |  | 2025-12-17 08:30 | q | -29 |  | 2025-11-17 14:43
699 | 6477 | m1G8PrmdvRxZwBbLlVUQ | Normal | 7 | 1.9.3.1.2.7 | 1.9.3.1.2.7 |  | 2025-12-29 08:30 | q | -32 |  | 2025-11-26 14:19
700 | 6478 | ZDDqpCGw2ELQiAxZVJFo | Normal | 7 | 1.9.3.1.2.8 | 1.9.3.1.2.8 |  | 2026-01-07 08:30 | q | -29 |  | 2025-12-08 08:48
701 | 6479 | i51TyrBkECB0t7wKJruE | Normal | 7 | 1.9.3.1.2.9 | 1.9.3.1.2.9 |  | 2026-01-16 08:30 | q | -28 |  | 2025-12-18 11:40
702 | 6480 | XeKgBzwPereNdZmXnTFt | Normal | 5 | 1.9.3.1.2.10 | 1.9.3.1.2.10 |  | 2026-01-23 08:30 | q | -27 |  | 2025-12-26 11:55
703 | 5335 | fBEkx0xCtVpw1OeE4jLB | Summary | 25 | 1.9.3.1.3 | 1.9.3.1.3 |  | 2026-02-27 08:30 | q | -29 |  | 2026-01-28 09:46
704 | 5336 | FIhKbBOHnlTp0loBBfvV | Normal | 3 | 1.9.3.1.3.1 | 1.9.3.1.3.1 |  | 2026-01-28 08:30 | q | -26 |  | 2026-01-01 08:58
705 | 5337 | TPAbtCx4KhMQiN0iVD1F | Normal | 0 | 1.9.3.1.3.2 | 1.9.3.1.3.2 |  | 2026-01-23 13:06 | q | -25 |  | 2025-12-29 08:14
706 | 5338 | NXWa8B3rzsUFws6lYttF | Normal | 5 | 1.9.3.1.3.3 | 1.9.3.1.3.3 |  | 2026-01-30 08:30 | q | -27 |  | 2026-01-02 14:46
707 | 5339 | o98eRuEZGwoxxa1Byl7H | Normal | 5 | 1.9.3.1.3.4 | 1.9.3.1.3.4 |  | 2026-01-30 08:30 | q | -27 |  | 2026-01-02 13:17
708 | 5340 | lQJTDBnvPE8mTPnPre3v | Normal | 10 | 1.9.3.1.3.5 | 1.9.3.1.3.5 |  | 2026-02-13 08:30 | q | -29 |  | 2026-01-14 10:30
709 | 5341 | nevxwfefPkBzu42CDbNd | Normal | 10 | 1.9.3.1.3.6 | 1.9.3.1.3.6 |  | 2026-02-27 08:30 | q | -29 |  | 2026-01-28 09:46
710 | 5342 | s0JiBiXDLP6oybWmkZ43 | Normal | 6 | 1.9.3.1.4 | 1.9.3.1.4 |  | 2026-03-09 08:30 | q | -31 |  | 2026-02-05 15:31
711 | 5343 | NROXqcLUoQ0RLz64rMVc | Normal | 5 | 1.9.3.1.5 | 1.9.3.1.5 |  | 2026-03-16 08:30 | q | -31 |  | 2026-02-12 16:16
712 | 5344 | Kw3Fj6kwk5uOl7tQyqrL | Milestone | 0 | 1.9.3.1.6 | 1.9.3.1.6 |  | 2026-03-16 08:30 | q | -31 |  | 2026-02-12 16:16
713 | 6275 | OL3lkJGtK3tkk0d4SBRn | Summary | 288 | 1.9.9 | 1.9.9 |  | 2026-10-05 12:00 | p | 927 |  | 2029-04-20 09:27
714 | 795 | 85yV4lhIxXIziyB5R2QA | Normal | 1 | 1.9.9.1 | 1.9.9.1 |  | 2026-09-17 12:00 | p | 929 |  | 2029-04-04 11:08
715 | 844 | 1qfp8o9PQxr9vZvO7S5k | Normal | 1 | 1.9.9.4 | 1.9.9.4 |  | 2026-10-05 12:00 | p | 927 |  | 2029-04-20 09:27
716 | 845 | U1v5hScHSOPPxa5ohjfI | Summary | 189 | 1.9.9.7 | 1.9.9.7 |  | 2025-12-31 17:00 | p | 27 |  | 2026-01-28 08:39
717 | 847 | JilJNxxBcx7QrT5PcKLM | Summary | 189 | 1.9.9.7.2 | 1.9.9.7.2 |  | 2025-12-31 17:00 | p | 27 |  | 2026-01-28 08:39
718 | 866 | 0rLFG0X22Uukcn0axQTO | Normal | 50 | 1.9.9.7.2.6 | 1.9.9.7.2.6 |  | 2025-06-25 17:00 | p | 26 |  | 2025-07-22 15:07
719 | 869 | 8QCM3LZ8SN5y0jCLtGNh | Summary | 129 | 1.9.9.7.2.7 | 1.9.9.7.2.7 |  | 2025-12-31 17:00 | p | 27 |  | 2026-01-28 08:39
720 | 6419 | NORPsF566zq8VZyN1UzF | Normal | 10 | 1.9.9.7.2.7.1 | 1.9.9.7.2.7.1 |  | 2025-07-10 17:00 | p | 26 |  | 2025-08-06 11:19
721 | 6420 | 043wOhyyEd8vJkuUBkFf | Normal | 40 | 1.9.9.7.2.7.2 | 1.9.9.7.2.7.2 |  | 2025-09-05 17:00 | p | 23 |  | 2025-09-29 08:24
722 | 6421 | JZROXyECnTBG3SBjYZJ8 | Normal | 79 | 1.9.9.7.2.7.3 | 1.9.9.7.2.7.3 |  | 2025-12-31 17:00 | p | 27 |  | 2026-01-28 08:39
723 | 6418 | W9pbV5i9WFkdVEGtW75H | Normal | 45 | 1.9.9.7.2.5 | 1.9.9.7.2.5 |  | 2025-04-14 17:00 | p | 23 |  | 2025-05-08 13:10
724 | 870 | m3oEXpasu7ssfpw9dqLv | Summary | 267 | 1.9.9.14 | 1.9.9.14 |  | 2026-05-22 12:00 | p | 934 |  | 2028-12-11 13:54
725 | 4667 | gXRr1908PexMoLIDosFv | Normal | 100 | 1.9.9.14.3 | 1.9.9.14.3 |  | 2025-11-21 17:00 | p | 53 |  | 2026-01-14 08:57
726 | 4668 | G3SLCzd88WLMRnAF5Et7 | Normal | 0 | 1.9.9.14.4 | 1.9.9.14.4 |  | 2026-04-20 12:00 | p | 935 |  | 2028-11-10 15:58
727 | 4669 | aeClBbTsJ3qrKHWqQ1Rw | Normal | 40 | 1.9.9.14.5 | 1.9.9.14.5 |  | 2026-01-22 17:00 | p | 42 |  | 2026-03-06 16:15
728 | 4679 | rpzkOhA603pApmNdMeVE | Normal | 0 | 1.9.9.14.6 | 1.9.9.14.6 |  | 2026-05-22 12:00 | p | 934 |  | 2028-12-11 13:54
729 | 5786 | d3N6cqydEgoPO1XBMSTu | Normal | 7 | 1.9.9.14.1 | 1.9.9.14.1 |  | 2025-02-19 17:00 | p | 28 |  | 2025-03-20 08:03
730 | 5787 | r6JEZEKCpBbNZRe1W7Ef | Normal | 91 | 1.9.9.14.2 | 1.9.9.14.2 |  | 2025-06-30 17:00 | p | 58 |  | 2025-08-28 14:51
731 | 899 | w1GWQdUx9oG06oopRYZx | Summary | 24 | 1.9.9.15 | 1.9.9.15 |  | 2026-05-21 17:00 | p | 935 |  | 2028-12-12 15:12
732 | 900 | ANUK0HdVlI2Jd5hSzs0f | Milestone | 0 | 1.9.9.15.1 | 1.9.9.15.1 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
733 | 901 | HcFqHITfVdYMyzVb3S8v | Normal | 18 | 1.9.9.15.2 | 1.9.9.15.2 |  | 2026-05-13 17:00 | p | 939 |  | 2028-12-08 16:02
734 | 902 | nIjAIVHCOoi1ijXym0cI | Normal | 3 | 1.9.9.15.3 | 1.9.9.15.3 |  | 2026-04-22 17:00 | p | 937 |  | 2028-11-15 11:13
735 | 903 | UDGopgZ2sb1QsQEooZ9G | Normal | 8 | 1.9.9.15.4 | 1.9.9.15.4 |  | 2026-05-04 17:00 | p | 934 |  | 2028-11-24 11:14
736 | 904 | 4CH3NSJx1luiHbrrAEJg | Normal | 2 | 1.9.9.15.5 | 1.9.9.15.5 |  | 2026-05-15 17:00 | p | 941 |  | 2028-12-12 15:12
737 | 905 | MxRWNVEH6ZVBPqNnA2hI | Normal | 8 | 1.9.9.15.6 | 1.9.9.15.6 |  | 2026-05-14 17:00 | p | 934 |  | 2028-12-04 09:48
738 | 906 | PL0zn2U2NPPXQqakkHLb | Normal | 5 | 1.9.9.15.7 | 1.9.9.15.7 |  | 2026-05-21 17:00 | p | 931 |  | 2028-12-08 16:08
739 | 907 | 5mTVpVcHzmsYLVY8xpKs | Normal | 5 | 1.9.9.15.8 | 1.9.9.15.8 |  | 2026-05-21 17:00 | p | 934 |  | 2028-12-11 08:48
740 | 914 | q0UeyWaeMXFoeUDjjzhX | Summary | 18 | 1.9.9.5 | 1.9.9.5 |  | 2025-09-05 17:00 | p | 941 |  | 2028-04-04 14:54
741 | 915 | jxzEE3EBeGWt1nE3uHcj | Summary | 18 | 1.9.9.5.1 | 1.9.9.5.1 |  | 2025-09-05 17:00 | p | 941 |  | 2028-04-04 14:54
742 | 916 | d4bxhxtQW3GaLrDrUlf9 | Normal | 17 | 1.9.9.5.1.1 | 1.9.9.5.1.1 |  | 2025-09-04 17:00 | p | 941 |  | 2028-04-03 11:32
743 | 917 | mbDdHZHm9OoYye329Ue6 | Normal | 1 | 1.9.9.5.1.2 | 1.9.9.5.1.2 |  | 2025-09-05 17:00 | p | 941 |  | 2028-04-04 14:54
744 | 4538 | aTyUglf0WPX6H8Zd17Iq | Summary | 71 | 1.9.9.16 | 1.9.9.16 |  | 2026-07-31 12:00 | p | 929 |  | 2029-02-14 13:47
745 | 6509 | sp3XFaPtGgzrVeC1wvvV | Normal | 10 | 1.9.9.16.3 | 1.9.9.16.3 |  | 2026-06-09 12:00 | p | 926 |  | 2028-12-22 10:04
746 | 6510 | dar9hgzhSUYJxC1MeoTS | Normal | 10 | 1.9.9.16.4 | 1.9.9.16.4 |  | 2026-06-09 12:00 | p | 933 |  | 2028-12-28 15:13
747 | 6513 | IG8fHoH3vjERJ6iSB3Rj | Normal | 36 | 1.9.9.16.5 | 1.9.9.16.5 |  | 2026-07-31 12:00 | p | 929 |  | 2029-02-14 13:47
748 | 6514 | imV319lPgBwI8oLVT5sB | Normal | 1 | 1.9.9.16.2 | 1.9.9.16.2 |  | 2026-05-26 12:00 | p | 931 |  | 2028-12-12 13:13
749 | 6515 | a8Kdm3F6uLeIN4SEhwX9 | Normal | 1 | 1.9.9.16.1 | 1.9.9.16.1 |  | 2026-04-21 12:00 | p | 937 |  | 2028-11-13 14:53
750 | 5783 | BOvEGIzyTacp1vvD9v7M | Normal | 1 | 1.9.9.2 | 1.9.9.2 |  | 2026-01-02 17:00 | p | 26 |  | 2026-01-29 08:16
751 | 6128 | 7jXaekqqhUCDWSDfnxzo | Summary | 28 | 1.7.4.2 | 1.7.4.2 |  | 2025-03-10 17:00 | p | 0 |  | 2025-03-11 10:42
752 | 6130 | 3AAePL8Vt5bI7qDxsaDX | Normal | 20 | 1.7.4.2.3 | 1.7.4.2.3 |  | 2025-03-10 17:00 | p | 0 |  | 2025-03-11 10:42
753 | 6685 | 2nkdQcaVv7LgM8d4dFld | Summary | 1 | 1.9.9.12 | 1.9.9.12 |  | 2025-08-29 17:00 | q | -164 |  | 2025-03-18 10:12
754 | 6687 | RiyOBd4mBIE5Cq6C0A4h | Normal | 1 | 1.9.9.12.1 | 1.9.9.12.1 |  | 2025-08-29 17:00 | q | -164 |  | 2025-03-18 10:12
755 | 6686 | IDiuvzfQRXyu7MCMX1jW | Normal | 5 | 1.9.9.11 | 1.9.9.11 |  | 2025-02-14 17:00 | p | 30 |  | 2025-03-17 11:08
756 | 7388 | subTjNOw9tjXphx2xXzW | Summary | 324 | 1.9.9.13 | 1.9.9.13 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
757 | 7389 | xTfJP5JFEqXIDmLDdKVZ | Summary | 43 | 1.9.9.13.1 | 1.9.9.13.1 |  | 2025-08-19 17:00 | p | 943 |  | 2028-03-20 09:05
758 | 7390 | GV26YG775A5KHHrrMIRV | Summary | 32 | 1.9.9.13.1.1 | 1.9.9.13.1.1 |  | 2025-08-05 12:00 | p | 940 |  | 2028-03-03 08:58
759 | 7391 | UumEMUqxjwvZXtHBx1rg | Normal | 3 | 1.9.9.13.1.1.1 | 1.9.9.13.1.1.1 |  | 2025-06-23 17:00 | p | 933 |  | 2028-01-13 08:07
760 | 7392 | ylVP19AJuwY485wgDJEG | Normal | 10 | 1.9.9.13.1.1.2 | 1.9.9.13.1.1.2 |  | 2025-07-08 12:00 | p | 931 |  | 2028-01-25 14:39
761 | 7393 | RzIyrLZKRoqlWdOJYpGf | Normal | 3 | 1.9.9.13.1.1.3 | 1.9.9.13.1.1.3 |  | 2025-07-08 17:00 | p | 932 |  | 2028-01-27 11:46
762 | 7394 | zHoRZ9fggWfe9FGnA954 | Normal | 10 | 1.9.9.13.1.1.4 | 1.9.9.13.1.1.4 |  | 2025-07-22 12:00 | p | 939 |  | 2028-02-16 15:40
763 | 7395 | PMjQe1vYJ6mxUbNABucF | Normal | 3 | 1.9.9.13.1.1.5 | 1.9.9.13.1.1.5 |  | 2025-07-22 17:00 | p | 932 |  | 2028-02-10 13:38
764 | 7396 | gQKdIVV4LZyvHUAfFFFg | Normal | 10 | 1.9.9.13.1.1.6 | 1.9.9.13.1.1.6 |  | 2025-08-05 12:00 | p | 940 |  | 2028-03-03 08:58
765 | 7397 | gmOEJCOmO6SQ6HMlGXfq | Summary | 12 | 1.9.9.13.1.2 | 1.9.9.13.1.2 |  | 2025-08-19 17:00 | p | 943 |  | 2028-03-20 09:05
766 | 7398 | ItOQSxoXEYWD5clVNK0n | Normal | 3 | 1.9.9.13.1.2.1 | 1.9.9.13.1.2.1 |  | 2025-08-06 17:00 | p | 931 |  | 2028-02-24 11:48
767 | 7399 | cXpFrNuZR7O8wPV6KZK3 | Normal | 9 | 1.9.9.13.1.2.2 | 1.9.9.13.1.2.2 |  | 2025-08-19 17:00 | p | 943 |  | 2028-03-20 09:05
768 | 7400 | VGtguPWpaIPmF0Ojsz8a | Summary | 176 | 1.9.9.13.2 | 1.9.9.13.2 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
769 | 7401 | H3MyBOTVJ4MGxcXcavMD | Normal | 2 | 1.9.9.13.2.1 | 1.9.9.13.2.1 |  | 2025-08-06 17:00 | p | 942 |  | 2028-03-06 15:47
770 | 7402 | pMiEhGou1QDK96DPu7Q8 | Normal | 1 | 1.9.9.13.2.2 | 1.9.9.13.2.2 |  | 2025-08-20 17:00 | p | 943 |  | 2028-03-21 09:16
771 | 7403 | pHZBXvaYVwug2p7gN6jp | Summary | 17 | 1.9.9.13.2.3 | 1.9.9.13.2.3 |  | 2025-09-15 17:00 | p | 939 |  | 2028-04-12 13:04
772 | 7404 | EvHLT3cR3tYYGwcq6SC1 | Normal | 5 | 1.9.9.13.2.3.1 | 1.9.9.13.2.3.1 |  | 2025-08-27 17:00 | p | 943 |  | 2028-03-28 09:50
773 | 7405 | 5GpI6xkgfIoVOnU9egD8 | Normal | 12 | 1.9.9.13.2.3.2 | 1.9.9.13.2.3.2 |  | 2025-09-15 17:00 | p | 939 |  | 2028-04-12 13:04
774 | 7406 | WxzG2sAIbVYYiem4v3mk | Normal | 12 | 1.9.9.13.2.3.3 | 1.9.9.13.2.3.3 |  | 2025-09-15 17:00 | p | 938 |  | 2028-04-11 14:45
775 | 7407 | 0eiyRK1I5mgUCdtpXpqY | Summary | 44 | 1.9.9.13.2.4 | 1.9.9.13.2.4 |  | 2025-11-18 17:00 | p | 937 |  | 2028-06-13 08:48
776 | 7408 | uKngouP2QMMQmu6HFm0I | Normal | 11 | 1.9.9.13.2.4.1 | 1.9.9.13.2.4.1 |  | 2025-09-30 17:00 | p | 938 |  | 2028-04-26 11:31
777 | 7409 | C7eZzAQkBbKewE4wmmOD | Normal | 11 | 1.9.9.13.2.4.2 | 1.9.9.13.2.4.2 |  | 2025-10-16 17:00 | p | 936 |  | 2028-05-10 14:48
778 | 7410 | VCdEPtbQjRcgNUnNprkZ | Normal | 11 | 1.9.9.13.2.4.3 | 1.9.9.13.2.4.3 |  | 2025-10-31 17:00 | p | 936 |  | 2028-05-25 13:17
779 | 7411 | OzHccTXr25Mf4pmiIMuT | Normal | 11 | 1.9.9.13.2.4.4 | 1.9.9.13.2.4.4 |  | 2025-11-18 17:00 | p | 937 |  | 2028-06-13 08:48
780 | 7412 | obz02flxb00pYjKUpMNx | Normal | 12 | 1.9.9.13.2.5 | 1.9.9.13.2.5 |  | 2025-12-12 17:00 | p | 930 |  | 2028-06-30 09:58
781 | 7413 | xazO1XwNp5eROWJmaREL | Summary | 36 | 1.9.9.13.2.6 | 1.9.9.13.2.6 |  | 2026-01-12 17:00 | p | 938 |  | 2028-08-08 14:51
782 | 7414 | DrM34eAIT9imz4vRHbHm | Normal | 2 | 1.9.9.13.2.6.1 | 1.9.9.13.2.6.1 |  | 2025-11-20 17:00 | p | 937 |  | 2028-06-15 09:53
783 | 7415 | RsULMViXRZoYahxlMUQ4 | Normal | 20 | 1.9.9.13.2.6.2 | 1.9.9.13.2.6.2 |  | 2025-12-19 17:00 | p | 942 |  | 2028-07-19 11:22
784 | 7416 | U8irVJqpjJwQWU5FcpMo | Normal | 3 | 1.9.9.13.2.6.3 | 1.9.9.13.2.6.3 |  | 2025-12-24 17:00 | p | 942 |  | 2028-07-24 15:52
785 | 7417 | yrCdbpyUp4mqkbXiv5Nc | Normal | 6 | 1.9.9.13.2.6.4 | 1.9.9.13.2.6.4 |  | 2026-01-05 17:00 | p | 938 |  | 2028-08-01 09:30
786 | 7418 | Iw5sTi596kP8d52cBWYm | Normal | 5 | 1.9.9.13.2.6.5 | 1.9.9.13.2.6.5 |  | 2026-01-12 17:00 | p | 938 |  | 2028-08-08 14:51
787 | 7419 | s9reBpLseCBnslseiKA6 | Normal | 2 | 1.9.9.13.2.7 | 1.9.9.13.2.7 |  | 2026-01-14 17:00 | p | 939 |  | 2028-08-11 09:38
788 | 7420 | ia01m1zWF4qAvVLVg5It | Summary | 54 | 1.9.9.13.2.8 | 1.9.9.13.2.8 |  | 2026-04-02 17:00 | p | 935 |  | 2028-10-24 13:16
789 | 7421 | 5PvQN5TGe8y7KbK2rRhO | Normal | 8 | 1.9.9.13.2.8.1 | 1.9.9.13.2.8.1 |  | 2026-01-27 17:00 | p | 938 |  | 2028-08-23 13:49
790 | 7422 | fj19MvsSAfWHeVGXiA1H | Normal | 5 | 1.9.9.13.2.8.2 | 1.9.9.13.2.8.2 |  | 2026-01-22 17:00 | p | 937 |  | 2028-08-17 15:34
791 | 7423 | hs9Gt4WgG9pENnEIaC7X | Normal | 14 | 1.9.9.13.2.8.3 | 1.9.9.13.2.8.3 |  | 2026-02-17 17:00 | p | 938 |  | 2028-09-13 10:12
792 | 7424 | WqCakGr8mHgCENNWHHjW | Normal | 5 | 1.9.9.13.2.8.4 | 1.9.9.13.2.8.4 |  | 2026-02-03 17:00 | p | 939 |  | 2028-08-31 09:22
793 | 7425 | Pv27HXd826jlfuUJmTLH | Normal | 20 | 1.9.9.13.2.8.5 | 1.9.9.13.2.8.5 |  | 2026-03-17 17:00 | p | 936 |  | 2028-10-09 10:02
794 | 7426 | UjcYgNHyPV73fWy2GGNA | Normal | 5 | 1.9.9.13.2.8.6 | 1.9.9.13.2.8.6 |  | 2026-02-24 17:00 | p | 939 |  | 2028-09-21 09:53
795 | 7427 | 5QMAV8W19uO0knxuRgYc | Normal | 6 | 1.9.9.13.2.8.7 | 1.9.9.13.2.8.7 |  | 2026-03-25 17:00 | p | 936 |  | 2028-10-16 17:00
796 | 7428 | C3roUkJ3GEdxAvfnxnUE | Normal | 6 | 1.9.9.13.2.8.8 | 1.9.9.13.2.8.8 |  | 2026-03-25 17:00 | p | 937 |  | 2028-10-18 08:20
797 | 7429 | GMfJSktlv5oUXA5LFNgA | Normal | 6 | 1.9.9.13.2.8.9 | 1.9.9.13.2.8.9 |  | 2026-04-02 17:00 | p | 935 |  | 2028-10-24 13:16
798 | 7430 | AjX0fOJfuCWTWcoFWrZe | Summary | 11 | 1.9.9.13.2.9 | 1.9.9.13.2.9 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
799 | 7431 | YKkcKAxBNBkRs3Gs0cxp | Normal | 7 | 1.9.9.13.2.9.1 | 1.9.9.13.2.9.1 |  | 2026-04-13 17:00 | p | 933 |  | 2028-11-02 14:33
800 | 7432 | HbmHLQTrqR87hE03VIdq | Normal | 3 | 1.9.9.13.2.9.2 | 1.9.9.13.2.9.2 |  | 2026-04-07 17:00 | p | 933 |  | 2028-10-27 11:33
801 | 7433 | FxBsJSw4ZNEIyIQA8bL9 | Normal | 8 | 1.9.9.13.2.9.3 | 1.9.9.13.2.9.3 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
802 | 7434 | MkjgnYEnwrIrITdXMEl9 | Milestone | 0 | 1.9.9.13.3 | 1.9.9.13.3 |  | 2026-07-31 12:00 | p | 929 |  | 2029-02-14 13:47
803 | 7435 | nSo6tYchIu2Aw4YtE45u | Summary | 44 | 1.9.9.13.4 | 1.9.9.13.4 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
804 | 7436 | Y83lvWkQwfsc3dMGwfVN | Summary | 30 | 1.9.9.13.4.1 | 1.9.9.13.4.1 |  | 2026-09-14 12:00 | p | 928 |  | 2029-03-30 14:22
805 | 7437 | E8EwVgjFQaEPGP66WsCb | Summary | 30 | 1.9.9.13.4.1.1 | 1.9.9.13.4.1.1 |  | 2026-09-14 12:00 | p | 919 |  | 2029-03-21 15:23
806 | 7438 | y2P0mgWq1uFkM4aVxtQJ | Normal | 15 | 1.9.9.13.4.1.1.1 | 1.9.9.13.4.1.1.1 |  | 2026-08-21 12:00 | p | 926 |  | 2029-03-05 08:26
807 | 7439 | nsJKxwZOWJc3LdYsNOwr | Normal | 5 | 1.9.9.13.4.1.1.2 | 1.9.9.13.4.1.1.2 |  | 2026-08-28 12:00 | p | 924 |  | 2029-03-09 14:27
808 | 7440 | 3ZzL4TktDwncii0hY2dA | Normal | 10 | 1.9.9.13.4.1.1.3 | 1.9.9.13.4.1.1.3 |  | 2026-09-14 12:00 | p | 919 |  | 2029-03-21 15:23
809 | 7441 | IcgrxiRjEYJLwuugm8N7 | Summary | 30 | 1.9.9.13.4.1.2 | 1.9.9.13.4.1.2 |  | 2026-09-14 12:00 | p | 928 |  | 2029-03-30 14:22
810 | 7442 | B8zfbswYxyRxHa21jaE6 | Normal | 15 | 1.9.9.13.4.1.2.1 | 1.9.9.13.4.1.2.1 |  | 2026-08-21 12:00 | p | 929 |  | 2029-03-08 09:14
811 | 7443 | lvFKaF8Jtq8DkkB0s9nv | Normal | 15 | 1.9.9.13.4.1.2.2 | 1.9.9.13.4.1.2.2 |  | 2026-09-14 12:00 | p | 928 |  | 2029-03-30 14:22
812 | 7444 | 419IszMaZW6XNIQptprk | Normal | 20 | 1.9.9.13.4.1.3 | 1.9.9.13.4.1.3 |  | 2026-08-28 12:00 | p | 936 |  | 2029-03-21 15:57
813 | 7445 | oNfFp4VAwKEpoSujTbHZ | Normal | 10 | 1.9.9.13.4.1.4 | 1.9.9.13.4.1.4 |  | 2026-08-14 12:00 | p | 931 |  | 2029-03-02 13:35
814 | 7446 | NnBZUSVumxDXwVdCLN8g | Summary | 12 | 1.9.9.13.4.2 | 1.9.9.13.4.2 |  | 2026-09-30 12:00 | p | 930 |  | 2029-04-17 15:30
815 | 7447 | CAsJ3atkVCS14hehUB9Y | Normal | 4 | 1.9.9.13.4.2.1 | 1.9.9.13.4.2.1 |  | 2026-09-18 12:00 | p | 930 |  | 2029-04-05 15:42
816 | 7448 | 8tMCh2h8AwE53TPPkfEv | Normal | 3 | 1.9.9.13.4.2.2 | 1.9.9.13.4.2.2 |  | 2026-09-21 12:00 | p | 928 |  | 2029-04-06 13:07
817 | 7449 | LaZxXVdUnGzqswRGUiV5 | Normal | 7 | 1.9.9.13.4.2.3 | 1.9.9.13.4.2.3 |  | 2026-09-30 12:00 | p | 930 |  | 2029-04-17 15:30
818 | 7450 | F3vtt1T8lz7mQWFPgUKT | Normal | 2 | 1.9.9.13.4.3 | 1.9.9.13.4.3 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
819 | 7451 | nShmtMdGhMi3SzNeAZjW | Milestone | 0 | 1.9.9.13.4.4 | 1.9.9.13.4.4 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
820 | 7510 | 4i5VLTIa98HteWhFzYjv | Normal | 3 | 1.7.10.24 | 1.7.10.24 |  | 2025-06-17 17:00 | p | 933 |  | 2028-01-07 16:28
821 | 7511 | tHPdmsBqm9kHM69dtq3h | Normal | 7 | 1.7.10.25 | 1.7.10.25 |  | 2025-07-02 17:00 | p | 935 |  | 2028-01-24 08:24
822 | 7512 | hmOTDv9qQbSDcHudIm9x | Normal | 7 | 1.7.10.26 | 1.7.10.26 |  | 2025-07-17 17:00 | p | 934 |  | 2028-02-07 14:23
823 | 7513 | NbiRgc4Tdvxa900kw7Xq | Normal | 8 | 1.7.10.27 | 1.7.10.27 |  | 2025-08-01 17:00 | p | 933 |  | 2028-02-21 11:14
824 | 7539 | ROucR7pug9aGzObG8pvW | Normal | 1 | 1.7.10.8 | 1.7.10.8 |  | 2025-02-28 17:00 | q | -570 |  | 2023-08-08 08:37
825 | 7540 | njszlznNRnCyRW2hgoMI | Normal | 10 | 1.7.10.9 | 1.7.10.9 |  | 2025-03-14 17:00 | q | -570 |  | 2023-08-22 10:22
826 | 7541 | R63tw5xkvmDGiWpIPQRa | Normal | 1 | 1.7.10.10 | 1.7.10.10 |  | 2025-03-31 17:00 | q | -601 |  | 2023-08-08 08:07
827 | 7542 | E3YdLEfamF0eZCISJiqw | Normal | 10 | 1.7.10.11 | 1.7.10.11 |  | 2025-04-25 17:00 | q | -616 |  | 2023-08-18 11:21
828 | 7543 | nhpJxewK7uClQLzGXJQJ | Normal | 1 | 1.7.10.12 | 1.7.10.12 |  | 2025-05-30 17:00 | q | -661 |  | 2023-08-08 10:06
829 | 7544 | cfuUTFyz3WOPAOOiNQOb | Normal | 1 | 1.7.10.13 | 1.7.10.13 |  | 2025-05-30 17:00 | q | -662 |  | 2023-08-07 15:37
830 | 6279 | p7EJXT1muDSglD2OZLFH | Summary | 274 | 1.9.7 | 1.9.7 |  | 2026-09-16 12:00 | p | 929 |  | 2029-04-03 11:47
831 | 1484 | 6ARiGRg3KLswRpJLOmGD | Summary | 229 | 1.9.7.18 | 1.9.7.18 |  | 2025-11-04 17:00 | q | -222 |  | 2025-03-27 10:18
832 | 1485 | R0QJsNVi0JzXq4FadBdS | Normal | 20 | 1.9.7.18.4 | 1.9.7.18.4 |  | 2025-07-17 17:00 | q | -2820 |  | 2017-10-27 15:51
833 | 1486 | 9VYbXOz4xuMas0igEBkB | Summary | 56 | 1.9.7.18.6 | 1.9.7.18.6 |  | 2025-11-04 17:00 | q | -2812 |  | 2018-02-22 16:01
834 | 6540 | BF294XdCZHw2CEg81bOs | Normal | 19 | 1.9.7.18.6.1 | 1.9.7.18.6.1 |  | 2025-09-11 17:00 | q | -2814 |  | 2017-12-28 16:20
835 | 6541 | X8phwYugZBkIbn0OysQW | Normal | 19 | 1.9.7.18.6.2 | 1.9.7.18.6.2 |  | 2025-10-08 17:00 | q | -2809 |  | 2018-01-29 14:01
836 | 6542 | fphO3nZhiS43G9CLfKfB | Normal | 18 | 1.9.7.18.6.3 | 1.9.7.18.6.3 |  | 2025-11-04 17:00 | q | -2812 |  | 2018-02-22 16:01
837 | 1489 | pYq4lU1lCt1U75q3gu6M | Normal | 11 | 1.9.7.18.1 | 1.9.7.18.1 |  | 2025-02-26 17:00 | p | 28 |  | 2025-03-27 10:18
838 | 1490 | hF9FI1LNvFfgTTXhqPsR | Normal | 77 | 1.9.7.18.2 | 1.9.7.18.2 |  | 2025-06-16 17:00 | q | -2820 |  | 2017-09-26 16:07
839 | 1491 | XpTPefWn9TT3C06gw8rA | Normal | 1 | 1.9.7.18.3 | 1.9.7.18.3 |  | 2025-06-17 17:00 | q | -2819 |  | 2017-09-28 08:18
840 | 1495 | 0kid3Dd3U5gCQNrt2pwY | Normal | 1 | 1.9.7.18.8 | 1.9.7.18.8 |  | 2025-02-26 17:00 | q | -22 |  | 2025-02-04 08:47
841 | 1504 | ndaml8HRsqEWzWIKrI7h | Normal | 5 | 1.9.7.18.10 | 1.9.7.18.10 |  | 2025-03-04 17:00 | q | -22 |  | 2025-02-10 11:29
842 | 4587 | 5uS9ktvplxYkrLheR3Q9 | Normal | 20 | 1.9.7.18.5 | 1.9.7.18.5 |  | 2025-08-14 17:00 | q | -2810 |  | 2017-12-04 08:30
843 | 1496 | 5t2MhilpkZRDQA3VTcGS | Normal | 48 | 1.9.7.7 | 1.9.7.7 |  | 2025-05-05 17:00 | q | -20 |  | 2025-04-15 16:33
844 | 1505 | 4c3z8pWafVxAWNC1MpC9 | Normal | 106 | 1.9.7.8 | 1.9.7.8 |  | 2025-08-04 17:00 | q | -27 |  | 2025-07-08 16:49
845 | 1508 | SDZ1pqYbdynEzXZrWujj | Normal | 30 | 1.9.7.6 | 1.9.7.6 |  | 2025-03-24 17:00 | p | 23 |  | 2025-04-17 10:54
846 | 1529 | WOa3B8SPUOSM5ThLE2Jo | Summary | 69 | 1.9.7.14 | 1.9.7.14 |  | 2025-07-16 17:00 | p | 13 |  | 2025-07-30 16:47
847 | 1531 | KX1eD2ASIZaZBZuqoVp4 | Normal | 1 | 1.9.7.14.2 | 1.9.7.14.2 |  | 2025-05-01 17:00 | q | -191 |  | 2024-10-22 08:07
848 | 1532 | fQ3wcWF8uEWMRGpUCxEA | Normal | 1 | 1.9.7.14.4 | 1.9.7.14.4 |  | 2025-05-07 17:00 | q | -16 |  | 2025-04-21 15:17
849 | 1533 | juvdtwZkjArAkPOzLrhN | Normal | 15 | 1.9.7.14.5 | 1.9.7.14.5 |  | 2025-07-01 17:00 | p | 14 |  | 2025-07-16 10:48
850 | 1534 | SuchbNnj1ndABAEPQlrb | Normal | 10 | 1.9.7.14.6 | 1.9.7.14.6 |  | 2025-07-16 17:00 | p | 13 |  | 2025-07-30 16:47
851 | 4583 | QzcCl72pVAI4zSVR8VAE | Normal | 1 | 1.9.7.14.3 | 1.9.7.14.3 |  | 2025-05-02 17:00 | q | -192 |  | 2024-10-22 14:57
852 | 1535 | vIOpwJGhGrQ4pKl5nahR | Summary | 61 | 1.9.7.15 | 1.9.7.15 |  | 2025-05-16 17:00 | p | 34 |  | 2025-06-20 10:23
853 | 1537 | HoYmSEeaxBfAYgcISNXh | Normal | 5 | 1.9.7.15.2 | 1.9.7.15.2 |  | 2025-02-14 17:00 | p | 30 |  | 2025-03-17 16:37
854 | 1538 | 1Xm6i4dPIyAKJzF1jRtD | Normal | 45 | 1.9.7.15.3 | 1.9.7.15.3 |  | 2025-04-21 17:00 | p | 29 |  | 2025-05-21 11:41
855 | 1541 | ss8yD9dhZfTIp9UxqHnG | Normal | 1 | 1.9.7.15.7 | 1.9.7.15.7 |  | 2025-04-22 17:00 | p | 29 |  | 2025-05-22 10:13
856 | 1542 | VmFPpoMfVfLEXeRBF7Um | Normal | 9 | 1.9.7.15.8 | 1.9.7.15.8 |  | 2025-05-05 17:00 | p | 29 |  | 2025-06-04 09:43
857 | 1543 | P2oxmSB7jXG6Ib9VEZ89 | Normal | 9 | 1.9.7.15.9 | 1.9.7.15.9 |  | 2025-05-16 17:00 | p | 34 |  | 2025-06-20 10:23
858 | 4585 | Z4QB23UBk58Dyd3318zD | Normal | 10 | 1.9.7.15.6 | 1.9.7.15.6 |  | 2025-02-27 17:00 | q | -2 |  | 2025-02-25 10:58
859 | 1544 | dYtuUpkdltDWUtvWJGdC | Summary | 80 | 1.9.7.16 | 1.9.7.16 |  | 2025-04-01 17:00 | q | -6 |  | 2025-03-26 11:36
860 | 1547 | K0gsOWDMqaySswr72BAQ | Normal | 1 | 1.9.7.16.3 | 1.9.7.16.3 |  | 2025-02-21 17:00 | q | -360 |  | 2024-02-27 08:41
861 | 1548 | 4jCrHn72KCapTPEI9TzQ | Normal | 2 | 1.9.7.16.5 | 1.9.7.16.5 |  | 2025-02-26 17:00 | q | -362 |  | 2024-03-01 08:50
862 | 1549 | s8gTUDwRZFDpCO4enZqk | Normal | 15 | 1.9.7.16.6 | 1.9.7.16.6 |  | 2025-03-19 17:00 | q | -5 |  | 2025-03-14 09:48
863 | 1550 | UoQFPyMNVa9QPyq2kgrl | Normal | 9 | 1.9.7.16.7 | 1.9.7.16.7 |  | 2025-04-01 17:00 | q | -6 |  | 2025-03-26 11:36
864 | 4586 | kRWFuIGKur6ToFmAr9JC | Normal | 1 | 1.9.7.16.4 | 1.9.7.16.4 |  | 2025-02-24 17:00 | q | -362 |  | 2024-02-28 08:10
865 | 1551 | FTwSjNJQyZH6RsSSqWG9 | Summary | 78 | 1.9.7.19 | 1.9.7.19 |  | 2025-05-19 17:00 | p | 1 |  | 2025-05-21 11:08
866 | 1561 | 8BMHpFsmSFY1BvBQKfdD | Normal | 10 | 1.9.7.19.11 | 1.9.7.19.11 |  | 2025-02-25 17:00 | p | 1 |  | 2025-02-27 13:07
867 | 1562 | lBuCdKTmKHrCdvS4FVbB | Normal | 40 | 1.9.7.19.12 | 1.9.7.19.12 |  | 2025-04-22 17:00 | p | 1 |  | 2025-04-24 15:44
868 | 1563 | TUxQ6kz9ittb2zcmlLCL | Normal | 10 | 1.9.7.19.13 | 1.9.7.19.13 |  | 2025-05-06 17:00 | p | 1 |  | 2025-05-08 11:23
869 | 1564 | OkMyUpJo7fqJaif9Jvyb | Normal | 5 | 1.9.7.19.14 | 1.9.7.19.14 |  | 2025-05-13 17:00 | p | 1 |  | 2025-05-15 09:42
870 | 1565 | 9BGxipQLCi4kED7E7faW | Normal | 4 | 1.9.7.19.15 | 1.9.7.19.15 |  | 2025-05-19 17:00 | p | 1 |  | 2025-05-21 11:08
871 | 4571 | grLKm3VpZ98OhRQH2gBq | Normal | 29 | 1.9.7.1 | 1.9.7.1 |  | 2025-03-21 17:00 | p | 27 |  | 2025-04-18 16:03
872 | 4572 | 5hxJeLGqqaIlIue4XwRC | Normal | 1 | 1.9.7.2 | 1.9.7.2 |  | 2025-03-21 17:00 | p | 27 |  | 2025-04-18 16:03
873 | 4574 | z7UYZlhr663oN8lfFWmH | Summary | 29 | 1.9.7.11 | 1.9.7.11 |  | 2025-08-05 17:00 | q | -26 |  | 2025-07-10 10:52
874 | 1497 | q56IdotBOPeXlK3605d6 | Normal | 1 | 1.9.7.11.4 | 1.9.7.11.4 |  | 2025-05-06 17:00 | q | -20 |  | 2025-04-16 16:26
875 | 1506 | zNKWNUMZ7wFR6LBQ8bZ2 | Normal | 1 | 1.9.7.11.5 | 1.9.7.11.5 |  | 2025-08-05 17:00 | q | -26 |  | 2025-07-10 10:52
876 | 1509 | xdWSZU8MxGE52WBHNu6X | Normal | 1 | 1.9.7.11.3 | 1.9.7.11.3 |  | 2025-03-25 17:00 | p | 23 |  | 2025-04-18 13:26
877 | 6440 | u5F2XJPKXxmZ5m99Yx5A | Normal | 1 | 1.9.7.11.7 | 1.9.7.11.7 |  | 2025-04-30 17:00 | q | -5 |  | 2025-04-25 13:35
878 | 4575 | nPe6rBdPLk408ntp39jn | Normal | 1 | 1.9.7.3 | 1.9.7.3 |  | 2025-06-06 17:00 | q | -669 |  | 2023-08-07 16:47
879 | 4578 | kBeLaux8MTugqoi5KPvZ | Summary | 74 | 1.9.7.13 | 1.9.7.13 |  | 2025-07-17 17:00 | p | 13 |  | 2025-07-31 15:37
880 | 1462 | 2Cc6AJ3gtv1XGHwG4F9W | Normal | 1 | 1.9.7.13.3 | 1.9.7.13.3 |  | 2025-04-07 17:00 | p | 27 |  | 2025-05-05 10:48
881 | 1518 | qXbL36bdYftxHm1TCntK | Normal | 1 | 1.9.7.13.4 | 1.9.7.13.4 |  | 2025-07-17 17:00 | p | 13 |  | 2025-07-31 15:37
882 | 4579 | xoTCeJS6YwjvMvm1YAvH | Normal | 1 | 1.9.7.13.2 | 1.9.7.13.2 |  | 2025-05-19 17:00 | p | 34 |  | 2025-06-23 10:29
883 | 4580 | llDwDvQQbSyeeXMs3M2a | Normal | 1 | 1.9.7.13.1 | 1.9.7.13.1 |  | 2025-04-02 17:00 | q | -6 |  | 2025-03-27 13:16
884 | 4581 | FxGRGf2kppDMdfFrZkS4 | Normal | 36 | 1.9.7.12 | 1.9.7.12 |  | 2025-04-01 17:00 | p | 16 |  | 2025-04-18 13:39
885 | 4588 | L1kgBhMEjlIJ4HNHh1TQ | Summary | 141 | 1.9.7.20 | 1.9.7.20 |  | 2025-12-11 17:00 | q | -1 |  | 2025-12-10 09:09
886 | 1566 | KFj0hxHWvExDoqTqgDeg | Normal | 118 | 1.9.7.20.1 | 1.9.7.20.1 |  | 2025-11-06 17:00 | q | 0 |  | 2025-11-06 08:08
887 | 1567 | GV5or0ucuouXZiqAkH0N | Normal | 10 | 1.9.7.20.2 | 1.9.7.20.2 |  | 2025-11-21 17:00 | p | 2 |  | 2025-11-24 13:31
888 | 1568 | JI4xSRBKV4FYnRXdw7Wz | Normal | 9 | 1.9.7.20.3 | 1.9.7.20.3 |  | 2025-12-05 17:00 | q | 0 |  | 2025-12-05 10:32
889 | 1569 | DVuFJt4FGQSIgeZkA41d | Normal | 4 | 1.9.7.20.4 | 1.9.7.20.4 |  | 2025-12-11 17:00 | q | -1 |  | 2025-12-10 09:09
890 | 4590 | 21lrGsmJiPqRYOd4yY3H | Summary | 2 | 1.9.7.21 | 1.9.7.21 |  | 2026-09-16 12:00 | p | 929 |  | 2029-04-03 11:47
891 | 1570 | 9hmrS48cr19KgrseY4yN | Normal | 2 | 1.9.7.21.1 | 1.9.7.21.1 |  | 2026-09-16 12:00 | p | 929 |  | 2029-04-03 11:47
892 | 6439 | JoFd6fDKN7NWznuQx6gK | Normal | 56 | 1.9.7.10 | 1.9.7.10 |  | 2025-04-29 17:00 | q | -5 |  | 2025-04-24 11:28
893 | 7323 | p8rF5Tk8321hO30p5zSy | Summary | 79 | 1.7.8.18 | 1.7.8.18 |  | 2025-06-06 17:00 | p | 13 |  | 2025-06-20 15:38
894 | 7454 | JYERhD3wllXGZEgPk4Fl | Normal | 5 | 1.7.8.18.1 | 1.7.8.18.1 |  | 2025-02-14 17:00 | p | 31 |  | 2025-03-18 09:56
895 | 7455 | hQlezwT73UjuGPZkyuVr | Normal | 9 | 1.7.8.18.2 | 1.7.8.18.2 |  | 2025-02-28 17:00 | p | 27 |  | 2025-03-28 10:02
896 | 7456 | 3cfjdZ38xGBNf8roD7He | Normal | 9 | 1.7.8.18.3 | 1.7.8.18.3 |  | 2025-03-13 17:00 | p | 26 |  | 2025-04-09 14:59
897 | 7457 | abNwDWOnFoe0xwhiRueS | Normal | 1 | 1.7.8.18.4 | 1.7.8.18.4 |  | 2025-03-19 17:00 | p | 21 |  | 2025-04-10 14:30
898 | 7458 | cMhUMuxC0sax27543As7 | Normal | 24 | 1.7.8.18.5 | 1.7.8.18.5 |  | 2025-05-08 17:00 | p | 7 |  | 2025-05-16 10:07
899 | 7459 | xf7OMyoiQ38QdcweBYiq | Normal | 20 | 1.7.8.18.6 | 1.7.8.18.6 |  | 2025-06-06 17:00 | p | 13 |  | 2025-06-20 15:38
900 | 7324 | GVXYroUMjcAFUHa4B19H | Normal | 1 | 1.7.8.19 | 1.7.8.19 |  | 2025-03-28 17:00 | q | -554 |  | 2023-09-21 08:50
901 | 7325 | wl82vK5NXqnnsHIySTFp | Normal | 1 | 1.7.8.20 | 1.7.8.20 |  | 2025-06-09 17:00 | p | 13 |  | 2025-06-23 16:18
902 | 7382 | GJk3wpkfagyrb21gVciV | Summary | 288 | 1.9.7.22 | 1.9.7.22 |  | 2026-04-20 17:00 | p | 933 |  | 2028-11-09 11:11
903 | 7383 | chM988R4AoJxJINOHhOy | Normal | 1 | 1.9.7.22.1 | 1.9.7.22.1 |  | 2025-02-26 17:00 | q | -569 |  | 2023-08-07 16:42
904 | 7384 | xn1TRUhUfNd3ygHlAMk1 | Normal | 16 | 1.9.7.22.2 | 1.9.7.22.2 |  | 2025-03-20 17:00 | q | -575 |  | 2023-08-23 16:37
905 | 7385 | cYlWo9e2zkkP7jtt7iLZ | Normal | 1 | 1.9.7.22.3 | 1.9.7.22.3 |  | 2025-03-21 17:00 | q | -575 |  | 2023-08-24 15:42
906 | 7386 | F9n9tFj3S3xXbwXNgAjU | Normal | 5 | 1.9.7.22.4 | 1.9.7.22.4 |  | 2026-04-20 17:00 | p | 933 |  | 2028-11-09 11:11
907 | 6285 | 0inPdnysTnfuJeCJJEwo | Summary | 131 | 1.9.1 | 1.9.1 |  | 2025-11-28 17:00 | p | 23 |  | 2025-12-22 09:42
908 | 4593 | XK8YU5H8vMrR7jBOr6fS | Normal | 99 | 1.9.1.1 | 1.9.1.1 |  | 2025-07-01 17:00 | p | 19 |  | 2025-07-21 08:37
909 | 4594 | EUFkYGsAZWO3vgZroOTA | Normal | 1 | 1.9.1.2 | 1.9.1.2 |  | 2025-07-02 17:00 | p | 19 |  | 2025-07-22 08:41
910 | 4595 | 0i30zTvKTrSo3R9n999e | Normal | 2 | 1.9.1.3 | 1.9.1.3 |  | 2025-07-07 17:00 | p | 15 |  | 2025-07-23 15:28
911 | 4605 | jXRAJqcdCYbTQqzq5oVG | Normal | 14 | 1.7.3.2 | 1.7.3.2 |  | 2025-02-28 17:00 | p | 31 |  | 2025-04-01 09:25
912 | 4606 | e1c7TqZJ2saEXqSPx9Ca | Normal | 1 | 1.7.3.3 | 1.7.3.3 |  | 2025-05-27 17:00 | p | 33 |  | 2025-06-30 15:35
913 | 4607 | 9Rf8xh1sYqA0mX8AIEgx | Summary | 52 | 1.7.3.5 | 1.7.3.5 |  | 2025-10-16 17:00 | p | 31 |  | 2025-11-17 09:47
914 | 4608 | tlJeJHdE7OwhwWyVvZ8P | Normal | 5 | 1.7.3.5.1 | 1.7.3.5.1 |  | 2025-08-08 17:00 | p | 34 |  | 2025-09-12 13:59
915 | 4609 | PoeQu0I6Io83IRbk7WtS | Normal | 5 | 1.7.3.5.2 | 1.7.3.5.2 |  | 2025-08-15 17:00 | p | 34 |  | 2025-09-19 14:20
916 | 4610 | UGUZlny6Ut8S0mLRTL2X | Normal | 1 | 1.7.3.5.3 | 1.7.3.5.3 |  | 2025-08-18 17:00 | p | 34 |  | 2025-09-22 13:08
917 | 4611 | 1TZOFiOcsBCmkfhi03Iw | Normal | 5 | 1.7.3.5.4 | 1.7.3.5.4 |  | 2025-09-02 17:00 | p | 33 |  | 2025-10-06 11:44
918 | 4612 | ZwEXlYv6PrV1t0gzfqom | Normal | 10 | 1.7.3.5.5 | 1.7.3.5.5 |  | 2025-09-16 17:00 | p | 34 |  | 2025-10-21 10:58
919 | 4613 | z0DGpsje53b33zXA5t1P | Normal | 20 | 1.7.3.5.6 | 1.7.3.5.6 |  | 2025-10-15 17:00 | p | 29 |  | 2025-11-14 09:46
920 | 4614 | cqs4HA7sR83mroZvcBiw | Normal | 1 | 1.7.3.5.7 | 1.7.3.5.7 |  | 2025-10-16 17:00 | p | 31 |  | 2025-11-17 09:47
921 | 4615 | Io6EVgFdyRjG7CB2g0Wy | Summary | 98 | 1.7.3.4 | 1.7.3.4 |  | 2025-08-05 17:00 | p | 35 |  | 2025-09-10 14:26
922 | 4616 | FR5tuVwQGmPNYmz6BeMP | Normal | 2 | 1.7.3.4.1 | 1.7.3.4.1 |  | 2025-02-14 17:00 | p | 25 |  | 2025-03-12 11:53
923 | 4617 | OziRB3N5b7cM46iEETGg | Normal | 5 | 1.7.3.4.2 | 1.7.3.4.2 |  | 2025-02-14 17:00 | p | 31 |  | 2025-03-18 11:06
924 | 4618 | mRqsjEijsp2iSp4l7aof | Normal | 5 | 1.7.3.4.3 | 1.7.3.4.3 |  | 2025-02-24 17:00 | p | 30 |  | 2025-03-27 09:05
925 | 4619 | 8asUr7UOO8nabPagFvw9 | Normal | 40 | 1.7.3.4.4 | 1.7.3.4.4 |  | 2025-04-14 17:00 | p | 24 |  | 2025-05-09 08:39
926 | 4620 | UWR5akRFo4eKiDyQVnYr | Normal | 23 | 1.7.3.4.5 | 1.7.3.4.5 |  | 2025-03-20 17:00 | p | 14 |  | 2025-04-04 08:42
927 | 4621 | pGB9dynKUfIMuzj3AWVv | Normal | 1 | 1.7.3.4.6 | 1.7.3.4.6 |  | 2025-05-28 17:00 | p | 33 |  | 2025-07-01 14:45
928 | 4622 | Bm2ajkWBwO6Cvc6RoPdK | Normal | 5 | 1.7.3.4.7 | 1.7.3.4.7 |  | 2025-06-04 17:00 | p | 36 |  | 2025-07-11 16:20
929 | 4623 | sDTQ4X48dvup817zb0Do | Normal | 20 | 1.7.3.4.8 | 1.7.3.4.8 |  | 2025-07-03 17:00 | p | 38 |  | 2025-08-11 16:17
930 | 4624 | 3CGv61AS00FFpM5LrRat | Normal | 20 | 1.7.3.4.9 | 1.7.3.4.9 |  | 2025-08-01 17:00 | p | 37 |  | 2025-09-08 13:07
931 | 4625 | NkJyZ342jkgJkVCalD4F | Normal | 2 | 1.7.3.4.10 | 1.7.3.4.10 |  | 2025-08-05 17:00 | p | 35 |  | 2025-09-10 14:26
932 | 4626 | 92oajspBBxTpnlNQO91I | Summary | 90 | 1.7.3.6 | 1.7.3.6 |  | 2025-11-28 17:00 | p | 23 |  | 2025-12-22 09:42
933 | 4630 | pjdWghPSPBEOfTIZFZhV | Normal | 5 | 1.7.3.6.4 | 1.7.3.6.4 |  | 2025-02-14 17:00 | p | 30 |  | 2025-03-17 08:01
934 | 4631 | EXJQS9o5Eq3lGkaYsCap | Normal | 1 | 1.7.3.6.5 | 1.7.3.6.5 |  | 2025-02-18 17:00 | p | 26 |  | 2025-03-17 16:23
935 | 4632 | VGp2Ji3lCAas2O4B01f5 | Normal | 1 | 1.7.3.6.6 | 1.7.3.6.6 |  | 2025-02-19 17:00 | p | 26 |  | 2025-03-18 16:09
936 | 4633 | STHfhyBuM5qFiEzHSgws | Normal | 19 | 1.7.3.6.7 | 1.7.3.6.7 |  | 2025-03-18 17:00 | p | 22 |  | 2025-04-10 09:43
937 | 4634 | cbBLoWE0dwfwOCS04ga7 | Normal | 15 | 1.7.3.6.8 | 1.7.3.6.8 |  | 2025-04-08 17:00 | p | 22 |  | 2025-05-01 09:46
938 | 4635 | vrd0V7BeylNxhzgI26F9 | Normal | 8 | 1.7.3.6.11 | 1.7.3.6.11 |  | 2025-04-21 17:00 | p | 22 |  | 2025-05-14 14:26
939 | 4636 | DgPDbwa39NNm3em6lmtZ | Normal | 1 | 1.7.3.6.12 | 1.7.3.6.12 |  | 2025-11-28 17:00 | p | 23 |  | 2025-12-22 09:42
940 | 4663 | X9pjxOrdX8ZwQAfQziSu | Normal | 1 | 1.7.3.6.9 | 1.7.3.6.9 |  | 2025-04-09 17:00 | p | 22 |  | 2025-05-02 09:31
941 | 4664 | DAxARpEpHAwipBCK81bc | Normal | 8 | 1.7.3.6.10 | 1.7.3.6.10 |  | 2025-04-21 17:00 | p | 22 |  | 2025-05-14 10:26
942 | 4637 | ohQUE8EwZLGEmkE5FTpA | Summary | 8 | 1.7.3.7 | 1.7.3.7 |  | 2025-02-28 17:00 | p | 27 |  | 2025-03-28 08:59
943 | 6608 | ifCvUSq9UjUAw7FKKXTR | Normal | 14 | 1.7.3.7.3 | 1.7.3.7.3 |  | 2025-02-28 17:00 | p | 27 |  | 2025-03-28 08:59
944 | 7259 | Dcjo2uskRMoBajU90pQq | Normal | 60 | 1.7.1.4 | 1.7.1.4 |  | 2025-05-23 17:00 | p | 34 |  | 2025-06-27 15:19
945 | 6294 | Jtjxi70STISSeVqV8OJy | Summary | 163 | 1.9.6 | 1.9.6 |  | 2026-09-10 17:00 | p | 823 |  | 2028-12-12 13:30
946 | 3745 | D0mR64Wbk6oru5hoL4DG | Summary | 62 | 1.7.1.2 | 1.7.1.2 |  | 2025-04-08 17:00 | p | 28 |  | 2025-05-07 16:40
947 | 3773 | jfB1zdAbu7JeWEH3ijwy | Summary | 73 | 1.7.1.2.6 | 1.7.1.2.6 |  | 2025-04-08 17:00 | p | 28 |  | 2025-05-07 16:40
948 | 3776 | GHLE38QRMYNBeSYAGB18 | Normal | 32 | 1.7.1.2.6.3 | 1.7.1.2.6.3 |  | 2025-03-26 17:00 | p | 29 |  | 2025-04-25 15:31
949 | 3777 | YuGKQIQDxLVYRZzgUQjw | Normal | 9 | 1.7.1.2.6.4 | 1.7.1.2.6.4 |  | 2025-04-08 17:00 | p | 28 |  | 2025-05-07 16:40
950 | 3783 | FcDlmkxQNUOM36qP0M0H | Summary | 58 | 1.7.1.3 | 1.7.1.3 |  | 2025-06-02 17:00 | p | 34 |  | 2025-07-07 10:07
951 | 3790 | Om0YwWoKF5usOVLnDccR | Summary | 13 | 1.7.1.3.4 | 1.7.1.3.4 |  | 2025-02-28 17:00 | p | 31 |  | 2025-04-01 13:07
952 | 6977 | F0juzsyqTnJm6sTJe4ff | Normal | 14 | 1.7.1.3.4.7 | 1.7.1.3.4.7 |  | 2025-02-28 17:00 | p | 31 |  | 2025-04-01 13:07
953 | 6138 | EvFVoaLHb5OgszmS4Hdy | Summary | 44 | 1.7.1.3.9 | 1.7.1.3.9 |  | 2025-06-02 17:00 | p | 34 |  | 2025-07-07 10:07
954 | 6139 | VECMPYMi2oWf71g3eai1 | Normal | 29 | 1.7.1.3.9.1 | 1.7.1.3.9.1 |  | 2025-05-09 17:00 | p | 27 |  | 2025-06-06 16:23
955 | 6140 | mO0F0FFUdRVKYlb84WcT | Normal | 15 | 1.7.1.3.9.2 | 1.7.1.3.9.2 |  | 2025-06-02 17:00 | p | 34 |  | 2025-07-07 10:07
956 | 6978 | z4sj2SQJw3pdZet8Am0U | Normal | 9 | 1.7.1.3.5 | 1.7.1.3.5 |  | 2025-03-20 17:00 | p | 26 |  | 2025-04-16 09:22
957 | 6983 | PcmQnh6ym2R5IAKzFgwu | Summary | 141 | 1.7.1.3.7 | 1.7.1.3.7 |  | 2025-03-24 17:00 | p | 29 |  | 2025-04-23 10:16
958 | 6985 | eGeEyEDP9xa0SwHKf7WR | Normal | 7 | 1.7.1.3.7.4 | 1.7.1.3.7.4 |  | 2025-03-11 17:00 | p | 29 |  | 2025-04-10 09:59
959 | 6986 | 31qYZ6wVIReV9ZOAqgem | Summary | 9 | 1.7.1.3.7.5 | 1.7.1.3.7.5 |  | 2025-03-24 17:00 | p | 29 |  | 2025-04-23 10:16
960 | 6987 | 50so1NYgvDTnEeNkdrjv | Normal | 3 | 1.7.1.3.7.5.1 | 1.7.1.3.7.5.1 |  | 2025-03-14 17:00 | p | 30 |  | 2025-04-14 16:39
961 | 6988 | bmsC3uFxKZ3RPA57Ivjb | Normal | 3 | 1.7.1.3.7.5.2 | 1.7.1.3.7.5.2 |  | 2025-03-19 17:00 | p | 29 |  | 2025-04-18 11:00
962 | 6989 | okOYULy0nclsZMYhl4sg | Normal | 3 | 1.7.1.3.7.5.3 | 1.7.1.3.7.5.3 |  | 2025-03-24 17:00 | p | 29 |  | 2025-04-23 10:16
963 | 7184 | gKjyagqR1BEsAZjZk4l5 | Milestone | 0 | 1.7.1.3.7.3 | 1.7.1.3.7.3 |  | 2025-02-28 08:00 | q | -29 |  | 2025-01-30 08:00
964 | 6990 | K8cvVDryBsyahUujiNmr | Summary | 22 | 1.7.1.3.8 | 1.7.1.3.8 |  | 2025-03-31 17:00 | p | 28 |  | 2025-04-29 15:49
965 | 6136 | bVRB0EhNo1xoyHBU8R0I | Normal | 1 | 1.7.1.3.8.2 | 1.7.1.3.8.2 |  | 2025-03-21 17:00 | p | 26 |  | 2025-04-17 09:11
966 | 6982 | E06yVWmTg8kRS6Gv9kOV | Summary | 6 | 1.7.1.3.8.3 | 1.7.1.3.8.3 |  | 2025-03-31 17:00 | p | 28 |  | 2025-04-29 15:49
967 | 6137 | gagQpjsDXV4QnJ1bUthb | Normal | 2 | 1.7.1.3.8.3.1 | 1.7.1.3.8.3.1 |  | 2025-03-25 17:00 | p | 26 |  | 2025-04-21 09:05
968 | 6979 | ZYA6dvbLVog9FL6DNJRb | Normal | 5 | 1.7.1.3.8.3.2 | 1.7.1.3.8.3.2 |  | 2025-03-31 17:00 | p | 28 |  | 2025-04-29 15:49
969 | 6991 | RAhO7UtYgqwLkhTknwrO | Normal | 6 | 1.7.1.3.8.1 | 1.7.1.3.8.1 |  | 2025-03-07 17:00 | q | -30 |  | 2025-02-05 15:52
970 | 3803 | vx1oFVBFPqydBxZJ7V4g | Summary | 112 | 1.7.1.5 | 1.7.1.5 |  | 2025-06-04 17:00 | p | 50 |  | 2025-07-25 15:30
971 | 3808 | mNtnU9AYiACOeBrTPE9f | Summary | 29 | 1.7.1.5.3 | 1.7.1.5.3 |  | 2025-03-21 17:00 | p | 24 |  | 2025-04-15 15:59
972 | 3809 | ukioB4iHiwrfEXpseTiK | Normal | 15 | 1.7.1.5.3.1 | 1.7.1.5.3.1 |  | 2025-03-03 17:00 | p | 28 |  | 2025-04-01 15:07
973 | 3810 | CJxWy7PnZPcI4EPHEeme | Normal | 9 | 1.7.1.5.3.2 | 1.7.1.5.3.2 |  | 2025-03-14 17:00 | p | 26 |  | 2025-04-10 11:21
974 | 3811 | wGtgxCT3lCK6u2EOL8xN | Normal | 5 | 1.7.1.5.3.3 | 1.7.1.5.3.3 |  | 2025-03-21 17:00 | p | 24 |  | 2025-04-15 15:59
975 | 3813 | sYeTNUsya13QYMbMJg21 | Normal | 25 | 1.7.1.5.7 | 1.7.1.5.7 |  | 2025-04-03 17:00 | p | 31 |  | 2025-05-05 11:31
976 | 3814 | c3HTuVFoRVefrW72mxSE | Normal | 3 | 1.7.1.5.8 | 1.7.1.5.8 |  | 2025-04-10 17:00 | p | 54 |  | 2025-06-04 10:07
977 | 3815 | nJJAkVwt0aHLNZMMtbkw | Normal | 3 | 1.7.1.5.9 | 1.7.1.5.9 |  | 2025-04-08 17:00 | p | 29 |  | 2025-05-08 08:56
978 | 3816 | 6MWmVgC0FSCF3lMoTGjJ | Summary | 40 | 1.7.1.5.10 | 1.7.1.5.10 |  | 2025-06-04 17:00 | p | 50 |  | 2025-07-25 15:30
979 | 3817 | LqjKPVRVNU7j1iAlkL3t | Normal | 2 | 1.7.1.5.10.1 | 1.7.1.5.10.1 |  | 2025-04-10 17:00 | p | 31 |  | 2025-05-12 09:26
980 | 3818 | Cmm1EfLtBPedDjXV8dAv | Normal | 5 | 1.7.1.5.10.2 | 1.7.1.5.10.2 |  | 2025-04-17 17:00 | p | 31 |  | 2025-05-19 08:29
981 | 3819 | FSVjbKFfUmqE2fpbGGPv | Normal | 3 | 1.7.1.5.10.3 | 1.7.1.5.10.3 |  | 2025-04-22 17:00 | p | 28 |  | 2025-05-21 11:29
982 | 3820 | FhKtXXrOwkDfPm4RFzRW | Normal | 10 | 1.7.1.5.10.4 | 1.7.1.5.10.4 |  | 2025-05-06 17:00 | p | 44 |  | 2025-06-20 10:34
983 | 3821 | cHjYAw102skS4vR6DXqX | Normal | 20 | 1.7.1.5.10.5 | 1.7.1.5.10.5 |  | 2025-06-04 17:00 | p | 50 |  | 2025-07-25 15:30
984 | 6147 | BUcWclFVChflBnUDJ9UM | Normal | 40 | 1.7.1.5.4 | 1.7.1.5.4 |  | 2025-04-07 17:00 | p | 52 |  | 2025-05-30 10:39
985 | 6148 | V03eKqopjAXoUvRodLvQ | Normal | 13 | 1.7.1.5.6 | 1.7.1.5.6 |  | 2025-02-27 17:00 | p | 28 |  | 2025-03-28 13:11
986 | 4078 | ybbKeBChK3D60QzH8ONZ | Normal | 76 | 1.9.6.5 | 1.9.6.5 |  | 2025-05-28 17:00 | p | 26 |  | 2025-06-24 09:52
987 | 4129 | G6dPcJRrq5zqLYx4Vr0R | Summary | 475 | 1.9.6.10 | 1.9.6.10 |  | 2026-05-26 12:00 | p | 931 |  | 2028-12-12 13:30
988 | 4131 | 3WZTLr4e3INGux4LMgj0 | Summary | 146 | 1.9.6.10.2 | 1.9.6.10.2 |  | 2025-09-29 17:00 | p | 863 |  | 2028-02-10 10:41
989 | 5857 | g9TizAnooUcHoXglcd4n | Milestone | 0 | 1.9.6.10.2.1 | 1.9.6.10.2.1 |  | 2025-07-25 17:00 | p | 906 |  | 2028-01-18 08:48
990 | 5858 | 9N3N0HBhBeb82jbbU7Vx | Milestone | 0 | 1.9.6.10.2.2 | 1.9.6.10.2.2 |  | 2025-03-03 17:00 | p | 927 |  | 2027-09-17 14:49
991 | 5859 | RMhsXtyk4773BtipN2HO | Normal | 1 | 1.9.6.10.2.3 | 1.9.6.10.2.3 |  | 2025-03-04 17:00 | p | 929 |  | 2027-09-20 14:29
992 | 5860 | AMUT2hrMeOWSIoK5dO6S | Normal | 10 | 1.9.6.10.2.4 | 1.9.6.10.2.4 |  | 2025-05-16 17:00 | p | 870 |  | 2027-10-04 10:58
993 | 5861 | adMwYb1cwVT0ja23ZKPV | Normal | 10 | 1.9.6.10.2.5 | 1.9.6.10.2.5 |  | 2025-06-02 17:00 | p | 864 |  | 2027-10-15 15:33
994 | 5862 | rkVKH7eSVnkv5Rz0hIbo | Normal | 25 | 1.9.6.10.2.6 | 1.9.6.10.2.6 |  | 2025-07-09 17:00 | p | 868 |  | 2027-11-25 10:07
995 | 5863 | axx1H8vuWtNbWz6aJYpW | Normal | 20 | 1.9.6.10.2.7 | 1.9.6.10.2.7 |  | 2025-08-06 17:00 | p | 873 |  | 2027-12-28 09:23
996 | 5864 | ZuXAUp7kzm7PDgs0Clm4 | Normal | 20 | 1.9.6.10.2.8 | 1.9.6.10.2.8 |  | 2025-09-04 17:00 | p | 866 |  | 2028-01-19 16:30
997 | 5865 | pfx92tyIHO0nDV8Eg4vj | Normal | 3 | 1.9.6.10.2.9 | 1.9.6.10.2.9 |  | 2025-09-09 17:00 | p | 866 |  | 2028-01-24 14:23
998 | 5866 | qnFTkxNSvGIYOwHhqElS | Normal | 5 | 1.9.6.10.2.10 | 1.9.6.10.2.10 |  | 2025-09-16 17:00 | p | 866 |  | 2028-01-31 13:50
999 | 5867 | 6vMprMC9ZRYTg9c055cw | Normal | 3 | 1.9.6.10.2.11 | 1.9.6.10.2.11 |  | 2025-09-19 17:00 | p | 865 |  | 2028-02-02 13:03
1000 | 5868 | qP5P60WlJm98gR28uFOw | Normal | 1 | 1.9.6.10.2.12 | 1.9.6.10.2.12 |  | 2025-09-22 17:00 | p | 863 |  | 2028-02-03 11:32
1001 | 5869 | 5FBVtcv48JlyNzpes7ps | Normal | 5 | 1.9.6.10.2.13 | 1.9.6.10.2.13 |  | 2025-09-29 17:00 | p | 863 |  | 2028-02-10 10:41
1002 | 5870 | rLlKwDBGmyMe6lxLtymf | Summary | 59 | 1.9.6.10.3 | 1.9.6.10.3 |  | 2025-12-24 17:00 | p | 868 |  | 2028-05-11 14:47
1003 | 5871 | owx5unCKcaLauhH4kWyj | Normal | 5 | 1.9.6.10.3.1 | 1.9.6.10.3.1 |  | 2025-10-06 17:00 | p | 864 |  | 2028-02-18 13:09
1004 | 5872 | qImIYF1Y50rp0FNnsaoS | Normal | 10 | 1.9.6.10.3.2 | 1.9.6.10.3.2 |  | 2025-10-21 17:00 | p | 867 |  | 2028-03-07 11:58
1005 | 5873 | FfFQqcMQ2fY5X0GvK0Xd | Normal | 20 | 1.9.6.10.3.3 | 1.9.6.10.3.3 |  | 2025-11-19 17:00 | p | 873 |  | 2028-04-11 11:46
1006 | 5874 | fHTDjpnY2Gm0gViXPiAD | Normal | 2 | 1.9.6.10.3.6 | 1.9.6.10.3.6 |  | 2025-12-22 17:00 | p | 869 |  | 2028-05-10 09:09
1007 | 5875 | TQZary26m4SvJkpuQUlv | Normal | 1 | 1.9.6.10.3.7 | 1.9.6.10.3.7 |  | 2025-12-23 17:00 | p | 868 |  | 2028-05-10 16:29
1008 | 5876 | 5ZRJqmbhPGswffOWtWat | Normal | 1 | 1.9.6.10.3.8 | 1.9.6.10.3.8 |  | 2025-12-24 17:00 | p | 868 |  | 2028-05-11 14:47
1009 | 6624 | sVpbcWAee9M5eeft5sdO | Normal | 15 | 1.9.6.10.3.4 | 1.9.6.10.3.4 |  | 2025-12-11 17:00 | p | 868 |  | 2028-04-28 14:05
1010 | 6625 | it5qGsWYKIf8fEL1a2TB | Normal | 5 | 1.9.6.10.3.5 | 1.9.6.10.3.5 |  | 2025-12-18 17:00 | p | 871 |  | 2028-05-08 10:44
1011 | 5877 | 8uIO0L3CbsjXfYIL70ur | Summary | 162 | 1.9.6.10.4 | 1.9.6.10.4 |  | 2026-05-26 12:00 | p | 931 |  | 2028-12-12 13:30
1012 | 5878 | eKJmpIIS7eePXp789pq5 | Summary | 60 | 1.9.6.10.4.1 | 1.9.6.10.4.1 |  | 2025-12-26 17:00 | p | 859 |  | 2028-05-04 16:46
1013 | 5879 | CJrwB1y6NRnYYg7kpaRv | Summary | 30 | 1.9.6.10.4.1.1 | 1.9.6.10.4.1.1 |  | 2025-11-12 17:00 | p | 860 |  | 2028-03-22 15:58
1014 | 5880 | z8rht75g90pc62Jd1j8e | Normal | 15 | 1.9.6.10.4.1.1.1 | 1.9.6.10.4.1.1.1 |  | 2025-10-21 17:00 | p | 860 |  | 2028-02-29 13:49
1015 | 5881 | ZPPJV7wrbqyTumtl84NX | Normal | 15 | 1.9.6.10.4.1.1.2 | 1.9.6.10.4.1.1.2 |  | 2025-11-12 17:00 | p | 860 |  | 2028-03-22 15:58
1016 | 5882 | PdfqDNDAaUS1Z9tfvPSB | Normal | 15 | 1.9.6.10.4.1.2 | 1.9.6.10.4.1.2 |  | 2025-12-04 17:00 | p | 858 |  | 2028-04-11 16:56
1017 | 5883 | 3J3dFKPf8v7HKW1lSal4 | Normal | 15 | 1.9.6.10.4.1.3 | 1.9.6.10.4.1.3 |  | 2025-12-26 17:00 | p | 859 |  | 2028-05-04 16:46
1018 | 5884 | J3ZDJxR9DKKi4JquRb3Q | Summary | 20 | 1.9.6.10.4.2 | 1.9.6.10.4.2 |  | 2025-10-28 17:00 | p | 866 |  | 2028-03-13 08:09
1019 | 5885 | p0UOLQYQkw5raD9Hf7AI | Normal | 5 | 1.9.6.10.4.2.1 | 1.9.6.10.4.2.1 |  | 2025-10-06 17:00 | p | 863 |  | 2028-02-17 11:18
1020 | 5886 | mfBVa7VrtMT45ZcRp9ur | Normal | 5 | 1.9.6.10.4.2.2 | 1.9.6.10.4.2.2 |  | 2025-10-14 17:00 | p | 862 |  | 2028-02-24 11:50
1021 | 5887 | xjL6okqGZuFc1ChaUzA0 | Normal | 5 | 1.9.6.10.4.2.3 | 1.9.6.10.4.2.3 |  | 2025-10-21 17:00 | p | 863 |  | 2028-03-03 15:24
1022 | 5888 | 0NLdruhvCSk61FiIPSJA | Normal | 5 | 1.9.6.10.4.2.4 | 1.9.6.10.4.2.4 |  | 2025-10-28 17:00 | p | 866 |  | 2028-03-13 08:09
1023 | 5889 | vcqfMiWzgD0sBRK91JrP | Normal | 3 | 1.9.6.10.4.3 | 1.9.6.10.4.3 |  | 2025-10-31 17:00 | p | 865 |  | 2028-03-15 15:38
1024 | 5890 | r7iAplKyl5D3dW7yC0Jk | Normal | 5 | 1.9.6.10.4.4 | 1.9.6.10.4.4 |  | 2025-11-07 17:00 | p | 865 |  | 2028-03-22 15:32
1025 | 5891 | 55B0pL3dU2GPDxU6IZLg | Normal | 1 | 1.9.6.10.4.5 | 1.9.6.10.4.5 |  | 2025-11-10 17:00 | p | 863 |  | 2028-03-23 13:30
1026 | 5892 | zyPP7s8BBmPhydQ5fB2g | Normal | 1 | 1.9.6.10.4.8 | 1.9.6.10.4.8 |  | 2026-05-26 12:00 | p | 931 |  | 2028-12-12 13:30
1027 | 5893 | JSBvauC3wpirasqwMrC9 | Normal | 1 | 1.9.6.10.4.6 | 1.9.6.10.4.6 |  | 2025-11-12 17:00 | p | 862 |  | 2028-03-24 13:34
1028 | 5894 | AO4SgiivKvvxQJupi2GS | Normal | 1 | 1.9.6.10.4.7 | 1.9.6.10.4.7 |  | 2025-11-13 17:00 | p | 864 |  | 2028-03-27 10:02
1029 | 4134 | 86JmjjOtZxj7XQRp3CQF | Summary | 466 | 1.9.6.11 | 1.9.6.11 |  | 2026-09-10 17:00 | p | 648 |  | 2028-06-20 14:26
1030 | 4135 | 0voiyAtBe9AzaXfs8cVF | Summary | 322 | 1.9.6.11.1 | 1.9.6.11.1 |  | 2026-07-02 17:00 | p | 649 |  | 2028-04-12 13:02
1031 | 4136 | bllhlvXmXgF1yFG9Nwfe | Normal | 16 | 1.9.6.11.1.1 | 1.9.6.11.1.1 |  | 2026-05-11 17:00 | p | 654 |  | 2028-02-25 10:36
1032 | 4137 | rnRXxVdKdR5NUADIB31n | Normal | 1 | 1.9.6.11.1.2 | 1.9.6.11.1.2 |  | 2026-05-12 17:00 | p | 656 |  | 2028-02-28 11:51
1033 | 4138 | 75WgU7H7MCC8DDgOcnsD | Normal | 30 | 1.9.6.11.1.3 | 1.9.6.11.1.3 |  | 2026-06-25 17:00 | p | 650 |  | 2028-04-06 09:05
1034 | 4139 | 9SKpfzivi43NDDuHUq0B | Normal | 5 | 1.9.6.11.1.4 | 1.9.6.11.1.4 |  | 2026-07-02 17:00 | p | 649 |  | 2028-04-12 13:02
1035 | 4140 | Lk7gef35zB3WaxM8Xyxe | Summary | 48 | 1.9.6.11.2 | 1.9.6.11.2 |  | 2026-09-10 17:00 | p | 648 |  | 2028-06-20 14:26
1036 | 4141 | HGo5Ep3pqhcsiM5K4QjA | Summary | 23 | 1.9.6.11.2.1 | 1.9.6.11.2.1 |  | 2026-08-05 17:00 | p | 650 |  | 2028-05-17 11:22
1037 | 4142 | VTqJrDLpWuaSlvRQajcM | Normal | 12 | 1.9.6.11.2.1.1 | 1.9.6.11.2.1.1 |  | 2026-07-21 17:00 | p | 649 |  | 2028-05-01 15:56
1038 | 4143 | UwGhtpl5Mnq9WQrcrXRR | Normal | 11 | 1.9.6.11.2.1.2 | 1.9.6.11.2.1.2 |  | 2026-08-05 17:00 | p | 650 |  | 2028-05-17 11:22
1039 | 4144 | zaFQ6K5wegGvKt6DGuoz | Summary | 25 | 1.9.6.11.2.2 | 1.9.6.11.2.2 |  | 2026-09-10 17:00 | p | 648 |  | 2028-06-20 14:26
1040 | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Normal | 10 | 1.9.6.11.2.2.1 | 1.9.6.11.2.2.1 |  | 2026-08-19 17:00 | p | 649 |  | 2028-05-30 13:43
1041 | 4146 | rTeXGnIwGPt6ES3ynSHq | Normal | 5 | 1.9.6.11.2.2.2 | 1.9.6.11.2.2.2 |  | 2026-08-26 17:00 | p | 648 |  | 2028-06-05 15:25
1042 | 4147 | hQaW5HIstT5bbsPEBxyQ | Normal | 10 | 1.9.6.11.2.2.3 | 1.9.6.11.2.2.3 |  | 2026-09-10 17:00 | p | 648 |  | 2028-06-20 14:26
1043 | 5753 | ZptYdARXANY2IOcoHhB1 | Summary | 78 | 1.9.6.1 | 1.9.6.1 |  | 2025-07-28 17:00 | p | 904 |  | 2028-01-19 08:06
1044 | 5998 | aRBXPvE6pbVbcbhlDtu4 | Summary | 47 | 1.9.6.1.7 | 1.9.6.1.7 |  | 2025-07-25 17:00 | p | 906 |  | 2028-01-18 08:48
1045 | 5999 | hTF24jclc5ogfsrVWXZd | Normal | 40 | 1.9.6.1.7.1 | 1.9.6.1.7.1 |  | 2025-07-16 17:00 | p | 904 |  | 2028-01-07 09:53
1046 | 6000 | dvNXA0SZWky1SGhKE7td | Normal | 5 | 1.9.6.1.7.2 | 1.9.6.1.7.2 |  | 2025-07-23 17:00 | p | 904 |  | 2028-01-14 10:43
1047 | 6001 | z8HVZ6SyP3QpkaT54VAm | Normal | 1 | 1.9.6.1.7.3 | 1.9.6.1.7.3 |  | 2025-07-24 17:00 | p | 906 |  | 2028-01-17 10:37
1048 | 6002 | rmlzSal3Nkh8gQGzhscw | Normal | 1 | 1.9.6.1.7.4 | 1.9.6.1.7.4 |  | 2025-07-25 17:00 | p | 906 |  | 2028-01-18 08:48
1049 | 6003 | zkyCYMQIHOywdkyzbjbi | Summary | 48 | 1.9.6.1.8 | 1.9.6.1.8 |  | 2025-07-28 17:00 | p | 904 |  | 2028-01-19 08:06
1050 | 6004 | xOhJcEwgSz1TAvNHU4tB | Normal | 40 | 1.9.6.1.8.1 | 1.9.6.1.8.1 |  | 2025-07-16 17:00 | p | 887 |  | 2027-12-21 11:00
1051 | 6005 | gw3ZFSF3nzLqLqYBiqR7 | Normal | 5 | 1.9.6.1.8.2 | 1.9.6.1.8.2 |  | 2025-07-23 17:00 | p | 887 |  | 2027-12-28 10:31
1052 | 6006 | HEKaqqmbwSXnCRXB6fED | Normal | 1 | 1.9.6.1.8.3 | 1.9.6.1.8.3 |  | 2025-07-24 17:00 | p | 887 |  | 2027-12-29 10:01
1053 | 6007 | vdBzwsumrXxpXNAKvnKh | Normal | 1 | 1.9.6.1.8.4 | 1.9.6.1.8.4 |  | 2025-07-28 17:00 | p | 904 |  | 2028-01-19 08:06
1054 | 6008 | Ph5VFx7Ghit4AwZEFBXT | Summary | 50 | 1.9.6.1.6 | 1.9.6.1.6 |  | 2025-06-16 17:00 | p | 903 |  | 2027-12-07 08:46
1055 | 6009 | NVgukc0KZBShUa0wIlyx | Normal | 30 | 1.9.6.1.6.1 | 1.9.6.1.6.1 |  | 2025-05-16 17:00 | p | 908 |  | 2027-11-11 13:59
1056 | 6010 | tIYqVtlT4yOF2YQ2FRYY | Normal | 10 | 1.9.6.1.6.2 | 1.9.6.1.6.2 |  | 2025-06-02 17:00 | p | 904 |  | 2027-11-24 11:11
1057 | 6011 | 9Y3pHbqvwzl2AwHfvrBG | Normal | 5 | 1.9.6.1.6.3 | 1.9.6.1.6.3 |  | 2025-06-09 17:00 | p | 904 |  | 2027-12-01 10:24
1058 | 6012 | Z1jpWQx4GyFcVoEVg0i0 | Normal | 5 | 1.9.6.1.6.4 | 1.9.6.1.6.4 |  | 2025-06-16 17:00 | p | 903 |  | 2027-12-07 08:46
1059 | 6013 | y2dxMv99iLhGOXikZGuK | Summary | 34 | 1.9.6.1.5 | 1.9.6.1.5 |  | 2025-05-01 17:00 | p | 26 |  | 2025-05-28 15:08
1060 | 6014 | hYHiAVYfHXdDTdWEk9J8 | Normal | 15 | 1.9.6.1.5.1 | 1.9.6.1.5.1 |  | 2025-04-04 17:00 | p | 26 |  | 2025-05-01 14:39
1061 | 6015 | MXdxqc8Y6tIByFeEqluF | Normal | 10 | 1.9.6.1.5.2 | 1.9.6.1.5.2 |  | 2025-04-18 17:00 | p | 26 |  | 2025-05-15 14:44
1062 | 6016 | gwhB80Lv7eu4PoYwev8o | Normal | 5 | 1.9.6.1.5.3 | 1.9.6.1.5.3 |  | 2025-04-25 17:00 | p | 25 |  | 2025-05-21 13:41
1063 | 6017 | VCyTBN0y7V3erCRNMvm4 | Normal | 4 | 1.9.6.1.5.4 | 1.9.6.1.5.4 |  | 2025-05-01 17:00 | p | 26 |  | 2025-05-28 15:08
1064 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | 2025-03-17 17:00 | p | 925 |  | 2027-09-28 17:00
1065 | 6957 | ar01N24L63iczVEh1mVo | Summary | 24 | 1.9.6.1.4 | 1.9.6.1.4 |  | 2025-04-04 17:00 | p | 27 |  | 2025-05-02 08:12
1066 | 6958 | 6Ul4V6iAcnpVqewOp14Y | Normal | 4 | 1.9.6.1.4.1 | 1.9.6.1.4.1 |  | 2025-03-07 17:00 | p | 30 |  | 2025-04-07 13:43
1067 | 6959 | w9Vvv79ftt4PUqInNFyD | Normal | 5 | 1.9.6.1.4.2 | 1.9.6.1.4.2 |  | 2025-03-14 17:00 | p | 27 |  | 2025-04-11 15:34
1068 | 6960 | xIgpHAurEQ244gHa2T5q | Normal | 5 | 1.9.6.1.4.3 | 1.9.6.1.4.3 |  | 2025-03-21 17:00 | p | 27 |  | 2025-04-18 14:07
1069 | 6961 | NOksVV7sTymsgwMrnh6x | Normal | 10 | 1.9.6.1.4.4 | 1.9.6.1.4.4 |  | 2025-04-04 17:00 | p | 27 |  | 2025-05-02 08:12
1070 | 5762 | BY50RWHTB6QfyvgvJksd | Summary | 36 | 1.9.6.9 | 1.9.6.9 |  | 2025-04-01 17:00 | p | 27 |  | 2025-04-29 14:50
1071 | 4074 | H2vE7zxiBRw3YTdo2zSW | Normal | 35 | 1.9.6.9.2 | 1.9.6.9.2 |  | 2025-03-31 17:00 | p | 27 |  | 2025-04-28 13:41
1072 | 4075 | dGbNHsOLhslKk8CjhyjE | Normal | 1 | 1.9.6.9.3 | 1.9.6.9.3 |  | 2025-04-01 17:00 | p | 27 |  | 2025-04-29 14:50
1073 | 6424 | xU9ngPKik2IYPonksYTK | Summary | 24 | 1.7.1.8 | 1.7.1.8 |  | 2025-03-14 17:00 | q | -101 |  | 2024-12-03 16:57
1074 | 6427 | NeAxFJaqSLize8VPNJ6N | Normal | 1 | 1.7.1.8.3 | 1.7.1.8.3 |  | 2025-03-14 17:00 | q | -101 |  | 2024-12-03 16:57
1075 | 6296 | SlR21lje1Tex9DLMlAM1 | Summary | 222 | 1.9.8 | 1.9.8 |  | 2026-10-05 12:00 | p | 927 |  | 2029-04-20 09:39
1076 | 4192 | vUDAXlHZqbmK6WAsX9hH | Summary | 139 | 1.9.8.1 | 1.9.8.1 |  | 2025-09-22 17:00 | q | -17 |  | 2025-09-05 08:03
1077 | 4196 | 2ZwOzHGH45ywtPvfASSG | Normal | 5 | 1.9.8.1.5 | 1.9.8.1.5 |  | 2025-09-22 17:00 | q | -17 |  | 2025-09-05 08:03
1078 | 4197 | 4xVk2zrTd9sJnt9BJFir | Summary | 36 | 1.9.8.1.6 | 1.9.8.1.6 |  | 2025-02-27 17:00 | q | -36 |  | 2025-01-22 17:00
1079 | 5974 | cJ7VeFZezCBnvYlHxCmb | Normal | 1 | 1.9.8.1.6.7 | 1.9.8.1.6.7 |  | 2025-02-27 17:00 | q | -119 |  | 2024-10-31 11:25
1080 | 4198 | k6X8NWhjfeQOPZdDpmna | Normal | 20 | 1.9.8.1.9 | 1.9.8.1.9 |  | 2025-03-10 17:00 | p | 29 |  | 2025-04-09 09:57
1081 | 5985 | AUKn3E7aViOsULw8HdKV | Normal | 131 | 1.9.8.1.12 | 1.9.8.1.12 |  | 2025-09-15 17:00 | q | -20 |  | 2025-08-26 15:35
1082 | 4222 | uotgqiCu1xVBvHdpBC3E | Summary | 97 | 1.9.8.2 | 1.9.8.2 |  | 2025-11-25 17:00 | q | -11 |  | 2025-11-14 11:45
1083 | 4231 | 8h0WH2qeIC7tfvcerCPa | Normal | 1 | 1.9.8.2.3 | 1.9.8.2.3 |  | 2025-06-24 17:00 | q | -183 |  | 2024-12-23 16:21
1084 | 4235 | QiaATNQSPId7svzcuO8r | Normal | 91 | 1.9.8.2.7 | 1.9.8.2.7 |  | 2025-11-25 17:00 | q | -11 |  | 2025-11-14 11:45
1085 | 4238 | ReJqSs3gutB053iVY5c7 | Summary | 76 | 1.9.8.4 | 1.9.8.4 |  | 2025-05-28 17:00 | p | 43 |  | 2025-07-11 10:20
1086 | 4242 | RIVyyga7UReDeuixs5m9 | Normal | 66 | 1.9.8.4.4 | 1.9.8.4.4 |  | 2025-05-13 17:00 | p | 44 |  | 2025-06-27 11:52
1087 | 4243 | LpPx7AWOh1V8dzWVWc6j | Normal | 1 | 1.9.8.4.5 | 1.9.8.4.5 |  | 2025-05-13 17:00 | q | -357 |  | 2024-05-21 15:48
1088 | 4246 | ANAzXnUTz1PCb3xsov4Y | Normal | 10 | 1.9.8.4.7 | 1.9.8.4.7 |  | 2025-05-28 17:00 | p | 43 |  | 2025-07-11 10:20
1089 | 4248 | E1RJwJWM8qrsKP3o7Toy | Normal | 1 | 1.9.8.7 | 1.9.8.7 |  | 2025-08-05 17:00 | q | -18 |  | 2025-07-18 16:27
1090 | 4251 | IBg36OMMKUy3vwEnRNF0 | Normal | 1 | 1.9.8.6 | 1.9.8.6 |  | 2025-06-05 17:00 | q | -667 |  | 2023-08-08 09:48
1091 | 4253 | hnujWIe1JDNg9VHs3TWw | Normal | 1 | 1.9.8.8 | 1.9.8.8 |  | 2025-08-12 17:00 | q | -22 |  | 2025-07-21 16:58
1092 | 4255 | TAfq40Sin0H6Q2YT0OS5 | Milestone | 0 | 1.9.8.3 | 1.9.8.3 |  | 2025-11-25 17:00 | q | -11 |  | 2025-11-14 11:45
1093 | 4256 | G2pYfP7dsnHVTgqQD6mD | Summary | 82 | 1.9.8.10 | 1.9.8.10 |  | 2026-01-27 17:00 | q | -783 |  | 2023-12-06 08:59
1094 | 4258 | GzQkXlTiYJMdE6nBDVeb | Normal | 6 | 1.9.8.10.1 | 1.9.8.10.1 |  | 2025-10-03 17:00 | q | -784 |  | 2023-08-11 16:09
1095 | 6090 | LkexiRQNUDyJAwm8EPYV | Normal | 32 | 1.9.8.10.7 | 1.9.8.10.7 |  | 2026-01-27 17:00 | q | -783 |  | 2023-12-06 08:59
1096 | 6187 | kIPGiItVAbHq2ks8DK41 | Normal | 5 | 1.9.8.10.6 | 1.9.8.10.6 |  | 2025-12-09 17:00 | q | -788 |  | 2023-10-13 16:14
1097 | 6430 | IYyY3jK4t9QuDyuxqyQ5 | Normal | 15 | 1.9.8.10.2 | 1.9.8.10.2 |  | 2025-10-27 17:00 | q | -789 |  | 2023-08-30 13:04
1098 | 6431 | mXx66gQ5BZWpD3idmZgM | Normal | 10 | 1.9.8.10.3 | 1.9.8.10.3 |  | 2025-11-10 17:00 | q | -784 |  | 2023-09-18 11:27
1099 | 6432 | vMoeJo3Rc30lMwFim6rn | Normal | 10 | 1.9.8.10.4 | 1.9.8.10.4 |  | 2025-11-25 17:00 | q | -784 |  | 2023-10-03 11:25
1100 | 6433 | zONKYXhH5yZJE26xvIWD | Normal | 4 | 1.9.8.10.5 | 1.9.8.10.5 |  | 2025-12-02 17:00 | q | -785 |  | 2023-10-09 09:37
1101 | 6083 | 3dsblDK1X9ztc27EZU3v | Normal | 1 | 1.9.8.5 | 1.9.8.5 |  | 2025-12-12 17:00 | p | 930 |  | 2028-06-30 09:58
1102 | 6084 | deZM0xh115wln716GUoI | Normal | 1 | 1.9.8.9 | 1.9.8.9 |  | 2026-10-05 12:00 | p | 927 |  | 2029-04-20 09:39
1103 | 7321 | CTokiQfH6gyOyeZJGrxP | Normal | 1 | 1.7.9.11 | 1.7.9.11 |  | 2025-05-30 17:00 | q | -662 |  | 2023-08-07 16:52
1104 | 6314 | PaZTrKFuMaJQzXHDclW5 | Summary | 34 | 1.9.2 | 1.9.2 |  | 2025-04-29 17:00 | p | 28 |  | 2025-05-28 09:44
1105 | 5666 | lc2LPCzbTjVw9vZ8eS89 | Summary | 23 | 1.9.2.2 | 1.9.2.2 |  | 2025-02-27 17:00 | p | 25 |  | 2025-03-25 16:29
1106 | 5667 | chBvra0KGhqU3lfHBAI4 | Summary | 23 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-02-27 17:00 | p | 25 |  | 2025-03-25 16:29
1107 | 5669 | bBSx7g3AuM8uxZcIYlIi | Normal | 20 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-02-27 17:00 | p | 25 |  | 2025-03-25 16:29
1108 | 5672 | 2GDxhVAL0LbO4lfSMjXo | Summary | 47 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-29 17:00 | p | 28 |  | 2025-05-28 09:44
1109 | 5690 | jLB7gq1wR8egZrMIoAc7 | Summary | 24 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-02 17:00 | p | 22 |  | 2025-04-25 09:18
1110 | 5691 | glUuWw43f2R9t2hl6VHO | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-03-13 17:00 | p | 21 |  | 2025-04-04 10:19
1111 | 5692 | KeXnvnZRx0KMyut3yw5s | Milestone | 0 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-03-13 17:00 | p | 21 |  | 2025-04-04 10:19
1112 | 5693 | VdKRFLdSc60knizSqFXc | Normal | 14 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-02 17:00 | p | 22 |  | 2025-04-25 09:18
1113 | 5694 | Gb0taOZcQ8l0cdHliY6j | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-16 17:00 | p | 25 |  | 2025-05-12 15:52
1114 | 5695 | ePp2idADlztrdEpItyCc | Milestone | 0 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-16 17:00 | p | 25 |  | 2025-05-12 15:52
1115 | 5696 | npE0RnxADwI7cDPG1fDa | Normal | 4 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-22 17:00 | p | 26 |  | 2025-05-19 10:36
1116 | 5697 | 4nIBzBv3LSP60HeOLv0f | Normal | 5 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-29 17:00 | p | 28 |  | 2025-05-28 09:44
1117 | 6315 | 2iW64uJmzViIcLEo0dMn | Summary | 181 | 1.9.5 | 1.9.5 |  | 2025-12-08 17:00 | p | 944 |  | 2028-07-10 11:57
1118 | 5532 | NHN4dwEEPEqCDqA4Rwlr | Summary | 74 | 1.9.5.1 | 1.9.5.1 |  | 2025-04-28 17:00 | p | 57 |  | 2025-06-25 09:29
1119 | 5535 | XVk7S0ldLHQUWflKhMBn | Normal | 11 | 1.9.5.1.2 | 1.9.5.1.2 |  | 2025-02-25 17:00 | p | 26 |  | 2025-03-24 10:42
1120 | 5536 | cYU0DBZylLxVRoLEp7Bc | Normal | 40 | 1.9.5.1.4 | 1.9.5.1.4 |  | 2025-04-28 17:00 | p | 57 |  | 2025-06-25 09:29
1121 | 5537 | 9xVQhmyTVkChMoMOy91g | Summary | 193 | 1.9.5.2 | 1.9.5.2 |  | 2025-10-24 17:00 | p | 950 |  | 2028-06-01 10:32
1122 | 5539 | kRsO3PSMDsMxji3dmdNc | Normal | 5 | 1.9.5.2.2 | 1.9.5.2.2 |  | 2025-02-14 17:00 | p | 929 |  | 2027-09-02 13:26
1123 | 5540 | GKx3XnA1BSbhTsgdKbqP | Normal | 14 | 1.9.5.2.8 | 1.9.5.2.8 |  | 2025-03-03 17:00 | p | 31 |  | 2025-04-04 14:59
1124 | 5541 | LhqIvyBzzdwllIHwrPz2 | Normal | 5 | 1.9.5.2.7 | 1.9.5.2.7 |  | 2025-03-03 17:00 | p | 29 |  | 2025-04-02 09:07
1125 | 5542 | 4ivItsonCrTGke19i41Z | Normal | 15 | 1.9.5.2.6 | 1.9.5.2.6 |  | 2025-03-03 17:00 | p | 29 |  | 2025-04-02 09:07
1126 | 5543 | XaHBDo6QUBfyTg5ESk7j | Normal | 15 | 1.9.5.2.9 | 1.9.5.2.9 |  | 2025-03-03 17:00 | p | 34 |  | 2025-04-07 16:10
1127 | 5544 | cIc3ARzcdrbXv6maHllr | Summary | 129 | 1.9.5.2.13 | 1.9.5.2.13 |  | 2025-09-17 17:00 | p | 944 |  | 2028-04-19 10:01
1128 | 5545 | 7UVU8IboY6NG7sqZCrUC | Normal | 7 | 1.9.5.2.13.2 | 1.9.5.2.13.2 |  | 2025-05-30 17:00 | p | 942 |  | 2027-12-29 16:29
1129 | 5546 | Shs5wuYOFSkTF1YslX8w | Normal | 6 | 1.9.5.2.13.5 | 1.9.5.2.13.5 |  | 2025-06-16 17:00 | p | 941 |  | 2028-01-14 10:46
1130 | 5547 | KglXvc5QwlHEboIvY96Q | Normal | 4 | 1.9.5.2.13.8 | 1.9.5.2.13.8 |  | 2025-07-14 17:00 | p | 939 |  | 2028-02-09 13:14
1131 | 5548 | Zfzda0CfmpiN8ZL93G3t | Normal | 5 | 1.9.5.2.13.9 | 1.9.5.2.13.9 |  | 2025-07-21 17:00 | p | 940 |  | 2028-02-17 13:18
1132 | 5549 | PgYJem7PJFdGgV04ojeL | Normal | 1 | 1.4.17 | 1.4.17 |  | 2025-07-22 17:00 | p | 940 |  | 2028-02-18 16:01
1133 | 5556 | fOMVaiOa0jnHOJyDUdVQ | Normal | 25 | 1.9.5.2.13.11 | 1.9.5.2.13.11 |  | 2025-09-17 17:00 | p | 944 |  | 2028-04-19 10:01
1134 | 5730 | ypyrsmMFJqJ9aPla6UhQ | Normal | 4 | 1.9.5.2.13.3 | 1.9.5.2.13.3 |  | 2025-06-05 17:00 | p | 942 |  | 2028-01-04 15:46
1135 | 5731 | uQF6Ff0bc2cqy3b37ZQc | Normal | 1 | 1.9.5.2.13.4 | 1.9.5.2.13.4 |  | 2025-06-06 17:00 | p | 942 |  | 2028-01-05 14:48
1136 | 5732 | OQKwpwUgImWCC2Fp5G0Q | Normal | 7 | 1.9.5.2.13.6 | 1.9.5.2.13.6 |  | 2025-06-26 17:00 | p | 942 |  | 2028-01-25 11:46
1137 | 5733 | wyOxVAS94HubPKo2yHJm | Normal | 7 | 1.9.5.2.13.7 | 1.9.5.2.13.7 |  | 2025-07-08 17:00 | p | 939 |  | 2028-02-03 13:14
1138 | 7000 | yP1oDcnUQTy3g68ZLgu0 | Normal | 8 | 1.9.5.2.13.1 | 1.9.5.2.13.1 |  | 2025-03-26 17:00 | p | 27 |  | 2025-04-23 16:51
1139 | 5557 | U376LwOjKfNZoVLUlmMD | Summary | 113 | 1.9.5.2.12 | 1.9.5.2.12 |  | 2025-08-12 17:00 | p | 944 |  | 2028-03-14 13:46
1140 | 5558 | RXAxJx3BHWNVdWFPfZ2a | Normal | 13 | 1.9.5.2.12.2 | 1.9.5.2.12.2 |  | 2025-05-09 17:00 | p | 943 |  | 2027-12-09 10:24
1141 | 5559 | jJoy8dUJMWD3ZuNw52D0 | Normal | 8 | 1.9.5.2.12.5 | 1.9.5.2.12.5 |  | 2025-06-02 17:00 | p | 941 |  | 2027-12-31 14:10
1142 | 5560 | wu3sL1wqoiodUr5mG52N | Normal | 4 | 1.9.5.2.12.8 | 1.9.5.2.12.8 |  | 2025-06-27 17:00 | p | 943 |  | 2028-01-27 11:57
1143 | 5561 | Vb2zzMF18WNANxlCzGiz | Normal | 5 | 1.9.5.2.12.9 | 1.9.5.2.12.9 |  | 2025-07-07 17:00 | p | 939 |  | 2028-02-02 14:54
1144 | 5562 | vp7j6GBYm2dAMLvxEFuE | Normal | 1 | 1.4.20 | 1.4.20 |  | 2025-07-08 17:00 | p | 939 |  | 2028-02-03 15:25
1145 | 5569 | 35aiC9HLOSrIl2OBwDvd | Normal | 25 | 1.9.5.2.12.11 | 1.9.5.2.12.11 |  | 2025-08-12 17:00 | p | 944 |  | 2028-03-14 13:46
1146 | 5734 | iq9bjqBZvH9Bj6912271 | Normal | 6 | 1.9.5.2.12.3 | 1.9.5.2.12.3 |  | 2025-05-19 17:00 | p | 944 |  | 2027-12-20 13:06
1147 | 5735 | Z8zFgfwvHK2hwW2AW8Qa | Normal | 1 | 1.9.5.2.12.4 | 1.9.5.2.12.4 |  | 2025-05-20 17:00 | p | 944 |  | 2027-12-21 13:16
1148 | 5736 | QgUmTWGvxjzq3xqrWPJK | Normal | 7 | 1.9.5.2.12.6 | 1.9.5.2.12.6 |  | 2025-06-11 17:00 | p | 943 |  | 2028-01-11 10:01
1149 | 5737 | iDzIA8f8DQgg2wVNkaUu | Normal | 7 | 1.9.5.2.12.7 | 1.9.5.2.12.7 |  | 2025-06-23 17:00 | p | 941 |  | 2028-01-21 13:29
1150 | 7001 | WpRQh8HvPfyDha8FH5FR | Normal | 9 | 1.9.5.2.12.1 | 1.9.5.2.12.1 |  | 2025-03-14 17:00 | p | 31 |  | 2025-04-15 16:20
1151 | 5570 | MuDwSgsBJjDxwFkSMWYJ | Summary | 116 | 1.9.5.2.11 | 1.9.5.2.11 |  | 2025-07-30 17:00 | p | 928 |  | 2028-02-14 08:18
1152 | 5571 | lfRAbO0c5jl7NaC6s7pm | Normal | 21 | 1.9.5.2.11.2 | 1.9.5.2.11.2 |  | 2025-04-14 17:00 | p | 940 |  | 2027-11-11 09:42
1153 | 5572 | jk3Vm36iIGViuk9dpLfQ | Normal | 8 | 1.9.5.2.11.5 | 1.9.5.2.11.5 |  | 2025-05-02 17:00 | p | 937 |  | 2027-11-26 08:06
1154 | 5573 | u3MfiduPa05JsS2ly7WD | Normal | 4 | 1.9.5.2.11.8 | 1.9.5.2.11.8 |  | 2025-06-12 17:00 | p | 936 |  | 2028-01-05 08:46
1155 | 5574 | 3iKE3riinMPRUpVpTfwx | Normal | 5 | 1.9.5.2.11.9 | 1.9.5.2.11.9 |  | 2025-06-20 17:00 | p | 935 |  | 2028-01-12 14:00
1156 | 5575 | 48yotl4pDzxbk5y0VDbK | Normal | 1 | 1.4.23 | 1.4.23 |  | 2025-06-23 17:00 | p | 933 |  | 2028-01-13 14:31
1157 | 5582 | 6tLu8emqwotxTkeBbEpy | Normal | 26 | 1.9.5.2.11.11 | 1.9.5.2.11.11 |  | 2025-07-30 17:00 | p | 928 |  | 2028-02-14 08:18
1158 | 5738 | ME2oX9BwgLu5cggaunhg | Normal | 5 | 1.9.5.2.11.3 | 1.9.5.2.11.3 |  | 2025-04-21 17:00 | p | 940 |  | 2027-11-18 09:40
1159 | 5739 | IivOSmNLtmlF9JKFLUrl | Normal | 1 | 1.9.5.2.11.4 | 1.9.5.2.11.4 |  | 2025-04-22 17:00 | p | 940 |  | 2027-11-19 08:41
1160 | 5740 | eRxCjL3dV2CpHvAG84r7 | Normal | 12 | 1.9.5.2.11.6 | 1.9.5.2.11.6 |  | 2025-05-20 17:00 | p | 936 |  | 2027-12-13 15:36
1161 | 5741 | 8Y4jq7dOt4lN4NYBT6r1 | Normal | 12 | 1.9.5.2.11.7 | 1.9.5.2.11.7 |  | 2025-06-06 17:00 | p | 935 |  | 2027-12-29 16:03
1162 | 6998 | CyWehBzIvIWKBi1qju4z | Normal | 15 | 1.9.5.2.11.1 | 1.9.5.2.11.1 |  | 2025-03-03 17:00 | p | 29 |  | 2025-04-02 09:07
1163 | 5583 | gkFBoXdv1oJb2jtBcO5M | Summary | 147 | 1.9.5.2.14 | 1.9.5.2.14 |  | 2025-10-24 17:00 | p | 950 |  | 2028-06-01 10:32
1164 | 5584 | 6WMzJdzS7tY0wFFuXnrc | Normal | 7 | 1.9.5.2.14.2 | 1.9.5.2.14.2 |  | 2025-06-17 17:00 | p | 940 |  | 2028-01-14 16:57
1165 | 5585 | KljMWvDEBGSuBTW4zQhZ | Normal | 7 | 1.9.5.2.14.5 | 1.9.5.2.14.5 |  | 2025-07-07 17:00 | p | 939 |  | 2028-02-02 15:52
1166 | 5586 | Z3ZWpIsgJCSKUX161hV0 | Normal | 4 | 1.9.5.2.14.8 | 1.9.5.2.14.8 |  | 2025-07-29 17:00 | p | 939 |  | 2028-02-24 11:24
1167 | 5587 | OXOUsYDejGVlgqn4Z1vl | Normal | 5 | 1.9.5.2.14.9 | 1.9.5.2.14.9 |  | 2025-08-05 17:00 | p | 940 |  | 2028-03-03 15:26
1168 | 5588 | MFjHKzinVVI0Ndx8qx0B | Normal | 1 | 1.4.26 | 1.4.26 |  | 2025-08-06 17:00 | p | 942 |  | 2028-03-06 16:52
1169 | 5595 | REFTk0AP9RBTibJWVhuH | Normal | 26 | 1.9.5.2.14.11 | 1.9.5.2.14.11 |  | 2025-10-24 17:00 | p | 950 |  | 2028-06-01 10:32
1170 | 5742 | 88bEv4EMiOL2y8w1ttIM | Normal | 4 | 1.9.5.2.14.3 | 1.9.5.2.14.3 |  | 2025-06-24 17:00 | p | 940 |  | 2028-01-21 16:37
1171 | 5743 | 0Uz4krHDVCdAlMd5aRwh | Normal | 1 | 1.9.5.2.14.4 | 1.9.5.2.14.4 |  | 2025-06-25 17:00 | p | 943 |  | 2028-01-25 09:57
1172 | 5744 | cSBfnbrbVLLFYTMEfBKA | Normal | 6 | 1.9.5.2.14.6 | 1.9.5.2.14.6 |  | 2025-07-15 17:00 | p | 943 |  | 2028-02-14 09:20
1173 | 5745 | ZY99Y6JX4jBylnfeedvo | Normal | 6 | 1.9.5.2.14.7 | 1.9.5.2.14.7 |  | 2025-07-23 17:00 | p | 939 |  | 2028-02-18 14:37
1174 | 6999 | AnycnugTW971av3hMZXE | Normal | 8 | 1.9.5.2.14.1 | 1.9.5.2.14.1 |  | 2025-04-07 17:00 | p | 27 |  | 2025-05-05 14:02
1175 | 6446 | XvbStahAymwCoqNIbMJG | Summary | 32 | 1.9.5.2.4 | 1.9.5.2.4 |  | 2025-04-15 17:00 | q | -365 |  | 2024-04-15 08:29
1176 | 6532 | 15e7xcLR1b1jSikaz0S2 | Normal | 32 | 1.9.5.2.4.2 | 1.9.5.2.4.2 |  | 2025-04-15 17:00 | q | -369 |  | 2024-04-11 13:05
1177 | 6533 | b0mutjzKj8FRw4zkbb8K | Normal | 32 | 1.9.5.2.4.1 | 1.9.5.2.4.1 |  | 2025-04-15 17:00 | q | -365 |  | 2024-04-15 08:29
1178 | 6534 | 8Gl2bk4Fxxo2fsClDJqG | Normal | 32 | 1.9.5.2.4.3 | 1.9.5.2.4.3 |  | 2025-04-15 17:00 | q | -370 |  | 2024-04-10 16:36
1179 | 6535 | dWze9AnK8NrEMD9LOEyU | Normal | 32 | 1.9.5.2.4.4 | 1.9.5.2.4.4 |  | 2025-04-15 17:00 | q | -369 |  | 2024-04-11 08:19
1180 | 6528 | LROLnQke0gWnMONa67YB | Summary | 50 | 1.9.5.2.5 | 1.9.5.2.5 |  | 2025-03-31 17:00 | p | 29 |  | 2025-04-30 11:27
1181 | 6531 | iX155TL3hNg9Ca4Bsb4A | Normal | 35 | 1.9.5.2.5.2 | 1.9.5.2.5.2 |  | 2025-03-31 17:00 | p | 29 |  | 2025-04-30 11:27
1182 | 6955 | CPACk87DS0kpO7pXcdwS | Normal | 10 | 1.9.5.2.10 | 1.9.5.2.10 |  | 2025-03-03 17:00 | p | 927 |  | 2027-09-17 14:49
1183 | 6997 | MBGoTUikAECGvIHYk1uV | Normal | 24 | 1.9.5.2.3 | 1.9.5.2.3 |  | 2025-03-14 17:00 | p | 941 |  | 2027-10-12 11:58
1184 | 5596 | upn4QoZvaKBmBMoyhnq5 | Summary | 90 | 1.9.5.3 | 1.9.5.3 |  | 2025-12-08 17:00 | p | 944 |  | 2028-07-10 11:57
1185 | 5597 | zKJsJYNcPRFZ7wBjvprv | Normal | 18 | 1.9.5.3.1 | 1.9.5.3.1 |  | 2025-08-22 17:00 | p | 940 |  | 2028-03-20 10:47
1186 | 5598 | zvvzNQqIPXzcVRwy0N44 | Summary | 52 | 1.9.5.3.2 | 1.9.5.3.2 |  | 2025-12-01 17:00 | p | 944 |  | 2028-07-03 15:24
1187 | 5599 | T0Oh47cWIVU9y2MKPB0U | Normal | 12 | 1.9.5.3.2.1 | 1.9.5.3.2.1 |  | 2025-10-01 17:00 | p | 942 |  | 2028-05-01 15:11
1188 | 5600 | oTkX6bjokLXQ590hdeFy | Normal | 12 | 1.9.5.3.2.2 | 1.9.5.3.2.2 |  | 2025-10-20 17:00 | p | 945 |  | 2028-05-23 11:10
1189 | 5601 | xa7cRxeKgQxZnuHNAYMQ | Normal | 12 | 1.9.5.3.2.3 | 1.9.5.3.2.3 |  | 2025-11-12 17:00 | p | 944 |  | 2028-06-14 08:04
1190 | 5602 | QlxDegibloFbHrPNJwyW | Normal | 12 | 1.9.5.3.2.4 | 1.9.5.3.2.4 |  | 2025-12-01 17:00 | p | 944 |  | 2028-07-03 15:24
1191 | 5603 | dwMYG7lg76TqxtTxZNCR | Normal | 5 | 1.9.5.3.3 | 1.9.5.3.3 |  | 2025-12-08 17:00 | p | 944 |  | 2028-07-10 11:57
1192 | 6189 | OaskfHPb0rGXxqxmUlvr | Summary | 69 | 1.7.2.7 | 1.7.2.7 |  | 2025-04-29 17:00 | p | 41 |  | 2025-06-10 15:50
1193 | 6248 | DGpV8AP7Q4dyYuiDaoIl | Summary | 56 | 1.7.2.7.2 | 1.7.2.7.2 |  | 2025-04-29 17:00 | p | 41 |  | 2025-06-10 15:50
1194 | 6251 | Ha7ZmVRhPp4EjAGEFQOQ | Normal | 56 | 1.7.2.7.2.3 | 1.7.2.7.2.3 |  | 2025-04-29 17:00 | p | 41 |  | 2025-06-10 15:50
1195 | 6252 | FwTW8u2nmxBgH6wyvtoz | Summary | 56 | 1.7.2.7.3 | 1.7.2.7.3 |  | 2025-04-29 17:00 | p | 29 |  | 2025-05-29 15:06
1196 | 6255 | 6Rcxv4eHz2WhxfD2wxtd | Normal | 56 | 1.7.2.7.3.3 | 1.7.2.7.3.3 |  | 2025-04-29 17:00 | p | 29 |  | 2025-05-29 15:06
1197 | 6256 | TcRehVKUpIeirJTvWiO5 | Summary | 14 | 1.7.2.7.4 | 1.7.2.7.4 |  | 2025-02-28 17:00 | p | 30 |  | 2025-03-31 14:46
1198 | 6259 | q6ww59eaDtL5Df1J4lsR | Normal | 14 | 1.7.2.7.4.3 | 1.7.2.7.4.3 |  | 2025-02-28 17:00 | p | 30 |  | 2025-03-31 14:46
1199 | 6260 | nYwGXpoj6WqcdUPfZoTk | Summary | 14 | 1.7.2.7.5 | 1.7.2.7.5 |  | 2025-02-28 17:00 | p | 33 |  | 2025-04-03 10:39
1200 | 6263 | aKytB1b2oD2t1WVaznUP | Normal | 14 | 1.7.2.7.5.3 | 1.7.2.7.5.3 |  | 2025-02-28 17:00 | p | 33 |  | 2025-04-03 10:39
1201 | 6317 | NzqiT3qChWGoVO5Oxj9C | Summary | 111 | 1.9.4 | 1.9.4 |  | 2025-09-16 17:00 | p | 397 |  | 2026-10-19 13:36
1202 | 5355 | lohINUHwZqjP23W1PYQO | Summary | 26 | 1.9.4.1 | 1.9.4.1 |  | 2025-04-14 17:00 | q | 0 |  | 2025-04-14 08:31
1203 | 5360 | ARncD9Nx3De5DONPy9Bs | Normal | 3 | 1.9.4.1.4 | 1.9.4.1.4 |  | 2025-04-14 17:00 | q | 0 |  | 2025-04-14 08:31
1204 | 7263 | mjGxmWsUF3dJi6MlhQpM | Normal | 1 | 1.7.4.1.5 | 1.7.4.1.5 |  | 2025-04-09 17:00 | q | 0 |  | 2025-04-09 16:48
1205 | 5362 | 4bsxfawvV6TKTvCq9VoB | Summary | 6 | 1.9.4.2 | 1.9.4.2 |  | 2025-02-25 17:00 | p | 497 |  | 2026-07-08 08:23
1206 | 5368 | NKJL1ZJN3KgUArkbA4qS | Normal | 3 | 1.9.4.2.4 | 1.9.4.2.4 |  | 2025-02-25 17:00 | p | 497 |  | 2026-07-08 08:23
1207 | 7260 | DPsh83rHAyIaiD8XYnO0 | Normal | 6 | 1.7.4.2.4 | 1.7.4.2.4 |  | 2025-02-19 17:00 | p | 496 |  | 2026-07-01 13:56
1208 | 7261 | isfym7y8CMuc9Vq3Mbcl | Normal | 1 | 1.7.4.2.5 | 1.7.4.2.5 |  | 2025-02-20 17:00 | p | 496 |  | 2026-07-02 11:08
1209 | 5375 | zkXPpJkHw8DPAtspwcmA | Summary | 124 | 1.9.4.4 | 1.9.4.4 |  | 2025-07-01 17:00 | p | 464 |  | 2026-10-09 11:51
1210 | 5376 | zSTdFwWI5FOaluV37lYS | Normal | 63 | 1.9.4.4.1 | 1.9.4.4.1 |  | 2025-07-01 17:00 | p | 464 |  | 2026-10-09 11:51
1211 | 5377 | Wv5w7NMYDRM71nE6dVi0 | Summary | 58 | 1.9.4.5 | 1.9.4.5 |  | 2025-06-09 17:00 | p | 3 |  | 2025-06-13 10:42
1212 | 5382 | VlX4WunUzdS7Nqvh5ftn | Normal | 20 | 1.9.4.5.5 | 1.9.4.5.5 |  | 2025-03-14 17:00 | p | 2 |  | 2025-03-17 08:25
1213 | 5383 | u1aficyBQ2O9A8MnpdfZ | Normal | 20 | 1.9.4.5.6 | 1.9.4.5.6 |  | 2025-04-11 17:00 | p | 6 |  | 2025-04-18 13:59
1214 | 5384 | d8i6C63YfOF3EovUl19W | Normal | 10 | 1.9.4.5.7 | 1.9.4.5.7 |  | 2025-04-25 17:00 | p | 6 |  | 2025-05-02 14:06
1215 | 5385 | ohwsmv9qOoV0RNzIdjJI | Normal | 15 | 1.9.4.5.8 | 1.9.4.5.8 |  | 2025-05-16 17:00 | p | 11 |  | 2025-05-28 10:53
1216 | 5386 | tSuemAovBYAaHNhFiwaF | Normal | 15 | 1.9.4.5.9 | 1.9.4.5.9 |  | 2025-06-09 17:00 | p | 3 |  | 2025-06-13 10:42
1217 | 5387 | 9gTKo9vjb1rQAbWcTOOW | Summary | 58 | 1.9.4.6 | 1.9.4.6 |  | 2025-06-09 17:00 | q | -6 |  | 2025-06-03 09:26
1218 | 5392 | TRJmldmXNRf3NwsZhgng | Normal | 20 | 1.9.4.6.5 | 1.9.4.6.5 |  | 2025-03-14 17:00 | q | -2 |  | 2025-03-12 13:55
1219 | 5393 | 3qvg7di25vdBD8UUvM1a | Normal | 20 | 1.9.4.6.6 | 1.9.4.6.6 |  | 2025-04-11 17:00 | q | -2 |  | 2025-04-09 13:03
1220 | 5394 | ungpeNo64cspVo3BuO9g | Normal | 10 | 1.9.4.6.7 | 1.9.4.6.7 |  | 2025-04-25 17:00 | q | -1 |  | 2025-04-24 13:29
1221 | 5395 | KZXvYFda88KgX9w7a3ES | Normal | 15 | 1.9.4.6.8 | 1.9.4.6.8 |  | 2025-05-16 17:00 | q | -2 |  | 2025-05-14 14:24
1222 | 5396 | FNjsTUKVT29tBcVlvaM6 | Normal | 15 | 1.9.4.6.9 | 1.9.4.6.9 |  | 2025-06-09 17:00 | q | -6 |  | 2025-06-03 09:26
1223 | 5397 | KGrMeH5y6HH9dj1tr8uB | Summary | 53 | 1.9.4.7 | 1.9.4.7 |  | 2025-08-25 17:00 | p | 10 |  | 2025-09-05 13:16
1224 | 5398 | EMMfZLgDhvN5O0lAfznQ | Normal | 15 | 1.9.4.7.1 | 1.9.4.7.1 |  | 2025-07-01 17:00 | p | 7 |  | 2025-07-09 13:26
1225 | 5399 | 5K7jeUOrZ3wka9S2O1Dn | Normal | 15 | 1.9.4.7.2 | 1.9.4.7.2 |  | 2025-07-23 17:00 | p | 6 |  | 2025-07-30 13:24
1226 | 5400 | I2IZFfCcy2hUSTtihPWq | Normal | 15 | 1.9.4.7.3 | 1.9.4.7.3 |  | 2025-08-13 17:00 | p | 6 |  | 2025-08-20 11:13
1227 | 5401 | WWZjxA63YxH38hnYmVKG | Normal | 8 | 1.9.4.7.4 | 1.9.4.7.4 |  | 2025-08-25 17:00 | p | 10 |  | 2025-09-05 13:16
1228 | 5402 | zDUD70mdAG3rcozejCwk | Summary | 15 | 1.9.4.8 | 1.9.4.8 |  | 2025-09-16 17:00 | p | 397 |  | 2026-10-19 13:36
1229 | 5403 | wP2WbhW6upJb7JmdzCw1 | Normal | 9 | 1.9.4.8.1 | 1.9.4.8.1 |  | 2025-09-08 17:00 | p | 10 |  | 2025-09-19 09:44
1230 | 5404 | UrewlDJ3J2c8Ueci7p9E | Normal | 6 | 1.9.4.8.2 | 1.9.4.8.2 |  | 2025-09-16 17:00 | p | 397 |  | 2026-10-19 13:36
1231 | 7264 | vNqQNKJIEgg8BiBzdWeI | Summary | 57 | 1.7.4.3.6 | 1.7.4.3.6 |  | 2025-07-01 17:00 | p | 448 |  | 2026-09-23 14:34
1232 | 7265 | uNFJkQaxxZ7oOYaM8QxX | Normal | 13 | 1.7.4.3.6.1 | 1.7.4.3.6.1 |  | 2025-04-29 17:00 | p | 449 |  | 2026-07-23 15:35
1233 | 7266 | y7TR6NxR4uOKxinxsnEt | Normal | 13 | 1.7.4.3.6.2 | 1.7.4.3.6.2 |  | 2025-05-16 17:00 | p | 451 |  | 2026-08-11 09:18
1234 | 7267 | f0BUmD79ZhKqjjzrwXUq | Normal | 13 | 1.7.4.3.6.3 | 1.7.4.3.6.3 |  | 2025-06-05 17:00 | p | 448 |  | 2026-08-28 16:14
1235 | 7268 | sP1zO7OhzT9CUKqdzecJ | Normal | 12 | 1.7.4.3.6.4 | 1.7.4.3.6.4 |  | 2025-06-24 17:00 | p | 448 |  | 2026-09-16 15:45
1236 | 7269 | 7v5GPnNw6yREyKfoeMiZ | Normal | 5 | 1.7.4.3.6.5 | 1.7.4.3.6.5 |  | 2025-07-01 17:00 | p | 448 |  | 2026-09-23 14:34
1237 | 7322 | XsHCl5GkwKVP3xy7r0jT | Summary | 85 | 1.7.5 | 1.7.5 |  | 2025-07-01 17:00 | q | -566 |  | 2023-12-13 10:24
1238 | 7528 | 8SnF5zCB4rJyZyQZLLZc | Normal | 8 | 1.7.5.1 | 1.7.5.1 |  | 2025-03-12 17:00 | q | -569 |  | 2023-08-21 13:24
1239 | 7529 | ugdLGMeRoSNQZE98ehwR | Normal | 8 | 1.7.5.2 | 1.7.5.2 |  | 2025-03-12 17:00 | q | -574 |  | 2023-08-16 13:45
1240 | 7530 | tZgNvNsEFqNHmYVKXpMu | Normal | 7 | 1.7.5.3 | 1.7.5.3 |  | 2025-03-21 17:00 | q | -569 |  | 2023-08-30 10:14
1241 | 7531 | WsQS39Ko43y2ykuRUNnk | Normal | 8 | 1.7.5.4 | 1.7.5.4 |  | 2025-04-02 17:00 | q | -566 |  | 2023-09-14 09:50
1242 | 7532 | tNKjUDGuH9lZvW14y0xJ | Normal | 22 | 1.7.5.5 | 1.7.5.5 |  | 2025-05-02 17:00 | q | -563 |  | 2023-10-17 11:23
1243 | 7533 | HKUUjAeDBFLcgj42uw3c | Normal | 19 | 1.7.5.6 | 1.7.5.6 |  | 2025-05-30 17:00 | q | -562 |  | 2023-11-15 13:09
1244 | 7534 | s7VTtgJqjYjf9pbLYcYj | Normal | 8 | 1.7.5.7 | 1.7.5.7 |  | 2025-06-11 17:00 | q | -562 |  | 2023-11-27 10:34
1245 | 7535 | uGgP1gHCy12zlVFcLeTG | Normal | 6 | 1.7.5.8 | 1.7.5.8 |  | 2025-06-20 17:00 | q | -567 |  | 2023-12-01 16:48
1246 | 7536 | kbIucnV7qsI0ZjxbK1cH | Normal | 6 | 1.7.5.9 | 1.7.5.9 |  | 2025-06-30 17:00 | q | -566 |  | 2023-12-12 13:17
1247 | 7537 | ZiOXL4e3BgetRuJ4aYKK | Normal | 1 | 1.7.5.10 | 1.7.5.10 |  | 2025-07-01 17:00 | q | -566 |  | 2023-12-13 10:24
1248 | 6688 | aKOlgm9Tw9oPXF0YCFLp | Summary | 911 | 1.11 | 1.11 |  | 2028-09-27 17:00 | q | -588 |  | 2027-02-17 10:32
1249 | 6689 | fEYxMDiPOAwjjU8zha5c | Normal | 396 | 1.11.1 | 1.11.1 |  | 2026-09-08 17:00 | q | -119 |  | 2026-05-12 11:12
1250 | 6690 | bopLkaAZbmZjIM9EGI6L | Normal | 532 | 1.11.2 | 1.11.2 |  | 2028-09-27 17:00 | q | -1017 |  | 2025-12-15 14:47
1251 | 6691 | xLErpFHjPEH3ifHRbBMY | Normal | 396 | 1.11.3 | 1.11.3 |  | 2026-09-08 17:00 | p | 161 |  | 2027-02-17 10:32
1252 | 6692 | g8WcEZ6I6SGdlePHrYPP | Normal | 248 | 1.11.4 | 1.11.4 |  | 2026-02-05 17:00 | p | 62 |  | 2026-04-09 16:49
1253 | 6695 | Bx0BPJ0BcPw49QEL7Psq | Normal | 313 | 1.11.8 | 1.11.8 |  | 2026-05-08 17:00 | q | -66 |  | 2026-03-03 16:50
1254 | 6696 | XbFIp383UbA72xJPH4hJ | Normal | 101 | 1.11.9 | 1.11.9 |  | 2025-07-03 17:00 | p | 28 |  | 2025-08-01 10:33
1255 | 6697 | gpkN7vTMpz4ZZxhDAmeL | Normal | 126 | 1.11.10 | 1.11.10 |  | 2025-08-08 17:00 | p | 32 |  | 2025-09-10 09:29
1256 | 6698 | eRsel9yyFaDkcYLZgvjC | Normal | 142 | 1.11.11 | 1.11.11 |  | 2025-09-02 17:00 | p | 42 |  | 2025-10-15 13:26
1257 | 6699 | k8943lu4TS9ZW2TcUvha | Normal | 256 | 1.11.12 | 1.11.12 |  | 2026-02-18 17:00 | p | 75 |  | 2026-05-05 10:14
1258 | 7376 | FfEUU5kpALOu6FlmjosD | Normal | 396 | 1.10.3 | 1.10.3 |  | 2026-09-08 17:00 | p | 58 |  | 2026-11-06 16:05
1259 | 7378 | YjoFZZooPnFRzsk2Ba2E | Normal | 288 | 1.10.6 | 1.10.6 |  | 2026-04-03 17:00 | p | 138 |  | 2026-08-20 08:40
1260 | 7379 | 7GajZBAFakrGWC1WlgE6 | Normal | 142 | 1.10.14 | 1.10.14 |  | 2025-09-02 17:00 | q | -25 |  | 2025-08-08 10:53
1261 | 7380 | wkyoOF6gHS9pA0Dm9pZY | Normal | 140 | 1.10.17 | 1.10.17 |  | 2025-08-28 17:00 | p | 0 |  | 2025-08-29 09:36
1262 | 7131 | XTX9Wl5SzTxAD1rtsh9U | Summary | 0 | 1.10 | 1.10 |  | 2027-01-01 08:05 | p | 496 |  | 2028-05-11 14:47
1263 | 156 | 0RXSkgYJdrs7AeQvgU3w | Milestone | 0 | 1.10.24 | 1.10.24 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
1264 | 157 | DYCfhHgWVvjY4WPSrw6q | Milestone | 0 | 1.10.25 | 1.10.25 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
1265 | 7107 | fjlRoMsMUGjOnNWoUkGJ | Milestone | 0 | 1.10.16 | 1.10.16 |  | 2027-01-01 08:05 | p | 5 |  | 2027-01-06 08:12
1266 | 7108 | wFwSqsIrP0eolc7owrIn | Milestone | 0 | 1.10.3 | 1.10.3 |  | 2025-04-10 17:00 | q | -3 |  | 2025-04-07 10:08
1267 | 7110 | fycPVr34q6lr2y2bEJNl | Milestone | 0 | 1.10.9 | 1.10.9 |  | 2025-08-05 17:00 | p | 35 |  | 2025-09-10 14:26
1268 | 7111 | gs1r9nT3BBBdW42nHT47 | Milestone | 0 | 1.10.13 | 1.10.13 |  | 2025-10-16 17:00 | p | 31 |  | 2025-11-17 09:47
1269 | 7112 | a270fhhuENq55tFKO8IB | Milestone | 0 | 1.10.10 | 1.10.10 |  | 2025-11-28 17:00 | p | 23 |  | 2025-12-22 09:42
1270 | 7114 | pZqvbi91bBhqyjB86evl | Milestone | 0 | 1.10.2 | 1.10.2 |  | 2026-03-06 17:00 | p | 20 |  | 2026-03-27 11:53
1271 | 7115 | mxRJVREYCLlOZtWGohdT | Milestone | 0 | 1.10.8 | 1.10.8 |  | 2026-04-03 17:00 | p | 9 |  | 2026-04-13 11:49
1272 | 7116 | 4gFjRlWXKNF16b9sFMXr | Milestone | 0 | 1.10.11 | 1.10.11 |  | 2025-09-24 17:00 | q | -170 |  | 2025-04-07 15:53
1273 | 7117 | zFlqKdf38AVahGy9Q9X8 | Milestone | 0 | 1.10.12 | 1.10.12 |  | 2026-01-14 17:00 | q | -8 |  | 2026-01-06 13:47
1274 | 7118 | 6jNHf85fMsjQD6qn9QnY | Milestone | 0 | 1.10.14 | 1.10.14 |  | 2025-12-15 17:00 | p | 27 |  | 2026-01-12 08:25
1275 | 7119 | OQnmDeJwrgb4ibYKrZjo | Milestone | 0 | 1.10.15 | 1.10.15 |  | 2025-10-01 17:00 | q | -586 |  | 2024-02-23 09:07
1276 | 7120 | ewfCDE69jjk4Zb5M5CES | Milestone | 0 | 1.10.4 | 1.10.4 |  | 2025-04-02 17:00 | q | -6 |  | 2025-03-27 13:16
1277 | 7121 | V4W6CQQo6lTjRlhYdPDq | Milestone | 0 | 1.10.5 | 1.10.5 |  | 2025-05-19 17:00 | p | 34 |  | 2025-06-23 10:29
1278 | 7122 | ZQwX0qpiGy3bERfpXjQ0 | Milestone | 0 | 1.10.6 | 1.10.6 |  | 2025-04-07 17:00 | p | 27 |  | 2025-05-05 10:48
1279 | 7123 | 0fpNMQTy9Zfk1YAC7GK2 | Milestone | 0 | 1.10.7 | 1.10.7 |  | 2025-04-01 17:00 | q | -6 |  | 2025-03-26 11:36
1280 | 7124 | yYQOOagkBr46kWICPuG6 | Milestone | 0 | 1.10.17 | 1.10.17 |  | 2025-09-11 17:00 | q | -2814 |  | 2017-12-28 16:20
1281 | 7125 | a4xeGKWGk9YyWLffVRQZ | Milestone | 0 | 1.10.18 | 1.10.18 |  | 2025-10-08 17:00 | q | -2809 |  | 2018-01-29 14:01
1282 | 7126 | XIH51zzlt2AXqf8IkYxf | Milestone | 0 | 1.10.19 | 1.10.19 |  | 2025-11-04 17:00 | q | -2812 |  | 2018-02-22 16:01
1283 | 7129 | kvNY0frGkARL99AbSHw0 | Milestone | 0 | 1.10.22 | 1.10.22 |  | 2025-05-19 17:00 | p | 1 |  | 2025-05-21 11:08

## Actual-Start
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Actual Start - 25 (1%) | Actual Start - 25 (1%) | Actual Start - 25 (1%) | Actual Start - 25 (1%) | Actual Start - 25 (1%) | Actual Start - 25 (1%) | Actual Start - 25 (1%) | Actual Start - 25 (1%) | Actual Start - 25 (1%) | Actual Start - 25 (1%) | Actual Start - 25 (1%) | Actual Start - 25 (1%) | Actual Start - 25 (1%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 7219 | tMHxEODKuKminmE9Mjg5 | Normal | 1 | 1.3.2.3.2.4.4 | 1.3.2.3.2.4.4 |  | O | p |  |  | 2025-02-12 08:00
2 | 1457 | W1XQ7yoZAeSgm7UftoXN | Normal | 1 | 1.5.5.1.2 | 1.5.5.1.2 |  | O | p |  |  | 2025-02-14 08:00
3 | 5627 | s0vjJX7zGlVyBdE0eigo | Summary | 15 | 1.5.2.2.8 | 1.5.2.2.8 |  | O | p |  |  | 2025-02-10 08:00
4 | 7545 | 65jUkOPqlMfpoMROhJ4O | Normal | 5 | 1.5.3.2.9.1 | 1.5.3.2.9.1 |  | O | p |  |  | 2025-02-10 08:00
5 | 5637 | agdOsAK6kuG5dvRDXVyv | Milestone | 0 | 1.5.2.2.9.2 | 1.5.2.2.9.2 |  | 2025-01-08 17:00 | q |  |  | O
6 | 5638 | jBSFjjY1RfmWgqa8tOlO | Normal | 0 | 1.5.2.2.9.3 | 1.5.2.2.9.3 |  | 2025-01-09 08:00 | q |  |  | O
7 | 5639 | ymvGdGMdlU958QTwMU9V | Normal | 0 | 1.5.2.2.9.4 | 1.5.2.2.9.4 |  | 2025-01-27 08:00 | q |  |  | O
8 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | 2025-01-27 13:00 | q |  |  | O
9 | 1463 | IQX94tuow2VKmVJTuhEN | Normal | 1 | 1.6.6.1.3 | 1.6.6.1.3 |  | O | p |  |  | 2025-02-13 08:00
10 | 6738 | XB1ZMgqMWvDJpnRGKTB3 | Normal | 3 | 1.6.4.18.3.3.2.10 | 1.6.4.18.3.3.2.10 |  | O | p |  |  | 2025-02-11 08:00
11 | 7270 | 3AlavOi01JfJwLM1b81K | Milestone | 0 | 1.6.4.18.3.3.2.6 | 1.6.4.18.3.3.2.6 |  | O | p |  |  | 2025-02-13 17:00
12 | 7277 | hIopgQViPH34dy6jPgEs | Normal | 6 | 1.6.4.18.3.3.7.5 | 1.6.4.18.3.3.7.5 |  | O | p |  |  | 2025-03-07 08:00
13 | 7295 | tyaakhlAtuOpVSt7bVvo | Normal | 1 | 1.6.4.18.3.3.6.2 | 1.6.4.18.3.3.6.2 |  | O | p |  |  | 2025-02-10 08:00
14 | 7312 | ZHpaj2955bjmxPKFBEf2 | Normal | 2 | 1.6.3.11.1.3.5.3 | 1.6.3.11.1.3.5.3 |  | O | p |  |  | 2025-02-10 08:00
15 | 6295 | uPS9GNqRLP4065SnBhEr | Summary | 387 | 1.8.5 | 1.8.5 |  | 2024-09-03 08:00 | q | -393 |  | 2023-08-07 08:00
16 | 3679 | 1KDcwGZKgevw1MizqBh0 | Summary | 387 | 1.8.5.1 | 1.8.5.1 |  | 2024-09-03 08:00 | q | -393 |  | 2023-08-07 08:00
17 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 2021-01-04 08:00 | q | -1307 |  | 2017-06-07 08:00
18 | 6279 | p7EJXT1muDSglD2OZLFH | Summary | 274 | 1.9.7 | 1.9.7 |  | 2022-03-07 08:00 | q | -1734 |  | 2017-06-07 08:00
19 | 1484 | 6ARiGRg3KLswRpJLOmGD | Summary | 229 | 1.9.7.18 | 1.9.7.18 |  | 2023-10-24 08:00 | q | -2330 |  | 2017-06-07 08:00
20 | 1540 | GIXHFfgJ4jA0lgUlb0GT | Normal | 1 | 1.9.7.15.5 | 1.9.7.15.5 |  | O | p |  |  | 2025-02-12 08:00
21 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | O | p |  |  | 2027-09-01 08:00
22 | 5533 | g1oQNBzKk6OrBukgGH7R | Normal | 40 | 1.9.5.1.3 | 1.9.5.1.3 |  | O | p |  |  | 2025-03-04 08:00
23 | 7262 | dH18W6KApKWC8TAOWb50 | Normal | 36 | 1.7.4.1.4 | 1.7.4.1.4 |  | O | p |  |  | 2025-02-12 08:00
24 | 7551 | G4afE8kOleATkD8qyqeP | Normal | 1 | 1.10.19 | 1.10.19 |  | O | p |  |  | 2017-06-07 08:00
25 | 7131 | XTX9Wl5SzTxAD1rtsh9U | Summary | 0 | 1.10 | 1.10 |  | 2023-10-12 17:00 | q | -2114 |  | 2017-12-28 16:20

## Actual-Finish
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Actual Finish - 35 (2%) | Actual Finish - 35 (2%) | Actual Finish - 35 (2%) | Actual Finish - 35 (2%) | Actual Finish - 35 (2%) | Actual Finish - 35 (2%) | Actual Finish - 35 (2%) | Actual Finish - 35 (2%) | Actual Finish - 35 (2%) | Actual Finish - 35 (2%) | Actual Finish - 35 (2%) | Actual Finish - 35 (2%) | Actual Finish - 35 (2%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 7211 | wSDYMNBcPlclxMN6Hc8V | Normal | 5 | 1.3.2.3.2.3.1 | 1.3.2.3.2.3.1 |  | O | p |  |  | 2025-02-14 17:00
2 | 7218 | 5fSpBiSdaCD1mvMsYs0j | Normal | 2 | 1.3.2.3.2.4.3 | 1.3.2.3.2.4.3 |  | O | p |  |  | 2025-02-11 17:00
3 | 7219 | tMHxEODKuKminmE9Mjg5 | Normal | 1 | 1.3.2.3.2.4.4 | 1.3.2.3.2.4.4 |  | O | p |  |  | 2025-02-12 17:00
4 | 7226 | fsyu9CvTMAXTCK7e04ez | Normal | 1 | 1.3.2.3.2.5.3 | 1.3.2.3.2.5.3 |  | O | p |  |  | 2025-02-10 17:00
5 | 7515 | jdxLrBmn54gbF5MbPNVU | Normal | 5 | 1.3.2.3.2.5.8 | 1.3.2.3.2.5.8 |  | O | p |  |  | 2025-02-14 17:00
6 | 631 | jjFU6HpNq2otAi9zmRWR | Normal | 2 | 1.5.6.6.2.7 | 1.5.6.6.2.7 |  | O | p |  |  | 2025-02-11 17:00
7 | 6141 | PCEOtJROHHMKXYkoR4rp | Normal | 3 | 1.5.6.5.1 | 1.5.6.5.1 |  | O | p |  |  | 2025-02-12 17:00
8 | 1457 | W1XQ7yoZAeSgm7UftoXN | Normal | 1 | 1.5.5.1.2 | 1.5.5.1.2 |  | O | p |  |  | 2025-02-14 17:00
9 | 7545 | 65jUkOPqlMfpoMROhJ4O | Normal | 5 | 1.5.3.2.9.1 | 1.5.3.2.9.1 |  | O | p |  |  | 2025-02-14 17:00
10 | 5635 | ZYzv9KOmVdYL2d3ZPb8b | Summary | 0 | 1.5.2.2.9 | 1.5.2.2.9 |  | 2025-02-03 12:00 | q |  |  | O
11 | 5637 | agdOsAK6kuG5dvRDXVyv | Milestone | 0 | 1.5.2.2.9.2 | 1.5.2.2.9.2 |  | 2025-01-08 17:00 | q |  |  | O
12 | 5638 | jBSFjjY1RfmWgqa8tOlO | Normal | 0 | 1.5.2.2.9.3 | 1.5.2.2.9.3 |  | 2025-01-24 17:00 | q |  |  | O
13 | 5639 | ymvGdGMdlU958QTwMU9V | Normal | 0 | 1.5.2.2.9.4 | 1.5.2.2.9.4 |  | 2025-01-27 12:00 | q |  |  | O
14 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | 2025-02-03 12:00 | q |  |  | O
15 | 1463 | IQX94tuow2VKmVJTuhEN | Normal | 1 | 1.6.6.1.3 | 1.6.6.1.3 |  | O | p |  |  | 2025-02-13 17:00
16 | 3973 | 00qHhBlTe8pinGtKpu3n | Normal | 4 | 1.6.4.6 | 1.6.4.6 |  | O | p |  |  | 2025-02-13 17:00
17 | 6738 | XB1ZMgqMWvDJpnRGKTB3 | Normal | 3 | 1.6.4.18.3.3.2.10 | 1.6.4.18.3.3.2.10 |  | O | p |  |  | 2025-02-13 17:00
18 | 7003 | XfnOKCk0EbakXF7t35fN | Normal | 1 | 1.6.4.18.3.3.2.9 | 1.6.4.18.3.3.2.9 |  | O | p |  |  | 2025-02-10 17:00
19 | 7270 | 3AlavOi01JfJwLM1b81K | Milestone | 0 | 1.6.4.18.3.3.2.6 | 1.6.4.18.3.3.2.6 |  | O | p |  |  | 2025-02-13 17:00
20 | 7277 | hIopgQViPH34dy6jPgEs | Normal | 6 | 1.6.4.18.3.3.7.5 | 1.6.4.18.3.3.7.5 |  | O | p |  |  | 2025-03-14 17:00
21 | 7295 | tyaakhlAtuOpVSt7bVvo | Normal | 1 | 1.6.4.18.3.3.6.2 | 1.6.4.18.3.3.6.2 |  | O | p |  |  | 2025-02-10 17:00
22 | 7312 | ZHpaj2955bjmxPKFBEf2 | Normal | 2 | 1.6.3.11.1.3.5.3 | 1.6.3.11.1.3.5.3 |  | O | p |  |  | 2025-02-11 17:00
23 | 1539 | ySsQ3GXU4tpHt4hn7HeO | Normal | 2 | 1.9.7.15.4 | 1.9.7.15.4 |  | O | p |  |  | 2025-02-11 17:00
24 | 1540 | GIXHFfgJ4jA0lgUlb0GT | Normal | 1 | 1.9.7.15.5 | 1.9.7.15.5 |  | O | p |  |  | 2025-02-12 17:00
25 | 1560 | fBOtciokyA85OuE15WSO | Normal | 1 | 1.9.7.19.10 | 1.9.7.19.10 |  | O | p |  |  | 2025-02-10 17:00
26 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | O | p |  |  | 2027-09-28 17:00
27 | 5533 | g1oQNBzKk6OrBukgGH7R | Normal | 40 | 1.9.5.1.3 | 1.9.5.1.3 |  | O | p |  |  | 2025-04-28 17:00
28 | 5358 | Tenn83cNUrlWZNLgXJG2 | Normal | 2 | 1.9.4.1.2 | 1.9.4.1.2 |  | O | p |  |  | 2025-02-11 17:00
29 | 5359 | VhUQP0fhGYyFZ67e4nln | Normal | 2 | 1.9.4.1.3 | 1.9.4.1.3 |  | O | p |  |  | 2025-02-11 17:00
30 | 7262 | dH18W6KApKWC8TAOWb50 | Normal | 36 | 1.7.4.1.4 | 1.7.4.1.4 |  | O | p |  |  | 2025-04-08 17:00
31 | 5379 | 7aIIakNe0KPRF0TCK1un | Normal | 2 | 1.9.4.5.2 | 1.9.4.5.2 |  | O | p |  |  | 2025-02-11 17:00
32 | 5381 | HgkAkSCruVdxdZyXC7sW | Normal | 4 | 1.9.4.5.4 | 1.9.4.5.4 |  | O | p |  |  | 2025-02-13 17:00
33 | 5389 | 0FrUudkzBjpolAMz4tT0 | Normal | 2 | 1.9.4.6.2 | 1.9.4.6.2 |  | O | p |  |  | 2025-02-11 17:00
34 | 5391 | rUGJjnqPCImSizDtYOdy | Normal | 4 | 1.9.4.6.4 | 1.9.4.6.4 |  | O | p |  |  | 2025-02-13 17:00
35 | 7551 | G4afE8kOleATkD8qyqeP | Normal | 1 | 1.10.19 | 1.10.19 |  | O | p |  |  | 2017-06-07 17:00

## Baseline-Start
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2

## Baseline-Finish
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2

## Early-Start
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Early Start - 1010 (48%) | Early Start - 1010 (48%) | Early Start - 1010 (48%) | Early Start - 1010 (48%) | Early Start - 1010 (48%) | Early Start - 1010 (48%) | Early Start - 1010 (48%) | Early Start - 1010 (48%) | Early Start - 1010 (48%) | Early Start - 1010 (48%) | Early Start - 1010 (48%) | Early Start - 1010 (48%) | Early Start - 1010 (48%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 152 | QJ29ZvAvtEjBcpqHDer1 | Milestone | 0 | 1.2.3 | 1.2.3 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
2 | 155 | 1yu6CrDX9QU5hWE1UWMV | Milestone | 0 | 1.2.7.11 | 1.2.7.11 |  | 2026-10-08 16:58 | p | 620 |  | 2028-06-20 14:26
3 | 166 | KkWbk0R1FXz2L56lHFvV | Normal | 2 | 1.2.7.4 | 1.2.7.4 |  | 2025-09-17 08:00 | p | 15 |  | 2025-10-02 14:07
4 | 6618 | LspmB73Oe2b9O1GVbm64 | Milestone | 0 | 1.2.7.2 | 1.2.7.2 |  | 2025-04-30 17:00 | p | 15 |  | 2025-05-16 13:13
5 | 6338 | whnkqeDzsaW1H7xphaZA | Normal | 49 | 1.2.7.3.4 | 1.2.7.3.4 |  | 2025-05-13 08:00 | p | 14 |  | 2025-05-27 08:33
6 | 6640 | QUv6m7GotPkUb98mhJX7 | Normal | 14 | 1.2.7.3.6 | 1.2.7.3.6 |  | 2025-08-27 08:00 | p | 16 |  | 2025-09-12 09:49
7 | 6872 | SjyWialEYK436pEnV5Nr | Normal | 1 | 1.2.7.5 | 1.2.7.5 |  | 2025-09-19 08:00 | p | 17 |  | 2025-10-06 13:01
8 | 6874 | 1XFpbhK6U752FQe8voXZ | Normal | 1 | 1.2.7.6 | 1.2.7.6 |  | 2026-01-29 15:00 | p | 33 |  | 2026-03-03 15:34
9 | 6878 | VU7w4voCV7rMMsz4AnPW | Normal | 1 | 1.2.7.10 | 1.2.7.10 |  | 2025-05-28 08:00 | q | 0 |  | 2025-05-27 08:17
10 | 6879 | Vbp0cBOXY9azJeyTE4S4 | Normal | 3 | 1.2.7.7 | 1.2.7.7 |  | 2026-03-17 15:00 | p | 30 |  | 2026-04-17 09:06
11 | 6880 | ZuauWvCPNW7n2NMscMO2 | Normal | 4 | 1.2.7.8 | 1.2.7.8 |  | 2026-07-24 16:58 | q | 0 |  | 2026-07-24 15:08
12 | 6881 | XekYY8n1P4vELtk4BUks | Normal | 1 | 1.2.7.9 | 1.2.7.9 |  | 2026-08-04 16:58 | q | 0 |  | 2026-08-04 11:54
13 | 7550 | fUEnUBwdI1z3bgOngjaQ | Milestone | 0 | 1.2.7.5 | 1.2.7.5 |  | 2025-11-13 08:00 | q | -37 |  | 2025-10-06 15:42
14 | 168 | MT1CsCIMkhjJER6f3fjG | Milestone | 0 | 1.2.8.4 | 1.2.8.4 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
15 | 5294 | A0MDYkkQxesjEWQub0UM | Milestone | 0 | 1.2.8.3 | 1.2.8.3 |  | 2025-09-18 17:00 | p | 17 |  | 2025-10-06 13:01
16 | 173 | vJHK0TlIBzGpfYqdt8YI | Milestone | 0 | 1.2.9.4 | 1.2.9.4 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
17 | 177 | V4ys3lAm8KEbtjGqLAuR | Milestone | 0 | 1.2.9.2 | 1.2.9.2 |  | 2025-10-21 12:00 | p | 28 |  | 2025-11-19 09:32
18 | 178 | Cncpm0GACo0ppNIEy1Gp | Milestone | 0 | 1.2.9.3 | 1.2.9.3 |  | 2025-10-27 12:00 | p | 29 |  | 2025-11-25 16:19
19 | 180 | 9Vp3PBZnh9TpV8TGBWRG | Milestone | 0 | 1.2.10.14 | 1.2.10.14 |  | 2026-09-25 17:00 | p | 104 |  | 2027-01-08 08:25
20 | 193 | nJh7oj8wCJYW8hyepdLI | Milestone | 0 | 1.2.10.12 | 1.2.10.12 |  | 2025-09-09 17:00 | p | 12 |  | 2025-09-22 16:40
21 | 194 | wTcNF86mfD2cPQPmQB1c | Milestone | 0 | 1.2.10.13 | 1.2.10.13 |  | 2026-04-02 17:00 | p | 84 |  | 2026-06-26 11:47
22 | 7132 | osdxrWYmqQZxyGZXe9Pr | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 2025-03-24 17:00 | q | -31 |  | 2025-02-21 16:57
23 | 7546 | tdocr3pqURBYHZWcAyMG | Normal | 1 | 1.2.10.12 | 1.2.10.12 |  | 2025-03-28 08:00 | q | -90 |  | 2024-12-27 08:56
24 | 7547 | 2p5uMAQ0v8mT9pq4KeWp | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 2025-03-14 08:00 | q | -80 |  | 2024-12-23 17:00
25 | 7548 | TdNnLE8G4vf1vBjggzLw | Normal | 1 | 1.2.10.15 | 1.2.10.15 |  | 2025-03-10 08:00 | q | -73 |  | 2024-12-26 08:22
26 | 7549 | yUAt6Fi3Vichq9Ai1DSh | Normal | 1 | 1.2.10.13 | 1.2.10.13 |  | 2025-02-20 08:00 | q | -58 |  | 2024-12-24 08:00
27 | 195 | jWoM7YMyhsN7uWtVDNIl | Summary | 276 | 1.2.11 | 1.2.11 |  | 2025-06-23 17:00 | p | 87 |  | 2025-09-19 09:47
28 | 196 | kzYOxx4jS6vhIcTyxNFn | Milestone | 0 | 1.2.11.11 | 1.2.11.11 |  | 2026-07-31 12:00 | p | 929 |  | 2029-02-14 13:47
29 | 197 | LZAvhCOF77OBkAngJSDi | Milestone | 0 | 1.2.11.1 | 1.2.11.1 |  | 2025-06-23 17:00 | p | 933 |  | 2028-01-13 14:31
30 | 198 | X7Nxs9NuQXJ5Bf6aQwVp | Milestone | 0 | 1.2.11.2 | 1.2.11.2 |  | 2025-07-08 17:00 | p | 939 |  | 2028-02-03 15:25
31 | 199 | TiaYdQ98Ovd3qBAfSAyG | Milestone | 0 | 1.2.11.3 | 1.2.11.3 |  | 2025-07-22 17:00 | p | 940 |  | 2028-02-18 16:01
32 | 200 | yynHcCtrZd0Ye6iQJb2E | Milestone | 0 | 1.2.11.4 | 1.2.11.4 |  | 2025-08-06 17:00 | p | 942 |  | 2028-03-06 16:52
33 | 202 | mjF0YLun5LIdlxtu3zFl | Milestone | 0 | 1.2.11.5 | 1.2.11.5 |  | 2025-08-26 17:00 | p | 23 |  | 2025-09-19 09:47
34 | 203 | 2a1x42QofxcVsgjcXtkr | Milestone | 0 | 1.2.11.6 | 1.2.11.6 |  | 2025-06-23 17:00 | p | 933 |  | 2028-01-13 14:31
35 | 204 | 8T22gllTunmLl2jY7IMk | Milestone | 0 | 1.2.11.7 | 1.2.11.7 |  | 2025-07-08 17:00 | p | 939 |  | 2028-02-03 15:25
36 | 205 | dm3U5Xjvi5rN2LqWegXW | Milestone | 0 | 1.2.11.8 | 1.2.11.8 |  | 2025-07-22 17:00 | p | 940 |  | 2028-02-18 16:01
37 | 206 | ZOAcdJHtChBG5MUjo5uw | Milestone | 0 | 1.2.11.9 | 1.2.11.9 |  | 2025-08-06 17:00 | p | 942 |  | 2028-03-06 16:52
38 | 209 | 0FNuAiL5ZzPZSZ3dZfoV | Milestone | 0 | 1.2.11.10 | 1.2.11.10 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
39 | 6077 | 9YjbRTuPDmKPhAucMUDE | Milestone | 0 | 1.2.6 | 1.2.6 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
40 | 7015 | U0mup1noPd6mH1CxWGtr | Milestone | 0 | 1.2.5 | 1.2.5 |  | 2027-01-01 08:05 | p | 840 |  | 2029-04-20 09:27
41 | 7016 | pVOP21cemlwRUbhUeRME | Milestone | 0 | 1.2.4 | 1.2.4 |  | 2027-01-07 16:58 | p | 529 |  | 2028-06-20 14:26
42 | 150 | 7cu6yvdJV8ndF0CYMHk8 | Milestone | 0 | 1.1 | 1.1 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
43 | 436 | OGXVzK31PKUn8DxCdn94 | Normal | 33 | 1.3.3.2.10 | 1.3.3.2.10 |  | 2025-03-27 08:00 | p | 11 |  | 2025-04-07 16:46
44 | 428 | pxWL5EoMWeaDmapfAV7m | Normal | 2 | 1.3.3.4.2 | 1.3.3.4.2 |  | 2025-09-17 08:00 | p | 15 |  | 2025-10-02 14:07
45 | 3859 | xrpLG6wlwOL4sRwHPU5B | Normal | 28 | 1.3.2.1.2.2.2 | 1.3.2.1.2.2.2 |  | 2025-03-17 08:00 | p | 21 |  | 2025-04-07 08:26
46 | 3861 | rvfyADOJtzNcPT3VL85f | Normal | 100 | 1.3.2.1.2.2.3 | 1.3.2.1.2.2.3 |  | 2025-05-13 08:00 | p | 14 |  | 2025-05-27 08:33
47 | 3862 | FUtleP4nAJHYxzLOWKZH | Normal | 20 | 1.3.2.1.2.2.4 | 1.3.2.1.2.2.4 |  | 2025-10-06 08:00 | p | 44 |  | 2025-11-19 09:25
48 | 3864 | kkmwKYrSq6DehQmbGkxo | Summary | 90 | 1.3.2.1.2.3.2 | 1.3.2.1.2.3.2 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
49 | 3865 | ZK3GDclfde20Vh8DU71K | Normal | 30 | 1.3.2.1.2.3.2.1 | 1.3.2.1.2.3.2.1 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
50 | 3866 | 8Zrc7ItBhrTjO1TWxqmf | Normal | 20 | 1.3.2.1.2.3.2.2 | 1.3.2.1.2.3.2.2 |  | 2025-09-05 08:00 | p | 19 |  | 2025-09-24 11:48
51 | 3867 | l8TRHVr9p6bfQBwzbTty | Normal | 5 | 1.3.2.1.2.3.2.5 | 1.3.2.1.2.3.2.5 |  | 2025-11-03 08:00 | p | 14 |  | 2025-11-17 16:33
52 | 3868 | NCkZSbtMfUxIg95lxXXn | Normal | 10 | 1.3.2.1.2.3.2.6 | 1.3.2.1.2.3.2.6 |  | 2025-11-10 08:00 | p | 15 |  | 2025-11-25 09:06
53 | 3869 | wbVbYxDNomEEsv0XDKnQ | Normal | 5 | 1.3.2.1.2.3.2.7 | 1.3.2.1.2.3.2.7 |  | 2025-11-25 08:00 | p | 13 |  | 2025-12-08 14:21
54 | 6562 | Z3AfJmLBpOLyJb1GhvwC | Normal | 10 | 1.3.2.1.2.3.2.3 | 1.3.2.1.2.3.2.3 |  | 2025-10-03 08:00 | p | 14 |  | 2025-10-17 08:06
55 | 6563 | 7FPcbor42GN7O6Ym4IZM | Normal | 10 | 1.3.2.1.2.3.2.4 | 1.3.2.1.2.3.2.4 |  | 2025-10-20 08:00 | p | 10 |  | 2025-10-30 14:23
56 | 7192 | rcBSOCAYFUxP7jsyoqGw | Normal | 11 | 1.3.2.3.2.1.1.2 | 1.3.2.3.2.1.1.2 |  | 2025-02-24 08:00 | q | -21 |  | 2025-02-03 08:00
57 | 7194 | mB0uoGZ1D1fuFzk350Kb | Normal | 30 | 1.3.2.3.2.1.2.1 | 1.3.2.3.2.1.2.1 |  | 2025-03-11 08:00 | q | -24 |  | 2025-02-14 10:33
58 | 7200 | 7Va2LPPEsZrLZmgpV2qc | Summary | 19 | 1.3.2.3.2.1.4 | 1.3.2.3.2.1.4 |  | 2025-04-22 08:00 | q | -14 |  | 2025-04-07 15:15
59 | 7201 | UKbpgMkpfrIPVoEOJEeO | Normal | 10 | 1.3.2.3.2.1.4.1 | 1.3.2.3.2.1.4.1 |  | 2025-04-22 08:00 | q | -14 |  | 2025-04-07 15:15
60 | 7202 | vy1jnuopIHJe5PhTsUNw | Normal | 5 | 1.3.2.3.2.1.4.2 | 1.3.2.3.2.1.4.2 |  | 2025-05-06 08:00 | q | -14 |  | 2025-04-21 10:40
61 | 7203 | KqVHIBvrHNAu5GlarotD | Normal | 3 | 1.3.2.3.2.1.4.3 | 1.3.2.3.2.1.4.3 |  | 2025-05-13 08:00 | q | -14 |  | 2025-04-28 14:19
62 | 7204 | BUAmcwglNtP3GEkJsPLR | Normal | 1 | 1.3.2.3.2.1.4.4 | 1.3.2.3.2.1.4.4 |  | 2025-05-16 08:00 | q | -14 |  | 2025-05-01 15:00
63 | 7207 | 51ZGrscW6XrNzeOMbLyw | Normal | 5 | 1.3.2.3.2.2.2 | 1.3.2.3.2.2.2 |  | 2025-03-18 08:00 | p | 27 |  | 2025-04-14 15:15
64 | 7208 | 5Vu53Z23NG8K3uSzUcYA | Normal | 3 | 1.3.2.3.2.2.3 | 1.3.2.3.2.2.3 |  | 2025-03-25 08:00 | p | 24 |  | 2025-04-18 11:26
65 | 7209 | r8OmtZddpdGbVxNEynIO | Normal | 1 | 1.3.2.3.2.2.4 | 1.3.2.3.2.2.4 |  | 2025-03-28 08:00 | p | 26 |  | 2025-04-23 15:28
66 | 7213 | GkAhONTSL0EMIVzc5bXh | Normal | 3 | 1.3.2.3.2.3.3 | 1.3.2.3.2.3.3 |  | 2025-02-25 08:00 | q | -3 |  | 2025-02-21 09:11
67 | 7214 | ysGFXohNyFRFQ06jmkjW | Normal | 1 | 1.3.2.3.2.3.4 | 1.3.2.3.2.3.4 |  | 2025-02-28 08:00 | q | -1 |  | 2025-02-26 09:58
68 | 7221 | PYoR7OoHLcblZDJJ1hTC | Normal | 20 | 1.3.2.3.2.4.6 | 1.3.2.3.2.4.6 |  | 2025-02-28 08:00 | p | 3 |  | 2025-03-03 15:22
69 | 7222 | W1KVKgORO9KqmU1uQFqG | Normal | 1 | 1.3.2.3.2.4.7 | 1.3.2.3.2.4.7 |  | 2025-03-28 08:00 | p | 11 |  | 2025-04-08 09:39
70 | 7228 | SSqxRWtJ8NkhLwkx3Zp5 | Normal | 15 | 1.3.2.3.2.5.5 | 1.3.2.3.2.5.5 |  | 2025-03-18 08:00 | p | 35 |  | 2025-04-22 16:25
71 | 7231 | Kz2H44CrN943Xn6RI0Et | Summary | 19 | 1.3.2.3.3 | 1.3.2.3.3 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
72 | 7232 | cCMYeGs7uzTIiiDhvAui | Summary | 12 | 1.3.2.3.3.1 | 1.3.2.3.3.1 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
73 | 7233 | rgerXXfH5cOVWHlSbXtk | Normal | 2 | 1.3.2.3.3.1.1 | 1.3.2.3.3.1.1 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
74 | 7234 | 4Nk8AWONEAABjENRSl4s | Normal | 3 | 1.3.2.3.3.1.2 | 1.3.2.3.3.1.2 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
75 | 7235 | uR7e5eYUOS8ur8CkZgir | Normal | 2 | 1.3.2.3.3.1.3 | 1.3.2.3.3.1.3 |  | 2025-07-29 08:00 | p | 15 |  | 2025-08-13 16:17
76 | 7236 | OqdHv6QLhEyFdmarh5Mg | Normal | 5 | 1.3.2.3.3.1.4 | 1.3.2.3.3.1.4 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
77 | 7237 | xLl9f1S8pVLgozw4LZw4 | Normal | 10 | 1.3.2.3.3.1.5 | 1.3.2.3.3.1.5 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
78 | 7238 | hj0QAuvemNr4BSx0wqCM | Normal | 10 | 1.3.2.3.3.1.6 | 1.3.2.3.3.1.6 |  | 2025-07-24 08:00 | p | 15 |  | 2025-08-08 14:24
79 | 7239 | sGRMuNmZsu5Ap3rRR6Ja | Normal | 2 | 1.3.2.3.3.1.7 | 1.3.2.3.3.1.7 |  | 2025-08-07 08:00 | p | 15 |  | 2025-08-22 13:46
80 | 7240 | jJgg05qz3M4QbDAQ4nmn | Summary | 7 | 1.3.2.3.3.2 | 1.3.2.3.3.2 |  | 2025-08-11 08:00 | p | 15 |  | 2025-08-26 10:04
81 | 7241 | RP09WyAKLetAyeWXIWbd | Normal | 1 | 1.3.2.3.3.2.1 | 1.3.2.3.3.2.1 |  | 2025-08-11 08:00 | p | 15 |  | 2025-08-26 10:04
82 | 7242 | PNiOufePi0cnwKsaAHa8 | Normal | 3 | 1.3.2.3.3.2.2 | 1.3.2.3.3.2.2 |  | 2025-08-12 08:00 | p | 15 |  | 2025-08-27 11:29
83 | 7243 | nppwsC1hz1MTRepHit5q | Normal | 3 | 1.3.2.3.3.2.3 | 1.3.2.3.3.2.3 |  | 2025-08-15 08:00 | p | 18 |  | 2025-09-02 09:31
84 | 7244 | FpvbIzqyAjmrguHRtjoA | Summary | 68 | 1.3.2.3.4 | 1.3.2.3.4 |  | 2025-08-20 08:00 | p | 16 |  | 2025-09-05 14:36
85 | 7245 | ysJ2Wz17vAaH50NFOd3r | Normal | 2 | 1.3.2.3.4.1 | 1.3.2.3.4.1 |  | 2025-08-20 08:00 | p | 16 |  | 2025-09-05 14:36
86 | 7246 | w8OYvCOBO1azAOar59yv | Normal | 3 | 1.3.2.3.4.2 | 1.3.2.3.4.2 |  | 2025-08-20 08:00 | p | 16 |  | 2025-09-05 14:36
87 | 7247 | QmLDbLdk9YgltF6FQxKi | Normal | 2 | 1.3.2.3.4.3 | 1.3.2.3.4.3 |  | 2025-08-25 08:00 | p | 16 |  | 2025-09-10 10:05
88 | 7248 | nqyBToLUXvLl91VDFcK9 | Summary | 20 | 1.3.2.3.4.4 | 1.3.2.3.4.4 |  | 2025-08-20 08:00 | p | 16 |  | 2025-09-05 14:36
89 | 7249 | T3rEQsXy5TFYVzdnmRkQ | Normal | 20 | 1.3.2.3.4.4.1 | 1.3.2.3.4.4.1 |  | 2025-08-20 08:00 | p | 16 |  | 2025-09-05 14:36
90 | 7250 | G5mdz8DmOa8TGNlmxmOk | Normal | 20 | 1.3.2.3.4.4.2 | 1.3.2.3.4.4.2 |  | 2025-08-20 08:00 | p | 16 |  | 2025-09-05 14:36
91 | 7251 | p2IEwFFq1YxDgQwaqReT | Summary | 48 | 1.3.2.3.4.5 | 1.3.2.3.4.5 |  | 2025-09-18 08:00 | p | 19 |  | 2025-10-07 14:40
92 | 7252 | R4hlQqYwslHcXudIUORM | Normal | 20 | 1.3.2.3.4.5.1 | 1.3.2.3.4.5.1 |  | 2025-09-18 08:00 | p | 19 |  | 2025-10-07 14:40
93 | 7253 | 5Q6OCjUddDwnqpg2shNG | Normal | 5 | 1.3.2.3.4.5.2 | 1.3.2.3.4.5.2 |  | 2025-10-17 08:00 | p | 24 |  | 2025-11-10 09:00
94 | 7254 | aZsc8OQGYCtOtLNUDl4p | Normal | 7 | 1.3.2.3.4.5.3 | 1.3.2.3.4.5.3 |  | 2025-10-24 08:00 | p | 25 |  | 2025-11-18 09:39
95 | 7255 | GiGIxdlKVFOGW1rlVkpg | Normal | 5 | 1.3.2.3.4.5.4 | 1.3.2.3.4.5.4 |  | 2025-11-04 08:00 | p | 22 |  | 2025-11-26 15:22
96 | 7256 | ZTFxKau19KKCcFlUDIYg | Normal | 7 | 1.3.2.3.4.5.5 | 1.3.2.3.4.5.5 |  | 2025-11-12 08:00 | p | 22 |  | 2025-12-04 15:27
97 | 7257 | EmkT3sq6aGy3vx96JSsX | Normal | 3 | 1.3.2.3.4.5.6 | 1.3.2.3.4.5.6 |  | 2025-11-21 08:00 | p | 25 |  | 2025-12-16 08:47
98 | 7258 | PBxke5bv0Yk6xXbQcvVe | Normal | 1 | 1.3.2.3.4.5.7 | 1.3.2.3.4.5.7 |  | 2025-11-26 08:00 | p | 22 |  | 2025-12-18 10:41
99 | 633 | FgJ5XjjThZN85XQOJ0nJ | Normal | 21 | 1.5.6.6.2.10 | 1.5.6.6.2.10 |  | 2025-06-18 08:00 | p | 33 |  | 2025-07-21 15:45
100 | 634 | o4DRQRcsScdVmCSXNbxF | Normal | 10 | 1.5.6.6.2.9 | 1.5.6.6.2.9 |  | 2025-07-21 08:00 | p | 28 |  | 2025-08-18 13:19
101 | 635 | ztvy5zkS4z9HirKgvHGY | Normal | 20 | 1.5.6.6.2.11 | 1.5.6.6.2.11 |  | 2025-08-01 13:00 | p | 32 |  | 2025-09-02 15:12
102 | 636 | ZpIfqMwIaczq2BqznW2q | Normal | 6 | 1.5.6.6.2.12 | 1.5.6.6.2.12 |  | 2025-08-29 13:00 | p | 27 |  | 2025-09-26 11:01
103 | 637 | 3VAZwvp2NS6usl0wrvOM | Normal | 7 | 1.5.6.6.2.13 | 1.5.6.6.2.13 |  | 2025-09-09 13:00 | p | 28 |  | 2025-10-08 09:26
104 | 638 | 34zoFClD9RS7gLTCPZs0 | Normal | 5 | 1.5.6.6.2.14 | 1.5.6.6.2.14 |  | 2025-09-18 13:00 | p | 31 |  | 2025-10-20 11:33
105 | 640 | 10AmMHkCz4b8n0xqbyCt | Normal | 5 | 1.5.6.6.2.16 | 1.5.6.6.2.16 |  | 2025-09-25 13:00 | p | 31 |  | 2025-10-27 11:29
106 | 641 | KUqcSNVxncHPLVJNV5ca | Normal | 2 | 1.5.6.6.2.17 | 1.5.6.6.2.17 |  | 2025-10-02 13:00 | p | 29 |  | 2025-10-31 16:23
107 | 642 | chCwawHUqn0ea2ArCnKB | Normal | 0 | 1.5.6.6.2.18 | 1.5.6.6.2.18 |  | 2025-10-06 08:00 | p | 29 |  | 2025-11-04 08:38
108 | 643 | xZBRzE3QVYmQCjnzxLQv | Normal | 4 | 1.5.6.6.2.19 | 1.5.6.6.2.19 |  | 2025-10-06 13:00 | p | 29 |  | 2025-11-04 13:00
109 | 644 | tUTeQ74YpmkuuOiouSXU | Normal | 5 | 1.5.6.6.2.20 | 1.5.6.6.2.20 |  | 2025-10-10 13:00 | p | 31 |  | 2025-11-10 15:13
110 | 645 | mSrjcTZmK12EdJmOEYFi | Normal | 1 | 1.5.6.6.2.21 | 1.5.6.6.2.21 |  | 2025-10-20 13:00 | p | 28 |  | 2025-11-18 10:28
111 | 646 | Haue3rYYySw3jbXWnBeq | Normal | 3 | 1.5.6.6.3 | 1.5.6.6.3 |  | 2025-10-21 13:00 | p | 28 |  | 2025-11-19 09:32
112 | 647 | 6jlP0Y4QQ5KPQWxvolLg | Normal | 1 | 1.5.6.6.4 | 1.5.6.6.4 |  | 2025-10-24 13:00 | p | 31 |  | 2025-11-24 16:06
113 | 656 | lzPFAx9Fh8cDxyQ3uxFX | Normal | 1 | 1.5.6.6.5.3 | 1.5.6.6.5.3 |  | 2025-10-27 13:00 | p | 29 |  | 2025-11-25 16:19
114 | 657 | nePaKBbqDo6OltylvukE | Summary | 14 | 1.5.6.6.5.4 | 1.5.6.6.5.4 |  | 2025-10-28 15:00 | p | 30 |  | 2025-11-28 09:44
115 | 658 | PyBKEPMZMe2YeOC66yut | Normal | 11 | 1.5.6.6.5.4.1 | 1.5.6.6.5.4.1 |  | 2025-10-28 15:00 | p | 30 |  | 2025-11-28 09:44
116 | 664 | H1KB0K8mM12Opvc4oDP1 | Normal | 3 | 1.5.6.6.5.4.2 | 1.5.6.6.5.4.2 |  | 2025-11-13 15:00 | p | 28 |  | 2025-12-12 13:16
117 | 665 | FIEbexlYHnOcZkEBs7WM | Normal | 5 | 1.5.6.6.5.5 | 1.5.6.6.5.5 |  | 2025-11-19 15:00 | p | 29 |  | 2025-12-18 16:45
118 | 666 | OcAHNnZWZgiwxfUiheGU | Normal | 5 | 1.5.6.6.5.6 | 1.5.6.6.5.6 |  | 2025-11-26 15:00 | p | 30 |  | 2025-12-26 15:53
119 | 667 | HPj21Hyun1nWvxJOQMhf | Normal | 28 | 1.5.6.6.5.7 | 1.5.6.6.5.7 |  | 2025-12-04 15:00 | p | 28 |  | 2026-01-02 14:34
120 | 671 | ZM52W2kHJJCM7052Da3J | Normal | 2 | 1.5.6.5.2 | 1.5.6.5.2 |  | 2025-10-24 13:00 | p | 31 |  | 2025-11-24 16:06
121 | 672 | AcRvLPQ7WrNfvcLBOWzV | Normal | 1 | 1.5.6.5.3 | 1.5.6.5.3 |  | 2025-11-18 15:00 | p | 28 |  | 2025-12-17 14:16
122 | 1459 | MxsNofofvf6CR0hsGInx | Normal | 1 | 1.5.5.1.4 | 1.5.5.1.4 |  | 2025-03-06 08:00 | p | 0 |  | 2025-03-06 09:25
123 | 1469 | MZooHRTMNCHrNy0nPaCQ | Normal | 1 | 1.5.5.1.6 | 1.5.5.1.6 |  | 2025-02-18 08:00 | p | 27 |  | 2025-03-17 15:37
124 | 1470 | PdTqfNwd2IKBXe26tWkB | Normal | 1 | 1.5.5.1.8 | 1.5.5.1.8 |  | 2025-03-07 08:00 | p | 24 |  | 2025-03-31 15:24
125 | 1471 | FsiT4ZMTOq9hGqZQQdYf | Normal | 11 | 1.5.5.1.9 | 1.5.5.1.9 |  | 2025-03-10 08:00 | p | 23 |  | 2025-04-02 10:21
126 | 1472 | KG0YDAdikr58WjA79FVb | Normal | 9 | 1.5.5.1.10 | 1.5.5.1.10 |  | 2025-03-25 08:00 | p | 27 |  | 2025-04-21 16:39
127 | 4584 | H2uIo7s6dGmX6mrjT7jd | Normal | 9 | 1.5.5.1.7 | 1.5.5.1.7 |  | 2025-02-19 08:00 | p | 27 |  | 2025-03-18 16:39
128 | 3945 | bJfaWXH8yBacWp0eqnXx | Normal | 1 | 1.5.4.3 | 1.5.4.3 |  | 2025-04-02 08:00 | p | 30 |  | 2025-05-02 11:55
129 | 3952 | HkhDGF3pWO8GORFQnyh9 | Normal | 5 | 1.5.4.5.1.2 | 1.5.4.5.1.2 |  | 2025-03-24 08:00 | p | 36 |  | 2025-04-29 09:11
130 | 3953 | dYr7YcYkpYYUeESNUSkl | Normal | 2 | 1.5.4.5.1.3 | 1.5.4.5.1.3 |  | 2025-03-31 08:00 | p | 36 |  | 2025-05-06 10:35
131 | 3954 | r37KEs6OIDoMKT5Yz5nA | Normal | 1 | 1.5.4.5.1.4 | 1.5.4.5.1.4 |  | 2025-04-02 08:00 | p | 36 |  | 2025-05-08 11:53
132 | 6606 | pKonEcYtBOhP3mqLQIUx | Normal | 5 | 1.5.4.4.8 | 1.5.4.4.8 |  | 2025-02-19 08:00 | p | 29 |  | 2025-03-20 10:14
133 | 4215 | I07WrBLpDQufO3mvIdSu | Normal | 1 | 1.5.1.1.4 | 1.5.1.1.4 |  | 2025-06-17 08:00 | p | 31 |  | 2025-07-18 16:22
134 | 6445 | Wo6GLLiu9tXQyZ8t43hX | Normal | 43 | 1.5.1.1.3 | 1.5.1.1.3 |  | 2025-04-16 08:00 | p | 19 |  | 2025-05-05 08:35
135 | 6081 | VjHQD510O4fPJGbP9Knq | Normal | 1 | 1.5.1.2 | 1.5.1.2 |  | 2026-01-14 15:00 | p | 34 |  | 2026-02-17 15:29
136 | 6681 | NHiN8b86HRxpkLb9JGGD | Normal | 10 | 1.5.1.3.9 | 1.5.1.3.9 |  | 2025-04-04 08:00 | p | 32 |  | 2025-05-06 13:11
137 | 6682 | 695WEwNqpcHeAbXSBRci | Normal | 2 | 1.5.1.3.10 | 1.5.1.3.10 |  | 2025-05-23 08:00 | q | 0 |  | 2025-05-22 09:52
138 | 6684 | TL3Mtv3QlGNejnoXktH7 | Normal | 1 | 1.5.1.3.8 | 1.5.1.3.8 |  | 2025-04-03 08:00 | p | 32 |  | 2025-05-05 10:33
139 | 5612 | JBIAfh9fImNsEXfXoHCz | Summary | 5 | 1.5.2.2.10 | 1.5.2.2.10 |  | 2025-03-03 17:00 | q | 0 |  | 2025-03-03 08:55
140 | 5613 | cc9QdsdOkkgaQ8ateKZX | Normal | 1 | 1.5.2.2.10.1 | 1.5.2.2.10.1 |  | 2025-03-03 17:00 | q | 0 |  | 2025-03-03 08:55
141 | 5614 | COTl0owSvMhEdF9iuXCz | Normal | 0 | 1.5.2.2.10.2 | 1.5.2.2.10.2 |  | 2025-03-05 09:36 | q | 0 |  | 2025-03-04 10:46
142 | 5615 | 0lLRNnxfg3utwoPLwt26 | Normal | 2 | 1.5.2.2.10.3 | 1.5.2.2.10.3 |  | 2025-03-05 14:36 | q | 0 |  | 2025-03-04 16:11
143 | 5616 | 5Z54Ad8GhuwKLjQHaz2Y | Normal | 1 | 1.5.2.2.10.4 | 1.5.2.2.10.4 |  | 2025-03-07 14:36 | q | 0 |  | 2025-03-06 16:11
144 | 5617 | fALGtnsfw381gf0W53Ia | Normal | 0 | 1.5.2.2.10.5 | 1.5.2.2.10.5 |  | 2025-03-10 14:36 | q | -2 |  | 2025-03-07 16:45
145 | 5629 | ghMhRqrbgVxCQv51dU2T | Normal | 0 | 1.5.2.2.8.2 | 1.5.2.2.8.2 |  | 2025-02-20 13:00 | q | 0 |  | 2025-02-20 11:50
146 | 5630 | eU3bwvC6wgraOvc5hiLt | Milestone | 0 | 1.5.2.2.8.3 | 1.5.2.2.8.3 |  | 2025-02-20 17:00 | p | 0 |  | 2025-02-21 08:01
147 | 5631 | gvTQVNdftDRXYXclyMFo | Normal | 3 | 1.5.2.2.8.4 | 1.5.2.2.8.4 |  | 2025-02-21 08:00 | p | 0 |  | 2025-02-21 08:01
148 | 5632 | DfRDIp64TG1m6LE7SSYQ | Milestone | 0 | 1.5.2.2.8.5 | 1.5.2.2.8.5 |  | 2025-02-25 17:00 | q | 0 |  | 2025-02-25 15:53
149 | 5633 | 2UPBwQymcCOUpuUjnBTe | Normal | 3 | 1.5.2.2.8.6 | 1.5.2.2.8.6 |  | 2025-02-26 08:00 | q | 0 |  | 2025-02-25 15:53
150 | 5634 | gm5pLWvICR0pU7aShOGD | Normal | 1 | 1.5.2.2.8.7 | 1.5.2.2.8.7 |  | 2025-03-03 08:00 | q | -2 |  | 2025-02-28 08:37
151 | 5639 | ymvGdGMdlU958QTwMU9V | Normal | 0 | 1.5.2.2.9.4 | 1.5.2.2.9.4 |  | 2025-01-27 08:00 | p | 1 |  | 2025-01-28 10:34
152 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | 2025-01-27 13:00 | p | 1 |  | 2025-01-28 15:01
153 | 5641 | QjWOhv4eRSTZWx0ATAUl | Normal | 23 | 1.5.2.2.11 | 1.5.2.2.11 |  | 2025-03-11 08:00 | q | 0 |  | 2025-03-10 10:07
154 | 5447 | ijJ4zfbEfOInLYX7Vu9Z | Normal | 6 | 1.5.3.1.2.2 | 1.5.3.1.2.2 |  | 2025-02-26 08:00 | p | 29 |  | 2025-03-27 11:44
155 | 5448 | cS9oDqhLQ00Df4o4XStO | Normal | 6 | 1.5.3.1.2.3 | 1.5.3.1.2.3 |  | 2025-03-06 08:00 | p | 28 |  | 2025-04-03 13:50
156 | 5449 | 6It4K5O7iZJhLoLO2jyi | Normal | 6 | 1.5.3.1.2.4 | 1.5.3.1.2.4 |  | 2025-03-14 08:00 | p | 28 |  | 2025-04-11 09:26
157 | 5450 | maMtUzorvxHWuMFIlXlq | Normal | 5 | 1.5.3.1.3 | 1.5.3.1.3 |  | 2025-03-24 08:00 | p | 25 |  | 2025-04-18 10:47
158 | 7381 | Ao7wteklS85dOuCCMM3I | Normal | 124 | 1.5.1 | 1.5.1 |  | 2025-08-01 13:00 | p | 32 |  | 2025-09-02 15:12
159 | 576 | m8O5CFAYfVbtxxZI5qQW | Normal | 15 | 1.4.3.1.2 | 1.4.3.1.2 |  | 2025-11-13 08:00 | q | -37 |  | 2025-10-06 15:42
160 | 5854 | 2kqOvhRPajU4Q0ZPsUnx | Normal | 8 | 1.4.3.1.4 | 1.4.3.1.4 |  | 2026-03-03 15:00 | p | 30 |  | 2026-04-03 13:41
161 | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Normal | 49 | 1.4.3.1.5 | 1.4.3.1.5 |  | 2026-07-30 16:58 | q | 0 |  | 2026-07-30 10:58
162 | 6607 | IhYDHpDNbof6PVOjQ9lw | Normal | 4 | 1.4.3.1.3 | 1.4.3.1.3 |  | 2026-02-18 15:00 | p | 33 |  | 2026-03-24 09:15
163 | 3901 | Jj1toL1YzUk95oK7OfgU | Normal | 4 | 1.4.1.1.2.4 | 1.4.1.1.2.4 |  | 2025-03-03 08:00 | p | 23 |  | 2025-03-26 16:16
164 | 6566 | gAyE6SkFHV1MNEAJitQ7 | Normal | 1 | 1.4.1.2.1.6 | 1.4.1.2.1.6 |  | 2025-05-01 08:00 | q | -21 |  | 2025-04-09 11:48
165 | 3907 | pFYLZycbgH4KMn6pLhBU | Summary | 272 | 1.4.1.3 | 1.4.1.3 |  | 2025-06-27 08:00 | q | -77 |  | 2025-04-10 11:58
166 | 3908 | y9tKov3jCEzWGyA9B1wJ | Normal | 5 | 1.4.1.3.1 | 1.4.1.3.1 |  | 2025-06-27 08:00 | q | -77 |  | 2025-04-10 11:58
167 | 3909 | VvjZ0oHXTTG06m5XlL1B | Normal | 10 | 1.4.1.3.2 | 1.4.1.3.2 |  | 2025-07-07 08:00 | q | -80 |  | 2025-04-17 14:24
168 | 3910 | pNRX5rV0uvvHnR27z1AO | Normal | 8 | 1.4.1.3.3 | 1.4.1.3.3 |  | 2026-03-03 15:00 | p | 30 |  | 2026-04-03 13:41
169 | 3911 | R3AK39H17lCC16PE9DkR | Normal | 10 | 1.4.1.3.4 | 1.4.1.3.4 |  | 2026-03-13 15:00 | p | 32 |  | 2026-04-14 16:59
170 | 3912 | BSEXS69UjCPQ6j2zF47p | Normal | 15 | 1.4.1.3.5 | 1.4.1.3.5 |  | 2026-03-27 15:00 | p | 28 |  | 2026-04-24 15:54
171 | 3913 | nUmJBAacPI2xORV8OCED | Normal | 20 | 1.4.1.3.6 | 1.4.1.3.6 |  | 2026-04-17 15:00 | p | 26 |  | 2026-05-14 09:13
172 | 3914 | e7efPn2W4IFyilt2hNai | Normal | 30 | 1.4.1.3.7 | 1.4.1.3.7 |  | 2026-05-15 15:00 | p | 32 |  | 2026-06-16 16:59
173 | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Normal | 5 | 1.4.1.3.8 | 1.4.1.3.8 |  | 2026-06-30 15:00 | p | 23 |  | 2026-07-24 08:09
174 | 3916 | xcLTkuiw0V5a2mOSGmcP | Normal | 10 | 1.4.1.3.9 | 1.4.1.3.9 |  | 2026-07-08 15:00 | p | 25 |  | 2026-08-03 08:38
175 | 3917 | hmttcJptV92JIo4OpANW | Normal | 5 | 1.4.1.3.10 | 1.4.1.3.10 |  | 2026-07-22 15:00 | p | 22 |  | 2026-08-14 14:20
176 | 3918 | VKkEEklTkhlAtqntT93x | Summary | 160 | 1.4.1.4 | 1.4.1.4 |  | 2026-05-15 15:00 | p | 32 |  | 2026-06-16 16:59
177 | 3919 | 70MdVf3krr3KZdDhEaoj | Normal | 1 | 1.4.1.4.1 | 1.4.1.4.1 |  | 2026-05-15 15:00 | p | 32 |  | 2026-06-16 16:59
178 | 3920 | mBVNyTIN7rvKyNQxzyxZ | Normal | 9 | 1.4.1.4.2 | 1.4.1.4.2 |  | 2026-05-18 15:00 | p | 30 |  | 2026-06-18 09:43
179 | 3921 | jEuseC90wYhkn0V4svXs | Normal | 3 | 1.4.1.4.3 | 1.4.1.4.3 |  | 2026-07-30 16:58 | q | 0 |  | 2026-07-30 10:58
180 | 3922 | yD55zWPn8USsNa4i8nCC | Normal | 5 | 1.4.1.4.4 | 1.4.1.4.4 |  | 2026-10-08 16:58 | p | 12 |  | 2026-10-21 15:39
181 | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Normal | 15 | 1.4.1.4.5 | 1.4.1.4.5 |  | 2026-10-16 16:58 | p | 13 |  | 2026-10-30 14:41
182 | 3924 | N1CigBiMQE2J41ZAMkt0 | Normal | 20 | 1.4.1.4.6 | 1.4.1.4.6 |  | 2026-11-06 16:58 | p | 26 |  | 2026-12-03 15:30
183 | 3925 | hSr4t1vn7GiB6Kp7YK0M | Normal | 5 | 1.4.1.4.7 | 1.4.1.4.7 |  | 2026-12-08 16:58 | p | 28 |  | 2027-01-06 15:40
184 | 3926 | vGJMK6sejFbKR6Gom2up | Normal | 5 | 1.4.1.4.8 | 1.4.1.4.8 |  | 2026-12-15 16:58 | p | 27 |  | 2027-01-12 15:02
185 | 3927 | 3RLmiC17tI4E2ggNuRe0 | Normal | 5 | 1.4.1.4.9 | 1.4.1.4.9 |  | 2026-12-22 16:58 | p | 29 |  | 2027-01-21 14:26
186 | 3928 | hCBFci3gUopMkWW2dQQj | Normal | 5 | 1.4.1.4.10 | 1.4.1.4.10 |  | 2026-12-30 16:58 | p | 29 |  | 2027-01-29 15:28
187 | 5213 | 6YmlQVHNVjUNryBHQf8a | Summary | 61 | 1.4.2.2.3 | 1.4.2.2.3 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
188 | 5214 | KnSim1DOJ7A0BYyW8QOP | Milestone | 0 | 1.4.2.2.3.1 | 1.4.2.2.3.1 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
189 | 5215 | KawuX1icbWQB8WlKVKy9 | Normal | 60 | 1.4.2.2.3.2 | 1.4.2.2.3.2 |  | 2025-08-13 08:00 | q | -26 |  | 2025-07-17 16:02
190 | 5216 | xOecB4tLtQXauOnWGD4l | Normal | 1 | 1.4.2.2.3.3 | 1.4.2.2.3.3 |  | 2025-11-07 08:00 | q | -34 |  | 2025-10-03 16:30
191 | 5217 | e116DivbRDCkLiH2zNhl | Summary | 61 | 1.4.2.2.4 | 1.4.2.2.4 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
192 | 5218 | 8GMyARBjPLtiSR4txAaa | Milestone | 0 | 1.4.2.2.4.1 | 1.4.2.2.4.1 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
193 | 5219 | Uz3hspiJXkYJElXZ00I5 | Normal | 60 | 1.4.2.2.4.2 | 1.4.2.2.4.2 |  | 2025-08-13 08:00 | q | -26 |  | 2025-07-17 16:02
194 | 5220 | QAqXx5k5ldQJaugZyYbR | Normal | 1 | 1.4.2.2.4.3 | 1.4.2.2.4.3 |  | 2025-11-07 08:00 | q | -21 |  | 2025-10-16 09:10
195 | 5221 | iTaWceiQKMF6gUaF3DCB | Summary | 61 | 1.4.2.2.5 | 1.4.2.2.5 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
196 | 5222 | 4u5ocGGr0fcTRpzuglXZ | Milestone | 0 | 1.4.2.2.5.1 | 1.4.2.2.5.1 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
197 | 5223 | 3nEJb4lsc7akFmF6ULw7 | Normal | 60 | 1.4.2.2.5.2 | 1.4.2.2.5.2 |  | 2025-08-13 08:00 | q | -26 |  | 2025-07-17 16:02
198 | 5224 | PvORb6t1pqf23aOFbh3S | Normal | 1 | 1.4.2.2.5.3 | 1.4.2.2.5.3 |  | 2025-11-07 08:00 | q | -28 |  | 2025-10-09 15:42
199 | 5225 | b44Ij1WE7Qrra8bO7ZTN | Normal | 1 | 1.4.2.2.6 | 1.4.2.2.6 |  | 2026-07-20 16:58 | q | 0 |  | 2026-07-20 11:30
200 | 5277 | TgmqG1sR4A60sNmMtPcE | Summary | 193 | 1.4.2.2.7 | 1.4.2.2.7 |  | 2025-10-07 16:09 | q | -32 |  | 2025-09-04 16:24
201 | 5278 | OmCdw3tKtVsW24V2aNqQ | Normal | 8 | 1.4.2.2.7.1 | 1.4.2.2.7.1 |  | 2025-10-07 16:09 | q | -32 |  | 2025-09-04 16:24
202 | 5279 | htHZ3VhuaadgfKg1VQls | Summary | 47 | 1.4.2.2.7.11 | 1.4.2.2.7.11 |  | 2026-04-21 08:01 | q | -31 |  | 2026-03-20 13:20
203 | 5280 | q0a2rl5NSMPQe2o4IYAd | Normal | 3 | 1.4.2.2.7.11.1 | 1.4.2.2.7.11.1 |  | 2026-05-12 15:05 | q | -35 |  | 2026-04-07 14:50
204 | 5281 | 3GO4XZOZrW4CEje40UJT | Normal | 5 | 1.4.2.2.7.11.2 | 1.4.2.2.7.11.2 |  | 2026-04-21 08:01 | q | -21 |  | 2026-03-30 09:44
205 | 5282 | qBzS7vPbhPVzs7sVXgmM | Normal | 5 | 1.4.2.2.7.11.3 | 1.4.2.2.7.11.3 |  | 2026-04-28 08:01 | q | -21 |  | 2026-04-06 10:47
206 | 5283 | fU0pzeQGz2MN3lZmznFh | Normal | 5 | 1.4.2.2.7.11.4 | 1.4.2.2.7.11.4 |  | 2026-05-05 08:01 | q | -45 |  | 2026-03-20 13:20
207 | 5284 | epM0xPGW4QTSpblHVWYc | Normal | 10 | 1.4.2.2.7.11.5 | 1.4.2.2.7.11.5 |  | 2026-05-28 08:58 | q | -28 |  | 2026-04-29 11:35
208 | 5285 | ffNcVsnPBySsZbQiEShc | Normal | 10 | 1.4.2.2.7.11.6 | 1.4.2.2.7.11.6 |  | 2026-06-11 08:58 | q | -19 |  | 2026-05-22 15:08
209 | 5286 | Yb8sH9U5B9gBzfVjcJKN | Normal | 6 | 1.4.2.2.7.12 | 1.4.2.2.7.12 |  | 2026-06-25 08:58 | q | -16 |  | 2026-06-09 08:48
210 | 5287 | bhDhrVJ9ZVKMNyReuPKm | Normal | 5 | 1.4.2.2.7.13 | 1.4.2.2.7.13 |  | 2026-07-02 16:58 | q | -16 |  | 2026-06-16 16:30
211 | 5288 | RIVzpLwElpoiAIgfwKiL | Milestone | 0 | 1.4.2.2.7.14 | 1.4.2.2.7.14 |  | 2026-07-09 16:58 | q | -16 |  | 2026-06-23 15:58
212 | 6457 | PFYaNHtSBj97Eh5ysTvH | Normal | 7 | 1.4.2.2.7.2 | 1.4.2.2.7.2 |  | 2026-01-19 08:01 | q | -33 |  | 2025-12-16 08:32
213 | 6458 | pDFztlVdvvSj2i4Cz5Z9 | Normal | 5 | 1.4.2.2.7.3 | 1.4.2.2.7.3 |  | 2026-01-28 08:01 | q | -35 |  | 2025-12-23 11:39
214 | 6459 | ylmwXTiOnCLJpwlHTaRg | Normal | 10 | 1.4.2.2.7.4 | 1.4.2.2.7.4 |  | 2026-02-04 08:01 | q | -34 |  | 2025-12-31 11:37
215 | 6460 | CystLMJtc4xxgICiEMDQ | Normal | 8 | 1.4.2.2.7.5 | 1.4.2.2.7.5 |  | 2026-02-18 08:01 | q | -32 |  | 2026-01-16 09:43
216 | 6461 | 7ypQo0ZyAHzCHmFRlywg | Normal | 10 | 1.4.2.2.7.6 | 1.4.2.2.7.6 |  | 2026-03-02 08:01 | q | -32 |  | 2026-01-28 08:58
217 | 6462 | BWDOi71UCejcEb1fgeoY | Normal | 7 | 1.4.2.2.7.7 | 1.4.2.2.7.7 |  | 2026-03-16 08:01 | q | -30 |  | 2026-02-13 08:15
218 | 6463 | OelD6citgJccZhV0UyvH | Normal | 7 | 1.4.2.2.7.8 | 1.4.2.2.7.8 |  | 2026-03-25 08:01 | q | -29 |  | 2026-02-23 15:14
219 | 6464 | McSTYqZ3LCfaYSSmZoTn | Normal | 7 | 1.4.2.2.7.9 | 1.4.2.2.7.9 |  | 2026-04-03 08:01 | q | -28 |  | 2026-03-05 08:27
220 | 6465 | WAyiiuxKOgY7bZWYUV9d | Normal | 5 | 1.4.2.2.7.10 | 1.4.2.2.7.10 |  | 2026-04-14 08:01 | q | -31 |  | 2026-03-13 10:58
221 | 5240 | NSmZbDTp76mGzDSQ7Ceh | Summary | 56 | 1.4.2.1.3 | 1.4.2.1.3 |  | 2025-05-23 08:00 | q | -235 |  | 2024-09-30 08:00
222 | 5241 | v6EKIZLcnDHW8CXOrD7y | Normal | 21 | 1.4.2.1.3.1 | 1.4.2.1.3.1 |  | 2025-05-23 08:00 | q | -235 |  | 2024-09-30 08:00
223 | 5242 | JYCfpao49G3jD8M94S66 | Normal | 10 | 1.4.2.1.3.2 | 1.4.2.1.3.2 |  | 2025-06-24 08:00 | q | -188 |  | 2024-12-18 08:00
224 | 5243 | 0XN39P602kPVdw6rXYZi | Normal | 10 | 1.4.2.1.3.3 | 1.4.2.1.3.3 |  | 2025-07-09 08:00 | q | -56 |  | 2025-05-13 10:18
225 | 5244 | Nwqnc6xsOuQ8oMDbKNfv | Normal | 15 | 1.4.2.1.3.4 | 1.4.2.1.3.4 |  | 2025-07-23 08:00 | q | -27 |  | 2025-06-25 08:52
226 | 5265 | ATYnDTN93dB3aTXfzslo | Normal | 6 | 1.4.2.1.6.2 | 1.4.2.1.6.2 |  | 2025-03-25 14:00 | p | 28 |  | 2025-04-22 14:42
227 | 5266 | G5H4IlBy3M3Zxs38gcIH | Normal | 10 | 1.4.2.1.6.3 | 1.4.2.1.6.3 |  | 2025-04-15 11:00 | p | 27 |  | 2025-05-13 10:18
228 | 5267 | 3RI5G3ymKjaLn96cfboa | Normal | 11 | 1.4.2.1.6.4 | 1.4.2.1.6.4 |  | 2025-04-15 11:00 | p | 27 |  | 2025-05-13 10:18
229 | 5268 | fG9nayiE82fFlNFtuyfN | Normal | 8 | 1.4.2.1.6.5 | 1.4.2.1.6.5 |  | 2025-06-03 08:00 | q | 0 |  | 2025-06-02 15:18
230 | 5269 | UP8sWsDXCDMiwOqWz3ib | Normal | 5 | 1.4.2.1.6.6 | 1.4.2.1.6.6 |  | 2025-05-13 14:00 | p | 20 |  | 2025-06-02 15:18
231 | 5270 | 0UA65kBzwzHULCayr1Gq | Normal | 8 | 1.4.2.1.6.7 | 1.4.2.1.6.7 |  | 2025-07-25 09:00 | q | -38 |  | 2025-06-16 11:06
232 | 5271 | mtztJWmm2OBnfmSsuoGt | Normal | 10 | 1.4.2.1.6.8 | 1.4.2.1.6.8 |  | 2025-08-08 08:30 | q | -38 |  | 2025-06-30 09:21
233 | 5272 | kvS9pO69DNwaLvofAQcb | Normal | 11 | 1.4.2.1.6.9 | 1.4.2.1.6.9 |  | 2025-08-22 08:30 | q | -36 |  | 2025-07-16 08:39
234 | 5273 | fGHKYfAaAseAkWqOpGpv | Normal | 10 | 1.4.2.1.6.10 | 1.4.2.1.6.10 |  | 2025-09-09 08:30 | q | -33 |  | 2025-08-06 13:53
235 | 5274 | zjsmmZ1Zvuz0mxAk4wzH | Normal | 10 | 1.4.2.1.6.11 | 1.4.2.1.6.11 |  | 2025-09-23 08:30 | q | -33 |  | 2025-08-20 11:00
236 | 5275 | lBTJLZ8EG6vqarjSz7m6 | Milestone | 0 | 1.4.2.1.6.12 | 1.4.2.1.6.12 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
237 | 5264 | 2BYRPY9ftrCpjg2j3vxJ | Milestone | 0 | 1.4.2.1.8 | 1.4.2.1.8 |  | 2025-02-21 08:00 | q | -328 |  | 2024-03-29 17:00
238 | 5276 | yja2Gk0YbNXya3vsxrwh | Milestone | 0 | 1.4.2.1.7 | 1.4.2.1.7 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
239 | 5289 | tqKGxL2oceRufkd47wnf | Summary | 319 | 1.4.2.3 | 1.4.2.3 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
240 | 5290 | NEvSl0zKCrGJ6lqshTZO | Milestone | 0 | 1.4.2.3.1 | 1.4.2.3.1 |  | 2025-11-07 17:00 | q | -28 |  | 2025-10-10 15:45
241 | 5313 | 3y8KKUl940HiJi7UFKFT | Summary | 106 | 1.4.2.3.3 | 1.4.2.3.3 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
242 | 5314 | SRtjKDi8lC5PBWdNdIAU | Normal | 10 | 1.4.2.3.3.1 | 1.4.2.3.3.1 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
243 | 5316 | LCfcLPfxTjnSY0dCrjlE | Normal | 10 | 1.4.2.3.3.2 | 1.4.2.3.3.2 |  | 2026-08-19 16:59 | q | 0 |  | 2026-08-19 15:33
244 | 5317 | pw6YyMXR7oeqsrtIHdqo | Normal | 9 | 1.4.2.3.3.3 | 1.4.2.3.3.3 |  | 2026-09-16 11:59 | p | 0 |  | 2026-09-16 13:30
245 | 5318 | KMG5hXAC4X2MZPfyVOSc | Normal | 5 | 1.4.2.3.3.8 | 1.4.2.3.3.8 |  | 2026-11-06 10:08 | p | 0 |  | 2026-11-06 15:15
246 | 5319 | mDGXCmTQB2ITo8MYwlYq | Normal | 5 | 1.4.2.3.3.9 | 1.4.2.3.3.9 |  | 2026-11-13 10:08 | p | 3 |  | 2026-11-16 11:36
247 | 5320 | hu6UActfLD0rLfdNqC55 | Normal | 5 | 1.4.2.3.3.10 | 1.4.2.3.3.10 |  | 2026-11-20 10:08 | p | 3 |  | 2026-11-24 08:25
248 | 5321 | pG9QTaeiPcJe7Bm3iI1s | Normal | 5 | 1.4.2.3.3.11 | 1.4.2.3.3.11 |  | 2026-11-27 10:08 | p | 3 |  | 2026-12-01 08:22
249 | 5322 | oNpYocgOFdrRcJiQE0H5 | Normal | 5 | 1.4.2.3.3.12 | 1.4.2.3.3.12 |  | 2026-12-04 10:08 | p | 4 |  | 2026-12-08 11:18
250 | 5323 | Tt5dEbDabBigq84Eat5c | Normal | 5 | 1.4.2.3.3.13 | 1.4.2.3.3.13 |  | 2026-12-11 10:08 | p | 4 |  | 2026-12-16 08:59
251 | 5324 | INz2wzhVzgQCZLXqwTZc | Normal | 5 | 1.4.2.3.3.14 | 1.4.2.3.3.14 |  | 2026-12-18 13:39 | p | 5 |  | 2026-12-23 13:51
252 | 5325 | D5c4JntP5EU4thbOE4hi | Normal | 1 | 1.4.2.3.3.15 | 1.4.2.3.3.15 |  | 2026-12-31 08:05 | p | 5 |  | 2027-01-05 08:10
253 | 6467 | n3qEWBmgcrCNzbacKk03 | Normal | 5 | 1.4.2.3.3.4 | 1.4.2.3.3.4 |  | 2026-10-09 10:08 | p | 0 |  | 2026-10-09 11:37
254 | 6468 | BqsEZH5IWCI59bWKml0D | Normal | 5 | 1.4.2.3.3.5 | 1.4.2.3.3.5 |  | 2026-10-16 10:08 | p | 0 |  | 2026-10-16 11:31
255 | 6469 | TtC6fzAb8zClFAVfKkP8 | Normal | 5 | 1.4.2.3.3.6 | 1.4.2.3.3.6 |  | 2026-10-23 10:08 | p | 0 |  | 2026-10-23 15:39
256 | 6470 | UrgnPc0HjVwpN7twGsWX | Normal | 5 | 1.4.2.3.3.7 | 1.4.2.3.3.7 |  | 2026-10-30 10:08 | p | 0 |  | 2026-10-30 15:11
257 | 5326 | esDa5lJIA5zg0nP58cRd | Summary | 32 | 1.4.2.3.4 | 1.4.2.3.4 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
258 | 5327 | iRZmxts3rKQ38tplQw52 | Normal | 30 | 1.4.2.3.4.1 | 1.4.2.3.4.1 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
259 | 5328 | ngeJL3ilFttQtHxnOEwX | Normal | 1 | 1.4.2.3.4.2 | 1.4.2.3.4.2 |  | 2025-11-20 08:30 | q | -36 |  | 2025-10-14 11:56
260 | 5329 | GYUaK0PI1fV4kag2egD8 | Normal | 1 | 1.4.2.3.4.3 | 1.4.2.3.4.3 |  | 2025-11-21 08:30 | q | -36 |  | 2025-10-15 13:36
261 | 6321 | KAyzIHlSkkFZqIIdJ9JD | Summary | 144 | 1.4.2.3.2 | 1.4.2.3.2 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
262 | 5298 | c4SSanbHhynqs8RkqT3I | Normal | 3 | 1.4.2.3.2.2 | 1.4.2.3.2.2 |  | 2026-01-29 15:00 | p | 33 |  | 2026-03-03 15:34
263 | 5299 | HB5wL9z8KlZFeAas0WUQ | Normal | 11 | 1.4.2.3.2.3 | 1.4.2.3.2.3 |  | 2026-02-03 15:00 | p | 33 |  | 2026-03-09 14:34
264 | 5301 | hHw9byxBfgMW8zXuSsdj | Milestone | 0 | 1.4.2.3.2.12 | 1.4.2.3.2.12 |  | 2026-04-02 15:00 | p | 33 |  | 2026-05-05 15:37
265 | 5302 | 2rc67Y2hzAhRvE7YihWA | Normal | 10 | 1.4.2.3.2.1 | 1.4.2.3.2.1 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
266 | 5303 | SgeIRg4ykwxbNqD9urWV | Normal | 2 | 1.4.2.3.2.8 | 1.4.2.3.2.8 |  | 2026-03-20 15:00 | p | 32 |  | 2026-04-22 11:45
267 | 5304 | KRXQrBZsFBKS9k4FvAsp | Normal | 3 | 1.4.2.3.2.9 | 1.4.2.3.2.9 |  | 2026-03-24 15:00 | p | 30 |  | 2026-04-24 14:59
268 | 5305 | TyGQYH0bANBrFjXmh15D | Normal | 2 | 1.4.2.3.2.10 | 1.4.2.3.2.10 |  | 2026-03-27 15:00 | p | 33 |  | 2026-04-29 15:04
269 | 5306 | yar7ts7ASIpTQqyvnwQd | Normal | 5 | 1.4.2.3.2.13 | 1.4.2.3.2.13 |  | 2026-04-02 15:00 | p | 33 |  | 2026-05-05 15:37
270 | 5307 | yRByGMPgEQcCecr5HzAA | Normal | 2 | 1.4.2.3.2.15 | 1.4.2.3.2.15 |  | 2026-04-10 15:00 | p | 34 |  | 2026-05-15 09:22
271 | 5308 | JBAsTSNPb9OQmIAmtadV | Normal | 20 | 1.4.2.3.2.17 | 1.4.2.3.2.17 |  | 2026-04-21 08:01 | p | 34 |  | 2026-05-25 16:19
272 | 5309 | xRRT514kq8kwyv7njrs5 | Normal | 5 | 1.4.2.3.2.19 | 1.4.2.3.2.19 |  | 2026-07-09 16:58 | q | 0 |  | 2026-07-09 10:39
273 | 5310 | RMnJ5j2lLGlokfxLAfSa | Normal | 2 | 1.4.2.3.2.20 | 1.4.2.3.2.20 |  | 2026-07-16 16:58 | q | 0 |  | 2026-07-16 10:39
274 | 5311 | BowxNbb4uXSnAk8z8ZkC | Normal | 2 | 1.4.2.3.2.22 | 1.4.2.3.2.22 |  | 2026-07-20 16:58 | q | 0 |  | 2026-07-20 14:13
275 | 5312 | mmXMEY1kphvE51vXPbq6 | Milestone | 0 | 1.4.2.3.2.25 | 1.4.2.3.2.25 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
276 | 6516 | qmbk7ROGAo4AwJOySAlG | Normal | 4 | 1.4.2.3.2.4 | 1.4.2.3.2.4 |  | 2026-02-18 15:00 | p | 33 |  | 2026-03-24 09:15
277 | 6517 | YGaikKlMVGc6fqtUBZ7h | Normal | 5 | 1.4.2.3.2.5 | 1.4.2.3.2.5 |  | 2026-02-24 15:00 | p | 31 |  | 2026-03-27 16:17
278 | 6518 | 0rDsNLFYCabTnyCcopAQ | Normal | 8 | 1.4.2.3.2.6 | 1.4.2.3.2.6 |  | 2026-03-03 15:00 | p | 30 |  | 2026-04-03 13:41
279 | 6519 | UldK3RoYRJH5Hsfv02Lh | Normal | 2 | 1.4.2.3.2.7 | 1.4.2.3.2.7 |  | 2026-03-13 15:00 | p | 32 |  | 2026-04-15 13:51
280 | 6520 | UaqqB30tdDFCsCHRRpeh | Normal | 2 | 1.4.2.3.2.11 | 1.4.2.3.2.11 |  | 2026-03-31 15:00 | p | 31 |  | 2026-05-01 16:04
281 | 6521 | LDY9CVOjImzsQ4NE65Qz | Normal | 1 | 1.4.2.3.2.16 | 1.4.2.3.2.16 |  | 2026-04-14 15:00 | p | 38 |  | 2026-05-22 15:08
282 | 6522 | WYJvDx3FrKALT2lj4FIo | Normal | 2 | 1.4.2.3.2.18 | 1.4.2.3.2.18 |  | 2026-05-19 08:01 | p | 49 |  | 2026-07-07 09:10
283 | 6523 | TvM5XBX3OaVljTSOZ4e2 | Normal | 2 | 1.4.2.3.2.21 | 1.4.2.3.2.21 |  | 2026-07-16 16:58 | q | 0 |  | 2026-07-16 10:39
284 | 6524 | cvaJgvK8KpGYV8ykH12h | Normal | 2 | 1.4.2.3.2.23 | 1.4.2.3.2.23 |  | 2026-07-22 16:58 | q | 0 |  | 2026-07-22 14:13
285 | 6525 | GtEwLNkefPtnncnl90X4 | Normal | 3 | 1.4.2.3.2.24 | 1.4.2.3.2.24 |  | 2026-07-30 16:58 | q | 0 |  | 2026-07-30 10:58
286 | 6873 | gSZIbC6fsU6IM6McOJy8 | Normal | 1 | 1.4.2.3.2.14 | 1.4.2.3.2.14 |  | 2026-04-09 15:00 | p | 34 |  | 2026-05-14 08:39
287 | 678 | N57z7OkXN935WcKbC4jO | Normal | 1 | 1.6.7.2 | 1.6.7.2 |  | 2026-03-26 08:00 | p | 75 |  | 2026-06-09 09:07
288 | 751 | AADJzuTGAb4gWytj7CQi | Normal | 18 | 1.6.7.9.3.8 | 1.6.7.9.3.8 |  | 2025-08-07 08:00 | p | 14 |  | 2025-08-21 13:22
289 | 752 | r0c0rFS4EkOGynasmiCG | Normal | 36 | 1.6.7.9.3.7 | 1.6.7.9.3.7 |  | 2025-07-08 08:00 | p | 21 |  | 2025-07-29 09:13
290 | 759 | cZuo3MY7iyDrOJC1qVJx | Normal | 5 | 1.6.7.9.3.9 | 1.6.7.9.3.9 |  | 2025-09-03 08:00 | p | 13 |  | 2025-09-16 11:56
291 | 765 | qOEfFivvitnF8cw9csOP | Normal | 1 | 1.6.7.9.3.13 | 1.6.7.9.3.13 |  | 2026-03-26 08:00 | p | 75 |  | 2026-06-09 09:07
292 | 5773 | OCcI80TDGF8LlIXj66uV | Normal | 3 | 1.6.7.9.3.14 | 1.6.7.9.3.14 |  | 2026-03-27 08:00 | p | 75 |  | 2026-06-10 09:42
293 | 746 | qMC0J8brk1dsdpzlKrk7 | Normal | 12 | 1.6.7.9.3.5.3 | 1.6.7.9.3.5.3 |  | 2025-04-01 08:00 | q | -4 |  | 2025-03-27 10:10
294 | 6324 | gthK0FxwJBk3laTELp8O | Summary | 45 | 1.6.7.9.3.6 | 1.6.7.9.3.6 |  | 2025-05-01 08:00 | p | 15 |  | 2025-05-16 13:13
295 | 747 | nul8vpOEtI2Q6W5Q0Qo9 | Normal | 12 | 1.6.7.9.3.6.1 | 1.6.7.9.3.6.1 |  | 2025-05-01 08:00 | p | 15 |  | 2025-05-16 13:13
296 | 748 | M1HHh2K01o23jS8vpDxS | Normal | 11 | 1.6.7.9.3.6.2 | 1.6.7.9.3.6.2 |  | 2025-05-19 08:00 | p | 16 |  | 2025-06-04 15:23
297 | 749 | Q6UXOpf9Kvzek7IGY0vp | Normal | 11 | 1.6.7.9.3.6.3 | 1.6.7.9.3.6.3 |  | 2025-06-04 08:00 | p | 16 |  | 2025-06-20 14:07
298 | 750 | lsyrPytnmjLTpXFywa7Z | Normal | 11 | 1.6.7.9.3.6.4 | 1.6.7.9.3.6.4 |  | 2025-06-20 08:00 | p | 13 |  | 2025-07-03 16:35
299 | 6325 | SeCXD5wMvkrEekc1PKVb | Summary | 48 | 1.6.7.9.3.10 | 1.6.7.9.3.10 |  | 2025-09-10 08:00 | p | 12 |  | 2025-09-22 16:40
300 | 753 | 8158sxzbHZvZEVAAqewP | Normal | 47 | 1.6.7.9.3.10.1 | 1.6.7.9.3.10.1 |  | 2025-09-10 08:00 | p | 12 |  | 2025-09-22 16:40
301 | 754 | hfPeDXfQSV7Nx9zb2rD7 | Normal | 8 | 1.6.7.9.3.10.2 | 1.6.7.9.3.10.2 |  | 2025-09-10 08:00 | p | 99 |  | 2025-12-18 08:10
302 | 755 | DQUdswbbJv1Qpkj0EGFX | Normal | 8 | 1.6.7.9.3.10.3 | 1.6.7.9.3.10.3 |  | 2025-09-22 08:00 | p | 98 |  | 2025-12-29 11:51
303 | 756 | ae3T3d3nFoXZXK7gqkAr | Normal | 20 | 1.6.7.9.3.10.4 | 1.6.7.9.3.10.4 |  | 2025-10-02 08:00 | p | 99 |  | 2026-01-09 10:16
304 | 757 | wbc1AZ0GUhXzQk6SoWIe | Normal | 6 | 1.6.7.9.3.10.6 | 1.6.7.9.3.10.6 |  | 2025-10-31 08:00 | p | 101 |  | 2026-02-09 11:31
305 | 758 | FbN1rrQYTlsz1haWZnFy | Normal | 6 | 1.6.7.9.3.10.8 | 1.6.7.9.3.10.8 |  | 2025-11-10 08:00 | p | 100 |  | 2026-02-18 15:32
306 | 5780 | XCMvjmTKbAUuCZwuNlSF | Normal | 6 | 1.6.7.9.3.10.5 | 1.6.7.9.3.10.5 |  | 2025-10-02 08:00 | p | 99 |  | 2026-01-09 10:16
307 | 5782 | EYY3j1SjnoLUV06T0QHs | Normal | 5 | 1.6.7.9.3.10.7 | 1.6.7.9.3.10.7 |  | 2025-10-31 08:00 | p | 101 |  | 2026-02-09 11:31
308 | 6326 | F4s3MnfyyA74WCIympSi | Summary | 75 | 1.6.7.9.3.11 | 1.6.7.9.3.11 |  | 2025-09-10 08:00 | p | 12 |  | 2025-09-22 16:40
309 | 760 | 7IpOsslq7gyebnCTulxX | Normal | 66 | 1.6.7.9.3.11.1 | 1.6.7.9.3.11.1 |  | 2025-09-10 08:00 | p | 12 |  | 2025-09-22 16:40
310 | 761 | x6fNhJzs4uMW9trtiNEW | Normal | 1 | 1.6.7.9.3.11.2 | 1.6.7.9.3.11.2 |  | 2025-12-16 08:00 | p | 72 |  | 2026-02-26 13:37
311 | 762 | nRInnITHYgcDsU5KDg6m | Normal | 8 | 1.6.7.9.3.11.3 | 1.6.7.9.3.11.3 |  | 2025-12-17 08:00 | p | 72 |  | 2026-02-27 13:36
312 | 6327 | dOJS0LaWQU970ssSiqsz | Summary | 59 | 1.6.7.9.3.12 | 1.6.7.9.3.12 |  | 2025-12-30 08:00 | p | 69 |  | 2026-03-09 16:30
313 | 763 | hLK2cdXSS7IhOZR53PgI | Normal | 6 | 1.6.7.9.3.12.1 | 1.6.7.9.3.12.1 |  | 2025-12-30 08:00 | p | 69 |  | 2026-03-09 16:30
314 | 764 | wTf98lLeHiXAkWj17mAH | Normal | 53 | 1.6.7.9.3.12.2 | 1.6.7.9.3.12.2 |  | 2026-01-08 08:00 | p | 68 |  | 2026-03-17 09:11
315 | 786 | 5RJIBxVgSA4dodMzOCsx | Normal | 1 | 1.6.7.8.5 | 1.6.7.8.5 |  | 2025-05-13 08:00 | p | 24 |  | 2025-06-06 08:25
316 | 5785 | xIbBdattr1YLWDiqGWPC | Summary | 126 | 1.6.7.11 | 1.6.7.11 |  | 2026-04-01 08:00 | p | 84 |  | 2026-06-24 13:57
317 | 5774 | Dvlkt7hdSzdJ7ChIr4xD | Normal | 2 | 1.6.7.11.1 | 1.6.7.11.1 |  | 2026-04-01 08:00 | p | 84 |  | 2026-06-24 13:57
318 | 5775 | D3NIdGcGrWNhiaQ0dYbY | Normal | 2 | 1.6.7.11.3 | 1.6.7.11.3 |  | 2026-09-28 08:00 | p | 102 |  | 2027-01-08 08:25
319 | 6435 | Ql00ScpYzqtI9PQP57zu | Normal | 122 | 1.6.7.11.2 | 1.6.7.11.2 |  | 2026-04-03 08:00 | p | 84 |  | 2026-06-26 11:47
320 | 1465 | i7zbkIpCuBMJlMsq6ma0 | Normal | 1 | 1.6.6.1.5 | 1.6.6.1.5 |  | 2025-03-31 08:00 | p | 10 |  | 2025-04-10 08:56
321 | 1476 | gbuDNYIgLq2nB3WERl4p | Normal | 30 | 1.6.6.1.7 | 1.6.6.1.7 |  | 2025-02-19 08:00 | p | 0 |  | 2025-02-19 14:02
322 | 1477 | BC1NYB3fqAlfckX7ECXI | Normal | 1 | 1.6.6.1.8 | 1.6.6.1.8 |  | 2025-04-02 08:00 | p | 9 |  | 2025-04-11 13:03
323 | 1478 | UR7xa7LgN3sMlpzxRjvW | Normal | 3 | 1.6.6.1.9 | 1.6.6.1.9 |  | 2025-12-16 08:00 | p | 13 |  | 2025-12-29 08:26
324 | 3932 | RKLg9Drqo40Q82TFH1VL | Normal | 1 | 1.6.4.15.2 | 1.6.4.15.2 |  | 2025-03-28 08:00 | p | 21 |  | 2025-04-18 16:49
325 | 3934 | 10Oh1H5M5HjeoWxU1u0w | Normal | 1 | 1.6.4.15.4 | 1.6.4.15.4 |  | 2025-03-28 08:00 | p | 38 |  | 2025-05-05 11:02
326 | 3936 | hwXDQy0MWIQ4jzjNT4oM | Normal | 1 | 1.6.4.15.3 | 1.6.4.15.3 |  | 2025-03-28 08:00 | p | 26 |  | 2025-04-23 14:13
327 | 3940 | 8UqvtHTIMRT16eupajKq | Normal | 1 | 1.6.4.15.5 | 1.6.4.15.5 |  | 2025-03-28 08:00 | p | 41 |  | 2025-05-08 08:55
328 | 3992 | cy141kwlo0X5isTqv3ku | Summary | 25 | 1.6.4.17.4 | 1.6.4.17.4 |  | 2025-04-24 08:00 | p | 34 |  | 2025-05-28 09:23
329 | 3993 | LBRozXrRhpq69SKlxnDb | Normal | 10 | 1.6.4.17.4.1 | 1.6.4.17.4.1 |  | 2025-04-24 08:00 | p | 34 |  | 2025-05-28 09:23
330 | 3994 | DvOjAQ6C9aXKnpaAVD1H | Normal | 5 | 1.6.4.17.4.2 | 1.6.4.17.4.2 |  | 2025-05-08 08:00 | p | 36 |  | 2025-06-13 15:55
331 | 3995 | AUkl27NW1i9i5huez8Rg | Normal | 5 | 1.6.4.17.4.3 | 1.6.4.17.4.3 |  | 2025-05-15 08:00 | p | 40 |  | 2025-06-24 13:47
332 | 3996 | Bw8X4DjnSuQgBiA6BEKp | Normal | 5 | 1.6.4.17.4.4 | 1.6.4.17.4.4 |  | 2025-05-22 08:00 | p | 40 |  | 2025-07-01 13:18
333 | 3997 | KJPP8ivswwWTIeIfPXEM | Summary | 25 | 1.6.4.17.3 | 1.6.4.17.3 |  | 2025-03-20 08:00 | p | 32 |  | 2025-04-21 16:12
334 | 3998 | 5UhDwyM7phAycUkk1Nye | Normal | 10 | 1.6.4.17.3.1 | 1.6.4.17.3.1 |  | 2025-03-20 08:00 | p | 32 |  | 2025-04-21 16:12
335 | 3999 | v6kjlf8aEDhSJHzOK2Uo | Normal | 5 | 1.6.4.17.3.2 | 1.6.4.17.3.2 |  | 2025-04-03 08:00 | p | 33 |  | 2025-05-06 13:19
336 | 4000 | Y3aJp60cYMHromf8xgAE | Normal | 5 | 1.6.4.17.3.3 | 1.6.4.17.3.3 |  | 2025-04-10 08:00 | p | 33 |  | 2025-05-13 13:44
337 | 4001 | Cjtbc2cmKWchyZlcOxo3 | Normal | 5 | 1.6.4.17.3.4 | 1.6.4.17.3.4 |  | 2025-04-17 08:00 | p | 32 |  | 2025-05-19 16:26
338 | 4004 | fF1Y54WMybWnXZsBJgYM | Normal | 1 | 1.6.4.17.2.2 | 1.6.4.17.2.2 |  | 2025-03-10 08:00 | p | 28 |  | 2025-04-07 16:11
339 | 4005 | NxZ8rMz5ZnJaz6z1SXKM | Normal | 3 | 1.6.4.17.2.3 | 1.6.4.17.2.3 |  | 2025-03-11 08:00 | p | 29 |  | 2025-04-09 08:26
340 | 4006 | fOTuJvqH3OcilXcZuEM5 | Normal | 4 | 1.6.4.17.2.4 | 1.6.4.17.2.4 |  | 2025-03-14 08:00 | p | 31 |  | 2025-04-14 15:27
341 | 6168 | BHtkkzlMW8757DY2qb23 | Summary | 143 | 1.6.4.19.3 | 1.6.4.19.3 |  | 2025-05-02 08:00 | q | -253 |  | 2024-08-22 08:00
342 | 6169 | gdW3U4pURjb9iKkAVexH | Summary | 60 | 1.6.4.19.3.1 | 1.6.4.19.3.1 |  | 2025-05-02 08:00 | q | -253 |  | 2024-08-22 08:00
343 | 6170 | AwYLgXY6Mo1DqCbUEhPQ | Summary | 30 | 1.6.4.19.3.1.1 | 1.6.4.19.3.1.1 |  | 2025-05-02 08:00 | q | -253 |  | 2024-08-22 08:00
344 | 6171 | ZR4zae2ZYhCMcZhj7T05 | Normal | 15 | 1.6.4.19.3.1.1.1 | 1.6.4.19.3.1.1.1 |  | 2025-05-02 08:00 | q | -253 |  | 2024-08-22 08:00
345 | 6172 | QgFskomqU31VYtYzB2O0 | Normal | 15 | 1.6.4.19.3.1.1.2 | 1.6.4.19.3.1.1.2 |  | 2025-05-23 08:00 | q | -251 |  | 2024-09-13 08:51
346 | 6173 | nRc7GqDGMG4VP1O5IlEd | Normal | 15 | 1.6.4.19.3.1.2 | 1.6.4.19.3.1.2 |  | 2025-06-16 08:00 | q | -250 |  | 2024-10-08 13:09
347 | 6174 | dvLkHNDhuFTU7AO5XWky | Normal | 15 | 1.6.4.19.3.1.3 | 1.6.4.19.3.1.3 |  | 2025-07-09 08:00 | q | -252 |  | 2024-10-29 13:56
348 | 6175 | IEttja5qNJ6P760Cd9De | Summary | 40 | 1.6.4.19.3.2 | 1.6.4.19.3.2 |  | 2025-07-30 08:00 | q | -250 |  | 2024-11-21 11:58
349 | 6176 | B6x3R7fnpOwupecmo90D | Normal | 10 | 1.6.4.19.3.2.1 | 1.6.4.19.3.2.1 |  | 2025-07-30 08:00 | q | -250 |  | 2024-11-21 11:58
350 | 6177 | vkZhJMfsZWiMPLTjgcam | Normal | 10 | 1.6.4.19.3.2.2 | 1.6.4.19.3.2.2 |  | 2025-08-13 08:00 | q | -245 |  | 2024-12-10 13:52
351 | 6178 | XEU5rnQh2VnDpMl1eT0o | Normal | 10 | 1.6.4.19.3.2.3 | 1.6.4.19.3.2.3 |  | 2025-08-27 08:00 | q | -245 |  | 2024-12-24 10:02
352 | 6179 | xksMzlhYjvKZ4p1XJwSB | Normal | 10 | 1.6.4.19.3.2.4 | 1.6.4.19.3.2.4 |  | 2025-09-11 08:00 | q | -244 |  | 2025-01-09 11:14
353 | 6180 | oR7r0RquVFe2h8pCK9HY | Normal | 10 | 1.6.4.19.3.3 | 1.6.4.19.3.3 |  | 2025-09-25 08:00 | q | -240 |  | 2025-01-27 13:26
354 | 6181 | UJ3hrxCJ5NslZjdDLEyu | Normal | 20 | 1.6.4.19.3.4 | 1.6.4.19.3.4 |  | 2025-10-09 08:00 | q | -240 |  | 2025-02-10 14:35
355 | 6182 | JQHbjwkPqIslt5thIOgQ | Normal | 5 | 1.6.4.19.3.5 | 1.6.4.19.3.5 |  | 2025-11-07 08:00 | q | -240 |  | 2025-03-11 14:19
356 | 6183 | 5NqxhAyIl3JXTpWWvSnV | Normal | 2 | 1.6.4.19.3.6 | 1.6.4.19.3.6 |  | 2025-11-17 08:00 | q | -244 |  | 2025-03-17 15:31
357 | 6184 | vx8CoW16lw8uEEVKaVp7 | Normal | 5 | 1.6.4.19.3.7 | 1.6.4.19.3.7 |  | 2025-11-19 08:00 | q | -244 |  | 2025-03-19 11:26
358 | 6185 | A91LND4pEy61zvjvAsaQ | Normal | 1 | 1.6.4.19.3.8 | 1.6.4.19.3.8 |  | 2025-11-26 08:00 | q | -244 |  | 2025-03-26 10:08
359 | 4040 | g5zNgGHP8U11wPTJKhcB | Normal | 20 | 1.6.4.20.1.3 | 1.6.4.20.1.3 |  | 2025-05-23 08:00 | q | -251 |  | 2024-09-13 10:10
360 | 4041 | f0PORH3GhEIXFjYfGbTd | Normal | 97 | 1.6.4.20.1.6 | 1.6.4.20.1.6 |  | 2025-05-23 08:00 | q | -251 |  | 2024-09-13 10:10
361 | 4042 | SyfMayqY4a7i0nZLPz6Y | Normal | 129 | 1.6.4.20.1.7 | 1.6.4.20.1.7 |  | 2025-09-15 08:00 | p | 99 |  | 2025-12-23 14:42
362 | 6621 | pXe0ZxltUhDf1quSL5q2 | Normal | 15 | 1.6.4.20.1.2 | 1.6.4.20.1.2 |  | 2025-05-02 08:00 | q | -253 |  | 2024-08-22 08:00
363 | 6622 | EmEy5gJckBYofEEYNXFv | Normal | 20 | 1.6.4.20.1.4 | 1.6.4.20.1.4 |  | 2026-02-26 08:00 | p | 69 |  | 2026-05-06 14:45
364 | 6623 | BVU87KMg9Rhzc6j5yKVh | Normal | 20 | 1.6.4.20.1.5 | 1.6.4.20.1.5 |  | 2026-03-26 08:00 | p | 75 |  | 2026-06-09 09:07
365 | 4043 | XbXkjxtfHUxhg4CK1elt | Summary | 127 | 1.6.4.20.2 | 1.6.4.20.2 |  | 2026-04-23 08:00 | p | 76 |  | 2026-07-08 11:24
366 | 4045 | mDphgqAAxA2RnvA52x8A | Normal | 20 | 1.6.4.20.2.1 | 1.6.4.20.2.1 |  | 2026-04-23 08:00 | p | 76 |  | 2026-07-08 11:24
367 | 4046 | 5HyQBVwuqRdeW1HhaSOP | Normal | 10 | 1.6.4.20.2.2 | 1.6.4.20.2.2 |  | 2026-05-21 08:00 | p | 82 |  | 2026-08-11 16:05
368 | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Normal | 72 | 1.6.4.20.2.3 | 1.6.4.20.2.3 |  | 2026-06-05 08:00 | p | 83 |  | 2026-08-27 10:41
369 | 4048 | ybbKhm9jdtNbVzABGZ8L | Normal | 20 | 1.6.4.20.2.4 | 1.6.4.20.2.4 |  | 2026-09-18 08:00 | p | 96 |  | 2026-12-23 10:38
370 | 4049 | kP1jeiEwkYg4HRpUjG4p | Normal | 5 | 1.6.4.20.2.5 | 1.6.4.20.2.5 |  | 2026-10-19 08:00 | p | 102 |  | 2027-01-29 09:24
371 | 4050 | jQIHIDf5FTnJxQysEvnn | Summary | 37 | 1.6.4.20.3 | 1.6.4.20.3 |  | 2026-09-18 08:00 | p | 96 |  | 2026-12-23 10:38
372 | 4051 | bizigDTezGi1mMHxJ1gi | Summary | 32 | 1.6.4.20.3.1 | 1.6.4.20.3.1 |  | 2026-09-18 08:00 | p | 96 |  | 2026-12-23 10:38
373 | 4052 | JSSXcLTdD9VQNM766DgK | Normal | 20 | 1.6.4.20.3.1.1 | 1.6.4.20.3.1.1 |  | 2026-09-18 08:00 | p | 96 |  | 2026-12-23 10:38
374 | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Normal | 12 | 1.6.4.20.3.1.2 | 1.6.4.20.3.1.2 |  | 2026-10-19 08:00 | p | 95 |  | 2027-01-22 15:39
375 | 4054 | WhXMUGkGRid5sulqMW8S | Summary | 5 | 1.6.4.20.3.2 | 1.6.4.20.3.2 |  | 2026-11-04 08:00 | p | 97 |  | 2027-02-09 08:06
376 | 4055 | dWrJCmOwv1i72p29KBXE | Normal | 2 | 1.6.4.20.3.2.1 | 1.6.4.20.3.2.1 |  | 2026-11-04 08:00 | p | 97 |  | 2027-02-09 08:06
377 | 4056 | a1SRK7UWhIIMlkKKriy9 | Normal | 1 | 1.6.4.20.3.2.2 | 1.6.4.20.3.2.2 |  | 2026-11-06 08:00 | p | 96 |  | 2027-02-10 16:11
378 | 4057 | NKnvgqAHKv63TOKudyZQ | Normal | 1 | 1.6.4.20.3.2.3 | 1.6.4.20.3.2.3 |  | 2026-11-09 08:00 | p | 94 |  | 2027-02-11 16:13
379 | 4058 | cbANjhwCBqAluf1RM04K | Normal | 1 | 1.6.4.20.3.2.4 | 1.6.4.20.3.2.4 |  | 2026-11-10 08:00 | p | 94 |  | 2027-02-12 15:25
380 | 4059 | sH9kz6O2EFda2hu4x8Kx | Summary | 12 | 1.6.4.20.3.3 | 1.6.4.20.3.3 |  | 2026-10-26 08:00 | p | 101 |  | 2027-02-04 09:16
381 | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Normal | 3 | 1.6.4.20.3.3.1 | 1.6.4.20.3.3.1 |  | 2026-10-26 08:00 | p | 101 |  | 2027-02-04 09:16
382 | 4061 | ViM2psfxppAdWr3IoYdq | Normal | 3 | 1.6.4.20.3.3.2 | 1.6.4.20.3.3.2 |  | 2026-10-29 08:00 | p | 102 |  | 2027-02-08 13:21
383 | 4062 | RvsEFsErXikPrAOovPaZ | Normal | 1 | 1.6.4.20.3.3.3 | 1.6.4.20.3.3.3 |  | 2026-11-03 08:00 | p | 100 |  | 2027-02-11 14:06
384 | 4063 | ma6GKJ3GzeKmeF4AshaM | Normal | 4 | 1.6.4.20.3.3.4 | 1.6.4.20.3.3.4 |  | 2026-11-04 08:00 | p | 100 |  | 2027-02-12 10:03
385 | 4064 | OALhjNOvEaqSDAmsS5Il | Normal | 1 | 1.6.4.20.3.3.5 | 1.6.4.20.3.3.5 |  | 2026-11-10 08:00 | p | 100 |  | 2027-02-18 09:34
386 | 7010 | l7MAqMN94R7DBQRgok6z | Normal | 5 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 2025-04-07 08:00 | p | 3 |  | 2025-04-10 13:11
387 | 7278 | 4Ma7Z2LiPmWBC9UI6vyb | Normal | 5 | 1.6.4.18.3.3.7.7 | 1.6.4.18.3.3.7.7 |  | 2025-03-24 08:00 | p | 0 |  | 2025-03-24 13:52
388 | 7300 | JMkMoXIhBdn9ICcOd798 | Normal | 5 | 1.6.4.18.3.3.7.4 | 1.6.4.18.3.3.7.4 |  | 2025-03-03 08:00 | q | -2 |  | 2025-02-28 08:19
389 | 7302 | 6S1rSJxqNAmNyzjZVL7L | Normal | 5 | 1.6.4.18.3.3.7.8 | 1.6.4.18.3.3.7.8 |  | 2025-03-31 08:00 | p | 4 |  | 2025-04-04 11:17
390 | 7282 | sTVLhyKAe9uIrxTuOSsB | Normal | 2 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 2025-02-20 08:00 | q | -8 |  | 2025-02-11 10:23
391 | 7283 | GyFcZSlU29ifaVubQEBd | Normal | 2 | 1.6.4.18.3.3.4.4 | 1.6.4.18.3.3.4.4 |  | 2025-02-24 08:00 | q | -10 |  | 2025-02-13 10:49
392 | 7284 | AoDPK2hmzwZjnwdc6ENo | Normal | 1 | 1.6.4.18.3.3.4.5 | 1.6.4.18.3.3.4.5 |  | 2025-02-26 08:00 | q | -7 |  | 2025-02-18 09:49
393 | 7285 | UP4KQN3vFTNJJtYiVHhd | Normal | 10 | 1.6.4.18.3.3.4.6 | 1.6.4.18.3.3.4.6 |  | 2025-02-27 08:00 | q | -7 |  | 2025-02-19 08:43
394 | 7289 | YNbMTserJcwdDTx8O6lt | Normal | 5 | 1.6.4.18.3.3.5.3 | 1.6.4.18.3.3.5.3 |  | 2025-02-21 08:00 | p | 0 |  | 2025-02-21 16:57
395 | 7290 | rpRUKocvSOF2GnoJsxWr | Normal | 2 | 1.6.4.18.3.3.5.4 | 1.6.4.18.3.3.5.4 |  | 2025-02-28 08:00 | p | 4 |  | 2025-03-04 09:58
396 | 7291 | ThxkR8uStFOgKr5Kajlm | Normal | 1 | 1.6.4.18.3.3.5.5 | 1.6.4.18.3.3.5.5 |  | 2025-03-04 08:00 | p | 2 |  | 2025-03-06 09:58
397 | 7292 | 6vEOHVPLFOaXnW1xcDp6 | Normal | 10 | 1.6.4.18.3.3.5.6 | 1.6.4.18.3.3.5.6 |  | 2025-03-05 08:00 | p | 2 |  | 2025-03-07 09:02
398 | 7296 | PnFVdPiNKahDkradYWdd | Normal | 5 | 1.6.4.18.3.3.6.3 | 1.6.4.18.3.3.6.3 |  | 2025-03-05 08:00 | p | 1 |  | 2025-03-06 11:06
399 | 7297 | JA5LCeR4tD4Vqq2Jfy9o | Normal | 2 | 1.6.4.18.3.3.6.4 | 1.6.4.18.3.3.6.4 |  | 2025-03-12 08:00 | p | 5 |  | 2025-03-17 09:24
400 | 7298 | uHK4wyA8DzlXgqm5UKoq | Normal | 1 | 1.6.4.18.3.3.6.5 | 1.6.4.18.3.3.6.5 |  | 2025-03-14 08:00 | p | 4 |  | 2025-03-18 16:05
401 | 7299 | ymtRqRQZa4AjGraGOZVd | Normal | 10 | 1.6.4.18.3.3.6.6 | 1.6.4.18.3.3.6.6 |  | 2025-03-17 08:00 | p | 2 |  | 2025-03-19 14:52
402 | 4204 | CRzwy8942pbCOpcOMW2v | Normal | 20 | 1.6.1.1.4 | 1.6.1.1.4 |  | 2025-06-16 08:00 | p | 32 |  | 2025-07-18 08:03
403 | 4218 | T5g2El1CSAmFZNlboxQh | Normal | 1 | 1.6.1.4 | 1.6.1.4 |  | 2025-07-16 08:00 | p | 30 |  | 2025-08-15 13:39
404 | 6080 | jFrzSNmYyPDtKSvRlBw2 | Normal | 1 | 1.6.1.6 | 1.6.1.6 |  | 2026-08-26 08:00 | q | -1115 |  | 2023-08-07 08:00
405 | 5507 | 1r4d5DbY2YIgMhg8HKuO | Normal | 3 | 1.6.3.3.2 | 1.6.3.3.2 |  | 2025-04-08 08:00 | p | 14 |  | 2025-04-22 10:47
406 | 5508 | wHSntGHJkj4aA0wA3fA2 | Normal | 14 | 1.6.3.3.3 | 1.6.3.3.3 |  | 2025-04-11 08:00 | p | 14 |  | 2025-04-25 15:13
407 | 5509 | 1FHP32ReWIveKb3JOWEG | Summary | 44 | 1.6.3.3.4 | 1.6.3.3.4 |  | 2025-05-01 08:00 | p | 15 |  | 2025-05-16 13:13
408 | 5510 | LTFwTsrnxYhrGNFUv7CM | Normal | 12 | 1.6.3.3.4.1 | 1.6.3.3.4.1 |  | 2025-05-01 08:00 | p | 15 |  | 2025-05-16 13:13
409 | 5511 | Od3mMFxB7LjrJLF1slz4 | Normal | 11 | 1.6.3.3.4.2 | 1.6.3.3.4.2 |  | 2025-05-19 08:00 | p | 21 |  | 2025-06-09 13:11
410 | 5512 | Des2hDKSMjcJndTJRzoQ | Normal | 11 | 1.6.3.3.4.3 | 1.6.3.3.4.3 |  | 2025-06-04 08:00 | p | 22 |  | 2025-06-26 15:16
411 | 5513 | z1vb48lrGwUUDjKbD3gr | Normal | 10 | 1.6.3.3.4.4 | 1.6.3.3.4.4 |  | 2025-06-20 08:00 | p | 25 |  | 2025-07-15 10:49
412 | 5514 | leNXdZKmybH4tpy20cQU | Normal | 5 | 1.6.3.3.5 | 1.6.3.3.5 |  | 2025-07-07 08:00 | p | 156 |  | 2025-12-10 16:55
413 | 7307 | eye8r8DevGvPITcdrMUe | Normal | 6 | 1.6.3.11.1.3.4.4 | 1.6.3.11.1.3.4.4 |  | 2025-02-10 08:00 | q | -7 |  | 2025-02-03 08:00
414 | 7308 | BXoPyB4GmzJwvFdrkJ7b | Normal | 1 | 1.6.3.11.1.3.4.5 | 1.6.3.11.1.3.4.5 |  | 2025-02-19 08:00 | q | -8 |  | 2025-02-10 11:28
415 | 7314 | zaliCdoIQDW2tx8wBQyt | Normal | 1 | 1.6.3.11.1.3.5.5 | 1.6.3.11.1.3.5.5 |  | 2025-02-20 08:00 | p | 0 |  | 2025-02-20 15:12
416 | 7318 | vWglY3BMmZCigDWMEMyY | Normal | 3 | 1.6.3.11.1.3.6.3 | 1.6.3.11.1.3.6.3 |  | 2025-02-20 08:00 | p | 0 |  | 2025-02-20 15:12
417 | 7319 | Fr6VbOwwg75s6X3Xcfql | Normal | 5 | 1.6.3.11.1.3.6.4 | 1.6.3.11.1.3.6.4 |  | 2025-02-25 08:00 | p | 1 |  | 2025-02-26 15:34
418 | 7320 | MRmQHJYBr9cc2OfLUSYd | Normal | 1 | 1.6.3.11.1.3.6.5 | 1.6.3.11.1.3.6.5 |  | 2025-03-04 08:00 | p | 1 |  | 2025-03-05 13:53
419 | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Milestone | 0 | 1.8.2.1 | 1.8.2.1 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
420 | 6295 | uPS9GNqRLP4065SnBhEr | Summary | 387 | 1.8.5 | 1.8.5 |  | 2024-09-03 08:00 | q | -393 |  | 2023-08-07 08:00
421 | 3679 | 1KDcwGZKgevw1MizqBh0 | Summary | 387 | 1.8.5.1 | 1.8.5.1 |  | 2024-09-03 08:00 | q | -393 |  | 2023-08-07 08:00
422 | 3680 | E8qsx9NjEz7vaL5H7EFb | Summary | 189 | 1.8.5.1.1 | 1.8.5.1.1 |  | 2025-03-24 08:00 | p | 16 |  | 2025-04-09 09:57
423 | 3681 | wdhUrQuIMTMPn1LoqO1m | Normal | 24 | 1.8.5.1.1.1 | 1.8.5.1.1.1 |  | 2025-03-24 08:00 | p | 16 |  | 2025-04-09 09:57
424 | 3682 | 38PSIqFGHzjKldiudT82 | Summary | 25 | 1.8.5.1.1.4 | 1.8.5.1.1.4 |  | 2025-04-25 08:00 | p | 7 |  | 2025-05-02 09:24
425 | 3683 | JW3LUw009FZ7ddD6CdLX | Normal | 20 | 1.8.5.1.1.4.1 | 1.8.5.1.1.4.1 |  | 2025-04-25 08:00 | p | 7 |  | 2025-05-02 09:24
426 | 3684 | g3f8U3i4iakOhylueut6 | Normal | 5 | 1.8.5.1.1.4.2 | 1.8.5.1.1.4.2 |  | 2025-05-23 08:00 | p | 11 |  | 2025-06-03 16:26
427 | 3685 | eStRoX3vnaDmRLAWk58C | Summary | 40 | 1.8.5.1.1.5 | 1.8.5.1.1.5 |  | 2025-06-02 08:00 | p | 10 |  | 2025-06-12 11:53
428 | 3686 | 7zhxjkpiLTAH9tiW1eYy | Normal | 20 | 1.8.5.1.1.5.1 | 1.8.5.1.1.5.1 |  | 2025-06-02 08:00 | p | 10 |  | 2025-06-12 11:53
429 | 3687 | 0zzWvesUS18qEUfjK5NH | Normal | 5 | 1.8.5.1.1.5.2 | 1.8.5.1.1.5.2 |  | 2025-07-01 08:00 | p | 17 |  | 2025-07-18 15:02
430 | 3688 | zSUYYsBrfiOGi6qJakS6 | Normal | 5 | 1.8.5.1.1.5.3 | 1.8.5.1.1.5.3 |  | 2025-07-09 08:00 | p | 16 |  | 2025-07-25 16:44
431 | 3689 | X7sWUqInOJZ9zcVzmfT1 | Normal | 5 | 1.8.5.1.1.5.4 | 1.8.5.1.1.5.4 |  | 2025-07-16 08:00 | p | 19 |  | 2025-08-04 10:03
432 | 3690 | 8YDpqEvemQaMsfVmGpF8 | Normal | 5 | 1.8.5.1.1.5.5 | 1.8.5.1.1.5.5 |  | 2025-07-23 08:00 | p | 19 |  | 2025-08-11 11:02
433 | 3691 | ofZrlktbiXkVpuhhIeO5 | Summary | 25 | 1.8.5.1.1.6 | 1.8.5.1.1.6 |  | 2025-07-01 08:00 | p | 17 |  | 2025-07-18 15:02
434 | 3692 | xRsKOxB8zGAnVTXugcHQ | Normal | 20 | 1.8.5.1.1.6.1 | 1.8.5.1.1.6.1 |  | 2025-07-01 08:00 | p | 17 |  | 2025-07-18 15:02
435 | 3693 | Hn8rBaTvxeP9Vb10zF48 | Normal | 5 | 1.8.5.1.1.6.2 | 1.8.5.1.1.6.2 |  | 2025-07-30 08:00 | p | 19 |  | 2025-08-18 16:30
436 | 3694 | 4tipOydrC0LTNincaMDW | Summary | 35 | 1.8.5.1.1.7 | 1.8.5.1.1.7 |  | 2025-07-30 08:00 | p | 19 |  | 2025-08-18 16:30
437 | 3695 | lT6NpgfSYqKHtVYFLSzF | Normal | 20 | 1.8.5.1.1.7.1 | 1.8.5.1.1.7.1 |  | 2025-07-30 08:00 | p | 19 |  | 2025-08-18 16:30
438 | 3696 | gijouZuJR1ZVcSfHKSTf | Normal | 5 | 1.8.5.1.1.7.2 | 1.8.5.1.1.7.2 |  | 2025-08-27 08:00 | p | 33 |  | 2025-09-29 09:56
439 | 3697 | 1158ttL4JEmZYV6RmdcS | Normal | 5 | 1.8.5.1.1.7.3 | 1.8.5.1.1.7.3 |  | 2025-09-04 08:00 | p | 33 |  | 2025-10-07 10:03
440 | 3698 | AKCwPpEPQi4iH3XDRpiM | Normal | 5 | 1.8.5.1.1.7.4 | 1.8.5.1.1.7.4 |  | 2025-09-11 08:00 | p | 35 |  | 2025-10-16 08:57
441 | 3699 | AYANEA6OuC5b95kp3uyI | Summary | 30 | 1.8.5.1.1.8 | 1.8.5.1.1.8 |  | 2025-08-27 08:00 | p | 33 |  | 2025-09-29 09:56
442 | 3700 | WE9bFDn3y5M7oiID5UPj | Normal | 20 | 1.8.5.1.1.8.1 | 1.8.5.1.1.8.1 |  | 2025-08-27 08:00 | p | 33 |  | 2025-09-29 09:56
443 | 3701 | CXSHp4tESy2S0nMNpo3C | Normal | 5 | 1.8.5.1.1.8.2 | 1.8.5.1.1.8.2 |  | 2025-09-25 08:00 | p | 29 |  | 2025-10-24 13:58
444 | 3702 | sTuPByKbZEfSXxt0Z2G9 | Normal | 5 | 1.8.5.1.1.8.3 | 1.8.5.1.1.8.3 |  | 2025-10-02 08:00 | p | 29 |  | 2025-10-31 16:47
445 | 3703 | WHZRJAK4v6S9Zk2EBeP3 | Summary | 40 | 1.8.5.1.1.9 | 1.8.5.1.1.9 |  | 2025-09-25 08:00 | p | 29 |  | 2025-10-24 13:58
446 | 3704 | 3CXbrhXJooXd98jlpAkg | Normal | 20 | 1.8.5.1.1.9.1 | 1.8.5.1.1.9.1 |  | 2025-09-25 08:00 | p | 29 |  | 2025-10-24 13:58
447 | 3705 | RO9RShNcg0h7x9fD24Zk | Normal | 5 | 1.8.5.1.1.9.2 | 1.8.5.1.1.9.2 |  | 2025-10-24 08:00 | p | 21 |  | 2025-11-14 10:21
448 | 3706 | w8MhGnhxyXFIHvJdw6bc | Normal | 5 | 1.8.5.1.1.9.3 | 1.8.5.1.1.9.3 |  | 2025-10-31 08:00 | p | 19 |  | 2025-11-19 13:23
449 | 3707 | dJNKgtiJ1M8pNoPOlZcZ | Normal | 5 | 1.8.5.1.1.9.4 | 1.8.5.1.1.9.4 |  | 2025-11-07 08:00 | p | 21 |  | 2025-11-28 11:01
450 | 3708 | 84VtM14FQkMGurZDdBLv | Normal | 5 | 1.8.5.1.1.9.5 | 1.8.5.1.1.9.5 |  | 2025-11-17 08:00 | p | 21 |  | 2025-12-08 08:35
451 | 3709 | gpO5WcJkYid7jZAXZwbn | Summary | 40 | 1.8.5.1.1.10 | 1.8.5.1.1.10 |  | 2025-10-24 08:00 | p | 21 |  | 2025-11-14 10:21
452 | 3710 | KOKaQwRJEoC6vlU3mKjm | Normal | 20 | 1.8.5.1.1.10.1 | 1.8.5.1.1.10.1 |  | 2025-10-24 08:00 | p | 21 |  | 2025-11-14 10:21
453 | 3711 | XXu8BmtFqx4o2r8a6o98 | Normal | 5 | 1.8.5.1.1.10.2 | 1.8.5.1.1.10.2 |  | 2025-11-24 08:00 | p | 22 |  | 2025-12-16 13:41
454 | 3712 | sZwrgRbHYjKWcIa9rVK3 | Normal | 5 | 1.8.5.1.1.10.3 | 1.8.5.1.1.10.3 |  | 2025-12-02 08:00 | p | 22 |  | 2025-12-24 08:37
455 | 3713 | 4NbryuRKpmrExDEDqArG | Normal | 5 | 1.8.5.1.1.10.4 | 1.8.5.1.1.10.4 |  | 2025-12-09 08:00 | p | 24 |  | 2026-01-02 15:25
456 | 3714 | Fbm1iHrhCX8z8SNRXJuq | Normal | 5 | 1.8.5.1.1.10.5 | 1.8.5.1.1.10.5 |  | 2025-12-16 08:00 | p | 24 |  | 2026-01-09 09:53
457 | 6646 | CmmxWTpZgFyyAwkQnNh3 | Normal | 10 | 1.8.5.1.1.2 | 1.8.5.1.1.2 |  | 2025-04-25 08:00 | p | 7 |  | 2025-05-02 09:24
458 | 6647 | hWzCSsDre5WTTpryk1b0 | Normal | 5 | 1.8.5.1.1.3 | 1.8.5.1.1.3 |  | 2025-05-09 08:00 | p | 6 |  | 2025-05-15 15:57
459 | 3715 | V6i7uYjEJBRYHjhIimqJ | Summary | 50 | 1.8.5.1.2 | 1.8.5.1.2 |  | 2025-12-23 08:00 | p | 28 |  | 2026-01-20 16:54
460 | 3716 | bdy5zVX59rD935sK6M5v | Normal | 20 | 1.8.5.1.2.1 | 1.8.5.1.2.1 |  | 2025-12-23 08:00 | p | 28 |  | 2026-01-20 16:54
461 | 3717 | 5PdqCAMtbYgi5VsFO6ls | Normal | 20 | 1.8.5.1.2.4 | 1.8.5.1.2.4 |  | 2026-02-06 08:00 | p | 25 |  | 2026-03-03 10:48
462 | 6671 | 0oTh3tmNX3iVSaVNVmGK | Normal | 5 | 1.8.5.1.2.2 | 1.8.5.1.2.2 |  | 2026-01-23 08:00 | p | 26 |  | 2026-02-18 09:11
463 | 6672 | BKyGOzVPyPwKpI9CyseJ | Normal | 5 | 1.8.5.1.2.3 | 1.8.5.1.2.3 |  | 2026-01-30 08:00 | p | 27 |  | 2026-02-26 09:38
464 | 3718 | vTyTgxcbRSz6H6lqDAEf | Summary | 20 | 1.8.5.1.3 | 1.8.5.1.3 |  | 2026-03-09 08:00 | p | 18 |  | 2026-03-27 11:53
465 | 3719 | B9ymEBZ7zimHMMqNS20Q | Normal | 20 | 1.8.5.1.3.1 | 1.8.5.1.3.1 |  | 2026-03-09 08:00 | p | 18 |  | 2026-03-27 11:53
466 | 3720 | rPRo0RE1uNkj9oG127hu | Summary | 109 | 1.8.5.1.4 | 1.8.5.1.4 |  | 2025-03-19 08:00 | q | -590 |  | 2023-08-07 08:00
467 | 3721 | 45j7fpB55qVEeWfRBgCv | Normal | 1 | 1.8.5.1.4.1 | 1.8.5.1.4.1 |  | 2025-03-19 08:00 | q | -590 |  | 2023-08-07 08:00
468 | 3722 | hYa6Ppkzu6veYWmxHffd | Normal | 27 | 1.8.5.1.4.2 | 1.8.5.1.4.2 |  | 2025-03-20 08:00 | q | -590 |  | 2023-08-07 16:59
469 | 6649 | TeFWDZJ3h8q4yVNptUYE | Normal | 28 | 1.8.5.1.4.3 | 1.8.5.1.4.3 |  | 2025-04-28 08:00 | q | -591 |  | 2023-09-14 10:45
470 | 6650 | FvuNLI4Jaew3VjPpwL3e | Normal | 28 | 1.8.5.1.4.4 | 1.8.5.1.4.4 |  | 2025-06-06 08:00 | q | -590 |  | 2023-10-24 11:20
471 | 6651 | T3J0AzovT4qFTLJ7Lgki | Normal | 15 | 1.8.5.1.4.5 | 1.8.5.1.4.5 |  | 2025-07-18 08:00 | q | -603 |  | 2023-11-22 11:54
472 | 6652 | 0afM7N7hGdWHQjlFenVR | Normal | 10 | 1.8.5.1.4.6 | 1.8.5.1.4.6 |  | 2025-08-08 08:00 | q | -602 |  | 2023-12-14 08:10
473 | 3724 | ZCOxRRLLrh9Pa7VnBAyk | Normal | 27 | 1.8.5.1.5.1 | 1.8.5.1.5.1 |  | 2025-03-24 08:00 | p | 16 |  | 2025-04-09 09:57
474 | 6661 | bQxmmL7mcUsEGpKkQTDo | Normal | 28 | 1.8.5.1.5.2 | 1.8.5.1.5.2 |  | 2025-04-30 08:00 | p | 12 |  | 2025-05-12 16:01
475 | 6662 | CVNpv9CNU8XhfLmVwl8x | Normal | 28 | 1.8.5.1.5.3 | 1.8.5.1.5.3 |  | 2025-06-10 08:00 | p | 14 |  | 2025-06-24 09:50
476 | 6663 | LVExlIxeJ6XB3yqm0Dzs | Normal | 28 | 1.8.5.1.5.4 | 1.8.5.1.5.4 |  | 2025-07-22 08:00 | p | 13 |  | 2025-08-04 10:00
477 | 6664 | Io9oZ1dPqEE9GDlMTPxh | Normal | 28 | 1.8.5.1.5.5 | 1.8.5.1.5.5 |  | 2025-08-29 08:00 | p | 13 |  | 2025-09-11 10:43
478 | 6665 | ycT0qtEFjd4p02S4Ehf1 | Normal | 28 | 1.8.5.1.5.6 | 1.8.5.1.5.6 |  | 2025-10-09 08:00 | p | 13 |  | 2025-10-22 16:20
479 | 6666 | sX3PHseynvzwKI9my2AH | Normal | 15 | 1.8.5.1.5.7 | 1.8.5.1.5.7 |  | 2025-11-20 08:00 | p | 11 |  | 2025-12-01 13:30
480 | 6667 | 0dYk2X7XWh2rSSHkHo2L | Normal | 10 | 1.8.5.1.5.8 | 1.8.5.1.5.8 |  | 2025-12-12 08:00 | p | 21 |  | 2026-01-02 13:43
481 | 6668 | NGuTznXCCG5yuIi6lGQO | Normal | 1 | 1.8.5.1.5.10 | 1.8.5.1.5.10 |  | 2025-06-20 08:00 | q | -7 |  | 2025-06-12 16:22
482 | 6669 | t8MCocRefa6DhiQNsJVn | Normal | 1 | 1.8.5.1.5.11 | 1.8.5.1.5.11 |  | 2025-06-23 08:00 | q | -6 |  | 2025-06-16 09:10
483 | 6670 | vWxPVjk5e7KHTev8998h | Normal | 1 | 1.8.5.1.5.12 | 1.8.5.1.5.12 |  | 2025-06-24 08:00 | q | -6 |  | 2025-06-17 10:26
484 | 3726 | 5hjTNIk7WmpZNtmCLhPN | Summary | 96 | 1.8.5.1.6 | 1.8.5.1.6 |  | 2025-05-08 08:00 | q | -191 |  | 2024-10-29 08:00
485 | 3727 | rGcF2XgkgPtqRDM3KJ2D | Normal | 28 | 1.8.5.1.6.1 | 1.8.5.1.6.1 |  | 2025-05-08 08:00 | q | -191 |  | 2024-10-29 08:00
486 | 3728 | Hgqc9wbzS3SDikBm20zt | Normal | 28 | 1.8.5.1.6.3 | 1.8.5.1.6.3 |  | 2025-07-11 08:00 | q | -183 |  | 2025-01-08 13:33
487 | 6653 | K0AYRckqpyO0HzRrxXG6 | Normal | 15 | 1.8.5.1.6.2 | 1.8.5.1.6.2 |  | 2025-06-18 08:00 | q | -183 |  | 2024-12-16 08:38
488 | 6654 | MMK0qYycfTMCrFAZcf8J | Normal | 15 | 1.8.5.1.6.4 | 1.8.5.1.6.4 |  | 2025-08-20 08:00 | q | -172 |  | 2025-02-28 09:27
489 | 6655 | gl8c5oVG5KfrLbsQSFL4 | Normal | 10 | 1.8.5.1.6.5 | 1.8.5.1.6.5 |  | 2025-09-11 08:00 | q | -170 |  | 2025-03-24 14:21
490 | 3729 | Y6b5KP0DE9c4tlFzqxp3 | Summary | 81 | 1.8.5.1.7 | 1.8.5.1.7 |  | 2025-03-11 08:00 | q | -582 |  | 2023-08-07 08:00
491 | 3730 | TswICWhG0Mjj1DenbPW5 | Normal | 28 | 1.8.5.1.7.1 | 1.8.5.1.7.1 |  | 2025-03-11 08:00 | q | -582 |  | 2023-08-07 08:00
492 | 6626 | 9d2gtkuh8SmNZwArNzpn | Normal | 10 | 1.8.5.1.7.4 | 1.8.5.1.7.4 |  | 2025-06-20 08:00 | q | -583 |  | 2023-11-14 08:25
493 | 6627 | QBgG0JxqOymB6vyjKsRZ | Normal | 28 | 1.8.5.1.7.2 | 1.8.5.1.7.2 |  | 2025-04-18 08:00 | q | -577 |  | 2023-09-18 16:36
494 | 6628 | PAI9VZBMaYriaY1wvhOi | Normal | 15 | 1.8.5.1.7.3 | 1.8.5.1.7.3 |  | 2025-05-29 08:00 | q | -581 |  | 2023-10-25 15:22
495 | 3733 | ufu7SWDoeBfTzZW24BQU | Summary | 189 | 1.8.5.1.9 | 1.8.5.1.9 |  | 2025-03-17 08:00 | q | -588 |  | 2023-08-07 08:00
496 | 3734 | cAszcoDUs4YPdXAiXa4B | Milestone | 0 | 1.8.5.1.9.1 | 1.8.5.1.9.1 |  | 2025-03-17 08:00 | q | -588 |  | 2023-08-07 08:00
497 | 3735 | rgqtw8hyurrfag2amXLA | Normal | 109 | 1.8.5.1.9.2 | 1.8.5.1.9.2 |  | 2025-03-17 08:00 | q | -588 |  | 2023-08-07 08:00
498 | 3736 | eIMYQUSTObIc5Lp6kKBE | Normal | 40 | 1.8.5.1.9.3 | 1.8.5.1.9.3 |  | 2025-08-20 08:00 | q | -588 |  | 2024-01-09 09:41
499 | 3737 | z19Wnme0hJcfEI4IfIQR | Normal | 25 | 1.8.5.1.9.4 | 1.8.5.1.9.4 |  | 2025-10-17 08:00 | p | 26 |  | 2025-11-12 10:27
500 | 6657 | uq5fluI8KT8LkPx57ktn | Normal | 10 | 1.8.5.1.9.5 | 1.8.5.1.9.5 |  | 2025-11-24 08:00 | p | 21 |  | 2025-12-15 14:16
501 | 6658 | ktg0XNnAmjjc1caqICt2 | Normal | 5 | 1.8.5.1.9.6 | 1.8.5.1.9.6 |  | 2025-12-09 08:00 | p | 24 |  | 2026-01-02 09:26
502 | 3738 | bohrZqwOTsvUL4DEUnjh | Summary | 139 | 1.8.5.1.10 | 1.8.5.1.10 |  | 2025-03-17 08:00 | q | -588 |  | 2023-08-07 08:00
503 | 3739 | Ba23bBwg4xGpRd3Ht4kS | Normal | 24 | 1.8.5.1.10.1 | 1.8.5.1.10.1 |  | 2025-03-17 08:00 | q | -588 |  | 2023-08-07 08:00
504 | 3740 | lRtbtcrLyr1QGd0laoJi | Normal | 25 | 1.8.5.1.10.2 | 1.8.5.1.10.2 |  | 2025-04-18 08:00 | q | -589 |  | 2023-09-06 09:53
505 | 3741 | V05WnFKB5t2LuixhoKHO | Normal | 25 | 1.8.5.1.10.3 | 1.8.5.1.10.3 |  | 2025-05-23 08:00 | q | -588 |  | 2023-10-12 14:10
506 | 3742 | LRjVz0hoZuIRlQgcLYzs | Normal | 25 | 1.8.5.1.10.6 | 1.8.5.1.10.6 |  | 2025-08-06 08:00 | q | -592 |  | 2023-12-22 13:47
507 | 6648 | Z5T3n0GGVz8PB0IY5TXC | Normal | 10 | 1.8.5.1.10.5 | 1.8.5.1.10.5 |  | 2025-07-23 08:00 | q | -588 |  | 2023-12-12 14:39
508 | 6656 | tqprQgHoroqT051BXug3 | Normal | 15 | 1.8.5.1.10.4 | 1.8.5.1.10.4 |  | 2025-07-01 08:00 | q | -586 |  | 2023-11-22 14:32
509 | 6659 | NN3Qiea1foOxv05JqXnT | Normal | 10 | 1.8.5.1.10.7 | 1.8.5.1.10.7 |  | 2025-09-11 08:00 | q | -583 |  | 2024-02-05 11:06
510 | 6660 | pWIs4hM6SgH2pFjSQ3qo | Normal | 5 | 1.8.5.1.10.8 | 1.8.5.1.10.8 |  | 2025-09-25 08:00 | q | -586 |  | 2024-02-16 09:31
511 | 6642 | A7Bd82G8YCk8VjEZkcvi | Summary | 135 | 1.8.5.1.8 | 1.8.5.1.8 |  | 2025-10-17 08:00 | q | -608 |  | 2024-02-16 08:12
512 | 3731 | 02LiOyWN4DF8GOeNSP5s | Normal | 20 | 1.8.5.1.8.1 | 1.8.5.1.8.1 |  | 2025-10-17 08:00 | q | -608 |  | 2024-02-16 08:12
513 | 3732 | x85AkT9s5HT2a4U2goND | Normal | 20 | 1.8.5.1.8.8 | 1.8.5.1.8.8 |  | 2025-11-17 08:00 | q | -615 |  | 2024-03-11 09:57
514 | 6629 | n59ds33sZr9JNOobmYWE | Normal | 30 | 1.8.5.1.8.2 | 1.8.5.1.8.2 |  | 2025-11-17 08:00 | q | -615 |  | 2024-03-11 09:57
515 | 6630 | y36QmeQSyS7BZflkeM7e | Normal | 10 | 1.8.5.1.8.3 | 1.8.5.1.8.3 |  | 2025-12-31 08:00 | q | -631 |  | 2024-04-08 11:05
516 | 6631 | Ghk1eKq5exIyUH3hdAeR | Normal | 20 | 1.8.5.1.8.4 | 1.8.5.1.8.4 |  | 2026-01-15 08:00 | q | -632 |  | 2024-04-22 15:09
517 | 6632 | 5y36mClzGR7vkSsODb4C | Normal | 15 | 1.8.5.1.8.5 | 1.8.5.1.8.5 |  | 2026-02-13 08:00 | q | -632 |  | 2024-05-21 08:31
518 | 6633 | uS272glxjETpDiVeJyGv | Normal | 20 | 1.8.5.1.8.6 | 1.8.5.1.8.6 |  | 2026-03-09 08:00 | q | -640 |  | 2024-06-06 13:24
519 | 6634 | 65ghvPiwU0AxSKrC11rG | Normal | 20 | 1.8.5.1.8.7 | 1.8.5.1.8.7 |  | 2026-04-06 08:00 | q | -635 |  | 2024-07-09 11:38
520 | 6643 | sKnPCsxlq51dE8cz52fo | Normal | 10 | 1.8.5.1.8.9 | 1.8.5.1.8.9 |  | 2025-12-16 08:00 | q | -612 |  | 2024-04-12 08:54
521 | 6644 | 0NVu6ABxwy3imKaZ2MTJ | Normal | 10 | 1.8.5.1.8.10 | 1.8.5.1.8.10 |  | 2025-12-31 08:00 | q | -11 |  | 2025-12-19 09:31
522 | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Summary | 1 | 1.8.1 | 1.8.1 |  | 2026-10-07 16:58 | p | 580 |  | 2028-05-10 13:40
523 | 6082 | YsSSuERf5VIDKO5m8eZo | Normal | 1 | 1.8.1.1 | 1.8.1.1 |  | 2026-10-07 16:58 | p | 580 |  | 2028-05-10 13:40
524 | 6313 | 8HYxn50EKf1DU0fX0MF7 | Summary | 391 | 1.8.4 | 1.8.4 |  | 2025-03-20 08:00 | q | -591 |  | 2023-08-07 08:00
525 | 5516 | dd6fm1lW4tBXPtNV5RGW | Summary | 391 | 1.8.4.1 | 1.8.4.1 |  | 2025-03-20 08:00 | q | -591 |  | 2023-08-07 08:00
526 | 5517 | IHfroMkwx3TZoTXYbBOK | Normal | 40 | 1.8.4.1.1 | 1.8.4.1.1 |  | 2025-03-20 08:00 | q | -591 |  | 2023-08-07 08:00
527 | 5518 | V0a5XEJ0jxIkhnpEDg8e | Normal | 40 | 1.8.4.1.2 | 1.8.4.1.2 |  | 2025-03-20 08:00 | q | -591 |  | 2023-08-07 08:00
528 | 5519 | D5sl3M5NpO77EU7TPYT0 | Normal | 40 | 1.8.4.1.3 | 1.8.4.1.3 |  | 2025-03-20 08:00 | q | -591 |  | 2023-08-07 08:00
529 | 5523 | APkwTVep7mUhgmcCl4NB | Milestone | 0 | 1.8.4.1.4 | 1.8.4.1.4 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
530 | 5527 | Mw5Re8SivA42laH7UhJE | Milestone | 0 | 1.8.4.1.5 | 1.8.4.1.5 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
531 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 2021-01-04 08:00 | q | -1307 |  | 2017-06-07 08:00
532 | 5332 | Jas5wmBgln6JvMRLtRUk | Summary | 110 | 1.9.3.1 | 1.9.3.1 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
533 | 5333 | NEZJUiuEFBeqDBEbXbzQ | Milestone | 0 | 1.9.3.1.1 | 1.9.3.1.1 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
534 | 5334 | 5Bt8vyiG2PJ2FKCjQPP1 | Summary | 74 | 1.9.3.1.2 | 1.9.3.1.2 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
535 | 6471 | xmZvSzAhf2D9ir29atKO | Normal | 8 | 1.9.3.1.2.1 | 1.9.3.1.2.1 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
536 | 6472 | j0VQ7fJsNHb1HpOVRoJN | Normal | 7 | 1.9.3.1.2.2 | 1.9.3.1.2.2 |  | 2025-10-20 08:30 | q | -33 |  | 2025-09-16 10:33
537 | 6473 | FN1N5cBOnOQJN0lvtY6J | Normal | 5 | 1.9.3.1.2.3 | 1.9.3.1.2.3 |  | 2025-10-29 08:30 | q | -32 |  | 2025-09-26 09:27
538 | 6474 | k77H7bJ7aRKhBrZeZFzu | Normal | 10 | 1.9.3.1.2.4 | 1.9.3.1.2.4 |  | 2025-11-05 08:30 | q | -32 |  | 2025-10-03 14:29
539 | 6475 | TkBVMCiZTEhYxjcnMNRI | Normal | 8 | 1.9.3.1.2.5 | 1.9.3.1.2.5 |  | 2025-11-20 08:30 | q | -30 |  | 2025-10-20 14:59
540 | 6476 | HdsfOo0UbW7iVGjY7L1O | Normal | 10 | 1.9.3.1.2.6 | 1.9.3.1.2.6 |  | 2025-12-03 08:30 | q | -35 |  | 2025-10-28 16:00
541 | 6477 | m1G8PrmdvRxZwBbLlVUQ | Normal | 7 | 1.9.3.1.2.7 | 1.9.3.1.2.7 |  | 2025-12-17 08:30 | q | -29 |  | 2025-11-17 14:43
542 | 6478 | ZDDqpCGw2ELQiAxZVJFo | Normal | 7 | 1.9.3.1.2.8 | 1.9.3.1.2.8 |  | 2025-12-29 08:30 | q | -32 |  | 2025-11-26 14:19
543 | 6479 | i51TyrBkECB0t7wKJruE | Normal | 7 | 1.9.3.1.2.9 | 1.9.3.1.2.9 |  | 2026-01-07 08:30 | q | -29 |  | 2025-12-08 08:48
544 | 6480 | XeKgBzwPereNdZmXnTFt | Normal | 5 | 1.9.3.1.2.10 | 1.9.3.1.2.10 |  | 2026-01-16 08:30 | q | -28 |  | 2025-12-18 11:40
545 | 5335 | fBEkx0xCtVpw1OeE4jLB | Summary | 25 | 1.9.3.1.3 | 1.9.3.1.3 |  | 2026-01-23 08:30 | q | -27 |  | 2025-12-26 11:55
546 | 5336 | FIhKbBOHnlTp0loBBfvV | Normal | 3 | 1.9.3.1.3.1 | 1.9.3.1.3.1 |  | 2026-01-23 08:30 | q | -27 |  | 2025-12-26 11:55
547 | 5337 | TPAbtCx4KhMQiN0iVD1F | Normal | 0 | 1.9.3.1.3.2 | 1.9.3.1.3.2 |  | 2026-01-23 08:30 | q | -27 |  | 2025-12-26 11:55
548 | 5338 | NXWa8B3rzsUFws6lYttF | Normal | 5 | 1.9.3.1.3.3 | 1.9.3.1.3.3 |  | 2026-01-23 08:30 | q | -27 |  | 2025-12-26 11:55
549 | 5339 | o98eRuEZGwoxxa1Byl7H | Normal | 5 | 1.9.3.1.3.4 | 1.9.3.1.3.4 |  | 2026-01-23 08:30 | q | -27 |  | 2025-12-26 11:55
550 | 5340 | lQJTDBnvPE8mTPnPre3v | Normal | 10 | 1.9.3.1.3.5 | 1.9.3.1.3.5 |  | 2026-01-30 08:30 | q | -27 |  | 2026-01-02 14:46
551 | 5341 | nevxwfefPkBzu42CDbNd | Normal | 10 | 1.9.3.1.3.6 | 1.9.3.1.3.6 |  | 2026-02-13 08:30 | q | -29 |  | 2026-01-14 13:07
552 | 5342 | s0JiBiXDLP6oybWmkZ43 | Normal | 6 | 1.9.3.1.4 | 1.9.3.1.4 |  | 2026-02-27 08:30 | q | -28 |  | 2026-01-29 08:33
553 | 5343 | NROXqcLUoQ0RLz64rMVc | Normal | 5 | 1.9.3.1.5 | 1.9.3.1.5 |  | 2026-03-09 08:30 | q | -31 |  | 2026-02-05 15:31
554 | 5344 | Kw3Fj6kwk5uOl7tQyqrL | Milestone | 0 | 1.9.3.1.6 | 1.9.3.1.6 |  | 2026-03-16 08:30 | q | -31 |  | 2026-02-12 16:16
555 | 795 | 85yV4lhIxXIziyB5R2QA | Normal | 1 | 1.9.9.1 | 1.9.9.1 |  | 2026-09-16 13:00 | p | 929 |  | 2029-04-03 11:47
556 | 844 | 1qfp8o9PQxr9vZvO7S5k | Normal | 1 | 1.9.9.4 | 1.9.9.4 |  | 2026-10-02 13:00 | p | 929 |  | 2029-04-19 10:06
557 | 866 | 0rLFG0X22Uukcn0axQTO | Normal | 50 | 1.9.9.7.2.6 | 1.9.9.7.2.6 |  | 2025-04-15 08:00 | p | 23 |  | 2025-05-08 13:10
558 | 869 | 8QCM3LZ8SN5y0jCLtGNh | Summary | 129 | 1.9.9.7.2.7 | 1.9.9.7.2.7 |  | 2025-06-26 08:00 | p | 26 |  | 2025-07-22 15:07
559 | 6419 | NORPsF566zq8VZyN1UzF | Normal | 10 | 1.9.9.7.2.7.1 | 1.9.9.7.2.7.1 |  | 2025-06-26 08:00 | p | 26 |  | 2025-07-22 15:07
560 | 6420 | 043wOhyyEd8vJkuUBkFf | Normal | 40 | 1.9.9.7.2.7.2 | 1.9.9.7.2.7.2 |  | 2025-07-11 08:00 | p | 26 |  | 2025-08-06 11:19
561 | 6421 | JZROXyECnTBG3SBjYZJ8 | Normal | 79 | 1.9.9.7.2.7.3 | 1.9.9.7.2.7.3 |  | 2025-09-08 08:00 | p | 21 |  | 2025-09-29 08:24
562 | 4667 | gXRr1908PexMoLIDosFv | Normal | 100 | 1.9.9.14.3 | 1.9.9.14.3 |  | 2025-07-01 08:00 | p | 58 |  | 2025-08-28 14:51
563 | 4668 | G3SLCzd88WLMRnAF5Et7 | Normal | 0 | 1.9.9.14.4 | 1.9.9.14.4 |  | 2026-04-20 08:00 | p | 935 |  | 2028-11-10 11:17
564 | 4669 | aeClBbTsJ3qrKHWqQ1Rw | Normal | 40 | 1.9.9.14.5 | 1.9.9.14.5 |  | 2025-11-24 08:00 | p | 51 |  | 2026-01-14 08:57
565 | 4679 | rpzkOhA603pApmNdMeVE | Normal | 0 | 1.9.9.14.6 | 1.9.9.14.6 |  | 2026-05-22 08:00 | p | 934 |  | 2028-12-11 08:48
566 | 5787 | r6JEZEKCpBbNZRe1W7Ef | Normal | 91 | 1.9.9.14.2 | 1.9.9.14.2 |  | 2025-02-20 08:00 | p | 28 |  | 2025-03-20 08:03
567 | 899 | w1GWQdUx9oG06oopRYZx | Summary | 24 | 1.9.9.15 | 1.9.9.15 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
568 | 900 | ANUK0HdVlI2Jd5hSzs0f | Milestone | 0 | 1.9.9.15.1 | 1.9.9.15.1 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
569 | 901 | HcFqHITfVdYMyzVb3S8v | Normal | 18 | 1.9.9.15.2 | 1.9.9.15.2 |  | 2026-04-20 08:00 | p | 935 |  | 2028-11-10 11:17
570 | 902 | nIjAIVHCOoi1ijXym0cI | Normal | 3 | 1.9.9.15.3 | 1.9.9.15.3 |  | 2026-04-20 08:00 | p | 935 |  | 2028-11-10 11:17
571 | 903 | UDGopgZ2sb1QsQEooZ9G | Normal | 8 | 1.9.9.15.4 | 1.9.9.15.4 |  | 2026-04-23 08:00 | p | 937 |  | 2028-11-15 11:13
572 | 904 | 4CH3NSJx1luiHbrrAEJg | Normal | 2 | 1.9.9.15.5 | 1.9.9.15.5 |  | 2026-05-14 08:00 | p | 939 |  | 2028-12-08 16:02
573 | 905 | MxRWNVEH6ZVBPqNnA2hI | Normal | 8 | 1.9.9.15.6 | 1.9.9.15.6 |  | 2026-05-05 08:00 | p | 934 |  | 2028-11-24 11:14
574 | 906 | PL0zn2U2NPPXQqakkHLb | Normal | 5 | 1.9.9.15.7 | 1.9.9.15.7 |  | 2026-05-15 08:00 | p | 934 |  | 2028-12-04 09:48
575 | 907 | 5mTVpVcHzmsYLVY8xpKs | Normal | 5 | 1.9.9.15.8 | 1.9.9.15.8 |  | 2026-05-15 08:00 | p | 934 |  | 2028-12-04 09:48
576 | 914 | q0UeyWaeMXFoeUDjjzhX | Summary | 18 | 1.9.9.5 | 1.9.9.5 |  | 2025-08-12 08:00 | p | 937 |  | 2028-03-06 16:52
577 | 915 | jxzEE3EBeGWt1nE3uHcj | Summary | 18 | 1.9.9.5.1 | 1.9.9.5.1 |  | 2025-08-12 08:00 | p | 937 |  | 2028-03-06 16:52
578 | 916 | d4bxhxtQW3GaLrDrUlf9 | Normal | 17 | 1.9.9.5.1.1 | 1.9.9.5.1.1 |  | 2025-08-12 08:00 | p | 937 |  | 2028-03-06 16:52
579 | 917 | mbDdHZHm9OoYye329Ue6 | Normal | 1 | 1.9.9.5.1.2 | 1.9.9.5.1.2 |  | 2025-09-05 08:00 | p | 941 |  | 2028-04-03 11:32
580 | 4538 | aTyUglf0WPX6H8Zd17Iq | Summary | 71 | 1.9.9.16 | 1.9.9.16 |  | 2026-04-20 13:00 | p | 935 |  | 2028-11-10 15:58
581 | 6509 | sp3XFaPtGgzrVeC1wvvV | Normal | 10 | 1.9.9.16.3 | 1.9.9.16.3 |  | 2026-05-26 13:00 | p | 931 |  | 2028-12-12 15:12
582 | 6510 | dar9hgzhSUYJxC1MeoTS | Normal | 10 | 1.9.9.16.4 | 1.9.9.16.4 |  | 2026-05-26 13:00 | p | 931 |  | 2028-12-12 13:13
583 | 6513 | IG8fHoH3vjERJ6iSB3Rj | Normal | 36 | 1.9.9.16.5 | 1.9.9.16.5 |  | 2026-06-09 13:00 | p | 933 |  | 2028-12-28 15:13
584 | 6514 | imV319lPgBwI8oLVT5sB | Normal | 1 | 1.9.9.16.2 | 1.9.9.16.2 |  | 2026-05-22 13:00 | p | 934 |  | 2028-12-11 13:54
585 | 6515 | a8Kdm3F6uLeIN4SEhwX9 | Normal | 1 | 1.9.9.16.1 | 1.9.9.16.1 |  | 2026-04-20 13:00 | p | 935 |  | 2028-11-10 15:58
586 | 5783 | BOvEGIzyTacp1vvD9v7M | Normal | 1 | 1.9.9.2 | 1.9.9.2 |  | 2026-01-02 08:00 | p | 26 |  | 2026-01-28 08:39
587 | 6685 | 2nkdQcaVv7LgM8d4dFld | Summary | 1 | 1.9.9.12 | 1.9.9.12 |  | 2025-08-29 08:00 | q | -164 |  | 2025-03-17 11:08
588 | 6687 | RiyOBd4mBIE5Cq6C0A4h | Normal | 1 | 1.9.9.12.1 | 1.9.9.12.1 |  | 2025-08-29 08:00 | q | -164 |  | 2025-03-17 11:08
589 | 7388 | subTjNOw9tjXphx2xXzW | Summary | 324 | 1.9.9.13 | 1.9.9.13 |  | 2025-06-18 08:00 | p | 933 |  | 2028-01-07 16:28
590 | 7389 | xTfJP5JFEqXIDmLDdKVZ | Summary | 43 | 1.9.9.13.1 | 1.9.9.13.1 |  | 2025-06-18 08:00 | p | 933 |  | 2028-01-07 16:28
591 | 7390 | GV26YG775A5KHHrrMIRV | Summary | 32 | 1.9.9.13.1.1 | 1.9.9.13.1.1 |  | 2025-06-18 08:00 | p | 933 |  | 2028-01-07 16:28
592 | 7391 | UumEMUqxjwvZXtHBx1rg | Normal | 3 | 1.9.9.13.1.1.1 | 1.9.9.13.1.1.1 |  | 2025-06-18 08:00 | p | 933 |  | 2028-01-07 16:28
593 | 7392 | ylVP19AJuwY485wgDJEG | Normal | 10 | 1.9.9.13.1.1.2 | 1.9.9.13.1.1.2 |  | 2025-06-24 08:00 | p | 933 |  | 2028-01-13 14:31
594 | 7393 | RzIyrLZKRoqlWdOJYpGf | Normal | 3 | 1.9.9.13.1.1.3 | 1.9.9.13.1.1.3 |  | 2025-07-03 08:00 | p | 935 |  | 2028-01-24 08:24
595 | 7394 | zHoRZ9fggWfe9FGnA954 | Normal | 10 | 1.9.9.13.1.1.4 | 1.9.9.13.1.1.4 |  | 2025-07-09 08:00 | p | 939 |  | 2028-02-03 15:25
596 | 7395 | PMjQe1vYJ6mxUbNABucF | Normal | 3 | 1.9.9.13.1.1.5 | 1.9.9.13.1.1.5 |  | 2025-07-18 08:00 | p | 934 |  | 2028-02-07 14:23
597 | 7396 | gQKdIVV4LZyvHUAfFFFg | Normal | 10 | 1.9.9.13.1.1.6 | 1.9.9.13.1.1.6 |  | 2025-07-23 08:00 | p | 940 |  | 2028-02-18 16:01
598 | 7397 | gmOEJCOmO6SQ6HMlGXfq | Summary | 12 | 1.9.9.13.1.2 | 1.9.9.13.1.2 |  | 2025-08-04 08:00 | p | 931 |  | 2028-02-21 11:14
599 | 7398 | ItOQSxoXEYWD5clVNK0n | Normal | 3 | 1.9.9.13.1.2.1 | 1.9.9.13.1.2.1 |  | 2025-08-04 08:00 | p | 931 |  | 2028-02-21 11:14
600 | 7399 | cXpFrNuZR7O8wPV6KZK3 | Normal | 9 | 1.9.9.13.1.2.2 | 1.9.9.13.1.2.2 |  | 2025-08-07 08:00 | p | 942 |  | 2028-03-06 16:52
601 | 7400 | VGtguPWpaIPmF0Ojsz8a | Summary | 176 | 1.9.9.13.2 | 1.9.9.13.2 |  | 2025-08-05 13:00 | p | 940 |  | 2028-03-03 08:58
602 | 7401 | H3MyBOTVJ4MGxcXcavMD | Normal | 2 | 1.9.9.13.2.1 | 1.9.9.13.2.1 |  | 2025-08-05 13:00 | p | 940 |  | 2028-03-03 08:58
603 | 7402 | pMiEhGou1QDK96DPu7Q8 | Normal | 1 | 1.9.9.13.2.2 | 1.9.9.13.2.2 |  | 2025-08-20 08:00 | p | 943 |  | 2028-03-20 09:05
604 | 7403 | pHZBXvaYVwug2p7gN6jp | Summary | 17 | 1.9.9.13.2.3 | 1.9.9.13.2.3 |  | 2025-08-21 08:00 | p | 943 |  | 2028-03-21 09:16
605 | 7404 | EvHLT3cR3tYYGwcq6SC1 | Normal | 5 | 1.9.9.13.2.3.1 | 1.9.9.13.2.3.1 |  | 2025-08-21 08:00 | p | 943 |  | 2028-03-21 09:16
606 | 7405 | 5GpI6xkgfIoVOnU9egD8 | Normal | 12 | 1.9.9.13.2.3.2 | 1.9.9.13.2.3.2 |  | 2025-08-28 08:00 | p | 943 |  | 2028-03-28 09:50
607 | 7406 | WxzG2sAIbVYYiem4v3mk | Normal | 12 | 1.9.9.13.2.3.3 | 1.9.9.13.2.3.3 |  | 2025-08-28 08:00 | p | 943 |  | 2028-03-28 09:50
608 | 7407 | 0eiyRK1I5mgUCdtpXpqY | Summary | 44 | 1.9.9.13.2.4 | 1.9.9.13.2.4 |  | 2025-09-16 08:00 | p | 939 |  | 2028-04-12 13:04
609 | 7408 | uKngouP2QMMQmu6HFm0I | Normal | 11 | 1.9.9.13.2.4.1 | 1.9.9.13.2.4.1 |  | 2025-09-16 08:00 | p | 939 |  | 2028-04-12 13:04
610 | 7409 | C7eZzAQkBbKewE4wmmOD | Normal | 11 | 1.9.9.13.2.4.2 | 1.9.9.13.2.4.2 |  | 2025-10-01 08:00 | p | 938 |  | 2028-04-26 11:31
611 | 7410 | VCdEPtbQjRcgNUnNprkZ | Normal | 11 | 1.9.9.13.2.4.3 | 1.9.9.13.2.4.3 |  | 2025-10-17 08:00 | p | 936 |  | 2028-05-10 14:48
612 | 7411 | OzHccTXr25Mf4pmiIMuT | Normal | 11 | 1.9.9.13.2.4.4 | 1.9.9.13.2.4.4 |  | 2025-11-03 08:00 | p | 934 |  | 2028-05-25 13:17
613 | 7412 | obz02flxb00pYjKUpMNx | Normal | 12 | 1.9.9.13.2.5 | 1.9.9.13.2.5 |  | 2025-11-26 08:00 | p | 930 |  | 2028-06-13 08:48
614 | 7413 | xazO1XwNp5eROWJmaREL | Summary | 36 | 1.9.9.13.2.6 | 1.9.9.13.2.6 |  | 2025-11-19 08:00 | p | 937 |  | 2028-06-13 08:48
615 | 7414 | DrM34eAIT9imz4vRHbHm | Normal | 2 | 1.9.9.13.2.6.1 | 1.9.9.13.2.6.1 |  | 2025-11-19 08:00 | p | 937 |  | 2028-06-13 08:48
616 | 7415 | RsULMViXRZoYahxlMUQ4 | Normal | 20 | 1.9.9.13.2.6.2 | 1.9.9.13.2.6.2 |  | 2025-11-21 08:00 | p | 937 |  | 2028-06-15 09:53
617 | 7416 | U8irVJqpjJwQWU5FcpMo | Normal | 3 | 1.9.9.13.2.6.3 | 1.9.9.13.2.6.3 |  | 2025-12-22 08:00 | p | 940 |  | 2028-07-19 11:22
618 | 7417 | yrCdbpyUp4mqkbXiv5Nc | Normal | 6 | 1.9.9.13.2.6.4 | 1.9.9.13.2.6.4 |  | 2025-12-26 08:00 | p | 941 |  | 2028-07-24 15:52
619 | 7418 | Iw5sTi596kP8d52cBWYm | Normal | 5 | 1.9.9.13.2.6.5 | 1.9.9.13.2.6.5 |  | 2026-01-06 08:00 | p | 938 |  | 2028-08-01 09:30
620 | 7419 | s9reBpLseCBnslseiKA6 | Normal | 2 | 1.9.9.13.2.7 | 1.9.9.13.2.7 |  | 2026-01-13 08:00 | p | 938 |  | 2028-08-08 14:51
621 | 7420 | ia01m1zWF4qAvVLVg5It | Summary | 54 | 1.9.9.13.2.8 | 1.9.9.13.2.8 |  | 2026-01-15 08:00 | p | 939 |  | 2028-08-11 09:38
622 | 7421 | 5PvQN5TGe8y7KbK2rRhO | Normal | 8 | 1.9.9.13.2.8.1 | 1.9.9.13.2.8.1 |  | 2026-01-15 08:00 | p | 939 |  | 2028-08-11 09:38
623 | 7422 | fj19MvsSAfWHeVGXiA1H | Normal | 5 | 1.9.9.13.2.8.2 | 1.9.9.13.2.8.2 |  | 2026-01-15 08:00 | p | 939 |  | 2028-08-11 09:38
624 | 7423 | hs9Gt4WgG9pENnEIaC7X | Normal | 14 | 1.9.9.13.2.8.3 | 1.9.9.13.2.8.3 |  | 2026-01-28 08:00 | p | 938 |  | 2028-08-23 13:49
625 | 7424 | WqCakGr8mHgCENNWHHjW | Normal | 5 | 1.9.9.13.2.8.4 | 1.9.9.13.2.8.4 |  | 2026-01-28 08:00 | p | 938 |  | 2028-08-23 13:49
626 | 7425 | Pv27HXd826jlfuUJmTLH | Normal | 20 | 1.9.9.13.2.8.5 | 1.9.9.13.2.8.5 |  | 2026-02-18 08:00 | p | 938 |  | 2028-09-13 10:12
627 | 7426 | UjcYgNHyPV73fWy2GGNA | Normal | 5 | 1.9.9.13.2.8.6 | 1.9.9.13.2.8.6 |  | 2026-02-18 08:00 | p | 938 |  | 2028-09-13 10:12
628 | 7427 | 5QMAV8W19uO0knxuRgYc | Normal | 6 | 1.9.9.13.2.8.7 | 1.9.9.13.2.8.7 |  | 2026-03-18 08:00 | p | 936 |  | 2028-10-09 10:02
629 | 7428 | C3roUkJ3GEdxAvfnxnUE | Normal | 6 | 1.9.9.13.2.8.8 | 1.9.9.13.2.8.8 |  | 2026-03-18 08:00 | p | 936 |  | 2028-10-09 10:02
630 | 7429 | GMfJSktlv5oUXA5LFNgA | Normal | 6 | 1.9.9.13.2.8.9 | 1.9.9.13.2.8.9 |  | 2026-03-26 08:00 | p | 937 |  | 2028-10-18 08:20
631 | 7430 | AjX0fOJfuCWTWcoFWrZe | Summary | 11 | 1.9.9.13.2.9 | 1.9.9.13.2.9 |  | 2026-04-03 08:00 | p | 935 |  | 2028-10-24 13:16
632 | 7431 | YKkcKAxBNBkRs3Gs0cxp | Normal | 7 | 1.9.9.13.2.9.1 | 1.9.9.13.2.9.1 |  | 2026-04-03 08:00 | p | 935 |  | 2028-10-24 13:16
633 | 7432 | HbmHLQTrqR87hE03VIdq | Normal | 3 | 1.9.9.13.2.9.2 | 1.9.9.13.2.9.2 |  | 2026-04-03 08:00 | p | 935 |  | 2028-10-24 13:16
634 | 7433 | FxBsJSw4ZNEIyIQA8bL9 | Normal | 8 | 1.9.9.13.2.9.3 | 1.9.9.13.2.9.3 |  | 2026-04-08 08:00 | p | 933 |  | 2028-10-27 11:33
635 | 7434 | MkjgnYEnwrIrITdXMEl9 | Milestone | 0 | 1.9.9.13.3 | 1.9.9.13.3 |  | 2026-07-31 12:00 | p | 929 |  | 2029-02-14 13:47
636 | 7435 | nSo6tYchIu2Aw4YtE45u | Summary | 44 | 1.9.9.13.4 | 1.9.9.13.4 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
637 | 7436 | Y83lvWkQwfsc3dMGwfVN | Summary | 30 | 1.9.9.13.4.1 | 1.9.9.13.4.1 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
638 | 7437 | E8EwVgjFQaEPGP66WsCb | Summary | 30 | 1.9.9.13.4.1.1 | 1.9.9.13.4.1.1 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
639 | 7438 | y2P0mgWq1uFkM4aVxtQJ | Normal | 15 | 1.9.9.13.4.1.1.1 | 1.9.9.13.4.1.1.1 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
640 | 7439 | nsJKxwZOWJc3LdYsNOwr | Normal | 5 | 1.9.9.13.4.1.1.2 | 1.9.9.13.4.1.1.2 |  | 2026-08-21 13:00 | p | 926 |  | 2029-03-05 08:26
641 | 7440 | 3ZzL4TktDwncii0hY2dA | Normal | 10 | 1.9.9.13.4.1.1.3 | 1.9.9.13.4.1.1.3 |  | 2026-08-28 13:00 | p | 924 |  | 2029-03-09 14:27
642 | 7441 | IcgrxiRjEYJLwuugm8N7 | Summary | 30 | 1.9.9.13.4.1.2 | 1.9.9.13.4.1.2 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
643 | 7442 | B8zfbswYxyRxHa21jaE6 | Normal | 15 | 1.9.9.13.4.1.2.1 | 1.9.9.13.4.1.2.1 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
644 | 7443 | lvFKaF8Jtq8DkkB0s9nv | Normal | 15 | 1.9.9.13.4.1.2.2 | 1.9.9.13.4.1.2.2 |  | 2026-08-21 13:00 | p | 929 |  | 2029-03-08 09:14
645 | 7444 | 419IszMaZW6XNIQptprk | Normal | 20 | 1.9.9.13.4.1.3 | 1.9.9.13.4.1.3 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
646 | 7445 | oNfFp4VAwKEpoSujTbHZ | Normal | 10 | 1.9.9.13.4.1.4 | 1.9.9.13.4.1.4 |  | 2026-07-31 13:00 | p | 929 |  | 2029-02-14 13:47
647 | 7446 | NnBZUSVumxDXwVdCLN8g | Summary | 12 | 1.9.9.13.4.2 | 1.9.9.13.4.2 |  | 2026-09-14 13:00 | p | 928 |  | 2029-03-30 14:22
648 | 7447 | CAsJ3atkVCS14hehUB9Y | Normal | 4 | 1.9.9.13.4.2.1 | 1.9.9.13.4.2.1 |  | 2026-09-14 13:00 | p | 928 |  | 2029-03-30 14:22
649 | 7448 | 8tMCh2h8AwE53TPPkfEv | Normal | 3 | 1.9.9.13.4.2.2 | 1.9.9.13.4.2.2 |  | 2026-09-16 13:00 | p | 929 |  | 2029-04-03 11:47
650 | 7449 | LaZxXVdUnGzqswRGUiV5 | Normal | 7 | 1.9.9.13.4.2.3 | 1.9.9.13.4.2.3 |  | 2026-09-21 13:00 | p | 928 |  | 2029-04-06 13:07
651 | 7450 | F3vtt1T8lz7mQWFPgUKT | Normal | 2 | 1.9.9.13.4.3 | 1.9.9.13.4.3 |  | 2026-09-30 13:00 | p | 930 |  | 2029-04-17 15:30
652 | 7451 | nShmtMdGhMi3SzNeAZjW | Milestone | 0 | 1.9.9.13.4.4 | 1.9.9.13.4.4 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
653 | 7510 | 4i5VLTIa98HteWhFzYjv | Normal | 3 | 1.7.10.24 | 1.7.10.24 |  | 2025-06-13 08:00 | p | 936 |  | 2028-01-05 08:46
654 | 7511 | tHPdmsBqm9kHM69dtq3h | Normal | 7 | 1.7.10.25 | 1.7.10.25 |  | 2025-06-24 08:00 | p | 933 |  | 2028-01-13 08:07
655 | 7512 | hmOTDv9qQbSDcHudIm9x | Normal | 7 | 1.7.10.26 | 1.7.10.26 |  | 2025-07-09 08:00 | p | 932 |  | 2028-01-27 11:46
656 | 7513 | NbiRgc4Tdvxa900kw7Xq | Normal | 8 | 1.7.10.27 | 1.7.10.27 |  | 2025-07-23 08:00 | p | 932 |  | 2028-02-10 13:38
657 | 7539 | ROucR7pug9aGzObG8pvW | Normal | 1 | 1.7.10.8 | 1.7.10.8 |  | 2025-02-28 08:00 | q | -571 |  | 2023-08-07 08:00
658 | 7540 | njszlznNRnCyRW2hgoMI | Normal | 10 | 1.7.10.9 | 1.7.10.9 |  | 2025-03-03 08:00 | q | -572 |  | 2023-08-08 08:37
659 | 7541 | R63tw5xkvmDGiWpIPQRa | Normal | 1 | 1.7.10.10 | 1.7.10.10 |  | 2025-03-31 08:00 | q | -602 |  | 2023-08-07 08:00
660 | 7542 | E3YdLEfamF0eZCISJiqw | Normal | 10 | 1.7.10.11 | 1.7.10.11 |  | 2025-04-14 08:00 | q | -616 |  | 2023-08-07 08:00
661 | 7543 | nhpJxewK7uClQLzGXJQJ | Normal | 1 | 1.7.10.12 | 1.7.10.12 |  | 2025-05-30 08:00 | q | -662 |  | 2023-08-07 08:00
662 | 7544 | cfuUTFyz3WOPAOOiNQOb | Normal | 1 | 1.7.10.13 | 1.7.10.13 |  | 2025-05-30 08:00 | q | -662 |  | 2023-08-07 08:00
663 | 6279 | p7EJXT1muDSglD2OZLFH | Summary | 274 | 1.9.7 | 1.9.7 |  | 2022-03-07 08:00 | q | -1734 |  | 2017-06-07 08:00
664 | 1484 | 6ARiGRg3KLswRpJLOmGD | Summary | 229 | 1.9.7.18 | 1.9.7.18 |  | 2023-10-24 08:00 | q | -2330 |  | 2017-06-07 08:00
665 | 1485 | R0QJsNVi0JzXq4FadBdS | Normal | 20 | 1.9.7.18.4 | 1.9.7.18.4 |  | 2025-06-18 08:00 | q | -2819 |  | 2017-09-28 08:18
666 | 1486 | 9VYbXOz4xuMas0igEBkB | Summary | 56 | 1.9.7.18.6 | 1.9.7.18.6 |  | 2025-08-15 08:00 | q | -2810 |  | 2017-12-04 08:30
667 | 6540 | BF294XdCZHw2CEg81bOs | Normal | 19 | 1.9.7.18.6.1 | 1.9.7.18.6.1 |  | 2025-08-15 08:00 | q | -2810 |  | 2017-12-04 08:30
668 | 6541 | X8phwYugZBkIbn0OysQW | Normal | 19 | 1.9.7.18.6.2 | 1.9.7.18.6.2 |  | 2025-09-12 08:00 | q | -2814 |  | 2017-12-28 16:20
669 | 6542 | fphO3nZhiS43G9CLfKfB | Normal | 18 | 1.9.7.18.6.3 | 1.9.7.18.6.3 |  | 2025-10-09 08:00 | q | -2809 |  | 2018-01-29 14:01
670 | 1490 | hF9FI1LNvFfgTTXhqPsR | Normal | 77 | 1.9.7.18.2 | 1.9.7.18.2 |  | 2025-02-27 08:00 | q | -2822 |  | 2017-06-07 08:00
671 | 1491 | XpTPefWn9TT3C06gw8rA | Normal | 1 | 1.9.7.18.3 | 1.9.7.18.3 |  | 2025-06-17 08:00 | q | -2820 |  | 2017-09-26 16:07
672 | 1495 | 0kid3Dd3U5gCQNrt2pwY | Normal | 1 | 1.9.7.18.8 | 1.9.7.18.8 |  | 2025-02-26 08:00 | q | -23 |  | 2025-02-03 08:00
673 | 1504 | ndaml8HRsqEWzWIKrI7h | Normal | 5 | 1.9.7.18.10 | 1.9.7.18.10 |  | 2025-02-26 08:00 | q | -23 |  | 2025-02-03 08:00
674 | 4587 | 5uS9ktvplxYkrLheR3Q9 | Normal | 20 | 1.9.7.18.5 | 1.9.7.18.5 |  | 2025-07-18 08:00 | q | -2820 |  | 2017-10-27 15:51
675 | 1496 | 5t2MhilpkZRDQA3VTcGS | Normal | 48 | 1.9.7.7 | 1.9.7.7 |  | 2025-02-27 08:00 | q | -22 |  | 2025-02-04 08:47
676 | 1505 | 4c3z8pWafVxAWNC1MpC9 | Normal | 106 | 1.9.7.8 | 1.9.7.8 |  | 2025-03-05 08:00 | q | -22 |  | 2025-02-10 11:29
677 | 1531 | KX1eD2ASIZaZBZuqoVp4 | Normal | 1 | 1.9.7.14.2 | 1.9.7.14.2 |  | 2025-05-01 08:00 | q | -192 |  | 2024-10-21 08:00
678 | 1532 | fQ3wcWF8uEWMRGpUCxEA | Normal | 1 | 1.9.7.14.4 | 1.9.7.14.4 |  | 2025-05-07 08:00 | q | -18 |  | 2025-04-18 16:03
679 | 1533 | juvdtwZkjArAkPOzLrhN | Normal | 15 | 1.9.7.14.5 | 1.9.7.14.5 |  | 2025-06-10 08:00 | p | 13 |  | 2025-06-23 16:18
680 | 1534 | SuchbNnj1ndABAEPQlrb | Normal | 10 | 1.9.7.14.6 | 1.9.7.14.6 |  | 2025-07-02 08:00 | p | 14 |  | 2025-07-16 10:48
681 | 4583 | QzcCl72pVAI4zSVR8VAE | Normal | 1 | 1.9.7.14.3 | 1.9.7.14.3 |  | 2025-05-02 08:00 | q | -191 |  | 2024-10-22 08:07
682 | 1538 | 1Xm6i4dPIyAKJzF1jRtD | Normal | 45 | 1.9.7.15.3 | 1.9.7.15.3 |  | 2025-02-18 08:00 | p | 27 |  | 2025-03-17 16:37
683 | 1541 | ss8yD9dhZfTIp9UxqHnG | Normal | 1 | 1.9.7.15.7 | 1.9.7.15.7 |  | 2025-04-22 08:00 | p | 29 |  | 2025-05-21 11:41
684 | 1542 | VmFPpoMfVfLEXeRBF7Um | Normal | 9 | 1.9.7.15.8 | 1.9.7.15.8 |  | 2025-04-23 08:00 | p | 29 |  | 2025-05-22 10:13
685 | 1543 | P2oxmSB7jXG6Ib9VEZ89 | Normal | 9 | 1.9.7.15.9 | 1.9.7.15.9 |  | 2025-05-06 08:00 | p | 29 |  | 2025-06-04 09:43
686 | 1547 | K0gsOWDMqaySswr72BAQ | Normal | 1 | 1.9.7.16.3 | 1.9.7.16.3 |  | 2025-02-21 08:00 | q | -361 |  | 2024-02-26 08:00
687 | 1548 | 4jCrHn72KCapTPEI9TzQ | Normal | 2 | 1.9.7.16.5 | 1.9.7.16.5 |  | 2025-02-25 08:00 | q | -362 |  | 2024-02-28 08:10
688 | 1549 | s8gTUDwRZFDpCO4enZqk | Normal | 15 | 1.9.7.16.6 | 1.9.7.16.6 |  | 2025-02-27 08:00 | q | -362 |  | 2024-03-01 08:50
689 | 1550 | UoQFPyMNVa9QPyq2kgrl | Normal | 9 | 1.9.7.16.7 | 1.9.7.16.7 |  | 2025-03-20 08:00 | q | -5 |  | 2025-03-14 09:48
690 | 4586 | kRWFuIGKur6ToFmAr9JC | Normal | 1 | 1.9.7.16.4 | 1.9.7.16.4 |  | 2025-02-24 08:00 | q | -362 |  | 2024-02-27 08:41
691 | 1562 | lBuCdKTmKHrCdvS4FVbB | Normal | 40 | 1.9.7.19.12 | 1.9.7.19.12 |  | 2025-02-26 08:00 | p | 1 |  | 2025-02-27 13:07
692 | 1563 | TUxQ6kz9ittb2zcmlLCL | Normal | 10 | 1.9.7.19.13 | 1.9.7.19.13 |  | 2025-04-23 08:00 | p | 1 |  | 2025-04-24 15:44
693 | 1564 | OkMyUpJo7fqJaif9Jvyb | Normal | 5 | 1.9.7.19.14 | 1.9.7.19.14 |  | 2025-05-07 08:00 | p | 1 |  | 2025-05-08 11:23
694 | 1565 | 9BGxipQLCi4kED7E7faW | Normal | 4 | 1.9.7.19.15 | 1.9.7.19.15 |  | 2025-05-14 08:00 | p | 1 |  | 2025-05-15 09:42
695 | 4572 | 5hxJeLGqqaIlIue4XwRC | Normal | 1 | 1.9.7.2 | 1.9.7.2 |  | 2025-03-21 08:00 | p | 27 |  | 2025-04-17 16:18
696 | 1497 | q56IdotBOPeXlK3605d6 | Normal | 1 | 1.9.7.11.4 | 1.9.7.11.4 |  | 2025-05-06 08:00 | q | -20 |  | 2025-04-15 16:33
697 | 1506 | zNKWNUMZ7wFR6LBQ8bZ2 | Normal | 1 | 1.9.7.11.5 | 1.9.7.11.5 |  | 2025-08-05 08:00 | q | -27 |  | 2025-07-08 16:49
698 | 1509 | xdWSZU8MxGE52WBHNu6X | Normal | 1 | 1.9.7.11.3 | 1.9.7.11.3 |  | 2025-03-25 08:00 | p | 23 |  | 2025-04-17 10:54
699 | 6440 | u5F2XJPKXxmZ5m99Yx5A | Normal | 1 | 1.9.7.11.7 | 1.9.7.11.7 |  | 2025-04-30 08:00 | q | -5 |  | 2025-04-24 11:28
700 | 4575 | nPe6rBdPLk408ntp39jn | Normal | 1 | 1.9.7.3 | 1.9.7.3 |  | 2025-06-06 08:00 | q | -669 |  | 2023-08-07 08:00
701 | 4578 | kBeLaux8MTugqoi5KPvZ | Summary | 74 | 1.9.7.13 | 1.9.7.13 |  | 2025-04-02 08:00 | q | -6 |  | 2025-03-26 11:36
702 | 1462 | 2Cc6AJ3gtv1XGHwG4F9W | Normal | 1 | 1.9.7.13.3 | 1.9.7.13.3 |  | 2025-04-07 08:00 | p | 24 |  | 2025-05-01 16:08
703 | 1518 | qXbL36bdYftxHm1TCntK | Normal | 1 | 1.9.7.13.4 | 1.9.7.13.4 |  | 2025-07-17 08:00 | p | 13 |  | 2025-07-30 16:47
704 | 4579 | xoTCeJS6YwjvMvm1YAvH | Normal | 1 | 1.9.7.13.2 | 1.9.7.13.2 |  | 2025-05-19 08:00 | p | 32 |  | 2025-06-20 10:23
705 | 4580 | llDwDvQQbSyeeXMs3M2a | Normal | 1 | 1.9.7.13.1 | 1.9.7.13.1 |  | 2025-04-02 08:00 | q | -6 |  | 2025-03-26 11:36
706 | 4588 | L1kgBhMEjlIJ4HNHh1TQ | Summary | 141 | 1.9.7.20 | 1.9.7.20 |  | 2025-05-20 08:00 | p | 1 |  | 2025-05-21 11:08
707 | 1566 | KFj0hxHWvExDoqTqgDeg | Normal | 118 | 1.9.7.20.1 | 1.9.7.20.1 |  | 2025-05-20 08:00 | p | 1 |  | 2025-05-21 11:08
708 | 1567 | GV5or0ucuouXZiqAkH0N | Normal | 10 | 1.9.7.20.2 | 1.9.7.20.2 |  | 2025-11-07 08:00 | q | 0 |  | 2025-11-06 08:08
709 | 1568 | JI4xSRBKV4FYnRXdw7Wz | Normal | 9 | 1.9.7.20.3 | 1.9.7.20.3 |  | 2025-11-24 08:00 | p | 0 |  | 2025-11-24 13:31
710 | 1569 | DVuFJt4FGQSIgeZkA41d | Normal | 4 | 1.9.7.20.4 | 1.9.7.20.4 |  | 2025-12-08 08:00 | q | -2 |  | 2025-12-05 10:32
711 | 4590 | 21lrGsmJiPqRYOd4yY3H | Summary | 2 | 1.9.7.21 | 1.9.7.21 |  | 2026-09-14 13:00 | p | 928 |  | 2029-03-30 14:22
712 | 1570 | 9hmrS48cr19KgrseY4yN | Normal | 2 | 1.9.7.21.1 | 1.9.7.21.1 |  | 2026-09-14 13:00 | p | 928 |  | 2029-03-30 14:22
713 | 7455 | hQlezwT73UjuGPZkyuVr | Normal | 9 | 1.7.8.18.2 | 1.7.8.18.2 |  | 2025-02-18 08:00 | p | 28 |  | 2025-03-18 09:56
714 | 7456 | 3cfjdZ38xGBNf8roD7He | Normal | 9 | 1.7.8.18.3 | 1.7.8.18.3 |  | 2025-03-03 08:00 | p | 25 |  | 2025-03-28 10:02
715 | 7457 | abNwDWOnFoe0xwhiRueS | Normal | 1 | 1.7.8.18.4 | 1.7.8.18.4 |  | 2025-03-19 08:00 | p | 21 |  | 2025-04-09 14:59
716 | 7458 | cMhUMuxC0sax27543As7 | Normal | 24 | 1.7.8.18.5 | 1.7.8.18.5 |  | 2025-04-07 08:00 | p | 3 |  | 2025-04-10 14:30
717 | 7459 | xf7OMyoiQ38QdcweBYiq | Normal | 20 | 1.7.8.18.6 | 1.7.8.18.6 |  | 2025-05-09 08:00 | p | 7 |  | 2025-05-16 10:07
718 | 7324 | GVXYroUMjcAFUHa4B19H | Normal | 1 | 1.7.8.19 | 1.7.8.19 |  | 2025-03-28 08:00 | q | -555 |  | 2023-09-20 08:00
719 | 7325 | wl82vK5NXqnnsHIySTFp | Normal | 1 | 1.7.8.20 | 1.7.8.20 |  | 2025-06-09 08:00 | p | 11 |  | 2025-06-20 15:38
720 | 7382 | GJk3wpkfagyrb21gVciV | Summary | 288 | 1.9.7.22 | 1.9.7.22 |  | 2025-02-26 08:00 | q | -569 |  | 2023-08-07 08:00
721 | 7383 | chM988R4AoJxJINOHhOy | Normal | 1 | 1.9.7.22.1 | 1.9.7.22.1 |  | 2025-02-26 08:00 | q | -569 |  | 2023-08-07 08:00
722 | 7384 | xn1TRUhUfNd3ygHlAMk1 | Normal | 16 | 1.9.7.22.2 | 1.9.7.22.2 |  | 2025-02-27 08:00 | q | -569 |  | 2023-08-07 16:42
723 | 7385 | cYlWo9e2zkkP7jtt7iLZ | Normal | 1 | 1.9.7.22.3 | 1.9.7.22.3 |  | 2025-03-21 08:00 | q | -575 |  | 2023-08-23 16:37
724 | 7386 | F9n9tFj3S3xXbwXNgAjU | Normal | 5 | 1.9.7.22.4 | 1.9.7.22.4 |  | 2026-04-14 08:00 | p | 933 |  | 2028-11-02 14:33
725 | 4594 | EUFkYGsAZWO3vgZroOTA | Normal | 1 | 1.9.1.2 | 1.9.1.2 |  | 2025-07-02 08:00 | p | 19 |  | 2025-07-21 08:37
726 | 4595 | 0i30zTvKTrSo3R9n999e | Normal | 2 | 1.9.1.3 | 1.9.1.3 |  | 2025-07-03 08:00 | p | 19 |  | 2025-07-22 08:41
727 | 4606 | e1c7TqZJ2saEXqSPx9Ca | Normal | 1 | 1.7.3.3 | 1.7.3.3 |  | 2025-05-27 08:00 | p | 31 |  | 2025-06-27 15:19
728 | 4607 | 9Rf8xh1sYqA0mX8AIEgx | Summary | 52 | 1.7.3.5 | 1.7.3.5 |  | 2025-08-04 08:00 | p | 35 |  | 2025-09-08 13:07
729 | 4608 | tlJeJHdE7OwhwWyVvZ8P | Normal | 5 | 1.7.3.5.1 | 1.7.3.5.1 |  | 2025-08-04 08:00 | p | 35 |  | 2025-09-08 13:07
730 | 4609 | PoeQu0I6Io83IRbk7WtS | Normal | 5 | 1.7.3.5.2 | 1.7.3.5.2 |  | 2025-08-11 08:00 | p | 32 |  | 2025-09-12 13:59
731 | 4610 | UGUZlny6Ut8S0mLRTL2X | Normal | 1 | 1.7.3.5.3 | 1.7.3.5.3 |  | 2025-08-18 08:00 | p | 32 |  | 2025-09-19 14:20
732 | 4611 | 1TZOFiOcsBCmkfhi03Iw | Normal | 5 | 1.7.3.5.4 | 1.7.3.5.4 |  | 2025-08-26 08:00 | p | 34 |  | 2025-09-29 13:08
733 | 4612 | ZwEXlYv6PrV1t0gzfqom | Normal | 10 | 1.7.3.5.5 | 1.7.3.5.5 |  | 2025-09-03 08:00 | p | 33 |  | 2025-10-06 11:44
734 | 4613 | z0DGpsje53b33zXA5t1P | Normal | 20 | 1.7.3.5.6 | 1.7.3.5.6 |  | 2025-09-17 08:00 | p | 34 |  | 2025-10-21 10:58
735 | 4614 | cqs4HA7sR83mroZvcBiw | Normal | 1 | 1.7.3.5.7 | 1.7.3.5.7 |  | 2025-10-16 08:00 | p | 29 |  | 2025-11-14 09:46
736 | 4618 | mRqsjEijsp2iSp4l7aof | Normal | 5 | 1.7.3.4.3 | 1.7.3.4.3 |  | 2025-02-18 08:00 | p | 28 |  | 2025-03-18 11:06
737 | 4619 | 8asUr7UOO8nabPagFvw9 | Normal | 40 | 1.7.3.4.4 | 1.7.3.4.4 |  | 2025-02-18 08:00 | p | 28 |  | 2025-03-18 11:06
738 | 4620 | UWR5akRFo4eKiDyQVnYr | Normal | 23 | 1.7.3.4.5 | 1.7.3.4.5 |  | 2025-02-18 08:00 | p | 22 |  | 2025-03-12 11:53
739 | 4621 | pGB9dynKUfIMuzj3AWVv | Normal | 1 | 1.7.3.4.6 | 1.7.3.4.6 |  | 2025-05-28 08:00 | p | 33 |  | 2025-06-30 15:35
740 | 4622 | Bm2ajkWBwO6Cvc6RoPdK | Normal | 5 | 1.7.3.4.7 | 1.7.3.4.7 |  | 2025-05-29 08:00 | p | 33 |  | 2025-07-01 14:45
741 | 4623 | sDTQ4X48dvup817zb0Do | Normal | 20 | 1.7.3.4.8 | 1.7.3.4.8 |  | 2025-06-05 08:00 | p | 36 |  | 2025-07-11 16:20
742 | 4624 | 3CGv61AS00FFpM5LrRat | Normal | 20 | 1.7.3.4.9 | 1.7.3.4.9 |  | 2025-07-07 08:00 | p | 35 |  | 2025-08-11 16:17
743 | 4625 | NkJyZ342jkgJkVCalD4F | Normal | 2 | 1.7.3.4.10 | 1.7.3.4.10 |  | 2025-08-04 08:00 | p | 35 |  | 2025-09-08 13:07
744 | 4631 | EXJQS9o5Eq3lGkaYsCap | Normal | 1 | 1.7.3.6.5 | 1.7.3.6.5 |  | 2025-02-18 08:00 | p | 27 |  | 2025-03-17 08:01
745 | 4632 | VGp2Ji3lCAas2O4B01f5 | Normal | 1 | 1.7.3.6.6 | 1.7.3.6.6 |  | 2025-02-19 08:00 | p | 26 |  | 2025-03-17 16:23
746 | 4633 | STHfhyBuM5qFiEzHSgws | Normal | 19 | 1.7.3.6.7 | 1.7.3.6.7 |  | 2025-02-20 08:00 | p | 26 |  | 2025-03-18 16:09
747 | 4634 | cbBLoWE0dwfwOCS04ga7 | Normal | 15 | 1.7.3.6.8 | 1.7.3.6.8 |  | 2025-03-19 08:00 | p | 22 |  | 2025-04-10 09:43
748 | 4635 | vrd0V7BeylNxhzgI26F9 | Normal | 8 | 1.7.3.6.11 | 1.7.3.6.11 |  | 2025-04-10 08:00 | p | 22 |  | 2025-05-02 09:31
749 | 4636 | DgPDbwa39NNm3em6lmtZ | Normal | 1 | 1.7.3.6.12 | 1.7.3.6.12 |  | 2025-11-28 08:00 | p | 21 |  | 2025-12-19 09:31
750 | 4663 | X9pjxOrdX8ZwQAfQziSu | Normal | 1 | 1.7.3.6.9 | 1.7.3.6.9 |  | 2025-04-09 08:00 | p | 22 |  | 2025-05-01 09:46
751 | 4664 | DAxARpEpHAwipBCK81bc | Normal | 8 | 1.7.3.6.10 | 1.7.3.6.10 |  | 2025-04-10 08:00 | p | 22 |  | 2025-05-02 09:31
752 | 7259 | Dcjo2uskRMoBajU90pQq | Normal | 60 | 1.7.1.4 | 1.7.1.4 |  | 2025-03-03 08:00 | p | 29 |  | 2025-04-01 09:25
753 | 3777 | YuGKQIQDxLVYRZzgUQjw | Normal | 9 | 1.7.1.2.6.4 | 1.7.1.2.6.4 |  | 2025-03-27 08:00 | p | 29 |  | 2025-04-25 15:31
754 | 6138 | EvFVoaLHb5OgszmS4Hdy | Summary | 44 | 1.7.1.3.9 | 1.7.1.3.9 |  | 2025-04-01 08:00 | p | 28 |  | 2025-04-29 15:49
755 | 6139 | VECMPYMi2oWf71g3eai1 | Normal | 29 | 1.7.1.3.9.1 | 1.7.1.3.9.1 |  | 2025-04-01 08:00 | p | 28 |  | 2025-04-29 15:49
756 | 6140 | mO0F0FFUdRVKYlb84WcT | Normal | 15 | 1.7.1.3.9.2 | 1.7.1.3.9.2 |  | 2025-05-12 08:00 | p | 25 |  | 2025-06-06 16:23
757 | 6978 | z4sj2SQJw3pdZet8Am0U | Normal | 9 | 1.7.1.3.5 | 1.7.1.3.5 |  | 2025-03-10 08:00 | p | 22 |  | 2025-04-01 13:07
758 | 6985 | eGeEyEDP9xa0SwHKf7WR | Normal | 7 | 1.7.1.3.7.4 | 1.7.1.3.7.4 |  | 2025-03-03 08:00 | p | 29 |  | 2025-04-01 13:07
759 | 6986 | 31qYZ6wVIReV9ZOAqgem | Summary | 9 | 1.7.1.3.7.5 | 1.7.1.3.7.5 |  | 2025-03-12 08:00 | p | 29 |  | 2025-04-10 09:59
760 | 6987 | 50so1NYgvDTnEeNkdrjv | Normal | 3 | 1.7.1.3.7.5.1 | 1.7.1.3.7.5.1 |  | 2025-03-12 08:00 | p | 29 |  | 2025-04-10 09:59
761 | 6988 | bmsC3uFxKZ3RPA57Ivjb | Normal | 3 | 1.7.1.3.7.5.2 | 1.7.1.3.7.5.2 |  | 2025-03-17 08:00 | p | 28 |  | 2025-04-14 16:39
762 | 6989 | okOYULy0nclsZMYhl4sg | Normal | 3 | 1.7.1.3.7.5.3 | 1.7.1.3.7.5.3 |  | 2025-03-20 08:00 | p | 29 |  | 2025-04-18 11:00
763 | 7184 | gKjyagqR1BEsAZjZk4l5 | Milestone | 0 | 1.7.1.3.7.3 | 1.7.1.3.7.3 |  | 2025-02-28 08:00 | q | -29 |  | 2025-01-30 08:00
764 | 6990 | K8cvVDryBsyahUujiNmr | Summary | 22 | 1.7.1.3.8 | 1.7.1.3.8 |  | 2025-02-28 08:00 | q | -29 |  | 2025-01-30 08:00
765 | 6136 | bVRB0EhNo1xoyHBU8R0I | Normal | 1 | 1.7.1.3.8.2 | 1.7.1.3.8.2 |  | 2025-03-21 08:00 | p | 26 |  | 2025-04-16 09:22
766 | 6982 | E06yVWmTg8kRS6Gv9kOV | Summary | 6 | 1.7.1.3.8.3 | 1.7.1.3.8.3 |  | 2025-03-24 08:00 | p | 24 |  | 2025-04-17 09:11
767 | 6137 | gagQpjsDXV4QnJ1bUthb | Normal | 2 | 1.7.1.3.8.3.1 | 1.7.1.3.8.3.1 |  | 2025-03-24 08:00 | p | 24 |  | 2025-04-17 09:11
768 | 6979 | ZYA6dvbLVog9FL6DNJRb | Normal | 5 | 1.7.1.3.8.3.2 | 1.7.1.3.8.3.2 |  | 2025-03-25 08:00 | p | 29 |  | 2025-04-23 10:16
769 | 6991 | RAhO7UtYgqwLkhTknwrO | Normal | 6 | 1.7.1.3.8.1 | 1.7.1.3.8.1 |  | 2025-02-28 08:00 | q | -29 |  | 2025-01-30 08:00
770 | 3810 | CJxWy7PnZPcI4EPHEeme | Normal | 9 | 1.7.1.5.3.2 | 1.7.1.5.3.2 |  | 2025-03-04 08:00 | p | 28 |  | 2025-04-01 15:07
771 | 3811 | wGtgxCT3lCK6u2EOL8xN | Normal | 5 | 1.7.1.5.3.3 | 1.7.1.5.3.3 |  | 2025-03-17 08:00 | p | 24 |  | 2025-04-10 11:21
772 | 3813 | sYeTNUsya13QYMbMJg21 | Normal | 25 | 1.7.1.5.7 | 1.7.1.5.7 |  | 2025-02-28 08:00 | p | 28 |  | 2025-03-28 13:11
773 | 3814 | c3HTuVFoRVefrW72mxSE | Normal | 3 | 1.7.1.5.8 | 1.7.1.5.8 |  | 2025-04-08 08:00 | p | 52 |  | 2025-05-30 10:39
774 | 3815 | nJJAkVwt0aHLNZMMtbkw | Normal | 3 | 1.7.1.5.9 | 1.7.1.5.9 |  | 2025-04-04 08:00 | p | 31 |  | 2025-05-05 11:31
775 | 3816 | 6MWmVgC0FSCF3lMoTGjJ | Summary | 40 | 1.7.1.5.10 | 1.7.1.5.10 |  | 2025-04-09 08:00 | p | 29 |  | 2025-05-08 08:56
776 | 3817 | LqjKPVRVNU7j1iAlkL3t | Normal | 2 | 1.7.1.5.10.1 | 1.7.1.5.10.1 |  | 2025-04-09 08:00 | p | 29 |  | 2025-05-08 08:56
777 | 3818 | Cmm1EfLtBPedDjXV8dAv | Normal | 5 | 1.7.1.5.10.2 | 1.7.1.5.10.2 |  | 2025-04-11 08:00 | p | 31 |  | 2025-05-12 09:26
778 | 3819 | FSVjbKFfUmqE2fpbGGPv | Normal | 3 | 1.7.1.5.10.3 | 1.7.1.5.10.3 |  | 2025-04-18 08:00 | p | 31 |  | 2025-05-19 08:29
779 | 3820 | FhKtXXrOwkDfPm4RFzRW | Normal | 10 | 1.7.1.5.10.4 | 1.7.1.5.10.4 |  | 2025-04-23 08:00 | p | 42 |  | 2025-06-04 10:07
780 | 3821 | cHjYAw102skS4vR6DXqX | Normal | 20 | 1.7.1.5.10.5 | 1.7.1.5.10.5 |  | 2025-05-07 08:00 | p | 44 |  | 2025-06-20 10:34
781 | 4131 | 3WZTLr4e3INGux4LMgj0 | Summary | 146 | 1.9.6.10.2 | 1.9.6.10.2 |  | 2025-03-03 17:00 | p | 927 |  | 2027-09-17 14:49
782 | 5857 | g9TizAnooUcHoXglcd4n | Milestone | 0 | 1.9.6.10.2.1 | 1.9.6.10.2.1 |  | 2025-07-25 17:00 | p | 906 |  | 2028-01-18 08:48
783 | 5858 | 9N3N0HBhBeb82jbbU7Vx | Milestone | 0 | 1.9.6.10.2.2 | 1.9.6.10.2.2 |  | 2025-03-03 17:00 | p | 927 |  | 2027-09-17 14:49
784 | 5859 | RMhsXtyk4773BtipN2HO | Normal | 1 | 1.9.6.10.2.3 | 1.9.6.10.2.3 |  | 2025-03-04 08:00 | p | 927 |  | 2027-09-17 14:49
785 | 5860 | AMUT2hrMeOWSIoK5dO6S | Normal | 10 | 1.9.6.10.2.4 | 1.9.6.10.2.4 |  | 2025-05-05 08:00 | p | 868 |  | 2027-09-20 14:29
786 | 5861 | adMwYb1cwVT0ja23ZKPV | Normal | 10 | 1.9.6.10.2.5 | 1.9.6.10.2.5 |  | 2025-05-19 08:00 | p | 868 |  | 2027-10-04 10:58
787 | 5862 | rkVKH7eSVnkv5Rz0hIbo | Normal | 25 | 1.9.6.10.2.6 | 1.9.6.10.2.6 |  | 2025-06-03 08:00 | p | 864 |  | 2027-10-15 15:33
788 | 5863 | axx1H8vuWtNbWz6aJYpW | Normal | 20 | 1.9.6.10.2.7 | 1.9.6.10.2.7 |  | 2025-07-10 08:00 | p | 868 |  | 2027-11-25 10:07
789 | 5864 | ZuXAUp7kzm7PDgs0Clm4 | Normal | 20 | 1.9.6.10.2.8 | 1.9.6.10.2.8 |  | 2025-08-07 08:00 | p | 873 |  | 2027-12-28 09:23
790 | 5865 | pfx92tyIHO0nDV8Eg4vj | Normal | 3 | 1.9.6.10.2.9 | 1.9.6.10.2.9 |  | 2025-09-05 08:00 | p | 866 |  | 2028-01-19 16:30
791 | 5866 | qnFTkxNSvGIYOwHhqElS | Normal | 5 | 1.9.6.10.2.10 | 1.9.6.10.2.10 |  | 2025-09-10 08:00 | p | 866 |  | 2028-01-24 14:23
792 | 5867 | 6vMprMC9ZRYTg9c055cw | Normal | 3 | 1.9.6.10.2.11 | 1.9.6.10.2.11 |  | 2025-09-17 08:00 | p | 866 |  | 2028-01-31 13:50
793 | 5868 | qP5P60WlJm98gR28uFOw | Normal | 1 | 1.9.6.10.2.12 | 1.9.6.10.2.12 |  | 2025-09-22 08:00 | p | 863 |  | 2028-02-02 13:03
794 | 5869 | 5FBVtcv48JlyNzpes7ps | Normal | 5 | 1.9.6.10.2.13 | 1.9.6.10.2.13 |  | 2025-09-23 08:00 | p | 863 |  | 2028-02-03 11:32
795 | 5870 | rLlKwDBGmyMe6lxLtymf | Summary | 59 | 1.9.6.10.3 | 1.9.6.10.3 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
796 | 5871 | owx5unCKcaLauhH4kWyj | Normal | 5 | 1.9.6.10.3.1 | 1.9.6.10.3.1 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
797 | 5872 | qImIYF1Y50rp0FNnsaoS | Normal | 10 | 1.9.6.10.3.2 | 1.9.6.10.3.2 |  | 2025-10-07 08:00 | p | 864 |  | 2028-02-18 13:09
798 | 5873 | FfFQqcMQ2fY5X0GvK0Xd | Normal | 20 | 1.9.6.10.3.3 | 1.9.6.10.3.3 |  | 2025-10-22 08:00 | p | 867 |  | 2028-03-07 11:58
799 | 5874 | fHTDjpnY2Gm0gViXPiAD | Normal | 2 | 1.9.6.10.3.6 | 1.9.6.10.3.6 |  | 2025-12-19 08:00 | p | 871 |  | 2028-05-08 10:44
800 | 5875 | TQZary26m4SvJkpuQUlv | Normal | 1 | 1.9.6.10.3.7 | 1.9.6.10.3.7 |  | 2025-12-23 08:00 | p | 869 |  | 2028-05-10 09:09
801 | 5876 | 5ZRJqmbhPGswffOWtWat | Normal | 1 | 1.9.6.10.3.8 | 1.9.6.10.3.8 |  | 2025-12-24 08:00 | p | 868 |  | 2028-05-10 16:29
802 | 6624 | sVpbcWAee9M5eeft5sdO | Normal | 15 | 1.9.6.10.3.4 | 1.9.6.10.3.4 |  | 2025-11-20 08:00 | p | 873 |  | 2028-04-11 11:46
803 | 6625 | it5qGsWYKIf8fEL1a2TB | Normal | 5 | 1.9.6.10.3.5 | 1.9.6.10.3.5 |  | 2025-12-12 08:00 | p | 868 |  | 2028-04-28 14:05
804 | 5877 | 8uIO0L3CbsjXfYIL70ur | Summary | 162 | 1.9.6.10.4 | 1.9.6.10.4 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
805 | 5878 | eKJmpIIS7eePXp789pq5 | Summary | 60 | 1.9.6.10.4.1 | 1.9.6.10.4.1 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
806 | 5879 | CJrwB1y6NRnYYg7kpaRv | Summary | 30 | 1.9.6.10.4.1.1 | 1.9.6.10.4.1.1 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
807 | 5880 | z8rht75g90pc62Jd1j8e | Normal | 15 | 1.9.6.10.4.1.1.1 | 1.9.6.10.4.1.1.1 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
808 | 5881 | ZPPJV7wrbqyTumtl84NX | Normal | 15 | 1.9.6.10.4.1.1.2 | 1.9.6.10.4.1.1.2 |  | 2025-10-22 08:00 | p | 860 |  | 2028-02-29 13:49
809 | 5882 | PdfqDNDAaUS1Z9tfvPSB | Normal | 15 | 1.9.6.10.4.1.2 | 1.9.6.10.4.1.2 |  | 2025-11-13 08:00 | p | 860 |  | 2028-03-22 15:58
810 | 5883 | 3J3dFKPf8v7HKW1lSal4 | Normal | 15 | 1.9.6.10.4.1.3 | 1.9.6.10.4.1.3 |  | 2025-12-05 08:00 | p | 858 |  | 2028-04-11 16:56
811 | 5884 | J3ZDJxR9DKKi4JquRb3Q | Summary | 20 | 1.9.6.10.4.2 | 1.9.6.10.4.2 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
812 | 5885 | p0UOLQYQkw5raD9Hf7AI | Normal | 5 | 1.9.6.10.4.2.1 | 1.9.6.10.4.2.1 |  | 2025-09-30 08:00 | p | 863 |  | 2028-02-10 10:41
813 | 5886 | mfBVa7VrtMT45ZcRp9ur | Normal | 5 | 1.9.6.10.4.2.2 | 1.9.6.10.4.2.2 |  | 2025-10-07 08:00 | p | 863 |  | 2028-02-17 11:18
814 | 5887 | xjL6okqGZuFc1ChaUzA0 | Normal | 5 | 1.9.6.10.4.2.3 | 1.9.6.10.4.2.3 |  | 2025-10-15 08:00 | p | 862 |  | 2028-02-24 11:50
815 | 5888 | 0NLdruhvCSk61FiIPSJA | Normal | 5 | 1.9.6.10.4.2.4 | 1.9.6.10.4.2.4 |  | 2025-10-22 08:00 | p | 863 |  | 2028-03-03 15:24
816 | 5889 | vcqfMiWzgD0sBRK91JrP | Normal | 3 | 1.9.6.10.4.3 | 1.9.6.10.4.3 |  | 2025-10-29 08:00 | p | 866 |  | 2028-03-13 08:09
817 | 5890 | r7iAplKyl5D3dW7yC0Jk | Normal | 5 | 1.9.6.10.4.4 | 1.9.6.10.4.4 |  | 2025-11-03 08:00 | p | 863 |  | 2028-03-15 15:38
818 | 5891 | 55B0pL3dU2GPDxU6IZLg | Normal | 1 | 1.9.6.10.4.5 | 1.9.6.10.4.5 |  | 2025-11-10 08:00 | p | 863 |  | 2028-03-22 15:32
819 | 5892 | zyPP7s8BBmPhydQ5fB2g | Normal | 1 | 1.9.6.10.4.8 | 1.9.6.10.4.8 |  | 2026-05-22 13:00 | p | 934 |  | 2028-12-11 13:54
820 | 5893 | JSBvauC3wpirasqwMrC9 | Normal | 1 | 1.9.6.10.4.6 | 1.9.6.10.4.6 |  | 2025-11-12 08:00 | p | 862 |  | 2028-03-23 13:30
821 | 5894 | AO4SgiivKvvxQJupi2GS | Normal | 1 | 1.9.6.10.4.7 | 1.9.6.10.4.7 |  | 2025-11-13 08:00 | p | 862 |  | 2028-03-24 13:34
822 | 4137 | rnRXxVdKdR5NUADIB31n | Normal | 1 | 1.9.6.11.1.2 | 1.9.6.11.1.2 |  | 2026-05-12 08:00 | p | 654 |  | 2028-02-25 10:36
823 | 4138 | 75WgU7H7MCC8DDgOcnsD | Normal | 30 | 1.9.6.11.1.3 | 1.9.6.11.1.3 |  | 2026-05-13 08:00 | p | 656 |  | 2028-02-28 11:51
824 | 4139 | 9SKpfzivi43NDDuHUq0B | Normal | 5 | 1.9.6.11.1.4 | 1.9.6.11.1.4 |  | 2026-06-26 08:00 | p | 650 |  | 2028-04-06 09:05
825 | 4140 | Lk7gef35zB3WaxM8Xyxe | Summary | 48 | 1.9.6.11.2 | 1.9.6.11.2 |  | 2026-07-06 08:00 | p | 646 |  | 2028-04-12 13:02
826 | 4141 | HGo5Ep3pqhcsiM5K4QjA | Summary | 23 | 1.9.6.11.2.1 | 1.9.6.11.2.1 |  | 2026-07-06 08:00 | p | 646 |  | 2028-04-12 13:02
827 | 4142 | VTqJrDLpWuaSlvRQajcM | Normal | 12 | 1.9.6.11.2.1.1 | 1.9.6.11.2.1.1 |  | 2026-07-06 08:00 | p | 646 |  | 2028-04-12 13:02
828 | 4143 | UwGhtpl5Mnq9WQrcrXRR | Normal | 11 | 1.9.6.11.2.1.2 | 1.9.6.11.2.1.2 |  | 2026-07-22 08:00 | p | 649 |  | 2028-05-01 15:56
829 | 4144 | zaFQ6K5wegGvKt6DGuoz | Summary | 25 | 1.9.6.11.2.2 | 1.9.6.11.2.2 |  | 2026-08-06 08:00 | p | 650 |  | 2028-05-17 11:22
830 | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Normal | 10 | 1.9.6.11.2.2.1 | 1.9.6.11.2.2.1 |  | 2026-08-06 08:00 | p | 650 |  | 2028-05-17 11:22
831 | 4146 | rTeXGnIwGPt6ES3ynSHq | Normal | 5 | 1.9.6.11.2.2.2 | 1.9.6.11.2.2.2 |  | 2026-08-20 08:00 | p | 649 |  | 2028-05-30 13:43
832 | 4147 | hQaW5HIstT5bbsPEBxyQ | Normal | 10 | 1.9.6.11.2.2.3 | 1.9.6.11.2.2.3 |  | 2026-08-27 08:00 | p | 648 |  | 2028-06-05 15:25
833 | 5998 | aRBXPvE6pbVbcbhlDtu4 | Summary | 47 | 1.9.6.1.7 | 1.9.6.1.7 |  | 2025-05-19 08:00 | p | 906 |  | 2027-11-11 13:59
834 | 5999 | hTF24jclc5ogfsrVWXZd | Normal | 40 | 1.9.6.1.7.1 | 1.9.6.1.7.1 |  | 2025-05-19 08:00 | p | 906 |  | 2027-11-11 13:59
835 | 6000 | dvNXA0SZWky1SGhKE7td | Normal | 5 | 1.9.6.1.7.2 | 1.9.6.1.7.2 |  | 2025-07-17 08:00 | p | 904 |  | 2028-01-07 09:53
836 | 6001 | z8HVZ6SyP3QpkaT54VAm | Normal | 1 | 1.9.6.1.7.3 | 1.9.6.1.7.3 |  | 2025-07-24 08:00 | p | 904 |  | 2028-01-14 10:43
837 | 6002 | rmlzSal3Nkh8gQGzhscw | Normal | 1 | 1.9.6.1.7.4 | 1.9.6.1.7.4 |  | 2025-07-25 08:00 | p | 906 |  | 2028-01-17 10:37
838 | 6003 | zkyCYMQIHOywdkyzbjbi | Summary | 48 | 1.9.6.1.8 | 1.9.6.1.8 |  | 2025-05-19 08:00 | p | 906 |  | 2027-11-11 13:59
839 | 6004 | xOhJcEwgSz1TAvNHU4tB | Normal | 40 | 1.9.6.1.8.1 | 1.9.6.1.8.1 |  | 2025-05-19 08:00 | p | 906 |  | 2027-11-11 13:59
840 | 6005 | gw3ZFSF3nzLqLqYBiqR7 | Normal | 5 | 1.9.6.1.8.2 | 1.9.6.1.8.2 |  | 2025-07-17 08:00 | p | 887 |  | 2027-12-21 11:00
841 | 6006 | HEKaqqmbwSXnCRXB6fED | Normal | 1 | 1.9.6.1.8.3 | 1.9.6.1.8.3 |  | 2025-07-24 08:00 | p | 887 |  | 2027-12-28 10:31
842 | 6007 | vdBzwsumrXxpXNAKvnKh | Normal | 1 | 1.9.6.1.8.4 | 1.9.6.1.8.4 |  | 2025-07-28 08:00 | p | 904 |  | 2028-01-18 08:48
843 | 6008 | Ph5VFx7Ghit4AwZEFBXT | Summary | 50 | 1.9.6.1.6 | 1.9.6.1.6 |  | 2025-04-07 08:00 | p | 905 |  | 2027-09-29 08:00
844 | 6009 | NVgukc0KZBShUa0wIlyx | Normal | 30 | 1.9.6.1.6.1 | 1.9.6.1.6.1 |  | 2025-04-07 08:00 | p | 905 |  | 2027-09-29 08:00
845 | 6010 | tIYqVtlT4yOF2YQ2FRYY | Normal | 10 | 1.9.6.1.6.2 | 1.9.6.1.6.2 |  | 2025-05-19 08:00 | p | 906 |  | 2027-11-11 13:59
846 | 6011 | 9Y3pHbqvwzl2AwHfvrBG | Normal | 5 | 1.9.6.1.6.3 | 1.9.6.1.6.3 |  | 2025-06-03 08:00 | p | 904 |  | 2027-11-24 11:11
847 | 6012 | Z1jpWQx4GyFcVoEVg0i0 | Normal | 5 | 1.9.6.1.6.4 | 1.9.6.1.6.4 |  | 2025-06-10 08:00 | p | 904 |  | 2027-12-01 10:24
848 | 6013 | y2dxMv99iLhGOXikZGuK | Summary | 34 | 1.9.6.1.5 | 1.9.6.1.5 |  | 2025-03-17 08:00 | p | 25 |  | 2025-04-11 15:34
849 | 6014 | hYHiAVYfHXdDTdWEk9J8 | Normal | 15 | 1.9.6.1.5.1 | 1.9.6.1.5.1 |  | 2025-03-17 08:00 | p | 25 |  | 2025-04-11 15:34
850 | 6015 | MXdxqc8Y6tIByFeEqluF | Normal | 10 | 1.9.6.1.5.2 | 1.9.6.1.5.2 |  | 2025-04-07 08:00 | p | 24 |  | 2025-05-01 14:39
851 | 6016 | gwhB80Lv7eu4PoYwev8o | Normal | 5 | 1.9.6.1.5.3 | 1.9.6.1.5.3 |  | 2025-04-21 08:00 | p | 24 |  | 2025-05-15 14:44
852 | 6017 | VCyTBN0y7V3erCRNMvm4 | Normal | 4 | 1.9.6.1.5.4 | 1.9.6.1.5.4 |  | 2025-04-28 08:00 | p | 23 |  | 2025-05-21 13:41
853 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | 2025-02-18 08:00 | p | 925 |  | 2027-09-01 08:00
854 | 6957 | ar01N24L63iczVEh1mVo | Summary | 24 | 1.9.6.1.4 | 1.9.6.1.4 |  | 2025-03-04 08:00 | p | 29 |  | 2025-04-02 09:07
855 | 6958 | 6Ul4V6iAcnpVqewOp14Y | Normal | 4 | 1.9.6.1.4.1 | 1.9.6.1.4.1 |  | 2025-03-04 08:00 | p | 29 |  | 2025-04-02 09:07
856 | 6959 | w9Vvv79ftt4PUqInNFyD | Normal | 5 | 1.9.6.1.4.2 | 1.9.6.1.4.2 |  | 2025-03-10 08:00 | p | 28 |  | 2025-04-07 13:43
857 | 6960 | xIgpHAurEQ244gHa2T5q | Normal | 5 | 1.9.6.1.4.3 | 1.9.6.1.4.3 |  | 2025-03-17 08:00 | p | 25 |  | 2025-04-11 15:34
858 | 6961 | NOksVV7sTymsgwMrnh6x | Normal | 10 | 1.9.6.1.4.4 | 1.9.6.1.4.4 |  | 2025-03-24 08:00 | p | 25 |  | 2025-04-18 14:07
859 | 4075 | dGbNHsOLhslKk8CjhyjE | Normal | 1 | 1.9.6.9.3 | 1.9.6.9.3 |  | 2025-04-01 08:00 | p | 27 |  | 2025-04-28 13:41
860 | 6427 | NeAxFJaqSLize8VPNJ6N | Normal | 1 | 1.7.1.8.3 | 1.7.1.8.3 |  | 2025-03-14 08:00 | q | -101 |  | 2024-12-03 08:00
861 | 4196 | 2ZwOzHGH45ywtPvfASSG | Normal | 5 | 1.9.8.1.5 | 1.9.8.1.5 |  | 2025-09-16 08:00 | q | -20 |  | 2025-08-26 15:35
862 | 5974 | cJ7VeFZezCBnvYlHxCmb | Normal | 1 | 1.9.8.1.6.7 | 1.9.8.1.6.7 |  | 2025-02-27 08:00 | q | -120 |  | 2024-10-30 08:00
863 | 5985 | AUKn3E7aViOsULw8HdKV | Normal | 131 | 1.9.8.1.12 | 1.9.8.1.12 |  | 2025-03-11 08:00 | p | 29 |  | 2025-04-09 09:57
864 | 4231 | 8h0WH2qeIC7tfvcerCPa | Normal | 1 | 1.9.8.2.3 | 1.9.8.2.3 |  | 2025-06-24 08:00 | q | -183 |  | 2024-12-23 08:00
865 | 4235 | QiaATNQSPId7svzcuO8r | Normal | 91 | 1.9.8.2.7 | 1.9.8.2.7 |  | 2025-07-17 08:00 | p | 32 |  | 2025-08-18 14:35
866 | 4243 | LpPx7AWOh1V8dzWVWc6j | Normal | 1 | 1.9.8.4.5 | 1.9.8.4.5 |  | 2025-05-13 08:00 | q | -357 |  | 2024-05-21 08:00
867 | 4246 | ANAzXnUTz1PCb3xsov4Y | Normal | 10 | 1.9.8.4.7 | 1.9.8.4.7 |  | 2025-05-14 08:00 | p | 44 |  | 2025-06-27 11:52
868 | 4248 | E1RJwJWM8qrsKP3o7Toy | Normal | 1 | 1.9.8.7 | 1.9.8.7 |  | 2025-08-05 08:00 | q | -17 |  | 2025-07-18 08:03
869 | 4251 | IBg36OMMKUy3vwEnRNF0 | Normal | 1 | 1.9.8.6 | 1.9.8.6 |  | 2025-06-05 08:00 | q | -668 |  | 2023-08-07 08:00
870 | 4253 | hnujWIe1JDNg9VHs3TWw | Normal | 1 | 1.9.8.8 | 1.9.8.8 |  | 2025-08-12 08:00 | q | -24 |  | 2025-07-18 16:27
871 | 4255 | TAfq40Sin0H6Q2YT0OS5 | Milestone | 0 | 1.9.8.3 | 1.9.8.3 |  | 2025-11-25 17:00 | q | -11 |  | 2025-11-14 11:45
872 | 4256 | G2pYfP7dsnHVTgqQD6mD | Summary | 82 | 1.9.8.10 | 1.9.8.10 |  | 2025-09-26 08:00 | q | -781 |  | 2023-08-07 08:00
873 | 4258 | GzQkXlTiYJMdE6nBDVeb | Normal | 6 | 1.9.8.10.1 | 1.9.8.10.1 |  | 2025-09-26 08:00 | q | -781 |  | 2023-08-07 08:00
874 | 6090 | LkexiRQNUDyJAwm8EPYV | Normal | 32 | 1.9.8.10.7 | 1.9.8.10.7 |  | 2025-12-10 08:00 | q | -788 |  | 2023-10-13 16:14
875 | 6187 | kIPGiItVAbHq2ks8DK41 | Normal | 5 | 1.9.8.10.6 | 1.9.8.10.6 |  | 2025-12-03 08:00 | q | -785 |  | 2023-10-09 09:37
876 | 6430 | IYyY3jK4t9QuDyuxqyQ5 | Normal | 15 | 1.9.8.10.2 | 1.9.8.10.2 |  | 2025-10-06 08:00 | q | -786 |  | 2023-08-11 16:09
877 | 6431 | mXx66gQ5BZWpD3idmZgM | Normal | 10 | 1.9.8.10.3 | 1.9.8.10.3 |  | 2025-10-28 08:00 | q | -789 |  | 2023-08-30 13:04
878 | 6432 | vMoeJo3Rc30lMwFim6rn | Normal | 10 | 1.9.8.10.4 | 1.9.8.10.4 |  | 2025-11-12 08:00 | q | -785 |  | 2023-09-18 11:27
879 | 6433 | zONKYXhH5yZJE26xvIWD | Normal | 4 | 1.9.8.10.5 | 1.9.8.10.5 |  | 2025-11-26 08:00 | q | -784 |  | 2023-10-03 11:25
880 | 6083 | 3dsblDK1X9ztc27EZU3v | Normal | 1 | 1.9.8.5 | 1.9.8.5 |  | 2025-12-12 08:00 | p | 930 |  | 2028-06-29 10:44
881 | 6084 | deZM0xh115wln716GUoI | Normal | 1 | 1.9.8.9 | 1.9.8.9 |  | 2026-10-02 13:00 | p | 929 |  | 2029-04-19 10:06
882 | 7321 | CTokiQfH6gyOyeZJGrxP | Normal | 1 | 1.7.9.11 | 1.7.9.11 |  | 2025-05-30 08:00 | q | -662 |  | 2023-08-07 08:00
883 | 5690 | jLB7gq1wR8egZrMIoAc7 | Summary | 24 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-02-27 17:00 | p | 25 |  | 2025-03-25 16:29
884 | 5691 | glUuWw43f2R9t2hl6VHO | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-02-27 17:00 | p | 25 |  | 2025-03-25 16:29
885 | 5692 | KeXnvnZRx0KMyut3yw5s | Milestone | 0 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-03-13 17:00 | p | 21 |  | 2025-04-04 10:19
886 | 5693 | VdKRFLdSc60knizSqFXc | Normal | 14 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-03-13 17:00 | p | 21 |  | 2025-04-04 10:19
887 | 5694 | Gb0taOZcQ8l0cdHliY6j | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-02 17:00 | p | 22 |  | 2025-04-25 09:18
888 | 5695 | ePp2idADlztrdEpItyCc | Milestone | 0 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-16 17:00 | p | 25 |  | 2025-05-12 15:52
889 | 5696 | npE0RnxADwI7cDPG1fDa | Normal | 4 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-16 17:00 | p | 25 |  | 2025-05-12 15:52
890 | 5697 | 4nIBzBv3LSP60HeOLv0f | Normal | 5 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-23 08:00 | p | 26 |  | 2025-05-19 10:36
891 | 5536 | cYU0DBZylLxVRoLEp7Bc | Normal | 40 | 1.9.5.1.4 | 1.9.5.1.4 |  | 2025-03-04 08:00 | p | 34 |  | 2025-04-07 16:10
892 | 5544 | cIc3ARzcdrbXv6maHllr | Summary | 129 | 1.9.5.2.13 | 1.9.5.2.13 |  | 2025-03-17 08:00 | p | 29 |  | 2025-04-15 16:20
893 | 5545 | 7UVU8IboY6NG7sqZCrUC | Normal | 7 | 1.9.5.2.13.2 | 1.9.5.2.13.2 |  | 2025-05-21 08:00 | p | 944 |  | 2027-12-21 13:16
894 | 5546 | Shs5wuYOFSkTF1YslX8w | Normal | 6 | 1.9.5.2.13.5 | 1.9.5.2.13.5 |  | 2025-06-09 08:00 | p | 940 |  | 2028-01-05 14:48
895 | 5547 | KglXvc5QwlHEboIvY96Q | Normal | 4 | 1.9.5.2.13.8 | 1.9.5.2.13.8 |  | 2025-07-09 08:00 | p | 939 |  | 2028-02-03 13:14
896 | 5548 | Zfzda0CfmpiN8ZL93G3t | Normal | 5 | 1.9.5.2.13.9 | 1.9.5.2.13.9 |  | 2025-07-15 08:00 | p | 939 |  | 2028-02-09 13:14
897 | 5549 | PgYJem7PJFdGgV04ojeL | Normal | 1 | 1.4.17 | 1.4.17 |  | 2025-07-22 08:00 | p | 940 |  | 2028-02-17 13:18
898 | 5556 | fOMVaiOa0jnHOJyDUdVQ | Normal | 25 | 1.9.5.2.13.11 | 1.9.5.2.13.11 |  | 2025-08-13 08:00 | p | 944 |  | 2028-03-14 13:46
899 | 5730 | ypyrsmMFJqJ9aPla6UhQ | Normal | 4 | 1.9.5.2.13.3 | 1.9.5.2.13.3 |  | 2025-06-02 08:00 | p | 940 |  | 2027-12-29 16:29
900 | 5731 | uQF6Ff0bc2cqy3b37ZQc | Normal | 1 | 1.9.5.2.13.4 | 1.9.5.2.13.4 |  | 2025-06-06 08:00 | p | 942 |  | 2028-01-04 15:46
901 | 5732 | OQKwpwUgImWCC2Fp5G0Q | Normal | 7 | 1.9.5.2.13.6 | 1.9.5.2.13.6 |  | 2025-06-17 08:00 | p | 941 |  | 2028-01-14 10:46
902 | 5733 | wyOxVAS94HubPKo2yHJm | Normal | 7 | 1.9.5.2.13.7 | 1.9.5.2.13.7 |  | 2025-06-27 08:00 | p | 942 |  | 2028-01-25 11:46
903 | 7000 | yP1oDcnUQTy3g68ZLgu0 | Normal | 8 | 1.9.5.2.13.1 | 1.9.5.2.13.1 |  | 2025-03-17 08:00 | p | 29 |  | 2025-04-15 16:20
904 | 5557 | U376LwOjKfNZoVLUlmMD | Summary | 113 | 1.9.5.2.12 | 1.9.5.2.12 |  | 2025-03-04 08:00 | p | 29 |  | 2025-04-02 09:07
905 | 5558 | RXAxJx3BHWNVdWFPfZ2a | Normal | 13 | 1.9.5.2.12.2 | 1.9.5.2.12.2 |  | 2025-04-23 08:00 | p | 940 |  | 2027-11-19 08:41
906 | 5559 | jJoy8dUJMWD3ZuNw52D0 | Normal | 8 | 1.9.5.2.12.5 | 1.9.5.2.12.5 |  | 2025-05-21 08:00 | p | 944 |  | 2027-12-21 13:16
907 | 5560 | wu3sL1wqoiodUr5mG52N | Normal | 4 | 1.9.5.2.12.8 | 1.9.5.2.12.8 |  | 2025-06-24 08:00 | p | 941 |  | 2028-01-21 13:29
908 | 5561 | Vb2zzMF18WNANxlCzGiz | Normal | 5 | 1.9.5.2.12.9 | 1.9.5.2.12.9 |  | 2025-06-30 08:00 | p | 941 |  | 2028-01-27 11:57
909 | 5562 | vp7j6GBYm2dAMLvxEFuE | Normal | 1 | 1.4.20 | 1.4.20 |  | 2025-07-08 08:00 | p | 939 |  | 2028-02-02 14:54
910 | 5569 | 35aiC9HLOSrIl2OBwDvd | Normal | 25 | 1.9.5.2.12.11 | 1.9.5.2.12.11 |  | 2025-07-09 08:00 | p | 939 |  | 2028-02-03 15:25
911 | 5734 | iq9bjqBZvH9Bj6912271 | Normal | 6 | 1.9.5.2.12.3 | 1.9.5.2.12.3 |  | 2025-05-12 08:00 | p | 941 |  | 2027-12-09 10:24
912 | 5735 | Z8zFgfwvHK2hwW2AW8Qa | Normal | 1 | 1.9.5.2.12.4 | 1.9.5.2.12.4 |  | 2025-05-20 08:00 | p | 944 |  | 2027-12-20 13:06
913 | 5736 | QgUmTWGvxjzq3xqrWPJK | Normal | 7 | 1.9.5.2.12.6 | 1.9.5.2.12.6 |  | 2025-06-03 08:00 | p | 941 |  | 2027-12-31 14:10
914 | 5737 | iDzIA8f8DQgg2wVNkaUu | Normal | 7 | 1.9.5.2.12.7 | 1.9.5.2.12.7 |  | 2025-06-12 08:00 | p | 943 |  | 2028-01-11 10:01
915 | 7001 | WpRQh8HvPfyDha8FH5FR | Normal | 9 | 1.9.5.2.12.1 | 1.9.5.2.12.1 |  | 2025-03-04 08:00 | p | 29 |  | 2025-04-02 09:07
916 | 5571 | lfRAbO0c5jl7NaC6s7pm | Normal | 21 | 1.9.5.2.11.2 | 1.9.5.2.11.2 |  | 2025-03-17 08:00 | p | 939 |  | 2027-10-12 11:58
917 | 5572 | jk3Vm36iIGViuk9dpLfQ | Normal | 8 | 1.9.5.2.11.5 | 1.9.5.2.11.5 |  | 2025-04-23 08:00 | p | 940 |  | 2027-11-19 08:41
918 | 5573 | u3MfiduPa05JsS2ly7WD | Normal | 4 | 1.9.5.2.11.8 | 1.9.5.2.11.8 |  | 2025-06-09 08:00 | p | 933 |  | 2027-12-29 16:03
919 | 5574 | 3iKE3riinMPRUpVpTfwx | Normal | 5 | 1.9.5.2.11.9 | 1.9.5.2.11.9 |  | 2025-06-13 08:00 | p | 936 |  | 2028-01-05 08:46
920 | 5575 | 48yotl4pDzxbk5y0VDbK | Normal | 1 | 1.4.23 | 1.4.23 |  | 2025-06-23 08:00 | p | 933 |  | 2028-01-12 14:00
921 | 5582 | 6tLu8emqwotxTkeBbEpy | Normal | 26 | 1.9.5.2.11.11 | 1.9.5.2.11.11 |  | 2025-06-24 08:00 | p | 933 |  | 2028-01-13 14:31
922 | 5738 | ME2oX9BwgLu5cggaunhg | Normal | 5 | 1.9.5.2.11.3 | 1.9.5.2.11.3 |  | 2025-04-15 08:00 | p | 940 |  | 2027-11-11 09:42
923 | 5739 | IivOSmNLtmlF9JKFLUrl | Normal | 1 | 1.9.5.2.11.4 | 1.9.5.2.11.4 |  | 2025-04-22 08:00 | p | 940 |  | 2027-11-18 09:40
924 | 5740 | eRxCjL3dV2CpHvAG84r7 | Normal | 12 | 1.9.5.2.11.6 | 1.9.5.2.11.6 |  | 2025-05-05 08:00 | p | 935 |  | 2027-11-26 08:06
925 | 5741 | 8Y4jq7dOt4lN4NYBT6r1 | Normal | 12 | 1.9.5.2.11.7 | 1.9.5.2.11.7 |  | 2025-05-21 08:00 | p | 936 |  | 2027-12-13 15:36
926 | 5583 | gkFBoXdv1oJb2jtBcO5M | Summary | 147 | 1.9.5.2.14 | 1.9.5.2.14 |  | 2025-03-27 08:00 | p | 27 |  | 2025-04-23 16:51
927 | 5584 | 6WMzJdzS7tY0wFFuXnrc | Normal | 7 | 1.9.5.2.14.2 | 1.9.5.2.14.2 |  | 2025-06-09 08:00 | p | 940 |  | 2028-01-05 14:48
928 | 5585 | KljMWvDEBGSuBTW4zQhZ | Normal | 7 | 1.9.5.2.14.5 | 1.9.5.2.14.5 |  | 2025-06-26 08:00 | p | 943 |  | 2028-01-25 09:57
929 | 5586 | Z3ZWpIsgJCSKUX161hV0 | Normal | 4 | 1.9.5.2.14.8 | 1.9.5.2.14.8 |  | 2025-07-24 08:00 | p | 939 |  | 2028-02-18 14:37
930 | 5587 | OXOUsYDejGVlgqn4Z1vl | Normal | 5 | 1.9.5.2.14.9 | 1.9.5.2.14.9 |  | 2025-07-30 08:00 | p | 939 |  | 2028-02-24 11:24
931 | 5588 | MFjHKzinVVI0Ndx8qx0B | Normal | 1 | 1.4.26 | 1.4.26 |  | 2025-08-06 08:00 | p | 940 |  | 2028-03-03 15:26
932 | 5595 | REFTk0AP9RBTibJWVhuH | Normal | 26 | 1.9.5.2.14.11 | 1.9.5.2.14.11 |  | 2025-09-18 08:00 | p | 944 |  | 2028-04-19 10:01
933 | 5742 | 88bEv4EMiOL2y8w1ttIM | Normal | 4 | 1.9.5.2.14.3 | 1.9.5.2.14.3 |  | 2025-06-18 08:00 | p | 940 |  | 2028-01-14 16:57
934 | 5743 | 0Uz4krHDVCdAlMd5aRwh | Normal | 1 | 1.9.5.2.14.4 | 1.9.5.2.14.4 |  | 2025-06-25 08:00 | p | 940 |  | 2028-01-21 16:37
935 | 5744 | cSBfnbrbVLLFYTMEfBKA | Normal | 6 | 1.9.5.2.14.6 | 1.9.5.2.14.6 |  | 2025-07-08 08:00 | p | 939 |  | 2028-02-02 15:52
936 | 5745 | ZY99Y6JX4jBylnfeedvo | Normal | 6 | 1.9.5.2.14.7 | 1.9.5.2.14.7 |  | 2025-07-16 08:00 | p | 943 |  | 2028-02-14 09:20
937 | 6999 | AnycnugTW971av3hMZXE | Normal | 8 | 1.9.5.2.14.1 | 1.9.5.2.14.1 |  | 2025-03-27 08:00 | p | 27 |  | 2025-04-23 16:51
938 | 6446 | XvbStahAymwCoqNIbMJG | Summary | 32 | 1.9.5.2.4 | 1.9.5.2.4 |  | 2025-03-03 08:00 | q | -364 |  | 2024-03-04 08:00
939 | 6532 | 15e7xcLR1b1jSikaz0S2 | Normal | 32 | 1.9.5.2.4.2 | 1.9.5.2.4.2 |  | 2025-03-03 08:00 | q | -364 |  | 2024-03-04 08:00
940 | 6533 | b0mutjzKj8FRw4zkbb8K | Normal | 32 | 1.9.5.2.4.1 | 1.9.5.2.4.1 |  | 2025-03-03 08:00 | q | -364 |  | 2024-03-04 08:00
941 | 6534 | 8Gl2bk4Fxxo2fsClDJqG | Normal | 32 | 1.9.5.2.4.3 | 1.9.5.2.4.3 |  | 2025-03-03 08:00 | q | -364 |  | 2024-03-04 08:00
942 | 6535 | dWze9AnK8NrEMD9LOEyU | Normal | 32 | 1.9.5.2.4.4 | 1.9.5.2.4.4 |  | 2025-03-03 08:00 | q | -364 |  | 2024-03-04 08:00
943 | 6955 | CPACk87DS0kpO7pXcdwS | Normal | 10 | 1.9.5.2.10 | 1.9.5.2.10 |  | 2025-02-18 08:00 | p | 926 |  | 2027-09-02 13:26
944 | 5596 | upn4QoZvaKBmBMoyhnq5 | Summary | 90 | 1.9.5.3 | 1.9.5.3 |  | 2025-07-30 08:00 | p | 939 |  | 2028-02-24 11:24
945 | 5597 | zKJsJYNcPRFZ7wBjvprv | Normal | 18 | 1.9.5.3.1 | 1.9.5.3.1 |  | 2025-07-30 08:00 | p | 939 |  | 2028-02-24 11:24
946 | 5598 | zvvzNQqIPXzcVRwy0N44 | Summary | 52 | 1.9.5.3.2 | 1.9.5.3.2 |  | 2025-09-16 08:00 | p | 939 |  | 2028-04-12 13:04
947 | 5599 | T0Oh47cWIVU9y2MKPB0U | Normal | 12 | 1.9.5.3.2.1 | 1.9.5.3.2.1 |  | 2025-09-16 08:00 | p | 939 |  | 2028-04-12 13:04
948 | 5600 | oTkX6bjokLXQ590hdeFy | Normal | 12 | 1.9.5.3.2.2 | 1.9.5.3.2.2 |  | 2025-10-02 08:00 | p | 942 |  | 2028-05-01 15:11
949 | 5601 | xa7cRxeKgQxZnuHNAYMQ | Normal | 12 | 1.9.5.3.2.3 | 1.9.5.3.2.3 |  | 2025-10-27 08:00 | p | 948 |  | 2028-06-01 10:32
950 | 5602 | QlxDegibloFbHrPNJwyW | Normal | 12 | 1.9.5.3.2.4 | 1.9.5.3.2.4 |  | 2025-11-13 08:00 | p | 944 |  | 2028-06-14 08:04
951 | 5603 | dwMYG7lg76TqxtTxZNCR | Normal | 5 | 1.9.5.3.3 | 1.9.5.3.3 |  | 2025-12-02 08:00 | p | 944 |  | 2028-07-03 15:24
952 | 5360 | ARncD9Nx3De5DONPy9Bs | Normal | 3 | 1.9.4.1.4 | 1.9.4.1.4 |  | 2025-04-10 08:00 | q | 0 |  | 2025-04-09 16:48
953 | 5368 | NKJL1ZJN3KgUArkbA4qS | Normal | 3 | 1.9.4.2.4 | 1.9.4.2.4 |  | 2025-02-21 08:00 | p | 496 |  | 2026-07-02 11:08
954 | 7261 | isfym7y8CMuc9Vq3Mbcl | Normal | 1 | 1.7.4.2.5 | 1.7.4.2.5 |  | 2025-02-20 08:00 | p | 496 |  | 2026-07-01 13:56
955 | 5383 | u1aficyBQ2O9A8MnpdfZ | Normal | 20 | 1.9.4.5.6 | 1.9.4.5.6 |  | 2025-03-17 08:00 | p | 0 |  | 2025-03-17 08:25
956 | 5384 | d8i6C63YfOF3EovUl19W | Normal | 10 | 1.9.4.5.7 | 1.9.4.5.7 |  | 2025-04-14 08:00 | p | 4 |  | 2025-04-18 13:59
957 | 5385 | ohwsmv9qOoV0RNzIdjJI | Normal | 15 | 1.9.4.5.8 | 1.9.4.5.8 |  | 2025-04-28 08:00 | p | 4 |  | 2025-05-02 14:06
958 | 5386 | tSuemAovBYAaHNhFiwaF | Normal | 15 | 1.9.4.5.9 | 1.9.4.5.9 |  | 2025-05-19 08:00 | p | 9 |  | 2025-05-28 10:53
959 | 5393 | 3qvg7di25vdBD8UUvM1a | Normal | 20 | 1.9.4.6.6 | 1.9.4.6.6 |  | 2025-03-17 08:00 | q | -4 |  | 2025-03-12 13:55
960 | 5394 | ungpeNo64cspVo3BuO9g | Normal | 10 | 1.9.4.6.7 | 1.9.4.6.7 |  | 2025-04-14 08:00 | q | -4 |  | 2025-04-09 13:03
961 | 5395 | KZXvYFda88KgX9w7a3ES | Normal | 15 | 1.9.4.6.8 | 1.9.4.6.8 |  | 2025-04-28 08:00 | q | -3 |  | 2025-04-24 13:29
962 | 5396 | FNjsTUKVT29tBcVlvaM6 | Normal | 15 | 1.9.4.6.9 | 1.9.4.6.9 |  | 2025-05-19 08:00 | q | -4 |  | 2025-05-14 14:24
963 | 5397 | KGrMeH5y6HH9dj1tr8uB | Summary | 53 | 1.9.4.7 | 1.9.4.7 |  | 2025-06-10 08:00 | p | 3 |  | 2025-06-13 10:42
964 | 5398 | EMMfZLgDhvN5O0lAfznQ | Normal | 15 | 1.9.4.7.1 | 1.9.4.7.1 |  | 2025-06-10 08:00 | p | 3 |  | 2025-06-13 10:42
965 | 5399 | 5K7jeUOrZ3wka9S2O1Dn | Normal | 15 | 1.9.4.7.2 | 1.9.4.7.2 |  | 2025-07-02 08:00 | p | 7 |  | 2025-07-09 13:26
966 | 5400 | I2IZFfCcy2hUSTtihPWq | Normal | 15 | 1.9.4.7.3 | 1.9.4.7.3 |  | 2025-07-24 08:00 | p | 6 |  | 2025-07-30 13:24
967 | 5401 | WWZjxA63YxH38hnYmVKG | Normal | 8 | 1.9.4.7.4 | 1.9.4.7.4 |  | 2025-08-14 08:00 | p | 6 |  | 2025-08-20 11:13
968 | 5402 | zDUD70mdAG3rcozejCwk | Summary | 15 | 1.9.4.8 | 1.9.4.8 |  | 2025-08-26 08:00 | p | 10 |  | 2025-09-05 13:16
969 | 5403 | wP2WbhW6upJb7JmdzCw1 | Normal | 9 | 1.9.4.8.1 | 1.9.4.8.1 |  | 2025-08-26 08:00 | p | 10 |  | 2025-09-05 13:16
970 | 5404 | UrewlDJ3J2c8Ueci7p9E | Normal | 6 | 1.9.4.8.2 | 1.9.4.8.2 |  | 2025-09-09 08:00 | p | 395 |  | 2026-10-09 11:51
971 | 7264 | vNqQNKJIEgg8BiBzdWeI | Summary | 57 | 1.7.4.3.6 | 1.7.4.3.6 |  | 2025-04-10 08:00 | p | 448 |  | 2026-07-02 11:08
972 | 7265 | uNFJkQaxxZ7oOYaM8QxX | Normal | 13 | 1.7.4.3.6.1 | 1.7.4.3.6.1 |  | 2025-04-10 08:00 | p | 448 |  | 2026-07-02 11:08
973 | 7266 | y7TR6NxR4uOKxinxsnEt | Normal | 13 | 1.7.4.3.6.2 | 1.7.4.3.6.2 |  | 2025-04-30 08:00 | p | 449 |  | 2026-07-23 15:35
974 | 7267 | f0BUmD79ZhKqjjzrwXUq | Normal | 13 | 1.7.4.3.6.3 | 1.7.4.3.6.3 |  | 2025-05-19 08:00 | p | 449 |  | 2026-08-11 09:18
975 | 7268 | sP1zO7OhzT9CUKqdzecJ | Normal | 12 | 1.7.4.3.6.4 | 1.7.4.3.6.4 |  | 2025-06-06 08:00 | p | 448 |  | 2026-08-28 16:14
976 | 7269 | 7v5GPnNw6yREyKfoeMiZ | Normal | 5 | 1.7.4.3.6.5 | 1.7.4.3.6.5 |  | 2025-06-25 08:00 | p | 448 |  | 2026-09-16 15:45
977 | 7322 | XsHCl5GkwKVP3xy7r0jT | Summary | 85 | 1.7.5 | 1.7.5 |  | 2025-03-03 08:00 | q | -574 |  | 2023-08-07 08:00
978 | 7528 | 8SnF5zCB4rJyZyQZLLZc | Normal | 8 | 1.7.5.1 | 1.7.5.1 |  | 2025-03-03 08:00 | q | -574 |  | 2023-08-07 08:00
979 | 7529 | ugdLGMeRoSNQZE98ehwR | Normal | 8 | 1.7.5.2 | 1.7.5.2 |  | 2025-03-03 08:00 | q | -574 |  | 2023-08-07 08:00
980 | 7530 | tZgNvNsEFqNHmYVKXpMu | Normal | 7 | 1.7.5.3 | 1.7.5.3 |  | 2025-03-13 08:00 | q | -569 |  | 2023-08-21 13:24
981 | 7531 | WsQS39Ko43y2ykuRUNnk | Normal | 8 | 1.7.5.4 | 1.7.5.4 |  | 2025-03-24 08:00 | q | -571 |  | 2023-08-30 10:14
982 | 7532 | tNKjUDGuH9lZvW14y0xJ | Normal | 22 | 1.7.5.5 | 1.7.5.5 |  | 2025-04-03 08:00 | q | -566 |  | 2023-09-14 09:50
983 | 7533 | HKUUjAeDBFLcgj42uw3c | Normal | 19 | 1.7.5.6 | 1.7.5.6 |  | 2025-05-05 08:00 | q | -565 |  | 2023-10-17 11:23
984 | 7534 | s7VTtgJqjYjf9pbLYcYj | Normal | 8 | 1.7.5.7 | 1.7.5.7 |  | 2025-06-02 08:00 | q | -564 |  | 2023-11-15 13:09
985 | 7535 | uGgP1gHCy12zlVFcLeTG | Normal | 6 | 1.7.5.8 | 1.7.5.8 |  | 2025-06-12 08:00 | q | -562 |  | 2023-11-27 10:34
986 | 7536 | kbIucnV7qsI0ZjxbK1cH | Normal | 6 | 1.7.5.9 | 1.7.5.9 |  | 2025-06-23 08:00 | q | -569 |  | 2023-12-01 16:48
987 | 7537 | ZiOXL4e3BgetRuJ4aYKK | Normal | 1 | 1.7.5.10 | 1.7.5.10 |  | 2025-07-01 08:00 | q | -566 |  | 2023-12-12 13:17
988 | 6690 | bopLkaAZbmZjIM9EGI6L | Normal | 532 | 1.11.2 | 1.11.2 |  | 2026-09-08 08:00 | q | -1128 |  | 2023-08-07 08:00
989 | 7131 | XTX9Wl5SzTxAD1rtsh9U | Summary | 0 | 1.10 | 1.10 |  | 2023-10-12 17:00 | q | -2114 |  | 2017-12-28 16:20
990 | 156 | 0RXSkgYJdrs7AeQvgU3w | Milestone | 0 | 1.10.24 | 1.10.24 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
991 | 157 | DYCfhHgWVvjY4WPSrw6q | Milestone | 0 | 1.10.25 | 1.10.25 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
992 | 7107 | fjlRoMsMUGjOnNWoUkGJ | Milestone | 0 | 1.10.16 | 1.10.16 |  | 2027-01-01 08:05 | p | 5 |  | 2027-01-06 08:12
993 | 7108 | wFwSqsIrP0eolc7owrIn | Milestone | 0 | 1.10.3 | 1.10.3 |  | 2025-04-10 17:00 | q | -3 |  | 2025-04-07 10:08
994 | 7110 | fycPVr34q6lr2y2bEJNl | Milestone | 0 | 1.10.9 | 1.10.9 |  | 2025-08-05 17:00 | p | 35 |  | 2025-09-10 14:26
995 | 7111 | gs1r9nT3BBBdW42nHT47 | Milestone | 0 | 1.10.13 | 1.10.13 |  | 2025-10-16 17:00 | p | 31 |  | 2025-11-17 09:47
996 | 7112 | a270fhhuENq55tFKO8IB | Milestone | 0 | 1.10.10 | 1.10.10 |  | 2025-11-28 17:00 | p | 23 |  | 2025-12-22 09:42
997 | 7114 | pZqvbi91bBhqyjB86evl | Milestone | 0 | 1.10.2 | 1.10.2 |  | 2026-03-06 17:00 | p | 20 |  | 2026-03-27 11:53
998 | 7115 | mxRJVREYCLlOZtWGohdT | Milestone | 0 | 1.10.8 | 1.10.8 |  | 2026-04-03 17:00 | p | 9 |  | 2026-04-13 11:49
999 | 7116 | 4gFjRlWXKNF16b9sFMXr | Milestone | 0 | 1.10.11 | 1.10.11 |  | 2025-09-24 17:00 | q | -170 |  | 2025-04-07 15:53
1000 | 7117 | zFlqKdf38AVahGy9Q9X8 | Milestone | 0 | 1.10.12 | 1.10.12 |  | 2026-01-14 17:00 | q | -8 |  | 2026-01-06 13:47
1001 | 7118 | 6jNHf85fMsjQD6qn9QnY | Milestone | 0 | 1.10.14 | 1.10.14 |  | 2025-12-15 17:00 | p | 27 |  | 2026-01-12 08:25
1002 | 7119 | OQnmDeJwrgb4ibYKrZjo | Milestone | 0 | 1.10.15 | 1.10.15 |  | 2025-10-01 17:00 | q | -586 |  | 2024-02-23 09:07
1003 | 7120 | ewfCDE69jjk4Zb5M5CES | Milestone | 0 | 1.10.4 | 1.10.4 |  | 2025-04-02 17:00 | q | -6 |  | 2025-03-27 13:16
1004 | 7121 | V4W6CQQo6lTjRlhYdPDq | Milestone | 0 | 1.10.5 | 1.10.5 |  | 2025-05-19 17:00 | p | 34 |  | 2025-06-23 10:29
1005 | 7122 | ZQwX0qpiGy3bERfpXjQ0 | Milestone | 0 | 1.10.6 | 1.10.6 |  | 2025-04-07 17:00 | p | 27 |  | 2025-05-05 10:48
1006 | 7123 | 0fpNMQTy9Zfk1YAC7GK2 | Milestone | 0 | 1.10.7 | 1.10.7 |  | 2025-04-01 17:00 | q | -6 |  | 2025-03-26 11:36
1007 | 7124 | yYQOOagkBr46kWICPuG6 | Milestone | 0 | 1.10.17 | 1.10.17 |  | 2025-09-11 17:00 | q | -2814 |  | 2017-12-28 16:20
1008 | 7125 | a4xeGKWGk9YyWLffVRQZ | Milestone | 0 | 1.10.18 | 1.10.18 |  | 2025-10-08 17:00 | q | -2809 |  | 2018-01-29 14:01
1009 | 7126 | XIH51zzlt2AXqf8IkYxf | Milestone | 0 | 1.10.19 | 1.10.19 |  | 2025-11-04 17:00 | q | -2812 |  | 2018-02-22 16:01
1010 | 7129 | kvNY0frGkARL99AbSHw0 | Milestone | 0 | 1.10.22 | 1.10.22 |  | 2025-05-19 17:00 | p | 1 |  | 2025-05-21 11:08

## Early-Finish
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Early Finish - 1283 (60%) | Early Finish - 1283 (60%) | Early Finish - 1283 (60%) | Early Finish - 1283 (60%) | Early Finish - 1283 (60%) | Early Finish - 1283 (60%) | Early Finish - 1283 (60%) | Early Finish - 1283 (60%) | Early Finish - 1283 (60%) | Early Finish - 1283 (60%) | Early Finish - 1283 (60%) | Early Finish - 1283 (60%) | Early Finish - 1283 (60%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 1249 | v1zgYyoO7UpynPZXt29g | Summary | 611 | 1 | 1 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
2 | 147 | DEZpxiHWY7fkyvQEaEGc | Summary | 1132 | 1.2 | 1.2 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
3 | 152 | QJ29ZvAvtEjBcpqHDer1 | Milestone | 0 | 1.2.3 | 1.2.3 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
4 | 158 | D5C8AUNeoI4YKF3PggKx | Summary | 255 | 1.2.7 | 1.2.7 |  | 2026-10-08 16:58 | p | 620 |  | 2028-06-20 14:26
5 | 155 | 1yu6CrDX9QU5hWE1UWMV | Milestone | 0 | 1.2.7.11 | 1.2.7.11 |  | 2026-10-08 16:58 | p | 620 |  | 2028-06-20 14:26
6 | 166 | KkWbk0R1FXz2L56lHFvV | Normal | 2 | 1.2.7.4 | 1.2.7.4 |  | 2025-09-18 17:00 | p | 17 |  | 2025-10-06 15:42
7 | 6618 | LspmB73Oe2b9O1GVbm64 | Milestone | 0 | 1.2.7.2 | 1.2.7.2 |  | 2025-04-30 17:00 | p | 15 |  | 2025-05-16 13:13
8 | 6636 | 3J1qFTgnrSSZVnoYdTv5 | Summary | 140 | 1.2.7.3 | 1.2.7.3 |  | 2025-09-16 17:00 | p | 15 |  | 2025-10-02 14:07
9 | 6338 | whnkqeDzsaW1H7xphaZA | Normal | 49 | 1.2.7.3.4 | 1.2.7.3.4 |  | 2025-07-23 17:00 | p | 15 |  | 2025-08-08 14:24
10 | 6640 | QUv6m7GotPkUb98mhJX7 | Normal | 14 | 1.2.7.3.6 | 1.2.7.3.6 |  | 2025-09-16 17:00 | p | 15 |  | 2025-10-02 14:07
11 | 6673 | sIWmvaXMX3ZF9ctRNm7s | Normal | 34 | 1.2.7.3.3 | 1.2.7.3.3 |  | 2025-03-28 17:00 | p | 26 |  | 2025-04-24 15:12
12 | 6872 | SjyWialEYK436pEnV5Nr | Normal | 1 | 1.2.7.5 | 1.2.7.5 |  | 2025-09-19 17:00 | p | 17 |  | 2025-10-07 13:03
13 | 6874 | 1XFpbhK6U752FQe8voXZ | Normal | 1 | 1.2.7.6 | 1.2.7.6 |  | 2026-01-30 15:00 | p | 33 |  | 2026-03-04 16:32
14 | 6878 | VU7w4voCV7rMMsz4AnPW | Normal | 1 | 1.2.7.10 | 1.2.7.10 |  | 2025-05-28 17:00 | q | 0 |  | 2025-05-28 09:06
15 | 6879 | Vbp0cBOXY9azJeyTE4S4 | Normal | 3 | 1.2.7.7 | 1.2.7.7 |  | 2026-03-20 15:00 | p | 32 |  | 2026-04-22 11:45
16 | 6880 | ZuauWvCPNW7n2NMscMO2 | Normal | 4 | 1.2.7.8 | 1.2.7.8 |  | 2026-07-30 16:58 | q | 0 |  | 2026-07-30 10:58
17 | 6881 | XekYY8n1P4vELtk4BUks | Normal | 1 | 1.2.7.9 | 1.2.7.9 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
18 | 7550 | fUEnUBwdI1z3bgOngjaQ | Milestone | 0 | 1.2.7.5 | 1.2.7.5 |  | 2025-11-13 08:00 | q | -37 |  | 2025-10-06 15:42
19 | 160 | gFTVv5U5XORyz5ZEYbdN | Summary | 703 | 1.2.8 | 1.2.8 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
20 | 168 | MT1CsCIMkhjJER6f3fjG | Milestone | 0 | 1.2.8.4 | 1.2.8.4 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
21 | 5294 | A0MDYkkQxesjEWQub0UM | Milestone | 0 | 1.2.8.3 | 1.2.8.3 |  | 2025-09-18 17:00 | p | 17 |  | 2025-10-06 13:01
22 | 172 | EY5PMcgR4N5ReAIF6NHn | Summary | 582 | 1.2.9 | 1.2.9 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
23 | 173 | vJHK0TlIBzGpfYqdt8YI | Milestone | 0 | 1.2.9.4 | 1.2.9.4 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
24 | 177 | V4ys3lAm8KEbtjGqLAuR | Milestone | 0 | 1.2.9.2 | 1.2.9.2 |  | 2025-10-21 12:00 | p | 28 |  | 2025-11-19 09:32
25 | 178 | Cncpm0GACo0ppNIEy1Gp | Milestone | 0 | 1.2.9.3 | 1.2.9.3 |  | 2025-10-27 12:00 | p | 29 |  | 2025-11-25 16:19
26 | 179 | jSOjvYE1qiHOKdcV2ixu | Summary | 554 | 1.2.10 | 1.2.10 |  | 2026-09-25 17:00 | p | 104 |  | 2027-01-08 08:25
27 | 180 | 9Vp3PBZnh9TpV8TGBWRG | Milestone | 0 | 1.2.10.14 | 1.2.10.14 |  | 2026-09-25 17:00 | p | 104 |  | 2027-01-08 08:25
28 | 193 | nJh7oj8wCJYW8hyepdLI | Milestone | 0 | 1.2.10.12 | 1.2.10.12 |  | 2025-09-09 17:00 | p | 12 |  | 2025-09-22 16:40
29 | 194 | wTcNF86mfD2cPQPmQB1c | Milestone | 0 | 1.2.10.13 | 1.2.10.13 |  | 2026-04-02 17:00 | p | 84 |  | 2026-06-26 11:47
30 | 7132 | osdxrWYmqQZxyGZXe9Pr | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 2025-03-24 17:00 | q | -31 |  | 2025-02-21 16:57
31 | 7546 | tdocr3pqURBYHZWcAyMG | Normal | 1 | 1.2.10.12 | 1.2.10.12 |  | 2025-03-28 17:00 | q | -91 |  | 2024-12-27 15:38
32 | 7547 | 2p5uMAQ0v8mT9pq4KeWp | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 2025-03-14 08:00 | q | -80 |  | 2024-12-23 17:00
33 | 7548 | TdNnLE8G4vf1vBjggzLw | Normal | 1 | 1.2.10.15 | 1.2.10.15 |  | 2025-03-10 17:00 | q | -73 |  | 2024-12-27 08:56
34 | 7549 | yUAt6Fi3Vichq9Ai1DSh | Normal | 1 | 1.2.10.13 | 1.2.10.13 |  | 2025-02-20 17:00 | q | -56 |  | 2024-12-26 08:22
35 | 195 | jWoM7YMyhsN7uWtVDNIl | Summary | 276 | 1.2.11 | 1.2.11 |  | 2026-07-31 12:00 | p | 929 |  | 2029-02-14 13:47
36 | 196 | kzYOxx4jS6vhIcTyxNFn | Milestone | 0 | 1.2.11.11 | 1.2.11.11 |  | 2026-07-31 12:00 | p | 929 |  | 2029-02-14 13:47
37 | 197 | LZAvhCOF77OBkAngJSDi | Milestone | 0 | 1.2.11.1 | 1.2.11.1 |  | 2025-06-23 17:00 | p | 933 |  | 2028-01-13 14:31
38 | 198 | X7Nxs9NuQXJ5Bf6aQwVp | Milestone | 0 | 1.2.11.2 | 1.2.11.2 |  | 2025-07-08 17:00 | p | 939 |  | 2028-02-03 15:25
39 | 199 | TiaYdQ98Ovd3qBAfSAyG | Milestone | 0 | 1.2.11.3 | 1.2.11.3 |  | 2025-07-22 17:00 | p | 940 |  | 2028-02-18 16:01
40 | 200 | yynHcCtrZd0Ye6iQJb2E | Milestone | 0 | 1.2.11.4 | 1.2.11.4 |  | 2025-08-06 17:00 | p | 942 |  | 2028-03-06 16:52
41 | 202 | mjF0YLun5LIdlxtu3zFl | Milestone | 0 | 1.2.11.5 | 1.2.11.5 |  | 2025-08-26 17:00 | p | 23 |  | 2025-09-19 09:47
42 | 203 | 2a1x42QofxcVsgjcXtkr | Milestone | 0 | 1.2.11.6 | 1.2.11.6 |  | 2025-06-23 17:00 | p | 933 |  | 2028-01-13 14:31
43 | 204 | 8T22gllTunmLl2jY7IMk | Milestone | 0 | 1.2.11.7 | 1.2.11.7 |  | 2025-07-08 17:00 | p | 939 |  | 2028-02-03 15:25
44 | 205 | dm3U5Xjvi5rN2LqWegXW | Milestone | 0 | 1.2.11.8 | 1.2.11.8 |  | 2025-07-22 17:00 | p | 940 |  | 2028-02-18 16:01
45 | 206 | ZOAcdJHtChBG5MUjo5uw | Milestone | 0 | 1.2.11.9 | 1.2.11.9 |  | 2025-08-06 17:00 | p | 942 |  | 2028-03-06 16:52
46 | 209 | 0FNuAiL5ZzPZSZ3dZfoV | Milestone | 0 | 1.2.11.10 | 1.2.11.10 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
47 | 6077 | 9YjbRTuPDmKPhAucMUDE | Milestone | 0 | 1.2.6 | 1.2.6 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
48 | 7015 | U0mup1noPd6mH1CxWGtr | Milestone | 0 | 1.2.5 | 1.2.5 |  | 2027-01-01 08:05 | p | 840 |  | 2029-04-20 09:27
49 | 7016 | pVOP21cemlwRUbhUeRME | Milestone | 0 | 1.2.4 | 1.2.4 |  | 2027-01-07 16:58 | p | 529 |  | 2028-06-20 14:26
50 | 150 | 7cu6yvdJV8ndF0CYMHk8 | Milestone | 0 | 1.1 | 1.1 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
51 | 4180 | LxVAz76PSOUu8y7B8sy3 | Summary | 218 | 1.3 | 1.3 |  | 2025-12-02 17:00 | p | 16 |  | 2025-12-19 09:31
52 | 384 | GE3w1SHplCQZN7aYDVw8 | Summary | 34 | 1.3.3 | 1.3.3 |  | 2025-09-18 17:00 | p | 17 |  | 2025-10-06 13:01
53 | 429 | Pbs0MxOqvHazWgB8fpDs | Summary | 41 | 1.3.3.2 | 1.3.3.2 |  | 2025-05-12 17:00 | p | 14 |  | 2025-05-27 08:33
54 | 436 | OGXVzK31PKUn8DxCdn94 | Normal | 33 | 1.3.3.2.10 | 1.3.3.2.10 |  | 2025-05-12 17:00 | p | 14 |  | 2025-05-27 08:33
55 | 437 | kEyeaq7ebxWRSvBqGkHC | Summary | 19 | 1.3.3.1 | 1.3.3.1 |  | 2025-03-04 17:00 | p | 28 |  | 2025-04-02 11:41
56 | 438 | QjVW4dYK4boDcUrG7MUx | Summary | 23 | 1.3.3.1.2 | 1.3.3.1.2 |  | 2025-03-04 17:00 | p | 28 |  | 2025-04-02 11:41
57 | 445 | cIIfBfMFMZUbJxswwNzj | Summary | 28 | 1.3.3.1.2.4 | 1.3.3.1.2.4 |  | 2025-03-04 17:00 | p | 28 |  | 2025-04-02 11:41
58 | 6438 | sSGfho0IWOHZYw1Z8jLl | Normal | 16 | 1.3.3.1.2.4.5 | 1.3.3.1.2.4.5 |  | 2025-03-04 17:00 | p | 28 |  | 2025-04-02 11:41
59 | 5768 | 9l9o7D6Il8vKVgGgZRMW | Summary | 197 | 1.3.3.4 | 1.3.3.4 |  | 2025-09-18 17:00 | p | 17 |  | 2025-10-06 13:01
60 | 428 | pxWL5EoMWeaDmapfAV7m | Normal | 2 | 1.3.3.4.2 | 1.3.3.4.2 |  | 2025-09-18 17:00 | p | 17 |  | 2025-10-06 13:01
61 | 6289 | NknbxY1EWobhbJ98SVRq | Summary | 270 | 1.3.2 | 1.3.2 |  | 2025-12-02 17:00 | p | 16 |  | 2025-12-19 09:31
62 | 3848 | g0gBmZeXCCPZTY4kkYs8 | Summary | 210 | 1.3.2.1 | 1.3.2.1 |  | 2025-12-02 17:00 | p | 14 |  | 2025-12-17 08:23
63 | 3849 | PKYN5IsyqbTocjyswPFM | Normal | 17 | 1.3.2.1.1 | 1.3.2.1.1 |  | 2025-03-14 17:00 | p | 23 |  | 2025-04-07 16:46
64 | 3850 | sk2pEdmn2KeVBRyrQzgn | Summary | 233 | 1.3.2.1.2 | 1.3.2.1.2 |  | 2025-12-02 17:00 | p | 14 |  | 2025-12-17 08:23
65 | 3857 | FObPKa3HJ5KI4gFmAx2r | Summary | 210 | 1.3.2.1.2.2 | 1.3.2.1.2.2 |  | 2025-11-03 17:00 | p | 43 |  | 2025-12-17 08:23
66 | 3858 | pWvg9Owxac1jXAINT5hs | Normal | 24 | 1.3.2.1.2.2.1 | 1.3.2.1.2.2.1 |  | 2025-03-14 17:00 | p | 23 |  | 2025-04-07 08:26
67 | 3859 | xrpLG6wlwOL4sRwHPU5B | Normal | 28 | 1.3.2.1.2.2.2 | 1.3.2.1.2.2.2 |  | 2025-04-23 17:00 | p | 21 |  | 2025-05-15 16:03
68 | 3861 | rvfyADOJtzNcPT3VL85f | Normal | 100 | 1.3.2.1.2.2.3 | 1.3.2.1.2.2.3 |  | 2025-10-03 17:00 | p | 46 |  | 2025-11-19 09:25
69 | 3862 | FUtleP4nAJHYxzLOWKZH | Normal | 20 | 1.3.2.1.2.2.4 | 1.3.2.1.2.2.4 |  | 2025-11-03 17:00 | p | 43 |  | 2025-12-17 08:23
70 | 3863 | WaF24jcpD2qzV3M05hSl | Summary | 178 | 1.3.2.1.2.3 | 1.3.2.1.2.3 |  | 2025-12-02 17:00 | p | 12 |  | 2025-12-15 14:11
71 | 3864 | kkmwKYrSq6DehQmbGkxo | Summary | 90 | 1.3.2.1.2.3.2 | 1.3.2.1.2.3.2 |  | 2025-12-02 17:00 | p | 12 |  | 2025-12-15 14:11
72 | 3865 | ZK3GDclfde20Vh8DU71K | Normal | 30 | 1.3.2.1.2.3.2.1 | 1.3.2.1.2.3.2.1 |  | 2025-09-04 17:00 | p | 19 |  | 2025-09-24 11:48
73 | 3866 | 8Zrc7ItBhrTjO1TWxqmf | Normal | 20 | 1.3.2.1.2.3.2.2 | 1.3.2.1.2.3.2.2 |  | 2025-10-02 17:00 | p | 14 |  | 2025-10-17 08:06
74 | 3867 | l8TRHVr9p6bfQBwzbTty | Normal | 5 | 1.3.2.1.2.3.2.5 | 1.3.2.1.2.3.2.5 |  | 2025-11-07 17:00 | p | 17 |  | 2025-11-25 09:06
75 | 3868 | NCkZSbtMfUxIg95lxXXn | Normal | 10 | 1.3.2.1.2.3.2.6 | 1.3.2.1.2.3.2.6 |  | 2025-11-24 17:00 | p | 13 |  | 2025-12-08 14:21
76 | 3869 | wbVbYxDNomEEsv0XDKnQ | Normal | 5 | 1.3.2.1.2.3.2.7 | 1.3.2.1.2.3.2.7 |  | 2025-12-02 17:00 | p | 12 |  | 2025-12-15 14:11
77 | 6562 | Z3AfJmLBpOLyJb1GhvwC | Normal | 10 | 1.3.2.1.2.3.2.3 | 1.3.2.1.2.3.2.3 |  | 2025-10-17 17:00 | p | 12 |  | 2025-10-30 14:23
78 | 6563 | 7FPcbor42GN7O6Ym4IZM | Normal | 10 | 1.3.2.1.2.3.2.4 | 1.3.2.1.2.3.2.4 |  | 2025-10-31 17:00 | p | 16 |  | 2025-11-17 16:33
79 | 7186 | ttl1FahPn0WwOuyGdmk6 | Summary | 138 | 1.3.2.3 | 1.3.2.3 |  | 2025-11-26 17:00 | p | 22 |  | 2025-12-19 09:31
80 | 7188 | yn5QOVI2BZ7jor10JaQN | Summary | 55 | 1.3.2.3.2 | 1.3.2.3.2 |  | 2025-05-16 17:00 | q | 0 |  | 2025-05-16 10:05
81 | 7189 | jup7puBG1dNvbV8jB14f | Summary | 69 | 1.3.2.3.2.1 | 1.3.2.3.2.1 |  | 2025-05-16 17:00 | q | -14 |  | 2025-05-02 15:39
82 | 7190 | Ob13piboJI4zFNOVPzZD | Summary | 50 | 1.3.2.3.2.1.1 | 1.3.2.3.2.1.1 |  | 2025-03-10 17:00 | q | -24 |  | 2025-02-14 10:33
83 | 7192 | rcBSOCAYFUxP7jsyoqGw | Normal | 11 | 1.3.2.3.2.1.1.2 | 1.3.2.3.2.1.1.2 |  | 2025-03-10 17:00 | q | -24 |  | 2025-02-14 10:33
84 | 7193 | hzdeRXxytBFeNJPq5eHn | Summary | 50 | 1.3.2.3.2.1.2 | 1.3.2.3.2.1.2 |  | 2025-04-21 17:00 | q | -32 |  | 2025-03-20 13:33
85 | 7194 | mB0uoGZ1D1fuFzk350Kb | Normal | 30 | 1.3.2.3.2.1.2.1 | 1.3.2.3.2.1.2.1 |  | 2025-04-21 17:00 | q | -32 |  | 2025-03-20 13:33
86 | 7196 | fFBpC2vR2qp5KXHLtypR | Summary | 23 | 1.3.2.3.2.1.3 | 1.3.2.3.2.1.3 |  | 2025-03-10 17:00 | p | 27 |  | 2025-04-07 15:15
87 | 7199 | G7LfPy6euQCIQjteO0x8 | Normal | 20 | 1.3.2.3.2.1.3.3 | 1.3.2.3.2.1.3.3 |  | 2025-03-10 17:00 | p | 27 |  | 2025-04-07 15:15
88 | 7200 | 7Va2LPPEsZrLZmgpV2qc | Summary | 19 | 1.3.2.3.2.1.4 | 1.3.2.3.2.1.4 |  | 2025-05-16 17:00 | q | -14 |  | 2025-05-02 15:39
89 | 7201 | UKbpgMkpfrIPVoEOJEeO | Normal | 10 | 1.3.2.3.2.1.4.1 | 1.3.2.3.2.1.4.1 |  | 2025-05-05 17:00 | q | -14 |  | 2025-04-21 10:40
90 | 7202 | vy1jnuopIHJe5PhTsUNw | Normal | 5 | 1.3.2.3.2.1.4.2 | 1.3.2.3.2.1.4.2 |  | 2025-05-12 17:00 | q | -14 |  | 2025-04-28 14:19
91 | 7203 | KqVHIBvrHNAu5GlarotD | Normal | 3 | 1.3.2.3.2.1.4.3 | 1.3.2.3.2.1.4.3 |  | 2025-05-15 17:00 | q | -14 |  | 2025-05-01 15:00
92 | 7204 | BUAmcwglNtP3GEkJsPLR | Normal | 1 | 1.3.2.3.2.1.4.4 | 1.3.2.3.2.1.4.4 |  | 2025-05-16 17:00 | q | -14 |  | 2025-05-02 15:39
93 | 7205 | 688LmElxek6WZQ34zEgD | Summary | 40 | 1.3.2.3.2.2 | 1.3.2.3.2.2 |  | 2025-03-28 17:00 | p | 26 |  | 2025-04-24 15:38
94 | 7206 | bMXBNIC1fF7AjliDPdfr | Normal | 25 | 1.3.2.3.2.2.1 | 1.3.2.3.2.2.1 |  | 2025-03-17 17:00 | p | 27 |  | 2025-04-14 15:15
95 | 7207 | 51ZGrscW6XrNzeOMbLyw | Normal | 5 | 1.3.2.3.2.2.2 | 1.3.2.3.2.2.2 |  | 2025-03-24 17:00 | p | 24 |  | 2025-04-18 11:26
96 | 7208 | 5Vu53Z23NG8K3uSzUcYA | Normal | 3 | 1.3.2.3.2.2.3 | 1.3.2.3.2.2.3 |  | 2025-03-27 17:00 | p | 26 |  | 2025-04-23 15:28
97 | 7209 | r8OmtZddpdGbVxNEynIO | Normal | 1 | 1.3.2.3.2.2.4 | 1.3.2.3.2.2.4 |  | 2025-03-28 17:00 | p | 26 |  | 2025-04-24 15:38
98 | 7210 | 5vpOUfvEpSU2AKPwltv0 | Summary | 14 | 1.3.2.3.2.3 | 1.3.2.3.2.3 |  | 2025-02-28 17:00 | q | -1 |  | 2025-02-27 10:09
99 | 7212 | IA5BwO4PzPuXs5yI3XzH | Normal | 5 | 1.3.2.3.2.3.2 | 1.3.2.3.2.3.2 |  | 2025-02-24 17:00 | q | -3 |  | 2025-02-21 09:11
100 | 7213 | GkAhONTSL0EMIVzc5bXh | Normal | 3 | 1.3.2.3.2.3.3 | 1.3.2.3.2.3.3 |  | 2025-02-27 17:00 | q | -1 |  | 2025-02-26 09:58
101 | 7214 | ysGFXohNyFRFQ06jmkjW | Normal | 1 | 1.3.2.3.2.3.4 | 1.3.2.3.2.3.4 |  | 2025-02-28 17:00 | q | -1 |  | 2025-02-27 10:09
102 | 7215 | a8OJFGtOVEyM75c9puYK | Summary | 34 | 1.3.2.3.2.4 | 1.3.2.3.2.4 |  | 2025-03-28 17:00 | p | 11 |  | 2025-04-09 09:47
103 | 7220 | nvywSXdnd0LSUGSiB3or | Normal | 10 | 1.3.2.3.2.4.5 | 1.3.2.3.2.4.5 |  | 2025-02-27 17:00 | p | 3 |  | 2025-03-03 15:22
104 | 7221 | PYoR7OoHLcblZDJJ1hTC | Normal | 20 | 1.3.2.3.2.4.6 | 1.3.2.3.2.4.6 |  | 2025-03-27 17:00 | p | 11 |  | 2025-04-08 09:39
105 | 7222 | W1KVKgORO9KqmU1uQFqG | Normal | 1 | 1.3.2.3.2.4.7 | 1.3.2.3.2.4.7 |  | 2025-03-28 17:00 | p | 11 |  | 2025-04-09 09:47
106 | 7223 | 2cLCJpvBPh4ccgbvKrEi | Summary | 38 | 1.3.2.3.2.5 | 1.3.2.3.2.5 |  | 2025-04-07 17:00 | p | 38 |  | 2025-05-16 10:05
107 | 7227 | QiFvht1v2EB9ODLdNK6M | Normal | 25 | 1.3.2.3.2.5.4 | 1.3.2.3.2.5.4 |  | 2025-03-17 17:00 | p | 35 |  | 2025-04-22 16:25
108 | 7228 | SSqxRWtJ8NkhLwkx3Zp5 | Normal | 15 | 1.3.2.3.2.5.5 | 1.3.2.3.2.5.5 |  | 2025-04-07 17:00 | p | 38 |  | 2025-05-16 10:05
109 | 7514 | 4jhJaLUHxegkfPxUyChC | Normal | 15 | 1.3.2.3.2.5.9 | 1.3.2.3.2.5.9 |  | 2025-03-10 17:00 | q | -3 |  | 2025-03-07 14:10
110 | 7231 | Kz2H44CrN943Xn6RI0Et | Summary | 19 | 1.3.2.3.3 | 1.3.2.3.3 |  | 2025-08-19 17:00 | p | 16 |  | 2025-09-05 14:36
111 | 7232 | cCMYeGs7uzTIiiDhvAui | Summary | 12 | 1.3.2.3.3.1 | 1.3.2.3.3.1 |  | 2025-08-08 17:00 | p | 17 |  | 2025-08-26 10:04
112 | 7233 | rgerXXfH5cOVWHlSbXtk | Normal | 2 | 1.3.2.3.3.1.1 | 1.3.2.3.3.1.1 |  | 2025-07-25 17:00 | p | 17 |  | 2025-08-12 11:23
113 | 7234 | 4Nk8AWONEAABjENRSl4s | Normal | 3 | 1.3.2.3.3.1.2 | 1.3.2.3.3.1.2 |  | 2025-07-28 17:00 | p | 15 |  | 2025-08-13 16:17
114 | 7235 | uR7e5eYUOS8ur8CkZgir | Normal | 2 | 1.3.2.3.3.1.3 | 1.3.2.3.3.1.3 |  | 2025-07-30 17:00 | p | 18 |  | 2025-08-18 09:29
115 | 7236 | OqdHv6QLhEyFdmarh5Mg | Normal | 5 | 1.3.2.3.3.1.4 | 1.3.2.3.3.1.4 |  | 2025-07-30 17:00 | p | 18 |  | 2025-08-18 13:54
116 | 7237 | xLl9f1S8pVLgozw4LZw4 | Normal | 10 | 1.3.2.3.3.1.5 | 1.3.2.3.3.1.5 |  | 2025-08-06 17:00 | p | 14 |  | 2025-08-21 10:04
117 | 7238 | hj0QAuvemNr4BSx0wqCM | Normal | 10 | 1.3.2.3.3.1.6 | 1.3.2.3.3.1.6 |  | 2025-08-06 17:00 | p | 15 |  | 2025-08-22 13:46
118 | 7239 | sGRMuNmZsu5Ap3rRR6Ja | Normal | 2 | 1.3.2.3.3.1.7 | 1.3.2.3.3.1.7 |  | 2025-08-08 17:00 | p | 17 |  | 2025-08-26 10:04
119 | 7240 | jJgg05qz3M4QbDAQ4nmn | Summary | 7 | 1.3.2.3.3.2 | 1.3.2.3.3.2 |  | 2025-08-19 17:00 | p | 16 |  | 2025-09-05 14:36
120 | 7241 | RP09WyAKLetAyeWXIWbd | Normal | 1 | 1.3.2.3.3.2.1 | 1.3.2.3.3.2.1 |  | 2025-08-11 17:00 | p | 15 |  | 2025-08-27 11:29
121 | 7242 | PNiOufePi0cnwKsaAHa8 | Normal | 3 | 1.3.2.3.3.2.2 | 1.3.2.3.3.2.2 |  | 2025-08-14 17:00 | p | 18 |  | 2025-09-02 09:31
122 | 7243 | nppwsC1hz1MTRepHit5q | Normal | 3 | 1.3.2.3.3.2.3 | 1.3.2.3.3.2.3 |  | 2025-08-19 17:00 | p | 16 |  | 2025-09-05 14:36
123 | 7244 | FpvbIzqyAjmrguHRtjoA | Summary | 68 | 1.3.2.3.4 | 1.3.2.3.4 |  | 2025-11-26 17:00 | p | 22 |  | 2025-12-19 09:31
124 | 7245 | ysJ2Wz17vAaH50NFOd3r | Normal | 2 | 1.3.2.3.4.1 | 1.3.2.3.4.1 |  | 2025-08-21 17:00 | p | 19 |  | 2025-09-10 10:05
125 | 7246 | w8OYvCOBO1azAOar59yv | Normal | 3 | 1.3.2.3.4.2 | 1.3.2.3.4.2 |  | 2025-08-22 17:00 | p | 18 |  | 2025-09-10 09:32
126 | 7247 | QmLDbLdk9YgltF6FQxKi | Normal | 2 | 1.3.2.3.4.3 | 1.3.2.3.4.3 |  | 2025-08-26 17:00 | p | 16 |  | 2025-09-12 09:49
127 | 7248 | nqyBToLUXvLl91VDFcK9 | Summary | 20 | 1.3.2.3.4.4 | 1.3.2.3.4.4 |  | 2025-09-17 17:00 | p | 19 |  | 2025-10-07 14:40
128 | 7249 | T3rEQsXy5TFYVzdnmRkQ | Normal | 20 | 1.3.2.3.4.4.1 | 1.3.2.3.4.4.1 |  | 2025-09-17 17:00 | p | 15 |  | 2025-10-03 15:17
129 | 7250 | G5mdz8DmOa8TGNlmxmOk | Normal | 20 | 1.3.2.3.4.4.2 | 1.3.2.3.4.4.2 |  | 2025-09-17 17:00 | p | 19 |  | 2025-10-07 14:40
130 | 7251 | p2IEwFFq1YxDgQwaqReT | Summary | 48 | 1.3.2.3.4.5 | 1.3.2.3.4.5 |  | 2025-11-26 17:00 | p | 22 |  | 2025-12-19 09:31
131 | 7252 | R4hlQqYwslHcXudIUORM | Normal | 20 | 1.3.2.3.4.5.1 | 1.3.2.3.4.5.1 |  | 2025-10-16 17:00 | p | 24 |  | 2025-11-10 09:00
132 | 7253 | 5Q6OCjUddDwnqpg2shNG | Normal | 5 | 1.3.2.3.4.5.2 | 1.3.2.3.4.5.2 |  | 2025-10-23 17:00 | p | 25 |  | 2025-11-18 09:39
133 | 7254 | aZsc8OQGYCtOtLNUDl4p | Normal | 7 | 1.3.2.3.4.5.3 | 1.3.2.3.4.5.3 |  | 2025-11-03 17:00 | p | 22 |  | 2025-11-26 15:22
134 | 7255 | GiGIxdlKVFOGW1rlVkpg | Normal | 5 | 1.3.2.3.4.5.4 | 1.3.2.3.4.5.4 |  | 2025-11-10 17:00 | p | 23 |  | 2025-12-04 15:27
135 | 7256 | ZTFxKau19KKCcFlUDIYg | Normal | 7 | 1.3.2.3.4.5.5 | 1.3.2.3.4.5.5 |  | 2025-11-20 17:00 | p | 25 |  | 2025-12-16 08:47
136 | 7257 | EmkT3sq6aGy3vx96JSsX | Normal | 3 | 1.3.2.3.4.5.6 | 1.3.2.3.4.5.6 |  | 2025-11-25 17:00 | p | 22 |  | 2025-12-18 10:41
137 | 7258 | PBxke5bv0Yk6xXbQcvVe | Normal | 1 | 1.3.2.3.4.5.7 | 1.3.2.3.4.5.7 |  | 2025-11-26 17:00 | p | 22 |  | 2025-12-19 09:31
138 | 6269 | tUCxonMalaI13D6hsUSU | Summary | 99 | 1.5 | 1.5 |  | 2026-02-02 12:00 | p | 16 |  | 2026-02-18 15:29
139 | 6278 | SNMcp7h74WVvBiN3lPNB | Summary | 66 | 1.5.6 | 1.5.6 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
140 | 605 | HP2TrbmUH5Qc4V2P2k1T | Normal | 14 | 1.5.6.1 | 1.5.6.1 |  | 2025-02-28 17:00 | p | 33 |  | 2025-04-03 08:33
141 | 620 | q8advjPa5PEndSFXJ05j | Summary | 158 | 1.5.6.6 | 1.5.6.6 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
142 | 622 | Q48N5ZSDLesB1Bsda2wx | Summary | 156 | 1.5.6.6.2 | 1.5.6.6.2 |  | 2025-10-21 12:00 | p | 28 |  | 2025-11-19 09:32
143 | 632 | tuv9OmQcJHKkVCVrbrrv | Normal | 6 | 1.5.6.6.2.8 | 1.5.6.6.2.8 |  | 2025-02-20 17:00 | p | 0 |  | 2025-02-21 10:54
144 | 633 | FgJ5XjjThZN85XQOJ0nJ | Normal | 21 | 1.5.6.6.2.10 | 1.5.6.6.2.10 |  | 2025-07-18 17:00 | p | 30 |  | 2025-08-18 13:19
145 | 634 | o4DRQRcsScdVmCSXNbxF | Normal | 10 | 1.5.6.6.2.9 | 1.5.6.6.2.9 |  | 2025-08-01 12:00 | p | 32 |  | 2025-09-02 15:12
146 | 635 | ztvy5zkS4z9HirKgvHGY | Normal | 20 | 1.5.6.6.2.11 | 1.5.6.6.2.11 |  | 2025-08-29 12:00 | p | 27 |  | 2025-09-26 11:01
147 | 636 | ZpIfqMwIaczq2BqznW2q | Normal | 6 | 1.5.6.6.2.12 | 1.5.6.6.2.12 |  | 2025-09-09 12:00 | p | 28 |  | 2025-10-08 09:26
148 | 637 | 3VAZwvp2NS6usl0wrvOM | Normal | 7 | 1.5.6.6.2.13 | 1.5.6.6.2.13 |  | 2025-09-18 12:00 | p | 31 |  | 2025-10-20 11:33
149 | 638 | 34zoFClD9RS7gLTCPZs0 | Normal | 5 | 1.5.6.6.2.14 | 1.5.6.6.2.14 |  | 2025-09-25 12:00 | p | 31 |  | 2025-10-27 11:29
150 | 640 | 10AmMHkCz4b8n0xqbyCt | Normal | 5 | 1.5.6.6.2.16 | 1.5.6.6.2.16 |  | 2025-10-02 12:00 | p | 29 |  | 2025-10-31 16:23
151 | 641 | KUqcSNVxncHPLVJNV5ca | Normal | 2 | 1.5.6.6.2.17 | 1.5.6.6.2.17 |  | 2025-10-03 17:00 | p | 31 |  | 2025-11-04 08:38
152 | 642 | chCwawHUqn0ea2ArCnKB | Normal | 0 | 1.5.6.6.2.18 | 1.5.6.6.2.18 |  | 2025-10-06 12:00 | p | 29 |  | 2025-11-04 12:00
153 | 643 | xZBRzE3QVYmQCjnzxLQv | Normal | 4 | 1.5.6.6.2.19 | 1.5.6.6.2.19 |  | 2025-10-10 12:00 | p | 31 |  | 2025-11-10 15:13
154 | 644 | tUTeQ74YpmkuuOiouSXU | Normal | 5 | 1.5.6.6.2.20 | 1.5.6.6.2.20 |  | 2025-10-20 12:00 | p | 28 |  | 2025-11-18 10:28
155 | 645 | mSrjcTZmK12EdJmOEYFi | Normal | 1 | 1.5.6.6.2.21 | 1.5.6.6.2.21 |  | 2025-10-21 12:00 | p | 28 |  | 2025-11-19 09:32
156 | 646 | Haue3rYYySw3jbXWnBeq | Normal | 3 | 1.5.6.6.3 | 1.5.6.6.3 |  | 2025-10-24 12:00 | p | 31 |  | 2025-11-24 16:06
157 | 647 | 6jlP0Y4QQ5KPQWxvolLg | Normal | 1 | 1.5.6.6.4 | 1.5.6.6.4 |  | 2025-10-27 12:00 | p | 29 |  | 2025-11-25 16:19
158 | 648 | 6WPgljRre9DjhHGVsVUH | Summary | 120 | 1.5.6.6.5 | 1.5.6.6.5 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
159 | 656 | lzPFAx9Fh8cDxyQ3uxFX | Normal | 1 | 1.5.6.6.5.3 | 1.5.6.6.5.3 |  | 2025-10-28 15:00 | p | 30 |  | 2025-11-28 09:44
160 | 657 | nePaKBbqDo6OltylvukE | Summary | 14 | 1.5.6.6.5.4 | 1.5.6.6.5.4 |  | 2025-11-18 15:00 | p | 28 |  | 2025-12-17 14:16
161 | 658 | PyBKEPMZMe2YeOC66yut | Normal | 11 | 1.5.6.6.5.4.1 | 1.5.6.6.5.4.1 |  | 2025-11-13 15:00 | p | 28 |  | 2025-12-12 13:16
162 | 664 | H1KB0K8mM12Opvc4oDP1 | Normal | 3 | 1.5.6.6.5.4.2 | 1.5.6.6.5.4.2 |  | 2025-11-18 15:00 | p | 28 |  | 2025-12-17 14:16
163 | 665 | FIEbexlYHnOcZkEBs7WM | Normal | 5 | 1.5.6.6.5.5 | 1.5.6.6.5.5 |  | 2025-11-26 15:00 | p | 30 |  | 2025-12-26 15:53
164 | 666 | OcAHNnZWZgiwxfUiheGU | Normal | 5 | 1.5.6.6.5.6 | 1.5.6.6.5.6 |  | 2025-12-04 15:00 | p | 28 |  | 2026-01-02 14:34
165 | 667 | HPj21Hyun1nWvxJOQMhf | Normal | 28 | 1.5.6.6.5.7 | 1.5.6.6.5.7 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
166 | 670 | zBtIFoyMK1KgXAv407C9 | Summary | 29 | 1.5.6.5 | 1.5.6.5 |  | 2025-11-19 15:00 | p | 29 |  | 2025-12-18 16:45
167 | 671 | ZM52W2kHJJCM7052Da3J | Normal | 2 | 1.5.6.5.2 | 1.5.6.5.2 |  | 2025-10-28 12:00 | p | 29 |  | 2025-11-26 13:52
168 | 672 | AcRvLPQ7WrNfvcLBOWzV | Normal | 1 | 1.5.6.5.3 | 1.5.6.5.3 |  | 2025-11-19 15:00 | p | 29 |  | 2025-12-18 16:45
169 | 6281 | RYPcKAyzQapOQ3GupQll | Summary | 104 | 1.5.5 | 1.5.5 |  | 2025-04-04 17:00 | p | 26 |  | 2025-05-01 16:08
170 | 1466 | LmBGiI2jXQ3lZF0l79sj | Summary | 104 | 1.5.5.1 | 1.5.5.1 |  | 2025-04-04 17:00 | p | 26 |  | 2025-05-01 16:08
171 | 1458 | W2l89btZYbaZZjxZTUR4 | Normal | 12 | 1.5.5.1.3 | 1.5.5.1.3 |  | 2025-03-05 17:00 | p | 0 |  | 2025-03-06 09:25
172 | 1459 | MxsNofofvf6CR0hsGInx | Normal | 1 | 1.5.5.1.4 | 1.5.5.1.4 |  | 2025-03-06 17:00 | p | 0 |  | 2025-03-07 09:07
173 | 1468 | 8e77YoSi4abIbMILI8hH | Normal | 5 | 1.5.5.1.5 | 1.5.5.1.5 |  | 2025-02-14 17:00 | p | 30 |  | 2025-03-17 15:37
174 | 1469 | MZooHRTMNCHrNy0nPaCQ | Normal | 1 | 1.5.5.1.6 | 1.5.5.1.6 |  | 2025-02-18 17:00 | p | 27 |  | 2025-03-18 16:39
175 | 1470 | PdTqfNwd2IKBXe26tWkB | Normal | 1 | 1.5.5.1.8 | 1.5.5.1.8 |  | 2025-03-07 17:00 | p | 25 |  | 2025-04-02 10:21
176 | 1471 | FsiT4ZMTOq9hGqZQQdYf | Normal | 11 | 1.5.5.1.9 | 1.5.5.1.9 |  | 2025-03-24 17:00 | p | 27 |  | 2025-04-21 16:39
177 | 1472 | KG0YDAdikr58WjA79FVb | Normal | 9 | 1.5.5.1.10 | 1.5.5.1.10 |  | 2025-04-04 17:00 | p | 26 |  | 2025-05-01 16:08
178 | 4584 | H2uIo7s6dGmX6mrjT7jd | Normal | 9 | 1.5.5.1.7 | 1.5.5.1.7 |  | 2025-03-03 17:00 | p | 27 |  | 2025-03-31 15:24
179 | 6292 | 1Cm9NXihvfL2WEnYcHvT | Summary | 42 | 1.5.4 | 1.5.4 |  | 2025-04-02 17:00 | p | 36 |  | 2025-05-09 13:29
180 | 3944 | HRTLaCTjRjqysGxmE6ve | Normal | 36 | 1.5.4.2 | 1.5.4.2 |  | 2025-04-01 17:00 | p | 30 |  | 2025-05-02 11:55
181 | 3945 | bJfaWXH8yBacWp0eqnXx | Normal | 1 | 1.5.4.3 | 1.5.4.3 |  | 2025-04-02 17:00 | p | 32 |  | 2025-05-05 14:25
182 | 3949 | knRWxUZkgPmXKgij09tb | Summary | 25 | 1.5.4.5 | 1.5.4.5 |  | 2025-04-02 17:00 | p | 36 |  | 2025-05-09 13:29
183 | 3950 | NJx1RMKdqhuNKRLGMSBQ | Summary | 27 | 1.5.4.5.1 | 1.5.4.5.1 |  | 2025-04-02 17:00 | p | 36 |  | 2025-05-09 13:29
184 | 3951 | BNWJw3sHADBJTHA2Ybu0 | Normal | 16 | 1.5.4.5.1.1 | 1.5.4.5.1.1 |  | 2025-03-21 17:00 | p | 38 |  | 2025-04-29 09:11
185 | 3952 | HkhDGF3pWO8GORFQnyh9 | Normal | 5 | 1.5.4.5.1.2 | 1.5.4.5.1.2 |  | 2025-03-28 17:00 | p | 38 |  | 2025-05-06 10:35
186 | 3953 | dYr7YcYkpYYUeESNUSkl | Normal | 2 | 1.5.4.5.1.3 | 1.5.4.5.1.3 |  | 2025-04-01 17:00 | p | 36 |  | 2025-05-08 11:53
187 | 3954 | r37KEs6OIDoMKT5Yz5nA | Normal | 1 | 1.5.4.5.1.4 | 1.5.4.5.1.4 |  | 2025-04-02 17:00 | p | 36 |  | 2025-05-09 13:29
188 | 3964 | ZzcX1hV2BTbfmTYJl5AE | Summary | 19 | 1.5.4.5.4 | 1.5.4.5.4 |  | 2025-03-07 17:00 | p | 38 |  | 2025-04-15 09:11
189 | 3967 | BaECEBO5p44IeRhOgeK2 | Normal | 19 | 1.5.4.5.4.3 | 1.5.4.5.4.3 |  | 2025-03-07 17:00 | p | 38 |  | 2025-04-15 09:11
190 | 5996 | M6DLFbZyZKXroBVfXncj | Summary | 19 | 1.5.4.4 | 1.5.4.4 |  | 2025-02-28 17:00 | p | 27 |  | 2025-03-28 14:33
191 | 3948 | 6ze4BjeYc1B5uifD0Fqa | Normal | 10 | 1.5.4.4.9 | 1.5.4.4.9 |  | 2025-02-25 17:00 | p | 29 |  | 2025-03-27 11:44
192 | 6202 | X3XRH6pSpuIgaacqwHSp | Normal | 14 | 1.5.4.4.10 | 1.5.4.4.10 |  | 2025-02-28 17:00 | p | 27 |  | 2025-03-28 14:33
193 | 6605 | Qtljmhuq3GHp8HrV3pPP | Normal | 6 | 1.5.4.4.7 | 1.5.4.4.7 |  | 2025-02-18 17:00 | p | 29 |  | 2025-03-20 10:14
194 | 6606 | pKonEcYtBOhP3mqLQIUx | Normal | 5 | 1.5.4.4.8 | 1.5.4.4.8 |  | 2025-02-25 17:00 | p | 29 |  | 2025-03-27 11:44
195 | 6299 | JvNaxkj9UdrgV7BcBski | Summary | 134 | 1.5.1 | 1.5.1 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
196 | 4213 | pNBoUl9px0n4wFhfXXqQ | Summary | 90 | 1.5.1.1 | 1.5.1.1 |  | 2025-06-17 17:00 | p | 33 |  | 2025-07-21 15:45
197 | 4215 | I07WrBLpDQufO3mvIdSu | Normal | 1 | 1.5.1.1.4 | 1.5.1.1.4 |  | 2025-06-17 17:00 | p | 33 |  | 2025-07-21 15:45
198 | 6444 | XymP4MvJgra2aDdoc9vw | Normal | 46 | 1.5.1.1.2 | 1.5.1.1.2 |  | 2025-04-15 17:00 | p | 19 |  | 2025-05-05 08:35
199 | 6445 | Wo6GLLiu9tXQyZ8t43hX | Normal | 43 | 1.5.1.1.3 | 1.5.1.1.3 |  | 2025-06-16 17:00 | p | 31 |  | 2025-07-18 16:22
200 | 6081 | VjHQD510O4fPJGbP9Knq | Normal | 1 | 1.5.1.2 | 1.5.1.2 |  | 2026-01-15 15:00 | p | 34 |  | 2026-02-18 15:29
201 | 6674 | 3EUoGYyEaAia67bx8maJ | Summary | 69 | 1.5.1.3 | 1.5.1.3 |  | 2025-05-27 17:00 | q | 0 |  | 2025-05-27 08:17
202 | 6680 | ttlvn3uwilh7nqgbHtE7 | Normal | 37 | 1.5.1.3.7 | 1.5.1.3.7 |  | 2025-04-02 17:00 | p | 32 |  | 2025-05-05 10:33
203 | 6681 | NHiN8b86HRxpkLb9JGGD | Normal | 10 | 1.5.1.3.9 | 1.5.1.3.9 |  | 2025-04-17 17:00 | p | 34 |  | 2025-05-22 09:52
204 | 6682 | 695WEwNqpcHeAbXSBRci | Normal | 2 | 1.5.1.3.10 | 1.5.1.3.10 |  | 2025-05-27 17:00 | q | 0 |  | 2025-05-27 08:17
205 | 6684 | TL3Mtv3QlGNejnoXktH7 | Normal | 1 | 1.5.1.3.8 | 1.5.1.3.8 |  | 2025-04-03 17:00 | p | 32 |  | 2025-05-06 13:11
206 | 6308 | 9d1kbrq4aHbr7FOmo76u | Summary | 27 | 1.5.2 | 1.5.2 |  | 2025-04-10 17:00 | q | -3 |  | 2025-04-07 10:08
207 | 5611 | e3AOkT5PZcArPsKmcVqB | Summary | 48 | 1.5.2.2 | 1.5.2.2 |  | 2025-04-10 17:00 | q | -3 |  | 2025-04-07 10:08
208 | 5612 | JBIAfh9fImNsEXfXoHCz | Summary | 5 | 1.5.2.2.10 | 1.5.2.2.10 |  | 2025-03-10 17:00 | q | 0 |  | 2025-03-10 10:07
209 | 5613 | cc9QdsdOkkgaQ8ateKZX | Normal | 1 | 1.5.2.2.10.1 | 1.5.2.2.10.1 |  | 2025-03-05 09:36 | q | 0 |  | 2025-03-04 10:46
210 | 5614 | COTl0owSvMhEdF9iuXCz | Normal | 0 | 1.5.2.2.10.2 | 1.5.2.2.10.2 |  | 2025-03-05 14:36 | q | 0 |  | 2025-03-04 16:11
211 | 5615 | 0lLRNnxfg3utwoPLwt26 | Normal | 2 | 1.5.2.2.10.3 | 1.5.2.2.10.3 |  | 2025-03-07 14:36 | q | 0 |  | 2025-03-06 16:11
212 | 5616 | 5Z54Ad8GhuwKLjQHaz2Y | Normal | 1 | 1.5.2.2.10.4 | 1.5.2.2.10.4 |  | 2025-03-10 14:36 | q | -2 |  | 2025-03-07 16:45
213 | 5617 | fALGtnsfw381gf0W53Ia | Normal | 0 | 1.5.2.2.10.5 | 1.5.2.2.10.5 |  | 2025-03-10 17:00 | q | 0 |  | 2025-03-10 10:07
214 | 5627 | s0vjJX7zGlVyBdE0eigo | Summary | 15 | 1.5.2.2.8 | 1.5.2.2.8 |  | 2025-03-03 17:00 | q | 0 |  | 2025-03-03 08:55
215 | 5628 | JolyrZVyKy7n75ZL5gZI | Normal | 2 | 1.5.2.2.8.1 | 1.5.2.2.8.1 |  | 2025-02-20 12:00 | q | 0 |  | 2025-02-20 11:50
216 | 5629 | ghMhRqrbgVxCQv51dU2T | Normal | 0 | 1.5.2.2.8.2 | 1.5.2.2.8.2 |  | 2025-02-20 17:00 | p | 0 |  | 2025-02-21 08:01
217 | 5630 | eU3bwvC6wgraOvc5hiLt | Milestone | 0 | 1.5.2.2.8.3 | 1.5.2.2.8.3 |  | 2025-02-20 17:00 | p | 0 |  | 2025-02-21 08:01
218 | 5631 | gvTQVNdftDRXYXclyMFo | Normal | 3 | 1.5.2.2.8.4 | 1.5.2.2.8.4 |  | 2025-02-25 17:00 | q | 0 |  | 2025-02-25 15:53
219 | 5632 | DfRDIp64TG1m6LE7SSYQ | Milestone | 0 | 1.5.2.2.8.5 | 1.5.2.2.8.5 |  | 2025-02-25 17:00 | q | 0 |  | 2025-02-25 15:53
220 | 5633 | 2UPBwQymcCOUpuUjnBTe | Normal | 3 | 1.5.2.2.8.6 | 1.5.2.2.8.6 |  | 2025-02-28 17:00 | q | 0 |  | 2025-02-28 08:37
221 | 5634 | gm5pLWvICR0pU7aShOGD | Normal | 1 | 1.5.2.2.8.7 | 1.5.2.2.8.7 |  | 2025-03-03 17:00 | q | 0 |  | 2025-03-03 08:55
222 | 5635 | ZYzv9KOmVdYL2d3ZPb8b | Summary | 0 | 1.5.2.2.9 | 1.5.2.2.9 |  | 2025-02-03 12:00 | p | 1 |  | 2025-02-04 16:37
223 | 5638 | jBSFjjY1RfmWgqa8tOlO | Normal | 0 | 1.5.2.2.9.3 | 1.5.2.2.9.3 |  | 2025-01-24 17:00 | p | 3 |  | 2025-01-28 10:34
224 | 5639 | ymvGdGMdlU958QTwMU9V | Normal | 0 | 1.5.2.2.9.4 | 1.5.2.2.9.4 |  | 2025-01-27 12:00 | p | 1 |  | 2025-01-28 15:01
225 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | 2025-02-03 12:00 | p | 1 |  | 2025-02-04 16:37
226 | 5641 | QjWOhv4eRSTZWx0ATAUl | Normal | 23 | 1.5.2.2.11 | 1.5.2.2.11 |  | 2025-04-10 17:00 | q | -3 |  | 2025-04-07 10:08
227 | 6309 | taNk8S9bKnlDToaFycS6 | Summary | 37 | 1.5.3 | 1.5.3 |  | 2025-03-28 17:00 | p | 27 |  | 2025-04-25 11:28
228 | 5443 | L0xk8h495fvdhlwnri8N | Summary | 37 | 1.5.3.1 | 1.5.3.1 |  | 2025-03-28 17:00 | p | 27 |  | 2025-04-25 11:28
229 | 5445 | 95pLIsxhFDdrMJGVBrpQ | Summary | 35 | 1.5.3.1.2 | 1.5.3.1.2 |  | 2025-03-21 17:00 | p | 27 |  | 2025-04-18 10:47
230 | 5447 | ijJ4zfbEfOInLYX7Vu9Z | Normal | 6 | 1.5.3.1.2.2 | 1.5.3.1.2.2 |  | 2025-03-05 17:00 | p | 28 |  | 2025-04-03 13:50
231 | 5448 | cS9oDqhLQ00Df4o4XStO | Normal | 6 | 1.5.3.1.2.3 | 1.5.3.1.2.3 |  | 2025-03-13 17:00 | p | 28 |  | 2025-04-11 09:26
232 | 5449 | 6It4K5O7iZJhLoLO2jyi | Normal | 6 | 1.5.3.1.2.4 | 1.5.3.1.2.4 |  | 2025-03-21 17:00 | p | 27 |  | 2025-04-18 10:47
233 | 5450 | maMtUzorvxHWuMFIlXlq | Normal | 5 | 1.5.3.1.3 | 1.5.3.1.3 |  | 2025-03-28 17:00 | p | 27 |  | 2025-04-25 11:28
234 | 7381 | Ao7wteklS85dOuCCMM3I | Normal | 124 | 1.5.1 | 1.5.1 |  | 2026-02-02 12:00 | p | 10 |  | 2026-02-12 16:14
235 | 6270 | Wwp4MRWhcV55WleZhe1f | Summary | 288 | 1.4 | 1.4 |  | 2027-01-07 16:58 | p | 31 |  | 2027-02-08 09:57
236 | 6290 | VuOK0YK760zOpXaJ9U7h | Summary | 140 | 1.4.3 | 1.4.3 |  | 2026-10-08 16:58 | p | 12 |  | 2026-10-21 15:39
237 | 4537 | FhESv2GOKRYErv6rS2Ko | Summary | 140 | 1.4.3.1 | 1.4.3.1 |  | 2026-10-08 16:58 | p | 12 |  | 2026-10-21 15:39
238 | 576 | m8O5CFAYfVbtxxZI5qQW | Normal | 15 | 1.4.3.1.2 | 1.4.3.1.2 |  | 2025-12-04 17:00 | q | -37 |  | 2025-10-28 13:56
239 | 4536 | zU98x2LHVd7UXovDFMXu | Normal | 14 | 1.4.3.1.1 | 1.4.3.1.1 |  | 2025-02-28 17:00 | p | 32 |  | 2025-04-02 14:38
240 | 5854 | 2kqOvhRPajU4Q0ZPsUnx | Normal | 8 | 1.4.3.1.4 | 1.4.3.1.4 |  | 2026-03-13 15:00 | p | 33 |  | 2026-04-16 14:51
241 | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Normal | 49 | 1.4.3.1.5 | 1.4.3.1.5 |  | 2026-10-08 16:58 | p | 12 |  | 2026-10-21 15:39
242 | 6607 | IhYDHpDNbof6PVOjQ9lw | Normal | 4 | 1.4.3.1.3 | 1.4.3.1.3 |  | 2026-02-24 15:00 | p | 33 |  | 2026-03-30 11:05
243 | 6291 | 7X6NK9qir9GRz5m7bXmK | Summary | 297 | 1.4.1 | 1.4.1 |  | 2027-01-07 16:58 | p | 31 |  | 2027-02-08 09:57
244 | 3891 | VQVEpj4HfOnKALplb4t9 | Summary | 43 | 1.4.1.1 | 1.4.1.1 |  | 2025-03-06 17:00 | p | 26 |  | 2025-04-02 09:46
245 | 3897 | cqWsQsQWdy7etYVMNQBf | Summary | 53 | 1.4.1.1.2 | 1.4.1.1.2 |  | 2025-03-06 17:00 | p | 26 |  | 2025-04-02 09:46
246 | 3900 | fYbjIfZDvkbYu7p7dq3N | Normal | 14 | 1.4.1.1.2.3 | 1.4.1.1.2.3 |  | 2025-02-28 17:00 | p | 25 |  | 2025-03-26 16:16
247 | 3901 | Jj1toL1YzUk95oK7OfgU | Normal | 4 | 1.4.1.1.2.4 | 1.4.1.1.2.4 |  | 2025-03-06 17:00 | p | 26 |  | 2025-04-02 09:46
248 | 3902 | FL4HGNxujC5zK4lN6AVO | Summary | 30 | 1.4.1.2 | 1.4.1.2 |  | 2025-05-01 17:00 | q | -21 |  | 2025-04-10 11:58
249 | 3903 | e0nMZ5CLCmjCURLrKpol | Summary | 30 | 1.4.1.2.1 | 1.4.1.2.1 |  | 2025-05-01 17:00 | q | -21 |  | 2025-04-10 11:58
250 | 6565 | XyBOyY3JpPW2h1I7PEur | Normal | 21 | 1.4.1.2.1.5 | 1.4.1.2.1.5 |  | 2025-04-30 17:00 | q | -21 |  | 2025-04-09 11:48
251 | 6566 | gAyE6SkFHV1MNEAJitQ7 | Normal | 1 | 1.4.1.2.1.6 | 1.4.1.2.1.6 |  | 2025-05-01 17:00 | q | -21 |  | 2025-04-10 11:58
252 | 3907 | pFYLZycbgH4KMn6pLhBU | Summary | 272 | 1.4.1.3 | 1.4.1.3 |  | 2026-07-29 15:00 | p | 25 |  | 2026-08-24 10:42
253 | 3908 | y9tKov3jCEzWGyA9B1wJ | Normal | 5 | 1.4.1.3.1 | 1.4.1.3.1 |  | 2025-07-03 17:00 | q | -77 |  | 2025-04-17 14:24
254 | 3909 | VvjZ0oHXTTG06m5XlL1B | Normal | 10 | 1.4.1.3.2 | 1.4.1.3.2 |  | 2025-07-18 17:00 | q | -78 |  | 2025-05-01 14:14
255 | 3910 | pNRX5rV0uvvHnR27z1AO | Normal | 8 | 1.4.1.3.3 | 1.4.1.3.3 |  | 2026-03-13 15:00 | p | 32 |  | 2026-04-14 16:59
256 | 3911 | R3AK39H17lCC16PE9DkR | Normal | 10 | 1.4.1.3.4 | 1.4.1.3.4 |  | 2026-03-27 15:00 | p | 28 |  | 2026-04-24 15:54
257 | 3912 | BSEXS69UjCPQ6j2zF47p | Normal | 15 | 1.4.1.3.5 | 1.4.1.3.5 |  | 2026-04-17 15:00 | p | 26 |  | 2026-05-14 09:13
258 | 3913 | nUmJBAacPI2xORV8OCED | Normal | 20 | 1.4.1.3.6 | 1.4.1.3.6 |  | 2026-05-15 15:00 | p | 32 |  | 2026-06-16 16:59
259 | 3914 | e7efPn2W4IFyilt2hNai | Normal | 30 | 1.4.1.3.7 | 1.4.1.3.7 |  | 2026-06-30 15:00 | p | 23 |  | 2026-07-24 08:09
260 | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Normal | 5 | 1.4.1.3.8 | 1.4.1.3.8 |  | 2026-07-08 15:00 | p | 25 |  | 2026-08-03 08:38
261 | 3916 | xcLTkuiw0V5a2mOSGmcP | Normal | 10 | 1.4.1.3.9 | 1.4.1.3.9 |  | 2026-07-22 15:00 | p | 22 |  | 2026-08-14 14:20
262 | 3917 | hmttcJptV92JIo4OpANW | Normal | 5 | 1.4.1.3.10 | 1.4.1.3.10 |  | 2026-07-29 15:00 | p | 25 |  | 2026-08-24 10:42
263 | 3918 | VKkEEklTkhlAtqntT93x | Summary | 160 | 1.4.1.4 | 1.4.1.4 |  | 2027-01-07 16:58 | p | 31 |  | 2027-02-08 09:57
264 | 3919 | 70MdVf3krr3KZdDhEaoj | Normal | 1 | 1.4.1.4.1 | 1.4.1.4.1 |  | 2026-05-18 15:00 | p | 30 |  | 2026-06-18 09:43
265 | 3920 | mBVNyTIN7rvKyNQxzyxZ | Normal | 9 | 1.4.1.4.2 | 1.4.1.4.2 |  | 2026-06-01 15:00 | p | 30 |  | 2026-07-01 16:36
266 | 3921 | jEuseC90wYhkn0V4svXs | Normal | 3 | 1.4.1.4.3 | 1.4.1.4.3 |  | 2026-08-04 16:58 | q | 0 |  | 2026-08-04 09:54
267 | 3922 | yD55zWPn8USsNa4i8nCC | Normal | 5 | 1.4.1.4.4 | 1.4.1.4.4 |  | 2026-10-16 16:58 | p | 13 |  | 2026-10-30 14:41
268 | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Normal | 15 | 1.4.1.4.5 | 1.4.1.4.5 |  | 2026-11-06 16:58 | p | 26 |  | 2026-12-03 15:30
269 | 3924 | N1CigBiMQE2J41ZAMkt0 | Normal | 20 | 1.4.1.4.6 | 1.4.1.4.6 |  | 2026-12-08 16:58 | p | 28 |  | 2027-01-06 15:40
270 | 3925 | hSr4t1vn7GiB6Kp7YK0M | Normal | 5 | 1.4.1.4.7 | 1.4.1.4.7 |  | 2026-12-15 16:58 | p | 27 |  | 2027-01-12 15:02
271 | 3926 | vGJMK6sejFbKR6Gom2up | Normal | 5 | 1.4.1.4.8 | 1.4.1.4.8 |  | 2026-12-22 16:58 | p | 29 |  | 2027-01-21 14:26
272 | 3927 | 3RLmiC17tI4E2ggNuRe0 | Normal | 5 | 1.4.1.4.9 | 1.4.1.4.9 |  | 2026-12-30 16:58 | p | 29 |  | 2027-01-29 15:28
273 | 3928 | hCBFci3gUopMkWW2dQQj | Normal | 5 | 1.4.1.4.10 | 1.4.1.4.10 |  | 2027-01-07 16:58 | p | 31 |  | 2027-02-08 09:57
274 | 6318 | cM5VCGnPiK1mfNJo8YLF | Summary | 309 | 1.4.2 | 1.4.2 |  | 2027-01-01 08:05 | p | 5 |  | 2027-01-06 08:12
275 | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Summary | 707 | 1.4.2.2 | 1.4.2.2 |  | 2026-07-21 16:58 | q | 0 |  | 2026-07-21 13:25
276 | 5213 | 6YmlQVHNVjUNryBHQf8a | Summary | 61 | 1.4.2.2.3 | 1.4.2.2.3 |  | 2025-11-07 17:00 | q | -31 |  | 2025-10-07 11:20
277 | 5214 | KnSim1DOJ7A0BYyW8QOP | Milestone | 0 | 1.4.2.2.3.1 | 1.4.2.2.3.1 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
278 | 5215 | KawuX1icbWQB8WlKVKy9 | Normal | 60 | 1.4.2.2.3.2 | 1.4.2.2.3.2 |  | 2025-11-06 17:00 | q | -34 |  | 2025-10-03 16:30
279 | 5216 | xOecB4tLtQXauOnWGD4l | Normal | 1 | 1.4.2.2.3.3 | 1.4.2.2.3.3 |  | 2025-11-07 17:00 | q | -31 |  | 2025-10-07 11:20
280 | 5217 | e116DivbRDCkLiH2zNhl | Summary | 61 | 1.4.2.2.4 | 1.4.2.2.4 |  | 2025-11-07 17:00 | q | -21 |  | 2025-10-17 08:36
281 | 5218 | 8GMyARBjPLtiSR4txAaa | Milestone | 0 | 1.4.2.2.4.1 | 1.4.2.2.4.1 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
282 | 5219 | Uz3hspiJXkYJElXZ00I5 | Normal | 60 | 1.4.2.2.4.2 | 1.4.2.2.4.2 |  | 2025-11-06 17:00 | q | -21 |  | 2025-10-16 09:10
283 | 5220 | QAqXx5k5ldQJaugZyYbR | Normal | 1 | 1.4.2.2.4.3 | 1.4.2.2.4.3 |  | 2025-11-07 17:00 | q | -21 |  | 2025-10-17 08:36
284 | 5221 | iTaWceiQKMF6gUaF3DCB | Summary | 61 | 1.4.2.2.5 | 1.4.2.2.5 |  | 2025-11-07 17:00 | q | -28 |  | 2025-10-10 15:45
285 | 5222 | 4u5ocGGr0fcTRpzuglXZ | Milestone | 0 | 1.4.2.2.5.1 | 1.4.2.2.5.1 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
286 | 5223 | 3nEJb4lsc7akFmF6ULw7 | Normal | 60 | 1.4.2.2.5.2 | 1.4.2.2.5.2 |  | 2025-11-06 17:00 | q | -28 |  | 2025-10-09 15:42
287 | 5224 | PvORb6t1pqf23aOFbh3S | Normal | 1 | 1.4.2.2.5.3 | 1.4.2.2.5.3 |  | 2025-11-07 17:00 | q | -28 |  | 2025-10-10 15:45
288 | 5225 | b44Ij1WE7Qrra8bO7ZTN | Normal | 1 | 1.4.2.2.6 | 1.4.2.2.6 |  | 2026-07-21 16:58 | q | 0 |  | 2026-07-21 13:25
289 | 5277 | TgmqG1sR4A60sNmMtPcE | Summary | 193 | 1.4.2.2.7 | 1.4.2.2.7 |  | 2026-07-09 16:58 | q | -16 |  | 2026-06-23 15:58
290 | 5278 | OmCdw3tKtVsW24V2aNqQ | Normal | 8 | 1.4.2.2.7.1 | 1.4.2.2.7.1 |  | 2026-01-19 08:01 | q | -33 |  | 2025-12-16 08:32
291 | 5279 | htHZ3VhuaadgfKg1VQls | Summary | 47 | 1.4.2.2.7.11 | 1.4.2.2.7.11 |  | 2026-06-25 08:58 | q | -16 |  | 2026-06-09 08:39
292 | 5280 | q0a2rl5NSMPQe2o4IYAd | Normal | 3 | 1.4.2.2.7.11.1 | 1.4.2.2.7.11.1 |  | 2026-05-28 08:58 | q | -34 |  | 2026-04-23 09:05
293 | 5281 | 3GO4XZOZrW4CEje40UJT | Normal | 5 | 1.4.2.2.7.11.2 | 1.4.2.2.7.11.2 |  | 2026-04-28 08:01 | q | -21 |  | 2026-04-06 08:30
294 | 5282 | qBzS7vPbhPVzs7sVXgmM | Normal | 5 | 1.4.2.2.7.11.3 | 1.4.2.2.7.11.3 |  | 2026-05-05 08:01 | q | -5 |  | 2026-04-29 11:35
295 | 5283 | fU0pzeQGz2MN3lZmznFh | Normal | 5 | 1.4.2.2.7.11.4 | 1.4.2.2.7.11.4 |  | 2026-05-12 08:01 | q | -42 |  | 2026-03-30 09:44
296 | 5284 | epM0xPGW4QTSpblHVWYc | Normal | 10 | 1.4.2.2.7.11.5 | 1.4.2.2.7.11.5 |  | 2026-06-11 08:58 | q | -21 |  | 2026-05-20 13:10
297 | 5285 | ffNcVsnPBySsZbQiEShc | Normal | 10 | 1.4.2.2.7.11.6 | 1.4.2.2.7.11.6 |  | 2026-06-25 08:58 | q | -16 |  | 2026-06-09 08:39
298 | 5286 | Yb8sH9U5B9gBzfVjcJKN | Normal | 6 | 1.4.2.2.7.12 | 1.4.2.2.7.12 |  | 2026-07-02 16:58 | q | -16 |  | 2026-06-16 16:30
299 | 5287 | bhDhrVJ9ZVKMNyReuPKm | Normal | 5 | 1.4.2.2.7.13 | 1.4.2.2.7.13 |  | 2026-07-09 16:58 | q | -16 |  | 2026-06-23 15:58
300 | 5288 | RIVzpLwElpoiAIgfwKiL | Milestone | 0 | 1.4.2.2.7.14 | 1.4.2.2.7.14 |  | 2026-07-09 16:58 | q | -16 |  | 2026-06-23 15:58
301 | 6457 | PFYaNHtSBj97Eh5ysTvH | Normal | 7 | 1.4.2.2.7.2 | 1.4.2.2.7.2 |  | 2026-01-28 08:01 | q | -35 |  | 2025-12-23 11:39
302 | 6458 | pDFztlVdvvSj2i4Cz5Z9 | Normal | 5 | 1.4.2.2.7.3 | 1.4.2.2.7.3 |  | 2026-02-04 08:01 | q | -34 |  | 2025-12-31 11:37
303 | 6459 | ylmwXTiOnCLJpwlHTaRg | Normal | 10 | 1.4.2.2.7.4 | 1.4.2.2.7.4 |  | 2026-02-18 08:01 | q | -32 |  | 2026-01-16 09:43
304 | 6460 | CystLMJtc4xxgICiEMDQ | Normal | 8 | 1.4.2.2.7.5 | 1.4.2.2.7.5 |  | 2026-03-02 08:01 | q | -32 |  | 2026-01-28 08:58
305 | 6461 | 7ypQo0ZyAHzCHmFRlywg | Normal | 10 | 1.4.2.2.7.6 | 1.4.2.2.7.6 |  | 2026-03-16 08:01 | q | -30 |  | 2026-02-13 08:15
306 | 6462 | BWDOi71UCejcEb1fgeoY | Normal | 7 | 1.4.2.2.7.7 | 1.4.2.2.7.7 |  | 2026-03-25 08:01 | q | -29 |  | 2026-02-23 15:14
307 | 6463 | OelD6citgJccZhV0UyvH | Normal | 7 | 1.4.2.2.7.8 | 1.4.2.2.7.8 |  | 2026-04-03 08:01 | q | -28 |  | 2026-03-05 08:27
308 | 6464 | McSTYqZ3LCfaYSSmZoTn | Normal | 7 | 1.4.2.2.7.9 | 1.4.2.2.7.9 |  | 2026-04-14 08:01 | q | -31 |  | 2026-03-13 10:58
309 | 6465 | WAyiiuxKOgY7bZWYUV9d | Normal | 5 | 1.4.2.2.7.10 | 1.4.2.2.7.10 |  | 2026-04-21 08:01 | q | -31 |  | 2026-03-20 13:20
310 | 5226 | R9JO9mOSGmg0eoDimoJT | Summary | 71 | 1.4.2.1 | 1.4.2.1 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
311 | 5240 | NSmZbDTp76mGzDSQ7Ceh | Summary | 56 | 1.4.2.1.3 | 1.4.2.1.3 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
312 | 5241 | v6EKIZLcnDHW8CXOrD7y | Normal | 21 | 1.4.2.1.3.1 | 1.4.2.1.3.1 |  | 2025-06-23 17:00 | q | -237 |  | 2024-10-29 11:37
313 | 5242 | JYCfpao49G3jD8M94S66 | Normal | 10 | 1.4.2.1.3.2 | 1.4.2.1.3.2 |  | 2025-07-08 17:00 | q | -183 |  | 2025-01-06 08:46
314 | 5243 | 0XN39P602kPVdw6rXYZi | Normal | 10 | 1.4.2.1.3.3 | 1.4.2.1.3.3 |  | 2025-07-22 17:00 | q | -27 |  | 2025-06-25 08:52
315 | 5244 | Nwqnc6xsOuQ8oMDbKNfv | Normal | 15 | 1.4.2.1.3.4 | 1.4.2.1.3.4 |  | 2025-08-12 17:00 | q | -26 |  | 2025-07-17 16:02
316 | 5262 | PI0DE6xTKT4gLnHpqgjE | Summary | 137 | 1.4.2.1.6 | 1.4.2.1.6 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
317 | 5263 | URhzXaXmWu6rBPIMitrn | Normal | 30 | 1.4.2.1.6.1 | 1.4.2.1.6.1 |  | 2025-03-24 17:00 | p | 28 |  | 2025-04-22 14:42
318 | 5265 | ATYnDTN93dB3aTXfzslo | Normal | 6 | 1.4.2.1.6.2 | 1.4.2.1.6.2 |  | 2025-04-15 11:00 | p | 27 |  | 2025-05-13 10:18
319 | 5266 | G5H4IlBy3M3Zxs38gcIH | Normal | 10 | 1.4.2.1.6.3 | 1.4.2.1.6.3 |  | 2025-04-29 14:00 | p | 29 |  | 2025-05-29 10:56
320 | 5267 | 3RI5G3ymKjaLn96cfboa | Normal | 11 | 1.4.2.1.6.4 | 1.4.2.1.6.4 |  | 2025-05-13 14:00 | p | 20 |  | 2025-06-02 15:18
321 | 5268 | fG9nayiE82fFlNFtuyfN | Normal | 8 | 1.4.2.1.6.5 | 1.4.2.1.6.5 |  | 2025-06-12 17:00 | p | 20 |  | 2025-07-03 08:50
322 | 5269 | UP8sWsDXCDMiwOqWz3ib | Normal | 5 | 1.4.2.1.6.6 | 1.4.2.1.6.6 |  | 2025-07-25 09:00 | q | -38 |  | 2025-06-16 11:06
323 | 5270 | 0UA65kBzwzHULCayr1Gq | Normal | 8 | 1.4.2.1.6.7 | 1.4.2.1.6.7 |  | 2025-08-08 08:30 | q | -38 |  | 2025-06-30 09:21
324 | 5271 | mtztJWmm2OBnfmSsuoGt | Normal | 10 | 1.4.2.1.6.8 | 1.4.2.1.6.8 |  | 2025-08-22 08:30 | q | -36 |  | 2025-07-16 08:39
325 | 5272 | kvS9pO69DNwaLvofAQcb | Normal | 11 | 1.4.2.1.6.9 | 1.4.2.1.6.9 |  | 2025-09-09 08:30 | q | -33 |  | 2025-08-06 13:53
326 | 5273 | fGHKYfAaAseAkWqOpGpv | Normal | 10 | 1.4.2.1.6.10 | 1.4.2.1.6.10 |  | 2025-09-23 08:30 | q | -33 |  | 2025-08-20 11:00
327 | 5274 | zjsmmZ1Zvuz0mxAk4wzH | Normal | 10 | 1.4.2.1.6.11 | 1.4.2.1.6.11 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
328 | 5275 | lBTJLZ8EG6vqarjSz7m6 | Milestone | 0 | 1.4.2.1.6.12 | 1.4.2.1.6.12 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
329 | 5264 | 2BYRPY9ftrCpjg2j3vxJ | Milestone | 0 | 1.4.2.1.8 | 1.4.2.1.8 |  | 2025-02-21 08:00 | q | -328 |  | 2024-03-29 17:00
330 | 5276 | yja2Gk0YbNXya3vsxrwh | Milestone | 0 | 1.4.2.1.7 | 1.4.2.1.7 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
331 | 5289 | tqKGxL2oceRufkd47wnf | Summary | 319 | 1.4.2.3 | 1.4.2.3 |  | 2027-01-01 08:05 | p | 5 |  | 2027-01-06 08:12
332 | 5290 | NEvSl0zKCrGJ6lqshTZO | Milestone | 0 | 1.4.2.3.1 | 1.4.2.3.1 |  | 2025-11-07 17:00 | q | -28 |  | 2025-10-10 15:45
333 | 5313 | 3y8KKUl940HiJi7UFKFT | Summary | 106 | 1.4.2.3.3 | 1.4.2.3.3 |  | 2027-01-01 08:05 | p | 5 |  | 2027-01-06 08:12
334 | 5314 | SRtjKDi8lC5PBWdNdIAU | Normal | 10 | 1.4.2.3.3.1 | 1.4.2.3.3.1 |  | 2026-08-19 16:58 | q | 0 |  | 2026-08-19 13:44
335 | 5316 | LCfcLPfxTjnSY0dCrjlE | Normal | 10 | 1.4.2.3.3.2 | 1.4.2.3.3.2 |  | 2026-09-16 11:59 | q | 0 |  | 2026-09-16 10:06
336 | 5317 | pw6YyMXR7oeqsrtIHdqo | Normal | 9 | 1.4.2.3.3.3 | 1.4.2.3.3.3 |  | 2026-10-09 10:08 | p | 0 |  | 2026-10-09 11:37
337 | 5318 | KMG5hXAC4X2MZPfyVOSc | Normal | 5 | 1.4.2.3.3.8 | 1.4.2.3.3.8 |  | 2026-11-13 10:08 | p | 3 |  | 2026-11-16 11:36
338 | 5319 | mDGXCmTQB2ITo8MYwlYq | Normal | 5 | 1.4.2.3.3.9 | 1.4.2.3.3.9 |  | 2026-11-20 10:08 | p | 3 |  | 2026-11-24 08:25
339 | 5320 | hu6UActfLD0rLfdNqC55 | Normal | 5 | 1.4.2.3.3.10 | 1.4.2.3.3.10 |  | 2026-11-27 10:08 | p | 3 |  | 2026-12-01 08:22
340 | 5321 | pG9QTaeiPcJe7Bm3iI1s | Normal | 5 | 1.4.2.3.3.11 | 1.4.2.3.3.11 |  | 2026-12-04 10:08 | p | 4 |  | 2026-12-08 11:18
341 | 5322 | oNpYocgOFdrRcJiQE0H5 | Normal | 5 | 1.4.2.3.3.12 | 1.4.2.3.3.12 |  | 2026-12-11 10:08 | p | 4 |  | 2026-12-16 08:59
342 | 5323 | Tt5dEbDabBigq84Eat5c | Normal | 5 | 1.4.2.3.3.13 | 1.4.2.3.3.13 |  | 2026-12-18 10:08 | p | 5 |  | 2026-12-23 10:18
343 | 5324 | INz2wzhVzgQCZLXqwTZc | Normal | 5 | 1.4.2.3.3.14 | 1.4.2.3.3.14 |  | 2026-12-31 08:05 | p | 5 |  | 2027-01-05 08:10
344 | 5325 | D5c4JntP5EU4thbOE4hi | Normal | 1 | 1.4.2.3.3.15 | 1.4.2.3.3.15 |  | 2027-01-01 08:05 | p | 5 |  | 2027-01-06 08:12
345 | 6467 | n3qEWBmgcrCNzbacKk03 | Normal | 5 | 1.4.2.3.3.4 | 1.4.2.3.3.4 |  | 2026-10-16 10:08 | p | 0 |  | 2026-10-16 11:31
346 | 6468 | BqsEZH5IWCI59bWKml0D | Normal | 5 | 1.4.2.3.3.5 | 1.4.2.3.3.5 |  | 2026-10-23 10:08 | p | 0 |  | 2026-10-23 15:39
347 | 6469 | TtC6fzAb8zClFAVfKkP8 | Normal | 5 | 1.4.2.3.3.6 | 1.4.2.3.3.6 |  | 2026-10-30 10:08 | p | 0 |  | 2026-10-30 15:11
348 | 6470 | UrgnPc0HjVwpN7twGsWX | Normal | 5 | 1.4.2.3.3.7 | 1.4.2.3.3.7 |  | 2026-11-06 10:08 | p | 0 |  | 2026-11-06 15:15
349 | 5326 | esDa5lJIA5zg0nP58cRd | Summary | 32 | 1.4.2.3.4 | 1.4.2.3.4 |  | 2025-11-24 08:30 | q | -38 |  | 2025-10-16 13:50
350 | 5327 | iRZmxts3rKQ38tplQw52 | Normal | 30 | 1.4.2.3.4.1 | 1.4.2.3.4.1 |  | 2025-11-20 08:30 | q | -36 |  | 2025-10-14 11:56
351 | 5328 | ngeJL3ilFttQtHxnOEwX | Normal | 1 | 1.4.2.3.4.2 | 1.4.2.3.4.2 |  | 2025-11-21 08:30 | q | -36 |  | 2025-10-15 13:36
352 | 5329 | GYUaK0PI1fV4kag2egD8 | Normal | 1 | 1.4.2.3.4.3 | 1.4.2.3.4.3 |  | 2025-11-24 08:30 | q | -38 |  | 2025-10-16 13:50
353 | 6321 | KAyzIHlSkkFZqIIdJ9JD | Summary | 144 | 1.4.2.3.2 | 1.4.2.3.2 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
354 | 5298 | c4SSanbHhynqs8RkqT3I | Normal | 3 | 1.4.2.3.2.2 | 1.4.2.3.2.2 |  | 2026-02-03 15:00 | p | 33 |  | 2026-03-09 14:34
355 | 5299 | HB5wL9z8KlZFeAas0WUQ | Normal | 11 | 1.4.2.3.2.3 | 1.4.2.3.2.3 |  | 2026-02-18 15:00 | p | 33 |  | 2026-03-24 09:15
356 | 5301 | hHw9byxBfgMW8zXuSsdj | Milestone | 0 | 1.4.2.3.2.12 | 1.4.2.3.2.12 |  | 2026-04-02 15:00 | p | 33 |  | 2026-05-05 15:37
357 | 5302 | 2rc67Y2hzAhRvE7YihWA | Normal | 10 | 1.4.2.3.2.1 | 1.4.2.3.2.1 |  | 2026-01-29 15:00 | p | 33 |  | 2026-03-03 15:34
358 | 5303 | SgeIRg4ykwxbNqD9urWV | Normal | 2 | 1.4.2.3.2.8 | 1.4.2.3.2.8 |  | 2026-03-24 15:00 | p | 30 |  | 2026-04-24 14:59
359 | 5304 | KRXQrBZsFBKS9k4FvAsp | Normal | 3 | 1.4.2.3.2.9 | 1.4.2.3.2.9 |  | 2026-03-27 15:00 | p | 33 |  | 2026-04-29 15:04
360 | 5305 | TyGQYH0bANBrFjXmh15D | Normal | 2 | 1.4.2.3.2.10 | 1.4.2.3.2.10 |  | 2026-03-31 15:00 | p | 31 |  | 2026-05-01 16:04
361 | 5306 | yar7ts7ASIpTQqyvnwQd | Normal | 5 | 1.4.2.3.2.13 | 1.4.2.3.2.13 |  | 2026-04-09 15:00 | p | 34 |  | 2026-05-14 08:39
362 | 5307 | yRByGMPgEQcCecr5HzAA | Normal | 2 | 1.4.2.3.2.15 | 1.4.2.3.2.15 |  | 2026-04-14 15:00 | p | 38 |  | 2026-05-22 15:08
363 | 5308 | JBAsTSNPb9OQmIAmtadV | Normal | 20 | 1.4.2.3.2.17 | 1.4.2.3.2.17 |  | 2026-05-19 08:01 | p | 49 |  | 2026-07-07 09:10
364 | 5309 | xRRT514kq8kwyv7njrs5 | Normal | 5 | 1.4.2.3.2.19 | 1.4.2.3.2.19 |  | 2026-07-16 16:58 | q | 0 |  | 2026-07-16 10:39
365 | 5310 | RMnJ5j2lLGlokfxLAfSa | Normal | 2 | 1.4.2.3.2.20 | 1.4.2.3.2.20 |  | 2026-07-20 16:58 | q | 0 |  | 2026-07-20 11:30
366 | 5311 | BowxNbb4uXSnAk8z8ZkC | Normal | 2 | 1.4.2.3.2.22 | 1.4.2.3.2.22 |  | 2026-07-22 16:58 | q | 0 |  | 2026-07-22 14:13
367 | 5312 | mmXMEY1kphvE51vXPbq6 | Milestone | 0 | 1.4.2.3.2.25 | 1.4.2.3.2.25 |  | 2026-08-05 16:58 | q | 0 |  | 2026-08-05 11:49
368 | 6516 | qmbk7ROGAo4AwJOySAlG | Normal | 4 | 1.4.2.3.2.4 | 1.4.2.3.2.4 |  | 2026-02-24 15:00 | p | 31 |  | 2026-03-27 16:17
369 | 6517 | YGaikKlMVGc6fqtUBZ7h | Normal | 5 | 1.4.2.3.2.5 | 1.4.2.3.2.5 |  | 2026-03-03 15:00 | p | 30 |  | 2026-04-03 13:41
370 | 6518 | 0rDsNLFYCabTnyCcopAQ | Normal | 8 | 1.4.2.3.2.6 | 1.4.2.3.2.6 |  | 2026-03-13 15:00 | p | 32 |  | 2026-04-15 13:51
371 | 6519 | UldK3RoYRJH5Hsfv02Lh | Normal | 2 | 1.4.2.3.2.7 | 1.4.2.3.2.7 |  | 2026-03-17 15:00 | p | 30 |  | 2026-04-17 09:06
372 | 6520 | UaqqB30tdDFCsCHRRpeh | Normal | 2 | 1.4.2.3.2.11 | 1.4.2.3.2.11 |  | 2026-04-02 15:00 | p | 33 |  | 2026-05-05 15:37
373 | 6521 | LDY9CVOjImzsQ4NE65Qz | Normal | 1 | 1.4.2.3.2.16 | 1.4.2.3.2.16 |  | 2026-04-15 15:00 | p | 40 |  | 2026-05-25 16:19
374 | 6522 | WYJvDx3FrKALT2lj4FIo | Normal | 2 | 1.4.2.3.2.18 | 1.4.2.3.2.18 |  | 2026-05-21 08:01 | p | 49 |  | 2026-07-09 10:39
375 | 6523 | TvM5XBX3OaVljTSOZ4e2 | Normal | 2 | 1.4.2.3.2.21 | 1.4.2.3.2.21 |  | 2026-07-20 16:58 | q | 0 |  | 2026-07-20 14:13
376 | 6524 | cvaJgvK8KpGYV8ykH12h | Normal | 2 | 1.4.2.3.2.23 | 1.4.2.3.2.23 |  | 2026-07-24 16:58 | q | 0 |  | 2026-07-24 15:08
377 | 6525 | GtEwLNkefPtnncnl90X4 | Normal | 3 | 1.4.2.3.2.24 | 1.4.2.3.2.24 |  | 2026-08-04 16:58 | q | 0 |  | 2026-08-04 11:54
378 | 6873 | gSZIbC6fsU6IM6McOJy8 | Normal | 1 | 1.4.2.3.2.14 | 1.4.2.3.2.14 |  | 2026-04-10 15:00 | p | 34 |  | 2026-05-15 09:22
379 | 6271 | Q6QswYSvhipRUbZBXuiu | Summary | 315 | 1.6 | 1.6 |  | 2026-11-10 17:00 | p | 100 |  | 2027-02-19 10:11
380 | 6277 | moVS9Ou3GclDwNSW1OnS | Summary | 264 | 1.6.7 | 1.6.7 |  | 2026-09-29 17:00 | p | 104 |  | 2027-01-12 08:36
381 | 678 | N57z7OkXN935WcKbC4jO | Normal | 1 | 1.6.7.2 | 1.6.7.2 |  | 2026-03-26 17:00 | p | 75 |  | 2026-06-10 09:28
382 | 700 | PZaQwD8fp0dlxZIxEZEd | Normal | 279 | 1.6.7.10 | 1.6.7.10 |  | 2026-03-23 17:00 | p | 92 |  | 2026-06-24 13:57
383 | 728 | 4dRz6TQj3FOK8lstTqZK | Summary | 396 | 1.6.7.9 | 1.6.7.9 |  | 2026-03-31 17:00 | p | 75 |  | 2026-06-15 09:17
384 | 741 | cktDjgZ5bp36SrQnCM1w | Summary | 458 | 1.6.7.9.3 | 1.6.7.9.3 |  | 2026-03-31 17:00 | p | 75 |  | 2026-06-15 09:17
385 | 751 | AADJzuTGAb4gWytj7CQi | Normal | 18 | 1.6.7.9.3.8 | 1.6.7.9.3.8 |  | 2025-09-02 17:00 | p | 13 |  | 2025-09-16 11:56
386 | 752 | r0c0rFS4EkOGynasmiCG | Normal | 36 | 1.6.7.9.3.7 | 1.6.7.9.3.7 |  | 2025-08-26 17:00 | p | 23 |  | 2025-09-19 09:47
387 | 759 | cZuo3MY7iyDrOJC1qVJx | Normal | 5 | 1.6.7.9.3.9 | 1.6.7.9.3.9 |  | 2025-09-09 17:00 | p | 12 |  | 2025-09-22 16:40
388 | 765 | qOEfFivvitnF8cw9csOP | Normal | 1 | 1.6.7.9.3.13 | 1.6.7.9.3.13 |  | 2026-03-26 17:00 | p | 75 |  | 2026-06-10 09:42
389 | 5773 | OCcI80TDGF8LlIXj66uV | Normal | 3 | 1.6.7.9.3.14 | 1.6.7.9.3.14 |  | 2026-03-31 17:00 | p | 75 |  | 2026-06-15 09:17
390 | 6323 | aU24Z8SrLl20SyyllZuy | Summary | 80 | 1.6.7.9.3.5 | 1.6.7.9.3.5 |  | 2025-04-16 17:00 | q | -5 |  | 2025-04-11 09:33
391 | 745 | aO52oWR4hBrrP5GVCo2a | Normal | 11 | 1.6.7.9.3.5.2 | 1.6.7.9.3.5.2 |  | 2025-03-31 17:00 | q | -4 |  | 2025-03-27 10:10
392 | 746 | qMC0J8brk1dsdpzlKrk7 | Normal | 12 | 1.6.7.9.3.5.3 | 1.6.7.9.3.5.3 |  | 2025-04-16 17:00 | q | -5 |  | 2025-04-11 09:33
393 | 6324 | gthK0FxwJBk3laTELp8O | Summary | 45 | 1.6.7.9.3.6 | 1.6.7.9.3.6 |  | 2025-07-07 17:00 | p | 14 |  | 2025-07-22 13:22
394 | 747 | nul8vpOEtI2Q6W5Q0Qo9 | Normal | 12 | 1.6.7.9.3.6.1 | 1.6.7.9.3.6.1 |  | 2025-05-16 17:00 | p | 18 |  | 2025-06-04 15:23
395 | 748 | M1HHh2K01o23jS8vpDxS | Normal | 11 | 1.6.7.9.3.6.2 | 1.6.7.9.3.6.2 |  | 2025-06-03 17:00 | p | 16 |  | 2025-06-20 14:07
396 | 749 | Q6UXOpf9Kvzek7IGY0vp | Normal | 11 | 1.6.7.9.3.6.3 | 1.6.7.9.3.6.3 |  | 2025-06-18 17:00 | p | 14 |  | 2025-07-03 16:35
397 | 750 | lsyrPytnmjLTpXFywa7Z | Normal | 11 | 1.6.7.9.3.6.4 | 1.6.7.9.3.6.4 |  | 2025-07-07 17:00 | p | 14 |  | 2025-07-22 13:22
398 | 6325 | SeCXD5wMvkrEekc1PKVb | Summary | 48 | 1.6.7.9.3.10 | 1.6.7.9.3.10 |  | 2025-11-18 17:00 | p | 99 |  | 2026-02-26 13:37
399 | 753 | 8158sxzbHZvZEVAAqewP | Normal | 47 | 1.6.7.9.3.10.1 | 1.6.7.9.3.10.1 |  | 2025-11-17 17:00 | p | 48 |  | 2026-01-05 10:21
400 | 754 | hfPeDXfQSV7Nx9zb2rD7 | Normal | 8 | 1.6.7.9.3.10.2 | 1.6.7.9.3.10.2 |  | 2025-09-19 17:00 | p | 100 |  | 2025-12-29 11:51
401 | 755 | DQUdswbbJv1Qpkj0EGFX | Normal | 8 | 1.6.7.9.3.10.3 | 1.6.7.9.3.10.3 |  | 2025-10-01 17:00 | p | 99 |  | 2026-01-09 10:16
402 | 756 | ae3T3d3nFoXZXK7gqkAr | Normal | 20 | 1.6.7.9.3.10.4 | 1.6.7.9.3.10.4 |  | 2025-10-30 17:00 | p | 101 |  | 2026-02-09 11:31
403 | 757 | wbc1AZ0GUhXzQk6SoWIe | Normal | 6 | 1.6.7.9.3.10.6 | 1.6.7.9.3.10.6 |  | 2025-11-07 17:00 | p | 102 |  | 2026-02-18 15:32
404 | 758 | FbN1rrQYTlsz1haWZnFy | Normal | 6 | 1.6.7.9.3.10.8 | 1.6.7.9.3.10.8 |  | 2025-11-18 17:00 | p | 99 |  | 2026-02-26 13:37
405 | 5780 | XCMvjmTKbAUuCZwuNlSF | Normal | 6 | 1.6.7.9.3.10.5 | 1.6.7.9.3.10.5 |  | 2025-10-09 17:00 | p | 102 |  | 2026-01-20 09:43
406 | 5782 | EYY3j1SjnoLUV06T0QHs | Normal | 5 | 1.6.7.9.3.10.7 | 1.6.7.9.3.10.7 |  | 2025-11-06 17:00 | p | 97 |  | 2026-02-12 15:16
407 | 6326 | F4s3MnfyyA74WCIympSi | Summary | 75 | 1.6.7.9.3.11 | 1.6.7.9.3.11 |  | 2025-12-29 17:00 | p | 69 |  | 2026-03-09 16:30
408 | 760 | 7IpOsslq7gyebnCTulxX | Normal | 66 | 1.6.7.9.3.11.1 | 1.6.7.9.3.11.1 |  | 2025-12-15 17:00 | p | 13 |  | 2025-12-29 08:26
409 | 761 | x6fNhJzs4uMW9trtiNEW | Normal | 1 | 1.6.7.9.3.11.2 | 1.6.7.9.3.11.2 |  | 2025-12-16 17:00 | p | 72 |  | 2026-02-27 13:36
410 | 762 | nRInnITHYgcDsU5KDg6m | Normal | 8 | 1.6.7.9.3.11.3 | 1.6.7.9.3.11.3 |  | 2025-12-29 17:00 | p | 69 |  | 2026-03-09 16:30
411 | 6327 | dOJS0LaWQU970ssSiqsz | Summary | 59 | 1.6.7.9.3.12 | 1.6.7.9.3.12 |  | 2026-03-25 17:00 | p | 75 |  | 2026-06-09 09:07
412 | 763 | hLK2cdXSS7IhOZR53PgI | Normal | 6 | 1.6.7.9.3.12.1 | 1.6.7.9.3.12.1 |  | 2026-01-07 17:00 | p | 68 |  | 2026-03-17 09:11
413 | 764 | wTf98lLeHiXAkWj17mAH | Normal | 53 | 1.6.7.9.3.12.2 | 1.6.7.9.3.12.2 |  | 2026-03-25 17:00 | p | 75 |  | 2026-06-09 09:07
414 | 770 | cHAOkWrFbu094CNd9eCk | Summary | 91 | 1.6.7.8 | 1.6.7.8 |  | 2025-05-13 17:00 | p | 26 |  | 2025-06-09 09:54
415 | 786 | 5RJIBxVgSA4dodMzOCsx | Normal | 1 | 1.6.7.8.5 | 1.6.7.8.5 |  | 2025-05-13 17:00 | p | 26 |  | 2025-06-09 09:54
416 | 6434 | cc8WGEqtonq4zOxPHtWc | Normal | 65 | 1.6.7.8.4 | 1.6.7.8.4 |  | 2025-05-12 17:00 | p | 24 |  | 2025-06-06 08:25
417 | 5785 | xIbBdattr1YLWDiqGWPC | Summary | 126 | 1.6.7.11 | 1.6.7.11 |  | 2026-09-29 17:00 | p | 104 |  | 2027-01-12 08:36
418 | 5774 | Dvlkt7hdSzdJ7ChIr4xD | Normal | 2 | 1.6.7.11.1 | 1.6.7.11.1 |  | 2026-04-02 17:00 | p | 84 |  | 2026-06-26 11:47
419 | 5775 | D3NIdGcGrWNhiaQ0dYbY | Normal | 2 | 1.6.7.11.3 | 1.6.7.11.3 |  | 2026-09-29 17:00 | p | 104 |  | 2027-01-12 08:36
420 | 6435 | Ql00ScpYzqtI9PQP57zu | Normal | 122 | 1.6.7.11.2 | 1.6.7.11.2 |  | 2026-09-25 17:00 | p | 104 |  | 2027-01-08 08:25
421 | 6284 | T6s1mlIi1Lu4cscBpq9h | Summary | 273 | 1.6.6 | 1.6.6 |  | 2025-12-18 17:00 | p | 12 |  | 2025-12-31 11:08
422 | 1519 | Ig6aeqJATmPNbReGQrzj | Summary | 273 | 1.6.6.1 | 1.6.6.1 |  | 2025-12-18 17:00 | p | 12 |  | 2025-12-31 11:08
423 | 1464 | VN7GLU7alOC9oD3kkW9q | Normal | 30 | 1.6.6.1.4 | 1.6.6.1.4 |  | 2025-03-28 17:00 | p | 12 |  | 2025-04-10 08:56
424 | 1465 | i7zbkIpCuBMJlMsq6ma0 | Normal | 1 | 1.6.6.1.5 | 1.6.6.1.5 |  | 2025-03-31 17:00 | p | 10 |  | 2025-04-11 08:54
425 | 1475 | suCYO4gIoCSrnZchT6aQ | Normal | 3 | 1.6.6.1.6 | 1.6.6.1.6 |  | 2025-02-18 17:00 | p | 0 |  | 2025-02-19 14:02
426 | 1476 | gbuDNYIgLq2nB3WERl4p | Normal | 30 | 1.6.6.1.7 | 1.6.6.1.7 |  | 2025-04-01 17:00 | p | 9 |  | 2025-04-11 13:03
427 | 1477 | BC1NYB3fqAlfckX7ECXI | Normal | 1 | 1.6.6.1.8 | 1.6.6.1.8 |  | 2025-04-02 17:00 | p | 11 |  | 2025-04-14 09:35
428 | 1478 | UR7xa7LgN3sMlpzxRjvW | Normal | 3 | 1.6.6.1.9 | 1.6.6.1.9 |  | 2025-12-18 17:00 | p | 12 |  | 2025-12-31 11:08
429 | 6293 | WhUcOZjaj9TDZe74ojmh | Summary | 172 | 1.6.4 | 1.6.4 |  | 2026-11-10 17:00 | p | 100 |  | 2027-02-19 10:11
430 | 3929 | GkmiaraCbWdBUaRv136y | Summary | 19 | 1.6.4.15 | 1.6.4.15 |  | 2025-03-28 17:00 | p | 41 |  | 2025-05-09 09:49
431 | 3932 | RKLg9Drqo40Q82TFH1VL | Normal | 1 | 1.6.4.15.2 | 1.6.4.15.2 |  | 2025-03-28 17:00 | p | 24 |  | 2025-04-22 10:47
432 | 3934 | 10Oh1H5M5HjeoWxU1u0w | Normal | 1 | 1.6.4.15.4 | 1.6.4.15.4 |  | 2025-03-28 17:00 | p | 38 |  | 2025-05-06 13:01
433 | 3936 | hwXDQy0MWIQ4jzjNT4oM | Normal | 1 | 1.6.4.15.3 | 1.6.4.15.3 |  | 2025-03-28 17:00 | p | 26 |  | 2025-04-24 14:24
434 | 3938 | 2iJ091mlhEkJyqoddB4L | Normal | 14 | 1.6.4.15.1 | 1.6.4.15.1 |  | 2025-02-28 17:00 | p | 20 |  | 2025-03-21 09:14
435 | 3940 | 8UqvtHTIMRT16eupajKq | Normal | 1 | 1.6.4.15.5 | 1.6.4.15.5 |  | 2025-03-28 17:00 | p | 41 |  | 2025-05-09 09:49
436 | 3931 | GleHIX38gd9vOXaUQYVA | Normal | 33 | 1.6.4.11 | 1.6.4.11 |  | 2025-03-27 17:00 | p | 21 |  | 2025-04-18 16:49
437 | 3933 | FbGZSJQTtuDZR2p8qmxq | Normal | 33 | 1.6.4.13 | 1.6.4.13 |  | 2025-03-27 17:00 | p | 38 |  | 2025-05-05 11:02
438 | 3935 | IRdaiLeeauelAg4QWklz | Normal | 33 | 1.6.4.12 | 1.6.4.12 |  | 2025-03-27 17:00 | p | 26 |  | 2025-04-23 14:13
439 | 3939 | cuQ4HC0Kn3S6GTvqv7QE | Normal | 33 | 1.6.4.14 | 1.6.4.14 |  | 2025-03-27 17:00 | p | 41 |  | 2025-05-08 08:55
440 | 3971 | mB1p68eekBqQhgV8es2U | Summary | 19 | 1.6.4.7 | 1.6.4.7 |  | 2025-04-07 17:00 | p | 35 |  | 2025-05-13 09:38
441 | 3974 | xzlIrgrrtbLscLWLbbQq | Normal | 1 | 1.6.4.7.1 | 1.6.4.7.1 |  | 2025-02-14 17:00 | p | 3 |  | 2025-02-18 08:40
442 | 3981 | YTm9sByrDxPUc7AlWXh1 | Normal | 15 | 1.6.4.7.2 | 1.6.4.7.2 |  | 2025-04-07 17:00 | p | 35 |  | 2025-05-13 09:38
443 | 3980 | po54OWwjtqomy5uOkFBU | Normal | 40 | 1.6.4.4 | 1.6.4.4 |  | 2025-04-07 17:00 | p | 35 |  | 2025-05-13 09:38
444 | 3991 | kc0LQmDrjfLGJeMU4QIH | Summary | 70 | 1.6.4.17 | 1.6.4.17 |  | 2025-05-29 17:00 | p | 40 |  | 2025-07-09 11:49
445 | 3992 | cy141kwlo0X5isTqv3ku | Summary | 25 | 1.6.4.17.4 | 1.6.4.17.4 |  | 2025-05-29 17:00 | p | 40 |  | 2025-07-09 11:49
446 | 3993 | LBRozXrRhpq69SKlxnDb | Normal | 10 | 1.6.4.17.4.1 | 1.6.4.17.4.1 |  | 2025-05-07 17:00 | p | 36 |  | 2025-06-13 15:55
447 | 3994 | DvOjAQ6C9aXKnpaAVD1H | Normal | 5 | 1.6.4.17.4.2 | 1.6.4.17.4.2 |  | 2025-05-14 17:00 | p | 40 |  | 2025-06-24 13:47
448 | 3995 | AUkl27NW1i9i5huez8Rg | Normal | 5 | 1.6.4.17.4.3 | 1.6.4.17.4.3 |  | 2025-05-21 17:00 | p | 40 |  | 2025-07-01 13:18
449 | 3996 | Bw8X4DjnSuQgBiA6BEKp | Normal | 5 | 1.6.4.17.4.4 | 1.6.4.17.4.4 |  | 2025-05-29 17:00 | p | 40 |  | 2025-07-09 11:49
450 | 3997 | KJPP8ivswwWTIeIfPXEM | Summary | 25 | 1.6.4.17.3 | 1.6.4.17.3 |  | 2025-04-23 17:00 | p | 34 |  | 2025-05-28 09:23
451 | 3998 | 5UhDwyM7phAycUkk1Nye | Normal | 10 | 1.6.4.17.3.1 | 1.6.4.17.3.1 |  | 2025-04-02 17:00 | p | 33 |  | 2025-05-06 13:19
452 | 3999 | v6kjlf8aEDhSJHzOK2Uo | Normal | 5 | 1.6.4.17.3.2 | 1.6.4.17.3.2 |  | 2025-04-09 17:00 | p | 33 |  | 2025-05-13 13:44
453 | 4000 | Y3aJp60cYMHromf8xgAE | Normal | 5 | 1.6.4.17.3.3 | 1.6.4.17.3.3 |  | 2025-04-16 17:00 | p | 32 |  | 2025-05-19 16:26
454 | 4001 | Cjtbc2cmKWchyZlcOxo3 | Normal | 5 | 1.6.4.17.3.4 | 1.6.4.17.3.4 |  | 2025-04-23 17:00 | p | 34 |  | 2025-05-28 09:23
455 | 4002 | nJzh0eFJGsqvOmQRJzHn | Summary | 27 | 1.6.4.17.2 | 1.6.4.17.2 |  | 2025-03-19 17:00 | p | 32 |  | 2025-04-21 16:12
456 | 4003 | gjf3v6NdOQannovTvAoE | Normal | 19 | 1.6.4.17.2.1 | 1.6.4.17.2.1 |  | 2025-03-07 17:00 | p | 30 |  | 2025-04-07 16:11
457 | 4004 | fF1Y54WMybWnXZsBJgYM | Normal | 1 | 1.6.4.17.2.2 | 1.6.4.17.2.2 |  | 2025-03-10 17:00 | p | 29 |  | 2025-04-09 08:26
458 | 4005 | NxZ8rMz5ZnJaz6z1SXKM | Normal | 3 | 1.6.4.17.2.3 | 1.6.4.17.2.3 |  | 2025-03-13 17:00 | p | 31 |  | 2025-04-14 15:27
459 | 4006 | fOTuJvqH3OcilXcZuEM5 | Normal | 4 | 1.6.4.17.2.4 | 1.6.4.17.2.4 |  | 2025-03-19 17:00 | p | 32 |  | 2025-04-21 16:12
460 | 4012 | A4Ck0Reyqf4cLzrM8uUY | Summary | 206 | 1.6.4.19 | 1.6.4.19 |  | 2025-11-26 17:00 | q | -244 |  | 2025-03-27 10:14
461 | 6168 | BHtkkzlMW8757DY2qb23 | Summary | 143 | 1.6.4.19.3 | 1.6.4.19.3 |  | 2025-11-26 17:00 | q | -244 |  | 2025-03-27 10:14
462 | 6169 | gdW3U4pURjb9iKkAVexH | Summary | 60 | 1.6.4.19.3.1 | 1.6.4.19.3.1 |  | 2025-07-29 17:00 | q | -250 |  | 2024-11-21 11:58
463 | 6170 | AwYLgXY6Mo1DqCbUEhPQ | Summary | 30 | 1.6.4.19.3.1.1 | 1.6.4.19.3.1.1 |  | 2025-06-13 17:00 | q | -248 |  | 2024-10-08 13:09
464 | 6171 | ZR4zae2ZYhCMcZhj7T05 | Normal | 15 | 1.6.4.19.3.1.1.1 | 1.6.4.19.3.1.1.1 |  | 2025-05-22 17:00 | q | -251 |  | 2024-09-13 08:51
465 | 6172 | QgFskomqU31VYtYzB2O0 | Normal | 15 | 1.6.4.19.3.1.1.2 | 1.6.4.19.3.1.1.2 |  | 2025-06-13 17:00 | q | -248 |  | 2024-10-08 13:09
466 | 6173 | nRc7GqDGMG4VP1O5IlEd | Normal | 15 | 1.6.4.19.3.1.2 | 1.6.4.19.3.1.2 |  | 2025-07-08 17:00 | q | -252 |  | 2024-10-29 13:56
467 | 6174 | dvLkHNDhuFTU7AO5XWky | Normal | 15 | 1.6.4.19.3.1.3 | 1.6.4.19.3.1.3 |  | 2025-07-29 17:00 | q | -250 |  | 2024-11-21 11:58
468 | 6175 | IEttja5qNJ6P760Cd9De | Summary | 40 | 1.6.4.19.3.2 | 1.6.4.19.3.2 |  | 2025-09-24 17:00 | q | -240 |  | 2025-01-27 13:26
469 | 6176 | B6x3R7fnpOwupecmo90D | Normal | 10 | 1.6.4.19.3.2.1 | 1.6.4.19.3.2.1 |  | 2025-08-12 17:00 | q | -245 |  | 2024-12-10 13:52
470 | 6177 | vkZhJMfsZWiMPLTjgcam | Normal | 10 | 1.6.4.19.3.2.2 | 1.6.4.19.3.2.2 |  | 2025-08-26 17:00 | q | -245 |  | 2024-12-24 10:02
471 | 6178 | XEU5rnQh2VnDpMl1eT0o | Normal | 10 | 1.6.4.19.3.2.3 | 1.6.4.19.3.2.3 |  | 2025-09-10 17:00 | q | -244 |  | 2025-01-09 11:14
472 | 6179 | xksMzlhYjvKZ4p1XJwSB | Normal | 10 | 1.6.4.19.3.2.4 | 1.6.4.19.3.2.4 |  | 2025-09-24 17:00 | q | -240 |  | 2025-01-27 13:26
473 | 6180 | oR7r0RquVFe2h8pCK9HY | Normal | 10 | 1.6.4.19.3.3 | 1.6.4.19.3.3 |  | 2025-10-08 17:00 | q | -240 |  | 2025-02-10 14:35
474 | 6181 | UJ3hrxCJ5NslZjdDLEyu | Normal | 20 | 1.6.4.19.3.4 | 1.6.4.19.3.4 |  | 2025-11-06 17:00 | q | -240 |  | 2025-03-11 14:19
475 | 6182 | JQHbjwkPqIslt5thIOgQ | Normal | 5 | 1.6.4.19.3.5 | 1.6.4.19.3.5 |  | 2025-11-14 17:00 | q | -242 |  | 2025-03-17 15:31
476 | 6183 | 5NqxhAyIl3JXTpWWvSnV | Normal | 2 | 1.6.4.19.3.6 | 1.6.4.19.3.6 |  | 2025-11-18 17:00 | q | -244 |  | 2025-03-19 11:26
477 | 6184 | vx8CoW16lw8uEEVKaVp7 | Normal | 5 | 1.6.4.19.3.7 | 1.6.4.19.3.7 |  | 2025-11-25 17:00 | q | -244 |  | 2025-03-26 10:08
478 | 6185 | A91LND4pEy61zvjvAsaQ | Normal | 1 | 1.6.4.19.3.8 | 1.6.4.19.3.8 |  | 2025-11-26 17:00 | q | -244 |  | 2025-03-27 10:14
479 | 4037 | hMBnPD0NfYpjSqEpRMYY | Summary | 554 | 1.6.4.20 | 1.6.4.20 |  | 2026-11-10 17:00 | p | 100 |  | 2027-02-19 10:11
480 | 4038 | VkrURyJwsSkEVRV6WcXe | Summary | 411 | 1.6.4.20.1 | 1.6.4.20.1 |  | 2026-04-22 17:00 | p | 76 |  | 2026-07-08 11:24
481 | 4040 | g5zNgGHP8U11wPTJKhcB | Normal | 20 | 1.6.4.20.1.3 | 1.6.4.20.1.3 |  | 2025-06-23 17:00 | q | -262 |  | 2024-10-04 16:18
482 | 4041 | f0PORH3GhEIXFjYfGbTd | Normal | 97 | 1.6.4.20.1.6 | 1.6.4.20.1.6 |  | 2025-10-10 17:00 | q | -217 |  | 2025-03-07 08:15
483 | 4042 | SyfMayqY4a7i0nZLPz6Y | Normal | 129 | 1.6.4.20.1.7 | 1.6.4.20.1.7 |  | 2026-03-23 17:00 | p | 92 |  | 2026-06-24 13:57
484 | 6621 | pXe0ZxltUhDf1quSL5q2 | Normal | 15 | 1.6.4.20.1.2 | 1.6.4.20.1.2 |  | 2025-05-22 17:00 | q | -251 |  | 2024-09-13 10:10
485 | 6622 | EmEy5gJckBYofEEYNXFv | Normal | 20 | 1.6.4.20.1.4 | 1.6.4.20.1.4 |  | 2026-03-25 17:00 | p | 75 |  | 2026-06-09 09:07
486 | 6623 | BVU87KMg9Rhzc6j5yKVh | Normal | 20 | 1.6.4.20.1.5 | 1.6.4.20.1.5 |  | 2026-04-22 17:00 | p | 76 |  | 2026-07-08 11:24
487 | 4043 | XbXkjxtfHUxhg4CK1elt | Summary | 127 | 1.6.4.20.2 | 1.6.4.20.2 |  | 2026-10-23 17:00 | p | 103 |  | 2027-02-04 09:16
488 | 4045 | mDphgqAAxA2RnvA52x8A | Normal | 20 | 1.6.4.20.2.1 | 1.6.4.20.2.1 |  | 2026-05-20 17:00 | p | 82 |  | 2026-08-11 16:05
489 | 4046 | 5HyQBVwuqRdeW1HhaSOP | Normal | 10 | 1.6.4.20.2.2 | 1.6.4.20.2.2 |  | 2026-06-04 17:00 | p | 83 |  | 2026-08-27 10:41
490 | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Normal | 72 | 1.6.4.20.2.3 | 1.6.4.20.2.3 |  | 2026-09-17 17:00 | p | 96 |  | 2026-12-23 10:38
491 | 4048 | ybbKhm9jdtNbVzABGZ8L | Normal | 20 | 1.6.4.20.2.4 | 1.6.4.20.2.4 |  | 2026-10-16 17:00 | p | 104 |  | 2027-01-29 09:24
492 | 4049 | kP1jeiEwkYg4HRpUjG4p | Normal | 5 | 1.6.4.20.2.5 | 1.6.4.20.2.5 |  | 2026-10-23 17:00 | p | 103 |  | 2027-02-04 09:16
493 | 4050 | jQIHIDf5FTnJxQysEvnn | Summary | 37 | 1.6.4.20.3 | 1.6.4.20.3 |  | 2026-11-10 17:00 | p | 100 |  | 2027-02-19 10:11
494 | 4051 | bizigDTezGi1mMHxJ1gi | Summary | 32 | 1.6.4.20.3.1 | 1.6.4.20.3.1 |  | 2026-11-03 17:00 | p | 97 |  | 2027-02-09 08:06
495 | 4052 | JSSXcLTdD9VQNM766DgK | Normal | 20 | 1.6.4.20.3.1.1 | 1.6.4.20.3.1.1 |  | 2026-10-16 17:00 | p | 97 |  | 2027-01-22 15:39
496 | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Normal | 12 | 1.6.4.20.3.1.2 | 1.6.4.20.3.1.2 |  | 2026-11-03 17:00 | p | 97 |  | 2027-02-09 08:06
497 | 4054 | WhXMUGkGRid5sulqMW8S | Summary | 5 | 1.6.4.20.3.2 | 1.6.4.20.3.2 |  | 2026-11-10 17:00 | p | 96 |  | 2027-02-15 15:07
498 | 4055 | dWrJCmOwv1i72p29KBXE | Normal | 2 | 1.6.4.20.3.2.1 | 1.6.4.20.3.2.1 |  | 2026-11-05 17:00 | p | 96 |  | 2027-02-10 16:11
499 | 4056 | a1SRK7UWhIIMlkKKriy9 | Normal | 1 | 1.6.4.20.3.2.2 | 1.6.4.20.3.2.2 |  | 2026-11-06 17:00 | p | 96 |  | 2027-02-11 16:13
500 | 4057 | NKnvgqAHKv63TOKudyZQ | Normal | 1 | 1.6.4.20.3.2.3 | 1.6.4.20.3.2.3 |  | 2026-11-09 17:00 | p | 94 |  | 2027-02-12 15:25
501 | 4058 | cbANjhwCBqAluf1RM04K | Normal | 1 | 1.6.4.20.3.2.4 | 1.6.4.20.3.2.4 |  | 2026-11-10 17:00 | p | 96 |  | 2027-02-15 15:07
502 | 4059 | sH9kz6O2EFda2hu4x8Kx | Summary | 12 | 1.6.4.20.3.3 | 1.6.4.20.3.3 |  | 2026-11-10 17:00 | p | 100 |  | 2027-02-19 10:11
503 | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Normal | 3 | 1.6.4.20.3.3.1 | 1.6.4.20.3.3.1 |  | 2026-10-28 17:00 | p | 102 |  | 2027-02-08 13:21
504 | 4061 | ViM2psfxppAdWr3IoYdq | Normal | 3 | 1.6.4.20.3.3.2 | 1.6.4.20.3.3.2 |  | 2026-11-02 17:00 | p | 100 |  | 2027-02-11 14:06
505 | 4062 | RvsEFsErXikPrAOovPaZ | Normal | 1 | 1.6.4.20.3.3.3 | 1.6.4.20.3.3.3 |  | 2026-11-03 17:00 | p | 100 |  | 2027-02-12 10:03
506 | 4063 | ma6GKJ3GzeKmeF4AshaM | Normal | 4 | 1.6.4.20.3.3.4 | 1.6.4.20.3.3.4 |  | 2026-11-09 17:00 | p | 100 |  | 2027-02-18 09:34
507 | 4064 | OALhjNOvEaqSDAmsS5Il | Normal | 1 | 1.6.4.20.3.3.5 | 1.6.4.20.3.3.5 |  | 2026-11-10 17:00 | p | 100 |  | 2027-02-19 10:11
508 | 5748 | cHP8KcDQZp8MvOi5a8Wj | Summary | 64 | 1.6.4.18 | 1.6.4.18 |  | 2025-04-11 17:00 | p | 4 |  | 2025-04-16 15:51
509 | 6701 | vwWJ3SVwW3tYdDDMDgOK | Summary | 60 | 1.6.4.18.3 | 1.6.4.18.3 |  | 2025-04-11 17:00 | p | 4 |  | 2025-04-16 15:51
510 | 6713 | JQXHTZXJblKyiNyxM0eT | Summary | 78 | 1.6.4.18.3.3 | 1.6.4.18.3.3 |  | 2025-04-11 17:00 | p | 4 |  | 2025-04-16 15:51
511 | 6727 | 5BlmDU3ct4fwjT54EODG | Summary | 21 | 1.6.4.18.3.3.2 | 1.6.4.18.3.3.2 |  | 2025-02-28 17:00 | q | 0 |  | 2025-02-28 08:19
512 | 7271 | 7ZvC3KC1rMxIYvbhicKJ | Normal | 10 | 1.6.4.18.3.3.2.7 | 1.6.4.18.3.3.2.7 |  | 2025-02-28 17:00 | q | 0 |  | 2025-02-28 08:19
513 | 7007 | 9uputDeZmGdSlUY8oN4J | Summary | 64 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 2025-04-11 17:00 | p | 4 |  | 2025-04-16 15:51
514 | 7010 | l7MAqMN94R7DBQRgok6z | Normal | 5 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 2025-04-11 17:00 | p | 4 |  | 2025-04-16 15:51
515 | 7278 | 4Ma7Z2LiPmWBC9UI6vyb | Normal | 5 | 1.6.4.18.3.3.7.7 | 1.6.4.18.3.3.7.7 |  | 2025-03-28 17:00 | p | 2 |  | 2025-03-31 11:26
516 | 7300 | JMkMoXIhBdn9ICcOd798 | Normal | 5 | 1.6.4.18.3.3.7.4 | 1.6.4.18.3.3.7.4 |  | 2025-03-07 17:00 | q | 0 |  | 2025-03-07 11:52
517 | 7301 | mVBynbXAicTgOFud0Dl3 | Normal | 5 | 1.6.4.18.3.3.7.6 | 1.6.4.18.3.3.7.6 |  | 2025-03-21 17:00 | p | 2 |  | 2025-03-24 13:52
518 | 7302 | 6S1rSJxqNAmNyzjZVL7L | Normal | 5 | 1.6.4.18.3.3.7.8 | 1.6.4.18.3.3.7.8 |  | 2025-04-04 17:00 | p | 5 |  | 2025-04-10 13:11
519 | 7279 | uD2jpviUMAewZ4YhDj8P | Summary | 32 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 2025-03-12 17:00 | q | -7 |  | 2025-03-05 08:36
520 | 7282 | sTVLhyKAe9uIrxTuOSsB | Normal | 2 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 2025-02-21 17:00 | q | -8 |  | 2025-02-13 10:49
521 | 7283 | GyFcZSlU29ifaVubQEBd | Normal | 2 | 1.6.4.18.3.3.4.4 | 1.6.4.18.3.3.4.4 |  | 2025-02-25 17:00 | q | -7 |  | 2025-02-18 09:49
522 | 7284 | AoDPK2hmzwZjnwdc6ENo | Normal | 1 | 1.6.4.18.3.3.4.5 | 1.6.4.18.3.3.4.5 |  | 2025-02-26 17:00 | q | -7 |  | 2025-02-19 08:43
523 | 7285 | UP4KQN3vFTNJJtYiVHhd | Normal | 10 | 1.6.4.18.3.3.4.6 | 1.6.4.18.3.3.4.6 |  | 2025-03-12 17:00 | q | -7 |  | 2025-03-05 08:36
524 | 7286 | weppsWRcwILLbxkFpraK | Summary | 39 | 1.6.4.18.3.3.5 | 1.6.4.18.3.3.5 |  | 2025-03-18 17:00 | p | 1 |  | 2025-03-20 09:30
525 | 7289 | YNbMTserJcwdDTx8O6lt | Normal | 5 | 1.6.4.18.3.3.5.3 | 1.6.4.18.3.3.5.3 |  | 2025-02-27 17:00 | p | 4 |  | 2025-03-04 09:58
526 | 7290 | rpRUKocvSOF2GnoJsxWr | Normal | 2 | 1.6.4.18.3.3.5.4 | 1.6.4.18.3.3.5.4 |  | 2025-03-03 17:00 | p | 2 |  | 2025-03-06 09:58
527 | 7291 | ThxkR8uStFOgKr5Kajlm | Normal | 1 | 1.6.4.18.3.3.5.5 | 1.6.4.18.3.3.5.5 |  | 2025-03-04 17:00 | p | 2 |  | 2025-03-07 09:02
528 | 7292 | 6vEOHVPLFOaXnW1xcDp6 | Normal | 10 | 1.6.4.18.3.3.5.6 | 1.6.4.18.3.3.5.6 |  | 2025-03-18 17:00 | p | 1 |  | 2025-03-20 09:30
529 | 7293 | ep0qwejNT11UOlW5WmY0 | Summary | 28 | 1.6.4.18.3.3.6 | 1.6.4.18.3.3.6 |  | 2025-03-28 17:00 | p | 6 |  | 2025-04-04 11:17
530 | 7296 | PnFVdPiNKahDkradYWdd | Normal | 5 | 1.6.4.18.3.3.6.3 | 1.6.4.18.3.3.6.3 |  | 2025-03-11 17:00 | p | 5 |  | 2025-03-17 09:24
531 | 7297 | JA5LCeR4tD4Vqq2Jfy9o | Normal | 2 | 1.6.4.18.3.3.6.4 | 1.6.4.18.3.3.6.4 |  | 2025-03-13 17:00 | p | 4 |  | 2025-03-18 16:05
532 | 7298 | uHK4wyA8DzlXgqm5UKoq | Normal | 1 | 1.6.4.18.3.3.6.5 | 1.6.4.18.3.3.6.5 |  | 2025-03-14 17:00 | p | 4 |  | 2025-03-19 14:52
533 | 7299 | ymtRqRQZa4AjGraGOZVd | Normal | 10 | 1.6.4.18.3.3.6.6 | 1.6.4.18.3.3.6.6 |  | 2025-03-28 17:00 | p | 6 |  | 2025-04-04 11:17
534 | 6297 | AqdIsKbIPOfZJkjKYjnG | Summary | 118 | 1.6.1 | 1.6.1 |  | 2026-08-26 17:00 | q | -373 |  | 2025-08-18 14:35
535 | 4200 | YSdvLAa6ztbhOKei71CV | Summary | 108 | 1.6.1.1 | 1.6.1.1 |  | 2025-07-15 17:00 | p | 30 |  | 2025-08-15 13:39
536 | 4202 | N5DTU5adYVhKR5So2Uvc | Normal | 88 | 1.6.1.1.3 | 1.6.1.1.3 |  | 2025-06-13 17:00 | p | 34 |  | 2025-07-18 08:03
537 | 4204 | CRzwy8942pbCOpcOMW2v | Normal | 20 | 1.6.1.1.4 | 1.6.1.1.4 |  | 2025-07-15 17:00 | p | 30 |  | 2025-08-15 13:39
538 | 4209 | 0Ck6gz1ZilLs9fM0b7nU | Summary | 46 | 1.6.1.3 | 1.6.1.3 |  | 2025-04-15 17:00 | p | 15 |  | 2025-05-01 09:01
539 | 4212 | yktUOUuzQyzOVBFBfL42 | Normal | 46 | 1.6.1.3.1 | 1.6.1.3.1 |  | 2025-04-15 17:00 | p | 15 |  | 2025-05-01 09:01
540 | 4218 | T5g2El1CSAmFZNlboxQh | Normal | 1 | 1.6.1.4 | 1.6.1.4 |  | 2025-07-16 17:00 | p | 32 |  | 2025-08-18 14:35
541 | 6080 | jFrzSNmYyPDtKSvRlBw2 | Normal | 1 | 1.6.1.6 | 1.6.1.6 |  | 2026-08-26 17:00 | q | -1115 |  | 2023-08-07 16:17
542 | 6311 | tQdu1pFxVkY2bj5IQjxI | Summary | 77 | 1.6.3 | 1.6.3 |  | 2025-07-11 17:00 | p | 159 |  | 2025-12-18 08:10
543 | 5452 | u9nFTwEoKsBrgeg8njOT | Normal | 5 | 1.6.3.1 | 1.6.3.1 |  | 2025-02-14 17:00 | p | 298 |  | 2025-12-10 16:55
544 | 5457 | kGunJCROCjWQWqBfRKBZ | Summary | 1 | 1.6.3.2 | 1.6.3.2 |  | 2025-02-14 17:00 | p | 25 |  | 2025-03-12 09:58
545 | 5458 | DngVHB2HpHpsOjFWu5hu | Summary | 1 | 1.6.3.2.1 | 1.6.3.2.1 |  | 2025-02-14 17:00 | p | 25 |  | 2025-03-12 09:58
546 | 5505 | nVzBMSNTKKq9KPWblsw1 | Normal | 1 | 1.6.3.2.1.9 | 1.6.3.2.1.9 |  | 2025-02-14 17:00 | p | 25 |  | 2025-03-12 09:58
547 | 5506 | wLM81Xdu8B5geOMMQz6m | Summary | 119 | 1.6.3.3 | 1.6.3.3 |  | 2025-07-11 17:00 | p | 159 |  | 2025-12-18 08:10
548 | 5507 | 1r4d5DbY2YIgMhg8HKuO | Normal | 3 | 1.6.3.3.2 | 1.6.3.3.2 |  | 2025-04-10 17:00 | p | 14 |  | 2025-04-25 15:13
549 | 5508 | wHSntGHJkj4aA0wA3fA2 | Normal | 14 | 1.6.3.3.3 | 1.6.3.3.3 |  | 2025-04-30 17:00 | p | 15 |  | 2025-05-16 13:13
550 | 5509 | 1FHP32ReWIveKb3JOWEG | Summary | 44 | 1.6.3.3.4 | 1.6.3.3.4 |  | 2025-07-03 17:00 | p | 25 |  | 2025-07-29 09:13
551 | 5510 | LTFwTsrnxYhrGNFUv7CM | Normal | 12 | 1.6.3.3.4.1 | 1.6.3.3.4.1 |  | 2025-05-16 12:00 | p | 24 |  | 2025-06-09 13:11
552 | 5511 | Od3mMFxB7LjrJLF1slz4 | Normal | 11 | 1.6.3.3.4.2 | 1.6.3.3.4.2 |  | 2025-06-03 17:00 | p | 22 |  | 2025-06-26 15:16
553 | 5512 | Des2hDKSMjcJndTJRzoQ | Normal | 11 | 1.6.3.3.4.3 | 1.6.3.3.4.3 |  | 2025-06-18 17:00 | p | 26 |  | 2025-07-15 10:49
554 | 5513 | z1vb48lrGwUUDjKbD3gr | Normal | 10 | 1.6.3.3.4.4 | 1.6.3.3.4.4 |  | 2025-07-03 17:00 | p | 25 |  | 2025-07-29 09:13
555 | 5514 | leNXdZKmybH4tpy20cQU | Normal | 5 | 1.6.3.3.5 | 1.6.3.3.5 |  | 2025-07-11 17:00 | p | 159 |  | 2025-12-18 08:10
556 | 6890 | QKIolSsTnUWZiIhR6M5v | Normal | 40 | 1.6.3.3.1 | 1.6.3.3.1 |  | 2025-04-07 17:00 | p | 14 |  | 2025-04-22 10:47
557 | 6359 | hvfa0617w1FgmEnjjKwJ | Summary | 26 | 1.7.2.16 | 1.7.2.16 |  | 2025-03-04 17:00 | p | 1 |  | 2025-03-06 11:06
558 | 6360 | DMXbIVCeMtVR5pi4d5UN | Summary | 26 | 1.7.2.16.1 | 1.7.2.16.1 |  | 2025-03-04 17:00 | p | 1 |  | 2025-03-06 11:06
559 | 6361 | VEKeY9azNIVSZDSjYyKy | Summary | 33 | 1.7.2.16.1.3 | 1.7.2.16.1.3 |  | 2025-03-04 17:00 | p | 1 |  | 2025-03-06 11:06
560 | 7303 | fpLHmKjlfpy4s4tap5Xw | Summary | 39 | 1.6.3.11.1.3.4 | 1.6.3.11.1.3.4 |  | 2025-02-19 17:00 | q | -8 |  | 2025-02-11 10:23
561 | 7307 | eye8r8DevGvPITcdrMUe | Normal | 6 | 1.6.3.11.1.3.4.4 | 1.6.3.11.1.3.4.4 |  | 2025-02-18 17:00 | q | -8 |  | 2025-02-10 11:28
562 | 7308 | BXoPyB4GmzJwvFdrkJ7b | Normal | 1 | 1.6.3.11.1.3.4.5 | 1.6.3.11.1.3.4.5 |  | 2025-02-19 17:00 | q | -8 |  | 2025-02-11 10:23
563 | 7309 | 19skeJKmh3pRSfTF3DDB | Summary | 30 | 1.6.3.11.1.3.5 | 1.6.3.11.1.3.5 |  | 2025-02-20 17:00 | p | 0 |  | 2025-02-21 16:57
564 | 7313 | boaUnlKi0h6sKdwgAbmA | Normal | 5 | 1.6.3.11.1.3.5.4 | 1.6.3.11.1.3.5.4 |  | 2025-02-19 17:00 | p | 0 |  | 2025-02-20 15:12
565 | 7314 | zaliCdoIQDW2tx8wBQyt | Normal | 1 | 1.6.3.11.1.3.5.5 | 1.6.3.11.1.3.5.5 |  | 2025-02-20 17:00 | p | 0 |  | 2025-02-21 16:57
566 | 7315 | 9LywAxRsXdHsCrCcjGKV | Summary | 27 | 1.6.3.11.1.3.6 | 1.6.3.11.1.3.6 |  | 2025-03-04 17:00 | p | 1 |  | 2025-03-06 11:06
567 | 7318 | vWglY3BMmZCigDWMEMyY | Normal | 3 | 1.6.3.11.1.3.6.3 | 1.6.3.11.1.3.6.3 |  | 2025-02-24 17:00 | p | 1 |  | 2025-02-26 15:34
568 | 7319 | Fr6VbOwwg75s6X3Xcfql | Normal | 5 | 1.6.3.11.1.3.6.4 | 1.6.3.11.1.3.6.4 |  | 2025-03-03 17:00 | p | 1 |  | 2025-03-05 13:53
569 | 7320 | MRmQHJYBr9cc2OfLUSYd | Normal | 1 | 1.6.3.11.1.3.6.5 | 1.6.3.11.1.3.6.5 |  | 2025-03-04 17:00 | p | 1 |  | 2025-03-06 11:06
570 | 6273 | ljz6i2ltFwqcRU3btDx0 | Summary | 552 | 1.8 | 1.8 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
571 | 1639 | mkPE1mMWzawwUBF3KKzV | Summary | 277 | 1.8.2 | 1.8.2 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
572 | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Milestone | 0 | 1.8.2.1 | 1.8.2.1 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
573 | 6074 | fkBL64dyW7paLwgGr0ue | Normal | 212 | 1.8.2.3 | 1.8.2.3 |  | 2025-12-12 17:00 | p | 27 |  | 2026-01-09 16:28
574 | 6075 | pe2nScqRc5pgTwGaT5Zd | Normal | 193 | 1.8.2.2 | 1.8.2.2 |  | 2025-11-14 17:00 | p | 51 |  | 2026-01-05 15:20
575 | 6295 | uPS9GNqRLP4065SnBhEr | Summary | 387 | 1.8.5 | 1.8.5 |  | 2026-05-01 17:00 | q | -18 |  | 2026-04-13 11:49
576 | 3679 | 1KDcwGZKgevw1MizqBh0 | Summary | 387 | 1.8.5.1 | 1.8.5.1 |  | 2026-05-01 17:00 | q | -18 |  | 2026-04-13 11:49
577 | 3680 | E8qsx9NjEz7vaL5H7EFb | Summary | 189 | 1.8.5.1.1 | 1.8.5.1.1 |  | 2025-12-22 17:00 | p | 28 |  | 2026-01-20 16:54
578 | 3681 | wdhUrQuIMTMPn1LoqO1m | Normal | 24 | 1.8.5.1.1.1 | 1.8.5.1.1.1 |  | 2025-04-24 17:00 | p | 7 |  | 2025-05-02 09:24
579 | 3682 | 38PSIqFGHzjKldiudT82 | Summary | 25 | 1.8.5.1.1.4 | 1.8.5.1.1.4 |  | 2025-05-30 17:00 | p | 12 |  | 2025-06-12 11:53
580 | 3683 | JW3LUw009FZ7ddD6CdLX | Normal | 20 | 1.8.5.1.1.4.1 | 1.8.5.1.1.4.1 |  | 2025-05-22 17:00 | p | 11 |  | 2025-06-03 16:26
581 | 3684 | g3f8U3i4iakOhylueut6 | Normal | 5 | 1.8.5.1.1.4.2 | 1.8.5.1.1.4.2 |  | 2025-05-30 17:00 | p | 12 |  | 2025-06-12 11:53
582 | 3685 | eStRoX3vnaDmRLAWk58C | Summary | 40 | 1.8.5.1.1.5 | 1.8.5.1.1.5 |  | 2025-07-29 17:00 | p | 20 |  | 2025-08-19 08:33
583 | 3686 | 7zhxjkpiLTAH9tiW1eYy | Normal | 20 | 1.8.5.1.1.5.1 | 1.8.5.1.1.5.1 |  | 2025-06-30 17:00 | p | 17 |  | 2025-07-18 15:02
584 | 3687 | 0zzWvesUS18qEUfjK5NH | Normal | 5 | 1.8.5.1.1.5.2 | 1.8.5.1.1.5.2 |  | 2025-07-08 17:00 | p | 16 |  | 2025-07-25 16:44
585 | 3688 | zSUYYsBrfiOGi6qJakS6 | Normal | 5 | 1.8.5.1.1.5.3 | 1.8.5.1.1.5.3 |  | 2025-07-15 17:00 | p | 19 |  | 2025-08-04 10:03
586 | 3689 | X7sWUqInOJZ9zcVzmfT1 | Normal | 5 | 1.8.5.1.1.5.4 | 1.8.5.1.1.5.4 |  | 2025-07-22 17:00 | p | 19 |  | 2025-08-11 11:02
587 | 3690 | 8YDpqEvemQaMsfVmGpF8 | Normal | 5 | 1.8.5.1.1.5.5 | 1.8.5.1.1.5.5 |  | 2025-07-29 17:00 | p | 20 |  | 2025-08-19 08:33
588 | 3691 | ofZrlktbiXkVpuhhIeO5 | Summary | 25 | 1.8.5.1.1.6 | 1.8.5.1.1.6 |  | 2025-08-05 17:00 | p | 20 |  | 2025-08-26 08:33
589 | 3692 | xRsKOxB8zGAnVTXugcHQ | Normal | 20 | 1.8.5.1.1.6.1 | 1.8.5.1.1.6.1 |  | 2025-07-29 17:00 | p | 19 |  | 2025-08-18 16:30
590 | 3693 | Hn8rBaTvxeP9Vb10zF48 | Normal | 5 | 1.8.5.1.1.6.2 | 1.8.5.1.1.6.2 |  | 2025-08-05 17:00 | p | 20 |  | 2025-08-26 08:33
591 | 3694 | 4tipOydrC0LTNincaMDW | Summary | 35 | 1.8.5.1.1.7 | 1.8.5.1.1.7 |  | 2025-09-17 17:00 | p | 36 |  | 2025-10-24 13:49
592 | 3695 | lT6NpgfSYqKHtVYFLSzF | Normal | 20 | 1.8.5.1.1.7.1 | 1.8.5.1.1.7.1 |  | 2025-08-26 17:00 | p | 33 |  | 2025-09-29 09:56
593 | 3696 | gijouZuJR1ZVcSfHKSTf | Normal | 5 | 1.8.5.1.1.7.2 | 1.8.5.1.1.7.2 |  | 2025-09-03 17:00 | p | 33 |  | 2025-10-07 10:03
594 | 3697 | 1158ttL4JEmZYV6RmdcS | Normal | 5 | 1.8.5.1.1.7.3 | 1.8.5.1.1.7.3 |  | 2025-09-10 17:00 | p | 35 |  | 2025-10-16 08:57
595 | 3698 | AKCwPpEPQi4iH3XDRpiM | Normal | 5 | 1.8.5.1.1.7.4 | 1.8.5.1.1.7.4 |  | 2025-09-17 17:00 | p | 36 |  | 2025-10-24 13:49
596 | 3699 | AYANEA6OuC5b95kp3uyI | Summary | 30 | 1.8.5.1.1.8 | 1.8.5.1.1.8 |  | 2025-10-08 17:00 | p | 34 |  | 2025-11-12 10:27
597 | 3700 | WE9bFDn3y5M7oiID5UPj | Normal | 20 | 1.8.5.1.1.8.1 | 1.8.5.1.1.8.1 |  | 2025-09-24 17:00 | p | 29 |  | 2025-10-24 13:58
598 | 3701 | CXSHp4tESy2S0nMNpo3C | Normal | 5 | 1.8.5.1.1.8.2 | 1.8.5.1.1.8.2 |  | 2025-10-01 17:00 | p | 29 |  | 2025-10-31 16:47
599 | 3702 | sTuPByKbZEfSXxt0Z2G9 | Normal | 5 | 1.8.5.1.1.8.3 | 1.8.5.1.1.8.3 |  | 2025-10-08 17:00 | p | 34 |  | 2025-11-12 10:27
600 | 3703 | WHZRJAK4v6S9Zk2EBeP3 | Summary | 40 | 1.8.5.1.1.9 | 1.8.5.1.1.9 |  | 2025-11-21 17:00 | p | 23 |  | 2025-12-15 08:23
601 | 3704 | 3CXbrhXJooXd98jlpAkg | Normal | 20 | 1.8.5.1.1.9.1 | 1.8.5.1.1.9.1 |  | 2025-10-23 17:00 | p | 21 |  | 2025-11-14 10:21
602 | 3705 | RO9RShNcg0h7x9fD24Zk | Normal | 5 | 1.8.5.1.1.9.2 | 1.8.5.1.1.9.2 |  | 2025-10-30 17:00 | p | 19 |  | 2025-11-19 13:23
603 | 3706 | w8MhGnhxyXFIHvJdw6bc | Normal | 5 | 1.8.5.1.1.9.3 | 1.8.5.1.1.9.3 |  | 2025-11-06 17:00 | p | 21 |  | 2025-11-28 11:01
604 | 3707 | dJNKgtiJ1M8pNoPOlZcZ | Normal | 5 | 1.8.5.1.1.9.4 | 1.8.5.1.1.9.4 |  | 2025-11-14 17:00 | p | 23 |  | 2025-12-08 08:35
605 | 3708 | 84VtM14FQkMGurZDdBLv | Normal | 5 | 1.8.5.1.1.9.5 | 1.8.5.1.1.9.5 |  | 2025-11-21 17:00 | p | 23 |  | 2025-12-15 08:23
606 | 3709 | gpO5WcJkYid7jZAXZwbn | Summary | 40 | 1.8.5.1.1.10 | 1.8.5.1.1.10 |  | 2025-12-22 17:00 | p | 28 |  | 2026-01-20 16:54
607 | 3710 | KOKaQwRJEoC6vlU3mKjm | Normal | 20 | 1.8.5.1.1.10.1 | 1.8.5.1.1.10.1 |  | 2025-11-21 17:00 | p | 24 |  | 2025-12-16 13:41
608 | 3711 | XXu8BmtFqx4o2r8a6o98 | Normal | 5 | 1.8.5.1.1.10.2 | 1.8.5.1.1.10.2 |  | 2025-12-01 17:00 | p | 22 |  | 2025-12-24 08:37
609 | 3712 | sZwrgRbHYjKWcIa9rVK3 | Normal | 5 | 1.8.5.1.1.10.3 | 1.8.5.1.1.10.3 |  | 2025-12-08 17:00 | p | 24 |  | 2026-01-02 15:25
610 | 3713 | 4NbryuRKpmrExDEDqArG | Normal | 5 | 1.8.5.1.1.10.4 | 1.8.5.1.1.10.4 |  | 2025-12-15 17:00 | p | 24 |  | 2026-01-09 09:53
611 | 3714 | Fbm1iHrhCX8z8SNRXJuq | Normal | 5 | 1.8.5.1.1.10.5 | 1.8.5.1.1.10.5 |  | 2025-12-22 17:00 | p | 28 |  | 2026-01-20 16:54
612 | 6646 | CmmxWTpZgFyyAwkQnNh3 | Normal | 10 | 1.8.5.1.1.2 | 1.8.5.1.1.2 |  | 2025-05-08 17:00 | p | 6 |  | 2025-05-15 15:57
613 | 6647 | hWzCSsDre5WTTpryk1b0 | Normal | 5 | 1.8.5.1.1.3 | 1.8.5.1.1.3 |  | 2025-05-15 17:00 | p | 7 |  | 2025-05-23 15:38
614 | 3715 | V6i7uYjEJBRYHjhIimqJ | Summary | 50 | 1.8.5.1.2 | 1.8.5.1.2 |  | 2026-03-06 17:00 | p | 20 |  | 2026-03-27 11:53
615 | 3716 | bdy5zVX59rD935sK6M5v | Normal | 20 | 1.8.5.1.2.1 | 1.8.5.1.2.1 |  | 2026-01-22 17:00 | p | 26 |  | 2026-02-18 09:11
616 | 3717 | 5PdqCAMtbYgi5VsFO6ls | Normal | 20 | 1.8.5.1.2.4 | 1.8.5.1.2.4 |  | 2026-03-06 17:00 | p | 20 |  | 2026-03-27 11:53
617 | 6671 | 0oTh3tmNX3iVSaVNVmGK | Normal | 5 | 1.8.5.1.2.2 | 1.8.5.1.2.2 |  | 2026-01-29 17:00 | p | 27 |  | 2026-02-26 09:38
618 | 6672 | BKyGOzVPyPwKpI9CyseJ | Normal | 5 | 1.8.5.1.2.3 | 1.8.5.1.2.3 |  | 2026-02-05 17:00 | p | 25 |  | 2026-03-03 10:48
619 | 3718 | vTyTgxcbRSz6H6lqDAEf | Summary | 20 | 1.8.5.1.3 | 1.8.5.1.3 |  | 2026-04-03 17:00 | p | 9 |  | 2026-04-13 11:49
620 | 3719 | B9ymEBZ7zimHMMqNS20Q | Normal | 20 | 1.8.5.1.3.1 | 1.8.5.1.3.1 |  | 2026-04-03 17:00 | p | 9 |  | 2026-04-13 11:49
621 | 3720 | rPRo0RE1uNkj9oG127hu | Summary | 109 | 1.8.5.1.4 | 1.8.5.1.4 |  | 2025-08-21 17:00 | q | -603 |  | 2023-12-27 10:48
622 | 3721 | 45j7fpB55qVEeWfRBgCv | Normal | 1 | 1.8.5.1.4.1 | 1.8.5.1.4.1 |  | 2025-03-19 17:00 | q | -590 |  | 2023-08-07 16:59
623 | 3722 | hYa6Ppkzu6veYWmxHffd | Normal | 27 | 1.8.5.1.4.2 | 1.8.5.1.4.2 |  | 2025-04-25 17:00 | q | -589 |  | 2023-09-14 10:45
624 | 6649 | TeFWDZJ3h8q4yVNptUYE | Normal | 28 | 1.8.5.1.4.3 | 1.8.5.1.4.3 |  | 2025-06-05 17:00 | q | -590 |  | 2023-10-24 11:20
625 | 6650 | FvuNLI4Jaew3VjPpwL3e | Normal | 28 | 1.8.5.1.4.4 | 1.8.5.1.4.4 |  | 2025-07-17 17:00 | q | -603 |  | 2023-11-22 11:54
626 | 6651 | T3J0AzovT4qFTLJ7Lgki | Normal | 15 | 1.8.5.1.4.5 | 1.8.5.1.4.5 |  | 2025-08-07 17:00 | q | -602 |  | 2023-12-14 08:10
627 | 6652 | 0afM7N7hGdWHQjlFenVR | Normal | 10 | 1.8.5.1.4.6 | 1.8.5.1.4.6 |  | 2025-08-21 17:00 | q | -603 |  | 2023-12-27 10:48
628 | 3723 | 4qmbzAmtSx0gvDVaBsYe | Summary | 239 | 1.8.5.1.5 | 1.8.5.1.5 |  | 2025-12-26 17:00 | p | 18 |  | 2026-01-14 08:31
629 | 3724 | ZCOxRRLLrh9Pa7VnBAyk | Normal | 27 | 1.8.5.1.5.1 | 1.8.5.1.5.1 |  | 2025-04-29 17:00 | p | 12 |  | 2025-05-12 16:01
630 | 3725 | 8cgOIQk4rBKvjXdBm8mF | Normal | 91 | 1.8.5.1.5.9 | 1.8.5.1.5.9 |  | 2025-06-18 17:00 | q | -6 |  | 2025-06-12 16:22
631 | 6661 | bQxmmL7mcUsEGpKkQTDo | Normal | 28 | 1.8.5.1.5.2 | 1.8.5.1.5.2 |  | 2025-06-09 17:00 | p | 14 |  | 2025-06-24 09:50
632 | 6662 | CVNpv9CNU8XhfLmVwl8x | Normal | 28 | 1.8.5.1.5.3 | 1.8.5.1.5.3 |  | 2025-07-21 17:00 | p | 13 |  | 2025-08-04 10:00
633 | 6663 | LVExlIxeJ6XB3yqm0Dzs | Normal | 28 | 1.8.5.1.5.4 | 1.8.5.1.5.4 |  | 2025-08-28 17:00 | p | 13 |  | 2025-09-11 10:43
634 | 6664 | Io9oZ1dPqEE9GDlMTPxh | Normal | 28 | 1.8.5.1.5.5 | 1.8.5.1.5.5 |  | 2025-10-08 17:00 | p | 13 |  | 2025-10-22 16:20
635 | 6665 | ycT0qtEFjd4p02S4Ehf1 | Normal | 28 | 1.8.5.1.5.6 | 1.8.5.1.5.6 |  | 2025-11-19 17:00 | p | 11 |  | 2025-12-01 13:30
636 | 6666 | sX3PHseynvzwKI9my2AH | Normal | 15 | 1.8.5.1.5.7 | 1.8.5.1.5.7 |  | 2025-12-11 17:00 | p | 21 |  | 2026-01-02 13:43
637 | 6667 | 0dYk2X7XWh2rSSHkHo2L | Normal | 10 | 1.8.5.1.5.8 | 1.8.5.1.5.8 |  | 2025-12-26 17:00 | p | 18 |  | 2026-01-14 08:31
638 | 6668 | NGuTznXCCG5yuIi6lGQO | Normal | 1 | 1.8.5.1.5.10 | 1.8.5.1.5.10 |  | 2025-06-20 17:00 | q | -4 |  | 2025-06-16 09:10
639 | 6669 | t8MCocRefa6DhiQNsJVn | Normal | 1 | 1.8.5.1.5.11 | 1.8.5.1.5.11 |  | 2025-06-23 17:00 | q | -6 |  | 2025-06-17 10:26
640 | 6670 | vWxPVjk5e7KHTev8998h | Normal | 1 | 1.8.5.1.5.12 | 1.8.5.1.5.12 |  | 2025-06-24 17:00 | q | -6 |  | 2025-06-18 11:53
641 | 3726 | 5hjTNIk7WmpZNtmCLhPN | Summary | 96 | 1.8.5.1.6 | 1.8.5.1.6 |  | 2025-09-24 17:00 | q | -170 |  | 2025-04-07 15:53
642 | 3727 | rGcF2XgkgPtqRDM3KJ2D | Normal | 28 | 1.8.5.1.6.1 | 1.8.5.1.6.1 |  | 2025-06-17 17:00 | q | -183 |  | 2024-12-16 08:38
643 | 3728 | Hgqc9wbzS3SDikBm20zt | Normal | 28 | 1.8.5.1.6.3 | 1.8.5.1.6.3 |  | 2025-08-19 17:00 | q | -172 |  | 2025-02-28 09:27
644 | 6653 | K0AYRckqpyO0HzRrxXG6 | Normal | 15 | 1.8.5.1.6.2 | 1.8.5.1.6.2 |  | 2025-07-10 17:00 | q | -183 |  | 2025-01-08 13:33
645 | 6654 | MMK0qYycfTMCrFAZcf8J | Normal | 15 | 1.8.5.1.6.4 | 1.8.5.1.6.4 |  | 2025-09-10 17:00 | q | -170 |  | 2025-03-24 14:21
646 | 6655 | gl8c5oVG5KfrLbsQSFL4 | Normal | 10 | 1.8.5.1.6.5 | 1.8.5.1.6.5 |  | 2025-09-24 17:00 | q | -170 |  | 2025-04-07 15:53
647 | 3729 | Y6b5KP0DE9c4tlFzqxp3 | Summary | 81 | 1.8.5.1.7 | 1.8.5.1.7 |  | 2025-07-03 17:00 | q | -584 |  | 2023-11-27 11:06
648 | 3730 | TswICWhG0Mjj1DenbPW5 | Normal | 28 | 1.8.5.1.7.1 | 1.8.5.1.7.1 |  | 2025-04-17 17:00 | q | -577 |  | 2023-09-18 16:36
649 | 6626 | 9d2gtkuh8SmNZwArNzpn | Normal | 10 | 1.8.5.1.7.4 | 1.8.5.1.7.4 |  | 2025-07-03 17:00 | q | -584 |  | 2023-11-27 11:06
650 | 6627 | QBgG0JxqOymB6vyjKsRZ | Normal | 28 | 1.8.5.1.7.2 | 1.8.5.1.7.2 |  | 2025-05-28 17:00 | q | -581 |  | 2023-10-25 15:22
651 | 6628 | PAI9VZBMaYriaY1wvhOi | Normal | 15 | 1.8.5.1.7.3 | 1.8.5.1.7.3 |  | 2025-06-18 17:00 | q | -582 |  | 2023-11-14 08:25
652 | 3733 | ufu7SWDoeBfTzZW24BQU | Summary | 189 | 1.8.5.1.9 | 1.8.5.1.9 |  | 2025-12-15 17:00 | p | 27 |  | 2026-01-12 08:25
653 | 3734 | cAszcoDUs4YPdXAiXa4B | Milestone | 0 | 1.8.5.1.9.1 | 1.8.5.1.9.1 |  | 2025-03-17 08:00 | q | -588 |  | 2023-08-07 08:00
654 | 3735 | rgqtw8hyurrfag2amXLA | Normal | 109 | 1.8.5.1.9.2 | 1.8.5.1.9.2 |  | 2025-08-19 17:00 | q | -588 |  | 2024-01-09 09:41
655 | 3736 | eIMYQUSTObIc5Lp6kKBE | Normal | 40 | 1.8.5.1.9.3 | 1.8.5.1.9.3 |  | 2025-10-16 17:00 | q | -608 |  | 2024-02-16 08:12
656 | 3737 | z19Wnme0hJcfEI4IfIQR | Normal | 25 | 1.8.5.1.9.4 | 1.8.5.1.9.4 |  | 2025-11-21 17:00 | p | 23 |  | 2025-12-15 14:16
657 | 6657 | uq5fluI8KT8LkPx57ktn | Normal | 10 | 1.8.5.1.9.5 | 1.8.5.1.9.5 |  | 2025-12-08 17:00 | p | 24 |  | 2026-01-02 09:26
658 | 6658 | ktg0XNnAmjjc1caqICt2 | Normal | 5 | 1.8.5.1.9.6 | 1.8.5.1.9.6 |  | 2025-12-15 17:00 | p | 27 |  | 2026-01-12 08:25
659 | 3738 | bohrZqwOTsvUL4DEUnjh | Summary | 139 | 1.8.5.1.10 | 1.8.5.1.10 |  | 2025-10-01 17:00 | q | -586 |  | 2024-02-23 09:07
660 | 3739 | Ba23bBwg4xGpRd3Ht4kS | Normal | 24 | 1.8.5.1.10.1 | 1.8.5.1.10.1 |  | 2025-04-17 17:00 | q | -589 |  | 2023-09-06 09:53
661 | 3740 | lRtbtcrLyr1QGd0laoJi | Normal | 25 | 1.8.5.1.10.2 | 1.8.5.1.10.2 |  | 2025-05-22 17:00 | q | -588 |  | 2023-10-12 14:10
662 | 3741 | V05WnFKB5t2LuixhoKHO | Normal | 25 | 1.8.5.1.10.3 | 1.8.5.1.10.3 |  | 2025-06-30 17:00 | q | -586 |  | 2023-11-22 14:32
663 | 3742 | LRjVz0hoZuIRlQgcLYzs | Normal | 25 | 1.8.5.1.10.6 | 1.8.5.1.10.6 |  | 2025-09-10 17:00 | q | -583 |  | 2024-02-05 11:06
664 | 6648 | Z5T3n0GGVz8PB0IY5TXC | Normal | 10 | 1.8.5.1.10.5 | 1.8.5.1.10.5 |  | 2025-08-05 17:00 | q | -592 |  | 2023-12-22 13:47
665 | 6656 | tqprQgHoroqT051BXug3 | Normal | 15 | 1.8.5.1.10.4 | 1.8.5.1.10.4 |  | 2025-07-22 17:00 | q | -588 |  | 2023-12-12 14:39
666 | 6659 | NN3Qiea1foOxv05JqXnT | Normal | 10 | 1.8.5.1.10.7 | 1.8.5.1.10.7 |  | 2025-09-24 17:00 | q | -586 |  | 2024-02-16 09:31
667 | 6660 | pWIs4hM6SgH2pFjSQ3qo | Normal | 5 | 1.8.5.1.10.8 | 1.8.5.1.10.8 |  | 2025-10-01 17:00 | q | -586 |  | 2024-02-23 09:07
668 | 6642 | A7Bd82G8YCk8VjEZkcvi | Summary | 135 | 1.8.5.1.8 | 1.8.5.1.8 |  | 2026-05-01 17:00 | q | -115 |  | 2026-01-06 13:47
669 | 3731 | 02LiOyWN4DF8GOeNSP5s | Normal | 20 | 1.8.5.1.8.1 | 1.8.5.1.8.1 |  | 2025-11-14 17:00 | q | -613 |  | 2024-03-11 09:57
670 | 3732 | x85AkT9s5HT2a4U2goND | Normal | 20 | 1.8.5.1.8.8 | 1.8.5.1.8.8 |  | 2025-12-15 17:00 | q | -612 |  | 2024-04-12 08:54
671 | 6629 | n59ds33sZr9JNOobmYWE | Normal | 30 | 1.8.5.1.8.2 | 1.8.5.1.8.2 |  | 2025-12-30 17:00 | q | -631 |  | 2024-04-08 11:05
672 | 6630 | y36QmeQSyS7BZflkeM7e | Normal | 10 | 1.8.5.1.8.3 | 1.8.5.1.8.3 |  | 2026-01-14 17:00 | q | -632 |  | 2024-04-22 15:09
673 | 6631 | Ghk1eKq5exIyUH3hdAeR | Normal | 20 | 1.8.5.1.8.4 | 1.8.5.1.8.4 |  | 2026-02-12 17:00 | q | -632 |  | 2024-05-21 08:31
674 | 6632 | 5y36mClzGR7vkSsODb4C | Normal | 15 | 1.8.5.1.8.5 | 1.8.5.1.8.5 |  | 2026-03-06 17:00 | q | -638 |  | 2024-06-06 13:24
675 | 6633 | uS272glxjETpDiVeJyGv | Normal | 20 | 1.8.5.1.8.6 | 1.8.5.1.8.6 |  | 2026-04-03 17:00 | q | -633 |  | 2024-07-09 11:38
676 | 6634 | 65ghvPiwU0AxSKrC11rG | Normal | 20 | 1.8.5.1.8.7 | 1.8.5.1.8.7 |  | 2026-05-01 17:00 | q | -623 |  | 2024-08-16 10:21
677 | 6643 | sKnPCsxlq51dE8cz52fo | Normal | 10 | 1.8.5.1.8.9 | 1.8.5.1.8.9 |  | 2025-12-30 17:00 | q | -614 |  | 2024-04-25 11:25
678 | 6644 | 0NVu6ABxwy3imKaZ2MTJ | Normal | 10 | 1.8.5.1.8.10 | 1.8.5.1.8.10 |  | 2026-01-14 17:00 | q | -8 |  | 2026-01-06 13:47
679 | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Summary | 1 | 1.8.1 | 1.8.1 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
680 | 6082 | YsSSuERf5VIDKO5m8eZo | Normal | 1 | 1.8.1.1 | 1.8.1.1 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
681 | 6313 | 8HYxn50EKf1DU0fX0MF7 | Summary | 391 | 1.8.4 | 1.8.4 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
682 | 5516 | dd6fm1lW4tBXPtNV5RGW | Summary | 391 | 1.8.4.1 | 1.8.4.1 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
683 | 5517 | IHfroMkwx3TZoTXYbBOK | Normal | 40 | 1.8.4.1.1 | 1.8.4.1.1 |  | 2025-05-14 17:00 | q | -609 |  | 2023-09-13 16:06
684 | 5518 | V0a5XEJ0jxIkhnpEDg8e | Normal | 40 | 1.8.4.1.2 | 1.8.4.1.2 |  | 2025-05-14 17:00 | q | -579 |  | 2023-10-13 08:50
685 | 5519 | D5sl3M5NpO77EU7TPYT0 | Normal | 40 | 1.8.4.1.3 | 1.8.4.1.3 |  | 2025-05-14 17:00 | q | -594 |  | 2023-09-28 09:53
686 | 5523 | APkwTVep7mUhgmcCl4NB | Milestone | 0 | 1.8.4.1.4 | 1.8.4.1.4 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
687 | 5527 | Mw5Re8SivA42laH7UhJE | Milestone | 0 | 1.8.4.1.5 | 1.8.4.1.5 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
688 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 2026-10-05 12:00 | p | 927 |  | 2029-04-20 09:39
689 | 5331 | emM9tIPUc6I6BRQdDkUj | Summary | 325 | 1.9.3 | 1.9.3 |  | 2026-03-16 08:30 | q | -31 |  | 2026-02-12 16:16
690 | 5332 | Jas5wmBgln6JvMRLtRUk | Summary | 110 | 1.9.3.1 | 1.9.3.1 |  | 2026-03-16 08:30 | q | -31 |  | 2026-02-12 16:16
691 | 5333 | NEZJUiuEFBeqDBEbXbzQ | Milestone | 0 | 1.9.3.1.1 | 1.9.3.1.1 |  | 2025-10-07 08:30 | q | -32 |  | 2025-09-04 11:49
692 | 5334 | 5Bt8vyiG2PJ2FKCjQPP1 | Summary | 74 | 1.9.3.1.2 | 1.9.3.1.2 |  | 2026-01-23 08:30 | q | -27 |  | 2025-12-26 11:55
693 | 6471 | xmZvSzAhf2D9ir29atKO | Normal | 8 | 1.9.3.1.2.1 | 1.9.3.1.2.1 |  | 2025-10-20 08:30 | q | -33 |  | 2025-09-16 10:33
694 | 6472 | j0VQ7fJsNHb1HpOVRoJN | Normal | 7 | 1.9.3.1.2.2 | 1.9.3.1.2.2 |  | 2025-10-29 08:30 | q | -32 |  | 2025-09-26 09:27
695 | 6473 | FN1N5cBOnOQJN0lvtY6J | Normal | 5 | 1.9.3.1.2.3 | 1.9.3.1.2.3 |  | 2025-11-05 08:30 | q | -32 |  | 2025-10-03 14:29
696 | 6474 | k77H7bJ7aRKhBrZeZFzu | Normal | 10 | 1.9.3.1.2.4 | 1.9.3.1.2.4 |  | 2025-11-20 08:30 | q | -30 |  | 2025-10-20 14:59
697 | 6475 | TkBVMCiZTEhYxjcnMNRI | Normal | 8 | 1.9.3.1.2.5 | 1.9.3.1.2.5 |  | 2025-12-03 08:30 | q | -35 |  | 2025-10-28 16:00
698 | 6476 | HdsfOo0UbW7iVGjY7L1O | Normal | 10 | 1.9.3.1.2.6 | 1.9.3.1.2.6 |  | 2025-12-17 08:30 | q | -29 |  | 2025-11-17 14:43
699 | 6477 | m1G8PrmdvRxZwBbLlVUQ | Normal | 7 | 1.9.3.1.2.7 | 1.9.3.1.2.7 |  | 2025-12-29 08:30 | q | -32 |  | 2025-11-26 14:19
700 | 6478 | ZDDqpCGw2ELQiAxZVJFo | Normal | 7 | 1.9.3.1.2.8 | 1.9.3.1.2.8 |  | 2026-01-07 08:30 | q | -29 |  | 2025-12-08 08:48
701 | 6479 | i51TyrBkECB0t7wKJruE | Normal | 7 | 1.9.3.1.2.9 | 1.9.3.1.2.9 |  | 2026-01-16 08:30 | q | -28 |  | 2025-12-18 11:40
702 | 6480 | XeKgBzwPereNdZmXnTFt | Normal | 5 | 1.9.3.1.2.10 | 1.9.3.1.2.10 |  | 2026-01-23 08:30 | q | -27 |  | 2025-12-26 11:55
703 | 5335 | fBEkx0xCtVpw1OeE4jLB | Summary | 25 | 1.9.3.1.3 | 1.9.3.1.3 |  | 2026-02-27 08:30 | q | -29 |  | 2026-01-28 09:46
704 | 5336 | FIhKbBOHnlTp0loBBfvV | Normal | 3 | 1.9.3.1.3.1 | 1.9.3.1.3.1 |  | 2026-01-28 08:30 | q | -26 |  | 2026-01-01 08:58
705 | 5337 | TPAbtCx4KhMQiN0iVD1F | Normal | 0 | 1.9.3.1.3.2 | 1.9.3.1.3.2 |  | 2026-01-23 13:06 | q | -25 |  | 2025-12-29 08:14
706 | 5338 | NXWa8B3rzsUFws6lYttF | Normal | 5 | 1.9.3.1.3.3 | 1.9.3.1.3.3 |  | 2026-01-30 08:30 | q | -27 |  | 2026-01-02 14:46
707 | 5339 | o98eRuEZGwoxxa1Byl7H | Normal | 5 | 1.9.3.1.3.4 | 1.9.3.1.3.4 |  | 2026-01-30 08:30 | q | -27 |  | 2026-01-02 13:17
708 | 5340 | lQJTDBnvPE8mTPnPre3v | Normal | 10 | 1.9.3.1.3.5 | 1.9.3.1.3.5 |  | 2026-02-13 08:30 | q | -29 |  | 2026-01-14 10:30
709 | 5341 | nevxwfefPkBzu42CDbNd | Normal | 10 | 1.9.3.1.3.6 | 1.9.3.1.3.6 |  | 2026-02-27 08:30 | q | -29 |  | 2026-01-28 09:46
710 | 5342 | s0JiBiXDLP6oybWmkZ43 | Normal | 6 | 1.9.3.1.4 | 1.9.3.1.4 |  | 2026-03-09 08:30 | q | -31 |  | 2026-02-05 15:31
711 | 5343 | NROXqcLUoQ0RLz64rMVc | Normal | 5 | 1.9.3.1.5 | 1.9.3.1.5 |  | 2026-03-16 08:30 | q | -31 |  | 2026-02-12 16:16
712 | 5344 | Kw3Fj6kwk5uOl7tQyqrL | Milestone | 0 | 1.9.3.1.6 | 1.9.3.1.6 |  | 2026-03-16 08:30 | q | -31 |  | 2026-02-12 16:16
713 | 6275 | OL3lkJGtK3tkk0d4SBRn | Summary | 288 | 1.9.9 | 1.9.9 |  | 2026-10-05 12:00 | p | 927 |  | 2029-04-20 09:27
714 | 795 | 85yV4lhIxXIziyB5R2QA | Normal | 1 | 1.9.9.1 | 1.9.9.1 |  | 2026-09-17 12:00 | p | 929 |  | 2029-04-04 11:08
715 | 844 | 1qfp8o9PQxr9vZvO7S5k | Normal | 1 | 1.9.9.4 | 1.9.9.4 |  | 2026-10-05 12:00 | p | 927 |  | 2029-04-20 09:27
716 | 845 | U1v5hScHSOPPxa5ohjfI | Summary | 189 | 1.9.9.7 | 1.9.9.7 |  | 2025-12-31 17:00 | p | 27 |  | 2026-01-28 08:39
717 | 847 | JilJNxxBcx7QrT5PcKLM | Summary | 189 | 1.9.9.7.2 | 1.9.9.7.2 |  | 2025-12-31 17:00 | p | 27 |  | 2026-01-28 08:39
718 | 866 | 0rLFG0X22Uukcn0axQTO | Normal | 50 | 1.9.9.7.2.6 | 1.9.9.7.2.6 |  | 2025-06-25 17:00 | p | 26 |  | 2025-07-22 15:07
719 | 869 | 8QCM3LZ8SN5y0jCLtGNh | Summary | 129 | 1.9.9.7.2.7 | 1.9.9.7.2.7 |  | 2025-12-31 17:00 | p | 27 |  | 2026-01-28 08:39
720 | 6419 | NORPsF566zq8VZyN1UzF | Normal | 10 | 1.9.9.7.2.7.1 | 1.9.9.7.2.7.1 |  | 2025-07-10 17:00 | p | 26 |  | 2025-08-06 11:19
721 | 6420 | 043wOhyyEd8vJkuUBkFf | Normal | 40 | 1.9.9.7.2.7.2 | 1.9.9.7.2.7.2 |  | 2025-09-05 17:00 | p | 23 |  | 2025-09-29 08:24
722 | 6421 | JZROXyECnTBG3SBjYZJ8 | Normal | 79 | 1.9.9.7.2.7.3 | 1.9.9.7.2.7.3 |  | 2025-12-31 17:00 | p | 27 |  | 2026-01-28 08:39
723 | 6418 | W9pbV5i9WFkdVEGtW75H | Normal | 45 | 1.9.9.7.2.5 | 1.9.9.7.2.5 |  | 2025-04-14 17:00 | p | 23 |  | 2025-05-08 13:10
724 | 870 | m3oEXpasu7ssfpw9dqLv | Summary | 267 | 1.9.9.14 | 1.9.9.14 |  | 2026-05-22 12:00 | p | 934 |  | 2028-12-11 13:54
725 | 4667 | gXRr1908PexMoLIDosFv | Normal | 100 | 1.9.9.14.3 | 1.9.9.14.3 |  | 2025-11-21 17:00 | p | 53 |  | 2026-01-14 08:57
726 | 4668 | G3SLCzd88WLMRnAF5Et7 | Normal | 0 | 1.9.9.14.4 | 1.9.9.14.4 |  | 2026-04-20 12:00 | p | 935 |  | 2028-11-10 15:58
727 | 4669 | aeClBbTsJ3qrKHWqQ1Rw | Normal | 40 | 1.9.9.14.5 | 1.9.9.14.5 |  | 2026-01-22 17:00 | p | 42 |  | 2026-03-06 16:15
728 | 4679 | rpzkOhA603pApmNdMeVE | Normal | 0 | 1.9.9.14.6 | 1.9.9.14.6 |  | 2026-05-22 12:00 | p | 934 |  | 2028-12-11 13:54
729 | 5786 | d3N6cqydEgoPO1XBMSTu | Normal | 7 | 1.9.9.14.1 | 1.9.9.14.1 |  | 2025-02-19 17:00 | p | 28 |  | 2025-03-20 08:03
730 | 5787 | r6JEZEKCpBbNZRe1W7Ef | Normal | 91 | 1.9.9.14.2 | 1.9.9.14.2 |  | 2025-06-30 17:00 | p | 58 |  | 2025-08-28 14:51
731 | 899 | w1GWQdUx9oG06oopRYZx | Summary | 24 | 1.9.9.15 | 1.9.9.15 |  | 2026-05-21 17:00 | p | 935 |  | 2028-12-12 15:12
732 | 900 | ANUK0HdVlI2Jd5hSzs0f | Milestone | 0 | 1.9.9.15.1 | 1.9.9.15.1 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
733 | 901 | HcFqHITfVdYMyzVb3S8v | Normal | 18 | 1.9.9.15.2 | 1.9.9.15.2 |  | 2026-05-13 17:00 | p | 939 |  | 2028-12-08 16:02
734 | 902 | nIjAIVHCOoi1ijXym0cI | Normal | 3 | 1.9.9.15.3 | 1.9.9.15.3 |  | 2026-04-22 17:00 | p | 937 |  | 2028-11-15 11:13
735 | 903 | UDGopgZ2sb1QsQEooZ9G | Normal | 8 | 1.9.9.15.4 | 1.9.9.15.4 |  | 2026-05-04 17:00 | p | 934 |  | 2028-11-24 11:14
736 | 904 | 4CH3NSJx1luiHbrrAEJg | Normal | 2 | 1.9.9.15.5 | 1.9.9.15.5 |  | 2026-05-15 17:00 | p | 941 |  | 2028-12-12 15:12
737 | 905 | MxRWNVEH6ZVBPqNnA2hI | Normal | 8 | 1.9.9.15.6 | 1.9.9.15.6 |  | 2026-05-14 17:00 | p | 934 |  | 2028-12-04 09:48
738 | 906 | PL0zn2U2NPPXQqakkHLb | Normal | 5 | 1.9.9.15.7 | 1.9.9.15.7 |  | 2026-05-21 17:00 | p | 931 |  | 2028-12-08 16:08
739 | 907 | 5mTVpVcHzmsYLVY8xpKs | Normal | 5 | 1.9.9.15.8 | 1.9.9.15.8 |  | 2026-05-21 17:00 | p | 934 |  | 2028-12-11 08:48
740 | 914 | q0UeyWaeMXFoeUDjjzhX | Summary | 18 | 1.9.9.5 | 1.9.9.5 |  | 2025-09-05 17:00 | p | 941 |  | 2028-04-04 14:54
741 | 915 | jxzEE3EBeGWt1nE3uHcj | Summary | 18 | 1.9.9.5.1 | 1.9.9.5.1 |  | 2025-09-05 17:00 | p | 941 |  | 2028-04-04 14:54
742 | 916 | d4bxhxtQW3GaLrDrUlf9 | Normal | 17 | 1.9.9.5.1.1 | 1.9.9.5.1.1 |  | 2025-09-04 17:00 | p | 941 |  | 2028-04-03 11:32
743 | 917 | mbDdHZHm9OoYye329Ue6 | Normal | 1 | 1.9.9.5.1.2 | 1.9.9.5.1.2 |  | 2025-09-05 17:00 | p | 941 |  | 2028-04-04 14:54
744 | 4538 | aTyUglf0WPX6H8Zd17Iq | Summary | 71 | 1.9.9.16 | 1.9.9.16 |  | 2026-07-31 12:00 | p | 929 |  | 2029-02-14 13:47
745 | 6509 | sp3XFaPtGgzrVeC1wvvV | Normal | 10 | 1.9.9.16.3 | 1.9.9.16.3 |  | 2026-06-09 12:00 | p | 926 |  | 2028-12-22 10:04
746 | 6510 | dar9hgzhSUYJxC1MeoTS | Normal | 10 | 1.9.9.16.4 | 1.9.9.16.4 |  | 2026-06-09 12:00 | p | 933 |  | 2028-12-28 15:13
747 | 6513 | IG8fHoH3vjERJ6iSB3Rj | Normal | 36 | 1.9.9.16.5 | 1.9.9.16.5 |  | 2026-07-31 12:00 | p | 929 |  | 2029-02-14 13:47
748 | 6514 | imV319lPgBwI8oLVT5sB | Normal | 1 | 1.9.9.16.2 | 1.9.9.16.2 |  | 2026-05-26 12:00 | p | 931 |  | 2028-12-12 13:13
749 | 6515 | a8Kdm3F6uLeIN4SEhwX9 | Normal | 1 | 1.9.9.16.1 | 1.9.9.16.1 |  | 2026-04-21 12:00 | p | 937 |  | 2028-11-13 14:53
750 | 5783 | BOvEGIzyTacp1vvD9v7M | Normal | 1 | 1.9.9.2 | 1.9.9.2 |  | 2026-01-02 17:00 | p | 26 |  | 2026-01-29 08:16
751 | 6128 | 7jXaekqqhUCDWSDfnxzo | Summary | 28 | 1.7.4.2 | 1.7.4.2 |  | 2025-03-10 17:00 | p | 0 |  | 2025-03-11 10:42
752 | 6130 | 3AAePL8Vt5bI7qDxsaDX | Normal | 20 | 1.7.4.2.3 | 1.7.4.2.3 |  | 2025-03-10 17:00 | p | 0 |  | 2025-03-11 10:42
753 | 6685 | 2nkdQcaVv7LgM8d4dFld | Summary | 1 | 1.9.9.12 | 1.9.9.12 |  | 2025-08-29 17:00 | q | -164 |  | 2025-03-18 10:12
754 | 6687 | RiyOBd4mBIE5Cq6C0A4h | Normal | 1 | 1.9.9.12.1 | 1.9.9.12.1 |  | 2025-08-29 17:00 | q | -164 |  | 2025-03-18 10:12
755 | 6686 | IDiuvzfQRXyu7MCMX1jW | Normal | 5 | 1.9.9.11 | 1.9.9.11 |  | 2025-02-14 17:00 | p | 30 |  | 2025-03-17 11:08
756 | 7388 | subTjNOw9tjXphx2xXzW | Summary | 324 | 1.9.9.13 | 1.9.9.13 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
757 | 7389 | xTfJP5JFEqXIDmLDdKVZ | Summary | 43 | 1.9.9.13.1 | 1.9.9.13.1 |  | 2025-08-19 17:00 | p | 943 |  | 2028-03-20 09:05
758 | 7390 | GV26YG775A5KHHrrMIRV | Summary | 32 | 1.9.9.13.1.1 | 1.9.9.13.1.1 |  | 2025-08-05 12:00 | p | 940 |  | 2028-03-03 08:58
759 | 7391 | UumEMUqxjwvZXtHBx1rg | Normal | 3 | 1.9.9.13.1.1.1 | 1.9.9.13.1.1.1 |  | 2025-06-23 17:00 | p | 933 |  | 2028-01-13 08:07
760 | 7392 | ylVP19AJuwY485wgDJEG | Normal | 10 | 1.9.9.13.1.1.2 | 1.9.9.13.1.1.2 |  | 2025-07-08 12:00 | p | 931 |  | 2028-01-25 14:39
761 | 7393 | RzIyrLZKRoqlWdOJYpGf | Normal | 3 | 1.9.9.13.1.1.3 | 1.9.9.13.1.1.3 |  | 2025-07-08 17:00 | p | 932 |  | 2028-01-27 11:46
762 | 7394 | zHoRZ9fggWfe9FGnA954 | Normal | 10 | 1.9.9.13.1.1.4 | 1.9.9.13.1.1.4 |  | 2025-07-22 12:00 | p | 939 |  | 2028-02-16 15:40
763 | 7395 | PMjQe1vYJ6mxUbNABucF | Normal | 3 | 1.9.9.13.1.1.5 | 1.9.9.13.1.1.5 |  | 2025-07-22 17:00 | p | 932 |  | 2028-02-10 13:38
764 | 7396 | gQKdIVV4LZyvHUAfFFFg | Normal | 10 | 1.9.9.13.1.1.6 | 1.9.9.13.1.1.6 |  | 2025-08-05 12:00 | p | 940 |  | 2028-03-03 08:58
765 | 7397 | gmOEJCOmO6SQ6HMlGXfq | Summary | 12 | 1.9.9.13.1.2 | 1.9.9.13.1.2 |  | 2025-08-19 17:00 | p | 943 |  | 2028-03-20 09:05
766 | 7398 | ItOQSxoXEYWD5clVNK0n | Normal | 3 | 1.9.9.13.1.2.1 | 1.9.9.13.1.2.1 |  | 2025-08-06 17:00 | p | 931 |  | 2028-02-24 11:48
767 | 7399 | cXpFrNuZR7O8wPV6KZK3 | Normal | 9 | 1.9.9.13.1.2.2 | 1.9.9.13.1.2.2 |  | 2025-08-19 17:00 | p | 943 |  | 2028-03-20 09:05
768 | 7400 | VGtguPWpaIPmF0Ojsz8a | Summary | 176 | 1.9.9.13.2 | 1.9.9.13.2 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
769 | 7401 | H3MyBOTVJ4MGxcXcavMD | Normal | 2 | 1.9.9.13.2.1 | 1.9.9.13.2.1 |  | 2025-08-06 17:00 | p | 942 |  | 2028-03-06 15:47
770 | 7402 | pMiEhGou1QDK96DPu7Q8 | Normal | 1 | 1.9.9.13.2.2 | 1.9.9.13.2.2 |  | 2025-08-20 17:00 | p | 943 |  | 2028-03-21 09:16
771 | 7403 | pHZBXvaYVwug2p7gN6jp | Summary | 17 | 1.9.9.13.2.3 | 1.9.9.13.2.3 |  | 2025-09-15 17:00 | p | 939 |  | 2028-04-12 13:04
772 | 7404 | EvHLT3cR3tYYGwcq6SC1 | Normal | 5 | 1.9.9.13.2.3.1 | 1.9.9.13.2.3.1 |  | 2025-08-27 17:00 | p | 943 |  | 2028-03-28 09:50
773 | 7405 | 5GpI6xkgfIoVOnU9egD8 | Normal | 12 | 1.9.9.13.2.3.2 | 1.9.9.13.2.3.2 |  | 2025-09-15 17:00 | p | 939 |  | 2028-04-12 13:04
774 | 7406 | WxzG2sAIbVYYiem4v3mk | Normal | 12 | 1.9.9.13.2.3.3 | 1.9.9.13.2.3.3 |  | 2025-09-15 17:00 | p | 938 |  | 2028-04-11 14:45
775 | 7407 | 0eiyRK1I5mgUCdtpXpqY | Summary | 44 | 1.9.9.13.2.4 | 1.9.9.13.2.4 |  | 2025-11-18 17:00 | p | 937 |  | 2028-06-13 08:48
776 | 7408 | uKngouP2QMMQmu6HFm0I | Normal | 11 | 1.9.9.13.2.4.1 | 1.9.9.13.2.4.1 |  | 2025-09-30 17:00 | p | 938 |  | 2028-04-26 11:31
777 | 7409 | C7eZzAQkBbKewE4wmmOD | Normal | 11 | 1.9.9.13.2.4.2 | 1.9.9.13.2.4.2 |  | 2025-10-16 17:00 | p | 936 |  | 2028-05-10 14:48
778 | 7410 | VCdEPtbQjRcgNUnNprkZ | Normal | 11 | 1.9.9.13.2.4.3 | 1.9.9.13.2.4.3 |  | 2025-10-31 17:00 | p | 936 |  | 2028-05-25 13:17
779 | 7411 | OzHccTXr25Mf4pmiIMuT | Normal | 11 | 1.9.9.13.2.4.4 | 1.9.9.13.2.4.4 |  | 2025-11-18 17:00 | p | 937 |  | 2028-06-13 08:48
780 | 7412 | obz02flxb00pYjKUpMNx | Normal | 12 | 1.9.9.13.2.5 | 1.9.9.13.2.5 |  | 2025-12-12 17:00 | p | 930 |  | 2028-06-30 09:58
781 | 7413 | xazO1XwNp5eROWJmaREL | Summary | 36 | 1.9.9.13.2.6 | 1.9.9.13.2.6 |  | 2026-01-12 17:00 | p | 938 |  | 2028-08-08 14:51
782 | 7414 | DrM34eAIT9imz4vRHbHm | Normal | 2 | 1.9.9.13.2.6.1 | 1.9.9.13.2.6.1 |  | 2025-11-20 17:00 | p | 937 |  | 2028-06-15 09:53
783 | 7415 | RsULMViXRZoYahxlMUQ4 | Normal | 20 | 1.9.9.13.2.6.2 | 1.9.9.13.2.6.2 |  | 2025-12-19 17:00 | p | 942 |  | 2028-07-19 11:22
784 | 7416 | U8irVJqpjJwQWU5FcpMo | Normal | 3 | 1.9.9.13.2.6.3 | 1.9.9.13.2.6.3 |  | 2025-12-24 17:00 | p | 942 |  | 2028-07-24 15:52
785 | 7417 | yrCdbpyUp4mqkbXiv5Nc | Normal | 6 | 1.9.9.13.2.6.4 | 1.9.9.13.2.6.4 |  | 2026-01-05 17:00 | p | 938 |  | 2028-08-01 09:30
786 | 7418 | Iw5sTi596kP8d52cBWYm | Normal | 5 | 1.9.9.13.2.6.5 | 1.9.9.13.2.6.5 |  | 2026-01-12 17:00 | p | 938 |  | 2028-08-08 14:51
787 | 7419 | s9reBpLseCBnslseiKA6 | Normal | 2 | 1.9.9.13.2.7 | 1.9.9.13.2.7 |  | 2026-01-14 17:00 | p | 939 |  | 2028-08-11 09:38
788 | 7420 | ia01m1zWF4qAvVLVg5It | Summary | 54 | 1.9.9.13.2.8 | 1.9.9.13.2.8 |  | 2026-04-02 17:00 | p | 935 |  | 2028-10-24 13:16
789 | 7421 | 5PvQN5TGe8y7KbK2rRhO | Normal | 8 | 1.9.9.13.2.8.1 | 1.9.9.13.2.8.1 |  | 2026-01-27 17:00 | p | 938 |  | 2028-08-23 13:49
790 | 7422 | fj19MvsSAfWHeVGXiA1H | Normal | 5 | 1.9.9.13.2.8.2 | 1.9.9.13.2.8.2 |  | 2026-01-22 17:00 | p | 937 |  | 2028-08-17 15:34
791 | 7423 | hs9Gt4WgG9pENnEIaC7X | Normal | 14 | 1.9.9.13.2.8.3 | 1.9.9.13.2.8.3 |  | 2026-02-17 17:00 | p | 938 |  | 2028-09-13 10:12
792 | 7424 | WqCakGr8mHgCENNWHHjW | Normal | 5 | 1.9.9.13.2.8.4 | 1.9.9.13.2.8.4 |  | 2026-02-03 17:00 | p | 939 |  | 2028-08-31 09:22
793 | 7425 | Pv27HXd826jlfuUJmTLH | Normal | 20 | 1.9.9.13.2.8.5 | 1.9.9.13.2.8.5 |  | 2026-03-17 17:00 | p | 936 |  | 2028-10-09 10:02
794 | 7426 | UjcYgNHyPV73fWy2GGNA | Normal | 5 | 1.9.9.13.2.8.6 | 1.9.9.13.2.8.6 |  | 2026-02-24 17:00 | p | 939 |  | 2028-09-21 09:53
795 | 7427 | 5QMAV8W19uO0knxuRgYc | Normal | 6 | 1.9.9.13.2.8.7 | 1.9.9.13.2.8.7 |  | 2026-03-25 17:00 | p | 936 |  | 2028-10-16 17:00
796 | 7428 | C3roUkJ3GEdxAvfnxnUE | Normal | 6 | 1.9.9.13.2.8.8 | 1.9.9.13.2.8.8 |  | 2026-03-25 17:00 | p | 937 |  | 2028-10-18 08:20
797 | 7429 | GMfJSktlv5oUXA5LFNgA | Normal | 6 | 1.9.9.13.2.8.9 | 1.9.9.13.2.8.9 |  | 2026-04-02 17:00 | p | 935 |  | 2028-10-24 13:16
798 | 7430 | AjX0fOJfuCWTWcoFWrZe | Summary | 11 | 1.9.9.13.2.9 | 1.9.9.13.2.9 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
799 | 7431 | YKkcKAxBNBkRs3Gs0cxp | Normal | 7 | 1.9.9.13.2.9.1 | 1.9.9.13.2.9.1 |  | 2026-04-13 17:00 | p | 933 |  | 2028-11-02 14:33
800 | 7432 | HbmHLQTrqR87hE03VIdq | Normal | 3 | 1.9.9.13.2.9.2 | 1.9.9.13.2.9.2 |  | 2026-04-07 17:00 | p | 933 |  | 2028-10-27 11:33
801 | 7433 | FxBsJSw4ZNEIyIQA8bL9 | Normal | 8 | 1.9.9.13.2.9.3 | 1.9.9.13.2.9.3 |  | 2026-04-17 17:00 | p | 937 |  | 2028-11-10 11:17
802 | 7434 | MkjgnYEnwrIrITdXMEl9 | Milestone | 0 | 1.9.9.13.3 | 1.9.9.13.3 |  | 2026-07-31 12:00 | p | 929 |  | 2029-02-14 13:47
803 | 7435 | nSo6tYchIu2Aw4YtE45u | Summary | 44 | 1.9.9.13.4 | 1.9.9.13.4 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
804 | 7436 | Y83lvWkQwfsc3dMGwfVN | Summary | 30 | 1.9.9.13.4.1 | 1.9.9.13.4.1 |  | 2026-09-14 12:00 | p | 928 |  | 2029-03-30 14:22
805 | 7437 | E8EwVgjFQaEPGP66WsCb | Summary | 30 | 1.9.9.13.4.1.1 | 1.9.9.13.4.1.1 |  | 2026-09-14 12:00 | p | 919 |  | 2029-03-21 15:23
806 | 7438 | y2P0mgWq1uFkM4aVxtQJ | Normal | 15 | 1.9.9.13.4.1.1.1 | 1.9.9.13.4.1.1.1 |  | 2026-08-21 12:00 | p | 926 |  | 2029-03-05 08:26
807 | 7439 | nsJKxwZOWJc3LdYsNOwr | Normal | 5 | 1.9.9.13.4.1.1.2 | 1.9.9.13.4.1.1.2 |  | 2026-08-28 12:00 | p | 924 |  | 2029-03-09 14:27
808 | 7440 | 3ZzL4TktDwncii0hY2dA | Normal | 10 | 1.9.9.13.4.1.1.3 | 1.9.9.13.4.1.1.3 |  | 2026-09-14 12:00 | p | 919 |  | 2029-03-21 15:23
809 | 7441 | IcgrxiRjEYJLwuugm8N7 | Summary | 30 | 1.9.9.13.4.1.2 | 1.9.9.13.4.1.2 |  | 2026-09-14 12:00 | p | 928 |  | 2029-03-30 14:22
810 | 7442 | B8zfbswYxyRxHa21jaE6 | Normal | 15 | 1.9.9.13.4.1.2.1 | 1.9.9.13.4.1.2.1 |  | 2026-08-21 12:00 | p | 929 |  | 2029-03-08 09:14
811 | 7443 | lvFKaF8Jtq8DkkB0s9nv | Normal | 15 | 1.9.9.13.4.1.2.2 | 1.9.9.13.4.1.2.2 |  | 2026-09-14 12:00 | p | 928 |  | 2029-03-30 14:22
812 | 7444 | 419IszMaZW6XNIQptprk | Normal | 20 | 1.9.9.13.4.1.3 | 1.9.9.13.4.1.3 |  | 2026-08-28 12:00 | p | 936 |  | 2029-03-21 15:57
813 | 7445 | oNfFp4VAwKEpoSujTbHZ | Normal | 10 | 1.9.9.13.4.1.4 | 1.9.9.13.4.1.4 |  | 2026-08-14 12:00 | p | 931 |  | 2029-03-02 13:35
814 | 7446 | NnBZUSVumxDXwVdCLN8g | Summary | 12 | 1.9.9.13.4.2 | 1.9.9.13.4.2 |  | 2026-09-30 12:00 | p | 930 |  | 2029-04-17 15:30
815 | 7447 | CAsJ3atkVCS14hehUB9Y | Normal | 4 | 1.9.9.13.4.2.1 | 1.9.9.13.4.2.1 |  | 2026-09-18 12:00 | p | 930 |  | 2029-04-05 15:42
816 | 7448 | 8tMCh2h8AwE53TPPkfEv | Normal | 3 | 1.9.9.13.4.2.2 | 1.9.9.13.4.2.2 |  | 2026-09-21 12:00 | p | 928 |  | 2029-04-06 13:07
817 | 7449 | LaZxXVdUnGzqswRGUiV5 | Normal | 7 | 1.9.9.13.4.2.3 | 1.9.9.13.4.2.3 |  | 2026-09-30 12:00 | p | 930 |  | 2029-04-17 15:30
818 | 7450 | F3vtt1T8lz7mQWFPgUKT | Normal | 2 | 1.9.9.13.4.3 | 1.9.9.13.4.3 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
819 | 7451 | nShmtMdGhMi3SzNeAZjW | Milestone | 0 | 1.9.9.13.4.4 | 1.9.9.13.4.4 |  | 2026-10-02 12:00 | p | 929 |  | 2029-04-19 10:06
820 | 7510 | 4i5VLTIa98HteWhFzYjv | Normal | 3 | 1.7.10.24 | 1.7.10.24 |  | 2025-06-17 17:00 | p | 933 |  | 2028-01-07 16:28
821 | 7511 | tHPdmsBqm9kHM69dtq3h | Normal | 7 | 1.7.10.25 | 1.7.10.25 |  | 2025-07-02 17:00 | p | 935 |  | 2028-01-24 08:24
822 | 7512 | hmOTDv9qQbSDcHudIm9x | Normal | 7 | 1.7.10.26 | 1.7.10.26 |  | 2025-07-17 17:00 | p | 934 |  | 2028-02-07 14:23
823 | 7513 | NbiRgc4Tdvxa900kw7Xq | Normal | 8 | 1.7.10.27 | 1.7.10.27 |  | 2025-08-01 17:00 | p | 933 |  | 2028-02-21 11:14
824 | 7539 | ROucR7pug9aGzObG8pvW | Normal | 1 | 1.7.10.8 | 1.7.10.8 |  | 2025-02-28 17:00 | q | -570 |  | 2023-08-08 08:37
825 | 7540 | njszlznNRnCyRW2hgoMI | Normal | 10 | 1.7.10.9 | 1.7.10.9 |  | 2025-03-14 17:00 | q | -570 |  | 2023-08-22 10:22
826 | 7541 | R63tw5xkvmDGiWpIPQRa | Normal | 1 | 1.7.10.10 | 1.7.10.10 |  | 2025-03-31 17:00 | q | -601 |  | 2023-08-08 08:07
827 | 7542 | E3YdLEfamF0eZCISJiqw | Normal | 10 | 1.7.10.11 | 1.7.10.11 |  | 2025-04-25 17:00 | q | -616 |  | 2023-08-18 11:21
828 | 7543 | nhpJxewK7uClQLzGXJQJ | Normal | 1 | 1.7.10.12 | 1.7.10.12 |  | 2025-05-30 17:00 | q | -661 |  | 2023-08-08 10:06
829 | 7544 | cfuUTFyz3WOPAOOiNQOb | Normal | 1 | 1.7.10.13 | 1.7.10.13 |  | 2025-05-30 17:00 | q | -662 |  | 2023-08-07 15:37
830 | 6279 | p7EJXT1muDSglD2OZLFH | Summary | 274 | 1.9.7 | 1.9.7 |  | 2026-09-16 12:00 | p | 929 |  | 2029-04-03 11:47
831 | 1484 | 6ARiGRg3KLswRpJLOmGD | Summary | 229 | 1.9.7.18 | 1.9.7.18 |  | 2025-11-04 17:00 | q | -222 |  | 2025-03-27 10:18
832 | 1485 | R0QJsNVi0JzXq4FadBdS | Normal | 20 | 1.9.7.18.4 | 1.9.7.18.4 |  | 2025-07-17 17:00 | q | -2820 |  | 2017-10-27 15:51
833 | 1486 | 9VYbXOz4xuMas0igEBkB | Summary | 56 | 1.9.7.18.6 | 1.9.7.18.6 |  | 2025-11-04 17:00 | q | -2812 |  | 2018-02-22 16:01
834 | 6540 | BF294XdCZHw2CEg81bOs | Normal | 19 | 1.9.7.18.6.1 | 1.9.7.18.6.1 |  | 2025-09-11 17:00 | q | -2814 |  | 2017-12-28 16:20
835 | 6541 | X8phwYugZBkIbn0OysQW | Normal | 19 | 1.9.7.18.6.2 | 1.9.7.18.6.2 |  | 2025-10-08 17:00 | q | -2809 |  | 2018-01-29 14:01
836 | 6542 | fphO3nZhiS43G9CLfKfB | Normal | 18 | 1.9.7.18.6.3 | 1.9.7.18.6.3 |  | 2025-11-04 17:00 | q | -2812 |  | 2018-02-22 16:01
837 | 1489 | pYq4lU1lCt1U75q3gu6M | Normal | 11 | 1.9.7.18.1 | 1.9.7.18.1 |  | 2025-02-26 17:00 | p | 28 |  | 2025-03-27 10:18
838 | 1490 | hF9FI1LNvFfgTTXhqPsR | Normal | 77 | 1.9.7.18.2 | 1.9.7.18.2 |  | 2025-06-16 17:00 | q | -2820 |  | 2017-09-26 16:07
839 | 1491 | XpTPefWn9TT3C06gw8rA | Normal | 1 | 1.9.7.18.3 | 1.9.7.18.3 |  | 2025-06-17 17:00 | q | -2819 |  | 2017-09-28 08:18
840 | 1495 | 0kid3Dd3U5gCQNrt2pwY | Normal | 1 | 1.9.7.18.8 | 1.9.7.18.8 |  | 2025-02-26 17:00 | q | -22 |  | 2025-02-04 08:47
841 | 1504 | ndaml8HRsqEWzWIKrI7h | Normal | 5 | 1.9.7.18.10 | 1.9.7.18.10 |  | 2025-03-04 17:00 | q | -22 |  | 2025-02-10 11:29
842 | 4587 | 5uS9ktvplxYkrLheR3Q9 | Normal | 20 | 1.9.7.18.5 | 1.9.7.18.5 |  | 2025-08-14 17:00 | q | -2810 |  | 2017-12-04 08:30
843 | 1496 | 5t2MhilpkZRDQA3VTcGS | Normal | 48 | 1.9.7.7 | 1.9.7.7 |  | 2025-05-05 17:00 | q | -20 |  | 2025-04-15 16:33
844 | 1505 | 4c3z8pWafVxAWNC1MpC9 | Normal | 106 | 1.9.7.8 | 1.9.7.8 |  | 2025-08-04 17:00 | q | -27 |  | 2025-07-08 16:49
845 | 1508 | SDZ1pqYbdynEzXZrWujj | Normal | 30 | 1.9.7.6 | 1.9.7.6 |  | 2025-03-24 17:00 | p | 23 |  | 2025-04-17 10:54
846 | 1529 | WOa3B8SPUOSM5ThLE2Jo | Summary | 69 | 1.9.7.14 | 1.9.7.14 |  | 2025-07-16 17:00 | p | 13 |  | 2025-07-30 16:47
847 | 1531 | KX1eD2ASIZaZBZuqoVp4 | Normal | 1 | 1.9.7.14.2 | 1.9.7.14.2 |  | 2025-05-01 17:00 | q | -191 |  | 2024-10-22 08:07
848 | 1532 | fQ3wcWF8uEWMRGpUCxEA | Normal | 1 | 1.9.7.14.4 | 1.9.7.14.4 |  | 2025-05-07 17:00 | q | -16 |  | 2025-04-21 15:17
849 | 1533 | juvdtwZkjArAkPOzLrhN | Normal | 15 | 1.9.7.14.5 | 1.9.7.14.5 |  | 2025-07-01 17:00 | p | 14 |  | 2025-07-16 10:48
850 | 1534 | SuchbNnj1ndABAEPQlrb | Normal | 10 | 1.9.7.14.6 | 1.9.7.14.6 |  | 2025-07-16 17:00 | p | 13 |  | 2025-07-30 16:47
851 | 4583 | QzcCl72pVAI4zSVR8VAE | Normal | 1 | 1.9.7.14.3 | 1.9.7.14.3 |  | 2025-05-02 17:00 | q | -192 |  | 2024-10-22 14:57
852 | 1535 | vIOpwJGhGrQ4pKl5nahR | Summary | 61 | 1.9.7.15 | 1.9.7.15 |  | 2025-05-16 17:00 | p | 34 |  | 2025-06-20 10:23
853 | 1537 | HoYmSEeaxBfAYgcISNXh | Normal | 5 | 1.9.7.15.2 | 1.9.7.15.2 |  | 2025-02-14 17:00 | p | 30 |  | 2025-03-17 16:37
854 | 1538 | 1Xm6i4dPIyAKJzF1jRtD | Normal | 45 | 1.9.7.15.3 | 1.9.7.15.3 |  | 2025-04-21 17:00 | p | 29 |  | 2025-05-21 11:41
855 | 1541 | ss8yD9dhZfTIp9UxqHnG | Normal | 1 | 1.9.7.15.7 | 1.9.7.15.7 |  | 2025-04-22 17:00 | p | 29 |  | 2025-05-22 10:13
856 | 1542 | VmFPpoMfVfLEXeRBF7Um | Normal | 9 | 1.9.7.15.8 | 1.9.7.15.8 |  | 2025-05-05 17:00 | p | 29 |  | 2025-06-04 09:43
857 | 1543 | P2oxmSB7jXG6Ib9VEZ89 | Normal | 9 | 1.9.7.15.9 | 1.9.7.15.9 |  | 2025-05-16 17:00 | p | 34 |  | 2025-06-20 10:23
858 | 4585 | Z4QB23UBk58Dyd3318zD | Normal | 10 | 1.9.7.15.6 | 1.9.7.15.6 |  | 2025-02-27 17:00 | q | -2 |  | 2025-02-25 10:58
859 | 1544 | dYtuUpkdltDWUtvWJGdC | Summary | 80 | 1.9.7.16 | 1.9.7.16 |  | 2025-04-01 17:00 | q | -6 |  | 2025-03-26 11:36
860 | 1547 | K0gsOWDMqaySswr72BAQ | Normal | 1 | 1.9.7.16.3 | 1.9.7.16.3 |  | 2025-02-21 17:00 | q | -360 |  | 2024-02-27 08:41
861 | 1548 | 4jCrHn72KCapTPEI9TzQ | Normal | 2 | 1.9.7.16.5 | 1.9.7.16.5 |  | 2025-02-26 17:00 | q | -362 |  | 2024-03-01 08:50
862 | 1549 | s8gTUDwRZFDpCO4enZqk | Normal | 15 | 1.9.7.16.6 | 1.9.7.16.6 |  | 2025-03-19 17:00 | q | -5 |  | 2025-03-14 09:48
863 | 1550 | UoQFPyMNVa9QPyq2kgrl | Normal | 9 | 1.9.7.16.7 | 1.9.7.16.7 |  | 2025-04-01 17:00 | q | -6 |  | 2025-03-26 11:36
864 | 4586 | kRWFuIGKur6ToFmAr9JC | Normal | 1 | 1.9.7.16.4 | 1.9.7.16.4 |  | 2025-02-24 17:00 | q | -362 |  | 2024-02-28 08:10
865 | 1551 | FTwSjNJQyZH6RsSSqWG9 | Summary | 78 | 1.9.7.19 | 1.9.7.19 |  | 2025-05-19 17:00 | p | 1 |  | 2025-05-21 11:08
866 | 1561 | 8BMHpFsmSFY1BvBQKfdD | Normal | 10 | 1.9.7.19.11 | 1.9.7.19.11 |  | 2025-02-25 17:00 | p | 1 |  | 2025-02-27 13:07
867 | 1562 | lBuCdKTmKHrCdvS4FVbB | Normal | 40 | 1.9.7.19.12 | 1.9.7.19.12 |  | 2025-04-22 17:00 | p | 1 |  | 2025-04-24 15:44
868 | 1563 | TUxQ6kz9ittb2zcmlLCL | Normal | 10 | 1.9.7.19.13 | 1.9.7.19.13 |  | 2025-05-06 17:00 | p | 1 |  | 2025-05-08 11:23
869 | 1564 | OkMyUpJo7fqJaif9Jvyb | Normal | 5 | 1.9.7.19.14 | 1.9.7.19.14 |  | 2025-05-13 17:00 | p | 1 |  | 2025-05-15 09:42
870 | 1565 | 9BGxipQLCi4kED7E7faW | Normal | 4 | 1.9.7.19.15 | 1.9.7.19.15 |  | 2025-05-19 17:00 | p | 1 |  | 2025-05-21 11:08
871 | 4571 | grLKm3VpZ98OhRQH2gBq | Normal | 29 | 1.9.7.1 | 1.9.7.1 |  | 2025-03-21 17:00 | p | 27 |  | 2025-04-18 16:03
872 | 4572 | 5hxJeLGqqaIlIue4XwRC | Normal | 1 | 1.9.7.2 | 1.9.7.2 |  | 2025-03-21 17:00 | p | 27 |  | 2025-04-18 16:03
873 | 4574 | z7UYZlhr663oN8lfFWmH | Summary | 29 | 1.9.7.11 | 1.9.7.11 |  | 2025-08-05 17:00 | q | -26 |  | 2025-07-10 10:52
874 | 1497 | q56IdotBOPeXlK3605d6 | Normal | 1 | 1.9.7.11.4 | 1.9.7.11.4 |  | 2025-05-06 17:00 | q | -20 |  | 2025-04-16 16:26
875 | 1506 | zNKWNUMZ7wFR6LBQ8bZ2 | Normal | 1 | 1.9.7.11.5 | 1.9.7.11.5 |  | 2025-08-05 17:00 | q | -26 |  | 2025-07-10 10:52
876 | 1509 | xdWSZU8MxGE52WBHNu6X | Normal | 1 | 1.9.7.11.3 | 1.9.7.11.3 |  | 2025-03-25 17:00 | p | 23 |  | 2025-04-18 13:26
877 | 6440 | u5F2XJPKXxmZ5m99Yx5A | Normal | 1 | 1.9.7.11.7 | 1.9.7.11.7 |  | 2025-04-30 17:00 | q | -5 |  | 2025-04-25 13:35
878 | 4575 | nPe6rBdPLk408ntp39jn | Normal | 1 | 1.9.7.3 | 1.9.7.3 |  | 2025-06-06 17:00 | q | -669 |  | 2023-08-07 16:47
879 | 4578 | kBeLaux8MTugqoi5KPvZ | Summary | 74 | 1.9.7.13 | 1.9.7.13 |  | 2025-07-17 17:00 | p | 13 |  | 2025-07-31 15:37
880 | 1462 | 2Cc6AJ3gtv1XGHwG4F9W | Normal | 1 | 1.9.7.13.3 | 1.9.7.13.3 |  | 2025-04-07 17:00 | p | 27 |  | 2025-05-05 10:48
881 | 1518 | qXbL36bdYftxHm1TCntK | Normal | 1 | 1.9.7.13.4 | 1.9.7.13.4 |  | 2025-07-17 17:00 | p | 13 |  | 2025-07-31 15:37
882 | 4579 | xoTCeJS6YwjvMvm1YAvH | Normal | 1 | 1.9.7.13.2 | 1.9.7.13.2 |  | 2025-05-19 17:00 | p | 34 |  | 2025-06-23 10:29
883 | 4580 | llDwDvQQbSyeeXMs3M2a | Normal | 1 | 1.9.7.13.1 | 1.9.7.13.1 |  | 2025-04-02 17:00 | q | -6 |  | 2025-03-27 13:16
884 | 4581 | FxGRGf2kppDMdfFrZkS4 | Normal | 36 | 1.9.7.12 | 1.9.7.12 |  | 2025-04-01 17:00 | p | 16 |  | 2025-04-18 13:39
885 | 4588 | L1kgBhMEjlIJ4HNHh1TQ | Summary | 141 | 1.9.7.20 | 1.9.7.20 |  | 2025-12-11 17:00 | q | -1 |  | 2025-12-10 09:09
886 | 1566 | KFj0hxHWvExDoqTqgDeg | Normal | 118 | 1.9.7.20.1 | 1.9.7.20.1 |  | 2025-11-06 17:00 | q | 0 |  | 2025-11-06 08:08
887 | 1567 | GV5or0ucuouXZiqAkH0N | Normal | 10 | 1.9.7.20.2 | 1.9.7.20.2 |  | 2025-11-21 17:00 | p | 2 |  | 2025-11-24 13:31
888 | 1568 | JI4xSRBKV4FYnRXdw7Wz | Normal | 9 | 1.9.7.20.3 | 1.9.7.20.3 |  | 2025-12-05 17:00 | q | 0 |  | 2025-12-05 10:32
889 | 1569 | DVuFJt4FGQSIgeZkA41d | Normal | 4 | 1.9.7.20.4 | 1.9.7.20.4 |  | 2025-12-11 17:00 | q | -1 |  | 2025-12-10 09:09
890 | 4590 | 21lrGsmJiPqRYOd4yY3H | Summary | 2 | 1.9.7.21 | 1.9.7.21 |  | 2026-09-16 12:00 | p | 929 |  | 2029-04-03 11:47
891 | 1570 | 9hmrS48cr19KgrseY4yN | Normal | 2 | 1.9.7.21.1 | 1.9.7.21.1 |  | 2026-09-16 12:00 | p | 929 |  | 2029-04-03 11:47
892 | 6439 | JoFd6fDKN7NWznuQx6gK | Normal | 56 | 1.9.7.10 | 1.9.7.10 |  | 2025-04-29 17:00 | q | -5 |  | 2025-04-24 11:28
893 | 7323 | p8rF5Tk8321hO30p5zSy | Summary | 79 | 1.7.8.18 | 1.7.8.18 |  | 2025-06-06 17:00 | p | 13 |  | 2025-06-20 15:38
894 | 7454 | JYERhD3wllXGZEgPk4Fl | Normal | 5 | 1.7.8.18.1 | 1.7.8.18.1 |  | 2025-02-14 17:00 | p | 31 |  | 2025-03-18 09:56
895 | 7455 | hQlezwT73UjuGPZkyuVr | Normal | 9 | 1.7.8.18.2 | 1.7.8.18.2 |  | 2025-02-28 17:00 | p | 27 |  | 2025-03-28 10:02
896 | 7456 | 3cfjdZ38xGBNf8roD7He | Normal | 9 | 1.7.8.18.3 | 1.7.8.18.3 |  | 2025-03-13 17:00 | p | 26 |  | 2025-04-09 14:59
897 | 7457 | abNwDWOnFoe0xwhiRueS | Normal | 1 | 1.7.8.18.4 | 1.7.8.18.4 |  | 2025-03-19 17:00 | p | 21 |  | 2025-04-10 14:30
898 | 7458 | cMhUMuxC0sax27543As7 | Normal | 24 | 1.7.8.18.5 | 1.7.8.18.5 |  | 2025-05-08 17:00 | p | 7 |  | 2025-05-16 10:07
899 | 7459 | xf7OMyoiQ38QdcweBYiq | Normal | 20 | 1.7.8.18.6 | 1.7.8.18.6 |  | 2025-06-06 17:00 | p | 13 |  | 2025-06-20 15:38
900 | 7324 | GVXYroUMjcAFUHa4B19H | Normal | 1 | 1.7.8.19 | 1.7.8.19 |  | 2025-03-28 17:00 | q | -554 |  | 2023-09-21 08:50
901 | 7325 | wl82vK5NXqnnsHIySTFp | Normal | 1 | 1.7.8.20 | 1.7.8.20 |  | 2025-06-09 17:00 | p | 13 |  | 2025-06-23 16:18
902 | 7382 | GJk3wpkfagyrb21gVciV | Summary | 288 | 1.9.7.22 | 1.9.7.22 |  | 2026-04-20 17:00 | p | 933 |  | 2028-11-09 11:11
903 | 7383 | chM988R4AoJxJINOHhOy | Normal | 1 | 1.9.7.22.1 | 1.9.7.22.1 |  | 2025-02-26 17:00 | q | -569 |  | 2023-08-07 16:42
904 | 7384 | xn1TRUhUfNd3ygHlAMk1 | Normal | 16 | 1.9.7.22.2 | 1.9.7.22.2 |  | 2025-03-20 17:00 | q | -575 |  | 2023-08-23 16:37
905 | 7385 | cYlWo9e2zkkP7jtt7iLZ | Normal | 1 | 1.9.7.22.3 | 1.9.7.22.3 |  | 2025-03-21 17:00 | q | -575 |  | 2023-08-24 15:42
906 | 7386 | F9n9tFj3S3xXbwXNgAjU | Normal | 5 | 1.9.7.22.4 | 1.9.7.22.4 |  | 2026-04-20 17:00 | p | 933 |  | 2028-11-09 11:11
907 | 6285 | 0inPdnysTnfuJeCJJEwo | Summary | 131 | 1.9.1 | 1.9.1 |  | 2025-11-28 17:00 | p | 23 |  | 2025-12-22 09:42
908 | 4593 | XK8YU5H8vMrR7jBOr6fS | Normal | 99 | 1.9.1.1 | 1.9.1.1 |  | 2025-07-01 17:00 | p | 19 |  | 2025-07-21 08:37
909 | 4594 | EUFkYGsAZWO3vgZroOTA | Normal | 1 | 1.9.1.2 | 1.9.1.2 |  | 2025-07-02 17:00 | p | 19 |  | 2025-07-22 08:41
910 | 4595 | 0i30zTvKTrSo3R9n999e | Normal | 2 | 1.9.1.3 | 1.9.1.3 |  | 2025-07-07 17:00 | p | 15 |  | 2025-07-23 15:28
911 | 4605 | jXRAJqcdCYbTQqzq5oVG | Normal | 14 | 1.7.3.2 | 1.7.3.2 |  | 2025-02-28 17:00 | p | 31 |  | 2025-04-01 09:25
912 | 4606 | e1c7TqZJ2saEXqSPx9Ca | Normal | 1 | 1.7.3.3 | 1.7.3.3 |  | 2025-05-27 17:00 | p | 33 |  | 2025-06-30 15:35
913 | 4607 | 9Rf8xh1sYqA0mX8AIEgx | Summary | 52 | 1.7.3.5 | 1.7.3.5 |  | 2025-10-16 17:00 | p | 31 |  | 2025-11-17 09:47
914 | 4608 | tlJeJHdE7OwhwWyVvZ8P | Normal | 5 | 1.7.3.5.1 | 1.7.3.5.1 |  | 2025-08-08 17:00 | p | 34 |  | 2025-09-12 13:59
915 | 4609 | PoeQu0I6Io83IRbk7WtS | Normal | 5 | 1.7.3.5.2 | 1.7.3.5.2 |  | 2025-08-15 17:00 | p | 34 |  | 2025-09-19 14:20
916 | 4610 | UGUZlny6Ut8S0mLRTL2X | Normal | 1 | 1.7.3.5.3 | 1.7.3.5.3 |  | 2025-08-18 17:00 | p | 34 |  | 2025-09-22 13:08
917 | 4611 | 1TZOFiOcsBCmkfhi03Iw | Normal | 5 | 1.7.3.5.4 | 1.7.3.5.4 |  | 2025-09-02 17:00 | p | 33 |  | 2025-10-06 11:44
918 | 4612 | ZwEXlYv6PrV1t0gzfqom | Normal | 10 | 1.7.3.5.5 | 1.7.3.5.5 |  | 2025-09-16 17:00 | p | 34 |  | 2025-10-21 10:58
919 | 4613 | z0DGpsje53b33zXA5t1P | Normal | 20 | 1.7.3.5.6 | 1.7.3.5.6 |  | 2025-10-15 17:00 | p | 29 |  | 2025-11-14 09:46
920 | 4614 | cqs4HA7sR83mroZvcBiw | Normal | 1 | 1.7.3.5.7 | 1.7.3.5.7 |  | 2025-10-16 17:00 | p | 31 |  | 2025-11-17 09:47
921 | 4615 | Io6EVgFdyRjG7CB2g0Wy | Summary | 98 | 1.7.3.4 | 1.7.3.4 |  | 2025-08-05 17:00 | p | 35 |  | 2025-09-10 14:26
922 | 4616 | FR5tuVwQGmPNYmz6BeMP | Normal | 2 | 1.7.3.4.1 | 1.7.3.4.1 |  | 2025-02-14 17:00 | p | 25 |  | 2025-03-12 11:53
923 | 4617 | OziRB3N5b7cM46iEETGg | Normal | 5 | 1.7.3.4.2 | 1.7.3.4.2 |  | 2025-02-14 17:00 | p | 31 |  | 2025-03-18 11:06
924 | 4618 | mRqsjEijsp2iSp4l7aof | Normal | 5 | 1.7.3.4.3 | 1.7.3.4.3 |  | 2025-02-24 17:00 | p | 30 |  | 2025-03-27 09:05
925 | 4619 | 8asUr7UOO8nabPagFvw9 | Normal | 40 | 1.7.3.4.4 | 1.7.3.4.4 |  | 2025-04-14 17:00 | p | 24 |  | 2025-05-09 08:39
926 | 4620 | UWR5akRFo4eKiDyQVnYr | Normal | 23 | 1.7.3.4.5 | 1.7.3.4.5 |  | 2025-03-20 17:00 | p | 14 |  | 2025-04-04 08:42
927 | 4621 | pGB9dynKUfIMuzj3AWVv | Normal | 1 | 1.7.3.4.6 | 1.7.3.4.6 |  | 2025-05-28 17:00 | p | 33 |  | 2025-07-01 14:45
928 | 4622 | Bm2ajkWBwO6Cvc6RoPdK | Normal | 5 | 1.7.3.4.7 | 1.7.3.4.7 |  | 2025-06-04 17:00 | p | 36 |  | 2025-07-11 16:20
929 | 4623 | sDTQ4X48dvup817zb0Do | Normal | 20 | 1.7.3.4.8 | 1.7.3.4.8 |  | 2025-07-03 17:00 | p | 38 |  | 2025-08-11 16:17
930 | 4624 | 3CGv61AS00FFpM5LrRat | Normal | 20 | 1.7.3.4.9 | 1.7.3.4.9 |  | 2025-08-01 17:00 | p | 37 |  | 2025-09-08 13:07
931 | 4625 | NkJyZ342jkgJkVCalD4F | Normal | 2 | 1.7.3.4.10 | 1.7.3.4.10 |  | 2025-08-05 17:00 | p | 35 |  | 2025-09-10 14:26
932 | 4626 | 92oajspBBxTpnlNQO91I | Summary | 90 | 1.7.3.6 | 1.7.3.6 |  | 2025-11-28 17:00 | p | 23 |  | 2025-12-22 09:42
933 | 4630 | pjdWghPSPBEOfTIZFZhV | Normal | 5 | 1.7.3.6.4 | 1.7.3.6.4 |  | 2025-02-14 17:00 | p | 30 |  | 2025-03-17 08:01
934 | 4631 | EXJQS9o5Eq3lGkaYsCap | Normal | 1 | 1.7.3.6.5 | 1.7.3.6.5 |  | 2025-02-18 17:00 | p | 26 |  | 2025-03-17 16:23
935 | 4632 | VGp2Ji3lCAas2O4B01f5 | Normal | 1 | 1.7.3.6.6 | 1.7.3.6.6 |  | 2025-02-19 17:00 | p | 26 |  | 2025-03-18 16:09
936 | 4633 | STHfhyBuM5qFiEzHSgws | Normal | 19 | 1.7.3.6.7 | 1.7.3.6.7 |  | 2025-03-18 17:00 | p | 22 |  | 2025-04-10 09:43
937 | 4634 | cbBLoWE0dwfwOCS04ga7 | Normal | 15 | 1.7.3.6.8 | 1.7.3.6.8 |  | 2025-04-08 17:00 | p | 22 |  | 2025-05-01 09:46
938 | 4635 | vrd0V7BeylNxhzgI26F9 | Normal | 8 | 1.7.3.6.11 | 1.7.3.6.11 |  | 2025-04-21 17:00 | p | 22 |  | 2025-05-14 14:26
939 | 4636 | DgPDbwa39NNm3em6lmtZ | Normal | 1 | 1.7.3.6.12 | 1.7.3.6.12 |  | 2025-11-28 17:00 | p | 23 |  | 2025-12-22 09:42
940 | 4663 | X9pjxOrdX8ZwQAfQziSu | Normal | 1 | 1.7.3.6.9 | 1.7.3.6.9 |  | 2025-04-09 17:00 | p | 22 |  | 2025-05-02 09:31
941 | 4664 | DAxARpEpHAwipBCK81bc | Normal | 8 | 1.7.3.6.10 | 1.7.3.6.10 |  | 2025-04-21 17:00 | p | 22 |  | 2025-05-14 10:26
942 | 4637 | ohQUE8EwZLGEmkE5FTpA | Summary | 8 | 1.7.3.7 | 1.7.3.7 |  | 2025-02-28 17:00 | p | 27 |  | 2025-03-28 08:59
943 | 6608 | ifCvUSq9UjUAw7FKKXTR | Normal | 14 | 1.7.3.7.3 | 1.7.3.7.3 |  | 2025-02-28 17:00 | p | 27 |  | 2025-03-28 08:59
944 | 7259 | Dcjo2uskRMoBajU90pQq | Normal | 60 | 1.7.1.4 | 1.7.1.4 |  | 2025-05-23 17:00 | p | 34 |  | 2025-06-27 15:19
945 | 6294 | Jtjxi70STISSeVqV8OJy | Summary | 163 | 1.9.6 | 1.9.6 |  | 2026-09-10 17:00 | p | 823 |  | 2028-12-12 13:30
946 | 3745 | D0mR64Wbk6oru5hoL4DG | Summary | 62 | 1.7.1.2 | 1.7.1.2 |  | 2025-04-08 17:00 | p | 28 |  | 2025-05-07 16:40
947 | 3773 | jfB1zdAbu7JeWEH3ijwy | Summary | 73 | 1.7.1.2.6 | 1.7.1.2.6 |  | 2025-04-08 17:00 | p | 28 |  | 2025-05-07 16:40
948 | 3776 | GHLE38QRMYNBeSYAGB18 | Normal | 32 | 1.7.1.2.6.3 | 1.7.1.2.6.3 |  | 2025-03-26 17:00 | p | 29 |  | 2025-04-25 15:31
949 | 3777 | YuGKQIQDxLVYRZzgUQjw | Normal | 9 | 1.7.1.2.6.4 | 1.7.1.2.6.4 |  | 2025-04-08 17:00 | p | 28 |  | 2025-05-07 16:40
950 | 3783 | FcDlmkxQNUOM36qP0M0H | Summary | 58 | 1.7.1.3 | 1.7.1.3 |  | 2025-06-02 17:00 | p | 34 |  | 2025-07-07 10:07
951 | 3790 | Om0YwWoKF5usOVLnDccR | Summary | 13 | 1.7.1.3.4 | 1.7.1.3.4 |  | 2025-02-28 17:00 | p | 31 |  | 2025-04-01 13:07
952 | 6977 | F0juzsyqTnJm6sTJe4ff | Normal | 14 | 1.7.1.3.4.7 | 1.7.1.3.4.7 |  | 2025-02-28 17:00 | p | 31 |  | 2025-04-01 13:07
953 | 6138 | EvFVoaLHb5OgszmS4Hdy | Summary | 44 | 1.7.1.3.9 | 1.7.1.3.9 |  | 2025-06-02 17:00 | p | 34 |  | 2025-07-07 10:07
954 | 6139 | VECMPYMi2oWf71g3eai1 | Normal | 29 | 1.7.1.3.9.1 | 1.7.1.3.9.1 |  | 2025-05-09 17:00 | p | 27 |  | 2025-06-06 16:23
955 | 6140 | mO0F0FFUdRVKYlb84WcT | Normal | 15 | 1.7.1.3.9.2 | 1.7.1.3.9.2 |  | 2025-06-02 17:00 | p | 34 |  | 2025-07-07 10:07
956 | 6978 | z4sj2SQJw3pdZet8Am0U | Normal | 9 | 1.7.1.3.5 | 1.7.1.3.5 |  | 2025-03-20 17:00 | p | 26 |  | 2025-04-16 09:22
957 | 6983 | PcmQnh6ym2R5IAKzFgwu | Summary | 141 | 1.7.1.3.7 | 1.7.1.3.7 |  | 2025-03-24 17:00 | p | 29 |  | 2025-04-23 10:16
958 | 6985 | eGeEyEDP9xa0SwHKf7WR | Normal | 7 | 1.7.1.3.7.4 | 1.7.1.3.7.4 |  | 2025-03-11 17:00 | p | 29 |  | 2025-04-10 09:59
959 | 6986 | 31qYZ6wVIReV9ZOAqgem | Summary | 9 | 1.7.1.3.7.5 | 1.7.1.3.7.5 |  | 2025-03-24 17:00 | p | 29 |  | 2025-04-23 10:16
960 | 6987 | 50so1NYgvDTnEeNkdrjv | Normal | 3 | 1.7.1.3.7.5.1 | 1.7.1.3.7.5.1 |  | 2025-03-14 17:00 | p | 30 |  | 2025-04-14 16:39
961 | 6988 | bmsC3uFxKZ3RPA57Ivjb | Normal | 3 | 1.7.1.3.7.5.2 | 1.7.1.3.7.5.2 |  | 2025-03-19 17:00 | p | 29 |  | 2025-04-18 11:00
962 | 6989 | okOYULy0nclsZMYhl4sg | Normal | 3 | 1.7.1.3.7.5.3 | 1.7.1.3.7.5.3 |  | 2025-03-24 17:00 | p | 29 |  | 2025-04-23 10:16
963 | 7184 | gKjyagqR1BEsAZjZk4l5 | Milestone | 0 | 1.7.1.3.7.3 | 1.7.1.3.7.3 |  | 2025-02-28 08:00 | q | -29 |  | 2025-01-30 08:00
964 | 6990 | K8cvVDryBsyahUujiNmr | Summary | 22 | 1.7.1.3.8 | 1.7.1.3.8 |  | 2025-03-31 17:00 | p | 28 |  | 2025-04-29 15:49
965 | 6136 | bVRB0EhNo1xoyHBU8R0I | Normal | 1 | 1.7.1.3.8.2 | 1.7.1.3.8.2 |  | 2025-03-21 17:00 | p | 26 |  | 2025-04-17 09:11
966 | 6982 | E06yVWmTg8kRS6Gv9kOV | Summary | 6 | 1.7.1.3.8.3 | 1.7.1.3.8.3 |  | 2025-03-31 17:00 | p | 28 |  | 2025-04-29 15:49
967 | 6137 | gagQpjsDXV4QnJ1bUthb | Normal | 2 | 1.7.1.3.8.3.1 | 1.7.1.3.8.3.1 |  | 2025-03-25 17:00 | p | 26 |  | 2025-04-21 09:05
968 | 6979 | ZYA6dvbLVog9FL6DNJRb | Normal | 5 | 1.7.1.3.8.3.2 | 1.7.1.3.8.3.2 |  | 2025-03-31 17:00 | p | 28 |  | 2025-04-29 15:49
969 | 6991 | RAhO7UtYgqwLkhTknwrO | Normal | 6 | 1.7.1.3.8.1 | 1.7.1.3.8.1 |  | 2025-03-07 17:00 | q | -30 |  | 2025-02-05 15:52
970 | 3803 | vx1oFVBFPqydBxZJ7V4g | Summary | 112 | 1.7.1.5 | 1.7.1.5 |  | 2025-06-04 17:00 | p | 50 |  | 2025-07-25 15:30
971 | 3808 | mNtnU9AYiACOeBrTPE9f | Summary | 29 | 1.7.1.5.3 | 1.7.1.5.3 |  | 2025-03-21 17:00 | p | 24 |  | 2025-04-15 15:59
972 | 3809 | ukioB4iHiwrfEXpseTiK | Normal | 15 | 1.7.1.5.3.1 | 1.7.1.5.3.1 |  | 2025-03-03 17:00 | p | 28 |  | 2025-04-01 15:07
973 | 3810 | CJxWy7PnZPcI4EPHEeme | Normal | 9 | 1.7.1.5.3.2 | 1.7.1.5.3.2 |  | 2025-03-14 17:00 | p | 26 |  | 2025-04-10 11:21
974 | 3811 | wGtgxCT3lCK6u2EOL8xN | Normal | 5 | 1.7.1.5.3.3 | 1.7.1.5.3.3 |  | 2025-03-21 17:00 | p | 24 |  | 2025-04-15 15:59
975 | 3813 | sYeTNUsya13QYMbMJg21 | Normal | 25 | 1.7.1.5.7 | 1.7.1.5.7 |  | 2025-04-03 17:00 | p | 31 |  | 2025-05-05 11:31
976 | 3814 | c3HTuVFoRVefrW72mxSE | Normal | 3 | 1.7.1.5.8 | 1.7.1.5.8 |  | 2025-04-10 17:00 | p | 54 |  | 2025-06-04 10:07
977 | 3815 | nJJAkVwt0aHLNZMMtbkw | Normal | 3 | 1.7.1.5.9 | 1.7.1.5.9 |  | 2025-04-08 17:00 | p | 29 |  | 2025-05-08 08:56
978 | 3816 | 6MWmVgC0FSCF3lMoTGjJ | Summary | 40 | 1.7.1.5.10 | 1.7.1.5.10 |  | 2025-06-04 17:00 | p | 50 |  | 2025-07-25 15:30
979 | 3817 | LqjKPVRVNU7j1iAlkL3t | Normal | 2 | 1.7.1.5.10.1 | 1.7.1.5.10.1 |  | 2025-04-10 17:00 | p | 31 |  | 2025-05-12 09:26
980 | 3818 | Cmm1EfLtBPedDjXV8dAv | Normal | 5 | 1.7.1.5.10.2 | 1.7.1.5.10.2 |  | 2025-04-17 17:00 | p | 31 |  | 2025-05-19 08:29
981 | 3819 | FSVjbKFfUmqE2fpbGGPv | Normal | 3 | 1.7.1.5.10.3 | 1.7.1.5.10.3 |  | 2025-04-22 17:00 | p | 28 |  | 2025-05-21 11:29
982 | 3820 | FhKtXXrOwkDfPm4RFzRW | Normal | 10 | 1.7.1.5.10.4 | 1.7.1.5.10.4 |  | 2025-05-06 17:00 | p | 44 |  | 2025-06-20 10:34
983 | 3821 | cHjYAw102skS4vR6DXqX | Normal | 20 | 1.7.1.5.10.5 | 1.7.1.5.10.5 |  | 2025-06-04 17:00 | p | 50 |  | 2025-07-25 15:30
984 | 6147 | BUcWclFVChflBnUDJ9UM | Normal | 40 | 1.7.1.5.4 | 1.7.1.5.4 |  | 2025-04-07 17:00 | p | 52 |  | 2025-05-30 10:39
985 | 6148 | V03eKqopjAXoUvRodLvQ | Normal | 13 | 1.7.1.5.6 | 1.7.1.5.6 |  | 2025-02-27 17:00 | p | 28 |  | 2025-03-28 13:11
986 | 4078 | ybbKeBChK3D60QzH8ONZ | Normal | 76 | 1.9.6.5 | 1.9.6.5 |  | 2025-05-28 17:00 | p | 26 |  | 2025-06-24 09:52
987 | 4129 | G6dPcJRrq5zqLYx4Vr0R | Summary | 475 | 1.9.6.10 | 1.9.6.10 |  | 2026-05-26 12:00 | p | 931 |  | 2028-12-12 13:30
988 | 4131 | 3WZTLr4e3INGux4LMgj0 | Summary | 146 | 1.9.6.10.2 | 1.9.6.10.2 |  | 2025-09-29 17:00 | p | 863 |  | 2028-02-10 10:41
989 | 5857 | g9TizAnooUcHoXglcd4n | Milestone | 0 | 1.9.6.10.2.1 | 1.9.6.10.2.1 |  | 2025-07-25 17:00 | p | 906 |  | 2028-01-18 08:48
990 | 5858 | 9N3N0HBhBeb82jbbU7Vx | Milestone | 0 | 1.9.6.10.2.2 | 1.9.6.10.2.2 |  | 2025-03-03 17:00 | p | 927 |  | 2027-09-17 14:49
991 | 5859 | RMhsXtyk4773BtipN2HO | Normal | 1 | 1.9.6.10.2.3 | 1.9.6.10.2.3 |  | 2025-03-04 17:00 | p | 929 |  | 2027-09-20 14:29
992 | 5860 | AMUT2hrMeOWSIoK5dO6S | Normal | 10 | 1.9.6.10.2.4 | 1.9.6.10.2.4 |  | 2025-05-16 17:00 | p | 870 |  | 2027-10-04 10:58
993 | 5861 | adMwYb1cwVT0ja23ZKPV | Normal | 10 | 1.9.6.10.2.5 | 1.9.6.10.2.5 |  | 2025-06-02 17:00 | p | 864 |  | 2027-10-15 15:33
994 | 5862 | rkVKH7eSVnkv5Rz0hIbo | Normal | 25 | 1.9.6.10.2.6 | 1.9.6.10.2.6 |  | 2025-07-09 17:00 | p | 868 |  | 2027-11-25 10:07
995 | 5863 | axx1H8vuWtNbWz6aJYpW | Normal | 20 | 1.9.6.10.2.7 | 1.9.6.10.2.7 |  | 2025-08-06 17:00 | p | 873 |  | 2027-12-28 09:23
996 | 5864 | ZuXAUp7kzm7PDgs0Clm4 | Normal | 20 | 1.9.6.10.2.8 | 1.9.6.10.2.8 |  | 2025-09-04 17:00 | p | 866 |  | 2028-01-19 16:30
997 | 5865 | pfx92tyIHO0nDV8Eg4vj | Normal | 3 | 1.9.6.10.2.9 | 1.9.6.10.2.9 |  | 2025-09-09 17:00 | p | 866 |  | 2028-01-24 14:23
998 | 5866 | qnFTkxNSvGIYOwHhqElS | Normal | 5 | 1.9.6.10.2.10 | 1.9.6.10.2.10 |  | 2025-09-16 17:00 | p | 866 |  | 2028-01-31 13:50
999 | 5867 | 6vMprMC9ZRYTg9c055cw | Normal | 3 | 1.9.6.10.2.11 | 1.9.6.10.2.11 |  | 2025-09-19 17:00 | p | 865 |  | 2028-02-02 13:03
1000 | 5868 | qP5P60WlJm98gR28uFOw | Normal | 1 | 1.9.6.10.2.12 | 1.9.6.10.2.12 |  | 2025-09-22 17:00 | p | 863 |  | 2028-02-03 11:32
1001 | 5869 | 5FBVtcv48JlyNzpes7ps | Normal | 5 | 1.9.6.10.2.13 | 1.9.6.10.2.13 |  | 2025-09-29 17:00 | p | 863 |  | 2028-02-10 10:41
1002 | 5870 | rLlKwDBGmyMe6lxLtymf | Summary | 59 | 1.9.6.10.3 | 1.9.6.10.3 |  | 2025-12-24 17:00 | p | 868 |  | 2028-05-11 14:47
1003 | 5871 | owx5unCKcaLauhH4kWyj | Normal | 5 | 1.9.6.10.3.1 | 1.9.6.10.3.1 |  | 2025-10-06 17:00 | p | 864 |  | 2028-02-18 13:09
1004 | 5872 | qImIYF1Y50rp0FNnsaoS | Normal | 10 | 1.9.6.10.3.2 | 1.9.6.10.3.2 |  | 2025-10-21 17:00 | p | 867 |  | 2028-03-07 11:58
1005 | 5873 | FfFQqcMQ2fY5X0GvK0Xd | Normal | 20 | 1.9.6.10.3.3 | 1.9.6.10.3.3 |  | 2025-11-19 17:00 | p | 873 |  | 2028-04-11 11:46
1006 | 5874 | fHTDjpnY2Gm0gViXPiAD | Normal | 2 | 1.9.6.10.3.6 | 1.9.6.10.3.6 |  | 2025-12-22 17:00 | p | 869 |  | 2028-05-10 09:09
1007 | 5875 | TQZary26m4SvJkpuQUlv | Normal | 1 | 1.9.6.10.3.7 | 1.9.6.10.3.7 |  | 2025-12-23 17:00 | p | 868 |  | 2028-05-10 16:29
1008 | 5876 | 5ZRJqmbhPGswffOWtWat | Normal | 1 | 1.9.6.10.3.8 | 1.9.6.10.3.8 |  | 2025-12-24 17:00 | p | 868 |  | 2028-05-11 14:47
1009 | 6624 | sVpbcWAee9M5eeft5sdO | Normal | 15 | 1.9.6.10.3.4 | 1.9.6.10.3.4 |  | 2025-12-11 17:00 | p | 868 |  | 2028-04-28 14:05
1010 | 6625 | it5qGsWYKIf8fEL1a2TB | Normal | 5 | 1.9.6.10.3.5 | 1.9.6.10.3.5 |  | 2025-12-18 17:00 | p | 871 |  | 2028-05-08 10:44
1011 | 5877 | 8uIO0L3CbsjXfYIL70ur | Summary | 162 | 1.9.6.10.4 | 1.9.6.10.4 |  | 2026-05-26 12:00 | p | 931 |  | 2028-12-12 13:30
1012 | 5878 | eKJmpIIS7eePXp789pq5 | Summary | 60 | 1.9.6.10.4.1 | 1.9.6.10.4.1 |  | 2025-12-26 17:00 | p | 859 |  | 2028-05-04 16:46
1013 | 5879 | CJrwB1y6NRnYYg7kpaRv | Summary | 30 | 1.9.6.10.4.1.1 | 1.9.6.10.4.1.1 |  | 2025-11-12 17:00 | p | 860 |  | 2028-03-22 15:58
1014 | 5880 | z8rht75g90pc62Jd1j8e | Normal | 15 | 1.9.6.10.4.1.1.1 | 1.9.6.10.4.1.1.1 |  | 2025-10-21 17:00 | p | 860 |  | 2028-02-29 13:49
1015 | 5881 | ZPPJV7wrbqyTumtl84NX | Normal | 15 | 1.9.6.10.4.1.1.2 | 1.9.6.10.4.1.1.2 |  | 2025-11-12 17:00 | p | 860 |  | 2028-03-22 15:58
1016 | 5882 | PdfqDNDAaUS1Z9tfvPSB | Normal | 15 | 1.9.6.10.4.1.2 | 1.9.6.10.4.1.2 |  | 2025-12-04 17:00 | p | 858 |  | 2028-04-11 16:56
1017 | 5883 | 3J3dFKPf8v7HKW1lSal4 | Normal | 15 | 1.9.6.10.4.1.3 | 1.9.6.10.4.1.3 |  | 2025-12-26 17:00 | p | 859 |  | 2028-05-04 16:46
1018 | 5884 | J3ZDJxR9DKKi4JquRb3Q | Summary | 20 | 1.9.6.10.4.2 | 1.9.6.10.4.2 |  | 2025-10-28 17:00 | p | 866 |  | 2028-03-13 08:09
1019 | 5885 | p0UOLQYQkw5raD9Hf7AI | Normal | 5 | 1.9.6.10.4.2.1 | 1.9.6.10.4.2.1 |  | 2025-10-06 17:00 | p | 863 |  | 2028-02-17 11:18
1020 | 5886 | mfBVa7VrtMT45ZcRp9ur | Normal | 5 | 1.9.6.10.4.2.2 | 1.9.6.10.4.2.2 |  | 2025-10-14 17:00 | p | 862 |  | 2028-02-24 11:50
1021 | 5887 | xjL6okqGZuFc1ChaUzA0 | Normal | 5 | 1.9.6.10.4.2.3 | 1.9.6.10.4.2.3 |  | 2025-10-21 17:00 | p | 863 |  | 2028-03-03 15:24
1022 | 5888 | 0NLdruhvCSk61FiIPSJA | Normal | 5 | 1.9.6.10.4.2.4 | 1.9.6.10.4.2.4 |  | 2025-10-28 17:00 | p | 866 |  | 2028-03-13 08:09
1023 | 5889 | vcqfMiWzgD0sBRK91JrP | Normal | 3 | 1.9.6.10.4.3 | 1.9.6.10.4.3 |  | 2025-10-31 17:00 | p | 865 |  | 2028-03-15 15:38
1024 | 5890 | r7iAplKyl5D3dW7yC0Jk | Normal | 5 | 1.9.6.10.4.4 | 1.9.6.10.4.4 |  | 2025-11-07 17:00 | p | 865 |  | 2028-03-22 15:32
1025 | 5891 | 55B0pL3dU2GPDxU6IZLg | Normal | 1 | 1.9.6.10.4.5 | 1.9.6.10.4.5 |  | 2025-11-10 17:00 | p | 863 |  | 2028-03-23 13:30
1026 | 5892 | zyPP7s8BBmPhydQ5fB2g | Normal | 1 | 1.9.6.10.4.8 | 1.9.6.10.4.8 |  | 2026-05-26 12:00 | p | 931 |  | 2028-12-12 13:30
1027 | 5893 | JSBvauC3wpirasqwMrC9 | Normal | 1 | 1.9.6.10.4.6 | 1.9.6.10.4.6 |  | 2025-11-12 17:00 | p | 862 |  | 2028-03-24 13:34
1028 | 5894 | AO4SgiivKvvxQJupi2GS | Normal | 1 | 1.9.6.10.4.7 | 1.9.6.10.4.7 |  | 2025-11-13 17:00 | p | 864 |  | 2028-03-27 10:02
1029 | 4134 | 86JmjjOtZxj7XQRp3CQF | Summary | 466 | 1.9.6.11 | 1.9.6.11 |  | 2026-09-10 17:00 | p | 648 |  | 2028-06-20 14:26
1030 | 4135 | 0voiyAtBe9AzaXfs8cVF | Summary | 322 | 1.9.6.11.1 | 1.9.6.11.1 |  | 2026-07-02 17:00 | p | 649 |  | 2028-04-12 13:02
1031 | 4136 | bllhlvXmXgF1yFG9Nwfe | Normal | 16 | 1.9.6.11.1.1 | 1.9.6.11.1.1 |  | 2026-05-11 17:00 | p | 654 |  | 2028-02-25 10:36
1032 | 4137 | rnRXxVdKdR5NUADIB31n | Normal | 1 | 1.9.6.11.1.2 | 1.9.6.11.1.2 |  | 2026-05-12 17:00 | p | 656 |  | 2028-02-28 11:51
1033 | 4138 | 75WgU7H7MCC8DDgOcnsD | Normal | 30 | 1.9.6.11.1.3 | 1.9.6.11.1.3 |  | 2026-06-25 17:00 | p | 650 |  | 2028-04-06 09:05
1034 | 4139 | 9SKpfzivi43NDDuHUq0B | Normal | 5 | 1.9.6.11.1.4 | 1.9.6.11.1.4 |  | 2026-07-02 17:00 | p | 649 |  | 2028-04-12 13:02
1035 | 4140 | Lk7gef35zB3WaxM8Xyxe | Summary | 48 | 1.9.6.11.2 | 1.9.6.11.2 |  | 2026-09-10 17:00 | p | 648 |  | 2028-06-20 14:26
1036 | 4141 | HGo5Ep3pqhcsiM5K4QjA | Summary | 23 | 1.9.6.11.2.1 | 1.9.6.11.2.1 |  | 2026-08-05 17:00 | p | 650 |  | 2028-05-17 11:22
1037 | 4142 | VTqJrDLpWuaSlvRQajcM | Normal | 12 | 1.9.6.11.2.1.1 | 1.9.6.11.2.1.1 |  | 2026-07-21 17:00 | p | 649 |  | 2028-05-01 15:56
1038 | 4143 | UwGhtpl5Mnq9WQrcrXRR | Normal | 11 | 1.9.6.11.2.1.2 | 1.9.6.11.2.1.2 |  | 2026-08-05 17:00 | p | 650 |  | 2028-05-17 11:22
1039 | 4144 | zaFQ6K5wegGvKt6DGuoz | Summary | 25 | 1.9.6.11.2.2 | 1.9.6.11.2.2 |  | 2026-09-10 17:00 | p | 648 |  | 2028-06-20 14:26
1040 | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Normal | 10 | 1.9.6.11.2.2.1 | 1.9.6.11.2.2.1 |  | 2026-08-19 17:00 | p | 649 |  | 2028-05-30 13:43
1041 | 4146 | rTeXGnIwGPt6ES3ynSHq | Normal | 5 | 1.9.6.11.2.2.2 | 1.9.6.11.2.2.2 |  | 2026-08-26 17:00 | p | 648 |  | 2028-06-05 15:25
1042 | 4147 | hQaW5HIstT5bbsPEBxyQ | Normal | 10 | 1.9.6.11.2.2.3 | 1.9.6.11.2.2.3 |  | 2026-09-10 17:00 | p | 648 |  | 2028-06-20 14:26
1043 | 5753 | ZptYdARXANY2IOcoHhB1 | Summary | 78 | 1.9.6.1 | 1.9.6.1 |  | 2025-07-28 17:00 | p | 904 |  | 2028-01-19 08:06
1044 | 5998 | aRBXPvE6pbVbcbhlDtu4 | Summary | 47 | 1.9.6.1.7 | 1.9.6.1.7 |  | 2025-07-25 17:00 | p | 906 |  | 2028-01-18 08:48
1045 | 5999 | hTF24jclc5ogfsrVWXZd | Normal | 40 | 1.9.6.1.7.1 | 1.9.6.1.7.1 |  | 2025-07-16 17:00 | p | 904 |  | 2028-01-07 09:53
1046 | 6000 | dvNXA0SZWky1SGhKE7td | Normal | 5 | 1.9.6.1.7.2 | 1.9.6.1.7.2 |  | 2025-07-23 17:00 | p | 904 |  | 2028-01-14 10:43
1047 | 6001 | z8HVZ6SyP3QpkaT54VAm | Normal | 1 | 1.9.6.1.7.3 | 1.9.6.1.7.3 |  | 2025-07-24 17:00 | p | 906 |  | 2028-01-17 10:37
1048 | 6002 | rmlzSal3Nkh8gQGzhscw | Normal | 1 | 1.9.6.1.7.4 | 1.9.6.1.7.4 |  | 2025-07-25 17:00 | p | 906 |  | 2028-01-18 08:48
1049 | 6003 | zkyCYMQIHOywdkyzbjbi | Summary | 48 | 1.9.6.1.8 | 1.9.6.1.8 |  | 2025-07-28 17:00 | p | 904 |  | 2028-01-19 08:06
1050 | 6004 | xOhJcEwgSz1TAvNHU4tB | Normal | 40 | 1.9.6.1.8.1 | 1.9.6.1.8.1 |  | 2025-07-16 17:00 | p | 887 |  | 2027-12-21 11:00
1051 | 6005 | gw3ZFSF3nzLqLqYBiqR7 | Normal | 5 | 1.9.6.1.8.2 | 1.9.6.1.8.2 |  | 2025-07-23 17:00 | p | 887 |  | 2027-12-28 10:31
1052 | 6006 | HEKaqqmbwSXnCRXB6fED | Normal | 1 | 1.9.6.1.8.3 | 1.9.6.1.8.3 |  | 2025-07-24 17:00 | p | 887 |  | 2027-12-29 10:01
1053 | 6007 | vdBzwsumrXxpXNAKvnKh | Normal | 1 | 1.9.6.1.8.4 | 1.9.6.1.8.4 |  | 2025-07-28 17:00 | p | 904 |  | 2028-01-19 08:06
1054 | 6008 | Ph5VFx7Ghit4AwZEFBXT | Summary | 50 | 1.9.6.1.6 | 1.9.6.1.6 |  | 2025-06-16 17:00 | p | 903 |  | 2027-12-07 08:46
1055 | 6009 | NVgukc0KZBShUa0wIlyx | Normal | 30 | 1.9.6.1.6.1 | 1.9.6.1.6.1 |  | 2025-05-16 17:00 | p | 908 |  | 2027-11-11 13:59
1056 | 6010 | tIYqVtlT4yOF2YQ2FRYY | Normal | 10 | 1.9.6.1.6.2 | 1.9.6.1.6.2 |  | 2025-06-02 17:00 | p | 904 |  | 2027-11-24 11:11
1057 | 6011 | 9Y3pHbqvwzl2AwHfvrBG | Normal | 5 | 1.9.6.1.6.3 | 1.9.6.1.6.3 |  | 2025-06-09 17:00 | p | 904 |  | 2027-12-01 10:24
1058 | 6012 | Z1jpWQx4GyFcVoEVg0i0 | Normal | 5 | 1.9.6.1.6.4 | 1.9.6.1.6.4 |  | 2025-06-16 17:00 | p | 903 |  | 2027-12-07 08:46
1059 | 6013 | y2dxMv99iLhGOXikZGuK | Summary | 34 | 1.9.6.1.5 | 1.9.6.1.5 |  | 2025-05-01 17:00 | p | 26 |  | 2025-05-28 15:08
1060 | 6014 | hYHiAVYfHXdDTdWEk9J8 | Normal | 15 | 1.9.6.1.5.1 | 1.9.6.1.5.1 |  | 2025-04-04 17:00 | p | 26 |  | 2025-05-01 14:39
1061 | 6015 | MXdxqc8Y6tIByFeEqluF | Normal | 10 | 1.9.6.1.5.2 | 1.9.6.1.5.2 |  | 2025-04-18 17:00 | p | 26 |  | 2025-05-15 14:44
1062 | 6016 | gwhB80Lv7eu4PoYwev8o | Normal | 5 | 1.9.6.1.5.3 | 1.9.6.1.5.3 |  | 2025-04-25 17:00 | p | 25 |  | 2025-05-21 13:41
1063 | 6017 | VCyTBN0y7V3erCRNMvm4 | Normal | 4 | 1.9.6.1.5.4 | 1.9.6.1.5.4 |  | 2025-05-01 17:00 | p | 26 |  | 2025-05-28 15:08
1064 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | 2025-03-17 17:00 | p | 925 |  | 2027-09-28 17:00
1065 | 6957 | ar01N24L63iczVEh1mVo | Summary | 24 | 1.9.6.1.4 | 1.9.6.1.4 |  | 2025-04-04 17:00 | p | 27 |  | 2025-05-02 08:12
1066 | 6958 | 6Ul4V6iAcnpVqewOp14Y | Normal | 4 | 1.9.6.1.4.1 | 1.9.6.1.4.1 |  | 2025-03-07 17:00 | p | 30 |  | 2025-04-07 13:43
1067 | 6959 | w9Vvv79ftt4PUqInNFyD | Normal | 5 | 1.9.6.1.4.2 | 1.9.6.1.4.2 |  | 2025-03-14 17:00 | p | 27 |  | 2025-04-11 15:34
1068 | 6960 | xIgpHAurEQ244gHa2T5q | Normal | 5 | 1.9.6.1.4.3 | 1.9.6.1.4.3 |  | 2025-03-21 17:00 | p | 27 |  | 2025-04-18 14:07
1069 | 6961 | NOksVV7sTymsgwMrnh6x | Normal | 10 | 1.9.6.1.4.4 | 1.9.6.1.4.4 |  | 2025-04-04 17:00 | p | 27 |  | 2025-05-02 08:12
1070 | 5762 | BY50RWHTB6QfyvgvJksd | Summary | 36 | 1.9.6.9 | 1.9.6.9 |  | 2025-04-01 17:00 | p | 27 |  | 2025-04-29 14:50
1071 | 4074 | H2vE7zxiBRw3YTdo2zSW | Normal | 35 | 1.9.6.9.2 | 1.9.6.9.2 |  | 2025-03-31 17:00 | p | 27 |  | 2025-04-28 13:41
1072 | 4075 | dGbNHsOLhslKk8CjhyjE | Normal | 1 | 1.9.6.9.3 | 1.9.6.9.3 |  | 2025-04-01 17:00 | p | 27 |  | 2025-04-29 14:50
1073 | 6424 | xU9ngPKik2IYPonksYTK | Summary | 24 | 1.7.1.8 | 1.7.1.8 |  | 2025-03-14 17:00 | q | -101 |  | 2024-12-03 16:57
1074 | 6427 | NeAxFJaqSLize8VPNJ6N | Normal | 1 | 1.7.1.8.3 | 1.7.1.8.3 |  | 2025-03-14 17:00 | q | -101 |  | 2024-12-03 16:57
1075 | 6296 | SlR21lje1Tex9DLMlAM1 | Summary | 222 | 1.9.8 | 1.9.8 |  | 2026-10-05 12:00 | p | 927 |  | 2029-04-20 09:39
1076 | 4192 | vUDAXlHZqbmK6WAsX9hH | Summary | 139 | 1.9.8.1 | 1.9.8.1 |  | 2025-09-22 17:00 | q | -17 |  | 2025-09-05 08:03
1077 | 4196 | 2ZwOzHGH45ywtPvfASSG | Normal | 5 | 1.9.8.1.5 | 1.9.8.1.5 |  | 2025-09-22 17:00 | q | -17 |  | 2025-09-05 08:03
1078 | 4197 | 4xVk2zrTd9sJnt9BJFir | Summary | 36 | 1.9.8.1.6 | 1.9.8.1.6 |  | 2025-02-27 17:00 | q | -36 |  | 2025-01-22 17:00
1079 | 5974 | cJ7VeFZezCBnvYlHxCmb | Normal | 1 | 1.9.8.1.6.7 | 1.9.8.1.6.7 |  | 2025-02-27 17:00 | q | -119 |  | 2024-10-31 11:25
1080 | 4198 | k6X8NWhjfeQOPZdDpmna | Normal | 20 | 1.9.8.1.9 | 1.9.8.1.9 |  | 2025-03-10 17:00 | p | 29 |  | 2025-04-09 09:57
1081 | 5985 | AUKn3E7aViOsULw8HdKV | Normal | 131 | 1.9.8.1.12 | 1.9.8.1.12 |  | 2025-09-15 17:00 | q | -20 |  | 2025-08-26 15:35
1082 | 4222 | uotgqiCu1xVBvHdpBC3E | Summary | 97 | 1.9.8.2 | 1.9.8.2 |  | 2025-11-25 17:00 | q | -11 |  | 2025-11-14 11:45
1083 | 4231 | 8h0WH2qeIC7tfvcerCPa | Normal | 1 | 1.9.8.2.3 | 1.9.8.2.3 |  | 2025-06-24 17:00 | q | -183 |  | 2024-12-23 16:21
1084 | 4235 | QiaATNQSPId7svzcuO8r | Normal | 91 | 1.9.8.2.7 | 1.9.8.2.7 |  | 2025-11-25 17:00 | q | -11 |  | 2025-11-14 11:45
1085 | 4238 | ReJqSs3gutB053iVY5c7 | Summary | 76 | 1.9.8.4 | 1.9.8.4 |  | 2025-05-28 17:00 | p | 43 |  | 2025-07-11 10:20
1086 | 4242 | RIVyyga7UReDeuixs5m9 | Normal | 66 | 1.9.8.4.4 | 1.9.8.4.4 |  | 2025-05-13 17:00 | p | 44 |  | 2025-06-27 11:52
1087 | 4243 | LpPx7AWOh1V8dzWVWc6j | Normal | 1 | 1.9.8.4.5 | 1.9.8.4.5 |  | 2025-05-13 17:00 | q | -357 |  | 2024-05-21 15:48
1088 | 4246 | ANAzXnUTz1PCb3xsov4Y | Normal | 10 | 1.9.8.4.7 | 1.9.8.4.7 |  | 2025-05-28 17:00 | p | 43 |  | 2025-07-11 10:20
1089 | 4248 | E1RJwJWM8qrsKP3o7Toy | Normal | 1 | 1.9.8.7 | 1.9.8.7 |  | 2025-08-05 17:00 | q | -18 |  | 2025-07-18 16:27
1090 | 4251 | IBg36OMMKUy3vwEnRNF0 | Normal | 1 | 1.9.8.6 | 1.9.8.6 |  | 2025-06-05 17:00 | q | -667 |  | 2023-08-08 09:48
1091 | 4253 | hnujWIe1JDNg9VHs3TWw | Normal | 1 | 1.9.8.8 | 1.9.8.8 |  | 2025-08-12 17:00 | q | -22 |  | 2025-07-21 16:58
1092 | 4255 | TAfq40Sin0H6Q2YT0OS5 | Milestone | 0 | 1.9.8.3 | 1.9.8.3 |  | 2025-11-25 17:00 | q | -11 |  | 2025-11-14 11:45
1093 | 4256 | G2pYfP7dsnHVTgqQD6mD | Summary | 82 | 1.9.8.10 | 1.9.8.10 |  | 2026-01-27 17:00 | q | -783 |  | 2023-12-06 08:59
1094 | 4258 | GzQkXlTiYJMdE6nBDVeb | Normal | 6 | 1.9.8.10.1 | 1.9.8.10.1 |  | 2025-10-03 17:00 | q | -784 |  | 2023-08-11 16:09
1095 | 6090 | LkexiRQNUDyJAwm8EPYV | Normal | 32 | 1.9.8.10.7 | 1.9.8.10.7 |  | 2026-01-27 17:00 | q | -783 |  | 2023-12-06 08:59
1096 | 6187 | kIPGiItVAbHq2ks8DK41 | Normal | 5 | 1.9.8.10.6 | 1.9.8.10.6 |  | 2025-12-09 17:00 | q | -788 |  | 2023-10-13 16:14
1097 | 6430 | IYyY3jK4t9QuDyuxqyQ5 | Normal | 15 | 1.9.8.10.2 | 1.9.8.10.2 |  | 2025-10-27 17:00 | q | -789 |  | 2023-08-30 13:04
1098 | 6431 | mXx66gQ5BZWpD3idmZgM | Normal | 10 | 1.9.8.10.3 | 1.9.8.10.3 |  | 2025-11-10 17:00 | q | -784 |  | 2023-09-18 11:27
1099 | 6432 | vMoeJo3Rc30lMwFim6rn | Normal | 10 | 1.9.8.10.4 | 1.9.8.10.4 |  | 2025-11-25 17:00 | q | -784 |  | 2023-10-03 11:25
1100 | 6433 | zONKYXhH5yZJE26xvIWD | Normal | 4 | 1.9.8.10.5 | 1.9.8.10.5 |  | 2025-12-02 17:00 | q | -785 |  | 2023-10-09 09:37
1101 | 6083 | 3dsblDK1X9ztc27EZU3v | Normal | 1 | 1.9.8.5 | 1.9.8.5 |  | 2025-12-12 17:00 | p | 930 |  | 2028-06-30 09:58
1102 | 6084 | deZM0xh115wln716GUoI | Normal | 1 | 1.9.8.9 | 1.9.8.9 |  | 2026-10-05 12:00 | p | 927 |  | 2029-04-20 09:39
1103 | 7321 | CTokiQfH6gyOyeZJGrxP | Normal | 1 | 1.7.9.11 | 1.7.9.11 |  | 2025-05-30 17:00 | q | -662 |  | 2023-08-07 16:52
1104 | 6314 | PaZTrKFuMaJQzXHDclW5 | Summary | 34 | 1.9.2 | 1.9.2 |  | 2025-04-29 17:00 | p | 28 |  | 2025-05-28 09:44
1105 | 5666 | lc2LPCzbTjVw9vZ8eS89 | Summary | 23 | 1.9.2.2 | 1.9.2.2 |  | 2025-02-27 17:00 | p | 25 |  | 2025-03-25 16:29
1106 | 5667 | chBvra0KGhqU3lfHBAI4 | Summary | 23 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-02-27 17:00 | p | 25 |  | 2025-03-25 16:29
1107 | 5669 | bBSx7g3AuM8uxZcIYlIi | Normal | 20 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-02-27 17:00 | p | 25 |  | 2025-03-25 16:29
1108 | 5672 | 2GDxhVAL0LbO4lfSMjXo | Summary | 47 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-29 17:00 | p | 28 |  | 2025-05-28 09:44
1109 | 5690 | jLB7gq1wR8egZrMIoAc7 | Summary | 24 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-02 17:00 | p | 22 |  | 2025-04-25 09:18
1110 | 5691 | glUuWw43f2R9t2hl6VHO | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-03-13 17:00 | p | 21 |  | 2025-04-04 10:19
1111 | 5692 | KeXnvnZRx0KMyut3yw5s | Milestone | 0 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-03-13 17:00 | p | 21 |  | 2025-04-04 10:19
1112 | 5693 | VdKRFLdSc60knizSqFXc | Normal | 14 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-02 17:00 | p | 22 |  | 2025-04-25 09:18
1113 | 5694 | Gb0taOZcQ8l0cdHliY6j | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-16 17:00 | p | 25 |  | 2025-05-12 15:52
1114 | 5695 | ePp2idADlztrdEpItyCc | Milestone | 0 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-16 17:00 | p | 25 |  | 2025-05-12 15:52
1115 | 5696 | npE0RnxADwI7cDPG1fDa | Normal | 4 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-22 17:00 | p | 26 |  | 2025-05-19 10:36
1116 | 5697 | 4nIBzBv3LSP60HeOLv0f | Normal | 5 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-04-29 17:00 | p | 28 |  | 2025-05-28 09:44
1117 | 6315 | 2iW64uJmzViIcLEo0dMn | Summary | 181 | 1.9.5 | 1.9.5 |  | 2025-12-08 17:00 | p | 944 |  | 2028-07-10 11:57
1118 | 5532 | NHN4dwEEPEqCDqA4Rwlr | Summary | 74 | 1.9.5.1 | 1.9.5.1 |  | 2025-04-28 17:00 | p | 57 |  | 2025-06-25 09:29
1119 | 5535 | XVk7S0ldLHQUWflKhMBn | Normal | 11 | 1.9.5.1.2 | 1.9.5.1.2 |  | 2025-02-25 17:00 | p | 26 |  | 2025-03-24 10:42
1120 | 5536 | cYU0DBZylLxVRoLEp7Bc | Normal | 40 | 1.9.5.1.4 | 1.9.5.1.4 |  | 2025-04-28 17:00 | p | 57 |  | 2025-06-25 09:29
1121 | 5537 | 9xVQhmyTVkChMoMOy91g | Summary | 193 | 1.9.5.2 | 1.9.5.2 |  | 2025-10-24 17:00 | p | 950 |  | 2028-06-01 10:32
1122 | 5539 | kRsO3PSMDsMxji3dmdNc | Normal | 5 | 1.9.5.2.2 | 1.9.5.2.2 |  | 2025-02-14 17:00 | p | 929 |  | 2027-09-02 13:26
1123 | 5540 | GKx3XnA1BSbhTsgdKbqP | Normal | 14 | 1.9.5.2.8 | 1.9.5.2.8 |  | 2025-03-03 17:00 | p | 31 |  | 2025-04-04 14:59
1124 | 5541 | LhqIvyBzzdwllIHwrPz2 | Normal | 5 | 1.9.5.2.7 | 1.9.5.2.7 |  | 2025-03-03 17:00 | p | 29 |  | 2025-04-02 09:07
1125 | 5542 | 4ivItsonCrTGke19i41Z | Normal | 15 | 1.9.5.2.6 | 1.9.5.2.6 |  | 2025-03-03 17:00 | p | 29 |  | 2025-04-02 09:07
1126 | 5543 | XaHBDo6QUBfyTg5ESk7j | Normal | 15 | 1.9.5.2.9 | 1.9.5.2.9 |  | 2025-03-03 17:00 | p | 34 |  | 2025-04-07 16:10
1127 | 5544 | cIc3ARzcdrbXv6maHllr | Summary | 129 | 1.9.5.2.13 | 1.9.5.2.13 |  | 2025-09-17 17:00 | p | 944 |  | 2028-04-19 10:01
1128 | 5545 | 7UVU8IboY6NG7sqZCrUC | Normal | 7 | 1.9.5.2.13.2 | 1.9.5.2.13.2 |  | 2025-05-30 17:00 | p | 942 |  | 2027-12-29 16:29
1129 | 5546 | Shs5wuYOFSkTF1YslX8w | Normal | 6 | 1.9.5.2.13.5 | 1.9.5.2.13.5 |  | 2025-06-16 17:00 | p | 941 |  | 2028-01-14 10:46
1130 | 5547 | KglXvc5QwlHEboIvY96Q | Normal | 4 | 1.9.5.2.13.8 | 1.9.5.2.13.8 |  | 2025-07-14 17:00 | p | 939 |  | 2028-02-09 13:14
1131 | 5548 | Zfzda0CfmpiN8ZL93G3t | Normal | 5 | 1.9.5.2.13.9 | 1.9.5.2.13.9 |  | 2025-07-21 17:00 | p | 940 |  | 2028-02-17 13:18
1132 | 5549 | PgYJem7PJFdGgV04ojeL | Normal | 1 | 1.4.17 | 1.4.17 |  | 2025-07-22 17:00 | p | 940 |  | 2028-02-18 16:01
1133 | 5556 | fOMVaiOa0jnHOJyDUdVQ | Normal | 25 | 1.9.5.2.13.11 | 1.9.5.2.13.11 |  | 2025-09-17 17:00 | p | 944 |  | 2028-04-19 10:01
1134 | 5730 | ypyrsmMFJqJ9aPla6UhQ | Normal | 4 | 1.9.5.2.13.3 | 1.9.5.2.13.3 |  | 2025-06-05 17:00 | p | 942 |  | 2028-01-04 15:46
1135 | 5731 | uQF6Ff0bc2cqy3b37ZQc | Normal | 1 | 1.9.5.2.13.4 | 1.9.5.2.13.4 |  | 2025-06-06 17:00 | p | 942 |  | 2028-01-05 14:48
1136 | 5732 | OQKwpwUgImWCC2Fp5G0Q | Normal | 7 | 1.9.5.2.13.6 | 1.9.5.2.13.6 |  | 2025-06-26 17:00 | p | 942 |  | 2028-01-25 11:46
1137 | 5733 | wyOxVAS94HubPKo2yHJm | Normal | 7 | 1.9.5.2.13.7 | 1.9.5.2.13.7 |  | 2025-07-08 17:00 | p | 939 |  | 2028-02-03 13:14
1138 | 7000 | yP1oDcnUQTy3g68ZLgu0 | Normal | 8 | 1.9.5.2.13.1 | 1.9.5.2.13.1 |  | 2025-03-26 17:00 | p | 27 |  | 2025-04-23 16:51
1139 | 5557 | U376LwOjKfNZoVLUlmMD | Summary | 113 | 1.9.5.2.12 | 1.9.5.2.12 |  | 2025-08-12 17:00 | p | 944 |  | 2028-03-14 13:46
1140 | 5558 | RXAxJx3BHWNVdWFPfZ2a | Normal | 13 | 1.9.5.2.12.2 | 1.9.5.2.12.2 |  | 2025-05-09 17:00 | p | 943 |  | 2027-12-09 10:24
1141 | 5559 | jJoy8dUJMWD3ZuNw52D0 | Normal | 8 | 1.9.5.2.12.5 | 1.9.5.2.12.5 |  | 2025-06-02 17:00 | p | 941 |  | 2027-12-31 14:10
1142 | 5560 | wu3sL1wqoiodUr5mG52N | Normal | 4 | 1.9.5.2.12.8 | 1.9.5.2.12.8 |  | 2025-06-27 17:00 | p | 943 |  | 2028-01-27 11:57
1143 | 5561 | Vb2zzMF18WNANxlCzGiz | Normal | 5 | 1.9.5.2.12.9 | 1.9.5.2.12.9 |  | 2025-07-07 17:00 | p | 939 |  | 2028-02-02 14:54
1144 | 5562 | vp7j6GBYm2dAMLvxEFuE | Normal | 1 | 1.4.20 | 1.4.20 |  | 2025-07-08 17:00 | p | 939 |  | 2028-02-03 15:25
1145 | 5569 | 35aiC9HLOSrIl2OBwDvd | Normal | 25 | 1.9.5.2.12.11 | 1.9.5.2.12.11 |  | 2025-08-12 17:00 | p | 944 |  | 2028-03-14 13:46
1146 | 5734 | iq9bjqBZvH9Bj6912271 | Normal | 6 | 1.9.5.2.12.3 | 1.9.5.2.12.3 |  | 2025-05-19 17:00 | p | 944 |  | 2027-12-20 13:06
1147 | 5735 | Z8zFgfwvHK2hwW2AW8Qa | Normal | 1 | 1.9.5.2.12.4 | 1.9.5.2.12.4 |  | 2025-05-20 17:00 | p | 944 |  | 2027-12-21 13:16
1148 | 5736 | QgUmTWGvxjzq3xqrWPJK | Normal | 7 | 1.9.5.2.12.6 | 1.9.5.2.12.6 |  | 2025-06-11 17:00 | p | 943 |  | 2028-01-11 10:01
1149 | 5737 | iDzIA8f8DQgg2wVNkaUu | Normal | 7 | 1.9.5.2.12.7 | 1.9.5.2.12.7 |  | 2025-06-23 17:00 | p | 941 |  | 2028-01-21 13:29
1150 | 7001 | WpRQh8HvPfyDha8FH5FR | Normal | 9 | 1.9.5.2.12.1 | 1.9.5.2.12.1 |  | 2025-03-14 17:00 | p | 31 |  | 2025-04-15 16:20
1151 | 5570 | MuDwSgsBJjDxwFkSMWYJ | Summary | 116 | 1.9.5.2.11 | 1.9.5.2.11 |  | 2025-07-30 17:00 | p | 928 |  | 2028-02-14 08:18
1152 | 5571 | lfRAbO0c5jl7NaC6s7pm | Normal | 21 | 1.9.5.2.11.2 | 1.9.5.2.11.2 |  | 2025-04-14 17:00 | p | 940 |  | 2027-11-11 09:42
1153 | 5572 | jk3Vm36iIGViuk9dpLfQ | Normal | 8 | 1.9.5.2.11.5 | 1.9.5.2.11.5 |  | 2025-05-02 17:00 | p | 937 |  | 2027-11-26 08:06
1154 | 5573 | u3MfiduPa05JsS2ly7WD | Normal | 4 | 1.9.5.2.11.8 | 1.9.5.2.11.8 |  | 2025-06-12 17:00 | p | 936 |  | 2028-01-05 08:46
1155 | 5574 | 3iKE3riinMPRUpVpTfwx | Normal | 5 | 1.9.5.2.11.9 | 1.9.5.2.11.9 |  | 2025-06-20 17:00 | p | 935 |  | 2028-01-12 14:00
1156 | 5575 | 48yotl4pDzxbk5y0VDbK | Normal | 1 | 1.4.23 | 1.4.23 |  | 2025-06-23 17:00 | p | 933 |  | 2028-01-13 14:31
1157 | 5582 | 6tLu8emqwotxTkeBbEpy | Normal | 26 | 1.9.5.2.11.11 | 1.9.5.2.11.11 |  | 2025-07-30 17:00 | p | 928 |  | 2028-02-14 08:18
1158 | 5738 | ME2oX9BwgLu5cggaunhg | Normal | 5 | 1.9.5.2.11.3 | 1.9.5.2.11.3 |  | 2025-04-21 17:00 | p | 940 |  | 2027-11-18 09:40
1159 | 5739 | IivOSmNLtmlF9JKFLUrl | Normal | 1 | 1.9.5.2.11.4 | 1.9.5.2.11.4 |  | 2025-04-22 17:00 | p | 940 |  | 2027-11-19 08:41
1160 | 5740 | eRxCjL3dV2CpHvAG84r7 | Normal | 12 | 1.9.5.2.11.6 | 1.9.5.2.11.6 |  | 2025-05-20 17:00 | p | 936 |  | 2027-12-13 15:36
1161 | 5741 | 8Y4jq7dOt4lN4NYBT6r1 | Normal | 12 | 1.9.5.2.11.7 | 1.9.5.2.11.7 |  | 2025-06-06 17:00 | p | 935 |  | 2027-12-29 16:03
1162 | 6998 | CyWehBzIvIWKBi1qju4z | Normal | 15 | 1.9.5.2.11.1 | 1.9.5.2.11.1 |  | 2025-03-03 17:00 | p | 29 |  | 2025-04-02 09:07
1163 | 5583 | gkFBoXdv1oJb2jtBcO5M | Summary | 147 | 1.9.5.2.14 | 1.9.5.2.14 |  | 2025-10-24 17:00 | p | 950 |  | 2028-06-01 10:32
1164 | 5584 | 6WMzJdzS7tY0wFFuXnrc | Normal | 7 | 1.9.5.2.14.2 | 1.9.5.2.14.2 |  | 2025-06-17 17:00 | p | 940 |  | 2028-01-14 16:57
1165 | 5585 | KljMWvDEBGSuBTW4zQhZ | Normal | 7 | 1.9.5.2.14.5 | 1.9.5.2.14.5 |  | 2025-07-07 17:00 | p | 939 |  | 2028-02-02 15:52
1166 | 5586 | Z3ZWpIsgJCSKUX161hV0 | Normal | 4 | 1.9.5.2.14.8 | 1.9.5.2.14.8 |  | 2025-07-29 17:00 | p | 939 |  | 2028-02-24 11:24
1167 | 5587 | OXOUsYDejGVlgqn4Z1vl | Normal | 5 | 1.9.5.2.14.9 | 1.9.5.2.14.9 |  | 2025-08-05 17:00 | p | 940 |  | 2028-03-03 15:26
1168 | 5588 | MFjHKzinVVI0Ndx8qx0B | Normal | 1 | 1.4.26 | 1.4.26 |  | 2025-08-06 17:00 | p | 942 |  | 2028-03-06 16:52
1169 | 5595 | REFTk0AP9RBTibJWVhuH | Normal | 26 | 1.9.5.2.14.11 | 1.9.5.2.14.11 |  | 2025-10-24 17:00 | p | 950 |  | 2028-06-01 10:32
1170 | 5742 | 88bEv4EMiOL2y8w1ttIM | Normal | 4 | 1.9.5.2.14.3 | 1.9.5.2.14.3 |  | 2025-06-24 17:00 | p | 940 |  | 2028-01-21 16:37
1171 | 5743 | 0Uz4krHDVCdAlMd5aRwh | Normal | 1 | 1.9.5.2.14.4 | 1.9.5.2.14.4 |  | 2025-06-25 17:00 | p | 943 |  | 2028-01-25 09:57
1172 | 5744 | cSBfnbrbVLLFYTMEfBKA | Normal | 6 | 1.9.5.2.14.6 | 1.9.5.2.14.6 |  | 2025-07-15 17:00 | p | 943 |  | 2028-02-14 09:20
1173 | 5745 | ZY99Y6JX4jBylnfeedvo | Normal | 6 | 1.9.5.2.14.7 | 1.9.5.2.14.7 |  | 2025-07-23 17:00 | p | 939 |  | 2028-02-18 14:37
1174 | 6999 | AnycnugTW971av3hMZXE | Normal | 8 | 1.9.5.2.14.1 | 1.9.5.2.14.1 |  | 2025-04-07 17:00 | p | 27 |  | 2025-05-05 14:02
1175 | 6446 | XvbStahAymwCoqNIbMJG | Summary | 32 | 1.9.5.2.4 | 1.9.5.2.4 |  | 2025-04-15 17:00 | q | -365 |  | 2024-04-15 08:29
1176 | 6532 | 15e7xcLR1b1jSikaz0S2 | Normal | 32 | 1.9.5.2.4.2 | 1.9.5.2.4.2 |  | 2025-04-15 17:00 | q | -369 |  | 2024-04-11 13:05
1177 | 6533 | b0mutjzKj8FRw4zkbb8K | Normal | 32 | 1.9.5.2.4.1 | 1.9.5.2.4.1 |  | 2025-04-15 17:00 | q | -365 |  | 2024-04-15 08:29
1178 | 6534 | 8Gl2bk4Fxxo2fsClDJqG | Normal | 32 | 1.9.5.2.4.3 | 1.9.5.2.4.3 |  | 2025-04-15 17:00 | q | -370 |  | 2024-04-10 16:36
1179 | 6535 | dWze9AnK8NrEMD9LOEyU | Normal | 32 | 1.9.5.2.4.4 | 1.9.5.2.4.4 |  | 2025-04-15 17:00 | q | -369 |  | 2024-04-11 08:19
1180 | 6528 | LROLnQke0gWnMONa67YB | Summary | 50 | 1.9.5.2.5 | 1.9.5.2.5 |  | 2025-03-31 17:00 | p | 29 |  | 2025-04-30 11:27
1181 | 6531 | iX155TL3hNg9Ca4Bsb4A | Normal | 35 | 1.9.5.2.5.2 | 1.9.5.2.5.2 |  | 2025-03-31 17:00 | p | 29 |  | 2025-04-30 11:27
1182 | 6955 | CPACk87DS0kpO7pXcdwS | Normal | 10 | 1.9.5.2.10 | 1.9.5.2.10 |  | 2025-03-03 17:00 | p | 927 |  | 2027-09-17 14:49
1183 | 6997 | MBGoTUikAECGvIHYk1uV | Normal | 24 | 1.9.5.2.3 | 1.9.5.2.3 |  | 2025-03-14 17:00 | p | 941 |  | 2027-10-12 11:58
1184 | 5596 | upn4QoZvaKBmBMoyhnq5 | Summary | 90 | 1.9.5.3 | 1.9.5.3 |  | 2025-12-08 17:00 | p | 944 |  | 2028-07-10 11:57
1185 | 5597 | zKJsJYNcPRFZ7wBjvprv | Normal | 18 | 1.9.5.3.1 | 1.9.5.3.1 |  | 2025-08-22 17:00 | p | 940 |  | 2028-03-20 10:47
1186 | 5598 | zvvzNQqIPXzcVRwy0N44 | Summary | 52 | 1.9.5.3.2 | 1.9.5.3.2 |  | 2025-12-01 17:00 | p | 944 |  | 2028-07-03 15:24
1187 | 5599 | T0Oh47cWIVU9y2MKPB0U | Normal | 12 | 1.9.5.3.2.1 | 1.9.5.3.2.1 |  | 2025-10-01 17:00 | p | 942 |  | 2028-05-01 15:11
1188 | 5600 | oTkX6bjokLXQ590hdeFy | Normal | 12 | 1.9.5.3.2.2 | 1.9.5.3.2.2 |  | 2025-10-20 17:00 | p | 945 |  | 2028-05-23 11:10
1189 | 5601 | xa7cRxeKgQxZnuHNAYMQ | Normal | 12 | 1.9.5.3.2.3 | 1.9.5.3.2.3 |  | 2025-11-12 17:00 | p | 944 |  | 2028-06-14 08:04
1190 | 5602 | QlxDegibloFbHrPNJwyW | Normal | 12 | 1.9.5.3.2.4 | 1.9.5.3.2.4 |  | 2025-12-01 17:00 | p | 944 |  | 2028-07-03 15:24
1191 | 5603 | dwMYG7lg76TqxtTxZNCR | Normal | 5 | 1.9.5.3.3 | 1.9.5.3.3 |  | 2025-12-08 17:00 | p | 944 |  | 2028-07-10 11:57
1192 | 6189 | OaskfHPb0rGXxqxmUlvr | Summary | 69 | 1.7.2.7 | 1.7.2.7 |  | 2025-04-29 17:00 | p | 41 |  | 2025-06-10 15:50
1193 | 6248 | DGpV8AP7Q4dyYuiDaoIl | Summary | 56 | 1.7.2.7.2 | 1.7.2.7.2 |  | 2025-04-29 17:00 | p | 41 |  | 2025-06-10 15:50
1194 | 6251 | Ha7ZmVRhPp4EjAGEFQOQ | Normal | 56 | 1.7.2.7.2.3 | 1.7.2.7.2.3 |  | 2025-04-29 17:00 | p | 41 |  | 2025-06-10 15:50
1195 | 6252 | FwTW8u2nmxBgH6wyvtoz | Summary | 56 | 1.7.2.7.3 | 1.7.2.7.3 |  | 2025-04-29 17:00 | p | 29 |  | 2025-05-29 15:06
1196 | 6255 | 6Rcxv4eHz2WhxfD2wxtd | Normal | 56 | 1.7.2.7.3.3 | 1.7.2.7.3.3 |  | 2025-04-29 17:00 | p | 29 |  | 2025-05-29 15:06
1197 | 6256 | TcRehVKUpIeirJTvWiO5 | Summary | 14 | 1.7.2.7.4 | 1.7.2.7.4 |  | 2025-02-28 17:00 | p | 30 |  | 2025-03-31 14:46
1198 | 6259 | q6ww59eaDtL5Df1J4lsR | Normal | 14 | 1.7.2.7.4.3 | 1.7.2.7.4.3 |  | 2025-02-28 17:00 | p | 30 |  | 2025-03-31 14:46
1199 | 6260 | nYwGXpoj6WqcdUPfZoTk | Summary | 14 | 1.7.2.7.5 | 1.7.2.7.5 |  | 2025-02-28 17:00 | p | 33 |  | 2025-04-03 10:39
1200 | 6263 | aKytB1b2oD2t1WVaznUP | Normal | 14 | 1.7.2.7.5.3 | 1.7.2.7.5.3 |  | 2025-02-28 17:00 | p | 33 |  | 2025-04-03 10:39
1201 | 6317 | NzqiT3qChWGoVO5Oxj9C | Summary | 111 | 1.9.4 | 1.9.4 |  | 2025-09-16 17:00 | p | 397 |  | 2026-10-19 13:36
1202 | 5355 | lohINUHwZqjP23W1PYQO | Summary | 26 | 1.9.4.1 | 1.9.4.1 |  | 2025-04-14 17:00 | q | 0 |  | 2025-04-14 08:31
1203 | 5360 | ARncD9Nx3De5DONPy9Bs | Normal | 3 | 1.9.4.1.4 | 1.9.4.1.4 |  | 2025-04-14 17:00 | q | 0 |  | 2025-04-14 08:31
1204 | 7263 | mjGxmWsUF3dJi6MlhQpM | Normal | 1 | 1.7.4.1.5 | 1.7.4.1.5 |  | 2025-04-09 17:00 | q | 0 |  | 2025-04-09 16:48
1205 | 5362 | 4bsxfawvV6TKTvCq9VoB | Summary | 6 | 1.9.4.2 | 1.9.4.2 |  | 2025-02-25 17:00 | p | 497 |  | 2026-07-08 08:23
1206 | 5368 | NKJL1ZJN3KgUArkbA4qS | Normal | 3 | 1.9.4.2.4 | 1.9.4.2.4 |  | 2025-02-25 17:00 | p | 497 |  | 2026-07-08 08:23
1207 | 7260 | DPsh83rHAyIaiD8XYnO0 | Normal | 6 | 1.7.4.2.4 | 1.7.4.2.4 |  | 2025-02-19 17:00 | p | 496 |  | 2026-07-01 13:56
1208 | 7261 | isfym7y8CMuc9Vq3Mbcl | Normal | 1 | 1.7.4.2.5 | 1.7.4.2.5 |  | 2025-02-20 17:00 | p | 496 |  | 2026-07-02 11:08
1209 | 5375 | zkXPpJkHw8DPAtspwcmA | Summary | 124 | 1.9.4.4 | 1.9.4.4 |  | 2025-07-01 17:00 | p | 464 |  | 2026-10-09 11:51
1210 | 5376 | zSTdFwWI5FOaluV37lYS | Normal | 63 | 1.9.4.4.1 | 1.9.4.4.1 |  | 2025-07-01 17:00 | p | 464 |  | 2026-10-09 11:51
1211 | 5377 | Wv5w7NMYDRM71nE6dVi0 | Summary | 58 | 1.9.4.5 | 1.9.4.5 |  | 2025-06-09 17:00 | p | 3 |  | 2025-06-13 10:42
1212 | 5382 | VlX4WunUzdS7Nqvh5ftn | Normal | 20 | 1.9.4.5.5 | 1.9.4.5.5 |  | 2025-03-14 17:00 | p | 2 |  | 2025-03-17 08:25
1213 | 5383 | u1aficyBQ2O9A8MnpdfZ | Normal | 20 | 1.9.4.5.6 | 1.9.4.5.6 |  | 2025-04-11 17:00 | p | 6 |  | 2025-04-18 13:59
1214 | 5384 | d8i6C63YfOF3EovUl19W | Normal | 10 | 1.9.4.5.7 | 1.9.4.5.7 |  | 2025-04-25 17:00 | p | 6 |  | 2025-05-02 14:06
1215 | 5385 | ohwsmv9qOoV0RNzIdjJI | Normal | 15 | 1.9.4.5.8 | 1.9.4.5.8 |  | 2025-05-16 17:00 | p | 11 |  | 2025-05-28 10:53
1216 | 5386 | tSuemAovBYAaHNhFiwaF | Normal | 15 | 1.9.4.5.9 | 1.9.4.5.9 |  | 2025-06-09 17:00 | p | 3 |  | 2025-06-13 10:42
1217 | 5387 | 9gTKo9vjb1rQAbWcTOOW | Summary | 58 | 1.9.4.6 | 1.9.4.6 |  | 2025-06-09 17:00 | q | -6 |  | 2025-06-03 09:26
1218 | 5392 | TRJmldmXNRf3NwsZhgng | Normal | 20 | 1.9.4.6.5 | 1.9.4.6.5 |  | 2025-03-14 17:00 | q | -2 |  | 2025-03-12 13:55
1219 | 5393 | 3qvg7di25vdBD8UUvM1a | Normal | 20 | 1.9.4.6.6 | 1.9.4.6.6 |  | 2025-04-11 17:00 | q | -2 |  | 2025-04-09 13:03
1220 | 5394 | ungpeNo64cspVo3BuO9g | Normal | 10 | 1.9.4.6.7 | 1.9.4.6.7 |  | 2025-04-25 17:00 | q | -1 |  | 2025-04-24 13:29
1221 | 5395 | KZXvYFda88KgX9w7a3ES | Normal | 15 | 1.9.4.6.8 | 1.9.4.6.8 |  | 2025-05-16 17:00 | q | -2 |  | 2025-05-14 14:24
1222 | 5396 | FNjsTUKVT29tBcVlvaM6 | Normal | 15 | 1.9.4.6.9 | 1.9.4.6.9 |  | 2025-06-09 17:00 | q | -6 |  | 2025-06-03 09:26
1223 | 5397 | KGrMeH5y6HH9dj1tr8uB | Summary | 53 | 1.9.4.7 | 1.9.4.7 |  | 2025-08-25 17:00 | p | 10 |  | 2025-09-05 13:16
1224 | 5398 | EMMfZLgDhvN5O0lAfznQ | Normal | 15 | 1.9.4.7.1 | 1.9.4.7.1 |  | 2025-07-01 17:00 | p | 7 |  | 2025-07-09 13:26
1225 | 5399 | 5K7jeUOrZ3wka9S2O1Dn | Normal | 15 | 1.9.4.7.2 | 1.9.4.7.2 |  | 2025-07-23 17:00 | p | 6 |  | 2025-07-30 13:24
1226 | 5400 | I2IZFfCcy2hUSTtihPWq | Normal | 15 | 1.9.4.7.3 | 1.9.4.7.3 |  | 2025-08-13 17:00 | p | 6 |  | 2025-08-20 11:13
1227 | 5401 | WWZjxA63YxH38hnYmVKG | Normal | 8 | 1.9.4.7.4 | 1.9.4.7.4 |  | 2025-08-25 17:00 | p | 10 |  | 2025-09-05 13:16
1228 | 5402 | zDUD70mdAG3rcozejCwk | Summary | 15 | 1.9.4.8 | 1.9.4.8 |  | 2025-09-16 17:00 | p | 397 |  | 2026-10-19 13:36
1229 | 5403 | wP2WbhW6upJb7JmdzCw1 | Normal | 9 | 1.9.4.8.1 | 1.9.4.8.1 |  | 2025-09-08 17:00 | p | 10 |  | 2025-09-19 09:44
1230 | 5404 | UrewlDJ3J2c8Ueci7p9E | Normal | 6 | 1.9.4.8.2 | 1.9.4.8.2 |  | 2025-09-16 17:00 | p | 397 |  | 2026-10-19 13:36
1231 | 7264 | vNqQNKJIEgg8BiBzdWeI | Summary | 57 | 1.7.4.3.6 | 1.7.4.3.6 |  | 2025-07-01 17:00 | p | 448 |  | 2026-09-23 14:34
1232 | 7265 | uNFJkQaxxZ7oOYaM8QxX | Normal | 13 | 1.7.4.3.6.1 | 1.7.4.3.6.1 |  | 2025-04-29 17:00 | p | 449 |  | 2026-07-23 15:35
1233 | 7266 | y7TR6NxR4uOKxinxsnEt | Normal | 13 | 1.7.4.3.6.2 | 1.7.4.3.6.2 |  | 2025-05-16 17:00 | p | 451 |  | 2026-08-11 09:18
1234 | 7267 | f0BUmD79ZhKqjjzrwXUq | Normal | 13 | 1.7.4.3.6.3 | 1.7.4.3.6.3 |  | 2025-06-05 17:00 | p | 448 |  | 2026-08-28 16:14
1235 | 7268 | sP1zO7OhzT9CUKqdzecJ | Normal | 12 | 1.7.4.3.6.4 | 1.7.4.3.6.4 |  | 2025-06-24 17:00 | p | 448 |  | 2026-09-16 15:45
1236 | 7269 | 7v5GPnNw6yREyKfoeMiZ | Normal | 5 | 1.7.4.3.6.5 | 1.7.4.3.6.5 |  | 2025-07-01 17:00 | p | 448 |  | 2026-09-23 14:34
1237 | 7322 | XsHCl5GkwKVP3xy7r0jT | Summary | 85 | 1.7.5 | 1.7.5 |  | 2025-07-01 17:00 | q | -566 |  | 2023-12-13 10:24
1238 | 7528 | 8SnF5zCB4rJyZyQZLLZc | Normal | 8 | 1.7.5.1 | 1.7.5.1 |  | 2025-03-12 17:00 | q | -569 |  | 2023-08-21 13:24
1239 | 7529 | ugdLGMeRoSNQZE98ehwR | Normal | 8 | 1.7.5.2 | 1.7.5.2 |  | 2025-03-12 17:00 | q | -574 |  | 2023-08-16 13:45
1240 | 7530 | tZgNvNsEFqNHmYVKXpMu | Normal | 7 | 1.7.5.3 | 1.7.5.3 |  | 2025-03-21 17:00 | q | -569 |  | 2023-08-30 10:14
1241 | 7531 | WsQS39Ko43y2ykuRUNnk | Normal | 8 | 1.7.5.4 | 1.7.5.4 |  | 2025-04-02 17:00 | q | -566 |  | 2023-09-14 09:50
1242 | 7532 | tNKjUDGuH9lZvW14y0xJ | Normal | 22 | 1.7.5.5 | 1.7.5.5 |  | 2025-05-02 17:00 | q | -563 |  | 2023-10-17 11:23
1243 | 7533 | HKUUjAeDBFLcgj42uw3c | Normal | 19 | 1.7.5.6 | 1.7.5.6 |  | 2025-05-30 17:00 | q | -562 |  | 2023-11-15 13:09
1244 | 7534 | s7VTtgJqjYjf9pbLYcYj | Normal | 8 | 1.7.5.7 | 1.7.5.7 |  | 2025-06-11 17:00 | q | -562 |  | 2023-11-27 10:34
1245 | 7535 | uGgP1gHCy12zlVFcLeTG | Normal | 6 | 1.7.5.8 | 1.7.5.8 |  | 2025-06-20 17:00 | q | -567 |  | 2023-12-01 16:48
1246 | 7536 | kbIucnV7qsI0ZjxbK1cH | Normal | 6 | 1.7.5.9 | 1.7.5.9 |  | 2025-06-30 17:00 | q | -566 |  | 2023-12-12 13:17
1247 | 7537 | ZiOXL4e3BgetRuJ4aYKK | Normal | 1 | 1.7.5.10 | 1.7.5.10 |  | 2025-07-01 17:00 | q | -566 |  | 2023-12-13 10:24
1248 | 6688 | aKOlgm9Tw9oPXF0YCFLp | Summary | 911 | 1.11 | 1.11 |  | 2028-09-27 17:00 | q | -588 |  | 2027-02-17 10:32
1249 | 6689 | fEYxMDiPOAwjjU8zha5c | Normal | 396 | 1.11.1 | 1.11.1 |  | 2026-09-08 17:00 | q | -119 |  | 2026-05-12 11:12
1250 | 6690 | bopLkaAZbmZjIM9EGI6L | Normal | 532 | 1.11.2 | 1.11.2 |  | 2028-09-27 17:00 | q | -1017 |  | 2025-12-15 14:47
1251 | 6691 | xLErpFHjPEH3ifHRbBMY | Normal | 396 | 1.11.3 | 1.11.3 |  | 2026-09-08 17:00 | p | 161 |  | 2027-02-17 10:32
1252 | 6692 | g8WcEZ6I6SGdlePHrYPP | Normal | 248 | 1.11.4 | 1.11.4 |  | 2026-02-05 17:00 | p | 62 |  | 2026-04-09 16:49
1253 | 6695 | Bx0BPJ0BcPw49QEL7Psq | Normal | 313 | 1.11.8 | 1.11.8 |  | 2026-05-08 17:00 | q | -66 |  | 2026-03-03 16:50
1254 | 6696 | XbFIp383UbA72xJPH4hJ | Normal | 101 | 1.11.9 | 1.11.9 |  | 2025-07-03 17:00 | p | 28 |  | 2025-08-01 10:33
1255 | 6697 | gpkN7vTMpz4ZZxhDAmeL | Normal | 126 | 1.11.10 | 1.11.10 |  | 2025-08-08 17:00 | p | 32 |  | 2025-09-10 09:29
1256 | 6698 | eRsel9yyFaDkcYLZgvjC | Normal | 142 | 1.11.11 | 1.11.11 |  | 2025-09-02 17:00 | p | 42 |  | 2025-10-15 13:26
1257 | 6699 | k8943lu4TS9ZW2TcUvha | Normal | 256 | 1.11.12 | 1.11.12 |  | 2026-02-18 17:00 | p | 75 |  | 2026-05-05 10:14
1258 | 7376 | FfEUU5kpALOu6FlmjosD | Normal | 396 | 1.10.3 | 1.10.3 |  | 2026-09-08 17:00 | p | 58 |  | 2026-11-06 16:05
1259 | 7378 | YjoFZZooPnFRzsk2Ba2E | Normal | 288 | 1.10.6 | 1.10.6 |  | 2026-04-03 17:00 | p | 138 |  | 2026-08-20 08:40
1260 | 7379 | 7GajZBAFakrGWC1WlgE6 | Normal | 142 | 1.10.14 | 1.10.14 |  | 2025-09-02 17:00 | q | -25 |  | 2025-08-08 10:53
1261 | 7380 | wkyoOF6gHS9pA0Dm9pZY | Normal | 140 | 1.10.17 | 1.10.17 |  | 2025-08-28 17:00 | p | 0 |  | 2025-08-29 09:36
1262 | 7131 | XTX9Wl5SzTxAD1rtsh9U | Summary | 0 | 1.10 | 1.10 |  | 2027-01-01 08:05 | p | 496 |  | 2028-05-11 14:47
1263 | 156 | 0RXSkgYJdrs7AeQvgU3w | Milestone | 0 | 1.10.24 | 1.10.24 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
1264 | 157 | DYCfhHgWVvjY4WPSrw6q | Milestone | 0 | 1.10.25 | 1.10.25 |  | 2026-10-08 16:58 | p | 580 |  | 2028-05-11 14:47
1265 | 7107 | fjlRoMsMUGjOnNWoUkGJ | Milestone | 0 | 1.10.16 | 1.10.16 |  | 2027-01-01 08:05 | p | 5 |  | 2027-01-06 08:12
1266 | 7108 | wFwSqsIrP0eolc7owrIn | Milestone | 0 | 1.10.3 | 1.10.3 |  | 2025-04-10 17:00 | q | -3 |  | 2025-04-07 10:08
1267 | 7110 | fycPVr34q6lr2y2bEJNl | Milestone | 0 | 1.10.9 | 1.10.9 |  | 2025-08-05 17:00 | p | 35 |  | 2025-09-10 14:26
1268 | 7111 | gs1r9nT3BBBdW42nHT47 | Milestone | 0 | 1.10.13 | 1.10.13 |  | 2025-10-16 17:00 | p | 31 |  | 2025-11-17 09:47
1269 | 7112 | a270fhhuENq55tFKO8IB | Milestone | 0 | 1.10.10 | 1.10.10 |  | 2025-11-28 17:00 | p | 23 |  | 2025-12-22 09:42
1270 | 7114 | pZqvbi91bBhqyjB86evl | Milestone | 0 | 1.10.2 | 1.10.2 |  | 2026-03-06 17:00 | p | 20 |  | 2026-03-27 11:53
1271 | 7115 | mxRJVREYCLlOZtWGohdT | Milestone | 0 | 1.10.8 | 1.10.8 |  | 2026-04-03 17:00 | p | 9 |  | 2026-04-13 11:49
1272 | 7116 | 4gFjRlWXKNF16b9sFMXr | Milestone | 0 | 1.10.11 | 1.10.11 |  | 2025-09-24 17:00 | q | -170 |  | 2025-04-07 15:53
1273 | 7117 | zFlqKdf38AVahGy9Q9X8 | Milestone | 0 | 1.10.12 | 1.10.12 |  | 2026-01-14 17:00 | q | -8 |  | 2026-01-06 13:47
1274 | 7118 | 6jNHf85fMsjQD6qn9QnY | Milestone | 0 | 1.10.14 | 1.10.14 |  | 2025-12-15 17:00 | p | 27 |  | 2026-01-12 08:25
1275 | 7119 | OQnmDeJwrgb4ibYKrZjo | Milestone | 0 | 1.10.15 | 1.10.15 |  | 2025-10-01 17:00 | q | -586 |  | 2024-02-23 09:07
1276 | 7120 | ewfCDE69jjk4Zb5M5CES | Milestone | 0 | 1.10.4 | 1.10.4 |  | 2025-04-02 17:00 | q | -6 |  | 2025-03-27 13:16
1277 | 7121 | V4W6CQQo6lTjRlhYdPDq | Milestone | 0 | 1.10.5 | 1.10.5 |  | 2025-05-19 17:00 | p | 34 |  | 2025-06-23 10:29
1278 | 7122 | ZQwX0qpiGy3bERfpXjQ0 | Milestone | 0 | 1.10.6 | 1.10.6 |  | 2025-04-07 17:00 | p | 27 |  | 2025-05-05 10:48
1279 | 7123 | 0fpNMQTy9Zfk1YAC7GK2 | Milestone | 0 | 1.10.7 | 1.10.7 |  | 2025-04-01 17:00 | q | -6 |  | 2025-03-26 11:36
1280 | 7124 | yYQOOagkBr46kWICPuG6 | Milestone | 0 | 1.10.17 | 1.10.17 |  | 2025-09-11 17:00 | q | -2814 |  | 2017-12-28 16:20
1281 | 7125 | a4xeGKWGk9YyWLffVRQZ | Milestone | 0 | 1.10.18 | 1.10.18 |  | 2025-10-08 17:00 | q | -2809 |  | 2018-01-29 14:01
1282 | 7126 | XIH51zzlt2AXqf8IkYxf | Milestone | 0 | 1.10.19 | 1.10.19 |  | 2025-11-04 17:00 | q | -2812 |  | 2018-02-22 16:01
1283 | 7129 | kvNY0frGkARL99AbSHw0 | Milestone | 0 | 1.10.22 | 1.10.22 |  | 2025-05-19 17:00 | p | 1 |  | 2025-05-21 11:08

## Late-Start
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Late Start - 1015 (48%) | Late Start - 1015 (48%) | Late Start - 1015 (48%) | Late Start - 1015 (48%) | Late Start - 1015 (48%) | Late Start - 1015 (48%) | Late Start - 1015 (48%) | Late Start - 1015 (48%) | Late Start - 1015 (48%) | Late Start - 1015 (48%) | Late Start - 1015 (48%) | Late Start - 1015 (48%) | Late Start - 1015 (48%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 152 | QJ29ZvAvtEjBcpqHDer1 | Milestone | 0 | 1.2.3 | 1.2.3 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 10:06
2 | 155 | 1yu6CrDX9QU5hWE1UWMV | Milestone | 0 | 1.2.7.11 | 1.2.7.11 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
3 | 166 | KkWbk0R1FXz2L56lHFvV | Normal | 2 | 1.2.7.4 | 1.2.7.4 |  | 2025-11-10 08:00 | p | 46 |  | 2025-12-26 15:15
4 | 6618 | LspmB73Oe2b9O1GVbm64 | Milestone | 0 | 1.2.7.2 | 1.2.7.2 |  | 2027-04-13 08:00 | p | 178 |  | 2027-10-08 16:52
5 | 6338 | whnkqeDzsaW1H7xphaZA | Normal | 49 | 1.2.7.3.4 | 1.2.7.3.4 |  | 2025-07-08 08:00 | p | 41 |  | 2025-08-18 09:41
6 | 6640 | QUv6m7GotPkUb98mhJX7 | Normal | 14 | 1.2.7.3.6 | 1.2.7.3.6 |  | 2025-10-21 08:00 | p | 45 |  | 2025-12-05 10:57
7 | 6872 | SjyWialEYK436pEnV5Nr | Normal | 1 | 1.2.7.5 | 1.2.7.5 |  | 2026-03-18 08:00 | q | -34 |  | 2026-02-11 15:00
8 | 6874 | 1XFpbhK6U752FQe8voXZ | Normal | 1 | 1.2.7.6 | 1.2.7.6 |  | 2026-03-05 08:00 | q | -33 |  | 2026-01-30 09:38
9 | 6878 | VU7w4voCV7rMMsz4AnPW | Normal | 1 | 1.2.7.10 | 1.2.7.10 |  | 2026-09-01 08:00 | q | 0 |  | 2026-08-31 16:11
10 | 6879 | Vbp0cBOXY9azJeyTE4S4 | Normal | 3 | 1.2.7.7 | 1.2.7.7 |  | 2026-04-02 08:00 | q | -34 |  | 2026-02-26 10:27
11 | 6880 | ZuauWvCPNW7n2NMscMO2 | Normal | 4 | 1.2.7.8 | 1.2.7.8 |  | 2026-06-17 08:00 | q | -12 |  | 2026-06-04 16:29
12 | 6881 | XekYY8n1P4vELtk4BUks | Normal | 1 | 1.2.7.9 | 1.2.7.9 |  | 2026-09-01 08:00 | p | 0 |  | 2026-09-01 08:05
13 | 7185 | 9DFzvUnK8UE41lq7OD40 | Milestone | 0 | 1.2.7.1 | 1.2.7.1 |  | 2027-02-25 08:00 | p | 182 |  | 2027-08-26 13:16
14 | 7550 | fUEnUBwdI1z3bgOngjaQ | Milestone | 0 | 1.2.7.5 | 1.2.7.5 |  | 2025-11-13 08:00 | p | 47 |  | 2025-12-30 16:50
15 | 5294 | A0MDYkkQxesjEWQub0UM | Milestone | 0 | 1.2.8.3 | 1.2.8.3 |  | 2025-11-13 08:00 | p | 47 |  | 2025-12-30 16:50
16 | 180 | 9Vp3PBZnh9TpV8TGBWRG | Milestone | 0 | 1.2.10.14 | 1.2.10.14 |  | 2028-09-20 08:00 | p | 203 |  | 2029-04-11 11:27
17 | 193 | nJh7oj8wCJYW8hyepdLI | Milestone | 0 | 1.2.10.12 | 1.2.10.12 |  | 2028-04-03 08:00 | p | 186 |  | 2028-10-06 15:49
18 | 194 | wTcNF86mfD2cPQPmQB1c | Milestone | 0 | 1.2.10.13 | 1.2.10.13 |  | 2028-04-03 08:00 | p | 186 |  | 2028-10-06 15:49
19 | 7132 | osdxrWYmqQZxyGZXe9Pr | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 2027-04-13 08:00 | p | 178 |  | 2027-10-08 16:52
20 | 7546 | tdocr3pqURBYHZWcAyMG | Normal | 1 | 1.2.10.12 | 1.2.10.12 |  | 2027-04-12 08:00 | p | 179 |  | 2027-10-08 10:10
21 | 7547 | 2p5uMAQ0v8mT9pq4KeWp | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 2027-04-13 08:00 | p | 178 |  | 2027-10-08 16:52
22 | 7548 | TdNnLE8G4vf1vBjggzLw | Normal | 1 | 1.2.10.15 | 1.2.10.15 |  | 2027-04-09 08:00 | p | 181 |  | 2027-10-07 09:36
23 | 7549 | yUAt6Fi3Vichq9Ai1DSh | Normal | 1 | 1.2.10.13 | 1.2.10.13 |  | 2027-04-08 08:00 | p | 181 |  | 2027-10-06 09:14
24 | 195 | jWoM7YMyhsN7uWtVDNIl | Summary | 276 | 1.2.11 | 1.2.11 |  | 2027-07-12 08:00 | p | 200 |  | 2028-01-28 14:32
25 | 196 | kzYOxx4jS6vhIcTyxNFn | Milestone | 0 | 1.2.11.11 | 1.2.11.11 |  | 2028-07-31 08:00 | p | 210 |  | 2029-02-26 09:11
26 | 197 | LZAvhCOF77OBkAngJSDi | Milestone | 0 | 1.2.11.1 | 1.2.11.1 |  | 2027-07-12 08:00 | p | 200 |  | 2028-01-28 14:32
27 | 198 | X7Nxs9NuQXJ5Bf6aQwVp | Milestone | 0 | 1.2.11.2 | 1.2.11.2 |  | 2027-07-23 13:00 | p | 201 |  | 2028-02-09 14:40
28 | 199 | TiaYdQ98Ovd3qBAfSAyG | Milestone | 0 | 1.2.11.3 | 1.2.11.3 |  | 2027-08-06 08:00 | p | 200 |  | 2028-02-22 14:55
29 | 200 | yynHcCtrZd0Ye6iQJb2E | Milestone | 0 | 1.2.11.4 | 1.2.11.4 |  | 2027-09-01 13:00 | p | 200 |  | 2028-03-20 09:05
30 | 202 | mjF0YLun5LIdlxtu3zFl | Milestone | 0 | 1.2.11.5 | 1.2.11.5 |  | 2028-05-25 08:00 | p | 208 |  | 2028-12-19 10:21
31 | 203 | 2a1x42QofxcVsgjcXtkr | Milestone | 0 | 1.2.11.6 | 1.2.11.6 |  | 2027-07-12 08:00 | p | 200 |  | 2028-01-28 14:32
32 | 204 | 8T22gllTunmLl2jY7IMk | Milestone | 0 | 1.2.11.7 | 1.2.11.7 |  | 2027-07-23 13:00 | p | 201 |  | 2028-02-09 14:40
33 | 205 | dm3U5Xjvi5rN2LqWegXW | Milestone | 0 | 1.2.11.8 | 1.2.11.8 |  | 2027-08-06 08:00 | p | 200 |  | 2028-02-22 14:55
34 | 206 | ZOAcdJHtChBG5MUjo5uw | Milestone | 0 | 1.2.11.9 | 1.2.11.9 |  | 2027-09-01 13:00 | p | 200 |  | 2028-03-20 09:05
35 | 209 | 0FNuAiL5ZzPZSZ3dZfoV | Milestone | 0 | 1.2.11.10 | 1.2.11.10 |  | 2028-05-25 08:00 | p | 208 |  | 2028-12-19 10:21
36 | 6077 | 9YjbRTuPDmKPhAucMUDE | Milestone | 0 | 1.2.6 | 1.2.6 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
37 | 7015 | U0mup1noPd6mH1CxWGtr | Milestone | 0 | 1.2.5 | 1.2.5 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
38 | 7016 | pVOP21cemlwRUbhUeRME | Milestone | 0 | 1.2.4 | 1.2.4 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
39 | 150 | 7cu6yvdJV8ndF0CYMHk8 | Milestone | 0 | 1.1 | 1.1 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 10:06
40 | 436 | OGXVzK31PKUn8DxCdn94 | Normal | 33 | 1.3.3.2.10 | 1.3.3.2.10 |  | 2025-05-19 08:00 | p | 42 |  | 2025-06-30 08:54
41 | 428 | pxWL5EoMWeaDmapfAV7m | Normal | 2 | 1.3.3.4.2 | 1.3.3.4.2 |  | 2025-11-10 08:00 | p | 46 |  | 2025-12-26 15:15
42 | 3859 | xrpLG6wlwOL4sRwHPU5B | Normal | 28 | 1.3.2.1.2.2.2 | 1.3.2.1.2.2.2 |  | 2026-02-02 08:00 | q | -32 |  | 2025-12-31 09:33
43 | 3861 | rvfyADOJtzNcPT3VL85f | Normal | 100 | 1.3.2.1.2.2.3 | 1.3.2.1.2.2.3 |  | 2026-03-13 08:00 | q | -28 |  | 2026-02-12 08:10
44 | 3862 | FUtleP4nAJHYxzLOWKZH | Normal | 20 | 1.3.2.1.2.2.4 | 1.3.2.1.2.2.4 |  | 2026-08-05 08:00 | p | 1 |  | 2026-08-06 09:02
45 | 3864 | kkmwKYrSq6DehQmbGkxo | Summary | 90 | 1.3.2.1.2.3.2 | 1.3.2.1.2.3.2 |  | 2026-04-24 08:00 | p | 5 |  | 2026-04-29 08:13
46 | 3865 | ZK3GDclfde20Vh8DU71K | Normal | 30 | 1.3.2.1.2.3.2.1 | 1.3.2.1.2.3.2.1 |  | 2026-04-24 08:00 | p | 5 |  | 2026-04-29 08:13
47 | 3866 | 8Zrc7ItBhrTjO1TWxqmf | Normal | 20 | 1.3.2.1.2.3.2.2 | 1.3.2.1.2.3.2.2 |  | 2026-06-08 08:00 | p | 4 |  | 2026-06-12 15:37
48 | 3867 | l8TRHVr9p6bfQBwzbTty | Normal | 5 | 1.3.2.1.2.3.2.5 | 1.3.2.1.2.3.2.5 |  | 2026-08-05 08:00 | p | 1 |  | 2026-08-06 10:22
49 | 3868 | NCkZSbtMfUxIg95lxXXn | Normal | 10 | 1.3.2.1.2.3.2.6 | 1.3.2.1.2.3.2.6 |  | 2026-08-12 08:00 | p | 1 |  | 2026-08-13 11:55
50 | 3869 | wbVbYxDNomEEsv0XDKnQ | Normal | 5 | 1.3.2.1.2.3.2.7 | 1.3.2.1.2.3.2.7 |  | 2026-08-26 08:00 | p | 0 |  | 2026-08-26 08:10
51 | 6562 | Z3AfJmLBpOLyJb1GhvwC | Normal | 10 | 1.3.2.1.2.3.2.3 | 1.3.2.1.2.3.2.3 |  | 2026-07-08 08:00 | p | 0 |  | 2026-07-08 10:55
52 | 6563 | 7FPcbor42GN7O6Ym4IZM | Normal | 10 | 1.3.2.1.2.3.2.4 | 1.3.2.1.2.3.2.4 |  | 2026-07-22 08:00 | p | 0 |  | 2026-07-22 08:12
53 | 7192 | rcBSOCAYFUxP7jsyoqGw | Normal | 11 | 1.3.2.3.2.1.1.2 | 1.3.2.3.2.1.1.2 |  | 2025-07-09 08:00 | p | 56 |  | 2025-09-03 15:15
54 | 7194 | mB0uoGZ1D1fuFzk350Kb | Normal | 30 | 1.3.2.3.2.1.2.1 | 1.3.2.3.2.1.2.1 |  | 2025-07-24 08:00 | p | 55 |  | 2025-09-17 08:48
55 | 7200 | 7Va2LPPEsZrLZmgpV2qc | Summary | 19 | 1.3.2.3.2.1.4 | 1.3.2.3.2.1.4 |  | 2025-09-05 08:00 | p | 46 |  | 2025-10-21 10:48
56 | 7201 | UKbpgMkpfrIPVoEOJEeO | Normal | 10 | 1.3.2.3.2.1.4.1 | 1.3.2.3.2.1.4.1 |  | 2025-09-05 08:00 | p | 46 |  | 2025-10-21 10:48
57 | 7202 | vy1jnuopIHJe5PhTsUNw | Normal | 5 | 1.3.2.3.2.1.4.2 | 1.3.2.3.2.1.4.2 |  | 2025-09-19 08:00 | p | 45 |  | 2025-11-03 16:13
58 | 7203 | KqVHIBvrHNAu5GlarotD | Normal | 3 | 1.3.2.3.2.1.4.3 | 1.3.2.3.2.1.4.3 |  | 2025-09-26 08:00 | p | 47 |  | 2025-11-12 09:52
59 | 7204 | BUAmcwglNtP3GEkJsPLR | Normal | 1 | 1.3.2.3.2.1.4.4 | 1.3.2.3.2.1.4.4 |  | 2025-10-01 08:00 | p | 47 |  | 2025-11-17 10:33
60 | 7207 | 51ZGrscW6XrNzeOMbLyw | Normal | 5 | 1.3.2.3.2.2.2 | 1.3.2.3.2.2.2 |  | 2025-09-19 08:00 | p | 47 |  | 2025-11-05 10:49
61 | 7208 | 5Vu53Z23NG8K3uSzUcYA | Normal | 3 | 1.3.2.3.2.2.3 | 1.3.2.3.2.2.3 |  | 2025-09-26 08:00 | p | 45 |  | 2025-11-10 17:00
62 | 7209 | r8OmtZddpdGbVxNEynIO | Normal | 1 | 1.3.2.3.2.2.4 | 1.3.2.3.2.2.4 |  | 2025-10-01 08:00 | p | 47 |  | 2025-11-17 11:02
63 | 7212 | IA5BwO4PzPuXs5yI3XzH | Normal | 5 | 1.3.2.3.2.3.2 | 1.3.2.3.2.3.2 |  | 2025-08-28 08:00 | p | 43 |  | 2025-10-10 15:23
64 | 7213 | GkAhONTSL0EMIVzc5bXh | Normal | 3 | 1.3.2.3.2.3.3 | 1.3.2.3.2.3.3 |  | 2025-09-05 08:00 | p | 41 |  | 2025-10-16 16:34
65 | 7214 | ysGFXohNyFRFQ06jmkjW | Normal | 1 | 1.3.2.3.2.3.4 | 1.3.2.3.2.3.4 |  | 2025-09-10 08:00 | p | 42 |  | 2025-10-22 08:21
66 | 7219 | tMHxEODKuKminmE9Mjg5 | Normal | 1 | 1.3.2.3.2.4.4 | 1.3.2.3.2.4.4 |  | 2025-08-18 08:00 | q | -187 |  | 2025-02-12 08:00
67 | 7220 | nvywSXdnd0LSUGSiB3or | Normal | 10 | 1.3.2.3.2.4.5 | 1.3.2.3.2.4.5 |  | 2025-08-19 08:00 | p | 35 |  | 2025-09-23 09:25
68 | 7221 | PYoR7OoHLcblZDJJ1hTC | Normal | 20 | 1.3.2.3.2.4.6 | 1.3.2.3.2.4.6 |  | 2025-09-03 08:00 | p | 35 |  | 2025-10-08 16:47
69 | 7222 | W1KVKgORO9KqmU1uQFqG | Normal | 1 | 1.3.2.3.2.4.7 | 1.3.2.3.2.4.7 |  | 2025-10-01 08:00 | p | 47 |  | 2025-11-17 11:04
70 | 7228 | SSqxRWtJ8NkhLwkx3Zp5 | Normal | 15 | 1.3.2.3.2.5.5 | 1.3.2.3.2.5.5 |  | 2025-09-11 08:00 | p | 42 |  | 2025-10-23 08:32
71 | 7514 | 4jhJaLUHxegkfPxUyChC | Normal | 15 | 1.3.2.3.2.5.9 | 1.3.2.3.2.5.9 |  | 2025-09-29 08:00 | p | 46 |  | 2025-11-14 14:47
72 | 7231 | Kz2H44CrN943Xn6RI0Et | Summary | 19 | 1.3.2.3.3 | 1.3.2.3.3 |  | 2025-09-16 08:00 | p | 44 |  | 2025-10-30 15:32
73 | 7232 | cCMYeGs7uzTIiiDhvAui | Summary | 12 | 1.3.2.3.3.1 | 1.3.2.3.3.1 |  | 2025-09-16 08:00 | p | 44 |  | 2025-10-30 15:32
74 | 7233 | rgerXXfH5cOVWHlSbXtk | Normal | 2 | 1.3.2.3.3.1.1 | 1.3.2.3.3.1.1 |  | 2025-09-26 08:00 | p | 47 |  | 2025-11-12 11:01
75 | 7234 | 4Nk8AWONEAABjENRSl4s | Normal | 3 | 1.3.2.3.3.1.2 | 1.3.2.3.3.1.2 |  | 2025-09-25 08:00 | p | 43 |  | 2025-11-07 16:07
76 | 7235 | uR7e5eYUOS8ur8CkZgir | Normal | 2 | 1.3.2.3.3.1.3 | 1.3.2.3.3.1.3 |  | 2025-09-30 08:00 | p | 45 |  | 2025-11-14 09:00
77 | 7236 | OqdHv6QLhEyFdmarh5Mg | Normal | 5 | 1.3.2.3.3.1.4 | 1.3.2.3.3.1.4 |  | 2025-09-25 08:00 | p | 43 |  | 2025-11-07 11:42
78 | 7237 | xLl9f1S8pVLgozw4LZw4 | Normal | 10 | 1.3.2.3.3.1.5 | 1.3.2.3.3.1.5 |  | 2025-09-16 08:00 | p | 48 |  | 2025-11-03 09:14
79 | 7238 | hj0QAuvemNr4BSx0wqCM | Normal | 10 | 1.3.2.3.3.1.6 | 1.3.2.3.3.1.6 |  | 2025-09-16 08:00 | p | 44 |  | 2025-10-30 15:32
80 | 7239 | sGRMuNmZsu5Ap3rRR6Ja | Normal | 2 | 1.3.2.3.3.1.7 | 1.3.2.3.3.1.7 |  | 2025-09-30 08:00 | p | 45 |  | 2025-11-14 14:54
81 | 7240 | jJgg05qz3M4QbDAQ4nmn | Summary | 7 | 1.3.2.3.3.2 | 1.3.2.3.3.2 |  | 2025-10-02 08:00 | p | 47 |  | 2025-11-18 11:12
82 | 7241 | RP09WyAKLetAyeWXIWbd | Normal | 1 | 1.3.2.3.3.2.1 | 1.3.2.3.3.2.1 |  | 2025-10-02 08:00 | p | 47 |  | 2025-11-18 11:12
83 | 7242 | PNiOufePi0cnwKsaAHa8 | Normal | 3 | 1.3.2.3.3.2.2 | 1.3.2.3.3.2.2 |  | 2025-10-03 08:00 | p | 47 |  | 2025-11-19 13:37
84 | 7243 | nppwsC1hz1MTRepHit5q | Normal | 3 | 1.3.2.3.3.2.3 | 1.3.2.3.3.2.3 |  | 2025-10-08 08:00 | p | 47 |  | 2025-11-24 10:39
85 | 7244 | FpvbIzqyAjmrguHRtjoA | Summary | 68 | 1.3.2.3.4 | 1.3.2.3.4 |  | 2025-10-14 08:00 | p | 45 |  | 2025-11-28 15:44
86 | 7245 | ysJ2Wz17vAaH50NFOd3r | Normal | 2 | 1.3.2.3.4.1 | 1.3.2.3.4.1 |  | 2025-10-15 08:00 | p | 44 |  | 2025-11-28 15:44
87 | 7246 | w8OYvCOBO1azAOar59yv | Normal | 3 | 1.3.2.3.4.2 | 1.3.2.3.4.2 |  | 2025-10-14 08:00 | p | 45 |  | 2025-11-28 16:17
88 | 7247 | QmLDbLdk9YgltF6FQxKi | Normal | 2 | 1.3.2.3.4.3 | 1.3.2.3.4.3 |  | 2025-10-17 08:00 | p | 47 |  | 2025-12-03 11:13
89 | 7248 | nqyBToLUXvLl91VDFcK9 | Summary | 20 | 1.3.2.3.4.4 | 1.3.2.3.4.4 |  | 2026-05-12 08:00 | q | -5 |  | 2026-05-06 08:49
90 | 7249 | T3rEQsXy5TFYVzdnmRkQ | Normal | 20 | 1.3.2.3.4.4.1 | 1.3.2.3.4.4.1 |  | 2026-05-12 08:00 | q | -3 |  | 2026-05-08 08:12
91 | 7250 | G5mdz8DmOa8TGNlmxmOk | Normal | 20 | 1.3.2.3.4.4.2 | 1.3.2.3.4.4.2 |  | 2026-05-12 08:00 | q | -5 |  | 2026-05-06 08:49
92 | 7251 | p2IEwFFq1YxDgQwaqReT | Summary | 48 | 1.3.2.3.4.5 | 1.3.2.3.4.5 |  | 2026-06-10 08:00 | q | -1 |  | 2026-06-08 08:53
93 | 7252 | R4hlQqYwslHcXudIUORM | Normal | 20 | 1.3.2.3.4.5.1 | 1.3.2.3.4.5.1 |  | 2026-06-10 08:00 | q | -1 |  | 2026-06-08 08:53
94 | 7253 | 5Q6OCjUddDwnqpg2shNG | Normal | 5 | 1.3.2.3.4.5.2 | 1.3.2.3.4.5.2 |  | 2026-07-10 08:00 | p | 0 |  | 2026-07-10 13:13
95 | 7254 | aZsc8OQGYCtOtLNUDl4p | Normal | 7 | 1.3.2.3.4.5.3 | 1.3.2.3.4.5.3 |  | 2026-07-17 08:00 | p | 0 |  | 2026-07-17 13:52
96 | 7255 | GiGIxdlKVFOGW1rlVkpg | Normal | 5 | 1.3.2.3.4.5.4 | 1.3.2.3.4.5.4 |  | 2026-07-28 08:00 | p | 0 |  | 2026-07-28 09:35
97 | 7256 | ZTFxKau19KKCcFlUDIYg | Normal | 7 | 1.3.2.3.4.5.5 | 1.3.2.3.4.5.5 |  | 2026-08-04 08:00 | p | 0 |  | 2026-08-04 09:40
98 | 7257 | EmkT3sq6aGy3vx96JSsX | Normal | 3 | 1.3.2.3.4.5.6 | 1.3.2.3.4.5.6 |  | 2026-08-13 08:00 | p | 0 |  | 2026-08-13 13:00
99 | 7258 | PBxke5bv0Yk6xXbQcvVe | Normal | 1 | 1.3.2.3.4.5.7 | 1.3.2.3.4.5.7 |  | 2026-08-18 08:00 | q | 0 |  | 2026-08-17 14:54
100 | 632 | tuv9OmQcJHKkVCVrbrrv | Normal | 6 | 1.5.6.6.2.8 | 1.5.6.6.2.8 |  | 2025-06-17 10:00 | q | -31 |  | 2025-05-16 15:04
101 | 633 | FgJ5XjjThZN85XQOJ0nJ | Normal | 21 | 1.5.6.6.2.10 | 1.5.6.6.2.10 |  | 2025-07-03 10:00 | q | -30 |  | 2025-06-03 08:06
102 | 634 | o4DRQRcsScdVmCSXNbxF | Normal | 10 | 1.5.6.6.2.9 | 1.5.6.6.2.9 |  | 2025-08-04 10:00 | q | -33 |  | 2025-07-01 14:40
103 | 635 | ztvy5zkS4z9HirKgvHGY | Normal | 20 | 1.5.6.6.2.11 | 1.5.6.6.2.11 |  | 2025-08-15 15:00 | q | -29 |  | 2025-07-16 16:33
104 | 636 | ZpIfqMwIaczq2BqznW2q | Normal | 6 | 1.5.6.6.2.12 | 1.5.6.6.2.12 |  | 2025-09-15 15:00 | q | -35 |  | 2025-08-11 13:22
105 | 637 | 3VAZwvp2NS6usl0wrvOM | Normal | 7 | 1.5.6.6.2.13 | 1.5.6.6.2.13 |  | 2025-09-23 15:00 | q | -33 |  | 2025-08-21 10:47
106 | 638 | 34zoFClD9RS7gLTCPZs0 | Normal | 5 | 1.5.6.6.2.14 | 1.5.6.6.2.14 |  | 2025-10-02 15:00 | q | -30 |  | 2025-09-02 13:54
107 | 640 | 10AmMHkCz4b8n0xqbyCt | Normal | 5 | 1.5.6.6.2.16 | 1.5.6.6.2.16 |  | 2025-10-09 15:00 | q | -30 |  | 2025-09-09 13:50
108 | 641 | KUqcSNVxncHPLVJNV5ca | Normal | 2 | 1.5.6.6.2.17 | 1.5.6.6.2.17 |  | 2025-10-17 15:00 | q | -31 |  | 2025-09-16 08:44
109 | 642 | chCwawHUqn0ea2ArCnKB | Normal | 0 | 1.5.6.6.2.18 | 1.5.6.6.2.18 |  | 2025-10-21 10:00 | q | -34 |  | 2025-09-17 09:59
110 | 643 | xZBRzE3QVYmQCjnzxLQv | Normal | 4 | 1.5.6.6.2.19 | 1.5.6.6.2.19 |  | 2025-10-21 15:00 | q | -34 |  | 2025-09-17 14:21
111 | 644 | tUTeQ74YpmkuuOiouSXU | Normal | 5 | 1.5.6.6.2.20 | 1.5.6.6.2.20 |  | 2025-10-27 15:00 | q | -33 |  | 2025-09-23 16:34
112 | 645 | mSrjcTZmK12EdJmOEYFi | Normal | 1 | 1.5.6.6.2.21 | 1.5.6.6.2.21 |  | 2025-11-03 15:00 | q | -34 |  | 2025-09-30 11:49
113 | 646 | Haue3rYYySw3jbXWnBeq | Normal | 3 | 1.5.6.6.3 | 1.5.6.6.3 |  | 2025-11-04 15:00 | q | -34 |  | 2025-10-01 10:53
114 | 647 | 6jlP0Y4QQ5KPQWxvolLg | Normal | 1 | 1.5.6.6.4 | 1.5.6.6.4 |  | 2025-11-07 15:00 | q | -31 |  | 2025-10-07 08:27
115 | 656 | lzPFAx9Fh8cDxyQ3uxFX | Normal | 1 | 1.5.6.6.5.3 | 1.5.6.6.5.3 |  | 2025-11-10 15:00 | q | -33 |  | 2025-10-08 08:40
116 | 657 | nePaKBbqDo6OltylvukE | Summary | 14 | 1.5.6.6.5.4 | 1.5.6.6.5.4 |  | 2025-11-13 08:00 | q | -34 |  | 2025-10-09 11:05
117 | 658 | PyBKEPMZMe2YeOC66yut | Normal | 11 | 1.5.6.6.5.4.1 | 1.5.6.6.5.4.1 |  | 2025-11-13 08:00 | q | -34 |  | 2025-10-09 11:05
118 | 664 | H1KB0K8mM12Opvc4oDP1 | Normal | 3 | 1.5.6.6.5.4.2 | 1.5.6.6.5.4.2 |  | 2025-12-01 08:00 | q | -37 |  | 2025-10-24 14:37
119 | 665 | FIEbexlYHnOcZkEBs7WM | Normal | 5 | 1.5.6.6.5.5 | 1.5.6.6.5.5 |  | 2025-12-05 08:00 | q | -34 |  | 2025-10-31 09:06
120 | 666 | OcAHNnZWZgiwxfUiheGU | Normal | 5 | 1.5.6.6.5.6 | 1.5.6.6.5.6 |  | 2025-12-12 08:00 | q | -34 |  | 2025-11-07 08:14
121 | 667 | HPj21Hyun1nWvxJOQMhf | Normal | 28 | 1.5.6.6.5.7 | 1.5.6.6.5.7 |  | 2025-12-19 08:00 | q | -35 |  | 2025-11-13 15:55
122 | 671 | ZM52W2kHJJCM7052Da3J | Normal | 2 | 1.5.6.5.2 | 1.5.6.5.2 |  | 2025-12-02 08:00 | q | -34 |  | 2025-10-28 08:51
123 | 672 | AcRvLPQ7WrNfvcLBOWzV | Normal | 1 | 1.5.6.5.3 | 1.5.6.5.3 |  | 2025-12-04 08:00 | q | -35 |  | 2025-10-29 15:37
124 | 1457 | W1XQ7yoZAeSgm7UftoXN | Normal | 1 | 1.5.5.1.2 | 1.5.5.1.2 |  | 2026-07-14 08:00 | q | -515 |  | 2025-02-14 08:00
125 | 1458 | W2l89btZYbaZZjxZTUR4 | Normal | 12 | 1.5.5.1.3 | 1.5.5.1.3 |  | 2026-07-15 08:00 | q | -4 |  | 2026-07-10 10:29
126 | 1459 | MxsNofofvf6CR0hsGInx | Normal | 1 | 1.5.5.1.4 | 1.5.5.1.4 |  | 2026-07-31 08:00 | q | -2 |  | 2026-07-28 11:54
127 | 1469 | MZooHRTMNCHrNy0nPaCQ | Normal | 1 | 1.5.5.1.6 | 1.5.5.1.6 |  | 2026-07-20 08:00 | q | -4 |  | 2026-07-15 11:49
128 | 1470 | PdTqfNwd2IKBXe26tWkB | Normal | 1 | 1.5.5.1.8 | 1.5.5.1.8 |  | 2026-08-03 08:00 | q | -4 |  | 2026-07-29 11:36
129 | 1471 | FsiT4ZMTOq9hGqZQQdYf | Normal | 11 | 1.5.5.1.9 | 1.5.5.1.9 |  | 2026-08-04 08:00 | q | -4 |  | 2026-07-30 16:33
130 | 1472 | KG0YDAdikr58WjA79FVb | Normal | 9 | 1.5.5.1.10 | 1.5.5.1.10 |  | 2026-08-19 08:00 | p | 0 |  | 2026-08-19 13:51
131 | 4584 | H2uIo7s6dGmX6mrjT7jd | Normal | 9 | 1.5.5.1.7 | 1.5.5.1.7 |  | 2026-07-21 08:00 | q | -4 |  | 2026-07-16 13:51
132 | 3945 | bJfaWXH8yBacWp0eqnXx | Normal | 1 | 1.5.4.3 | 1.5.4.3 |  | 2025-07-02 10:00 | q | -32 |  | 2025-05-30 15:36
133 | 3952 | HkhDGF3pWO8GORFQnyh9 | Normal | 5 | 1.5.4.5.1.2 | 1.5.4.5.1.2 |  | 2025-09-11 15:00 | q | -33 |  | 2025-08-08 16:29
134 | 3953 | dYr7YcYkpYYUeESNUSkl | Normal | 2 | 1.5.4.5.1.3 | 1.5.4.5.1.3 |  | 2025-09-18 15:00 | q | -31 |  | 2025-08-18 08:53
135 | 3954 | r37KEs6OIDoMKT5Yz5nA | Normal | 1 | 1.5.4.5.1.4 | 1.5.4.5.1.4 |  | 2025-09-22 15:00 | q | -33 |  | 2025-08-20 10:11
136 | 6606 | pKonEcYtBOhP3mqLQIUx | Normal | 5 | 1.5.4.4.8 | 1.5.4.4.8 |  | 2025-05-22 10:00 | q | -27 |  | 2025-04-24 15:52
137 | 4215 | I07WrBLpDQufO3mvIdSu | Normal | 1 | 1.5.1.1.4 | 1.5.1.1.4 |  | 2025-07-02 10:00 | q | -30 |  | 2025-06-02 08:43
138 | 6445 | Wo6GLLiu9tXQyZ8t43hX | Normal | 43 | 1.5.1.1.3 | 1.5.1.1.3 |  | 2025-04-30 10:00 | q | -42 |  | 2025-03-19 09:56
139 | 6681 | NHiN8b86HRxpkLb9JGGD | Normal | 10 | 1.5.1.3.9 | 1.5.1.3.9 |  | 2026-08-14 08:00 | q | -1 |  | 2026-08-12 11:05
140 | 6682 | 695WEwNqpcHeAbXSBRci | Normal | 2 | 1.5.1.3.10 | 1.5.1.3.10 |  | 2026-08-28 08:00 | p | 0 |  | 2026-08-28 08:46
141 | 6684 | TL3Mtv3QlGNejnoXktH7 | Normal | 1 | 1.5.1.3.8 | 1.5.1.3.8 |  | 2026-08-13 08:00 | q | -1 |  | 2026-08-11 09:27
142 | 5612 | JBIAfh9fImNsEXfXoHCz | Summary | 5 | 1.5.2.2.10 | 1.5.2.2.10 |  | 2026-07-24 08:00 | p | 4 |  | 2026-07-28 15:47
143 | 5613 | cc9QdsdOkkgaQ8ateKZX | Normal | 1 | 1.5.2.2.10.1 | 1.5.2.2.10.1 |  | 2026-07-24 08:00 | p | 4 |  | 2026-07-28 15:47
144 | 5614 | COTl0owSvMhEdF9iuXCz | Normal | 0 | 1.5.2.2.10.2 | 1.5.2.2.10.2 |  | 2026-07-27 09:36 | p | 2 |  | 2026-07-30 08:38
145 | 5615 | 0lLRNnxfg3utwoPLwt26 | Normal | 2 | 1.5.2.2.10.3 | 1.5.2.2.10.3 |  | 2026-07-27 14:36 | p | 2 |  | 2026-07-30 14:03
146 | 5616 | 5Z54Ad8GhuwKLjQHaz2Y | Normal | 1 | 1.5.2.2.10.4 | 1.5.2.2.10.4 |  | 2026-07-29 14:36 | p | 4 |  | 2026-08-03 14:03
147 | 5617 | fALGtnsfw381gf0W53Ia | Normal | 0 | 1.5.2.2.10.5 | 1.5.2.2.10.5 |  | 2026-07-30 14:36 | p | 5 |  | 2026-08-04 14:37
148 | 5627 | s0vjJX7zGlVyBdE0eigo | Summary | 15 | 1.5.2.2.8 | 1.5.2.2.8 |  | 2026-07-02 08:00 | q | -507 |  | 2025-02-10 08:00
149 | 5628 | JolyrZVyKy7n75ZL5gZI | Normal | 2 | 1.5.2.2.8.1 | 1.5.2.2.8.1 |  | 2026-07-10 08:00 | p | 5 |  | 2026-07-15 14:52
150 | 5629 | ghMhRqrbgVxCQv51dU2T | Normal | 0 | 1.5.2.2.8.2 | 1.5.2.2.8.2 |  | 2026-07-14 13:00 | p | 5 |  | 2026-07-20 09:42
151 | 5630 | eU3bwvC6wgraOvc5hiLt | Milestone | 0 | 1.5.2.2.8.3 | 1.5.2.2.8.3 |  | 2026-07-15 08:00 | p | 5 |  | 2026-07-20 14:53
152 | 5631 | gvTQVNdftDRXYXclyMFo | Normal | 3 | 1.5.2.2.8.4 | 1.5.2.2.8.4 |  | 2026-07-15 08:00 | p | 5 |  | 2026-07-20 14:53
153 | 5632 | DfRDIp64TG1m6LE7SSYQ | Milestone | 0 | 1.5.2.2.8.5 | 1.5.2.2.8.5 |  | 2026-07-20 08:00 | p | 3 |  | 2026-07-23 13:45
154 | 5633 | 2UPBwQymcCOUpuUjnBTe | Normal | 3 | 1.5.2.2.8.6 | 1.5.2.2.8.6 |  | 2026-07-20 08:00 | p | 3 |  | 2026-07-23 13:45
155 | 5634 | gm5pLWvICR0pU7aShOGD | Normal | 1 | 1.5.2.2.8.7 | 1.5.2.2.8.7 |  | 2026-07-23 08:00 | p | 4 |  | 2026-07-27 15:29
156 | 7545 | 65jUkOPqlMfpoMROhJ4O | Normal | 5 | 1.5.3.2.9.1 | 1.5.3.2.9.1 |  | 2026-07-02 08:00 | q | -507 |  | 2025-02-10 08:00
157 | 5637 | agdOsAK6kuG5dvRDXVyv | Milestone | 0 | 1.5.2.2.9.2 | 1.5.2.2.9.2 |  | 2025-01-08 17:00 | p | 538 |  | 2026-07-01 16:10
158 | 5638 | jBSFjjY1RfmWgqa8tOlO | Normal | 0 | 1.5.2.2.9.3 | 1.5.2.2.9.3 |  | 2025-01-09 08:00 | p | 538 |  | 2026-07-01 16:10
159 | 5639 | ymvGdGMdlU958QTwMU9V | Normal | 0 | 1.5.2.2.9.4 | 1.5.2.2.9.4 |  | 2025-01-27 08:00 | p | 540 |  | 2026-07-21 09:44
160 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | 2025-01-27 13:00 | p | 540 |  | 2026-07-21 14:11
161 | 5641 | QjWOhv4eRSTZWx0ATAUl | Normal | 23 | 1.5.2.2.11 | 1.5.2.2.11 |  | 2026-07-31 08:00 | p | 4 |  | 2026-08-04 16:59
162 | 5447 | ijJ4zfbEfOInLYX7Vu9Z | Normal | 6 | 1.5.3.1.2.2 | 1.5.3.1.2.2 |  | 2025-05-30 10:00 | q | -28 |  | 2025-05-02 08:22
163 | 5448 | cS9oDqhLQ00Df4o4XStO | Normal | 6 | 1.5.3.1.2.3 | 1.5.3.1.2.3 |  | 2025-06-09 10:00 | q | -31 |  | 2025-05-09 09:28
164 | 5449 | 6It4K5O7iZJhLoLO2jyi | Normal | 6 | 1.5.3.1.2.4 | 1.5.3.1.2.4 |  | 2025-06-17 10:00 | q | -31 |  | 2025-05-16 15:04
165 | 5450 | maMtUzorvxHWuMFIlXlq | Normal | 5 | 1.5.3.1.3 | 1.5.3.1.3 |  | 2025-06-26 10:00 | q | -33 |  | 2025-05-23 16:25
166 | 7381 | Ao7wteklS85dOuCCMM3I | Normal | 124 | 1.5.1 | 1.5.1 |  | 2026-03-09 08:00 | p | 16 |  | 2026-03-25 15:58
167 | 576 | m8O5CFAYfVbtxxZI5qQW | Normal | 15 | 1.4.3.1.2 | 1.4.3.1.2 |  | 2026-02-19 08:00 | q | -34 |  | 2026-01-15 10:24
168 | 5854 | 2kqOvhRPajU4Q0ZPsUnx | Normal | 8 | 1.4.3.1.4 | 1.4.3.1.4 |  | 2026-03-19 08:00 | q | -34 |  | 2026-02-12 15:02
169 | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Normal | 49 | 1.4.3.1.5 | 1.4.3.1.5 |  | 2026-06-24 08:00 | q | -13 |  | 2026-06-10 13:19
170 | 6607 | IhYDHpDNbof6PVOjQ9lw | Normal | 4 | 1.4.3.1.3 | 1.4.3.1.3 |  | 2026-03-13 08:00 | q | -34 |  | 2026-02-06 13:12
171 | 3901 | Jj1toL1YzUk95oK7OfgU | Normal | 4 | 1.4.1.1.2.4 | 1.4.1.1.2.4 |  | 2026-02-12 08:00 | q | -34 |  | 2026-01-08 16:54
172 | 6566 | gAyE6SkFHV1MNEAJitQ7 | Normal | 1 | 1.4.1.2.1.6 | 1.4.1.2.1.6 |  | 2026-03-16 08:00 | p | 7 |  | 2026-03-23 08:33
173 | 3907 | pFYLZycbgH4KMn6pLhBU | Summary | 272 | 1.4.1.3 | 1.4.1.3 |  | 2026-03-17 08:00 | p | 7 |  | 2026-03-24 08:43
174 | 3908 | y9tKov3jCEzWGyA9B1wJ | Normal | 5 | 1.4.1.3.1 | 1.4.1.3.1 |  | 2026-03-17 08:00 | p | 7 |  | 2026-03-24 08:43
175 | 3909 | VvjZ0oHXTTG06m5XlL1B | Normal | 10 | 1.4.1.3.2 | 1.4.1.3.2 |  | 2026-03-24 08:00 | p | 7 |  | 2026-03-31 10:09
176 | 3910 | pNRX5rV0uvvHnR27z1AO | Normal | 8 | 1.4.1.3.3 | 1.4.1.3.3 |  | 2026-04-07 08:00 | p | 7 |  | 2026-04-14 09:59
177 | 3911 | R3AK39H17lCC16PE9DkR | Normal | 10 | 1.4.1.3.4 | 1.4.1.3.4 |  | 2026-04-17 08:00 | p | 6 |  | 2026-04-23 14:17
178 | 3912 | BSEXS69UjCPQ6j2zF47p | Normal | 15 | 1.4.1.3.5 | 1.4.1.3.5 |  | 2026-05-01 08:00 | p | 4 |  | 2026-05-05 13:12
179 | 3913 | nUmJBAacPI2xORV8OCED | Normal | 20 | 1.4.1.3.6 | 1.4.1.3.6 |  | 2026-05-22 08:00 | p | 0 |  | 2026-05-22 15:31
180 | 3914 | e7efPn2W4IFyilt2hNai | Normal | 30 | 1.4.1.3.7 | 1.4.1.3.7 |  | 2026-06-23 08:00 | p | 3 |  | 2026-06-26 14:17
181 | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Normal | 5 | 1.4.1.3.8 | 1.4.1.3.8 |  | 2026-08-05 08:00 | q | -1 |  | 2026-08-03 14:27
182 | 3916 | xcLTkuiw0V5a2mOSGmcP | Normal | 10 | 1.4.1.3.9 | 1.4.1.3.9 |  | 2026-08-12 08:00 | q | 0 |  | 2026-08-11 14:56
183 | 3917 | hmttcJptV92JIo4OpANW | Normal | 5 | 1.4.1.3.10 | 1.4.1.3.10 |  | 2026-08-26 08:00 | q | 0 |  | 2026-08-25 10:38
184 | 3918 | VKkEEklTkhlAtqntT93x | Summary | 160 | 1.4.1.4 | 1.4.1.4 |  | 2028-06-20 08:00 | p | 183 |  | 2028-12-20 16:48
185 | 3919 | 70MdVf3krr3KZdDhEaoj | Normal | 1 | 1.4.1.4.1 | 1.4.1.4.1 |  | 2028-06-20 08:00 | p | 183 |  | 2028-12-20 16:48
186 | 3920 | mBVNyTIN7rvKyNQxzyxZ | Normal | 9 | 1.4.1.4.2 | 1.4.1.4.2 |  | 2028-06-21 08:00 | p | 184 |  | 2028-12-22 09:32
187 | 3921 | jEuseC90wYhkn0V4svXs | Normal | 3 | 1.4.1.4.3 | 1.4.1.4.3 |  | 2028-07-04 08:00 | p | 183 |  | 2029-01-03 16:25
188 | 3922 | yD55zWPn8USsNa4i8nCC | Normal | 5 | 1.4.1.4.4 | 1.4.1.4.4 |  | 2028-07-07 08:00 | p | 185 |  | 2029-01-08 15:21
189 | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Normal | 15 | 1.4.1.4.5 | 1.4.1.4.5 |  | 2028-07-14 08:00 | p | 187 |  | 2029-01-17 14:23
190 | 3924 | N1CigBiMQE2J41ZAMkt0 | Normal | 20 | 1.4.1.4.6 | 1.4.1.4.6 |  | 2028-08-04 08:00 | p | 196 |  | 2029-02-16 15:12
191 | 3925 | hSr4t1vn7GiB6Kp7YK0M | Normal | 5 | 1.4.1.4.7 | 1.4.1.4.7 |  | 2028-09-01 08:00 | p | 200 |  | 2029-03-20 15:22
192 | 3926 | vGJMK6sejFbKR6Gom2up | Normal | 5 | 1.4.1.4.8 | 1.4.1.4.8 |  | 2028-09-08 08:00 | p | 199 |  | 2029-03-26 14:44
193 | 3927 | 3RLmiC17tI4E2ggNuRe0 | Normal | 5 | 1.4.1.4.9 | 1.4.1.4.9 |  | 2028-09-15 08:00 | p | 201 |  | 2029-04-04 14:08
194 | 3928 | hCBFci3gUopMkWW2dQQj | Normal | 5 | 1.4.1.4.10 | 1.4.1.4.10 |  | 2028-09-22 08:00 | p | 202 |  | 2029-04-12 15:10
195 | 5213 | 6YmlQVHNVjUNryBHQf8a | Summary | 61 | 1.4.2.2.3 | 1.4.2.2.3 |  | 2025-11-04 08:00 | q | -27 |  | 2025-10-07 11:32
196 | 5214 | KnSim1DOJ7A0BYyW8QOP | Milestone | 0 | 1.4.2.2.3.1 | 1.4.2.2.3.1 |  | 2025-11-04 08:00 | q | -27 |  | 2025-10-07 11:32
197 | 5215 | KawuX1icbWQB8WlKVKy9 | Normal | 60 | 1.4.2.2.3.2 | 1.4.2.2.3.2 |  | 2025-11-04 08:00 | q | -27 |  | 2025-10-07 11:32
198 | 5216 | xOecB4tLtQXauOnWGD4l | Normal | 1 | 1.4.2.2.3.3 | 1.4.2.2.3.3 |  | 2026-01-30 08:00 | q | -31 |  | 2025-12-29 12:00
199 | 5217 | e116DivbRDCkLiH2zNhl | Summary | 61 | 1.4.2.2.4 | 1.4.2.2.4 |  | 2025-12-16 08:00 | q | -40 |  | 2025-11-05 16:04
200 | 5218 | 8GMyARBjPLtiSR4txAaa | Milestone | 0 | 1.4.2.2.4.1 | 1.4.2.2.4.1 |  | 2025-12-16 08:00 | q | -40 |  | 2025-11-05 16:04
201 | 5219 | Uz3hspiJXkYJElXZ00I5 | Normal | 60 | 1.4.2.2.4.2 | 1.4.2.2.4.2 |  | 2025-12-16 08:00 | q | -40 |  | 2025-11-05 16:04
202 | 5220 | QAqXx5k5ldQJaugZyYbR | Normal | 1 | 1.4.2.2.4.3 | 1.4.2.2.4.3 |  | 2026-03-11 08:00 | q | -33 |  | 2026-02-05 09:12
203 | 5221 | iTaWceiQKMF6gUaF3DCB | Summary | 61 | 1.4.2.2.5 | 1.4.2.2.5 |  | 2026-01-30 08:00 | q | -29 |  | 2025-12-31 10:17
204 | 5222 | 4u5ocGGr0fcTRpzuglXZ | Milestone | 0 | 1.4.2.2.5.1 | 1.4.2.2.5.1 |  | 2026-01-30 08:00 | q | -29 |  | 2025-12-31 10:17
205 | 5223 | 3nEJb4lsc7akFmF6ULw7 | Normal | 60 | 1.4.2.2.5.2 | 1.4.2.2.5.2 |  | 2026-01-30 08:00 | q | -29 |  | 2025-12-31 10:17
206 | 5224 | PvORb6t1pqf23aOFbh3S | Normal | 1 | 1.4.2.2.5.3 | 1.4.2.2.5.3 |  | 2026-04-24 08:00 | q | -30 |  | 2026-03-24 09:57
207 | 5225 | b44Ij1WE7Qrra8bO7ZTN | Normal | 1 | 1.4.2.2.6 | 1.4.2.2.6 |  | 2026-09-01 08:00 | q | 0 |  | 2026-08-31 16:05
208 | 5277 | TgmqG1sR4A60sNmMtPcE | Summary | 193 | 1.4.2.2.7 | 1.4.2.2.7 |  | 2025-08-27 16:11 | q | -27 |  | 2025-07-31 11:04
209 | 5278 | OmCdw3tKtVsW24V2aNqQ | Normal | 8 | 1.4.2.2.7.1 | 1.4.2.2.7.1 |  | 2025-08-27 16:11 | q | -27 |  | 2025-07-31 11:04
210 | 5279 | htHZ3VhuaadgfKg1VQls | Summary | 47 | 1.4.2.2.7.11 | 1.4.2.2.7.11 |  | 2026-04-02 15:07 | q | -28 |  | 2026-03-04 15:37
211 | 5280 | q0a2rl5NSMPQe2o4IYAd | Normal | 3 | 1.4.2.2.7.11.1 | 1.4.2.2.7.11.1 |  | 2026-04-02 15:07 | q | -21 |  | 2026-03-12 13:10
212 | 5281 | 3GO4XZOZrW4CEje40UJT | Normal | 5 | 1.4.2.2.7.11.2 | 1.4.2.2.7.11.2 |  | 2026-04-13 09:00 | q | -21 |  | 2026-03-23 08:39
213 | 5282 | qBzS7vPbhPVzs7sVXgmM | Normal | 5 | 1.4.2.2.7.11.3 | 1.4.2.2.7.11.3 |  | 2026-04-13 09:00 | q | -39 |  | 2026-03-04 15:37
214 | 5283 | fU0pzeQGz2MN3lZmznFh | Normal | 5 | 1.4.2.2.7.11.4 | 1.4.2.2.7.11.4 |  | 2026-04-13 09:00 | q | -23 |  | 2026-03-20 10:01
215 | 5284 | epM0xPGW4QTSpblHVWYc | Normal | 10 | 1.4.2.2.7.11.5 | 1.4.2.2.7.11.5 |  | 2026-04-20 09:00 | q | -23 |  | 2026-03-27 16:25
216 | 5285 | ffNcVsnPBySsZbQiEShc | Normal | 10 | 1.4.2.2.7.11.6 | 1.4.2.2.7.11.6 |  | 2026-05-04 09:00 | q | -13 |  | 2026-04-20 11:10
217 | 5286 | Yb8sH9U5B9gBzfVjcJKN | Normal | 6 | 1.4.2.2.7.12 | 1.4.2.2.7.12 |  | 2026-05-18 09:00 | q | -12 |  | 2026-05-05 14:50
218 | 5287 | bhDhrVJ9ZVKMNyReuPKm | Normal | 5 | 1.4.2.2.7.13 | 1.4.2.2.7.13 |  | 2026-05-26 08:00 | q | -12 |  | 2026-05-13 13:32
219 | 5288 | RIVzpLwElpoiAIgfwKiL | Milestone | 0 | 1.4.2.2.7.14 | 1.4.2.2.7.14 |  | 2026-06-02 08:00 | q | -12 |  | 2026-05-20 13:00
220 | 6457 | PFYaNHtSBj97Eh5ysTvH | Normal | 7 | 1.4.2.2.7.2 | 1.4.2.2.7.2 |  | 2025-12-09 08:03 | q | -31 |  | 2025-11-07 13:12
221 | 6458 | pDFztlVdvvSj2i4Cz5Z9 | Normal | 5 | 1.4.2.2.7.3 | 1.4.2.2.7.3 |  | 2025-12-18 08:03 | q | -30 |  | 2025-11-17 16:19
222 | 6459 | ylmwXTiOnCLJpwlHTaRg | Normal | 10 | 1.4.2.2.7.4 | 1.4.2.2.7.4 |  | 2025-12-26 08:03 | q | -31 |  | 2025-11-24 16:17
223 | 6460 | CystLMJtc4xxgICiEMDQ | Normal | 8 | 1.4.2.2.7.5 | 1.4.2.2.7.5 |  | 2026-01-09 08:03 | q | -28 |  | 2025-12-11 14:23
224 | 6461 | 7ypQo0ZyAHzCHmFRlywg | Normal | 10 | 1.4.2.2.7.6 | 1.4.2.2.7.6 |  | 2026-01-21 08:03 | q | -28 |  | 2025-12-23 13:38
225 | 6462 | BWDOi71UCejcEb1fgeoY | Normal | 7 | 1.4.2.2.7.7 | 1.4.2.2.7.7 |  | 2026-02-04 08:03 | q | -25 |  | 2026-01-09 11:55
226 | 6463 | OelD6citgJccZhV0UyvH | Normal | 7 | 1.4.2.2.7.8 | 1.4.2.2.7.8 |  | 2026-02-13 08:03 | q | -23 |  | 2026-01-20 09:54
227 | 6464 | McSTYqZ3LCfaYSSmZoTn | Normal | 7 | 1.4.2.2.7.9 | 1.4.2.2.7.9 |  | 2026-02-24 08:03 | q | -25 |  | 2026-01-29 13:07
228 | 6465 | WAyiiuxKOgY7bZWYUV9d | Normal | 5 | 1.4.2.2.7.10 | 1.4.2.2.7.10 |  | 2026-03-05 08:03 | q | -26 |  | 2026-02-06 15:38
229 | 5240 | NSmZbDTp76mGzDSQ7Ceh | Summary | 56 | 1.4.2.1.3 | 1.4.2.1.3 |  | 2025-06-09 08:32 | q | -59 |  | 2025-04-10 15:54
230 | 5241 | v6EKIZLcnDHW8CXOrD7y | Normal | 21 | 1.4.2.1.3.1 | 1.4.2.1.3.1 |  | 2025-06-09 08:32 | q | -59 |  | 2025-04-10 15:54
231 | 5242 | JYCfpao49G3jD8M94S66 | Normal | 10 | 1.4.2.1.3.2 | 1.4.2.1.3.2 |  | 2025-07-09 08:32 | q | -60 |  | 2025-05-09 10:30
232 | 5243 | 0XN39P602kPVdw6rXYZi | Normal | 10 | 1.4.2.1.3.3 | 1.4.2.1.3.3 |  | 2025-07-23 08:32 | q | -56 |  | 2025-05-27 11:17
233 | 5244 | Nwqnc6xsOuQ8oMDbKNfv | Normal | 15 | 1.4.2.1.3.4 | 1.4.2.1.3.4 |  | 2025-08-06 08:32 | q | -27 |  | 2025-07-09 09:50
234 | 5265 | ATYnDTN93dB3aTXfzslo | Normal | 6 | 1.4.2.1.6.2 | 1.4.2.1.6.2 |  | 2025-02-12 14:02 | p | 34 |  | 2025-03-19 09:53
235 | 5266 | G5H4IlBy3M3Zxs38gcIH | Normal | 10 | 1.4.2.1.6.3 | 1.4.2.1.6.3 |  | 2025-03-06 11:02 | p | 33 |  | 2025-04-08 15:30
236 | 5267 | 3RI5G3ymKjaLn96cfboa | Normal | 11 | 1.4.2.1.6.4 | 1.4.2.1.6.4 |  | 2025-03-06 11:02 | p | 33 |  | 2025-04-08 15:30
237 | 5268 | fG9nayiE82fFlNFtuyfN | Normal | 8 | 1.4.2.1.6.5 | 1.4.2.1.6.5 |  | 2025-08-15 08:32 | q | -48 |  | 2025-06-27 14:28
238 | 5269 | UP8sWsDXCDMiwOqWz3ib | Normal | 5 | 1.4.2.1.6.6 | 1.4.2.1.6.6 |  | 2025-04-03 14:02 | p | 24 |  | 2025-04-28 10:29
239 | 5270 | 0UA65kBzwzHULCayr1Gq | Normal | 8 | 1.4.2.1.6.7 | 1.4.2.1.6.7 |  | 2025-06-16 09:02 | q | -37 |  | 2025-05-09 16:18
240 | 5271 | mtztJWmm2OBnfmSsuoGt | Normal | 10 | 1.4.2.1.6.8 | 1.4.2.1.6.8 |  | 2025-06-30 08:32 | q | -37 |  | 2025-05-23 14:32
241 | 5272 | kvS9pO69DNwaLvofAQcb | Normal | 11 | 1.4.2.1.6.9 | 1.4.2.1.6.9 |  | 2025-07-15 08:32 | q | -34 |  | 2025-06-10 13:50
242 | 5273 | fGHKYfAaAseAkWqOpGpv | Normal | 10 | 1.4.2.1.6.10 | 1.4.2.1.6.10 |  | 2025-07-30 08:32 | q | -27 |  | 2025-07-02 09:04
243 | 5274 | zjsmmZ1Zvuz0mxAk4wzH | Normal | 10 | 1.4.2.1.6.11 | 1.4.2.1.6.11 |  | 2025-08-13 08:32 | q | -27 |  | 2025-07-16 16:12
244 | 5275 | lBTJLZ8EG6vqarjSz7m6 | Milestone | 0 | 1.4.2.1.6.12 | 1.4.2.1.6.12 |  | 2025-08-27 08:32 | q | -27 |  | 2025-07-31 06:29
245 | 5264 | 2BYRPY9ftrCpjg2j3vxJ | Milestone | 0 | 1.4.2.1.8 | 1.4.2.1.8 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 10:06
246 | 5276 | yja2Gk0YbNXya3vsxrwh | Milestone | 0 | 1.4.2.1.7 | 1.4.2.1.7 |  | 2025-08-27 08:32 | q | -27 |  | 2025-07-31 06:29
247 | 5289 | tqKGxL2oceRufkd47wnf | Summary | 319 | 1.4.2.3 | 1.4.2.3 |  | 2026-02-02 08:00 | q | -33 |  | 2025-12-30 16:50
248 | 5290 | NEvSl0zKCrGJ6lqshTZO | Milestone | 0 | 1.4.2.3.1 | 1.4.2.3.1 |  | 2026-04-27 08:00 | q | -32 |  | 2026-03-25 10:00
249 | 5313 | 3y8KKUl940HiJi7UFKFT | Summary | 106 | 1.4.2.3.3 | 1.4.2.3.3 |  | 2028-05-16 11:53 | p | 197 |  | 2028-11-29 16:05
250 | 5314 | SRtjKDi8lC5PBWdNdIAU | Normal | 10 | 1.4.2.3.3.1 | 1.4.2.3.3.1 |  | 2028-05-16 11:53 | p | 197 |  | 2028-11-29 16:05
251 | 5316 | LCfcLPfxTjnSY0dCrjlE | Normal | 10 | 1.4.2.3.3.2 | 1.4.2.3.3.2 |  | 2028-05-17 16:54 | p | 198 |  | 2028-12-01 17:00
252 | 5317 | pw6YyMXR7oeqsrtIHdqo | Normal | 9 | 1.4.2.3.3.3 | 1.4.2.3.3.3 |  | 2028-06-14 11:54 | p | 198 |  | 2028-12-29 14:56
253 | 5318 | KMG5hXAC4X2MZPfyVOSc | Normal | 5 | 1.4.2.3.3.8 | 1.4.2.3.3.8 |  | 2028-08-04 10:04 | p | 200 |  | 2029-02-20 16:42
254 | 5319 | mDGXCmTQB2ITo8MYwlYq | Normal | 5 | 1.4.2.3.3.9 | 1.4.2.3.3.9 |  | 2028-08-11 10:04 | p | 201 |  | 2029-02-28 14:03
255 | 5320 | hu6UActfLD0rLfdNqC55 | Normal | 5 | 1.4.2.3.3.10 | 1.4.2.3.3.10 |  | 2028-08-18 10:04 | p | 201 |  | 2029-03-08 09:52
256 | 5321 | pG9QTaeiPcJe7Bm3iI1s | Normal | 5 | 1.4.2.3.3.11 | 1.4.2.3.3.11 |  | 2028-08-25 10:04 | p | 201 |  | 2029-03-15 09:49
257 | 5322 | oNpYocgOFdrRcJiQE0H5 | Normal | 5 | 1.4.2.3.3.12 | 1.4.2.3.3.12 |  | 2028-09-01 10:04 | p | 202 |  | 2029-03-22 13:45
258 | 5323 | Tt5dEbDabBigq84Eat5c | Normal | 5 | 1.4.2.3.3.13 | 1.4.2.3.3.13 |  | 2028-09-08 10:04 | p | 203 |  | 2029-03-30 10:26
259 | 5324 | INz2wzhVzgQCZLXqwTZc | Normal | 5 | 1.4.2.3.3.14 | 1.4.2.3.3.14 |  | 2028-09-15 13:34 | p | 203 |  | 2029-04-06 15:17
260 | 5325 | D5c4JntP5EU4thbOE4hi | Normal | 1 | 1.4.2.3.3.15 | 1.4.2.3.3.15 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 09:37
261 | 6467 | n3qEWBmgcrCNzbacKk03 | Normal | 5 | 1.4.2.3.3.4 | 1.4.2.3.3.4 |  | 2028-07-07 10:04 | p | 200 |  | 2029-01-23 14:04
262 | 6468 | BqsEZH5IWCI59bWKml0D | Normal | 5 | 1.4.2.3.3.5 | 1.4.2.3.3.5 |  | 2028-07-14 10:04 | p | 200 |  | 2029-01-30 13:58
263 | 6469 | TtC6fzAb8zClFAVfKkP8 | Normal | 5 | 1.4.2.3.3.6 | 1.4.2.3.3.6 |  | 2028-07-21 10:04 | p | 200 |  | 2029-02-07 08:06
264 | 6470 | UrgnPc0HjVwpN7twGsWX | Normal | 5 | 1.4.2.3.3.7 | 1.4.2.3.3.7 |  | 2028-07-28 10:04 | p | 200 |  | 2029-02-13 16:38
265 | 5326 | esDa5lJIA5zg0nP58cRd | Summary | 32 | 1.4.2.3.4 | 1.4.2.3.4 |  | 2026-07-21 08:00 | p | 2 |  | 2026-07-23 16:13
266 | 5327 | iRZmxts3rKQ38tplQw52 | Normal | 30 | 1.4.2.3.4.1 | 1.4.2.3.4.1 |  | 2026-07-21 08:00 | p | 2 |  | 2026-07-23 16:13
267 | 5328 | ngeJL3ilFttQtHxnOEwX | Normal | 1 | 1.4.2.3.4.2 | 1.4.2.3.4.2 |  | 2026-09-01 08:00 | q | 0 |  | 2026-08-31 16:20
268 | 5329 | GYUaK0PI1fV4kag2egD8 | Normal | 1 | 1.4.2.3.4.3 | 1.4.2.3.4.3 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 09:25
269 | 6321 | KAyzIHlSkkFZqIIdJ9JD | Summary | 144 | 1.4.2.3.2 | 1.4.2.3.2 |  | 2026-02-02 08:00 | q | -33 |  | 2025-12-30 16:50
270 | 5298 | c4SSanbHhynqs8RkqT3I | Normal | 3 | 1.4.2.3.2.2 | 1.4.2.3.2.2 |  | 2026-02-16 08:00 | q | -34 |  | 2026-01-12 16:55
271 | 5299 | HB5wL9z8KlZFeAas0WUQ | Normal | 11 | 1.4.2.3.2.3 | 1.4.2.3.2.3 |  | 2026-02-19 08:00 | q | -33 |  | 2026-01-16 15:55
272 | 5301 | hHw9byxBfgMW8zXuSsdj | Milestone | 0 | 1.4.2.3.2.12 | 1.4.2.3.2.12 |  | 2026-04-20 08:00 | q | -34 |  | 2026-03-16 16:58
273 | 5302 | 2rc67Y2hzAhRvE7YihWA | Normal | 10 | 1.4.2.3.2.1 | 1.4.2.3.2.1 |  | 2026-02-02 08:00 | q | -33 |  | 2025-12-30 16:50
274 | 5303 | SgeIRg4ykwxbNqD9urWV | Normal | 2 | 1.4.2.3.2.8 | 1.4.2.3.2.8 |  | 2026-04-07 08:00 | q | -34 |  | 2026-03-03 14:06
275 | 5304 | KRXQrBZsFBKS9k4FvAsp | Normal | 3 | 1.4.2.3.2.9 | 1.4.2.3.2.9 |  | 2026-04-09 08:00 | q | -34 |  | 2026-03-05 16:20
276 | 5305 | TyGQYH0bANBrFjXmh15D | Normal | 2 | 1.4.2.3.2.10 | 1.4.2.3.2.10 |  | 2026-04-14 08:00 | q | -34 |  | 2026-03-10 16:25
277 | 5306 | yar7ts7ASIpTQqyvnwQd | Normal | 5 | 1.4.2.3.2.13 | 1.4.2.3.2.13 |  | 2026-04-20 08:00 | q | -34 |  | 2026-03-16 16:58
278 | 5307 | yRByGMPgEQcCecr5HzAA | Normal | 2 | 1.4.2.3.2.15 | 1.4.2.3.2.15 |  | 2026-04-28 08:00 | q | -32 |  | 2026-03-26 10:43
279 | 5308 | JBAsTSNPb9OQmIAmtadV | Normal | 20 | 1.4.2.3.2.17 | 1.4.2.3.2.17 |  | 2026-05-01 08:00 | q | -24 |  | 2026-04-06 08:40
280 | 5309 | xRRT514kq8kwyv7njrs5 | Normal | 5 | 1.4.2.3.2.19 | 1.4.2.3.2.19 |  | 2026-06-02 08:00 | q | -12 |  | 2026-05-20 13:00
281 | 5310 | RMnJ5j2lLGlokfxLAfSa | Normal | 2 | 1.4.2.3.2.20 | 1.4.2.3.2.20 |  | 2026-08-28 08:00 | q | 0 |  | 2026-08-27 15:14
282 | 5311 | BowxNbb4uXSnAk8z8ZkC | Normal | 2 | 1.4.2.3.2.22 | 1.4.2.3.2.22 |  | 2026-06-11 08:00 | q | -12 |  | 2026-05-29 15:34
283 | 6516 | qmbk7ROGAo4AwJOySAlG | Normal | 4 | 1.4.2.3.2.4 | 1.4.2.3.2.4 |  | 2026-03-06 08:00 | q | -31 |  | 2026-02-02 10:36
284 | 6517 | YGaikKlMVGc6fqtUBZ7h | Normal | 5 | 1.4.2.3.2.5 | 1.4.2.3.2.5 |  | 2026-03-12 08:00 | q | -33 |  | 2026-02-06 08:38
285 | 6518 | 0rDsNLFYCabTnyCcopAQ | Normal | 8 | 1.4.2.3.2.6 | 1.4.2.3.2.6 |  | 2026-03-19 08:00 | q | -34 |  | 2026-02-12 15:02
286 | 6519 | UldK3RoYRJH5Hsfv02Lh | Normal | 2 | 1.4.2.3.2.7 | 1.4.2.3.2.7 |  | 2026-03-31 08:00 | q | -34 |  | 2026-02-24 15:12
287 | 6520 | UaqqB30tdDFCsCHRRpeh | Normal | 2 | 1.4.2.3.2.11 | 1.4.2.3.2.11 |  | 2026-04-16 08:00 | q | -33 |  | 2026-03-13 08:25
288 | 6521 | LDY9CVOjImzsQ4NE65Qz | Normal | 1 | 1.4.2.3.2.16 | 1.4.2.3.2.16 |  | 2026-04-30 08:00 | q | -27 |  | 2026-04-02 16:29
289 | 6522 | WYJvDx3FrKALT2lj4FIo | Normal | 2 | 1.4.2.3.2.18 | 1.4.2.3.2.18 |  | 2026-05-29 08:00 | q | -10 |  | 2026-05-18 10:31
290 | 6523 | TvM5XBX3OaVljTSOZ4e2 | Normal | 2 | 1.4.2.3.2.21 | 1.4.2.3.2.21 |  | 2026-06-09 08:00 | q | -12 |  | 2026-05-27 13:00
291 | 6524 | cvaJgvK8KpGYV8ykH12h | Normal | 2 | 1.4.2.3.2.23 | 1.4.2.3.2.23 |  | 2026-06-15 08:00 | q | -12 |  | 2026-06-02 15:34
292 | 6525 | GtEwLNkefPtnncnl90X4 | Normal | 3 | 1.4.2.3.2.24 | 1.4.2.3.2.24 |  | 2026-06-24 08:00 | q | -13 |  | 2026-06-10 13:19
293 | 6873 | gSZIbC6fsU6IM6McOJy8 | Normal | 1 | 1.4.2.3.2.14 | 1.4.2.3.2.14 |  | 2026-04-27 08:00 | q | -32 |  | 2026-03-25 10:00
294 | 678 | N57z7OkXN935WcKbC4jO | Normal | 1 | 1.6.7.2 | 1.6.7.2 |  | 2028-03-24 08:00 | p | 189 |  | 2028-09-29 08:03
295 | 751 | AADJzuTGAb4gWytj7CQi | Normal | 18 | 1.6.7.9.3.8 | 1.6.7.9.3.8 |  | 2027-07-15 08:00 | p | 180 |  | 2028-01-11 08:01
296 | 752 | r0c0rFS4EkOGynasmiCG | Normal | 36 | 1.6.7.9.3.7 | 1.6.7.9.3.7 |  | 2027-07-15 08:00 | p | 168 |  | 2027-12-30 14:24
297 | 759 | cZuo3MY7iyDrOJC1qVJx | Normal | 5 | 1.6.7.9.3.9 | 1.6.7.9.3.9 |  | 2027-08-10 08:00 | p | 176 |  | 2028-02-02 16:35
298 | 765 | qOEfFivvitnF8cw9csOP | Normal | 1 | 1.6.7.9.3.13 | 1.6.7.9.3.13 |  | 2028-03-24 08:00 | p | 188 |  | 2028-09-28 16:49
299 | 5773 | OCcI80TDGF8LlIXj66uV | Normal | 3 | 1.6.7.9.3.14 | 1.6.7.9.3.14 |  | 2028-03-27 08:00 | p | 189 |  | 2028-10-02 08:24
300 | 745 | aO52oWR4hBrrP5GVCo2a | Normal | 11 | 1.6.7.9.3.5.2 | 1.6.7.9.3.5.2 |  | 2027-02-25 08:00 | p | 182 |  | 2027-08-26 13:16
301 | 746 | qMC0J8brk1dsdpzlKrk7 | Normal | 12 | 1.6.7.9.3.5.3 | 1.6.7.9.3.5.3 |  | 2027-03-26 08:00 | p | 182 |  | 2027-09-24 08:29
302 | 6324 | gthK0FxwJBk3laTELp8O | Summary | 45 | 1.6.7.9.3.6 | 1.6.7.9.3.6 |  | 2027-04-13 08:00 | p | 178 |  | 2027-10-08 16:52
303 | 747 | nul8vpOEtI2Q6W5Q0Qo9 | Normal | 12 | 1.6.7.9.3.6.1 | 1.6.7.9.3.6.1 |  | 2027-04-13 08:00 | p | 178 |  | 2027-10-08 16:52
304 | 748 | M1HHh2K01o23jS8vpDxS | Normal | 11 | 1.6.7.9.3.6.2 | 1.6.7.9.3.6.2 |  | 2027-04-29 08:00 | p | 181 |  | 2027-10-27 10:02
305 | 749 | Q6UXOpf9Kvzek7IGY0vp | Normal | 11 | 1.6.7.9.3.6.3 | 1.6.7.9.3.6.3 |  | 2027-05-14 08:00 | p | 181 |  | 2027-11-11 08:46
306 | 750 | lsyrPytnmjLTpXFywa7Z | Normal | 11 | 1.6.7.9.3.6.4 | 1.6.7.9.3.6.4 |  | 2027-05-31 08:00 | p | 177 |  | 2027-11-24 11:14
307 | 6325 | SeCXD5wMvkrEekc1PKVb | Summary | 48 | 1.6.7.9.3.10 | 1.6.7.9.3.10 |  | 2027-09-10 08:00 | p | 164 |  | 2028-02-21 14:58
308 | 753 | 8158sxzbHZvZEVAAqewP | Normal | 47 | 1.6.7.9.3.10.1 | 1.6.7.9.3.10.1 |  | 2027-10-04 08:00 | p | 140 |  | 2028-02-21 14:58
309 | 754 | hfPeDXfQSV7Nx9zb2rD7 | Normal | 8 | 1.6.7.9.3.10.2 | 1.6.7.9.3.10.2 |  | 2027-09-10 08:00 | p | 178 |  | 2028-03-06 16:38
310 | 755 | DQUdswbbJv1Qpkj0EGFX | Normal | 8 | 1.6.7.9.3.10.3 | 1.6.7.9.3.10.3 |  | 2027-09-22 08:00 | p | 175 |  | 2028-03-15 11:19
311 | 756 | ae3T3d3nFoXZXK7gqkAr | Normal | 20 | 1.6.7.9.3.10.4 | 1.6.7.9.3.10.4 |  | 2027-10-04 08:00 | p | 175 |  | 2028-03-27 09:44
312 | 757 | wbc1AZ0GUhXzQk6SoWIe | Normal | 6 | 1.6.7.9.3.10.6 | 1.6.7.9.3.10.6 |  | 2027-11-01 08:00 | p | 175 |  | 2028-04-24 10:59
313 | 758 | FbN1rrQYTlsz1haWZnFy | Normal | 6 | 1.6.7.9.3.10.8 | 1.6.7.9.3.10.8 |  | 2027-11-09 08:00 | p | 175 |  | 2028-05-02 15:00
314 | 5780 | XCMvjmTKbAUuCZwuNlSF | Normal | 6 | 1.6.7.9.3.10.5 | 1.6.7.9.3.10.5 |  | 2027-10-22 08:00 | p | 175 |  | 2028-04-14 11:32
315 | 5782 | EYY3j1SjnoLUV06T0QHs | Normal | 5 | 1.6.7.9.3.10.7 | 1.6.7.9.3.10.7 |  | 2027-11-10 08:00 | p | 177 |  | 2028-05-05 09:20
316 | 6326 | F4s3MnfyyA74WCIympSi | Summary | 75 | 1.6.7.9.3.11 | 1.6.7.9.3.11 |  | 2027-08-17 08:00 | p | 176 |  | 2028-02-09 11:19
317 | 760 | 7IpOsslq7gyebnCTulxX | Normal | 66 | 1.6.7.9.3.11.1 | 1.6.7.9.3.11.1 |  | 2027-08-17 08:00 | p | 176 |  | 2028-02-09 11:19
318 | 761 | x6fNhJzs4uMW9trtiNEW | Normal | 1 | 1.6.7.9.3.11.2 | 1.6.7.9.3.11.2 |  | 2027-11-17 08:00 | p | 175 |  | 2028-05-10 13:05
319 | 762 | nRInnITHYgcDsU5KDg6m | Normal | 8 | 1.6.7.9.3.11.3 | 1.6.7.9.3.11.3 |  | 2027-11-18 08:00 | p | 175 |  | 2028-05-11 13:04
320 | 6327 | dOJS0LaWQU970ssSiqsz | Summary | 59 | 1.6.7.9.3.12 | 1.6.7.9.3.12 |  | 2027-11-30 08:00 | p | 171 |  | 2028-05-19 15:58
321 | 763 | hLK2cdXSS7IhOZR53PgI | Normal | 6 | 1.6.7.9.3.12.1 | 1.6.7.9.3.12.1 |  | 2027-11-30 08:00 | p | 171 |  | 2028-05-19 15:58
322 | 764 | wTf98lLeHiXAkWj17mAH | Normal | 53 | 1.6.7.9.3.12.2 | 1.6.7.9.3.12.2 |  | 2027-12-08 08:00 | p | 173 |  | 2028-05-29 08:39
323 | 786 | 5RJIBxVgSA4dodMzOCsx | Normal | 1 | 1.6.7.8.5 | 1.6.7.8.5 |  | 2027-12-07 08:00 | p | 170 |  | 2028-05-25 16:10
324 | 5785 | xIbBdattr1YLWDiqGWPC | Summary | 126 | 1.6.7.11 | 1.6.7.11 |  | 2028-03-30 08:00 | p | 188 |  | 2028-10-04 16:59
325 | 5774 | Dvlkt7hdSzdJ7ChIr4xD | Normal | 2 | 1.6.7.11.1 | 1.6.7.11.1 |  | 2028-03-30 08:00 | p | 188 |  | 2028-10-04 16:59
326 | 5775 | D3NIdGcGrWNhiaQ0dYbY | Normal | 2 | 1.6.7.11.3 | 1.6.7.11.3 |  | 2028-09-20 08:00 | p | 203 |  | 2029-04-11 11:27
327 | 6435 | Ql00ScpYzqtI9PQP57zu | Normal | 122 | 1.6.7.11.2 | 1.6.7.11.2 |  | 2028-04-03 08:00 | p | 186 |  | 2028-10-06 15:49
328 | 1463 | IQX94tuow2VKmVJTuhEN | Normal | 1 | 1.6.6.1.3 | 1.6.6.1.3 |  | 2025-08-07 15:00 | q | -175 |  | 2025-02-13 08:00
329 | 1464 | VN7GLU7alOC9oD3kkW9q | Normal | 30 | 1.6.6.1.4 | 1.6.6.1.4 |  | 2025-08-08 15:00 | q | -43 |  | 2025-06-26 09:53
330 | 1465 | i7zbkIpCuBMJlMsq6ma0 | Normal | 1 | 1.6.6.1.5 | 1.6.6.1.5 |  | 2025-09-22 15:00 | q | -33 |  | 2025-08-20 10:49
331 | 1475 | suCYO4gIoCSrnZchT6aQ | Normal | 3 | 1.6.6.1.6 | 1.6.6.1.6 |  | 2027-06-30 08:00 | p | 167 |  | 2027-12-14 09:44
332 | 1476 | gbuDNYIgLq2nB3WERl4p | Normal | 30 | 1.6.6.1.7 | 1.6.6.1.7 |  | 2027-07-05 08:00 | p | 165 |  | 2027-12-17 15:46
333 | 1477 | BC1NYB3fqAlfckX7ECXI | Normal | 1 | 1.6.6.1.8 | 1.6.6.1.8 |  | 2027-08-16 08:00 | p | 176 |  | 2028-02-08 14:47
334 | 1478 | UR7xa7LgN3sMlpzxRjvW | Normal | 3 | 1.6.6.1.9 | 1.6.6.1.9 |  | 2028-05-15 08:00 | p | 207 |  | 2028-12-08 10:01
335 | 3932 | RKLg9Drqo40Q82TFH1VL | Normal | 1 | 1.6.4.15.2 | 1.6.4.15.2 |  | 2027-03-18 08:00 | p | 179 |  | 2027-09-13 11:28
336 | 3934 | 10Oh1H5M5HjeoWxU1u0w | Normal | 1 | 1.6.4.15.4 | 1.6.4.15.4 |  | 2027-09-24 13:00 | p | 199 |  | 2028-04-11 11:05
337 | 3936 | hwXDQy0MWIQ4jzjNT4oM | Normal | 1 | 1.6.4.15.3 | 1.6.4.15.3 |  | 2027-09-24 13:00 | p | 199 |  | 2028-04-11 11:53
338 | 3940 | 8UqvtHTIMRT16eupajKq | Normal | 1 | 1.6.4.15.5 | 1.6.4.15.5 |  | 2027-09-24 13:00 | p | 199 |  | 2028-04-11 11:10
339 | 3974 | xzlIrgrrtbLscLWLbbQq | Normal | 1 | 1.6.4.7.1 | 1.6.4.7.1 |  | 2027-07-14 08:00 | p | 177 |  | 2028-01-07 16:21
340 | 3992 | cy141kwlo0X5isTqv3ku | Summary | 25 | 1.6.4.17.4 | 1.6.4.17.4 |  | 2026-07-29 08:00 | q | -5 |  | 2026-07-23 14:34
341 | 3993 | LBRozXrRhpq69SKlxnDb | Normal | 10 | 1.6.4.17.4.1 | 1.6.4.17.4.1 |  | 2026-07-29 08:00 | q | -5 |  | 2026-07-23 14:34
342 | 3994 | DvOjAQ6C9aXKnpaAVD1H | Normal | 5 | 1.6.4.17.4.2 | 1.6.4.17.4.2 |  | 2026-08-12 08:00 | q | 0 |  | 2026-08-11 11:06
343 | 3995 | AUkl27NW1i9i5huez8Rg | Normal | 5 | 1.6.4.17.4.3 | 1.6.4.17.4.3 |  | 2026-08-19 08:00 | p | 0 |  | 2026-08-19 08:58
344 | 3996 | Bw8X4DjnSuQgBiA6BEKp | Normal | 5 | 1.6.4.17.4.4 | 1.6.4.17.4.4 |  | 2026-08-26 08:00 | p | 0 |  | 2026-08-26 08:29
345 | 3997 | KJPP8ivswwWTIeIfPXEM | Summary | 25 | 1.6.4.17.3 | 1.6.4.17.3 |  | 2026-06-23 08:00 | q | -6 |  | 2026-06-16 11:23
346 | 3998 | 5UhDwyM7phAycUkk1Nye | Normal | 10 | 1.6.4.17.3.1 | 1.6.4.17.3.1 |  | 2026-06-23 08:00 | q | -6 |  | 2026-06-16 11:23
347 | 3999 | v6kjlf8aEDhSJHzOK2Uo | Normal | 5 | 1.6.4.17.3.2 | 1.6.4.17.3.2 |  | 2026-07-08 08:00 | q | -5 |  | 2026-07-02 08:30
348 | 4000 | Y3aJp60cYMHromf8xgAE | Normal | 5 | 1.6.4.17.3.3 | 1.6.4.17.3.3 |  | 2026-07-15 08:00 | q | -4 |  | 2026-07-10 08:55
349 | 4001 | Cjtbc2cmKWchyZlcOxo3 | Normal | 5 | 1.6.4.17.3.4 | 1.6.4.17.3.4 |  | 2026-07-22 08:00 | q | -5 |  | 2026-07-16 11:37
350 | 4004 | fF1Y54WMybWnXZsBJgYM | Normal | 1 | 1.6.4.17.2.2 | 1.6.4.17.2.2 |  | 2026-06-10 08:00 | q | -7 |  | 2026-06-02 11:22
351 | 4005 | NxZ8rMz5ZnJaz6z1SXKM | Normal | 3 | 1.6.4.17.2.3 | 1.6.4.17.2.3 |  | 2026-06-11 08:00 | q | -7 |  | 2026-06-03 13:37
352 | 4006 | fOTuJvqH3OcilXcZuEM5 | Normal | 4 | 1.6.4.17.2.4 | 1.6.4.17.2.4 |  | 2026-06-16 08:00 | q | -6 |  | 2026-06-09 10:38
353 | 6168 | BHtkkzlMW8757DY2qb23 | Summary | 143 | 1.6.4.19.3 | 1.6.4.19.3 |  | 2026-02-09 08:00 | q | -9 |  | 2026-01-30 14:46
354 | 6169 | gdW3U4pURjb9iKkAVexH | Summary | 60 | 1.6.4.19.3.1 | 1.6.4.19.3.1 |  | 2026-02-09 08:00 | q | -9 |  | 2026-01-30 14:46
355 | 6170 | AwYLgXY6Mo1DqCbUEhPQ | Summary | 30 | 1.6.4.19.3.1.1 | 1.6.4.19.3.1.1 |  | 2026-02-09 08:00 | q | -9 |  | 2026-01-30 14:46
356 | 6171 | ZR4zae2ZYhCMcZhj7T05 | Normal | 15 | 1.6.4.19.3.1.1.1 | 1.6.4.19.3.1.1.1 |  | 2026-02-09 08:00 | q | -9 |  | 2026-01-30 14:46
357 | 6172 | QgFskomqU31VYtYzB2O0 | Normal | 15 | 1.6.4.19.3.1.1.2 | 1.6.4.19.3.1.1.2 |  | 2026-03-03 08:00 | q | -7 |  | 2026-02-23 15:37
358 | 6173 | nRc7GqDGMG4VP1O5IlEd | Normal | 15 | 1.6.4.19.3.1.2 | 1.6.4.19.3.1.2 |  | 2026-03-24 08:00 | q | -4 |  | 2026-03-19 09:55
359 | 6174 | dvLkHNDhuFTU7AO5XWky | Normal | 15 | 1.6.4.19.3.1.3 | 1.6.4.19.3.1.3 |  | 2026-04-14 08:00 | q | -4 |  | 2026-04-09 10:42
360 | 6175 | IEttja5qNJ6P760Cd9De | Summary | 40 | 1.6.4.19.3.2 | 1.6.4.19.3.2 |  | 2026-05-05 08:00 | q | 0 |  | 2026-05-04 09:44
361 | 6176 | B6x3R7fnpOwupecmo90D | Normal | 10 | 1.6.4.19.3.2.1 | 1.6.4.19.3.2.1 |  | 2026-05-05 08:00 | q | 0 |  | 2026-05-04 09:44
362 | 6177 | vkZhJMfsZWiMPLTjgcam | Normal | 10 | 1.6.4.19.3.2.2 | 1.6.4.19.3.2.2 |  | 2026-05-19 08:00 | p | 0 |  | 2026-05-19 10:38
363 | 6178 | XEU5rnQh2VnDpMl1eT0o | Normal | 10 | 1.6.4.19.3.2.3 | 1.6.4.19.3.2.3 |  | 2026-06-03 08:00 | q | 0 |  | 2026-06-02 16:48
364 | 6179 | xksMzlhYjvKZ4p1XJwSB | Normal | 10 | 1.6.4.19.3.2.4 | 1.6.4.19.3.2.4 |  | 2026-06-17 08:00 | p | 0 |  | 2026-06-17 09:00
365 | 6180 | oR7r0RquVFe2h8pCK9HY | Normal | 10 | 1.6.4.19.3.3 | 1.6.4.19.3.3 |  | 2026-07-02 08:00 | p | 4 |  | 2026-07-06 10:12
366 | 6181 | UJ3hrxCJ5NslZjdDLEyu | Normal | 20 | 1.6.4.19.3.4 | 1.6.4.19.3.4 |  | 2026-07-17 08:00 | p | 3 |  | 2026-07-20 11:21
367 | 6182 | JQHbjwkPqIslt5thIOgQ | Normal | 5 | 1.6.4.19.3.5 | 1.6.4.19.3.5 |  | 2026-08-14 08:00 | p | 3 |  | 2026-08-17 11:05
368 | 6183 | 5NqxhAyIl3JXTpWWvSnV | Normal | 2 | 1.6.4.19.3.6 | 1.6.4.19.3.6 |  | 2026-08-21 08:00 | p | 0 |  | 2026-08-21 13:17
369 | 6184 | vx8CoW16lw8uEEVKaVp7 | Normal | 5 | 1.6.4.19.3.7 | 1.6.4.19.3.7 |  | 2026-08-25 08:00 | p | 0 |  | 2026-08-25 09:12
370 | 6185 | A91LND4pEy61zvjvAsaQ | Normal | 1 | 1.6.4.19.3.8 | 1.6.4.19.3.8 |  | 2026-09-01 08:00 | q | 0 |  | 2026-08-31 16:54
371 | 4040 | g5zNgGHP8U11wPTJKhcB | Normal | 20 | 1.6.4.20.1.3 | 1.6.4.20.1.3 |  | 2027-12-27 08:00 | p | 183 |  | 2028-06-27 08:05
372 | 4041 | f0PORH3GhEIXFjYfGbTd | Normal | 97 | 1.6.4.20.1.6 | 1.6.4.20.1.6 |  | 2027-11-04 08:00 | p | 148 |  | 2028-03-31 13:47
373 | 4042 | SyfMayqY4a7i0nZLPz6Y | Normal | 129 | 1.6.4.20.1.7 | 1.6.4.20.1.7 |  | 2027-09-21 08:00 | p | 184 |  | 2028-03-23 11:37
374 | 6621 | pXe0ZxltUhDf1quSL5q2 | Normal | 15 | 1.6.4.20.1.2 | 1.6.4.20.1.2 |  | 2026-02-09 08:00 | q | -9 |  | 2026-01-30 14:46
375 | 6622 | EmEy5gJckBYofEEYNXFv | Normal | 20 | 1.6.4.20.1.4 | 1.6.4.20.1.4 |  | 2028-01-24 08:00 | p | 176 |  | 2028-07-18 14:13
376 | 6623 | BVU87KMg9Rhzc6j5yKVh | Normal | 20 | 1.6.4.20.1.5 | 1.6.4.20.1.5 |  | 2028-02-21 08:00 | p | 179 |  | 2028-08-18 08:35
377 | 4043 | XbXkjxtfHUxhg4CK1elt | Summary | 127 | 1.6.4.20.2 | 1.6.4.20.2 |  | 2028-03-20 08:00 | p | 178 |  | 2028-09-14 10:52
378 | 4045 | mDphgqAAxA2RnvA52x8A | Normal | 20 | 1.6.4.20.2.1 | 1.6.4.20.2.1 |  | 2028-03-20 08:00 | p | 178 |  | 2028-09-14 10:52
379 | 4046 | 5HyQBVwuqRdeW1HhaSOP | Normal | 10 | 1.6.4.20.2.2 | 1.6.4.20.2.2 |  | 2028-04-17 08:00 | p | 184 |  | 2028-10-18 15:33
380 | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Normal | 72 | 1.6.4.20.2.3 | 1.6.4.20.2.3 |  | 2028-05-01 08:00 | p | 186 |  | 2028-11-03 10:09
381 | 4048 | ybbKhm9jdtNbVzABGZ8L | Normal | 20 | 1.6.4.20.2.4 | 1.6.4.20.2.4 |  | 2028-08-09 08:00 | p | 198 |  | 2029-02-23 10:06
382 | 4049 | kP1jeiEwkYg4HRpUjG4p | Normal | 5 | 1.6.4.20.2.5 | 1.6.4.20.2.5 |  | 2028-09-06 08:00 | p | 205 |  | 2029-03-30 08:52
383 | 4050 | jQIHIDf5FTnJxQysEvnn | Summary | 37 | 1.6.4.20.3 | 1.6.4.20.3 |  | 2028-08-09 08:00 | p | 203 |  | 2029-02-28 15:10
384 | 4051 | bizigDTezGi1mMHxJ1gi | Summary | 32 | 1.6.4.20.3.1 | 1.6.4.20.3.1 |  | 2028-08-09 08:00 | p | 203 |  | 2029-02-28 15:10
385 | 4052 | JSSXcLTdD9VQNM766DgK | Normal | 20 | 1.6.4.20.3.1.1 | 1.6.4.20.3.1.1 |  | 2028-08-09 08:00 | p | 203 |  | 2029-02-28 15:10
386 | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Normal | 12 | 1.6.4.20.3.1.2 | 1.6.4.20.3.1.2 |  | 2028-09-06 08:00 | p | 204 |  | 2029-03-29 10:11
387 | 4054 | WhXMUGkGRid5sulqMW8S | Summary | 5 | 1.6.4.20.3.2 | 1.6.4.20.3.2 |  | 2028-09-22 08:00 | p | 203 |  | 2029-04-13 11:38
388 | 4055 | dWrJCmOwv1i72p29KBXE | Normal | 2 | 1.6.4.20.3.2.1 | 1.6.4.20.3.2.1 |  | 2028-09-22 08:00 | p | 203 |  | 2029-04-13 11:38
389 | 4056 | a1SRK7UWhIIMlkKKriy9 | Normal | 1 | 1.6.4.20.3.2.2 | 1.6.4.20.3.2.2 |  | 2028-09-26 08:00 | p | 203 |  | 2029-04-17 10:43
390 | 4057 | NKnvgqAHKv63TOKudyZQ | Normal | 1 | 1.6.4.20.3.2.3 | 1.6.4.20.3.2.3 |  | 2028-09-27 08:00 | p | 203 |  | 2029-04-18 10:45
391 | 4058 | cbANjhwCBqAluf1RM04K | Normal | 1 | 1.6.4.20.3.2.4 | 1.6.4.20.3.2.4 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 09:57
392 | 4059 | sH9kz6O2EFda2hu4x8Kx | Summary | 12 | 1.6.4.20.3.3 | 1.6.4.20.3.3 |  | 2028-09-13 08:00 | p | 204 |  | 2029-04-05 08:44
393 | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Normal | 3 | 1.6.4.20.3.3.1 | 1.6.4.20.3.3.1 |  | 2028-09-13 08:00 | p | 204 |  | 2029-04-05 08:44
394 | 4061 | ViM2psfxppAdWr3IoYdq | Normal | 3 | 1.6.4.20.3.3.2 | 1.6.4.20.3.3.2 |  | 2028-09-18 08:00 | p | 203 |  | 2029-04-09 11:49
395 | 4062 | RvsEFsErXikPrAOovPaZ | Normal | 1 | 1.6.4.20.3.3.3 | 1.6.4.20.3.3.3 |  | 2028-09-21 08:00 | p | 203 |  | 2029-04-12 13:34
396 | 4063 | ma6GKJ3GzeKmeF4AshaM | Normal | 4 | 1.6.4.20.3.3.4 | 1.6.4.20.3.3.4 |  | 2028-09-22 08:00 | p | 203 |  | 2029-04-13 09:31
397 | 4064 | OALhjNOvEaqSDAmsS5Il | Normal | 1 | 1.6.4.20.3.3.5 | 1.6.4.20.3.3.5 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 09:02
398 | 6738 | XB1ZMgqMWvDJpnRGKTB3 | Normal | 3 | 1.6.4.18.3.3.2.10 | 1.6.4.18.3.3.2.10 |  | 2027-03-11 08:00 | q | -758 |  | 2025-02-11 08:00
399 | 7270 | 3AlavOi01JfJwLM1b81K | Milestone | 0 | 1.6.4.18.3.3.2.6 | 1.6.4.18.3.3.2.6 |  | 2027-03-16 08:00 | q | -760 |  | 2025-02-13 17:00
400 | 7271 | 7ZvC3KC1rMxIYvbhicKJ | Normal | 10 | 1.6.4.18.3.3.2.7 | 1.6.4.18.3.3.2.7 |  | 2027-03-16 08:00 | p | 182 |  | 2027-09-14 09:20
401 | 7010 | l7MAqMN94R7DBQRgok6z | Normal | 5 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 2027-04-06 08:00 | p | 181 |  | 2027-10-04 14:12
402 | 7277 | hIopgQViPH34dy6jPgEs | Normal | 6 | 1.6.4.18.3.3.7.5 | 1.6.4.18.3.3.7.5 |  | 2027-02-17 08:00 | q | -712 |  | 2025-03-07 08:00
403 | 7278 | 4Ma7Z2LiPmWBC9UI6vyb | Normal | 5 | 1.6.4.18.3.3.7.7 | 1.6.4.18.3.3.7.7 |  | 2027-03-23 08:00 | p | 182 |  | 2027-09-21 14:44
404 | 7300 | JMkMoXIhBdn9ICcOd798 | Normal | 5 | 1.6.4.18.3.3.7.4 | 1.6.4.18.3.3.7.4 |  | 2027-03-30 08:00 | p | 181 |  | 2027-09-27 09:39
405 | 7301 | mVBynbXAicTgOFud0Dl3 | Normal | 5 | 1.6.4.18.3.3.7.6 | 1.6.4.18.3.3.7.6 |  | 2027-03-16 08:00 | p | 182 |  | 2027-09-14 08:52
406 | 7302 | 6S1rSJxqNAmNyzjZVL7L | Normal | 5 | 1.6.4.18.3.3.7.8 | 1.6.4.18.3.3.7.8 |  | 2027-03-30 08:00 | p | 182 |  | 2027-09-28 13:18
407 | 7282 | sTVLhyKAe9uIrxTuOSsB | Normal | 2 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 2027-02-23 08:00 | p | 182 |  | 2027-08-24 10:39
408 | 7283 | GyFcZSlU29ifaVubQEBd | Normal | 2 | 1.6.4.18.3.3.4.4 | 1.6.4.18.3.3.4.4 |  | 2027-02-25 08:00 | p | 182 |  | 2027-08-26 11:05
409 | 7284 | AoDPK2hmzwZjnwdc6ENo | Normal | 1 | 1.6.4.18.3.3.4.5 | 1.6.4.18.3.3.4.5 |  | 2027-03-01 08:00 | p | 182 |  | 2027-08-30 10:05
410 | 7285 | UP4KQN3vFTNJJtYiVHhd | Normal | 10 | 1.6.4.18.3.3.4.6 | 1.6.4.18.3.3.4.6 |  | 2027-03-02 08:00 | p | 182 |  | 2027-08-31 08:59
411 | 7289 | YNbMTserJcwdDTx8O6lt | Normal | 5 | 1.6.4.18.3.3.5.3 | 1.6.4.18.3.3.5.3 |  | 2027-02-25 08:00 | p | 182 |  | 2027-08-26 13:11
412 | 7290 | rpRUKocvSOF2GnoJsxWr | Normal | 2 | 1.6.4.18.3.3.5.4 | 1.6.4.18.3.3.5.4 |  | 2027-03-04 08:00 | p | 183 |  | 2027-09-03 15:12
413 | 7291 | ThxkR8uStFOgKr5Kajlm | Normal | 1 | 1.6.4.18.3.3.5.5 | 1.6.4.18.3.3.5.5 |  | 2027-03-08 08:00 | p | 183 |  | 2027-09-07 15:12
414 | 7292 | 6vEOHVPLFOaXnW1xcDp6 | Normal | 10 | 1.6.4.18.3.3.5.6 | 1.6.4.18.3.3.5.6 |  | 2027-03-09 08:00 | p | 183 |  | 2027-09-08 14:16
415 | 7295 | tyaakhlAtuOpVSt7bVvo | Normal | 1 | 1.6.4.18.3.3.6.2 | 1.6.4.18.3.3.6.2 |  | 2027-02-18 08:00 | q | -738 |  | 2025-02-10 08:00
416 | 7296 | PnFVdPiNKahDkradYWdd | Normal | 5 | 1.6.4.18.3.3.6.3 | 1.6.4.18.3.3.6.3 |  | 2027-03-04 08:00 | p | 179 |  | 2027-08-30 13:07
417 | 7297 | JA5LCeR4tD4Vqq2Jfy9o | Normal | 2 | 1.6.4.18.3.3.6.4 | 1.6.4.18.3.3.6.4 |  | 2027-03-11 08:00 | p | 181 |  | 2027-09-08 10:25
418 | 7298 | uHK4wyA8DzlXgqm5UKoq | Normal | 1 | 1.6.4.18.3.3.6.5 | 1.6.4.18.3.3.6.5 |  | 2027-03-15 08:00 | p | 179 |  | 2027-09-10 08:06
419 | 7299 | ymtRqRQZa4AjGraGOZVd | Normal | 10 | 1.6.4.18.3.3.6.6 | 1.6.4.18.3.3.6.6 |  | 2027-03-16 08:00 | p | 178 |  | 2027-09-10 15:53
420 | 4204 | CRzwy8942pbCOpcOMW2v | Normal | 20 | 1.6.1.1.4 | 1.6.1.1.4 |  | 2027-07-27 13:00 | p | 244 |  | 2028-03-28 08:59
421 | 4218 | T5g2El1CSAmFZNlboxQh | Normal | 1 | 1.6.1.4 | 1.6.1.4 |  | 2027-08-24 13:00 | p | 245 |  | 2028-04-25 14:35
422 | 6080 | jFrzSNmYyPDtKSvRlBw2 | Normal | 1 | 1.6.1.6 | 1.6.1.6 |  | 2028-09-27 08:00 | p | 203 |  | 2029-04-18 10:49
423 | 5507 | 1r4d5DbY2YIgMhg8HKuO | Normal | 3 | 1.6.3.3.2 | 1.6.3.3.2 |  | 2027-03-19 08:00 | p | 179 |  | 2027-09-14 15:26
424 | 5508 | wHSntGHJkj4aA0wA3fA2 | Normal | 14 | 1.6.3.3.3 | 1.6.3.3.3 |  | 2027-03-24 08:00 | p | 180 |  | 2027-09-20 09:52
425 | 5509 | 1FHP32ReWIveKb3JOWEG | Summary | 44 | 1.6.3.3.4 | 1.6.3.3.4 |  | 2027-05-14 13:00 | p | 163 |  | 2027-10-25 08:24
426 | 5510 | LTFwTsrnxYhrGNFUv7CM | Normal | 12 | 1.6.3.3.4.1 | 1.6.3.3.4.1 |  | 2027-05-14 13:00 | p | 163 |  | 2027-10-25 08:24
427 | 5511 | Od3mMFxB7LjrJLF1slz4 | Normal | 11 | 1.6.3.3.4.2 | 1.6.3.3.4.2 |  | 2027-06-01 08:00 | p | 167 |  | 2027-11-15 08:22
428 | 5512 | Des2hDKSMjcJndTJRzoQ | Normal | 11 | 1.6.3.3.4.3 | 1.6.3.3.4.3 |  | 2027-06-16 08:00 | p | 168 |  | 2027-12-01 10:27
429 | 5513 | z1vb48lrGwUUDjKbD3gr | Normal | 10 | 1.6.3.3.4.4 | 1.6.3.3.4.4 |  | 2027-07-01 08:00 | p | 168 |  | 2027-12-16 16:00
430 | 5514 | leNXdZKmybH4tpy20cQU | Normal | 5 | 1.6.3.3.5 | 1.6.3.3.5 |  | 2027-09-03 08:00 | p | 178 |  | 2028-02-28 16:23
431 | 7307 | eye8r8DevGvPITcdrMUe | Normal | 6 | 1.6.3.11.1.3.4.4 | 1.6.3.11.1.3.4.4 |  | 2027-02-12 08:00 | p | 185 |  | 2027-08-16 08:16
432 | 7308 | BXoPyB4GmzJwvFdrkJ7b | Normal | 1 | 1.6.3.11.1.3.4.5 | 1.6.3.11.1.3.4.5 |  | 2027-02-22 08:00 | p | 182 |  | 2027-08-23 11:44
433 | 7312 | ZHpaj2955bjmxPKFBEf2 | Normal | 2 | 1.6.3.11.1.3.5.3 | 1.6.3.11.1.3.5.3 |  | 2027-02-10 08:00 | q | -730 |  | 2025-02-10 08:00
434 | 7313 | boaUnlKi0h6sKdwgAbmA | Normal | 5 | 1.6.3.11.1.3.5.4 | 1.6.3.11.1.3.5.4 |  | 2027-02-12 08:00 | p | 178 |  | 2027-08-09 09:01
435 | 7314 | zaliCdoIQDW2tx8wBQyt | Normal | 1 | 1.6.3.11.1.3.5.5 | 1.6.3.11.1.3.5.5 |  | 2027-02-24 08:00 | p | 182 |  | 2027-08-25 10:26
436 | 7318 | vWglY3BMmZCigDWMEMyY | Normal | 3 | 1.6.3.11.1.3.6.3 | 1.6.3.11.1.3.6.3 |  | 2027-02-19 08:00 | p | 178 |  | 2027-08-16 16:13
437 | 7319 | Fr6VbOwwg75s6X3Xcfql | Normal | 5 | 1.6.3.11.1.3.6.4 | 1.6.3.11.1.3.6.4 |  | 2027-02-24 08:00 | p | 177 |  | 2027-08-20 16:35
438 | 7320 | MRmQHJYBr9cc2OfLUSYd | Normal | 1 | 1.6.3.11.1.3.6.5 | 1.6.3.11.1.3.6.5 |  | 2027-03-03 08:00 | p | 177 |  | 2027-08-27 14:54
439 | 3680 | E8qsx9NjEz7vaL5H7EFb | Summary | 189 | 1.8.5.1.1 | 1.8.5.1.1 |  | 2025-08-20 08:00 | p | 8 |  | 2025-08-28 15:08
440 | 3681 | wdhUrQuIMTMPn1LoqO1m | Normal | 24 | 1.8.5.1.1.1 | 1.8.5.1.1.1 |  | 2025-08-20 08:00 | p | 8 |  | 2025-08-28 15:08
441 | 3682 | 38PSIqFGHzjKldiudT82 | Summary | 25 | 1.8.5.1.1.4 | 1.8.5.1.1.4 |  | 2025-09-24 08:00 | q | 0 |  | 2025-09-23 14:35
442 | 3683 | JW3LUw009FZ7ddD6CdLX | Normal | 20 | 1.8.5.1.1.4.1 | 1.8.5.1.1.4.1 |  | 2025-09-24 08:00 | q | 0 |  | 2025-09-23 14:35
443 | 3684 | g3f8U3i4iakOhylueut6 | Normal | 5 | 1.8.5.1.1.4.2 | 1.8.5.1.1.4.2 |  | 2025-10-23 08:00 | p | 1 |  | 2025-10-24 11:37
444 | 3685 | eStRoX3vnaDmRLAWk58C | Summary | 40 | 1.8.5.1.1.5 | 1.8.5.1.1.5 |  | 2025-10-30 08:00 | p | 5 |  | 2025-11-04 08:04
445 | 3686 | 7zhxjkpiLTAH9tiW1eYy | Normal | 20 | 1.8.5.1.1.5.1 | 1.8.5.1.1.5.1 |  | 2025-10-30 08:00 | p | 5 |  | 2025-11-04 08:04
446 | 3687 | 0zzWvesUS18qEUfjK5NH | Normal | 5 | 1.8.5.1.1.5.2 | 1.8.5.1.1.5.2 |  | 2026-04-24 08:00 | p | 17 |  | 2026-05-11 09:34
447 | 3688 | zSUYYsBrfiOGi6qJakS6 | Normal | 5 | 1.8.5.1.1.5.3 | 1.8.5.1.1.5.3 |  | 2026-05-01 08:00 | p | 17 |  | 2026-05-18 11:16
448 | 3689 | X7sWUqInOJZ9zcVzmfT1 | Normal | 5 | 1.8.5.1.1.5.4 | 1.8.5.1.1.5.4 |  | 2026-05-08 08:00 | p | 18 |  | 2026-05-26 14:35
449 | 3690 | 8YDpqEvemQaMsfVmGpF8 | Normal | 5 | 1.8.5.1.1.5.5 | 1.8.5.1.1.5.5 |  | 2026-05-15 08:00 | p | 18 |  | 2026-06-02 15:34
450 | 3691 | ofZrlktbiXkVpuhhIeO5 | Summary | 25 | 1.8.5.1.1.6 | 1.8.5.1.1.6 |  | 2025-12-01 08:00 | p | 9 |  | 2025-12-10 10:13
451 | 3692 | xRsKOxB8zGAnVTXugcHQ | Normal | 20 | 1.8.5.1.1.6.1 | 1.8.5.1.1.6.1 |  | 2025-12-01 08:00 | p | 9 |  | 2025-12-10 10:13
452 | 3693 | Hn8rBaTvxeP9Vb10zF48 | Normal | 5 | 1.8.5.1.1.6.2 | 1.8.5.1.1.6.2 |  | 2026-05-15 08:00 | p | 19 |  | 2026-06-03 11:02
453 | 3694 | 4tipOydrC0LTNincaMDW | Summary | 35 | 1.8.5.1.1.7 | 1.8.5.1.1.7 |  | 2025-12-30 08:00 | p | 13 |  | 2026-01-12 11:41
454 | 3695 | lT6NpgfSYqKHtVYFLSzF | Normal | 20 | 1.8.5.1.1.7.1 | 1.8.5.1.1.7.1 |  | 2025-12-30 08:00 | p | 13 |  | 2026-01-12 11:41
455 | 3696 | gijouZuJR1ZVcSfHKSTf | Normal | 5 | 1.8.5.1.1.7.2 | 1.8.5.1.1.7.2 |  | 2026-05-01 08:00 | p | 13 |  | 2026-05-14 09:12
456 | 3697 | 1158ttL4JEmZYV6RmdcS | Normal | 5 | 1.8.5.1.1.7.3 | 1.8.5.1.1.7.3 |  | 2026-05-08 08:00 | p | 14 |  | 2026-05-22 09:19
457 | 3698 | AKCwPpEPQi4iH3XDRpiM | Normal | 5 | 1.8.5.1.1.7.4 | 1.8.5.1.1.7.4 |  | 2026-05-15 08:00 | p | 18 |  | 2026-06-02 08:13
458 | 3699 | AYANEA6OuC5b95kp3uyI | Summary | 30 | 1.8.5.1.1.8 | 1.8.5.1.1.8 |  | 2026-01-29 08:00 | p | 25 |  | 2026-02-23 15:07
459 | 3700 | WE9bFDn3y5M7oiID5UPj | Normal | 20 | 1.8.5.1.1.8.1 | 1.8.5.1.1.8.1 |  | 2026-01-29 08:00 | p | 25 |  | 2026-02-23 15:07
460 | 3701 | CXSHp4tESy2S0nMNpo3C | Normal | 5 | 1.8.5.1.1.8.2 | 1.8.5.1.1.8.2 |  | 2026-06-23 08:00 | q | -4 |  | 2026-06-18 13:33
461 | 3702 | sTuPByKbZEfSXxt0Z2G9 | Normal | 5 | 1.8.5.1.1.8.3 | 1.8.5.1.1.8.3 |  | 2026-06-30 08:00 | q | -3 |  | 2026-06-26 16:22
462 | 3703 | WHZRJAK4v6S9Zk2EBeP3 | Summary | 40 | 1.8.5.1.1.9 | 1.8.5.1.1.9 |  | 2026-02-27 08:00 | p | 21 |  | 2026-03-20 09:09
463 | 3704 | 3CXbrhXJooXd98jlpAkg | Normal | 20 | 1.8.5.1.1.9.1 | 1.8.5.1.1.9.1 |  | 2026-02-27 08:00 | p | 21 |  | 2026-03-20 09:09
464 | 3705 | RO9RShNcg0h7x9fD24Zk | Normal | 5 | 1.8.5.1.1.9.2 | 1.8.5.1.1.9.2 |  | 2026-04-24 08:00 | p | 18 |  | 2026-05-12 15:03
465 | 3706 | w8MhGnhxyXFIHvJdw6bc | Normal | 5 | 1.8.5.1.1.9.3 | 1.8.5.1.1.9.3 |  | 2026-05-01 08:00 | p | 17 |  | 2026-05-18 08:05
466 | 3707 | dJNKgtiJ1M8pNoPOlZcZ | Normal | 5 | 1.8.5.1.1.9.4 | 1.8.5.1.1.9.4 |  | 2026-05-08 08:00 | p | 18 |  | 2026-05-26 15:43
467 | 3708 | 84VtM14FQkMGurZDdBLv | Normal | 5 | 1.8.5.1.1.9.5 | 1.8.5.1.1.9.5 |  | 2026-05-15 08:00 | p | 19 |  | 2026-06-03 13:17
468 | 3709 | gpO5WcJkYid7jZAXZwbn | Summary | 40 | 1.8.5.1.1.10 | 1.8.5.1.1.10 |  | 2026-03-27 08:00 | p | 12 |  | 2026-04-08 15:32
469 | 3710 | KOKaQwRJEoC6vlU3mKjm | Normal | 20 | 1.8.5.1.1.10.1 | 1.8.5.1.1.10.1 |  | 2026-03-27 08:00 | p | 12 |  | 2026-04-08 15:32
470 | 3711 | XXu8BmtFqx4o2r8a6o98 | Normal | 5 | 1.8.5.1.1.10.2 | 1.8.5.1.1.10.2 |  | 2026-04-24 08:00 | p | 14 |  | 2026-05-08 08:52
471 | 3712 | sZwrgRbHYjKWcIa9rVK3 | Normal | 5 | 1.8.5.1.1.10.3 | 1.8.5.1.1.10.3 |  | 2026-05-01 08:00 | p | 14 |  | 2026-05-15 13:48
472 | 3713 | 4NbryuRKpmrExDEDqArG | Normal | 5 | 1.8.5.1.1.10.4 | 1.8.5.1.1.10.4 |  | 2026-05-08 08:00 | p | 18 |  | 2026-05-26 10:36
473 | 3714 | Fbm1iHrhCX8z8SNRXJuq | Normal | 5 | 1.8.5.1.1.10.5 | 1.8.5.1.1.10.5 |  | 2026-05-15 08:00 | p | 17 |  | 2026-06-01 15:04
474 | 6646 | CmmxWTpZgFyyAwkQnNh3 | Normal | 10 | 1.8.5.1.1.2 | 1.8.5.1.1.2 |  | 2026-08-12 08:00 | q | 0 |  | 2026-08-11 10:46
475 | 6647 | hWzCSsDre5WTTpryk1b0 | Normal | 5 | 1.8.5.1.1.3 | 1.8.5.1.1.3 |  | 2026-08-26 08:00 | q | 0 |  | 2026-08-25 08:19
476 | 3715 | V6i7uYjEJBRYHjhIimqJ | Summary | 50 | 1.8.5.1.2 | 1.8.5.1.2 |  | 2026-05-22 08:00 | p | 19 |  | 2026-06-10 13:05
477 | 3716 | bdy5zVX59rD935sK6M5v | Normal | 20 | 1.8.5.1.2.1 | 1.8.5.1.2.1 |  | 2026-05-22 08:00 | p | 19 |  | 2026-06-10 13:05
478 | 3717 | 5PdqCAMtbYgi5VsFO6ls | Normal | 20 | 1.8.5.1.2.4 | 1.8.5.1.2.4 |  | 2026-07-08 08:00 | p | 14 |  | 2026-07-22 15:59
479 | 6671 | 0oTh3tmNX3iVSaVNVmGK | Normal | 5 | 1.8.5.1.2.2 | 1.8.5.1.2.2 |  | 2026-06-23 08:00 | p | 16 |  | 2026-07-09 14:22
480 | 6672 | BKyGOzVPyPwKpI9CyseJ | Normal | 5 | 1.8.5.1.2.3 | 1.8.5.1.2.3 |  | 2026-06-30 08:00 | p | 17 |  | 2026-07-17 14:49
481 | 3718 | vTyTgxcbRSz6H6lqDAEf | Summary | 20 | 1.8.5.1.3 | 1.8.5.1.3 |  | 2026-08-05 08:00 | p | 13 |  | 2026-08-18 08:04
482 | 3719 | B9ymEBZ7zimHMMqNS20Q | Normal | 20 | 1.8.5.1.3.1 | 1.8.5.1.3.1 |  | 2026-08-05 08:00 | p | 13 |  | 2026-08-18 08:04
483 | 3720 | rPRo0RE1uNkj9oG127hu | Summary | 109 | 1.8.5.1.4 | 1.8.5.1.4 |  | 2025-08-20 08:00 | p | 8 |  | 2025-08-28 15:08
484 | 3721 | 45j7fpB55qVEeWfRBgCv | Normal | 1 | 1.8.5.1.4.1 | 1.8.5.1.4.1 |  | 2025-08-20 08:00 | p | 8 |  | 2025-08-28 15:08
485 | 3722 | hYa6Ppkzu6veYWmxHffd | Normal | 27 | 1.8.5.1.4.2 | 1.8.5.1.4.2 |  | 2026-03-31 08:00 | p | 13 |  | 2026-04-13 14:11
486 | 6649 | TeFWDZJ3h8q4yVNptUYE | Normal | 28 | 1.8.5.1.4.3 | 1.8.5.1.4.3 |  | 2026-05-07 08:00 | p | 12 |  | 2026-05-19 16:57
487 | 6650 | FvuNLI4Jaew3VjPpwL3e | Normal | 28 | 1.8.5.1.4.4 | 1.8.5.1.4.4 |  | 2026-06-17 08:00 | p | 14 |  | 2026-07-01 08:32
488 | 6651 | T3J0AzovT4qFTLJ7Lgki | Normal | 15 | 1.8.5.1.4.5 | 1.8.5.1.4.5 |  | 2026-07-29 08:00 | p | 2 |  | 2026-07-31 09:06
489 | 6652 | 0afM7N7hGdWHQjlFenVR | Normal | 10 | 1.8.5.1.4.6 | 1.8.5.1.4.6 |  | 2026-08-19 08:00 | p | 1 |  | 2026-08-20 14:22
490 | 3724 | ZCOxRRLLrh9Pa7VnBAyk | Normal | 27 | 1.8.5.1.5.1 | 1.8.5.1.5.1 |  | 2025-08-20 08:00 | p | 8 |  | 2025-08-28 15:08
491 | 6661 | bQxmmL7mcUsEGpKkQTDo | Normal | 28 | 1.8.5.1.5.2 | 1.8.5.1.5.2 |  | 2026-01-07 08:00 | q | -4 |  | 2026-01-02 15:30
492 | 6662 | CVNpv9CNU8XhfLmVwl8x | Normal | 28 | 1.8.5.1.5.3 | 1.8.5.1.5.3 |  | 2026-02-18 08:00 | q | -4 |  | 2026-02-13 09:19
493 | 6663 | LVExlIxeJ6XB3yqm0Dzs | Normal | 28 | 1.8.5.1.5.4 | 1.8.5.1.5.4 |  | 2026-03-30 08:00 | q | -3 |  | 2026-03-26 09:29
494 | 6664 | Io9oZ1dPqEE9GDlMTPxh | Normal | 28 | 1.8.5.1.5.5 | 1.8.5.1.5.5 |  | 2026-05-07 08:00 | q | -2 |  | 2026-05-04 10:12
495 | 6665 | ycT0qtEFjd4p02S4Ehf1 | Normal | 28 | 1.8.5.1.5.6 | 1.8.5.1.5.6 |  | 2026-06-17 08:00 | q | -4 |  | 2026-06-12 15:49
496 | 6666 | sX3PHseynvzwKI9my2AH | Normal | 15 | 1.8.5.1.5.7 | 1.8.5.1.5.7 |  | 2026-07-29 08:00 | q | -6 |  | 2026-07-22 11:59
497 | 6667 | 0dYk2X7XWh2rSSHkHo2L | Normal | 10 | 1.8.5.1.5.8 | 1.8.5.1.5.8 |  | 2026-08-19 08:00 | p | 2 |  | 2026-08-21 13:12
498 | 6668 | NGuTznXCCG5yuIi6lGQO | Normal | 1 | 1.8.5.1.5.10 | 1.8.5.1.5.10 |  | 2026-08-28 08:00 | q | 0 |  | 2026-08-27 11:29
499 | 6669 | t8MCocRefa6DhiQNsJVn | Normal | 1 | 1.8.5.1.5.11 | 1.8.5.1.5.11 |  | 2026-08-31 08:00 | q | -2 |  | 2026-08-28 14:17
500 | 6670 | vWxPVjk5e7KHTev8998h | Normal | 1 | 1.8.5.1.5.12 | 1.8.5.1.5.12 |  | 2026-09-01 08:00 | q | 0 |  | 2026-08-31 15:33
501 | 3726 | 5hjTNIk7WmpZNtmCLhPN | Summary | 96 | 1.8.5.1.6 | 1.8.5.1.6 |  | 2026-04-16 08:00 | q | -16 |  | 2026-03-30 09:07
502 | 3727 | rGcF2XgkgPtqRDM3KJ2D | Normal | 28 | 1.8.5.1.6.1 | 1.8.5.1.6.1 |  | 2026-04-16 08:00 | q | -16 |  | 2026-03-30 09:07
503 | 3728 | Hgqc9wbzS3SDikBm20zt | Normal | 28 | 1.8.5.1.6.3 | 1.8.5.1.6.3 |  | 2026-06-17 08:00 | q | -12 |  | 2026-06-04 14:40
504 | 6653 | K0AYRckqpyO0HzRrxXG6 | Normal | 15 | 1.8.5.1.6.2 | 1.8.5.1.6.2 |  | 2026-05-27 08:00 | q | -13 |  | 2026-05-13 09:45
505 | 6654 | MMK0qYycfTMCrFAZcf8J | Normal | 15 | 1.8.5.1.6.4 | 1.8.5.1.6.4 |  | 2026-07-29 08:00 | q | -1 |  | 2026-07-27 10:34
506 | 6655 | gl8c5oVG5KfrLbsQSFL4 | Normal | 10 | 1.8.5.1.6.5 | 1.8.5.1.6.5 |  | 2026-08-19 08:00 | q | 0 |  | 2026-08-18 15:28
507 | 3729 | Y6b5KP0DE9c4tlFzqxp3 | Summary | 81 | 1.8.5.1.7 | 1.8.5.1.7 |  | 2026-05-07 08:00 | p | 4 |  | 2026-05-11 13:54
508 | 3730 | TswICWhG0Mjj1DenbPW5 | Normal | 28 | 1.8.5.1.7.1 | 1.8.5.1.7.1 |  | 2026-05-07 08:00 | p | 4 |  | 2026-05-11 13:54
509 | 6626 | 9d2gtkuh8SmNZwArNzpn | Normal | 10 | 1.8.5.1.7.4 | 1.8.5.1.7.4 |  | 2026-08-19 08:00 | p | 1 |  | 2026-08-20 14:19
510 | 6627 | QBgG0JxqOymB6vyjKsRZ | Normal | 28 | 1.8.5.1.7.2 | 1.8.5.1.7.2 |  | 2026-06-17 08:00 | p | 7 |  | 2026-06-24 13:30
511 | 6628 | PAI9VZBMaYriaY1wvhOi | Normal | 15 | 1.8.5.1.7.3 | 1.8.5.1.7.3 |  | 2026-07-29 08:00 | p | 5 |  | 2026-08-03 11:16
512 | 3733 | ufu7SWDoeBfTzZW24BQU | Summary | 189 | 1.8.5.1.9 | 1.8.5.1.9 |  | 2025-07-16 08:00 | p | 29 |  | 2025-08-14 14:39
513 | 3734 | cAszcoDUs4YPdXAiXa4B | Milestone | 0 | 1.8.5.1.9.1 | 1.8.5.1.9.1 |  | 2025-07-16 08:00 | p | 29 |  | 2025-08-14 14:39
514 | 3735 | rgqtw8hyurrfag2amXLA | Normal | 109 | 1.8.5.1.9.2 | 1.8.5.1.9.2 |  | 2025-07-16 08:00 | p | 29 |  | 2025-08-14 14:39
515 | 3736 | eIMYQUSTObIc5Lp6kKBE | Normal | 40 | 1.8.5.1.9.3 | 1.8.5.1.9.3 |  | 2025-12-22 08:00 | p | 30 |  | 2026-01-21 16:20
516 | 3737 | z19Wnme0hJcfEI4IfIQR | Normal | 25 | 1.8.5.1.9.4 | 1.8.5.1.9.4 |  | 2026-07-08 08:00 | p | 0 |  | 2026-07-08 10:02
517 | 6657 | uq5fluI8KT8LkPx57ktn | Normal | 10 | 1.8.5.1.9.5 | 1.8.5.1.9.5 |  | 2026-08-12 08:00 | q | -4 |  | 2026-08-07 13:51
518 | 6658 | ktg0XNnAmjjc1caqICt2 | Normal | 5 | 1.8.5.1.9.6 | 1.8.5.1.9.6 |  | 2026-08-26 08:00 | q | 0 |  | 2026-08-25 09:01
519 | 3738 | bohrZqwOTsvUL4DEUnjh | Summary | 139 | 1.8.5.1.10 | 1.8.5.1.10 |  | 2025-08-20 08:00 | p | 8 |  | 2025-08-28 15:08
520 | 3739 | Ba23bBwg4xGpRd3Ht4kS | Normal | 24 | 1.8.5.1.10.1 | 1.8.5.1.10.1 |  | 2025-08-20 08:00 | p | 8 |  | 2025-08-28 15:08
521 | 3740 | lRtbtcrLyr1QGd0laoJi | Normal | 25 | 1.8.5.1.10.2 | 1.8.5.1.10.2 |  | 2026-03-20 08:00 | q | -2 |  | 2026-03-17 08:46
522 | 3741 | V05WnFKB5t2LuixhoKHO | Normal | 25 | 1.8.5.1.10.3 | 1.8.5.1.10.3 |  | 2026-04-24 08:00 | q | -1 |  | 2026-04-22 13:03
523 | 3742 | LRjVz0hoZuIRlQgcLYzs | Normal | 25 | 1.8.5.1.10.6 | 1.8.5.1.10.6 |  | 2026-07-08 08:00 | q | -1 |  | 2026-07-06 11:40
524 | 6648 | Z5T3n0GGVz8PB0IY5TXC | Normal | 10 | 1.8.5.1.10.5 | 1.8.5.1.10.5 |  | 2026-06-23 08:00 | p | 0 |  | 2026-06-23 13:32
525 | 6656 | tqprQgHoroqT051BXug3 | Normal | 15 | 1.8.5.1.10.4 | 1.8.5.1.10.4 |  | 2026-06-01 08:00 | p | 2 |  | 2026-06-03 13:25
526 | 6659 | NN3Qiea1foOxv05JqXnT | Normal | 10 | 1.8.5.1.10.7 | 1.8.5.1.10.7 |  | 2026-08-12 08:00 | p | 1 |  | 2026-08-13 09:59
527 | 6660 | pWIs4hM6SgH2pFjSQ3qo | Normal | 5 | 1.8.5.1.10.8 | 1.8.5.1.10.8 |  | 2026-08-26 08:00 | p | 0 |  | 2026-08-26 08:24
528 | 6642 | A7Bd82G8YCk8VjEZkcvi | Summary | 135 | 1.8.5.1.8 | 1.8.5.1.8 |  | 2026-02-20 08:00 | p | 10 |  | 2026-03-02 14:51
529 | 3731 | 02LiOyWN4DF8GOeNSP5s | Normal | 20 | 1.8.5.1.8.1 | 1.8.5.1.8.1 |  | 2026-02-20 08:00 | p | 10 |  | 2026-03-02 14:51
530 | 3732 | x85AkT9s5HT2a4U2goND | Normal | 20 | 1.8.5.1.8.8 | 1.8.5.1.8.8 |  | 2026-07-08 08:00 | q | -6 |  | 2026-07-01 11:16
531 | 6629 | n59ds33sZr9JNOobmYWE | Normal | 30 | 1.8.5.1.8.2 | 1.8.5.1.8.2 |  | 2026-03-20 08:00 | p | 4 |  | 2026-03-24 16:36
532 | 6630 | y36QmeQSyS7BZflkeM7e | Normal | 10 | 1.8.5.1.8.3 | 1.8.5.1.8.3 |  | 2026-05-01 08:00 | q | -8 |  | 2026-04-22 08:44
533 | 6631 | Ghk1eKq5exIyUH3hdAeR | Normal | 20 | 1.8.5.1.8.4 | 1.8.5.1.8.4 |  | 2026-05-15 08:00 | q | -8 |  | 2026-05-06 11:48
534 | 6632 | 5y36mClzGR7vkSsODb4C | Normal | 15 | 1.8.5.1.8.5 | 1.8.5.1.8.5 |  | 2026-06-15 08:00 | q | -10 |  | 2026-06-04 15:10
535 | 6633 | uS272glxjETpDiVeJyGv | Normal | 20 | 1.8.5.1.8.6 | 1.8.5.1.8.6 |  | 2026-07-08 08:00 | q | -14 |  | 2026-06-23 10:03
536 | 6634 | 65ghvPiwU0AxSKrC11rG | Normal | 20 | 1.8.5.1.8.7 | 1.8.5.1.8.7 |  | 2026-08-05 08:00 | q | -11 |  | 2026-07-24 09:17
537 | 6643 | sKnPCsxlq51dE8cz52fo | Normal | 10 | 1.8.5.1.8.9 | 1.8.5.1.8.9 |  | 2026-08-05 08:00 | p | 0 |  | 2026-08-05 10:13
538 | 6644 | 0NVu6ABxwy3imKaZ2MTJ | Normal | 10 | 1.8.5.1.8.10 | 1.8.5.1.8.10 |  | 2026-08-19 08:00 | q | 0 |  | 2026-08-18 13:44
539 | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Summary | 1 | 1.8.1 | 1.8.1 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 08:32
540 | 6082 | YsSSuERf5VIDKO5m8eZo | Normal | 1 | 1.8.1.1 | 1.8.1.1 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 08:32
541 | 6313 | 8HYxn50EKf1DU0fX0MF7 | Summary | 391 | 1.8.4 | 1.8.4 |  | 2026-07-08 08:00 | q | -13 |  | 2026-06-24 16:10
542 | 5516 | dd6fm1lW4tBXPtNV5RGW | Summary | 391 | 1.8.4.1 | 1.8.4.1 |  | 2026-07-08 08:00 | q | -13 |  | 2026-06-24 16:10
543 | 5517 | IHfroMkwx3TZoTXYbBOK | Normal | 40 | 1.8.4.1.1 | 1.8.4.1.1 |  | 2026-07-08 08:00 | p | 19 |  | 2026-07-27 08:54
544 | 5518 | V0a5XEJ0jxIkhnpEDg8e | Normal | 40 | 1.8.4.1.2 | 1.8.4.1.2 |  | 2026-07-08 08:00 | q | -13 |  | 2026-06-24 16:10
545 | 5519 | D5sl3M5NpO77EU7TPYT0 | Normal | 40 | 1.8.4.1.3 | 1.8.4.1.3 |  | 2026-07-08 08:00 | p | 2 |  | 2026-07-10 15:07
546 | 5523 | APkwTVep7mUhgmcCl4NB | Milestone | 0 | 1.8.4.1.4 | 1.8.4.1.4 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
547 | 5527 | Mw5Re8SivA42laH7UhJE | Milestone | 0 | 1.8.4.1.5 | 1.8.4.1.5 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
548 | 5332 | Jas5wmBgln6JvMRLtRUk | Summary | 110 | 1.9.3.1 | 1.9.3.1 |  | 2028-02-28 08:00 | p | 206 |  | 2028-09-21 14:19
549 | 5333 | NEZJUiuEFBeqDBEbXbzQ | Milestone | 0 | 1.9.3.1.1 | 1.9.3.1.1 |  | 2028-02-28 08:00 | p | 206 |  | 2028-09-21 14:19
550 | 5334 | 5Bt8vyiG2PJ2FKCjQPP1 | Summary | 74 | 1.9.3.1.2 | 1.9.3.1.2 |  | 2028-02-28 08:00 | p | 206 |  | 2028-09-21 14:19
551 | 6471 | xmZvSzAhf2D9ir29atKO | Normal | 8 | 1.9.3.1.2.1 | 1.9.3.1.2.1 |  | 2028-02-28 08:00 | p | 206 |  | 2028-09-21 14:19
552 | 6472 | j0VQ7fJsNHb1HpOVRoJN | Normal | 7 | 1.9.3.1.2.2 | 1.9.3.1.2.2 |  | 2028-03-09 08:00 | p | 208 |  | 2028-10-03 13:03
553 | 6473 | FN1N5cBOnOQJN0lvtY6J | Normal | 5 | 1.9.3.1.2.3 | 1.9.3.1.2.3 |  | 2028-03-20 08:00 | p | 207 |  | 2028-10-13 10:57
554 | 6474 | k77H7bJ7aRKhBrZeZFzu | Normal | 10 | 1.9.3.1.2.4 | 1.9.3.1.2.4 |  | 2028-03-27 08:00 | p | 207 |  | 2028-10-20 15:59
555 | 6475 | TkBVMCiZTEhYxjcnMNRI | Normal | 8 | 1.9.3.1.2.5 | 1.9.3.1.2.5 |  | 2028-04-10 08:00 | p | 207 |  | 2028-11-03 16:29
556 | 6476 | HdsfOo0UbW7iVGjY7L1O | Normal | 10 | 1.9.3.1.2.6 | 1.9.3.1.2.6 |  | 2028-04-20 08:00 | p | 208 |  | 2028-11-14 08:30
557 | 6477 | m1G8PrmdvRxZwBbLlVUQ | Normal | 7 | 1.9.3.1.2.7 | 1.9.3.1.2.7 |  | 2028-05-04 08:00 | p | 210 |  | 2028-11-30 16:13
558 | 6478 | ZDDqpCGw2ELQiAxZVJFo | Normal | 7 | 1.9.3.1.2.8 | 1.9.3.1.2.8 |  | 2028-05-15 08:00 | p | 210 |  | 2028-12-11 15:49
559 | 6479 | i51TyrBkECB0t7wKJruE | Normal | 7 | 1.9.3.1.2.9 | 1.9.3.1.2.9 |  | 2028-05-24 08:00 | p | 210 |  | 2028-12-20 10:18
560 | 6480 | XeKgBzwPereNdZmXnTFt | Normal | 5 | 1.9.3.1.2.10 | 1.9.3.1.2.10 |  | 2028-06-02 08:00 | p | 213 |  | 2029-01-01 14:10
561 | 5335 | fBEkx0xCtVpw1OeE4jLB | Summary | 25 | 1.9.3.1.3 | 1.9.3.1.3 |  | 2028-06-09 08:00 | p | 213 |  | 2029-01-08 14:25
562 | 5336 | FIhKbBOHnlTp0loBBfvV | Normal | 3 | 1.9.3.1.3.1 | 1.9.3.1.3.1 |  | 2028-06-13 08:00 | p | 211 |  | 2029-01-10 10:13
563 | 5337 | TPAbtCx4KhMQiN0iVD1F | Normal | 0 | 1.9.3.1.3.2 | 1.9.3.1.3.2 |  | 2028-06-15 13:24 | p | 213 |  | 2029-01-15 10:57
564 | 5338 | NXWa8B3rzsUFws6lYttF | Normal | 5 | 1.9.3.1.3.3 | 1.9.3.1.3.3 |  | 2028-06-09 08:00 | p | 213 |  | 2029-01-08 14:25
565 | 5339 | o98eRuEZGwoxxa1Byl7H | Normal | 5 | 1.9.3.1.3.4 | 1.9.3.1.3.4 |  | 2028-06-09 08:00 | p | 213 |  | 2029-01-08 15:54
566 | 5340 | lQJTDBnvPE8mTPnPre3v | Normal | 10 | 1.9.3.1.3.5 | 1.9.3.1.3.5 |  | 2028-06-16 08:00 | p | 213 |  | 2029-01-15 16:16
567 | 5341 | nevxwfefPkBzu42CDbNd | Normal | 10 | 1.9.3.1.3.6 | 1.9.3.1.3.6 |  | 2028-06-30 08:00 | p | 209 |  | 2029-01-25 15:02
568 | 5342 | s0JiBiXDLP6oybWmkZ43 | Normal | 6 | 1.9.3.1.4 | 1.9.3.1.4 |  | 2028-07-14 08:00 | p | 210 |  | 2029-02-09 10:28
569 | 5343 | NROXqcLUoQ0RLz64rMVc | Normal | 5 | 1.9.3.1.5 | 1.9.3.1.5 |  | 2028-07-24 08:00 | p | 210 |  | 2029-02-19 08:26
570 | 5344 | Kw3Fj6kwk5uOl7tQyqrL | Milestone | 0 | 1.9.3.1.6 | 1.9.3.1.6 |  | 2028-07-31 08:00 | p | 210 |  | 2029-02-26 09:11
571 | 795 | 85yV4lhIxXIziyB5R2QA | Normal | 1 | 1.9.9.1 | 1.9.9.1 |  | 2028-09-27 08:00 | p | 203 |  | 2029-04-18 10:45
572 | 844 | 1qfp8o9PQxr9vZvO7S5k | Normal | 1 | 1.9.9.4 | 1.9.9.4 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 10:18
573 | 866 | 0rLFG0X22Uukcn0axQTO | Normal | 50 | 1.9.9.7.2.6 | 1.9.9.7.2.6 |  | 2027-08-11 13:00 | p | 205 |  | 2028-03-03 16:11
574 | 869 | 8QCM3LZ8SN5y0jCLtGNh | Summary | 129 | 1.9.9.7.2.7 | 1.9.9.7.2.7 |  | 2027-10-20 13:00 | p | 207 |  | 2028-05-15 09:08
575 | 6419 | NORPsF566zq8VZyN1UzF | Normal | 10 | 1.9.9.7.2.7.1 | 1.9.9.7.2.7.1 |  | 2027-10-20 13:00 | p | 207 |  | 2028-05-15 09:08
576 | 6420 | 043wOhyyEd8vJkuUBkFf | Normal | 40 | 1.9.9.7.2.7.2 | 1.9.9.7.2.7.2 |  | 2027-11-03 13:00 | p | 208 |  | 2028-05-29 15:20
577 | 6421 | JZROXyECnTBG3SBjYZJ8 | Normal | 79 | 1.9.9.7.2.7.3 | 1.9.9.7.2.7.3 |  | 2027-12-29 13:00 | p | 202 |  | 2028-07-19 11:25
578 | 4667 | gXRr1908PexMoLIDosFv | Normal | 100 | 1.9.9.14.3 | 1.9.9.14.3 |  | 2027-11-09 13:00 | p | 217 |  | 2028-06-13 16:24
579 | 4668 | G3SLCzd88WLMRnAF5Et7 | Normal | 0 | 1.9.9.14.4 | 1.9.9.14.4 |  | 2028-05-22 13:00 | p | 199 |  | 2028-12-08 10:18
580 | 4669 | aeClBbTsJ3qrKHWqQ1Rw | Normal | 40 | 1.9.9.14.5 | 1.9.9.14.5 |  | 2028-03-28 13:00 | p | 205 |  | 2028-10-20 10:30
581 | 4679 | rpzkOhA603pApmNdMeVE | Normal | 0 | 1.9.9.14.6 | 1.9.9.14.6 |  | 2028-05-23 13:00 | p | 201 |  | 2028-12-11 08:48
582 | 5787 | r6JEZEKCpBbNZRe1W7Ef | Normal | 91 | 1.9.9.14.2 | 1.9.9.14.2 |  | 2027-07-05 13:00 | p | 185 |  | 2028-01-07 09:36
583 | 899 | w1GWQdUx9oG06oopRYZx | Summary | 24 | 1.9.9.15 | 1.9.9.15 |  | 2028-04-19 13:00 | p | 204 |  | 2028-11-10 11:17
584 | 900 | ANUK0HdVlI2Jd5hSzs0f | Milestone | 0 | 1.9.9.15.1 | 1.9.9.15.1 |  | 2028-04-19 13:00 | p | 204 |  | 2028-11-10 11:17
585 | 901 | HcFqHITfVdYMyzVb3S8v | Normal | 18 | 1.9.9.15.2 | 1.9.9.15.2 |  | 2028-04-27 08:00 | p | 203 |  | 2028-11-16 16:26
586 | 902 | nIjAIVHCOoi1ijXym0cI | Normal | 3 | 1.9.9.15.3 | 1.9.9.15.3 |  | 2028-04-19 13:00 | p | 204 |  | 2028-11-10 11:17
587 | 903 | UDGopgZ2sb1QsQEooZ9G | Normal | 8 | 1.9.9.15.4 | 1.9.9.15.4 |  | 2028-04-24 13:00 | p | 204 |  | 2028-11-15 11:13
588 | 904 | 4CH3NSJx1luiHbrrAEJg | Normal | 2 | 1.9.9.15.5 | 1.9.9.15.5 |  | 2028-05-23 08:00 | p | 206 |  | 2028-12-15 11:11
589 | 905 | MxRWNVEH6ZVBPqNnA2hI | Normal | 8 | 1.9.9.15.6 | 1.9.9.15.6 |  | 2028-05-04 13:00 | p | 203 |  | 2028-11-24 11:14
590 | 906 | PL0zn2U2NPPXQqakkHLb | Normal | 5 | 1.9.9.15.7 | 1.9.9.15.7 |  | 2028-05-16 13:00 | p | 201 |  | 2028-12-04 11:28
591 | 907 | 5mTVpVcHzmsYLVY8xpKs | Normal | 5 | 1.9.9.15.8 | 1.9.9.15.8 |  | 2028-05-16 13:00 | p | 201 |  | 2028-12-04 09:48
592 | 914 | q0UeyWaeMXFoeUDjjzhX | Summary | 18 | 1.9.9.5 | 1.9.9.5 |  | 2028-09-04 08:00 | p | 198 |  | 2029-03-21 13:04
593 | 915 | jxzEE3EBeGWt1nE3uHcj | Summary | 18 | 1.9.9.5.1 | 1.9.9.5.1 |  | 2028-09-04 08:00 | p | 198 |  | 2029-03-21 13:04
594 | 916 | d4bxhxtQW3GaLrDrUlf9 | Normal | 17 | 1.9.9.5.1.1 | 1.9.9.5.1.1 |  | 2028-09-04 08:00 | p | 198 |  | 2029-03-21 13:04
595 | 917 | mbDdHZHm9OoYye329Ue6 | Normal | 1 | 1.9.9.5.1.2 | 1.9.9.5.1.2 |  | 2028-09-27 08:00 | p | 202 |  | 2029-04-17 16:44
596 | 4538 | aTyUglf0WPX6H8Zd17Iq | Summary | 71 | 1.9.9.16 | 1.9.9.16 |  | 2028-05-23 08:00 | p | 199 |  | 2028-12-08 14:59
597 | 6509 | sp3XFaPtGgzrVeC1wvvV | Normal | 10 | 1.9.9.16.3 | 1.9.9.16.3 |  | 2028-05-25 08:00 | p | 208 |  | 2028-12-19 10:21
598 | 6510 | dar9hgzhSUYJxC1MeoTS | Normal | 10 | 1.9.9.16.4 | 1.9.9.16.4 |  | 2028-05-25 08:00 | p | 201 |  | 2028-12-12 13:13
599 | 6513 | IG8fHoH3vjERJ6iSB3Rj | Normal | 36 | 1.9.9.16.5 | 1.9.9.16.5 |  | 2028-06-08 08:00 | p | 203 |  | 2028-12-28 15:13
600 | 6514 | imV319lPgBwI8oLVT5sB | Normal | 1 | 1.9.9.16.2 | 1.9.9.16.2 |  | 2028-05-24 08:00 | p | 201 |  | 2028-12-11 13:54
601 | 6515 | a8Kdm3F6uLeIN4SEhwX9 | Normal | 1 | 1.9.9.16.1 | 1.9.9.16.1 |  | 2028-05-23 08:00 | p | 199 |  | 2028-12-08 14:59
602 | 5783 | BOvEGIzyTacp1vvD9v7M | Normal | 1 | 1.9.9.2 | 1.9.9.2 |  | 2028-04-18 13:00 | p | 204 |  | 2028-11-09 11:40
603 | 6130 | 3AAePL8Vt5bI7qDxsaDX | Normal | 20 | 1.7.4.2.3 | 1.7.4.2.3 |  | 2025-07-23 08:00 | p | 8 |  | 2025-07-31 11:26
604 | 6685 | 2nkdQcaVv7LgM8d4dFld | Summary | 1 | 1.9.9.12 | 1.9.9.12 |  | 2028-07-28 08:00 | p | 210 |  | 2029-02-23 10:07
605 | 6687 | RiyOBd4mBIE5Cq6C0A4h | Normal | 1 | 1.9.9.12.1 | 1.9.9.12.1 |  | 2028-07-28 08:00 | p | 210 |  | 2029-02-23 10:07
606 | 7388 | subTjNOw9tjXphx2xXzW | Summary | 324 | 1.9.9.13 | 1.9.9.13 |  | 2027-07-02 13:00 | p | 200 |  | 2028-01-19 11:32
607 | 7389 | xTfJP5JFEqXIDmLDdKVZ | Summary | 43 | 1.9.9.13.1 | 1.9.9.13.1 |  | 2027-07-02 13:00 | p | 200 |  | 2028-01-19 11:32
608 | 7390 | GV26YG775A5KHHrrMIRV | Summary | 32 | 1.9.9.13.1.1 | 1.9.9.13.1.1 |  | 2027-07-02 13:00 | p | 200 |  | 2028-01-19 11:32
609 | 7391 | UumEMUqxjwvZXtHBx1rg | Normal | 3 | 1.9.9.13.1.1.1 | 1.9.9.13.1.1.1 |  | 2027-07-02 13:00 | p | 200 |  | 2028-01-19 11:32
610 | 7392 | ylVP19AJuwY485wgDJEG | Normal | 10 | 1.9.9.13.1.1.2 | 1.9.9.13.1.1.2 |  | 2027-07-12 08:00 | p | 200 |  | 2028-01-28 14:32
611 | 7393 | RzIyrLZKRoqlWdOJYpGf | Normal | 3 | 1.9.9.13.1.1.3 | 1.9.9.13.1.1.3 |  | 2027-07-16 13:00 | p | 201 |  | 2028-02-02 13:28
612 | 7394 | zHoRZ9fggWfe9FGnA954 | Normal | 10 | 1.9.9.13.1.1.4 | 1.9.9.13.1.1.4 |  | 2027-07-23 13:00 | p | 201 |  | 2028-02-09 14:40
613 | 7395 | PMjQe1vYJ6mxUbNABucF | Normal | 3 | 1.9.9.13.1.1.5 | 1.9.9.13.1.1.5 |  | 2027-07-30 13:00 | p | 201 |  | 2028-02-17 09:27
614 | 7396 | gQKdIVV4LZyvHUAfFFFg | Normal | 10 | 1.9.9.13.1.1.6 | 1.9.9.13.1.1.6 |  | 2027-08-06 08:00 | p | 200 |  | 2028-02-22 14:55
615 | 7397 | gmOEJCOmO6SQ6HMlGXfq | Summary | 12 | 1.9.9.13.1.2 | 1.9.9.13.1.2 |  | 2027-08-16 13:00 | p | 198 |  | 2028-03-01 16:18
616 | 7398 | ItOQSxoXEYWD5clVNK0n | Normal | 3 | 1.9.9.13.1.2.1 | 1.9.9.13.1.2.1 |  | 2027-08-16 13:00 | p | 198 |  | 2028-03-01 16:18
617 | 7399 | cXpFrNuZR7O8wPV6KZK3 | Normal | 9 | 1.9.9.13.1.2.2 | 1.9.9.13.1.2.2 |  | 2027-08-19 13:00 | p | 200 |  | 2028-03-06 16:52
618 | 7400 | VGtguPWpaIPmF0Ojsz8a | Summary | 176 | 1.9.9.13.2 | 1.9.9.13.2 |  | 2027-08-31 08:00 | p | 198 |  | 2028-03-16 11:16
619 | 7401 | H3MyBOTVJ4MGxcXcavMD | Normal | 2 | 1.9.9.13.2.1 | 1.9.9.13.2.1 |  | 2027-08-31 08:00 | p | 198 |  | 2028-03-16 11:16
620 | 7402 | pMiEhGou1QDK96DPu7Q8 | Normal | 1 | 1.9.9.13.2.2 | 1.9.9.13.2.2 |  | 2027-09-01 13:00 | p | 200 |  | 2028-03-20 09:05
621 | 7403 | pHZBXvaYVwug2p7gN6jp | Summary | 17 | 1.9.9.13.2.3 | 1.9.9.13.2.3 |  | 2027-09-02 13:00 | p | 200 |  | 2028-03-21 09:16
622 | 7404 | EvHLT3cR3tYYGwcq6SC1 | Normal | 5 | 1.9.9.13.2.3.1 | 1.9.9.13.2.3.1 |  | 2027-09-02 13:00 | p | 200 |  | 2028-03-21 09:16
623 | 7405 | 5GpI6xkgfIoVOnU9egD8 | Normal | 12 | 1.9.9.13.2.3.2 | 1.9.9.13.2.3.2 |  | 2027-09-09 13:00 | p | 200 |  | 2028-03-28 09:50
624 | 7406 | WxzG2sAIbVYYiem4v3mk | Normal | 12 | 1.9.9.13.2.3.3 | 1.9.9.13.2.3.3 |  | 2027-09-09 13:00 | p | 201 |  | 2028-03-29 08:09
625 | 7407 | 0eiyRK1I5mgUCdtpXpqY | Summary | 44 | 1.9.9.13.2.4 | 1.9.9.13.2.4 |  | 2027-09-27 13:00 | p | 198 |  | 2028-04-12 13:04
626 | 7408 | uKngouP2QMMQmu6HFm0I | Normal | 11 | 1.9.9.13.2.4.1 | 1.9.9.13.2.4.1 |  | 2027-09-27 13:00 | p | 198 |  | 2028-04-12 13:04
627 | 7409 | C7eZzAQkBbKewE4wmmOD | Normal | 11 | 1.9.9.13.2.4.2 | 1.9.9.13.2.4.2 |  | 2027-10-12 13:00 | p | 196 |  | 2028-04-26 11:31
628 | 7410 | VCdEPtbQjRcgNUnNprkZ | Normal | 11 | 1.9.9.13.2.4.3 | 1.9.9.13.2.4.3 |  | 2027-10-27 13:00 | p | 196 |  | 2028-05-10 14:48
629 | 7411 | OzHccTXr25Mf4pmiIMuT | Normal | 11 | 1.9.9.13.2.4.4 | 1.9.9.13.2.4.4 |  | 2027-11-11 13:00 | p | 196 |  | 2028-05-25 13:17
630 | 7412 | obz02flxb00pYjKUpMNx | Normal | 12 | 1.9.9.13.2.5 | 1.9.9.13.2.5 |  | 2027-12-30 13:00 | p | 203 |  | 2028-07-20 13:41
631 | 7413 | xazO1XwNp5eROWJmaREL | Summary | 36 | 1.9.9.13.2.6 | 1.9.9.13.2.6 |  | 2027-11-26 13:00 | p | 199 |  | 2028-06-13 08:48
632 | 7414 | DrM34eAIT9imz4vRHbHm | Normal | 2 | 1.9.9.13.2.6.1 | 1.9.9.13.2.6.1 |  | 2027-11-26 13:00 | p | 199 |  | 2028-06-13 08:48
633 | 7415 | RsULMViXRZoYahxlMUQ4 | Normal | 20 | 1.9.9.13.2.6.2 | 1.9.9.13.2.6.2 |  | 2027-11-30 13:00 | p | 197 |  | 2028-06-15 09:53
634 | 7416 | U8irVJqpjJwQWU5FcpMo | Normal | 3 | 1.9.9.13.2.6.3 | 1.9.9.13.2.6.3 |  | 2027-12-28 13:00 | p | 203 |  | 2028-07-19 11:22
635 | 7417 | yrCdbpyUp4mqkbXiv5Nc | Normal | 6 | 1.9.9.13.2.6.4 | 1.9.9.13.2.6.4 |  | 2027-12-31 13:00 | p | 206 |  | 2028-07-24 15:52
636 | 7418 | Iw5sTi596kP8d52cBWYm | Normal | 5 | 1.9.9.13.2.6.5 | 1.9.9.13.2.6.5 |  | 2028-01-10 13:00 | p | 203 |  | 2028-08-01 09:30
637 | 7419 | s9reBpLseCBnslseiKA6 | Normal | 2 | 1.9.9.13.2.7 | 1.9.9.13.2.7 |  | 2028-01-17 13:00 | p | 204 |  | 2028-08-08 14:51
638 | 7420 | ia01m1zWF4qAvVLVg5It | Summary | 54 | 1.9.9.13.2.8 | 1.9.9.13.2.8 |  | 2028-01-19 13:00 | p | 204 |  | 2028-08-11 09:38
639 | 7421 | 5PvQN5TGe8y7KbK2rRhO | Normal | 8 | 1.9.9.13.2.8.1 | 1.9.9.13.2.8.1 |  | 2028-01-19 13:00 | p | 204 |  | 2028-08-11 09:38
640 | 7422 | fj19MvsSAfWHeVGXiA1H | Normal | 5 | 1.9.9.13.2.8.2 | 1.9.9.13.2.8.2 |  | 2028-02-25 13:00 | p | 202 |  | 2028-09-15 08:52
641 | 7423 | hs9Gt4WgG9pENnEIaC7X | Normal | 14 | 1.9.9.13.2.8.3 | 1.9.9.13.2.8.3 |  | 2028-01-31 13:00 | p | 205 |  | 2028-08-23 13:49
642 | 7424 | WqCakGr8mHgCENNWHHjW | Normal | 5 | 1.9.9.13.2.8.4 | 1.9.9.13.2.8.4 |  | 2028-03-03 13:00 | p | 202 |  | 2028-09-21 14:48
643 | 7425 | Pv27HXd826jlfuUJmTLH | Normal | 20 | 1.9.9.13.2.8.5 | 1.9.9.13.2.8.5 |  | 2028-02-18 13:00 | p | 207 |  | 2028-09-13 10:12
644 | 7426 | UjcYgNHyPV73fWy2GGNA | Normal | 5 | 1.9.9.13.2.8.6 | 1.9.9.13.2.8.6 |  | 2028-03-10 13:00 | p | 202 |  | 2028-09-29 10:21
645 | 7427 | 5QMAV8W19uO0knxuRgYc | Normal | 6 | 1.9.9.13.2.8.7 | 1.9.9.13.2.8.7 |  | 2028-03-17 13:00 | p | 205 |  | 2028-10-09 10:02
646 | 7428 | C3roUkJ3GEdxAvfnxnUE | Normal | 6 | 1.9.9.13.2.8.8 | 1.9.9.13.2.8.8 |  | 2028-03-17 13:00 | p | 205 |  | 2028-10-09 10:02
647 | 7429 | GMfJSktlv5oUXA5LFNgA | Normal | 6 | 1.9.9.13.2.8.9 | 1.9.9.13.2.8.9 |  | 2028-03-27 13:00 | p | 204 |  | 2028-10-18 08:20
648 | 7430 | AjX0fOJfuCWTWcoFWrZe | Summary | 11 | 1.9.9.13.2.9 | 1.9.9.13.2.9 |  | 2028-04-04 13:00 | p | 203 |  | 2028-10-24 13:16
649 | 7431 | YKkcKAxBNBkRs3Gs0cxp | Normal | 7 | 1.9.9.13.2.9.1 | 1.9.9.13.2.9.1 |  | 2028-05-09 08:00 | p | 206 |  | 2028-12-01 11:26
650 | 7432 | HbmHLQTrqR87hE03VIdq | Normal | 3 | 1.9.9.13.2.9.2 | 1.9.9.13.2.9.2 |  | 2028-04-04 13:00 | p | 203 |  | 2028-10-24 13:16
651 | 7433 | FxBsJSw4ZNEIyIQA8bL9 | Normal | 8 | 1.9.9.13.2.9.3 | 1.9.9.13.2.9.3 |  | 2028-04-07 13:00 | p | 202 |  | 2028-10-27 11:33
652 | 7434 | MkjgnYEnwrIrITdXMEl9 | Milestone | 0 | 1.9.9.13.3 | 1.9.9.13.3 |  | 2028-07-28 08:00 | p | 201 |  | 2029-02-14 13:47
653 | 7435 | nSo6tYchIu2Aw4YtE45u | Summary | 44 | 1.9.9.13.4 | 1.9.9.13.4 |  | 2028-07-28 08:00 | p | 201 |  | 2029-02-14 13:47
654 | 7436 | Y83lvWkQwfsc3dMGwfVN | Summary | 30 | 1.9.9.13.4.1 | 1.9.9.13.4.1 |  | 2028-07-28 08:00 | p | 201 |  | 2029-02-14 13:47
655 | 7437 | E8EwVgjFQaEPGP66WsCb | Summary | 30 | 1.9.9.13.4.1.1 | 1.9.9.13.4.1.1 |  | 2028-07-31 08:00 | p | 210 |  | 2029-02-26 09:11
656 | 7438 | y2P0mgWq1uFkM4aVxtQJ | Normal | 15 | 1.9.9.13.4.1.1.1 | 1.9.9.13.4.1.1.1 |  | 2028-07-31 08:00 | p | 210 |  | 2029-02-26 09:11
657 | 7439 | nsJKxwZOWJc3LdYsNOwr | Normal | 5 | 1.9.9.13.4.1.1.2 | 1.9.9.13.4.1.1.2 |  | 2028-08-21 08:00 | p | 205 |  | 2029-03-14 13:50
658 | 7440 | 3ZzL4TktDwncii0hY2dA | Normal | 10 | 1.9.9.13.4.1.1.3 | 1.9.9.13.4.1.1.3 |  | 2028-08-28 08:00 | p | 205 |  | 2029-03-21 09:51
659 | 7441 | IcgrxiRjEYJLwuugm8N7 | Summary | 30 | 1.9.9.13.4.1.2 | 1.9.9.13.4.1.2 |  | 2028-07-28 08:00 | p | 201 |  | 2029-02-14 13:47
660 | 7442 | B8zfbswYxyRxHa21jaE6 | Normal | 15 | 1.9.9.13.4.1.2.1 | 1.9.9.13.4.1.2.1 |  | 2028-07-28 08:00 | p | 201 |  | 2029-02-14 13:47
661 | 7443 | lvFKaF8Jtq8DkkB0s9nv | Normal | 15 | 1.9.9.13.4.1.2.2 | 1.9.9.13.4.1.2.2 |  | 2028-08-18 08:00 | p | 202 |  | 2029-03-08 09:14
662 | 7444 | 419IszMaZW6XNIQptprk | Normal | 20 | 1.9.9.13.4.1.3 | 1.9.9.13.4.1.3 |  | 2028-08-14 08:00 | p | 196 |  | 2029-02-26 08:37
663 | 7445 | oNfFp4VAwKEpoSujTbHZ | Normal | 10 | 1.9.9.13.4.1.4 | 1.9.9.13.4.1.4 |  | 2028-08-28 08:00 | p | 199 |  | 2029-03-15 10:59
664 | 7446 | NnBZUSVumxDXwVdCLN8g | Summary | 12 | 1.9.9.13.4.2 | 1.9.9.13.4.2 |  | 2028-09-11 08:00 | p | 203 |  | 2029-04-02 10:47
665 | 7447 | CAsJ3atkVCS14hehUB9Y | Normal | 4 | 1.9.9.13.4.2.1 | 1.9.9.13.4.2.1 |  | 2028-09-11 08:00 | p | 203 |  | 2029-04-02 10:47
666 | 7448 | 8tMCh2h8AwE53TPPkfEv | Normal | 3 | 1.9.9.13.4.2.2 | 1.9.9.13.4.2.2 |  | 2028-09-12 08:00 | p | 203 |  | 2029-04-03 11:47
667 | 7449 | LaZxXVdUnGzqswRGUiV5 | Normal | 7 | 1.9.9.13.4.2.3 | 1.9.9.13.4.2.3 |  | 2028-09-15 08:00 | p | 203 |  | 2029-04-06 13:07
668 | 7450 | F3vtt1T8lz7mQWFPgUKT | Normal | 2 | 1.9.9.13.4.3 | 1.9.9.13.4.3 |  | 2028-09-26 08:00 | p | 203 |  | 2029-04-17 15:30
669 | 7451 | nShmtMdGhMi3SzNeAZjW | Milestone | 0 | 1.9.9.13.4.4 | 1.9.9.13.4.4 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 10:06
670 | 7510 | 4i5VLTIa98HteWhFzYjv | Normal | 3 | 1.7.10.24 | 1.7.10.24 |  | 2027-06-29 13:00 | p | 199 |  | 2028-01-14 13:50
671 | 7511 | tHPdmsBqm9kHM69dtq3h | Normal | 7 | 1.7.10.25 | 1.7.10.25 |  | 2027-07-07 13:00 | p | 201 |  | 2028-01-24 13:11
672 | 7512 | hmOTDv9qQbSDcHudIm9x | Normal | 7 | 1.7.10.26 | 1.7.10.26 |  | 2027-07-21 13:00 | p | 201 |  | 2028-02-07 16:50
673 | 7513 | NbiRgc4Tdvxa900kw7Xq | Normal | 8 | 1.7.10.27 | 1.7.10.27 |  | 2027-08-04 13:00 | p | 201 |  | 2028-02-22 08:42
674 | 7539 | ROucR7pug9aGzObG8pvW | Normal | 1 | 1.7.10.8 | 1.7.10.8 |  | 2027-06-17 13:00 | p | 200 |  | 2028-01-04 09:10
675 | 7540 | njszlznNRnCyRW2hgoMI | Normal | 10 | 1.7.10.9 | 1.7.10.9 |  | 2027-06-18 13:00 | p | 200 |  | 2028-01-05 09:47
676 | 7541 | R63tw5xkvmDGiWpIPQRa | Normal | 1 | 1.7.10.10 | 1.7.10.10 |  | 2027-07-01 13:00 | p | 200 |  | 2028-01-18 11:25
677 | 7542 | E3YdLEfamF0eZCISJiqw | Normal | 10 | 1.7.10.11 | 1.7.10.11 |  | 2027-06-18 13:00 | p | 201 |  | 2028-01-06 08:11
678 | 7543 | nhpJxewK7uClQLzGXJQJ | Normal | 1 | 1.7.10.12 | 1.7.10.12 |  | 2027-07-01 13:00 | p | 200 |  | 2028-01-18 09:26
679 | 7544 | cfuUTFyz3WOPAOOiNQOb | Normal | 1 | 1.7.10.13 | 1.7.10.13 |  | 2027-07-01 13:00 | p | 201 |  | 2028-01-18 13:55
680 | 1485 | R0QJsNVi0JzXq4FadBdS | Normal | 20 | 1.9.7.18.4 | 1.9.7.18.4 |  | 2026-04-16 08:00 | q | -7 |  | 2026-04-08 09:17
681 | 1486 | 9VYbXOz4xuMas0igEBkB | Summary | 56 | 1.9.7.18.6 | 1.9.7.18.6 |  | 2026-06-12 08:00 | q | 0 |  | 2026-06-11 09:29
682 | 6540 | BF294XdCZHw2CEg81bOs | Normal | 19 | 1.9.7.18.6.1 | 1.9.7.18.6.1 |  | 2026-06-12 08:00 | q | 0 |  | 2026-06-11 09:29
683 | 6541 | X8phwYugZBkIbn0OysQW | Normal | 19 | 1.9.7.18.6.2 | 1.9.7.18.6.2 |  | 2026-07-13 08:00 | q | -3 |  | 2026-07-09 08:19
684 | 6542 | fphO3nZhiS43G9CLfKfB | Normal | 18 | 1.9.7.18.6.3 | 1.9.7.18.6.3 |  | 2026-08-07 08:00 | q | 0 |  | 2026-08-06 15:00
685 | 1490 | hF9FI1LNvFfgTTXhqPsR | Normal | 77 | 1.9.7.18.2 | 1.9.7.18.2 |  | 2025-12-23 08:00 | q | -10 |  | 2025-12-12 08:59
686 | 1491 | XpTPefWn9TT3C06gw8rA | Normal | 1 | 1.9.7.18.3 | 1.9.7.18.3 |  | 2026-04-15 08:00 | q | -7 |  | 2026-04-07 08:06
687 | 1495 | 0kid3Dd3U5gCQNrt2pwY | Normal | 1 | 1.9.7.18.8 | 1.9.7.18.8 |  | 2028-05-19 08:00 | p | 199 |  | 2028-12-04 14:21
688 | 1504 | ndaml8HRsqEWzWIKrI7h | Normal | 5 | 1.9.7.18.10 | 1.9.7.18.10 |  | 2028-02-23 08:00 | p | 204 |  | 2028-09-14 09:55
689 | 4587 | 5uS9ktvplxYkrLheR3Q9 | Normal | 20 | 1.9.7.18.5 | 1.9.7.18.5 |  | 2026-05-14 08:00 | q | -6 |  | 2026-05-07 16:50
690 | 1496 | 5t2MhilpkZRDQA3VTcGS | Normal | 48 | 1.9.7.7 | 1.9.7.7 |  | 2028-05-22 08:00 | p | 197 |  | 2028-12-05 15:08
691 | 1505 | 4c3z8pWafVxAWNC1MpC9 | Normal | 106 | 1.9.7.8 | 1.9.7.8 |  | 2028-03-01 08:00 | p | 204 |  | 2028-09-21 14:24
692 | 1531 | KX1eD2ASIZaZBZuqoVp4 | Normal | 1 | 1.9.7.14.2 | 1.9.7.14.2 |  | 2028-08-21 08:00 | p | 200 |  | 2029-03-09 14:09
693 | 1532 | fQ3wcWF8uEWMRGpUCxEA | Normal | 1 | 1.9.7.14.4 | 1.9.7.14.4 |  | 2028-08-23 08:00 | p | 202 |  | 2029-03-13 11:06
694 | 1533 | juvdtwZkjArAkPOzLrhN | Normal | 15 | 1.9.7.14.5 | 1.9.7.14.5 |  | 2028-08-24 08:00 | p | 202 |  | 2029-03-14 10:20
695 | 1534 | SuchbNnj1ndABAEPQlrb | Normal | 10 | 1.9.7.14.6 | 1.9.7.14.6 |  | 2028-09-14 08:00 | p | 202 |  | 2029-04-04 14:50
696 | 4583 | QzcCl72pVAI4zSVR8VAE | Normal | 1 | 1.9.7.14.3 | 1.9.7.14.3 |  | 2028-08-22 08:00 | p | 202 |  | 2029-03-12 14:16
697 | 1538 | 1Xm6i4dPIyAKJzF1jRtD | Normal | 45 | 1.9.7.15.3 | 1.9.7.15.3 |  | 2026-06-01 08:00 | q | -4 |  | 2026-05-27 14:08
698 | 1540 | GIXHFfgJ4jA0lgUlb0GT | Normal | 1 | 1.9.7.15.5 | 1.9.7.15.5 |  | 2026-07-21 08:00 | q | -524 |  | 2025-02-12 08:00
699 | 1541 | ss8yD9dhZfTIp9UxqHnG | Normal | 1 | 1.9.7.15.7 | 1.9.7.15.7 |  | 2026-08-05 08:00 | q | 0 |  | 2026-08-04 09:12
700 | 1542 | VmFPpoMfVfLEXeRBF7Um | Normal | 9 | 1.9.7.15.8 | 1.9.7.15.8 |  | 2026-08-06 08:00 | q | -1 |  | 2026-08-04 16:44
701 | 1543 | P2oxmSB7jXG6Ib9VEZ89 | Normal | 9 | 1.9.7.15.9 | 1.9.7.15.9 |  | 2026-08-19 08:00 | q | -4 |  | 2026-08-14 16:14
702 | 4585 | Z4QB23UBk58Dyd3318zD | Normal | 10 | 1.9.7.15.6 | 1.9.7.15.6 |  | 2026-07-22 08:00 | p | 1 |  | 2026-07-23 15:14
703 | 1547 | K0gsOWDMqaySswr72BAQ | Normal | 1 | 1.9.7.16.3 | 1.9.7.16.3 |  | 2026-07-23 08:00 | q | -356 |  | 2025-07-31 11:44
704 | 1548 | 4jCrHn72KCapTPEI9TzQ | Normal | 2 | 1.9.7.16.5 | 1.9.7.16.5 |  | 2026-07-27 08:00 | q | -356 |  | 2025-08-04 11:54
705 | 1549 | s8gTUDwRZFDpCO4enZqk | Normal | 15 | 1.9.7.16.6 | 1.9.7.16.6 |  | 2026-07-29 08:00 | q | -356 |  | 2025-08-06 13:34
706 | 1550 | UoQFPyMNVa9QPyq2kgrl | Normal | 9 | 1.9.7.16.7 | 1.9.7.16.7 |  | 2026-08-19 08:00 | p | 0 |  | 2026-08-19 14:32
707 | 4586 | kRWFuIGKur6ToFmAr9JC | Normal | 1 | 1.9.7.16.4 | 1.9.7.16.4 |  | 2026-07-24 08:00 | q | -356 |  | 2025-08-01 13:25
708 | 1561 | 8BMHpFsmSFY1BvBQKfdD | Normal | 10 | 1.9.7.19.11 | 1.9.7.19.11 |  | 2026-05-26 08:00 | q | -4 |  | 2026-05-21 13:52
709 | 1562 | lBuCdKTmKHrCdvS4FVbB | Normal | 40 | 1.9.7.19.12 | 1.9.7.19.12 |  | 2026-06-09 08:00 | p | 0 |  | 2026-06-09 08:59
710 | 1563 | TUxQ6kz9ittb2zcmlLCL | Normal | 10 | 1.9.7.19.13 | 1.9.7.19.13 |  | 2026-08-06 08:00 | p | 0 |  | 2026-08-06 11:36
711 | 1564 | OkMyUpJo7fqJaif9Jvyb | Normal | 5 | 1.9.7.19.14 | 1.9.7.19.14 |  | 2026-08-20 08:00 | p | 0 |  | 2026-08-20 08:15
712 | 1565 | 9BGxipQLCi4kED7E7faW | Normal | 4 | 1.9.7.19.15 | 1.9.7.19.15 |  | 2026-08-27 08:00 | q | 0 |  | 2026-08-26 15:34
713 | 4572 | 5hxJeLGqqaIlIue4XwRC | Normal | 1 | 1.9.7.2 | 1.9.7.2 |  | 2028-08-22 08:00 | p | 202 |  | 2029-03-12 11:21
714 | 1497 | q56IdotBOPeXlK3605d6 | Normal | 1 | 1.9.7.11.4 | 1.9.7.11.4 |  | 2028-07-27 08:00 | p | 201 |  | 2029-02-13 13:54
715 | 1506 | zNKWNUMZ7wFR6LBQ8bZ2 | Normal | 1 | 1.9.7.11.5 | 1.9.7.11.5 |  | 2028-07-27 08:00 | p | 201 |  | 2029-02-13 09:44
716 | 1509 | xdWSZU8MxGE52WBHNu6X | Normal | 1 | 1.9.7.11.3 | 1.9.7.11.3 |  | 2028-07-27 08:00 | p | 201 |  | 2029-02-13 11:15
717 | 6440 | u5F2XJPKXxmZ5m99Yx5A | Normal | 1 | 1.9.7.11.7 | 1.9.7.11.7 |  | 2028-07-27 08:00 | p | 201 |  | 2029-02-13 11:40
718 | 4575 | nPe6rBdPLk408ntp39jn | Normal | 1 | 1.9.7.3 | 1.9.7.3 |  | 2028-07-27 08:00 | p | 201 |  | 2029-02-13 14:00
719 | 4578 | kBeLaux8MTugqoi5KPvZ | Summary | 74 | 1.9.7.13 | 1.9.7.13 |  | 2026-09-01 08:00 | q | 0 |  | 2026-08-31 13:20
720 | 1462 | 2Cc6AJ3gtv1XGHwG4F9W | Normal | 1 | 1.9.7.13.3 | 1.9.7.13.3 |  | 2026-09-01 08:00 | q | 0 |  | 2026-08-31 13:20
721 | 1518 | qXbL36bdYftxHm1TCntK | Normal | 1 | 1.9.7.13.4 | 1.9.7.13.4 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 10:49
722 | 4579 | xoTCeJS6YwjvMvm1YAvH | Normal | 1 | 1.9.7.13.2 | 1.9.7.13.2 |  | 2026-09-01 08:00 | q | 0 |  | 2026-08-31 16:54
723 | 4580 | llDwDvQQbSyeeXMs3M2a | Normal | 1 | 1.9.7.13.1 | 1.9.7.13.1 |  | 2026-09-01 08:00 | q | 0 |  | 2026-08-31 16:20
724 | 4588 | L1kgBhMEjlIJ4HNHh1TQ | Summary | 141 | 1.9.7.20 | 1.9.7.20 |  | 2028-01-13 08:00 | p | 204 |  | 2028-08-04 15:46
725 | 1566 | KFj0hxHWvExDoqTqgDeg | Normal | 118 | 1.9.7.20.1 | 1.9.7.20.1 |  | 2028-01-13 08:00 | p | 204 |  | 2028-08-04 15:46
726 | 1567 | GV5or0ucuouXZiqAkH0N | Normal | 10 | 1.9.7.20.2 | 1.9.7.20.2 |  | 2028-06-27 08:00 | p | 202 |  | 2029-01-15 11:46
727 | 1568 | JI4xSRBKV4FYnRXdw7Wz | Normal | 9 | 1.9.7.20.3 | 1.9.7.20.3 |  | 2028-07-11 08:00 | p | 204 |  | 2029-01-31 08:09
728 | 1569 | DVuFJt4FGQSIgeZkA41d | Normal | 4 | 1.9.7.20.4 | 1.9.7.20.4 |  | 2028-07-24 08:00 | p | 200 |  | 2029-02-09 15:10
729 | 4590 | 21lrGsmJiPqRYOd4yY3H | Summary | 2 | 1.9.7.21 | 1.9.7.21 |  | 2028-09-08 08:00 | p | 203 |  | 2029-03-30 14:22
730 | 1570 | 9hmrS48cr19KgrseY4yN | Normal | 2 | 1.9.7.21.1 | 1.9.7.21.1 |  | 2028-09-08 08:00 | p | 203 |  | 2029-03-30 14:22
731 | 6439 | JoFd6fDKN7NWznuQx6gK | Normal | 56 | 1.9.7.10 | 1.9.7.10 |  | 2028-05-10 08:00 | p | 205 |  | 2028-12-01 08:12
732 | 7455 | hQlezwT73UjuGPZkyuVr | Normal | 9 | 1.7.8.18.2 | 1.7.8.18.2 |  | 2028-05-26 08:00 | p | 196 |  | 2028-12-08 13:58
733 | 7456 | 3cfjdZ38xGBNf8roD7He | Normal | 9 | 1.7.8.18.3 | 1.7.8.18.3 |  | 2028-06-08 08:00 | p | 195 |  | 2028-12-20 14:04
734 | 7457 | abNwDWOnFoe0xwhiRueS | Normal | 1 | 1.7.8.18.4 | 1.7.8.18.4 |  | 2028-06-21 08:00 | p | 195 |  | 2029-01-02 09:01
735 | 7458 | cMhUMuxC0sax27543As7 | Normal | 24 | 1.7.8.18.5 | 1.7.8.18.5 |  | 2028-06-22 08:00 | p | 195 |  | 2029-01-03 08:32
736 | 7459 | xf7OMyoiQ38QdcweBYiq | Normal | 20 | 1.7.8.18.6 | 1.7.8.18.6 |  | 2028-07-26 08:00 | p | 196 |  | 2029-02-07 14:09
737 | 7324 | GVXYroUMjcAFUHa4B19H | Normal | 1 | 1.7.8.19 | 1.7.8.19 |  | 2028-06-21 08:00 | p | 194 |  | 2029-01-01 16:42
738 | 7325 | wl82vK5NXqnnsHIySTFp | Normal | 1 | 1.7.8.20 | 1.7.8.20 |  | 2028-08-23 08:00 | p | 202 |  | 2029-03-13 09:40
739 | 7382 | GJk3wpkfagyrb21gVciV | Summary | 288 | 1.9.7.22 | 1.9.7.22 |  | 2028-04-13 08:00 | p | 214 |  | 2028-11-13 13:44
740 | 7383 | chM988R4AoJxJINOHhOy | Normal | 1 | 1.9.7.22.1 | 1.9.7.22.1 |  | 2028-04-13 08:00 | p | 214 |  | 2028-11-13 13:44
741 | 7384 | xn1TRUhUfNd3ygHlAMk1 | Normal | 16 | 1.9.7.22.2 | 1.9.7.22.2 |  | 2028-04-14 08:00 | p | 214 |  | 2028-11-14 13:26
742 | 7385 | cYlWo9e2zkkP7jtt7iLZ | Normal | 1 | 1.9.7.22.3 | 1.9.7.22.3 |  | 2028-05-08 08:00 | p | 206 |  | 2028-11-30 13:21
743 | 7386 | F9n9tFj3S3xXbwXNgAjU | Normal | 5 | 1.9.7.22.4 | 1.9.7.22.4 |  | 2028-05-18 08:00 | p | 208 |  | 2028-12-12 13:43
744 | 4594 | EUFkYGsAZWO3vgZroOTA | Normal | 1 | 1.9.1.2 | 1.9.1.2 |  | 2026-06-30 08:00 | p | 6 |  | 2026-07-06 14:42
745 | 4595 | 0i30zTvKTrSo3R9n999e | Normal | 2 | 1.9.1.3 | 1.9.1.3 |  | 2026-07-01 08:00 | p | 6 |  | 2026-07-07 14:46
746 | 4606 | e1c7TqZJ2saEXqSPx9Ca | Normal | 1 | 1.7.3.3 | 1.7.3.3 |  | 2026-04-13 08:00 | p | 2 |  | 2026-04-15 13:32
747 | 4607 | 9Rf8xh1sYqA0mX8AIEgx | Summary | 52 | 1.7.3.5 | 1.7.3.5 |  | 2026-06-18 08:00 | p | 7 |  | 2026-06-25 10:20
748 | 4608 | tlJeJHdE7OwhwWyVvZ8P | Normal | 5 | 1.7.3.5.1 | 1.7.3.5.1 |  | 2026-06-18 08:00 | p | 7 |  | 2026-06-25 10:20
749 | 4609 | PoeQu0I6Io83IRbk7WtS | Normal | 5 | 1.7.3.5.2 | 1.7.3.5.2 |  | 2026-06-26 08:00 | p | 5 |  | 2026-07-01 11:12
750 | 4610 | UGUZlny6Ut8S0mLRTL2X | Normal | 1 | 1.7.3.5.3 | 1.7.3.5.3 |  | 2026-07-06 08:00 | p | 3 |  | 2026-07-09 11:33
751 | 4611 | 1TZOFiOcsBCmkfhi03Iw | Normal | 5 | 1.7.3.5.4 | 1.7.3.5.4 |  | 2026-07-14 08:00 | p | 3 |  | 2026-07-17 10:21
752 | 4612 | ZwEXlYv6PrV1t0gzfqom | Normal | 10 | 1.7.3.5.5 | 1.7.3.5.5 |  | 2026-07-21 08:00 | p | 3 |  | 2026-07-24 09:57
753 | 4613 | z0DGpsje53b33zXA5t1P | Normal | 20 | 1.7.3.5.6 | 1.7.3.5.6 |  | 2026-08-04 08:00 | p | 3 |  | 2026-08-07 09:11
754 | 4614 | cqs4HA7sR83mroZvcBiw | Normal | 1 | 1.7.3.5.7 | 1.7.3.5.7 |  | 2026-09-01 08:00 | q | 0 |  | 2026-08-31 16:59
755 | 4618 | mRqsjEijsp2iSp4l7aof | Normal | 5 | 1.7.3.4.3 | 1.7.3.4.3 |  | 2026-04-07 08:00 | p | 0 |  | 2026-04-07 15:49
756 | 4619 | 8asUr7UOO8nabPagFvw9 | Normal | 40 | 1.7.3.4.4 | 1.7.3.4.4 |  | 2026-02-18 08:00 | p | 6 |  | 2026-02-24 15:25
757 | 4620 | UWR5akRFo4eKiDyQVnYr | Normal | 23 | 1.7.3.4.5 | 1.7.3.4.5 |  | 2026-03-12 08:00 | p | 12 |  | 2026-03-24 16:59
758 | 4621 | pGB9dynKUfIMuzj3AWVv | Normal | 1 | 1.7.3.4.6 | 1.7.3.4.6 |  | 2026-04-14 08:00 | p | 2 |  | 2026-04-16 13:48
759 | 4622 | Bm2ajkWBwO6Cvc6RoPdK | Normal | 5 | 1.7.3.4.7 | 1.7.3.4.7 |  | 2026-04-15 08:00 | p | 2 |  | 2026-04-17 11:58
760 | 4623 | sDTQ4X48dvup817zb0Do | Normal | 20 | 1.7.3.4.8 | 1.7.3.4.8 |  | 2026-04-22 08:00 | p | 6 |  | 2026-04-28 14:33
761 | 4624 | 3CGv61AS00FFpM5LrRat | Normal | 20 | 1.7.3.4.9 | 1.7.3.4.9 |  | 2026-05-20 08:00 | p | 8 |  | 2026-05-28 14:30
762 | 4625 | NkJyZ342jkgJkVCalD4F | Normal | 2 | 1.7.3.4.10 | 1.7.3.4.10 |  | 2026-08-31 08:00 | q | -2 |  | 2026-08-28 15:41
763 | 4631 | EXJQS9o5Eq3lGkaYsCap | Normal | 1 | 1.7.3.6.5 | 1.7.3.6.5 |  | 2026-06-29 08:00 | p | 2 |  | 2026-07-01 10:24
764 | 4632 | VGp2Ji3lCAas2O4B01f5 | Normal | 1 | 1.7.3.6.6 | 1.7.3.6.6 |  | 2026-06-30 08:00 | p | 2 |  | 2026-07-02 09:46
765 | 4633 | STHfhyBuM5qFiEzHSgws | Normal | 19 | 1.7.3.6.7 | 1.7.3.6.7 |  | 2026-07-01 08:00 | p | 5 |  | 2026-07-06 09:32
766 | 4634 | cbBLoWE0dwfwOCS04ga7 | Normal | 15 | 1.7.3.6.8 | 1.7.3.6.8 |  | 2026-07-29 08:00 | q | 0 |  | 2026-07-28 13:06
767 | 4635 | vrd0V7BeylNxhzgI26F9 | Normal | 8 | 1.7.3.6.11 | 1.7.3.6.11 |  | 2026-08-20 08:00 | q | 0 |  | 2026-08-19 11:54
768 | 4636 | DgPDbwa39NNm3em6lmtZ | Normal | 1 | 1.7.3.6.12 | 1.7.3.6.12 |  | 2026-09-01 08:00 | q | 0 |  | 2026-08-31 16:49
769 | 4663 | X9pjxOrdX8ZwQAfQziSu | Normal | 1 | 1.7.3.6.9 | 1.7.3.6.9 |  | 2026-08-19 08:00 | q | 0 |  | 2026-08-18 13:09
770 | 4664 | DAxARpEpHAwipBCK81bc | Normal | 8 | 1.7.3.6.10 | 1.7.3.6.10 |  | 2026-08-20 08:00 | q | 0 |  | 2026-08-19 15:54
771 | 7259 | Dcjo2uskRMoBajU90pQq | Normal | 60 | 1.7.1.4 | 1.7.1.4 |  | 2026-01-15 08:00 | p | 0 |  | 2026-01-15 16:38
772 | 3777 | YuGKQIQDxLVYRZzgUQjw | Normal | 9 | 1.7.1.2.6.4 | 1.7.1.2.6.4 |  | 2026-08-20 08:00 | p | 0 |  | 2026-08-20 15:51
773 | 6138 | EvFVoaLHb5OgszmS4Hdy | Summary | 44 | 1.7.1.3.9 | 1.7.1.3.9 |  | 2026-07-01 08:00 | q | -1 |  | 2026-06-29 13:42
774 | 6139 | VECMPYMi2oWf71g3eai1 | Normal | 29 | 1.7.1.3.9.1 | 1.7.1.3.9.1 |  | 2026-07-01 08:00 | q | -1 |  | 2026-06-29 13:42
775 | 6140 | mO0F0FFUdRVKYlb84WcT | Normal | 15 | 1.7.1.3.9.2 | 1.7.1.3.9.2 |  | 2026-08-12 08:00 | q | -5 |  | 2026-08-06 14:16
776 | 6978 | z4sj2SQJw3pdZet8Am0U | Normal | 9 | 1.7.1.3.5 | 1.7.1.3.5 |  | 2026-07-27 08:00 | q | -6 |  | 2026-07-20 08:18
777 | 6985 | eGeEyEDP9xa0SwHKf7WR | Normal | 7 | 1.7.1.3.7.4 | 1.7.1.3.7.4 |  | 2026-06-01 08:00 | q | -2 |  | 2026-05-29 10:00
778 | 6986 | 31qYZ6wVIReV9ZOAqgem | Summary | 9 | 1.7.1.3.7.5 | 1.7.1.3.7.5 |  | 2026-06-10 08:00 | q | -1 |  | 2026-06-08 16:52
779 | 6987 | 50so1NYgvDTnEeNkdrjv | Normal | 3 | 1.7.1.3.7.5.1 | 1.7.1.3.7.5.1 |  | 2026-06-10 08:00 | q | -1 |  | 2026-06-08 16:52
780 | 6988 | bmsC3uFxKZ3RPA57Ivjb | Normal | 3 | 1.7.1.3.7.5.2 | 1.7.1.3.7.5.2 |  | 2026-06-15 08:00 | q | -3 |  | 2026-06-11 14:32
781 | 6989 | okOYULy0nclsZMYhl4sg | Normal | 3 | 1.7.1.3.7.5.3 | 1.7.1.3.7.5.3 |  | 2026-06-18 08:00 | q | 0 |  | 2026-06-17 08:53
782 | 7184 | gKjyagqR1BEsAZjZk4l5 | Milestone | 0 | 1.7.1.3.7.3 | 1.7.1.3.7.3 |  | 2026-06-01 08:00 | q | -2 |  | 2026-05-29 10:00
783 | 6990 | K8cvVDryBsyahUujiNmr | Summary | 22 | 1.7.1.3.8 | 1.7.1.3.8 |  | 2026-06-24 08:00 | q | 0 |  | 2026-06-23 08:09
784 | 6136 | bVRB0EhNo1xoyHBU8R0I | Normal | 1 | 1.7.1.3.8.2 | 1.7.1.3.8.2 |  | 2026-08-07 08:00 | q | -3 |  | 2026-08-03 14:33
785 | 6982 | E06yVWmTg8kRS6Gv9kOV | Summary | 6 | 1.7.1.3.8.3 | 1.7.1.3.8.3 |  | 2026-06-24 08:00 | q | 0 |  | 2026-06-23 08:09
786 | 6137 | gagQpjsDXV4QnJ1bUthb | Normal | 2 | 1.7.1.3.8.3.1 | 1.7.1.3.8.3.1 |  | 2026-08-10 08:00 | q | -5 |  | 2026-08-04 14:22
787 | 6979 | ZYA6dvbLVog9FL6DNJRb | Normal | 5 | 1.7.1.3.8.3.2 | 1.7.1.3.8.3.2 |  | 2026-06-24 08:00 | q | 0 |  | 2026-06-23 08:09
788 | 6991 | RAhO7UtYgqwLkhTknwrO | Normal | 6 | 1.7.1.3.8.1 | 1.7.1.3.8.1 |  | 2026-07-17 08:00 | q | -3 |  | 2026-07-13 09:26
789 | 3810 | CJxWy7PnZPcI4EPHEeme | Normal | 9 | 1.7.1.5.3.2 | 1.7.1.5.3.2 |  | 2026-06-26 08:00 | q | -1 |  | 2026-06-24 11:17
790 | 3811 | wGtgxCT3lCK6u2EOL8xN | Normal | 5 | 1.7.1.5.3.3 | 1.7.1.5.3.3 |  | 2026-07-10 08:00 | q | -3 |  | 2026-07-06 08:31
791 | 3813 | sYeTNUsya13QYMbMJg21 | Normal | 25 | 1.7.1.5.7 | 1.7.1.5.7 |  | 2026-05-27 08:00 | q | -8 |  | 2026-05-18 13:19
792 | 3814 | c3HTuVFoRVefrW72mxSE | Normal | 3 | 1.7.1.5.8 | 1.7.1.5.8 |  | 2026-07-17 08:00 | q | -7 |  | 2026-07-09 13:09
793 | 3815 | nJJAkVwt0aHLNZMMtbkw | Normal | 3 | 1.7.1.5.9 | 1.7.1.5.9 |  | 2026-07-02 08:00 | q | -6 |  | 2026-06-25 11:39
794 | 3816 | 6MWmVgC0FSCF3lMoTGjJ | Summary | 40 | 1.7.1.5.10 | 1.7.1.5.10 |  | 2026-07-08 08:00 | q | -7 |  | 2026-06-30 09:04
795 | 3817 | LqjKPVRVNU7j1iAlkL3t | Normal | 2 | 1.7.1.5.10.1 | 1.7.1.5.10.1 |  | 2026-07-08 08:00 | q | -7 |  | 2026-06-30 09:04
796 | 3818 | Cmm1EfLtBPedDjXV8dAv | Normal | 5 | 1.7.1.5.10.2 | 1.7.1.5.10.2 |  | 2026-07-10 08:00 | q | -7 |  | 2026-07-02 09:34
797 | 3819 | FSVjbKFfUmqE2fpbGGPv | Normal | 3 | 1.7.1.5.10.3 | 1.7.1.5.10.3 |  | 2026-07-17 08:00 | q | -6 |  | 2026-07-10 08:37
798 | 3820 | FhKtXXrOwkDfPm4RFzRW | Normal | 10 | 1.7.1.5.10.4 | 1.7.1.5.10.4 |  | 2026-07-22 08:00 | q | -7 |  | 2026-07-14 11:37
799 | 3821 | cHjYAw102skS4vR6DXqX | Normal | 20 | 1.7.1.5.10.5 | 1.7.1.5.10.5 |  | 2026-08-05 08:00 | q | -6 |  | 2026-07-29 13:04
800 | 4131 | 3WZTLr4e3INGux4LMgj0 | Summary | 146 | 1.9.6.10.2 | 1.9.6.10.2 |  | 2026-01-12 08:00 | q | -11 |  | 2025-12-31 08:02
801 | 5857 | g9TizAnooUcHoXglcd4n | Milestone | 0 | 1.9.6.10.2.1 | 1.9.6.10.2.1 |  | 2026-05-19 08:00 | q | -7 |  | 2026-05-11 16:36
802 | 5858 | 9N3N0HBhBeb82jbbU7Vx | Milestone | 0 | 1.9.6.10.2.2 | 1.9.6.10.2.2 |  | 2026-01-12 08:00 | q | -11 |  | 2025-12-31 08:02
803 | 5859 | RMhsXtyk4773BtipN2HO | Normal | 1 | 1.9.6.10.2.3 | 1.9.6.10.2.3 |  | 2026-01-12 08:00 | q | -11 |  | 2025-12-31 08:02
804 | 5860 | AMUT2hrMeOWSIoK5dO6S | Normal | 10 | 1.9.6.10.2.4 | 1.9.6.10.2.4 |  | 2026-01-13 08:00 | q | -12 |  | 2025-12-31 16:42
805 | 5861 | adMwYb1cwVT0ja23ZKPV | Normal | 10 | 1.9.6.10.2.5 | 1.9.6.10.2.5 |  | 2026-01-28 08:00 | q | -12 |  | 2026-01-15 14:11
806 | 5862 | rkVKH7eSVnkv5Rz0hIbo | Normal | 25 | 1.9.6.10.2.6 | 1.9.6.10.2.6 |  | 2026-02-11 08:00 | q | -11 |  | 2026-01-30 08:46
807 | 5863 | axx1H8vuWtNbWz6aJYpW | Normal | 20 | 1.9.6.10.2.7 | 1.9.6.10.2.7 |  | 2026-03-19 08:00 | q | -6 |  | 2026-03-12 13:20
808 | 5864 | ZuXAUp7kzm7PDgs0Clm4 | Normal | 20 | 1.9.6.10.2.8 | 1.9.6.10.2.8 |  | 2026-04-16 08:00 | q | -1 |  | 2026-04-14 11:36
809 | 5865 | pfx92tyIHO0nDV8Eg4vj | Normal | 3 | 1.9.6.10.2.9 | 1.9.6.10.2.9 |  | 2026-05-14 08:00 | q | -6 |  | 2026-05-07 09:43
810 | 5866 | qnFTkxNSvGIYOwHhqElS | Normal | 5 | 1.9.6.10.2.10 | 1.9.6.10.2.10 |  | 2026-05-19 08:00 | q | -7 |  | 2026-05-11 16:36
811 | 5867 | 6vMprMC9ZRYTg9c055cw | Normal | 3 | 1.9.6.10.2.11 | 1.9.6.10.2.11 |  | 2026-05-27 08:00 | q | -8 |  | 2026-05-18 16:03
812 | 5868 | qP5P60WlJm98gR28uFOw | Normal | 1 | 1.9.6.10.2.12 | 1.9.6.10.2.12 |  | 2026-06-01 08:00 | q | -11 |  | 2026-05-20 15:16
813 | 5869 | 5FBVtcv48JlyNzpes7ps | Normal | 5 | 1.9.6.10.2.13 | 1.9.6.10.2.13 |  | 2026-06-02 08:00 | q | -11 |  | 2026-05-21 14:45
814 | 5870 | rLlKwDBGmyMe6lxLtymf | Summary | 59 | 1.9.6.10.3 | 1.9.6.10.3 |  | 2026-06-09 08:00 | q | -10 |  | 2026-05-29 13:54
815 | 5871 | owx5unCKcaLauhH4kWyj | Normal | 5 | 1.9.6.10.3.1 | 1.9.6.10.3.1 |  | 2026-06-09 08:00 | q | -10 |  | 2026-05-29 13:54
816 | 5872 | qImIYF1Y50rp0FNnsaoS | Normal | 10 | 1.9.6.10.3.2 | 1.9.6.10.3.2 |  | 2026-06-16 08:00 | q | -7 |  | 2026-06-08 15:22
817 | 5873 | FfFQqcMQ2fY5X0GvK0Xd | Normal | 20 | 1.9.6.10.3.3 | 1.9.6.10.3.3 |  | 2026-07-01 08:00 | q | -5 |  | 2026-06-25 15:11
818 | 5874 | fHTDjpnY2Gm0gViXPiAD | Normal | 2 | 1.9.6.10.3.6 | 1.9.6.10.3.6 |  | 2026-08-27 08:00 | p | 0 |  | 2026-08-27 13:57
819 | 5875 | TQZary26m4SvJkpuQUlv | Normal | 1 | 1.9.6.10.3.7 | 1.9.6.10.3.7 |  | 2026-08-31 08:00 | p | 0 |  | 2026-08-31 11:22
820 | 5876 | 5ZRJqmbhPGswffOWtWat | Normal | 1 | 1.9.6.10.3.8 | 1.9.6.10.3.8 |  | 2026-09-01 08:00 | p | 0 |  | 2026-09-01 09:42
821 | 6624 | sVpbcWAee9M5eeft5sdO | Normal | 15 | 1.9.6.10.3.4 | 1.9.6.10.3.4 |  | 2026-07-30 08:00 | p | 1 |  | 2026-07-31 14:59
822 | 6625 | it5qGsWYKIf8fEL1a2TB | Normal | 5 | 1.9.6.10.3.5 | 1.9.6.10.3.5 |  | 2026-08-20 08:00 | q | 0 |  | 2026-08-19 16:18
823 | 5877 | 8uIO0L3CbsjXfYIL70ur | Summary | 162 | 1.9.6.10.4 | 1.9.6.10.4 |  | 2028-03-01 08:00 | p | 205 |  | 2028-09-22 14:40
824 | 5878 | eKJmpIIS7eePXp789pq5 | Summary | 60 | 1.9.6.10.4.1 | 1.9.6.10.4.1 |  | 2028-03-01 08:00 | p | 205 |  | 2028-09-22 14:40
825 | 5879 | CJrwB1y6NRnYYg7kpaRv | Summary | 30 | 1.9.6.10.4.1.1 | 1.9.6.10.4.1.1 |  | 2028-03-01 08:00 | p | 205 |  | 2028-09-22 14:40
826 | 5880 | z8rht75g90pc62Jd1j8e | Normal | 15 | 1.9.6.10.4.1.1.1 | 1.9.6.10.4.1.1.1 |  | 2028-03-01 08:00 | p | 205 |  | 2028-09-22 14:40
827 | 5881 | ZPPJV7wrbqyTumtl84NX | Normal | 15 | 1.9.6.10.4.1.1.2 | 1.9.6.10.4.1.1.2 |  | 2028-03-22 08:00 | p | 203 |  | 2028-10-11 16:48
828 | 5882 | PdfqDNDAaUS1Z9tfvPSB | Normal | 15 | 1.9.6.10.4.1.2 | 1.9.6.10.4.1.2 |  | 2028-04-12 08:00 | p | 205 |  | 2028-11-03 09:57
829 | 5883 | 3J3dFKPf8v7HKW1lSal4 | Normal | 15 | 1.9.6.10.4.1.3 | 1.9.6.10.4.1.3 |  | 2028-05-03 08:00 | p | 204 |  | 2028-11-23 10:55
830 | 5884 | J3ZDJxR9DKKi4JquRb3Q | Summary | 20 | 1.9.6.10.4.2 | 1.9.6.10.4.2 |  | 2028-04-11 08:00 | p | 205 |  | 2028-11-02 11:24
831 | 5885 | p0UOLQYQkw5raD9Hf7AI | Normal | 5 | 1.9.6.10.4.2.1 | 1.9.6.10.4.2.1 |  | 2028-04-11 08:00 | p | 205 |  | 2028-11-02 11:24
832 | 5886 | mfBVa7VrtMT45ZcRp9ur | Normal | 5 | 1.9.6.10.4.2.2 | 1.9.6.10.4.2.2 |  | 2028-04-18 08:00 | p | 205 |  | 2028-11-09 13:01
833 | 5887 | xjL6okqGZuFc1ChaUzA0 | Normal | 5 | 1.9.6.10.4.2.3 | 1.9.6.10.4.2.3 |  | 2028-04-25 08:00 | p | 205 |  | 2028-11-16 13:33
834 | 5888 | 0NLdruhvCSk61FiIPSJA | Normal | 5 | 1.9.6.10.4.2.4 | 1.9.6.10.4.2.4 |  | 2028-05-02 08:00 | p | 206 |  | 2028-11-24 16:07
835 | 5889 | vcqfMiWzgD0sBRK91JrP | Normal | 3 | 1.9.6.10.4.3 | 1.9.6.10.4.3 |  | 2028-05-09 08:00 | p | 209 |  | 2028-12-04 08:52
836 | 5890 | r7iAplKyl5D3dW7yC0Jk | Normal | 5 | 1.9.6.10.4.4 | 1.9.6.10.4.4 |  | 2028-05-12 08:00 | p | 208 |  | 2028-12-06 16:21
837 | 5891 | 55B0pL3dU2GPDxU6IZLg | Normal | 1 | 1.9.6.10.4.5 | 1.9.6.10.4.5 |  | 2028-05-19 08:00 | p | 208 |  | 2028-12-13 16:15
838 | 5892 | zyPP7s8BBmPhydQ5fB2g | Normal | 1 | 1.9.6.10.4.8 | 1.9.6.10.4.8 |  | 2028-05-24 08:00 | p | 208 |  | 2028-12-18 10:45
839 | 5893 | JSBvauC3wpirasqwMrC9 | Normal | 1 | 1.9.6.10.4.6 | 1.9.6.10.4.6 |  | 2028-05-22 08:00 | p | 206 |  | 2028-12-14 14:13
840 | 5894 | AO4SgiivKvvxQJupi2GS | Normal | 1 | 1.9.6.10.4.7 | 1.9.6.10.4.7 |  | 2028-05-23 08:00 | p | 206 |  | 2028-12-15 14:17
841 | 4137 | rnRXxVdKdR5NUADIB31n | Normal | 1 | 1.9.6.11.1.2 | 1.9.6.11.1.2 |  | 2028-06-05 08:00 | p | 204 |  | 2028-12-26 15:49
842 | 4138 | 75WgU7H7MCC8DDgOcnsD | Normal | 30 | 1.9.6.11.1.3 | 1.9.6.11.1.3 |  | 2028-06-06 08:00 | p | 205 |  | 2028-12-28 08:04
843 | 4139 | 9SKpfzivi43NDDuHUq0B | Normal | 5 | 1.9.6.11.1.4 | 1.9.6.11.1.4 |  | 2028-07-18 08:00 | p | 202 |  | 2029-02-05 14:18
844 | 4140 | Lk7gef35zB3WaxM8Xyxe | Summary | 48 | 1.9.6.11.2 | 1.9.6.11.2 |  | 2028-07-25 08:00 | p | 202 |  | 2029-02-12 08:15
845 | 4141 | HGo5Ep3pqhcsiM5K4QjA | Summary | 23 | 1.9.6.11.2.1 | 1.9.6.11.2.1 |  | 2028-07-25 08:00 | p | 202 |  | 2029-02-12 08:15
846 | 4142 | VTqJrDLpWuaSlvRQajcM | Normal | 12 | 1.9.6.11.2.1.1 | 1.9.6.11.2.1.1 |  | 2028-07-25 08:00 | p | 202 |  | 2029-02-12 08:15
847 | 4143 | UwGhtpl5Mnq9WQrcrXRR | Normal | 11 | 1.9.6.11.2.1.2 | 1.9.6.11.2.1.2 |  | 2028-08-10 08:00 | p | 203 |  | 2029-03-01 11:09
848 | 4144 | zaFQ6K5wegGvKt6DGuoz | Summary | 25 | 1.9.6.11.2.2 | 1.9.6.11.2.2 |  | 2028-08-25 08:00 | p | 203 |  | 2029-03-16 16:35
849 | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Normal | 10 | 1.9.6.11.2.2.1 | 1.9.6.11.2.2.1 |  | 2028-08-25 08:00 | p | 203 |  | 2029-03-16 16:35
850 | 4146 | rTeXGnIwGPt6ES3ynSHq | Normal | 5 | 1.9.6.11.2.2.2 | 1.9.6.11.2.2.2 |  | 2028-09-08 08:00 | p | 203 |  | 2029-03-30 08:56
851 | 4147 | hQaW5HIstT5bbsPEBxyQ | Normal | 10 | 1.9.6.11.2.2.3 | 1.9.6.11.2.2.3 |  | 2028-09-15 08:00 | p | 202 |  | 2029-04-05 10:38
852 | 5998 | aRBXPvE6pbVbcbhlDtu4 | Summary | 47 | 1.9.6.1.7 | 1.9.6.1.7 |  | 2026-03-13 08:00 | q | -7 |  | 2026-03-05 11:47
853 | 5999 | hTF24jclc5ogfsrVWXZd | Normal | 40 | 1.9.6.1.7.1 | 1.9.6.1.7.1 |  | 2026-03-13 08:00 | q | -7 |  | 2026-03-05 11:47
854 | 6000 | dvNXA0SZWky1SGhKE7td | Normal | 5 | 1.9.6.1.7.2 | 1.9.6.1.7.2 |  | 2026-05-08 08:00 | q | -6 |  | 2026-05-01 08:41
855 | 6001 | z8HVZ6SyP3QpkaT54VAm | Normal | 1 | 1.9.6.1.7.3 | 1.9.6.1.7.3 |  | 2026-05-15 08:00 | q | -6 |  | 2026-05-08 09:31
856 | 6002 | rmlzSal3Nkh8gQGzhscw | Normal | 1 | 1.9.6.1.7.4 | 1.9.6.1.7.4 |  | 2026-05-18 08:00 | q | -6 |  | 2026-05-11 09:25
857 | 6003 | zkyCYMQIHOywdkyzbjbi | Summary | 48 | 1.9.6.1.8 | 1.9.6.1.8 |  | 2026-06-26 08:00 | p | 19 |  | 2026-07-15 11:40
858 | 6004 | xOhJcEwgSz1TAvNHU4tB | Normal | 40 | 1.9.6.1.8.1 | 1.9.6.1.8.1 |  | 2026-06-26 08:00 | p | 19 |  | 2026-07-15 11:40
859 | 6005 | gw3ZFSF3nzLqLqYBiqR7 | Normal | 5 | 1.9.6.1.8.2 | 1.9.6.1.8.2 |  | 2026-08-24 08:00 | p | 0 |  | 2026-08-24 09:41
860 | 6006 | HEKaqqmbwSXnCRXB6fED | Normal | 1 | 1.9.6.1.8.3 | 1.9.6.1.8.3 |  | 2026-08-31 08:00 | p | 0 |  | 2026-08-31 09:12
861 | 6007 | vdBzwsumrXxpXNAKvnKh | Normal | 1 | 1.9.6.1.8.4 | 1.9.6.1.8.4 |  | 2026-09-01 08:00 | p | 0 |  | 2026-09-01 08:42
862 | 6008 | Ph5VFx7Ghit4AwZEFBXT | Summary | 50 | 1.9.6.1.6 | 1.9.6.1.6 |  | 2026-01-29 08:00 | q | -12 |  | 2026-01-16 15:48
863 | 6009 | NVgukc0KZBShUa0wIlyx | Normal | 30 | 1.9.6.1.6.1 | 1.9.6.1.6.1 |  | 2026-01-29 08:00 | q | -12 |  | 2026-01-16 15:48
864 | 6010 | tIYqVtlT4yOF2YQ2FRYY | Normal | 10 | 1.9.6.1.6.2 | 1.9.6.1.6.2 |  | 2026-04-20 08:00 | q | -4 |  | 2026-04-15 14:38
865 | 6011 | 9Y3pHbqvwzl2AwHfvrBG | Normal | 5 | 1.9.6.1.6.3 | 1.9.6.1.6.3 |  | 2026-05-04 08:00 | q | -5 |  | 2026-04-28 11:50
866 | 6012 | Z1jpWQx4GyFcVoEVg0i0 | Normal | 5 | 1.9.6.1.6.4 | 1.9.6.1.6.4 |  | 2026-05-11 08:00 | q | -5 |  | 2026-05-05 11:03
867 | 6013 | y2dxMv99iLhGOXikZGuK | Summary | 34 | 1.9.6.1.5 | 1.9.6.1.5 |  | 2026-01-07 08:00 | q | -11 |  | 2025-12-26 16:43
868 | 6014 | hYHiAVYfHXdDTdWEk9J8 | Normal | 15 | 1.9.6.1.5.1 | 1.9.6.1.5.1 |  | 2026-01-07 08:00 | q | -11 |  | 2025-12-26 16:43
869 | 6015 | MXdxqc8Y6tIByFeEqluF | Normal | 10 | 1.9.6.1.5.2 | 1.9.6.1.5.2 |  | 2026-04-21 08:00 | q | -5 |  | 2026-04-15 08:56
870 | 6016 | gwhB80Lv7eu4PoYwev8o | Normal | 5 | 1.9.6.1.5.3 | 1.9.6.1.5.3 |  | 2026-05-05 08:00 | q | -5 |  | 2026-04-29 09:01
871 | 6017 | VCyTBN0y7V3erCRNMvm4 | Normal | 4 | 1.9.6.1.5.4 | 1.9.6.1.5.4 |  | 2026-05-12 08:00 | q | -7 |  | 2026-05-04 16:58
872 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | 2025-12-30 08:00 | p | 610 |  | 2027-09-01 08:00
873 | 6957 | ar01N24L63iczVEh1mVo | Summary | 24 | 1.9.6.1.4 | 1.9.6.1.4 |  | 2025-12-23 08:00 | q | -6 |  | 2025-12-16 10:16
874 | 6958 | 6Ul4V6iAcnpVqewOp14Y | Normal | 4 | 1.9.6.1.4.1 | 1.9.6.1.4.1 |  | 2025-12-23 08:00 | q | -6 |  | 2025-12-16 10:16
875 | 6959 | w9Vvv79ftt4PUqInNFyD | Normal | 5 | 1.9.6.1.4.2 | 1.9.6.1.4.2 |  | 2025-12-30 08:00 | q | -10 |  | 2025-12-19 14:52
876 | 6960 | xIgpHAurEQ244gHa2T5q | Normal | 5 | 1.9.6.1.4.3 | 1.9.6.1.4.3 |  | 2026-04-21 08:00 | q | -6 |  | 2026-04-14 15:20
877 | 6961 | NOksVV7sTymsgwMrnh6x | Normal | 10 | 1.9.6.1.4.4 | 1.9.6.1.4.4 |  | 2026-04-28 08:00 | q | -6 |  | 2026-04-21 13:53
878 | 4075 | dGbNHsOLhslKk8CjhyjE | Normal | 1 | 1.9.6.9.3 | 1.9.6.9.3 |  | 2027-12-29 13:00 | p | 202 |  | 2028-07-19 11:32
879 | 6427 | NeAxFJaqSLize8VPNJ6N | Normal | 1 | 1.7.1.8.3 | 1.7.1.8.3 |  | 2028-09-27 08:00 | p | 203 |  | 2029-04-18 10:09
880 | 4196 | 2ZwOzHGH45ywtPvfASSG | Normal | 5 | 1.9.8.1.5 | 1.9.8.1.5 |  | 2028-03-20 13:00 | p | 203 |  | 2028-10-09 15:52
881 | 5974 | cJ7VeFZezCBnvYlHxCmb | Normal | 1 | 1.9.8.1.6.7 | 1.9.8.1.6.7 |  | 2028-03-24 13:00 | p | 206 |  | 2028-10-16 13:55
882 | 5985 | AUKn3E7aViOsULw8HdKV | Normal | 131 | 1.9.8.1.12 | 1.9.8.1.12 |  | 2027-09-17 13:00 | p | 251 |  | 2028-05-26 10:14
883 | 4231 | 8h0WH2qeIC7tfvcerCPa | Normal | 1 | 1.9.8.2.3 | 1.9.8.2.3 |  | 2027-08-24 13:00 | p | 245 |  | 2028-04-25 16:10
884 | 4235 | QiaATNQSPId7svzcuO8r | Normal | 91 | 1.9.8.2.7 | 1.9.8.2.7 |  | 2027-08-25 13:00 | p | 245 |  | 2028-04-26 15:31
885 | 4243 | LpPx7AWOh1V8dzWVWc6j | Normal | 1 | 1.9.8.4.5 | 1.9.8.4.5 |  | 2026-08-14 08:00 | p | 3 |  | 2026-08-17 10:49
886 | 4246 | ANAzXnUTz1PCb3xsov4Y | Normal | 10 | 1.9.8.4.7 | 1.9.8.4.7 |  | 2026-08-17 08:00 | p | 1 |  | 2026-08-18 09:37
887 | 4248 | E1RJwJWM8qrsKP3o7Toy | Normal | 1 | 1.9.8.7 | 1.9.8.7 |  | 2026-08-31 08:00 | p | 0 |  | 2026-08-31 08:05
888 | 4251 | IBg36OMMKUy3vwEnRNF0 | Normal | 1 | 1.9.8.6 | 1.9.8.6 |  | 2026-08-31 08:00 | q | -2 |  | 2026-08-28 14:41
889 | 4253 | hnujWIe1JDNg9VHs3TWw | Normal | 1 | 1.9.8.8 | 1.9.8.8 |  | 2026-09-01 08:00 | q | 0 |  | 2026-08-31 16:29
890 | 4255 | TAfq40Sin0H6Q2YT0OS5 | Milestone | 0 | 1.9.8.3 | 1.9.8.3 |  | 2027-12-30 13:00 | p | 203 |  | 2028-07-20 13:41
891 | 4256 | G2pYfP7dsnHVTgqQD6mD | Summary | 82 | 1.9.8.10 | 1.9.8.10 |  | 2026-05-06 08:00 | q | -5 |  | 2026-04-30 16:01
892 | 4258 | GzQkXlTiYJMdE6nBDVeb | Normal | 6 | 1.9.8.10.1 | 1.9.8.10.1 |  | 2026-05-06 08:00 | q | -5 |  | 2026-04-30 16:01
893 | 6090 | LkexiRQNUDyJAwm8EPYV | Normal | 32 | 1.9.8.10.7 | 1.9.8.10.7 |  | 2026-07-20 08:00 | q | -6 |  | 2026-07-13 15:15
894 | 6187 | kIPGiItVAbHq2ks8DK41 | Normal | 5 | 1.9.8.10.6 | 1.9.8.10.6 |  | 2026-07-13 08:00 | q | -5 |  | 2026-07-07 08:38
895 | 6430 | IYyY3jK4t9QuDyuxqyQ5 | Normal | 15 | 1.9.8.10.2 | 1.9.8.10.2 |  | 2026-05-14 08:00 | q | -6 |  | 2026-05-07 15:10
896 | 6431 | mXx66gQ5BZWpD3idmZgM | Normal | 10 | 1.9.8.10.3 | 1.9.8.10.3 |  | 2026-06-05 08:00 | q | -8 |  | 2026-05-27 11:05
897 | 6432 | vMoeJo3Rc30lMwFim6rn | Normal | 10 | 1.9.8.10.4 | 1.9.8.10.4 |  | 2026-06-22 08:00 | q | -9 |  | 2026-06-12 10:28
898 | 6433 | zONKYXhH5yZJE26xvIWD | Normal | 4 | 1.9.8.10.5 | 1.9.8.10.5 |  | 2026-07-07 08:00 | q | -6 |  | 2026-06-30 10:26
899 | 6083 | 3dsblDK1X9ztc27EZU3v | Normal | 1 | 1.9.8.5 | 1.9.8.5 |  | 2028-05-24 08:00 | p | 208 |  | 2028-12-18 11:07
900 | 6084 | deZM0xh115wln716GUoI | Normal | 1 | 1.9.8.9 | 1.9.8.9 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 10:06
901 | 7321 | CTokiQfH6gyOyeZJGrxP | Normal | 1 | 1.7.9.11 | 1.7.9.11 |  | 2026-08-31 08:00 | q | -2 |  | 2026-08-28 16:37
902 | 5690 | jLB7gq1wR8egZrMIoAc7 | Summary | 24 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2027-12-21 13:00 | p | 204 |  | 2028-07-12 16:57
903 | 5691 | glUuWw43f2R9t2hl6VHO | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2027-12-21 13:00 | p | 204 |  | 2028-07-12 16:57
904 | 5692 | KeXnvnZRx0KMyut3yw5s | Milestone | 0 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2028-01-04 13:00 | p | 201 |  | 2028-07-24 10:47
905 | 5693 | VdKRFLdSc60knizSqFXc | Normal | 14 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2028-01-04 13:00 | p | 201 |  | 2028-07-24 10:47
906 | 5694 | Gb0taOZcQ8l0cdHliY6j | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2028-01-24 13:00 | p | 202 |  | 2028-08-14 09:46
907 | 5695 | ePp2idADlztrdEpItyCc | Milestone | 0 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2028-02-07 13:00 | p | 204 |  | 2028-08-29 16:20
908 | 5696 | npE0RnxADwI7cDPG1fDa | Normal | 4 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2028-02-07 13:00 | p | 204 |  | 2028-08-29 16:20
909 | 5697 | 4nIBzBv3LSP60HeOLv0f | Normal | 5 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2028-02-11 13:00 | p | 206 |  | 2028-09-05 11:04
910 | 5533 | g1oQNBzKk6OrBukgGH7R | Normal | 40 | 1.9.5.1.3 | 1.9.5.1.3 |  | 2027-06-07 13:00 | q | -825 |  | 2025-03-04 08:00
911 | 5536 | cYU0DBZylLxVRoLEp7Bc | Normal | 40 | 1.9.5.1.4 | 1.9.5.1.4 |  | 2027-05-10 13:00 | p | 192 |  | 2027-11-19 08:41
912 | 5544 | cIc3ARzcdrbXv6maHllr | Summary | 129 | 1.9.5.2.13 | 1.9.5.2.13 |  | 2027-05-26 13:00 | p | 200 |  | 2027-12-13 11:45
913 | 5545 | 7UVU8IboY6NG7sqZCrUC | Normal | 7 | 1.9.5.2.13.2 | 1.9.5.2.13.2 |  | 2027-06-07 13:00 | p | 197 |  | 2027-12-21 13:16
914 | 5546 | Shs5wuYOFSkTF1YslX8w | Normal | 6 | 1.9.5.2.13.5 | 1.9.5.2.13.5 |  | 2027-06-25 08:00 | p | 196 |  | 2028-01-07 13:42
915 | 5547 | KglXvc5QwlHEboIvY96Q | Normal | 4 | 1.9.5.2.13.8 | 1.9.5.2.13.8 |  | 2027-07-23 08:00 | p | 199 |  | 2028-02-07 11:08
916 | 5548 | Zfzda0CfmpiN8ZL93G3t | Normal | 5 | 1.9.5.2.13.9 | 1.9.5.2.13.9 |  | 2027-07-29 08:00 | p | 197 |  | 2028-02-11 11:08
917 | 5549 | PgYJem7PJFdGgV04ojeL | Normal | 1 | 1.4.17 | 1.4.17 |  | 2027-08-05 08:00 | p | 200 |  | 2028-02-21 11:12
918 | 5556 | fOMVaiOa0jnHOJyDUdVQ | Normal | 25 | 1.9.5.2.13.11 | 1.9.5.2.13.11 |  | 2027-09-29 13:00 | p | 200 |  | 2028-04-17 10:27
919 | 5730 | ypyrsmMFJqJ9aPla6UhQ | Normal | 4 | 1.9.5.2.13.3 | 1.9.5.2.13.3 |  | 2027-06-16 13:00 | p | 196 |  | 2027-12-29 16:29
920 | 5731 | uQF6Ff0bc2cqy3b37ZQc | Normal | 1 | 1.9.5.2.13.4 | 1.9.5.2.13.4 |  | 2027-06-22 13:00 | p | 196 |  | 2028-01-04 15:46
921 | 5732 | OQKwpwUgImWCC2Fp5G0Q | Normal | 7 | 1.9.5.2.13.6 | 1.9.5.2.13.6 |  | 2027-07-05 08:00 | p | 197 |  | 2028-01-18 09:40
922 | 5733 | wyOxVAS94HubPKo2yHJm | Normal | 7 | 1.9.5.2.13.7 | 1.9.5.2.13.7 |  | 2027-07-14 08:00 | p | 197 |  | 2028-01-27 10:40
923 | 7000 | yP1oDcnUQTy3g68ZLgu0 | Normal | 8 | 1.9.5.2.13.1 | 1.9.5.2.13.1 |  | 2027-05-26 13:00 | p | 200 |  | 2027-12-13 11:45
924 | 5557 | U376LwOjKfNZoVLUlmMD | Summary | 113 | 1.9.5.2.12 | 1.9.5.2.12 |  | 2027-04-27 13:00 | p | 191 |  | 2027-11-05 10:28
925 | 5558 | RXAxJx3BHWNVdWFPfZ2a | Normal | 13 | 1.9.5.2.12.2 | 1.9.5.2.12.2 |  | 2027-05-10 13:00 | p | 192 |  | 2027-11-19 08:41
926 | 5559 | jJoy8dUJMWD3ZuNw52D0 | Normal | 8 | 1.9.5.2.12.5 | 1.9.5.2.12.5 |  | 2027-06-09 13:00 | p | 200 |  | 2027-12-27 11:31
927 | 5560 | wu3sL1wqoiodUr5mG52N | Normal | 4 | 1.9.5.2.12.8 | 1.9.5.2.12.8 |  | 2027-07-09 13:00 | p | 201 |  | 2028-01-27 11:44
928 | 5561 | Vb2zzMF18WNANxlCzGiz | Normal | 5 | 1.9.5.2.12.9 | 1.9.5.2.12.9 |  | 2027-07-15 13:00 | p | 201 |  | 2028-02-02 11:12
929 | 5562 | vp7j6GBYm2dAMLvxEFuE | Normal | 1 | 1.4.20 | 1.4.20 |  | 2027-07-22 13:00 | p | 201 |  | 2028-02-08 14:09
930 | 5569 | 35aiC9HLOSrIl2OBwDvd | Normal | 25 | 1.9.5.2.12.11 | 1.9.5.2.12.11 |  | 2027-08-25 13:00 | p | 196 |  | 2028-03-08 13:06
931 | 5734 | iq9bjqBZvH9Bj6912271 | Normal | 6 | 1.9.5.2.12.3 | 1.9.5.2.12.3 |  | 2027-05-27 13:00 | p | 195 |  | 2027-12-09 10:24
932 | 5735 | Z8zFgfwvHK2hwW2AW8Qa | Normal | 1 | 1.9.5.2.12.4 | 1.9.5.2.12.4 |  | 2027-06-04 13:00 | p | 199 |  | 2027-12-20 13:06
933 | 5736 | QgUmTWGvxjzq3xqrWPJK | Normal | 7 | 1.9.5.2.12.6 | 1.9.5.2.12.6 |  | 2027-06-21 13:00 | p | 199 |  | 2028-01-06 13:25
934 | 5737 | iDzIA8f8DQgg2wVNkaUu | Normal | 7 | 1.9.5.2.12.7 | 1.9.5.2.12.7 |  | 2027-06-30 13:00 | p | 200 |  | 2028-01-17 09:16
935 | 7001 | WpRQh8HvPfyDha8FH5FR | Normal | 9 | 1.9.5.2.12.1 | 1.9.5.2.12.1 |  | 2027-04-27 13:00 | p | 191 |  | 2027-11-05 10:28
936 | 5571 | lfRAbO0c5jl7NaC6s7pm | Normal | 21 | 1.9.5.2.11.2 | 1.9.5.2.11.2 |  | 2027-04-01 13:00 | p | 193 |  | 2027-10-12 11:58
937 | 5572 | jk3Vm36iIGViuk9dpLfQ | Normal | 8 | 1.9.5.2.11.5 | 1.9.5.2.11.5 |  | 2027-05-10 13:00 | p | 204 |  | 2027-11-30 13:45
938 | 5573 | u3MfiduPa05JsS2ly7WD | Normal | 4 | 1.9.5.2.11.8 | 1.9.5.2.11.8 |  | 2027-06-23 13:00 | p | 200 |  | 2028-01-10 11:07
939 | 5574 | 3iKE3riinMPRUpVpTfwx | Normal | 5 | 1.9.5.2.11.9 | 1.9.5.2.11.9 |  | 2027-07-02 08:00 | p | 202 |  | 2028-01-20 08:47
940 | 5575 | 48yotl4pDzxbk5y0VDbK | Normal | 1 | 1.4.23 | 1.4.23 |  | 2027-07-09 08:00 | p | 202 |  | 2028-01-27 14:01
941 | 5582 | 6tLu8emqwotxTkeBbEpy | Normal | 26 | 1.9.5.2.11.11 | 1.9.5.2.11.11 |  | 2027-08-24 13:00 | p | 205 |  | 2028-03-16 16:40
942 | 5738 | ME2oX9BwgLu5cggaunhg | Normal | 5 | 1.9.5.2.11.3 | 1.9.5.2.11.3 |  | 2027-04-30 13:00 | p | 194 |  | 2027-11-11 09:42
943 | 5739 | IivOSmNLtmlF9JKFLUrl | Normal | 1 | 1.9.5.2.11.4 | 1.9.5.2.11.4 |  | 2027-05-07 13:00 | p | 194 |  | 2027-11-18 09:40
944 | 5740 | eRxCjL3dV2CpHvAG84r7 | Normal | 12 | 1.9.5.2.11.6 | 1.9.5.2.11.6 |  | 2027-05-20 13:00 | p | 201 |  | 2027-12-07 13:10
945 | 5741 | 8Y4jq7dOt4lN4NYBT6r1 | Normal | 12 | 1.9.5.2.11.7 | 1.9.5.2.11.7 |  | 2027-06-07 13:00 | p | 198 |  | 2027-12-23 10:40
946 | 5583 | gkFBoXdv1oJb2jtBcO5M | Summary | 147 | 1.9.5.2.14 | 1.9.5.2.14 |  | 2027-06-11 13:00 | p | 198 |  | 2027-12-27 08:37
947 | 5584 | 6WMzJdzS7tY0wFFuXnrc | Normal | 7 | 1.9.5.2.14.2 | 1.9.5.2.14.2 |  | 2027-06-23 13:00 | p | 196 |  | 2028-01-05 14:48
948 | 5585 | KljMWvDEBGSuBTW4zQhZ | Normal | 7 | 1.9.5.2.14.5 | 1.9.5.2.14.5 |  | 2027-07-09 13:00 | p | 199 |  | 2028-01-25 09:57
949 | 5586 | Z3ZWpIsgJCSKUX161hV0 | Normal | 4 | 1.9.5.2.14.8 | 1.9.5.2.14.8 |  | 2027-08-05 13:00 | p | 197 |  | 2028-02-18 14:37
950 | 5587 | OXOUsYDejGVlgqn4Z1vl | Normal | 5 | 1.9.5.2.14.9 | 1.9.5.2.14.9 |  | 2027-08-11 13:00 | p | 196 |  | 2028-02-24 11:24
951 | 5588 | MFjHKzinVVI0Ndx8qx0B | Normal | 1 | 1.4.26 | 1.4.26 |  | 2027-08-18 13:00 | p | 198 |  | 2028-03-03 15:26
952 | 5595 | REFTk0AP9RBTibJWVhuH | Normal | 26 | 1.9.5.2.14.11 | 1.9.5.2.14.11 |  | 2027-11-03 13:00 | p | 201 |  | 2028-05-22 16:42
953 | 5742 | 88bEv4EMiOL2y8w1ttIM | Normal | 4 | 1.9.5.2.14.3 | 1.9.5.2.14.3 |  | 2027-07-02 13:00 | p | 196 |  | 2028-01-14 16:57
954 | 5743 | 0Uz4krHDVCdAlMd5aRwh | Normal | 1 | 1.9.5.2.14.4 | 1.9.5.2.14.4 |  | 2027-07-08 13:00 | p | 197 |  | 2028-01-21 16:37
955 | 5744 | cSBfnbrbVLLFYTMEfBKA | Normal | 6 | 1.9.5.2.14.6 | 1.9.5.2.14.6 |  | 2027-07-20 13:00 | p | 197 |  | 2028-02-02 15:52
956 | 5745 | ZY99Y6JX4jBylnfeedvo | Normal | 6 | 1.9.5.2.14.7 | 1.9.5.2.14.7 |  | 2027-07-28 13:00 | p | 200 |  | 2028-02-14 09:20
957 | 6999 | AnycnugTW971av3hMZXE | Normal | 8 | 1.9.5.2.14.1 | 1.9.5.2.14.1 |  | 2027-06-11 13:00 | p | 198 |  | 2027-12-27 08:37
958 | 6446 | XvbStahAymwCoqNIbMJG | Summary | 32 | 1.9.5.2.4 | 1.9.5.2.4 |  | 2027-04-06 13:00 | p | 202 |  | 2027-10-26 11:41
959 | 6532 | 15e7xcLR1b1jSikaz0S2 | Normal | 32 | 1.9.5.2.4.2 | 1.9.5.2.4.2 |  | 2027-05-06 13:00 | p | 206 |  | 2027-11-29 08:20
960 | 6533 | b0mutjzKj8FRw4zkbb8K | Normal | 32 | 1.9.5.2.4.1 | 1.9.5.2.4.1 |  | 2027-04-06 13:00 | p | 202 |  | 2027-10-26 11:41
961 | 6534 | 8Gl2bk4Fxxo2fsClDJqG | Normal | 32 | 1.9.5.2.4.3 | 1.9.5.2.4.3 |  | 2027-05-20 08:00 | p | 203 |  | 2027-12-09 10:04
962 | 6535 | dWze9AnK8NrEMD9LOEyU | Normal | 32 | 1.9.5.2.4.4 | 1.9.5.2.4.4 |  | 2027-06-04 13:00 | p | 203 |  | 2027-12-24 15:33
963 | 6955 | CPACk87DS0kpO7pXcdwS | Normal | 10 | 1.9.5.2.10 | 1.9.5.2.10 |  | 2025-12-26 08:00 | q | -13 |  | 2025-12-12 15:39
964 | 5596 | upn4QoZvaKBmBMoyhnq5 | Summary | 90 | 1.9.5.3 | 1.9.5.3 |  | 2027-10-12 13:00 | p | 202 |  | 2028-05-02 09:44
965 | 5597 | zKJsJYNcPRFZ7wBjvprv | Normal | 18 | 1.9.5.3.1 | 1.9.5.3.1 |  | 2027-10-12 13:00 | p | 202 |  | 2028-05-02 09:44
966 | 5598 | zvvzNQqIPXzcVRwy0N44 | Summary | 52 | 1.9.5.3.2 | 1.9.5.3.2 |  | 2027-11-05 13:00 | p | 201 |  | 2028-05-25 09:07
967 | 5599 | T0Oh47cWIVU9y2MKPB0U | Normal | 12 | 1.9.5.3.2.1 | 1.9.5.3.2.1 |  | 2027-11-05 13:00 | p | 201 |  | 2028-05-25 09:07
968 | 5600 | oTkX6bjokLXQ590hdeFy | Normal | 12 | 1.9.5.3.2.2 | 1.9.5.3.2.2 |  | 2027-11-23 13:00 | p | 202 |  | 2028-06-13 11:14
969 | 5601 | xa7cRxeKgQxZnuHNAYMQ | Normal | 12 | 1.9.5.3.2.3 | 1.9.5.3.2.3 |  | 2027-12-09 13:00 | p | 208 |  | 2028-07-05 08:13
970 | 5602 | QlxDegibloFbHrPNJwyW | Normal | 12 | 1.9.5.3.2.4 | 1.9.5.3.2.4 |  | 2027-12-27 13:00 | p | 203 |  | 2028-07-17 14:45
971 | 5603 | dwMYG7lg76TqxtTxZNCR | Normal | 5 | 1.9.5.3.3 | 1.9.5.3.3 |  | 2028-01-12 13:00 | p | 205 |  | 2028-08-04 13:05
972 | 5360 | ARncD9Nx3De5DONPy9Bs | Normal | 3 | 1.9.4.1.4 | 1.9.4.1.4 |  | 2027-11-03 13:00 | p | 207 |  | 2028-05-29 09:38
973 | 7262 | dH18W6KApKWC8TAOWb50 | Normal | 36 | 1.7.4.1.4 | 1.7.4.1.4 |  | 2027-09-08 13:00 | q | -938 |  | 2025-02-12 08:00
974 | 7263 | mjGxmWsUF3dJi6MlhQpM | Normal | 1 | 1.7.4.1.5 | 1.7.4.1.5 |  | 2027-11-02 13:00 | p | 205 |  | 2028-05-26 09:50
975 | 5368 | NKJL1ZJN3KgUArkbA4qS | Normal | 3 | 1.9.4.2.4 | 1.9.4.2.4 |  | 2027-11-03 13:00 | p | 207 |  | 2028-05-29 09:38
976 | 7261 | isfym7y8CMuc9Vq3Mbcl | Normal | 1 | 1.7.4.2.5 | 1.7.4.2.5 |  | 2027-11-02 13:00 | p | 205 |  | 2028-05-26 11:26
977 | 5382 | VlX4WunUzdS7Nqvh5ftn | Normal | 20 | 1.9.4.5.5 | 1.9.4.5.5 |  | 2027-07-07 13:00 | p | 195 |  | 2028-01-19 10:20
978 | 5383 | u1aficyBQ2O9A8MnpdfZ | Normal | 20 | 1.9.4.5.6 | 1.9.4.5.6 |  | 2027-08-04 13:00 | p | 195 |  | 2028-02-16 10:45
979 | 5384 | d8i6C63YfOF3EovUl19W | Normal | 10 | 1.9.4.5.7 | 1.9.4.5.7 |  | 2027-09-01 13:00 | p | 202 |  | 2028-03-21 16:19
980 | 5385 | ohwsmv9qOoV0RNzIdjJI | Normal | 15 | 1.9.4.5.8 | 1.9.4.5.8 |  | 2027-09-15 13:00 | p | 202 |  | 2028-04-04 16:26
981 | 5386 | tSuemAovBYAaHNhFiwaF | Normal | 15 | 1.9.4.5.9 | 1.9.4.5.9 |  | 2027-10-06 13:00 | p | 204 |  | 2028-04-27 14:13
982 | 5392 | TRJmldmXNRf3NwsZhgng | Normal | 20 | 1.9.4.6.5 | 1.9.4.6.5 |  | 2027-07-07 13:00 | p | 207 |  | 2028-01-31 11:36
983 | 5393 | 3qvg7di25vdBD8UUvM1a | Normal | 20 | 1.9.4.6.6 | 1.9.4.6.6 |  | 2027-08-04 13:00 | p | 203 |  | 2028-02-24 08:31
984 | 5394 | ungpeNo64cspVo3BuO9g | Normal | 10 | 1.9.4.6.7 | 1.9.4.6.7 |  | 2027-09-01 13:00 | p | 203 |  | 2028-03-22 16:39
985 | 5395 | KZXvYFda88KgX9w7a3ES | Normal | 15 | 1.9.4.6.8 | 1.9.4.6.8 |  | 2027-09-15 13:00 | p | 204 |  | 2028-04-07 08:05
986 | 5396 | FNjsTUKVT29tBcVlvaM6 | Normal | 15 | 1.9.4.6.9 | 1.9.4.6.9 |  | 2027-10-06 13:00 | p | 203 |  | 2028-04-27 09:00
987 | 5397 | KGrMeH5y6HH9dj1tr8uB | Summary | 53 | 1.9.4.7 | 1.9.4.7 |  | 2027-10-27 13:00 | p | 201 |  | 2028-05-15 14:02
988 | 5398 | EMMfZLgDhvN5O0lAfznQ | Normal | 15 | 1.9.4.7.1 | 1.9.4.7.1 |  | 2027-10-27 13:00 | p | 201 |  | 2028-05-15 14:02
989 | 5399 | 5K7jeUOrZ3wka9S2O1Dn | Normal | 15 | 1.9.4.7.2 | 1.9.4.7.2 |  | 2027-11-17 13:00 | p | 202 |  | 2028-06-06 15:46
990 | 5400 | I2IZFfCcy2hUSTtihPWq | Normal | 15 | 1.9.4.7.3 | 1.9.4.7.3 |  | 2027-12-08 13:00 | p | 202 |  | 2028-06-27 15:44
991 | 5401 | WWZjxA63YxH38hnYmVKG | Normal | 8 | 1.9.4.7.4 | 1.9.4.7.4 |  | 2027-12-29 13:00 | p | 202 |  | 2028-07-18 14:33
992 | 5402 | zDUD70mdAG3rcozejCwk | Summary | 15 | 1.9.4.8 | 1.9.4.8 |  | 2028-01-10 13:00 | p | 205 |  | 2028-08-02 15:36
993 | 5403 | wP2WbhW6upJb7JmdzCw1 | Normal | 9 | 1.9.4.8.1 | 1.9.4.8.1 |  | 2028-01-10 13:00 | p | 205 |  | 2028-08-02 15:36
994 | 5404 | UrewlDJ3J2c8Ueci7p9E | Normal | 6 | 1.9.4.8.2 | 1.9.4.8.2 |  | 2028-01-21 13:00 | p | 208 |  | 2028-08-16 13:04
995 | 7264 | vNqQNKJIEgg8BiBzdWeI | Summary | 57 | 1.7.4.3.6 | 1.7.4.3.6 |  | 2027-11-03 13:00 | p | 207 |  | 2028-05-29 09:38
996 | 7265 | uNFJkQaxxZ7oOYaM8QxX | Normal | 13 | 1.7.4.3.6.1 | 1.7.4.3.6.1 |  | 2027-11-03 13:00 | p | 207 |  | 2028-05-29 09:38
997 | 7266 | y7TR6NxR4uOKxinxsnEt | Normal | 13 | 1.7.4.3.6.2 | 1.7.4.3.6.2 |  | 2027-11-23 13:00 | p | 206 |  | 2028-06-16 14:05
998 | 7267 | f0BUmD79ZhKqjjzrwXUq | Normal | 13 | 1.7.4.3.6.3 | 1.7.4.3.6.3 |  | 2027-12-10 13:00 | p | 207 |  | 2028-07-04 16:48
999 | 7268 | sP1zO7OhzT9CUKqdzecJ | Normal | 12 | 1.7.4.3.6.4 | 1.7.4.3.6.4 |  | 2027-12-29 13:00 | p | 208 |  | 2028-07-24 14:44
1000 | 7269 | 7v5GPnNw6yREyKfoeMiZ | Normal | 5 | 1.7.4.3.6.5 | 1.7.4.3.6.5 |  | 2028-01-14 13:00 | p | 208 |  | 2028-08-09 14:15
1001 | 7322 | XsHCl5GkwKVP3xy7r0jT | Summary | 85 | 1.7.5 | 1.7.5 |  | 2026-05-01 08:00 | q | -7 |  | 2026-04-23 14:36
1002 | 7528 | 8SnF5zCB4rJyZyQZLLZc | Normal | 8 | 1.7.5.1 | 1.7.5.1 |  | 2026-05-01 08:00 | q | -7 |  | 2026-04-23 14:36
1003 | 7529 | ugdLGMeRoSNQZE98ehwR | Normal | 8 | 1.7.5.2 | 1.7.5.2 |  | 2026-05-01 08:00 | q | -2 |  | 2026-04-28 14:15
1004 | 7530 | tZgNvNsEFqNHmYVKXpMu | Normal | 7 | 1.7.5.3 | 1.7.5.3 |  | 2026-05-13 08:00 | q | -4 |  | 2026-05-08 10:00
1005 | 7531 | WsQS39Ko43y2ykuRUNnk | Normal | 8 | 1.7.5.4 | 1.7.5.4 |  | 2026-05-22 08:00 | q | -3 |  | 2026-05-18 16:50
1006 | 7532 | tNKjUDGuH9lZvW14y0xJ | Normal | 22 | 1.7.5.5 | 1.7.5.5 |  | 2026-06-04 08:00 | q | -1 |  | 2026-06-02 16:26
1007 | 7533 | HKUUjAeDBFLcgj42uw3c | Normal | 19 | 1.7.5.6 | 1.7.5.6 |  | 2026-07-08 08:00 | p | 0 |  | 2026-07-08 08:59
1008 | 7534 | s7VTtgJqjYjf9pbLYcYj | Normal | 8 | 1.7.5.7 | 1.7.5.7 |  | 2026-08-04 08:00 | p | 2 |  | 2026-08-06 09:45
1009 | 7535 | uGgP1gHCy12zlVFcLeTG | Normal | 6 | 1.7.5.8 | 1.7.5.8 |  | 2026-08-14 08:00 | p | 3 |  | 2026-08-17 08:10
1010 | 7536 | kbIucnV7qsI0ZjxbK1cH | Normal | 6 | 1.7.5.9 | 1.7.5.9 |  | 2026-08-24 08:00 | q | -2 |  | 2026-08-21 14:24
1011 | 7537 | ZiOXL4e3BgetRuJ4aYKK | Normal | 1 | 1.7.5.10 | 1.7.5.10 |  | 2026-09-01 08:00 | p | 0 |  | 2026-09-01 09:53
1012 | 6688 | aKOlgm9Tw9oPXF0YCFLp | Summary | 911 | 1.11 | 1.11 |  | 2019-04-01 08:00 | q | -663 |  | 2017-06-07 08:00
1013 | 6690 | bopLkaAZbmZjIM9EGI6L | Normal | 532 | 1.11.2 | 1.11.2 |  | 2026-09-09 08:00 | p | 121 |  | 2027-01-08 11:52
1014 | 7551 | G4afE8kOleATkD8qyqeP | Normal | 1 | 1.10.19 | 1.10.19 |  | 2028-09-28 08:00 | q | -4131 |  | 2017-06-07 08:00
1015 | 7107 | fjlRoMsMUGjOnNWoUkGJ | Milestone | 0 | 1.10.16 | 1.10.16 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39

## Late-Finish
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Late Finish - 1184 (56%) | Late Finish - 1184 (56%) | Late Finish - 1184 (56%) | Late Finish - 1184 (56%) | Late Finish - 1184 (56%) | Late Finish - 1184 (56%) | Late Finish - 1184 (56%) | Late Finish - 1184 (56%) | Late Finish - 1184 (56%) | Late Finish - 1184 (56%) | Late Finish - 1184 (56%) | Late Finish - 1184 (56%) | Late Finish - 1184 (56%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 1249 | v1zgYyoO7UpynPZXt29g | Summary | 611 | 1 | 1 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
2 | 147 | DEZpxiHWY7fkyvQEaEGc | Summary | 1132 | 1.2 | 1.2 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
3 | 152 | QJ29ZvAvtEjBcpqHDer1 | Milestone | 0 | 1.2.3 | 1.2.3 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 10:06
4 | 158 | D5C8AUNeoI4YKF3PggKx | Summary | 255 | 1.2.7 | 1.2.7 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
5 | 155 | 1yu6CrDX9QU5hWE1UWMV | Milestone | 0 | 1.2.7.11 | 1.2.7.11 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
6 | 166 | KkWbk0R1FXz2L56lHFvV | Normal | 2 | 1.2.7.4 | 1.2.7.4 |  | 2025-11-12 17:00 | p | 47 |  | 2025-12-30 16:50
7 | 6618 | LspmB73Oe2b9O1GVbm64 | Milestone | 0 | 1.2.7.2 | 1.2.7.2 |  | 2027-04-13 08:00 | p | 178 |  | 2027-10-08 16:52
8 | 6636 | 3J1qFTgnrSSZVnoYdTv5 | Summary | 140 | 1.2.7.3 | 1.2.7.3 |  | 2025-11-07 17:00 | p | 48 |  | 2025-12-26 15:15
9 | 6338 | whnkqeDzsaW1H7xphaZA | Normal | 49 | 1.2.7.3.4 | 1.2.7.3.4 |  | 2025-09-15 17:00 | p | 44 |  | 2025-10-30 15:32
10 | 6640 | QUv6m7GotPkUb98mhJX7 | Normal | 14 | 1.2.7.3.6 | 1.2.7.3.6 |  | 2025-11-07 17:00 | p | 48 |  | 2025-12-26 15:15
11 | 6673 | sIWmvaXMX3ZF9ctRNm7s | Normal | 34 | 1.2.7.3.3 | 1.2.7.3.3 |  | 2025-07-07 17:00 | p | 41 |  | 2025-08-18 09:41
12 | 6872 | SjyWialEYK436pEnV5Nr | Normal | 1 | 1.2.7.5 | 1.2.7.5 |  | 2026-03-18 17:00 | q | -34 |  | 2026-02-12 15:02
13 | 6874 | 1XFpbhK6U752FQe8voXZ | Normal | 1 | 1.2.7.6 | 1.2.7.6 |  | 2026-03-05 17:00 | q | -31 |  | 2026-02-02 10:36
14 | 6879 | Vbp0cBOXY9azJeyTE4S4 | Normal | 3 | 1.2.7.7 | 1.2.7.7 |  | 2026-04-06 17:00 | q | -34 |  | 2026-03-03 14:06
15 | 6880 | ZuauWvCPNW7n2NMscMO2 | Normal | 4 | 1.2.7.8 | 1.2.7.8 |  | 2026-06-23 17:00 | q | -13 |  | 2026-06-10 13:19
16 | 7185 | 9DFzvUnK8UE41lq7OD40 | Milestone | 0 | 1.2.7.1 | 1.2.7.1 |  | 2027-02-25 08:00 | p | 182 |  | 2027-08-26 13:16
17 | 7550 | fUEnUBwdI1z3bgOngjaQ | Milestone | 0 | 1.2.7.5 | 1.2.7.5 |  | 2025-11-13 08:00 | p | 47 |  | 2025-12-30 16:50
18 | 5294 | A0MDYkkQxesjEWQub0UM | Milestone | 0 | 1.2.8.3 | 1.2.8.3 |  | 2025-11-13 08:00 | p | 47 |  | 2025-12-30 16:50
19 | 179 | jSOjvYE1qiHOKdcV2ixu | Summary | 554 | 1.2.10 | 1.2.10 |  | 2028-09-20 08:00 | p | 203 |  | 2029-04-11 11:27
20 | 180 | 9Vp3PBZnh9TpV8TGBWRG | Milestone | 0 | 1.2.10.14 | 1.2.10.14 |  | 2028-09-20 08:00 | p | 203 |  | 2029-04-11 11:27
21 | 193 | nJh7oj8wCJYW8hyepdLI | Milestone | 0 | 1.2.10.12 | 1.2.10.12 |  | 2028-04-03 08:00 | p | 186 |  | 2028-10-06 15:49
22 | 194 | wTcNF86mfD2cPQPmQB1c | Milestone | 0 | 1.2.10.13 | 1.2.10.13 |  | 2028-04-03 08:00 | p | 186 |  | 2028-10-06 15:49
23 | 7132 | osdxrWYmqQZxyGZXe9Pr | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 2027-04-13 08:00 | p | 178 |  | 2027-10-08 16:52
24 | 7546 | tdocr3pqURBYHZWcAyMG | Normal | 1 | 1.2.10.12 | 1.2.10.12 |  | 2027-04-12 17:00 | p | 178 |  | 2027-10-08 16:52
25 | 7547 | 2p5uMAQ0v8mT9pq4KeWp | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 2027-04-13 08:00 | p | 178 |  | 2027-10-08 16:52
26 | 7548 | TdNnLE8G4vf1vBjggzLw | Normal | 1 | 1.2.10.15 | 1.2.10.15 |  | 2027-04-09 17:00 | p | 181 |  | 2027-10-08 10:10
27 | 7549 | yUAt6Fi3Vichq9Ai1DSh | Normal | 1 | 1.2.10.13 | 1.2.10.13 |  | 2027-04-08 17:00 | p | 181 |  | 2027-10-07 09:36
28 | 195 | jWoM7YMyhsN7uWtVDNIl | Summary | 276 | 1.2.11 | 1.2.11 |  | 2028-07-31 08:00 | p | 210 |  | 2029-02-26 09:11
29 | 196 | kzYOxx4jS6vhIcTyxNFn | Milestone | 0 | 1.2.11.11 | 1.2.11.11 |  | 2028-07-31 08:00 | p | 210 |  | 2029-02-26 09:11
30 | 197 | LZAvhCOF77OBkAngJSDi | Milestone | 0 | 1.2.11.1 | 1.2.11.1 |  | 2027-07-12 08:00 | p | 200 |  | 2028-01-28 14:32
31 | 198 | X7Nxs9NuQXJ5Bf6aQwVp | Milestone | 0 | 1.2.11.2 | 1.2.11.2 |  | 2027-07-23 13:00 | p | 201 |  | 2028-02-09 14:40
32 | 199 | TiaYdQ98Ovd3qBAfSAyG | Milestone | 0 | 1.2.11.3 | 1.2.11.3 |  | 2027-08-06 08:00 | p | 200 |  | 2028-02-22 14:55
33 | 200 | yynHcCtrZd0Ye6iQJb2E | Milestone | 0 | 1.2.11.4 | 1.2.11.4 |  | 2027-09-01 13:00 | p | 200 |  | 2028-03-20 09:05
34 | 202 | mjF0YLun5LIdlxtu3zFl | Milestone | 0 | 1.2.11.5 | 1.2.11.5 |  | 2028-05-25 08:00 | p | 208 |  | 2028-12-19 10:21
35 | 203 | 2a1x42QofxcVsgjcXtkr | Milestone | 0 | 1.2.11.6 | 1.2.11.6 |  | 2027-07-12 08:00 | p | 200 |  | 2028-01-28 14:32
36 | 204 | 8T22gllTunmLl2jY7IMk | Milestone | 0 | 1.2.11.7 | 1.2.11.7 |  | 2027-07-23 13:00 | p | 201 |  | 2028-02-09 14:40
37 | 205 | dm3U5Xjvi5rN2LqWegXW | Milestone | 0 | 1.2.11.8 | 1.2.11.8 |  | 2027-08-06 08:00 | p | 200 |  | 2028-02-22 14:55
38 | 206 | ZOAcdJHtChBG5MUjo5uw | Milestone | 0 | 1.2.11.9 | 1.2.11.9 |  | 2027-09-01 13:00 | p | 200 |  | 2028-03-20 09:05
39 | 209 | 0FNuAiL5ZzPZSZ3dZfoV | Milestone | 0 | 1.2.11.10 | 1.2.11.10 |  | 2028-05-25 08:00 | p | 208 |  | 2028-12-19 10:21
40 | 6077 | 9YjbRTuPDmKPhAucMUDE | Milestone | 0 | 1.2.6 | 1.2.6 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
41 | 7015 | U0mup1noPd6mH1CxWGtr | Milestone | 0 | 1.2.5 | 1.2.5 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
42 | 7016 | pVOP21cemlwRUbhUeRME | Milestone | 0 | 1.2.4 | 1.2.4 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
43 | 150 | 7cu6yvdJV8ndF0CYMHk8 | Milestone | 0 | 1.1 | 1.1 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 10:06
44 | 384 | GE3w1SHplCQZN7aYDVw8 | Summary | 34 | 1.3.3 | 1.3.3 |  | 2025-11-12 17:00 | p | 47 |  | 2025-12-30 14:09
45 | 429 | Pbs0MxOqvHazWgB8fpDs | Summary | 41 | 1.3.3.2 | 1.3.3.2 |  | 2025-07-07 17:00 | p | 41 |  | 2025-08-18 09:41
46 | 436 | OGXVzK31PKUn8DxCdn94 | Normal | 33 | 1.3.3.2.10 | 1.3.3.2.10 |  | 2025-07-07 17:00 | p | 41 |  | 2025-08-18 09:41
47 | 437 | kEyeaq7ebxWRSvBqGkHC | Summary | 19 | 1.3.3.1 | 1.3.3.1 |  | 2025-05-16 17:00 | p | 44 |  | 2025-06-30 08:54
48 | 438 | QjVW4dYK4boDcUrG7MUx | Summary | 23 | 1.3.3.1.2 | 1.3.3.1.2 |  | 2025-05-16 17:00 | p | 44 |  | 2025-06-30 08:54
49 | 445 | cIIfBfMFMZUbJxswwNzj | Summary | 28 | 1.3.3.1.2.4 | 1.3.3.1.2.4 |  | 2025-05-16 17:00 | p | 44 |  | 2025-06-30 08:54
50 | 6438 | sSGfho0IWOHZYw1Z8jLl | Normal | 16 | 1.3.3.1.2.4.5 | 1.3.3.1.2.4.5 |  | 2025-05-16 17:00 | p | 44 |  | 2025-06-30 08:54
51 | 5768 | 9l9o7D6Il8vKVgGgZRMW | Summary | 197 | 1.3.3.4 | 1.3.3.4 |  | 2025-11-12 17:00 | p | 47 |  | 2025-12-30 14:09
52 | 428 | pxWL5EoMWeaDmapfAV7m | Normal | 2 | 1.3.3.4.2 | 1.3.3.4.2 |  | 2025-11-12 17:00 | p | 47 |  | 2025-12-30 14:09
53 | 3849 | PKYN5IsyqbTocjyswPFM | Normal | 17 | 1.3.2.1.1 | 1.3.2.1.1 |  | 2025-05-16 17:00 | p | 44 |  | 2025-06-30 08:54
54 | 3858 | pWvg9Owxac1jXAINT5hs | Normal | 24 | 1.3.2.1.2.2.1 | 1.3.2.1.2.2.1 |  | 2025-05-16 17:00 | p | 44 |  | 2025-06-30 08:54
55 | 3859 | xrpLG6wlwOL4sRwHPU5B | Normal | 28 | 1.3.2.1.2.2.2 | 1.3.2.1.2.2.2 |  | 2026-03-12 17:00 | q | -28 |  | 2026-02-12 08:10
56 | 3861 | rvfyADOJtzNcPT3VL85f | Normal | 100 | 1.3.2.1.2.2.3 | 1.3.2.1.2.2.3 |  | 2026-08-04 17:00 | p | 1 |  | 2026-08-06 09:02
57 | 3865 | ZK3GDclfde20Vh8DU71K | Normal | 30 | 1.3.2.1.2.3.2.1 | 1.3.2.1.2.3.2.1 |  | 2026-06-05 17:00 | p | 6 |  | 2026-06-12 15:37
58 | 3866 | 8Zrc7ItBhrTjO1TWxqmf | Normal | 20 | 1.3.2.1.2.3.2.2 | 1.3.2.1.2.3.2.2 |  | 2026-07-07 17:00 | p | 0 |  | 2026-07-08 10:55
59 | 3867 | l8TRHVr9p6bfQBwzbTty | Normal | 5 | 1.3.2.1.2.3.2.5 | 1.3.2.1.2.3.2.5 |  | 2026-08-11 17:00 | p | 1 |  | 2026-08-13 11:55
60 | 3868 | NCkZSbtMfUxIg95lxXXn | Normal | 10 | 1.3.2.1.2.3.2.6 | 1.3.2.1.2.3.2.6 |  | 2026-08-25 17:00 | p | 0 |  | 2026-08-26 08:10
61 | 6562 | Z3AfJmLBpOLyJb1GhvwC | Normal | 10 | 1.3.2.1.2.3.2.3 | 1.3.2.1.2.3.2.3 |  | 2026-07-21 17:00 | p | 0 |  | 2026-07-22 08:12
62 | 6563 | 7FPcbor42GN7O6Ym4IZM | Normal | 10 | 1.3.2.1.2.3.2.4 | 1.3.2.1.2.3.2.4 |  | 2026-08-04 17:00 | p | 1 |  | 2026-08-06 10:22
63 | 7186 | ttl1FahPn0WwOuyGdmk6 | Summary | 138 | 1.3.2.3 | 1.3.2.3 |  | 2026-08-18 17:00 | q | 0 |  | 2026-08-18 13:44
64 | 7188 | yn5QOVI2BZ7jor10JaQN | Summary | 55 | 1.3.2.3.2 | 1.3.2.3.2 |  | 2025-10-20 17:00 | p | 45 |  | 2025-12-05 10:57
65 | 7189 | jup7puBG1dNvbV8jB14f | Summary | 69 | 1.3.2.3.2.1 | 1.3.2.3.2.1 |  | 2025-10-01 17:00 | p | 47 |  | 2025-11-18 11:12
66 | 7190 | Ob13piboJI4zFNOVPzZD | Summary | 50 | 1.3.2.3.2.1.1 | 1.3.2.3.2.1.1 |  | 2025-07-23 17:00 | p | 55 |  | 2025-09-17 08:48
67 | 7192 | rcBSOCAYFUxP7jsyoqGw | Normal | 11 | 1.3.2.3.2.1.1.2 | 1.3.2.3.2.1.1.2 |  | 2025-07-23 17:00 | p | 55 |  | 2025-09-17 08:48
68 | 7193 | hzdeRXxytBFeNJPq5eHn | Summary | 50 | 1.3.2.3.2.1.2 | 1.3.2.3.2.1.2 |  | 2025-09-04 17:00 | p | 46 |  | 2025-10-21 10:48
69 | 7194 | mB0uoGZ1D1fuFzk350Kb | Normal | 30 | 1.3.2.3.2.1.2.1 | 1.3.2.3.2.1.2.1 |  | 2025-09-04 17:00 | p | 46 |  | 2025-10-21 10:48
70 | 7196 | fFBpC2vR2qp5KXHLtypR | Summary | 23 | 1.3.2.3.2.1.3 | 1.3.2.3.2.1.3 |  | 2025-09-04 17:00 | p | 46 |  | 2025-10-21 10:48
71 | 7199 | G7LfPy6euQCIQjteO0x8 | Normal | 20 | 1.3.2.3.2.1.3.3 | 1.3.2.3.2.1.3.3 |  | 2025-09-04 17:00 | p | 46 |  | 2025-10-21 10:48
72 | 7200 | 7Va2LPPEsZrLZmgpV2qc | Summary | 19 | 1.3.2.3.2.1.4 | 1.3.2.3.2.1.4 |  | 2025-10-01 17:00 | p | 47 |  | 2025-11-18 11:12
73 | 7201 | UKbpgMkpfrIPVoEOJEeO | Normal | 10 | 1.3.2.3.2.1.4.1 | 1.3.2.3.2.1.4.1 |  | 2025-09-18 17:00 | p | 45 |  | 2025-11-03 16:13
74 | 7202 | vy1jnuopIHJe5PhTsUNw | Normal | 5 | 1.3.2.3.2.1.4.2 | 1.3.2.3.2.1.4.2 |  | 2025-09-25 17:00 | p | 47 |  | 2025-11-12 09:52
75 | 7203 | KqVHIBvrHNAu5GlarotD | Normal | 3 | 1.3.2.3.2.1.4.3 | 1.3.2.3.2.1.4.3 |  | 2025-09-30 17:00 | p | 47 |  | 2025-11-17 10:33
76 | 7204 | BUAmcwglNtP3GEkJsPLR | Normal | 1 | 1.3.2.3.2.1.4.4 | 1.3.2.3.2.1.4.4 |  | 2025-10-01 17:00 | p | 47 |  | 2025-11-18 11:12
77 | 7205 | 688LmElxek6WZQ34zEgD | Summary | 40 | 1.3.2.3.2.2 | 1.3.2.3.2.2 |  | 2025-10-01 17:00 | p | 47 |  | 2025-11-18 11:12
78 | 7206 | bMXBNIC1fF7AjliDPdfr | Normal | 25 | 1.3.2.3.2.2.1 | 1.3.2.3.2.2.1 |  | 2025-09-18 17:00 | p | 47 |  | 2025-11-05 10:49
79 | 7207 | 51ZGrscW6XrNzeOMbLyw | Normal | 5 | 1.3.2.3.2.2.2 | 1.3.2.3.2.2.2 |  | 2025-09-25 17:00 | p | 45 |  | 2025-11-10 17:00
80 | 7208 | 5Vu53Z23NG8K3uSzUcYA | Normal | 3 | 1.3.2.3.2.2.3 | 1.3.2.3.2.2.3 |  | 2025-09-30 17:00 | p | 47 |  | 2025-11-17 11:02
81 | 7209 | r8OmtZddpdGbVxNEynIO | Normal | 1 | 1.3.2.3.2.2.4 | 1.3.2.3.2.2.4 |  | 2025-10-01 17:00 | p | 47 |  | 2025-11-18 11:12
82 | 7210 | 5vpOUfvEpSU2AKPwltv0 | Summary | 14 | 1.3.2.3.2.3 | 1.3.2.3.2.3 |  | 2025-09-10 17:00 | p | 42 |  | 2025-10-23 08:32
83 | 7211 | wSDYMNBcPlclxMN6Hc8V | Normal | 5 | 1.3.2.3.2.3.1 | 1.3.2.3.2.3.1 |  | 2025-08-27 17:00 | q | -194 |  | 2025-02-14 17:00
84 | 7212 | IA5BwO4PzPuXs5yI3XzH | Normal | 5 | 1.3.2.3.2.3.2 | 1.3.2.3.2.3.2 |  | 2025-09-04 17:00 | p | 41 |  | 2025-10-16 16:34
85 | 7213 | GkAhONTSL0EMIVzc5bXh | Normal | 3 | 1.3.2.3.2.3.3 | 1.3.2.3.2.3.3 |  | 2025-09-09 17:00 | p | 42 |  | 2025-10-22 08:21
86 | 7214 | ysGFXohNyFRFQ06jmkjW | Normal | 1 | 1.3.2.3.2.3.4 | 1.3.2.3.2.3.4 |  | 2025-09-10 17:00 | p | 42 |  | 2025-10-23 08:32
87 | 7215 | a8OJFGtOVEyM75c9puYK | Summary | 34 | 1.3.2.3.2.4 | 1.3.2.3.2.4 |  | 2025-10-01 17:00 | p | 47 |  | 2025-11-18 11:12
88 | 7218 | 5fSpBiSdaCD1mvMsYs0j | Normal | 2 | 1.3.2.3.2.4.3 | 1.3.2.3.2.4.3 |  | 2025-08-15 17:00 | q | -185 |  | 2025-02-11 17:00
89 | 7219 | tMHxEODKuKminmE9Mjg5 | Normal | 1 | 1.3.2.3.2.4.4 | 1.3.2.3.2.4.4 |  | 2025-08-18 17:00 | q | -187 |  | 2025-02-12 17:00
90 | 7220 | nvywSXdnd0LSUGSiB3or | Normal | 10 | 1.3.2.3.2.4.5 | 1.3.2.3.2.4.5 |  | 2025-09-02 17:00 | p | 35 |  | 2025-10-08 16:47
91 | 7221 | PYoR7OoHLcblZDJJ1hTC | Normal | 20 | 1.3.2.3.2.4.6 | 1.3.2.3.2.4.6 |  | 2025-09-30 17:00 | p | 47 |  | 2025-11-17 11:04
92 | 7222 | W1KVKgORO9KqmU1uQFqG | Normal | 1 | 1.3.2.3.2.4.7 | 1.3.2.3.2.4.7 |  | 2025-10-01 17:00 | p | 47 |  | 2025-11-18 11:12
93 | 7223 | 2cLCJpvBPh4ccgbvKrEi | Summary | 38 | 1.3.2.3.2.5 | 1.3.2.3.2.5 |  | 2025-10-20 17:00 | p | 45 |  | 2025-12-05 10:57
94 | 7226 | fsyu9CvTMAXTCK7e04ez | Normal | 1 | 1.3.2.3.2.5.3 | 1.3.2.3.2.5.3 |  | 2025-09-10 17:00 | q | -212 |  | 2025-02-10 17:00
95 | 7227 | QiFvht1v2EB9ODLdNK6M | Normal | 25 | 1.3.2.3.2.5.4 | 1.3.2.3.2.5.4 |  | 2025-09-10 17:00 | p | 42 |  | 2025-10-23 08:32
96 | 7228 | SSqxRWtJ8NkhLwkx3Zp5 | Normal | 15 | 1.3.2.3.2.5.5 | 1.3.2.3.2.5.5 |  | 2025-10-01 17:00 | p | 47 |  | 2025-11-18 11:12
97 | 7514 | 4jhJaLUHxegkfPxUyChC | Normal | 15 | 1.3.2.3.2.5.9 | 1.3.2.3.2.5.9 |  | 2025-10-20 17:00 | p | 45 |  | 2025-12-05 10:57
98 | 7515 | jdxLrBmn54gbF5MbPNVU | Normal | 5 | 1.3.2.3.2.5.8 | 1.3.2.3.2.5.8 |  | 2025-09-26 17:00 | q | -224 |  | 2025-02-14 17:00
99 | 7231 | Kz2H44CrN943Xn6RI0Et | Summary | 19 | 1.3.2.3.3 | 1.3.2.3.3 |  | 2025-10-10 17:00 | p | 48 |  | 2025-11-28 15:44
100 | 7232 | cCMYeGs7uzTIiiDhvAui | Summary | 12 | 1.3.2.3.3.1 | 1.3.2.3.3.1 |  | 2025-10-01 17:00 | p | 47 |  | 2025-11-18 11:12
101 | 7233 | rgerXXfH5cOVWHlSbXtk | Normal | 2 | 1.3.2.3.3.1.1 | 1.3.2.3.3.1.1 |  | 2025-09-29 17:00 | p | 45 |  | 2025-11-14 09:00
102 | 7234 | 4Nk8AWONEAABjENRSl4s | Normal | 3 | 1.3.2.3.3.1.2 | 1.3.2.3.3.1.2 |  | 2025-09-29 17:00 | p | 45 |  | 2025-11-14 09:00
103 | 7235 | uR7e5eYUOS8ur8CkZgir | Normal | 2 | 1.3.2.3.3.1.3 | 1.3.2.3.3.1.3 |  | 2025-10-01 17:00 | p | 47 |  | 2025-11-18 11:12
104 | 7236 | OqdHv6QLhEyFdmarh5Mg | Normal | 5 | 1.3.2.3.3.1.4 | 1.3.2.3.3.1.4 |  | 2025-10-01 17:00 | p | 47 |  | 2025-11-18 11:12
105 | 7237 | xLl9f1S8pVLgozw4LZw4 | Normal | 10 | 1.3.2.3.3.1.5 | 1.3.2.3.3.1.5 |  | 2025-09-29 17:00 | p | 45 |  | 2025-11-14 14:54
106 | 7238 | hj0QAuvemNr4BSx0wqCM | Normal | 10 | 1.3.2.3.3.1.6 | 1.3.2.3.3.1.6 |  | 2025-09-29 17:00 | p | 45 |  | 2025-11-14 14:54
107 | 7239 | sGRMuNmZsu5Ap3rRR6Ja | Normal | 2 | 1.3.2.3.3.1.7 | 1.3.2.3.3.1.7 |  | 2025-10-01 17:00 | p | 47 |  | 2025-11-18 11:12
108 | 7240 | jJgg05qz3M4QbDAQ4nmn | Summary | 7 | 1.3.2.3.3.2 | 1.3.2.3.3.2 |  | 2025-10-10 17:00 | p | 48 |  | 2025-11-28 15:44
109 | 7241 | RP09WyAKLetAyeWXIWbd | Normal | 1 | 1.3.2.3.3.2.1 | 1.3.2.3.3.2.1 |  | 2025-10-02 17:00 | p | 47 |  | 2025-11-19 13:37
110 | 7242 | PNiOufePi0cnwKsaAHa8 | Normal | 3 | 1.3.2.3.3.2.2 | 1.3.2.3.3.2.2 |  | 2025-10-07 17:00 | p | 47 |  | 2025-11-24 10:39
111 | 7243 | nppwsC1hz1MTRepHit5q | Normal | 3 | 1.3.2.3.3.2.3 | 1.3.2.3.3.2.3 |  | 2025-10-10 17:00 | p | 48 |  | 2025-11-28 15:44
112 | 7244 | FpvbIzqyAjmrguHRtjoA | Summary | 68 | 1.3.2.3.4 | 1.3.2.3.4 |  | 2026-08-18 17:00 | q | 0 |  | 2026-08-18 13:44
113 | 7245 | ysJ2Wz17vAaH50NFOd3r | Normal | 2 | 1.3.2.3.4.1 | 1.3.2.3.4.1 |  | 2025-10-16 17:00 | p | 47 |  | 2025-12-03 11:13
114 | 7246 | w8OYvCOBO1azAOar59yv | Normal | 3 | 1.3.2.3.4.2 | 1.3.2.3.4.2 |  | 2025-10-16 17:00 | p | 47 |  | 2025-12-03 11:13
115 | 7247 | QmLDbLdk9YgltF6FQxKi | Normal | 2 | 1.3.2.3.4.3 | 1.3.2.3.4.3 |  | 2025-10-20 17:00 | p | 45 |  | 2025-12-05 10:57
116 | 7248 | nqyBToLUXvLl91VDFcK9 | Summary | 20 | 1.3.2.3.4.4 | 1.3.2.3.4.4 |  | 2026-06-09 17:00 | q | -1 |  | 2026-06-08 08:53
117 | 7249 | T3rEQsXy5TFYVzdnmRkQ | Normal | 20 | 1.3.2.3.4.4.1 | 1.3.2.3.4.4.1 |  | 2026-06-09 17:00 | q | -1 |  | 2026-06-08 08:53
118 | 7250 | G5mdz8DmOa8TGNlmxmOk | Normal | 20 | 1.3.2.3.4.4.2 | 1.3.2.3.4.4.2 |  | 2026-06-09 17:00 | q | -1 |  | 2026-06-08 08:53
119 | 7251 | p2IEwFFq1YxDgQwaqReT | Summary | 48 | 1.3.2.3.4.5 | 1.3.2.3.4.5 |  | 2026-08-18 17:00 | q | 0 |  | 2026-08-18 13:44
120 | 7252 | R4hlQqYwslHcXudIUORM | Normal | 20 | 1.3.2.3.4.5.1 | 1.3.2.3.4.5.1 |  | 2026-07-09 17:00 | p | 0 |  | 2026-07-10 13:13
121 | 7253 | 5Q6OCjUddDwnqpg2shNG | Normal | 5 | 1.3.2.3.4.5.2 | 1.3.2.3.4.5.2 |  | 2026-07-16 17:00 | p | 0 |  | 2026-07-17 13:52
122 | 7254 | aZsc8OQGYCtOtLNUDl4p | Normal | 7 | 1.3.2.3.4.5.3 | 1.3.2.3.4.5.3 |  | 2026-07-27 17:00 | p | 0 |  | 2026-07-28 09:35
123 | 7255 | GiGIxdlKVFOGW1rlVkpg | Normal | 5 | 1.3.2.3.4.5.4 | 1.3.2.3.4.5.4 |  | 2026-08-03 17:00 | p | 0 |  | 2026-08-04 09:40
124 | 7256 | ZTFxKau19KKCcFlUDIYg | Normal | 7 | 1.3.2.3.4.5.5 | 1.3.2.3.4.5.5 |  | 2026-08-12 17:00 | p | 0 |  | 2026-08-13 12:00
125 | 7257 | EmkT3sq6aGy3vx96JSsX | Normal | 3 | 1.3.2.3.4.5.6 | 1.3.2.3.4.5.6 |  | 2026-08-17 17:00 | q | 0 |  | 2026-08-17 14:54
126 | 7258 | PBxke5bv0Yk6xXbQcvVe | Normal | 1 | 1.3.2.3.4.5.7 | 1.3.2.3.4.5.7 |  | 2026-08-18 17:00 | q | 0 |  | 2026-08-18 13:44
127 | 6278 | SNMcp7h74WVvBiN3lPNB | Summary | 66 | 1.5.6 | 1.5.6 |  | 2026-01-30 17:00 | q | -31 |  | 2025-12-30 16:50
128 | 605 | HP2TrbmUH5Qc4V2P2k1T | Normal | 14 | 1.5.6.1 | 1.5.6.1 |  | 2025-10-09 15:00 | q | -30 |  | 2025-09-09 13:50
129 | 620 | q8advjPa5PEndSFXJ05j | Summary | 158 | 1.5.6.6 | 1.5.6.6 |  | 2026-01-30 17:00 | q | -31 |  | 2025-12-30 16:50
130 | 622 | Q48N5ZSDLesB1Bsda2wx | Summary | 156 | 1.5.6.6.2 | 1.5.6.6.2 |  | 2025-11-04 15:00 | q | -34 |  | 2025-10-01 10:53
131 | 631 | jjFU6HpNq2otAi9zmRWR | Normal | 2 | 1.5.6.6.2.7 | 1.5.6.6.2.7 |  | 2025-06-17 10:00 | q | -125 |  | 2025-02-11 17:00
132 | 632 | tuv9OmQcJHKkVCVrbrrv | Normal | 6 | 1.5.6.6.2.8 | 1.5.6.6.2.8 |  | 2025-06-26 10:00 | q | -29 |  | 2025-05-28 08:58
133 | 633 | FgJ5XjjThZN85XQOJ0nJ | Normal | 21 | 1.5.6.6.2.10 | 1.5.6.6.2.10 |  | 2025-08-04 10:00 | q | -33 |  | 2025-07-01 14:40
134 | 634 | o4DRQRcsScdVmCSXNbxF | Normal | 10 | 1.5.6.6.2.9 | 1.5.6.6.2.9 |  | 2025-08-15 15:00 | q | -29 |  | 2025-07-16 16:33
135 | 635 | ztvy5zkS4z9HirKgvHGY | Normal | 20 | 1.5.6.6.2.11 | 1.5.6.6.2.11 |  | 2025-09-15 15:00 | q | -35 |  | 2025-08-11 13:22
136 | 636 | ZpIfqMwIaczq2BqznW2q | Normal | 6 | 1.5.6.6.2.12 | 1.5.6.6.2.12 |  | 2025-09-23 15:00 | q | -33 |  | 2025-08-21 10:47
137 | 637 | 3VAZwvp2NS6usl0wrvOM | Normal | 7 | 1.5.6.6.2.13 | 1.5.6.6.2.13 |  | 2025-10-02 15:00 | q | -30 |  | 2025-09-02 13:54
138 | 638 | 34zoFClD9RS7gLTCPZs0 | Normal | 5 | 1.5.6.6.2.14 | 1.5.6.6.2.14 |  | 2025-10-09 15:00 | q | -30 |  | 2025-09-09 13:50
139 | 640 | 10AmMHkCz4b8n0xqbyCt | Normal | 5 | 1.5.6.6.2.16 | 1.5.6.6.2.16 |  | 2025-10-17 15:00 | q | -31 |  | 2025-09-16 08:44
140 | 641 | KUqcSNVxncHPLVJNV5ca | Normal | 2 | 1.5.6.6.2.17 | 1.5.6.6.2.17 |  | 2025-10-21 10:00 | q | -34 |  | 2025-09-17 09:59
141 | 642 | chCwawHUqn0ea2ArCnKB | Normal | 0 | 1.5.6.6.2.18 | 1.5.6.6.2.18 |  | 2025-10-21 15:00 | q | -34 |  | 2025-09-17 14:21
142 | 643 | xZBRzE3QVYmQCjnzxLQv | Normal | 4 | 1.5.6.6.2.19 | 1.5.6.6.2.19 |  | 2025-10-27 15:00 | q | -33 |  | 2025-09-23 16:34
143 | 644 | tUTeQ74YpmkuuOiouSXU | Normal | 5 | 1.5.6.6.2.20 | 1.5.6.6.2.20 |  | 2025-11-03 15:00 | q | -34 |  | 2025-09-30 11:49
144 | 645 | mSrjcTZmK12EdJmOEYFi | Normal | 1 | 1.5.6.6.2.21 | 1.5.6.6.2.21 |  | 2025-11-04 15:00 | q | -34 |  | 2025-10-01 10:53
145 | 646 | Haue3rYYySw3jbXWnBeq | Normal | 3 | 1.5.6.6.3 | 1.5.6.6.3 |  | 2025-11-07 15:00 | q | -31 |  | 2025-10-07 08:27
146 | 647 | 6jlP0Y4QQ5KPQWxvolLg | Normal | 1 | 1.5.6.6.4 | 1.5.6.6.4 |  | 2025-11-10 15:00 | q | -33 |  | 2025-10-08 08:40
147 | 648 | 6WPgljRre9DjhHGVsVUH | Summary | 120 | 1.5.6.6.5 | 1.5.6.6.5 |  | 2026-01-30 17:00 | q | -31 |  | 2025-12-30 16:50
148 | 656 | lzPFAx9Fh8cDxyQ3uxFX | Normal | 1 | 1.5.6.6.5.3 | 1.5.6.6.5.3 |  | 2025-11-12 17:00 | q | -34 |  | 2025-10-09 11:05
149 | 657 | nePaKBbqDo6OltylvukE | Summary | 14 | 1.5.6.6.5.4 | 1.5.6.6.5.4 |  | 2025-12-03 17:00 | q | -35 |  | 2025-10-29 15:37
150 | 658 | PyBKEPMZMe2YeOC66yut | Normal | 11 | 1.5.6.6.5.4.1 | 1.5.6.6.5.4.1 |  | 2025-11-28 17:00 | q | -35 |  | 2025-10-24 14:37
151 | 664 | H1KB0K8mM12Opvc4oDP1 | Normal | 3 | 1.5.6.6.5.4.2 | 1.5.6.6.5.4.2 |  | 2025-12-03 17:00 | q | -35 |  | 2025-10-29 15:37
152 | 665 | FIEbexlYHnOcZkEBs7WM | Normal | 5 | 1.5.6.6.5.5 | 1.5.6.6.5.5 |  | 2025-12-11 17:00 | q | -34 |  | 2025-11-07 08:14
153 | 666 | OcAHNnZWZgiwxfUiheGU | Normal | 5 | 1.5.6.6.5.6 | 1.5.6.6.5.6 |  | 2025-12-18 17:00 | q | -35 |  | 2025-11-13 15:55
154 | 667 | HPj21Hyun1nWvxJOQMhf | Normal | 28 | 1.5.6.6.5.7 | 1.5.6.6.5.7 |  | 2026-01-30 17:00 | q | -31 |  | 2025-12-30 16:50
155 | 670 | zBtIFoyMK1KgXAv407C9 | Summary | 29 | 1.5.6.5 | 1.5.6.5 |  | 2025-12-04 17:00 | q | -34 |  | 2025-10-31 09:06
156 | 671 | ZM52W2kHJJCM7052Da3J | Normal | 2 | 1.5.6.5.2 | 1.5.6.5.2 |  | 2025-12-03 17:00 | q | -35 |  | 2025-10-29 15:37
157 | 672 | AcRvLPQ7WrNfvcLBOWzV | Normal | 1 | 1.5.6.5.3 | 1.5.6.5.3 |  | 2025-12-04 17:00 | q | -34 |  | 2025-10-31 09:06
158 | 6141 | PCEOtJROHHMKXYkoR4rp | Normal | 3 | 1.5.6.5.1 | 1.5.6.5.1 |  | 2025-12-01 17:00 | q | -292 |  | 2025-02-12 17:00
159 | 6281 | RYPcKAyzQapOQ3GupQll | Summary | 104 | 1.5.5 | 1.5.5 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 13:20
160 | 1466 | LmBGiI2jXQ3lZF0l79sj | Summary | 104 | 1.5.5.1 | 1.5.5.1 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 13:20
161 | 1457 | W1XQ7yoZAeSgm7UftoXN | Normal | 1 | 1.5.5.1.2 | 1.5.5.1.2 |  | 2026-07-14 17:00 | q | -515 |  | 2025-02-14 17:00
162 | 1458 | W2l89btZYbaZZjxZTUR4 | Normal | 12 | 1.5.5.1.3 | 1.5.5.1.3 |  | 2026-07-30 17:00 | q | -2 |  | 2026-07-28 11:54
163 | 1459 | MxsNofofvf6CR0hsGInx | Normal | 1 | 1.5.5.1.4 | 1.5.5.1.4 |  | 2026-07-31 17:00 | q | -2 |  | 2026-07-29 11:36
164 | 1468 | 8e77YoSi4abIbMILI8hH | Normal | 5 | 1.5.5.1.5 | 1.5.5.1.5 |  | 2026-07-17 17:00 | q | -2 |  | 2026-07-15 11:49
165 | 1469 | MZooHRTMNCHrNy0nPaCQ | Normal | 1 | 1.5.5.1.6 | 1.5.5.1.6 |  | 2026-07-20 17:00 | q | -4 |  | 2026-07-16 13:51
166 | 1470 | PdTqfNwd2IKBXe26tWkB | Normal | 1 | 1.5.5.1.8 | 1.5.5.1.8 |  | 2026-08-03 17:00 | q | -4 |  | 2026-07-30 16:33
167 | 1471 | FsiT4ZMTOq9hGqZQQdYf | Normal | 11 | 1.5.5.1.9 | 1.5.5.1.9 |  | 2026-08-18 17:00 | p | 0 |  | 2026-08-19 13:51
168 | 1472 | KG0YDAdikr58WjA79FVb | Normal | 9 | 1.5.5.1.10 | 1.5.5.1.10 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 13:20
169 | 4584 | H2uIo7s6dGmX6mrjT7jd | Normal | 9 | 1.5.5.1.7 | 1.5.5.1.7 |  | 2026-07-31 17:00 | q | -2 |  | 2026-07-29 11:36
170 | 6292 | 1Cm9NXihvfL2WEnYcHvT | Summary | 42 | 1.5.4 | 1.5.4 |  | 2025-10-09 15:00 | q | -30 |  | 2025-09-09 13:50
171 | 3944 | HRTLaCTjRjqysGxmE6ve | Normal | 36 | 1.5.4.2 | 1.5.4.2 |  | 2025-07-02 10:00 | q | -32 |  | 2025-05-30 15:36
172 | 3945 | bJfaWXH8yBacWp0eqnXx | Normal | 1 | 1.5.4.3 | 1.5.4.3 |  | 2025-07-03 10:00 | q | -30 |  | 2025-06-03 08:06
173 | 3949 | knRWxUZkgPmXKgij09tb | Summary | 25 | 1.5.4.5 | 1.5.4.5 |  | 2025-09-23 15:00 | q | -33 |  | 2025-08-21 10:47
174 | 3950 | NJx1RMKdqhuNKRLGMSBQ | Summary | 27 | 1.5.4.5.1 | 1.5.4.5.1 |  | 2025-09-23 15:00 | q | -33 |  | 2025-08-21 10:47
175 | 3951 | BNWJw3sHADBJTHA2Ybu0 | Normal | 16 | 1.5.4.5.1.1 | 1.5.4.5.1.1 |  | 2025-09-11 15:00 | q | -33 |  | 2025-08-08 16:29
176 | 3952 | HkhDGF3pWO8GORFQnyh9 | Normal | 5 | 1.5.4.5.1.2 | 1.5.4.5.1.2 |  | 2025-09-18 15:00 | q | -31 |  | 2025-08-18 08:53
177 | 3953 | dYr7YcYkpYYUeESNUSkl | Normal | 2 | 1.5.4.5.1.3 | 1.5.4.5.1.3 |  | 2025-09-22 15:00 | q | -33 |  | 2025-08-20 10:11
178 | 3954 | r37KEs6OIDoMKT5Yz5nA | Normal | 1 | 1.5.4.5.1.4 | 1.5.4.5.1.4 |  | 2025-09-23 15:00 | q | -33 |  | 2025-08-21 10:47
179 | 3964 | ZzcX1hV2BTbfmTYJl5AE | Summary | 19 | 1.5.4.5.4 | 1.5.4.5.4 |  | 2025-08-27 15:00 | q | -32 |  | 2025-07-25 16:29
180 | 3967 | BaECEBO5p44IeRhOgeK2 | Normal | 19 | 1.5.4.5.4.3 | 1.5.4.5.4.3 |  | 2025-08-27 15:00 | q | -32 |  | 2025-07-25 16:29
181 | 5996 | M6DLFbZyZKXroBVfXncj | Summary | 19 | 1.5.4.4 | 1.5.4.4 |  | 2025-10-09 15:00 | q | -30 |  | 2025-09-09 13:50
182 | 3948 | 6ze4BjeYc1B5uifD0Fqa | Normal | 10 | 1.5.4.4.9 | 1.5.4.4.9 |  | 2025-05-30 10:00 | q | -28 |  | 2025-05-02 08:22
183 | 6202 | X3XRH6pSpuIgaacqwHSp | Normal | 14 | 1.5.4.4.10 | 1.5.4.4.10 |  | 2025-10-09 15:00 | q | -30 |  | 2025-09-09 13:50
184 | 6605 | Qtljmhuq3GHp8HrV3pPP | Normal | 6 | 1.5.4.4.7 | 1.5.4.4.7 |  | 2025-05-22 10:00 | q | -27 |  | 2025-04-24 15:52
185 | 6606 | pKonEcYtBOhP3mqLQIUx | Normal | 5 | 1.5.4.4.8 | 1.5.4.4.8 |  | 2025-05-30 10:00 | q | -28 |  | 2025-05-02 08:22
186 | 4213 | pNBoUl9px0n4wFhfXXqQ | Summary | 90 | 1.5.1.1 | 1.5.1.1 |  | 2025-07-03 10:00 | q | -30 |  | 2025-06-03 08:06
187 | 4215 | I07WrBLpDQufO3mvIdSu | Normal | 1 | 1.5.1.1.4 | 1.5.1.1.4 |  | 2025-07-03 10:00 | q | -30 |  | 2025-06-03 08:06
188 | 6444 | XymP4MvJgra2aDdoc9vw | Normal | 46 | 1.5.1.1.2 | 1.5.1.1.2 |  | 2025-04-30 10:00 | p | 4 |  | 2025-05-05 08:35
189 | 6445 | Wo6GLLiu9tXQyZ8t43hX | Normal | 43 | 1.5.1.1.3 | 1.5.1.1.3 |  | 2025-07-02 10:00 | q | -30 |  | 2025-06-02 08:43
190 | 6674 | 3EUoGYyEaAia67bx8maJ | Summary | 69 | 1.5.1.3 | 1.5.1.3 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 16:11
191 | 6680 | ttlvn3uwilh7nqgbHtE7 | Normal | 37 | 1.5.1.3.7 | 1.5.1.3.7 |  | 2026-08-12 17:00 | q | -1 |  | 2026-08-11 09:27
192 | 6681 | NHiN8b86HRxpkLb9JGGD | Normal | 10 | 1.5.1.3.9 | 1.5.1.3.9 |  | 2026-08-27 17:00 | p | 0 |  | 2026-08-28 08:46
193 | 6682 | 695WEwNqpcHeAbXSBRci | Normal | 2 | 1.5.1.3.10 | 1.5.1.3.10 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 16:11
194 | 6684 | TL3Mtv3QlGNejnoXktH7 | Normal | 1 | 1.5.1.3.8 | 1.5.1.3.8 |  | 2026-08-13 17:00 | q | -1 |  | 2026-08-12 11:05
195 | 5612 | JBIAfh9fImNsEXfXoHCz | Summary | 5 | 1.5.2.2.10 | 1.5.2.2.10 |  | 2026-07-30 17:00 | p | 4 |  | 2026-08-04 16:59
196 | 5613 | cc9QdsdOkkgaQ8ateKZX | Normal | 1 | 1.5.2.2.10.1 | 1.5.2.2.10.1 |  | 2026-07-27 09:36 | p | 2 |  | 2026-07-30 08:38
197 | 5614 | COTl0owSvMhEdF9iuXCz | Normal | 0 | 1.5.2.2.10.2 | 1.5.2.2.10.2 |  | 2026-07-27 14:36 | p | 2 |  | 2026-07-30 14:03
198 | 5615 | 0lLRNnxfg3utwoPLwt26 | Normal | 2 | 1.5.2.2.10.3 | 1.5.2.2.10.3 |  | 2026-07-29 14:36 | p | 4 |  | 2026-08-03 14:03
199 | 5616 | 5Z54Ad8GhuwKLjQHaz2Y | Normal | 1 | 1.5.2.2.10.4 | 1.5.2.2.10.4 |  | 2026-07-30 14:36 | p | 5 |  | 2026-08-04 14:37
200 | 5617 | fALGtnsfw381gf0W53Ia | Normal | 0 | 1.5.2.2.10.5 | 1.5.2.2.10.5 |  | 2026-07-30 17:00 | p | 4 |  | 2026-08-04 16:59
201 | 5627 | s0vjJX7zGlVyBdE0eigo | Summary | 15 | 1.5.2.2.8 | 1.5.2.2.8 |  | 2026-07-23 17:00 | p | 4 |  | 2026-07-28 15:47
202 | 5628 | JolyrZVyKy7n75ZL5gZI | Normal | 2 | 1.5.2.2.8.1 | 1.5.2.2.8.1 |  | 2026-07-14 12:00 | p | 5 |  | 2026-07-20 09:42
203 | 5629 | ghMhRqrbgVxCQv51dU2T | Normal | 0 | 1.5.2.2.8.2 | 1.5.2.2.8.2 |  | 2026-07-14 17:00 | p | 5 |  | 2026-07-20 14:53
204 | 5630 | eU3bwvC6wgraOvc5hiLt | Milestone | 0 | 1.5.2.2.8.3 | 1.5.2.2.8.3 |  | 2026-07-15 08:00 | p | 5 |  | 2026-07-20 14:53
205 | 5631 | gvTQVNdftDRXYXclyMFo | Normal | 3 | 1.5.2.2.8.4 | 1.5.2.2.8.4 |  | 2026-07-17 17:00 | p | 5 |  | 2026-07-23 13:45
206 | 5632 | DfRDIp64TG1m6LE7SSYQ | Milestone | 0 | 1.5.2.2.8.5 | 1.5.2.2.8.5 |  | 2026-07-20 08:00 | p | 3 |  | 2026-07-23 13:45
207 | 5633 | 2UPBwQymcCOUpuUjnBTe | Normal | 3 | 1.5.2.2.8.6 | 1.5.2.2.8.6 |  | 2026-07-22 17:00 | p | 4 |  | 2026-07-27 15:29
208 | 5634 | gm5pLWvICR0pU7aShOGD | Normal | 1 | 1.5.2.2.8.7 | 1.5.2.2.8.7 |  | 2026-07-23 17:00 | p | 4 |  | 2026-07-28 15:47
209 | 7545 | 65jUkOPqlMfpoMROhJ4O | Normal | 5 | 1.5.3.2.9.1 | 1.5.3.2.9.1 |  | 2026-07-09 17:00 | q | -510 |  | 2025-02-14 17:00
210 | 5635 | ZYzv9KOmVdYL2d3ZPb8b | Summary | 0 | 1.5.2.2.9 | 1.5.2.2.9 |  | 2025-02-03 12:00 | p | 540 |  | 2026-07-28 15:47
211 | 5637 | agdOsAK6kuG5dvRDXVyv | Milestone | 0 | 1.5.2.2.9.2 | 1.5.2.2.9.2 |  | 2025-01-08 17:00 | p | 538 |  | 2026-07-01 16:10
212 | 5638 | jBSFjjY1RfmWgqa8tOlO | Normal | 0 | 1.5.2.2.9.3 | 1.5.2.2.9.3 |  | 2025-01-24 17:00 | p | 542 |  | 2026-07-21 09:44
213 | 5639 | ymvGdGMdlU958QTwMU9V | Normal | 0 | 1.5.2.2.9.4 | 1.5.2.2.9.4 |  | 2025-01-27 12:00 | p | 540 |  | 2026-07-21 14:11
214 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | 2025-02-03 12:00 | p | 540 |  | 2026-07-28 15:47
215 | 6309 | taNk8S9bKnlDToaFycS6 | Summary | 37 | 1.5.3 | 1.5.3 |  | 2025-07-03 10:00 | q | -30 |  | 2025-06-03 08:06
216 | 5443 | L0xk8h495fvdhlwnri8N | Summary | 37 | 1.5.3.1 | 1.5.3.1 |  | 2025-07-03 10:00 | q | -30 |  | 2025-06-03 08:06
217 | 5445 | 95pLIsxhFDdrMJGVBrpQ | Summary | 35 | 1.5.3.1.2 | 1.5.3.1.2 |  | 2025-06-26 10:00 | q | -33 |  | 2025-05-23 16:25
218 | 5447 | ijJ4zfbEfOInLYX7Vu9Z | Normal | 6 | 1.5.3.1.2.2 | 1.5.3.1.2.2 |  | 2025-06-09 10:00 | q | -31 |  | 2025-05-09 09:28
219 | 5448 | cS9oDqhLQ00Df4o4XStO | Normal | 6 | 1.5.3.1.2.3 | 1.5.3.1.2.3 |  | 2025-06-17 10:00 | q | -31 |  | 2025-05-16 15:04
220 | 5449 | 6It4K5O7iZJhLoLO2jyi | Normal | 6 | 1.5.3.1.2.4 | 1.5.3.1.2.4 |  | 2025-06-26 10:00 | q | -33 |  | 2025-05-23 16:25
221 | 5450 | maMtUzorvxHWuMFIlXlq | Normal | 5 | 1.5.3.1.3 | 1.5.3.1.3 |  | 2025-07-03 10:00 | q | -30 |  | 2025-06-03 08:06
222 | 6270 | Wwp4MRWhcV55WleZhe1f | Summary | 288 | 1.4 | 1.4 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
223 | 576 | m8O5CFAYfVbtxxZI5qQW | Normal | 15 | 1.4.3.1.2 | 1.4.3.1.2 |  | 2026-03-11 17:00 | q | -33 |  | 2026-02-06 08:38
224 | 4536 | zU98x2LHVd7UXovDFMXu | Normal | 14 | 1.4.3.1.1 | 1.4.3.1.1 |  | 2026-03-12 17:00 | q | -34 |  | 2026-02-06 13:12
225 | 5854 | 2kqOvhRPajU4Q0ZPsUnx | Normal | 8 | 1.4.3.1.4 | 1.4.3.1.4 |  | 2026-03-30 17:00 | q | -32 |  | 2026-02-26 16:12
226 | 6607 | IhYDHpDNbof6PVOjQ9lw | Normal | 4 | 1.4.3.1.3 | 1.4.3.1.3 |  | 2026-03-18 17:00 | q | -34 |  | 2026-02-12 15:02
227 | 6291 | 7X6NK9qir9GRz5m7bXmK | Summary | 297 | 1.4.1 | 1.4.1 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
228 | 3891 | VQVEpj4HfOnKALplb4t9 | Summary | 43 | 1.4.1.1 | 1.4.1.1 |  | 2026-02-18 17:00 | q | -34 |  | 2026-01-15 10:24
229 | 3897 | cqWsQsQWdy7etYVMNQBf | Summary | 53 | 1.4.1.1.2 | 1.4.1.1.2 |  | 2026-02-18 17:00 | q | -34 |  | 2026-01-15 10:24
230 | 3900 | fYbjIfZDvkbYu7p7dq3N | Normal | 14 | 1.4.1.1.2.3 | 1.4.1.1.2.3 |  | 2026-02-11 17:00 | q | -34 |  | 2026-01-08 16:54
231 | 3901 | Jj1toL1YzUk95oK7OfgU | Normal | 4 | 1.4.1.1.2.4 | 1.4.1.1.2.4 |  | 2026-02-18 17:00 | q | -34 |  | 2026-01-15 10:24
232 | 3902 | FL4HGNxujC5zK4lN6AVO | Summary | 30 | 1.4.1.2 | 1.4.1.2 |  | 2026-03-16 17:00 | p | 7 |  | 2026-03-24 08:43
233 | 3903 | e0nMZ5CLCmjCURLrKpol | Summary | 30 | 1.4.1.2.1 | 1.4.1.2.1 |  | 2026-03-16 17:00 | p | 7 |  | 2026-03-24 08:43
234 | 6565 | XyBOyY3JpPW2h1I7PEur | Normal | 21 | 1.4.1.2.1.5 | 1.4.1.2.1.5 |  | 2026-03-13 17:00 | p | 9 |  | 2026-03-23 08:33
235 | 6566 | gAyE6SkFHV1MNEAJitQ7 | Normal | 1 | 1.4.1.2.1.6 | 1.4.1.2.1.6 |  | 2026-03-16 17:00 | p | 7 |  | 2026-03-24 08:43
236 | 3908 | y9tKov3jCEzWGyA9B1wJ | Normal | 5 | 1.4.1.3.1 | 1.4.1.3.1 |  | 2026-03-23 17:00 | p | 7 |  | 2026-03-31 10:09
237 | 3909 | VvjZ0oHXTTG06m5XlL1B | Normal | 10 | 1.4.1.3.2 | 1.4.1.3.2 |  | 2026-04-06 17:00 | p | 7 |  | 2026-04-14 09:59
238 | 3910 | pNRX5rV0uvvHnR27z1AO | Normal | 8 | 1.4.1.3.3 | 1.4.1.3.3 |  | 2026-04-16 17:00 | p | 6 |  | 2026-04-23 14:17
239 | 3911 | R3AK39H17lCC16PE9DkR | Normal | 10 | 1.4.1.3.4 | 1.4.1.3.4 |  | 2026-04-30 17:00 | p | 4 |  | 2026-05-05 13:12
240 | 3912 | BSEXS69UjCPQ6j2zF47p | Normal | 15 | 1.4.1.3.5 | 1.4.1.3.5 |  | 2026-05-21 17:00 | p | 0 |  | 2026-05-22 15:31
241 | 3913 | nUmJBAacPI2xORV8OCED | Normal | 20 | 1.4.1.3.6 | 1.4.1.3.6 |  | 2026-06-22 17:00 | p | 3 |  | 2026-06-26 14:17
242 | 3914 | e7efPn2W4IFyilt2hNai | Normal | 30 | 1.4.1.3.7 | 1.4.1.3.7 |  | 2026-08-04 17:00 | q | -1 |  | 2026-08-03 14:27
243 | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Normal | 5 | 1.4.1.3.8 | 1.4.1.3.8 |  | 2026-08-11 17:00 | q | 0 |  | 2026-08-11 14:56
244 | 3916 | xcLTkuiw0V5a2mOSGmcP | Normal | 10 | 1.4.1.3.9 | 1.4.1.3.9 |  | 2026-08-25 17:00 | q | 0 |  | 2026-08-25 10:38
245 | 3918 | VKkEEklTkhlAtqntT93x | Summary | 160 | 1.4.1.4 | 1.4.1.4 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
246 | 3919 | 70MdVf3krr3KZdDhEaoj | Normal | 1 | 1.4.1.4.1 | 1.4.1.4.1 |  | 2028-06-20 17:00 | p | 184 |  | 2028-12-22 09:32
247 | 3920 | mBVNyTIN7rvKyNQxzyxZ | Normal | 9 | 1.4.1.4.2 | 1.4.1.4.2 |  | 2028-07-03 17:00 | p | 183 |  | 2029-01-03 16:25
248 | 3921 | jEuseC90wYhkn0V4svXs | Normal | 3 | 1.4.1.4.3 | 1.4.1.4.3 |  | 2028-07-06 17:00 | p | 185 |  | 2029-01-08 15:21
249 | 3922 | yD55zWPn8USsNa4i8nCC | Normal | 5 | 1.4.1.4.4 | 1.4.1.4.4 |  | 2028-07-13 17:00 | p | 187 |  | 2029-01-17 14:23
250 | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Normal | 15 | 1.4.1.4.5 | 1.4.1.4.5 |  | 2028-08-03 17:00 | p | 196 |  | 2029-02-16 15:12
251 | 3924 | N1CigBiMQE2J41ZAMkt0 | Normal | 20 | 1.4.1.4.6 | 1.4.1.4.6 |  | 2028-08-31 17:00 | p | 200 |  | 2029-03-20 15:22
252 | 3925 | hSr4t1vn7GiB6Kp7YK0M | Normal | 5 | 1.4.1.4.7 | 1.4.1.4.7 |  | 2028-09-07 17:00 | p | 199 |  | 2029-03-26 14:44
253 | 3926 | vGJMK6sejFbKR6Gom2up | Normal | 5 | 1.4.1.4.8 | 1.4.1.4.8 |  | 2028-09-14 17:00 | p | 201 |  | 2029-04-04 14:08
254 | 3927 | 3RLmiC17tI4E2ggNuRe0 | Normal | 5 | 1.4.1.4.9 | 1.4.1.4.9 |  | 2028-09-21 17:00 | p | 202 |  | 2029-04-12 15:10
255 | 3928 | hCBFci3gUopMkWW2dQQj | Normal | 5 | 1.4.1.4.10 | 1.4.1.4.10 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
256 | 6318 | cM5VCGnPiK1mfNJo8YLF | Summary | 309 | 1.4.2 | 1.4.2 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
257 | 5213 | 6YmlQVHNVjUNryBHQf8a | Summary | 61 | 1.4.2.2.3 | 1.4.2.2.3 |  | 2026-01-30 17:00 | q | -31 |  | 2025-12-30 16:50
258 | 5214 | KnSim1DOJ7A0BYyW8QOP | Milestone | 0 | 1.4.2.2.3.1 | 1.4.2.2.3.1 |  | 2025-11-04 08:00 | q | -27 |  | 2025-10-07 11:32
259 | 5215 | KawuX1icbWQB8WlKVKy9 | Normal | 60 | 1.4.2.2.3.2 | 1.4.2.2.3.2 |  | 2026-01-29 17:00 | q | -31 |  | 2025-12-29 12:00
260 | 5216 | xOecB4tLtQXauOnWGD4l | Normal | 1 | 1.4.2.2.3.3 | 1.4.2.2.3.3 |  | 2026-01-30 17:00 | q | -31 |  | 2025-12-30 16:50
261 | 5217 | e116DivbRDCkLiH2zNhl | Summary | 61 | 1.4.2.2.4 | 1.4.2.2.4 |  | 2026-03-11 17:00 | q | -33 |  | 2026-02-06 08:38
262 | 5218 | 8GMyARBjPLtiSR4txAaa | Milestone | 0 | 1.4.2.2.4.1 | 1.4.2.2.4.1 |  | 2025-12-16 08:00 | q | -40 |  | 2025-11-05 16:04
263 | 5219 | Uz3hspiJXkYJElXZ00I5 | Normal | 60 | 1.4.2.2.4.2 | 1.4.2.2.4.2 |  | 2026-03-10 17:00 | q | -33 |  | 2026-02-05 09:12
264 | 5220 | QAqXx5k5ldQJaugZyYbR | Normal | 1 | 1.4.2.2.4.3 | 1.4.2.2.4.3 |  | 2026-03-11 17:00 | q | -33 |  | 2026-02-06 08:38
265 | 5221 | iTaWceiQKMF6gUaF3DCB | Summary | 61 | 1.4.2.2.5 | 1.4.2.2.5 |  | 2026-04-24 17:00 | q | -30 |  | 2026-03-25 10:00
266 | 5222 | 4u5ocGGr0fcTRpzuglXZ | Milestone | 0 | 1.4.2.2.5.1 | 1.4.2.2.5.1 |  | 2026-01-30 08:00 | q | -29 |  | 2025-12-31 10:17
267 | 5223 | 3nEJb4lsc7akFmF6ULw7 | Normal | 60 | 1.4.2.2.5.2 | 1.4.2.2.5.2 |  | 2026-04-23 17:00 | q | -30 |  | 2026-03-24 09:57
268 | 5224 | PvORb6t1pqf23aOFbh3S | Normal | 1 | 1.4.2.2.5.3 | 1.4.2.2.5.3 |  | 2026-04-24 17:00 | q | -30 |  | 2026-03-25 10:00
269 | 5277 | TgmqG1sR4A60sNmMtPcE | Summary | 193 | 1.4.2.2.7 | 1.4.2.2.7 |  | 2026-06-02 08:00 | q | -12 |  | 2026-05-20 13:00
270 | 5278 | OmCdw3tKtVsW24V2aNqQ | Normal | 8 | 1.4.2.2.7.1 | 1.4.2.2.7.1 |  | 2025-12-09 08:03 | q | -31 |  | 2025-11-07 13:12
271 | 5279 | htHZ3VhuaadgfKg1VQls | Summary | 47 | 1.4.2.2.7.11 | 1.4.2.2.7.11 |  | 2026-05-18 09:00 | q | -12 |  | 2026-05-05 14:41
272 | 5280 | q0a2rl5NSMPQe2o4IYAd | Normal | 3 | 1.4.2.2.7.11.1 | 1.4.2.2.7.11.1 |  | 2026-04-20 09:00 | q | -23 |  | 2026-03-27 16:25
273 | 5281 | 3GO4XZOZrW4CEje40UJT | Normal | 5 | 1.4.2.2.7.11.2 | 1.4.2.2.7.11.2 |  | 2026-04-20 09:00 | q | -23 |  | 2026-03-27 16:25
274 | 5282 | qBzS7vPbhPVzs7sVXgmM | Normal | 5 | 1.4.2.2.7.11.3 | 1.4.2.2.7.11.3 |  | 2026-04-20 09:00 | q | -23 |  | 2026-03-27 16:25
275 | 5283 | fU0pzeQGz2MN3lZmznFh | Normal | 5 | 1.4.2.2.7.11.4 | 1.4.2.2.7.11.4 |  | 2026-04-20 09:00 | q | -23 |  | 2026-03-27 16:25
276 | 5284 | epM0xPGW4QTSpblHVWYc | Normal | 10 | 1.4.2.2.7.11.5 | 1.4.2.2.7.11.5 |  | 2026-05-04 09:00 | q | -16 |  | 2026-04-17 17:00
277 | 5285 | ffNcVsnPBySsZbQiEShc | Normal | 10 | 1.4.2.2.7.11.6 | 1.4.2.2.7.11.6 |  | 2026-05-18 09:00 | q | -12 |  | 2026-05-05 14:41
278 | 5286 | Yb8sH9U5B9gBzfVjcJKN | Normal | 6 | 1.4.2.2.7.12 | 1.4.2.2.7.12 |  | 2026-05-25 17:00 | q | -12 |  | 2026-05-13 13:32
279 | 5287 | bhDhrVJ9ZVKMNyReuPKm | Normal | 5 | 1.4.2.2.7.13 | 1.4.2.2.7.13 |  | 2026-06-01 17:00 | q | -12 |  | 2026-05-20 12:00
280 | 5288 | RIVzpLwElpoiAIgfwKiL | Milestone | 0 | 1.4.2.2.7.14 | 1.4.2.2.7.14 |  | 2026-06-02 08:00 | q | -12 |  | 2026-05-20 13:00
281 | 6457 | PFYaNHtSBj97Eh5ysTvH | Normal | 7 | 1.4.2.2.7.2 | 1.4.2.2.7.2 |  | 2025-12-18 08:03 | q | -30 |  | 2025-11-17 16:19
282 | 6458 | pDFztlVdvvSj2i4Cz5Z9 | Normal | 5 | 1.4.2.2.7.3 | 1.4.2.2.7.3 |  | 2025-12-26 08:03 | q | -31 |  | 2025-11-24 16:17
283 | 6459 | ylmwXTiOnCLJpwlHTaRg | Normal | 10 | 1.4.2.2.7.4 | 1.4.2.2.7.4 |  | 2026-01-09 08:03 | q | -28 |  | 2025-12-11 14:23
284 | 6460 | CystLMJtc4xxgICiEMDQ | Normal | 8 | 1.4.2.2.7.5 | 1.4.2.2.7.5 |  | 2026-01-21 08:03 | q | -28 |  | 2025-12-23 13:38
285 | 6461 | 7ypQo0ZyAHzCHmFRlywg | Normal | 10 | 1.4.2.2.7.6 | 1.4.2.2.7.6 |  | 2026-02-04 08:03 | q | -25 |  | 2026-01-09 11:55
286 | 6462 | BWDOi71UCejcEb1fgeoY | Normal | 7 | 1.4.2.2.7.7 | 1.4.2.2.7.7 |  | 2026-02-13 08:03 | q | -23 |  | 2026-01-20 09:54
287 | 6463 | OelD6citgJccZhV0UyvH | Normal | 7 | 1.4.2.2.7.8 | 1.4.2.2.7.8 |  | 2026-02-24 08:03 | q | -25 |  | 2026-01-29 13:07
288 | 6464 | McSTYqZ3LCfaYSSmZoTn | Normal | 7 | 1.4.2.2.7.9 | 1.4.2.2.7.9 |  | 2026-03-05 08:03 | q | -26 |  | 2026-02-06 15:38
289 | 6465 | WAyiiuxKOgY7bZWYUV9d | Normal | 5 | 1.4.2.2.7.10 | 1.4.2.2.7.10 |  | 2026-03-12 08:03 | q | -26 |  | 2026-02-13 17:00
290 | 5226 | R9JO9mOSGmg0eoDimoJT | Summary | 71 | 1.4.2.1 | 1.4.2.1 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 10:06
291 | 5240 | NSmZbDTp76mGzDSQ7Ceh | Summary | 56 | 1.4.2.1.3 | 1.4.2.1.3 |  | 2025-08-27 08:32 | q | -27 |  | 2025-07-30 17:00
292 | 5241 | v6EKIZLcnDHW8CXOrD7y | Normal | 21 | 1.4.2.1.3.1 | 1.4.2.1.3.1 |  | 2025-07-09 08:32 | q | -60 |  | 2025-05-09 10:30
293 | 5242 | JYCfpao49G3jD8M94S66 | Normal | 10 | 1.4.2.1.3.2 | 1.4.2.1.3.2 |  | 2025-07-23 08:32 | q | -56 |  | 2025-05-27 11:17
294 | 5243 | 0XN39P602kPVdw6rXYZi | Normal | 10 | 1.4.2.1.3.3 | 1.4.2.1.3.3 |  | 2025-08-06 08:32 | q | -27 |  | 2025-07-09 09:50
295 | 5244 | Nwqnc6xsOuQ8oMDbKNfv | Normal | 15 | 1.4.2.1.3.4 | 1.4.2.1.3.4 |  | 2025-08-27 08:32 | q | -27 |  | 2025-07-30 17:00
296 | 5262 | PI0DE6xTKT4gLnHpqgjE | Summary | 137 | 1.4.2.1.6 | 1.4.2.1.6 |  | 2025-08-27 08:32 | q | -27 |  | 2025-07-31 06:29
297 | 5263 | URhzXaXmWu6rBPIMitrn | Normal | 30 | 1.4.2.1.6.1 | 1.4.2.1.6.1 |  | 2025-03-24 17:00 | p | 28 |  | 2025-04-22 14:42
298 | 5265 | ATYnDTN93dB3aTXfzslo | Normal | 6 | 1.4.2.1.6.2 | 1.4.2.1.6.2 |  | 2025-03-06 11:02 | p | 33 |  | 2025-04-08 15:30
299 | 5266 | G5H4IlBy3M3Zxs38gcIH | Normal | 10 | 1.4.2.1.6.3 | 1.4.2.1.6.3 |  | 2025-03-20 14:02 | p | 34 |  | 2025-04-23 16:07
300 | 5267 | 3RI5G3ymKjaLn96cfboa | Normal | 11 | 1.4.2.1.6.4 | 1.4.2.1.6.4 |  | 2025-04-03 14:02 | p | 24 |  | 2025-04-28 10:29
301 | 5268 | fG9nayiE82fFlNFtuyfN | Normal | 8 | 1.4.2.1.6.5 | 1.4.2.1.6.5 |  | 2025-08-27 08:32 | q | -27 |  | 2025-07-30 17:00
302 | 5269 | UP8sWsDXCDMiwOqWz3ib | Normal | 5 | 1.4.2.1.6.6 | 1.4.2.1.6.6 |  | 2025-06-16 09:02 | q | -37 |  | 2025-05-09 16:18
303 | 5270 | 0UA65kBzwzHULCayr1Gq | Normal | 8 | 1.4.2.1.6.7 | 1.4.2.1.6.7 |  | 2025-06-30 08:32 | q | -37 |  | 2025-05-23 14:32
304 | 5271 | mtztJWmm2OBnfmSsuoGt | Normal | 10 | 1.4.2.1.6.8 | 1.4.2.1.6.8 |  | 2025-07-15 08:32 | q | -34 |  | 2025-06-10 13:50
305 | 5272 | kvS9pO69DNwaLvofAQcb | Normal | 11 | 1.4.2.1.6.9 | 1.4.2.1.6.9 |  | 2025-07-30 08:32 | q | -27 |  | 2025-07-02 09:04
306 | 5273 | fGHKYfAaAseAkWqOpGpv | Normal | 10 | 1.4.2.1.6.10 | 1.4.2.1.6.10 |  | 2025-08-13 08:32 | q | -27 |  | 2025-07-16 16:12
307 | 5274 | zjsmmZ1Zvuz0mxAk4wzH | Normal | 10 | 1.4.2.1.6.11 | 1.4.2.1.6.11 |  | 2025-08-27 08:32 | q | -27 |  | 2025-07-30 17:00
308 | 5275 | lBTJLZ8EG6vqarjSz7m6 | Milestone | 0 | 1.4.2.1.6.12 | 1.4.2.1.6.12 |  | 2025-08-27 08:32 | q | -27 |  | 2025-07-31 06:29
309 | 5264 | 2BYRPY9ftrCpjg2j3vxJ | Milestone | 0 | 1.4.2.1.8 | 1.4.2.1.8 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 10:06
310 | 5276 | yja2Gk0YbNXya3vsxrwh | Milestone | 0 | 1.4.2.1.7 | 1.4.2.1.7 |  | 2025-08-27 08:32 | q | -27 |  | 2025-07-31 06:29
311 | 5289 | tqKGxL2oceRufkd47wnf | Summary | 319 | 1.4.2.3 | 1.4.2.3 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
312 | 5290 | NEvSl0zKCrGJ6lqshTZO | Milestone | 0 | 1.4.2.3.1 | 1.4.2.3.1 |  | 2026-04-27 08:00 | q | -32 |  | 2026-03-25 10:00
313 | 5313 | 3y8KKUl940HiJi7UFKFT | Summary | 106 | 1.4.2.3.3 | 1.4.2.3.3 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
314 | 5314 | SRtjKDi8lC5PBWdNdIAU | Normal | 10 | 1.4.2.3.3.1 | 1.4.2.3.3.1 |  | 2028-05-30 11:53 | p | 197 |  | 2028-12-13 17:00
315 | 5316 | LCfcLPfxTjnSY0dCrjlE | Normal | 10 | 1.4.2.3.3.2 | 1.4.2.3.3.2 |  | 2028-06-14 11:54 | p | 197 |  | 2028-12-29 11:33
316 | 5317 | pw6YyMXR7oeqsrtIHdqo | Normal | 9 | 1.4.2.3.3.3 | 1.4.2.3.3.3 |  | 2028-07-07 10:04 | p | 200 |  | 2029-01-23 14:04
317 | 5318 | KMG5hXAC4X2MZPfyVOSc | Normal | 5 | 1.4.2.3.3.8 | 1.4.2.3.3.8 |  | 2028-08-11 10:04 | p | 201 |  | 2029-02-28 14:03
318 | 5319 | mDGXCmTQB2ITo8MYwlYq | Normal | 5 | 1.4.2.3.3.9 | 1.4.2.3.3.9 |  | 2028-08-18 10:04 | p | 201 |  | 2029-03-08 09:52
319 | 5320 | hu6UActfLD0rLfdNqC55 | Normal | 5 | 1.4.2.3.3.10 | 1.4.2.3.3.10 |  | 2028-08-25 10:04 | p | 201 |  | 2029-03-15 09:49
320 | 5321 | pG9QTaeiPcJe7Bm3iI1s | Normal | 5 | 1.4.2.3.3.11 | 1.4.2.3.3.11 |  | 2028-09-01 10:04 | p | 202 |  | 2029-03-22 13:45
321 | 5322 | oNpYocgOFdrRcJiQE0H5 | Normal | 5 | 1.4.2.3.3.12 | 1.4.2.3.3.12 |  | 2028-09-08 10:04 | p | 203 |  | 2029-03-30 10:26
322 | 5323 | Tt5dEbDabBigq84Eat5c | Normal | 5 | 1.4.2.3.3.13 | 1.4.2.3.3.13 |  | 2028-09-15 10:04 | p | 203 |  | 2029-04-06 11:45
323 | 5324 | INz2wzhVzgQCZLXqwTZc | Normal | 5 | 1.4.2.3.3.14 | 1.4.2.3.3.14 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 09:37
324 | 5325 | D5c4JntP5EU4thbOE4hi | Normal | 1 | 1.4.2.3.3.15 | 1.4.2.3.3.15 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
325 | 6467 | n3qEWBmgcrCNzbacKk03 | Normal | 5 | 1.4.2.3.3.4 | 1.4.2.3.3.4 |  | 2028-07-14 10:04 | p | 200 |  | 2029-01-30 13:58
326 | 6468 | BqsEZH5IWCI59bWKml0D | Normal | 5 | 1.4.2.3.3.5 | 1.4.2.3.3.5 |  | 2028-07-21 10:04 | p | 200 |  | 2029-02-07 08:06
327 | 6469 | TtC6fzAb8zClFAVfKkP8 | Normal | 5 | 1.4.2.3.3.6 | 1.4.2.3.3.6 |  | 2028-07-28 10:04 | p | 200 |  | 2029-02-13 16:38
328 | 6470 | UrgnPc0HjVwpN7twGsWX | Normal | 5 | 1.4.2.3.3.7 | 1.4.2.3.3.7 |  | 2028-08-04 10:04 | p | 200 |  | 2029-02-20 16:42
329 | 5326 | esDa5lJIA5zg0nP58cRd | Summary | 32 | 1.4.2.3.4 | 1.4.2.3.4 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
330 | 5327 | iRZmxts3rKQ38tplQw52 | Normal | 30 | 1.4.2.3.4.1 | 1.4.2.3.4.1 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 16:20
331 | 5329 | GYUaK0PI1fV4kag2egD8 | Normal | 1 | 1.4.2.3.4.3 | 1.4.2.3.4.3 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
332 | 5298 | c4SSanbHhynqs8RkqT3I | Normal | 3 | 1.4.2.3.2.2 | 1.4.2.3.2.2 |  | 2026-02-18 17:00 | q | -33 |  | 2026-01-16 15:55
333 | 5299 | HB5wL9z8KlZFeAas0WUQ | Normal | 11 | 1.4.2.3.2.3 | 1.4.2.3.2.3 |  | 2026-03-05 17:00 | q | -31 |  | 2026-02-02 10:36
334 | 5301 | hHw9byxBfgMW8zXuSsdj | Milestone | 0 | 1.4.2.3.2.12 | 1.4.2.3.2.12 |  | 2026-04-20 08:00 | q | -34 |  | 2026-03-16 16:58
335 | 5302 | 2rc67Y2hzAhRvE7YihWA | Normal | 10 | 1.4.2.3.2.1 | 1.4.2.3.2.1 |  | 2026-02-13 17:00 | q | -32 |  | 2026-01-12 16:55
336 | 5303 | SgeIRg4ykwxbNqD9urWV | Normal | 2 | 1.4.2.3.2.8 | 1.4.2.3.2.8 |  | 2026-04-08 17:00 | q | -34 |  | 2026-03-05 16:20
337 | 5304 | KRXQrBZsFBKS9k4FvAsp | Normal | 3 | 1.4.2.3.2.9 | 1.4.2.3.2.9 |  | 2026-04-13 17:00 | q | -34 |  | 2026-03-10 16:25
338 | 5305 | TyGQYH0bANBrFjXmh15D | Normal | 2 | 1.4.2.3.2.10 | 1.4.2.3.2.10 |  | 2026-04-15 17:00 | q | -33 |  | 2026-03-13 08:25
339 | 5306 | yar7ts7ASIpTQqyvnwQd | Normal | 5 | 1.4.2.3.2.13 | 1.4.2.3.2.13 |  | 2026-04-24 17:00 | q | -30 |  | 2026-03-25 10:00
340 | 5307 | yRByGMPgEQcCecr5HzAA | Normal | 2 | 1.4.2.3.2.15 | 1.4.2.3.2.15 |  | 2026-04-29 17:00 | q | -27 |  | 2026-04-02 16:29
341 | 5308 | JBAsTSNPb9OQmIAmtadV | Normal | 20 | 1.4.2.3.2.17 | 1.4.2.3.2.17 |  | 2026-05-28 17:00 | q | -10 |  | 2026-05-18 10:31
342 | 5309 | xRRT514kq8kwyv7njrs5 | Normal | 5 | 1.4.2.3.2.19 | 1.4.2.3.2.19 |  | 2026-06-08 17:00 | q | -12 |  | 2026-05-27 12:00
343 | 5310 | RMnJ5j2lLGlokfxLAfSa | Normal | 2 | 1.4.2.3.2.20 | 1.4.2.3.2.20 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 16:05
344 | 5311 | BowxNbb4uXSnAk8z8ZkC | Normal | 2 | 1.4.2.3.2.22 | 1.4.2.3.2.22 |  | 2026-06-12 17:00 | q | -10 |  | 2026-06-02 15:34
345 | 6516 | qmbk7ROGAo4AwJOySAlG | Normal | 4 | 1.4.2.3.2.4 | 1.4.2.3.2.4 |  | 2026-03-11 17:00 | q | -33 |  | 2026-02-06 08:38
346 | 6517 | YGaikKlMVGc6fqtUBZ7h | Normal | 5 | 1.4.2.3.2.5 | 1.4.2.3.2.5 |  | 2026-03-18 17:00 | q | -34 |  | 2026-02-12 15:02
347 | 6518 | 0rDsNLFYCabTnyCcopAQ | Normal | 8 | 1.4.2.3.2.6 | 1.4.2.3.2.6 |  | 2026-03-30 17:00 | q | -34 |  | 2026-02-24 15:12
348 | 6519 | UldK3RoYRJH5Hsfv02Lh | Normal | 2 | 1.4.2.3.2.7 | 1.4.2.3.2.7 |  | 2026-04-01 17:00 | q | -34 |  | 2026-02-26 10:27
349 | 6520 | UaqqB30tdDFCsCHRRpeh | Normal | 2 | 1.4.2.3.2.11 | 1.4.2.3.2.11 |  | 2026-04-17 17:00 | q | -32 |  | 2026-03-16 16:58
350 | 6521 | LDY9CVOjImzsQ4NE65Qz | Normal | 1 | 1.4.2.3.2.16 | 1.4.2.3.2.16 |  | 2026-04-30 17:00 | q | -24 |  | 2026-04-06 08:40
351 | 6522 | WYJvDx3FrKALT2lj4FIo | Normal | 2 | 1.4.2.3.2.18 | 1.4.2.3.2.18 |  | 2026-06-01 17:00 | q | -12 |  | 2026-05-20 12:00
352 | 6523 | TvM5XBX3OaVljTSOZ4e2 | Normal | 2 | 1.4.2.3.2.21 | 1.4.2.3.2.21 |  | 2026-06-10 17:00 | q | -12 |  | 2026-05-29 15:34
353 | 6524 | cvaJgvK8KpGYV8ykH12h | Normal | 2 | 1.4.2.3.2.23 | 1.4.2.3.2.23 |  | 2026-06-16 17:00 | q | -12 |  | 2026-06-04 16:29
354 | 6525 | GtEwLNkefPtnncnl90X4 | Normal | 3 | 1.4.2.3.2.24 | 1.4.2.3.2.24 |  | 2026-06-26 17:00 | q | -11 |  | 2026-06-15 14:15
355 | 6873 | gSZIbC6fsU6IM6McOJy8 | Normal | 1 | 1.4.2.3.2.14 | 1.4.2.3.2.14 |  | 2026-04-27 17:00 | q | -32 |  | 2026-03-26 10:43
356 | 6271 | Q6QswYSvhipRUbZBXuiu | Summary | 315 | 1.6 | 1.6 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
357 | 6277 | moVS9Ou3GclDwNSW1OnS | Summary | 264 | 1.6.7 | 1.6.7 |  | 2028-09-21 17:00 | p | 203 |  | 2029-04-13 11:38
358 | 678 | N57z7OkXN935WcKbC4jO | Normal | 1 | 1.6.7.2 | 1.6.7.2 |  | 2028-03-24 17:00 | p | 191 |  | 2028-10-02 08:24
359 | 700 | PZaQwD8fp0dlxZIxEZEd | Normal | 279 | 1.6.7.10 | 1.6.7.10 |  | 2028-03-17 17:00 | p | 180 |  | 2028-09-14 10:52
360 | 728 | 4dRz6TQj3FOK8lstTqZK | Summary | 396 | 1.6.7.9 | 1.6.7.9 |  | 2028-03-29 17:00 | p | 188 |  | 2028-10-04 16:59
361 | 741 | cktDjgZ5bp36SrQnCM1w | Summary | 458 | 1.6.7.9.3 | 1.6.7.9.3 |  | 2028-03-29 17:00 | p | 188 |  | 2028-10-04 16:59
362 | 751 | AADJzuTGAb4gWytj7CQi | Normal | 18 | 1.6.7.9.3.8 | 1.6.7.9.3.8 |  | 2027-08-09 17:00 | p | 176 |  | 2028-02-02 16:35
363 | 752 | r0c0rFS4EkOGynasmiCG | Normal | 36 | 1.6.7.9.3.7 | 1.6.7.9.3.7 |  | 2027-09-02 17:00 | p | 171 |  | 2028-02-21 14:58
364 | 759 | cZuo3MY7iyDrOJC1qVJx | Normal | 5 | 1.6.7.9.3.9 | 1.6.7.9.3.9 |  | 2027-08-16 17:00 | p | 176 |  | 2028-02-09 11:19
365 | 765 | qOEfFivvitnF8cw9csOP | Normal | 1 | 1.6.7.9.3.13 | 1.6.7.9.3.13 |  | 2028-03-24 17:00 | p | 191 |  | 2028-10-02 08:24
366 | 5773 | OCcI80TDGF8LlIXj66uV | Normal | 3 | 1.6.7.9.3.14 | 1.6.7.9.3.14 |  | 2028-03-29 17:00 | p | 188 |  | 2028-10-04 16:59
367 | 6323 | aU24Z8SrLl20SyyllZuy | Summary | 80 | 1.6.7.9.3.5 | 1.6.7.9.3.5 |  | 2027-04-12 17:00 | p | 178 |  | 2027-10-08 16:52
368 | 745 | aO52oWR4hBrrP5GVCo2a | Normal | 11 | 1.6.7.9.3.5.2 | 1.6.7.9.3.5.2 |  | 2027-03-11 17:00 | p | 179 |  | 2027-09-07 15:26
369 | 746 | qMC0J8brk1dsdpzlKrk7 | Normal | 12 | 1.6.7.9.3.5.3 | 1.6.7.9.3.5.3 |  | 2027-04-12 17:00 | p | 178 |  | 2027-10-08 16:52
370 | 6324 | gthK0FxwJBk3laTELp8O | Summary | 45 | 1.6.7.9.3.6 | 1.6.7.9.3.6 |  | 2027-06-14 17:00 | p | 178 |  | 2027-12-10 08:01
371 | 747 | nul8vpOEtI2Q6W5Q0Qo9 | Normal | 12 | 1.6.7.9.3.6.1 | 1.6.7.9.3.6.1 |  | 2027-04-28 17:00 | p | 181 |  | 2027-10-27 10:02
372 | 748 | M1HHh2K01o23jS8vpDxS | Normal | 11 | 1.6.7.9.3.6.2 | 1.6.7.9.3.6.2 |  | 2027-05-13 17:00 | p | 181 |  | 2027-11-11 08:46
373 | 749 | Q6UXOpf9Kvzek7IGY0vp | Normal | 11 | 1.6.7.9.3.6.3 | 1.6.7.9.3.6.3 |  | 2027-05-28 17:00 | p | 179 |  | 2027-11-24 11:14
374 | 750 | lsyrPytnmjLTpXFywa7Z | Normal | 11 | 1.6.7.9.3.6.4 | 1.6.7.9.3.6.4 |  | 2027-06-14 17:00 | p | 178 |  | 2027-12-10 08:01
375 | 6325 | SeCXD5wMvkrEekc1PKVb | Summary | 48 | 1.6.7.9.3.10 | 1.6.7.9.3.10 |  | 2027-12-07 17:00 | p | 173 |  | 2028-05-29 08:39
376 | 753 | 8158sxzbHZvZEVAAqewP | Normal | 47 | 1.6.7.9.3.10.1 | 1.6.7.9.3.10.1 |  | 2027-12-07 17:00 | p | 173 |  | 2028-05-29 08:39
377 | 754 | hfPeDXfQSV7Nx9zb2rD7 | Normal | 8 | 1.6.7.9.3.10.2 | 1.6.7.9.3.10.2 |  | 2027-09-21 17:00 | p | 175 |  | 2028-03-15 11:19
378 | 755 | DQUdswbbJv1Qpkj0EGFX | Normal | 8 | 1.6.7.9.3.10.3 | 1.6.7.9.3.10.3 |  | 2027-10-01 17:00 | p | 177 |  | 2028-03-27 09:44
379 | 756 | ae3T3d3nFoXZXK7gqkAr | Normal | 20 | 1.6.7.9.3.10.4 | 1.6.7.9.3.10.4 |  | 2027-10-29 17:00 | p | 177 |  | 2028-04-24 10:59
380 | 757 | wbc1AZ0GUhXzQk6SoWIe | Normal | 6 | 1.6.7.9.3.10.6 | 1.6.7.9.3.10.6 |  | 2027-11-08 17:00 | p | 175 |  | 2028-05-02 15:00
381 | 758 | FbN1rrQYTlsz1haWZnFy | Normal | 6 | 1.6.7.9.3.10.8 | 1.6.7.9.3.10.8 |  | 2027-11-16 17:00 | p | 175 |  | 2028-05-10 13:05
382 | 5780 | XCMvjmTKbAUuCZwuNlSF | Normal | 6 | 1.6.7.9.3.10.5 | 1.6.7.9.3.10.5 |  | 2027-10-29 17:00 | p | 177 |  | 2028-04-24 10:59
383 | 5782 | EYY3j1SjnoLUV06T0QHs | Normal | 5 | 1.6.7.9.3.10.7 | 1.6.7.9.3.10.7 |  | 2027-11-16 17:00 | p | 175 |  | 2028-05-10 13:05
384 | 6326 | F4s3MnfyyA74WCIympSi | Summary | 75 | 1.6.7.9.3.11 | 1.6.7.9.3.11 |  | 2027-11-29 17:00 | p | 171 |  | 2028-05-19 15:58
385 | 760 | 7IpOsslq7gyebnCTulxX | Normal | 66 | 1.6.7.9.3.11.1 | 1.6.7.9.3.11.1 |  | 2027-11-16 17:00 | p | 175 |  | 2028-05-10 13:05
386 | 761 | x6fNhJzs4uMW9trtiNEW | Normal | 1 | 1.6.7.9.3.11.2 | 1.6.7.9.3.11.2 |  | 2027-11-17 17:00 | p | 175 |  | 2028-05-11 13:04
387 | 762 | nRInnITHYgcDsU5KDg6m | Normal | 8 | 1.6.7.9.3.11.3 | 1.6.7.9.3.11.3 |  | 2027-11-29 17:00 | p | 171 |  | 2028-05-19 15:58
388 | 6327 | dOJS0LaWQU970ssSiqsz | Summary | 59 | 1.6.7.9.3.12 | 1.6.7.9.3.12 |  | 2028-02-18 17:00 | p | 181 |  | 2028-08-18 08:35
389 | 763 | hLK2cdXSS7IhOZR53PgI | Normal | 6 | 1.6.7.9.3.12.1 | 1.6.7.9.3.12.1 |  | 2027-12-07 17:00 | p | 173 |  | 2028-05-29 08:39
390 | 764 | wTf98lLeHiXAkWj17mAH | Normal | 53 | 1.6.7.9.3.12.2 | 1.6.7.9.3.12.2 |  | 2028-02-18 17:00 | p | 181 |  | 2028-08-18 08:35
391 | 770 | cHAOkWrFbu094CNd9eCk | Summary | 91 | 1.6.7.8 | 1.6.7.8 |  | 2027-12-07 17:00 | p | 173 |  | 2028-05-29 08:39
392 | 786 | 5RJIBxVgSA4dodMzOCsx | Normal | 1 | 1.6.7.8.5 | 1.6.7.8.5 |  | 2027-12-07 17:00 | p | 173 |  | 2028-05-29 08:39
393 | 6434 | cc8WGEqtonq4zOxPHtWc | Normal | 65 | 1.6.7.8.4 | 1.6.7.8.4 |  | 2027-12-06 17:00 | p | 170 |  | 2028-05-25 16:10
394 | 5785 | xIbBdattr1YLWDiqGWPC | Summary | 126 | 1.6.7.11 | 1.6.7.11 |  | 2028-09-21 17:00 | p | 203 |  | 2029-04-13 11:38
395 | 5774 | Dvlkt7hdSzdJ7ChIr4xD | Normal | 2 | 1.6.7.11.1 | 1.6.7.11.1 |  | 2028-03-31 17:00 | p | 188 |  | 2028-10-06 15:49
396 | 5775 | D3NIdGcGrWNhiaQ0dYbY | Normal | 2 | 1.6.7.11.3 | 1.6.7.11.3 |  | 2028-09-21 17:00 | p | 203 |  | 2029-04-13 11:38
397 | 6435 | Ql00ScpYzqtI9PQP57zu | Normal | 122 | 1.6.7.11.2 | 1.6.7.11.2 |  | 2028-09-19 17:00 | p | 203 |  | 2029-04-11 11:27
398 | 6284 | T6s1mlIi1Lu4cscBpq9h | Summary | 273 | 1.6.6 | 1.6.6 |  | 2028-05-17 17:00 | p | 208 |  | 2028-12-12 13:43
399 | 1519 | Ig6aeqJATmPNbReGQrzj | Summary | 273 | 1.6.6.1 | 1.6.6.1 |  | 2028-05-17 17:00 | p | 208 |  | 2028-12-12 13:43
400 | 1463 | IQX94tuow2VKmVJTuhEN | Normal | 1 | 1.6.6.1.3 | 1.6.6.1.3 |  | 2025-08-08 15:00 | q | -175 |  | 2025-02-13 17:00
401 | 1464 | VN7GLU7alOC9oD3kkW9q | Normal | 30 | 1.6.6.1.4 | 1.6.6.1.4 |  | 2025-09-22 15:00 | q | -33 |  | 2025-08-20 10:49
402 | 1465 | i7zbkIpCuBMJlMsq6ma0 | Normal | 1 | 1.6.6.1.5 | 1.6.6.1.5 |  | 2025-09-23 15:00 | q | -33 |  | 2025-08-21 10:47
403 | 1475 | suCYO4gIoCSrnZchT6aQ | Normal | 3 | 1.6.6.1.6 | 1.6.6.1.6 |  | 2027-07-02 17:00 | p | 167 |  | 2027-12-17 15:46
404 | 1476 | gbuDNYIgLq2nB3WERl4p | Normal | 30 | 1.6.6.1.7 | 1.6.6.1.7 |  | 2027-08-13 17:00 | p | 178 |  | 2028-02-08 14:47
405 | 1477 | BC1NYB3fqAlfckX7ECXI | Normal | 1 | 1.6.6.1.8 | 1.6.6.1.8 |  | 2027-08-16 17:00 | p | 176 |  | 2028-02-09 11:19
406 | 1478 | UR7xa7LgN3sMlpzxRjvW | Normal | 3 | 1.6.6.1.9 | 1.6.6.1.9 |  | 2028-05-17 17:00 | p | 208 |  | 2028-12-12 13:43
407 | 6293 | WhUcOZjaj9TDZe74ojmh | Summary | 172 | 1.6.4 | 1.6.4 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
408 | 3929 | GkmiaraCbWdBUaRv136y | Summary | 19 | 1.6.4.15 | 1.6.4.15 |  | 2027-09-27 12:00 | p | 198 |  | 2028-04-12 13:04
409 | 3932 | RKLg9Drqo40Q82TFH1VL | Normal | 1 | 1.6.4.15.2 | 1.6.4.15.2 |  | 2027-03-18 17:00 | p | 179 |  | 2027-09-14 15:26
410 | 3934 | 10Oh1H5M5HjeoWxU1u0w | Normal | 1 | 1.6.4.15.4 | 1.6.4.15.4 |  | 2027-09-27 12:00 | p | 198 |  | 2028-04-12 13:04
411 | 3936 | hwXDQy0MWIQ4jzjNT4oM | Normal | 1 | 1.6.4.15.3 | 1.6.4.15.3 |  | 2027-09-27 12:00 | p | 198 |  | 2028-04-12 13:04
412 | 3938 | 2iJ091mlhEkJyqoddB4L | Normal | 14 | 1.6.4.15.1 | 1.6.4.15.1 |  | 2027-09-27 12:00 | p | 198 |  | 2028-04-12 13:04
413 | 3940 | 8UqvtHTIMRT16eupajKq | Normal | 1 | 1.6.4.15.5 | 1.6.4.15.5 |  | 2027-09-27 12:00 | p | 198 |  | 2028-04-12 13:04
414 | 3931 | GleHIX38gd9vOXaUQYVA | Normal | 33 | 1.6.4.11 | 1.6.4.11 |  | 2027-03-17 17:00 | p | 179 |  | 2027-09-13 11:28
415 | 3933 | FbGZSJQTtuDZR2p8qmxq | Normal | 33 | 1.6.4.13 | 1.6.4.13 |  | 2027-09-24 12:00 | p | 199 |  | 2028-04-11 11:05
416 | 3935 | IRdaiLeeauelAg4QWklz | Normal | 33 | 1.6.4.12 | 1.6.4.12 |  | 2027-09-24 12:00 | p | 199 |  | 2028-04-11 11:53
417 | 3939 | cuQ4HC0Kn3S6GTvqv7QE | Normal | 33 | 1.6.4.14 | 1.6.4.14 |  | 2027-09-24 12:00 | p | 199 |  | 2028-04-11 11:10
418 | 3971 | mB1p68eekBqQhgV8es2U | Summary | 19 | 1.6.4.7 | 1.6.4.7 |  | 2027-11-08 17:00 | p | 175 |  | 2028-05-02 15:00
419 | 3974 | xzlIrgrrtbLscLWLbbQq | Normal | 1 | 1.6.4.7.1 | 1.6.4.7.1 |  | 2027-07-14 17:00 | p | 180 |  | 2028-01-11 08:01
420 | 3981 | YTm9sByrDxPUc7AlWXh1 | Normal | 15 | 1.6.4.7.2 | 1.6.4.7.2 |  | 2027-11-08 17:00 | p | 175 |  | 2028-05-02 15:00
421 | 3973 | 00qHhBlTe8pinGtKpu3n | Normal | 4 | 1.6.4.6 | 1.6.4.6 |  | 2027-07-13 17:00 | q | -880 |  | 2025-02-13 17:00
422 | 3980 | po54OWwjtqomy5uOkFBU | Normal | 40 | 1.6.4.4 | 1.6.4.4 |  | 2027-11-08 17:00 | p | 175 |  | 2028-05-02 15:00
423 | 3993 | LBRozXrRhpq69SKlxnDb | Normal | 10 | 1.6.4.17.4.1 | 1.6.4.17.4.1 |  | 2026-08-11 17:00 | q | 0 |  | 2026-08-11 11:06
424 | 3994 | DvOjAQ6C9aXKnpaAVD1H | Normal | 5 | 1.6.4.17.4.2 | 1.6.4.17.4.2 |  | 2026-08-18 17:00 | p | 0 |  | 2026-08-19 08:58
425 | 3995 | AUkl27NW1i9i5huez8Rg | Normal | 5 | 1.6.4.17.4.3 | 1.6.4.17.4.3 |  | 2026-08-25 17:00 | p | 0 |  | 2026-08-26 08:29
426 | 3997 | KJPP8ivswwWTIeIfPXEM | Summary | 25 | 1.6.4.17.3 | 1.6.4.17.3 |  | 2026-07-28 17:00 | q | -5 |  | 2026-07-23 14:34
427 | 3998 | 5UhDwyM7phAycUkk1Nye | Normal | 10 | 1.6.4.17.3.1 | 1.6.4.17.3.1 |  | 2026-07-07 17:00 | q | -5 |  | 2026-07-02 08:30
428 | 3999 | v6kjlf8aEDhSJHzOK2Uo | Normal | 5 | 1.6.4.17.3.2 | 1.6.4.17.3.2 |  | 2026-07-14 17:00 | q | -4 |  | 2026-07-10 08:55
429 | 4000 | Y3aJp60cYMHromf8xgAE | Normal | 5 | 1.6.4.17.3.3 | 1.6.4.17.3.3 |  | 2026-07-21 17:00 | q | -5 |  | 2026-07-16 11:37
430 | 4001 | Cjtbc2cmKWchyZlcOxo3 | Normal | 5 | 1.6.4.17.3.4 | 1.6.4.17.3.4 |  | 2026-07-28 17:00 | q | -5 |  | 2026-07-23 14:34
431 | 4002 | nJzh0eFJGsqvOmQRJzHn | Summary | 27 | 1.6.4.17.2 | 1.6.4.17.2 |  | 2026-06-22 17:00 | q | -6 |  | 2026-06-16 11:23
432 | 4003 | gjf3v6NdOQannovTvAoE | Normal | 19 | 1.6.4.17.2.1 | 1.6.4.17.2.1 |  | 2026-06-09 17:00 | q | -7 |  | 2026-06-02 11:22
433 | 4004 | fF1Y54WMybWnXZsBJgYM | Normal | 1 | 1.6.4.17.2.2 | 1.6.4.17.2.2 |  | 2026-06-10 17:00 | q | -7 |  | 2026-06-03 13:37
434 | 4005 | NxZ8rMz5ZnJaz6z1SXKM | Normal | 3 | 1.6.4.17.2.3 | 1.6.4.17.2.3 |  | 2026-06-15 17:00 | q | -6 |  | 2026-06-09 10:38
435 | 4006 | fOTuJvqH3OcilXcZuEM5 | Normal | 4 | 1.6.4.17.2.4 | 1.6.4.17.2.4 |  | 2026-06-22 17:00 | q | -6 |  | 2026-06-16 11:23
436 | 6169 | gdW3U4pURjb9iKkAVexH | Summary | 60 | 1.6.4.19.3.1 | 1.6.4.19.3.1 |  | 2026-05-04 17:00 | q | 0 |  | 2026-05-04 09:44
437 | 6170 | AwYLgXY6Mo1DqCbUEhPQ | Summary | 30 | 1.6.4.19.3.1.1 | 1.6.4.19.3.1.1 |  | 2026-03-23 17:00 | q | -4 |  | 2026-03-19 09:55
438 | 6171 | ZR4zae2ZYhCMcZhj7T05 | Normal | 15 | 1.6.4.19.3.1.1.1 | 1.6.4.19.3.1.1.1 |  | 2026-03-02 17:00 | q | -7 |  | 2026-02-23 15:37
439 | 6172 | QgFskomqU31VYtYzB2O0 | Normal | 15 | 1.6.4.19.3.1.1.2 | 1.6.4.19.3.1.1.2 |  | 2026-03-23 17:00 | q | -4 |  | 2026-03-19 09:55
440 | 6173 | nRc7GqDGMG4VP1O5IlEd | Normal | 15 | 1.6.4.19.3.1.2 | 1.6.4.19.3.1.2 |  | 2026-04-13 17:00 | q | -4 |  | 2026-04-09 10:42
441 | 6174 | dvLkHNDhuFTU7AO5XWky | Normal | 15 | 1.6.4.19.3.1.3 | 1.6.4.19.3.1.3 |  | 2026-05-04 17:00 | q | 0 |  | 2026-05-04 09:44
442 | 6175 | IEttja5qNJ6P760Cd9De | Summary | 40 | 1.6.4.19.3.2 | 1.6.4.19.3.2 |  | 2026-07-01 17:00 | p | 4 |  | 2026-07-06 10:12
443 | 6176 | B6x3R7fnpOwupecmo90D | Normal | 10 | 1.6.4.19.3.2.1 | 1.6.4.19.3.2.1 |  | 2026-05-18 17:00 | p | 0 |  | 2026-05-19 10:38
444 | 6177 | vkZhJMfsZWiMPLTjgcam | Normal | 10 | 1.6.4.19.3.2.2 | 1.6.4.19.3.2.2 |  | 2026-06-02 17:00 | q | 0 |  | 2026-06-02 16:48
445 | 6178 | XEU5rnQh2VnDpMl1eT0o | Normal | 10 | 1.6.4.19.3.2.3 | 1.6.4.19.3.2.3 |  | 2026-06-16 17:00 | p | 0 |  | 2026-06-17 09:00
446 | 6179 | xksMzlhYjvKZ4p1XJwSB | Normal | 10 | 1.6.4.19.3.2.4 | 1.6.4.19.3.2.4 |  | 2026-07-01 17:00 | p | 4 |  | 2026-07-06 10:12
447 | 6180 | oR7r0RquVFe2h8pCK9HY | Normal | 10 | 1.6.4.19.3.3 | 1.6.4.19.3.3 |  | 2026-07-16 17:00 | p | 3 |  | 2026-07-20 11:21
448 | 6181 | UJ3hrxCJ5NslZjdDLEyu | Normal | 20 | 1.6.4.19.3.4 | 1.6.4.19.3.4 |  | 2026-08-13 17:00 | p | 3 |  | 2026-08-17 11:05
449 | 6182 | JQHbjwkPqIslt5thIOgQ | Normal | 5 | 1.6.4.19.3.5 | 1.6.4.19.3.5 |  | 2026-08-20 17:00 | p | 0 |  | 2026-08-21 13:17
450 | 6183 | 5NqxhAyIl3JXTpWWvSnV | Normal | 2 | 1.6.4.19.3.6 | 1.6.4.19.3.6 |  | 2026-08-24 17:00 | p | 0 |  | 2026-08-25 09:12
451 | 6184 | vx8CoW16lw8uEEVKaVp7 | Normal | 5 | 1.6.4.19.3.7 | 1.6.4.19.3.7 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 16:54
452 | 4037 | hMBnPD0NfYpjSqEpRMYY | Summary | 554 | 1.6.4.20 | 1.6.4.20 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
453 | 4038 | VkrURyJwsSkEVRV6WcXe | Summary | 411 | 1.6.4.20.1 | 1.6.4.20.1 |  | 2028-03-17 17:00 | p | 180 |  | 2028-09-14 10:52
454 | 4040 | g5zNgGHP8U11wPTJKhcB | Normal | 20 | 1.6.4.20.1.3 | 1.6.4.20.1.3 |  | 2028-01-21 17:00 | p | 178 |  | 2028-07-18 14:13
455 | 4041 | f0PORH3GhEIXFjYfGbTd | Normal | 97 | 1.6.4.20.1.6 | 1.6.4.20.1.6 |  | 2028-03-17 17:00 | p | 180 |  | 2028-09-14 10:52
456 | 4042 | SyfMayqY4a7i0nZLPz6Y | Normal | 129 | 1.6.4.20.1.7 | 1.6.4.20.1.7 |  | 2028-03-17 17:00 | p | 180 |  | 2028-09-14 10:52
457 | 6621 | pXe0ZxltUhDf1quSL5q2 | Normal | 15 | 1.6.4.20.1.2 | 1.6.4.20.1.2 |  | 2026-03-02 17:00 | q | -7 |  | 2026-02-23 16:56
458 | 6622 | EmEy5gJckBYofEEYNXFv | Normal | 20 | 1.6.4.20.1.4 | 1.6.4.20.1.4 |  | 2028-02-18 17:00 | p | 181 |  | 2028-08-18 08:35
459 | 6623 | BVU87KMg9Rhzc6j5yKVh | Normal | 20 | 1.6.4.20.1.5 | 1.6.4.20.1.5 |  | 2028-03-17 17:00 | p | 180 |  | 2028-09-14 10:52
460 | 4043 | XbXkjxtfHUxhg4CK1elt | Summary | 127 | 1.6.4.20.2 | 1.6.4.20.2 |  | 2028-09-12 17:00 | p | 204 |  | 2029-04-05 08:44
461 | 4045 | mDphgqAAxA2RnvA52x8A | Normal | 20 | 1.6.4.20.2.1 | 1.6.4.20.2.1 |  | 2028-04-14 17:00 | p | 186 |  | 2028-10-18 15:33
462 | 4046 | 5HyQBVwuqRdeW1HhaSOP | Normal | 10 | 1.6.4.20.2.2 | 1.6.4.20.2.2 |  | 2028-04-28 17:00 | p | 188 |  | 2028-11-03 10:09
463 | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Normal | 72 | 1.6.4.20.2.3 | 1.6.4.20.2.3 |  | 2028-08-08 17:00 | p | 198 |  | 2029-02-23 10:06
464 | 4048 | ybbKhm9jdtNbVzABGZ8L | Normal | 20 | 1.6.4.20.2.4 | 1.6.4.20.2.4 |  | 2028-09-05 17:00 | p | 205 |  | 2029-03-30 08:52
465 | 4049 | kP1jeiEwkYg4HRpUjG4p | Normal | 5 | 1.6.4.20.2.5 | 1.6.4.20.2.5 |  | 2028-09-12 17:00 | p | 204 |  | 2029-04-05 08:44
466 | 4050 | jQIHIDf5FTnJxQysEvnn | Summary | 37 | 1.6.4.20.3 | 1.6.4.20.3 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
467 | 4051 | bizigDTezGi1mMHxJ1gi | Summary | 32 | 1.6.4.20.3.1 | 1.6.4.20.3.1 |  | 2028-09-21 17:00 | p | 203 |  | 2029-04-13 11:38
468 | 4052 | JSSXcLTdD9VQNM766DgK | Normal | 20 | 1.6.4.20.3.1.1 | 1.6.4.20.3.1.1 |  | 2028-09-05 17:00 | p | 204 |  | 2029-03-29 10:11
469 | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Normal | 12 | 1.6.4.20.3.1.2 | 1.6.4.20.3.1.2 |  | 2028-09-21 17:00 | p | 203 |  | 2029-04-13 11:38
470 | 4054 | WhXMUGkGRid5sulqMW8S | Summary | 5 | 1.6.4.20.3.2 | 1.6.4.20.3.2 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
471 | 4055 | dWrJCmOwv1i72p29KBXE | Normal | 2 | 1.6.4.20.3.2.1 | 1.6.4.20.3.2.1 |  | 2028-09-25 17:00 | p | 203 |  | 2029-04-17 10:43
472 | 4056 | a1SRK7UWhIIMlkKKriy9 | Normal | 1 | 1.6.4.20.3.2.2 | 1.6.4.20.3.2.2 |  | 2028-09-26 17:00 | p | 203 |  | 2029-04-18 10:45
473 | 4057 | NKnvgqAHKv63TOKudyZQ | Normal | 1 | 1.6.4.20.3.2.3 | 1.6.4.20.3.2.3 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 09:57
474 | 4058 | cbANjhwCBqAluf1RM04K | Normal | 1 | 1.6.4.20.3.2.4 | 1.6.4.20.3.2.4 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
475 | 4059 | sH9kz6O2EFda2hu4x8Kx | Summary | 12 | 1.6.4.20.3.3 | 1.6.4.20.3.3 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
476 | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Normal | 3 | 1.6.4.20.3.3.1 | 1.6.4.20.3.3.1 |  | 2028-09-15 17:00 | p | 205 |  | 2029-04-09 11:49
477 | 4061 | ViM2psfxppAdWr3IoYdq | Normal | 3 | 1.6.4.20.3.3.2 | 1.6.4.20.3.3.2 |  | 2028-09-20 17:00 | p | 203 |  | 2029-04-12 13:34
478 | 4062 | RvsEFsErXikPrAOovPaZ | Normal | 1 | 1.6.4.20.3.3.3 | 1.6.4.20.3.3.3 |  | 2028-09-21 17:00 | p | 203 |  | 2029-04-13 09:31
479 | 4063 | ma6GKJ3GzeKmeF4AshaM | Normal | 4 | 1.6.4.20.3.3.4 | 1.6.4.20.3.3.4 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 09:02
480 | 4064 | OALhjNOvEaqSDAmsS5Il | Normal | 1 | 1.6.4.20.3.3.5 | 1.6.4.20.3.3.5 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
481 | 5748 | cHP8KcDQZp8MvOi5a8Wj | Summary | 64 | 1.6.4.18 | 1.6.4.18 |  | 2027-04-12 17:00 | p | 178 |  | 2027-10-08 16:52
482 | 6701 | vwWJ3SVwW3tYdDDMDgOK | Summary | 60 | 1.6.4.18.3 | 1.6.4.18.3 |  | 2027-04-12 17:00 | p | 178 |  | 2027-10-08 16:52
483 | 6713 | JQXHTZXJblKyiNyxM0eT | Summary | 78 | 1.6.4.18.3.3 | 1.6.4.18.3.3 |  | 2027-04-12 17:00 | p | 178 |  | 2027-10-08 16:52
484 | 6727 | 5BlmDU3ct4fwjT54EODG | Summary | 21 | 1.6.4.18.3.3.2 | 1.6.4.18.3.3.2 |  | 2027-03-29 17:00 | p | 181 |  | 2027-09-27 09:39
485 | 6738 | XB1ZMgqMWvDJpnRGKTB3 | Normal | 3 | 1.6.4.18.3.3.2.10 | 1.6.4.18.3.3.2.10 |  | 2027-03-15 17:00 | q | -760 |  | 2025-02-13 17:00
486 | 7003 | XfnOKCk0EbakXF7t35fN | Normal | 1 | 1.6.4.18.3.3.2.9 | 1.6.4.18.3.3.2.9 |  | 2027-03-10 17:00 | q | -758 |  | 2025-02-10 17:00
487 | 7270 | 3AlavOi01JfJwLM1b81K | Milestone | 0 | 1.6.4.18.3.3.2.6 | 1.6.4.18.3.3.2.6 |  | 2027-03-16 08:00 | q | -760 |  | 2025-02-13 17:00
488 | 7271 | 7ZvC3KC1rMxIYvbhicKJ | Normal | 10 | 1.6.4.18.3.3.2.7 | 1.6.4.18.3.3.2.7 |  | 2027-03-29 17:00 | p | 181 |  | 2027-09-27 09:39
489 | 7007 | 9uputDeZmGdSlUY8oN4J | Summary | 64 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 2027-04-12 17:00 | p | 178 |  | 2027-10-08 16:52
490 | 7010 | l7MAqMN94R7DBQRgok6z | Normal | 5 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 2027-04-12 17:00 | p | 178 |  | 2027-10-08 16:52
491 | 7277 | hIopgQViPH34dy6jPgEs | Normal | 6 | 1.6.4.18.3.3.7.5 | 1.6.4.18.3.3.7.5 |  | 2027-02-24 17:00 | q | -712 |  | 2025-03-14 17:00
492 | 7278 | 4Ma7Z2LiPmWBC9UI6vyb | Normal | 5 | 1.6.4.18.3.3.7.7 | 1.6.4.18.3.3.7.7 |  | 2027-03-29 17:00 | p | 182 |  | 2027-09-28 13:18
493 | 7300 | JMkMoXIhBdn9ICcOd798 | Normal | 5 | 1.6.4.18.3.3.7.4 | 1.6.4.18.3.3.7.4 |  | 2027-04-05 17:00 | p | 181 |  | 2027-10-04 14:12
494 | 7301 | mVBynbXAicTgOFud0Dl3 | Normal | 5 | 1.6.4.18.3.3.7.6 | 1.6.4.18.3.3.7.6 |  | 2027-03-22 17:00 | p | 182 |  | 2027-09-21 14:44
495 | 7302 | 6S1rSJxqNAmNyzjZVL7L | Normal | 5 | 1.6.4.18.3.3.7.8 | 1.6.4.18.3.3.7.8 |  | 2027-04-05 17:00 | p | 181 |  | 2027-10-04 14:12
496 | 7279 | uD2jpviUMAewZ4YhDj8P | Summary | 32 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 2027-03-15 17:00 | p | 182 |  | 2027-09-14 08:52
497 | 7282 | sTVLhyKAe9uIrxTuOSsB | Normal | 2 | 1.6.4.18.3.3.4.3 | 1.6.4.18.3.3.4.3 |  | 2027-02-24 17:00 | p | 182 |  | 2027-08-26 11:05
498 | 7283 | GyFcZSlU29ifaVubQEBd | Normal | 2 | 1.6.4.18.3.3.4.4 | 1.6.4.18.3.3.4.4 |  | 2027-02-26 17:00 | p | 184 |  | 2027-08-30 10:05
499 | 7284 | AoDPK2hmzwZjnwdc6ENo | Normal | 1 | 1.6.4.18.3.3.4.5 | 1.6.4.18.3.3.4.5 |  | 2027-03-01 17:00 | p | 182 |  | 2027-08-31 08:59
500 | 7285 | UP4KQN3vFTNJJtYiVHhd | Normal | 10 | 1.6.4.18.3.3.4.6 | 1.6.4.18.3.3.4.6 |  | 2027-03-15 17:00 | p | 182 |  | 2027-09-14 08:52
501 | 7286 | weppsWRcwILLbxkFpraK | Summary | 39 | 1.6.4.18.3.3.5 | 1.6.4.18.3.3.5 |  | 2027-03-22 17:00 | p | 182 |  | 2027-09-21 14:44
502 | 7289 | YNbMTserJcwdDTx8O6lt | Normal | 5 | 1.6.4.18.3.3.5.3 | 1.6.4.18.3.3.5.3 |  | 2027-03-03 17:00 | p | 183 |  | 2027-09-03 15:12
503 | 7290 | rpRUKocvSOF2GnoJsxWr | Normal | 2 | 1.6.4.18.3.3.5.4 | 1.6.4.18.3.3.5.4 |  | 2027-03-05 17:00 | p | 185 |  | 2027-09-07 15:12
504 | 7291 | ThxkR8uStFOgKr5Kajlm | Normal | 1 | 1.6.4.18.3.3.5.5 | 1.6.4.18.3.3.5.5 |  | 2027-03-08 17:00 | p | 183 |  | 2027-09-08 14:16
505 | 7292 | 6vEOHVPLFOaXnW1xcDp6 | Normal | 10 | 1.6.4.18.3.3.5.6 | 1.6.4.18.3.3.5.6 |  | 2027-03-22 17:00 | p | 182 |  | 2027-09-21 14:44
506 | 7293 | ep0qwejNT11UOlW5WmY0 | Summary | 28 | 1.6.4.18.3.3.6 | 1.6.4.18.3.3.6 |  | 2027-03-29 17:00 | p | 182 |  | 2027-09-28 13:18
507 | 7295 | tyaakhlAtuOpVSt7bVvo | Normal | 1 | 1.6.4.18.3.3.6.2 | 1.6.4.18.3.3.6.2 |  | 2027-02-18 17:00 | q | -738 |  | 2025-02-10 17:00
508 | 7296 | PnFVdPiNKahDkradYWdd | Normal | 5 | 1.6.4.18.3.3.6.3 | 1.6.4.18.3.3.6.3 |  | 2027-03-10 17:00 | p | 181 |  | 2027-09-08 10:25
509 | 7297 | JA5LCeR4tD4Vqq2Jfy9o | Normal | 2 | 1.6.4.18.3.3.6.4 | 1.6.4.18.3.3.6.4 |  | 2027-03-12 17:00 | p | 181 |  | 2027-09-10 08:06
510 | 7298 | uHK4wyA8DzlXgqm5UKoq | Normal | 1 | 1.6.4.18.3.3.6.5 | 1.6.4.18.3.3.6.5 |  | 2027-03-15 17:00 | p | 178 |  | 2027-09-10 15:53
511 | 7299 | ymtRqRQZa4AjGraGOZVd | Normal | 10 | 1.6.4.18.3.3.6.6 | 1.6.4.18.3.3.6.6 |  | 2027-03-29 17:00 | p | 182 |  | 2027-09-28 13:18
512 | 6297 | AqdIsKbIPOfZJkjKYjnG | Summary | 118 | 1.6.1 | 1.6.1 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:06
513 | 4200 | YSdvLAa6ztbhOKei71CV | Summary | 108 | 1.6.1.1 | 1.6.1.1 |  | 2027-08-24 12:00 | p | 245 |  | 2028-04-25 14:35
514 | 4202 | N5DTU5adYVhKR5So2Uvc | Normal | 88 | 1.6.1.1.3 | 1.6.1.1.3 |  | 2026-08-28 17:00 | p | 2 |  | 2026-08-31 08:05
515 | 4204 | CRzwy8942pbCOpcOMW2v | Normal | 20 | 1.6.1.1.4 | 1.6.1.1.4 |  | 2027-08-24 12:00 | p | 245 |  | 2028-04-25 14:35
516 | 4209 | 0Ck6gz1ZilLs9fM0b7nU | Summary | 46 | 1.6.1.3 | 1.6.1.3 |  | 2027-07-14 17:00 | p | 180 |  | 2028-01-11 08:01
517 | 4212 | yktUOUuzQyzOVBFBfL42 | Normal | 46 | 1.6.1.3.1 | 1.6.1.3.1 |  | 2027-07-14 17:00 | p | 180 |  | 2028-01-11 08:01
518 | 4218 | T5g2El1CSAmFZNlboxQh | Normal | 1 | 1.6.1.4 | 1.6.1.4 |  | 2027-08-25 12:00 | p | 245 |  | 2028-04-26 15:31
519 | 6080 | jFrzSNmYyPDtKSvRlBw2 | Normal | 1 | 1.6.1.6 | 1.6.1.6 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:06
520 | 6311 | tQdu1pFxVkY2bj5IQjxI | Summary | 77 | 1.6.3 | 1.6.3 |  | 2027-09-09 17:00 | p | 178 |  | 2028-03-06 16:38
521 | 5452 | u9nFTwEoKsBrgeg8njOT | Normal | 5 | 1.6.3.1 | 1.6.3.1 |  | 2027-09-02 17:00 | p | 178 |  | 2028-02-28 16:23
522 | 5457 | kGunJCROCjWQWqBfRKBZ | Summary | 1 | 1.6.3.2 | 1.6.3.2 |  | 2027-09-02 17:00 | p | 178 |  | 2028-02-28 16:23
523 | 5458 | DngVHB2HpHpsOjFWu5hu | Summary | 1 | 1.6.3.2.1 | 1.6.3.2.1 |  | 2027-09-02 17:00 | p | 178 |  | 2028-02-28 16:23
524 | 5505 | nVzBMSNTKKq9KPWblsw1 | Normal | 1 | 1.6.3.2.1.9 | 1.6.3.2.1.9 |  | 2027-09-02 17:00 | p | 178 |  | 2028-02-28 16:23
525 | 5506 | wLM81Xdu8B5geOMMQz6m | Summary | 119 | 1.6.3.3 | 1.6.3.3 |  | 2027-09-09 17:00 | p | 178 |  | 2028-03-06 16:38
526 | 5507 | 1r4d5DbY2YIgMhg8HKuO | Normal | 3 | 1.6.3.3.2 | 1.6.3.3.2 |  | 2027-03-23 17:00 | p | 180 |  | 2027-09-20 09:52
527 | 5508 | wHSntGHJkj4aA0wA3fA2 | Normal | 14 | 1.6.3.3.3 | 1.6.3.3.3 |  | 2027-04-12 17:00 | p | 178 |  | 2027-10-08 16:52
528 | 5509 | 1FHP32ReWIveKb3JOWEG | Summary | 44 | 1.6.3.3.4 | 1.6.3.3.4 |  | 2027-07-14 17:00 | p | 168 |  | 2027-12-30 14:24
529 | 5510 | LTFwTsrnxYhrGNFUv7CM | Normal | 12 | 1.6.3.3.4.1 | 1.6.3.3.4.1 |  | 2027-05-31 17:00 | p | 167 |  | 2027-11-15 08:22
530 | 5511 | Od3mMFxB7LjrJLF1slz4 | Normal | 11 | 1.6.3.3.4.2 | 1.6.3.3.4.2 |  | 2027-06-15 17:00 | p | 168 |  | 2027-12-01 10:27
531 | 5512 | Des2hDKSMjcJndTJRzoQ | Normal | 11 | 1.6.3.3.4.3 | 1.6.3.3.4.3 |  | 2027-06-30 17:00 | p | 168 |  | 2027-12-16 16:00
532 | 5513 | z1vb48lrGwUUDjKbD3gr | Normal | 10 | 1.6.3.3.4.4 | 1.6.3.3.4.4 |  | 2027-07-14 17:00 | p | 168 |  | 2027-12-30 14:24
533 | 5514 | leNXdZKmybH4tpy20cQU | Normal | 5 | 1.6.3.3.5 | 1.6.3.3.5 |  | 2027-09-09 17:00 | p | 178 |  | 2028-03-06 16:38
534 | 6890 | QKIolSsTnUWZiIhR6M5v | Normal | 40 | 1.6.3.3.1 | 1.6.3.3.1 |  | 2027-03-18 17:00 | p | 179 |  | 2027-09-14 15:26
535 | 6359 | hvfa0617w1FgmEnjjKwJ | Summary | 26 | 1.7.2.16 | 1.7.2.16 |  | 2027-03-03 17:00 | p | 179 |  | 2027-08-30 13:07
536 | 6360 | DMXbIVCeMtVR5pi4d5UN | Summary | 26 | 1.7.2.16.1 | 1.7.2.16.1 |  | 2027-03-03 17:00 | p | 179 |  | 2027-08-30 13:07
537 | 6361 | VEKeY9azNIVSZDSjYyKy | Summary | 33 | 1.7.2.16.1.3 | 1.7.2.16.1.3 |  | 2027-03-03 17:00 | p | 179 |  | 2027-08-30 13:07
538 | 7303 | fpLHmKjlfpy4s4tap5Xw | Summary | 39 | 1.6.3.11.1.3.4 | 1.6.3.11.1.3.4 |  | 2027-02-22 17:00 | p | 182 |  | 2027-08-24 10:39
539 | 7307 | eye8r8DevGvPITcdrMUe | Normal | 6 | 1.6.3.11.1.3.4.4 | 1.6.3.11.1.3.4.4 |  | 2027-02-19 17:00 | p | 184 |  | 2027-08-23 11:44
540 | 7308 | BXoPyB4GmzJwvFdrkJ7b | Normal | 1 | 1.6.3.11.1.3.4.5 | 1.6.3.11.1.3.4.5 |  | 2027-02-22 17:00 | p | 182 |  | 2027-08-24 10:39
541 | 7309 | 19skeJKmh3pRSfTF3DDB | Summary | 30 | 1.6.3.11.1.3.5 | 1.6.3.11.1.3.5 |  | 2027-02-24 17:00 | p | 182 |  | 2027-08-26 13:11
542 | 7312 | ZHpaj2955bjmxPKFBEf2 | Normal | 2 | 1.6.3.11.1.3.5.3 | 1.6.3.11.1.3.5.3 |  | 2027-02-11 17:00 | q | -730 |  | 2025-02-11 17:00
543 | 7313 | boaUnlKi0h6sKdwgAbmA | Normal | 5 | 1.6.3.11.1.3.5.4 | 1.6.3.11.1.3.5.4 |  | 2027-02-18 17:00 | p | 178 |  | 2027-08-16 16:13
544 | 7314 | zaliCdoIQDW2tx8wBQyt | Normal | 1 | 1.6.3.11.1.3.5.5 | 1.6.3.11.1.3.5.5 |  | 2027-02-24 17:00 | p | 182 |  | 2027-08-26 13:11
545 | 7315 | 9LywAxRsXdHsCrCcjGKV | Summary | 27 | 1.6.3.11.1.3.6 | 1.6.3.11.1.3.6 |  | 2027-03-03 17:00 | p | 179 |  | 2027-08-30 13:07
546 | 7318 | vWglY3BMmZCigDWMEMyY | Normal | 3 | 1.6.3.11.1.3.6.3 | 1.6.3.11.1.3.6.3 |  | 2027-02-23 17:00 | p | 177 |  | 2027-08-20 16:35
547 | 7319 | Fr6VbOwwg75s6X3Xcfql | Normal | 5 | 1.6.3.11.1.3.6.4 | 1.6.3.11.1.3.6.4 |  | 2027-03-02 17:00 | p | 177 |  | 2027-08-27 14:54
548 | 7320 | MRmQHJYBr9cc2OfLUSYd | Normal | 1 | 1.6.3.11.1.3.6.5 | 1.6.3.11.1.3.6.5 |  | 2027-03-03 17:00 | p | 179 |  | 2027-08-30 13:07
549 | 6273 | ljz6i2ltFwqcRU3btDx0 | Summary | 552 | 1.8 | 1.8 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
550 | 3681 | wdhUrQuIMTMPn1LoqO1m | Normal | 24 | 1.8.5.1.1.1 | 1.8.5.1.1.1 |  | 2025-09-23 17:00 | q | 0 |  | 2025-09-23 14:35
551 | 3682 | 38PSIqFGHzjKldiudT82 | Summary | 25 | 1.8.5.1.1.4 | 1.8.5.1.1.4 |  | 2025-10-29 17:00 | p | 5 |  | 2025-11-04 08:04
552 | 3683 | JW3LUw009FZ7ddD6CdLX | Normal | 20 | 1.8.5.1.1.4.1 | 1.8.5.1.1.4.1 |  | 2025-10-22 17:00 | p | 1 |  | 2025-10-24 11:37
553 | 3684 | g3f8U3i4iakOhylueut6 | Normal | 5 | 1.8.5.1.1.4.2 | 1.8.5.1.1.4.2 |  | 2025-10-29 17:00 | p | 5 |  | 2025-11-04 08:04
554 | 3685 | eStRoX3vnaDmRLAWk58C | Summary | 40 | 1.8.5.1.1.5 | 1.8.5.1.1.5 |  | 2026-05-21 17:00 | p | 19 |  | 2026-06-10 13:05
555 | 3686 | 7zhxjkpiLTAH9tiW1eYy | Normal | 20 | 1.8.5.1.1.5.1 | 1.8.5.1.1.5.1 |  | 2025-11-28 17:00 | p | 11 |  | 2025-12-10 10:13
556 | 3687 | 0zzWvesUS18qEUfjK5NH | Normal | 5 | 1.8.5.1.1.5.2 | 1.8.5.1.1.5.2 |  | 2026-04-30 17:00 | p | 17 |  | 2026-05-18 11:16
557 | 3688 | zSUYYsBrfiOGi6qJakS6 | Normal | 5 | 1.8.5.1.1.5.3 | 1.8.5.1.1.5.3 |  | 2026-05-07 17:00 | p | 18 |  | 2026-05-26 14:35
558 | 3689 | X7sWUqInOJZ9zcVzmfT1 | Normal | 5 | 1.8.5.1.1.5.4 | 1.8.5.1.1.5.4 |  | 2026-05-14 17:00 | p | 18 |  | 2026-06-02 15:34
559 | 3690 | 8YDpqEvemQaMsfVmGpF8 | Normal | 5 | 1.8.5.1.1.5.5 | 1.8.5.1.1.5.5 |  | 2026-05-21 17:00 | p | 19 |  | 2026-06-10 13:05
560 | 3691 | ofZrlktbiXkVpuhhIeO5 | Summary | 25 | 1.8.5.1.1.6 | 1.8.5.1.1.6 |  | 2026-05-21 17:00 | p | 19 |  | 2026-06-10 13:05
561 | 3692 | xRsKOxB8zGAnVTXugcHQ | Normal | 20 | 1.8.5.1.1.6.1 | 1.8.5.1.1.6.1 |  | 2025-12-29 17:00 | p | 13 |  | 2026-01-12 11:41
562 | 3693 | Hn8rBaTvxeP9Vb10zF48 | Normal | 5 | 1.8.5.1.1.6.2 | 1.8.5.1.1.6.2 |  | 2026-05-21 17:00 | p | 19 |  | 2026-06-10 13:05
563 | 3694 | 4tipOydrC0LTNincaMDW | Summary | 35 | 1.8.5.1.1.7 | 1.8.5.1.1.7 |  | 2026-05-21 17:00 | p | 19 |  | 2026-06-10 13:05
564 | 3695 | lT6NpgfSYqKHtVYFLSzF | Normal | 20 | 1.8.5.1.1.7.1 | 1.8.5.1.1.7.1 |  | 2026-01-28 17:00 | p | 25 |  | 2026-02-23 15:07
565 | 3696 | gijouZuJR1ZVcSfHKSTf | Normal | 5 | 1.8.5.1.1.7.2 | 1.8.5.1.1.7.2 |  | 2026-05-07 17:00 | p | 14 |  | 2026-05-22 09:19
566 | 3697 | 1158ttL4JEmZYV6RmdcS | Normal | 5 | 1.8.5.1.1.7.3 | 1.8.5.1.1.7.3 |  | 2026-05-14 17:00 | p | 18 |  | 2026-06-02 08:13
567 | 3698 | AKCwPpEPQi4iH3XDRpiM | Normal | 5 | 1.8.5.1.1.7.4 | 1.8.5.1.1.7.4 |  | 2026-05-21 17:00 | p | 19 |  | 2026-06-10 13:05
568 | 3699 | AYANEA6OuC5b95kp3uyI | Summary | 30 | 1.8.5.1.1.8 | 1.8.5.1.1.8 |  | 2026-07-07 17:00 | p | 0 |  | 2026-07-08 10:02
569 | 3700 | WE9bFDn3y5M7oiID5UPj | Normal | 20 | 1.8.5.1.1.8.1 | 1.8.5.1.1.8.1 |  | 2026-02-26 17:00 | p | 21 |  | 2026-03-20 09:09
570 | 3701 | CXSHp4tESy2S0nMNpo3C | Normal | 5 | 1.8.5.1.1.8.2 | 1.8.5.1.1.8.2 |  | 2026-06-29 17:00 | q | -3 |  | 2026-06-26 16:22
571 | 3702 | sTuPByKbZEfSXxt0Z2G9 | Normal | 5 | 1.8.5.1.1.8.3 | 1.8.5.1.1.8.3 |  | 2026-07-07 17:00 | p | 0 |  | 2026-07-08 10:02
572 | 3703 | WHZRJAK4v6S9Zk2EBeP3 | Summary | 40 | 1.8.5.1.1.9 | 1.8.5.1.1.9 |  | 2026-05-21 17:00 | p | 19 |  | 2026-06-10 13:05
573 | 3704 | 3CXbrhXJooXd98jlpAkg | Normal | 20 | 1.8.5.1.1.9.1 | 1.8.5.1.1.9.1 |  | 2026-03-26 17:00 | p | 12 |  | 2026-04-08 15:32
574 | 3705 | RO9RShNcg0h7x9fD24Zk | Normal | 5 | 1.8.5.1.1.9.2 | 1.8.5.1.1.9.2 |  | 2026-04-30 17:00 | p | 17 |  | 2026-05-18 08:05
575 | 3706 | w8MhGnhxyXFIHvJdw6bc | Normal | 5 | 1.8.5.1.1.9.3 | 1.8.5.1.1.9.3 |  | 2026-05-07 17:00 | p | 18 |  | 2026-05-26 15:43
576 | 3707 | dJNKgtiJ1M8pNoPOlZcZ | Normal | 5 | 1.8.5.1.1.9.4 | 1.8.5.1.1.9.4 |  | 2026-05-14 17:00 | p | 19 |  | 2026-06-03 13:17
577 | 3708 | 84VtM14FQkMGurZDdBLv | Normal | 5 | 1.8.5.1.1.9.5 | 1.8.5.1.1.9.5 |  | 2026-05-21 17:00 | p | 19 |  | 2026-06-10 13:05
578 | 3709 | gpO5WcJkYid7jZAXZwbn | Summary | 40 | 1.8.5.1.1.10 | 1.8.5.1.1.10 |  | 2026-05-21 17:00 | p | 19 |  | 2026-06-10 13:05
579 | 3710 | KOKaQwRJEoC6vlU3mKjm | Normal | 20 | 1.8.5.1.1.10.1 | 1.8.5.1.1.10.1 |  | 2026-04-23 17:00 | p | 14 |  | 2026-05-08 08:52
580 | 3711 | XXu8BmtFqx4o2r8a6o98 | Normal | 5 | 1.8.5.1.1.10.2 | 1.8.5.1.1.10.2 |  | 2026-04-30 17:00 | p | 14 |  | 2026-05-15 13:48
581 | 3712 | sZwrgRbHYjKWcIa9rVK3 | Normal | 5 | 1.8.5.1.1.10.3 | 1.8.5.1.1.10.3 |  | 2026-05-07 17:00 | p | 18 |  | 2026-05-26 10:36
582 | 3713 | 4NbryuRKpmrExDEDqArG | Normal | 5 | 1.8.5.1.1.10.4 | 1.8.5.1.1.10.4 |  | 2026-05-14 17:00 | p | 17 |  | 2026-06-01 15:04
583 | 3714 | Fbm1iHrhCX8z8SNRXJuq | Normal | 5 | 1.8.5.1.1.10.5 | 1.8.5.1.1.10.5 |  | 2026-05-21 17:00 | p | 19 |  | 2026-06-10 13:05
584 | 6646 | CmmxWTpZgFyyAwkQnNh3 | Normal | 10 | 1.8.5.1.1.2 | 1.8.5.1.1.2 |  | 2026-08-25 17:00 | q | 0 |  | 2026-08-25 08:19
585 | 3715 | V6i7uYjEJBRYHjhIimqJ | Summary | 50 | 1.8.5.1.2 | 1.8.5.1.2 |  | 2026-08-04 17:00 | p | 13 |  | 2026-08-18 08:04
586 | 3716 | bdy5zVX59rD935sK6M5v | Normal | 20 | 1.8.5.1.2.1 | 1.8.5.1.2.1 |  | 2026-06-22 17:00 | p | 16 |  | 2026-07-09 14:22
587 | 3717 | 5PdqCAMtbYgi5VsFO6ls | Normal | 20 | 1.8.5.1.2.4 | 1.8.5.1.2.4 |  | 2026-08-04 17:00 | p | 13 |  | 2026-08-18 08:04
588 | 6671 | 0oTh3tmNX3iVSaVNVmGK | Normal | 5 | 1.8.5.1.2.2 | 1.8.5.1.2.2 |  | 2026-06-29 17:00 | p | 17 |  | 2026-07-17 14:49
589 | 6672 | BKyGOzVPyPwKpI9CyseJ | Normal | 5 | 1.8.5.1.2.3 | 1.8.5.1.2.3 |  | 2026-07-07 17:00 | p | 14 |  | 2026-07-22 15:59
590 | 3721 | 45j7fpB55qVEeWfRBgCv | Normal | 1 | 1.8.5.1.4.1 | 1.8.5.1.4.1 |  | 2025-08-20 17:00 | p | 8 |  | 2025-08-29 15:07
591 | 3722 | hYa6Ppkzu6veYWmxHffd | Normal | 27 | 1.8.5.1.4.2 | 1.8.5.1.4.2 |  | 2026-05-06 17:00 | p | 12 |  | 2026-05-19 16:57
592 | 6649 | TeFWDZJ3h8q4yVNptUYE | Normal | 28 | 1.8.5.1.4.3 | 1.8.5.1.4.3 |  | 2026-06-16 17:00 | p | 14 |  | 2026-07-01 08:32
593 | 6650 | FvuNLI4Jaew3VjPpwL3e | Normal | 28 | 1.8.5.1.4.4 | 1.8.5.1.4.4 |  | 2026-07-28 17:00 | p | 2 |  | 2026-07-31 09:06
594 | 6651 | T3J0AzovT4qFTLJ7Lgki | Normal | 15 | 1.8.5.1.4.5 | 1.8.5.1.4.5 |  | 2026-08-18 17:00 | p | 1 |  | 2026-08-20 14:22
595 | 3724 | ZCOxRRLLrh9Pa7VnBAyk | Normal | 27 | 1.8.5.1.5.1 | 1.8.5.1.5.1 |  | 2025-09-26 17:00 | p | 5 |  | 2025-10-02 11:12
596 | 3725 | 8cgOIQk4rBKvjXdBm8mF | Normal | 91 | 1.8.5.1.5.9 | 1.8.5.1.5.9 |  | 2026-08-27 17:00 | q | 0 |  | 2026-08-27 11:29
597 | 6661 | bQxmmL7mcUsEGpKkQTDo | Normal | 28 | 1.8.5.1.5.2 | 1.8.5.1.5.2 |  | 2026-02-17 17:00 | q | -4 |  | 2026-02-13 09:19
598 | 6662 | CVNpv9CNU8XhfLmVwl8x | Normal | 28 | 1.8.5.1.5.3 | 1.8.5.1.5.3 |  | 2026-03-27 17:00 | q | -1 |  | 2026-03-26 09:29
599 | 6663 | LVExlIxeJ6XB3yqm0Dzs | Normal | 28 | 1.8.5.1.5.4 | 1.8.5.1.5.4 |  | 2026-05-06 17:00 | q | -2 |  | 2026-05-04 10:12
600 | 6664 | Io9oZ1dPqEE9GDlMTPxh | Normal | 28 | 1.8.5.1.5.5 | 1.8.5.1.5.5 |  | 2026-06-16 17:00 | q | -4 |  | 2026-06-12 15:49
601 | 6665 | ycT0qtEFjd4p02S4Ehf1 | Normal | 28 | 1.8.5.1.5.6 | 1.8.5.1.5.6 |  | 2026-07-28 17:00 | q | -6 |  | 2026-07-22 11:59
602 | 6666 | sX3PHseynvzwKI9my2AH | Normal | 15 | 1.8.5.1.5.7 | 1.8.5.1.5.7 |  | 2026-08-18 17:00 | p | 2 |  | 2026-08-21 13:12
603 | 6668 | NGuTznXCCG5yuIi6lGQO | Normal | 1 | 1.8.5.1.5.10 | 1.8.5.1.5.10 |  | 2026-08-28 17:00 | q | 0 |  | 2026-08-28 14:17
604 | 6669 | t8MCocRefa6DhiQNsJVn | Normal | 1 | 1.8.5.1.5.11 | 1.8.5.1.5.11 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 15:33
605 | 3727 | rGcF2XgkgPtqRDM3KJ2D | Normal | 28 | 1.8.5.1.6.1 | 1.8.5.1.6.1 |  | 2026-05-26 17:00 | q | -13 |  | 2026-05-13 09:45
606 | 3728 | Hgqc9wbzS3SDikBm20zt | Normal | 28 | 1.8.5.1.6.3 | 1.8.5.1.6.3 |  | 2026-07-28 17:00 | q | -1 |  | 2026-07-27 10:34
607 | 6653 | K0AYRckqpyO0HzRrxXG6 | Normal | 15 | 1.8.5.1.6.2 | 1.8.5.1.6.2 |  | 2026-06-16 17:00 | q | -12 |  | 2026-06-04 14:40
608 | 6654 | MMK0qYycfTMCrFAZcf8J | Normal | 15 | 1.8.5.1.6.4 | 1.8.5.1.6.4 |  | 2026-08-18 17:00 | q | 0 |  | 2026-08-18 15:28
609 | 3730 | TswICWhG0Mjj1DenbPW5 | Normal | 28 | 1.8.5.1.7.1 | 1.8.5.1.7.1 |  | 2026-06-16 17:00 | p | 7 |  | 2026-06-24 13:30
610 | 6627 | QBgG0JxqOymB6vyjKsRZ | Normal | 28 | 1.8.5.1.7.2 | 1.8.5.1.7.2 |  | 2026-07-28 17:00 | p | 5 |  | 2026-08-03 11:16
611 | 6628 | PAI9VZBMaYriaY1wvhOi | Normal | 15 | 1.8.5.1.7.3 | 1.8.5.1.7.3 |  | 2026-08-18 17:00 | p | 1 |  | 2026-08-20 14:19
612 | 3734 | cAszcoDUs4YPdXAiXa4B | Milestone | 0 | 1.8.5.1.9.1 | 1.8.5.1.9.1 |  | 2025-07-16 08:00 | p | 29 |  | 2025-08-14 14:39
613 | 3735 | rgqtw8hyurrfag2amXLA | Normal | 109 | 1.8.5.1.9.2 | 1.8.5.1.9.2 |  | 2025-12-19 17:00 | p | 32 |  | 2026-01-21 16:20
614 | 3736 | eIMYQUSTObIc5Lp6kKBE | Normal | 40 | 1.8.5.1.9.3 | 1.8.5.1.9.3 |  | 2026-02-19 17:00 | p | 10 |  | 2026-03-02 14:51
615 | 3737 | z19Wnme0hJcfEI4IfIQR | Normal | 25 | 1.8.5.1.9.4 | 1.8.5.1.9.4 |  | 2026-08-11 17:00 | q | -4 |  | 2026-08-07 13:51
616 | 6657 | uq5fluI8KT8LkPx57ktn | Normal | 10 | 1.8.5.1.9.5 | 1.8.5.1.9.5 |  | 2026-08-25 17:00 | q | 0 |  | 2026-08-25 09:01
617 | 3739 | Ba23bBwg4xGpRd3Ht4kS | Normal | 24 | 1.8.5.1.10.1 | 1.8.5.1.10.1 |  | 2025-09-23 17:00 | p | 6 |  | 2025-09-30 08:01
618 | 3740 | lRtbtcrLyr1QGd0laoJi | Normal | 25 | 1.8.5.1.10.2 | 1.8.5.1.10.2 |  | 2026-04-23 17:00 | q | -1 |  | 2026-04-22 13:03
619 | 3741 | V05WnFKB5t2LuixhoKHO | Normal | 25 | 1.8.5.1.10.3 | 1.8.5.1.10.3 |  | 2026-05-29 17:00 | p | 4 |  | 2026-06-03 13:25
620 | 3742 | LRjVz0hoZuIRlQgcLYzs | Normal | 25 | 1.8.5.1.10.6 | 1.8.5.1.10.6 |  | 2026-08-11 17:00 | p | 1 |  | 2026-08-13 09:59
621 | 6648 | Z5T3n0GGVz8PB0IY5TXC | Normal | 10 | 1.8.5.1.10.5 | 1.8.5.1.10.5 |  | 2026-07-07 17:00 | q | -1 |  | 2026-07-06 11:40
622 | 6656 | tqprQgHoroqT051BXug3 | Normal | 15 | 1.8.5.1.10.4 | 1.8.5.1.10.4 |  | 2026-06-22 17:00 | p | 0 |  | 2026-06-23 13:32
623 | 6659 | NN3Qiea1foOxv05JqXnT | Normal | 10 | 1.8.5.1.10.7 | 1.8.5.1.10.7 |  | 2026-08-25 17:00 | p | 0 |  | 2026-08-26 08:24
624 | 3731 | 02LiOyWN4DF8GOeNSP5s | Normal | 20 | 1.8.5.1.8.1 | 1.8.5.1.8.1 |  | 2026-03-19 17:00 | p | 4 |  | 2026-03-24 16:36
625 | 3732 | x85AkT9s5HT2a4U2goND | Normal | 20 | 1.8.5.1.8.8 | 1.8.5.1.8.8 |  | 2026-08-04 17:00 | p | 0 |  | 2026-08-05 10:13
626 | 6629 | n59ds33sZr9JNOobmYWE | Normal | 30 | 1.8.5.1.8.2 | 1.8.5.1.8.2 |  | 2026-04-30 17:00 | q | -8 |  | 2026-04-22 08:44
627 | 6630 | y36QmeQSyS7BZflkeM7e | Normal | 10 | 1.8.5.1.8.3 | 1.8.5.1.8.3 |  | 2026-05-14 17:00 | q | -8 |  | 2026-05-06 11:48
628 | 6631 | Ghk1eKq5exIyUH3hdAeR | Normal | 20 | 1.8.5.1.8.4 | 1.8.5.1.8.4 |  | 2026-06-12 17:00 | q | -8 |  | 2026-06-04 15:10
629 | 6632 | 5y36mClzGR7vkSsODb4C | Normal | 15 | 1.8.5.1.8.5 | 1.8.5.1.8.5 |  | 2026-07-07 17:00 | q | -14 |  | 2026-06-23 10:03
630 | 6633 | uS272glxjETpDiVeJyGv | Normal | 20 | 1.8.5.1.8.6 | 1.8.5.1.8.6 |  | 2026-08-04 17:00 | q | -11 |  | 2026-07-24 09:17
631 | 6643 | sKnPCsxlq51dE8cz52fo | Normal | 10 | 1.8.5.1.8.9 | 1.8.5.1.8.9 |  | 2026-08-18 17:00 | q | 0 |  | 2026-08-18 13:44
632 | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Summary | 1 | 1.8.1 | 1.8.1 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
633 | 6082 | YsSSuERf5VIDKO5m8eZo | Normal | 1 | 1.8.1.1 | 1.8.1.1 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
634 | 6313 | 8HYxn50EKf1DU0fX0MF7 | Summary | 391 | 1.8.4 | 1.8.4 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
635 | 5516 | dd6fm1lW4tBXPtNV5RGW | Summary | 391 | 1.8.4.1 | 1.8.4.1 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
636 | 5523 | APkwTVep7mUhgmcCl4NB | Milestone | 0 | 1.8.4.1.4 | 1.8.4.1.4 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
637 | 5527 | Mw5Re8SivA42laH7UhJE | Milestone | 0 | 1.8.4.1.5 | 1.8.4.1.5 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
638 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
639 | 5331 | emM9tIPUc6I6BRQdDkUj | Summary | 325 | 1.9.3 | 1.9.3 |  | 2028-07-31 08:00 | p | 210 |  | 2029-02-26 09:11
640 | 5332 | Jas5wmBgln6JvMRLtRUk | Summary | 110 | 1.9.3.1 | 1.9.3.1 |  | 2028-07-31 08:00 | p | 210 |  | 2029-02-26 09:11
641 | 5333 | NEZJUiuEFBeqDBEbXbzQ | Milestone | 0 | 1.9.3.1.1 | 1.9.3.1.1 |  | 2028-02-28 08:00 | p | 206 |  | 2028-09-21 14:19
642 | 5334 | 5Bt8vyiG2PJ2FKCjQPP1 | Summary | 74 | 1.9.3.1.2 | 1.9.3.1.2 |  | 2028-06-08 17:00 | p | 213 |  | 2029-01-08 14:25
643 | 6471 | xmZvSzAhf2D9ir29atKO | Normal | 8 | 1.9.3.1.2.1 | 1.9.3.1.2.1 |  | 2028-03-08 17:00 | p | 208 |  | 2028-10-03 13:03
644 | 6472 | j0VQ7fJsNHb1HpOVRoJN | Normal | 7 | 1.9.3.1.2.2 | 1.9.3.1.2.2 |  | 2028-03-17 17:00 | p | 209 |  | 2028-10-13 10:57
645 | 6473 | FN1N5cBOnOQJN0lvtY6J | Normal | 5 | 1.9.3.1.2.3 | 1.9.3.1.2.3 |  | 2028-03-24 17:00 | p | 209 |  | 2028-10-20 15:59
646 | 6474 | k77H7bJ7aRKhBrZeZFzu | Normal | 10 | 1.9.3.1.2.4 | 1.9.3.1.2.4 |  | 2028-04-07 17:00 | p | 209 |  | 2028-11-03 16:29
647 | 6475 | TkBVMCiZTEhYxjcnMNRI | Normal | 8 | 1.9.3.1.2.5 | 1.9.3.1.2.5 |  | 2028-04-19 17:00 | p | 208 |  | 2028-11-14 08:30
648 | 6476 | HdsfOo0UbW7iVGjY7L1O | Normal | 10 | 1.9.3.1.2.6 | 1.9.3.1.2.6 |  | 2028-05-03 17:00 | p | 210 |  | 2028-11-30 16:13
649 | 6477 | m1G8PrmdvRxZwBbLlVUQ | Normal | 7 | 1.9.3.1.2.7 | 1.9.3.1.2.7 |  | 2028-05-12 17:00 | p | 212 |  | 2028-12-11 15:49
650 | 6478 | ZDDqpCGw2ELQiAxZVJFo | Normal | 7 | 1.9.3.1.2.8 | 1.9.3.1.2.8 |  | 2028-05-23 17:00 | p | 210 |  | 2028-12-20 10:18
651 | 6479 | i51TyrBkECB0t7wKJruE | Normal | 7 | 1.9.3.1.2.9 | 1.9.3.1.2.9 |  | 2028-06-01 17:00 | p | 213 |  | 2029-01-01 14:10
652 | 6480 | XeKgBzwPereNdZmXnTFt | Normal | 5 | 1.9.3.1.2.10 | 1.9.3.1.2.10 |  | 2028-06-08 17:00 | p | 213 |  | 2029-01-08 14:25
653 | 5335 | fBEkx0xCtVpw1OeE4jLB | Summary | 25 | 1.9.3.1.3 | 1.9.3.1.3 |  | 2028-07-13 17:00 | p | 209 |  | 2029-02-08 11:40
654 | 5336 | FIhKbBOHnlTp0loBBfvV | Normal | 3 | 1.9.3.1.3.1 | 1.9.3.1.3.1 |  | 2028-06-15 17:00 | p | 213 |  | 2029-01-15 16:16
655 | 5337 | TPAbtCx4KhMQiN0iVD1F | Normal | 0 | 1.9.3.1.3.2 | 1.9.3.1.3.2 |  | 2028-06-15 17:00 | p | 213 |  | 2029-01-15 16:16
656 | 5338 | NXWa8B3rzsUFws6lYttF | Normal | 5 | 1.9.3.1.3.3 | 1.9.3.1.3.3 |  | 2028-06-15 17:00 | p | 213 |  | 2029-01-15 16:16
657 | 5339 | o98eRuEZGwoxxa1Byl7H | Normal | 5 | 1.9.3.1.3.4 | 1.9.3.1.3.4 |  | 2028-06-15 17:00 | p | 213 |  | 2029-01-15 16:16
658 | 5340 | lQJTDBnvPE8mTPnPre3v | Normal | 10 | 1.9.3.1.3.5 | 1.9.3.1.3.5 |  | 2028-06-29 17:00 | p | 209 |  | 2029-01-25 12:00
659 | 5341 | nevxwfefPkBzu42CDbNd | Normal | 10 | 1.9.3.1.3.6 | 1.9.3.1.3.6 |  | 2028-07-13 17:00 | p | 209 |  | 2029-02-08 11:40
660 | 5342 | s0JiBiXDLP6oybWmkZ43 | Normal | 6 | 1.9.3.1.4 | 1.9.3.1.4 |  | 2028-07-21 17:00 | p | 212 |  | 2029-02-19 08:26
661 | 5343 | NROXqcLUoQ0RLz64rMVc | Normal | 5 | 1.9.3.1.5 | 1.9.3.1.5 |  | 2028-07-28 17:00 | p | 212 |  | 2029-02-26 09:11
662 | 5344 | Kw3Fj6kwk5uOl7tQyqrL | Milestone | 0 | 1.9.3.1.6 | 1.9.3.1.6 |  | 2028-07-31 08:00 | p | 210 |  | 2029-02-26 09:11
663 | 6275 | OL3lkJGtK3tkk0d4SBRn | Summary | 288 | 1.9.9 | 1.9.9 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
664 | 795 | 85yV4lhIxXIziyB5R2QA | Normal | 1 | 1.9.9.1 | 1.9.9.1 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:06
665 | 844 | 1qfp8o9PQxr9vZvO7S5k | Normal | 1 | 1.9.9.4 | 1.9.9.4 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
666 | 845 | U1v5hScHSOPPxa5ohjfI | Summary | 189 | 1.9.9.7 | 1.9.9.7 |  | 2028-04-18 12:00 | p | 204 |  | 2028-11-09 11:40
667 | 847 | JilJNxxBcx7QrT5PcKLM | Summary | 189 | 1.9.9.7.2 | 1.9.9.7.2 |  | 2028-04-18 12:00 | p | 204 |  | 2028-11-09 11:40
668 | 866 | 0rLFG0X22Uukcn0axQTO | Normal | 50 | 1.9.9.7.2.6 | 1.9.9.7.2.6 |  | 2027-10-20 12:00 | p | 207 |  | 2028-05-15 09:08
669 | 869 | 8QCM3LZ8SN5y0jCLtGNh | Summary | 129 | 1.9.9.7.2.7 | 1.9.9.7.2.7 |  | 2028-04-18 12:00 | p | 204 |  | 2028-11-09 11:40
670 | 6419 | NORPsF566zq8VZyN1UzF | Normal | 10 | 1.9.9.7.2.7.1 | 1.9.9.7.2.7.1 |  | 2027-11-03 12:00 | p | 208 |  | 2028-05-29 15:20
671 | 6420 | 043wOhyyEd8vJkuUBkFf | Normal | 40 | 1.9.9.7.2.7.2 | 1.9.9.7.2.7.2 |  | 2027-12-29 12:00 | p | 202 |  | 2028-07-19 11:25
672 | 6421 | JZROXyECnTBG3SBjYZJ8 | Normal | 79 | 1.9.9.7.2.7.3 | 1.9.9.7.2.7.3 |  | 2028-04-18 12:00 | p | 204 |  | 2028-11-09 11:40
673 | 6418 | W9pbV5i9WFkdVEGtW75H | Normal | 45 | 1.9.9.7.2.5 | 1.9.9.7.2.5 |  | 2027-08-11 12:00 | p | 205 |  | 2028-03-03 16:11
674 | 870 | m3oEXpasu7ssfpw9dqLv | Summary | 267 | 1.9.9.14 | 1.9.9.14 |  | 2028-05-23 17:00 | p | 201 |  | 2028-12-11 13:54
675 | 4667 | gXRr1908PexMoLIDosFv | Normal | 100 | 1.9.9.14.3 | 1.9.9.14.3 |  | 2028-03-28 12:00 | p | 205 |  | 2028-10-20 10:30
676 | 4668 | G3SLCzd88WLMRnAF5Et7 | Normal | 0 | 1.9.9.14.4 | 1.9.9.14.4 |  | 2028-05-22 17:00 | p | 199 |  | 2028-12-08 14:59
677 | 4669 | aeClBbTsJ3qrKHWqQ1Rw | Normal | 40 | 1.9.9.14.5 | 1.9.9.14.5 |  | 2028-05-23 12:00 | p | 201 |  | 2028-12-11 08:48
678 | 4679 | rpzkOhA603pApmNdMeVE | Normal | 0 | 1.9.9.14.6 | 1.9.9.14.6 |  | 2028-05-23 17:00 | p | 201 |  | 2028-12-11 13:54
679 | 5786 | d3N6cqydEgoPO1XBMSTu | Normal | 7 | 1.9.9.14.1 | 1.9.9.14.1 |  | 2027-07-05 12:00 | p | 185 |  | 2028-01-07 09:36
680 | 5787 | r6JEZEKCpBbNZRe1W7Ef | Normal | 91 | 1.9.9.14.2 | 1.9.9.14.2 |  | 2027-11-09 12:00 | p | 217 |  | 2028-06-13 16:24
681 | 899 | w1GWQdUx9oG06oopRYZx | Summary | 24 | 1.9.9.15 | 1.9.9.15 |  | 2028-05-24 17:00 | p | 208 |  | 2028-12-19 10:21
682 | 900 | ANUK0HdVlI2Jd5hSzs0f | Milestone | 0 | 1.9.9.15.1 | 1.9.9.15.1 |  | 2028-04-19 13:00 | p | 204 |  | 2028-11-10 11:17
683 | 901 | HcFqHITfVdYMyzVb3S8v | Normal | 18 | 1.9.9.15.2 | 1.9.9.15.2 |  | 2028-05-22 17:00 | p | 206 |  | 2028-12-15 11:11
684 | 902 | nIjAIVHCOoi1ijXym0cI | Normal | 3 | 1.9.9.15.3 | 1.9.9.15.3 |  | 2028-04-24 12:00 | p | 204 |  | 2028-11-15 11:13
685 | 903 | UDGopgZ2sb1QsQEooZ9G | Normal | 8 | 1.9.9.15.4 | 1.9.9.15.4 |  | 2028-05-04 12:00 | p | 203 |  | 2028-11-24 11:14
686 | 904 | 4CH3NSJx1luiHbrrAEJg | Normal | 2 | 1.9.9.15.5 | 1.9.9.15.5 |  | 2028-05-24 17:00 | p | 208 |  | 2028-12-19 10:21
687 | 905 | MxRWNVEH6ZVBPqNnA2hI | Normal | 8 | 1.9.9.15.6 | 1.9.9.15.6 |  | 2028-05-16 12:00 | p | 201 |  | 2028-12-04 09:48
688 | 906 | PL0zn2U2NPPXQqakkHLb | Normal | 5 | 1.9.9.15.7 | 1.9.9.15.7 |  | 2028-05-23 12:00 | p | 201 |  | 2028-12-11 08:48
689 | 907 | 5mTVpVcHzmsYLVY8xpKs | Normal | 5 | 1.9.9.15.8 | 1.9.9.15.8 |  | 2028-05-23 12:00 | p | 201 |  | 2028-12-11 08:48
690 | 914 | q0UeyWaeMXFoeUDjjzhX | Summary | 18 | 1.9.9.5 | 1.9.9.5 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:06
691 | 915 | jxzEE3EBeGWt1nE3uHcj | Summary | 18 | 1.9.9.5.1 | 1.9.9.5.1 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:06
692 | 916 | d4bxhxtQW3GaLrDrUlf9 | Normal | 17 | 1.9.9.5.1.1 | 1.9.9.5.1.1 |  | 2028-09-26 17:00 | p | 202 |  | 2029-04-17 16:44
693 | 917 | mbDdHZHm9OoYye329Ue6 | Normal | 1 | 1.9.9.5.1.2 | 1.9.9.5.1.2 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:06
694 | 4538 | aTyUglf0WPX6H8Zd17Iq | Summary | 71 | 1.9.9.16 | 1.9.9.16 |  | 2028-07-27 17:00 | p | 201 |  | 2029-02-14 13:47
695 | 6509 | sp3XFaPtGgzrVeC1wvvV | Normal | 10 | 1.9.9.16.3 | 1.9.9.16.3 |  | 2028-06-07 17:00 | p | 203 |  | 2028-12-28 15:13
696 | 6510 | dar9hgzhSUYJxC1MeoTS | Normal | 10 | 1.9.9.16.4 | 1.9.9.16.4 |  | 2028-06-07 17:00 | p | 203 |  | 2028-12-28 15:13
697 | 6513 | IG8fHoH3vjERJ6iSB3Rj | Normal | 36 | 1.9.9.16.5 | 1.9.9.16.5 |  | 2028-07-27 17:00 | p | 201 |  | 2029-02-14 13:47
698 | 6514 | imV319lPgBwI8oLVT5sB | Normal | 1 | 1.9.9.16.2 | 1.9.9.16.2 |  | 2028-05-24 17:00 | p | 201 |  | 2028-12-12 13:13
699 | 6515 | a8Kdm3F6uLeIN4SEhwX9 | Normal | 1 | 1.9.9.16.1 | 1.9.9.16.1 |  | 2028-05-23 17:00 | p | 201 |  | 2028-12-11 13:54
700 | 5783 | BOvEGIzyTacp1vvD9v7M | Normal | 1 | 1.9.9.2 | 1.9.9.2 |  | 2028-04-19 12:00 | p | 204 |  | 2028-11-10 11:17
701 | 6128 | 7jXaekqqhUCDWSDfnxzo | Summary | 28 | 1.7.4.2 | 1.7.4.2 |  | 2025-08-19 17:00 | p | 8 |  | 2025-08-28 15:08
702 | 6130 | 3AAePL8Vt5bI7qDxsaDX | Normal | 20 | 1.7.4.2.3 | 1.7.4.2.3 |  | 2025-08-19 17:00 | p | 8 |  | 2025-08-28 15:08
703 | 6685 | 2nkdQcaVv7LgM8d4dFld | Summary | 1 | 1.9.9.12 | 1.9.9.12 |  | 2028-07-28 17:00 | p | 212 |  | 2029-02-26 09:11
704 | 6687 | RiyOBd4mBIE5Cq6C0A4h | Normal | 1 | 1.9.9.12.1 | 1.9.9.12.1 |  | 2028-07-28 17:00 | p | 212 |  | 2029-02-26 09:11
705 | 6686 | IDiuvzfQRXyu7MCMX1jW | Normal | 5 | 1.9.9.11 | 1.9.9.11 |  | 2028-07-27 17:00 | p | 210 |  | 2029-02-23 10:07
706 | 7388 | subTjNOw9tjXphx2xXzW | Summary | 324 | 1.9.9.13 | 1.9.9.13 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 10:06
707 | 7389 | xTfJP5JFEqXIDmLDdKVZ | Summary | 43 | 1.9.9.13.1 | 1.9.9.13.1 |  | 2027-09-01 12:00 | p | 200 |  | 2028-03-20 09:05
708 | 7390 | GV26YG775A5KHHrrMIRV | Summary | 32 | 1.9.9.13.1.1 | 1.9.9.13.1.1 |  | 2027-08-19 12:00 | p | 200 |  | 2028-03-06 16:52
709 | 7391 | UumEMUqxjwvZXtHBx1rg | Normal | 3 | 1.9.9.13.1.1.1 | 1.9.9.13.1.1.1 |  | 2027-07-07 12:00 | p | 201 |  | 2028-01-24 13:11
710 | 7392 | ylVP19AJuwY485wgDJEG | Normal | 10 | 1.9.9.13.1.1.2 | 1.9.9.13.1.1.2 |  | 2027-07-23 12:00 | p | 201 |  | 2028-02-09 14:40
711 | 7393 | RzIyrLZKRoqlWdOJYpGf | Normal | 3 | 1.9.9.13.1.1.3 | 1.9.9.13.1.1.3 |  | 2027-07-21 12:00 | p | 201 |  | 2028-02-07 16:50
712 | 7394 | zHoRZ9fggWfe9FGnA954 | Normal | 10 | 1.9.9.13.1.1.4 | 1.9.9.13.1.1.4 |  | 2027-08-05 17:00 | p | 200 |  | 2028-02-22 14:55
713 | 7395 | PMjQe1vYJ6mxUbNABucF | Normal | 3 | 1.9.9.13.1.1.5 | 1.9.9.13.1.1.5 |  | 2027-08-04 12:00 | p | 201 |  | 2028-02-22 08:42
714 | 7396 | gQKdIVV4LZyvHUAfFFFg | Normal | 10 | 1.9.9.13.1.1.6 | 1.9.9.13.1.1.6 |  | 2027-08-19 12:00 | p | 200 |  | 2028-03-06 16:52
715 | 7397 | gmOEJCOmO6SQ6HMlGXfq | Summary | 12 | 1.9.9.13.1.2 | 1.9.9.13.1.2 |  | 2027-09-01 12:00 | p | 200 |  | 2028-03-20 09:05
716 | 7398 | ItOQSxoXEYWD5clVNK0n | Normal | 3 | 1.9.9.13.1.2.1 | 1.9.9.13.1.2.1 |  | 2027-08-19 12:00 | p | 200 |  | 2028-03-06 16:52
717 | 7399 | cXpFrNuZR7O8wPV6KZK3 | Normal | 9 | 1.9.9.13.1.2.2 | 1.9.9.13.1.2.2 |  | 2027-09-01 12:00 | p | 200 |  | 2028-03-20 09:05
718 | 7400 | VGtguPWpaIPmF0Ojsz8a | Summary | 176 | 1.9.9.13.2 | 1.9.9.13.2 |  | 2028-05-17 17:00 | p | 208 |  | 2028-12-12 13:43
719 | 7401 | H3MyBOTVJ4MGxcXcavMD | Normal | 2 | 1.9.9.13.2.1 | 1.9.9.13.2.1 |  | 2027-09-01 12:00 | p | 200 |  | 2028-03-20 09:05
720 | 7402 | pMiEhGou1QDK96DPu7Q8 | Normal | 1 | 1.9.9.13.2.2 | 1.9.9.13.2.2 |  | 2027-09-02 12:00 | p | 200 |  | 2028-03-21 09:16
721 | 7403 | pHZBXvaYVwug2p7gN6jp | Summary | 17 | 1.9.9.13.2.3 | 1.9.9.13.2.3 |  | 2027-09-27 12:00 | p | 198 |  | 2028-04-12 13:04
722 | 7404 | EvHLT3cR3tYYGwcq6SC1 | Normal | 5 | 1.9.9.13.2.3.1 | 1.9.9.13.2.3.1 |  | 2027-09-09 12:00 | p | 200 |  | 2028-03-28 09:50
723 | 7405 | 5GpI6xkgfIoVOnU9egD8 | Normal | 12 | 1.9.9.13.2.3.2 | 1.9.9.13.2.3.2 |  | 2027-09-27 12:00 | p | 198 |  | 2028-04-12 13:04
724 | 7406 | WxzG2sAIbVYYiem4v3mk | Normal | 12 | 1.9.9.13.2.3.3 | 1.9.9.13.2.3.3 |  | 2027-09-27 12:00 | p | 198 |  | 2028-04-12 13:04
725 | 7407 | 0eiyRK1I5mgUCdtpXpqY | Summary | 44 | 1.9.9.13.2.4 | 1.9.9.13.2.4 |  | 2027-11-26 12:00 | p | 199 |  | 2028-06-13 08:48
726 | 7408 | uKngouP2QMMQmu6HFm0I | Normal | 11 | 1.9.9.13.2.4.1 | 1.9.9.13.2.4.1 |  | 2027-10-12 12:00 | p | 196 |  | 2028-04-26 11:31
727 | 7409 | C7eZzAQkBbKewE4wmmOD | Normal | 11 | 1.9.9.13.2.4.2 | 1.9.9.13.2.4.2 |  | 2027-10-27 12:00 | p | 196 |  | 2028-05-10 14:48
728 | 7410 | VCdEPtbQjRcgNUnNprkZ | Normal | 11 | 1.9.9.13.2.4.3 | 1.9.9.13.2.4.3 |  | 2027-11-11 12:00 | p | 196 |  | 2028-05-25 13:17
729 | 7411 | OzHccTXr25Mf4pmiIMuT | Normal | 11 | 1.9.9.13.2.4.4 | 1.9.9.13.2.4.4 |  | 2027-11-26 12:00 | p | 199 |  | 2028-06-13 08:48
730 | 7412 | obz02flxb00pYjKUpMNx | Normal | 12 | 1.9.9.13.2.5 | 1.9.9.13.2.5 |  | 2028-01-17 12:00 | p | 204 |  | 2028-08-08 14:51
731 | 7413 | xazO1XwNp5eROWJmaREL | Summary | 36 | 1.9.9.13.2.6 | 1.9.9.13.2.6 |  | 2028-01-17 12:00 | p | 204 |  | 2028-08-08 14:51
732 | 7414 | DrM34eAIT9imz4vRHbHm | Normal | 2 | 1.9.9.13.2.6.1 | 1.9.9.13.2.6.1 |  | 2027-11-30 12:00 | p | 197 |  | 2028-06-15 09:53
733 | 7415 | RsULMViXRZoYahxlMUQ4 | Normal | 20 | 1.9.9.13.2.6.2 | 1.9.9.13.2.6.2 |  | 2027-12-28 12:00 | p | 203 |  | 2028-07-19 11:22
734 | 7416 | U8irVJqpjJwQWU5FcpMo | Normal | 3 | 1.9.9.13.2.6.3 | 1.9.9.13.2.6.3 |  | 2027-12-31 12:00 | p | 206 |  | 2028-07-24 15:52
735 | 7417 | yrCdbpyUp4mqkbXiv5Nc | Normal | 6 | 1.9.9.13.2.6.4 | 1.9.9.13.2.6.4 |  | 2028-01-10 12:00 | p | 203 |  | 2028-08-01 09:30
736 | 7418 | Iw5sTi596kP8d52cBWYm | Normal | 5 | 1.9.9.13.2.6.5 | 1.9.9.13.2.6.5 |  | 2028-01-17 12:00 | p | 204 |  | 2028-08-08 14:51
737 | 7419 | s9reBpLseCBnslseiKA6 | Normal | 2 | 1.9.9.13.2.7 | 1.9.9.13.2.7 |  | 2028-01-19 12:00 | p | 204 |  | 2028-08-11 09:38
738 | 7420 | ia01m1zWF4qAvVLVg5It | Summary | 54 | 1.9.9.13.2.8 | 1.9.9.13.2.8 |  | 2028-04-04 12:00 | p | 203 |  | 2028-10-24 13:16
739 | 7421 | 5PvQN5TGe8y7KbK2rRhO | Normal | 8 | 1.9.9.13.2.8.1 | 1.9.9.13.2.8.1 |  | 2028-01-31 12:00 | p | 205 |  | 2028-08-23 13:49
740 | 7422 | fj19MvsSAfWHeVGXiA1H | Normal | 5 | 1.9.9.13.2.8.2 | 1.9.9.13.2.8.2 |  | 2028-03-03 12:00 | p | 202 |  | 2028-09-21 14:48
741 | 7423 | hs9Gt4WgG9pENnEIaC7X | Normal | 14 | 1.9.9.13.2.8.3 | 1.9.9.13.2.8.3 |  | 2028-02-18 12:00 | p | 207 |  | 2028-09-13 10:12
742 | 7424 | WqCakGr8mHgCENNWHHjW | Normal | 5 | 1.9.9.13.2.8.4 | 1.9.9.13.2.8.4 |  | 2028-03-10 12:00 | p | 202 |  | 2028-09-29 10:21
743 | 7425 | Pv27HXd826jlfuUJmTLH | Normal | 20 | 1.9.9.13.2.8.5 | 1.9.9.13.2.8.5 |  | 2028-03-17 12:00 | p | 205 |  | 2028-10-09 10:02
744 | 7426 | UjcYgNHyPV73fWy2GGNA | Normal | 5 | 1.9.9.13.2.8.6 | 1.9.9.13.2.8.6 |  | 2028-03-17 12:00 | p | 205 |  | 2028-10-09 10:02
745 | 7427 | 5QMAV8W19uO0knxuRgYc | Normal | 6 | 1.9.9.13.2.8.7 | 1.9.9.13.2.8.7 |  | 2028-03-27 12:00 | p | 203 |  | 2028-10-16 17:00
746 | 7428 | C3roUkJ3GEdxAvfnxnUE | Normal | 6 | 1.9.9.13.2.8.8 | 1.9.9.13.2.8.8 |  | 2028-03-27 12:00 | p | 204 |  | 2028-10-18 08:20
747 | 7429 | GMfJSktlv5oUXA5LFNgA | Normal | 6 | 1.9.9.13.2.8.9 | 1.9.9.13.2.8.9 |  | 2028-04-04 12:00 | p | 203 |  | 2028-10-24 13:16
748 | 7430 | AjX0fOJfuCWTWcoFWrZe | Summary | 11 | 1.9.9.13.2.9 | 1.9.9.13.2.9 |  | 2028-05-17 17:00 | p | 208 |  | 2028-12-12 13:43
749 | 7431 | YKkcKAxBNBkRs3Gs0cxp | Normal | 7 | 1.9.9.13.2.9.1 | 1.9.9.13.2.9.1 |  | 2028-05-17 17:00 | p | 208 |  | 2028-12-12 13:43
750 | 7432 | HbmHLQTrqR87hE03VIdq | Normal | 3 | 1.9.9.13.2.9.2 | 1.9.9.13.2.9.2 |  | 2028-04-07 12:00 | p | 202 |  | 2028-10-27 11:33
751 | 7433 | FxBsJSw4ZNEIyIQA8bL9 | Normal | 8 | 1.9.9.13.2.9.3 | 1.9.9.13.2.9.3 |  | 2028-04-19 12:00 | p | 204 |  | 2028-11-10 11:17
752 | 7434 | MkjgnYEnwrIrITdXMEl9 | Milestone | 0 | 1.9.9.13.3 | 1.9.9.13.3 |  | 2028-07-28 08:00 | p | 201 |  | 2029-02-14 13:47
753 | 7435 | nSo6tYchIu2Aw4YtE45u | Summary | 44 | 1.9.9.13.4 | 1.9.9.13.4 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 10:06
754 | 7436 | Y83lvWkQwfsc3dMGwfVN | Summary | 30 | 1.9.9.13.4.1 | 1.9.9.13.4.1 |  | 2028-09-08 17:00 | p | 205 |  | 2029-04-02 10:47
755 | 7437 | E8EwVgjFQaEPGP66WsCb | Summary | 30 | 1.9.9.13.4.1.1 | 1.9.9.13.4.1.1 |  | 2028-09-08 17:00 | p | 205 |  | 2029-04-02 10:47
756 | 7438 | y2P0mgWq1uFkM4aVxtQJ | Normal | 15 | 1.9.9.13.4.1.1.1 | 1.9.9.13.4.1.1.1 |  | 2028-08-18 17:00 | p | 207 |  | 2029-03-14 13:50
757 | 7439 | nsJKxwZOWJc3LdYsNOwr | Normal | 5 | 1.9.9.13.4.1.1.2 | 1.9.9.13.4.1.1.2 |  | 2028-08-25 17:00 | p | 207 |  | 2029-03-21 09:51
758 | 7440 | 3ZzL4TktDwncii0hY2dA | Normal | 10 | 1.9.9.13.4.1.1.3 | 1.9.9.13.4.1.1.3 |  | 2028-09-08 17:00 | p | 205 |  | 2029-04-02 10:47
759 | 7441 | IcgrxiRjEYJLwuugm8N7 | Summary | 30 | 1.9.9.13.4.1.2 | 1.9.9.13.4.1.2 |  | 2028-09-07 17:00 | p | 203 |  | 2029-03-30 14:22
760 | 7442 | B8zfbswYxyRxHa21jaE6 | Normal | 15 | 1.9.9.13.4.1.2.1 | 1.9.9.13.4.1.2.1 |  | 2028-08-17 17:00 | p | 202 |  | 2029-03-08 09:14
761 | 7443 | lvFKaF8Jtq8DkkB0s9nv | Normal | 15 | 1.9.9.13.4.1.2.2 | 1.9.9.13.4.1.2.2 |  | 2028-09-07 17:00 | p | 203 |  | 2029-03-30 14:22
762 | 7444 | 419IszMaZW6XNIQptprk | Normal | 20 | 1.9.9.13.4.1.3 | 1.9.9.13.4.1.3 |  | 2028-09-08 17:00 | p | 205 |  | 2029-04-02 10:47
763 | 7445 | oNfFp4VAwKEpoSujTbHZ | Normal | 10 | 1.9.9.13.4.1.4 | 1.9.9.13.4.1.4 |  | 2028-09-08 17:00 | p | 205 |  | 2029-04-02 10:47
764 | 7446 | NnBZUSVumxDXwVdCLN8g | Summary | 12 | 1.9.9.13.4.2 | 1.9.9.13.4.2 |  | 2028-09-25 17:00 | p | 203 |  | 2029-04-17 15:30
765 | 7447 | CAsJ3atkVCS14hehUB9Y | Normal | 4 | 1.9.9.13.4.2.1 | 1.9.9.13.4.2.1 |  | 2028-09-14 17:00 | p | 203 |  | 2029-04-06 13:07
766 | 7448 | 8tMCh2h8AwE53TPPkfEv | Normal | 3 | 1.9.9.13.4.2.2 | 1.9.9.13.4.2.2 |  | 2028-09-14 17:00 | p | 203 |  | 2029-04-06 13:07
767 | 7449 | LaZxXVdUnGzqswRGUiV5 | Normal | 7 | 1.9.9.13.4.2.3 | 1.9.9.13.4.2.3 |  | 2028-09-25 17:00 | p | 203 |  | 2029-04-17 15:30
768 | 7450 | F3vtt1T8lz7mQWFPgUKT | Normal | 2 | 1.9.9.13.4.3 | 1.9.9.13.4.3 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:06
769 | 7451 | nShmtMdGhMi3SzNeAZjW | Milestone | 0 | 1.9.9.13.4.4 | 1.9.9.13.4.4 |  | 2028-09-28 08:00 | p | 203 |  | 2029-04-19 10:06
770 | 7510 | 4i5VLTIa98HteWhFzYjv | Normal | 3 | 1.7.10.24 | 1.7.10.24 |  | 2027-07-02 12:00 | p | 200 |  | 2028-01-19 11:32
771 | 7511 | tHPdmsBqm9kHM69dtq3h | Normal | 7 | 1.7.10.25 | 1.7.10.25 |  | 2027-07-16 12:00 | p | 201 |  | 2028-02-02 13:28
772 | 7512 | hmOTDv9qQbSDcHudIm9x | Normal | 7 | 1.7.10.26 | 1.7.10.26 |  | 2027-07-30 12:00 | p | 201 |  | 2028-02-17 09:27
773 | 7513 | NbiRgc4Tdvxa900kw7Xq | Normal | 8 | 1.7.10.27 | 1.7.10.27 |  | 2027-08-16 12:00 | p | 198 |  | 2028-03-01 16:18
774 | 7539 | ROucR7pug9aGzObG8pvW | Normal | 1 | 1.7.10.8 | 1.7.10.8 |  | 2027-06-18 12:00 | p | 200 |  | 2028-01-05 09:47
775 | 7540 | njszlznNRnCyRW2hgoMI | Normal | 10 | 1.7.10.9 | 1.7.10.9 |  | 2027-07-02 12:00 | p | 200 |  | 2028-01-19 11:32
776 | 7541 | R63tw5xkvmDGiWpIPQRa | Normal | 1 | 1.7.10.10 | 1.7.10.10 |  | 2027-07-02 12:00 | p | 200 |  | 2028-01-19 11:32
777 | 7542 | E3YdLEfamF0eZCISJiqw | Normal | 10 | 1.7.10.11 | 1.7.10.11 |  | 2027-07-02 12:00 | p | 200 |  | 2028-01-19 11:32
778 | 7543 | nhpJxewK7uClQLzGXJQJ | Normal | 1 | 1.7.10.12 | 1.7.10.12 |  | 2027-07-02 12:00 | p | 200 |  | 2028-01-19 11:32
779 | 7544 | cfuUTFyz3WOPAOOiNQOb | Normal | 1 | 1.7.10.13 | 1.7.10.13 |  | 2027-07-02 12:00 | p | 200 |  | 2028-01-19 11:32
780 | 6279 | p7EJXT1muDSglD2OZLFH | Summary | 274 | 1.9.7 | 1.9.7 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
781 | 1484 | 6ARiGRg3KLswRpJLOmGD | Summary | 229 | 1.9.7.18 | 1.9.7.18 |  | 2028-05-19 17:00 | p | 335 |  | 2029-04-20 09:39
782 | 1485 | R0QJsNVi0JzXq4FadBdS | Normal | 20 | 1.9.7.18.4 | 1.9.7.18.4 |  | 2026-05-13 17:00 | q | -6 |  | 2026-05-07 16:50
783 | 6540 | BF294XdCZHw2CEg81bOs | Normal | 19 | 1.9.7.18.6.1 | 1.9.7.18.6.1 |  | 2026-07-10 17:00 | q | -1 |  | 2026-07-09 08:19
784 | 6541 | X8phwYugZBkIbn0OysQW | Normal | 19 | 1.9.7.18.6.2 | 1.9.7.18.6.2 |  | 2026-08-06 17:00 | q | 0 |  | 2026-08-06 15:00
785 | 1489 | pYq4lU1lCt1U75q3gu6M | Normal | 11 | 1.9.7.18.1 | 1.9.7.18.1 |  | 2025-12-22 17:00 | p | 1214 |  | 2029-04-20 09:39
786 | 1490 | hF9FI1LNvFfgTTXhqPsR | Normal | 77 | 1.9.7.18.2 | 1.9.7.18.2 |  | 2026-04-14 17:00 | q | -7 |  | 2026-04-07 08:06
787 | 1491 | XpTPefWn9TT3C06gw8rA | Normal | 1 | 1.9.7.18.3 | 1.9.7.18.3 |  | 2026-04-15 17:00 | q | -7 |  | 2026-04-08 09:17
788 | 1495 | 0kid3Dd3U5gCQNrt2pwY | Normal | 1 | 1.9.7.18.8 | 1.9.7.18.8 |  | 2028-05-19 17:00 | p | 199 |  | 2028-12-05 15:08
789 | 1504 | ndaml8HRsqEWzWIKrI7h | Normal | 5 | 1.9.7.18.10 | 1.9.7.18.10 |  | 2028-02-29 17:00 | p | 204 |  | 2028-09-21 14:24
790 | 4587 | 5uS9ktvplxYkrLheR3Q9 | Normal | 20 | 1.9.7.18.5 | 1.9.7.18.5 |  | 2026-06-11 17:00 | q | 0 |  | 2026-06-11 09:29
791 | 1496 | 5t2MhilpkZRDQA3VTcGS | Normal | 48 | 1.9.7.7 | 1.9.7.7 |  | 2028-07-26 17:00 | p | 201 |  | 2029-02-13 13:54
792 | 1505 | 4c3z8pWafVxAWNC1MpC9 | Normal | 106 | 1.9.7.8 | 1.9.7.8 |  | 2028-07-26 17:00 | p | 201 |  | 2029-02-13 09:44
793 | 1508 | SDZ1pqYbdynEzXZrWujj | Normal | 30 | 1.9.7.6 | 1.9.7.6 |  | 2028-07-26 17:00 | p | 201 |  | 2029-02-13 11:15
794 | 1529 | WOa3B8SPUOSM5ThLE2Jo | Summary | 69 | 1.9.7.14 | 1.9.7.14 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:49
795 | 1531 | KX1eD2ASIZaZBZuqoVp4 | Normal | 1 | 1.9.7.14.2 | 1.9.7.14.2 |  | 2028-08-21 17:00 | p | 202 |  | 2029-03-12 14:16
796 | 1532 | fQ3wcWF8uEWMRGpUCxEA | Normal | 1 | 1.9.7.14.4 | 1.9.7.14.4 |  | 2028-08-23 17:00 | p | 202 |  | 2029-03-14 10:20
797 | 1533 | juvdtwZkjArAkPOzLrhN | Normal | 15 | 1.9.7.14.5 | 1.9.7.14.5 |  | 2028-09-13 17:00 | p | 202 |  | 2029-04-04 14:50
798 | 1534 | SuchbNnj1ndABAEPQlrb | Normal | 10 | 1.9.7.14.6 | 1.9.7.14.6 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:49
799 | 4583 | QzcCl72pVAI4zSVR8VAE | Normal | 1 | 1.9.7.14.3 | 1.9.7.14.3 |  | 2028-08-22 17:00 | p | 202 |  | 2029-03-13 11:06
800 | 1535 | vIOpwJGhGrQ4pKl5nahR | Summary | 61 | 1.9.7.15 | 1.9.7.15 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 16:54
801 | 1537 | HoYmSEeaxBfAYgcISNXh | Normal | 5 | 1.9.7.15.2 | 1.9.7.15.2 |  | 2026-05-29 17:00 | q | -2 |  | 2026-05-27 14:08
802 | 1538 | 1Xm6i4dPIyAKJzF1jRtD | Normal | 45 | 1.9.7.15.3 | 1.9.7.15.3 |  | 2026-08-04 17:00 | q | 0 |  | 2026-08-04 09:12
803 | 1539 | ySsQ3GXU4tpHt4hn7HeO | Normal | 2 | 1.9.7.15.4 | 1.9.7.15.4 |  | 2026-07-20 17:00 | q | -524 |  | 2025-02-11 17:00
804 | 1540 | GIXHFfgJ4jA0lgUlb0GT | Normal | 1 | 1.9.7.15.5 | 1.9.7.15.5 |  | 2026-07-21 17:00 | q | -524 |  | 2025-02-12 17:00
805 | 1541 | ss8yD9dhZfTIp9UxqHnG | Normal | 1 | 1.9.7.15.7 | 1.9.7.15.7 |  | 2026-08-05 17:00 | q | -1 |  | 2026-08-04 16:44
806 | 1542 | VmFPpoMfVfLEXeRBF7Um | Normal | 9 | 1.9.7.15.8 | 1.9.7.15.8 |  | 2026-08-18 17:00 | q | -4 |  | 2026-08-14 16:14
807 | 1543 | P2oxmSB7jXG6Ib9VEZ89 | Normal | 9 | 1.9.7.15.9 | 1.9.7.15.9 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 16:54
808 | 4585 | Z4QB23UBk58Dyd3318zD | Normal | 10 | 1.9.7.15.6 | 1.9.7.15.6 |  | 2026-08-04 17:00 | q | 0 |  | 2026-08-04 09:12
809 | 1544 | dYtuUpkdltDWUtvWJGdC | Summary | 80 | 1.9.7.16 | 1.9.7.16 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 16:20
810 | 1547 | K0gsOWDMqaySswr72BAQ | Normal | 1 | 1.9.7.16.3 | 1.9.7.16.3 |  | 2026-07-23 17:00 | q | -356 |  | 2025-08-01 13:25
811 | 1548 | 4jCrHn72KCapTPEI9TzQ | Normal | 2 | 1.9.7.16.5 | 1.9.7.16.5 |  | 2026-07-28 17:00 | q | -356 |  | 2025-08-06 13:34
812 | 1549 | s8gTUDwRZFDpCO4enZqk | Normal | 15 | 1.9.7.16.6 | 1.9.7.16.6 |  | 2026-08-18 17:00 | p | 0 |  | 2026-08-19 14:32
813 | 1550 | UoQFPyMNVa9QPyq2kgrl | Normal | 9 | 1.9.7.16.7 | 1.9.7.16.7 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 16:20
814 | 4586 | kRWFuIGKur6ToFmAr9JC | Normal | 1 | 1.9.7.16.4 | 1.9.7.16.4 |  | 2026-07-24 17:00 | q | -354 |  | 2025-08-04 11:54
815 | 1560 | fBOtciokyA85OuE15WSO | Normal | 1 | 1.9.7.19.10 | 1.9.7.19.10 |  | 2026-05-22 17:00 | q | -466 |  | 2025-02-10 17:00
816 | 1561 | 8BMHpFsmSFY1BvBQKfdD | Normal | 10 | 1.9.7.19.11 | 1.9.7.19.11 |  | 2026-06-08 17:00 | p | 0 |  | 2026-06-09 08:59
817 | 1562 | lBuCdKTmKHrCdvS4FVbB | Normal | 40 | 1.9.7.19.12 | 1.9.7.19.12 |  | 2026-08-05 17:00 | p | 0 |  | 2026-08-06 11:36
818 | 1563 | TUxQ6kz9ittb2zcmlLCL | Normal | 10 | 1.9.7.19.13 | 1.9.7.19.13 |  | 2026-08-19 17:00 | p | 0 |  | 2026-08-20 08:15
819 | 1564 | OkMyUpJo7fqJaif9Jvyb | Normal | 5 | 1.9.7.19.14 | 1.9.7.19.14 |  | 2026-08-26 17:00 | q | 0 |  | 2026-08-26 15:34
820 | 4571 | grLKm3VpZ98OhRQH2gBq | Normal | 29 | 1.9.7.1 | 1.9.7.1 |  | 2028-08-22 17:00 | p | 202 |  | 2029-03-13 11:06
821 | 4572 | 5hxJeLGqqaIlIue4XwRC | Normal | 1 | 1.9.7.2 | 1.9.7.2 |  | 2028-08-22 17:00 | p | 202 |  | 2029-03-13 11:06
822 | 4574 | z7UYZlhr663oN8lfFWmH | Summary | 29 | 1.9.7.11 | 1.9.7.11 |  | 2028-07-27 17:00 | p | 201 |  | 2029-02-14 13:47
823 | 1497 | q56IdotBOPeXlK3605d6 | Normal | 1 | 1.9.7.11.4 | 1.9.7.11.4 |  | 2028-07-27 17:00 | p | 201 |  | 2029-02-14 13:47
824 | 1506 | zNKWNUMZ7wFR6LBQ8bZ2 | Normal | 1 | 1.9.7.11.5 | 1.9.7.11.5 |  | 2028-07-27 17:00 | p | 201 |  | 2029-02-14 13:47
825 | 1509 | xdWSZU8MxGE52WBHNu6X | Normal | 1 | 1.9.7.11.3 | 1.9.7.11.3 |  | 2028-07-27 17:00 | p | 201 |  | 2029-02-14 13:47
826 | 6440 | u5F2XJPKXxmZ5m99Yx5A | Normal | 1 | 1.9.7.11.7 | 1.9.7.11.7 |  | 2028-07-27 17:00 | p | 201 |  | 2029-02-14 13:47
827 | 4575 | nPe6rBdPLk408ntp39jn | Normal | 1 | 1.9.7.3 | 1.9.7.3 |  | 2028-07-27 17:00 | p | 201 |  | 2029-02-14 13:47
828 | 4578 | kBeLaux8MTugqoi5KPvZ | Summary | 74 | 1.9.7.13 | 1.9.7.13 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
829 | 1518 | qXbL36bdYftxHm1TCntK | Normal | 1 | 1.9.7.13.4 | 1.9.7.13.4 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
830 | 4581 | FxGRGf2kppDMdfFrZkS4 | Normal | 36 | 1.9.7.12 | 1.9.7.12 |  | 2028-01-12 17:00 | p | 204 |  | 2028-08-04 15:46
831 | 4588 | L1kgBhMEjlIJ4HNHh1TQ | Summary | 141 | 1.9.7.20 | 1.9.7.20 |  | 2028-07-27 17:00 | p | 201 |  | 2029-02-14 13:47
832 | 1566 | KFj0hxHWvExDoqTqgDeg | Normal | 118 | 1.9.7.20.1 | 1.9.7.20.1 |  | 2028-06-26 17:00 | p | 202 |  | 2029-01-15 11:46
833 | 1567 | GV5or0ucuouXZiqAkH0N | Normal | 10 | 1.9.7.20.2 | 1.9.7.20.2 |  | 2028-07-10 17:00 | p | 204 |  | 2029-01-31 08:09
834 | 1568 | JI4xSRBKV4FYnRXdw7Wz | Normal | 9 | 1.9.7.20.3 | 1.9.7.20.3 |  | 2028-07-21 17:00 | p | 202 |  | 2029-02-09 15:10
835 | 1569 | DVuFJt4FGQSIgeZkA41d | Normal | 4 | 1.9.7.20.4 | 1.9.7.20.4 |  | 2028-07-27 17:00 | p | 201 |  | 2029-02-14 13:47
836 | 4590 | 21lrGsmJiPqRYOd4yY3H | Summary | 2 | 1.9.7.21 | 1.9.7.21 |  | 2028-09-11 17:00 | p | 203 |  | 2029-04-03 11:47
837 | 1570 | 9hmrS48cr19KgrseY4yN | Normal | 2 | 1.9.7.21.1 | 1.9.7.21.1 |  | 2028-09-11 17:00 | p | 203 |  | 2029-04-03 11:47
838 | 6439 | JoFd6fDKN7NWznuQx6gK | Normal | 56 | 1.9.7.10 | 1.9.7.10 |  | 2028-07-26 17:00 | p | 201 |  | 2029-02-13 11:40
839 | 7323 | p8rF5Tk8321hO30p5zSy | Summary | 79 | 1.7.8.18 | 1.7.8.18 |  | 2028-08-22 17:00 | p | 202 |  | 2029-03-13 09:40
840 | 7454 | JYERhD3wllXGZEgPk4Fl | Normal | 5 | 1.7.8.18.1 | 1.7.8.18.1 |  | 2028-05-25 17:00 | p | 196 |  | 2028-12-08 13:58
841 | 7455 | hQlezwT73UjuGPZkyuVr | Normal | 9 | 1.7.8.18.2 | 1.7.8.18.2 |  | 2028-06-07 17:00 | p | 195 |  | 2028-12-20 14:04
842 | 7456 | 3cfjdZ38xGBNf8roD7He | Normal | 9 | 1.7.8.18.3 | 1.7.8.18.3 |  | 2028-06-20 17:00 | p | 195 |  | 2029-01-02 09:01
843 | 7457 | abNwDWOnFoe0xwhiRueS | Normal | 1 | 1.7.8.18.4 | 1.7.8.18.4 |  | 2028-06-21 17:00 | p | 195 |  | 2029-01-03 08:32
844 | 7458 | cMhUMuxC0sax27543As7 | Normal | 24 | 1.7.8.18.5 | 1.7.8.18.5 |  | 2028-07-25 17:00 | p | 196 |  | 2029-02-07 14:09
845 | 7459 | xf7OMyoiQ38QdcweBYiq | Normal | 20 | 1.7.8.18.6 | 1.7.8.18.6 |  | 2028-08-22 17:00 | p | 202 |  | 2029-03-13 09:40
846 | 7324 | GVXYroUMjcAFUHa4B19H | Normal | 1 | 1.7.8.19 | 1.7.8.19 |  | 2028-06-21 17:00 | p | 195 |  | 2029-01-03 08:32
847 | 7325 | wl82vK5NXqnnsHIySTFp | Normal | 1 | 1.7.8.20 | 1.7.8.20 |  | 2028-08-23 17:00 | p | 202 |  | 2029-03-14 10:20
848 | 7382 | GJk3wpkfagyrb21gVciV | Summary | 288 | 1.9.7.22 | 1.9.7.22 |  | 2028-05-24 17:00 | p | 208 |  | 2028-12-19 10:21
849 | 7383 | chM988R4AoJxJINOHhOy | Normal | 1 | 1.9.7.22.1 | 1.9.7.22.1 |  | 2028-04-13 17:00 | p | 214 |  | 2028-11-14 13:26
850 | 7384 | xn1TRUhUfNd3ygHlAMk1 | Normal | 16 | 1.9.7.22.2 | 1.9.7.22.2 |  | 2028-05-05 17:00 | p | 208 |  | 2028-11-30 13:21
851 | 7385 | cYlWo9e2zkkP7jtt7iLZ | Normal | 1 | 1.9.7.22.3 | 1.9.7.22.3 |  | 2028-05-08 17:00 | p | 206 |  | 2028-12-01 11:26
852 | 7386 | F9n9tFj3S3xXbwXNgAjU | Normal | 5 | 1.9.7.22.4 | 1.9.7.22.4 |  | 2028-05-24 17:00 | p | 208 |  | 2028-12-19 10:21
853 | 4593 | XK8YU5H8vMrR7jBOr6fS | Normal | 99 | 1.9.1.1 | 1.9.1.1 |  | 2026-06-29 17:00 | p | 6 |  | 2026-07-06 14:42
854 | 4594 | EUFkYGsAZWO3vgZroOTA | Normal | 1 | 1.9.1.2 | 1.9.1.2 |  | 2026-06-30 17:00 | p | 6 |  | 2026-07-07 14:46
855 | 4595 | 0i30zTvKTrSo3R9n999e | Normal | 2 | 1.9.1.3 | 1.9.1.3 |  | 2026-07-02 17:00 | p | 6 |  | 2026-07-09 11:33
856 | 4605 | jXRAJqcdCYbTQqzq5oVG | Normal | 14 | 1.7.3.2 | 1.7.3.2 |  | 2026-01-14 17:00 | p | 0 |  | 2026-01-15 16:38
857 | 4606 | e1c7TqZJ2saEXqSPx9Ca | Normal | 1 | 1.7.3.3 | 1.7.3.3 |  | 2026-04-13 17:00 | p | 2 |  | 2026-04-16 13:48
858 | 4608 | tlJeJHdE7OwhwWyVvZ8P | Normal | 5 | 1.7.3.5.1 | 1.7.3.5.1 |  | 2026-06-25 17:00 | p | 5 |  | 2026-07-01 11:12
859 | 4609 | PoeQu0I6Io83IRbk7WtS | Normal | 5 | 1.7.3.5.2 | 1.7.3.5.2 |  | 2026-07-02 17:00 | p | 6 |  | 2026-07-09 11:33
860 | 4610 | UGUZlny6Ut8S0mLRTL2X | Normal | 1 | 1.7.3.5.3 | 1.7.3.5.3 |  | 2026-07-06 17:00 | p | 3 |  | 2026-07-10 10:21
861 | 4611 | 1TZOFiOcsBCmkfhi03Iw | Normal | 5 | 1.7.3.5.4 | 1.7.3.5.4 |  | 2026-07-20 17:00 | p | 3 |  | 2026-07-24 09:57
862 | 4612 | ZwEXlYv6PrV1t0gzfqom | Normal | 10 | 1.7.3.5.5 | 1.7.3.5.5 |  | 2026-08-03 17:00 | p | 3 |  | 2026-08-07 09:11
863 | 4613 | z0DGpsje53b33zXA5t1P | Normal | 20 | 1.7.3.5.6 | 1.7.3.5.6 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 16:59
864 | 4616 | FR5tuVwQGmPNYmz6BeMP | Normal | 2 | 1.7.3.4.1 | 1.7.3.4.1 |  | 2026-03-11 17:00 | p | 12 |  | 2026-03-24 16:59
865 | 4617 | OziRB3N5b7cM46iEETGg | Normal | 5 | 1.7.3.4.2 | 1.7.3.4.2 |  | 2026-02-17 17:00 | p | 6 |  | 2026-02-24 15:25
866 | 4618 | mRqsjEijsp2iSp4l7aof | Normal | 5 | 1.7.3.4.3 | 1.7.3.4.3 |  | 2026-04-13 17:00 | p | 2 |  | 2026-04-16 13:48
867 | 4619 | 8asUr7UOO8nabPagFvw9 | Normal | 40 | 1.7.3.4.4 | 1.7.3.4.4 |  | 2026-04-14 17:00 | p | 2 |  | 2026-04-17 11:58
868 | 4620 | UWR5akRFo4eKiDyQVnYr | Normal | 23 | 1.7.3.4.5 | 1.7.3.4.5 |  | 2026-04-13 17:00 | p | 2 |  | 2026-04-16 13:48
869 | 4621 | pGB9dynKUfIMuzj3AWVv | Normal | 1 | 1.7.3.4.6 | 1.7.3.4.6 |  | 2026-04-14 17:00 | p | 2 |  | 2026-04-17 11:58
870 | 4622 | Bm2ajkWBwO6Cvc6RoPdK | Normal | 5 | 1.7.3.4.7 | 1.7.3.4.7 |  | 2026-04-21 17:00 | p | 6 |  | 2026-04-28 14:33
871 | 4623 | sDTQ4X48dvup817zb0Do | Normal | 20 | 1.7.3.4.8 | 1.7.3.4.8 |  | 2026-05-19 17:00 | p | 8 |  | 2026-05-28 14:30
872 | 4624 | 3CGv61AS00FFpM5LrRat | Normal | 20 | 1.7.3.4.9 | 1.7.3.4.9 |  | 2026-06-17 17:00 | p | 7 |  | 2026-06-25 10:20
873 | 4630 | pjdWghPSPBEOfTIZFZhV | Normal | 5 | 1.7.3.6.4 | 1.7.3.6.4 |  | 2026-06-26 17:00 | p | 4 |  | 2026-07-01 10:24
874 | 4631 | EXJQS9o5Eq3lGkaYsCap | Normal | 1 | 1.7.3.6.5 | 1.7.3.6.5 |  | 2026-06-29 17:00 | p | 2 |  | 2026-07-02 09:46
875 | 4632 | VGp2Ji3lCAas2O4B01f5 | Normal | 1 | 1.7.3.6.6 | 1.7.3.6.6 |  | 2026-06-30 17:00 | p | 5 |  | 2026-07-06 09:32
876 | 4633 | STHfhyBuM5qFiEzHSgws | Normal | 19 | 1.7.3.6.7 | 1.7.3.6.7 |  | 2026-07-28 17:00 | q | 0 |  | 2026-07-28 13:06
877 | 4634 | cbBLoWE0dwfwOCS04ga7 | Normal | 15 | 1.7.3.6.8 | 1.7.3.6.8 |  | 2026-08-18 17:00 | q | 0 |  | 2026-08-18 13:09
878 | 4635 | vrd0V7BeylNxhzgI26F9 | Normal | 8 | 1.7.3.6.11 | 1.7.3.6.11 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 16:49
879 | 4663 | X9pjxOrdX8ZwQAfQziSu | Normal | 1 | 1.7.3.6.9 | 1.7.3.6.9 |  | 2026-08-19 17:00 | q | 0 |  | 2026-08-19 11:54
880 | 4664 | DAxARpEpHAwipBCK81bc | Normal | 8 | 1.7.3.6.10 | 1.7.3.6.10 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 16:49
881 | 4637 | ohQUE8EwZLGEmkE5FTpA | Summary | 8 | 1.7.3.7 | 1.7.3.7 |  | 2026-01-14 17:00 | p | 0 |  | 2026-01-15 16:38
882 | 6608 | ifCvUSq9UjUAw7FKKXTR | Normal | 14 | 1.7.3.7.3 | 1.7.3.7.3 |  | 2026-01-14 17:00 | p | 0 |  | 2026-01-15 16:38
883 | 7259 | Dcjo2uskRMoBajU90pQq | Normal | 60 | 1.7.1.4 | 1.7.1.4 |  | 2026-04-10 17:00 | p | 4 |  | 2026-04-15 13:32
884 | 6294 | Jtjxi70STISSeVqV8OJy | Summary | 163 | 1.9.6 | 1.9.6 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
885 | 3776 | GHLE38QRMYNBeSYAGB18 | Normal | 32 | 1.7.1.2.6.3 | 1.7.1.2.6.3 |  | 2026-08-19 17:00 | p | 0 |  | 2026-08-20 15:51
886 | 3790 | Om0YwWoKF5usOVLnDccR | Summary | 13 | 1.7.1.3.4 | 1.7.1.3.4 |  | 2026-05-29 17:00 | q | 0 |  | 2026-05-29 10:00
887 | 6977 | F0juzsyqTnJm6sTJe4ff | Normal | 14 | 1.7.1.3.4.7 | 1.7.1.3.4.7 |  | 2026-05-29 17:00 | q | 0 |  | 2026-05-29 10:00
888 | 6139 | VECMPYMi2oWf71g3eai1 | Normal | 29 | 1.7.1.3.9.1 | 1.7.1.3.9.1 |  | 2026-08-11 17:00 | q | -5 |  | 2026-08-06 14:16
889 | 6978 | z4sj2SQJw3pdZet8Am0U | Normal | 9 | 1.7.1.3.5 | 1.7.1.3.5 |  | 2026-08-06 17:00 | q | -3 |  | 2026-08-03 14:33
890 | 6983 | PcmQnh6ym2R5IAKzFgwu | Summary | 141 | 1.7.1.3.7 | 1.7.1.3.7 |  | 2026-06-23 17:00 | q | 0 |  | 2026-06-23 08:09
891 | 6985 | eGeEyEDP9xa0SwHKf7WR | Normal | 7 | 1.7.1.3.7.4 | 1.7.1.3.7.4 |  | 2026-06-09 17:00 | q | -1 |  | 2026-06-08 16:52
892 | 6986 | 31qYZ6wVIReV9ZOAqgem | Summary | 9 | 1.7.1.3.7.5 | 1.7.1.3.7.5 |  | 2026-06-23 17:00 | q | 0 |  | 2026-06-23 08:09
893 | 6987 | 50so1NYgvDTnEeNkdrjv | Normal | 3 | 1.7.1.3.7.5.1 | 1.7.1.3.7.5.1 |  | 2026-06-12 17:00 | q | -1 |  | 2026-06-11 14:32
894 | 6988 | bmsC3uFxKZ3RPA57Ivjb | Normal | 3 | 1.7.1.3.7.5.2 | 1.7.1.3.7.5.2 |  | 2026-06-17 17:00 | q | 0 |  | 2026-06-17 08:53
895 | 6989 | okOYULy0nclsZMYhl4sg | Normal | 3 | 1.7.1.3.7.5.3 | 1.7.1.3.7.5.3 |  | 2026-06-23 17:00 | q | 0 |  | 2026-06-23 08:09
896 | 7184 | gKjyagqR1BEsAZjZk4l5 | Milestone | 0 | 1.7.1.3.7.3 | 1.7.1.3.7.3 |  | 2026-06-01 08:00 | q | -2 |  | 2026-05-29 10:00
897 | 6990 | K8cvVDryBsyahUujiNmr | Summary | 22 | 1.7.1.3.8 | 1.7.1.3.8 |  | 2026-08-11 17:00 | q | -5 |  | 2026-08-06 14:16
898 | 6136 | bVRB0EhNo1xoyHBU8R0I | Normal | 1 | 1.7.1.3.8.2 | 1.7.1.3.8.2 |  | 2026-08-07 17:00 | q | -3 |  | 2026-08-04 14:22
899 | 6982 | E06yVWmTg8kRS6Gv9kOV | Summary | 6 | 1.7.1.3.8.3 | 1.7.1.3.8.3 |  | 2026-08-11 17:00 | q | -5 |  | 2026-08-06 14:16
900 | 6137 | gagQpjsDXV4QnJ1bUthb | Normal | 2 | 1.7.1.3.8.3.1 | 1.7.1.3.8.3.1 |  | 2026-08-11 17:00 | q | -5 |  | 2026-08-06 14:16
901 | 6979 | ZYA6dvbLVog9FL6DNJRb | Normal | 5 | 1.7.1.3.8.3.2 | 1.7.1.3.8.3.2 |  | 2026-06-30 17:00 | q | -1 |  | 2026-06-29 13:42
902 | 6991 | RAhO7UtYgqwLkhTknwrO | Normal | 6 | 1.7.1.3.8.1 | 1.7.1.3.8.1 |  | 2026-07-24 17:00 | q | -4 |  | 2026-07-20 08:18
903 | 3808 | mNtnU9AYiACOeBrTPE9f | Summary | 29 | 1.7.1.5.3 | 1.7.1.5.3 |  | 2026-07-16 17:00 | q | -7 |  | 2026-07-09 13:09
904 | 3809 | ukioB4iHiwrfEXpseTiK | Normal | 15 | 1.7.1.5.3.1 | 1.7.1.5.3.1 |  | 2026-06-25 17:00 | q | -1 |  | 2026-06-24 11:17
905 | 3810 | CJxWy7PnZPcI4EPHEeme | Normal | 9 | 1.7.1.5.3.2 | 1.7.1.5.3.2 |  | 2026-07-09 17:00 | q | -3 |  | 2026-07-06 08:31
906 | 3811 | wGtgxCT3lCK6u2EOL8xN | Normal | 5 | 1.7.1.5.3.3 | 1.7.1.5.3.3 |  | 2026-07-16 17:00 | q | -7 |  | 2026-07-09 13:09
907 | 3813 | sYeTNUsya13QYMbMJg21 | Normal | 25 | 1.7.1.5.7 | 1.7.1.5.7 |  | 2026-07-01 17:00 | q | -6 |  | 2026-06-25 11:39
908 | 3814 | c3HTuVFoRVefrW72mxSE | Normal | 3 | 1.7.1.5.8 | 1.7.1.5.8 |  | 2026-07-21 17:00 | q | -7 |  | 2026-07-14 11:37
909 | 3815 | nJJAkVwt0aHLNZMMtbkw | Normal | 3 | 1.7.1.5.9 | 1.7.1.5.9 |  | 2026-07-07 17:00 | q | -7 |  | 2026-06-30 09:04
910 | 3817 | LqjKPVRVNU7j1iAlkL3t | Normal | 2 | 1.7.1.5.10.1 | 1.7.1.5.10.1 |  | 2026-07-09 17:00 | q | -7 |  | 2026-07-02 09:34
911 | 3818 | Cmm1EfLtBPedDjXV8dAv | Normal | 5 | 1.7.1.5.10.2 | 1.7.1.5.10.2 |  | 2026-07-16 17:00 | q | -6 |  | 2026-07-10 08:37
912 | 3819 | FSVjbKFfUmqE2fpbGGPv | Normal | 3 | 1.7.1.5.10.3 | 1.7.1.5.10.3 |  | 2026-07-21 17:00 | q | -7 |  | 2026-07-14 11:37
913 | 3820 | FhKtXXrOwkDfPm4RFzRW | Normal | 10 | 1.7.1.5.10.4 | 1.7.1.5.10.4 |  | 2026-08-04 17:00 | q | -6 |  | 2026-07-29 13:04
914 | 6147 | BUcWclFVChflBnUDJ9UM | Normal | 40 | 1.7.1.5.4 | 1.7.1.5.4 |  | 2026-07-16 17:00 | q | -7 |  | 2026-07-09 13:09
915 | 6148 | V03eKqopjAXoUvRodLvQ | Normal | 13 | 1.7.1.5.6 | 1.7.1.5.6 |  | 2026-05-26 17:00 | q | -8 |  | 2026-05-18 13:19
916 | 4078 | ybbKeBChK3D60QzH8ONZ | Normal | 76 | 1.9.6.5 | 1.9.6.5 |  | 2028-03-27 12:00 | p | 204 |  | 2028-10-18 08:20
917 | 4129 | G6dPcJRrq5zqLYx4Vr0R | Summary | 475 | 1.9.6.10 | 1.9.6.10 |  | 2028-05-24 17:00 | p | 208 |  | 2028-12-19 10:21
918 | 4131 | 3WZTLr4e3INGux4LMgj0 | Summary | 146 | 1.9.6.10.2 | 1.9.6.10.2 |  | 2026-06-08 17:00 | q | -10 |  | 2026-05-29 13:54
919 | 5857 | g9TizAnooUcHoXglcd4n | Milestone | 0 | 1.9.6.10.2.1 | 1.9.6.10.2.1 |  | 2026-05-19 08:00 | q | -7 |  | 2026-05-11 16:36
920 | 5858 | 9N3N0HBhBeb82jbbU7Vx | Milestone | 0 | 1.9.6.10.2.2 | 1.9.6.10.2.2 |  | 2026-01-12 08:00 | q | -11 |  | 2025-12-31 08:02
921 | 5859 | RMhsXtyk4773BtipN2HO | Normal | 1 | 1.9.6.10.2.3 | 1.9.6.10.2.3 |  | 2026-01-12 17:00 | q | -12 |  | 2025-12-31 16:42
922 | 5860 | AMUT2hrMeOWSIoK5dO6S | Normal | 10 | 1.9.6.10.2.4 | 1.9.6.10.2.4 |  | 2026-01-27 17:00 | q | -12 |  | 2026-01-15 14:11
923 | 5861 | adMwYb1cwVT0ja23ZKPV | Normal | 10 | 1.9.6.10.2.5 | 1.9.6.10.2.5 |  | 2026-02-10 17:00 | q | -11 |  | 2026-01-30 08:46
924 | 5862 | rkVKH7eSVnkv5Rz0hIbo | Normal | 25 | 1.9.6.10.2.6 | 1.9.6.10.2.6 |  | 2026-03-18 17:00 | q | -6 |  | 2026-03-12 13:20
925 | 5863 | axx1H8vuWtNbWz6aJYpW | Normal | 20 | 1.9.6.10.2.7 | 1.9.6.10.2.7 |  | 2026-04-15 17:00 | q | -1 |  | 2026-04-14 11:36
926 | 5864 | ZuXAUp7kzm7PDgs0Clm4 | Normal | 20 | 1.9.6.10.2.8 | 1.9.6.10.2.8 |  | 2026-05-13 17:00 | q | -6 |  | 2026-05-07 09:43
927 | 5865 | pfx92tyIHO0nDV8Eg4vj | Normal | 3 | 1.9.6.10.2.9 | 1.9.6.10.2.9 |  | 2026-05-18 17:00 | q | -7 |  | 2026-05-11 16:36
928 | 5866 | qnFTkxNSvGIYOwHhqElS | Normal | 5 | 1.9.6.10.2.10 | 1.9.6.10.2.10 |  | 2026-05-26 17:00 | q | -8 |  | 2026-05-18 16:03
929 | 5867 | 6vMprMC9ZRYTg9c055cw | Normal | 3 | 1.9.6.10.2.11 | 1.9.6.10.2.11 |  | 2026-05-29 17:00 | q | -9 |  | 2026-05-20 15:16
930 | 5868 | qP5P60WlJm98gR28uFOw | Normal | 1 | 1.9.6.10.2.12 | 1.9.6.10.2.12 |  | 2026-06-01 17:00 | q | -11 |  | 2026-05-21 14:45
931 | 5869 | 5FBVtcv48JlyNzpes7ps | Normal | 5 | 1.9.6.10.2.13 | 1.9.6.10.2.13 |  | 2026-06-08 17:00 | q | -10 |  | 2026-05-29 13:54
932 | 5871 | owx5unCKcaLauhH4kWyj | Normal | 5 | 1.9.6.10.3.1 | 1.9.6.10.3.1 |  | 2026-06-15 17:00 | q | -7 |  | 2026-06-08 15:22
933 | 5872 | qImIYF1Y50rp0FNnsaoS | Normal | 10 | 1.9.6.10.3.2 | 1.9.6.10.3.2 |  | 2026-06-30 17:00 | q | -5 |  | 2026-06-25 15:11
934 | 5873 | FfFQqcMQ2fY5X0GvK0Xd | Normal | 20 | 1.9.6.10.3.3 | 1.9.6.10.3.3 |  | 2026-07-29 17:00 | p | 1 |  | 2026-07-31 14:59
935 | 5874 | fHTDjpnY2Gm0gViXPiAD | Normal | 2 | 1.9.6.10.3.6 | 1.9.6.10.3.6 |  | 2026-08-28 17:00 | p | 2 |  | 2026-08-31 11:22
936 | 5875 | TQZary26m4SvJkpuQUlv | Normal | 1 | 1.9.6.10.3.7 | 1.9.6.10.3.7 |  | 2026-08-31 17:00 | p | 0 |  | 2026-09-01 09:42
937 | 6624 | sVpbcWAee9M5eeft5sdO | Normal | 15 | 1.9.6.10.3.4 | 1.9.6.10.3.4 |  | 2026-08-19 17:00 | q | 0 |  | 2026-08-19 16:18
938 | 6625 | it5qGsWYKIf8fEL1a2TB | Normal | 5 | 1.9.6.10.3.5 | 1.9.6.10.3.5 |  | 2026-08-26 17:00 | p | 0 |  | 2026-08-27 13:57
939 | 5877 | 8uIO0L3CbsjXfYIL70ur | Summary | 162 | 1.9.6.10.4 | 1.9.6.10.4 |  | 2028-05-24 17:00 | p | 208 |  | 2028-12-19 10:21
940 | 5878 | eKJmpIIS7eePXp789pq5 | Summary | 60 | 1.9.6.10.4.1 | 1.9.6.10.4.1 |  | 2028-05-23 17:00 | p | 208 |  | 2028-12-18 10:45
941 | 5879 | CJrwB1y6NRnYYg7kpaRv | Summary | 30 | 1.9.6.10.4.1.1 | 1.9.6.10.4.1.1 |  | 2028-04-11 17:00 | p | 205 |  | 2028-11-03 09:57
942 | 5880 | z8rht75g90pc62Jd1j8e | Normal | 15 | 1.9.6.10.4.1.1.1 | 1.9.6.10.4.1.1.1 |  | 2028-03-21 17:00 | p | 203 |  | 2028-10-11 16:48
943 | 5881 | ZPPJV7wrbqyTumtl84NX | Normal | 15 | 1.9.6.10.4.1.1.2 | 1.9.6.10.4.1.1.2 |  | 2028-04-11 17:00 | p | 205 |  | 2028-11-03 09:57
944 | 5882 | PdfqDNDAaUS1Z9tfvPSB | Normal | 15 | 1.9.6.10.4.1.2 | 1.9.6.10.4.1.2 |  | 2028-05-02 17:00 | p | 204 |  | 2028-11-23 10:55
945 | 5883 | 3J3dFKPf8v7HKW1lSal4 | Normal | 15 | 1.9.6.10.4.1.3 | 1.9.6.10.4.1.3 |  | 2028-05-23 17:00 | p | 208 |  | 2028-12-18 10:45
946 | 5884 | J3ZDJxR9DKKi4JquRb3Q | Summary | 20 | 1.9.6.10.4.2 | 1.9.6.10.4.2 |  | 2028-05-08 17:00 | p | 209 |  | 2028-12-04 08:52
947 | 5885 | p0UOLQYQkw5raD9Hf7AI | Normal | 5 | 1.9.6.10.4.2.1 | 1.9.6.10.4.2.1 |  | 2028-04-17 17:00 | p | 205 |  | 2028-11-09 13:01
948 | 5886 | mfBVa7VrtMT45ZcRp9ur | Normal | 5 | 1.9.6.10.4.2.2 | 1.9.6.10.4.2.2 |  | 2028-04-24 17:00 | p | 205 |  | 2028-11-16 13:33
949 | 5887 | xjL6okqGZuFc1ChaUzA0 | Normal | 5 | 1.9.6.10.4.2.3 | 1.9.6.10.4.2.3 |  | 2028-05-01 17:00 | p | 206 |  | 2028-11-24 16:07
950 | 5888 | 0NLdruhvCSk61FiIPSJA | Normal | 5 | 1.9.6.10.4.2.4 | 1.9.6.10.4.2.4 |  | 2028-05-08 17:00 | p | 209 |  | 2028-12-04 08:52
951 | 5889 | vcqfMiWzgD0sBRK91JrP | Normal | 3 | 1.9.6.10.4.3 | 1.9.6.10.4.3 |  | 2028-05-11 17:00 | p | 208 |  | 2028-12-06 16:21
952 | 5890 | r7iAplKyl5D3dW7yC0Jk | Normal | 5 | 1.9.6.10.4.4 | 1.9.6.10.4.4 |  | 2028-05-18 17:00 | p | 208 |  | 2028-12-13 16:15
953 | 5891 | 55B0pL3dU2GPDxU6IZLg | Normal | 1 | 1.9.6.10.4.5 | 1.9.6.10.4.5 |  | 2028-05-19 17:00 | p | 208 |  | 2028-12-14 14:13
954 | 5892 | zyPP7s8BBmPhydQ5fB2g | Normal | 1 | 1.9.6.10.4.8 | 1.9.6.10.4.8 |  | 2028-05-24 17:00 | p | 208 |  | 2028-12-19 10:21
955 | 5893 | JSBvauC3wpirasqwMrC9 | Normal | 1 | 1.9.6.10.4.6 | 1.9.6.10.4.6 |  | 2028-05-22 17:00 | p | 206 |  | 2028-12-15 14:17
956 | 5894 | AO4SgiivKvvxQJupi2GS | Normal | 1 | 1.9.6.10.4.7 | 1.9.6.10.4.7 |  | 2028-05-23 17:00 | p | 208 |  | 2028-12-18 10:45
957 | 4134 | 86JmjjOtZxj7XQRp3CQF | Summary | 466 | 1.9.6.11 | 1.9.6.11 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
958 | 4135 | 0voiyAtBe9AzaXfs8cVF | Summary | 322 | 1.9.6.11.1 | 1.9.6.11.1 |  | 2028-07-24 17:00 | p | 202 |  | 2029-02-12 08:15
959 | 4136 | bllhlvXmXgF1yFG9Nwfe | Normal | 16 | 1.9.6.11.1.1 | 1.9.6.11.1.1 |  | 2028-06-02 17:00 | p | 206 |  | 2028-12-26 15:49
960 | 4137 | rnRXxVdKdR5NUADIB31n | Normal | 1 | 1.9.6.11.1.2 | 1.9.6.11.1.2 |  | 2028-06-05 17:00 | p | 205 |  | 2028-12-28 08:04
961 | 4138 | 75WgU7H7MCC8DDgOcnsD | Normal | 30 | 1.9.6.11.1.3 | 1.9.6.11.1.3 |  | 2028-07-17 17:00 | p | 202 |  | 2029-02-05 14:18
962 | 4139 | 9SKpfzivi43NDDuHUq0B | Normal | 5 | 1.9.6.11.1.4 | 1.9.6.11.1.4 |  | 2028-07-24 17:00 | p | 202 |  | 2029-02-12 08:15
963 | 4140 | Lk7gef35zB3WaxM8Xyxe | Summary | 48 | 1.9.6.11.2 | 1.9.6.11.2 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
964 | 4141 | HGo5Ep3pqhcsiM5K4QjA | Summary | 23 | 1.9.6.11.2.1 | 1.9.6.11.2.1 |  | 2028-08-24 17:00 | p | 203 |  | 2029-03-16 16:35
965 | 4142 | VTqJrDLpWuaSlvRQajcM | Normal | 12 | 1.9.6.11.2.1.1 | 1.9.6.11.2.1.1 |  | 2028-08-09 17:00 | p | 203 |  | 2029-03-01 11:09
966 | 4143 | UwGhtpl5Mnq9WQrcrXRR | Normal | 11 | 1.9.6.11.2.1.2 | 1.9.6.11.2.1.2 |  | 2028-08-24 17:00 | p | 203 |  | 2029-03-16 16:35
967 | 4144 | zaFQ6K5wegGvKt6DGuoz | Summary | 25 | 1.9.6.11.2.2 | 1.9.6.11.2.2 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
968 | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Normal | 10 | 1.9.6.11.2.2.1 | 1.9.6.11.2.2.1 |  | 2028-09-07 17:00 | p | 203 |  | 2029-03-30 08:56
969 | 4146 | rTeXGnIwGPt6ES3ynSHq | Normal | 5 | 1.9.6.11.2.2.2 | 1.9.6.11.2.2.2 |  | 2028-09-14 17:00 | p | 202 |  | 2029-04-05 10:38
970 | 4147 | hQaW5HIstT5bbsPEBxyQ | Normal | 10 | 1.9.6.11.2.2.3 | 1.9.6.11.2.2.3 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
971 | 5753 | ZptYdARXANY2IOcoHhB1 | Summary | 78 | 1.9.6.1 | 1.9.6.1 |  | 2026-09-01 17:00 | p | 392 |  | 2027-09-28 17:00
972 | 5998 | aRBXPvE6pbVbcbhlDtu4 | Summary | 47 | 1.9.6.1.7 | 1.9.6.1.7 |  | 2026-05-18 17:00 | q | -7 |  | 2026-05-11 16:36
973 | 5999 | hTF24jclc5ogfsrVWXZd | Normal | 40 | 1.9.6.1.7.1 | 1.9.6.1.7.1 |  | 2026-05-07 17:00 | q | -6 |  | 2026-05-01 08:41
974 | 6000 | dvNXA0SZWky1SGhKE7td | Normal | 5 | 1.9.6.1.7.2 | 1.9.6.1.7.2 |  | 2026-05-14 17:00 | q | -6 |  | 2026-05-08 09:31
975 | 6001 | z8HVZ6SyP3QpkaT54VAm | Normal | 1 | 1.9.6.1.7.3 | 1.9.6.1.7.3 |  | 2026-05-15 17:00 | q | -4 |  | 2026-05-11 09:25
976 | 6002 | rmlzSal3Nkh8gQGzhscw | Normal | 1 | 1.9.6.1.7.4 | 1.9.6.1.7.4 |  | 2026-05-18 17:00 | q | -7 |  | 2026-05-11 16:36
977 | 6004 | xOhJcEwgSz1TAvNHU4tB | Normal | 40 | 1.9.6.1.8.1 | 1.9.6.1.8.1 |  | 2026-08-21 17:00 | p | 2 |  | 2026-08-24 09:41
978 | 6005 | gw3ZFSF3nzLqLqYBiqR7 | Normal | 5 | 1.9.6.1.8.2 | 1.9.6.1.8.2 |  | 2026-08-28 17:00 | p | 2 |  | 2026-08-31 09:12
979 | 6006 | HEKaqqmbwSXnCRXB6fED | Normal | 1 | 1.9.6.1.8.3 | 1.9.6.1.8.3 |  | 2026-08-31 17:00 | p | 0 |  | 2026-09-01 08:42
980 | 6008 | Ph5VFx7Ghit4AwZEFBXT | Summary | 50 | 1.9.6.1.6 | 1.9.6.1.6 |  | 2026-05-15 17:00 | q | -4 |  | 2026-05-11 09:25
981 | 6009 | NVgukc0KZBShUa0wIlyx | Normal | 30 | 1.9.6.1.6.1 | 1.9.6.1.6.1 |  | 2026-03-12 17:00 | q | -7 |  | 2026-03-05 11:47
982 | 6010 | tIYqVtlT4yOF2YQ2FRYY | Normal | 10 | 1.9.6.1.6.2 | 1.9.6.1.6.2 |  | 2026-05-01 17:00 | q | -3 |  | 2026-04-28 11:50
983 | 6011 | 9Y3pHbqvwzl2AwHfvrBG | Normal | 5 | 1.9.6.1.6.3 | 1.9.6.1.6.3 |  | 2026-05-08 17:00 | q | -3 |  | 2026-05-05 11:03
984 | 6012 | Z1jpWQx4GyFcVoEVg0i0 | Normal | 5 | 1.9.6.1.6.4 | 1.9.6.1.6.4 |  | 2026-05-15 17:00 | q | -4 |  | 2026-05-11 09:25
985 | 6013 | y2dxMv99iLhGOXikZGuK | Summary | 34 | 1.9.6.1.5 | 1.9.6.1.5 |  | 2026-05-15 17:00 | q | -4 |  | 2026-05-11 09:25
986 | 6014 | hYHiAVYfHXdDTdWEk9J8 | Normal | 15 | 1.9.6.1.5.1 | 1.9.6.1.5.1 |  | 2026-01-28 17:00 | q | -12 |  | 2026-01-16 15:48
987 | 6015 | MXdxqc8Y6tIByFeEqluF | Normal | 10 | 1.9.6.1.5.2 | 1.9.6.1.5.2 |  | 2026-05-04 17:00 | q | -5 |  | 2026-04-29 09:01
988 | 6016 | gwhB80Lv7eu4PoYwev8o | Normal | 5 | 1.9.6.1.5.3 | 1.9.6.1.5.3 |  | 2026-05-11 17:00 | q | -7 |  | 2026-05-04 16:58
989 | 6017 | VCyTBN0y7V3erCRNMvm4 | Normal | 4 | 1.9.6.1.5.4 | 1.9.6.1.5.4 |  | 2026-05-15 17:00 | q | -4 |  | 2026-05-11 09:25
990 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | 2026-01-28 17:00 | p | 608 |  | 2027-09-28 17:00
991 | 6957 | ar01N24L63iczVEh1mVo | Summary | 24 | 1.9.6.1.4 | 1.9.6.1.4 |  | 2026-05-11 17:00 | q | -7 |  | 2026-05-04 16:58
992 | 6958 | 6Ul4V6iAcnpVqewOp14Y | Normal | 4 | 1.9.6.1.4.1 | 1.9.6.1.4.1 |  | 2025-12-29 17:00 | q | -10 |  | 2025-12-19 14:52
993 | 6959 | w9Vvv79ftt4PUqInNFyD | Normal | 5 | 1.9.6.1.4.2 | 1.9.6.1.4.2 |  | 2026-01-06 17:00 | q | -11 |  | 2025-12-26 16:43
994 | 6960 | xIgpHAurEQ244gHa2T5q | Normal | 5 | 1.9.6.1.4.3 | 1.9.6.1.4.3 |  | 2026-04-27 17:00 | q | -6 |  | 2026-04-21 13:53
995 | 6961 | NOksVV7sTymsgwMrnh6x | Normal | 10 | 1.9.6.1.4.4 | 1.9.6.1.4.4 |  | 2026-05-11 17:00 | q | -7 |  | 2026-05-04 16:58
996 | 5762 | BY50RWHTB6QfyvgvJksd | Summary | 36 | 1.9.6.9 | 1.9.6.9 |  | 2027-12-30 12:00 | p | 203 |  | 2028-07-20 13:41
997 | 4074 | H2vE7zxiBRw3YTdo2zSW | Normal | 35 | 1.9.6.9.2 | 1.9.6.9.2 |  | 2027-12-29 12:00 | p | 202 |  | 2028-07-19 11:32
998 | 4075 | dGbNHsOLhslKk8CjhyjE | Normal | 1 | 1.9.6.9.3 | 1.9.6.9.3 |  | 2027-12-30 12:00 | p | 203 |  | 2028-07-20 13:41
999 | 6424 | xU9ngPKik2IYPonksYTK | Summary | 24 | 1.7.1.8 | 1.7.1.8 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:06
1000 | 6427 | NeAxFJaqSLize8VPNJ6N | Normal | 1 | 1.7.1.8.3 | 1.7.1.8.3 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:06
1001 | 6296 | SlR21lje1Tex9DLMlAM1 | Summary | 222 | 1.9.8 | 1.9.8 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
1002 | 4192 | vUDAXlHZqbmK6WAsX9hH | Summary | 139 | 1.9.8.1 | 1.9.8.1 |  | 2028-03-27 12:00 | p | 204 |  | 2028-10-18 08:20
1003 | 4196 | 2ZwOzHGH45ywtPvfASSG | Normal | 5 | 1.9.8.1.5 | 1.9.8.1.5 |  | 2028-03-27 12:00 | p | 204 |  | 2028-10-18 08:20
1004 | 4197 | 4xVk2zrTd9sJnt9BJFir | Summary | 36 | 1.9.8.1.6 | 1.9.8.1.6 |  | 2028-03-27 12:00 | p | 204 |  | 2028-10-18 08:20
1005 | 5974 | cJ7VeFZezCBnvYlHxCmb | Normal | 1 | 1.9.8.1.6.7 | 1.9.8.1.6.7 |  | 2028-03-27 12:00 | p | 204 |  | 2028-10-18 08:20
1006 | 4198 | k6X8NWhjfeQOPZdDpmna | Normal | 20 | 1.9.8.1.9 | 1.9.8.1.9 |  | 2025-08-19 17:00 | p | 8 |  | 2025-08-28 15:08
1007 | 5985 | AUKn3E7aViOsULw8HdKV | Normal | 131 | 1.9.8.1.12 | 1.9.8.1.12 |  | 2028-03-20 12:00 | p | 203 |  | 2028-10-09 15:52
1008 | 4222 | uotgqiCu1xVBvHdpBC3E | Summary | 97 | 1.9.8.2 | 1.9.8.2 |  | 2027-12-30 12:00 | p | 203 |  | 2028-07-20 13:41
1009 | 4231 | 8h0WH2qeIC7tfvcerCPa | Normal | 1 | 1.9.8.2.3 | 1.9.8.2.3 |  | 2027-08-25 12:00 | p | 245 |  | 2028-04-26 15:31
1010 | 4235 | QiaATNQSPId7svzcuO8r | Normal | 91 | 1.9.8.2.7 | 1.9.8.2.7 |  | 2027-12-30 12:00 | p | 203 |  | 2028-07-20 13:41
1011 | 4238 | ReJqSs3gutB053iVY5c7 | Summary | 76 | 1.9.8.4 | 1.9.8.4 |  | 2026-08-28 17:00 | p | 2 |  | 2026-08-31 08:05
1012 | 4242 | RIVyyga7UReDeuixs5m9 | Normal | 66 | 1.9.8.4.4 | 1.9.8.4.4 |  | 2026-08-14 17:00 | p | 3 |  | 2026-08-18 09:37
1013 | 4243 | LpPx7AWOh1V8dzWVWc6j | Normal | 1 | 1.9.8.4.5 | 1.9.8.4.5 |  | 2026-08-14 17:00 | p | 3 |  | 2026-08-18 09:37
1014 | 4246 | ANAzXnUTz1PCb3xsov4Y | Normal | 10 | 1.9.8.4.7 | 1.9.8.4.7 |  | 2026-08-28 17:00 | p | 2 |  | 2026-08-31 08:05
1015 | 4248 | E1RJwJWM8qrsKP3o7Toy | Normal | 1 | 1.9.8.7 | 1.9.8.7 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 16:29
1016 | 4251 | IBg36OMMKUy3vwEnRNF0 | Normal | 1 | 1.9.8.6 | 1.9.8.6 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 16:29
1017 | 4255 | TAfq40Sin0H6Q2YT0OS5 | Milestone | 0 | 1.9.8.3 | 1.9.8.3 |  | 2027-12-30 13:00 | p | 203 |  | 2028-07-20 13:41
1018 | 4258 | GzQkXlTiYJMdE6nBDVeb | Normal | 6 | 1.9.8.10.1 | 1.9.8.10.1 |  | 2026-05-13 17:00 | q | -6 |  | 2026-05-07 15:10
1019 | 6187 | kIPGiItVAbHq2ks8DK41 | Normal | 5 | 1.9.8.10.6 | 1.9.8.10.6 |  | 2026-07-17 17:00 | q | -4 |  | 2026-07-13 15:15
1020 | 6430 | IYyY3jK4t9QuDyuxqyQ5 | Normal | 15 | 1.9.8.10.2 | 1.9.8.10.2 |  | 2026-06-04 17:00 | q | -8 |  | 2026-05-27 11:05
1021 | 6431 | mXx66gQ5BZWpD3idmZgM | Normal | 10 | 1.9.8.10.3 | 1.9.8.10.3 |  | 2026-06-18 17:00 | q | -6 |  | 2026-06-12 10:28
1022 | 6432 | vMoeJo3Rc30lMwFim6rn | Normal | 10 | 1.9.8.10.4 | 1.9.8.10.4 |  | 2026-07-06 17:00 | q | -6 |  | 2026-06-30 10:26
1023 | 6433 | zONKYXhH5yZJE26xvIWD | Normal | 4 | 1.9.8.10.5 | 1.9.8.10.5 |  | 2026-07-10 17:00 | q | -3 |  | 2026-07-07 08:38
1024 | 6083 | 3dsblDK1X9ztc27EZU3v | Normal | 1 | 1.9.8.5 | 1.9.8.5 |  | 2028-05-24 17:00 | p | 208 |  | 2028-12-19 10:21
1025 | 6084 | deZM0xh115wln716GUoI | Normal | 1 | 1.9.8.9 | 1.9.8.9 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
1026 | 7321 | CTokiQfH6gyOyeZJGrxP | Normal | 1 | 1.7.9.11 | 1.7.9.11 |  | 2026-08-31 17:00 | q | 0 |  | 2026-08-31 16:29
1027 | 6314 | PaZTrKFuMaJQzXHDclW5 | Summary | 34 | 1.9.2 | 1.9.2 |  | 2028-02-18 12:00 | p | 207 |  | 2028-09-13 10:12
1028 | 5666 | lc2LPCzbTjVw9vZ8eS89 | Summary | 23 | 1.9.2.2 | 1.9.2.2 |  | 2027-12-21 12:00 | p | 204 |  | 2028-07-12 16:57
1029 | 5667 | chBvra0KGhqU3lfHBAI4 | Summary | 23 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2027-12-21 12:00 | p | 204 |  | 2028-07-12 16:57
1030 | 5669 | bBSx7g3AuM8uxZcIYlIi | Normal | 20 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2027-12-21 12:00 | p | 204 |  | 2028-07-12 16:57
1031 | 5672 | 2GDxhVAL0LbO4lfSMjXo | Summary | 47 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2028-02-18 12:00 | p | 207 |  | 2028-09-13 10:12
1032 | 5690 | jLB7gq1wR8egZrMIoAc7 | Summary | 24 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2028-01-24 13:00 | p | 202 |  | 2028-08-14 09:46
1033 | 5691 | glUuWw43f2R9t2hl6VHO | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2028-01-04 13:00 | p | 201 |  | 2028-07-24 10:47
1034 | 5692 | KeXnvnZRx0KMyut3yw5s | Milestone | 0 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2028-01-04 13:00 | p | 201 |  | 2028-07-24 10:47
1035 | 5693 | VdKRFLdSc60knizSqFXc | Normal | 14 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2028-01-24 13:00 | p | 202 |  | 2028-08-14 09:46
1036 | 5694 | Gb0taOZcQ8l0cdHliY6j | Normal | 10 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2028-02-07 13:00 | p | 204 |  | 2028-08-29 16:20
1037 | 5695 | ePp2idADlztrdEpItyCc | Milestone | 0 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2028-02-07 13:00 | p | 204 |  | 2028-08-29 16:20
1038 | 5696 | npE0RnxADwI7cDPG1fDa | Normal | 4 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2028-02-11 13:00 | p | 206 |  | 2028-09-05 11:04
1039 | 5697 | 4nIBzBv3LSP60HeOLv0f | Normal | 5 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2028-02-18 12:00 | p | 207 |  | 2028-09-13 10:12
1040 | 6315 | 2iW64uJmzViIcLEo0dMn | Summary | 181 | 1.9.5 | 1.9.5 |  | 2028-01-19 12:00 | p | 204 |  | 2028-08-11 09:38
1041 | 5532 | NHN4dwEEPEqCDqA4Rwlr | Summary | 74 | 1.9.5.1 | 1.9.5.1 |  | 2027-11-05 12:00 | p | 201 |  | 2028-05-25 09:07
1042 | 5533 | g1oQNBzKk6OrBukgGH7R | Normal | 40 | 1.9.5.1.3 | 1.9.5.1.3 |  | 2027-08-02 12:00 | q | -825 |  | 2025-04-28 17:00
1043 | 5535 | XVk7S0ldLHQUWflKhMBn | Normal | 11 | 1.9.5.1.2 | 1.9.5.1.2 |  | 2027-11-05 12:00 | p | 201 |  | 2028-05-25 09:07
1044 | 5536 | cYU0DBZylLxVRoLEp7Bc | Normal | 40 | 1.9.5.1.4 | 1.9.5.1.4 |  | 2027-07-05 12:00 | p | 212 |  | 2028-02-03 11:00
1045 | 5537 | 9xVQhmyTVkChMoMOy91g | Summary | 193 | 1.9.5.2 | 1.9.5.2 |  | 2027-12-09 12:00 | p | 208 |  | 2028-07-05 08:13
1046 | 5539 | kRsO3PSMDsMxji3dmdNc | Normal | 5 | 1.9.5.2.2 | 1.9.5.2.2 |  | 2025-12-24 17:00 | p | 616 |  | 2027-09-02 13:26
1047 | 5540 | GKx3XnA1BSbhTsgdKbqP | Normal | 14 | 1.9.5.2.8 | 1.9.5.2.8 |  | 2026-04-20 17:00 | q | -6 |  | 2026-04-14 15:20
1048 | 5541 | LhqIvyBzzdwllIHwrPz2 | Normal | 5 | 1.9.5.2.7 | 1.9.5.2.7 |  | 2025-12-29 17:00 | q | -10 |  | 2025-12-19 14:52
1049 | 5542 | 4ivItsonCrTGke19i41Z | Normal | 15 | 1.9.5.2.6 | 1.9.5.2.6 |  | 2025-12-22 17:00 | q | -6 |  | 2025-12-16 10:16
1050 | 5543 | XaHBDo6QUBfyTg5ESk7j | Normal | 15 | 1.9.5.2.9 | 1.9.5.2.9 |  | 2026-04-27 17:00 | q | -6 |  | 2026-04-21 13:53
1051 | 5544 | cIc3ARzcdrbXv6maHllr | Summary | 129 | 1.9.5.2.13 | 1.9.5.2.13 |  | 2027-11-03 12:00 | p | 201 |  | 2028-05-22 16:42
1052 | 5545 | 7UVU8IboY6NG7sqZCrUC | Normal | 7 | 1.9.5.2.13.2 | 1.9.5.2.13.2 |  | 2027-06-16 12:00 | p | 196 |  | 2027-12-29 16:29
1053 | 5546 | Shs5wuYOFSkTF1YslX8w | Normal | 6 | 1.9.5.2.13.5 | 1.9.5.2.13.5 |  | 2027-07-02 17:00 | p | 199 |  | 2028-01-18 09:40
1054 | 5547 | KglXvc5QwlHEboIvY96Q | Normal | 4 | 1.9.5.2.13.8 | 1.9.5.2.13.8 |  | 2027-07-28 17:00 | p | 197 |  | 2028-02-11 11:08
1055 | 5548 | Zfzda0CfmpiN8ZL93G3t | Normal | 5 | 1.9.5.2.13.9 | 1.9.5.2.13.9 |  | 2027-08-04 17:00 | p | 200 |  | 2028-02-21 11:12
1056 | 5549 | PgYJem7PJFdGgV04ojeL | Normal | 1 | 1.4.17 | 1.4.17 |  | 2027-08-05 17:00 | p | 200 |  | 2028-02-22 14:55
1057 | 5556 | fOMVaiOa0jnHOJyDUdVQ | Normal | 25 | 1.9.5.2.13.11 | 1.9.5.2.13.11 |  | 2027-11-03 12:00 | p | 201 |  | 2028-05-22 16:42
1058 | 5730 | ypyrsmMFJqJ9aPla6UhQ | Normal | 4 | 1.9.5.2.13.3 | 1.9.5.2.13.3 |  | 2027-06-22 12:00 | p | 196 |  | 2028-01-04 15:46
1059 | 5731 | uQF6Ff0bc2cqy3b37ZQc | Normal | 1 | 1.9.5.2.13.4 | 1.9.5.2.13.4 |  | 2027-06-23 12:00 | p | 196 |  | 2028-01-05 14:48
1060 | 5732 | OQKwpwUgImWCC2Fp5G0Q | Normal | 7 | 1.9.5.2.13.6 | 1.9.5.2.13.6 |  | 2027-07-13 17:00 | p | 197 |  | 2028-01-27 10:40
1061 | 5733 | wyOxVAS94HubPKo2yHJm | Normal | 7 | 1.9.5.2.13.7 | 1.9.5.2.13.7 |  | 2027-07-22 17:00 | p | 199 |  | 2028-02-07 11:08
1062 | 7000 | yP1oDcnUQTy3g68ZLgu0 | Normal | 8 | 1.9.5.2.13.1 | 1.9.5.2.13.1 |  | 2027-06-07 12:00 | p | 197 |  | 2027-12-21 13:16
1063 | 5557 | U376LwOjKfNZoVLUlmMD | Summary | 113 | 1.9.5.2.12 | 1.9.5.2.12 |  | 2027-09-29 12:00 | p | 200 |  | 2028-04-17 10:27
1064 | 5558 | RXAxJx3BHWNVdWFPfZ2a | Normal | 13 | 1.9.5.2.12.2 | 1.9.5.2.12.2 |  | 2027-05-27 12:00 | p | 195 |  | 2027-12-09 10:24
1065 | 5559 | jJoy8dUJMWD3ZuNw52D0 | Normal | 8 | 1.9.5.2.12.5 | 1.9.5.2.12.5 |  | 2027-06-21 12:00 | p | 199 |  | 2028-01-06 13:25
1066 | 5560 | wu3sL1wqoiodUr5mG52N | Normal | 4 | 1.9.5.2.12.8 | 1.9.5.2.12.8 |  | 2027-07-15 12:00 | p | 201 |  | 2028-02-02 11:12
1067 | 5561 | Vb2zzMF18WNANxlCzGiz | Normal | 5 | 1.9.5.2.12.9 | 1.9.5.2.12.9 |  | 2027-07-22 12:00 | p | 201 |  | 2028-02-08 14:09
1068 | 5562 | vp7j6GBYm2dAMLvxEFuE | Normal | 1 | 1.4.20 | 1.4.20 |  | 2027-07-23 12:00 | p | 201 |  | 2028-02-09 14:40
1069 | 5569 | 35aiC9HLOSrIl2OBwDvd | Normal | 25 | 1.9.5.2.12.11 | 1.9.5.2.12.11 |  | 2027-09-29 12:00 | p | 200 |  | 2028-04-17 10:27
1070 | 5734 | iq9bjqBZvH9Bj6912271 | Normal | 6 | 1.9.5.2.12.3 | 1.9.5.2.12.3 |  | 2027-06-04 12:00 | p | 199 |  | 2027-12-20 13:06
1071 | 5735 | Z8zFgfwvHK2hwW2AW8Qa | Normal | 1 | 1.9.5.2.12.4 | 1.9.5.2.12.4 |  | 2027-06-07 12:00 | p | 197 |  | 2027-12-21 13:16
1072 | 5736 | QgUmTWGvxjzq3xqrWPJK | Normal | 7 | 1.9.5.2.12.6 | 1.9.5.2.12.6 |  | 2027-06-30 12:00 | p | 200 |  | 2028-01-17 09:16
1073 | 5737 | iDzIA8f8DQgg2wVNkaUu | Normal | 7 | 1.9.5.2.12.7 | 1.9.5.2.12.7 |  | 2027-07-09 12:00 | p | 201 |  | 2028-01-27 11:44
1074 | 7001 | WpRQh8HvPfyDha8FH5FR | Normal | 9 | 1.9.5.2.12.1 | 1.9.5.2.12.1 |  | 2027-05-10 12:00 | p | 192 |  | 2027-11-19 08:41
1075 | 5570 | MuDwSgsBJjDxwFkSMWYJ | Summary | 116 | 1.9.5.2.11 | 1.9.5.2.11 |  | 2027-09-29 12:00 | p | 200 |  | 2028-04-17 10:27
1076 | 5571 | lfRAbO0c5jl7NaC6s7pm | Normal | 21 | 1.9.5.2.11.2 | 1.9.5.2.11.2 |  | 2027-04-30 12:00 | p | 194 |  | 2027-11-11 09:42
1077 | 5572 | jk3Vm36iIGViuk9dpLfQ | Normal | 8 | 1.9.5.2.11.5 | 1.9.5.2.11.5 |  | 2027-05-20 12:00 | p | 201 |  | 2027-12-07 13:10
1078 | 5573 | u3MfiduPa05JsS2ly7WD | Normal | 4 | 1.9.5.2.11.8 | 1.9.5.2.11.8 |  | 2027-06-29 12:00 | p | 199 |  | 2028-01-14 13:50
1079 | 5574 | 3iKE3riinMPRUpVpTfwx | Normal | 5 | 1.9.5.2.11.9 | 1.9.5.2.11.9 |  | 2027-07-08 17:00 | p | 202 |  | 2028-01-27 14:01
1080 | 5575 | 48yotl4pDzxbk5y0VDbK | Normal | 1 | 1.4.23 | 1.4.23 |  | 2027-07-09 17:00 | p | 202 |  | 2028-01-28 14:32
1081 | 5582 | 6tLu8emqwotxTkeBbEpy | Normal | 26 | 1.9.5.2.11.11 | 1.9.5.2.11.11 |  | 2027-09-29 12:00 | p | 200 |  | 2028-04-17 10:27
1082 | 5738 | ME2oX9BwgLu5cggaunhg | Normal | 5 | 1.9.5.2.11.3 | 1.9.5.2.11.3 |  | 2027-05-07 12:00 | p | 194 |  | 2027-11-18 09:40
1083 | 5739 | IivOSmNLtmlF9JKFLUrl | Normal | 1 | 1.9.5.2.11.4 | 1.9.5.2.11.4 |  | 2027-05-10 12:00 | p | 192 |  | 2027-11-19 08:41
1084 | 5740 | eRxCjL3dV2CpHvAG84r7 | Normal | 12 | 1.9.5.2.11.6 | 1.9.5.2.11.6 |  | 2027-06-07 12:00 | p | 198 |  | 2027-12-23 10:40
1085 | 5741 | 8Y4jq7dOt4lN4NYBT6r1 | Normal | 12 | 1.9.5.2.11.7 | 1.9.5.2.11.7 |  | 2027-06-23 12:00 | p | 200 |  | 2028-01-10 11:07
1086 | 6998 | CyWehBzIvIWKBi1qju4z | Normal | 15 | 1.9.5.2.11.1 | 1.9.5.2.11.1 |  | 2027-04-01 12:00 | p | 193 |  | 2027-10-12 11:58
1087 | 5583 | gkFBoXdv1oJb2jtBcO5M | Summary | 147 | 1.9.5.2.14 | 1.9.5.2.14 |  | 2027-12-09 12:00 | p | 208 |  | 2028-07-05 08:13
1088 | 5584 | 6WMzJdzS7tY0wFFuXnrc | Normal | 7 | 1.9.5.2.14.2 | 1.9.5.2.14.2 |  | 2027-07-02 12:00 | p | 196 |  | 2028-01-14 16:57
1089 | 5585 | KljMWvDEBGSuBTW4zQhZ | Normal | 7 | 1.9.5.2.14.5 | 1.9.5.2.14.5 |  | 2027-07-20 12:00 | p | 197 |  | 2028-02-02 15:52
1090 | 5586 | Z3ZWpIsgJCSKUX161hV0 | Normal | 4 | 1.9.5.2.14.8 | 1.9.5.2.14.8 |  | 2027-08-11 12:00 | p | 196 |  | 2028-02-24 11:24
1091 | 5587 | OXOUsYDejGVlgqn4Z1vl | Normal | 5 | 1.9.5.2.14.9 | 1.9.5.2.14.9 |  | 2027-08-18 12:00 | p | 198 |  | 2028-03-03 15:26
1092 | 5588 | MFjHKzinVVI0Ndx8qx0B | Normal | 1 | 1.4.26 | 1.4.26 |  | 2027-08-19 12:00 | p | 200 |  | 2028-03-06 16:52
1093 | 5595 | REFTk0AP9RBTibJWVhuH | Normal | 26 | 1.9.5.2.14.11 | 1.9.5.2.14.11 |  | 2027-12-09 12:00 | p | 208 |  | 2028-07-05 08:13
1094 | 5742 | 88bEv4EMiOL2y8w1ttIM | Normal | 4 | 1.9.5.2.14.3 | 1.9.5.2.14.3 |  | 2027-07-08 12:00 | p | 197 |  | 2028-01-21 16:37
1095 | 5743 | 0Uz4krHDVCdAlMd5aRwh | Normal | 1 | 1.9.5.2.14.4 | 1.9.5.2.14.4 |  | 2027-07-09 12:00 | p | 199 |  | 2028-01-25 09:57
1096 | 5744 | cSBfnbrbVLLFYTMEfBKA | Normal | 6 | 1.9.5.2.14.6 | 1.9.5.2.14.6 |  | 2027-07-28 12:00 | p | 200 |  | 2028-02-14 09:20
1097 | 5745 | ZY99Y6JX4jBylnfeedvo | Normal | 6 | 1.9.5.2.14.7 | 1.9.5.2.14.7 |  | 2027-08-05 12:00 | p | 197 |  | 2028-02-18 14:37
1098 | 6999 | AnycnugTW971av3hMZXE | Normal | 8 | 1.9.5.2.14.1 | 1.9.5.2.14.1 |  | 2027-06-23 12:00 | p | 196 |  | 2028-01-05 14:48
1099 | 6446 | XvbStahAymwCoqNIbMJG | Summary | 32 | 1.9.5.2.4 | 1.9.5.2.4 |  | 2027-07-20 12:00 | p | 197 |  | 2028-02-02 15:52
1100 | 6532 | 15e7xcLR1b1jSikaz0S2 | Normal | 32 | 1.9.5.2.4.2 | 1.9.5.2.4.2 |  | 2027-06-21 12:00 | p | 199 |  | 2028-01-06 13:25
1101 | 6533 | b0mutjzKj8FRw4zkbb8K | Normal | 32 | 1.9.5.2.4.1 | 1.9.5.2.4.1 |  | 2027-05-20 12:00 | p | 201 |  | 2027-12-07 13:10
1102 | 6534 | 8Gl2bk4Fxxo2fsClDJqG | Normal | 32 | 1.9.5.2.4.3 | 1.9.5.2.4.3 |  | 2027-07-02 17:00 | p | 199 |  | 2028-01-18 09:40
1103 | 6535 | dWze9AnK8NrEMD9LOEyU | Normal | 32 | 1.9.5.2.4.4 | 1.9.5.2.4.4 |  | 2027-07-20 12:00 | p | 197 |  | 2028-02-02 15:52
1104 | 6528 | LROLnQke0gWnMONa67YB | Summary | 50 | 1.9.5.2.5 | 1.9.5.2.5 |  | 2027-04-30 12:00 | p | 194 |  | 2027-11-11 09:42
1105 | 6531 | iX155TL3hNg9Ca4Bsb4A | Normal | 35 | 1.9.5.2.5.2 | 1.9.5.2.5.2 |  | 2027-04-30 12:00 | p | 194 |  | 2027-11-11 09:42
1106 | 6955 | CPACk87DS0kpO7pXcdwS | Normal | 10 | 1.9.5.2.10 | 1.9.5.2.10 |  | 2026-01-09 17:00 | q | -9 |  | 2025-12-31 08:02
1107 | 6997 | MBGoTUikAECGvIHYk1uV | Normal | 24 | 1.9.5.2.3 | 1.9.5.2.3 |  | 2027-04-01 12:00 | p | 193 |  | 2027-10-12 11:58
1108 | 5596 | upn4QoZvaKBmBMoyhnq5 | Summary | 90 | 1.9.5.3 | 1.9.5.3 |  | 2028-01-19 12:00 | p | 204 |  | 2028-08-11 09:38
1109 | 5597 | zKJsJYNcPRFZ7wBjvprv | Normal | 18 | 1.9.5.3.1 | 1.9.5.3.1 |  | 2027-11-05 12:00 | p | 201 |  | 2028-05-25 09:07
1110 | 5598 | zvvzNQqIPXzcVRwy0N44 | Summary | 52 | 1.9.5.3.2 | 1.9.5.3.2 |  | 2028-01-12 12:00 | p | 205 |  | 2028-08-04 13:05
1111 | 5599 | T0Oh47cWIVU9y2MKPB0U | Normal | 12 | 1.9.5.3.2.1 | 1.9.5.3.2.1 |  | 2027-11-23 12:00 | p | 202 |  | 2028-06-13 11:14
1112 | 5600 | oTkX6bjokLXQ590hdeFy | Normal | 12 | 1.9.5.3.2.2 | 1.9.5.3.2.2 |  | 2027-12-09 12:00 | p | 208 |  | 2028-07-05 08:13
1113 | 5601 | xa7cRxeKgQxZnuHNAYMQ | Normal | 12 | 1.9.5.3.2.3 | 1.9.5.3.2.3 |  | 2027-12-27 12:00 | p | 203 |  | 2028-07-17 14:45
1114 | 5602 | QlxDegibloFbHrPNJwyW | Normal | 12 | 1.9.5.3.2.4 | 1.9.5.3.2.4 |  | 2028-01-12 12:00 | p | 205 |  | 2028-08-04 13:05
1115 | 5603 | dwMYG7lg76TqxtTxZNCR | Normal | 5 | 1.9.5.3.3 | 1.9.5.3.3 |  | 2028-01-19 12:00 | p | 204 |  | 2028-08-11 09:38
1116 | 6317 | NzqiT3qChWGoVO5Oxj9C | Summary | 111 | 1.9.4 | 1.9.4 |  | 2028-09-28 17:00 | q | -36 |  | 2028-08-23 13:49
1117 | 5355 | lohINUHwZqjP23W1PYQO | Summary | 26 | 1.9.4.1 | 1.9.4.1 |  | 2027-11-08 12:00 | p | 204 |  | 2028-05-31 10:21
1118 | 5358 | Tenn83cNUrlWZNLgXJG2 | Normal | 2 | 1.9.4.1.2 | 1.9.4.1.2 |  | 2027-11-03 12:00 | q | -994 |  | 2025-02-11 17:00
1119 | 5359 | VhUQP0fhGYyFZ67e4nln | Normal | 2 | 1.9.4.1.3 | 1.9.4.1.3 |  | 2027-09-08 12:00 | q | -938 |  | 2025-02-11 17:00
1120 | 5360 | ARncD9Nx3De5DONPy9Bs | Normal | 3 | 1.9.4.1.4 | 1.9.4.1.4 |  | 2027-11-08 12:00 | p | 204 |  | 2028-05-31 10:21
1121 | 7262 | dH18W6KApKWC8TAOWb50 | Normal | 36 | 1.7.4.1.4 | 1.7.4.1.4 |  | 2027-11-02 12:00 | q | -937 |  | 2025-04-08 17:00
1122 | 7263 | mjGxmWsUF3dJi6MlhQpM | Normal | 1 | 1.7.4.1.5 | 1.7.4.1.5 |  | 2027-11-03 12:00 | p | 207 |  | 2028-05-29 09:38
1123 | 5362 | 4bsxfawvV6TKTvCq9VoB | Summary | 6 | 1.9.4.2 | 1.9.4.2 |  | 2027-11-08 12:00 | p | 205 |  | 2028-05-31 15:53
1124 | 5368 | NKJL1ZJN3KgUArkbA4qS | Normal | 3 | 1.9.4.2.4 | 1.9.4.2.4 |  | 2027-11-08 12:00 | p | 205 |  | 2028-05-31 15:53
1125 | 7260 | DPsh83rHAyIaiD8XYnO0 | Normal | 6 | 1.7.4.2.4 | 1.7.4.2.4 |  | 2027-11-02 12:00 | p | 205 |  | 2028-05-26 11:26
1126 | 7261 | isfym7y8CMuc9Vq3Mbcl | Normal | 1 | 1.7.4.2.5 | 1.7.4.2.5 |  | 2027-11-03 12:00 | p | 207 |  | 2028-05-29 09:38
1127 | 5375 | zkXPpJkHw8DPAtspwcmA | Summary | 124 | 1.9.4.4 | 1.9.4.4 |  | 2028-01-21 12:00 | p | 208 |  | 2028-08-16 13:04
1128 | 5376 | zSTdFwWI5FOaluV37lYS | Normal | 63 | 1.9.4.4.1 | 1.9.4.4.1 |  | 2028-01-21 12:00 | p | 208 |  | 2028-08-16 13:04
1129 | 5377 | Wv5w7NMYDRM71nE6dVi0 | Summary | 58 | 1.9.4.5 | 1.9.4.5 |  | 2028-09-28 17:00 | q | -136 |  | 2028-05-15 14:02
1130 | 5379 | 7aIIakNe0KPRF0TCK1un | Normal | 2 | 1.9.4.5.2 | 1.9.4.5.2 |  | 2028-09-28 17:00 | q | -1325 |  | 2025-02-11 17:00
1131 | 5381 | HgkAkSCruVdxdZyXC7sW | Normal | 4 | 1.9.4.5.4 | 1.9.4.5.4 |  | 2027-07-07 12:00 | q | -873 |  | 2025-02-13 17:00
1132 | 5382 | VlX4WunUzdS7Nqvh5ftn | Normal | 20 | 1.9.4.5.5 | 1.9.4.5.5 |  | 2027-08-04 12:00 | p | 195 |  | 2028-02-16 10:45
1133 | 5383 | u1aficyBQ2O9A8MnpdfZ | Normal | 20 | 1.9.4.5.6 | 1.9.4.5.6 |  | 2027-09-01 12:00 | p | 202 |  | 2028-03-21 16:19
1134 | 5384 | d8i6C63YfOF3EovUl19W | Normal | 10 | 1.9.4.5.7 | 1.9.4.5.7 |  | 2027-09-15 12:00 | p | 202 |  | 2028-04-04 16:26
1135 | 5385 | ohwsmv9qOoV0RNzIdjJI | Normal | 15 | 1.9.4.5.8 | 1.9.4.5.8 |  | 2027-10-06 12:00 | p | 204 |  | 2028-04-27 14:13
1136 | 5386 | tSuemAovBYAaHNhFiwaF | Normal | 15 | 1.9.4.5.9 | 1.9.4.5.9 |  | 2027-10-27 12:00 | p | 201 |  | 2028-05-15 14:02
1137 | 5387 | 9gTKo9vjb1rQAbWcTOOW | Summary | 58 | 1.9.4.6 | 1.9.4.6 |  | 2028-09-28 17:00 | q | -136 |  | 2028-05-15 14:02
1138 | 5389 | 0FrUudkzBjpolAMz4tT0 | Normal | 2 | 1.9.4.6.2 | 1.9.4.6.2 |  | 2028-09-28 17:00 | q | -1325 |  | 2025-02-11 17:00
1139 | 5391 | rUGJjnqPCImSizDtYOdy | Normal | 4 | 1.9.4.6.4 | 1.9.4.6.4 |  | 2027-07-07 12:00 | q | -873 |  | 2025-02-13 17:00
1140 | 5392 | TRJmldmXNRf3NwsZhgng | Normal | 20 | 1.9.4.6.5 | 1.9.4.6.5 |  | 2027-08-04 12:00 | p | 203 |  | 2028-02-24 08:31
1141 | 5393 | 3qvg7di25vdBD8UUvM1a | Normal | 20 | 1.9.4.6.6 | 1.9.4.6.6 |  | 2027-09-01 12:00 | p | 203 |  | 2028-03-22 16:39
1142 | 5394 | ungpeNo64cspVo3BuO9g | Normal | 10 | 1.9.4.6.7 | 1.9.4.6.7 |  | 2027-09-15 12:00 | p | 204 |  | 2028-04-07 08:05
1143 | 5395 | KZXvYFda88KgX9w7a3ES | Normal | 15 | 1.9.4.6.8 | 1.9.4.6.8 |  | 2027-10-06 12:00 | p | 203 |  | 2028-04-27 09:00
1144 | 5396 | FNjsTUKVT29tBcVlvaM6 | Normal | 15 | 1.9.4.6.9 | 1.9.4.6.9 |  | 2027-10-27 12:00 | p | 201 |  | 2028-05-15 14:02
1145 | 5397 | KGrMeH5y6HH9dj1tr8uB | Summary | 53 | 1.9.4.7 | 1.9.4.7 |  | 2028-01-10 12:00 | p | 205 |  | 2028-08-02 15:36
1146 | 5398 | EMMfZLgDhvN5O0lAfznQ | Normal | 15 | 1.9.4.7.1 | 1.9.4.7.1 |  | 2027-11-17 12:00 | p | 202 |  | 2028-06-06 15:46
1147 | 5399 | 5K7jeUOrZ3wka9S2O1Dn | Normal | 15 | 1.9.4.7.2 | 1.9.4.7.2 |  | 2027-12-08 12:00 | p | 202 |  | 2028-06-27 15:44
1148 | 5400 | I2IZFfCcy2hUSTtihPWq | Normal | 15 | 1.9.4.7.3 | 1.9.4.7.3 |  | 2027-12-29 12:00 | p | 202 |  | 2028-07-18 14:33
1149 | 5401 | WWZjxA63YxH38hnYmVKG | Normal | 8 | 1.9.4.7.4 | 1.9.4.7.4 |  | 2028-01-10 12:00 | p | 205 |  | 2028-08-02 15:36
1150 | 5402 | zDUD70mdAG3rcozejCwk | Summary | 15 | 1.9.4.8 | 1.9.4.8 |  | 2028-01-31 12:00 | p | 205 |  | 2028-08-23 13:49
1151 | 5403 | wP2WbhW6upJb7JmdzCw1 | Normal | 9 | 1.9.4.8.1 | 1.9.4.8.1 |  | 2028-01-21 12:00 | p | 208 |  | 2028-08-16 13:04
1152 | 5404 | UrewlDJ3J2c8Ueci7p9E | Normal | 6 | 1.9.4.8.2 | 1.9.4.8.2 |  | 2028-01-31 12:00 | p | 205 |  | 2028-08-23 13:49
1153 | 7264 | vNqQNKJIEgg8BiBzdWeI | Summary | 57 | 1.7.4.3.6 | 1.7.4.3.6 |  | 2028-01-21 12:00 | p | 208 |  | 2028-08-16 13:04
1154 | 7265 | uNFJkQaxxZ7oOYaM8QxX | Normal | 13 | 1.7.4.3.6.1 | 1.7.4.3.6.1 |  | 2027-11-23 12:00 | p | 206 |  | 2028-06-16 14:05
1155 | 7266 | y7TR6NxR4uOKxinxsnEt | Normal | 13 | 1.7.4.3.6.2 | 1.7.4.3.6.2 |  | 2027-12-10 12:00 | p | 207 |  | 2028-07-04 16:48
1156 | 7267 | f0BUmD79ZhKqjjzrwXUq | Normal | 13 | 1.7.4.3.6.3 | 1.7.4.3.6.3 |  | 2027-12-29 12:00 | p | 208 |  | 2028-07-24 14:44
1157 | 7268 | sP1zO7OhzT9CUKqdzecJ | Normal | 12 | 1.7.4.3.6.4 | 1.7.4.3.6.4 |  | 2028-01-14 12:00 | p | 208 |  | 2028-08-09 14:15
1158 | 7269 | 7v5GPnNw6yREyKfoeMiZ | Normal | 5 | 1.7.4.3.6.5 | 1.7.4.3.6.5 |  | 2028-01-21 12:00 | p | 208 |  | 2028-08-16 13:04
1159 | 7528 | 8SnF5zCB4rJyZyQZLLZc | Normal | 8 | 1.7.5.1 | 1.7.5.1 |  | 2026-05-12 17:00 | q | -4 |  | 2026-05-08 10:00
1160 | 7529 | ugdLGMeRoSNQZE98ehwR | Normal | 8 | 1.7.5.2 | 1.7.5.2 |  | 2026-05-12 17:00 | q | -4 |  | 2026-05-08 10:00
1161 | 7530 | tZgNvNsEFqNHmYVKXpMu | Normal | 7 | 1.7.5.3 | 1.7.5.3 |  | 2026-05-21 17:00 | q | -3 |  | 2026-05-18 16:50
1162 | 7531 | WsQS39Ko43y2ykuRUNnk | Normal | 8 | 1.7.5.4 | 1.7.5.4 |  | 2026-06-03 17:00 | q | -1 |  | 2026-06-02 16:26
1163 | 7532 | tNKjUDGuH9lZvW14y0xJ | Normal | 22 | 1.7.5.5 | 1.7.5.5 |  | 2026-07-07 17:00 | p | 0 |  | 2026-07-08 08:59
1164 | 7533 | HKUUjAeDBFLcgj42uw3c | Normal | 19 | 1.7.5.6 | 1.7.5.6 |  | 2026-08-03 17:00 | p | 2 |  | 2026-08-06 09:45
1165 | 7534 | s7VTtgJqjYjf9pbLYcYj | Normal | 8 | 1.7.5.7 | 1.7.5.7 |  | 2026-08-13 17:00 | p | 3 |  | 2026-08-17 08:10
1166 | 7535 | uGgP1gHCy12zlVFcLeTG | Normal | 6 | 1.7.5.8 | 1.7.5.8 |  | 2026-08-21 17:00 | q | 0 |  | 2026-08-21 14:24
1167 | 7536 | kbIucnV7qsI0ZjxbK1cH | Normal | 6 | 1.7.5.9 | 1.7.5.9 |  | 2026-08-31 17:00 | p | 0 |  | 2026-09-01 09:53
1168 | 6688 | aKOlgm9Tw9oPXF0YCFLp | Summary | 911 | 1.11 | 1.11 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
1169 | 6689 | fEYxMDiPOAwjjU8zha5c | Normal | 396 | 1.11.1 | 1.11.1 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
1170 | 6690 | bopLkaAZbmZjIM9EGI6L | Normal | 532 | 1.11.2 | 1.11.2 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
1171 | 6691 | xLErpFHjPEH3ifHRbBMY | Normal | 396 | 1.11.3 | 1.11.3 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
1172 | 6692 | g8WcEZ6I6SGdlePHrYPP | Normal | 248 | 1.11.4 | 1.11.4 |  | 2028-07-28 17:00 | p | 212 |  | 2029-02-26 09:11
1173 | 6695 | Bx0BPJ0BcPw49QEL7Psq | Normal | 313 | 1.11.8 | 1.11.8 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:06
1174 | 6696 | XbFIp383UbA72xJPH4hJ | Normal | 101 | 1.11.9 | 1.11.9 |  | 2028-07-28 17:00 | p | 212 |  | 2029-02-26 09:11
1175 | 6697 | gpkN7vTMpz4ZZxhDAmeL | Normal | 126 | 1.11.10 | 1.11.10 |  | 2028-07-28 17:00 | p | 212 |  | 2029-02-26 09:11
1176 | 6698 | eRsel9yyFaDkcYLZgvjC | Normal | 142 | 1.11.11 | 1.11.11 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:06
1177 | 6699 | k8943lu4TS9ZW2TcUvha | Normal | 256 | 1.11.12 | 1.11.12 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
1178 | 7376 | FfEUU5kpALOu6FlmjosD | Normal | 396 | 1.10.3 | 1.10.3 |  | 2028-09-28 17:00 | p | 203 |  | 2029-04-20 09:39
1179 | 7378 | YjoFZZooPnFRzsk2Ba2E | Normal | 288 | 1.10.6 | 1.10.6 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:06
1180 | 7379 | 7GajZBAFakrGWC1WlgE6 | Normal | 142 | 1.10.14 | 1.10.14 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:06
1181 | 7380 | wkyoOF6gHS9pA0Dm9pZY | Normal | 140 | 1.10.17 | 1.10.17 |  | 2028-09-27 17:00 | p | 203 |  | 2029-04-19 10:06
1182 | 7551 | G4afE8kOleATkD8qyqeP | Normal | 1 | 1.10.19 | 1.10.19 |  | 2028-09-28 17:00 | q | -4131 |  | 2017-06-07 17:00
1183 | 7131 | XTX9Wl5SzTxAD1rtsh9U | Summary | 0 | 1.10 | 1.10 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39
1184 | 7107 | fjlRoMsMUGjOnNWoUkGJ | Milestone | 0 | 1.10.16 | 1.10.16 |  | 2028-09-29 08:00 | p | 203 |  | 2029-04-20 09:39

## Expected-Finish
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2

## Suspend-Date
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Suspend Date - 45 (2%) | Suspend Date - 45 (2%) | Suspend Date - 45 (2%) | Suspend Date - 45 (2%) | Suspend Date - 45 (2%) | Suspend Date - 45 (2%) | Suspend Date - 45 (2%) | Suspend Date - 45 (2%) | Suspend Date - 45 (2%) | Suspend Date - 45 (2%) | Suspend Date - 45 (2%) | Suspend Date - 45 (2%) | Suspend Date - 45 (2%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 7210 | 5vpOUfvEpSU2AKPwltv0 | Summary | 14 | 1.3.2.3.2.3 | 1.3.2.3.2.3 |  | 2025-02-07 17:00 | p | 7 |  | 2025-02-14 17:00
2 | 7211 | wSDYMNBcPlclxMN6Hc8V | Normal | 5 | 1.3.2.3.2.3.1 | 1.3.2.3.2.3.1 |  | 2025-02-07 17:00 | p | 7 |  | 2025-02-14 17:00
3 | 7218 | 5fSpBiSdaCD1mvMsYs0j | Normal | 2 | 1.3.2.3.2.4.3 | 1.3.2.3.2.4.3 |  | 2025-02-07 17:00 | p | 4 |  | 2025-02-11 17:00
4 | 7219 | tMHxEODKuKminmE9Mjg5 | Normal | 1 | 1.3.2.3.2.4.4 | 1.3.2.3.2.4.4 |  | O | p |  |  | 2025-02-12 17:00
5 | 7226 | fsyu9CvTMAXTCK7e04ez | Normal | 1 | 1.3.2.3.2.5.3 | 1.3.2.3.2.5.3 |  | 2025-02-07 17:00 | p | 3 |  | 2025-02-10 17:00
6 | 7515 | jdxLrBmn54gbF5MbPNVU | Normal | 5 | 1.3.2.3.2.5.8 | 1.3.2.3.2.5.8 |  | 2025-02-07 17:00 | p | 7 |  | 2025-02-14 17:00
7 | 631 | jjFU6HpNq2otAi9zmRWR | Normal | 2 | 1.5.6.6.2.7 | 1.5.6.6.2.7 |  | 2025-02-07 17:00 | p | 4 |  | 2025-02-11 17:00
8 | 670 | zBtIFoyMK1KgXAv407C9 | Summary | 29 | 1.5.6.5 | 1.5.6.5 |  | 2025-02-07 17:00 | p | 5 |  | 2025-02-12 17:00
9 | 6141 | PCEOtJROHHMKXYkoR4rp | Normal | 3 | 1.5.6.5.1 | 1.5.6.5.1 |  | 2025-02-07 17:00 | p | 5 |  | 2025-02-12 17:00
10 | 1457 | W1XQ7yoZAeSgm7UftoXN | Normal | 1 | 1.5.5.1.2 | 1.5.5.1.2 |  | O | p |  |  | 2025-02-14 17:00
11 | 5627 | s0vjJX7zGlVyBdE0eigo | Summary | 15 | 1.5.2.2.8 | 1.5.2.2.8 |  | O | p |  |  | 2025-02-14 17:00
12 | 7545 | 65jUkOPqlMfpoMROhJ4O | Normal | 5 | 1.5.3.2.9.1 | 1.5.3.2.9.1 |  | O | p |  |  | 2025-02-14 17:00
13 | 5637 | agdOsAK6kuG5dvRDXVyv | Milestone | 0 | 1.5.2.2.9.2 | 1.5.2.2.9.2 |  | 2025-01-08 17:00 | q |  |  | O
14 | 5638 | jBSFjjY1RfmWgqa8tOlO | Normal | 0 | 1.5.2.2.9.3 | 1.5.2.2.9.3 |  | 2025-01-24 17:00 | q |  |  | O
15 | 5639 | ymvGdGMdlU958QTwMU9V | Normal | 0 | 1.5.2.2.9.4 | 1.5.2.2.9.4 |  | 2025-01-27 12:00 | q |  |  | O
16 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | 2025-02-03 12:00 | q |  |  | O
17 | 1463 | IQX94tuow2VKmVJTuhEN | Normal | 1 | 1.6.6.1.3 | 1.6.6.1.3 |  | O | p |  |  | 2025-02-13 17:00
18 | 3973 | 00qHhBlTe8pinGtKpu3n | Normal | 4 | 1.6.4.6 | 1.6.4.6 |  | 2025-02-07 17:00 | p | 6 |  | 2025-02-13 17:00
19 | 6738 | XB1ZMgqMWvDJpnRGKTB3 | Normal | 3 | 1.6.4.18.3.3.2.10 | 1.6.4.18.3.3.2.10 |  | O | p |  |  | 2025-02-13 17:00
20 | 7003 | XfnOKCk0EbakXF7t35fN | Normal | 1 | 1.6.4.18.3.3.2.9 | 1.6.4.18.3.3.2.9 |  | 2025-02-07 17:00 | p | 3 |  | 2025-02-10 17:00
21 | 7270 | 3AlavOi01JfJwLM1b81K | Milestone | 0 | 1.6.4.18.3.3.2.6 | 1.6.4.18.3.3.2.6 |  | O | p |  |  | 2025-02-13 17:00
22 | 7277 | hIopgQViPH34dy6jPgEs | Normal | 6 | 1.6.4.18.3.3.7.5 | 1.6.4.18.3.3.7.5 |  | O | p |  |  | 2025-03-14 17:00
23 | 7295 | tyaakhlAtuOpVSt7bVvo | Normal | 1 | 1.6.4.18.3.3.6.2 | 1.6.4.18.3.3.6.2 |  | O | p |  |  | 2025-02-10 17:00
24 | 7312 | ZHpaj2955bjmxPKFBEf2 | Normal | 2 | 1.6.3.11.1.3.5.3 | 1.6.3.11.1.3.5.3 |  | O | p |  |  | 2025-02-11 17:00
25 | 6273 | ljz6i2ltFwqcRU3btDx0 | Summary | 552 | 1.8 | 1.8 |  | 2025-01-03 17:00 | q | -515 |  | 2023-08-07 08:00
26 | 6295 | uPS9GNqRLP4065SnBhEr | Summary | 387 | 1.8.5 | 1.8.5 |  | 2025-02-07 17:00 | q | -550 |  | 2023-08-07 08:00
27 | 3679 | 1KDcwGZKgevw1MizqBh0 | Summary | 387 | 1.8.5.1 | 1.8.5.1 |  | 2025-02-07 17:00 | q | -550 |  | 2023-08-07 08:00
28 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 2021-02-01 17:00 | q | -1335 |  | 2017-06-07 08:00
29 | 6279 | p7EJXT1muDSglD2OZLFH | Summary | 274 | 1.9.7 | 1.9.7 |  | 2023-03-29 17:00 | q | -2121 |  | 2017-06-07 08:00
30 | 1484 | 6ARiGRg3KLswRpJLOmGD | Summary | 229 | 1.9.7.18 | 1.9.7.18 |  | 2023-10-26 17:00 | q | -2332 |  | 2017-06-07 08:00
31 | 1539 | ySsQ3GXU4tpHt4hn7HeO | Normal | 2 | 1.9.7.15.4 | 1.9.7.15.4 |  | 2025-02-07 17:00 | p | 4 |  | 2025-02-11 17:00
32 | 1540 | GIXHFfgJ4jA0lgUlb0GT | Normal | 1 | 1.9.7.15.5 | 1.9.7.15.5 |  | O | p |  |  | 2025-02-12 17:00
33 | 1560 | fBOtciokyA85OuE15WSO | Normal | 1 | 1.9.7.19.10 | 1.9.7.19.10 |  | 2025-02-07 17:00 | p | 3 |  | 2025-02-10 17:00
34 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | O | p |  |  | 2027-09-28 17:00
35 | 5533 | g1oQNBzKk6OrBukgGH7R | Normal | 40 | 1.9.5.1.3 | 1.9.5.1.3 |  | O | p |  |  | 2025-04-28 17:00
36 | 5358 | Tenn83cNUrlWZNLgXJG2 | Normal | 2 | 1.9.4.1.2 | 1.9.4.1.2 |  | 2025-02-07 17:00 | p | 4 |  | 2025-02-11 17:00
37 | 5359 | VhUQP0fhGYyFZ67e4nln | Normal | 2 | 1.9.4.1.3 | 1.9.4.1.3 |  | 2025-02-07 17:00 | p | 4 |  | 2025-02-11 17:00
38 | 7262 | dH18W6KApKWC8TAOWb50 | Normal | 36 | 1.7.4.1.4 | 1.7.4.1.4 |  | O | p |  |  | 2025-04-08 17:00
39 | 5379 | 7aIIakNe0KPRF0TCK1un | Normal | 2 | 1.9.4.5.2 | 1.9.4.5.2 |  | 2025-02-07 17:00 | p | 4 |  | 2025-02-11 17:00
40 | 5381 | HgkAkSCruVdxdZyXC7sW | Normal | 4 | 1.9.4.5.4 | 1.9.4.5.4 |  | 2025-02-07 17:00 | p | 6 |  | 2025-02-13 17:00
41 | 5389 | 0FrUudkzBjpolAMz4tT0 | Normal | 2 | 1.9.4.6.2 | 1.9.4.6.2 |  | 2025-02-07 17:00 | p | 4 |  | 2025-02-11 17:00
42 | 5391 | rUGJjnqPCImSizDtYOdy | Normal | 4 | 1.9.4.6.4 | 1.9.4.6.4 |  | 2025-02-07 17:00 | p | 6 |  | 2025-02-13 17:00
43 | 6688 | aKOlgm9Tw9oPXF0YCFLp | Summary | 911 | 1.11 | 1.11 |  | 2017-06-07 08:00 | p | 0 |  | 2017-06-07 17:00
44 | 7551 | G4afE8kOleATkD8qyqeP | Normal | 1 | 1.10.19 | 1.10.19 |  | O | p |  |  | 2017-06-07 17:00
45 | 7131 | XTX9Wl5SzTxAD1rtsh9U | Summary | 0 | 1.10 | 1.10 |  | 2023-10-12 17:00 | q | -2114 |  | 2017-12-28 16:20

## Resume-Date
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Resume Date - 157 (7%) | Resume Date - 157 (7%) | Resume Date - 157 (7%) | Resume Date - 157 (7%) | Resume Date - 157 (7%) | Resume Date - 157 (7%) | Resume Date - 157 (7%) | Resume Date - 157 (7%) | Resume Date - 157 (7%) | Resume Date - 157 (7%) | Resume Date - 157 (7%) | Resume Date - 157 (7%) | Resume Date - 157 (7%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 6673 | sIWmvaXMX3ZF9ctRNm7s | Normal | 34 | 1.2.7.3.3 | 1.2.7.3.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
2 | 6438 | sSGfho0IWOHZYw1Z8jLl | Normal | 16 | 1.3.3.1.2.4.5 | 1.3.3.1.2.4.5 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
3 | 3849 | PKYN5IsyqbTocjyswPFM | Normal | 17 | 1.3.2.1.1 | 1.3.2.1.1 |  | 2025-02-20 08:00 | p | 28 |  | 2025-03-20 08:00
4 | 3857 | FObPKa3HJ5KI4gFmAx2r | Summary | 210 | 1.3.2.1.2.2 | 1.3.2.1.2.2 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
5 | 3858 | pWvg9Owxac1jXAINT5hs | Normal | 24 | 1.3.2.1.2.2.1 | 1.3.2.1.2.2.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
6 | 7199 | G7LfPy6euQCIQjteO0x8 | Normal | 20 | 1.3.2.3.2.1.3.3 | 1.3.2.3.2.1.3.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
7 | 7205 | 688LmElxek6WZQ34zEgD | Summary | 40 | 1.3.2.3.2.2 | 1.3.2.3.2.2 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 16:30
8 | 7206 | bMXBNIC1fF7AjliDPdfr | Normal | 25 | 1.3.2.3.2.2.1 | 1.3.2.3.2.2.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 16:30
9 | 7210 | 5vpOUfvEpSU2AKPwltv0 | Summary | 14 | 1.3.2.3.2.3 | 1.3.2.3.2.3 |  | 2025-02-10 08:00 | p | 4 |  | 2025-02-14 17:00
10 | 7211 | wSDYMNBcPlclxMN6Hc8V | Normal | 5 | 1.3.2.3.2.3.1 | 1.3.2.3.2.3.1 |  | 2025-02-10 08:00 | p | 4 |  | 2025-02-14 17:00
11 | 7218 | 5fSpBiSdaCD1mvMsYs0j | Normal | 2 | 1.3.2.3.2.4.3 | 1.3.2.3.2.4.3 |  | 2025-02-10 08:00 | p | 1 |  | 2025-02-11 17:00
12 | 7219 | tMHxEODKuKminmE9Mjg5 | Normal | 1 | 1.3.2.3.2.4.4 | 1.3.2.3.2.4.4 |  | O | p |  |  | 2025-02-12 17:00
13 | 7226 | fsyu9CvTMAXTCK7e04ez | Normal | 1 | 1.3.2.3.2.5.3 | 1.3.2.3.2.5.3 |  | 2025-02-10 08:00 | p | 0 |  | 2025-02-10 17:00
14 | 7227 | QiFvht1v2EB9ODLdNK6M | Normal | 25 | 1.3.2.3.2.5.4 | 1.3.2.3.2.5.4 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
15 | 7515 | jdxLrBmn54gbF5MbPNVU | Normal | 5 | 1.3.2.3.2.5.8 | 1.3.2.3.2.5.8 |  | 2025-02-10 08:00 | p | 4 |  | 2025-02-14 17:00
16 | 605 | HP2TrbmUH5Qc4V2P2k1T | Normal | 14 | 1.5.6.1 | 1.5.6.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
17 | 631 | jjFU6HpNq2otAi9zmRWR | Normal | 2 | 1.5.6.6.2.7 | 1.5.6.6.2.7 |  | 2025-02-10 08:00 | p | 1 |  | 2025-02-11 17:00
18 | 670 | zBtIFoyMK1KgXAv407C9 | Summary | 29 | 1.5.6.5 | 1.5.6.5 |  | 2025-02-10 08:00 | p | 2 |  | 2025-02-12 17:00
19 | 6141 | PCEOtJROHHMKXYkoR4rp | Normal | 3 | 1.5.6.5.1 | 1.5.6.5.1 |  | 2025-02-10 08:00 | p | 2 |  | 2025-02-12 17:00
20 | 1457 | W1XQ7yoZAeSgm7UftoXN | Normal | 1 | 1.5.5.1.2 | 1.5.5.1.2 |  | O | p |  |  | 2025-02-14 17:00
21 | 1468 | 8e77YoSi4abIbMILI8hH | Normal | 5 | 1.5.5.1.5 | 1.5.5.1.5 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
22 | 3944 | HRTLaCTjRjqysGxmE6ve | Normal | 36 | 1.5.4.2 | 1.5.4.2 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
23 | 3950 | NJx1RMKdqhuNKRLGMSBQ | Summary | 27 | 1.5.4.5.1 | 1.5.4.5.1 |  | 2025-02-28 08:00 | p | 34 |  | 2025-04-03 15:55
24 | 3951 | BNWJw3sHADBJTHA2Ybu0 | Normal | 16 | 1.5.4.5.1.1 | 1.5.4.5.1.1 |  | 2025-02-28 08:00 | p | 34 |  | 2025-04-03 15:55
25 | 3967 | BaECEBO5p44IeRhOgeK2 | Normal | 19 | 1.5.4.5.4.3 | 1.5.4.5.4.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
26 | 3948 | 6ze4BjeYc1B5uifD0Fqa | Normal | 10 | 1.5.4.4.9 | 1.5.4.4.9 |  | 2025-02-11 08:00 | p | 31 |  | 2025-03-14 14:35
27 | 6202 | X3XRH6pSpuIgaacqwHSp | Normal | 14 | 1.5.4.4.10 | 1.5.4.4.10 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
28 | 6605 | Qtljmhuq3GHp8HrV3pPP | Normal | 6 | 1.5.4.4.7 | 1.5.4.4.7 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
29 | 6444 | XymP4MvJgra2aDdoc9vw | Normal | 46 | 1.5.1.1.2 | 1.5.1.1.2 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
30 | 6680 | ttlvn3uwilh7nqgbHtE7 | Normal | 37 | 1.5.1.3.7 | 1.5.1.3.7 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
31 | 5627 | s0vjJX7zGlVyBdE0eigo | Summary | 15 | 1.5.2.2.8 | 1.5.2.2.8 |  | O | p |  |  | 2025-02-14 17:00
32 | 7545 | 65jUkOPqlMfpoMROhJ4O | Normal | 5 | 1.5.3.2.9.1 | 1.5.3.2.9.1 |  | O | p |  |  | 2025-02-14 17:00
33 | 5637 | agdOsAK6kuG5dvRDXVyv | Milestone | 0 | 1.5.2.2.9.2 | 1.5.2.2.9.2 |  | 2025-01-08 17:00 | q |  |  | O
34 | 5638 | jBSFjjY1RfmWgqa8tOlO | Normal | 0 | 1.5.2.2.9.3 | 1.5.2.2.9.3 |  | 2025-01-24 17:00 | q |  |  | O
35 | 5639 | ymvGdGMdlU958QTwMU9V | Normal | 0 | 1.5.2.2.9.4 | 1.5.2.2.9.4 |  | 2025-01-27 12:00 | q |  |  | O
36 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | 2025-02-03 12:00 | q |  |  | O
37 | 6290 | VuOK0YK760zOpXaJ9U7h | Summary | 140 | 1.4.3 | 1.4.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
38 | 4537 | FhESv2GOKRYErv6rS2Ko | Summary | 140 | 1.4.3.1 | 1.4.3.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
39 | 4536 | zU98x2LHVd7UXovDFMXu | Normal | 14 | 1.4.3.1.1 | 1.4.3.1.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
40 | 3900 | fYbjIfZDvkbYu7p7dq3N | Normal | 14 | 1.4.1.1.2.3 | 1.4.1.1.2.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
41 | 6565 | XyBOyY3JpPW2h1I7PEur | Normal | 21 | 1.4.1.2.1.5 | 1.4.1.2.1.5 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
42 | 5262 | PI0DE6xTKT4gLnHpqgjE | Summary | 137 | 1.4.2.1.6 | 1.4.2.1.6 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
43 | 5263 | URhzXaXmWu6rBPIMitrn | Normal | 30 | 1.4.2.1.6.1 | 1.4.2.1.6.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
44 | 700 | PZaQwD8fp0dlxZIxEZEd | Normal | 279 | 1.6.7.10 | 1.6.7.10 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
45 | 6434 | cc8WGEqtonq4zOxPHtWc | Normal | 65 | 1.6.7.8.4 | 1.6.7.8.4 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
46 | 1463 | IQX94tuow2VKmVJTuhEN | Normal | 1 | 1.6.6.1.3 | 1.6.6.1.3 |  | O | p |  |  | 2025-02-13 17:00
47 | 3929 | GkmiaraCbWdBUaRv136y | Summary | 19 | 1.6.4.15 | 1.6.4.15 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
48 | 3938 | 2iJ091mlhEkJyqoddB4L | Normal | 14 | 1.6.4.15.1 | 1.6.4.15.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
49 | 3931 | GleHIX38gd9vOXaUQYVA | Normal | 33 | 1.6.4.11 | 1.6.4.11 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
50 | 3933 | FbGZSJQTtuDZR2p8qmxq | Normal | 33 | 1.6.4.13 | 1.6.4.13 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
51 | 3935 | IRdaiLeeauelAg4QWklz | Normal | 33 | 1.6.4.12 | 1.6.4.12 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
52 | 3939 | cuQ4HC0Kn3S6GTvqv7QE | Normal | 33 | 1.6.4.14 | 1.6.4.14 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
53 | 3981 | YTm9sByrDxPUc7AlWXh1 | Normal | 15 | 1.6.4.7.2 | 1.6.4.7.2 |  | 2025-03-18 08:00 | p | 35 |  | 2025-04-22 16:11
54 | 3973 | 00qHhBlTe8pinGtKpu3n | Normal | 4 | 1.6.4.6 | 1.6.4.6 |  | 2025-02-10 08:00 | p | 3 |  | 2025-02-13 17:00
55 | 3980 | po54OWwjtqomy5uOkFBU | Normal | 40 | 1.6.4.4 | 1.6.4.4 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
56 | 4002 | nJzh0eFJGsqvOmQRJzHn | Summary | 27 | 1.6.4.17.2 | 1.6.4.17.2 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
57 | 4003 | gjf3v6NdOQannovTvAoE | Normal | 19 | 1.6.4.17.2.1 | 1.6.4.17.2.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
58 | 6738 | XB1ZMgqMWvDJpnRGKTB3 | Normal | 3 | 1.6.4.18.3.3.2.10 | 1.6.4.18.3.3.2.10 |  | O | p |  |  | 2025-02-13 17:00
59 | 7003 | XfnOKCk0EbakXF7t35fN | Normal | 1 | 1.6.4.18.3.3.2.9 | 1.6.4.18.3.3.2.9 |  | 2025-02-10 08:00 | p | 0 |  | 2025-02-10 17:00
60 | 7270 | 3AlavOi01JfJwLM1b81K | Milestone | 0 | 1.6.4.18.3.3.2.6 | 1.6.4.18.3.3.2.6 |  | O | p |  |  | 2025-02-13 17:00
61 | 7277 | hIopgQViPH34dy6jPgEs | Normal | 6 | 1.6.4.18.3.3.7.5 | 1.6.4.18.3.3.7.5 |  | O | p |  |  | 2025-03-14 17:00
62 | 7295 | tyaakhlAtuOpVSt7bVvo | Normal | 1 | 1.6.4.18.3.3.6.2 | 1.6.4.18.3.3.6.2 |  | O | p |  |  | 2025-02-10 17:00
63 | 4202 | N5DTU5adYVhKR5So2Uvc | Normal | 88 | 1.6.1.1.3 | 1.6.1.1.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
64 | 4209 | 0Ck6gz1ZilLs9fM0b7nU | Summary | 46 | 1.6.1.3 | 1.6.1.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
65 | 4212 | yktUOUuzQyzOVBFBfL42 | Normal | 46 | 1.6.1.3.1 | 1.6.1.3.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
66 | 5452 | u9nFTwEoKsBrgeg8njOT | Normal | 5 | 1.6.3.1 | 1.6.3.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
67 | 5505 | nVzBMSNTKKq9KPWblsw1 | Normal | 1 | 1.6.3.2.1.9 | 1.6.3.2.1.9 |  | 2025-02-13 14:46 | p | 25 |  | 2025-03-11 08:00
68 | 5506 | wLM81Xdu8B5geOMMQz6m | Summary | 119 | 1.6.3.3 | 1.6.3.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 10:55
69 | 6890 | QKIolSsTnUWZiIhR6M5v | Normal | 40 | 1.6.3.3.1 | 1.6.3.3.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 10:55
70 | 7312 | ZHpaj2955bjmxPKFBEf2 | Normal | 2 | 1.6.3.11.1.3.5.3 | 1.6.3.11.1.3.5.3 |  | O | p |  |  | 2025-02-11 17:00
71 | 6273 | ljz6i2ltFwqcRU3btDx0 | Summary | 552 | 1.8 | 1.8 |  | 2025-01-03 17:00 | q | -515 |  | 2023-08-07 08:00
72 | 1639 | mkPE1mMWzawwUBF3KKzV | Summary | 277 | 1.8.2 | 1.8.2 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
73 | 6074 | fkBL64dyW7paLwgGr0ue | Normal | 212 | 1.8.2.3 | 1.8.2.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
74 | 6075 | pe2nScqRc5pgTwGaT5Zd | Normal | 193 | 1.8.2.2 | 1.8.2.2 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
75 | 6295 | uPS9GNqRLP4065SnBhEr | Summary | 387 | 1.8.5 | 1.8.5 |  | 2025-02-10 08:00 | q | -553 |  | 2023-08-07 08:00
76 | 3679 | 1KDcwGZKgevw1MizqBh0 | Summary | 387 | 1.8.5.1 | 1.8.5.1 |  | 2025-02-10 08:00 | q | -553 |  | 2023-08-07 08:00
77 | 3723 | 4qmbzAmtSx0gvDVaBsYe | Summary | 239 | 1.8.5.1.5 | 1.8.5.1.5 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
78 | 3725 | 8cgOIQk4rBKvjXdBm8mF | Normal | 91 | 1.8.5.1.5.9 | 1.8.5.1.5.9 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
79 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 2021-02-01 17:00 | q | -1335 |  | 2017-06-07 08:00
80 | 6418 | W9pbV5i9WFkdVEGtW75H | Normal | 45 | 1.9.9.7.2.5 | 1.9.9.7.2.5 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
81 | 870 | m3oEXpasu7ssfpw9dqLv | Summary | 267 | 1.9.9.14 | 1.9.9.14 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
82 | 5786 | d3N6cqydEgoPO1XBMSTu | Normal | 7 | 1.9.9.14.1 | 1.9.9.14.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
83 | 6686 | IDiuvzfQRXyu7MCMX1jW | Normal | 5 | 1.9.9.11 | 1.9.9.11 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
84 | 6279 | p7EJXT1muDSglD2OZLFH | Summary | 274 | 1.9.7 | 1.9.7 |  | 2023-03-29 17:00 | q | -2121 |  | 2017-06-07 08:00
85 | 1484 | 6ARiGRg3KLswRpJLOmGD | Summary | 229 | 1.9.7.18 | 1.9.7.18 |  | 2023-10-26 17:00 | q | -2332 |  | 2017-06-07 08:00
86 | 1489 | pYq4lU1lCt1U75q3gu6M | Normal | 11 | 1.9.7.18.1 | 1.9.7.18.1 |  | 2025-02-10 13:24 | p | 28 |  | 2025-03-11 08:00
87 | 1508 | SDZ1pqYbdynEzXZrWujj | Normal | 30 | 1.9.7.6 | 1.9.7.6 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
88 | 1537 | HoYmSEeaxBfAYgcISNXh | Normal | 5 | 1.9.7.15.2 | 1.9.7.15.2 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
89 | 1539 | ySsQ3GXU4tpHt4hn7HeO | Normal | 2 | 1.9.7.15.4 | 1.9.7.15.4 |  | 2025-02-10 08:00 | p | 1 |  | 2025-02-11 17:00
90 | 1540 | GIXHFfgJ4jA0lgUlb0GT | Normal | 1 | 1.9.7.15.5 | 1.9.7.15.5 |  | O | p |  |  | 2025-02-12 17:00
91 | 1560 | fBOtciokyA85OuE15WSO | Normal | 1 | 1.9.7.19.10 | 1.9.7.19.10 |  | 2025-02-10 08:00 | p | 0 |  | 2025-02-10 17:00
92 | 4571 | grLKm3VpZ98OhRQH2gBq | Normal | 29 | 1.9.7.1 | 1.9.7.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
93 | 4581 | FxGRGf2kppDMdfFrZkS4 | Normal | 36 | 1.9.7.12 | 1.9.7.12 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
94 | 7323 | p8rF5Tk8321hO30p5zSy | Summary | 79 | 1.7.8.18 | 1.7.8.18 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
95 | 7454 | JYERhD3wllXGZEgPk4Fl | Normal | 5 | 1.7.8.18.1 | 1.7.8.18.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
96 | 4593 | XK8YU5H8vMrR7jBOr6fS | Normal | 99 | 1.9.1.1 | 1.9.1.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
97 | 4605 | jXRAJqcdCYbTQqzq5oVG | Normal | 14 | 1.7.3.2 | 1.7.3.2 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
98 | 4615 | Io6EVgFdyRjG7CB2g0Wy | Summary | 98 | 1.7.3.4 | 1.7.3.4 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
99 | 4616 | FR5tuVwQGmPNYmz6BeMP | Normal | 2 | 1.7.3.4.1 | 1.7.3.4.1 |  | 2025-02-13 11:02 | p | 25 |  | 2025-03-11 08:00
100 | 4617 | OziRB3N5b7cM46iEETGg | Normal | 5 | 1.7.3.4.2 | 1.7.3.4.2 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
101 | 4630 | pjdWghPSPBEOfTIZFZhV | Normal | 5 | 1.7.3.6.4 | 1.7.3.6.4 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
102 | 6608 | ifCvUSq9UjUAw7FKKXTR | Normal | 14 | 1.7.3.7.3 | 1.7.3.7.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
103 | 3776 | GHLE38QRMYNBeSYAGB18 | Normal | 32 | 1.7.1.2.6.3 | 1.7.1.2.6.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
104 | 6977 | F0juzsyqTnJm6sTJe4ff | Normal | 14 | 1.7.1.3.4.7 | 1.7.1.3.4.7 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
105 | 3808 | mNtnU9AYiACOeBrTPE9f | Summary | 29 | 1.7.1.5.3 | 1.7.1.5.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
106 | 3809 | ukioB4iHiwrfEXpseTiK | Normal | 15 | 1.7.1.5.3.1 | 1.7.1.5.3.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
107 | 6147 | BUcWclFVChflBnUDJ9UM | Normal | 40 | 1.7.1.5.4 | 1.7.1.5.4 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
108 | 6148 | V03eKqopjAXoUvRodLvQ | Normal | 13 | 1.7.1.5.6 | 1.7.1.5.6 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
109 | 4078 | ybbKeBChK3D60QzH8ONZ | Normal | 76 | 1.9.6.5 | 1.9.6.5 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
110 | 4134 | 86JmjjOtZxj7XQRp3CQF | Summary | 466 | 1.9.6.11 | 1.9.6.11 |  | 2026-04-20 08:00 | p | 654 |  | 2028-02-03 08:00
111 | 4135 | 0voiyAtBe9AzaXfs8cVF | Summary | 322 | 1.9.6.11.1 | 1.9.6.11.1 |  | 2026-04-20 08:00 | p | 654 |  | 2028-02-03 08:00
112 | 4136 | bllhlvXmXgF1yFG9Nwfe | Normal | 16 | 1.9.6.11.1.1 | 1.9.6.11.1.1 |  | 2026-04-20 08:00 | p | 654 |  | 2028-02-03 08:00
113 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | O | p |  |  | 2027-09-28 17:00
114 | 4074 | H2vE7zxiBRw3YTdo2zSW | Normal | 35 | 1.9.6.9.2 | 1.9.6.9.2 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
115 | 4198 | k6X8NWhjfeQOPZdDpmna | Normal | 20 | 1.9.8.1.9 | 1.9.8.1.9 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
116 | 4242 | RIVyyga7UReDeuixs5m9 | Normal | 66 | 1.9.8.4.4 | 1.9.8.4.4 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
117 | 5669 | bBSx7g3AuM8uxZcIYlIi | Normal | 20 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
118 | 5533 | g1oQNBzKk6OrBukgGH7R | Normal | 40 | 1.9.5.1.3 | 1.9.5.1.3 |  | O | p |  |  | 2025-04-28 17:00
119 | 5535 | XVk7S0ldLHQUWflKhMBn | Normal | 11 | 1.9.5.1.2 | 1.9.5.1.2 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
120 | 5539 | kRsO3PSMDsMxji3dmdNc | Normal | 5 | 1.9.5.2.2 | 1.9.5.2.2 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
121 | 5540 | GKx3XnA1BSbhTsgdKbqP | Normal | 14 | 1.9.5.2.8 | 1.9.5.2.8 |  | 2025-02-11 08:00 | p | 29 |  | 2025-03-12 08:00
122 | 5541 | LhqIvyBzzdwllIHwrPz2 | Normal | 5 | 1.9.5.2.7 | 1.9.5.2.7 |  | 2025-02-25 08:00 | p | 29 |  | 2025-03-26 10:14
123 | 5542 | 4ivItsonCrTGke19i41Z | Normal | 15 | 1.9.5.2.6 | 1.9.5.2.6 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
124 | 5543 | XaHBDo6QUBfyTg5ESk7j | Normal | 15 | 1.9.5.2.9 | 1.9.5.2.9 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
125 | 5570 | MuDwSgsBJjDxwFkSMWYJ | Summary | 116 | 1.9.5.2.11 | 1.9.5.2.11 |  | 2025-02-10 08:00 | p | 30 |  | 2025-03-12 13:00
126 | 6998 | CyWehBzIvIWKBi1qju4z | Normal | 15 | 1.9.5.2.11.1 | 1.9.5.2.11.1 |  | 2025-02-10 08:00 | p | 30 |  | 2025-03-12 13:00
127 | 6531 | iX155TL3hNg9Ca4Bsb4A | Normal | 35 | 1.9.5.2.5.2 | 1.9.5.2.5.2 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
128 | 6997 | MBGoTUikAECGvIHYk1uV | Normal | 24 | 1.9.5.2.3 | 1.9.5.2.3 |  | 2025-02-10 08:00 | p | 941 |  | 2027-09-09 08:00
129 | 6251 | Ha7ZmVRhPp4EjAGEFQOQ | Normal | 56 | 1.7.2.7.2.3 | 1.7.2.7.2.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
130 | 6255 | 6Rcxv4eHz2WhxfD2wxtd | Normal | 56 | 1.7.2.7.3.3 | 1.7.2.7.3.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
131 | 6259 | q6ww59eaDtL5Df1J4lsR | Normal | 14 | 1.7.2.7.4.3 | 1.7.2.7.4.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
132 | 6263 | aKytB1b2oD2t1WVaznUP | Normal | 14 | 1.7.2.7.5.3 | 1.7.2.7.5.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
133 | 5358 | Tenn83cNUrlWZNLgXJG2 | Normal | 2 | 1.9.4.1.2 | 1.9.4.1.2 |  | 2025-02-10 08:00 | p | 1 |  | 2025-02-11 17:00
134 | 5359 | VhUQP0fhGYyFZ67e4nln | Normal | 2 | 1.9.4.1.3 | 1.9.4.1.3 |  | 2025-02-10 08:00 | p | 1 |  | 2025-02-11 17:00
135 | 7262 | dH18W6KApKWC8TAOWb50 | Normal | 36 | 1.7.4.1.4 | 1.7.4.1.4 |  | O | p |  |  | 2025-04-08 17:00
136 | 7260 | DPsh83rHAyIaiD8XYnO0 | Normal | 6 | 1.7.4.2.4 | 1.7.4.2.4 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
137 | 5375 | zkXPpJkHw8DPAtspwcmA | Summary | 124 | 1.9.4.4 | 1.9.4.4 |  | 2025-03-27 08:00 | p | 476 |  | 2026-07-16 08:00
138 | 5376 | zSTdFwWI5FOaluV37lYS | Normal | 63 | 1.9.4.4.1 | 1.9.4.4.1 |  | 2025-03-27 08:00 | p | 476 |  | 2026-07-16 08:00
139 | 5379 | 7aIIakNe0KPRF0TCK1un | Normal | 2 | 1.9.4.5.2 | 1.9.4.5.2 |  | 2025-02-10 08:00 | p | 1 |  | 2025-02-11 17:00
140 | 5381 | HgkAkSCruVdxdZyXC7sW | Normal | 4 | 1.9.4.5.4 | 1.9.4.5.4 |  | 2025-02-10 08:00 | p | 3 |  | 2025-02-13 17:00
141 | 5389 | 0FrUudkzBjpolAMz4tT0 | Normal | 2 | 1.9.4.6.2 | 1.9.4.6.2 |  | 2025-02-10 08:00 | p | 1 |  | 2025-02-11 17:00
142 | 5391 | rUGJjnqPCImSizDtYOdy | Normal | 4 | 1.9.4.6.4 | 1.9.4.6.4 |  | 2025-02-10 08:00 | p | 3 |  | 2025-02-13 17:00
143 | 6688 | aKOlgm9Tw9oPXF0YCFLp | Summary | 911 | 1.11 | 1.11 |  | 2017-06-07 08:00 | p | 0 |  | 2017-06-07 17:00
144 | 6689 | fEYxMDiPOAwjjU8zha5c | Normal | 396 | 1.11.1 | 1.11.1 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
145 | 6691 | xLErpFHjPEH3ifHRbBMY | Normal | 396 | 1.11.3 | 1.11.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
146 | 6692 | g8WcEZ6I6SGdlePHrYPP | Normal | 248 | 1.11.4 | 1.11.4 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
147 | 6695 | Bx0BPJ0BcPw49QEL7Psq | Normal | 313 | 1.11.8 | 1.11.8 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
148 | 6696 | XbFIp383UbA72xJPH4hJ | Normal | 101 | 1.11.9 | 1.11.9 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
149 | 6697 | gpkN7vTMpz4ZZxhDAmeL | Normal | 126 | 1.11.10 | 1.11.10 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
150 | 6698 | eRsel9yyFaDkcYLZgvjC | Normal | 142 | 1.11.11 | 1.11.11 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
151 | 6699 | k8943lu4TS9ZW2TcUvha | Normal | 256 | 1.11.12 | 1.11.12 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
152 | 7376 | FfEUU5kpALOu6FlmjosD | Normal | 396 | 1.10.3 | 1.10.3 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
153 | 7378 | YjoFZZooPnFRzsk2Ba2E | Normal | 288 | 1.10.6 | 1.10.6 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
154 | 7379 | 7GajZBAFakrGWC1WlgE6 | Normal | 142 | 1.10.14 | 1.10.14 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
155 | 7380 | wkyoOF6gHS9pA0Dm9pZY | Normal | 140 | 1.10.17 | 1.10.17 |  | 2025-02-10 08:00 | p | 29 |  | 2025-03-11 08:00
156 | 7551 | G4afE8kOleATkD8qyqeP | Normal | 1 | 1.10.19 | 1.10.19 |  | O | p |  |  | 2017-06-07 17:00
157 | 7131 | XTX9Wl5SzTxAD1rtsh9U | Summary | 0 | 1.10 | 1.10 |  | 2023-10-12 17:00 | q | -2114 |  | 2017-12-28 16:20

## Activity-Status
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Activity Status - 36 (2%) | Activity Status - 36 (2%) | Activity Status - 36 (2%) | Activity Status - 36 (2%) | Activity Status - 36 (2%) | Activity Status - 36 (2%) | Activity Status - 36 (2%) | Activity Status - 36 (2%) | Activity Status - 36 (2%) | Activity Status - 36 (2%) | Activity Status - 36 (2%) | Activity Status - 36 (2%) | Activity Status - 36 (2%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 7211 | wSDYMNBcPlclxMN6Hc8V | Normal | 5 | 1.3.2.3.2.3.1 | 1.3.2.3.2.3.1 |  | InProgress |  |  |  | Complete
2 | 7218 | 5fSpBiSdaCD1mvMsYs0j | Normal | 2 | 1.3.2.3.2.4.3 | 1.3.2.3.2.4.3 |  | InProgress |  |  |  | Complete
3 | 7219 | tMHxEODKuKminmE9Mjg5 | Normal | 1 | 1.3.2.3.2.4.4 | 1.3.2.3.2.4.4 |  | Planned |  |  |  | Complete
4 | 7226 | fsyu9CvTMAXTCK7e04ez | Normal | 1 | 1.3.2.3.2.5.3 | 1.3.2.3.2.5.3 |  | InProgress |  |  |  | Complete
5 | 7515 | jdxLrBmn54gbF5MbPNVU | Normal | 5 | 1.3.2.3.2.5.8 | 1.3.2.3.2.5.8 |  | InProgress |  |  |  | Complete
6 | 631 | jjFU6HpNq2otAi9zmRWR | Normal | 2 | 1.5.6.6.2.7 | 1.5.6.6.2.7 |  | InProgress |  |  |  | Complete
7 | 6141 | PCEOtJROHHMKXYkoR4rp | Normal | 3 | 1.5.6.5.1 | 1.5.6.5.1 |  | InProgress |  |  |  | Complete
8 | 1457 | W1XQ7yoZAeSgm7UftoXN | Normal | 1 | 1.5.5.1.2 | 1.5.5.1.2 |  | Planned |  |  |  | Complete
9 | 5627 | s0vjJX7zGlVyBdE0eigo | Summary | 15 | 1.5.2.2.8 | 1.5.2.2.8 |  | Planned |  |  |  | InProgress
10 | 7545 | 65jUkOPqlMfpoMROhJ4O | Normal | 5 | 1.5.3.2.9.1 | 1.5.3.2.9.1 |  | Planned |  |  |  | Complete
11 | 5635 | ZYzv9KOmVdYL2d3ZPb8b | Summary | 0 | 1.5.2.2.9 | 1.5.2.2.9 |  | Complete |  |  |  | InProgress
12 | 5637 | agdOsAK6kuG5dvRDXVyv | Milestone | 0 | 1.5.2.2.9.2 | 1.5.2.2.9.2 |  | Complete |  |  |  | Planned
13 | 5638 | jBSFjjY1RfmWgqa8tOlO | Normal | 0 | 1.5.2.2.9.3 | 1.5.2.2.9.3 |  | Complete |  |  |  | Planned
14 | 5639 | ymvGdGMdlU958QTwMU9V | Normal | 0 | 1.5.2.2.9.4 | 1.5.2.2.9.4 |  | Complete |  |  |  | Planned
15 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | Complete |  |  |  | Planned
16 | 1463 | IQX94tuow2VKmVJTuhEN | Normal | 1 | 1.6.6.1.3 | 1.6.6.1.3 |  | Planned |  |  |  | Complete
17 | 3973 | 00qHhBlTe8pinGtKpu3n | Normal | 4 | 1.6.4.6 | 1.6.4.6 |  | InProgress |  |  |  | Complete
18 | 6738 | XB1ZMgqMWvDJpnRGKTB3 | Normal | 3 | 1.6.4.18.3.3.2.10 | 1.6.4.18.3.3.2.10 |  | Planned |  |  |  | Complete
19 | 7003 | XfnOKCk0EbakXF7t35fN | Normal | 1 | 1.6.4.18.3.3.2.9 | 1.6.4.18.3.3.2.9 |  | InProgress |  |  |  | Complete
20 | 7270 | 3AlavOi01JfJwLM1b81K | Milestone | 0 | 1.6.4.18.3.3.2.6 | 1.6.4.18.3.3.2.6 |  | Planned |  |  |  | Complete
21 | 7277 | hIopgQViPH34dy6jPgEs | Normal | 6 | 1.6.4.18.3.3.7.5 | 1.6.4.18.3.3.7.5 |  | Planned |  |  |  | Complete
22 | 7295 | tyaakhlAtuOpVSt7bVvo | Normal | 1 | 1.6.4.18.3.3.6.2 | 1.6.4.18.3.3.6.2 |  | Planned |  |  |  | Complete
23 | 7312 | ZHpaj2955bjmxPKFBEf2 | Normal | 2 | 1.6.3.11.1.3.5.3 | 1.6.3.11.1.3.5.3 |  | Planned |  |  |  | Complete
24 | 1539 | ySsQ3GXU4tpHt4hn7HeO | Normal | 2 | 1.9.7.15.4 | 1.9.7.15.4 |  | InProgress |  |  |  | Complete
25 | 1540 | GIXHFfgJ4jA0lgUlb0GT | Normal | 1 | 1.9.7.15.5 | 1.9.7.15.5 |  | Planned |  |  |  | Complete
26 | 1560 | fBOtciokyA85OuE15WSO | Normal | 1 | 1.9.7.19.10 | 1.9.7.19.10 |  | InProgress |  |  |  | Complete
27 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | Planned |  |  |  | Complete
28 | 5533 | g1oQNBzKk6OrBukgGH7R | Normal | 40 | 1.9.5.1.3 | 1.9.5.1.3 |  | Planned |  |  |  | Complete
29 | 5358 | Tenn83cNUrlWZNLgXJG2 | Normal | 2 | 1.9.4.1.2 | 1.9.4.1.2 |  | InProgress |  |  |  | Complete
30 | 5359 | VhUQP0fhGYyFZ67e4nln | Normal | 2 | 1.9.4.1.3 | 1.9.4.1.3 |  | InProgress |  |  |  | Complete
31 | 7262 | dH18W6KApKWC8TAOWb50 | Normal | 36 | 1.7.4.1.4 | 1.7.4.1.4 |  | Planned |  |  |  | Complete
32 | 5379 | 7aIIakNe0KPRF0TCK1un | Normal | 2 | 1.9.4.5.2 | 1.9.4.5.2 |  | InProgress |  |  |  | Complete
33 | 5381 | HgkAkSCruVdxdZyXC7sW | Normal | 4 | 1.9.4.5.4 | 1.9.4.5.4 |  | InProgress |  |  |  | Complete
34 | 5389 | 0FrUudkzBjpolAMz4tT0 | Normal | 2 | 1.9.4.6.2 | 1.9.4.6.2 |  | InProgress |  |  |  | Complete
35 | 5391 | rUGJjnqPCImSizDtYOdy | Normal | 4 | 1.9.4.6.4 | 1.9.4.6.4 |  | InProgress |  |  |  | Complete
36 | 7551 | G4afE8kOleATkD8qyqeP | Normal | 1 | 1.10.19 | 1.10.19 |  | Planned |  |  |  | Complete

## Percent-Complete
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Percent Complete - 201 (9%) | Percent Complete - 201 (9%) | Percent Complete - 201 (9%) | Percent Complete - 201 (9%) | Percent Complete - 201 (9%) | Percent Complete - 201 (9%) | Percent Complete - 201 (9%) | Percent Complete - 201 (9%) | Percent Complete - 201 (9%) | Percent Complete - 201 (9%) | Percent Complete - 201 (9%) | Percent Complete - 201 (9%) | Percent Complete - 201 (9%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 1249 | v1zgYyoO7UpynPZXt29g | Summary | 611 | 1 | 1 |  | 0.79 | q | -0.02 | (-3%) | 0.77
2 | 147 | DEZpxiHWY7fkyvQEaEGc | Summary | 1132 | 1.2 | 1.2 |  | 0.61 | q | -0.01 | (-2%) | 0.6
3 | 179 | jSOjvYE1qiHOKdcV2ixu | Summary | 554 | 1.2.10 | 1.2.10 |  | 0.25 | p | 0.01 | -4% | 0.26
4 | 445 | cIIfBfMFMZUbJxswwNzj | Summary | 28 | 1.3.3.1.2.4 | 1.3.3.1.2.4 |  | 0.93 | q | -0.01 | (-1%) | 0.92
5 | 5768 | 9l9o7D6Il8vKVgGgZRMW | Summary | 197 | 1.3.3.4 | 1.3.3.4 |  | 0.5 | p | 0.02 | -4% | 0.52
6 | 6289 | NknbxY1EWobhbJ98SVRq | Summary | 270 | 1.3.2 | 1.3.2 |  | 0.63 | p | 0.01 | -2% | 0.64
7 | 3849 | PKYN5IsyqbTocjyswPFM | Normal | 17 | 1.3.2.1.1 | 1.3.2.1.1 |  | 0.96 | p | 0.01 | -1% | 0.97
8 | 3850 | sk2pEdmn2KeVBRyrQzgn | Summary | 233 | 1.3.2.1.2 | 1.3.2.1.2 |  | 0.47 | q | -0.01 | (-2%) | 0.46
9 | 3857 | FObPKa3HJ5KI4gFmAx2r | Summary | 210 | 1.3.2.1.2.2 | 1.3.2.1.2.2 |  | 0.24 | q | -0.01 | (-4%) | 0.23
10 | 3858 | pWvg9Owxac1jXAINT5hs | Normal | 24 | 1.3.2.1.2.2.1 | 1.3.2.1.2.2.1 |  | 0.7 | p | 0.04 | -6% | 0.74
11 | 3863 | WaF24jcpD2qzV3M05hSl | Summary | 178 | 1.3.2.1.2.3 | 1.3.2.1.2.3 |  | 0.52 | p | 0.01 | -2% | 0.53
12 | 7186 | ttl1FahPn0WwOuyGdmk6 | Summary | 138 | 1.3.2.3 | 1.3.2.3 |  | 0.5 | p | 0.01 | -2% | 0.51
13 | 7188 | yn5QOVI2BZ7jor10JaQN | Summary | 55 | 1.3.2.3.2 | 1.3.2.3.2 |  | 0.62 | p | 0.02 | -3% | 0.64
14 | 7189 | jup7puBG1dNvbV8jB14f | Summary | 69 | 1.3.2.3.2.1 | 1.3.2.3.2.1 |  | 0.52 | p | 0.03 | -6% | 0.55
15 | 7190 | Ob13piboJI4zFNOVPzZD | Summary | 50 | 1.3.2.3.2.1.1 | 1.3.2.3.2.1.1 |  | 0.48 | p | 0.04 | -8% | 0.52
16 | 7193 | hzdeRXxytBFeNJPq5eHn | Summary | 50 | 1.3.2.3.2.1.2 | 1.3.2.3.2.1.2 |  | 0.32 | p | 0.06 | -19% | 0.38
17 | 7205 | 688LmElxek6WZQ34zEgD | Summary | 40 | 1.3.2.3.2.2 | 1.3.2.3.2.2 |  | 0.51 | p | 0.01 | -2% | 0.52
18 | 7206 | bMXBNIC1fF7AjliDPdfr | Normal | 25 | 1.3.2.3.2.2.1 | 1.3.2.3.2.2.1 |  | 0.58 | p | 0.01 | -2% | 0.59
19 | 7210 | 5vpOUfvEpSU2AKPwltv0 | Summary | 14 | 1.3.2.3.2.3 | 1.3.2.3.2.3 |  | 0.84 | p | 0.08 | -10% | 0.92
20 | 7211 | wSDYMNBcPlclxMN6Hc8V | Normal | 5 | 1.3.2.3.2.3.1 | 1.3.2.3.2.3.1 |  | 0.94 | p | 0.06 | -6% | 1
21 | 7215 | a8OJFGtOVEyM75c9puYK | Summary | 34 | 1.3.2.3.2.4 | 1.3.2.3.2.4 |  | 0.52 | q | -0.01 | (-2%) | 0.51
22 | 7218 | 5fSpBiSdaCD1mvMsYs0j | Normal | 2 | 1.3.2.3.2.4.3 | 1.3.2.3.2.4.3 |  | 0.75 | p | 0.25 | -33% | 1
23 | 7219 | tMHxEODKuKminmE9Mjg5 | Normal | 1 | 1.3.2.3.2.4.4 | 1.3.2.3.2.4.4 |  | 0 | p | 1 |  | 1
24 | 7223 | 2cLCJpvBPh4ccgbvKrEi | Summary | 38 | 1.3.2.3.2.5 | 1.3.2.3.2.5 |  | 0.67 | p | 0.01 | -1% | 0.68
25 | 7226 | fsyu9CvTMAXTCK7e04ez | Normal | 1 | 1.3.2.3.2.5.3 | 1.3.2.3.2.5.3 |  | 0.96 | p | 0.04 | -4% | 1
26 | 7227 | QiFvht1v2EB9ODLdNK6M | Normal | 25 | 1.3.2.3.2.5.4 | 1.3.2.3.2.5.4 |  | 0.17 | q | -0.03 | (-18%) | 0.14
27 | 7515 | jdxLrBmn54gbF5MbPNVU | Normal | 5 | 1.3.2.3.2.5.8 | 1.3.2.3.2.5.8 |  | 0.5 | p | 0.5 | -100% | 1
28 | 622 | Q48N5ZSDLesB1Bsda2wx | Summary | 156 | 1.5.6.6.2 | 1.5.6.6.2 |  | 0.67 | p | 0.01 | -1% | 0.68
29 | 631 | jjFU6HpNq2otAi9zmRWR | Normal | 2 | 1.5.6.6.2.7 | 1.5.6.6.2.7 |  | 0.67 | p | 0.33 | -49% | 1
30 | 648 | 6WPgljRre9DjhHGVsVUH | Summary | 120 | 1.5.6.6.5 | 1.5.6.6.5 |  | 0.72 | q | -0.01 | (-1%) | 0.71
31 | 670 | zBtIFoyMK1KgXAv407C9 | Summary | 29 | 1.5.6.5 | 1.5.6.5 |  | 0.88 | p | 0.06 | -7% | 0.94
32 | 6141 | PCEOtJROHHMKXYkoR4rp | Normal | 3 | 1.5.6.5.1 | 1.5.6.5.1 |  | 0.93 | p | 0.07 | -8% | 1
33 | 1457 | W1XQ7yoZAeSgm7UftoXN | Normal | 1 | 1.5.5.1.2 | 1.5.5.1.2 |  | 0 | p | 1 |  | 1
34 | 3949 | knRWxUZkgPmXKgij09tb | Summary | 25 | 1.5.4.5 | 1.5.4.5 |  | 0.94 | q | -0.01 | (-1%) | 0.93
35 | 3950 | NJx1RMKdqhuNKRLGMSBQ | Summary | 27 | 1.5.4.5.1 | 1.5.4.5.1 |  | 0.92 | q | -0.01 | (-1%) | 0.91
36 | 3951 | BNWJw3sHADBJTHA2Ybu0 | Normal | 16 | 1.5.4.5.1.1 | 1.5.4.5.1.1 |  | 0.95 | q | -0.01 | (-1%) | 0.94
37 | 3964 | ZzcX1hV2BTbfmTYJl5AE | Summary | 19 | 1.5.4.5.4 | 1.5.4.5.4 |  | 0.95 | q | -0.01 | (-1%) | 0.94
38 | 3967 | BaECEBO5p44IeRhOgeK2 | Normal | 19 | 1.5.4.5.4.3 | 1.5.4.5.4.3 |  | 0.86 | q | -0.04 | (-5%) | 0.82
39 | 6202 | X3XRH6pSpuIgaacqwHSp | Normal | 14 | 1.5.4.4.10 | 1.5.4.4.10 |  | 0.94 | p | 0.01 | -1% | 0.95
40 | 6605 | Qtljmhuq3GHp8HrV3pPP | Normal | 6 | 1.5.4.4.7 | 1.5.4.4.7 |  | 0.88 | q | -0.03 | (-3%) | 0.85
41 | 6299 | JvNaxkj9UdrgV7BcBski | Summary | 134 | 1.5.1 | 1.5.1 |  | 0.82 | q | -0.01 | (-1%) | 0.81
42 | 6444 | XymP4MvJgra2aDdoc9vw | Normal | 46 | 1.5.1.1.2 | 1.5.1.1.2 |  | 0.92 | p | 0.01 | -1% | 0.93
43 | 6674 | 3EUoGYyEaAia67bx8maJ | Summary | 69 | 1.5.1.3 | 1.5.1.3 |  | 0.72 | q | -0.01 | (-1%) | 0.71
44 | 6680 | ttlvn3uwilh7nqgbHtE7 | Normal | 37 | 1.5.1.3.7 | 1.5.1.3.7 |  | 0.66 | q | -0.01 | (-2%) | 0.65
45 | 5611 | e3AOkT5PZcArPsKmcVqB | Summary | 48 | 1.5.2.2 | 1.5.2.2 |  | 0.94 | q | -0.01 | (-1%) | 0.93
46 | 5627 | s0vjJX7zGlVyBdE0eigo | Summary | 15 | 1.5.2.2.8 | 1.5.2.2.8 |  | 0 | p | 0.35 |  | 0.35
47 | 7545 | 65jUkOPqlMfpoMROhJ4O | Normal | 5 | 1.5.3.2.9.1 | 1.5.3.2.9.1 |  | 0 | p | 1 |  | 1
48 | 5635 | ZYzv9KOmVdYL2d3ZPb8b | Summary | 0 | 1.5.2.2.9 | 1.5.2.2.9 |  | 1 | q | -0.95 | (-95%) | 0.05
49 | 5637 | agdOsAK6kuG5dvRDXVyv | Milestone | 0 | 1.5.2.2.9.2 | 1.5.2.2.9.2 |  | 1 | q | -1 | (-100%) | 0
50 | 5638 | jBSFjjY1RfmWgqa8tOlO | Normal | 0 | 1.5.2.2.9.3 | 1.5.2.2.9.3 |  | 1 | q | -1 | (-100%) | 0
51 | 5639 | ymvGdGMdlU958QTwMU9V | Normal | 0 | 1.5.2.2.9.4 | 1.5.2.2.9.4 |  | 1 | q | -1 | (-100%) | 0
52 | 5640 | AvXXkRY6V61W0WFfD9tU | Normal | 0 | 1.5.2.2.9.5 | 1.5.2.2.9.5 |  | 1 | q | -1 | (-100%) | 0
53 | 6309 | taNk8S9bKnlDToaFycS6 | Summary | 37 | 1.5.3 | 1.5.3 |  | 0.88 | p | 0.01 | -1% | 0.89
54 | 5443 | L0xk8h495fvdhlwnri8N | Summary | 37 | 1.5.3.1 | 1.5.3.1 |  | 0.88 | p | 0.01 | -1% | 0.89
55 | 5445 | 95pLIsxhFDdrMJGVBrpQ | Summary | 35 | 1.5.3.1.2 | 1.5.3.1.2 |  | 0.18 | p | 0.02 | -11% | 0.2
56 | 6270 | Wwp4MRWhcV55WleZhe1f | Summary | 288 | 1.4 | 1.4 |  | 0.7 | q | -0.01 | (-1%) | 0.69
57 | 6290 | VuOK0YK760zOpXaJ9U7h | Summary | 140 | 1.4.3 | 1.4.3 |  | 0.85 | q | -0.02 | (-2%) | 0.83
58 | 4537 | FhESv2GOKRYErv6rS2Ko | Summary | 140 | 1.4.3.1 | 1.4.3.1 |  | 0.85 | q | -0.02 | (-2%) | 0.83
59 | 3891 | VQVEpj4HfOnKALplb4t9 | Summary | 43 | 1.4.1.1 | 1.4.1.1 |  | 0.88 | p | 0.01 | -1% | 0.89
60 | 3897 | cqWsQsQWdy7etYVMNQBf | Summary | 53 | 1.4.1.1.2 | 1.4.1.1.2 |  | 0.84 | p | 0.01 | -1% | 0.85
61 | 3900 | fYbjIfZDvkbYu7p7dq3N | Normal | 14 | 1.4.1.1.2.3 | 1.4.1.1.2.3 |  | 0.74 | p | 0.03 | -4% | 0.77
62 | 6318 | cM5VCGnPiK1mfNJo8YLF | Summary | 309 | 1.4.2 | 1.4.2 |  | 0.68 | q | -0.01 | (-1%) | 0.67
63 | 5226 | R9JO9mOSGmg0eoDimoJT | Summary | 71 | 1.4.2.1 | 1.4.2.1 |  | 0.89 | q | -0.01 | (-1%) | 0.88
64 | 5262 | PI0DE6xTKT4gLnHpqgjE | Summary | 137 | 1.4.2.1.6 | 1.4.2.1.6 |  | 0.62 | q | -0.03 | (-5%) | 0.59
65 | 5263 | URhzXaXmWu6rBPIMitrn | Normal | 30 | 1.4.2.1.6.1 | 1.4.2.1.6.1 |  | 0.87 | q | -0.01 | (-1%) | 0.86
66 | 6271 | Q6QswYSvhipRUbZBXuiu | Summary | 315 | 1.6 | 1.6 |  | 0.84 | q | -0.02 | (-2%) | 0.82
67 | 6277 | moVS9Ou3GclDwNSW1OnS | Summary | 264 | 1.6.7 | 1.6.7 |  | 0.77 | q | -0.02 | (-3%) | 0.75
68 | 700 | PZaQwD8fp0dlxZIxEZEd | Normal | 279 | 1.6.7.10 | 1.6.7.10 |  | 0.64 | q | -0.03 | (-5%) | 0.61
69 | 728 | 4dRz6TQj3FOK8lstTqZK | Summary | 396 | 1.6.7.9 | 1.6.7.9 |  | 0.38 | q | -0.01 | (-3%) | 0.37
70 | 6323 | aU24Z8SrLl20SyyllZuy | Summary | 80 | 1.6.7.9.3.5 | 1.6.7.9.3.5 |  | 0.63 | p | 0.05 | -8% | 0.68
71 | 6434 | cc8WGEqtonq4zOxPHtWc | Normal | 65 | 1.6.7.8.4 | 1.6.7.8.4 |  | 0.31 | p | 0.01 | -3% | 0.32
72 | 6284 | T6s1mlIi1Lu4cscBpq9h | Summary | 273 | 1.6.6 | 1.6.6 |  | 0.39 | q | -0.04 | (-10%) | 0.35
73 | 1519 | Ig6aeqJATmPNbReGQrzj | Summary | 273 | 1.6.6.1 | 1.6.6.1 |  | 0.39 | q | -0.04 | (-10%) | 0.35
74 | 1463 | IQX94tuow2VKmVJTuhEN | Normal | 1 | 1.6.6.1.3 | 1.6.6.1.3 |  | 0 | p | 1 |  | 1
75 | 3929 | GkmiaraCbWdBUaRv136y | Summary | 19 | 1.6.4.15 | 1.6.4.15 |  | 0.94 | p | 0.02 | -2% | 0.96
76 | 3938 | 2iJ091mlhEkJyqoddB4L | Normal | 14 | 1.6.4.15.1 | 1.6.4.15.1 |  | 0.95 | p | 0.02 | -2% | 0.97
77 | 3931 | GleHIX38gd9vOXaUQYVA | Normal | 33 | 1.6.4.11 | 1.6.4.11 |  | 0.91 | p | 0.01 | -1% | 0.92
78 | 3933 | FbGZSJQTtuDZR2p8qmxq | Normal | 33 | 1.6.4.13 | 1.6.4.13 |  | 0.91 | q | -0.02 | (-2%) | 0.89
79 | 3939 | cuQ4HC0Kn3S6GTvqv7QE | Normal | 33 | 1.6.4.14 | 1.6.4.14 |  | 0.91 | q | -0.03 | (-3%) | 0.88
80 | 3981 | YTm9sByrDxPUc7AlWXh1 | Normal | 15 | 1.6.4.7.2 | 1.6.4.7.2 |  | 0.92 | p | 0.01 | -1% | 0.93
81 | 3973 | 00qHhBlTe8pinGtKpu3n | Normal | 4 | 1.6.4.6 | 1.6.4.6 |  | 0.99 | p | 0.01 | -1% | 1
82 | 3980 | po54OWwjtqomy5uOkFBU | Normal | 40 | 1.6.4.4 | 1.6.4.4 |  | 0.87 | q | -0.01 | (-1%) | 0.86
83 | 3991 | kc0LQmDrjfLGJeMU4QIH | Summary | 70 | 1.6.4.17 | 1.6.4.17 |  | 0.84 | q | -0.01 | (-1%) | 0.83
84 | 4002 | nJzh0eFJGsqvOmQRJzHn | Summary | 27 | 1.6.4.17.2 | 1.6.4.17.2 |  | 0.9 | q | -0.01 | (-1%) | 0.89
85 | 4003 | gjf3v6NdOQannovTvAoE | Normal | 19 | 1.6.4.17.2.1 | 1.6.4.17.2.1 |  | 0.93 | q | -0.01 | (-1%) | 0.92
86 | 4012 | A4Ck0Reyqf4cLzrM8uUY | Summary | 206 | 1.6.4.19 | 1.6.4.19 |  | 0.65 | q | -0.01 | (-2%) | 0.64
87 | 5748 | cHP8KcDQZp8MvOi5a8Wj | Summary | 64 | 1.6.4.18 | 1.6.4.18 |  | 0.83 | p | 0.02 | -2% | 0.85
88 | 6701 | vwWJ3SVwW3tYdDDMDgOK | Summary | 60 | 1.6.4.18.3 | 1.6.4.18.3 |  | 0.72 | p | 0.03 | -4% | 0.75
89 | 6713 | JQXHTZXJblKyiNyxM0eT | Summary | 78 | 1.6.4.18.3.3 | 1.6.4.18.3.3 |  | 0.62 | p | 0.04 | -6% | 0.66
90 | 6727 | 5BlmDU3ct4fwjT54EODG | Summary | 21 | 1.6.4.18.3.3.2 | 1.6.4.18.3.3.2 |  | 0.78 | p | 0.07 | -9% | 0.85
91 | 6738 | XB1ZMgqMWvDJpnRGKTB3 | Normal | 3 | 1.6.4.18.3.3.2.10 | 1.6.4.18.3.3.2.10 |  | 0 | p | 1 |  | 1
92 | 7003 | XfnOKCk0EbakXF7t35fN | Normal | 1 | 1.6.4.18.3.3.2.9 | 1.6.4.18.3.3.2.9 |  | 0.97 | p | 0.03 | -3% | 1
93 | 7270 | 3AlavOi01JfJwLM1b81K | Milestone | 0 | 1.6.4.18.3.3.2.6 | 1.6.4.18.3.3.2.6 |  | 0 | p | 1 |  | 1
94 | 7007 | 9uputDeZmGdSlUY8oN4J | Summary | 64 | 1.6.4.18.3.3.4 | 1.6.4.18.3.3.4 |  | 0.44 | p | 0.11 | -25% | 0.55
95 | 7277 | hIopgQViPH34dy6jPgEs | Normal | 6 | 1.6.4.18.3.3.7.5 | 1.6.4.18.3.3.7.5 |  | 0 | p | 1 |  | 1
96 | 7295 | tyaakhlAtuOpVSt7bVvo | Normal | 1 | 1.6.4.18.3.3.6.2 | 1.6.4.18.3.3.6.2 |  | 0 | p | 1 |  | 1
97 | 6297 | AqdIsKbIPOfZJkjKYjnG | Summary | 118 | 1.6.1 | 1.6.1 |  | 0.87 | p | 0.01 | -1% | 0.88
98 | 4209 | 0Ck6gz1ZilLs9fM0b7nU | Summary | 46 | 1.6.1.3 | 1.6.1.3 |  | 0.92 | p | 0.01 | -1% | 0.93
99 | 4212 | yktUOUuzQyzOVBFBfL42 | Normal | 46 | 1.6.1.3.1 | 1.6.1.3.1 |  | 0.92 | p | 0.01 | -1% | 0.93
100 | 6311 | tQdu1pFxVkY2bj5IQjxI | Summary | 77 | 1.6.3 | 1.6.3 |  | 0.95 | q | -0.06 | (-6%) | 0.89
101 | 5452 | u9nFTwEoKsBrgeg8njOT | Normal | 5 | 1.6.3.1 | 1.6.3.1 |  | 0.99 | q | -0.2 | (-20%) | 0.79
102 | 5506 | wLM81Xdu8B5geOMMQz6m | Summary | 119 | 1.6.3.3 | 1.6.3.3 |  | 0.54 | p | 0.01 | -2% | 0.55
103 | 6890 | QKIolSsTnUWZiIhR6M5v | Normal | 40 | 1.6.3.3.1 | 1.6.3.3.1 |  | 0.76 | p | 0.05 | -7% | 0.81
104 | 6359 | hvfa0617w1FgmEnjjKwJ | Summary | 26 | 1.7.2.16 | 1.7.2.16 |  | 0.86 | p | 0.01 | -1% | 0.87
105 | 6360 | DMXbIVCeMtVR5pi4d5UN | Summary | 26 | 1.7.2.16.1 | 1.7.2.16.1 |  | 0.86 | p | 0.01 | -1% | 0.87
106 | 6361 | VEKeY9azNIVSZDSjYyKy | Summary | 33 | 1.7.2.16.1.3 | 1.7.2.16.1.3 |  | 0.83 | p | 0.01 | -1% | 0.84
107 | 7303 | fpLHmKjlfpy4s4tap5Xw | Summary | 39 | 1.6.3.11.1.3.4 | 1.6.3.11.1.3.4 |  | 0.46 | p | 0.03 | -7% | 0.49
108 | 7309 | 19skeJKmh3pRSfTF3DDB | Summary | 30 | 1.6.3.11.1.3.5 | 1.6.3.11.1.3.5 |  | 0.53 | p | 0.08 | -15% | 0.61
109 | 7312 | ZHpaj2955bjmxPKFBEf2 | Normal | 2 | 1.6.3.11.1.3.5.3 | 1.6.3.11.1.3.5.3 |  | 0 | p | 1 |  | 1
110 | 7315 | 9LywAxRsXdHsCrCcjGKV | Summary | 27 | 1.6.3.11.1.3.6 | 1.6.3.11.1.3.6 |  | 0.57 | q | -0.01 | (-2%) | 0.56
111 | 6074 | fkBL64dyW7paLwgGr0ue | Normal | 212 | 1.8.2.3 | 1.8.2.3 |  | 0.64 | p | 0.01 | -2% | 0.65
112 | 6075 | pe2nScqRc5pgTwGaT5Zd | Normal | 193 | 1.8.2.2 | 1.8.2.2 |  | 0.66 | q | -0.01 | (-2%) | 0.65
113 | 3723 | 4qmbzAmtSx0gvDVaBsYe | Summary | 239 | 1.8.5.1.5 | 1.8.5.1.5 |  | 0.28 | p | 0.01 | -4% | 0.29
114 | 3725 | 8cgOIQk4rBKvjXdBm8mF | Normal | 91 | 1.8.5.1.5.9 | 1.8.5.1.5.9 |  | 0.55 | p | 0.07 | -13% | 0.62
115 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 0.82 | q | -0.03 | (-4%) | 0.79
116 | 6418 | W9pbV5i9WFkdVEGtW75H | Normal | 45 | 1.9.9.7.2.5 | 1.9.9.7.2.5 |  | 0.1 | p | 0.01 | -10% | 0.11
117 | 870 | m3oEXpasu7ssfpw9dqLv | Summary | 267 | 1.9.9.14 | 1.9.9.14 |  | 0.67 | q | -0.01 | (-1%) | 0.66
118 | 6128 | 7jXaekqqhUCDWSDfnxzo | Summary | 28 | 1.7.4.2 | 1.7.4.2 |  | 0.87 | q | -0.01 | (-1%) | 0.86
119 | 6279 | p7EJXT1muDSglD2OZLFH | Summary | 274 | 1.9.7 | 1.9.7 |  | 0.76 | q | -0.05 | (-7%) | 0.71
120 | 1484 | 6ARiGRg3KLswRpJLOmGD | Summary | 229 | 1.9.7.18 | 1.9.7.18 |  | 0.55 | q | -0.01 | (-2%) | 0.54
121 | 1508 | SDZ1pqYbdynEzXZrWujj | Normal | 30 | 1.9.7.6 | 1.9.7.6 |  | 0.9 | p | 0.01 | -1% | 0.91
122 | 1529 | WOa3B8SPUOSM5ThLE2Jo | Summary | 69 | 1.9.7.14 | 1.9.7.14 |  | 0.74 | q | -0.01 | (-1%) | 0.73
123 | 1535 | vIOpwJGhGrQ4pKl5nahR | Summary | 61 | 1.9.7.15 | 1.9.7.15 |  | 0.85 | p | 0.01 | -1% | 0.86
124 | 1539 | ySsQ3GXU4tpHt4hn7HeO | Normal | 2 | 1.9.7.15.4 | 1.9.7.15.4 |  | 0.99 | p | 0.01 | -1% | 1
125 | 1540 | GIXHFfgJ4jA0lgUlb0GT | Normal | 1 | 1.9.7.15.5 | 1.9.7.15.5 |  | 0 | p | 1 |  | 1
126 | 1544 | dYtuUpkdltDWUtvWJGdC | Summary | 80 | 1.9.7.16 | 1.9.7.16 |  | 0.79 | q | -0.55 | (-70%) | 0.24
127 | 1560 | fBOtciokyA85OuE15WSO | Normal | 1 | 1.9.7.19.10 | 1.9.7.19.10 |  | 0.99 | p | 0.01 | -1% | 1
128 | 4574 | z7UYZlhr663oN8lfFWmH | Summary | 29 | 1.9.7.11 | 1.9.7.11 |  | 0.93 | q | -0.01 | (-1%) | 0.92
129 | 4581 | FxGRGf2kppDMdfFrZkS4 | Normal | 36 | 1.9.7.12 | 1.9.7.12 |  | 0.14 | p | 0.03 | -21% | 0.17
130 | 7323 | p8rF5Tk8321hO30p5zSy | Summary | 79 | 1.7.8.18 | 1.7.8.18 |  | 0.24 | q | -0.01 | (-4%) | 0.23
131 | 6285 | 0inPdnysTnfuJeCJJEwo | Summary | 131 | 1.9.1 | 1.9.1 |  | 0.77 | p | 0.01 | -1% | 0.78
132 | 4615 | Io6EVgFdyRjG7CB2g0Wy | Summary | 98 | 1.7.3.4 | 1.7.3.4 |  | 0.72 | p | 0.01 | -1% | 0.73
133 | 4626 | 92oajspBBxTpnlNQO91I | Summary | 90 | 1.7.3.6 | 1.7.3.6 |  | 0.79 | p | 0.01 | -1% | 0.8
134 | 4637 | ohQUE8EwZLGEmkE5FTpA | Summary | 8 | 1.7.3.7 | 1.7.3.7 |  | 0.97 | p | 0.01 | -1% | 0.98
135 | 6608 | ifCvUSq9UjUAw7FKKXTR | Normal | 14 | 1.7.3.7.3 | 1.7.3.7.3 |  | 0.94 | p | 0.01 | -1% | 0.95
136 | 3776 | GHLE38QRMYNBeSYAGB18 | Normal | 32 | 1.7.1.2.6.3 | 1.7.1.2.6.3 |  | 0.14 | q | -0.01 | (-7%) | 0.13
137 | 3790 | Om0YwWoKF5usOVLnDccR | Summary | 13 | 1.7.1.3.4 | 1.7.1.3.4 |  | 0.97 | q | -0.01 | (-1%) | 0.96
138 | 3803 | vx1oFVBFPqydBxZJ7V4g | Summary | 112 | 1.7.1.5 | 1.7.1.5 |  | 0.75 | q | -0.03 | (-4%) | 0.72
139 | 3808 | mNtnU9AYiACOeBrTPE9f | Summary | 29 | 1.7.1.5.3 | 1.7.1.5.3 |  | 0.86 | p | 0.02 | -2% | 0.88
140 | 6147 | BUcWclFVChflBnUDJ9UM | Normal | 40 | 1.7.1.5.4 | 1.7.1.5.4 |  | 0.54 | q | -0.09 | (-17%) | 0.45
141 | 6148 | V03eKqopjAXoUvRodLvQ | Normal | 13 | 1.7.1.5.6 | 1.7.1.5.6 |  | 0.52 | q | -0.01 | (-2%) | 0.51
142 | 4078 | ybbKeBChK3D60QzH8ONZ | Normal | 76 | 1.9.6.5 | 1.9.6.5 |  | 0.57 | p | 0.01 | -2% | 0.58
143 | 4129 | G6dPcJRrq5zqLYx4Vr0R | Summary | 475 | 1.9.6.10 | 1.9.6.10 |  | 0.33 | q | -0.01 | (-3%) | 0.32
144 | 4135 | 0voiyAtBe9AzaXfs8cVF | Summary | 322 | 1.9.6.11.1 | 1.9.6.11.1 |  | 0.55 | p | 0.01 | -2% | 0.56
145 | 4136 | bllhlvXmXgF1yFG9Nwfe | Normal | 16 | 1.9.6.11.1.1 | 1.9.6.11.1.1 |  | 0.8 | q | -0.01 | (-1%) | 0.79
146 | 5753 | ZptYdARXANY2IOcoHhB1 | Summary | 78 | 1.9.6.1 | 1.9.6.1 |  | 0.84 | p | 0.03 | -4% | 0.87
147 | 6956 | orfutluYygtdxEqDFdAs | Normal | 20 | 1.9.6.1.3 | 1.9.6.1.3 |  | 0 | p | 1 |  | 1
148 | 6296 | SlR21lje1Tex9DLMlAM1 | Summary | 222 | 1.9.8 | 1.9.8 |  | 0.82 | p | 0.01 | -1% | 0.83
149 | 4192 | vUDAXlHZqbmK6WAsX9hH | Summary | 139 | 1.9.8.1 | 1.9.8.1 |  | 0.85 | p | 0.03 | -4% | 0.88
150 | 4197 | 4xVk2zrTd9sJnt9BJFir | Summary | 36 | 1.9.8.1.6 | 1.9.8.1.6 |  | 0.86 | q | -0.05 | (-6%) | 0.81
151 | 4222 | uotgqiCu1xVBvHdpBC3E | Summary | 97 | 1.9.8.2 | 1.9.8.2 |  | 0.83 | p | 0.05 | -6% | 0.88
152 | 4238 | ReJqSs3gutB053iVY5c7 | Summary | 76 | 1.9.8.4 | 1.9.8.4 |  | 0.86 | q | -0.01 | (-1%) | 0.85
153 | 4242 | RIVyyga7UReDeuixs5m9 | Normal | 66 | 1.9.8.4.4 | 1.9.8.4.4 |  | 0.81 | q | -0.02 | (-2%) | 0.79
154 | 6314 | PaZTrKFuMaJQzXHDclW5 | Summary | 34 | 1.9.2 | 1.9.2 |  | 0.93 | q | -0.02 | (-2%) | 0.91
155 | 5666 | lc2LPCzbTjVw9vZ8eS89 | Summary | 23 | 1.9.2.2 | 1.9.2.2 |  | 0.94 | q | -0.04 | (-4%) | 0.9
156 | 5667 | chBvra0KGhqU3lfHBAI4 | Summary | 23 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 0.94 | q | -0.04 | (-4%) | 0.9
157 | 5669 | bBSx7g3AuM8uxZcIYlIi | Normal | 20 | B.OZ619.AAL.11 | B.OZ619.AAL.11 |  | 0.81 | q | -0.11 | (-14%) | 0.7
158 | 6315 | 2iW64uJmzViIcLEo0dMn | Summary | 181 | 1.9.5 | 1.9.5 |  | 0.86 | q | -0.08 | (-9%) | 0.78
159 | 5532 | NHN4dwEEPEqCDqA4Rwlr | Summary | 74 | 1.9.5.1 | 1.9.5.1 |  | 0.78 | p | 0.07 | -9% | 0.85
160 | 5533 | g1oQNBzKk6OrBukgGH7R | Normal | 40 | 1.9.5.1.3 | 1.9.5.1.3 |  | 0 | p | 1 |  | 1
161 | 5535 | XVk7S0ldLHQUWflKhMBn | Normal | 11 | 1.9.5.1.2 | 1.9.5.1.2 |  | 0.83 | p | 0.02 | -2% | 0.85
162 | 5537 | 9xVQhmyTVkChMoMOy91g | Summary | 193 | 1.9.5.2 | 1.9.5.2 |  | 0.65 | q | -0.17 | (-26%) | 0.48
163 | 5539 | kRsO3PSMDsMxji3dmdNc | Normal | 5 | 1.9.5.2.2 | 1.9.5.2.2 |  | 0.99 | q | -0.62 | (-63%) | 0.37
164 | 5540 | GKx3XnA1BSbhTsgdKbqP | Normal | 14 | 1.9.5.2.8 | 1.9.5.2.8 |  | 0.88 | q | -0.03 | (-3%) | 0.85
165 | 5543 | XaHBDo6QUBfyTg5ESk7j | Normal | 15 | 1.9.5.2.9 | 1.9.5.2.9 |  | 0.9 | q | -0.03 | (-3%) | 0.87
166 | 5570 | MuDwSgsBJjDxwFkSMWYJ | Summary | 116 | 1.9.5.2.11 | 1.9.5.2.11 |  | 0.33 | p | 0.02 | -6% | 0.35
167 | 6528 | LROLnQke0gWnMONa67YB | Summary | 50 | 1.9.5.2.5 | 1.9.5.2.5 |  | 0.58 | q | -0.01 | (-2%) | 0.57
168 | 6531 | iX155TL3hNg9Ca4Bsb4A | Normal | 35 | 1.9.5.2.5.2 | 1.9.5.2.5.2 |  | 0.45 | q | -0.01 | (-2%) | 0.44
169 | 6997 | MBGoTUikAECGvIHYk1uV | Normal | 24 | 1.9.5.2.3 | 1.9.5.2.3 |  | 0.51 | p | 0.01 | -2% | 0.52
170 | 6189 | OaskfHPb0rGXxqxmUlvr | Summary | 69 | 1.7.2.7 | 1.7.2.7 |  | 0.94 | q | -0.01 | (-1%) | 0.93
171 | 6248 | DGpV8AP7Q4dyYuiDaoIl | Summary | 56 | 1.7.2.7.2 | 1.7.2.7.2 |  | 0.86 | q | -0.02 | (-2%) | 0.84
172 | 6251 | Ha7ZmVRhPp4EjAGEFQOQ | Normal | 56 | 1.7.2.7.2.3 | 1.7.2.7.2.3 |  | 0.71 | q | -0.03 | (-4%) | 0.68
173 | 6259 | q6ww59eaDtL5Df1J4lsR | Normal | 14 | 1.7.2.7.4.3 | 1.7.2.7.4.3 |  | 0.91 | q | -0.01 | (-1%) | 0.9
174 | 6260 | nYwGXpoj6WqcdUPfZoTk | Summary | 14 | 1.7.2.7.5 | 1.7.2.7.5 |  | 0.96 | q | -0.01 | (-1%) | 0.95
175 | 6263 | aKytB1b2oD2t1WVaznUP | Normal | 14 | 1.7.2.7.5.3 | 1.7.2.7.5.3 |  | 0.91 | q | -0.02 | (-2%) | 0.89
176 | 6317 | NzqiT3qChWGoVO5Oxj9C | Summary | 111 | 1.9.4 | 1.9.4 |  | 0.89 | q | -0.05 | (-6%) | 0.84
177 | 5355 | lohINUHwZqjP23W1PYQO | Summary | 26 | 1.9.4.1 | 1.9.4.1 |  | 0.97 | p | 0.02 | -2% | 0.99
178 | 5358 | Tenn83cNUrlWZNLgXJG2 | Normal | 2 | 1.9.4.1.2 | 1.9.4.1.2 |  | 0.99 | p | 0.01 | -1% | 1
179 | 5359 | VhUQP0fhGYyFZ67e4nln | Normal | 2 | 1.9.4.1.3 | 1.9.4.1.3 |  | 0.99 | p | 0.01 | -1% | 1
180 | 7262 | dH18W6KApKWC8TAOWb50 | Normal | 36 | 1.7.4.1.4 | 1.7.4.1.4 |  | 0 | p | 1 |  | 1
181 | 5362 | 4bsxfawvV6TKTvCq9VoB | Summary | 6 | 1.9.4.2 | 1.9.4.2 |  | 0.99 | q | -0.18 | (-18%) | 0.81
182 | 7260 | DPsh83rHAyIaiD8XYnO0 | Normal | 6 | 1.7.4.2.4 | 1.7.4.2.4 |  | 0.83 | q | -0.75 | (-90%) | 0.08
183 | 5375 | zkXPpJkHw8DPAtspwcmA | Summary | 124 | 1.9.4.4 | 1.9.4.4 |  | 0.74 | p | 0.02 | -3% | 0.76
184 | 5376 | zSTdFwWI5FOaluV37lYS | Normal | 63 | 1.9.4.4.1 | 1.9.4.4.1 |  | 0.74 | p | 0.02 | -3% | 0.76
185 | 5377 | Wv5w7NMYDRM71nE6dVi0 | Summary | 58 | 1.9.4.5 | 1.9.4.5 |  | 0.66 | p | 0.02 | -3% | 0.68
186 | 5379 | 7aIIakNe0KPRF0TCK1un | Normal | 2 | 1.9.4.5.2 | 1.9.4.5.2 |  | 0.97 | p | 0.03 | -3% | 1
187 | 5381 | HgkAkSCruVdxdZyXC7sW | Normal | 4 | 1.9.4.5.4 | 1.9.4.5.4 |  | 0.79 | p | 0.21 | -27% | 1
188 | 5387 | 9gTKo9vjb1rQAbWcTOOW | Summary | 58 | 1.9.4.6 | 1.9.4.6 |  | 0.66 | p | 0.04 | -6% | 0.7
189 | 5389 | 0FrUudkzBjpolAMz4tT0 | Normal | 2 | 1.9.4.6.2 | 1.9.4.6.2 |  | 0.97 | p | 0.03 | -3% | 1
190 | 5391 | rUGJjnqPCImSizDtYOdy | Normal | 4 | 1.9.4.6.4 | 1.9.4.6.4 |  | 0.79 | p | 0.21 | -27% | 1
191 | 6689 | fEYxMDiPOAwjjU8zha5c | Normal | 396 | 1.11.1 | 1.11.1 |  | 0.3 | p | 0.07 | -23% | 0.37
192 | 6691 | xLErpFHjPEH3ifHRbBMY | Normal | 396 | 1.11.3 | 1.11.3 |  | 0.3 | q | -0.04 | (-13%) | 0.26
193 | 6692 | g8WcEZ6I6SGdlePHrYPP | Normal | 248 | 1.11.4 | 1.11.4 |  | 0.41 | q | -0.02 | (-5%) | 0.39
194 | 6695 | Bx0BPJ0BcPw49QEL7Psq | Normal | 313 | 1.11.8 | 1.11.8 |  | 0.45 | p | 0.06 | -13% | 0.51
195 | 6698 | eRsel9yyFaDkcYLZgvjC | Normal | 142 | 1.11.11 | 1.11.11 |  | 0.64 | q | -0.01 | (-2%) | 0.63
196 | 6699 | k8943lu4TS9ZW2TcUvha | Normal | 256 | 1.11.12 | 1.11.12 |  | 0.36 | q | -0.03 | (-8%) | 0.33
197 | 7376 | FfEUU5kpALOu6FlmjosD | Normal | 396 | 1.10.3 | 1.10.3 |  | 0.79 | q | -0.01 | (-1%) | 0.78
198 | 7378 | YjoFZZooPnFRzsk2Ba2E | Normal | 288 | 1.10.6 | 1.10.6 |  | 0.84 | q | -0.04 | (-5%) | 0.8
199 | 7379 | 7GajZBAFakrGWC1WlgE6 | Normal | 142 | 1.10.14 | 1.10.14 |  | 0.86 | p | 0.04 | -5% | 0.9
200 | 7380 | wkyoOF6gHS9pA0Dm9pZY | Normal | 140 | 1.10.17 | 1.10.17 |  | 0.81 | p | 0.02 | -2% | 0.83
201 | 7551 | G4afE8kOleATkD8qyqeP | Normal | 1 | 1.10.19 | 1.10.19 |  | 0 | p | 1 |  | 1

## Physical---Complete
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2

## Critical
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Critical - 176 (8%) | Critical - 176 (8%) | Critical - 176 (8%) | Critical - 176 (8%) | Critical - 176 (8%) | Critical - 176 (8%) | Critical - 176 (8%) | Critical - 176 (8%) | Critical - 176 (8%) | Critical - 176 (8%) | Critical - 176 (8%) | Critical - 176 (8%) | Critical - 176 (8%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 152 | QJ29ZvAvtEjBcpqHDer1 | Milestone | 0 | 1.2.3 | 1.2.3 |  | O |  |  |  | P
2 | 6874 | 1XFpbhK6U752FQe8voXZ | Normal | 1 | 1.2.7.6 | 1.2.7.6 |  | O |  |  |  | P
3 | 6879 | Vbp0cBOXY9azJeyTE4S4 | Normal | 3 | 1.2.7.7 | 1.2.7.7 |  | O |  |  |  | P
4 | 7550 | fUEnUBwdI1z3bgOngjaQ | Milestone | 0 | 1.2.7.5 | 1.2.7.5 |  | P |  |  |  | O
5 | 150 | 7cu6yvdJV8ndF0CYMHk8 | Milestone | 0 | 1.1 | 1.1 |  | O |  |  |  | P
6 | 6278 | SNMcp7h74WVvBiN3lPNB | Summary | 66 | 1.5.6 | 1.5.6 |  | O |  |  |  | P
7 | 620 | q8advjPa5PEndSFXJ05j | Summary | 158 | 1.5.6.6 | 1.5.6.6 |  | O |  |  |  | P
8 | 622 | Q48N5ZSDLesB1Bsda2wx | Summary | 156 | 1.5.6.6.2 | 1.5.6.6.2 |  | O |  |  |  | P
9 | 633 | FgJ5XjjThZN85XQOJ0nJ | Normal | 21 | 1.5.6.6.2.10 | 1.5.6.6.2.10 |  | O |  |  |  | P
10 | 634 | o4DRQRcsScdVmCSXNbxF | Normal | 10 | 1.5.6.6.2.9 | 1.5.6.6.2.9 |  | O |  |  |  | P
11 | 635 | ztvy5zkS4z9HirKgvHGY | Normal | 20 | 1.5.6.6.2.11 | 1.5.6.6.2.11 |  | O |  |  |  | P
12 | 636 | ZpIfqMwIaczq2BqznW2q | Normal | 6 | 1.5.6.6.2.12 | 1.5.6.6.2.12 |  | O |  |  |  | P
13 | 637 | 3VAZwvp2NS6usl0wrvOM | Normal | 7 | 1.5.6.6.2.13 | 1.5.6.6.2.13 |  | O |  |  |  | P
14 | 638 | 34zoFClD9RS7gLTCPZs0 | Normal | 5 | 1.5.6.6.2.14 | 1.5.6.6.2.14 |  | O |  |  |  | P
15 | 640 | 10AmMHkCz4b8n0xqbyCt | Normal | 5 | 1.5.6.6.2.16 | 1.5.6.6.2.16 |  | O |  |  |  | P
16 | 641 | KUqcSNVxncHPLVJNV5ca | Normal | 2 | 1.5.6.6.2.17 | 1.5.6.6.2.17 |  | O |  |  |  | P
17 | 642 | chCwawHUqn0ea2ArCnKB | Normal | 0 | 1.5.6.6.2.18 | 1.5.6.6.2.18 |  | O |  |  |  | P
18 | 643 | xZBRzE3QVYmQCjnzxLQv | Normal | 4 | 1.5.6.6.2.19 | 1.5.6.6.2.19 |  | O |  |  |  | P
19 | 644 | tUTeQ74YpmkuuOiouSXU | Normal | 5 | 1.5.6.6.2.20 | 1.5.6.6.2.20 |  | O |  |  |  | P
20 | 645 | mSrjcTZmK12EdJmOEYFi | Normal | 1 | 1.5.6.6.2.21 | 1.5.6.6.2.21 |  | O |  |  |  | P
21 | 646 | Haue3rYYySw3jbXWnBeq | Normal | 3 | 1.5.6.6.3 | 1.5.6.6.3 |  | O |  |  |  | P
22 | 647 | 6jlP0Y4QQ5KPQWxvolLg | Normal | 1 | 1.5.6.6.4 | 1.5.6.6.4 |  | O |  |  |  | P
23 | 648 | 6WPgljRre9DjhHGVsVUH | Summary | 120 | 1.5.6.6.5 | 1.5.6.6.5 |  | O |  |  |  | P
24 | 656 | lzPFAx9Fh8cDxyQ3uxFX | Normal | 1 | 1.5.6.6.5.3 | 1.5.6.6.5.3 |  | O |  |  |  | P
25 | 657 | nePaKBbqDo6OltylvukE | Summary | 14 | 1.5.6.6.5.4 | 1.5.6.6.5.4 |  | O |  |  |  | P
26 | 658 | PyBKEPMZMe2YeOC66yut | Normal | 11 | 1.5.6.6.5.4.1 | 1.5.6.6.5.4.1 |  | O |  |  |  | P
27 | 664 | H1KB0K8mM12Opvc4oDP1 | Normal | 3 | 1.5.6.6.5.4.2 | 1.5.6.6.5.4.2 |  | O |  |  |  | P
28 | 665 | FIEbexlYHnOcZkEBs7WM | Normal | 5 | 1.5.6.6.5.5 | 1.5.6.6.5.5 |  | O |  |  |  | P
29 | 666 | OcAHNnZWZgiwxfUiheGU | Normal | 5 | 1.5.6.6.5.6 | 1.5.6.6.5.6 |  | O |  |  |  | P
30 | 667 | HPj21Hyun1nWvxJOQMhf | Normal | 28 | 1.5.6.6.5.7 | 1.5.6.6.5.7 |  | O |  |  |  | P
31 | 670 | zBtIFoyMK1KgXAv407C9 | Summary | 29 | 1.5.6.5 | 1.5.6.5 |  | O |  |  |  | P
32 | 671 | ZM52W2kHJJCM7052Da3J | Normal | 2 | 1.5.6.5.2 | 1.5.6.5.2 |  | O |  |  |  | P
33 | 672 | AcRvLPQ7WrNfvcLBOWzV | Normal | 1 | 1.5.6.5.3 | 1.5.6.5.3 |  | O |  |  |  | P
34 | 4213 | pNBoUl9px0n4wFhfXXqQ | Summary | 90 | 1.5.1.1 | 1.5.1.1 |  | O |  |  |  | P
35 | 4215 | I07WrBLpDQufO3mvIdSu | Normal | 1 | 1.5.1.1.4 | 1.5.1.1.4 |  | O |  |  |  | P
36 | 6444 | XymP4MvJgra2aDdoc9vw | Normal | 46 | 1.5.1.1.2 | 1.5.1.1.2 |  | O |  |  |  | P
37 | 6445 | Wo6GLLiu9tXQyZ8t43hX | Normal | 43 | 1.5.1.1.3 | 1.5.1.1.3 |  | O |  |  |  | P
38 | 5854 | 2kqOvhRPajU4Q0ZPsUnx | Normal | 8 | 1.4.3.1.4 | 1.4.3.1.4 |  | O |  |  |  | P
39 | 6607 | IhYDHpDNbof6PVOjQ9lw | Normal | 4 | 1.4.3.1.3 | 1.4.3.1.3 |  | O |  |  |  | P
40 | 6321 | KAyzIHlSkkFZqIIdJ9JD | Summary | 144 | 1.4.2.3.2 | 1.4.2.3.2 |  | O |  |  |  | P
41 | 5298 | c4SSanbHhynqs8RkqT3I | Normal | 3 | 1.4.2.3.2.2 | 1.4.2.3.2.2 |  | O |  |  |  | P
42 | 5299 | HB5wL9z8KlZFeAas0WUQ | Normal | 11 | 1.4.2.3.2.3 | 1.4.2.3.2.3 |  | O |  |  |  | P
43 | 5301 | hHw9byxBfgMW8zXuSsdj | Milestone | 0 | 1.4.2.3.2.12 | 1.4.2.3.2.12 |  | O |  |  |  | P
44 | 5302 | 2rc67Y2hzAhRvE7YihWA | Normal | 10 | 1.4.2.3.2.1 | 1.4.2.3.2.1 |  | O |  |  |  | P
45 | 5303 | SgeIRg4ykwxbNqD9urWV | Normal | 2 | 1.4.2.3.2.8 | 1.4.2.3.2.8 |  | O |  |  |  | P
46 | 5304 | KRXQrBZsFBKS9k4FvAsp | Normal | 3 | 1.4.2.3.2.9 | 1.4.2.3.2.9 |  | O |  |  |  | P
47 | 5305 | TyGQYH0bANBrFjXmh15D | Normal | 2 | 1.4.2.3.2.10 | 1.4.2.3.2.10 |  | O |  |  |  | P
48 | 5306 | yar7ts7ASIpTQqyvnwQd | Normal | 5 | 1.4.2.3.2.13 | 1.4.2.3.2.13 |  | O |  |  |  | P
49 | 5307 | yRByGMPgEQcCecr5HzAA | Normal | 2 | 1.4.2.3.2.15 | 1.4.2.3.2.15 |  | O |  |  |  | P
50 | 5308 | JBAsTSNPb9OQmIAmtadV | Normal | 20 | 1.4.2.3.2.17 | 1.4.2.3.2.17 |  | O |  |  |  | P
51 | 6516 | qmbk7ROGAo4AwJOySAlG | Normal | 4 | 1.4.2.3.2.4 | 1.4.2.3.2.4 |  | O |  |  |  | P
52 | 6517 | YGaikKlMVGc6fqtUBZ7h | Normal | 5 | 1.4.2.3.2.5 | 1.4.2.3.2.5 |  | O |  |  |  | P
53 | 6518 | 0rDsNLFYCabTnyCcopAQ | Normal | 8 | 1.4.2.3.2.6 | 1.4.2.3.2.6 |  | O |  |  |  | P
54 | 6519 | UldK3RoYRJH5Hsfv02Lh | Normal | 2 | 1.4.2.3.2.7 | 1.4.2.3.2.7 |  | O |  |  |  | P
55 | 6520 | UaqqB30tdDFCsCHRRpeh | Normal | 2 | 1.4.2.3.2.11 | 1.4.2.3.2.11 |  | O |  |  |  | P
56 | 6521 | LDY9CVOjImzsQ4NE65Qz | Normal | 1 | 1.4.2.3.2.16 | 1.4.2.3.2.16 |  | O |  |  |  | P
57 | 6522 | WYJvDx3FrKALT2lj4FIo | Normal | 2 | 1.4.2.3.2.18 | 1.4.2.3.2.18 |  | O |  |  |  | P
58 | 6873 | gSZIbC6fsU6IM6McOJy8 | Normal | 1 | 1.4.2.3.2.14 | 1.4.2.3.2.14 |  | O |  |  |  | P
59 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | O |  |  |  | P
60 | 870 | m3oEXpasu7ssfpw9dqLv | Summary | 267 | 1.9.9.14 | 1.9.9.14 |  | O |  |  |  | P
61 | 4679 | rpzkOhA603pApmNdMeVE | Normal | 0 | 1.9.9.14.6 | 1.9.9.14.6 |  | O |  |  |  | P
62 | 899 | w1GWQdUx9oG06oopRYZx | Summary | 24 | 1.9.9.15 | 1.9.9.15 |  | O |  |  |  | P
63 | 900 | ANUK0HdVlI2Jd5hSzs0f | Milestone | 0 | 1.9.9.15.1 | 1.9.9.15.1 |  | O |  |  |  | P
64 | 902 | nIjAIVHCOoi1ijXym0cI | Normal | 3 | 1.9.9.15.3 | 1.9.9.15.3 |  | O |  |  |  | P
65 | 903 | UDGopgZ2sb1QsQEooZ9G | Normal | 8 | 1.9.9.15.4 | 1.9.9.15.4 |  | O |  |  |  | P
66 | 905 | MxRWNVEH6ZVBPqNnA2hI | Normal | 8 | 1.9.9.15.6 | 1.9.9.15.6 |  | O |  |  |  | P
67 | 907 | 5mTVpVcHzmsYLVY8xpKs | Normal | 5 | 1.9.9.15.8 | 1.9.9.15.8 |  | O |  |  |  | P
68 | 4538 | aTyUglf0WPX6H8Zd17Iq | Summary | 71 | 1.9.9.16 | 1.9.9.16 |  | O |  |  |  | P
69 | 6510 | dar9hgzhSUYJxC1MeoTS | Normal | 10 | 1.9.9.16.4 | 1.9.9.16.4 |  | O |  |  |  | P
70 | 6513 | IG8fHoH3vjERJ6iSB3Rj | Normal | 36 | 1.9.9.16.5 | 1.9.9.16.5 |  | O |  |  |  | P
71 | 6514 | imV319lPgBwI8oLVT5sB | Normal | 1 | 1.9.9.16.2 | 1.9.9.16.2 |  | O |  |  |  | P
72 | 7388 | subTjNOw9tjXphx2xXzW | Summary | 324 | 1.9.9.13 | 1.9.9.13 |  | O |  |  |  | P
73 | 7389 | xTfJP5JFEqXIDmLDdKVZ | Summary | 43 | 1.9.9.13.1 | 1.9.9.13.1 |  | O |  |  |  | P
74 | 7397 | gmOEJCOmO6SQ6HMlGXfq | Summary | 12 | 1.9.9.13.1.2 | 1.9.9.13.1.2 |  | O |  |  |  | P
75 | 7399 | cXpFrNuZR7O8wPV6KZK3 | Normal | 9 | 1.9.9.13.1.2.2 | 1.9.9.13.1.2.2 |  | O |  |  |  | P
76 | 7402 | pMiEhGou1QDK96DPu7Q8 | Normal | 1 | 1.9.9.13.2.2 | 1.9.9.13.2.2 |  | O |  |  |  | P
77 | 7403 | pHZBXvaYVwug2p7gN6jp | Summary | 17 | 1.9.9.13.2.3 | 1.9.9.13.2.3 |  | O |  |  |  | P
78 | 7404 | EvHLT3cR3tYYGwcq6SC1 | Normal | 5 | 1.9.9.13.2.3.1 | 1.9.9.13.2.3.1 |  | O |  |  |  | P
79 | 7405 | 5GpI6xkgfIoVOnU9egD8 | Normal | 12 | 1.9.9.13.2.3.2 | 1.9.9.13.2.3.2 |  | O |  |  |  | P
80 | 7407 | 0eiyRK1I5mgUCdtpXpqY | Summary | 44 | 1.9.9.13.2.4 | 1.9.9.13.2.4 |  | O |  |  |  | P
81 | 7408 | uKngouP2QMMQmu6HFm0I | Normal | 11 | 1.9.9.13.2.4.1 | 1.9.9.13.2.4.1 |  | O |  |  |  | P
82 | 7409 | C7eZzAQkBbKewE4wmmOD | Normal | 11 | 1.9.9.13.2.4.2 | 1.9.9.13.2.4.2 |  | O |  |  |  | P
83 | 7410 | VCdEPtbQjRcgNUnNprkZ | Normal | 11 | 1.9.9.13.2.4.3 | 1.9.9.13.2.4.3 |  | O |  |  |  | P
84 | 7411 | OzHccTXr25Mf4pmiIMuT | Normal | 11 | 1.9.9.13.2.4.4 | 1.9.9.13.2.4.4 |  | O |  |  |  | P
85 | 7413 | xazO1XwNp5eROWJmaREL | Summary | 36 | 1.9.9.13.2.6 | 1.9.9.13.2.6 |  | O |  |  |  | P
86 | 7414 | DrM34eAIT9imz4vRHbHm | Normal | 2 | 1.9.9.13.2.6.1 | 1.9.9.13.2.6.1 |  | O |  |  |  | P
87 | 7415 | RsULMViXRZoYahxlMUQ4 | Normal | 20 | 1.9.9.13.2.6.2 | 1.9.9.13.2.6.2 |  | O |  |  |  | P
88 | 7416 | U8irVJqpjJwQWU5FcpMo | Normal | 3 | 1.9.9.13.2.6.3 | 1.9.9.13.2.6.3 |  | O |  |  |  | P
89 | 7417 | yrCdbpyUp4mqkbXiv5Nc | Normal | 6 | 1.9.9.13.2.6.4 | 1.9.9.13.2.6.4 |  | O |  |  |  | P
90 | 7418 | Iw5sTi596kP8d52cBWYm | Normal | 5 | 1.9.9.13.2.6.5 | 1.9.9.13.2.6.5 |  | O |  |  |  | P
91 | 7419 | s9reBpLseCBnslseiKA6 | Normal | 2 | 1.9.9.13.2.7 | 1.9.9.13.2.7 |  | O |  |  |  | P
92 | 7420 | ia01m1zWF4qAvVLVg5It | Summary | 54 | 1.9.9.13.2.8 | 1.9.9.13.2.8 |  | O |  |  |  | P
93 | 7421 | 5PvQN5TGe8y7KbK2rRhO | Normal | 8 | 1.9.9.13.2.8.1 | 1.9.9.13.2.8.1 |  | O |  |  |  | P
94 | 7423 | hs9Gt4WgG9pENnEIaC7X | Normal | 14 | 1.9.9.13.2.8.3 | 1.9.9.13.2.8.3 |  | O |  |  |  | P
95 | 7425 | Pv27HXd826jlfuUJmTLH | Normal | 20 | 1.9.9.13.2.8.5 | 1.9.9.13.2.8.5 |  | O |  |  |  | P
96 | 7427 | 5QMAV8W19uO0knxuRgYc | Normal | 6 | 1.9.9.13.2.8.7 | 1.9.9.13.2.8.7 |  | O |  |  |  | P
97 | 7428 | C3roUkJ3GEdxAvfnxnUE | Normal | 6 | 1.9.9.13.2.8.8 | 1.9.9.13.2.8.8 |  | O |  |  |  | P
98 | 7429 | GMfJSktlv5oUXA5LFNgA | Normal | 6 | 1.9.9.13.2.8.9 | 1.9.9.13.2.8.9 |  | O |  |  |  | P
99 | 7430 | AjX0fOJfuCWTWcoFWrZe | Summary | 11 | 1.9.9.13.2.9 | 1.9.9.13.2.9 |  | O |  |  |  | P
100 | 7432 | HbmHLQTrqR87hE03VIdq | Normal | 3 | 1.9.9.13.2.9.2 | 1.9.9.13.2.9.2 |  | O |  |  |  | P
101 | 7433 | FxBsJSw4ZNEIyIQA8bL9 | Normal | 8 | 1.9.9.13.2.9.3 | 1.9.9.13.2.9.3 |  | O |  |  |  | P
102 | 7434 | MkjgnYEnwrIrITdXMEl9 | Milestone | 0 | 1.9.9.13.3 | 1.9.9.13.3 |  | O |  |  |  | P
103 | 7435 | nSo6tYchIu2Aw4YtE45u | Summary | 44 | 1.9.9.13.4 | 1.9.9.13.4 |  | O |  |  |  | P
104 | 7436 | Y83lvWkQwfsc3dMGwfVN | Summary | 30 | 1.9.9.13.4.1 | 1.9.9.13.4.1 |  | O |  |  |  | P
105 | 7441 | IcgrxiRjEYJLwuugm8N7 | Summary | 30 | 1.9.9.13.4.1.2 | 1.9.9.13.4.1.2 |  | O |  |  |  | P
106 | 7442 | B8zfbswYxyRxHa21jaE6 | Normal | 15 | 1.9.9.13.4.1.2.1 | 1.9.9.13.4.1.2.1 |  | O |  |  |  | P
107 | 7443 | lvFKaF8Jtq8DkkB0s9nv | Normal | 15 | 1.9.9.13.4.1.2.2 | 1.9.9.13.4.1.2.2 |  | O |  |  |  | P
108 | 7446 | NnBZUSVumxDXwVdCLN8g | Summary | 12 | 1.9.9.13.4.2 | 1.9.9.13.4.2 |  | O |  |  |  | P
109 | 7448 | 8tMCh2h8AwE53TPPkfEv | Normal | 3 | 1.9.9.13.4.2.2 | 1.9.9.13.4.2.2 |  | O |  |  |  | P
110 | 7449 | LaZxXVdUnGzqswRGUiV5 | Normal | 7 | 1.9.9.13.4.2.3 | 1.9.9.13.4.2.3 |  | O |  |  |  | P
111 | 7450 | F3vtt1T8lz7mQWFPgUKT | Normal | 2 | 1.9.9.13.4.3 | 1.9.9.13.4.3 |  | O |  |  |  | P
112 | 7451 | nShmtMdGhMi3SzNeAZjW | Milestone | 0 | 1.9.9.13.4.4 | 1.9.9.13.4.4 |  | O |  |  |  | P
113 | 4590 | 21lrGsmJiPqRYOd4yY3H | Summary | 2 | 1.9.7.21 | 1.9.7.21 |  | O |  |  |  | P
114 | 1570 | 9hmrS48cr19KgrseY4yN | Normal | 2 | 1.9.7.21.1 | 1.9.7.21.1 |  | O |  |  |  | P
115 | 4131 | 3WZTLr4e3INGux4LMgj0 | Summary | 146 | 1.9.6.10.2 | 1.9.6.10.2 |  | O |  |  |  | P
116 | 5857 | g9TizAnooUcHoXglcd4n | Milestone | 0 | 1.9.6.10.2.1 | 1.9.6.10.2.1 |  | O |  |  |  | P
117 | 5858 | 9N3N0HBhBeb82jbbU7Vx | Milestone | 0 | 1.9.6.10.2.2 | 1.9.6.10.2.2 |  | O |  |  |  | P
118 | 5859 | RMhsXtyk4773BtipN2HO | Normal | 1 | 1.9.6.10.2.3 | 1.9.6.10.2.3 |  | O |  |  |  | P
119 | 5860 | AMUT2hrMeOWSIoK5dO6S | Normal | 10 | 1.9.6.10.2.4 | 1.9.6.10.2.4 |  | O |  |  |  | P
120 | 5861 | adMwYb1cwVT0ja23ZKPV | Normal | 10 | 1.9.6.10.2.5 | 1.9.6.10.2.5 |  | O |  |  |  | P
121 | 5862 | rkVKH7eSVnkv5Rz0hIbo | Normal | 25 | 1.9.6.10.2.6 | 1.9.6.10.2.6 |  | O |  |  |  | P
122 | 5863 | axx1H8vuWtNbWz6aJYpW | Normal | 20 | 1.9.6.10.2.7 | 1.9.6.10.2.7 |  | O |  |  |  | P
123 | 5864 | ZuXAUp7kzm7PDgs0Clm4 | Normal | 20 | 1.9.6.10.2.8 | 1.9.6.10.2.8 |  | O |  |  |  | P
124 | 5865 | pfx92tyIHO0nDV8Eg4vj | Normal | 3 | 1.9.6.10.2.9 | 1.9.6.10.2.9 |  | O |  |  |  | P
125 | 5866 | qnFTkxNSvGIYOwHhqElS | Normal | 5 | 1.9.6.10.2.10 | 1.9.6.10.2.10 |  | O |  |  |  | P
126 | 5867 | 6vMprMC9ZRYTg9c055cw | Normal | 3 | 1.9.6.10.2.11 | 1.9.6.10.2.11 |  | O |  |  |  | P
127 | 5868 | qP5P60WlJm98gR28uFOw | Normal | 1 | 1.9.6.10.2.12 | 1.9.6.10.2.12 |  | O |  |  |  | P
128 | 5869 | 5FBVtcv48JlyNzpes7ps | Normal | 5 | 1.9.6.10.2.13 | 1.9.6.10.2.13 |  | O |  |  |  | P
129 | 5870 | rLlKwDBGmyMe6lxLtymf | Summary | 59 | 1.9.6.10.3 | 1.9.6.10.3 |  | O |  |  |  | P
130 | 5871 | owx5unCKcaLauhH4kWyj | Normal | 5 | 1.9.6.10.3.1 | 1.9.6.10.3.1 |  | O |  |  |  | P
131 | 5872 | qImIYF1Y50rp0FNnsaoS | Normal | 10 | 1.9.6.10.3.2 | 1.9.6.10.3.2 |  | O |  |  |  | P
132 | 5873 | FfFQqcMQ2fY5X0GvK0Xd | Normal | 20 | 1.9.6.10.3.3 | 1.9.6.10.3.3 |  | O |  |  |  | P
133 | 5874 | fHTDjpnY2Gm0gViXPiAD | Normal | 2 | 1.9.6.10.3.6 | 1.9.6.10.3.6 |  | O |  |  |  | P
134 | 5875 | TQZary26m4SvJkpuQUlv | Normal | 1 | 1.9.6.10.3.7 | 1.9.6.10.3.7 |  | O |  |  |  | P
135 | 5876 | 5ZRJqmbhPGswffOWtWat | Normal | 1 | 1.9.6.10.3.8 | 1.9.6.10.3.8 |  | O |  |  |  | P
136 | 6624 | sVpbcWAee9M5eeft5sdO | Normal | 15 | 1.9.6.10.3.4 | 1.9.6.10.3.4 |  | O |  |  |  | P
137 | 6625 | it5qGsWYKIf8fEL1a2TB | Normal | 5 | 1.9.6.10.3.5 | 1.9.6.10.3.5 |  | O |  |  |  | P
138 | 5753 | ZptYdARXANY2IOcoHhB1 | Summary | 78 | 1.9.6.1 | 1.9.6.1 |  | O |  |  |  | P
139 | 5998 | aRBXPvE6pbVbcbhlDtu4 | Summary | 47 | 1.9.6.1.7 | 1.9.6.1.7 |  | O |  |  |  | P
140 | 5999 | hTF24jclc5ogfsrVWXZd | Normal | 40 | 1.9.6.1.7.1 | 1.9.6.1.7.1 |  | O |  |  |  | P
141 | 6000 | dvNXA0SZWky1SGhKE7td | Normal | 5 | 1.9.6.1.7.2 | 1.9.6.1.7.2 |  | O |  |  |  | P
142 | 6001 | z8HVZ6SyP3QpkaT54VAm | Normal | 1 | 1.9.6.1.7.3 | 1.9.6.1.7.3 |  | O |  |  |  | P
143 | 6002 | rmlzSal3Nkh8gQGzhscw | Normal | 1 | 1.9.6.1.7.4 | 1.9.6.1.7.4 |  | O |  |  |  | P
144 | 6003 | zkyCYMQIHOywdkyzbjbi | Summary | 48 | 1.9.6.1.8 | 1.9.6.1.8 |  | O |  |  |  | P
145 | 6004 | xOhJcEwgSz1TAvNHU4tB | Normal | 40 | 1.9.6.1.8.1 | 1.9.6.1.8.1 |  | O |  |  |  | P
146 | 6005 | gw3ZFSF3nzLqLqYBiqR7 | Normal | 5 | 1.9.6.1.8.2 | 1.9.6.1.8.2 |  | O |  |  |  | P
147 | 6006 | HEKaqqmbwSXnCRXB6fED | Normal | 1 | 1.9.6.1.8.3 | 1.9.6.1.8.3 |  | O |  |  |  | P
148 | 6007 | vdBzwsumrXxpXNAKvnKh | Normal | 1 | 1.9.6.1.8.4 | 1.9.6.1.8.4 |  | O |  |  |  | P
149 | 6008 | Ph5VFx7Ghit4AwZEFBXT | Summary | 50 | 1.9.6.1.6 | 1.9.6.1.6 |  | O |  |  |  | P
150 | 6009 | NVgukc0KZBShUa0wIlyx | Normal | 30 | 1.9.6.1.6.1 | 1.9.6.1.6.1 |  | O |  |  |  | P
151 | 6010 | tIYqVtlT4yOF2YQ2FRYY | Normal | 10 | 1.9.6.1.6.2 | 1.9.6.1.6.2 |  | O |  |  |  | P
152 | 6011 | 9Y3pHbqvwzl2AwHfvrBG | Normal | 5 | 1.9.6.1.6.3 | 1.9.6.1.6.3 |  | O |  |  |  | P
153 | 6012 | Z1jpWQx4GyFcVoEVg0i0 | Normal | 5 | 1.9.6.1.6.4 | 1.9.6.1.6.4 |  | O |  |  |  | P
154 | 6296 | SlR21lje1Tex9DLMlAM1 | Summary | 222 | 1.9.8 | 1.9.8 |  | O |  |  |  | P
155 | 6084 | deZM0xh115wln716GUoI | Normal | 1 | 1.9.8.9 | 1.9.8.9 |  | O |  |  |  | P
156 | 5539 | kRsO3PSMDsMxji3dmdNc | Normal | 5 | 1.9.5.2.2 | 1.9.5.2.2 |  | O |  |  |  | P
157 | 5545 | 7UVU8IboY6NG7sqZCrUC | Normal | 7 | 1.9.5.2.13.2 | 1.9.5.2.13.2 |  | O |  |  |  | P
158 | 5730 | ypyrsmMFJqJ9aPla6UhQ | Normal | 4 | 1.9.5.2.13.3 | 1.9.5.2.13.3 |  | O |  |  |  | P
159 | 5731 | uQF6Ff0bc2cqy3b37ZQc | Normal | 1 | 1.9.5.2.13.4 | 1.9.5.2.13.4 |  | O |  |  |  | P
160 | 5558 | RXAxJx3BHWNVdWFPfZ2a | Normal | 13 | 1.9.5.2.12.2 | 1.9.5.2.12.2 |  | O |  |  |  | P
161 | 5734 | iq9bjqBZvH9Bj6912271 | Normal | 6 | 1.9.5.2.12.3 | 1.9.5.2.12.3 |  | O |  |  |  | P
162 | 5735 | Z8zFgfwvHK2hwW2AW8Qa | Normal | 1 | 1.9.5.2.12.4 | 1.9.5.2.12.4 |  | O |  |  |  | P
163 | 5571 | lfRAbO0c5jl7NaC6s7pm | Normal | 21 | 1.9.5.2.11.2 | 1.9.5.2.11.2 |  | O |  |  |  | P
164 | 5738 | ME2oX9BwgLu5cggaunhg | Normal | 5 | 1.9.5.2.11.3 | 1.9.5.2.11.3 |  | O |  |  |  | P
165 | 5739 | IivOSmNLtmlF9JKFLUrl | Normal | 1 | 1.9.5.2.11.4 | 1.9.5.2.11.4 |  | O |  |  |  | P
166 | 5584 | 6WMzJdzS7tY0wFFuXnrc | Normal | 7 | 1.9.5.2.14.2 | 1.9.5.2.14.2 |  | O |  |  |  | P
167 | 5585 | KljMWvDEBGSuBTW4zQhZ | Normal | 7 | 1.9.5.2.14.5 | 1.9.5.2.14.5 |  | O |  |  |  | P
168 | 5586 | Z3ZWpIsgJCSKUX161hV0 | Normal | 4 | 1.9.5.2.14.8 | 1.9.5.2.14.8 |  | O |  |  |  | P
169 | 5587 | OXOUsYDejGVlgqn4Z1vl | Normal | 5 | 1.9.5.2.14.9 | 1.9.5.2.14.9 |  | O |  |  |  | P
170 | 5588 | MFjHKzinVVI0Ndx8qx0B | Normal | 1 | 1.4.26 | 1.4.26 |  | O |  |  |  | P
171 | 5742 | 88bEv4EMiOL2y8w1ttIM | Normal | 4 | 1.9.5.2.14.3 | 1.9.5.2.14.3 |  | O |  |  |  | P
172 | 5743 | 0Uz4krHDVCdAlMd5aRwh | Normal | 1 | 1.9.5.2.14.4 | 1.9.5.2.14.4 |  | O |  |  |  | P
173 | 5744 | cSBfnbrbVLLFYTMEfBKA | Normal | 6 | 1.9.5.2.14.6 | 1.9.5.2.14.6 |  | O |  |  |  | P
174 | 5745 | ZY99Y6JX4jBylnfeedvo | Normal | 6 | 1.9.5.2.14.7 | 1.9.5.2.14.7 |  | O |  |  |  | P
175 | 6955 | CPACk87DS0kpO7pXcdwS | Normal | 10 | 1.9.5.2.10 | 1.9.5.2.10 |  | O |  |  |  | P
176 | 6997 | MBGoTUikAECGvIHYk1uV | Normal | 24 | 1.9.5.2.3 | 1.9.5.2.3 |  | O |  |  |  | P

## Longest-Path
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Longest Path - 176 (8%) | Longest Path - 176 (8%) | Longest Path - 176 (8%) | Longest Path - 176 (8%) | Longest Path - 176 (8%) | Longest Path - 176 (8%) | Longest Path - 176 (8%) | Longest Path - 176 (8%) | Longest Path - 176 (8%) | Longest Path - 176 (8%) | Longest Path - 176 (8%) | Longest Path - 176 (8%) | Longest Path - 176 (8%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 152 | QJ29ZvAvtEjBcpqHDer1 | Milestone | 0 | 1.2.3 | 1.2.3 |  | O |  |  |  | P
2 | 6874 | 1XFpbhK6U752FQe8voXZ | Normal | 1 | 1.2.7.6 | 1.2.7.6 |  | O |  |  |  | P
3 | 6879 | Vbp0cBOXY9azJeyTE4S4 | Normal | 3 | 1.2.7.7 | 1.2.7.7 |  | O |  |  |  | P
4 | 7550 | fUEnUBwdI1z3bgOngjaQ | Milestone | 0 | 1.2.7.5 | 1.2.7.5 |  | P |  |  |  | O
5 | 150 | 7cu6yvdJV8ndF0CYMHk8 | Milestone | 0 | 1.1 | 1.1 |  | O |  |  |  | P
6 | 6278 | SNMcp7h74WVvBiN3lPNB | Summary | 66 | 1.5.6 | 1.5.6 |  | O |  |  |  | P
7 | 620 | q8advjPa5PEndSFXJ05j | Summary | 158 | 1.5.6.6 | 1.5.6.6 |  | O |  |  |  | P
8 | 622 | Q48N5ZSDLesB1Bsda2wx | Summary | 156 | 1.5.6.6.2 | 1.5.6.6.2 |  | O |  |  |  | P
9 | 633 | FgJ5XjjThZN85XQOJ0nJ | Normal | 21 | 1.5.6.6.2.10 | 1.5.6.6.2.10 |  | O |  |  |  | P
10 | 634 | o4DRQRcsScdVmCSXNbxF | Normal | 10 | 1.5.6.6.2.9 | 1.5.6.6.2.9 |  | O |  |  |  | P
11 | 635 | ztvy5zkS4z9HirKgvHGY | Normal | 20 | 1.5.6.6.2.11 | 1.5.6.6.2.11 |  | O |  |  |  | P
12 | 636 | ZpIfqMwIaczq2BqznW2q | Normal | 6 | 1.5.6.6.2.12 | 1.5.6.6.2.12 |  | O |  |  |  | P
13 | 637 | 3VAZwvp2NS6usl0wrvOM | Normal | 7 | 1.5.6.6.2.13 | 1.5.6.6.2.13 |  | O |  |  |  | P
14 | 638 | 34zoFClD9RS7gLTCPZs0 | Normal | 5 | 1.5.6.6.2.14 | 1.5.6.6.2.14 |  | O |  |  |  | P
15 | 640 | 10AmMHkCz4b8n0xqbyCt | Normal | 5 | 1.5.6.6.2.16 | 1.5.6.6.2.16 |  | O |  |  |  | P
16 | 641 | KUqcSNVxncHPLVJNV5ca | Normal | 2 | 1.5.6.6.2.17 | 1.5.6.6.2.17 |  | O |  |  |  | P
17 | 642 | chCwawHUqn0ea2ArCnKB | Normal | 0 | 1.5.6.6.2.18 | 1.5.6.6.2.18 |  | O |  |  |  | P
18 | 643 | xZBRzE3QVYmQCjnzxLQv | Normal | 4 | 1.5.6.6.2.19 | 1.5.6.6.2.19 |  | O |  |  |  | P
19 | 644 | tUTeQ74YpmkuuOiouSXU | Normal | 5 | 1.5.6.6.2.20 | 1.5.6.6.2.20 |  | O |  |  |  | P
20 | 645 | mSrjcTZmK12EdJmOEYFi | Normal | 1 | 1.5.6.6.2.21 | 1.5.6.6.2.21 |  | O |  |  |  | P
21 | 646 | Haue3rYYySw3jbXWnBeq | Normal | 3 | 1.5.6.6.3 | 1.5.6.6.3 |  | O |  |  |  | P
22 | 647 | 6jlP0Y4QQ5KPQWxvolLg | Normal | 1 | 1.5.6.6.4 | 1.5.6.6.4 |  | O |  |  |  | P
23 | 648 | 6WPgljRre9DjhHGVsVUH | Summary | 120 | 1.5.6.6.5 | 1.5.6.6.5 |  | O |  |  |  | P
24 | 656 | lzPFAx9Fh8cDxyQ3uxFX | Normal | 1 | 1.5.6.6.5.3 | 1.5.6.6.5.3 |  | O |  |  |  | P
25 | 657 | nePaKBbqDo6OltylvukE | Summary | 14 | 1.5.6.6.5.4 | 1.5.6.6.5.4 |  | O |  |  |  | P
26 | 658 | PyBKEPMZMe2YeOC66yut | Normal | 11 | 1.5.6.6.5.4.1 | 1.5.6.6.5.4.1 |  | O |  |  |  | P
27 | 664 | H1KB0K8mM12Opvc4oDP1 | Normal | 3 | 1.5.6.6.5.4.2 | 1.5.6.6.5.4.2 |  | O |  |  |  | P
28 | 665 | FIEbexlYHnOcZkEBs7WM | Normal | 5 | 1.5.6.6.5.5 | 1.5.6.6.5.5 |  | O |  |  |  | P
29 | 666 | OcAHNnZWZgiwxfUiheGU | Normal | 5 | 1.5.6.6.5.6 | 1.5.6.6.5.6 |  | O |  |  |  | P
30 | 667 | HPj21Hyun1nWvxJOQMhf | Normal | 28 | 1.5.6.6.5.7 | 1.5.6.6.5.7 |  | O |  |  |  | P
31 | 670 | zBtIFoyMK1KgXAv407C9 | Summary | 29 | 1.5.6.5 | 1.5.6.5 |  | O |  |  |  | P
32 | 671 | ZM52W2kHJJCM7052Da3J | Normal | 2 | 1.5.6.5.2 | 1.5.6.5.2 |  | O |  |  |  | P
33 | 672 | AcRvLPQ7WrNfvcLBOWzV | Normal | 1 | 1.5.6.5.3 | 1.5.6.5.3 |  | O |  |  |  | P
34 | 4213 | pNBoUl9px0n4wFhfXXqQ | Summary | 90 | 1.5.1.1 | 1.5.1.1 |  | O |  |  |  | P
35 | 4215 | I07WrBLpDQufO3mvIdSu | Normal | 1 | 1.5.1.1.4 | 1.5.1.1.4 |  | O |  |  |  | P
36 | 6444 | XymP4MvJgra2aDdoc9vw | Normal | 46 | 1.5.1.1.2 | 1.5.1.1.2 |  | O |  |  |  | P
37 | 6445 | Wo6GLLiu9tXQyZ8t43hX | Normal | 43 | 1.5.1.1.3 | 1.5.1.1.3 |  | O |  |  |  | P
38 | 5854 | 2kqOvhRPajU4Q0ZPsUnx | Normal | 8 | 1.4.3.1.4 | 1.4.3.1.4 |  | O |  |  |  | P
39 | 6607 | IhYDHpDNbof6PVOjQ9lw | Normal | 4 | 1.4.3.1.3 | 1.4.3.1.3 |  | O |  |  |  | P
40 | 6321 | KAyzIHlSkkFZqIIdJ9JD | Summary | 144 | 1.4.2.3.2 | 1.4.2.3.2 |  | O |  |  |  | P
41 | 5298 | c4SSanbHhynqs8RkqT3I | Normal | 3 | 1.4.2.3.2.2 | 1.4.2.3.2.2 |  | O |  |  |  | P
42 | 5299 | HB5wL9z8KlZFeAas0WUQ | Normal | 11 | 1.4.2.3.2.3 | 1.4.2.3.2.3 |  | O |  |  |  | P
43 | 5301 | hHw9byxBfgMW8zXuSsdj | Milestone | 0 | 1.4.2.3.2.12 | 1.4.2.3.2.12 |  | O |  |  |  | P
44 | 5302 | 2rc67Y2hzAhRvE7YihWA | Normal | 10 | 1.4.2.3.2.1 | 1.4.2.3.2.1 |  | O |  |  |  | P
45 | 5303 | SgeIRg4ykwxbNqD9urWV | Normal | 2 | 1.4.2.3.2.8 | 1.4.2.3.2.8 |  | O |  |  |  | P
46 | 5304 | KRXQrBZsFBKS9k4FvAsp | Normal | 3 | 1.4.2.3.2.9 | 1.4.2.3.2.9 |  | O |  |  |  | P
47 | 5305 | TyGQYH0bANBrFjXmh15D | Normal | 2 | 1.4.2.3.2.10 | 1.4.2.3.2.10 |  | O |  |  |  | P
48 | 5306 | yar7ts7ASIpTQqyvnwQd | Normal | 5 | 1.4.2.3.2.13 | 1.4.2.3.2.13 |  | O |  |  |  | P
49 | 5307 | yRByGMPgEQcCecr5HzAA | Normal | 2 | 1.4.2.3.2.15 | 1.4.2.3.2.15 |  | O |  |  |  | P
50 | 5308 | JBAsTSNPb9OQmIAmtadV | Normal | 20 | 1.4.2.3.2.17 | 1.4.2.3.2.17 |  | O |  |  |  | P
51 | 6516 | qmbk7ROGAo4AwJOySAlG | Normal | 4 | 1.4.2.3.2.4 | 1.4.2.3.2.4 |  | O |  |  |  | P
52 | 6517 | YGaikKlMVGc6fqtUBZ7h | Normal | 5 | 1.4.2.3.2.5 | 1.4.2.3.2.5 |  | O |  |  |  | P
53 | 6518 | 0rDsNLFYCabTnyCcopAQ | Normal | 8 | 1.4.2.3.2.6 | 1.4.2.3.2.6 |  | O |  |  |  | P
54 | 6519 | UldK3RoYRJH5Hsfv02Lh | Normal | 2 | 1.4.2.3.2.7 | 1.4.2.3.2.7 |  | O |  |  |  | P
55 | 6520 | UaqqB30tdDFCsCHRRpeh | Normal | 2 | 1.4.2.3.2.11 | 1.4.2.3.2.11 |  | O |  |  |  | P
56 | 6521 | LDY9CVOjImzsQ4NE65Qz | Normal | 1 | 1.4.2.3.2.16 | 1.4.2.3.2.16 |  | O |  |  |  | P
57 | 6522 | WYJvDx3FrKALT2lj4FIo | Normal | 2 | 1.4.2.3.2.18 | 1.4.2.3.2.18 |  | O |  |  |  | P
58 | 6873 | gSZIbC6fsU6IM6McOJy8 | Normal | 1 | 1.4.2.3.2.14 | 1.4.2.3.2.14 |  | O |  |  |  | P
59 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | O |  |  |  | P
60 | 870 | m3oEXpasu7ssfpw9dqLv | Summary | 267 | 1.9.9.14 | 1.9.9.14 |  | O |  |  |  | P
61 | 4679 | rpzkOhA603pApmNdMeVE | Normal | 0 | 1.9.9.14.6 | 1.9.9.14.6 |  | O |  |  |  | P
62 | 899 | w1GWQdUx9oG06oopRYZx | Summary | 24 | 1.9.9.15 | 1.9.9.15 |  | O |  |  |  | P
63 | 900 | ANUK0HdVlI2Jd5hSzs0f | Milestone | 0 | 1.9.9.15.1 | 1.9.9.15.1 |  | O |  |  |  | P
64 | 902 | nIjAIVHCOoi1ijXym0cI | Normal | 3 | 1.9.9.15.3 | 1.9.9.15.3 |  | O |  |  |  | P
65 | 903 | UDGopgZ2sb1QsQEooZ9G | Normal | 8 | 1.9.9.15.4 | 1.9.9.15.4 |  | O |  |  |  | P
66 | 905 | MxRWNVEH6ZVBPqNnA2hI | Normal | 8 | 1.9.9.15.6 | 1.9.9.15.6 |  | O |  |  |  | P
67 | 907 | 5mTVpVcHzmsYLVY8xpKs | Normal | 5 | 1.9.9.15.8 | 1.9.9.15.8 |  | O |  |  |  | P
68 | 4538 | aTyUglf0WPX6H8Zd17Iq | Summary | 71 | 1.9.9.16 | 1.9.9.16 |  | O |  |  |  | P
69 | 6510 | dar9hgzhSUYJxC1MeoTS | Normal | 10 | 1.9.9.16.4 | 1.9.9.16.4 |  | O |  |  |  | P
70 | 6513 | IG8fHoH3vjERJ6iSB3Rj | Normal | 36 | 1.9.9.16.5 | 1.9.9.16.5 |  | O |  |  |  | P
71 | 6514 | imV319lPgBwI8oLVT5sB | Normal | 1 | 1.9.9.16.2 | 1.9.9.16.2 |  | O |  |  |  | P
72 | 7388 | subTjNOw9tjXphx2xXzW | Summary | 324 | 1.9.9.13 | 1.9.9.13 |  | O |  |  |  | P
73 | 7389 | xTfJP5JFEqXIDmLDdKVZ | Summary | 43 | 1.9.9.13.1 | 1.9.9.13.1 |  | O |  |  |  | P
74 | 7397 | gmOEJCOmO6SQ6HMlGXfq | Summary | 12 | 1.9.9.13.1.2 | 1.9.9.13.1.2 |  | O |  |  |  | P
75 | 7399 | cXpFrNuZR7O8wPV6KZK3 | Normal | 9 | 1.9.9.13.1.2.2 | 1.9.9.13.1.2.2 |  | O |  |  |  | P
76 | 7402 | pMiEhGou1QDK96DPu7Q8 | Normal | 1 | 1.9.9.13.2.2 | 1.9.9.13.2.2 |  | O |  |  |  | P
77 | 7403 | pHZBXvaYVwug2p7gN6jp | Summary | 17 | 1.9.9.13.2.3 | 1.9.9.13.2.3 |  | O |  |  |  | P
78 | 7404 | EvHLT3cR3tYYGwcq6SC1 | Normal | 5 | 1.9.9.13.2.3.1 | 1.9.9.13.2.3.1 |  | O |  |  |  | P
79 | 7405 | 5GpI6xkgfIoVOnU9egD8 | Normal | 12 | 1.9.9.13.2.3.2 | 1.9.9.13.2.3.2 |  | O |  |  |  | P
80 | 7407 | 0eiyRK1I5mgUCdtpXpqY | Summary | 44 | 1.9.9.13.2.4 | 1.9.9.13.2.4 |  | O |  |  |  | P
81 | 7408 | uKngouP2QMMQmu6HFm0I | Normal | 11 | 1.9.9.13.2.4.1 | 1.9.9.13.2.4.1 |  | O |  |  |  | P
82 | 7409 | C7eZzAQkBbKewE4wmmOD | Normal | 11 | 1.9.9.13.2.4.2 | 1.9.9.13.2.4.2 |  | O |  |  |  | P
83 | 7410 | VCdEPtbQjRcgNUnNprkZ | Normal | 11 | 1.9.9.13.2.4.3 | 1.9.9.13.2.4.3 |  | O |  |  |  | P
84 | 7411 | OzHccTXr25Mf4pmiIMuT | Normal | 11 | 1.9.9.13.2.4.4 | 1.9.9.13.2.4.4 |  | O |  |  |  | P
85 | 7413 | xazO1XwNp5eROWJmaREL | Summary | 36 | 1.9.9.13.2.6 | 1.9.9.13.2.6 |  | O |  |  |  | P
86 | 7414 | DrM34eAIT9imz4vRHbHm | Normal | 2 | 1.9.9.13.2.6.1 | 1.9.9.13.2.6.1 |  | O |  |  |  | P
87 | 7415 | RsULMViXRZoYahxlMUQ4 | Normal | 20 | 1.9.9.13.2.6.2 | 1.9.9.13.2.6.2 |  | O |  |  |  | P
88 | 7416 | U8irVJqpjJwQWU5FcpMo | Normal | 3 | 1.9.9.13.2.6.3 | 1.9.9.13.2.6.3 |  | O |  |  |  | P
89 | 7417 | yrCdbpyUp4mqkbXiv5Nc | Normal | 6 | 1.9.9.13.2.6.4 | 1.9.9.13.2.6.4 |  | O |  |  |  | P
90 | 7418 | Iw5sTi596kP8d52cBWYm | Normal | 5 | 1.9.9.13.2.6.5 | 1.9.9.13.2.6.5 |  | O |  |  |  | P
91 | 7419 | s9reBpLseCBnslseiKA6 | Normal | 2 | 1.9.9.13.2.7 | 1.9.9.13.2.7 |  | O |  |  |  | P
92 | 7420 | ia01m1zWF4qAvVLVg5It | Summary | 54 | 1.9.9.13.2.8 | 1.9.9.13.2.8 |  | O |  |  |  | P
93 | 7421 | 5PvQN5TGe8y7KbK2rRhO | Normal | 8 | 1.9.9.13.2.8.1 | 1.9.9.13.2.8.1 |  | O |  |  |  | P
94 | 7423 | hs9Gt4WgG9pENnEIaC7X | Normal | 14 | 1.9.9.13.2.8.3 | 1.9.9.13.2.8.3 |  | O |  |  |  | P
95 | 7425 | Pv27HXd826jlfuUJmTLH | Normal | 20 | 1.9.9.13.2.8.5 | 1.9.9.13.2.8.5 |  | O |  |  |  | P
96 | 7427 | 5QMAV8W19uO0knxuRgYc | Normal | 6 | 1.9.9.13.2.8.7 | 1.9.9.13.2.8.7 |  | O |  |  |  | P
97 | 7428 | C3roUkJ3GEdxAvfnxnUE | Normal | 6 | 1.9.9.13.2.8.8 | 1.9.9.13.2.8.8 |  | O |  |  |  | P
98 | 7429 | GMfJSktlv5oUXA5LFNgA | Normal | 6 | 1.9.9.13.2.8.9 | 1.9.9.13.2.8.9 |  | O |  |  |  | P
99 | 7430 | AjX0fOJfuCWTWcoFWrZe | Summary | 11 | 1.9.9.13.2.9 | 1.9.9.13.2.9 |  | O |  |  |  | P
100 | 7432 | HbmHLQTrqR87hE03VIdq | Normal | 3 | 1.9.9.13.2.9.2 | 1.9.9.13.2.9.2 |  | O |  |  |  | P
101 | 7433 | FxBsJSw4ZNEIyIQA8bL9 | Normal | 8 | 1.9.9.13.2.9.3 | 1.9.9.13.2.9.3 |  | O |  |  |  | P
102 | 7434 | MkjgnYEnwrIrITdXMEl9 | Milestone | 0 | 1.9.9.13.3 | 1.9.9.13.3 |  | O |  |  |  | P
103 | 7435 | nSo6tYchIu2Aw4YtE45u | Summary | 44 | 1.9.9.13.4 | 1.9.9.13.4 |  | O |  |  |  | P
104 | 7436 | Y83lvWkQwfsc3dMGwfVN | Summary | 30 | 1.9.9.13.4.1 | 1.9.9.13.4.1 |  | O |  |  |  | P
105 | 7441 | IcgrxiRjEYJLwuugm8N7 | Summary | 30 | 1.9.9.13.4.1.2 | 1.9.9.13.4.1.2 |  | O |  |  |  | P
106 | 7442 | B8zfbswYxyRxHa21jaE6 | Normal | 15 | 1.9.9.13.4.1.2.1 | 1.9.9.13.4.1.2.1 |  | O |  |  |  | P
107 | 7443 | lvFKaF8Jtq8DkkB0s9nv | Normal | 15 | 1.9.9.13.4.1.2.2 | 1.9.9.13.4.1.2.2 |  | O |  |  |  | P
108 | 7446 | NnBZUSVumxDXwVdCLN8g | Summary | 12 | 1.9.9.13.4.2 | 1.9.9.13.4.2 |  | O |  |  |  | P
109 | 7448 | 8tMCh2h8AwE53TPPkfEv | Normal | 3 | 1.9.9.13.4.2.2 | 1.9.9.13.4.2.2 |  | O |  |  |  | P
110 | 7449 | LaZxXVdUnGzqswRGUiV5 | Normal | 7 | 1.9.9.13.4.2.3 | 1.9.9.13.4.2.3 |  | O |  |  |  | P
111 | 7450 | F3vtt1T8lz7mQWFPgUKT | Normal | 2 | 1.9.9.13.4.3 | 1.9.9.13.4.3 |  | O |  |  |  | P
112 | 7451 | nShmtMdGhMi3SzNeAZjW | Milestone | 0 | 1.9.9.13.4.4 | 1.9.9.13.4.4 |  | O |  |  |  | P
113 | 4590 | 21lrGsmJiPqRYOd4yY3H | Summary | 2 | 1.9.7.21 | 1.9.7.21 |  | O |  |  |  | P
114 | 1570 | 9hmrS48cr19KgrseY4yN | Normal | 2 | 1.9.7.21.1 | 1.9.7.21.1 |  | O |  |  |  | P
115 | 4131 | 3WZTLr4e3INGux4LMgj0 | Summary | 146 | 1.9.6.10.2 | 1.9.6.10.2 |  | O |  |  |  | P
116 | 5857 | g9TizAnooUcHoXglcd4n | Milestone | 0 | 1.9.6.10.2.1 | 1.9.6.10.2.1 |  | O |  |  |  | P
117 | 5858 | 9N3N0HBhBeb82jbbU7Vx | Milestone | 0 | 1.9.6.10.2.2 | 1.9.6.10.2.2 |  | O |  |  |  | P
118 | 5859 | RMhsXtyk4773BtipN2HO | Normal | 1 | 1.9.6.10.2.3 | 1.9.6.10.2.3 |  | O |  |  |  | P
119 | 5860 | AMUT2hrMeOWSIoK5dO6S | Normal | 10 | 1.9.6.10.2.4 | 1.9.6.10.2.4 |  | O |  |  |  | P
120 | 5861 | adMwYb1cwVT0ja23ZKPV | Normal | 10 | 1.9.6.10.2.5 | 1.9.6.10.2.5 |  | O |  |  |  | P
121 | 5862 | rkVKH7eSVnkv5Rz0hIbo | Normal | 25 | 1.9.6.10.2.6 | 1.9.6.10.2.6 |  | O |  |  |  | P
122 | 5863 | axx1H8vuWtNbWz6aJYpW | Normal | 20 | 1.9.6.10.2.7 | 1.9.6.10.2.7 |  | O |  |  |  | P
123 | 5864 | ZuXAUp7kzm7PDgs0Clm4 | Normal | 20 | 1.9.6.10.2.8 | 1.9.6.10.2.8 |  | O |  |  |  | P
124 | 5865 | pfx92tyIHO0nDV8Eg4vj | Normal | 3 | 1.9.6.10.2.9 | 1.9.6.10.2.9 |  | O |  |  |  | P
125 | 5866 | qnFTkxNSvGIYOwHhqElS | Normal | 5 | 1.9.6.10.2.10 | 1.9.6.10.2.10 |  | O |  |  |  | P
126 | 5867 | 6vMprMC9ZRYTg9c055cw | Normal | 3 | 1.9.6.10.2.11 | 1.9.6.10.2.11 |  | O |  |  |  | P
127 | 5868 | qP5P60WlJm98gR28uFOw | Normal | 1 | 1.9.6.10.2.12 | 1.9.6.10.2.12 |  | O |  |  |  | P
128 | 5869 | 5FBVtcv48JlyNzpes7ps | Normal | 5 | 1.9.6.10.2.13 | 1.9.6.10.2.13 |  | O |  |  |  | P
129 | 5870 | rLlKwDBGmyMe6lxLtymf | Summary | 59 | 1.9.6.10.3 | 1.9.6.10.3 |  | O |  |  |  | P
130 | 5871 | owx5unCKcaLauhH4kWyj | Normal | 5 | 1.9.6.10.3.1 | 1.9.6.10.3.1 |  | O |  |  |  | P
131 | 5872 | qImIYF1Y50rp0FNnsaoS | Normal | 10 | 1.9.6.10.3.2 | 1.9.6.10.3.2 |  | O |  |  |  | P
132 | 5873 | FfFQqcMQ2fY5X0GvK0Xd | Normal | 20 | 1.9.6.10.3.3 | 1.9.6.10.3.3 |  | O |  |  |  | P
133 | 5874 | fHTDjpnY2Gm0gViXPiAD | Normal | 2 | 1.9.6.10.3.6 | 1.9.6.10.3.6 |  | O |  |  |  | P
134 | 5875 | TQZary26m4SvJkpuQUlv | Normal | 1 | 1.9.6.10.3.7 | 1.9.6.10.3.7 |  | O |  |  |  | P
135 | 5876 | 5ZRJqmbhPGswffOWtWat | Normal | 1 | 1.9.6.10.3.8 | 1.9.6.10.3.8 |  | O |  |  |  | P
136 | 6624 | sVpbcWAee9M5eeft5sdO | Normal | 15 | 1.9.6.10.3.4 | 1.9.6.10.3.4 |  | O |  |  |  | P
137 | 6625 | it5qGsWYKIf8fEL1a2TB | Normal | 5 | 1.9.6.10.3.5 | 1.9.6.10.3.5 |  | O |  |  |  | P
138 | 5753 | ZptYdARXANY2IOcoHhB1 | Summary | 78 | 1.9.6.1 | 1.9.6.1 |  | O |  |  |  | P
139 | 5998 | aRBXPvE6pbVbcbhlDtu4 | Summary | 47 | 1.9.6.1.7 | 1.9.6.1.7 |  | O |  |  |  | P
140 | 5999 | hTF24jclc5ogfsrVWXZd | Normal | 40 | 1.9.6.1.7.1 | 1.9.6.1.7.1 |  | O |  |  |  | P
141 | 6000 | dvNXA0SZWky1SGhKE7td | Normal | 5 | 1.9.6.1.7.2 | 1.9.6.1.7.2 |  | O |  |  |  | P
142 | 6001 | z8HVZ6SyP3QpkaT54VAm | Normal | 1 | 1.9.6.1.7.3 | 1.9.6.1.7.3 |  | O |  |  |  | P
143 | 6002 | rmlzSal3Nkh8gQGzhscw | Normal | 1 | 1.9.6.1.7.4 | 1.9.6.1.7.4 |  | O |  |  |  | P
144 | 6003 | zkyCYMQIHOywdkyzbjbi | Summary | 48 | 1.9.6.1.8 | 1.9.6.1.8 |  | O |  |  |  | P
145 | 6004 | xOhJcEwgSz1TAvNHU4tB | Normal | 40 | 1.9.6.1.8.1 | 1.9.6.1.8.1 |  | O |  |  |  | P
146 | 6005 | gw3ZFSF3nzLqLqYBiqR7 | Normal | 5 | 1.9.6.1.8.2 | 1.9.6.1.8.2 |  | O |  |  |  | P
147 | 6006 | HEKaqqmbwSXnCRXB6fED | Normal | 1 | 1.9.6.1.8.3 | 1.9.6.1.8.3 |  | O |  |  |  | P
148 | 6007 | vdBzwsumrXxpXNAKvnKh | Normal | 1 | 1.9.6.1.8.4 | 1.9.6.1.8.4 |  | O |  |  |  | P
149 | 6008 | Ph5VFx7Ghit4AwZEFBXT | Summary | 50 | 1.9.6.1.6 | 1.9.6.1.6 |  | O |  |  |  | P
150 | 6009 | NVgukc0KZBShUa0wIlyx | Normal | 30 | 1.9.6.1.6.1 | 1.9.6.1.6.1 |  | O |  |  |  | P
151 | 6010 | tIYqVtlT4yOF2YQ2FRYY | Normal | 10 | 1.9.6.1.6.2 | 1.9.6.1.6.2 |  | O |  |  |  | P
152 | 6011 | 9Y3pHbqvwzl2AwHfvrBG | Normal | 5 | 1.9.6.1.6.3 | 1.9.6.1.6.3 |  | O |  |  |  | P
153 | 6012 | Z1jpWQx4GyFcVoEVg0i0 | Normal | 5 | 1.9.6.1.6.4 | 1.9.6.1.6.4 |  | O |  |  |  | P
154 | 6296 | SlR21lje1Tex9DLMlAM1 | Summary | 222 | 1.9.8 | 1.9.8 |  | O |  |  |  | P
155 | 6084 | deZM0xh115wln716GUoI | Normal | 1 | 1.9.8.9 | 1.9.8.9 |  | O |  |  |  | P
156 | 5539 | kRsO3PSMDsMxji3dmdNc | Normal | 5 | 1.9.5.2.2 | 1.9.5.2.2 |  | O |  |  |  | P
157 | 5545 | 7UVU8IboY6NG7sqZCrUC | Normal | 7 | 1.9.5.2.13.2 | 1.9.5.2.13.2 |  | O |  |  |  | P
158 | 5730 | ypyrsmMFJqJ9aPla6UhQ | Normal | 4 | 1.9.5.2.13.3 | 1.9.5.2.13.3 |  | O |  |  |  | P
159 | 5731 | uQF6Ff0bc2cqy3b37ZQc | Normal | 1 | 1.9.5.2.13.4 | 1.9.5.2.13.4 |  | O |  |  |  | P
160 | 5558 | RXAxJx3BHWNVdWFPfZ2a | Normal | 13 | 1.9.5.2.12.2 | 1.9.5.2.12.2 |  | O |  |  |  | P
161 | 5734 | iq9bjqBZvH9Bj6912271 | Normal | 6 | 1.9.5.2.12.3 | 1.9.5.2.12.3 |  | O |  |  |  | P
162 | 5735 | Z8zFgfwvHK2hwW2AW8Qa | Normal | 1 | 1.9.5.2.12.4 | 1.9.5.2.12.4 |  | O |  |  |  | P
163 | 5571 | lfRAbO0c5jl7NaC6s7pm | Normal | 21 | 1.9.5.2.11.2 | 1.9.5.2.11.2 |  | O |  |  |  | P
164 | 5738 | ME2oX9BwgLu5cggaunhg | Normal | 5 | 1.9.5.2.11.3 | 1.9.5.2.11.3 |  | O |  |  |  | P
165 | 5739 | IivOSmNLtmlF9JKFLUrl | Normal | 1 | 1.9.5.2.11.4 | 1.9.5.2.11.4 |  | O |  |  |  | P
166 | 5584 | 6WMzJdzS7tY0wFFuXnrc | Normal | 7 | 1.9.5.2.14.2 | 1.9.5.2.14.2 |  | O |  |  |  | P
167 | 5585 | KljMWvDEBGSuBTW4zQhZ | Normal | 7 | 1.9.5.2.14.5 | 1.9.5.2.14.5 |  | O |  |  |  | P
168 | 5586 | Z3ZWpIsgJCSKUX161hV0 | Normal | 4 | 1.9.5.2.14.8 | 1.9.5.2.14.8 |  | O |  |  |  | P
169 | 5587 | OXOUsYDejGVlgqn4Z1vl | Normal | 5 | 1.9.5.2.14.9 | 1.9.5.2.14.9 |  | O |  |  |  | P
170 | 5588 | MFjHKzinVVI0Ndx8qx0B | Normal | 1 | 1.4.26 | 1.4.26 |  | O |  |  |  | P
171 | 5742 | 88bEv4EMiOL2y8w1ttIM | Normal | 4 | 1.9.5.2.14.3 | 1.9.5.2.14.3 |  | O |  |  |  | P
172 | 5743 | 0Uz4krHDVCdAlMd5aRwh | Normal | 1 | 1.9.5.2.14.4 | 1.9.5.2.14.4 |  | O |  |  |  | P
173 | 5744 | cSBfnbrbVLLFYTMEfBKA | Normal | 6 | 1.9.5.2.14.6 | 1.9.5.2.14.6 |  | O |  |  |  | P
174 | 5745 | ZY99Y6JX4jBylnfeedvo | Normal | 6 | 1.9.5.2.14.7 | 1.9.5.2.14.7 |  | O |  |  |  | P
175 | 6955 | CPACk87DS0kpO7pXcdwS | Normal | 10 | 1.9.5.2.10 | 1.9.5.2.10 |  | O |  |  |  | P
176 | 6997 | MBGoTUikAECGvIHYk1uV | Normal | 24 | 1.9.5.2.3 | 1.9.5.2.3 |  | O |  |  |  | P

## Primary-Constraint
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Primary Constraint - 86 (4%) | Primary Constraint - 86 (4%) | Primary Constraint - 86 (4%) | Primary Constraint - 86 (4%) | Primary Constraint - 86 (4%) | Primary Constraint - 86 (4%) | Primary Constraint - 86 (4%) | Primary Constraint - 86 (4%) | Primary Constraint - 86 (4%) | Primary Constraint - 86 (4%) | Primary Constraint - 86 (4%) | Primary Constraint - 86 (4%) | Primary Constraint - 86 (4%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 155 | 1yu6CrDX9QU5hWE1UWMV | Milestone | 0 | 1.2.7.11 | 1.2.7.11 |  | StartOnOrAfter |  |  |  | None
2 | 7550 | fUEnUBwdI1z3bgOngjaQ | Milestone | 0 | 1.2.7.5 | 1.2.7.5 |  | MandatoryStart |  |  |  | None
3 | 7132 | osdxrWYmqQZxyGZXe9Pr | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | FinishOnOrAfter |  |  |  | None
4 | 7546 | tdocr3pqURBYHZWcAyMG | Normal | 1 | 1.2.10.12 | 1.2.10.12 |  | StartOnOrAfter |  |  |  | None
5 | 7547 | 2p5uMAQ0v8mT9pq4KeWp | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | StartOnOrAfter |  |  |  | None
6 | 7548 | TdNnLE8G4vf1vBjggzLw | Normal | 1 | 1.2.10.15 | 1.2.10.15 |  | StartOnOrAfter |  |  |  | None
7 | 7549 | yUAt6Fi3Vichq9Ai1DSh | Normal | 1 | 1.2.10.13 | 1.2.10.13 |  | StartOnOrAfter |  |  |  | None
8 | 6077 | 9YjbRTuPDmKPhAucMUDE | Milestone | 0 | 1.2.6 | 1.2.6 |  | StartOnOrAfter |  |  |  | None
9 | 436 | OGXVzK31PKUn8DxCdn94 | Normal | 33 | 1.3.3.2.10 | 1.3.3.2.10 |  | StartOnOrAfter |  |  |  | None
10 | 7192 | rcBSOCAYFUxP7jsyoqGw | Normal | 11 | 1.3.2.3.2.1.1.2 | 1.3.2.3.2.1.1.2 |  | StartOnOrAfter |  |  |  | None
11 | 1457 | W1XQ7yoZAeSgm7UftoXN | Normal | 1 | 1.5.5.1.2 | 1.5.5.1.2 |  | StartOnOrAfter |  |  |  | None
12 | 6682 | 695WEwNqpcHeAbXSBRci | Normal | 2 | 1.5.1.3.10 | 1.5.1.3.10 |  | StartOnOrAfter |  |  |  | None
13 | 7545 | 65jUkOPqlMfpoMROhJ4O | Normal | 5 | 1.5.3.2.9.1 | 1.5.3.2.9.1 |  | StartOnOrAfter |  |  |  | None
14 | 3908 | y9tKov3jCEzWGyA9B1wJ | Normal | 5 | 1.4.1.3.1 | 1.4.1.3.1 |  | StartOnOrAfter |  |  |  | None
15 | 5241 | v6EKIZLcnDHW8CXOrD7y | Normal | 21 | 1.4.2.1.3.1 | 1.4.2.1.3.1 |  | StartOnOrAfter |  |  |  | None
16 | 5268 | fG9nayiE82fFlNFtuyfN | Normal | 8 | 1.4.2.1.6.5 | 1.4.2.1.6.5 |  | StartOnOrAfter |  |  |  | None
17 | 5269 | UP8sWsDXCDMiwOqWz3ib | Normal | 5 | 1.4.2.1.6.6 | 1.4.2.1.6.6 |  | StartOnOrAfter |  |  |  | None
18 | 5270 | 0UA65kBzwzHULCayr1Gq | Normal | 8 | 1.4.2.1.6.7 | 1.4.2.1.6.7 |  | StartOnOrAfter |  |  |  | None
19 | 5271 | mtztJWmm2OBnfmSsuoGt | Normal | 10 | 1.4.2.1.6.8 | 1.4.2.1.6.8 |  | StartOnOrAfter |  |  |  | None
20 | 5273 | fGHKYfAaAseAkWqOpGpv | Normal | 10 | 1.4.2.1.6.10 | 1.4.2.1.6.10 |  | StartOnOrAfter |  |  |  | None
21 | 5264 | 2BYRPY9ftrCpjg2j3vxJ | Milestone | 0 | 1.4.2.1.8 | 1.4.2.1.8 |  | StartOnOrAfter |  |  |  | None
22 | 5329 | GYUaK0PI1fV4kag2egD8 | Normal | 1 | 1.4.2.3.4.3 | 1.4.2.3.4.3 |  | StartOnOrAfter |  |  |  | None
23 | 1463 | IQX94tuow2VKmVJTuhEN | Normal | 1 | 1.6.6.1.3 | 1.6.6.1.3 |  | StartOnOrAfter |  |  |  | None
24 | 6621 | pXe0ZxltUhDf1quSL5q2 | Normal | 15 | 1.6.4.20.1.2 | 1.6.4.20.1.2 |  | StartOnOrAfter |  |  |  | None
25 | 7277 | hIopgQViPH34dy6jPgEs | Normal | 6 | 1.6.4.18.3.3.7.5 | 1.6.4.18.3.3.7.5 |  | StartOnOrAfter |  |  |  | None
26 | 7288 | VSJ7G6vuAkApnyRQ2Pu0 | Normal | 0 | 1.6.4.18.3.3.5.2 | 1.6.4.18.3.3.5.2 |  | StartOnOrAfter |  |  |  | None
27 | 7294 | zyUxDMIn8WO6b7iu9x3f | Normal | 0 | 1.6.4.18.3.3.6.1 | 1.6.4.18.3.3.6.1 |  | StartOnOrAfter |  |  |  | None
28 | 6080 | jFrzSNmYyPDtKSvRlBw2 | Normal | 1 | 1.6.1.6 | 1.6.1.6 |  | StartOnOrAfter |  |  |  | None
29 | 7306 | eliMgwas57FZ9dl7RB5T | Normal | 0 | 1.6.3.11.1.3.4.3 | 1.6.3.11.1.3.4.3 |  | StartOnOrAfter |  |  |  | None
30 | 7307 | eye8r8DevGvPITcdrMUe | Normal | 6 | 1.6.3.11.1.3.4.4 | 1.6.3.11.1.3.4.4 |  | StartOnOrAfter |  |  |  | None
31 | 7312 | ZHpaj2955bjmxPKFBEf2 | Normal | 2 | 1.6.3.11.1.3.5.3 | 1.6.3.11.1.3.5.3 |  | StartOnOrAfter |  |  |  | None
32 | 3721 | 45j7fpB55qVEeWfRBgCv | Normal | 1 | 1.8.5.1.4.1 | 1.8.5.1.4.1 |  | StartOnOrAfter |  |  |  | None
33 | 3724 | ZCOxRRLLrh9Pa7VnBAyk | Normal | 27 | 1.8.5.1.5.1 | 1.8.5.1.5.1 |  | StartOnOrAfter |  |  |  | None
34 | 3727 | rGcF2XgkgPtqRDM3KJ2D | Normal | 28 | 1.8.5.1.6.1 | 1.8.5.1.6.1 |  | StartOnOrAfter |  |  |  | None
35 | 3730 | TswICWhG0Mjj1DenbPW5 | Normal | 28 | 1.8.5.1.7.1 | 1.8.5.1.7.1 |  | StartOnOrAfter |  |  |  | None
36 | 3734 | cAszcoDUs4YPdXAiXa4B | Milestone | 0 | 1.8.5.1.9.1 | 1.8.5.1.9.1 |  | StartOnOrAfter |  |  |  | None
37 | 3739 | Ba23bBwg4xGpRd3Ht4kS | Normal | 24 | 1.8.5.1.10.1 | 1.8.5.1.10.1 |  | StartOnOrAfter |  |  |  | None
38 | 5517 | IHfroMkwx3TZoTXYbBOK | Normal | 40 | 1.8.4.1.1 | 1.8.4.1.1 |  | StartOnOrAfter |  |  |  | None
39 | 5518 | V0a5XEJ0jxIkhnpEDg8e | Normal | 40 | 1.8.4.1.2 | 1.8.4.1.2 |  | StartOnOrAfter |  |  |  | None
40 | 5519 | D5sl3M5NpO77EU7TPYT0 | Normal | 40 | 1.8.4.1.3 | 1.8.4.1.3 |  | StartOnOrAfter |  |  |  | None
41 | 916 | d4bxhxtQW3GaLrDrUlf9 | Normal | 17 | 1.9.9.5.1.1 | 1.9.9.5.1.1 |  | StartOnOrAfter |  |  |  | None
42 | 6687 | RiyOBd4mBIE5Cq6C0A4h | Normal | 1 | 1.9.9.12.1 | 1.9.9.12.1 |  | StartOnOrAfter |  |  |  | None
43 | 7451 | nShmtMdGhMi3SzNeAZjW | Milestone | 0 | 1.9.9.13.4.4 | 1.9.9.13.4.4 |  | StartOnOrAfter |  |  |  | None
44 | 7539 | ROucR7pug9aGzObG8pvW | Normal | 1 | 1.7.10.8 | 1.7.10.8 |  | StartOnOrAfter |  |  |  | None
45 | 7541 | R63tw5xkvmDGiWpIPQRa | Normal | 1 | 1.7.10.10 | 1.7.10.10 |  | StartOnOrAfter |  |  |  | None
46 | 7542 | E3YdLEfamF0eZCISJiqw | Normal | 10 | 1.7.10.11 | 1.7.10.11 |  | StartOnOrAfter |  |  |  | None
47 | 7543 | nhpJxewK7uClQLzGXJQJ | Normal | 1 | 1.7.10.12 | 1.7.10.12 |  | StartOnOrAfter |  |  |  | None
48 | 7544 | cfuUTFyz3WOPAOOiNQOb | Normal | 1 | 1.7.10.13 | 1.7.10.13 |  | StartOnOrAfter |  |  |  | None
49 | 1495 | 0kid3Dd3U5gCQNrt2pwY | Normal | 1 | 1.9.7.18.8 | 1.9.7.18.8 |  | StartOnOrAfter |  |  |  | None
50 | 1504 | ndaml8HRsqEWzWIKrI7h | Normal | 5 | 1.9.7.18.10 | 1.9.7.18.10 |  | StartOnOrAfter |  |  |  | None
51 | 1496 | 5t2MhilpkZRDQA3VTcGS | Normal | 48 | 1.9.7.7 | 1.9.7.7 |  | StartOnOrAfter |  |  |  | None
52 | 1505 | 4c3z8pWafVxAWNC1MpC9 | Normal | 106 | 1.9.7.8 | 1.9.7.8 |  | StartOnOrAfter |  |  |  | None
53 | 1531 | KX1eD2ASIZaZBZuqoVp4 | Normal | 1 | 1.9.7.14.2 | 1.9.7.14.2 |  | StartOnOrAfter |  |  |  | None
54 | 1547 | K0gsOWDMqaySswr72BAQ | Normal | 1 | 1.9.7.16.3 | 1.9.7.16.3 |  | StartOnOrAfter |  |  |  | None
55 | 4575 | nPe6rBdPLk408ntp39jn | Normal | 1 | 1.9.7.3 | 1.9.7.3 |  | StartOnOrAfter |  |  |  | None
56 | 4581 | FxGRGf2kppDMdfFrZkS4 | Normal | 36 | 1.9.7.12 | 1.9.7.12 |  | StartOnOrAfter |  |  |  | None
57 | 7457 | abNwDWOnFoe0xwhiRueS | Normal | 1 | 1.7.8.18.4 | 1.7.8.18.4 |  | StartOnOrAfter |  |  |  | None
58 | 7458 | cMhUMuxC0sax27543As7 | Normal | 24 | 1.7.8.18.5 | 1.7.8.18.5 |  | StartOnOrAfter |  |  |  | None
59 | 7324 | GVXYroUMjcAFUHa4B19H | Normal | 1 | 1.7.8.19 | 1.7.8.19 |  | StartOnOrAfter |  |  |  | None
60 | 7383 | chM988R4AoJxJINOHhOy | Normal | 1 | 1.9.7.22.1 | 1.9.7.22.1 |  | StartOnOrAfter |  |  |  | None
61 | 3776 | GHLE38QRMYNBeSYAGB18 | Normal | 32 | 1.7.1.2.6.3 | 1.7.1.2.6.3 |  | StartOnOrAfter |  |  |  | None
62 | 7183 | 2TS72P2Q9EOAovcnBEYh | Milestone | 0 | 1.7.1.3.7.2 | 1.7.1.3.7.2 |  | StartOnOrAfter |  |  |  | None
63 | 7184 | gKjyagqR1BEsAZjZk4l5 | Milestone | 0 | 1.7.1.3.7.3 | 1.7.1.3.7.3 |  | StartOnOrAfter |  |  |  | None
64 | 6148 | V03eKqopjAXoUvRodLvQ | Normal | 13 | 1.7.1.5.6 | 1.7.1.5.6 |  | StartOnOrAfter |  |  |  | None
65 | 5860 | AMUT2hrMeOWSIoK5dO6S | Normal | 10 | 1.9.6.10.2.4 | 1.9.6.10.2.4 |  | StartOnOrAfter |  |  |  | None
66 | 6958 | 6Ul4V6iAcnpVqewOp14Y | Normal | 4 | 1.9.6.1.4.1 | 1.9.6.1.4.1 |  | StartOnOrAfter |  |  |  | None
67 | 6959 | w9Vvv79ftt4PUqInNFyD | Normal | 5 | 1.9.6.1.4.2 | 1.9.6.1.4.2 |  | StartOnOrAfter |  |  |  | None
68 | 6427 | NeAxFJaqSLize8VPNJ6N | Normal | 1 | 1.7.1.8.3 | 1.7.1.8.3 |  | StartOnOrAfter |  |  |  | None
69 | 5974 | cJ7VeFZezCBnvYlHxCmb | Normal | 1 | 1.9.8.1.6.7 | 1.9.8.1.6.7 |  | StartOnOrAfter |  |  |  | None
70 | 4231 | 8h0WH2qeIC7tfvcerCPa | Normal | 1 | 1.9.8.2.3 | 1.9.8.2.3 |  | StartOnOrAfter |  |  |  | None
71 | 4243 | LpPx7AWOh1V8dzWVWc6j | Normal | 1 | 1.9.8.4.5 | 1.9.8.4.5 |  | StartOnOrAfter |  |  |  | None
72 | 4248 | E1RJwJWM8qrsKP3o7Toy | Normal | 1 | 1.9.8.7 | 1.9.8.7 |  | StartOnOrAfter |  |  |  | None
73 | 4251 | IBg36OMMKUy3vwEnRNF0 | Normal | 1 | 1.9.8.6 | 1.9.8.6 |  | StartOnOrAfter |  |  |  | None
74 | 4253 | hnujWIe1JDNg9VHs3TWw | Normal | 1 | 1.9.8.8 | 1.9.8.8 |  | StartOnOrAfter |  |  |  | None
75 | 4258 | GzQkXlTiYJMdE6nBDVeb | Normal | 6 | 1.9.8.10.1 | 1.9.8.10.1 |  | StartOnOrAfter |  |  |  | None
76 | 6084 | deZM0xh115wln716GUoI | Normal | 1 | 1.9.8.9 | 1.9.8.9 |  | StartOnOrAfter |  |  |  | None
77 | 7321 | CTokiQfH6gyOyeZJGrxP | Normal | 1 | 1.7.9.11 | 1.7.9.11 |  | StartOnOrAfter |  |  |  | None
78 | 6532 | 15e7xcLR1b1jSikaz0S2 | Normal | 32 | 1.9.5.2.4.2 | 1.9.5.2.4.2 |  | StartOnOrAfter |  |  |  | None
79 | 6533 | b0mutjzKj8FRw4zkbb8K | Normal | 32 | 1.9.5.2.4.1 | 1.9.5.2.4.1 |  | StartOnOrAfter |  |  |  | None
80 | 6534 | 8Gl2bk4Fxxo2fsClDJqG | Normal | 32 | 1.9.5.2.4.3 | 1.9.5.2.4.3 |  | StartOnOrAfter |  |  |  | None
81 | 6535 | dWze9AnK8NrEMD9LOEyU | Normal | 32 | 1.9.5.2.4.4 | 1.9.5.2.4.4 |  | StartOnOrAfter |  |  |  | None
82 | 7528 | 8SnF5zCB4rJyZyQZLLZc | Normal | 8 | 1.7.5.1 | 1.7.5.1 |  | StartOnOrAfter |  |  |  | None
83 | 6690 | bopLkaAZbmZjIM9EGI6L | Normal | 532 | 1.11.2 | 1.11.2 |  | StartOnOrAfter |  |  |  | None
84 | 6697 | gpkN7vTMpz4ZZxhDAmeL | Normal | 126 | 1.11.10 | 1.11.10 |  | StartOnOrAfter |  |  |  | None
85 | 156 | 0RXSkgYJdrs7AeQvgU3w | Milestone | 0 | 1.10.24 | 1.10.24 |  | StartOnOrAfter |  |  |  | None
86 | 157 | DYCfhHgWVvjY4WPSrw6q | Milestone | 0 | 1.10.25 | 1.10.25 |  | StartOnOrAfter |  |  |  | Deadline

## Primary-Constraint-Date
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Primary Constraint Date - 86 (4%) | Primary Constraint Date - 86 (4%) | Primary Constraint Date - 86 (4%) | Primary Constraint Date - 86 (4%) | Primary Constraint Date - 86 (4%) | Primary Constraint Date - 86 (4%) | Primary Constraint Date - 86 (4%) | Primary Constraint Date - 86 (4%) | Primary Constraint Date - 86 (4%) | Primary Constraint Date - 86 (4%) | Primary Constraint Date - 86 (4%) | Primary Constraint Date - 86 (4%) | Primary Constraint Date - 86 (4%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 155 | 1yu6CrDX9QU5hWE1UWMV | Milestone | 0 | 1.2.7.11 | 1.2.7.11 |  | 2026-10-01 08:00 | q |  |  | O
2 | 7550 | fUEnUBwdI1z3bgOngjaQ | Milestone | 0 | 1.2.7.5 | 1.2.7.5 |  | 2025-11-13 08:00 | q |  |  | O
3 | 7132 | osdxrWYmqQZxyGZXe9Pr | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 2025-03-24 17:00 | q |  |  | O
4 | 7546 | tdocr3pqURBYHZWcAyMG | Normal | 1 | 1.2.10.12 | 1.2.10.12 |  | 2025-03-28 08:00 | q |  |  | O
5 | 7547 | 2p5uMAQ0v8mT9pq4KeWp | Milestone | 0 | 1.2.10.11 | 1.2.10.11 |  | 2025-03-14 08:00 | q |  |  | O
6 | 7548 | TdNnLE8G4vf1vBjggzLw | Normal | 1 | 1.2.10.15 | 1.2.10.15 |  | 2025-03-10 08:00 | q |  |  | O
7 | 7549 | yUAt6Fi3Vichq9Ai1DSh | Normal | 1 | 1.2.10.13 | 1.2.10.13 |  | 2025-02-20 08:00 | q |  |  | O
8 | 6077 | 9YjbRTuPDmKPhAucMUDE | Milestone | 0 | 1.2.6 | 1.2.6 |  | 2028-09-29 08:00 | q |  |  | O
9 | 436 | OGXVzK31PKUn8DxCdn94 | Normal | 33 | 1.3.3.2.10 | 1.3.3.2.10 |  | 2025-03-27 08:00 | q |  |  | O
10 | 7192 | rcBSOCAYFUxP7jsyoqGw | Normal | 11 | 1.3.2.3.2.1.1.2 | 1.3.2.3.2.1.1.2 |  | 2025-02-24 08:00 | q |  |  | O
11 | 1457 | W1XQ7yoZAeSgm7UftoXN | Normal | 1 | 1.5.5.1.2 | 1.5.5.1.2 |  | 2025-02-14 08:00 | q |  |  | O
12 | 6682 | 695WEwNqpcHeAbXSBRci | Normal | 2 | 1.5.1.3.10 | 1.5.1.3.10 |  | 2025-05-23 08:00 | q |  |  | O
13 | 7545 | 65jUkOPqlMfpoMROhJ4O | Normal | 5 | 1.5.3.2.9.1 | 1.5.3.2.9.1 |  | 2025-02-10 08:00 | q |  |  | O
14 | 3908 | y9tKov3jCEzWGyA9B1wJ | Normal | 5 | 1.4.1.3.1 | 1.4.1.3.1 |  | 2025-06-27 08:00 | q |  |  | O
15 | 5241 | v6EKIZLcnDHW8CXOrD7y | Normal | 21 | 1.4.2.1.3.1 | 1.4.2.1.3.1 |  | 2025-05-23 08:00 | q |  |  | O
16 | 5268 | fG9nayiE82fFlNFtuyfN | Normal | 8 | 1.4.2.1.6.5 | 1.4.2.1.6.5 |  | 2025-06-03 08:00 | q |  |  | O
17 | 5269 | UP8sWsDXCDMiwOqWz3ib | Normal | 5 | 1.4.2.1.6.6 | 1.4.2.1.6.6 |  | 2025-04-30 08:00 | q |  |  | O
18 | 5270 | 0UA65kBzwzHULCayr1Gq | Normal | 8 | 1.4.2.1.6.7 | 1.4.2.1.6.7 |  | 2025-05-12 08:00 | q |  |  | O
19 | 5271 | mtztJWmm2OBnfmSsuoGt | Normal | 10 | 1.4.2.1.6.8 | 1.4.2.1.6.8 |  | 2025-05-22 08:00 | q |  |  | O
20 | 5273 | fGHKYfAaAseAkWqOpGpv | Normal | 10 | 1.4.2.1.6.10 | 1.4.2.1.6.10 |  | 2025-06-30 08:00 | q |  |  | O
21 | 5264 | 2BYRPY9ftrCpjg2j3vxJ | Milestone | 0 | 1.4.2.1.8 | 1.4.2.1.8 |  | 2025-02-21 08:00 | q |  |  | O
22 | 5329 | GYUaK0PI1fV4kag2egD8 | Normal | 1 | 1.4.2.3.4.3 | 1.4.2.3.4.3 |  | 2025-08-14 08:00 | q |  |  | O
23 | 1463 | IQX94tuow2VKmVJTuhEN | Normal | 1 | 1.6.6.1.3 | 1.6.6.1.3 |  | 2025-02-13 08:00 | q |  |  | O
24 | 6621 | pXe0ZxltUhDf1quSL5q2 | Normal | 15 | 1.6.4.20.1.2 | 1.6.4.20.1.2 |  | 2025-05-02 08:00 | q |  |  | O
25 | 7277 | hIopgQViPH34dy6jPgEs | Normal | 6 | 1.6.4.18.3.3.7.5 | 1.6.4.18.3.3.7.5 |  | 2025-03-07 08:00 | q |  |  | O
26 | 7288 | VSJ7G6vuAkApnyRQ2Pu0 | Normal | 0 | 1.6.4.18.3.3.5.2 | 1.6.4.18.3.3.5.2 |  | 2025-01-20 08:00 | q |  |  | O
27 | 7294 | zyUxDMIn8WO6b7iu9x3f | Normal | 0 | 1.6.4.18.3.3.6.1 | 1.6.4.18.3.3.6.1 |  | 2025-01-20 08:00 | q |  |  | O
28 | 6080 | jFrzSNmYyPDtKSvRlBw2 | Normal | 1 | 1.6.1.6 | 1.6.1.6 |  | 2026-08-26 08:00 | q |  |  | O
29 | 7306 | eliMgwas57FZ9dl7RB5T | Normal | 0 | 1.6.3.11.1.3.4.3 | 1.6.3.11.1.3.4.3 |  | 2025-01-29 08:00 | q |  |  | O
30 | 7307 | eye8r8DevGvPITcdrMUe | Normal | 6 | 1.6.3.11.1.3.4.4 | 1.6.3.11.1.3.4.4 |  | 2025-02-10 08:00 | q |  |  | O
31 | 7312 | ZHpaj2955bjmxPKFBEf2 | Normal | 2 | 1.6.3.11.1.3.5.3 | 1.6.3.11.1.3.5.3 |  | 2025-02-10 08:00 | q |  |  | O
32 | 3721 | 45j7fpB55qVEeWfRBgCv | Normal | 1 | 1.8.5.1.4.1 | 1.8.5.1.4.1 |  | 2025-03-19 08:00 | q |  |  | O
33 | 3724 | ZCOxRRLLrh9Pa7VnBAyk | Normal | 27 | 1.8.5.1.5.1 | 1.8.5.1.5.1 |  | 2025-03-24 08:00 | q |  |  | O
34 | 3727 | rGcF2XgkgPtqRDM3KJ2D | Normal | 28 | 1.8.5.1.6.1 | 1.8.5.1.6.1 |  | 2025-05-08 08:00 | q |  |  | O
35 | 3730 | TswICWhG0Mjj1DenbPW5 | Normal | 28 | 1.8.5.1.7.1 | 1.8.5.1.7.1 |  | 2025-03-11 08:00 | q |  |  | O
36 | 3734 | cAszcoDUs4YPdXAiXa4B | Milestone | 0 | 1.8.5.1.9.1 | 1.8.5.1.9.1 |  | 2025-03-17 08:00 | q |  |  | O
37 | 3739 | Ba23bBwg4xGpRd3Ht4kS | Normal | 24 | 1.8.5.1.10.1 | 1.8.5.1.10.1 |  | 2025-03-17 08:00 | q |  |  | O
38 | 5517 | IHfroMkwx3TZoTXYbBOK | Normal | 40 | 1.8.4.1.1 | 1.8.4.1.1 |  | 2025-03-20 08:00 | q |  |  | O
39 | 5518 | V0a5XEJ0jxIkhnpEDg8e | Normal | 40 | 1.8.4.1.2 | 1.8.4.1.2 |  | 2025-03-20 08:00 | q |  |  | O
40 | 5519 | D5sl3M5NpO77EU7TPYT0 | Normal | 40 | 1.8.4.1.3 | 1.8.4.1.3 |  | 2025-03-20 08:00 | q |  |  | O
41 | 916 | d4bxhxtQW3GaLrDrUlf9 | Normal | 17 | 1.9.9.5.1.1 | 1.9.9.5.1.1 |  | 2025-08-12 08:00 | q |  |  | O
42 | 6687 | RiyOBd4mBIE5Cq6C0A4h | Normal | 1 | 1.9.9.12.1 | 1.9.9.12.1 |  | 2025-08-29 08:00 | q |  |  | O
43 | 7451 | nShmtMdGhMi3SzNeAZjW | Milestone | 0 | 1.9.9.13.4.4 | 1.9.9.13.4.4 |  | 2026-10-02 08:00 | q |  |  | O
44 | 7539 | ROucR7pug9aGzObG8pvW | Normal | 1 | 1.7.10.8 | 1.7.10.8 |  | 2025-02-28 08:00 | q |  |  | O
45 | 7541 | R63tw5xkvmDGiWpIPQRa | Normal | 1 | 1.7.10.10 | 1.7.10.10 |  | 2025-03-31 08:00 | q |  |  | O
46 | 7542 | E3YdLEfamF0eZCISJiqw | Normal | 10 | 1.7.10.11 | 1.7.10.11 |  | 2025-04-14 08:00 | q |  |  | O
47 | 7543 | nhpJxewK7uClQLzGXJQJ | Normal | 1 | 1.7.10.12 | 1.7.10.12 |  | 2025-05-30 08:00 | q |  |  | O
48 | 7544 | cfuUTFyz3WOPAOOiNQOb | Normal | 1 | 1.7.10.13 | 1.7.10.13 |  | 2025-05-30 08:00 | q |  |  | O
49 | 1495 | 0kid3Dd3U5gCQNrt2pwY | Normal | 1 | 1.9.7.18.8 | 1.9.7.18.8 |  | 2025-02-26 08:00 | q |  |  | O
50 | 1504 | ndaml8HRsqEWzWIKrI7h | Normal | 5 | 1.9.7.18.10 | 1.9.7.18.10 |  | 2025-02-26 08:00 | q |  |  | O
51 | 1496 | 5t2MhilpkZRDQA3VTcGS | Normal | 48 | 1.9.7.7 | 1.9.7.7 |  | 2025-02-26 08:00 | q |  |  | O
52 | 1505 | 4c3z8pWafVxAWNC1MpC9 | Normal | 106 | 1.9.7.8 | 1.9.7.8 |  | 2025-02-26 08:00 | q |  |  | O
53 | 1531 | KX1eD2ASIZaZBZuqoVp4 | Normal | 1 | 1.9.7.14.2 | 1.9.7.14.2 |  | 2025-05-01 08:00 | q |  |  | O
54 | 1547 | K0gsOWDMqaySswr72BAQ | Normal | 1 | 1.9.7.16.3 | 1.9.7.16.3 |  | 2025-02-21 08:00 | q |  |  | O
55 | 4575 | nPe6rBdPLk408ntp39jn | Normal | 1 | 1.9.7.3 | 1.9.7.3 |  | 2025-06-06 08:00 | q |  |  | O
56 | 4581 | FxGRGf2kppDMdfFrZkS4 | Normal | 36 | 1.9.7.12 | 1.9.7.12 |  | 2025-04-01 08:00 | q |  |  | O
57 | 7457 | abNwDWOnFoe0xwhiRueS | Normal | 1 | 1.7.8.18.4 | 1.7.8.18.4 |  | 2025-03-19 08:00 | q |  |  | O
58 | 7458 | cMhUMuxC0sax27543As7 | Normal | 24 | 1.7.8.18.5 | 1.7.8.18.5 |  | 2025-04-07 08:00 | q |  |  | O
59 | 7324 | GVXYroUMjcAFUHa4B19H | Normal | 1 | 1.7.8.19 | 1.7.8.19 |  | 2025-03-28 08:00 | q |  |  | O
60 | 7383 | chM988R4AoJxJINOHhOy | Normal | 1 | 1.9.7.22.1 | 1.9.7.22.1 |  | 2025-02-26 08:00 | q |  |  | O
61 | 3776 | GHLE38QRMYNBeSYAGB18 | Normal | 32 | 1.7.1.2.6.3 | 1.7.1.2.6.3 |  | 2025-02-03 08:00 | q |  |  | O
62 | 7183 | 2TS72P2Q9EOAovcnBEYh | Milestone | 0 | 1.7.1.3.7.2 | 1.7.1.3.7.2 |  | 2025-01-30 08:00 | q |  |  | O
63 | 7184 | gKjyagqR1BEsAZjZk4l5 | Milestone | 0 | 1.7.1.3.7.3 | 1.7.1.3.7.3 |  | 2025-02-28 08:00 | q |  |  | O
64 | 6148 | V03eKqopjAXoUvRodLvQ | Normal | 13 | 1.7.1.5.6 | 1.7.1.5.6 |  | 2025-01-21 08:00 | q |  |  | O
65 | 5860 | AMUT2hrMeOWSIoK5dO6S | Normal | 10 | 1.9.6.10.2.4 | 1.9.6.10.2.4 |  | 2025-05-05 08:00 | q |  |  | O
66 | 6958 | 6Ul4V6iAcnpVqewOp14Y | Normal | 4 | 1.9.6.1.4.1 | 1.9.6.1.4.1 |  | 2025-02-03 08:00 | q |  |  | O
67 | 6959 | w9Vvv79ftt4PUqInNFyD | Normal | 5 | 1.9.6.1.4.2 | 1.9.6.1.4.2 |  | 2025-02-03 08:00 | q |  |  | O
68 | 6427 | NeAxFJaqSLize8VPNJ6N | Normal | 1 | 1.7.1.8.3 | 1.7.1.8.3 |  | 2025-03-14 08:00 | q |  |  | O
69 | 5974 | cJ7VeFZezCBnvYlHxCmb | Normal | 1 | 1.9.8.1.6.7 | 1.9.8.1.6.7 |  | 2025-02-27 08:00 | q |  |  | O
70 | 4231 | 8h0WH2qeIC7tfvcerCPa | Normal | 1 | 1.9.8.2.3 | 1.9.8.2.3 |  | 2025-06-24 08:00 | q |  |  | O
71 | 4243 | LpPx7AWOh1V8dzWVWc6j | Normal | 1 | 1.9.8.4.5 | 1.9.8.4.5 |  | 2025-05-13 08:00 | q |  |  | O
72 | 4248 | E1RJwJWM8qrsKP3o7Toy | Normal | 1 | 1.9.8.7 | 1.9.8.7 |  | 2025-08-05 08:00 | q |  |  | O
73 | 4251 | IBg36OMMKUy3vwEnRNF0 | Normal | 1 | 1.9.8.6 | 1.9.8.6 |  | 2025-06-05 08:00 | q |  |  | O
74 | 4253 | hnujWIe1JDNg9VHs3TWw | Normal | 1 | 1.9.8.8 | 1.9.8.8 |  | 2025-08-12 08:00 | q |  |  | O
75 | 4258 | GzQkXlTiYJMdE6nBDVeb | Normal | 6 | 1.9.8.10.1 | 1.9.8.10.1 |  | 2025-09-26 08:00 | q |  |  | O
76 | 6084 | deZM0xh115wln716GUoI | Normal | 1 | 1.9.8.9 | 1.9.8.9 |  | 2026-09-15 08:00 | q |  |  | O
77 | 7321 | CTokiQfH6gyOyeZJGrxP | Normal | 1 | 1.7.9.11 | 1.7.9.11 |  | 2025-05-30 08:00 | q |  |  | O
78 | 6532 | 15e7xcLR1b1jSikaz0S2 | Normal | 32 | 1.9.5.2.4.2 | 1.9.5.2.4.2 |  | 2025-03-03 08:00 | q |  |  | O
79 | 6533 | b0mutjzKj8FRw4zkbb8K | Normal | 32 | 1.9.5.2.4.1 | 1.9.5.2.4.1 |  | 2025-03-03 08:00 | q |  |  | O
80 | 6534 | 8Gl2bk4Fxxo2fsClDJqG | Normal | 32 | 1.9.5.2.4.3 | 1.9.5.2.4.3 |  | 2025-03-03 08:00 | q |  |  | O
81 | 6535 | dWze9AnK8NrEMD9LOEyU | Normal | 32 | 1.9.5.2.4.4 | 1.9.5.2.4.4 |  | 2025-03-03 08:00 | q |  |  | O
82 | 7528 | 8SnF5zCB4rJyZyQZLLZc | Normal | 8 | 1.7.5.1 | 1.7.5.1 |  | 2025-03-03 08:00 | q |  |  | O
83 | 6690 | bopLkaAZbmZjIM9EGI6L | Normal | 532 | 1.11.2 | 1.11.2 |  | 2026-09-08 08:00 | q |  |  | O
84 | 6697 | gpkN7vTMpz4ZZxhDAmeL | Normal | 126 | 1.11.10 | 1.11.10 |  | 2025-02-03 08:00 | q |  |  | O
85 | 156 | 0RXSkgYJdrs7AeQvgU3w | Milestone | 0 | 1.10.24 | 1.10.24 |  | 2026-08-17 08:00 | q |  |  | O
86 | 157 | DYCfhHgWVvjY4WPSrw6q | Milestone | 0 | 1.10.25 | 1.10.25 |  | 2026-09-01 08:00 | p | 0 |  | 2026-09-01 17:00

## Baseline-Work
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2

## Actual-Work
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Actual Work - 0 (0%) | Actual Work - 0 (0%) | Actual Work - 0 (0%) | Actual Work - 0 (0%) | Actual Work - 0 (0%) | Actual Work - 0 (0%) | Actual Work - 0 (0%) | Actual Work - 0 (0%) | Actual Work - 0 (0%) | Actual Work - 0 (0%) | Actual Work - 0 (0%) | Actual Work - 0 (0%) | Actual Work - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2

## Remaining-Work
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Remaining Work - 9 (0%) | Remaining Work - 9 (0%) | Remaining Work - 9 (0%) | Remaining Work - 9 (0%) | Remaining Work - 9 (0%) | Remaining Work - 9 (0%) | Remaining Work - 9 (0%) | Remaining Work - 9 (0%) | Remaining Work - 9 (0%) | Remaining Work - 9 (0%) | Remaining Work - 9 (0%) | Remaining Work - 9 (0%) | Remaining Work - 9 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 1249 | v1zgYyoO7UpynPZXt29g | Summary | 611 | 1 | 1 |  | 49581.4577 | p | 2461.2317 | -5% | 52042.6893
2 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 44602.5138 | p | 2461.2317 | -6% | 47063.7455
3 | 6294 | Jtjxi70STISSeVqV8OJy | Summary | 163 | 1.9.6 | 1.9.6 |  | 328 | p | 7.6667 | -2% | 335.6667
4 | 3745 | D0mR64Wbk6oru5hoL4DG | Summary | 62 | 1.7.1.2 | 1.7.1.2 |  | 328 | p | 7.6667 | -2% | 335.6667
5 | 3773 | jfB1zdAbu7JeWEH3ijwy | Summary | 73 | 1.7.1.2.6 | 1.7.1.2.6 |  | 328 | p | 7.6667 | -2% | 335.6667
6 | 3776 | GHLE38QRMYNBeSYAGB18 | Normal | 32 | 1.7.1.2.6.3 | 1.7.1.2.6.3 |  | 256 | p | 14.5167 | -6% | 270.5167
7 | 3777 | YuGKQIQDxLVYRZzgUQjw | Normal | 9 | 1.7.1.2.6.4 | 1.7.1.2.6.4 |  | 72 | q | -6.85 | (-10%) | 65.15
8 | 6314 | PaZTrKFuMaJQzXHDclW5 | Summary | 34 | 1.9.2 | 1.9.2 |  | 44027.5138 | p | 2453.565 | -6% | 46481.0788
9 | 5666 | lc2LPCzbTjVw9vZ8eS89 | Summary | 23 | 1.9.2.2 | 1.9.2.2 |  | 43987.5138 | p | 2453.565 | -6% | 46441.0788

## Total-Work
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Total Work - 9 (0%) | Total Work - 9 (0%) | Total Work - 9 (0%) | Total Work - 9 (0%) | Total Work - 9 (0%) | Total Work - 9 (0%) | Total Work - 9 (0%) | Total Work - 9 (0%) | Total Work - 9 (0%) | Total Work - 9 (0%) | Total Work - 9 (0%) | Total Work - 9 (0%) | Total Work - 9 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2
1 | 1249 | v1zgYyoO7UpynPZXt29g | Summary | 611 | 1 | 1 |  | 65299.9112 | p | 2461.2317 | -4% | 67761.1428
2 | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Summary | 263 | 1.9 | 1.9 |  | 56483 | p | 2461.2317 | -4% | 58944.2317
3 | 6294 | Jtjxi70STISSeVqV8OJy | Summary | 163 | 1.9.6 | 1.9.6 |  | 1600 | p | 7.6667 | 0% | 1607.6667
4 | 3745 | D0mR64Wbk6oru5hoL4DG | Summary | 62 | 1.7.1.2 | 1.7.1.2 |  | 1600 | p | 7.6667 | 0% | 1607.6667
5 | 3773 | jfB1zdAbu7JeWEH3ijwy | Summary | 73 | 1.7.1.2.6 | 1.7.1.2.6 |  | 1072 | p | 7.6667 | -1% | 1079.6667
6 | 3776 | GHLE38QRMYNBeSYAGB18 | Normal | 32 | 1.7.1.2.6.3 | 1.7.1.2.6.3 |  | 296 | p | 14.5167 | -5% | 310.5167
7 | 3777 | YuGKQIQDxLVYRZzgUQjw | Normal | 9 | 1.7.1.2.6.4 | 1.7.1.2.6.4 |  | 72 | q | -6.85 | (-10%) | 65.15
8 | 6314 | PaZTrKFuMaJQzXHDclW5 | Summary | 34 | 1.9.2 | 1.9.2 |  | 54636 | p | 2453.565 | -4% | 57089.565
9 | 5666 | lc2LPCzbTjVw9vZ8eS89 | Summary | 23 | 1.9.2.2 | 1.9.2.2 |  | 54356 | p | 2453.565 | -5% | 56809.565

## Baseline-Cost
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2

## Budget-Cost
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2

## Actual-Cost
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2

## Remaining-Cost
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2

## Total-Cost
Acumen Fuse® Forensic Analysis Report
rge Test File vs Large Test File2
Large Test File - 2125 Activities
Compared to: 1 Snapshot
Created on: 7/21/2026
Created by: dpolitte
Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Large Test File | Large Test File2 | Large Test File2 | Large Test File2 | Large Test File2