# Acumen Fuse® Diagnostic Executive Briefing

Report Generated On Tuesday, July 21, 2026

Created by dpolitte

## rge Test File vs Large Test File2 Summary

An Acumen Fuse analysis was conducted on Tuesday, July 21, 2026 on the rge Test File vs Large Test File2 workbook. It contains 1 project: Large Test File, modeled in Microsoft® Office Project*. It also contains 1 snapshot: Large Test File2, modeled in Microsoft® Office Project*.

The earliest start date is Wednesday, June 7, 2017 with the latest completion date being Friday, April 20, 2029

### Ribbon Browser

| Ribbons \ Phases | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Large Test File |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Large Test File2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

### Trend Analysis

The following section details how the characteristics of the workbook vary over time. This provides useful insight by showing improving/worsening trends. The analysis was conducted using years as time intervals:

- Status Date : decreases over time with the highest period being 2017 (2/7/2025) and the lowest period being 2017 (2/7/2025).

- WBS: decreases over time with the highest period being 2017 (1) and the lowest period being 2017 (1).

- New Activity - Created (Snapshot): remains constant over time.

- New Activity - Already Finished (Snapshot) - check/compare: remains constant over time.

## Projects Summary

### Large Test File Project

The Large Test File project has a start date of Wednesday, June 7, 2017 and has Friday, September 29, 2028 as the completion date. The project is currently in progress with a status date of Friday, February 7, 2025. It has 1554 normal activities of which 609 (39.2%) are complete, 108 (6.9%) are in progress and 837 (53.9%) are still planned. It contains 169 milestones, 402 summaries and no LOEs.

The project baseline start date was Wednesday, June 7, 2017 with the baseline finish date being Friday, September 29, 2028. The project is currently on schedule.

The project has no baseline costs.

### Large Test File2 Project

The Large Test File2 project has a start date of Wednesday, June 7, 2017 and has Friday, April 20, 2029 as the completion date. The project is currently in progress with a status date of Monday, March 10, 2025. It has 1553 normal activities of which 634 (40.8%) are complete, 92 (5.9%) are in progress and 827 (53.3%) are still planned. It contains 169 milestones, 402 summaries and no LOEs.

The project baseline start date was Wednesday, June 7, 2017 with the baseline finish date being Friday, September 29, 2028. The project is currently behind schedule by 202 days.

The project has no baseline costs.

## Ribbon Analysis

A ribbon analysis shows how the results from the selected metrics vary across the selected groupings of activities. This is a useful means of comparing between such groupings. In addition, the scorecard value for each ribbon provides an overarching summary of each ribbon.

The workbook has been grouped by projects. The analysis contains 2 ribbons: "Large Test File" and "Large Test File2".

### Ribbon Analyzer

| Ribbons \ Phases | Status Date | Specific Task Finish | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Scorecard Value |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Large Test File | 2/7/2025 |  | 0 | 0 | 8 | 93 | 0 | 0 | 814 | 35 | 87 | 0 | 0 | 866 | 1115 | x | 0.97 | 0.52 | 33.4% |
| Large Test File2 | 3/10/2025 |  | 2 | 0 | 8 | 90 | 0 | 0 | 660 | 112 | 86 | 322 | 4 | 842 | 1095 | ✓ | 0.59 | 0.53 | 34.9% |

- Large Test File has the worst scorecard value with a score of 33.4%.

- Large Test File2 has the best scorecard value with a score of 34.9%.

### Large Test File Ribbon Analysis

The Large Test File ribbon contains 1554 normal activities, 169 milestones, 402 summaries and 0 LOEs spanning from Wednesday, June 7, 2017 to Friday, September 29, 2028.

38.4% of the activities in this ribbon are complete; 48.8% are planned and 12.8% are in progress.

The ribbon is 4132 days long.

The ribbon was analyzed using 18 metrics, as detailed below:

- 2/7/2025 activities have Status Date .

- 0 activities (0%) are 1. Logic. No Exceptions. Verify that the program logic is accurate.

- 0 activities (0%) have 2. Leads. No Exceptions. This is the target state.

- 8 activities (0%) have 3. Lags. 5% or fewer exceptions. Some improvements may be required.

- This ribbon has 93 4. SS/FF Relations (6%). 10% or fewer links are FF or SS.

- This ribbon has 0 4. SF Relations (0%). No SF predecessors have been used.

- 0 activities (0%) have 5. Hard Constraint. No exceptions.

- 814 activities (88%) have 6. High Float. 20% or more exceptions - Improvements are required.

- 35 activities (4%) have 7. Negative Float. Fewer than 5% of items have negative float. Corrective action plan to eliminate negative float recommended.

- 87 activities (9%) have 8. High Duration. Less than 20% exceptions. Some improvements may be required.

- 0 activities (0%) have 9. Invalid Forecast Dates. No Exceptions. This is the target state.

- 0 activities (0%) have 9. Invalid Actual Dates. No Exceptions. This is the target state.

- 866 activities (94%) have 10. Resources. Not all activities have cost/resources assigned.

- 1115 activities (91%) are 11. Missed Activities. 20% or more exceptions.

- This ribbon has a 12. Critical Path Test of x.

- This ribbon has a 13. CPLI of 0.97. Critical path length is greater than 95% of the duration of the project. This is the target state.

- This ribbon has a 14. BEI of 0.52. Less than 95% of all activities are completed on or ahead of schedule. Project review required.

### Large Test File2 Ribbon Analysis

The Large Test File2 ribbon contains 1553 normal activities, 169 milestones, 402 summaries and 0 LOEs spanning from Wednesday, June 7, 2017 to Friday, April 20, 2029.

39.5% of the activities in this ribbon are complete; 48.3% are planned and 12.1% are in progress.

The ribbon is 4335 days long.

The ribbon was analyzed using 18 metrics, as detailed below:

- 3/10/2025 activities have Status Date .

- 2 activities (0%) are 1. Logic. 5% or fewer exceptions. Some improvements may be required.

- 0 activities (0%) have 2. Leads. No Exceptions. This is the target state.

- 8 activities (0%) have 3. Lags. 5% or fewer exceptions. Some improvements may be required.

- This ribbon has 90 4. SS/FF Relations (6%). 10% or fewer links are FF or SS.

- This ribbon has 0 4. SF Relations (0%). No SF predecessors have been used.

- 0 activities (0%) have 5. Hard Constraint. No exceptions.

- 660 activities (73%) have 6. High Float. 20% or more exceptions - Improvements are required.

- 112 activities (12%) have 7. Negative Float. 5% or more exceptions. Corrective action plan to eliminate negative float recommended.

- 86 activities (10%) have 8. High Duration. Less than 20% exceptions. Some improvements may be required.

- 322 activities (36%) have 9. Invalid Forecast Dates. Exceptions. Forecast dates should not exist prior to the time now date.

- 4 activities (0%) have 9. Invalid Actual Dates. Exceptions. Actual dates should not be in the future.

- 842 activities (94%) have 10. Resources. Not all activities have cost/resources assigned.

- 1095 activities (87%) are 11. Missed Activities. 20% or more exceptions.

- This ribbon has a 12. Critical Path Test of ✓.

- This ribbon has a 13. CPLI of 0.59. Critical path length is less than 95% of the duration of the project. Review of the target completion dates is required.

- This ribbon has a 14. BEI of 0.53. Less than 95% of all activities are completed on or ahead of schedule. Project review required.