## Directional Path Export
Focus Task Name | Focus Task UID | Task Name | Unique ID | Start | Finish | Driving Slack | Drag | Trace Log Value | Project
Customer Service Program Development COMPLETE | 155 | Build technology infrastructure plan (separate project plan required) | 379 | 2026-10-13 08:00 | 2026-10-13 17:00 | 32 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Determine technology budget | 321 | 2026-10-14 08:00 | 2026-10-14 17:00 | 32 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Technology infrastructure planning COMPLETE | 381 | 2026-10-14 17:00 | 2026-10-14 17:00 | 32 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Design and develop technology solution (separate schedule required) | 396 | 2026-10-15 08:00 | 2026-10-15 17:00 | 32 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Test technology infrastructure | 398 | 2026-10-15 17:00 | 2026-10-16 17:00 | 32 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Deploy technology infrastructure | 408 | 2026-10-19 08:00 | 2026-10-19 17:00 | 32 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Create training delivery schedule | 261 | 2026-09-25 08:00 | 2026-09-25 17:00 | 34.1 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Determine training delivery locations | 281 | 2026-10-13 08:00 | 2026-10-13 17:00 | 23.1 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Review outsourcing options - event logistics | 289 | 2026-10-14 08:00 | 2026-10-14 17:00 | 23.1 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Develop training delivery budget | 267 | 2026-10-28 13:00 | 2026-10-30 11:12 | 13.6 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Review output of product review phase | 211 | 2026-08-19 17:00 | 2026-08-19 21:00 | 33.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Service Planning & Design COMPLETE | 323 | 2026-08-19 08:00 | 2026-08-19 08:00 | 29 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Estimate demand for customer support (all options) | 98 | 2026-08-19 08:00 | 2026-08-19 12:00 | 29 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Estimate resource requirements | 99 | 2026-08-19 13:00 | 2026-08-19 17:00 | 29 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Estimate effort to hire new resources | 131 | 2026-08-20 08:00 | 2026-08-20 12:00 | 29 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Resource Planning COMPLETE | 149 | 2026-08-20 12:00 | 2026-08-20 12:00 | 29 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Review anticipated skill sets of support resources | 210 | 2026-08-20 08:00 | 2026-08-25 17:00 | 29.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Determine product-specific training needs | 200 | 2026-08-25 17:00 | 2026-08-26 12:00 | 29.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Training Needs Assessment COMPLETE | 216 | 2026-08-26 12:00 | 2026-08-26 12:00 | 29.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Determine methods for delivering training | 241 | 2026-08-26 12:00 | 2026-08-27 04:00 | 29.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Determine form factor for training content | 249 | 2026-08-27 04:00 | 2026-08-27 12:00 | 29.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Identify internal resources that can review training materials | 251 | 2026-08-27 13:00 | 2026-08-28 12:00 | 29.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Determine training course topics | 254 | 2026-08-28 12:00 | 2026-08-28 20:00 | 29.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Determine number of training courses | 301 | 2026-08-28 20:00 | 2026-08-29 04:00 | 29.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Design student materials | 282 | 2026-08-29 04:00 | 2026-08-29 12:00 | 29.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Draft description of training program/courses | 255 | 2026-08-29 12:00 | 2026-08-29 20:00 | 29.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Draft content development budget | 303 | 2026-08-29 20:00 | 2026-08-30 04:00 | 29.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Content Development Planning COMPLETE | 300 | 2026-08-30 04:00 | 2026-08-30 04:00 | 29.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Identify internal resources that can serve as potential trainers | 199 | 2026-09-02 08:00 | 2026-09-02 17:00 | 27.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Determine whether additional trainers will be needed | 268 | 2026-09-03 08:00 | 2026-09-03 17:00 | 27.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Review expertise of potential vendors | 290 | 2026-09-04 08:00 | 2026-09-07 17:00 | 27.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Phone support | 179 | 2026-10-12 17:00 | 2026-10-13 08:00 | 0.864583333333333 day | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Online support | 180 | 2026-10-12 17:00 | 2026-10-13 08:00 | 0.864583333333333 day | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Read the note for an explanation of the purpose of the template | 412 | 2026-07-08 08:00 | 2026-07-08 08:00 | 60.625 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Identify typical product usage scenarios | 97 | 2026-07-08 08:00 | 2026-07-08 17:00 | 60.625 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Identify typical customer types | 96 | 2026-07-08 17:00 | 2026-07-09 08:00 | 60.625 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Identify anticipated product problem points | 95 | 2026-07-09 08:00 | 2026-07-28 17:00 | 60.625 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Determine solutions for product points | 94 | 2026-08-12 08:00 | 2026-08-12 17:00 | 36.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Document product review results | 157 | 2026-08-18 08:00 | 2026-08-19 17:00 | 33.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Product Review COMPLETE | 147 | 2026-08-19 17:00 | 2026-08-19 17:00 | 33.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | On-site support | 178 | 2026-10-12 17:00 | 2026-10-13 08:00 | 0.864583333333333 day | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Design of customer service contact scenarios COMPLETE | 181 | 2026-10-13 08:00 | 2026-10-13 08:00 | 0.864583333333333 day | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Identify types of problems to be solved | 189 | 2026-10-13 08:00 | 2026-10-13 17:00 | 0.864583333333333 day | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Identify service delivery options | 188 | 2026-10-13 17:00 | 2026-10-14 14:06 | 0.864583333333333 day | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Review cost | 291 | 2026-09-08 08:00 | 2026-09-08 17:00 | 27.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Review service levels | 295 | 2026-09-09 08:00 | 2026-09-09 17:00 | 27.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Review customer references | 296 | 2026-09-10 08:00 | 2026-09-10 17:00 | 27.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Determine time required to ready external trainers | 292 | 2026-09-11 08:00 | 2026-09-11 17:00 | 27.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Make outsourcing decision | 294 | 2026-09-14 08:00 | 2026-09-14 17:00 | 27.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Outsourcing Review COMPLETE | 297 | 2026-09-14 17:00 | 2026-09-14 17:00 | 27.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Trainer Needs Assessment COMPLETE | 298 | 2026-09-14 17:00 | 2026-09-14 17:00 | 27.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Training Delivery Logistics COMPLETE | 278 | 2026-10-13 08:00 | 2026-10-13 17:00 | 7.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Create training plan with outputs of Content Development & Training Delivery Phases | 302 | 2026-10-13 17:00 | 2026-10-21 12:00 | 7.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Training Delivery Planning Complete | 305 | 2026-10-21 12:00 | 2026-10-21 12:00 | 7.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Draft Overall Budget | 276 | 2026-10-21 13:00 | 2026-10-22 12:00 | 7.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Acquire executive sign-off on budget | 275 | 2026-10-22 13:00 | 2026-10-27 12:00 | 7.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Acquire executive sign-off on training plans | 307 | 2026-10-27 13:00 | 2026-10-28 12:00 | 7.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Training Planning COMPLETE | 256 | 2026-10-28 12:00 | 2026-10-28 12:00 | 7.5 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Determine required skill sets for various support options | 187 | 2026-08-05 08:00 | 2026-08-18 17:00 | 29 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Customer Service Level Design COMPLETE | 184 | 2026-08-18 17:00 | 2026-08-18 17:00 | 29 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Design of Support Services COMPLETE | 148 | 2026-08-18 17:00 | 2026-08-18 17:00 | 29 days | 0 | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Determine business objectives of support services | 384 | 2026-10-13 08:00 | 2026-10-13 17:00 | 0 days | 1 day | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Determine success metrics | 385 | 2026-10-13 17:00 | 2026-11-04 14:24 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Determine cost efficiency standards | 386 | 2026-11-04 14:24 | 2026-11-06 22:24 | 0 days | 1 day | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Business Performance Planning COMPLETE | 387 | 2026-11-06 22:24 | 2026-11-06 22:24 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Assemble content development team | 223 | 2026-11-09 08:00 | 2026-11-09 17:00 | 0 days | 1 day | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Define roles and responsibilities | 222 | 2026-11-10 08:00 | 2026-11-10 17:00 | 0 days | 1 day | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Create content development schedule | 253 | 2026-11-11 08:00 | 2026-11-11 17:00 | 0 days | 1 day | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Review existing intellectual property | 244 | 2026-11-11 17:00 | 2026-11-12 01:00 | 0 days | 1 day | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Develop beta content | 257 | 2026-11-12 01:00 | 2026-11-12 09:00 | 0 days | 1 day | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Perform SME review of training content | 228 | 2026-11-12 09:00 | 2026-11-12 17:00 | 0 days | 1 day | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Revise and update content | 258 | 2026-11-12 17:00 | 2026-11-13 01:00 | 0 days | 1 day | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Create "cheat sheets" and additional learning resources for customer support | 140 | 2026-11-13 01:00 | 2026-11-13 09:00 | 0 days | 1 day | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Acquire final content approval | 229 | 2026-11-13 09:00 | 2026-11-16 09:00 | 0 days | 1 day | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Content Development COMPLETE | 260 | 2026-11-16 09:00 | 2026-11-16 09:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Create additional "train the trainer" learning materials | 274 | 2026-11-16 09:00 | 2026-11-16 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Create proficiency exams | 264 | 2026-11-16 17:00 | 2026-11-18 01:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Train additional trainers | 262 | 2026-11-18 08:00 | 2026-11-18 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Prepare training venues | 269 | 2026-11-18 17:00 | 2026-11-19 01:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Create communications plan | 270 | 2026-11-19 08:00 | 2026-11-23 17:00 | 0 days | 2 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Provide new hires with information on training program | 272 | 2026-11-24 08:00 | 2026-11-24 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Send out communication to existing support resources regarding new training plan | 310 | 2026-11-25 08:00 | 2026-11-25 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Training Delivery Engine Development COMPLETE | 150 | 2026-11-25 17:00 | 2026-11-25 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Hire new resources | 49 | 2026-11-26 08:00 | 2026-11-26 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Train new resources | 34 | 2026-11-27 08:00 | 2026-11-27 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Certify new resources | 389 | 2026-11-30 08:00 | 2026-12-02 17:00 | 0 days | 2 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Deploy new customer service programs | 409 | 2026-12-03 08:00 | 2026-12-03 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Program Deployment COMPLETE | 410 | 2026-12-03 17:00 | 2026-12-03 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Determine success metrics | 13 | 2026-12-03 17:00 | 2026-12-04 08:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Create method for tracking common problems and solutions | 7 | 2026-12-04 08:00 | 2026-12-04 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Create method to track support issues vs. product aspects | 14 | 2026-12-04 17:00 | 2026-12-08 08:00 | 0 days | 1 day | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Create method for distributing common solutions to all support resources | 141 | 2026-12-08 08:00 | 2026-12-08 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Post Launch Preparation COMPLETE | 156 | 2026-12-08 17:00 | 2026-12-08 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Monitor customer support issues - look for common problems | 36 | 2026-12-08 17:00 | 2026-12-09 08:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Aggregate best practices (solutions) - distribute to support services | 9 | 2026-12-09 08:00 | 2026-12-09 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Review support data, determine which product aspects cause the most support incidents | 144 | 2026-12-09 17:00 | 2026-12-10 08:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Review resource performance, determine which ones are the most effective | 145 | 2026-12-10 08:00 | 2026-12-10 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Revise training materials based on data collected from customer service program | 146 | 2026-12-10 17:00 | 2026-12-12 17:00 | 0 days | 1 day | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Post Launch Activities COMPLETE | 411 | 2026-12-12 17:00 | 2026-12-12 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3
Customer Service Program Development COMPLETE | 155 | Customer Service Program Development COMPLETE | 155 | 2026-12-12 17:00 | 2026-12-12 17:00 | 0 days | 0 days | Path 01 | Hard_File_updated3