# Acumen Fuse® Diagnostic Executive Briefing

Report Generated On Wednesday, June 24, 2026

Created by dpolitte

## Workbook1 Summary

An Acumen Fuse analysis was conducted on Wednesday, June 24, 2026 on the Workbook1 workbook. It contains 1 project: Large Test File, modeled in Microsoft® Office Project*.

The earliest start date is Wednesday, June 7, 2017 with the latest completion date being Friday, September 29, 2028

### Ribbon Browser

| Ribbons \ Phases | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Large Test File |  |  |  |  |  |  |  |  |  |  |  |  |

### Trend Analysis

The following section details how the characteristics of the workbook vary over time. This provides useful insight by showing improving/worsening trends. The analysis was conducted using years as time intervals:

- Status Date : increases over time with the highest period being 2017 (2/7/2025) and the lowest period being 2017 (2/7/2025).

- WBS: increases over time with the highest period being 2017 (1) and the lowest period being 2017 (1).

- New Activity - Created (Snapshot): remains constant over time.

- New Activity - Already Finished (Snapshot) - check/compare: remains constant over time.

## Projects Summary

### Large Test File Project

The Large Test File project has a start date of Wednesday, June 7, 2017 and has Friday, September 29, 2028 as the completion date. The project is currently in progress with a status date of Friday, February 7, 2025. It has 1554 normal activities of which 609 (39.2%) are complete, 108 (6.9%) are in progress and 837 (53.9%) are still planned. It contains 169 milestones, 402 summaries and no LOEs.

The project baseline start date was Wednesday, June 7, 2017 with the baseline finish date being Friday, September 29, 2028. The project is currently on schedule.

The project has no baseline costs.

## Ribbon Analysis

A ribbon analysis shows how the results from the selected metrics vary across the selected groupings of activities. This is a useful means of comparing between such groupings. In addition, the scorecard value for each ribbon provides an overarching summary of each ribbon.

The workbook has been grouped by projects. The analysis contains 1 ribbon: "Large Test File".

### Ribbon Analyzer

| Ribbons \ Phases | Status Date | WBS | New Activity - Created (Snapshot) | New Activity - Already Finished (Snapshot) - check/compare | New Activity - Finished in Status Period (Snapshot) - check/compare | Specific Task Start | Specific Task Finish | Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Total New Tasks & Milestones in Status Period | Total New Completed Tasks & Milestones in Status Period | Riding Data Date | Remaining Days | Approx Rem Work Days | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Scorecard Value |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Large Test File | 2/7/2025 | 1 | 0 | 0 |  |  |  | 2/7/2025 | 2125 | 169 | 1554 | 402 | 0 | 0 | 1723 | 699 | 90 | 609 | 1309 | 1024 | 79 | 945 | 285 | 0 | 0 | 33 | 27 | 6 | 0 | 0 | 0 | 1,330 | 910 | 0 | 0 | 8 | 93 | 0 | 0 | 820 | 27 | 87 | 0 | 0 | 866 | 1115 | x | 0.99 | 0.52 | 33.4% |

The overall score for this ribbon is 33.4%.

### Large Test File Ribbon Analysis

The Large Test File ribbon contains 1554 normal activities, 169 milestones, 402 summaries and 0 LOEs spanning from Wednesday, June 7, 2017 to Friday, September 29, 2028.

38.4% of the activities in this ribbon are complete; 48.8% are planned and 12.8% are in progress.

The ribbon is 4132 days long.

The ribbon was analyzed using 49 metrics, as detailed below:

- 2/7/2025 activities have Status Date .

- 1 activity has WBS.

- 0 activities have New Activity - Created (Snapshot).

- 0 activities have New Activity - Already Finished (Snapshot) - check/compare.

- 2/7/2025 activities have Status Date.

- 2125 activities are Total Activities.

- 169 activities (8%) are Milestones.

- 1554 activities (73%) are Normal Tasks.

- 402 activities (19%) are Summaries.

- 0 activities (0%) are Hammocks.

- 0 activities (0%) are Recurring Normal Tasks.

- 1723 activities (81%) are Total Tasks & Milestones.

- 699 activities (41%) are Completed Tasks & Milestones. Some activities are complete.

- 90 activities (53%) are Completed Milestones. Some activities are complete.

- 609 activities (39%) are Completed Tasks. Some activities are complete.

- 1309 activities (62%) are Total Activities (To-Go) - % of Total.

- 1024 activities (78%) are Tasks & Milestones (To-Go) - % of Total To-Go.

- 79 activities (6%) are Milestones (To-Go).

- 945 activities (72%) are Normal Tasks (To-Go).

- 285 activities (22%) are Summaries (To-Go).

- 0 activities (0%) are Hammocks (To-Go).

- 0 activities (0%) are Recurring Tasks (To-Go).

- 33 activities (80%) are Longest Path (Tasks & Milestones).

- 27 activities (66%) are Longest Path (Normal Tasks).

- 6 activities (15%) are Longest Path (Milestones).

- 0 activities have Total New Tasks & Milestones in Status Period.

- 0 activities have Total New Completed Tasks & Milestones in Status Period.

- 0 activities (0%) have Riding Data Date.

- This ribbon has a Remaining Days  of 1,330.

- This ribbon has a Approx Rem Work Days  of 910.

- 0 activities (0%) are 1. Logic. No Exceptions. Verify that the program logic is accurate.

- 0 activities (0%) have 2. Leads. No Exceptions. This is the target state.

- 8 activities (0%) have 3. Lags. 5% or fewer exceptions. Some improvements may be required.

- This ribbon has 93 4. SS/FF Relations (6%). 10% or fewer links are FF or SS.

- This ribbon has 0 4. SF Relations (0%). No SF predecessors have been used.

- 0 activities (0%) have 5. Hard Constraint. No exceptions.

- 820 activities (88%) have 6. High Float. 20% or more exceptions - Improvements are required.

- 27 activities (3%) have 7. Negative Float. Fewer than 5% of items have negative float. Corrective action plan to eliminate negative float recommended.

- 87 activities (9%) have 8. High Duration. Less than 20% exceptions. Some improvements may be required.

- 0 activities (0%) have 9. Invalid Forecast Dates. No Exceptions. This is the target state.

- 0 activities (0%) have 9. Invalid Actual Dates. No Exceptions. This is the target state.

- 866 activities (94%) have 10. Resources. Not all activities have cost/resources assigned.

- 1115 activities (91%) are 11. Missed Activities. 20% or more exceptions.

- This ribbon has a 12. Critical Path Test of x.

- This ribbon has a 13. CPLI of 0.99. Critical path length is greater than 95% of the duration of the project. This is the target state.

- This ribbon has a 14. BEI of 0.52. Less than 95% of all activities are completed on or ahead of schedule. Project review required.