## Projects
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects
Name | Start | Start | Finish | Finish | Time Now | Time Now | Baseline Start | Baseline Start | Baseline Finish | Baseline Finish | Activities | Activities | Budget Duration | Budget Duration | Actual Duration | Actual Duration | Remaining Duration | Remaining Duration | Total Duration | Total Duration | Budget Cost | Budget Cost | Actual Cost | Actual Cost | Remaining Cost | Remaining Cost | Total Cost | Total Cost
Hard_File |  | 2026-07-08 08:00 |  | 2026-11-05 12:00 |  | 2026-07-07 17:00 |  | 2026-07-08 08:00 |  | 2026-11-05 12:00 |  | 141 |  | 120.1667 |  | 0 |  | 86 |  | 86 |  | 133400 |  | 0 |  | 133400 |  | 133400
Hard_File_updated | = | 2026-07-08 08:00 | = | 2026-11-05 12:00 | p | 2026-08-11 17:00 | = | 2026-07-08 08:00 | = | 2026-11-05 12:00 | = | 141 | = | 120.1667 | p | 25 | q | 62 | = | 86 | = | 133400 | p | 20800 | q | 116600 | p | 137400

## Activities
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated

## Relationships
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Relationships - 3 (3%) | Relationships - 3 (3%) | Relationships - 3 (3%) | Relationships - 3 (3%) | Relationships - 3 (3%) | Relationships - 3 (3%) | Relationships - 3 (3%) | Relationships - 3 (3%)
Predecessor ID | Predecessor | Predecessor Critical | Successor ID | Successor | Successor Critical | Hard_File | Hard_File_updated
188 | Identify service delivery options | False | 187 | Determine required skill sets for various support options | False | FinishToStart (0) | O
387 | Business Performance Planning COMPLETE | False | 400 | Build customer service programs | False | FinishToStart (0) | O
188 | Identify service delivery options | False | 291 | Review cost | False | O | FinishToStart (0)

## Leads-Lags
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%)
Predecessor ID | Predecessor | Predecessor Critical | Successor ID | Successor | Successor Critical | Hard_File Relationship Type | Hard_File_updated Relationship Type | Hard_File Lead/Lag | Hard_File_updated Lead/Lag
188 | Identify service delivery options | False | 187 | Determine required skill sets for various support options | False | FinishToStart | O | 0 | O
387 | Business Performance Planning COMPLETE | False | 400 | Build customer service programs | False | FinishToStart | O | 0 | O
188 | Identify service delivery options | False | 291 | Review cost | False | O | FinishToStart | O | 0

## Resources
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Resources - 7 (8%) | Resources - 7 (8%) | Resources - 7 (8%) | Resources - 7 (8%) | Resources - 7 (8%) | Resources - 7 (8%) | Resources - 7 (8%) | Resources - 7 (8%) | Resources - 7 (8%) | Resources - 7 (8%) | Resources - 7 (8%) | Resources - 7 (8%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Resource | Hard_File | Hard_File_updated | Hard_File_updated
1 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | Customer Service Team | 160 | q | 0
2 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | Customer Service Team | 8 | q | 0
3 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | Customer Service Team | 8 | q | 0
4 | 187 | Determine required skill sets for various support options | Normal | 15 | 3.1.2.3 | 3.1.2.3 |  | Customer Service Team | 120 | q | 48
5 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | Customer Service Team | 40 | q | 0
6 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | Customer Service Team | 8 | q | 0
7 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | Customer Service Team | 40 | q | 0

## Calendars
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars
Hard_File | Hard_File | Hard_File | Hard_File | Hard_File | Hard_File | Hard_File | Hard_File |  |  | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Used for Microsoft Project 98 Baseline Calendar
Hard_File | Hard_File | Hard_File | Hard_File | Hard_File | Hard_File | Hard_File | Hard_File |  |  | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: 24 Hours
Hard_File | Hard_File | Hard_File | Hard_File | Hard_File | Hard_File | Hard_File | Hard_File |  |  | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: 16 Hour Work Days
Hard_File | Hard_File | Hard_File | Hard_File | Hard_File | Hard_File | Hard_File | Hard_File |  |  | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Standard+Sat.
Hard_File | Hard_File | Hard_File | Hard_File | Hard_File | Hard_File | Hard_File | Hard_File |  |  | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00

## Calendar Exceptions
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Calendar: Standard
Hard_File | Hard_File_updated
Calendar: Used for Microsoft Project 98 Baseline Calendar
Hard_File | Hard_File_updated
Calendar: 24 Hours
Hard_File | Hard_File_updated
Calendar: 16 Hour Work Days
Hard_File | Hard_File_updated
2011-05-30 | 2011-05-30
2012-05-28 | 2012-05-28
2013-05-27 | 2013-05-27
2014-05-26 | 2014-05-26
2015-05-25 | 2015-05-25
2016-05-30 | 2016-05-30
2017-05-29 | 2017-05-29
2018-05-28 | 2018-05-28
2019-05-27 | 2019-05-27
2011-07-04 | 2011-07-04
2012-07-04 | 2012-07-04
2013-07-04 | 2013-07-04
2014-07-04 | 2014-07-04
2015-07-04 | 2015-07-04
2016-07-04 | 2016-07-04
2017-07-04 | 2017-07-04
2018-07-04 | 2018-07-04
2019-07-04 | 2019-07-04
2011-09-05 | 2011-09-05
2012-09-03 | 2012-09-03
2013-09-02 | 2013-09-02
2014-09-01 | 2014-09-01
2015-09-07 | 2015-09-07
2016-09-05 | 2016-09-05
2017-09-04 | 2017-09-04
2018-09-03 | 2018-09-03
2019-09-02 | 2019-09-02
2011-11-24 | 2011-11-24
2012-11-22 | 2012-11-22
2013-11-21 | 2013-11-21
2014-11-27 | 2014-11-27
2015-11-26 | 2015-11-26
2016-11-24 | 2016-11-24
2017-11-23 | 2017-11-23
2018-11-22 | 2018-11-22
2011-12-25 | 2011-12-25
2012-12-25 | 2012-12-25
2013-12-25 | 2013-12-25
2014-12-25 | 2014-12-25
2015-12-25 | 2015-12-25
2016-12-25 | 2016-12-25
2017-12-25 | 2017-12-25
2018-12-25 | 2018-12-25
2019-12-25 | 2019-12-25
2020-12-25 | 2020-12-25
2021-12-25 | 2021-12-25
2022-12-25 | 2022-12-25
2023-12-25 | 2023-12-25
2024-12-25 | 2024-12-25
2025-12-25 | 2025-12-25
2015-11-27 | 2015-11-27
2016-11-25 | 2016-11-25
2017-11-24 | 2017-11-24
2018-11-23 | 2018-11-23
2019-11-22 | 2019-11-22
2017-01-01 | 2017-01-01
2018-01-01 | 2018-01-01
2018-03-30 | 2018-03-30
2018-08-26 | 2018-08-26
2018-12-24 | 2018-12-24
2018-12-31 | 2018-12-31
2019-01-01 | 2019-01-01
2019-11-29 | 2019-11-29
2019-12-24 | 2019-12-24
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-05-25 | 2020-05-25
2020-07-06 | 2020-07-06
2020-09-07 | 2020-09-07
2020-11-26 | 2020-11-26
2021-01-18 | 2021-01-18
2021-05-31 | 2021-05-31
2021-07-05 | 2021-07-05
2021-09-06 | 2021-09-06
2021-11-25 | 2021-11-25
2021-12-24 | 2021-12-24
2021-12-31 | 2021-12-31
2022-01-17 | 2022-01-17
2022-05-30 | 2022-05-30
2022-07-04 | 2022-07-04
2022-09-05 | 2022-09-05
2022-11-24 | 2022-11-24
2022-12-26 | 2022-12-26
2023-01-02 | 2023-01-02
2023-01-16 | 2023-01-16
2023-05-29 | 2023-05-29
2023-07-04 | 2023-07-04
2023-09-04 | 2023-09-04
2023-11-23 | 2023-11-23
2024-01-01 | 2024-01-01
2024-01-15 | 2024-01-15
2024-05-27 | 2024-05-27
2024-07-04 | 2024-07-04
2024-09-02 | 2024-09-02
2024-11-28 | 2024-11-28
2025-01-01 | 2025-01-01
2025-01-20 | 2025-01-20
Calendar: Standard+Sat.
Hard_File | Hard_File_updated

## ID
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated

## Description
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated

## Activity-Type
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated

## Baseline-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated

## Original-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Original Duration - 14 (10%) | Original Duration - 14 (10%) | Original Duration - 14 (10%) | Original Duration - 14 (10%) | Original Duration - 14 (10%) | Original Duration - 14 (10%) | Original Duration - 14 (10%) | Original Duration - 14 (10%) | Original Duration - 14 (10%) | Original Duration - 14 (10%) | Original Duration - 14 (10%) | Original Duration - 14 (10%) | Original Duration - 14 (10%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | 18 | p | 11 | -61% | 29
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | 18 | p | 11 | -61% | 29
3 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 20 | p | 7 | -35% | 27
4 | 315 | Service Delivery Infrastructure Planning | Summary | 42 | 4 | 4 |  | 42 | q | -11 | (-26%) | 31
5 | 129 | Training & Readiness | Summary | 42 | 4.2 | 4.2 |  | 42 | q | -11 | (-26%) | 31
6 | 212 | Training Needs Assessment | Summary | 14 | 4.2.1 | 4.2.1 |  | 14 | q | -10 | (-71%) | 4
7 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | 11 | p | 1 | -9% | 12
8 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | 10 | p | 2 | -20% | 12
9 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | 9 | p | 3 | -33% | 12
10 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 1 | p | 1 | -100% | 2
11 | 373 | Build Customer Service Program | Summary | 42 | 6 | 6 |  | 42 | p | 15 | -36% | 57
12 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | 37 | p | 12 | -32% | 49
13 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 5 | p | 3 | -60% | 8
14 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 2 | p | 3 | -150% | 5

## Actual-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Actual Duration - 14 (10%) | Actual Duration - 14 (10%) | Actual Duration - 14 (10%) | Actual Duration - 14 (10%) | Actual Duration - 14 (10%) | Actual Duration - 14 (10%) | Actual Duration - 14 (10%) | Actual Duration - 14 (10%) | Actual Duration - 14 (10%) | Actual Duration - 14 (10%) | Actual Duration - 14 (10%) | Actual Duration - 14 (10%) | Actual Duration - 14 (10%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | 0 | p | 27 |  | 27
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | 0 | p | 27 |  | 27
3 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 0 | p | 27 |  | 27
4 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | 0 | p | 1 |  | 1
5 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | 0 | p | 1 |  | 1
6 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | 0 | p | 5 |  | 5
7 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | 0 | p | 5 |  | 5
8 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | 0 | p | 6 |  | 6
9 | 187 | Determine required skill sets for various support options | Normal | 15 | 3.1.2.3 | 3.1.2.3 |  | 0 | p | 9 |  | 9
10 | 373 | Build Customer Service Program | Summary | 42 | 6 | 6 |  | 0 | p | 18 |  | 18
11 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | 0 | p | 36 |  | 36
12 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | 0 | p | 5 |  | 5
13 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | 0 | p | 1 |  | 1
14 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 0 | p | 8 |  | 8

## Remaining-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Remaining Duration - 19 (13%) | Remaining Duration - 19 (13%) | Remaining Duration - 19 (13%) | Remaining Duration - 19 (13%) | Remaining Duration - 19 (13%) | Remaining Duration - 19 (13%) | Remaining Duration - 19 (13%) | Remaining Duration - 19 (13%) | Remaining Duration - 19 (13%) | Remaining Duration - 19 (13%) | Remaining Duration - 19 (13%) | Remaining Duration - 19 (13%) | Remaining Duration - 19 (13%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | 18 | q | -16 | (-89%) | 2
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | 18 | q | -16 | (-89%) | 2
3 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 20 | q | -20 | (-100%) | 0
4 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | 1 | q | -1 | (-100%) | 0
5 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | 1 | q | -1 | (-100%) | 0
6 | 315 | Service Delivery Infrastructure Planning | Summary | 42 | 4 | 4 |  | 42 | q | -11 | (-26%) | 31
7 | 129 | Training & Readiness | Summary | 42 | 4.2 | 4.2 |  | 42 | q | -11 | (-26%) | 31
8 | 212 | Training Needs Assessment | Summary | 14 | 4.2.1 | 4.2.1 |  | 14 | q | -10 | (-71%) | 4
9 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | 11 | q | -4 | (-36%) | 7
10 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | 10 | q | -3 | (-30%) | 7
11 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | 9 | q | -3 | (-33%) | 6
12 | 187 | Determine required skill sets for various support options | Normal | 15 | 3.1.2.3 | 3.1.2.3 |  | 15 | q | -9 | (-60%) | 6
13 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 1 | p | 1 | -100% | 2
14 | 373 | Build Customer Service Program | Summary | 42 | 6 | 6 |  | 42 | q | -3 | (-7%) | 39
15 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | 37 | q | -24 | (-65%) | 13
16 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | 5 | q | -5 | (-100%) | 0
17 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | 1 | q | -1 | (-100%) | 0
18 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 5 | q | -5 | (-100%) | 0
19 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 2 | p | 3 | -150% | 5

## Total-Float
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Total Float - 33 (23%) | Total Float - 33 (23%) | Total Float - 33 (23%) | Total Float - 33 (23%) | Total Float - 33 (23%) | Total Float - 33 (23%) | Total Float - 33 (23%) | Total Float - 33 (23%) | Total Float - 33 (23%) | Total Float - 33 (23%) | Total Float - 33 (23%) | Total Float - 33 (23%) | Total Float - 33 (23%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | 0 | p | 3 |  | 3
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | 0 | p | 3 |  | 3
3 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 7 | q | -5 | (-71%) | 2
4 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 6 | q | -6 | (-100%) | 0
5 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | 6 | q | -6 | (-100%) | 0
6 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | 6 | q | -6 | (-100%) | 0
7 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 0 | p | 3 |  | 3
8 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 6 | q | -3 | (-50%) | 3
9 | 315 | Service Delivery Infrastructure Planning | Summary | 42 | 4 | 4 |  | 12 | q | -12 | (-100%) | 0
10 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 14 | q | -11 | (-79%) | 3
11 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | 0 | p | 11 |  | 11
12 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | 0 | p | 11 |  | 11
13 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | 0 | p | 11 |  | 11
14 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | p | 11 |  | 11
15 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | p | 11 |  | 11
16 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 1 | p | 10 | -1000% | 11
17 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | p | 11 |  | 11
18 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 1 | p | 11 | -1100% | 12
19 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 2 | p | 11 | -550% | 13
20 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 1 | p | 10 | -1000% | 11
21 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | 20 | p | 2 | -10% | 22
22 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | 20 | q | -20 | (-100%) | 0
23 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | 20 | q | -20 | (-100%) | 0
24 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 20 | q | -20 | (-100%) | 0
25 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 20 | p | 2 | -10% | 22
26 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 20 | p | 2 | -10% | 22
27 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 20 | p | 2 | -10% | 22
28 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 20 | p | 33 | -165% | 53
29 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 20 | p | 33 | -165% | 53
30 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 20 | p | 33 | -165% | 53
31 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 20 | p | 34 | -170% | 54
32 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 20 | p | 34 | -170% | 54
33 | 412 | Read the note for an explanation of the purpose of the template | Milestone | 0 | 1 | 1 |  | 6 | q | -6 | (-100%) | 0

## Free-Float
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Free Float - 16 (11%) | Free Float - 16 (11%) | Free Float - 16 (11%) | Free Float - 16 (11%) | Free Float - 16 (11%) | Free Float - 16 (11%) | Free Float - 16 (11%) | Free Float - 16 (11%) | Free Float - 16 (11%) | Free Float - 16 (11%) | Free Float - 16 (11%) | Free Float - 16 (11%) | Free Float - 16 (11%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | 0 | p | 3 |  | 3
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | 0 | p | 3 |  | 3
3 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 6 | q | -6 | (-100%) | 0
4 | 315 | Service Delivery Infrastructure Planning | Summary | 42 | 4 | 4 |  | 12 | q | -12 | (-100%) | 0
5 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 14 | q | -11 | (-79%) | 3
6 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | 0 | p | 11 |  | 11
7 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | 0 | p | 11 |  | 11
8 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | 0 | p | 11 |  | 11
9 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | p | 11 |  | 11
10 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 1 | p | 10 | -1000% | 11
11 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | p | 1 |  | 1
12 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 1 | p | 1 | -100% | 2
13 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | 20 | p | 2 | -10% | 22
14 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 20 | p | 2 | -10% | 22
15 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 20 | p | 33 | -165% | 53
16 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | p | 54 |  | 54

## Calendar
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated

## Start
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Start - 30 (21%) | Start - 30 (21%) | Start - 30 (21%) | Start - 30 (21%) | Start - 30 (21%) | Start - 30 (21%) | Start - 30 (21%) | Start - 30 (21%) | Start - 30 (21%) | Start - 30 (21%) | Start - 30 (21%) | Start - 30 (21%) | Start - 30 (21%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 2026-07-23 08:00 | p | 20 |  | 2026-08-12 08:00
2 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
3 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 2026-07-23 17:00 | p | 24 |  | 2026-08-17 08:00
4 | 315 | Service Delivery Infrastructure Planning | Summary | 42 | 4 | 4 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
5 | 129 | Training & Readiness | Summary | 42 | 4.2 | 4.2 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
6 | 212 | Training Needs Assessment | Summary | 14 | 4.2.1 | 4.2.1 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
7 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
8 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | 2026-07-31 17:00 | p | 4 |  | 2026-08-05 08:00
9 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | 2026-07-31 17:00 | p | 4 |  | 2026-08-05 08:00
10 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | 2026-08-04 08:00 | p | 1 |  | 2026-08-05 08:00
11 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 2026-08-14 17:00 | p | 2 |  | 2026-08-17 08:00
12 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 2026-08-04 17:00 | p | 15 |  | 2026-08-20 08:00
13 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 2026-08-04 08:00 | p | 15 |  | 2026-08-19 17:00
14 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
15 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 2026-08-03 17:00 | p | 15 |  | 2026-08-19 08:00
16 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 2026-08-03 08:00 | p | 15 |  | 2026-08-18 17:00
17 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
18 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 2026-08-04 08:00 | p | 15 |  | 2026-08-19 17:00
19 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 2026-08-14 17:00 | p | 2 |  | 2026-08-17 08:00
20 | 373 | Build Customer Service Program | Summary | 42 | 6 | 6 |  | 2026-08-18 17:00 | q | -21 |  | 2026-07-28 17:00
21 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | 2026-08-18 17:00 | q | -21 |  | 2026-07-28 17:00
22 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | 2026-08-19 08:00 | q | -21 |  | 2026-07-29 08:00
23 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | 2026-08-18 17:00 | q | -21 |  | 2026-07-28 17:00
24 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 2026-08-21 17:00 | q | -21 |  | 2026-07-31 08:00
25 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 2026-08-27 08:00 | q | -6 |  | 2026-08-20 17:00
26 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 2026-09-22 15:00 | q | -32 |  | 2026-08-21 13:00
27 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 2026-10-08 15:00 | q | -2 |  | 2026-10-06 10:00
28 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 2026-08-17 17:00 | p | 0 |  | 2026-08-18 08:00
29 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 2026-08-18 08:00 | p | 3 |  | 2026-08-21 08:00
30 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 2026-08-18 17:00 | p | 3 |  | 2026-08-21 17:00

## Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Finish - 31 (22%) | Finish - 31 (22%) | Finish - 31 (22%) | Finish - 31 (22%) | Finish - 31 (22%) | Finish - 31 (22%) | Finish - 31 (22%) | Finish - 31 (22%) | Finish - 31 (22%) | Finish - 31 (22%) | Finish - 31 (22%) | Finish - 31 (22%) | Finish - 31 (22%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
3 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 2026-07-23 17:00 | p | 20 |  | 2026-08-12 17:00
4 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 2026-07-23 08:00 | p | 5 |  | 2026-07-28 17:00
5 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
6 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 2026-07-24 08:00 | p | 24 |  | 2026-08-17 17:00
7 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 2026-08-01 01:00 | p | 17 |  | 2026-08-18 01:00
8 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | 2026-08-17 17:00 | p | 3 |  | 2026-08-20 17:00
9 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | 2026-08-14 17:00 | p | 6 |  | 2026-08-20 17:00
10 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | 2026-08-14 17:00 | p | 6 |  | 2026-08-20 17:00
11 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 2026-08-14 17:00 | p | 2 |  | 2026-08-17 08:00
12 | 187 | Determine required skill sets for various support options | Normal | 15 | 3.1.2.3 | 3.1.2.3 |  | 2026-08-14 17:00 | p | 2 |  | 2026-08-17 08:00
13 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 2026-08-05 08:00 | p | 15 |  | 2026-08-20 17:00
14 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 2026-08-04 17:00 | p | 15 |  | 2026-08-20 08:00
15 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 2026-08-04 08:00 | p | 15 |  | 2026-08-19 17:00
16 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 2026-08-04 08:00 | p | 15 |  | 2026-08-19 17:00
17 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 2026-08-03 17:00 | p | 15 |  | 2026-08-19 08:00
18 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 2026-08-03 08:00 | p | 15 |  | 2026-08-18 08:00
19 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 2026-08-04 08:00 | p | 15 |  | 2026-08-19 17:00
20 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 2026-08-14 17:00 | p | 2 |  | 2026-08-17 08:00
21 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | 2026-10-08 15:00 | q | -2 |  | 2026-10-06 10:00
22 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | 2026-08-21 17:00 | q | -21 |  | 2026-07-31 17:00
23 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | 2026-08-19 08:00 | q | -21 |  | 2026-07-29 08:00
24 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 2026-08-27 08:00 | q | -20 |  | 2026-08-06 17:00
25 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 2026-08-27 17:00 | q | -6 |  | 2026-08-21 08:00
26 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 2026-10-08 15:00 | q | -2 |  | 2026-10-06 10:00
27 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 2026-10-08 15:00 | q | -2 |  | 2026-10-06 10:00
28 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 2026-08-18 17:00 | p | 3 |  | 2026-08-21 17:00
29 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 2026-08-18 08:00 | p | 0 |  | 2026-08-18 17:00
30 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 2026-08-18 17:00 | p | 3 |  | 2026-08-21 17:00
31 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 2026-08-18 17:00 | p | 3 |  | 2026-08-21 17:00

## Actual-Start
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Actual Start - 15 (11%) | Actual Start - 15 (11%) | Actual Start - 15 (11%) | Actual Start - 15 (11%) | Actual Start - 15 (11%) | Actual Start - 15 (11%) | Actual Start - 15 (11%) | Actual Start - 15 (11%) | Actual Start - 15 (11%) | Actual Start - 15 (11%) | Actual Start - 15 (11%) | Actual Start - 15 (11%) | Actual Start - 15 (11%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | O | p |  |  | 2026-07-08 08:00
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | O | p |  |  | 2026-07-08 08:00
3 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | O | p |  |  | 2026-07-09 08:00
4 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | O | p |  |  | 2026-07-08 17:00
5 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | O | p |  |  | 2026-07-08 08:00
6 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | O | p |  |  | 2026-08-05 08:00
7 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | O | p |  |  | 2026-08-05 08:00
8 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | O | p |  |  | 2026-08-05 08:00
9 | 187 | Determine required skill sets for various support options | Normal | 15 | 3.1.2.3 | 3.1.2.3 |  | O | p |  |  | 2026-08-05 08:00
10 | 373 | Build Customer Service Program | Summary | 42 | 6 | 6 |  | O | p |  |  | 2026-07-28 17:00
11 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | O | p |  |  | 2026-07-28 17:00
12 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | O | p |  |  | 2026-07-29 08:00
13 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | O | p |  |  | 2026-07-28 17:00
14 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | O | p |  |  | 2026-07-31 08:00
15 | 412 | Read the note for an explanation of the purpose of the template | Milestone | 0 | 1 | 1 |  | O | p |  |  | 2026-07-08 08:00

## Actual-Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Actual Finish - 7 (5%) | Actual Finish - 7 (5%) | Actual Finish - 7 (5%) | Actual Finish - 7 (5%) | Actual Finish - 7 (5%) | Actual Finish - 7 (5%) | Actual Finish - 7 (5%) | Actual Finish - 7 (5%) | Actual Finish - 7 (5%) | Actual Finish - 7 (5%) | Actual Finish - 7 (5%) | Actual Finish - 7 (5%) | Actual Finish - 7 (5%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | O | p |  |  | 2026-07-28 17:00
2 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | O | p |  |  | 2026-07-09 08:00
3 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | O | p |  |  | 2026-07-08 17:00
4 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | O | p |  |  | 2026-07-31 17:00
5 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | O | p |  |  | 2026-07-29 08:00
6 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | O | p |  |  | 2026-08-06 17:00
7 | 412 | Read the note for an explanation of the purpose of the template | Milestone | 0 | 1 | 1 |  | O | p |  |  | 2026-07-08 08:00

## Baseline-Start
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated

## Baseline-Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated

## Early-Start
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Early Start - 30 (21%) | Early Start - 30 (21%) | Early Start - 30 (21%) | Early Start - 30 (21%) | Early Start - 30 (21%) | Early Start - 30 (21%) | Early Start - 30 (21%) | Early Start - 30 (21%) | Early Start - 30 (21%) | Early Start - 30 (21%) | Early Start - 30 (21%) | Early Start - 30 (21%) | Early Start - 30 (21%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 2026-07-23 08:00 | p | 20 |  | 2026-08-12 08:00
2 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
3 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 2026-07-23 17:00 | p | 24 |  | 2026-08-17 08:00
4 | 315 | Service Delivery Infrastructure Planning | Summary | 42 | 4 | 4 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
5 | 129 | Training & Readiness | Summary | 42 | 4.2 | 4.2 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
6 | 212 | Training Needs Assessment | Summary | 14 | 4.2.1 | 4.2.1 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
7 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
8 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | 2026-07-31 17:00 | p | 4 |  | 2026-08-05 08:00
9 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | 2026-07-31 17:00 | p | 4 |  | 2026-08-05 08:00
10 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | 2026-08-04 08:00 | p | 1 |  | 2026-08-05 08:00
11 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 2026-08-14 17:00 | p | 2 |  | 2026-08-17 08:00
12 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 2026-08-04 17:00 | p | 15 |  | 2026-08-20 08:00
13 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 2026-08-04 08:00 | p | 15 |  | 2026-08-19 17:00
14 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
15 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 2026-08-03 17:00 | p | 15 |  | 2026-08-19 08:00
16 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 2026-08-03 08:00 | p | 15 |  | 2026-08-18 17:00
17 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
18 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 2026-08-04 08:00 | p | 15 |  | 2026-08-19 17:00
19 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 2026-08-14 17:00 | p | 2 |  | 2026-08-17 08:00
20 | 373 | Build Customer Service Program | Summary | 42 | 6 | 6 |  | 2026-08-18 17:00 | q | -21 |  | 2026-07-28 17:00
21 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | 2026-08-18 17:00 | q | -21 |  | 2026-07-28 17:00
22 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | 2026-08-19 08:00 | q | -21 |  | 2026-07-29 08:00
23 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | 2026-08-18 17:00 | q | -21 |  | 2026-07-28 17:00
24 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 2026-08-21 17:00 | q | -21 |  | 2026-07-31 08:00
25 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 2026-08-27 08:00 | q | -6 |  | 2026-08-20 17:00
26 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 2026-09-22 15:00 | q | -32 |  | 2026-08-21 13:00
27 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 2026-10-08 15:00 | q | -2 |  | 2026-10-06 10:00
28 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 2026-08-17 17:00 | p | 0 |  | 2026-08-18 08:00
29 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 2026-08-18 08:00 | p | 3 |  | 2026-08-21 08:00
30 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 2026-08-18 17:00 | p | 3 |  | 2026-08-21 17:00

## Early-Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Early Finish - 31 (22%) | Early Finish - 31 (22%) | Early Finish - 31 (22%) | Early Finish - 31 (22%) | Early Finish - 31 (22%) | Early Finish - 31 (22%) | Early Finish - 31 (22%) | Early Finish - 31 (22%) | Early Finish - 31 (22%) | Early Finish - 31 (22%) | Early Finish - 31 (22%) | Early Finish - 31 (22%) | Early Finish - 31 (22%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
3 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 2026-07-23 17:00 | p | 20 |  | 2026-08-12 17:00
4 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 2026-07-23 08:00 | p | 5 |  | 2026-07-28 17:00
5 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 2026-07-31 17:00 | p | 17 |  | 2026-08-17 17:00
6 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 2026-07-24 08:00 | p | 24 |  | 2026-08-17 17:00
7 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 2026-08-01 01:00 | p | 17 |  | 2026-08-18 01:00
8 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | 2026-08-17 17:00 | p | 3 |  | 2026-08-20 17:00
9 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | 2026-08-14 17:00 | p | 6 |  | 2026-08-20 17:00
10 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | 2026-08-14 17:00 | p | 6 |  | 2026-08-20 17:00
11 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 2026-08-14 17:00 | p | 2 |  | 2026-08-17 08:00
12 | 187 | Determine required skill sets for various support options | Normal | 15 | 3.1.2.3 | 3.1.2.3 |  | 2026-08-14 17:00 | p | 2 |  | 2026-08-17 08:00
13 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 2026-08-05 08:00 | p | 15 |  | 2026-08-20 17:00
14 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 2026-08-04 17:00 | p | 15 |  | 2026-08-20 08:00
15 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 2026-08-04 08:00 | p | 15 |  | 2026-08-19 17:00
16 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 2026-08-04 08:00 | p | 15 |  | 2026-08-19 17:00
17 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 2026-08-03 17:00 | p | 15 |  | 2026-08-19 08:00
18 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 2026-08-03 08:00 | p | 15 |  | 2026-08-18 08:00
19 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 2026-08-04 08:00 | p | 15 |  | 2026-08-19 17:00
20 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 2026-08-14 17:00 | p | 2 |  | 2026-08-17 08:00
21 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | 2026-10-08 15:00 | q | -2 |  | 2026-10-06 10:00
22 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | 2026-08-21 17:00 | q | -21 |  | 2026-07-31 17:00
23 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | 2026-08-19 08:00 | q | -21 |  | 2026-07-29 08:00
24 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 2026-08-27 08:00 | q | -20 |  | 2026-08-06 17:00
25 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 2026-08-27 17:00 | q | -6 |  | 2026-08-21 08:00
26 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 2026-10-08 15:00 | q | -2 |  | 2026-10-06 10:00
27 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 2026-10-08 15:00 | q | -2 |  | 2026-10-06 10:00
28 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 2026-08-18 17:00 | p | 3 |  | 2026-08-21 17:00
29 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 2026-08-18 08:00 | p | 0 |  | 2026-08-18 17:00
30 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 2026-08-18 17:00 | p | 3 |  | 2026-08-21 17:00
31 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 2026-08-18 17:00 | p | 3 |  | 2026-08-21 17:00

## Late-Start
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Late Start - 32 (23%) | Late Start - 32 (23%) | Late Start - 32 (23%) | Late Start - 32 (23%) | Late Start - 32 (23%) | Late Start - 32 (23%) | Late Start - 32 (23%) | Late Start - 32 (23%) | Late Start - 32 (23%) | Late Start - 32 (23%) | Late Start - 32 (23%) | Late Start - 32 (23%) | Late Start - 32 (23%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | 2026-07-15 22:00 | q | -7 |  | 2026-07-08 08:00
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | 2026-07-15 22:00 | q | -7 |  | 2026-07-08 08:00
3 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 2026-07-30 22:00 | p | 14 |  | 2026-08-14 14:30
4 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 2026-07-16 22:00 | q | -7 |  | 2026-07-09 08:00
5 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | 2026-07-16 14:00 | q | -7 |  | 2026-07-08 17:00
6 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | 2026-07-15 22:00 | q | -7 |  | 2026-07-08 08:00
7 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 2026-08-01 13:00 | p | 19 |  | 2026-08-21 05:00
8 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 2026-07-31 15:00 | p | 20 |  | 2026-08-20 15:00
9 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | 2026-08-04 13:00 | p | 0 |  | 2026-08-05 08:00
10 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | 2026-08-04 13:00 | p | 0 |  | 2026-08-05 08:00
11 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | 2026-08-04 21:00 | p | 0 |  | 2026-08-05 08:00
12 | 187 | Determine required skill sets for various support options | Normal | 15 | 3.1.2.3 | 3.1.2.3 |  | 2026-08-05 21:00 | q | 0 |  | 2026-08-05 08:00
13 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 2026-08-05 13:00 | p | 30 |  | 2026-09-04 19:00
14 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 2026-08-04 21:00 | p | 30 |  | 2026-09-04 10:00
15 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 2026-08-04 13:00 | p | 30 |  | 2026-09-03 19:00
16 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 2026-08-04 13:00 | p | 30 |  | 2026-09-03 19:00
17 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 2026-08-04 13:00 | p | 30 |  | 2026-09-03 19:00
18 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 2026-08-04 13:00 | p | 30 |  | 2026-09-03 19:00
19 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 2026-08-04 21:00 | p | 30 |  | 2026-09-04 10:00
20 | 373 | Build Customer Service Program | Summary | 42 | 6 | 6 |  | 2026-09-16 06:00 | q | -49 |  | 2026-07-28 17:00
21 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | 2026-09-16 06:00 | q | -49 |  | 2026-07-28 17:00
22 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | 2026-09-16 15:00 | q | -49 |  | 2026-07-29 08:00
23 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | 2026-09-16 06:00 | q | -49 |  | 2026-07-28 17:00
24 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 2026-09-21 06:00 | q | -51 |  | 2026-07-31 08:00
25 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 2026-09-24 15:00 | q | -2 |  | 2026-09-21 19:00
26 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 2026-10-20 13:00 | q | -27 |  | 2026-09-22 15:00
27 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 2026-09-14 08:00 | p | 45 |  | 2026-10-29 08:00
28 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 2026-09-14 08:00 | p | 45 |  | 2026-10-29 08:00
29 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 2026-09-15 06:00 | p | 45 |  | 2026-10-30 15:00
30 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 2026-09-15 15:00 | p | 50 |  | 2026-11-04 21:00
31 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 2026-09-16 06:00 | p | 50 |  | 2026-11-05 12:00
32 | 412 | Read the note for an explanation of the purpose of the template | Milestone | 0 | 1 | 1 |  | 2026-07-15 22:00 | q | -7 |  | 2026-07-08 08:00

## Late-Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Late Finish - 28 (20%) | Late Finish - 28 (20%) | Late Finish - 28 (20%) | Late Finish - 28 (20%) | Late Finish - 28 (20%) | Late Finish - 28 (20%) | Late Finish - 28 (20%) | Late Finish - 28 (20%) | Late Finish - 28 (20%) | Late Finish - 28 (20%) | Late Finish - 28 (20%) | Late Finish - 28 (20%) | Late Finish - 28 (20%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | 2026-08-01 13:00 | p | 19 |  | 2026-08-21 05:00
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | 2026-08-01 13:00 | p | 19 |  | 2026-08-21 05:00
3 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 2026-07-31 15:00 | p | 14 |  | 2026-08-14 23:00
4 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 2026-07-30 22:00 | q | -2 |  | 2026-07-28 17:00
5 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | 2026-07-16 22:00 | q | -7 |  | 2026-07-09 08:00
6 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | 2026-07-16 14:00 | q | -7 |  | 2026-07-08 17:00
7 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 2026-08-01 13:00 | p | 19 |  | 2026-08-21 05:00
8 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 2026-07-31 23:00 | p | 20 |  | 2026-08-20 23:00
9 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | 2026-08-18 12:00 | p | 19 |  | 2026-09-07 10:00
10 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | 2026-08-17 13:00 | p | 20 |  | 2026-09-07 10:00
11 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | 2026-08-17 13:00 | p | 20 |  | 2026-09-07 10:00
12 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 2026-08-05 21:00 | p | 32 |  | 2026-09-07 10:00
13 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 2026-08-05 12:00 | p | 30 |  | 2026-09-04 19:00
14 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 2026-08-04 21:00 | p | 30 |  | 2026-09-04 10:00
15 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 2026-08-04 21:00 | p | 30 |  | 2026-09-04 10:00
16 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 2026-08-04 21:00 | p | 30 |  | 2026-09-04 10:00
17 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 2026-08-04 21:00 | p | 30 |  | 2026-09-04 10:00
18 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 2026-08-04 21:00 | p | 30 |  | 2026-09-04 10:00
19 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | 2026-09-18 23:00 | q | -49 |  | 2026-07-31 17:00
20 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | 2026-09-16 15:00 | q | -49 |  | 2026-07-29 08:00
21 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 2026-09-24 15:00 | q | -48 |  | 2026-08-06 17:00
22 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 2026-09-24 23:00 | q | -2 |  | 2026-09-22 10:00
23 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 2026-09-16 06:00 | p | 50 |  | 2026-11-05 12:00
24 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 2026-09-14 17:00 | p | 45 |  | 2026-10-29 17:00
25 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 2026-09-15 15:00 | p | 45 |  | 2026-10-30 23:00
26 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 2026-09-15 23:00 | p | 50 |  | 2026-11-05 12:00
27 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 2026-09-16 06:00 | p | 50 |  | 2026-11-05 12:00
28 | 412 | Read the note for an explanation of the purpose of the template | Milestone | 0 | 1 | 1 |  | 2026-07-15 22:00 | q | -7 |  | 2026-07-08 08:00

## Expected-Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated

## Suspend-Date
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Suspend Date - 15 (11%) | Suspend Date - 15 (11%) | Suspend Date - 15 (11%) | Suspend Date - 15 (11%) | Suspend Date - 15 (11%) | Suspend Date - 15 (11%) | Suspend Date - 15 (11%) | Suspend Date - 15 (11%) | Suspend Date - 15 (11%) | Suspend Date - 15 (11%) | Suspend Date - 15 (11%) | Suspend Date - 15 (11%) | Suspend Date - 15 (11%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | O | p |  |  | 2026-07-08 17:00
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | O | p |  |  | 2026-07-08 17:00
3 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | O | p |  |  | 2026-07-28 17:00
4 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | O | p |  |  | 2026-07-09 08:00
5 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | O | p |  |  | 2026-07-08 17:00
6 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | O | p |  |  | 2026-08-11 17:00
7 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | O | p |  |  | 2026-08-11 17:00
8 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | O | p |  |  | 2026-08-11 17:00
9 | 187 | Determine required skill sets for various support options | Normal | 15 | 3.1.2.3 | 3.1.2.3 |  | O | p |  |  | 2026-08-11 17:00
10 | 373 | Build Customer Service Program | Summary | 42 | 6 | 6 |  | O | p |  |  | 2026-07-29 08:00
11 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | O | p |  |  | 2026-07-29 08:00
12 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | O | p |  |  | 2026-07-31 17:00
13 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | O | p |  |  | 2026-07-29 08:00
14 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | O | p |  |  | 2026-08-06 17:00
15 | 412 | Read the note for an explanation of the purpose of the template | Milestone | 0 | 1 | 1 |  | O | p |  |  | 2026-07-08 08:00

## Resume-Date
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Resume Date - 15 (11%) | Resume Date - 15 (11%) | Resume Date - 15 (11%) | Resume Date - 15 (11%) | Resume Date - 15 (11%) | Resume Date - 15 (11%) | Resume Date - 15 (11%) | Resume Date - 15 (11%) | Resume Date - 15 (11%) | Resume Date - 15 (11%) | Resume Date - 15 (11%) | Resume Date - 15 (11%) | Resume Date - 15 (11%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | O | p |  |  | 2026-07-08 17:00
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | O | p |  |  | 2026-07-08 17:00
3 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | O | p |  |  | 2026-07-28 17:00
4 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | O | p |  |  | 2026-07-09 08:00
5 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | O | p |  |  | 2026-07-08 17:00
6 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | O | p |  |  | 2026-08-11 17:00
7 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | O | p |  |  | 2026-08-11 17:00
8 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | O | p |  |  | 2026-08-11 17:00
9 | 187 | Determine required skill sets for various support options | Normal | 15 | 3.1.2.3 | 3.1.2.3 |  | O | p |  |  | 2026-08-11 17:00
10 | 373 | Build Customer Service Program | Summary | 42 | 6 | 6 |  | O | p |  |  | 2026-07-29 08:00
11 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | O | p |  |  | 2026-07-29 08:00
12 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | O | p |  |  | 2026-07-31 17:00
13 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | O | p |  |  | 2026-07-29 08:00
14 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | O | p |  |  | 2026-08-06 17:00
15 | 412 | Read the note for an explanation of the purpose of the template | Milestone | 0 | 1 | 1 |  | O | p |  |  | 2026-07-08 08:00

## Activity-Status
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Activity Status - 15 (11%) | Activity Status - 15 (11%) | Activity Status - 15 (11%) | Activity Status - 15 (11%) | Activity Status - 15 (11%) | Activity Status - 15 (11%) | Activity Status - 15 (11%) | Activity Status - 15 (11%) | Activity Status - 15 (11%) | Activity Status - 15 (11%) | Activity Status - 15 (11%) | Activity Status - 15 (11%) | Activity Status - 15 (11%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | Planned |  |  |  | InProgress
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | Planned |  |  |  | InProgress
3 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | Planned |  |  |  | Complete
4 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | Planned |  |  |  | Complete
5 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | Planned |  |  |  | Complete
6 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | Planned |  |  |  | InProgress
7 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | Planned |  |  |  | InProgress
8 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | Planned |  |  |  | InProgress
9 | 187 | Determine required skill sets for various support options | Normal | 15 | 3.1.2.3 | 3.1.2.3 |  | Planned |  |  |  | InProgress
10 | 373 | Build Customer Service Program | Summary | 42 | 6 | 6 |  | Planned |  |  |  | InProgress
11 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | Planned |  |  |  | InProgress
12 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | Planned |  |  |  | Complete
13 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | Planned |  |  |  | Complete
14 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | Planned |  |  |  | Complete
15 | 412 | Read the note for an explanation of the purpose of the template | Milestone | 0 | 1 | 1 |  | Planned |  |  |  | Complete

## Percent-Complete
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | 0 | p | 0.94 |  | 0.94
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | 0 | p | 0.94 |  | 0.94
3 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 0 | p | 1 |  | 1
4 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | 0 | p | 1 |  | 1
5 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | 0 | p | 1 |  | 1
6 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | 0 | p | 0.43 |  | 0.43
7 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | 0 | p | 0.45 |  | 0.45
8 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | 0 | p | 0.53 |  | 0.53
9 | 187 | Determine required skill sets for various support options | Normal | 15 | 3.1.2.3 | 3.1.2.3 |  | 0 | p | 0.6 |  | 0.6
10 | 373 | Build Customer Service Program | Summary | 42 | 6 | 6 |  | 0 | p | 0.32 |  | 0.32
11 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | 0 | p | 0.74 |  | 0.74
12 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | 0 | p | 1 |  | 1
13 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | 0 | p | 1 |  | 1
14 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 0 | p | 1 |  | 1
15 | 412 | Read the note for an explanation of the purpose of the template | Milestone | 0 | 1 | 1 |  | 0 | p | 1 |  | 1

## Physical---Complete
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Physical % Complete - 4 (3%) | Physical % Complete - 4 (3%) | Physical % Complete - 4 (3%) | Physical % Complete - 4 (3%) | Physical % Complete - 4 (3%) | Physical % Complete - 4 (3%) | Physical % Complete - 4 (3%) | Physical % Complete - 4 (3%) | Physical % Complete - 4 (3%) | Physical % Complete - 4 (3%) | Physical % Complete - 4 (3%) | Physical % Complete - 4 (3%) | Physical % Complete - 4 (3%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 0 | p | 1 |  | 1
2 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | 0 | p | 1 |  | 1
3 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | 0 | p | 1 |  | 1
4 | 412 | Read the note for an explanation of the purpose of the template | Milestone | 0 | 1 | 1 |  | 0 | p | 1 |  | 1

## Critical
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Critical - 3 (2%) | Critical - 3 (2%) | Critical - 3 (2%) | Critical - 3 (2%) | Critical - 3 (2%) | Critical - 3 (2%) | Critical - 3 (2%) | Critical - 3 (2%) | Critical - 3 (2%) | Critical - 3 (2%) | Critical - 3 (2%) | Critical - 3 (2%) | Critical - 3 (2%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | P |  |  |  | O
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | P |  |  |  | O
3 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | P |  |  |  | O

## Longest-Path
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Longest Path - 3 (2%) | Longest Path - 3 (2%) | Longest Path - 3 (2%) | Longest Path - 3 (2%) | Longest Path - 3 (2%) | Longest Path - 3 (2%) | Longest Path - 3 (2%) | Longest Path - 3 (2%) | Longest Path - 3 (2%) | Longest Path - 3 (2%) | Longest Path - 3 (2%) | Longest Path - 3 (2%) | Longest Path - 3 (2%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | P |  |  |  | O
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | P |  |  |  | O
3 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | P |  |  |  | O

## Primary-Constraint
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | None |  |  |  | StartOnOrAfter

## Secondary-Constraint
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated

## Primary-Constraint-Date
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | O | p |  |  | 2026-08-12 08:00

## Secondary-Constraint-Date
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated

## Baseline-Work
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated

## Actual-Work
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | 0 | p | 232 |  | 232
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | 0 | p | 232 |  | 232
3 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 0 | p | 216 |  | 216
4 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | 0 | p | 8 |  | 8
5 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | 0 | p | 8 |  | 8
6 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | 0 | p | 72 |  | 72
7 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | 0 | p | 72 |  | 72
8 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | 0 | p | 72 |  | 72
9 | 187 | Determine required skill sets for various support options | Normal | 15 | 3.1.2.3 | 3.1.2.3 |  | 0 | p | 72 |  | 72
10 | 373 | Build Customer Service Program | Summary | 42 | 6 | 6 |  | 0 | p | 112 |  | 112
11 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | 0 | p | 112 |  | 112
12 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | 0 | p | 40 |  | 40
13 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | 0 | p | 8 |  | 8
14 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 0 | p | 64 |  | 64

## Remaining-Work
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Remaining Work - 14 (10%) | Remaining Work - 14 (10%) | Remaining Work - 14 (10%) | Remaining Work - 14 (10%) | Remaining Work - 14 (10%) | Remaining Work - 14 (10%) | Remaining Work - 14 (10%) | Remaining Work - 14 (10%) | Remaining Work - 14 (10%) | Remaining Work - 14 (10%) | Remaining Work - 14 (10%) | Remaining Work - 14 (10%) | Remaining Work - 14 (10%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | 192 | q | -176 | (-92%) | 16
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | 192 | q | -176 | (-92%) | 16
3 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 160 | q | -160 | (-100%) | 0
4 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | 8 | q | -8 | (-100%) | 0
5 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | 8 | q | -8 | (-100%) | 0
6 | 322 | Service Planning | Summary | 11 | 3 | 3 |  | 160 | q | -72 | (-45%) | 88
7 | 125 | Design Support Services | Summary | 10 | 3.1 | 3.1 |  | 160 | q | -72 | (-45%) | 88
8 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 9 | 3.1.2 | 3.1.2 |  | 136 | q | -72 | (-53%) | 64
9 | 187 | Determine required skill sets for various support options | Normal | 15 | 3.1.2.3 | 3.1.2.3 |  | 120 | q | -72 | (-60%) | 48
10 | 373 | Build Customer Service Program | Summary | 42 | 6 | 6 |  | 328 | q | -88 | (-27%) | 240
11 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | 128 | q | -88 | (-69%) | 40
12 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | 40 | q | -40 | (-100%) | 0
13 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | 8 | q | -8 | (-100%) | 0
14 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 40 | q | -40 | (-100%) | 0

## Total-Work
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Total Work - 6 (4%) | Total Work - 6 (4%) | Total Work - 6 (4%) | Total Work - 6 (4%) | Total Work - 6 (4%) | Total Work - 6 (4%) | Total Work - 6 (4%) | Total Work - 6 (4%) | Total Work - 6 (4%) | Total Work - 6 (4%) | Total Work - 6 (4%) | Total Work - 6 (4%) | Total Work - 6 (4%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 91 | Initial Assessment | Summary | 18 | 2 | 2 |  | 192 | p | 56 | -29% | 248
2 | 92 | Perform Product Review | Summary | 18 | 2.1 | 2.1 |  | 192 | p | 56 | -29% | 248
3 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 160 | p | 56 | -35% | 216
4 | 373 | Build Customer Service Program | Summary | 42 | 6 | 6 |  | 328 | p | 24 | -7% | 352
5 | 392 | Customer Service Program Development | Summary | 37 | 6.3 | 6.3 |  | 128 | p | 24 | -19% | 152
6 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 40 | p | 24 | -60% | 64

## Baseline-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated

## Budget-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated

## Actual-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 0 | p | 10800 |  | 10800
2 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | 0 | p | 400 |  | 400
3 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | 0 | p | 400 |  | 400
4 | 187 | Determine required skill sets for various support options | Normal | 15 | 3.1.2.3 | 3.1.2.3 |  | 0 | p | 3600 |  | 3600
5 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | 0 | p | 2000 |  | 2000
6 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | 0 | p | 400 |  | 400
7 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 0 | p | 3200 |  | 3200

## Remaining-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Remaining Cost - 7 (5%) | Remaining Cost - 7 (5%) | Remaining Cost - 7 (5%) | Remaining Cost - 7 (5%) | Remaining Cost - 7 (5%) | Remaining Cost - 7 (5%) | Remaining Cost - 7 (5%) | Remaining Cost - 7 (5%) | Remaining Cost - 7 (5%) | Remaining Cost - 7 (5%) | Remaining Cost - 7 (5%) | Remaining Cost - 7 (5%) | Remaining Cost - 7 (5%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 8000 | q | -8000 | (-100%) | 0
2 | 96 | Identify typical customer types | Normal | 1 | 2.1.2 | 2.1.2 |  | 400 | q | -400 | (-100%) | 0
3 | 97 | Identify typical product usage scenarios | Normal | 1 | 2.1.1 | 2.1.1 |  | 400 | q | -400 | (-100%) | 0
4 | 187 | Determine required skill sets for various support options | Normal | 15 | 3.1.2.3 | 3.1.2.3 |  | 6000 | q | -3600 | (-60%) | 2400
5 | 399 | Perform subject matter expert review | Normal | 5 | 6.3.2 | 6.3.2 |  | 2000 | q | -2000 | (-100%) | 0
6 | 400 | Build customer service programs | Normal | 1 | 6.3.1 | 6.3.1 |  | 400 | q | -400 | (-100%) | 0
7 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 2000 | q | -2000 | (-100%) | 0

## Total-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
Total Cost - 2 (1%) | Total Cost - 2 (1%) | Total Cost - 2 (1%) | Total Cost - 2 (1%) | Total Cost - 2 (1%) | Total Cost - 2 (1%) | Total Cost - 2 (1%) | Total Cost - 2 (1%) | Total Cost - 2 (1%) | Total Cost - 2 (1%) | Total Cost - 2 (1%) | Total Cost - 2 (1%) | Total Cost - 2 (1%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated
1 | 95 | Identify anticipated product problem points | Normal | 20 | 2.1.3 | 2.1.3 |  | 8000 | p | 2800 | -35% | 10800
2 | 401 | Perform user acceptance testing with customers | Normal | 5 | 6.3.3 | 6.3.3 |  | 2000 | p | 1200 | -60% | 3200

## WBS-Code
Acumen Fuse® Forensic Analysis Report
Hard_File_Fuse
Hard_File - 141 Activities
Compared to: 1 Snapshot
Created on: 7/8/2026
Created by: dpolitte
WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Hard_File | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated