## Directional Path Export
Focus Task Name | Focus Task UID | Task Name | Unique ID | Start | Finish | Driving Slack | Drag | Trace Log Value | Project
QJ29ZvAvtEjBcpqHDer1 | 152 | zyPP7s8BBmPhydQ5fB2g | 5892 | 2026-05-22 13:00 | 2026-05-26 12:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | sp3XFaPtGgzrVeC1wvvV | 6509 | 2026-05-26 13:00 | 2026-06-09 12:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | 5mTVpVcHzmsYLVY8xpKs | 907 | 2026-05-15 08:00 | 2026-05-21 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | C3roUkJ3GEdxAvfnxnUE | 7428 | 2026-03-18 08:00 | 2026-03-25 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | WxzG2sAIbVYYiem4v3mk | 7406 | 2025-08-28 08:00 | 2025-09-15 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | RXAxJx3BHWNVdWFPfZ2a | 5558 | 2025-04-23 08:00 | 2025-05-09 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | iq9bjqBZvH9Bj6912271 | 5734 | 2025-05-12 08:00 | 2025-05-19 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | Z8zFgfwvHK2hwW2AW8Qa | 5735 | 2025-05-20 08:00 | 2025-05-20 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | 7UVU8IboY6NG7sqZCrUC | 5545 | 2025-05-21 08:00 | 2025-05-30 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | ypyrsmMFJqJ9aPla6UhQ | 5730 | 2025-06-02 08:00 | 2025-06-05 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | uQF6Ff0bc2cqy3b37ZQc | 5731 | 2025-06-06 08:00 | 2025-06-06 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | 6WMzJdzS7tY0wFFuXnrc | 5584 | 2025-06-09 08:00 | 2025-06-17 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | 88bEv4EMiOL2y8w1ttIM | 5742 | 2025-06-18 08:00 | 2025-06-24 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | 0Uz4krHDVCdAlMd5aRwh | 5743 | 2025-06-25 08:00 | 2025-06-25 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | KljMWvDEBGSuBTW4zQhZ | 5585 | 2025-06-26 08:00 | 2025-07-07 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | cSBfnbrbVLLFYTMEfBKA | 5744 | 2025-07-08 08:00 | 2025-07-15 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | ZY99Y6JX4jBylnfeedvo | 5745 | 2025-07-16 08:00 | 2025-07-23 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | Z3ZWpIsgJCSKUX161hV0 | 5586 | 2025-07-24 08:00 | 2025-07-29 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | OXOUsYDejGVlgqn4Z1vl | 5587 | 2025-07-30 08:00 | 2025-08-05 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | MFjHKzinVVI0Ndx8qx0B | 5588 | 2025-08-06 08:00 | 2025-08-06 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | MBGoTUikAECGvIHYk1uV | 6997 | 2024-11-01 08:00 | 2025-03-14 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | lfRAbO0c5jl7NaC6s7pm | 5571 | 2025-03-17 08:00 | 2025-04-14 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | ME2oX9BwgLu5cggaunhg | 5738 | 2025-04-15 08:00 | 2025-04-21 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | IivOSmNLtmlF9JKFLUrl | 5739 | 2025-04-22 08:00 | 2025-04-22 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | jk3Vm36iIGViuk9dpLfQ | 5572 | 2025-04-23 08:00 | 2025-05-02 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | eRxCjL3dV2CpHvAG84r7 | 5740 | 2025-05-05 08:00 | 2025-05-20 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | 8Y4jq7dOt4lN4NYBT6r1 | 5741 | 2025-05-21 08:00 | 2025-06-06 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | u3MfiduPa05JsS2ly7WD | 5573 | 2025-06-09 08:00 | 2025-06-12 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | 4i5VLTIa98HteWhFzYjv | 7510 | 2025-06-13 08:00 | 2025-06-17 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | UumEMUqxjwvZXtHBx1rg | 7391 | 2025-06-18 08:00 | 2025-06-23 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | tHPdmsBqm9kHM69dtq3h | 7511 | 2025-06-24 08:00 | 2025-07-02 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | RzIyrLZKRoqlWdOJYpGf | 7393 | 2025-07-03 08:00 | 2025-07-08 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | hmOTDv9qQbSDcHudIm9x | 7512 | 2025-07-09 08:00 | 2025-07-17 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | PMjQe1vYJ6mxUbNABucF | 7395 | 2025-07-18 08:00 | 2025-07-22 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | NbiRgc4Tdvxa900kw7Xq | 7513 | 2025-07-23 08:00 | 2025-08-01 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | ItOQSxoXEYWD5clVNK0n | 7398 | 2025-08-04 08:00 | 2025-08-06 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | cXpFrNuZR7O8wPV6KZK3 | 7399 | 2025-08-07 08:00 | 2025-08-19 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | pMiEhGou1QDK96DPu7Q8 | 7402 | 2025-08-20 08:00 | 2025-08-20 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | EvHLT3cR3tYYGwcq6SC1 | 7404 | 2025-08-21 08:00 | 2025-08-27 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | 5GpI6xkgfIoVOnU9egD8 | 7405 | 2025-08-28 08:00 | 2025-09-15 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | uKngouP2QMMQmu6HFm0I | 7408 | 2025-09-16 08:00 | 2025-09-30 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | C7eZzAQkBbKewE4wmmOD | 7409 | 2025-10-01 08:00 | 2025-10-16 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | VCdEPtbQjRcgNUnNprkZ | 7410 | 2025-10-17 08:00 | 2025-10-31 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | OzHccTXr25Mf4pmiIMuT | 7411 | 2025-11-03 08:00 | 2025-11-18 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | DrM34eAIT9imz4vRHbHm | 7414 | 2025-11-19 08:00 | 2025-11-20 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | RsULMViXRZoYahxlMUQ4 | 7415 | 2025-11-21 08:00 | 2025-12-19 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | U8irVJqpjJwQWU5FcpMo | 7416 | 2025-12-22 08:00 | 2025-12-24 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | yrCdbpyUp4mqkbXiv5Nc | 7417 | 2025-12-26 08:00 | 2026-01-05 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | Iw5sTi596kP8d52cBWYm | 7418 | 2026-01-06 08:00 | 2026-01-12 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | s9reBpLseCBnslseiKA6 | 7419 | 2026-01-13 08:00 | 2026-01-14 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | 5PvQN5TGe8y7KbK2rRhO | 7421 | 2026-01-15 08:00 | 2026-01-27 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | hs9Gt4WgG9pENnEIaC7X | 7423 | 2026-01-28 08:00 | 2026-02-17 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | Pv27HXd826jlfuUJmTLH | 7425 | 2026-02-18 08:00 | 2026-03-17 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | 5QMAV8W19uO0knxuRgYc | 7427 | 2026-03-18 08:00 | 2026-03-25 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | GMfJSktlv5oUXA5LFNgA | 7429 | 2026-03-26 08:00 | 2026-04-02 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | HbmHLQTrqR87hE03VIdq | 7432 | 2026-04-03 08:00 | 2026-04-07 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | FxBsJSw4ZNEIyIQA8bL9 | 7433 | 2026-04-08 08:00 | 2026-04-17 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | ANUK0HdVlI2Jd5hSzs0f | 900 | 2026-04-17 17:00 | 2026-04-17 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | nIjAIVHCOoi1ijXym0cI | 902 | 2026-04-20 08:00 | 2026-04-22 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | UDGopgZ2sb1QsQEooZ9G | 903 | 2026-04-23 08:00 | 2026-05-04 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | MxRWNVEH6ZVBPqNnA2hI | 905 | 2026-05-05 08:00 | 2026-05-14 17:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | PL0zn2U2NPPXQqakkHLb | 906 | 2026-05-15 08:00 | 2026-05-21 17:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | rpzkOhA603pApmNdMeVE | 4679 | 2026-05-22 08:00 | 2026-05-22 12:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | imV319lPgBwI8oLVT5sB | 6514 | 2026-05-22 13:00 | 2026-05-26 12:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | dar9hgzhSUYJxC1MeoTS | 6510 | 2026-05-26 13:00 | 2026-06-09 12:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | IG8fHoH3vjERJ6iSB3Rj | 6513 | 2026-06-09 13:00 | 2026-07-31 12:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | MkjgnYEnwrIrITdXMEl9 | 7434 | 2026-07-31 12:00 | 2026-07-31 12:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | B8zfbswYxyRxHa21jaE6 | 7442 | 2026-07-31 13:00 | 2026-08-21 12:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | lvFKaF8Jtq8DkkB0s9nv | 7443 | 2026-08-21 13:00 | 2026-09-14 12:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | 9hmrS48cr19KgrseY4yN | 1570 | 2026-09-14 13:00 | 2026-09-16 12:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | 8tMCh2h8AwE53TPPkfEv | 7448 | 2026-09-16 13:00 | 2026-09-21 12:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | LaZxXVdUnGzqswRGUiV5 | 7449 | 2026-09-21 13:00 | 2026-09-30 12:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | F3vtt1T8lz7mQWFPgUKT | 7450 | 2026-09-30 13:00 | 2026-10-02 12:00 | 0 days | 0.5 day | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | 7cu6yvdJV8ndF0CYMHk8 | 150 | 2026-10-02 12:00 | 2026-10-02 12:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | nShmtMdGhMi3SzNeAZjW | 7451 | 2026-10-02 12:00 | 2026-10-02 12:00 | 0 days | 0 days | Path 01 | Large_Test_File
QJ29ZvAvtEjBcpqHDer1 | 152 | QJ29ZvAvtEjBcpqHDer1 | 152 | 2026-10-02 12:00 | 2026-10-02 12:00 | 0 days | 0 days | Path 01 | Large_Test_File