## Directional Path Export
Focus Task Name | Focus Task UID | Task Name | Unique ID | Start | Finish | Driving Slack | Drag | Trace Log Value | Project
Pour roof slab | 67 | Form roof slab including all floor openings | 65 | 2027-03-23 08:00 | 2027-03-29 17:00 | 0 days | 0 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Form 3rd floor including all floor openings | 60 | 2027-03-01 08:00 | 2027-03-05 17:00 | 0 days | 0 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Form column piers and spread foundations | 35 | 2026-08-17 08:00 | 2026-09-18 17:00 | 0 days | 16 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Set reinforcing and anchor bolts | 38 | 2026-09-21 08:00 | 2026-09-24 17:00 | 0 days | 4 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Pour column piers and foundations | 39 | 2026-09-25 08:00 | 2026-10-23 17:00 | 0 days | 21 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Cure piers and foundations | 42 | 2026-10-26 08:00 | 2026-11-03 17:00 | 0 days | 7 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Strip column piers and foundation forms | 44 | 2026-11-04 08:00 | 2026-11-06 17:00 | 0 days | 3 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Erect steel columns, beams and joist - 1st and 2nd floors | 48 | 2026-11-09 08:00 | 2026-11-20 17:00 | 0 days | 10 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Erect steel columns, beams and joist - 3rd floor and roof | 49 | 2026-11-23 08:00 | 2026-12-15 17:00 | 0 days | 17 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Install miscellaneous iron and bracing - 3rd floor and roof | 51 | 2026-12-16 08:00 | 2026-12-29 17:00 | 0 days | 10 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Install stairs and miscellaneous iron railing | 52 | 2026-12-30 08:00 | 2027-01-12 17:00 | 0 days | 10 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Touch-up paint on steel | 53 | 2027-01-13 08:00 | 2027-01-19 17:00 | 0 days | 5 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Form 2nd floor including all floor openings | 55 | 2027-01-20 08:00 | 2027-02-11 17:00 | 0 days | 17 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Pour 2nd floor slab | 57 | 2027-02-12 08:00 | 2027-02-17 17:00 | 0 days | 4 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Cure 2nd floor slab | 58 | 2027-02-18 08:00 | 2027-02-26 17:00 | 0 days | 7 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 61 | 2027-03-01 08:00 | 2027-03-05 17:00 | 0 days | 0 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Pour 3rd floor slab | 62 | 2027-03-08 08:00 | 2027-03-11 17:00 | 0 days | 4 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Cure 3rd floor slab | 63 | 2027-03-12 08:00 | 2027-03-22 17:00 | 0 days | 7 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 66 | 2027-03-23 08:00 | 2027-03-29 17:00 | 0 days | 0 days | Path 01 | Project5_TAMPERED
Pour roof slab | 67 | Pour roof slab | 67 | 2027-03-30 08:00 | 2027-04-02 17:00 | 0 days | 4 days | Path 01 | Project5_TAMPERED