## Sensitivity Analysis
SRA Task UID | SRA Task Name | SRA Task BC Duration | SRA Task WC Duration | SRA Task ML Duration | SRA Event UID | SRA Event Name | Event Finish BC | Event Finish WC | Opportunity to Accelerate | Risk of Delay | Total Sensitivity | Total | Opportunity | Risk
107 | Install hardware and accessories | 24.8 days | 41.34 days | 5.51 wks | 145 | Issue final request for payment | 2027-11-30 | 2027-12-22 | 2.8 | 13.8 | 16.6 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
39 | Pour column piers and foundations | 20.58 days | 34.31 days | 22.87 days | 145 | Issue final request for payment | 2027-11-30 | 2027-12-20 | 2.3 | 11.9 | 14.2 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
35 | Form column piers and spread foundations | 10.27 days | 20.54 days | 17.11 days | 145 | Issue final request for payment | 2027-11-24 | 2027-12-08 | 6.8 | 3.4 | 10.2 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
52 | Install stairs and miscellaneous iron railing | 11.84 days | 19.73 days | 2.63 wks | 145 | Issue final request for payment | 2027-12-01 | 2027-12-13 | 1.3 | 6.9 | 8.2 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
51 | Install miscellaneous iron and bracing - 3rd floor and roof | 11.88 days | 19.81 days | 2.64 wks | 145 | Issue final request for payment | 2027-12-01 | 2027-12-13 | 1.3 | 6.9 | 8.2 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
55 | Form 2nd floor including all floor openings | 5.2 days | 11.45 days | 10.41 days | 145 | Issue final request for payment | 2027-11-25 | 2027-12-06 | 5.2 | 1.9 | 7.1 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
49 | Erect steel columns, beams and joist - 3rd floor and roof | 10.67 days | 19.82 days | 3.05 wks | 145 | Issue final request for payment | 2027-11-29 | 2027-12-08 | 3.1 | 3.6 | 6.7 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
142 | Complete punch list items from all inspections | 10.98 days | 19.21 days | 2.74 wks | 145 | Issue final request for payment | 2027-11-30 | 2027-12-08 | 2.7 | 3.5 | 6.2 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
58 | Cure 2nd floor slab | 5.84 days | 10.85 days | 8.35 days | 145 | Issue final request for payment | 2027-11-30 | 2027-12-07 | 2.5 | 2.5 | 5 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
42 | Cure piers and foundations | 6.36 days | 11.13 days | 7.95 days | 145 | Issue final request for payment | 2027-12-01 | 2027-12-08 | 1.6 | 3.2 | 4.8 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
48 | Erect steel columns, beams and joist - 1st and 2nd floors | 5.74 days | 10.67 days | 1.64 wks | 145 | Issue final request for payment | 2027-11-30 | 2027-12-06 | 2.5 | 1.9 | 4.4 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
53 | Touch-up paint on steel | 2.36 days | 5.19 days | 0.94 wks | 145 | Issue final request for payment | 2027-11-30 | 2027-12-06 | 2.4 | 1.9 | 4.3 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
135 | Remove debris from building and do final clean-up | 1.93 days | 3.86 days | 3.22 days | 145 | Issue final request for payment | 2027-12-01 | 2027-12-06 | 1.3 | 1.9 | 3.2 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
38 | Set reinforcing and anchor bolts | 2.78 days | 5.16 days | 3.97 days | 145 | Issue final request for payment | 2027-12-01 | 2027-12-06 | 1.2 | 1.9 | 3.1 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
44 | Strip column piers and foundation forms | 1.62 days | 3.23 days | 2.69 days | 145 | Issue final request for payment | 2027-12-01 | 2027-12-06 | 1.1 | 1.9 | 3 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
57 | Pour 2nd floor slab | 2.53 days | 4.7 days | 3.61 days | 145 | Issue final request for payment | 2027-12-01 | 2027-12-06 | 1.1 | 1.9 | 3 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
60 | Form 3rd floor including all floor openings | 3.29 days | 6.57 days | 5.48 days | 145 | Issue final request for payment | 2027-12-02 | 2027-12-06 | 0.5 | 1.9 | 2.4 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
69 | Strip forms from roof slab | 1.74 days | 3.04 days | 2.17 days | 145 | Issue final request for payment | 2027-12-02 | 2027-12-06 | 0.4 | 1.9 | 2.3 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | ¦¦¦¦ | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
140 | Perform local building agency inspection | 1.29 days | 2.15 days | 1.44 days | 145 | Issue final request for payment | 2027-12-02 | 2027-12-03 | 0.2 | 0.7 | 0.9 | ¦¦¦¦¦¦¦¦¦ | ¦¦ | ¦¦¦¦¦¦¦