## Directional Path Export
Focus Task Name | Focus Task UID | Task Name | Unique ID | Start | Finish | Driving Slack | Drag | Trace Log Value | Project
Issue final request for payment | 145 | Install interior doors and hardware | 96 | 2027-09-10 08:00 | 2027-09-23 17:00 | 20 days | 0 | Path 03 | Project5_TAMPERED
Issue final request for payment | 145 | Paint walls and woodwork | 100 | 2027-09-24 08:00 | 2027-10-21 17:00 | 20 days | 0 | Path 03 | Project5_TAMPERED
Issue final request for payment | 145 | Install hardware and accessories | 107 | 2027-10-22 08:00 | 2027-11-26 17:00 | 20 days | 0 | Path 03 | Project5_TAMPERED
Issue final request for payment | 145 | Remove debris from building and do final clean-up | 135 | 2027-11-29 08:00 | 2027-12-02 17:00 | 20 days | 0 | Path 03 | Project5_TAMPERED
Issue final request for payment | 145 | Complete elevator inspection and certification | 138 | 2027-12-03 08:00 | 2027-12-07 17:00 | 20 days | 0 | Path 03 | Project5_TAMPERED
Issue final request for payment | 145 | Perform architect's inspection | 139 | 2027-12-08 08:00 | 2027-12-08 17:00 | 20 days | 0 | Path 03 | Project5_TAMPERED
Issue final request for payment | 145 | Perform local building agency inspection | 140 | 2027-12-09 08:00 | 2027-12-09 17:00 | 20 days | 0 | Path 03 | Project5_TAMPERED
Issue final request for payment | 145 | Perform Fire Marshal's inspection | 141 | 2027-12-10 08:00 | 2027-12-10 17:00 | 20 days | 0 | Path 03 | Project5_TAMPERED
Issue final request for payment | 145 | Set HVAC trim and test and balance system | 131 | 2027-12-10 08:00 | 2028-01-06 17:00 | 1 day | 0 | Path 02 | Project5_TAMPERED
Issue final request for payment | 145 | Complete punch list items from all inspections | 142 | 2028-01-07 08:00 | 2028-01-20 17:00 | 1 day | 0 | Path 02 | Project5_TAMPERED
Issue final request for payment | 145 | Obtain certificate of occupancy | 143 | 2028-01-21 08:00 | 2028-01-24 17:00 | 1 day | 0 | Path 02 | Project5_TAMPERED
Issue final request for payment | 145 | Issue final completion documents including warranties | 144 | 2028-01-25 08:00 | 2028-01-25 17:00 | 0 days | 1 day | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Issue final request for payment | 145 | 2028-01-26 08:00 | 2028-01-26 17:00 | 0 days | 1 day | Path 01 | Project5_TAMPERED