## Directional Path Export
Focus Task Name | Focus Task UID | Task Name | Unique ID | Start | Finish | Driving Slack | Drag | Trace Log Value | Project
Issue final request for payment | 145 | Obtain certificate of occupancy | 143 | 2028-01-21 08:00 | 2028-01-24 17:00 | 1 day | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Pave, curb, and stripe parking lot | 109 | 2027-11-05 08:00 | 2027-11-18 17:00 | 33 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install hard tile flooring in common areas | 133 | 2027-08-20 08:00 | 2027-08-26 17:00 | 82 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Clean hard tile floors | 134 | 2027-08-27 08:00 | 2027-09-01 17:00 | 82 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install ceiling tile | 104 | 2027-09-24 08:00 | 2027-10-07 17:00 | 56 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Rough-in electrical in drywall walls | 121 | 2027-08-06 08:00 | 2027-09-02 17:00 | 56 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install and terminate electrical devices | 123 | 2027-09-24 08:00 | 2027-10-14 17:00 | 41 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install light fixtures - test and clean | 125 | 2027-10-19 08:00 | 2027-11-01 17:00 | 39 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Clean masonry | 85 | 2027-06-11 08:00 | 2027-06-17 17:00 | 116 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Tie-in fire line riser and set valves | 116 | 2027-06-18 08:00 | 2027-07-01 17:00 | 116 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Rough-in plumbing at toilets and masonry walls | 80 | 2027-04-20 08:00 | 2027-05-17 17:00 | 119 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install tile in toilet rooms | 84 | 2027-05-18 08:00 | 2027-05-31 17:00 | 119 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Clean toilet room tile | 86 | 2027-06-01 08:00 | 2027-06-07 17:00 | 119 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Rough-in plumbing in drywall walls | 115 | 2027-07-16 08:00 | 2027-08-12 17:00 | 71 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Set plumbing fixtures and trim | 117 | 2027-08-13 08:00 | 2027-09-02 17:00 | 71 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Flush, test, and clean piping and fixtures | 118 | 2027-10-22 08:00 | 2027-11-04 17:00 | 36 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Complete interior and exterior sod and plantings | 108 | 2027-10-22 08:00 | 2027-11-04 17:00 | 33 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Hang wallpaper | 105 | 2027-10-22 08:00 | 2027-11-04 17:00 | 36 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install store front doors and hardware | 97 | 2027-07-16 08:00 | 2027-08-05 17:00 | 40 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install millwork and wood trim | 99 | 2027-08-20 08:00 | 2027-09-09 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install interior doors and hardware | 96 | 2027-09-10 08:00 | 2027-09-23 17:00 | 20 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Paint walls and woodwork | 100 | 2027-09-24 08:00 | 2027-10-21 17:00 | 20 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install hardware and accessories | 107 | 2027-10-22 08:00 | 2027-11-26 17:00 | 20 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Remove debris from building and do final clean-up | 135 | 2027-11-29 08:00 | 2027-12-02 17:00 | 20 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Complete elevator inspection and certification | 138 | 2027-12-03 08:00 | 2027-12-07 17:00 | 20 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Perform architect's inspection | 139 | 2027-12-08 08:00 | 2027-12-08 17:00 | 20 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Perform local building agency inspection | 140 | 2027-12-09 08:00 | 2027-12-09 17:00 | 20 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Perform Fire Marshal's inspection | 141 | 2027-12-10 08:00 | 2027-12-10 17:00 | 20 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install miscellaneous iron and bracing - 1st and 2nd floors | 50 | 2027-01-13 08:00 | 2027-02-18 17:00 | 166 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Lay masonry at core, mechanical, and toilets | 81 | 2027-02-19 08:00 | 2027-03-18 17:00 | 166 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Set equipment in mechanical room | 127 | 2027-03-19 08:00 | 2027-04-01 17:00 | 166 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Rough-in mechanical in masonry walls | 128 | 2027-04-20 08:00 | 2027-05-17 17:00 | 134 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install duct in building chase | 130 | 2027-07-28 08:00 | 2027-08-17 17:00 | 83 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install interior stud walls and drywall | 95 | 2027-07-16 08:00 | 2027-08-19 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install duct in ceiling plenum space | 102 | 2027-08-20 08:00 | 2027-09-09 17:00 | 56 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install ceiling grid | 103 | 2027-09-10 08:00 | 2027-09-23 17:00 | 56 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Submit shop drawings and order long lead items - roofing | 12 | 2026-05-05 08:00 | 2026-05-29 17:00 | 371 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install flashing at parapet walls | 88 | 2027-06-11 08:00 | 2027-06-16 17:00 | 98 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install roof drains | 83 | 2027-06-17 08:00 | 2027-06-18 17:00 | 96 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Pour lightweight concrete roof fill | 89 | 2027-06-21 08:00 | 2027-06-22 17:00 | 96 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install seamless roofing material | 90 | 2027-06-30 08:00 | 2027-07-06 17:00 | 96 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Spread stone ballast on seamless roof | 91 | 2027-07-07 08:00 | 2027-07-13 17:00 | 96 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Set rooftop equipment | 92 | 2027-07-14 08:00 | 2027-07-27 17:00 | 96 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install rebar and in-floor utilities | 73 | 2027-03-10 08:00 | 2027-03-15 17:00 | 131 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Form 1st floor | 70 | 2027-03-10 08:00 | 2027-03-15 17:00 | 131 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install plumbing underground | 72 | 2027-03-16 08:00 | 2027-03-22 17:00 | 126 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Strip forms from 2nd floor slab | 59 | 2027-03-08 08:00 | 2027-03-09 17:00 | 130 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install electrical underground | 71 | 2027-03-16 08:00 | 2027-03-22 17:00 | 126 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Pour 1st floor slab | 74 | 2027-03-23 08:00 | 2027-03-26 17:00 | 126 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Cure 1st floor slab | 75 | 2027-04-01 08:00 | 2027-04-09 17:00 | 123 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Strip forms from 1st floor slab | 76 | 2027-04-16 08:00 | 2027-04-19 17:00 | 119 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Rough-in electrical in masonry walls | 120 | 2027-04-20 08:00 | 2027-05-17 17:00 | 119 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Strip forms from 3rd floor slab | 64 | 2027-03-30 08:00 | 2027-03-31 17:00 | 41 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Form roof slab including all floor openings | 65 | 2027-03-23 08:00 | 2027-03-29 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Form 3rd floor including all floor openings | 60 | 2027-03-01 08:00 | 2027-03-05 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 56 | 2026-12-16 08:00 | 2026-12-22 17:00 | 67 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Submit shop drawings and order long lead items - plumbing | 14 | 2026-05-05 08:00 | 2026-05-15 17:00 | 207 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Submit shop drawings and order long lead items - HVAC | 16 | 2026-05-05 08:00 | 2026-05-18 17:00 | 206 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Obtain building permits | 7 | 2026-03-05 08:00 | 2026-03-10 17:00 | 222 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Submit preliminary shop drawings | 8 | 2026-04-02 08:00 | 2026-05-04 17:00 | 206 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Submit shop drawings and order long lead items - electric | 15 | 2026-06-08 08:00 | 2026-06-19 17:00 | 182 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Submit monthly requests for payment | 9 | 2026-03-05 08:00 | 2026-03-05 17:00 | 130 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Submit shop drawings and order long lead items - steel | 11 | 2026-03-06 08:00 | 2026-03-27 17:00 | 130 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Detail, fabricate and deliver steel | 17 | 2026-03-30 08:00 | 2026-06-19 17:00 | 130 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install storm drainage | 28 | 2026-04-22 08:00 | 2026-05-19 17:00 | 67 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install temporary water service | 20 | 2026-03-05 08:00 | 2026-03-06 17:00 | 42 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Receive notice to proceed and sign contract | 3 | 2026-03-02 08:00 | 2026-03-04 17:00 | 42 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install temporary power | 19 | 2026-03-05 08:00 | 2026-03-06 17:00 | 42 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Set up site office | 21 | 2026-03-09 08:00 | 2026-03-11 17:00 | 42 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Set line and grade benchmarks | 22 | 2026-03-12 08:00 | 2026-03-25 17:00 | 42 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Prepare site - lay down yard and temporary fencing | 23 | 2026-03-26 08:00 | 2026-03-27 17:00 | 42 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Clear and grub site | 25 | 2026-04-06 08:00 | 2026-04-08 17:00 | 37 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Stone site access and temporary parking area | 26 | 2026-04-13 08:00 | 2026-04-14 17:00 | 35 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Rough grade site (cut and fill) | 27 | 2026-04-15 08:00 | 2026-04-21 17:00 | 35 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install exterior fire line and building fire riser | 29 | 2026-04-22 08:00 | 2026-06-19 17:00 | 35 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Perform final site grading | 30 | 2026-06-22 08:00 | 2026-07-03 17:00 | 35 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Erect building batter boards and layout building | 31 | 2026-07-06 08:00 | 2026-07-31 17:00 | 35 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Excavate foundations | 33 | 2026-08-03 08:00 | 2026-08-07 17:00 | 35 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Form column piers and spread foundations | 35 | 2026-08-17 08:00 | 2026-09-18 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Set reinforcing and anchor bolts | 38 | 2026-09-21 08:00 | 2026-09-24 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Pour column piers and foundations | 39 | 2026-09-25 08:00 | 2026-10-23 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Cure piers and foundations | 42 | 2026-10-26 08:00 | 2026-11-03 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Strip column piers and foundation forms | 44 | 2026-11-04 08:00 | 2026-11-06 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Erect steel columns, beams and joist - 1st and 2nd floors | 48 | 2026-11-09 08:00 | 2026-11-20 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Erect steel columns, beams and joist - 3rd floor and roof | 49 | 2026-11-23 08:00 | 2026-12-15 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install miscellaneous iron and bracing - 3rd floor and roof | 51 | 2026-12-16 08:00 | 2026-12-29 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install stairs and miscellaneous iron railing | 52 | 2026-12-30 08:00 | 2027-01-12 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Touch-up paint on steel | 53 | 2027-01-13 08:00 | 2027-01-19 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Form 2nd floor including all floor openings | 55 | 2027-01-20 08:00 | 2027-02-11 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Pour 2nd floor slab | 57 | 2027-02-12 08:00 | 2027-02-17 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Cure 2nd floor slab | 58 | 2027-02-18 08:00 | 2027-02-26 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 61 | 2027-03-01 08:00 | 2027-03-05 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Pour 3rd floor slab | 62 | 2027-03-08 08:00 | 2027-03-11 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Cure 3rd floor slab | 63 | 2027-03-12 08:00 | 2027-03-22 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 66 | 2027-03-23 08:00 | 2027-03-29 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Pour roof slab | 67 | 2027-03-30 08:00 | 2027-04-02 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Cure roof slab | 68 | 2027-04-05 08:00 | 2027-04-13 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Strip forms from roof slab | 69 | 2027-04-14 08:00 | 2027-04-15 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install exterior sheathing and metal studs | 78 | 2027-04-16 08:00 | 2027-05-06 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install exterior masonry work | 82 | 2027-05-07 08:00 | 2027-06-10 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install window wall aluminum and glass | 94 | 2027-06-11 08:00 | 2027-07-15 17:00 | 30 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Install conduit at ceiling plenum space | 101 | 2027-07-16 08:00 | 2027-08-05 17:00 | 61 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Pull wire in conduit and set area transformers | 122 | 2027-09-03 08:00 | 2027-09-23 17:00 | 41 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Make electrical terminations for HVAC equipment | 124 | 2027-10-15 08:00 | 2027-10-18 17:00 | 39 days | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Set HVAC trim and test and balance system | 131 | 2027-12-10 08:00 | 2028-01-06 17:00 | 1 day | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Complete punch list items from all inspections | 142 | 2028-01-07 08:00 | 2028-01-20 17:00 | 1 day | 0 | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Issue final completion documents including warranties | 144 | 2028-01-25 08:00 | 2028-01-25 17:00 | 0 days | 1 day | Path 01 | Project5_TAMPERED
Issue final request for payment | 145 | Issue final request for payment | 145 | 2028-01-26 08:00 | 2028-01-26 17:00 | 0 days | 1 day | Path 01 | Project5_TAMPERED