Schedule Risk Analysis Report - USA OTB Master IMS

Executive summary

This Schedule Risk Analysis evaluates the finish of Ready to Ship over 2000 Monte-Carlo iterations. The deterministic (logic-only) finish is 2027-10-19 (about P30). The risk-adjusted finish is most likely 2027-11-03 (P50); 2027-11-09 at P80 and 2027-11-23 at P90 carry progressively more contingency. The mean outcome is 2027-11-02 with a standard deviation of 7.8 working days (11.2 calendar days). 12 discrete risk/opportunity event(s) were modeled. The largest duration-sensitivity driver is task n/a.

| Measure | Value |
| --- | --- |
| Focus event | 152 - Ready to Ship |
| Deterministic finish | 2027-10-19 (P30.2) |
| P50 (most likely) | 2027-11-03 |
| P80 | 2027-11-09 |
| P90 | 2027-11-23 |
| Mean | 2027-11-02 |
| Std deviation (working days) | 7.8 |
| Std deviation (calendar days) | 11.2 |
| Risk / opportunity events | 12 |
| Top sensitivity driver | n/a |

How to read this: Read the P-values as confidence levels: a P80 date has an approximately 80% modeled chance of being met. The deterministic finish typically sits well below P50, so the gap between them is the contingency the current logic does not yet carry.

How to set up this analysis (inputs)

The forecast is driven entirely by the inputs below. Enter them on the Schedule Risk & Opportunity Analysis page, then run the Monte-Carlo. This section documents exactly what was used for this report so the analysis can be reviewed and reproduced.

| Input | How you enter it | What it does |
| --- | --- | --- |
| Focus event | Type the task UID whose finish you want to forecast (blank = project finish). | Every result (S-curve, percentiles, sensitivity) is measured at this event's finish. |
| Risk Ranking Factor (0-5) | Per task, in the grid or the 'Assign Risk Ranking Factor' box (one value, a list of UIDs, or paste a whole column from Excel/MS Project). | 0 = no duration uncertainty (uses the Remaining Duration as-is). 1-5 widen the Best/Worst-case spread using the Risk Factors table below. |
| Best / Worst-case duration | Auto-calculated from the factor (ML = current Remaining Duration), or type a value to override. | Sets the low/high ends of each task's sampled duration range. |
| Risk / Opportunity register | Add an event with a probability %, a schedule impact in days (positive = delay/risk, negative = acceleration/opportunity), and the affected task UID(s). | On each iteration the event may fire and add its impact to the affected tasks. |
| Occurrence mode | Choose 'Random each iteration' or 'Exact percentage overall'. | How often registered events fire across the run (see below). |
| Correlation | 0 to 1 (0 = independent; 0.3-0.5 typical). | Couples task durations so highs/lows do not fully cancel, widening the spread. |

Risk Factors table (factor -> Best/Worst case)

Best case = ML x (1 - subtract%/100); Worst case = ML x (1 + add%/100), where ML is the task's current Remaining Duration. These are the percentages used for this report:

| Risk Ranking Factor | % subtract (Best case) | % add (Worst case) |
| --- | --- | --- |
| 0 (no uncertainty) | 0 | 0 |
| 1 | 50 | 10 |
| 2 | 40 | 20 |
| 3 | 30 | 30 |
| 4 | 20 | 40 |
| 5 | 10 | 50 |

Random each iteration: When this option is selected, the probability of risks/opportunities occurring is evaluated independently on each iteration of the SRA using the entered probability of occurrence. Over many iterations the average result will be close to the entered percentage, but the exact number of occurrences may vary each time you run the SRA.

Exact percentage overall: When this option is selected, the total number of times a given risk/opportunity occurs is determined at the beginning of the SRA process based on the entered probability and the total number of SRA iterations chosen. That total is then randomly distributed across the iterations, so the risk/opportunity occurs the exact expected number of times overall.

Focus-finish results

The simulated finish-date distribution of the focus event: the deterministic finish, the P10/P50/P80/P90 confidence dates, the mean, and the spread (standard deviation).

| Measure | Value |
| --- | --- |
| Deterministic finish | 2027-10-19 |
| Deterministic percentile | 30.2 |
| P10 | 2027-10-19 |
| P50 | 2027-11-03 |
| P80 | 2027-11-09 |
| P90 | 2027-11-23 |
| Mean | 2027-11-02 |
| Std deviation (working days) | 7.8 |
| Std deviation (calendar days) | 11.2 |

Finish-date confidence (S-curve)

Finish-date confidence (S-curve)

0%

25%

50%

75%

100%

2027-10-19

2027-11-23

Forecast finish date  (y = % chance of finishing on or before)

P10  2027-10-19

P50  2027-11-03

P80  2027-11-09

P90  2027-11-23

Deterministic  2027-10-19

— confidence curve

- - deterministic (logic-only) finish

* P10-P90 markers

Cumulative probability of finishing on or before each date (blue). The dashed amber line is the deterministic finish; the red dots mark P10/P50/P80/P90.

Finish-date distribution

Finish-date distribution

0

448

896

Iterations

2027-10-19

2027-11-23

Forecast finish date  (y = number of simulated finishes)

most likely

2027-11-03 (896)

How many of the simulated runs landed on each finish date (taller = more likely). The labelled bar is the single most-likely finish date.

Duration sensitivity (one-at-a-time)

Each ranked activity's Best/Worst-case duration is swung independently to measure how far it can pull in (opportunity to accelerate, green) or push out (risk of delay, red) the focus finish. This deterministic one-at-a-time method is validated against the reference tool.

| UID | Task | Best case d | Worst case d | ML d | Opportunity wd | Risk wd | Total wd |
| --- | --- | --- | --- | --- | --- | --- | --- |

Float basis: Swings are measured on pure-logic CPM float; this tool does not consume the file's stored, progress-aware Critical flag (ADR-0010). A near-critical activity that a tool reading the stored float treats as driving can show a smaller delay-swing here, and vice-versa, so the mid/low ranking may differ slightly from such a tool even though the top drivers and the Best/Worst-case inputs agree.

Per-task Best/Worst-case durations

The Risk Ranking Factor assigned to each ranked task and the Best/Worst-case durations derived from it (ML = current Remaining Duration), or entered manually.

| UID | Task | Factor | Best case d | Worst case d |
| --- | --- | --- | --- | --- |

Risk / Opportunity register

Discrete risks and opportunities, each with its probability, additive schedule impact, simulated occurrence count, and 1-5 probability/consequence ratings.

| ID | Name | Probability % | Impact d | Affected | Consequence | Hits | Mean delta d |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | 687 | 10.0 | 120.0 | 8509 | 4 | 207 | 0.8 |
| R4 | 739 | 10.0 | 120.0 | 8519 | 4 | 217 | 0.3 |
| R5 | 104 | 30.0 | 45.0 | 8511 | 3 | 576 | -0.2 |
| R6 | 729 | 45.0 | 50.0 | 8518 | 3 | 896 | 0.4 |
| R7 | 766 | 25.0 | 40.0 | 8522 | 3 | 528 | 0.1 |
| R8 | 147 | 10.0 | 60.0 | 8513 | 3 | 224 | 0.8 |
| R9 | 745 | 50.0 | 20.0 | 8512 | 2 | 987 | -0.3 |
| R10 | 704 | 25.0 | 20.0 | 8515 | 2 | 506 | -0.4 |
| R11 | 725 | 50.0 | 30.0 | 8516 | 2 | 988 | -0.1 |
| R13 | 728 | 60.0 | 10.0 | 8517 | 2 | 1169 | 9.4 |
| R14 | 761 | 25.0 | 40.0 | 8521 | 3 | 500 | 14.0 |
| R15 | 760 | 80.0 | 45.0 | 8520 | 3 | 1588 | 0.2 |

Risk & Opportunity assessment matrices

Each event is placed by its Likelihood of Occurrence (rows, 1-5) and Consequence/Benefit of Occurrence (columns, 1-5). Each cell shows the NASA priority rank (1-25) and, in parentheses, the count of events that land there.

Risk Assessment Matrix

| L \ C | 1 Low | 2 Minor | 3 Moderate | 4 Significant | 5 Severe |
| --- | --- | --- | --- | --- | --- |
| 5 Near Certainty | 10 | 16 | 20 (1) | 23 | 25 |
| 4 Highly Likely | 7 | 13 (1) | 18 | 22 | 24 |
| 3 Possible | 4 | 9 (2) | 15 (1) | 19 | 21 |
| 2 Unlikely | 2 | 6 (1) | 11 (3) | 14 | 17 |
| 1 Remote | 1 | 3 | 5 (1) | 8 (2) | 12 |

Opportunity Assessment Matrix

| L \ C | 1 Low | 2 Minor | 3 Moderate | 4 High | 5 Very High |
| --- | --- | --- | --- | --- | --- |
| 5 Near Certainty | 10 | 16 | 20 | 23 | 25 |
| 4 Highly Likely | 7 | 13 | 18 | 22 | 24 |
| 3 Possible | 4 | 9 | 15 | 19 | 21 |
| 2 Unlikely | 2 | 6 | 11 | 14 | 17 |
| 1 Remote | 1 | 3 | 5 | 8 | 12 |

Methodology & assumptions

Best/Worst-case durations use ML = the current Remaining Duration; BC = ML x (1 - subtract%/100), WC = ML x (1 + add%/100) with the per-factor percentages from the Risk Factors table. Occurrence mode: random_each. Correlation: 0. Risk register: on. Consequence (1-5) is auto-rated from the schedule impact via the NASA Schedule guideline (impact days converted to calendar months: <1 week=1, 1 week to <1 month=2, 1 to <3 months=3, 3 to <=6 months=4, >6 months=5).

The Best/Worst-case derivation and the deterministic one-at-a-time sensitivity are validated against the reference tool. The stochastic distribution (S-curve, histogram, percentiles) uses a standard-library random generator that is statistically representative but NOT bit-identical to the reference tool's, so treat the P-values as close, not exact (ADR-0005/0106). All computation is local and offline; this document carries the CUI marking in its header and footer.