Schedule Risk Analysis Report - Commercial Construction

Executive summary

This Schedule Risk Analysis evaluates the finish of Issue final request for payment over 2000 Monte-Carlo iterations. The deterministic (logic-only) finish is 2027-12-03 (about P11). The risk-adjusted finish is most likely 2027-12-13 (P50); 2027-12-21 at P80 and 2027-12-26 at P90 carry progressively more contingency. The mean outcome is 2027-12-13 with a standard deviation of 6.8 working days. 1 discrete risk/opportunity event(s) were modeled. The largest duration-sensitivity driver is task 107 Install hardware and accessories (16.6 wd total swing).

| Measure | Value |
| --- | --- |
| Focus event | 145 - Issue final request for payment |
| Deterministic finish | 2027-12-03 (P10.8) |
| P50 (most likely) | 2027-12-13 |
| P80 | 2027-12-21 |
| P90 | 2027-12-26 |
| Mean | 2027-12-13 |
| Std deviation (working days) | 6.8 |
| Risk / opportunity events | 1 |
| Top sensitivity driver | 107 Install hardware and accessories (16.6 wd total swing) |

How to read this: Read the P-values as confidence levels: a P80 date has an approximately 80% modeled chance of being met. The deterministic finish typically sits well below P50, so the gap between them is the contingency the current logic does not yet carry.

How to set up this analysis (inputs)

The forecast is driven entirely by the inputs below. Enter them on the Schedule Risk & Opportunity Analysis page, then run the Monte-Carlo. This section documents exactly what was used for this report so the analysis can be reviewed and reproduced.

| Input | How you enter it | What it does |
| --- | --- | --- |
| Focus event | Type the task UID whose finish you want to forecast (blank = project finish). | Every result (S-curve, percentiles, sensitivity) is measured at this event's finish. |
| Risk Ranking Factor (0-5) | Per task, in the grid or the 'Assign Risk Ranking Factor' box (one value, a list of UIDs, or paste a whole column from Excel/MS Project). | 0 = no duration uncertainty (uses the Remaining Duration as-is). 1-5 widen the Best/Worst-case spread using the Risk Factors table below. |
| Best / Worst-case duration | Auto-calculated from the factor (ML = current Remaining Duration), or type a value to override. | Sets the low/high ends of each task's sampled duration range. |
| Risk / Opportunity register | Add an event with a probability %, a schedule impact in days (positive = delay/risk, negative = acceleration/opportunity), and the affected task UID(s). | On each iteration the event may fire and add its impact to the affected tasks. |
| Occurrence mode | Choose 'Random each iteration' or 'Exact percentage overall'. | How often registered events fire across the run (see below). |
| Correlation | 0 to 1 (0 = independent; 0.3-0.5 typical). | Couples task durations so highs/lows do not fully cancel, widening the spread. |

Risk Factors table (factor -> Best/Worst case)

Best case = ML x (1 - subtract%/100); Worst case = ML x (1 + add%/100), where ML is the task's current Remaining Duration. These are the percentages used for this report:

| Risk Ranking Factor | % subtract (Best case) | % add (Worst case) |
| --- | --- | --- |
| 0 (no uncertainty) | 0 | 0 |
| 1 | 50 | 10 |
| 2 | 40 | 20 |
| 3 | 30 | 30 |
| 4 | 20 | 40 |
| 5 | 10 | 50 |

Random each iteration: When this option is selected, the probability of risks/opportunities occurring is evaluated independently on each iteration of the SRA using the entered probability of occurrence. Over many iterations the average result will be close to the entered percentage, but the exact number of occurrences may vary each time you run the SRA.

Exact percentage overall: When this option is selected, the total number of times a given risk/opportunity occurs is determined at the beginning of the SRA process based on the entered probability and the total number of SRA iterations chosen. That total is then randomly distributed across the iterations, so the risk/opportunity occurs the exact expected number of times overall.

Focus-finish results

The simulated finish-date distribution of the focus event: the deterministic finish, the P10/P50/P80/P90 confidence dates, the mean, and the spread (standard deviation).

| Measure | Value |
| --- | --- |
| Deterministic finish | 2027-12-03 |
| Deterministic percentile | 10.8 |
| P10 | 2027-11-30 |
| P50 | 2027-12-13 |
| P80 | 2027-12-21 |
| P90 | 2027-12-26 |
| Mean | 2027-12-13 |
| Std deviation (working days) | 6.8 |

Finish-date confidence (S-curve)

Finish-date confidence (S-curve)

0%

25%

50%

75%

100%

2027-11-15

2028-01-18

Forecast finish date  (y = % chance of finishing on or before)

P10  2027-11-30

P50  2027-12-13

P80  2027-12-21

P90  2027-12-26

Deterministic  2027-12-03

— confidence curve

- - deterministic (logic-only) finish

* P10-P90 markers

Cumulative probability of finishing on or before each date (blue). The dashed amber line is the deterministic finish; the red dots mark P10/P50/P80/P90.

Finish-date distribution

Finish-date distribution

0

79

158

Iterations

2027-11-15

2028-01-18

Forecast finish date  (y = number of simulated finishes)

most likely

2027-12-13 (158)

How many of the simulated runs landed on each finish date (taller = more likely). The labelled bar is the single most-likely finish date.

Duration sensitivity (one-at-a-time)

Each ranked activity's Best/Worst-case duration is swung independently to measure how far it can pull in (opportunity to accelerate, green) or push out (risk of delay, red) the focus finish. This deterministic one-at-a-time method is validated to match SSI exactly.

Duration sensitivity (tornado) — working-day swing

◀ opportunity (accelerate)

risk (delay) ▶

0

-16.6 wd

+16.6 wd

Working days the focus finish moves when each task is swung Best↔Worst

107

16.6 wd

39

13.7 wd

35

10.2 wd

49

9.2 wd

142

8.2 wd

51

7.9 wd

52

7.9 wd

55

6.2 wd

48

5 wd

58

5 wd

42

4.8 wd

53

2.9 wd

Bars centred on zero: green extends left (acceleration), red right (delay); the longest total swing sets the scale. Top 12 of 19 ranked activities shown; the full set is in the table below.

| UID | Task | Best case d | Worst case d | ML d | Opportunity wd | Risk wd | Total wd |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 107 | Install hardware and accessories | 24.8 | 41.34 | 27.56 | 2.8 | 13.8 | 16.6 |
| 39 | Pour column piers and foundations | 20.58 | 34.31 | 22.87 | 2.3 | 11.4 | 13.7 |
| 35 | Form column piers and spread foundations | 10.27 | 20.54 | 17.11 | 6.8 | 3.4 | 10.2 |
| 49 | Erect steel columns, beams and joist - 3rd floor and roof | 10.67 | 19.82 | 15.25 | 4.6 | 4.6 | 9.2 |
| 142 | Complete punch list items from all inspections | 10.98 | 19.21 | 13.72 | 2.7 | 5.5 | 8.2 |
| 51 | Install miscellaneous iron and bracing - 3rd floor and roof | 11.88 | 19.81 | 13.2 | 1.3 | 6.6 | 7.9 |
| 52 | Install stairs and miscellaneous iron railing | 11.84 | 19.73 | 13.15 | 1.3 | 6.6 | 7.9 |
| 55 | Form 2nd floor including all floor openings | 5.2 | 11.45 | 10.41 | 5.2 | 1.0 | 6.2 |
| 48 | Erect steel columns, beams and joist - 1st and 2nd floors | 5.74 | 10.66 | 8.2 | 2.5 | 2.5 | 5.0 |
| 58 | Cure 2nd floor slab | 5.84 | 10.85 | 8.35 | 2.5 | 2.5 | 5.0 |
| 42 | Cure piers and foundations | 6.36 | 11.13 | 7.95 | 1.6 | 3.2 | 4.8 |
| 53 | Touch-up paint on steel | 2.36 | 5.19 | 4.71 | 2.4 | 0.5 | 2.9 |
| 38 | Set reinforcing and anchor bolts | 2.78 | 5.16 | 3.97 | 1.2 | 1.2 | 2.4 |
| 57 | Pour 2nd floor slab | 2.53 | 4.7 | 3.61 | 1.1 | 1.1 | 2.2 |
| 135 | Remove debris from building and do final clean-up | 1.93 | 3.86 | 3.22 | 1.3 | 0.6 | 1.9 |
| 44 | Strip column piers and foundation forms | 1.62 | 3.23 | 2.69 | 1.1 | 0.5 | 1.6 |
| 60 | Form 3rd floor including all floor openings | 3.29 | 6.57 | 5.47 | 0.5 | 1.1 | 1.6 |
| 69 | Strip forms from roof slab | 1.74 | 3.04 | 2.17 | 0.4 | 0.9 | 1.3 |
| 140 | Perform local building agency inspection | 1.29 | 2.15 | 1.44 | 0.1 | 0.7 | 0.8 |
| 3 | Receive notice to proceed and sign contract | 3.0 | 3.0 | 3.0 | 0.0 | 0.0 | 0.0 |
| 4 | Submit bond and insurance documents | 2.0 | 2.0 | 2.0 | 0.0 | 0.0 | 0.0 |
| 5 | Prepare and submit project schedule | 2.0 | 2.0 | 2.0 | 0.0 | 0.0 | 0.0 |
| 6 | Prepare and submit schedule of values | 2.0 | 2.0 | 2.0 | 0.0 | 0.0 | 0.0 |
| 7 | Obtain building permits | 4.0 | 4.0 | 4.0 | 0.0 | 0.0 | 0.0 |
| 8 | Submit preliminary shop drawings | 23.0 | 23.0 | 23.0 | 0.0 | 0.0 | 0.0 |
| 9 | Submit monthly requests for payment | 1.0 | 1.0 | 1.0 | 0.0 | 0.0 | 0.0 |
| 11 | Submit shop drawings and order long lead items - steel | 16.0 | 16.0 | 16.0 | 0.0 | 0.0 | 0.0 |
| 12 | Submit shop drawings and order long lead items - roofing | 19.0 | 19.0 | 19.0 | 0.0 | 0.0 | 0.0 |
| 13 | Submit shop drawings and order long lead items - elevator | 10.0 | 10.0 | 10.0 | 0.0 | 0.0 | 0.0 |
| 14 | Submit shop drawings and order long lead items - plumbing | 9.0 | 9.0 | 9.0 | 0.0 | 0.0 | 0.0 |
| 15 | Submit shop drawings and order long lead items - electric | 10.0 | 10.0 | 10.0 | 0.0 | 0.0 | 0.0 |
| 16 | Submit shop drawings and order long lead items - HVAC | 10.0 | 10.0 | 10.0 | 0.0 | 0.0 | 0.0 |
| 17 | Detail, fabricate and deliver steel | 60.0 | 60.0 | 60.0 | 0.0 | 0.0 | 0.0 |
| 19 | Install temporary power | 2.0 | 2.0 | 2.0 | 0.0 | 0.0 | 0.0 |
| 20 | Install temporary water service | 2.0 | 2.0 | 2.0 | 0.0 | 0.0 | 0.0 |
| 21 | Set up site office | 3.0 | 3.0 | 3.0 | 0.0 | 0.0 | 0.0 |
| 22 | Set line and grade benchmarks | 10.0 | 10.0 | 10.0 | 0.0 | 0.0 | 0.0 |
| 23 | Prepare site - lay down yard and temporary fencing | 2.0 | 2.0 | 2.0 | 0.0 | 0.0 | 0.0 |
| 25 | Clear and grub site | 3.0 | 3.0 | 3.0 | 0.0 | 0.0 | 0.0 |
| 26 | Stone site access and temporary parking area | 2.0 | 2.0 | 2.0 | 0.0 | 0.0 | 0.0 |
| 27 | Rough grade site (cut and fill) | 5.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 |
| 28 | Install storm drainage | 20.0 | 20.0 | 20.0 | 0.0 | 0.0 | 0.0 |
| 29 | Install exterior fire line and building fire riser | 43.0 | 43.0 | 43.0 | 0.0 | 0.0 | 0.0 |
| 30 | Perform final site grading | 10.0 | 10.0 | 10.0 | 0.0 | 0.0 | 0.0 |
| 31 | Erect building batter boards and layout building | 20.0 | 20.0 | 20.0 | 0.0 | 0.0 | 0.0 |
| 33 | Excavate foundations | 5.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 |
| 34 | Excavate elevator pit | 0.42 | 0.92 | 0.84 | 0.0 | 0.0 | 0.0 |
| 36 | Rough-in electric and plumbing in elevator | 2.66 | 4.94 | 3.8 | 0.0 | 0.0 | 0.0 |
| 37 | Form elevator pit walls | 2.64 | 4.9 | 3.77 | 0.0 | 0.0 | 0.0 |
| 40 | Pour concrete elevator walls | 0.93 | 1.55 | 1.04 | 0.0 | 0.0 | 0.0 |
| 41 | Cure elevator wall concrete | 5.36 | 9.96 | 7.66 | 0.0 | 0.0 | 0.0 |
| 43 | Strip wall forms | 1.0 | 1.0 | 1.0 | 0.0 | 0.0 | 0.0 |
| 45 | Install pneumatic tube in elevator pit | 1.91 | 3.83 | 3.19 | 0.0 | 0.0 | 0.0 |
| 46 | Prepare and pour concrete floor in elevator pit | 0.63 | 1.17 | 0.9 | 0.0 | 0.0 | 0.0 |
| 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | 20.0 | 37.14 | 28.57 | 0.0 | 0.0 | 0.0 |
| 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 2.7 | 5.94 | 5.4 | 0.0 | 0.0 | 0.0 |
| 59 | Strip forms from 2nd floor slab | 1.69 | 2.96 | 2.11 | 0.0 | 0.0 | 0.0 |
| 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 5.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 |
| 62 | Pour 3rd floor slab | 4.0 | 4.0 | 4.0 | 0.0 | 0.0 | 0.0 |
| 63 | Cure 3rd floor slab | 7.0 | 7.0 | 7.0 | 0.0 | 0.0 | 0.0 |
| 64 | Strip forms from 3rd floor slab | 1.88 | 3.29 | 2.35 | 0.0 | 0.0 | 0.0 |
| 65 | Form roof slab including all floor openings | 5.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 |
| 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 5.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 |
| 67 | Pour roof slab | 4.0 | 4.0 | 4.0 | 0.0 | 0.0 | 0.0 |
| 68 | Cure roof slab | 7.0 | 7.0 | 7.0 | 0.0 | 0.0 | 0.0 |
| 70 | Form 1st floor | 4.0 | 4.0 | 4.0 | 0.0 | 0.0 | 0.0 |
| 71 | Install electrical underground | 5.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 |
| 72 | Install plumbing underground | 5.69 | 9.47 | 6.32 | 0.0 | 0.0 | 0.0 |
| 73 | Install rebar and in-floor utilities | 4.0 | 4.0 | 4.0 | 0.0 | 0.0 | 0.0 |
| 74 | Pour 1st floor slab | 4.0 | 4.0 | 4.0 | 0.0 | 0.0 | 0.0 |
| 75 | Cure 1st floor slab | 7.0 | 7.0 | 7.0 | 0.0 | 0.0 | 0.0 |
| 76 | Strip forms from 1st floor slab | 2.0 | 2.0 | 2.0 | 0.0 | 0.0 | 0.0 |
| 78 | Install exterior sheathing and metal studs | 15.0 | 15.0 | 15.0 | 0.0 | 0.0 | 0.0 |
| 80 | Rough-in plumbing at toilets and masonry walls | 20.0 | 20.0 | 20.0 | 0.0 | 0.0 | 0.0 |
| 81 | Lay masonry at core, mechanical, and toilets | 13.94 | 25.88 | 19.91 | 0.0 | 0.0 | 0.0 |
| 82 | Install exterior masonry work | 25.0 | 25.0 | 25.0 | 0.0 | 0.0 | 0.0 |
| 83 | Install roof drains | 1.93 | 3.37 | 2.41 | 0.0 | 0.0 | 0.0 |
| 84 | Install tile in toilet rooms | 10.0 | 10.0 | 10.0 | 0.0 | 0.0 | 0.0 |
| 85 | Clean masonry | 5.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 |
| 86 | Clean toilet room tile | 5.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 |
| 88 | Install flashing at parapet walls | 4.0 | 4.0 | 4.0 | 0.0 | 0.0 | 0.0 |
| 89 | Pour lightweight concrete roof fill | 2.0 | 2.0 | 2.0 | 0.0 | 0.0 | 0.0 |
| 90 | Install seamless roofing material | 5.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 |
| 91 | Spread stone ballast on seamless roof | 5.0 | 5.0 | 5.0 | 0.0 | 0.0 | 0.0 |
| 92 | Set rooftop equipment | 10.0 | 10.0 | 10.0 | 0.0 | 0.0 | 0.0 |
| 94 | Install window wall aluminum and glass | 25.0 | 25.0 | 25.0 | 0.0 | 0.0 | 0.0 |
| 95 | Install interior stud walls and drywall | 25.0 | 25.0 | 25.0 | 0.0 | 0.0 | 0.0 |
| 96 | Install interior doors and hardware | 10.0 | 10.0 | 10.0 | 0.0 | 0.0 | 0.0 |
| 97 | Install store front doors and hardware | 15.0 | 15.0 | 15.0 | 0.0 | 0.0 | 0.0 |
| 99 | Install millwork and wood trim | 15.0 | 15.0 | 15.0 | 0.0 | 0.0 | 0.0 |
| 100 | Paint walls and woodwork | 20.0 | 20.0 | 20.0 | 0.0 | 0.0 | 0.0 |
| 101 | Install conduit at ceiling plenum space | 15.0 | 15.0 | 15.0 | 0.0 | 0.0 | 0.0 |
| 102 | Install duct in ceiling plenum space | 15.0 | 15.0 | 15.0 | 0.0 | 0.0 | 0.0 |
| 103 | Install ceiling grid | 10.0 | 10.0 | 10.0 | 0.0 | 0.0 | 0.0 |
| 104 | Install ceiling tile | 10.0 | 10.0 | 10.0 | 0.0 | 0.0 | 0.0 |
| 105 | Hang wallpaper | 10.0 | 10.0 | 10.0 | 0.0 | 0.0 | 0.0 |
| 108 | Complete interior and exterior sod and plantings | 3.91 | 7.83 | 6.52 | 0.0 | 0.0 | 0.0 |
| 109 | Pave, curb, and stripe parking lot | 10.0 | 10.0 | 10.0 | 0.0 | 0.0 | 0.0 |
| 111 | Set elevator equipment in shafts | 9.31 | 20.48 | 18.62 | 0.0 | 0.0 | 0.0 |
| 112 | Set equipment in mechanical room | 4.44 | 9.76 | 8.88 | 0.0 | 0.0 | 0.0 |
| 113 | Test and align doors and equipment | 5.52 | 11.04 | 9.2 | 0.0 | 0.0 | 0.0 |
| 115 | Rough-in plumbing in drywall walls | 16.04 | 29.78 | 22.91 | 0.0 | 0.0 | 0.0 |
| 116 | Tie-in fire line riser and set valves | 5.75 | 10.67 | 8.21 | 0.0 | 0.0 | 0.0 |
| 117 | Set plumbing fixtures and trim | 11.78 | 20.62 | 14.73 | 0.0 | 0.0 | 0.0 |
| 118 | Flush, test, and clean piping and fixtures | 5.06 | 11.12 | 10.11 | 0.0 | 0.0 | 0.0 |
| 120 | Rough-in electrical in masonry walls | 20.0 | 20.0 | 20.0 | 0.0 | 0.0 | 0.0 |
| 121 | Rough-in electrical in drywall walls | 20.0 | 20.0 | 20.0 | 0.0 | 0.0 | 0.0 |
| 122 | Pull wire in conduit and set area transformers | 15.0 | 15.0 | 15.0 | 0.0 | 0.0 | 0.0 |
| 123 | Install and terminate electrical devices | 15.0 | 15.0 | 15.0 | 0.0 | 0.0 | 0.0 |
| 124 | Make electrical terminations for HVAC equipment | 2.0 | 2.0 | 2.0 | 0.0 | 0.0 | 0.0 |
| 125 | Install light fixtures - test and clean | 10.0 | 10.0 | 10.0 | 0.0 | 0.0 | 0.0 |
| 127 | Set equipment in mechanical room | 10.0 | 10.0 | 10.0 | 0.0 | 0.0 | 0.0 |
| 128 | Rough-in mechanical in masonry walls | 13.97 | 25.94 | 19.96 | 0.0 | 0.0 | 0.0 |
| 129 | Rough-in mechanical in drywall walls | 8.71 | 15.25 | 10.89 | 0.0 | 0.0 | 0.0 |
| 130 | Install duct in building chase | 15.0 | 15.0 | 15.0 | 0.0 | 0.0 | 0.0 |
| 131 | Set HVAC trim and test and balance system | 9.9 | 21.77 | 19.79 | 0.0 | 0.0 | 0.0 |
| 133 | Install hard tile flooring in common areas | 4.0 | 7.0 | 5.0 | 0.0 | 0.0 | 0.0 |
| 134 | Clean hard tile floors | 1.54 | 3.38 | 3.07 | 0.0 | 0.0 | 0.0 |
| 136 | Substantial completion date | 1.0 | 1.0 | 1.0 | 0.0 | 0.0 | 0.0 |
| 138 | Complete elevator inspection and certification | 3.0 | 3.0 | 3.0 | 0.0 | 0.0 | 0.0 |
| 139 | Perform architect's inspection | 1.0 | 1.0 | 1.0 | 0.0 | 0.0 | 0.0 |
| 141 | Perform Fire Marshal's inspection | 1.0 | 1.0 | 1.0 | 0.0 | 0.0 | 0.0 |
| 143 | Obtain certificate of occupancy | 2.0 | 2.0 | 2.0 | 0.0 | 0.0 | 0.0 |
| 144 | Issue final completion documents including warranties | 1.0 | 1.0 | 1.0 | 0.0 | 0.0 | 0.0 |
| 145 | Issue final request for payment | 1.0 | 1.0 | 1.0 | 0.0 | 0.0 | 0.0 |

Per-task Best/Worst-case durations

The Risk Ranking Factor assigned to each ranked task and the Best/Worst-case durations derived from it (ML = current Remaining Duration), or entered manually.

| UID | Task | Factor | Best case d | Worst case d |
| --- | --- | --- | --- | --- |
| 3 | Receive notice to proceed and sign contract | 0 | 3.0 | 3.0 |
| 4 | Submit bond and insurance documents | 0 | 2.0 | 2.0 |
| 5 | Prepare and submit project schedule | 0 | 2.0 | 2.0 |
| 6 | Prepare and submit schedule of values | 0 | 2.0 | 2.0 |
| 7 | Obtain building permits | 0 | 4.0 | 4.0 |
| 8 | Submit preliminary shop drawings | 0 | 23.0 | 23.0 |
| 9 | Submit monthly requests for payment | 0 | 1.0 | 1.0 |
| 11 | Submit shop drawings and order long lead items - steel | 0 | 16.0 | 16.0 |
| 12 | Submit shop drawings and order long lead items - roofing | 0 | 19.0 | 19.0 |
| 13 | Submit shop drawings and order long lead items - elevator | 0 | 10.0 | 10.0 |
| 14 | Submit shop drawings and order long lead items - plumbing | 0 | 9.0 | 9.0 |
| 15 | Submit shop drawings and order long lead items - electric | 0 | 10.0 | 10.0 |
| 16 | Submit shop drawings and order long lead items - HVAC | 0 | 10.0 | 10.0 |
| 17 | Detail, fabricate and deliver steel | 0 | 60.0 | 60.0 |
| 19 | Install temporary power | 0 | 2.0 | 2.0 |
| 20 | Install temporary water service | 0 | 2.0 | 2.0 |
| 21 | Set up site office | 0 | 3.0 | 3.0 |
| 22 | Set line and grade benchmarks | 0 | 10.0 | 10.0 |
| 23 | Prepare site - lay down yard and temporary fencing | 0 | 2.0 | 2.0 |
| 25 | Clear and grub site | 0 | 3.0 | 3.0 |
| 26 | Stone site access and temporary parking area | 0 | 2.0 | 2.0 |
| 27 | Rough grade site (cut and fill) | 0 | 5.0 | 5.0 |
| 28 | Install storm drainage | 0 | 20.0 | 20.0 |
| 29 | Install exterior fire line and building fire riser | 0 | 43.0 | 43.0 |
| 30 | Perform final site grading | 0 | 10.0 | 10.0 |
| 31 | Erect building batter boards and layout building | 0 | 20.0 | 20.0 |
| 33 | Excavate foundations | 0 | 5.0 | 5.0 |
| 34 | Excavate elevator pit | 1 | 0.42 | 0.92 |
| 35 | Form column piers and spread foundations | 2 | 10.27 | 20.54 |
| 36 | Rough-in electric and plumbing in elevator | 3 | 2.66 | 4.94 |
| 37 | Form elevator pit walls | 3 | 2.64 | 4.9 |
| 38 | Set reinforcing and anchor bolts | 3 | 2.78 | 5.16 |
| 39 | Pour column piers and foundations | 5 | 20.58 | 34.31 |
| 40 | Pour concrete elevator walls | 5 | 0.93 | 1.55 |
| 41 | Cure elevator wall concrete | 3 | 5.36 | 9.96 |
| 42 | Cure piers and foundations | 4 | 6.36 | 11.13 |
| 43 | Strip wall forms | 0 | 1.0 | 1.0 |
| 44 | Strip column piers and foundation forms | 2 | 1.62 | 3.23 |
| 45 | Install pneumatic tube in elevator pit | 2 | 1.91 | 3.83 |
| 46 | Prepare and pour concrete floor in elevator pit | 3 | 0.63 | 1.17 |
| 48 | Erect steel columns, beams and joist - 1st and 2nd floors | 3 | 5.74 | 10.66 |
| 49 | Erect steel columns, beams and joist - 3rd floor and roof | 3 | 10.67 | 19.82 |
| 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | 3 | 20.0 | 37.14 |
| 51 | Install miscellaneous iron and bracing - 3rd floor and roof | 5 | 11.88 | 19.81 |
| 52 | Install stairs and miscellaneous iron railing | 5 | 11.84 | 19.73 |
| 53 | Touch-up paint on steel | 1 | 2.36 | 5.19 |
| 55 | Form 2nd floor including all floor openings | 1 | 5.2 | 11.45 |
| 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 1 | 2.7 | 5.94 |
| 57 | Pour 2nd floor slab | 3 | 2.53 | 4.7 |
| 58 | Cure 2nd floor slab | 3 | 5.84 | 10.85 |
| 59 | Strip forms from 2nd floor slab | 4 | 1.69 | 2.96 |
| 60 | Form 3rd floor including all floor openings | 2 | 3.29 | 6.57 |
| 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 0 | 5.0 | 5.0 |
| 62 | Pour 3rd floor slab | 0 | 4.0 | 4.0 |
| 63 | Cure 3rd floor slab | 0 | 7.0 | 7.0 |
| 64 | Strip forms from 3rd floor slab | 4 | 1.88 | 3.29 |
| 65 | Form roof slab including all floor openings | 0 | 5.0 | 5.0 |
| 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 0 | 5.0 | 5.0 |
| 67 | Pour roof slab | 0 | 4.0 | 4.0 |
| 68 | Cure roof slab | 0 | 7.0 | 7.0 |
| 69 | Strip forms from roof slab | 4 | 1.74 | 3.04 |
| 70 | Form 1st floor | 0 | 4.0 | 4.0 |
| 71 | Install electrical underground | 0 | 5.0 | 5.0 |
| 72 | Install plumbing underground | 5 | 5.69 | 9.47 |
| 73 | Install rebar and in-floor utilities | 0 | 4.0 | 4.0 |
| 74 | Pour 1st floor slab | 0 | 4.0 | 4.0 |
| 75 | Cure 1st floor slab | 0 | 7.0 | 7.0 |
| 76 | Strip forms from 1st floor slab | 0 | 2.0 | 2.0 |
| 78 | Install exterior sheathing and metal studs | 0 | 15.0 | 15.0 |
| 80 | Rough-in plumbing at toilets and masonry walls | 0 | 20.0 | 20.0 |
| 81 | Lay masonry at core, mechanical, and toilets | 3 | 13.94 | 25.88 |
| 82 | Install exterior masonry work | 0 | 25.0 | 25.0 |
| 83 | Install roof drains | 4 | 1.93 | 3.37 |
| 84 | Install tile in toilet rooms | 0 | 10.0 | 10.0 |
| 85 | Clean masonry | 0 | 5.0 | 5.0 |
| 86 | Clean toilet room tile | 0 | 5.0 | 5.0 |
| 88 | Install flashing at parapet walls | 0 | 4.0 | 4.0 |
| 89 | Pour lightweight concrete roof fill | 0 | 2.0 | 2.0 |
| 90 | Install seamless roofing material | 0 | 5.0 | 5.0 |
| 91 | Spread stone ballast on seamless roof | 0 | 5.0 | 5.0 |
| 92 | Set rooftop equipment | 0 | 10.0 | 10.0 |
| 94 | Install window wall aluminum and glass | 0 | 25.0 | 25.0 |
| 95 | Install interior stud walls and drywall | 0 | 25.0 | 25.0 |
| 96 | Install interior doors and hardware | 0 | 10.0 | 10.0 |
| 97 | Install store front doors and hardware | 0 | 15.0 | 15.0 |
| 99 | Install millwork and wood trim | 0 | 15.0 | 15.0 |
| 100 | Paint walls and woodwork | 0 | 20.0 | 20.0 |
| 101 | Install conduit at ceiling plenum space | 0 | 15.0 | 15.0 |
| 102 | Install duct in ceiling plenum space | 0 | 15.0 | 15.0 |
| 103 | Install ceiling grid | 0 | 10.0 | 10.0 |
| 104 | Install ceiling tile | 0 | 10.0 | 10.0 |
| 105 | Hang wallpaper | 0 | 10.0 | 10.0 |
| 106 | Install building carpet | 4 | 32.8 | 57.4 |
| 107 | Install hardware and accessories | 5 | 24.8 | 41.34 |
| 108 | Complete interior and exterior sod and plantings | 2 | 3.91 | 7.83 |
| 109 | Pave, curb, and stripe parking lot | 0 | 10.0 | 10.0 |
| 111 | Set elevator equipment in shafts | 1 | 9.31 | 20.48 |
| 112 | Set equipment in mechanical room | 1 | 4.44 | 9.76 |
| 113 | Test and align doors and equipment | 2 | 5.52 | 11.04 |
| 115 | Rough-in plumbing in drywall walls | 3 | 16.04 | 29.78 |
| 116 | Tie-in fire line riser and set valves | 3 | 5.75 | 10.67 |
| 117 | Set plumbing fixtures and trim | 4 | 11.78 | 20.62 |
| 118 | Flush, test, and clean piping and fixtures | 1 | 5.06 | 11.12 |
| 120 | Rough-in electrical in masonry walls | 0 | 20.0 | 20.0 |
| 121 | Rough-in electrical in drywall walls | 0 | 20.0 | 20.0 |
| 122 | Pull wire in conduit and set area transformers | 0 | 15.0 | 15.0 |
| 123 | Install and terminate electrical devices | 0 | 15.0 | 15.0 |
| 124 | Make electrical terminations for HVAC equipment | 0 | 2.0 | 2.0 |
| 125 | Install light fixtures - test and clean | 0 | 10.0 | 10.0 |
| 127 | Set equipment in mechanical room | 0 | 10.0 | 10.0 |
| 128 | Rough-in mechanical in masonry walls | 3 | 13.97 | 25.94 |
| 129 | Rough-in mechanical in drywall walls | 4 | 8.71 | 15.25 |
| 130 | Install duct in building chase | 0 | 15.0 | 15.0 |
| 131 | Set HVAC trim and test and balance system | 1 | 9.9 | 21.77 |
| 133 | Install hard tile flooring in common areas | 4 | 4.0 | 7.0 |
| 134 | Clean hard tile floors | 1 | 1.54 | 3.38 |
| 135 | Remove debris from building and do final clean-up | 2 | 1.93 | 3.86 |
| 136 | Substantial completion date | 0 | 1.0 | 1.0 |
| 138 | Complete elevator inspection and certification | 0 | 3.0 | 3.0 |
| 139 | Perform architect's inspection | 0 | 1.0 | 1.0 |
| 140 | Perform local building agency inspection | 5 | 1.29 | 2.15 |
| 141 | Perform Fire Marshal's inspection | 0 | 1.0 | 1.0 |
| 142 | Complete punch list items from all inspections | 4 | 10.98 | 19.21 |
| 143 | Obtain certificate of occupancy | 0 | 2.0 | 2.0 |
| 144 | Issue final completion documents including warranties | 0 | 1.0 | 1.0 |
| 145 | Issue final request for payment | 0 | 1.0 | 1.0 |

Risk / Opportunity register

Discrete risks and opportunities, each with its probability, additive schedule impact, simulated occurrence count, and 1-5 probability/consequence ratings.

| ID | Name | Probability % | Impact d | Affected | Consequence | Hits | Mean delta d |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | risk | 79.0 | 108.0 | 106 | 4 | 1601 | -0.1 |

Risk & Opportunity assessment matrices

Each event is placed by its Likelihood of Occurrence (rows, 1-5) and Consequence/Benefit of Occurrence (columns, 1-5). Each cell shows the NASA priority rank (1-25) and, in parentheses, the count of events that land there.

Risk Assessment Matrix

| L \ C | 1 Low | 2 Minor | 3 Moderate | 4 Significant | 5 Severe |
| --- | --- | --- | --- | --- | --- |
| 5 Near Certainty | 10 | 16 | 20 | 23 | 25 |
| 4 Highly Likely | 7 | 13 | 18 | 22 (1) | 24 |
| 3 Possible | 4 | 9 | 15 | 19 | 21 |
| 2 Unlikely | 2 | 6 | 11 | 14 | 17 |
| 1 Remote | 1 | 3 | 5 | 8 | 12 |

Opportunity Assessment Matrix

| L \ C | 1 Low | 2 Minor | 3 Moderate | 4 High | 5 Very High |
| --- | --- | --- | --- | --- | --- |
| 5 Near Certainty | 10 | 16 | 20 | 23 | 25 |
| 4 Highly Likely | 7 | 13 | 18 | 22 | 24 |
| 3 Possible | 4 | 9 | 15 | 19 | 21 |
| 2 Unlikely | 2 | 6 | 11 | 14 | 17 |
| 1 Remote | 1 | 3 | 5 | 8 | 12 |

Methodology & assumptions

Best/Worst-case durations use ML = the current Remaining Duration; BC = ML x (1 - subtract%/100), WC = ML x (1 + add%/100) with the per-factor percentages from the Risk Factors table. Occurrence mode: random_each. Correlation: 0. Risk register: on. Consequence (1-5) is auto-rated from the schedule impact via the NASA Schedule guideline (impact days converted to calendar months: <1 week=1, 1 week to <1 month=2, 1 to <3 months=3, 3 to <=6 months=4, >6 months=5).

The Best/Worst-case derivation and the deterministic one-at-a-time sensitivity are validated to match SSI Tools exactly. The stochastic distribution (S-curve, histogram, percentiles) uses a standard-library random generator that is statistically representative but NOT bit-identical to SSI's, so treat the P-values as close, not exact (ADR-0005/0106). All computation is local and offline; this document carries the CUI marking in its header and footer.