## Run setup
Field | Value
Focus event | 145 - Issue final request for payment
Occurrence mode | random_each
Correlation | 0
Risk register | on
Iterations | 2000
Schedule | Commercial Construction

## Per-task durations
UID | Task | Factor | Best case d | Worst case d
3 | Receive notice to proceed and sign contract | 0 | 3 | 3
4 | Submit bond and insurance documents | 0 | 2 | 2
5 | Prepare and submit project schedule | 0 | 2 | 2
6 | Prepare and submit schedule of values | 0 | 2 | 2
7 | Obtain building permits | 0 | 4 | 4
8 | Submit preliminary shop drawings | 0 | 23 | 23
9 | Submit monthly requests for payment | 0 | 1 | 1
11 | Submit shop drawings and order long lead items - steel | 0 | 16 | 16
12 | Submit shop drawings and order long lead items - roofing | 0 | 19 | 19
13 | Submit shop drawings and order long lead items - elevator | 0 | 10 | 10
14 | Submit shop drawings and order long lead items - plumbing | 0 | 9 | 9
15 | Submit shop drawings and order long lead items - electric | 0 | 10 | 10
16 | Submit shop drawings and order long lead items - HVAC | 0 | 10 | 10
17 | Detail, fabricate and deliver steel | 0 | 60 | 60
19 | Install temporary power | 0 | 2 | 2
20 | Install temporary water service | 0 | 2 | 2
21 | Set up site office | 0 | 3 | 3
22 | Set line and grade benchmarks | 0 | 10 | 10
23 | Prepare site - lay down yard and temporary fencing | 0 | 2 | 2
25 | Clear and grub site | 0 | 3 | 3
26 | Stone site access and temporary parking area | 0 | 2 | 2
27 | Rough grade site (cut and fill) | 0 | 5 | 5
28 | Install storm drainage | 0 | 20 | 20
29 | Install exterior fire line and building fire riser | 0 | 43 | 43
30 | Perform final site grading | 0 | 10 | 10
31 | Erect building batter boards and layout building | 0 | 20 | 20
33 | Excavate foundations | 0 | 5 | 5
34 | Excavate elevator pit | 1 | 0.42 | 0.92
35 | Form column piers and spread foundations | 2 | 10.27 | 20.54
36 | Rough-in electric and plumbing in elevator | 3 | 2.66 | 4.94
37 | Form elevator pit walls | 3 | 2.64 | 4.9
38 | Set reinforcing and anchor bolts | 3 | 2.78 | 5.16
39 | Pour column piers and foundations | 5 | 20.58 | 34.31
40 | Pour concrete elevator walls | 5 | 0.93 | 1.55
41 | Cure elevator wall concrete | 3 | 5.36 | 9.96
42 | Cure piers and foundations | 4 | 6.36 | 11.13
43 | Strip wall forms | 0 | 1 | 1
44 | Strip column piers and foundation forms | 2 | 1.62 | 3.23
45 | Install pneumatic tube in elevator pit | 2 | 1.91 | 3.83
46 | Prepare and pour concrete floor in elevator pit | 3 | 0.63 | 1.17
48 | Erect steel columns, beams and joist - 1st and 2nd floors | 3 | 5.74 | 10.66
49 | Erect steel columns, beams and joist - 3rd floor and roof | 3 | 10.67 | 19.82
50 | Install miscellaneous iron and bracing - 1st and 2nd floors | 3 | 20 | 37.14
51 | Install miscellaneous iron and bracing - 3rd floor and roof | 5 | 11.88 | 19.81
52 | Install stairs and miscellaneous iron railing | 5 | 11.84 | 19.73
53 | Touch-up paint on steel | 1 | 2.36 | 5.19
55 | Form 2nd floor including all floor openings | 1 | 5.2 | 11.45
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 1 | 2.7 | 5.94
57 | Pour 2nd floor slab | 3 | 2.53 | 4.7
58 | Cure 2nd floor slab | 3 | 5.84 | 10.85
59 | Strip forms from 2nd floor slab | 4 | 1.69 | 2.96
60 | Form 3rd floor including all floor openings | 2 | 3.29 | 6.57
61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 0 | 5 | 5
62 | Pour 3rd floor slab | 0 | 4 | 4
63 | Cure 3rd floor slab | 0 | 7 | 7
64 | Strip forms from 3rd floor slab | 4 | 1.88 | 3.29
65 | Form roof slab including all floor openings | 0 | 5 | 5
66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 0 | 5 | 5
67 | Pour roof slab | 0 | 4 | 4
68 | Cure roof slab | 0 | 7 | 7
69 | Strip forms from roof slab | 4 | 1.74 | 3.04
70 | Form 1st floor | 0 | 4 | 4
71 | Install electrical underground | 0 | 5 | 5
72 | Install plumbing underground | 5 | 5.69 | 9.47
73 | Install rebar and in-floor utilities | 0 | 4 | 4
74 | Pour 1st floor slab | 0 | 4 | 4
75 | Cure 1st floor slab | 0 | 7 | 7
76 | Strip forms from 1st floor slab | 0 | 2 | 2
78 | Install exterior sheathing and metal studs | 0 | 15 | 15
80 | Rough-in plumbing at toilets and masonry walls | 0 | 20 | 20
81 | Lay masonry at core, mechanical, and toilets | 3 | 13.94 | 25.88
82 | Install exterior masonry work | 0 | 25 | 25
83 | Install roof drains | 4 | 1.93 | 3.37
84 | Install tile in toilet rooms | 0 | 10 | 10
85 | Clean masonry | 0 | 5 | 5
86 | Clean toilet room tile | 0 | 5 | 5
88 | Install flashing at parapet walls | 0 | 4 | 4
89 | Pour lightweight concrete roof fill | 0 | 2 | 2
90 | Install seamless roofing material | 0 | 5 | 5
91 | Spread stone ballast on seamless roof | 0 | 5 | 5
92 | Set rooftop equipment | 0 | 10 | 10
94 | Install window wall aluminum and glass | 0 | 25 | 25
95 | Install interior stud walls and drywall | 0 | 25 | 25
96 | Install interior doors and hardware | 0 | 10 | 10
97 | Install store front doors and hardware | 0 | 15 | 15
99 | Install millwork and wood trim | 0 | 15 | 15
100 | Paint walls and woodwork | 0 | 20 | 20
101 | Install conduit at ceiling plenum space | 0 | 15 | 15
102 | Install duct in ceiling plenum space | 0 | 15 | 15
103 | Install ceiling grid | 0 | 10 | 10
104 | Install ceiling tile | 0 | 10 | 10
105 | Hang wallpaper | 0 | 10 | 10
106 | Install building carpet | 4 | 32.8 | 57.4
107 | Install hardware and accessories | 5 | 24.8 | 41.34
108 | Complete interior and exterior sod and plantings | 2 | 3.91 | 7.83
109 | Pave, curb, and stripe parking lot | 0 | 10 | 10
111 | Set elevator equipment in shafts | 1 | 9.31 | 20.48
112 | Set equipment in mechanical room | 1 | 4.44 | 9.76
113 | Test and align doors and equipment | 2 | 5.52 | 11.04
115 | Rough-in plumbing in drywall walls | 3 | 16.04 | 29.78
116 | Tie-in fire line riser and set valves | 3 | 5.75 | 10.67
117 | Set plumbing fixtures and trim | 4 | 11.78 | 20.62
118 | Flush, test, and clean piping and fixtures | 1 | 5.06 | 11.12
120 | Rough-in electrical in masonry walls | 0 | 20 | 20
121 | Rough-in electrical in drywall walls | 0 | 20 | 20
122 | Pull wire in conduit and set area transformers | 0 | 15 | 15
123 | Install and terminate electrical devices | 0 | 15 | 15
124 | Make electrical terminations for HVAC equipment | 0 | 2 | 2
125 | Install light fixtures - test and clean | 0 | 10 | 10
127 | Set equipment in mechanical room | 0 | 10 | 10
128 | Rough-in mechanical in masonry walls | 3 | 13.97 | 25.94
129 | Rough-in mechanical in drywall walls | 4 | 8.71 | 15.25
130 | Install duct in building chase | 0 | 15 | 15
131 | Set HVAC trim and test and balance system | 1 | 9.9 | 21.77
133 | Install hard tile flooring in common areas | 4 | 4 | 7
134 | Clean hard tile floors | 1 | 1.54 | 3.38
135 | Remove debris from building and do final clean-up | 2 | 1.93 | 3.86
136 | Substantial completion date | 0 | 1 | 1
138 | Complete elevator inspection and certification | 0 | 3 | 3
139 | Perform architect's inspection | 0 | 1 | 1
140 | Perform local building agency inspection | 5 | 1.29 | 2.15
141 | Perform Fire Marshal's inspection | 0 | 1 | 1
142 | Complete punch list items from all inspections | 4 | 10.98 | 19.21
143 | Obtain certificate of occupancy | 0 | 2 | 2
144 | Issue final completion documents including warranties | 0 | 1 | 1
145 | Issue final request for payment | 0 | 1 | 1

## Risk register
ID | Name | Probability % | Impact d | Affected | Consequence | Hits | Mean delta d
R1 | risk | 79 | 108 | 106 | 4 | 1601 | -0.1

## Focus-finish results
Measure | Value
Deterministic finish | 2027-12-03
Deterministic percentile | 10.8
P10 | 2027-11-30
P50 | 2027-12-13
P80 | 2027-12-21
P90 | 2027-12-26
Mean | 2027-12-13
Std deviation (working days) | 6.8

## OAT sensitivity
UID | Task | Best case d | Worst case d | ML d | Opportunity wd | Risk wd | Total wd
107 | Install hardware and accessories | 24.8 | 41.34 | 27.56 | 2.8 | 13.8 | 16.6
39 | Pour column piers and foundations | 20.58 | 34.31 | 22.87 | 2.3 | 11.4 | 13.7
35 | Form column piers and spread foundations | 10.27 | 20.54 | 17.11 | 6.8 | 3.4 | 10.2
49 | Erect steel columns, beams and joist - 3rd floor and roof | 10.67 | 19.82 | 15.25 | 4.6 | 4.6 | 9.2
142 | Complete punch list items from all inspections | 10.98 | 19.21 | 13.72 | 2.7 | 5.5 | 8.2
51 | Install miscellaneous iron and bracing - 3rd floor and roof | 11.88 | 19.81 | 13.2 | 1.3 | 6.6 | 7.9
52 | Install stairs and miscellaneous iron railing | 11.84 | 19.73 | 13.15 | 1.3 | 6.6 | 7.9
55 | Form 2nd floor including all floor openings | 5.2 | 11.45 | 10.41 | 5.2 | 1 | 6.2
48 | Erect steel columns, beams and joist - 1st and 2nd floors | 5.74 | 10.66 | 8.2 | 2.5 | 2.5 | 5
58 | Cure 2nd floor slab | 5.84 | 10.85 | 8.35 | 2.5 | 2.5 | 5
42 | Cure piers and foundations | 6.36 | 11.13 | 7.95 | 1.6 | 3.2 | 4.8
53 | Touch-up paint on steel | 2.36 | 5.19 | 4.71 | 2.4 | 0.5 | 2.9
38 | Set reinforcing and anchor bolts | 2.78 | 5.16 | 3.97 | 1.2 | 1.2 | 2.4
57 | Pour 2nd floor slab | 2.53 | 4.7 | 3.61 | 1.1 | 1.1 | 2.2
135 | Remove debris from building and do final clean-up | 1.93 | 3.86 | 3.22 | 1.3 | 0.6 | 1.9
44 | Strip column piers and foundation forms | 1.62 | 3.23 | 2.69 | 1.1 | 0.5 | 1.6
60 | Form 3rd floor including all floor openings | 3.29 | 6.57 | 5.47 | 0.5 | 1.1 | 1.6
69 | Strip forms from roof slab | 1.74 | 3.04 | 2.17 | 0.4 | 0.9 | 1.3
140 | Perform local building agency inspection | 1.29 | 2.15 | 1.44 | 0.1 | 0.7 | 0.8
3 | Receive notice to proceed and sign contract | 3 | 3 | 3 | 0 | 0 | 0
4 | Submit bond and insurance documents | 2 | 2 | 2 | 0 | 0 | 0
5 | Prepare and submit project schedule | 2 | 2 | 2 | 0 | 0 | 0
6 | Prepare and submit schedule of values | 2 | 2 | 2 | 0 | 0 | 0
7 | Obtain building permits | 4 | 4 | 4 | 0 | 0 | 0
8 | Submit preliminary shop drawings | 23 | 23 | 23 | 0 | 0 | 0
9 | Submit monthly requests for payment | 1 | 1 | 1 | 0 | 0 | 0
11 | Submit shop drawings and order long lead items - steel | 16 | 16 | 16 | 0 | 0 | 0
12 | Submit shop drawings and order long lead items - roofing | 19 | 19 | 19 | 0 | 0 | 0
13 | Submit shop drawings and order long lead items - elevator | 10 | 10 | 10 | 0 | 0 | 0
14 | Submit shop drawings and order long lead items - plumbing | 9 | 9 | 9 | 0 | 0 | 0
15 | Submit shop drawings and order long lead items - electric | 10 | 10 | 10 | 0 | 0 | 0
16 | Submit shop drawings and order long lead items - HVAC | 10 | 10 | 10 | 0 | 0 | 0
17 | Detail, fabricate and deliver steel | 60 | 60 | 60 | 0 | 0 | 0
19 | Install temporary power | 2 | 2 | 2 | 0 | 0 | 0
20 | Install temporary water service | 2 | 2 | 2 | 0 | 0 | 0
21 | Set up site office | 3 | 3 | 3 | 0 | 0 | 0
22 | Set line and grade benchmarks | 10 | 10 | 10 | 0 | 0 | 0
23 | Prepare site - lay down yard and temporary fencing | 2 | 2 | 2 | 0 | 0 | 0
25 | Clear and grub site | 3 | 3 | 3 | 0 | 0 | 0
26 | Stone site access and temporary parking area | 2 | 2 | 2 | 0 | 0 | 0
27 | Rough grade site (cut and fill) | 5 | 5 | 5 | 0 | 0 | 0
28 | Install storm drainage | 20 | 20 | 20 | 0 | 0 | 0
29 | Install exterior fire line and building fire riser | 43 | 43 | 43 | 0 | 0 | 0
30 | Perform final site grading | 10 | 10 | 10 | 0 | 0 | 0
31 | Erect building batter boards and layout building | 20 | 20 | 20 | 0 | 0 | 0
33 | Excavate foundations | 5 | 5 | 5 | 0 | 0 | 0
34 | Excavate elevator pit | 0.42 | 0.92 | 0.84 | 0 | 0 | 0
36 | Rough-in electric and plumbing in elevator | 2.66 | 4.94 | 3.8 | 0 | 0 | 0
37 | Form elevator pit walls | 2.64 | 4.9 | 3.77 | 0 | 0 | 0
40 | Pour concrete elevator walls | 0.93 | 1.55 | 1.04 | 0 | 0 | 0
41 | Cure elevator wall concrete | 5.36 | 9.96 | 7.66 | 0 | 0 | 0
43 | Strip wall forms | 1 | 1 | 1 | 0 | 0 | 0
45 | Install pneumatic tube in elevator pit | 1.91 | 3.83 | 3.19 | 0 | 0 | 0
46 | Prepare and pour concrete floor in elevator pit | 0.63 | 1.17 | 0.9 | 0 | 0 | 0
50 | Install miscellaneous iron and bracing - 1st and 2nd floors | 20 | 37.14 | 28.57 | 0 | 0 | 0
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 2.7 | 5.94 | 5.4 | 0 | 0 | 0
59 | Strip forms from 2nd floor slab | 1.69 | 2.96 | 2.11 | 0 | 0 | 0
61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 5 | 5 | 5 | 0 | 0 | 0
62 | Pour 3rd floor slab | 4 | 4 | 4 | 0 | 0 | 0
63 | Cure 3rd floor slab | 7 | 7 | 7 | 0 | 0 | 0
64 | Strip forms from 3rd floor slab | 1.88 | 3.29 | 2.35 | 0 | 0 | 0
65 | Form roof slab including all floor openings | 5 | 5 | 5 | 0 | 0 | 0
66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 5 | 5 | 5 | 0 | 0 | 0
67 | Pour roof slab | 4 | 4 | 4 | 0 | 0 | 0
68 | Cure roof slab | 7 | 7 | 7 | 0 | 0 | 0
70 | Form 1st floor | 4 | 4 | 4 | 0 | 0 | 0
71 | Install electrical underground | 5 | 5 | 5 | 0 | 0 | 0
72 | Install plumbing underground | 5.69 | 9.47 | 6.32 | 0 | 0 | 0
73 | Install rebar and in-floor utilities | 4 | 4 | 4 | 0 | 0 | 0
74 | Pour 1st floor slab | 4 | 4 | 4 | 0 | 0 | 0
75 | Cure 1st floor slab | 7 | 7 | 7 | 0 | 0 | 0
76 | Strip forms from 1st floor slab | 2 | 2 | 2 | 0 | 0 | 0
78 | Install exterior sheathing and metal studs | 15 | 15 | 15 | 0 | 0 | 0
80 | Rough-in plumbing at toilets and masonry walls | 20 | 20 | 20 | 0 | 0 | 0
81 | Lay masonry at core, mechanical, and toilets | 13.94 | 25.88 | 19.91 | 0 | 0 | 0
82 | Install exterior masonry work | 25 | 25 | 25 | 0 | 0 | 0
83 | Install roof drains | 1.93 | 3.37 | 2.41 | 0 | 0 | 0
84 | Install tile in toilet rooms | 10 | 10 | 10 | 0 | 0 | 0
85 | Clean masonry | 5 | 5 | 5 | 0 | 0 | 0
86 | Clean toilet room tile | 5 | 5 | 5 | 0 | 0 | 0
88 | Install flashing at parapet walls | 4 | 4 | 4 | 0 | 0 | 0
89 | Pour lightweight concrete roof fill | 2 | 2 | 2 | 0 | 0 | 0
90 | Install seamless roofing material | 5 | 5 | 5 | 0 | 0 | 0
91 | Spread stone ballast on seamless roof | 5 | 5 | 5 | 0 | 0 | 0
92 | Set rooftop equipment | 10 | 10 | 10 | 0 | 0 | 0
94 | Install window wall aluminum and glass | 25 | 25 | 25 | 0 | 0 | 0
95 | Install interior stud walls and drywall | 25 | 25 | 25 | 0 | 0 | 0
96 | Install interior doors and hardware | 10 | 10 | 10 | 0 | 0 | 0
97 | Install store front doors and hardware | 15 | 15 | 15 | 0 | 0 | 0
99 | Install millwork and wood trim | 15 | 15 | 15 | 0 | 0 | 0
100 | Paint walls and woodwork | 20 | 20 | 20 | 0 | 0 | 0
101 | Install conduit at ceiling plenum space | 15 | 15 | 15 | 0 | 0 | 0
102 | Install duct in ceiling plenum space | 15 | 15 | 15 | 0 | 0 | 0
103 | Install ceiling grid | 10 | 10 | 10 | 0 | 0 | 0
104 | Install ceiling tile | 10 | 10 | 10 | 0 | 0 | 0
105 | Hang wallpaper | 10 | 10 | 10 | 0 | 0 | 0
108 | Complete interior and exterior sod and plantings | 3.91 | 7.83 | 6.52 | 0 | 0 | 0
109 | Pave, curb, and stripe parking lot | 10 | 10 | 10 | 0 | 0 | 0
111 | Set elevator equipment in shafts | 9.31 | 20.48 | 18.62 | 0 | 0 | 0
112 | Set equipment in mechanical room | 4.44 | 9.76 | 8.88 | 0 | 0 | 0
113 | Test and align doors and equipment | 5.52 | 11.04 | 9.2 | 0 | 0 | 0
115 | Rough-in plumbing in drywall walls | 16.04 | 29.78 | 22.91 | 0 | 0 | 0
116 | Tie-in fire line riser and set valves | 5.75 | 10.67 | 8.21 | 0 | 0 | 0
117 | Set plumbing fixtures and trim | 11.78 | 20.62 | 14.73 | 0 | 0 | 0
118 | Flush, test, and clean piping and fixtures | 5.06 | 11.12 | 10.11 | 0 | 0 | 0
120 | Rough-in electrical in masonry walls | 20 | 20 | 20 | 0 | 0 | 0
121 | Rough-in electrical in drywall walls | 20 | 20 | 20 | 0 | 0 | 0
122 | Pull wire in conduit and set area transformers | 15 | 15 | 15 | 0 | 0 | 0
123 | Install and terminate electrical devices | 15 | 15 | 15 | 0 | 0 | 0
124 | Make electrical terminations for HVAC equipment | 2 | 2 | 2 | 0 | 0 | 0
125 | Install light fixtures - test and clean | 10 | 10 | 10 | 0 | 0 | 0
127 | Set equipment in mechanical room | 10 | 10 | 10 | 0 | 0 | 0
128 | Rough-in mechanical in masonry walls | 13.97 | 25.94 | 19.96 | 0 | 0 | 0
129 | Rough-in mechanical in drywall walls | 8.71 | 15.25 | 10.89 | 0 | 0 | 0
130 | Install duct in building chase | 15 | 15 | 15 | 0 | 0 | 0
131 | Set HVAC trim and test and balance system | 9.9 | 21.77 | 19.79 | 0 | 0 | 0
133 | Install hard tile flooring in common areas | 4 | 7 | 5 | 0 | 0 | 0
134 | Clean hard tile floors | 1.54 | 3.38 | 3.07 | 0 | 0 | 0
136 | Substantial completion date | 1 | 1 | 1 | 0 | 0 | 0
138 | Complete elevator inspection and certification | 3 | 3 | 3 | 0 | 0 | 0
139 | Perform architect's inspection | 1 | 1 | 1 | 0 | 0 | 0
141 | Perform Fire Marshal's inspection | 1 | 1 | 1 | 0 | 0 | 0
143 | Obtain certificate of occupancy | 2 | 2 | 2 | 0 | 0 | 0
144 | Issue final completion documents including warranties | 1 | 1 | 1 | 0 | 0 | 0
145 | Issue final request for payment | 1 | 1 | 1 | 0 | 0 | 0

## Risk matrix
Consequence \ Probability | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 1 | 0
3 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0

## Opportunity matrix
Consequence \ Probability | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0