## SRA-Large-Test-File2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
SRA Large Test File2 (3/10/2025 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2025-03-10
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 1 | 0%
| Wrong Status - Actual Finishes | F | 4 | 1%
| Invalid Forecast Dates | F | 338 | 34%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 4 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 3 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 122 | 12%
| Status Date | F | 2025-03-10
| High Float 44d | F | 717 | 72%
| Zero Days Float | F | 67 | 7%
| Hidden Duration (Planned) | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 2%
| Critical Merge Hotspot | F | 35 | 4%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Critical Diverge Hotspot | F | 22 | 2%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 354 | 35%
| Negative Float | F | 122 | 12%
| Tasks & Milestones (To Go) | F | 999 | 58%
| Milestones (To-Go) | F | 80 | 8%
| Normal Tasks (To-Go) | F | 919 | 92%
| Normal Tasks (To-Go, In Progress) | F | 92 | 9%
| Critical Path (Tasks & Milestones) | F | 186 | 19%
| Critical Path (Milestones) | F | 16 | 9%
| Critical Path (Normal Tasks) | F | 170 | 91%
| Critical Path (Normal In Progress) | F | 4 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11
| Negative Float | F | 122 | 12%
| Zero Days Float | F | 67 | 7%
| Near-Critical (<10 Days Float) | F | 243 | 24%
| CP Logic Density™ | F | 4.26
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1228
| BEI - Complete Tasks | F | 632 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| Status Date | F | 2025-03-10
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2028-03-06
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 0
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | 324 | 39%
| Status Date | F | 2025-03-10
| Total Activities | F | 2125
| Milestones | F | 170 | 8%
| Normal Tasks | F | 1553 | 73%
| Summaries | F | 402 | 19%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 1723 | 81%
| Completed Tasks & Milestones | F | 724 | 42%
| Completed Milestones | F | 90 | 53%
| Completed Tasks | F | 634 | 41%
| Total Activities (To-Go) - % of Total | F | 1285 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 999 | 78%
| Milestones (To-Go) | F | 80 | 6%
| Normal Tasks (To-Go) | F | 919 | 72%
| Summaries (To-Go) | F | 286 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 186 | 82%
| Longest Path (Normal Tasks) | F | 170 | 75%
| Longest Path (Milestones) | F | 16 | 7%
| Critical Milestones (To-Go) | F | 16 | 9%
| Critical Normal Tasks (To-Go) | F | 170 | 91%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 1543
| Scheduled to Start | F | 1553
| Actual Starts | F | 726
| Baselined to Finish | F | 1543
| Scheduled to Finish | F | 1553
| Actual Finishes | F | 634
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.49
| FEI - Value Task Finish - Cumulative | F | 2.75
| Current Baseline to Start & Started (BL Plan) | F | 723
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 820
| Current Baseline to Finish & Finished (BL Plan) | F | 632
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 911
| Duration Ratio Metric (DRM) | F | 608
| DRM Graph | F | 608
| Baselined to Start | F | 911
| Scheduled to Start | F | 919
| Baselined to Finish | F | 911
| Scheduled to Finish | F | 919
| BEI - Value Activities | F | 0.53
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 999 | 78%
| Critical Path To-Go | F | 186 | 19%
| Status Date | F | 2025-03-10
| Total Activities | F | 2125
| Milestones | F | 170 | 8%
| Normal Tasks | F | 1553 | 73%
| Summaries | F | 402 | 19%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 1723 | 81%
| Completed Tasks & Milestones | F | 724 | 42%
| Completed Milestones | F | 90 | 53%
| Completed Tasks | F | 634 | 41%
| Total Activities (To-Go) - % of Total | F | 1285 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 999 | 78%
| Milestones (To-Go) | F | 80 | 6%
| Normal Tasks (To-Go) | F | 919 | 72%
| Summaries (To-Go) | F | 286 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 186 | 82%
| Longest Path (Normal Tasks) | F | 170 | 75%
| Longest Path (Milestones) | F | 16 | 7%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2025-03-10
| Total Activities (To-Go) - % of Total | F | 1285 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 999 | 78%
| Summary-to-Task Ratio (To-Go) | F | 1:03 | 0.31
| Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 186 | 19%
| Wrong Status (To-Go) | F | 1 | 0%
| Invalid Forecast Dates | F | 338 | 34%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 999 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 999 | 78%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 4 | 0%
| Avg. Original Duration | F | 42
| Avg. Remaining Duration | F | 19
| High Baseline Duration (44d) | F | 86 | 9%
| High Planned Duration (44d) | F | 120 | 13%
| Insufficient Detail™ | F | 21 | 2%
| Critical Activities (To-Go) | F | 170 | 18%
| Avg. Critical Original Duration | F | 18
| Avg. Critical Remaining Duration | F | 12
| Critical w/High Baseline Duration (44d) | F | 4 | 0%
| Critical w/High Planned Duration (44d) | F | 6 | 4%
| Critical w/Insufficient Detail™ | F | 2 | 0%
| Activities (To-Go) | F | 919 | 59%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 3 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 999 | 100%
| No Constraints | F | 998 | 100%
| Logic Density™ | F | 3.15
| Logic Density™ - Predecessors | F | 1.78
| Logic Density™ - Successors | F | 1.37
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 906 | 100%
| SS Predecessors | F | 42 | 4%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 36 | 4%
| FS Predecessors | F | 995 | 100%
| All Activities w/Successors | F | 997 | 100%
| SS Successors | F | 42 | 4%
| FF Successors | F | 31 | 3%
| SF Successors | F | 0 | 0%
| FS Successors | F | 991 | 99%
| Missing Logic | F | 3 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 1 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.82
| All Activities w/Predecessors | F | 906 | 100%
| Total # Predecessors | F | 1650
| Activities Missing Predecessors | F | 1 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 2 | 0%
| Total # Predecessor Lags | F | 2
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 22
| Hidden Duration (Planned) | F | 2 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 123 | 14%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 35 | 4%
| Logic Hotspot™ | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 2%
| Logic Density™ - Successors | F | 1.37
| All Activities w/Successors | F | 997 | 100%
| Activities Missing Successors | F | 2 | 0%
| Total # Successors | F | 1365
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 8 | 1%
| Total# of Successor Lags | F | 8
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 72 | 7%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 22 | 2%
| Logic Hotspot™ | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 2%
| Actually Finished - Tasks & Milestones | F | 724 | 42%
| Completed Ahead - Tasks & Milestones | F | 55 | 8%
| Completed On-Schedule - Tasks & Milestones | F | 81 | 11%
| Completed Delayed - Tasks & Milestones | F | 585 | 81%
| Avg Days Finished Early - Tasks & Milestones | F | 24
| Avg Days Finished Late - Tasks & Milestones | F | 169
| Avg Finish Variance - Tasks & Milestones | F | 134
| Actually Finished - Tasks | F | 634 | 41%
| Completed Ahead - Tasks | F | 48 | 8%
| Completed On-Schedule - Tasks | F | 69 | 11%
| Completed Delayed - Tasks | F | 515 | 81%
| Accelerated Durations Early/On-Schedule - Tasks | F | 12 | 1%
| Accelerated Durations Late - Tasks | F | 105 | 7%
| Extended Durations - Tasks | F | 285 | 18%
| Actually Finished - Milestones | F | 90 | 53%
| Completed Ahead - Milestones | F | 7 | 8%
| Completed On-Schedule - Milestones | F | 12 | 13%
| Completed Delayed - Milestones | F | 70 | 78%
| Actually Started - Tasks | F | 92 | 6%
| In-Progress Started Ahead - Tasks | F | 8 | 9%
| In-Progress Started On-Schedule - Tasks | F | 15 | 16%
| In-Progress Started Delayed - Tasks | F | 68 | 74%
| In-Progress Delayed Finish - Tasks | F | 91 | 99%
| Avg Days Started Early | F | 16
| Avg Days Started Late | F | 118
| Avg Start Variance | F | 101
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 907 | 53%
| Planned Ahead Start - Tasks & Milestones | F | 97 | 11%
| Planned On Schedule Start - Tasks & Milestones | F | 1 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 798 | 88%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 827 | 53%
| Planned Ahead Start - Tasks | F | 89 | 11%
| Planned On Schedule Start - Tasks | F | 1 | 0%
| Planned Delayed Start - Tasks | F | 730 | 88%
| Planned Delayed Finish - Tasks | F | 731 | 88%
| Scheduled to Start - Milestones | F | 80 | 47%
| Planned Ahead Start - Milestones | F | 8 | 10%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 68 | 85%
| Planned Delayed Finish - Milestones | F | 68 | 85%
| Schedule Baseline Activities | F | 1708 | 99%
| Scheduled/Baselined to Start | F | 987
| Scheduled/Baselined to Finish | F | 987
| Start/ed | F | 816
| Finish/ed | F | 724
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 424 | 81%
| Completed Delayed (>30 days) | F | 443 | 86%
| SPI(t) | F | 8.14
| Scheduled Activities | F | 1723 | 100%
| Scheduled to Start | F | 999 | 58%
| Scheduled to Finish | F | 999 | 58%
| Longest Path - Critical Activities and Milestones | F | 186 | 19%
| Critical Milestones (To-Go) | F | 16 | 20%
| Critical Tasks (To-Go) | F | 170 | 18%
| Critical Tasks (In Progress) | F | 4 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| High Float 10% | F | 354 | 35%
| High Float 44d | F | 717 | 72%
| Zero Days Float | F | 67 | 7%
| Negative Float | F | 122 | 12%
| Longest Path - Critical Activities and Milestones | F | 186 | 19%
| Critical Milestones (To-Go) | F | 16 | 20%
| Critical Tasks (To-Go) | F | 170 | 18%
| Critical Tasks (In Progress) | F | 4 | 2%
| Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| Logic Density™ | F | 3.13
| CP Logic Density™ | F | 4.26
| Critical w/Missing Logic | F | 1 | 0%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 67 | 7%
| Negative Float | F | 122 | 12%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 4 | 0%
| Critical w/High Planned Duration (44d) | F | 6 | 4%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 1543
| Scheduled to Start | F | 1553
| Actual Starts | F | 726
| Baselined to Finish | F | 1543
| Scheduled to Finish | F | 1553
| Actual Finishes | F | 634
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| Baselined to Start | F | 1543
| Scheduled to Start | F | 1553
| Actual Starts | F | 726
| Current Baselined to Start & Started | F | 723
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 1543
| Scheduled to Finish | F | 1553
| Actual Finishes | F | 634
| Current Baselined to Finish & Finished | F | 632
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| Baselined to Start - To Time Now | F | 1247 | 81%
| Scheduled to Start - To Time Now | F | 1247 | 80%
| Started | F | 722
| Started Late | F | 522
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| BEI - Value Task Starts | F | 0.58
| Baselined to Finish - To Time Now | F | 1228 | 80%
| Scheduled to Finish - To Time Now | F | 1228 | 80%
| Finished | F | 632
| Finished Late | F | 515
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| BEI - Value Task Finishes | F | 0.51
| Started - Future | F | 1
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.49
| FEI - Value Task Finish - Cumulative | F | 2.75
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 723
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 820
| Baselined to Start - Check | F | 1543
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 632
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 911
| Baselined to Finish - Check | F | 1543
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 723
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 820
| Current Baseline to Finish & Finished (BL Plan) | F | 632
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 911
| Baselined to Start | F | 1247
| Scheduled to Start | F | 1247 | 100%
| Started - Scheduled | F | 722 | 58%
| Started - Baseline Comparison | F | 722 | 58%
| BEI - Value Task Starts | F | 0.58
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 1228
| Scheduled to Finish | F | 1228
| Finished | F | 632
| BEI - Value Task Finishes | F | 0.51
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2025-03-10
| Started (incl. Future Baseline Starts) - Scheduled | F | 726 | 47%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 723 | 47%
| Started Late (from Baseline) | F | 522
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 632 | 41%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 632 | 41%
| Finished Late | F | 515
| Completed Ahead | F | 48 | 8%
| Completed Delayed | F | 515 | 81%
| Completed On-Schedule | F | 69 | 11%
| Accelerated | F | 13 | 2%
| Days Variance | F | 91676 | 14460%
| Days Early | F | 1212 | 191%
| Days Late | F | 92888 | 14651%
| Avg Days Early | F | 25
| Avg Days Late | F | 180
| Avg Variance | F | 145
| Actually Finished | F | 634 | 37%
| Took Longer than Planned | F | 317 | 44%
| Took Less Than Planned | F | 160 | 22%
| Completed (w/Baseline Duration) | F | 608 | 39%
| Completed (w/o Baseline Duration) | F | 2 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 632 | 51%
| Missed Durations | F | 285 | 45%
| Missed Durations & Late Actual Finish | F | 267 | 42%
| Completed Ahead | F | 48 | 8%
| Completed Delayed | F | 515 | 81%
| Completed On-Schedule | F | 69 | 11%
| Accelerated | F | 13 | 2%
| Days Variance | F | 91676 | 14460%
| Days Early | F | 1212 | 191%
| Days Late | F | 92888 | 14651%
| Avg Days Early | F | 25
| Avg Days Late | F | 180
| Avg Variance | F | 145
| Actually Finished | F | 634 | 37%
| Took Longer than Planned | F | 317 | 44%
| Took Less Than Planned | F | 160 | 22%
| Completed (w/Baseline Duration) | F | 608 | 39%
| Completed (w/o Baseline Duration) | F | 2 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 632 | 51%
| Missed Durations | F | 285 | 45%
| Missed Durations & Late Actual Finish | F | 267 | 42%
| Baselined Tasks | F | 1543
| Baselined to Start - TOTAL | F | 1543
| Complete Task Starts - Cumulative | F | 722 | 58%
| Incomplete Task Starts - Cumulative (in work) | F | 525 | 42%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 1543
| Complete Task Finishes - Cumulative (in work) | F | 632 | 51%
| Incomplete Task Finishes - Cumulative | F | 596 | 51%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1228
| BEI - Complete Tasks | F | 632 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| BEI - Value Tasks (adjusted) | F | 0.51
| BEI - Complete Tasks (adjusted) | F | 632 | 51%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| BEI - Value Milestones | F | 0.69
| BEI - Total Milestones | F | 129
| BEI - Complete Milestones | F | 89 | 69%
| BEI - Incomplete Milestones | F | 40 | 31%
| BEI - Value Milestones (adjusted) | F | 0.69
| BEI - Complete Milestones (adjusted) | F | 89 | 69%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1228
| BEI - Incomplete Tasks | F | 596 | 49%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 89 | 69%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0.69
| BEI - Total Milestones | F | 129
| BEI - Complete Milestones | F | 89 | 69%
| BEI - Incomplete Milestones | F | 40 | 31%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.51
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0.69
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| Total Activities - DRM | F | 608
| Total Activities - DRM Graph | F | 608
| Status Date | F | 2025-03-10
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 0
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2028-03-06
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.49
| FEI - Value Task Finish - Cumulative | F | 2.75
| BEI - Value Tasks | F | 0.51
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0.69
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Complete Tasks | F | 632 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 1 | 0%
| Invalid Forecast Dates | F | 338 | 34%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 4 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 3 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 1 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 122 | 12%
| Status Date | F | 2025-03-10
| High Float 10% | F | 354 | 35%
| High Float 44d | F | 717 | 72%
| Zero Days Float | F | 67 | 7%
| Negative Float | F | 122 | 12%
| Hidden Duration (Planned) | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 2%
| Critical Merge Hotspot | F | 35 | 4%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Critical Diverge Hotspot | F | 22 | 2%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 170 | 75%
| Longest Path (Tasks & Milestones) | F | 186 | 82%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| Critical Milestones (To-Go) | F | 16 | 20%
| Longest Path (Milestones) | F | 16 | 7%
| Normal Tasks | F | 1553 | 73%
| Normal Tasks (To-Go) | F | 919 | 72%
| Critical Tasks (To-Go) | F | 170 | 18%
| Critical Tasks (In Progress) | F | 4 | 2%
| Zero Days Float | F | 67 | 7%
| Negative Float | F | 122 | 12%
| CP Logic Density™ | F | 4.26
| Time Now | F | 2025-03-10
| Forecast to be Finished | F | 1227 | 80%
| Completed On Time | T | 159 | 13%
| Completed Late | F | 581 | 47%
| Not Completed | F | 595 | 48%
| Baseline Finish Compliance | T | 13%
| Forecast to be Started | F | 1247 | 81%
| Started On Time | T | 250 | 20%
| Started Late | F | 605 | 49%
| Not Started | F | 525 | 42%
| Baseline Start Compliance | F | 26%
1 | Completed Activities | F | 630
HSD01 | Time Now | F | 2025-03-10
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 525 | 34%
HSD04 | Started Late | F | 605 | 49%
HSD05 | Forecast to be Finished but not Finished yet | T | 595 | 39%
HSD06 | Finished Late | F | 581 | 47%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2029-04-20
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 24 | 100%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.51
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | F | 1
SEM06 | BEI Cumulative | T | 0.51
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.42
SEM07 | To Go - Planned Task Starts - Count | T | 662
SEM07 | To Go - BEI - Task Finishes - Count | T | 766
SEM07 | To Go - Baselined Task Starts - Count | T | 655
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 398
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 263
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 492
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 279
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.42
SEM07 | To Go - Planned Task Starts - Count | T | 662
SEM07 | To Go - BEI - Task Finishes - Count | T | 766
SEM07 | To Go - Baselined Task Starts - Count | T | 655
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 661
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 398
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 263
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 771
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 492
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 279
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 398
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 263
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 492
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 279
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.42
SEM07 | To Go - Planned Task Starts - Count | T | 662
SEM07 | To Go - BEI - Task Finishes - Count | T | 766
SEM07 | To Go - Baselined Task Starts - Count | T | 655
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | TC-BEI | T | 2.45
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -1.91
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## TP4_DataCenter_v1
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v1 (1/30/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-01-30
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 1 | 8%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 8%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 8%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-01-30
| High Float 44d | F | 1 | 8%
| Zero Days Float | F | 8 | 62%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 8%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 1 | 8%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 2 | 15%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 13 | 87%
| Milestones (To-Go) | F | 1 | 8%
| Normal Tasks (To-Go) | F | 12 | 92%
| Normal Tasks (To-Go, In Progress) | F | 1 | 8%
| Critical Path (Tasks & Milestones) | F | 8 | 62%
| Critical Path (Milestones) | F | 1 | 13%
| Critical Path (Normal Tasks) | F | 7 | 88%
| Critical Path (Normal In Progress) | F | 1 | 13%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:07
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 8 | 62%
| Near-Critical (<10 Days Float) | F | 9 | 69%
| CP Logic Density™ | F | 3
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 1
| BEI - Total Tasks | F | 1
| BEI - Complete Tasks | F | 1 | 100%
| BEI - Incomplete Tasks | F | 0 | 0%
| Status Date | F | 2026-01-30
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-01-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-01-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-01-30
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 2 | 13%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 1 | 8%
| Total Activities (To-Go) - % of Total | F | 13 | 87%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 13 | 100%
| Milestones (To-Go) | F | 1 | 8%
| Normal Tasks (To-Go) | F | 12 | 92%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 8 | 100%
| Longest Path (Normal Tasks) | F | 7 | 88%
| Longest Path (Milestones) | F | 1 | 13%
| Critical Milestones (To-Go) | F | 1 | 13%
| Critical Normal Tasks (To-Go) | F | 7 | 88%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 2
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 1
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.67
| BEI - Value Task Finishes - Cumulative | F | 1
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Current Baseline to Start & Started (BL Plan) | F | 2
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 11
| Current Baseline to Finish & Finished (BL Plan) | F | 1
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 12
| Duration Ratio Metric (DRM) | F | 1
| DRM Graph | F | 1
| Baselined to Start | F | 12
| Scheduled to Start | F | 12
| Baselined to Finish | F | 12
| Scheduled to Finish | F | 12
| BEI - Value Activities | F | 1
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 13 | 100%
| Critical Path To-Go | F | 8 | 62%
| Status Date | F | 2026-01-30
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 2 | 13%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 1 | 8%
| Total Activities (To-Go) - % of Total | F | 13 | 87%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 13 | 100%
| Milestones (To-Go) | F | 1 | 8%
| Normal Tasks (To-Go) | F | 12 | 92%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 8 | 100%
| Longest Path (Normal Tasks) | F | 7 | 88%
| Longest Path (Milestones) | F | 1 | 13%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-01-30
| Total Activities (To-Go) - % of Total | F | 13 | 87%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 13 | 100%
| Summary-to-Task Ratio (To-Go) | F | N/A | 0
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.08
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:07 | 0.14
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 8 | 62%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 1 | 8%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 13 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 13 | 100%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 16
| Avg. Remaining Duration | F | 16
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 5 | 42%
| Critical Activities (To-Go) | F | 7 | 58%
| Avg. Critical Original Duration | F | 16
| Avg. Critical Remaining Duration | F | 16
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 3 | 25%
| Activities (To-Go) | F | 12 | 92%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 1 | 8%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 13 | 100%
| No Constraints | F | 13 | 100%
| Logic Density™ | F | 2.77
| Logic Density™ - Predecessors | F | 1.46
| Logic Density™ - Successors | F | 1.31
| Summary Links | F | N/A | 0%
| All Activities w/Predecessors | F | 12 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 13 | 100%
| All Activities w/Successors | F | 12 | 92%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 12 | 92%
| Missing Logic | F | 1 | 8%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 8%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.5
| All Activities w/Predecessors | F | 12 | 100%
| Total # Predecessors | F | 18
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 8%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 8%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.31
| All Activities w/Successors | F | 12 | 100%
| Activities Missing Successors | F | 1 | 8%
| Total # Successors | F | 17
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 1 | 8%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 1 | 8%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 2 | 13%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 2 | 100%
| Completed Delayed - Tasks & Milestones | F | 0 | 0%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 0
| Avg Finish Variance - Tasks & Milestones | F | 0
| Actually Finished - Tasks | F | 1 | 8%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 1 | 100%
| Completed Delayed - Tasks | F | 0 | 0%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 0 | 0%
| Actually Finished - Milestones | F | 1 | 50%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 1 | 100%
| Completed Delayed - Milestones | F | 0 | 0%
| Actually Started - Tasks | F | 1 | 8%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 1 | 100%
| In-Progress Started Delayed - Tasks | F | 0 | 0%
| In-Progress Delayed Finish - Tasks | F | 0 | 0%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 0
| Avg Start Variance | F | 0
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 12 | 80%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 12 | 100%
| Planned Delayed Start - Tasks & Milestones | F | 0 | 0%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 11 | 85%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 11 | 100%
| Planned Delayed Start - Tasks | F | 0 | 0%
| Planned Delayed Finish - Tasks | F | 0 | 0%
| Scheduled to Start - Milestones | F | 1 | 50%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 1 | 100%
| Planned Delayed Start - Milestones | F | 0 | 0%
| Planned Delayed Finish - Milestones | F | 0 | 0%
| Schedule Baseline Activities | F | 15 | 100%
| Scheduled/Baselined to Start | F | 13
| Scheduled/Baselined to Finish | F | 13
| Start/ed | F | 3
| Finish/ed | F | 2
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | 0.5
| Scheduled Activities | F | 15 | 100%
| Scheduled to Start | F | 13 | 87%
| Scheduled to Finish | F | 13 | 87%
| Longest Path - Critical Activities and Milestones | F | 8 | 62%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 7 | 58%
| Critical Tasks (In Progress) | F | 1 | 14%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:07 | 0.14
| High Float 10% | F | 2 | 15%
| High Float 44d | F | 1 | 8%
| Zero Days Float | F | 8 | 62%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 8 | 62%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 7 | 58%
| Critical Tasks (In Progress) | F | 1 | 14%
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.08
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:07 | 0.14
| Logic Density™ | F | 2.67
| CP Logic Density™ | F | 3
| Critical w/Missing Logic | F | 1 | 8%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 8 | 62%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 2
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 1
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 2
| Current Baselined to Start & Started | F | 2
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 1
| Current Baselined to Finish & Finished | F | 1
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | 3 | 23%
| Scheduled to Start - To Time Now | F | 3 | 23%
| Started | F | 2
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | 0.67
| Baselined to Finish - To Time Now | F | 1 | 8%
| Scheduled to Finish - To Time Now | F | 1 | 8%
| Finished | F | 1
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | 1
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.67
| BEI - Value Task Finishes - Cumulative | F | 1
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 2
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 11
| Baselined to Start - Check | F | 13
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 1
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 12
| Baselined to Finish - Check | F | 13
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 2
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 11
| Current Baseline to Finish & Finished (BL Plan) | F | 1
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 12
| Baselined to Start | F | 3
| Scheduled to Start | F | 3 | 100%
| Started - Scheduled | F | 2 | 67%
| Started - Baseline Comparison | F | 2 | 67%
| BEI - Value Task Starts | F | 0.67
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 1
| Scheduled to Finish | F | 1
| Finished | F | 1
| BEI - Value Task Finishes | F | 1
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-01-30
| Started (incl. Future Baseline Starts) - Scheduled | F | 2 | 15%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 2 | 15%
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 1 | 8%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 1 | 8%
| Finished Late | F | N/A
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 0 | 0%
| Completed On-Schedule | F | 1 | 100%
| Accelerated | F | 0 | 0%
| Days Variance | F | 0 | 0%
| Days Early | F | 0 | 0%
| Days Late | F | 0 | 0%
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 1 | 7%
| Took Longer than Planned | F | 0 | 0%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 1 | 8%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 1 | 100%
| Missed Durations | F | 0 | 0%
| Missed Durations & Late Actual Finish | F | 0 | 0%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 0 | 0%
| Completed On-Schedule | F | 1 | 100%
| Accelerated | F | 0 | 0%
| Days Variance | F | 0 | 0%
| Days Early | F | 0 | 0%
| Days Late | F | 0 | 0%
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 1 | 7%
| Took Longer than Planned | F | 0 | 0%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 1 | 8%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 1 | 100%
| Missed Durations | F | 0 | 0%
| Missed Durations & Late Actual Finish | F | 0 | 0%
| Baselined Tasks | F | 13
| Baselined to Start - TOTAL | F | 13
| Complete Task Starts - Cumulative | F | 2 | 67%
| Incomplete Task Starts - Cumulative (in work) | F | 1 | 33%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 13
| Complete Task Finishes - Cumulative (in work) | F | 1 | 100%
| Incomplete Task Finishes - Cumulative | F | 0 | 100%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 1
| BEI - Total Tasks | F | 1
| BEI - Complete Tasks | F | 1 | 100%
| BEI - Incomplete Tasks | F | 0 | 0%
| BEI - Value Tasks (adjusted) | F | 1
| BEI - Complete Tasks (adjusted) | F | 1 | 100%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-01-30
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| BEI - Value Milestones (adjusted) | F | 1
| BEI - Complete Milestones (adjusted) | F | 1 | 100%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-01-30
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-01-30
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-01-30
| BEI - Value Tasks | F | 1
| BEI - Total Tasks | F | 1
| BEI - Incomplete Tasks | F | 0 | 0%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 100%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 1
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 1
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-01-30
| Total Activities - DRM | F | 1
| Total Activities - DRM Graph | F | 1
| Status Date | F | 2026-01-30
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-01-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-01-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.67
| BEI - Value Task Finishes - Cumulative | F | 1
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| BEI - Value Tasks | F | 1
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 1
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 1
| BEI - Complete Tasks | F | 1 | 100%
| BEI - Incomplete Tasks | F | 0 | 0%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 1 | 8%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 8%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 8%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-01-30
| High Float 10% | F | 2 | 15%
| High Float 44d | F | 1 | 8%
| Zero Days Float | F | 8 | 62%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 8%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 1 | 8%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 7 | 88%
| Longest Path (Tasks & Milestones) | F | 8 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:07 | 0.14
| Critical Milestones (To-Go) | F | 1 | 100%
| Longest Path (Milestones) | F | 1 | 13%
| Normal Tasks | F | 13 | 87%
| Normal Tasks (To-Go) | F | 12 | 92%
| Critical Tasks (To-Go) | F | 7 | 58%
| Critical Tasks (In Progress) | F | 1 | 14%
| Zero Days Float | F | 8 | 62%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 3
| Time Now | F | 2026-01-30
| Forecast to be Finished | F | 1 | 8%
| Completed On Time | F | 1 | 100%
| Completed Late | F | 0 | 0%
| Not Completed | F | 0 | 0%
| Baseline Finish Compliance | F | 100%
| Forecast to be Started | F | 3 | 23%
| Started On Time | F | 3 | 100%
| Started Late | F | 0 | 0%
| Not Started | F | 1 | 33%
| Baseline Start Compliance | F | 100%
1 | Completed Activities | F | 1
HSD01 | Time Now | F | 2026-01-30
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 1 | 8%
HSD04 | Started Late | F | 0 | 0%
HSD05 | Forecast to be Finished but not Finished yet | F | 0 | 0%
HSD06 | Finished Late | F | 0 | 0%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-06-05
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 0 | 0%
SEM02 | BRI Current | F | 1
SEM03 | BRI Cumulative | F | 1
SEM04 | BPI Current | F | 1
SEM05 | BEI Current | F | 1
SEM06 | BEI Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 10
SEM07 | To Go - BEI - Task Finishes - Count | T | 12
SEM07 | To Go - Baselined Task Starts - Count | T | 10
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 10
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 12
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 10
SEM07 | To Go - BEI - Task Finishes - Count | T | 12
SEM07 | To Go - Baselined Task Starts - Count | T | 10
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 10
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 10
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 12
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 12
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 10
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 12
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 10
SEM07 | To Go - BEI - Task Finishes - Count | T | 12
SEM07 | To Go - Baselined Task Starts - Count | T | 10
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | TC-BEI | F | 1
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | 0
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## TP4_DataCenter_v2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v2 (2/27/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-02-27
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 9%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 9%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-02-27
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 64%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 13%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 1 | 9%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 11 | 73%
| Milestones (To-Go) | F | 1 | 9%
| Normal Tasks (To-Go) | F | 10 | 91%
| Normal Tasks (To-Go, In Progress) | F | 3 | 27%
| Critical Path (Tasks & Milestones) | F | 7 | 64%
| Critical Path (Milestones) | F | 1 | 14%
| Critical Path (Normal Tasks) | F | 6 | 86%
| Critical Path (Normal In Progress) | F | 1 | 14%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 7 | 64%
| Near-Critical (<10 Days Float) | F | 8 | 73%
| CP Logic Density™ | F | 2.86
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.75
| BEI - Total Tasks | F | 4
| BEI - Complete Tasks | F | 3 | 75%
| BEI - Incomplete Tasks | F | 1 | 25%
| Status Date | F | 2026-02-27
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-02-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-02-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-02-27
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 4 | 27%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 3 | 23%
| Total Activities (To-Go) - % of Total | F | 11 | 73%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 11 | 100%
| Milestones (To-Go) | F | 1 | 9%
| Normal Tasks (To-Go) | F | 10 | 91%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Milestones) | F | 1 | 14%
| Critical Milestones (To-Go) | F | 1 | 14%
| Critical Normal Tasks (To-Go) | F | 6 | 86%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 6
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 3
| Started Delayed (<=30 days) | F | 1 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | 1
| BEI - Value Task Finishes - Cumulative | F | 0.75
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1.1
| Current Baseline to Start & Started (BL Plan) | F | 6
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 7
| Current Baseline to Finish & Finished (BL Plan) | F | 3
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 10
| Duration Ratio Metric (DRM) | F | 3
| DRM Graph | F | 3
| Baselined to Start | F | 10
| Scheduled to Start | F | 10
| Baselined to Finish | F | 10
| Scheduled to Finish | F | 10
| BEI - Value Activities | F | 0.8
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 11 | 100%
| Critical Path To-Go | F | 7 | 64%
| Status Date | F | 2026-02-27
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 4 | 27%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 3 | 23%
| Total Activities (To-Go) - % of Total | F | 11 | 73%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 11 | 100%
| Milestones (To-Go) | F | 1 | 9%
| Normal Tasks (To-Go) | F | 10 | 91%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Milestones) | F | 1 | 14%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-02-27
| Total Activities (To-Go) - % of Total | F | 11 | 73%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 11 | 100%
| Summary-to-Task Ratio (To-Go) | F | N/A | 0
| Milestone-to-Task Ratio (To-Go) | F | 1:10 | 0.1
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 7 | 64%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 11 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 11 | 100%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 17
| Avg. Remaining Duration | F | 16
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 5 | 50%
| Critical Activities (To-Go) | F | 6 | 60%
| Avg. Critical Original Duration | F | 18
| Avg. Critical Remaining Duration | F | 17
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 3 | 30%
| Activities (To-Go) | F | 10 | 77%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 1 | 9%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 11 | 100%
| No Constraints | F | 11 | 100%
| Logic Density™ | F | 2.73
| Logic Density™ - Predecessors | F | 1.55
| Logic Density™ - Successors | F | 1.18
| Summary Links | F | N/A | 0%
| All Activities w/Predecessors | F | 8 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 11 | 100%
| All Activities w/Successors | F | 10 | 91%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 10 | 91%
| Missing Logic | F | 1 | 9%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 9%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.75
| All Activities w/Predecessors | F | 8 | 100%
| Total # Predecessors | F | 14
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 13%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 13%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.18
| All Activities w/Successors | F | 10 | 100%
| Activities Missing Successors | F | 1 | 9%
| Total # Successors | F | 13
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 4 | 27%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 4 | 100%
| Completed Delayed - Tasks & Milestones | F | 0 | 0%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 0
| Avg Finish Variance - Tasks & Milestones | F | 0
| Actually Finished - Tasks | F | 3 | 23%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 3 | 100%
| Completed Delayed - Tasks | F | 0 | 0%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 0 | 0%
| Actually Finished - Milestones | F | 1 | 50%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 1 | 100%
| Completed Delayed - Milestones | F | 0 | 0%
| Actually Started - Tasks | F | 3 | 23%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 2 | 67%
| In-Progress Started Delayed - Tasks | F | 1 | 33%
| In-Progress Delayed Finish - Tasks | F | 1 | 33%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 2
| Avg Start Variance | F | 2
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 8 | 53%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 8 | 100%
| Planned Delayed Start - Tasks & Milestones | F | 0 | 0%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 7 | 54%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 7 | 100%
| Planned Delayed Start - Tasks | F | 0 | 0%
| Planned Delayed Finish - Tasks | F | 0 | 0%
| Scheduled to Start - Milestones | F | 1 | 50%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 1 | 100%
| Planned Delayed Start - Milestones | F | 0 | 0%
| Planned Delayed Finish - Milestones | F | 0 | 0%
| Schedule Baseline Activities | F | 15 | 100%
| Scheduled/Baselined to Start | F | 11
| Scheduled/Baselined to Finish | F | 11
| Start/ed | F | 7
| Finish/ed | F | 4
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 0 | 0%
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | 0.5
| Scheduled Activities | F | 15 | 100%
| Scheduled to Start | F | 11 | 73%
| Scheduled to Finish | F | 11 | 73%
| Longest Path - Critical Activities and Milestones | F | 7 | 64%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 6 | 60%
| Critical Tasks (In Progress) | F | 1 | 17%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| High Float 10% | F | 1 | 9%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 64%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 7 | 64%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 6 | 60%
| Critical Tasks (In Progress) | F | 1 | 17%
| Milestone-to-Task Ratio (To-Go) | F | 1:10 | 0.1
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Logic Density™ | F | 2.67
| CP Logic Density™ | F | 2.86
| Critical w/Missing Logic | F | 1 | 9%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 7 | 64%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 6
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 3
| Started Delayed (<=30 days) | F | 1 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 6
| Current Baselined to Start & Started | F | 6
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 3
| Current Baselined to Finish & Finished | F | 3
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 1 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | 6 | 46%
| Scheduled to Start - To Time Now | F | 6 | 46%
| Started | F | 6
| Started Late | F | 1
| Started Delayed (<=30 days) | F | 1 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 1
| Baselined to Finish - To Time Now | F | 4 | 31%
| Scheduled to Finish - To Time Now | F | 4 | 31%
| Finished | F | 3
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | 0.75
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 1
| BEI - Value Task Finishes - Cumulative | F | 0.75
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1.1
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 6
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 7
| Baselined to Start - Check | F | 13
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 3
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 10
| Baselined to Finish - Check | F | 13
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 6
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 7
| Current Baseline to Finish & Finished (BL Plan) | F | 3
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 10
| Baselined to Start | F | 6
| Scheduled to Start | F | 6 | 100%
| Started - Scheduled | F | 6 | 100%
| Started - Baseline Comparison | F | 6 | 100%
| BEI - Value Task Starts | F | 1
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 4
| Scheduled to Finish | F | 4
| Finished | F | 3
| BEI - Value Task Finishes | F | 0.75
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-02-27
| Started (incl. Future Baseline Starts) - Scheduled | F | 6 | 46%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 6 | 46%
| Started Late (from Baseline) | F | 1
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 3 | 23%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 3 | 23%
| Finished Late | F | N/A
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 0 | 0%
| Completed On-Schedule | F | 3 | 100%
| Accelerated | F | 0 | 0%
| Days Variance | F | 0 | 0%
| Days Early | F | 0 | 0%
| Days Late | F | 0 | 0%
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 3 | 20%
| Took Longer than Planned | F | 0 | 0%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 3 | 23%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 3 | 75%
| Missed Durations | F | 0 | 0%
| Missed Durations & Late Actual Finish | F | 0 | 0%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 0 | 0%
| Completed On-Schedule | F | 3 | 100%
| Accelerated | F | 0 | 0%
| Days Variance | F | 0 | 0%
| Days Early | F | 0 | 0%
| Days Late | F | 0 | 0%
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 3 | 20%
| Took Longer than Planned | F | 0 | 0%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 3 | 23%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 3 | 75%
| Missed Durations | F | 0 | 0%
| Missed Durations & Late Actual Finish | F | 0 | 0%
| Baselined Tasks | F | 13
| Baselined to Start - TOTAL | F | 13
| Complete Task Starts - Cumulative | F | 6 | 100%
| Incomplete Task Starts - Cumulative (in work) | F | 0 | 0%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 13
| Complete Task Finishes - Cumulative (in work) | F | 3 | 75%
| Incomplete Task Finishes - Cumulative | F | 1 | 75%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.75
| BEI - Total Tasks | F | 4
| BEI - Complete Tasks | F | 3 | 75%
| BEI - Incomplete Tasks | F | 1 | 25%
| BEI - Value Tasks (adjusted) | F | 0.75
| BEI - Complete Tasks (adjusted) | F | 3 | 75%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-02-27
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| BEI - Value Milestones (adjusted) | F | 1
| BEI - Complete Milestones (adjusted) | F | 1 | 100%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-02-27
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-02-27
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-02-27
| BEI - Value Tasks | F | 0.75
| BEI - Total Tasks | F | 4
| BEI - Incomplete Tasks | F | 1 | 25%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 100%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.75
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 1
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-02-27
| Total Activities - DRM | F | 3
| Total Activities - DRM Graph | F | 3
| Status Date | F | 2026-02-27
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-02-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-02-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 1
| BEI - Value Task Finishes - Cumulative | F | 0.75
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1.1
| BEI - Value Tasks | F | 0.75
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 1
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.75
| BEI - Complete Tasks | F | 3 | 75%
| BEI - Incomplete Tasks | F | 1 | 25%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 9%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 9%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-02-27
| High Float 10% | F | 1 | 9%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 64%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 13%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Critical Milestones (To-Go) | F | 1 | 100%
| Longest Path (Milestones) | F | 1 | 14%
| Normal Tasks | F | 13 | 87%
| Normal Tasks (To-Go) | F | 10 | 91%
| Critical Tasks (To-Go) | F | 6 | 60%
| Critical Tasks (In Progress) | F | 1 | 17%
| Zero Days Float | F | 7 | 64%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.86
| Time Now | F | 2026-02-27
| Forecast to be Finished | F | 3 | 23%
| Completed On Time | F | 2 | 67%
| Completed Late | F | 0 | 0%
| Not Completed | F | 1 | 33%
| Baseline Finish Compliance | F | 67%
| Forecast to be Started | F | 6 | 46%
| Started On Time | F | 5 | 83%
| Started Late | F | 1 | 17%
| Not Started | F | 0 | 0%
| Baseline Start Compliance | F | 100%
1 | Completed Activities | F | 3
HSD01 | Time Now | F | 2026-02-27
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | 0 | 0%
HSD04 | Started Late | F | 1 | 17%
HSD05 | Forecast to be Finished but not Finished yet | T | 1 | 8%
HSD06 | Finished Late | F | 0 | 0%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-06-05
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 0 | 0%
SEM02 | BRI Current | F | 0.67
SEM03 | BRI Cumulative | F | 0.75
SEM04 | BPI Current | F | 0.67
SEM05 | BEI Current | T | 0.67
SEM06 | BEI Cumulative | T | 0.75
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.1
SEM07 | To Go - Planned Task Starts - Count | T | 7
SEM07 | To Go - BEI - Task Finishes - Count | T | 11
SEM07 | To Go - Baselined Task Starts - Count | T | 7
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 7
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 9
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.1
SEM07 | To Go - Planned Task Starts - Count | T | 7
SEM07 | To Go - BEI - Task Finishes - Count | T | 11
SEM07 | To Go - Baselined Task Starts - Count | T | 7
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 7
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 7
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 9
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 9
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 7
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 9
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.1
SEM07 | To Go - Planned Task Starts - Count | T | 7
SEM07 | To Go - BEI - Task Finishes - Count | T | 11
SEM07 | To Go - Baselined Task Starts - Count | T | 7
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | TC-BEI | T | 1.1
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.29
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## TP4_DataCenter_v3
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v3 (3/31/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-03-31
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 44%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-03-31
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 14%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 1 | 11%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 9 | 60%
| Milestones (To-Go) | F | 1 | 11%
| Normal Tasks (To-Go) | F | 8 | 89%
| Normal Tasks (To-Go, In Progress) | F | 2 | 22%
| Critical Path (Tasks & Milestones) | F | 7 | 78%
| Critical Path (Milestones) | F | 1 | 14%
| Critical Path (Normal Tasks) | F | 6 | 86%
| Critical Path (Normal In Progress) | F | 1 | 14%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Near-Critical (<10 Days Float) | F | 7 | 78%
| CP Logic Density™ | F | 2.86
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.71
| BEI - Total Tasks | F | 7
| BEI - Complete Tasks | F | 5 | 71%
| BEI - Incomplete Tasks | F | 2 | 29%
| Status Date | F | 2026-03-31
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-03-31
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 6 | 40%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 5 | 38%
| Total Activities (To-Go) - % of Total | F | 9 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Milestones (To-Go) | F | 1 | 11%
| Normal Tasks (To-Go) | F | 8 | 89%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Milestones) | F | 1 | 14%
| Critical Milestones (To-Go) | F | 1 | 14%
| Critical Normal Tasks (To-Go) | F | 6 | 86%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 7
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 5
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.78
| BEI - Value Task Finishes - Cumulative | F | 0.71
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Current Baseline to Start & Started (BL Plan) | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 6
| Current Baseline to Finish & Finished (BL Plan) | F | 5
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 8
| Duration Ratio Metric (DRM) | F | 5
| DRM Graph | F | 5
| Baselined to Start | F | 8
| Scheduled to Start | F | 8
| Baselined to Finish | F | 8
| Scheduled to Finish | F | 8
| BEI - Value Activities | F | 0.75
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Critical Path To-Go | F | 7 | 78%
| Status Date | F | 2026-03-31
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 6 | 40%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 5 | 38%
| Total Activities (To-Go) - % of Total | F | 9 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Milestones (To-Go) | F | 1 | 11%
| Normal Tasks (To-Go) | F | 8 | 89%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Milestones) | F | 1 | 14%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-03-31
| Total Activities (To-Go) - % of Total | F | 9 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Summary-to-Task Ratio (To-Go) | F | N/A | 0
| Milestone-to-Task Ratio (To-Go) | F | 1:08 | 0.13
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 7 | 78%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 44%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 9 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 18
| Avg. Remaining Duration | F | 16
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 4 | 50%
| Critical Activities (To-Go) | F | 6 | 75%
| Avg. Critical Original Duration | F | 18
| Avg. Critical Remaining Duration | F | 17
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 3 | 38%
| Activities (To-Go) | F | 8 | 62%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 1 | 11%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 9 | 100%
| No Constraints | F | 9 | 100%
| Logic Density™ | F | 2.78
| Logic Density™ - Predecessors | F | 1.67
| Logic Density™ - Successors | F | 1.11
| Summary Links | F | N/A | 0%
| All Activities w/Predecessors | F | 7 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 9 | 100%
| All Activities w/Successors | F | 8 | 89%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 8 | 89%
| Missing Logic | F | 1 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.86
| All Activities w/Predecessors | F | 7 | 100%
| Total # Predecessors | F | 13
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 14%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 14%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.11
| All Activities w/Successors | F | 8 | 100%
| Activities Missing Successors | F | 1 | 11%
| Total # Successors | F | 10
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 6 | 40%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 4 | 67%
| Completed Delayed - Tasks & Milestones | F | 2 | 33%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 4
| Avg Finish Variance - Tasks & Milestones | F | 1
| Actually Finished - Tasks | F | 5 | 38%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 3 | 60%
| Completed Delayed - Tasks | F | 2 | 40%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 1 | 8%
| Actually Finished - Milestones | F | 1 | 50%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 1 | 100%
| Completed Delayed - Milestones | F | 0 | 0%
| Actually Started - Tasks | F | 2 | 15%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 1 | 50%
| In-Progress Started Delayed - Tasks | F | 1 | 50%
| In-Progress Delayed Finish - Tasks | F | 1 | 50%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 4
| Avg Start Variance | F | 4
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 7 | 47%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 6 | 86%
| Planned Delayed Start - Tasks & Milestones | F | 1 | 14%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 6 | 46%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 5 | 83%
| Planned Delayed Start - Tasks | F | 1 | 17%
| Planned Delayed Finish - Tasks | F | 1 | 17%
| Scheduled to Start - Milestones | F | 1 | 50%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 1 | 100%
| Planned Delayed Start - Milestones | F | 0 | 0%
| Planned Delayed Finish - Milestones | F | 0 | 0%
| Schedule Baseline Activities | F | 15 | 100%
| Scheduled/Baselined to Start | F | 9
| Scheduled/Baselined to Finish | F | 9
| Start/ed | F | 8
| Finish/ed | F | 6
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 0 | 0%
| Completed Delayed (>30 days) | F | 0 | 0%
| SPI(t) | F | 0.67
| Scheduled Activities | F | 15 | 100%
| Scheduled to Start | F | 9 | 60%
| Scheduled to Finish | F | 9 | 60%
| Longest Path - Critical Activities and Milestones | F | 7 | 78%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 6 | 75%
| Critical Tasks (In Progress) | F | 1 | 17%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| High Float 10% | F | 1 | 11%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 7 | 78%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 6 | 75%
| Critical Tasks (In Progress) | F | 1 | 17%
| Milestone-to-Task Ratio (To-Go) | F | 1:08 | 0.13
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Logic Density™ | F | 2.67
| CP Logic Density™ | F | 2.86
| Critical w/Missing Logic | F | 1 | 11%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 7
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 5
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 7
| Current Baselined to Start & Started | F | 7
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 5
| Current Baselined to Finish & Finished | F | 5
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 9 | 69%
| Scheduled to Start - To Time Now | F | 9 | 69%
| Started | F | 7
| Started Late | F | 2
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 0.78
| Baselined to Finish - To Time Now | F | 7 | 54%
| Scheduled to Finish - To Time Now | F | 7 | 54%
| Finished | F | 5
| Finished Late | F | 2
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.71
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.78
| BEI - Value Task Finishes - Cumulative | F | 0.71
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 7
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 6
| Baselined to Start - Check | F | 13
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 5
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 8
| Baselined to Finish - Check | F | 13
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 6
| Current Baseline to Finish & Finished (BL Plan) | F | 5
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 8
| Baselined to Start | F | 9
| Scheduled to Start | F | 9 | 100%
| Started - Scheduled | F | 7 | 78%
| Started - Baseline Comparison | F | 7 | 78%
| BEI - Value Task Starts | F | 0.78
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 7
| Scheduled to Finish | F | 7
| Finished | F | 5
| BEI - Value Task Finishes | F | 0.71
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-03-31
| Started (incl. Future Baseline Starts) - Scheduled | F | 7 | 54%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 7 | 54%
| Started Late (from Baseline) | F | 2
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 5 | 38%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 5 | 38%
| Finished Late | F | 2
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 2 | 40%
| Completed On-Schedule | F | 3 | 60%
| Accelerated | F | 0 | 0%
| Days Variance | F | 8 | 160%
| Days Early | F | 0 | 0%
| Days Late | F | 8 | 160%
| Avg Days Early | F | 0
| Avg Days Late | F | 4
| Avg Variance | F | 2
| Actually Finished | F | 5 | 33%
| Took Longer than Planned | F | 2 | 33%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 5 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 5 | 71%
| Missed Durations | F | 1 | 20%
| Missed Durations & Late Actual Finish | F | 1 | 20%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 2 | 40%
| Completed On-Schedule | F | 3 | 60%
| Accelerated | F | 0 | 0%
| Days Variance | F | 8 | 160%
| Days Early | F | 0 | 0%
| Days Late | F | 8 | 160%
| Avg Days Early | F | 0
| Avg Days Late | F | 4
| Avg Variance | F | 2
| Actually Finished | F | 5 | 33%
| Took Longer than Planned | F | 2 | 33%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 5 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 5 | 71%
| Missed Durations | F | 1 | 20%
| Missed Durations & Late Actual Finish | F | 1 | 20%
| Baselined Tasks | F | 13
| Baselined to Start - TOTAL | F | 13
| Complete Task Starts - Cumulative | F | 7 | 78%
| Incomplete Task Starts - Cumulative (in work) | F | 2 | 22%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 13
| Complete Task Finishes - Cumulative (in work) | F | 5 | 71%
| Incomplete Task Finishes - Cumulative | F | 2 | 71%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.71
| BEI - Total Tasks | F | 7
| BEI - Complete Tasks | F | 5 | 71%
| BEI - Incomplete Tasks | F | 2 | 29%
| BEI - Value Tasks (adjusted) | F | 0.71
| BEI - Complete Tasks (adjusted) | F | 5 | 71%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| BEI - Value Milestones (adjusted) | F | 1
| BEI - Complete Milestones (adjusted) | F | 1 | 100%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| BEI - Value Tasks | F | 0.71
| BEI - Total Tasks | F | 7
| BEI - Incomplete Tasks | F | 2 | 29%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 100%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.71
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 1
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| Total Activities - DRM | F | 5
| Total Activities - DRM Graph | F | 5
| Status Date | F | 2026-03-31
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.78
| BEI - Value Task Finishes - Cumulative | F | 0.71
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| BEI - Value Tasks | F | 0.71
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 1
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.71
| BEI - Complete Tasks | F | 5 | 71%
| BEI - Incomplete Tasks | F | 2 | 29%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 44%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-03-31
| High Float 10% | F | 1 | 11%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 14%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Critical Milestones (To-Go) | F | 1 | 100%
| Longest Path (Milestones) | F | 1 | 14%
| Normal Tasks | F | 13 | 87%
| Normal Tasks (To-Go) | F | 8 | 89%
| Critical Tasks (To-Go) | F | 6 | 75%
| Critical Tasks (In Progress) | F | 1 | 17%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.86
| Time Now | F | 2026-03-31
| Forecast to be Finished | F | 7 | 54%
| Completed On Time | F | 4 | 57%
| Completed Late | F | 3 | 43%
| Not Completed | F | 2 | 29%
| Baseline Finish Compliance | F | 57%
| Forecast to be Started | F | 9 | 69%
| Started On Time | F | 6 | 67%
| Started Late | F | 3 | 33%
| Not Started | F | 2 | 22%
| Baseline Start Compliance | F | 100%
1 | Completed Activities | F | 5
HSD01 | Time Now | F | 2026-03-31
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 2 | 15%
HSD04 | Started Late | F | 3 | 33%
HSD05 | Forecast to be Finished but not Finished yet | T | 2 | 15%
HSD06 | Finished Late | F | 3 | 43%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-06-05
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 0 | 0%
SEM02 | BRI Current | F | 0.67
SEM03 | BRI Cumulative | F | 0.71
SEM04 | BPI Current | F | 0.67
SEM05 | BEI Current | T | 0.67
SEM06 | BEI Cumulative | T | 0.71
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 4
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 4
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 6
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 4
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Workoff Burden - Starts To-Go (Total) | F | 4
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | 4
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 6
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 6
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 4
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 6
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 4
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | TC-BEI | F | 1
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.25
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## TP4_DataCenter_v4
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v4 (4/30/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-04-30
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 57%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 14%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 14%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-04-30
| High Float 44d | F | 1 | 14%
| Zero Days Float | F | 5 | 71%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 20%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 2 | 29%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 7 | 47%
| Milestones (To-Go) | F | 1 | 14%
| Normal Tasks (To-Go) | F | 6 | 86%
| Normal Tasks (To-Go, In Progress) | F | 2 | 29%
| Critical Path (Tasks & Milestones) | F | 5 | 71%
| Critical Path (Milestones) | F | 1 | 20%
| Critical Path (Normal Tasks) | F | 4 | 80%
| Critical Path (Normal In Progress) | F | 2 | 40%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 5 | 71%
| Near-Critical (<10 Days Float) | F | 5 | 71%
| CP Logic Density™ | F | 2.6
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.78
| BEI - Total Tasks | F | 9
| BEI - Complete Tasks | F | 7 | 78%
| BEI - Incomplete Tasks | F | 2 | 22%
| Status Date | F | 2026-04-30
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-04-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-04-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-04-30
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 8 | 53%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 7 | 54%
| Total Activities (To-Go) - % of Total | F | 7 | 47%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Milestones (To-Go) | F | 1 | 14%
| Normal Tasks (To-Go) | F | 6 | 86%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 5 | 100%
| Longest Path (Normal Tasks) | F | 4 | 80%
| Longest Path (Milestones) | F | 1 | 20%
| Critical Milestones (To-Go) | F | 1 | 20%
| Critical Normal Tasks (To-Go) | F | 4 | 80%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 9
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 7
| Started Delayed (<=30 days) | F | 4 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.82
| BEI - Value Task Finishes - Cumulative | F | 0.78
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Current Baseline to Start & Started (BL Plan) | F | 9
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 4
| Current Baseline to Finish & Finished (BL Plan) | F | 7
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 6
| Duration Ratio Metric (DRM) | F | 7
| DRM Graph | F | 7
| Baselined to Start | F | 6
| Scheduled to Start | F | 6
| Baselined to Finish | F | 6
| Scheduled to Finish | F | 6
| BEI - Value Activities | F | 0.8
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Critical Path To-Go | F | 5 | 71%
| Status Date | F | 2026-04-30
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 8 | 53%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 7 | 54%
| Total Activities (To-Go) - % of Total | F | 7 | 47%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Milestones (To-Go) | F | 1 | 14%
| Normal Tasks (To-Go) | F | 6 | 86%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 5 | 100%
| Longest Path (Normal Tasks) | F | 4 | 80%
| Longest Path (Milestones) | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-04-30
| Total Activities (To-Go) - % of Total | F | 7 | 47%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Summary-to-Task Ratio (To-Go) | F | N/A | 0
| Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 5 | 71%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 57%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 7 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 17
| Avg. Remaining Duration | F | 16
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 3 | 50%
| Critical Activities (To-Go) | F | 4 | 67%
| Avg. Critical Original Duration | F | 16
| Avg. Critical Remaining Duration | F | 15
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 2 | 33%
| Activities (To-Go) | F | 6 | 46%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 1 | 14%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 7 | 100%
| No Constraints | F | 7 | 100%
| Logic Density™ | F | 2.57
| Logic Density™ - Predecessors | F | 1.71
| Logic Density™ - Successors | F | 0.86
| Summary Links | F | N/A | 0%
| All Activities w/Predecessors | F | 5 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 7 | 100%
| All Activities w/Successors | F | 6 | 86%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 6 | 86%
| Missing Logic | F | 1 | 14%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 14%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.8
| All Activities w/Predecessors | F | 5 | 100%
| Total # Predecessors | F | 9
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 20%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 20%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 0.86
| All Activities w/Successors | F | 6 | 100%
| Activities Missing Successors | F | 1 | 14%
| Total # Successors | F | 6
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 8 | 53%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 4 | 50%
| Completed Delayed - Tasks & Milestones | F | 4 | 50%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 13
| Avg Finish Variance - Tasks & Milestones | F | 6
| Actually Finished - Tasks | F | 7 | 54%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 3 | 43%
| Completed Delayed - Tasks | F | 4 | 57%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 2 | 15%
| Actually Finished - Milestones | F | 1 | 50%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 1 | 100%
| Completed Delayed - Milestones | F | 0 | 0%
| Actually Started - Tasks | F | 2 | 15%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 2 | 100%
| In-Progress Delayed Finish - Tasks | F | 2 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 21
| Avg Start Variance | F | 21
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 5 | 33%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 1 | 20%
| Planned Delayed Start - Tasks & Milestones | F | 4 | 80%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 4 | 31%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 1 | 25%
| Planned Delayed Start - Tasks | F | 3 | 75%
| Planned Delayed Finish - Tasks | F | 3 | 75%
| Scheduled to Start - Milestones | F | 1 | 50%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 1 | 100%
| Planned Delayed Finish - Milestones | F | 1 | 100%
| Schedule Baseline Activities | F | 15 | 100%
| Scheduled/Baselined to Start | F | 7
| Scheduled/Baselined to Finish | F | 7
| Start/ed | F | 10
| Finish/ed | F | 8
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 0 | 0%
| Completed Delayed (>30 days) | F | 0 | 0%
| SPI(t) | F | 0.7
| Scheduled Activities | F | 15 | 100%
| Scheduled to Start | F | 7 | 47%
| Scheduled to Finish | F | 7 | 47%
| Longest Path - Critical Activities and Milestones | F | 5 | 71%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 4 | 67%
| Critical Tasks (In Progress) | F | 2 | 50%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| High Float 10% | F | 2 | 29%
| High Float 44d | F | 1 | 14%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 5 | 71%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 4 | 67%
| Critical Tasks (In Progress) | F | 2 | 50%
| Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| Logic Density™ | F | 2.67
| CP Logic Density™ | F | 2.6
| Critical w/Missing Logic | F | 1 | 14%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 9
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 7
| Started Delayed (<=30 days) | F | 4 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 9
| Current Baselined to Start & Started | F | 9
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 7
| Current Baselined to Finish & Finished | F | 7
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 4 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 11 | 85%
| Scheduled to Start - To Time Now | F | 11 | 85%
| Started | F | 9
| Started Late | F | 4
| Started Delayed (<=30 days) | F | 4 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 0.82
| Baselined to Finish - To Time Now | F | 9 | 69%
| Scheduled to Finish - To Time Now | F | 9 | 69%
| Finished | F | 7
| Finished Late | F | 4
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.78
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.82
| BEI - Value Task Finishes - Cumulative | F | 0.78
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 9
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 4
| Baselined to Start - Check | F | 13
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 7
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 6
| Baselined to Finish - Check | F | 13
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 9
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 4
| Current Baseline to Finish & Finished (BL Plan) | F | 7
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 6
| Baselined to Start | F | 11
| Scheduled to Start | F | 11 | 100%
| Started - Scheduled | F | 9 | 82%
| Started - Baseline Comparison | F | 9 | 82%
| BEI - Value Task Starts | F | 0.82
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 9
| Scheduled to Finish | F | 9
| Finished | F | 7
| BEI - Value Task Finishes | F | 0.78
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-04-30
| Started (incl. Future Baseline Starts) - Scheduled | F | 9 | 69%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 9 | 69%
| Started Late (from Baseline) | F | 4
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 7 | 54%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 7 | 54%
| Finished Late | F | 4
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 4 | 57%
| Completed On-Schedule | F | 3 | 43%
| Accelerated | F | 0 | 0%
| Days Variance | F | 50 | 714%
| Days Early | F | 0 | 0%
| Days Late | F | 50 | 714%
| Avg Days Early | F | 0
| Avg Days Late | F | 13
| Avg Variance | F | 7
| Actually Finished | F | 7 | 47%
| Took Longer than Planned | F | 3 | 38%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 7 | 54%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 7 | 78%
| Missed Durations | F | 2 | 29%
| Missed Durations & Late Actual Finish | F | 2 | 29%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 4 | 57%
| Completed On-Schedule | F | 3 | 43%
| Accelerated | F | 0 | 0%
| Days Variance | F | 50 | 714%
| Days Early | F | 0 | 0%
| Days Late | F | 50 | 714%
| Avg Days Early | F | 0
| Avg Days Late | F | 13
| Avg Variance | F | 7
| Actually Finished | F | 7 | 47%
| Took Longer than Planned | F | 3 | 38%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 7 | 54%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 7 | 78%
| Missed Durations | F | 2 | 29%
| Missed Durations & Late Actual Finish | F | 2 | 29%
| Baselined Tasks | F | 13
| Baselined to Start - TOTAL | F | 13
| Complete Task Starts - Cumulative | F | 9 | 82%
| Incomplete Task Starts - Cumulative (in work) | F | 2 | 18%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 13
| Complete Task Finishes - Cumulative (in work) | F | 7 | 78%
| Incomplete Task Finishes - Cumulative | F | 2 | 78%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.78
| BEI - Total Tasks | F | 9
| BEI - Complete Tasks | F | 7 | 78%
| BEI - Incomplete Tasks | F | 2 | 22%
| BEI - Value Tasks (adjusted) | F | 0.78
| BEI - Complete Tasks (adjusted) | F | 7 | 78%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-04-30
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| BEI - Value Milestones (adjusted) | F | 1
| BEI - Complete Milestones (adjusted) | F | 1 | 100%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-04-30
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-04-30
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-04-30
| BEI - Value Tasks | F | 0.78
| BEI - Total Tasks | F | 9
| BEI - Incomplete Tasks | F | 2 | 22%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 100%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.78
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 1
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-04-30
| Total Activities - DRM | F | 7
| Total Activities - DRM Graph | F | 7
| Status Date | F | 2026-04-30
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-04-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-04-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.82
| BEI - Value Task Finishes - Cumulative | F | 0.78
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| BEI - Value Tasks | F | 0.78
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 1
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.78
| BEI - Complete Tasks | F | 7 | 78%
| BEI - Incomplete Tasks | F | 2 | 22%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 57%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 14%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 14%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-04-30
| High Float 10% | F | 2 | 29%
| High Float 44d | F | 1 | 14%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 20%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 4 | 80%
| Longest Path (Tasks & Milestones) | F | 5 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| Critical Milestones (To-Go) | F | 1 | 100%
| Longest Path (Milestones) | F | 1 | 20%
| Normal Tasks | F | 13 | 87%
| Normal Tasks (To-Go) | F | 6 | 86%
| Critical Tasks (To-Go) | F | 4 | 67%
| Critical Tasks (In Progress) | F | 2 | 50%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.6
| Time Now | F | 2026-04-30
| Forecast to be Finished | F | 9 | 69%
| Completed On Time | F | 4 | 44%
| Completed Late | F | 5 | 56%
| Not Completed | F | 2 | 22%
| Baseline Finish Compliance | F | 44%
| Forecast to be Started | F | 11 | 85%
| Started On Time | F | 6 | 55%
| Started Late | F | 5 | 45%
| Not Started | F | 2 | 18%
| Baseline Start Compliance | F | 91%
1 | Completed Activities | F | 7
HSD01 | Time Now | F | 2026-04-30
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 2 | 15%
HSD04 | Started Late | F | 5 | 45%
HSD05 | Forecast to be Finished but not Finished yet | T | 2 | 15%
HSD06 | Finished Late | F | 5 | 56%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-06-26
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 1 | 50%
SEM02 | BRI Current | F | 0.33
SEM03 | BRI Cumulative | F | 0.78
SEM04 | BPI Current | F | 0.33
SEM05 | BEI Current | T | 0.67
SEM06 | BEI Cumulative | T | 0.78
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 2
SEM07 | To Go - BEI - Task Finishes - Count | T | 4
SEM07 | To Go - Baselined Task Starts - Count | T | 2
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 2
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 2
SEM07 | To Go - BEI - Task Finishes - Count | T | 4
SEM07 | To Go - Baselined Task Starts - Count | T | 2
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Workoff Burden - Starts To-Go (Total) | F | 2
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | 2
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | 4
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 4
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 2
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 2
SEM07 | To Go - BEI - Task Finishes - Count | T | 4
SEM07 | To Go - Baselined Task Starts - Count | T | 2
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | TC-BEI | F | 1
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.2
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## TP4_DataCenter_v5
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v5 (5/29/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-05-29
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 57%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 14%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 14%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-05-29
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 5 | 71%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 25%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 7 | 47%
| Milestones (To-Go) | F | 1 | 14%
| Normal Tasks (To-Go) | F | 6 | 86%
| Normal Tasks (To-Go, In Progress) | F | 3 | 43%
| Critical Path (Tasks & Milestones) | F | 5 | 71%
| Critical Path (Milestones) | F | 1 | 20%
| Critical Path (Normal Tasks) | F | 4 | 80%
| Critical Path (Normal In Progress) | F | 1 | 20%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 5 | 71%
| Near-Critical (<10 Days Float) | F | 5 | 71%
| CP Logic Density™ | F | 2.6
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.58
| BEI - Total Tasks | F | 12
| BEI - Complete Tasks | F | 7 | 58%
| BEI - Incomplete Tasks | F | 5 | 42%
| Status Date | F | 2026-05-29
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-05-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-05-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-05-29
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 8 | 53%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 7 | 54%
| Total Activities (To-Go) - % of Total | F | 7 | 47%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Milestones (To-Go) | F | 1 | 14%
| Normal Tasks (To-Go) | F | 6 | 86%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 5 | 100%
| Longest Path (Normal Tasks) | F | 4 | 80%
| Longest Path (Milestones) | F | 1 | 20%
| Critical Milestones (To-Go) | F | 1 | 20%
| Critical Normal Tasks (To-Go) | F | 4 | 80%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 10
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 7
| Started Delayed (<=30 days) | F | 4 | 80%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 1 | 20%
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.77
| BEI - Value Task Finishes - Cumulative | F | 0.58
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | 3
| Current Baseline to Start & Started (BL Plan) | F | 10
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 3
| Current Baseline to Finish & Finished (BL Plan) | F | 7
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 6
| Duration Ratio Metric (DRM) | F | 7
| DRM Graph | F | 7
| Baselined to Start | F | 6
| Scheduled to Start | F | 6
| Baselined to Finish | F | 6
| Scheduled to Finish | F | 6
| BEI - Value Activities | F | 0.62
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Critical Path To-Go | F | 5 | 71%
| Status Date | F | 2026-05-29
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 8 | 53%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 7 | 54%
| Total Activities (To-Go) - % of Total | F | 7 | 47%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Milestones (To-Go) | F | 1 | 14%
| Normal Tasks (To-Go) | F | 6 | 86%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 5 | 100%
| Longest Path (Normal Tasks) | F | 4 | 80%
| Longest Path (Milestones) | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-05-29
| Total Activities (To-Go) - % of Total | F | 7 | 47%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Summary-to-Task Ratio (To-Go) | F | N/A | 0
| Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 5 | 71%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 57%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 7 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 17
| Avg. Remaining Duration | F | 14
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 3 | 50%
| Critical Activities (To-Go) | F | 4 | 67%
| Avg. Critical Original Duration | F | 15
| Avg. Critical Remaining Duration | F | 14
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 1 | 17%
| Activities (To-Go) | F | 6 | 46%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 1 | 14%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 7 | 100%
| No Constraints | F | 7 | 100%
| Logic Density™ | F | 2.57
| Logic Density™ - Predecessors | F | 1.71
| Logic Density™ - Successors | F | 0.86
| Summary Links | F | N/A | 0%
| All Activities w/Predecessors | F | 4 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 7 | 100%
| All Activities w/Successors | F | 6 | 86%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 6 | 86%
| Missing Logic | F | 1 | 14%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 14%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 2
| All Activities w/Predecessors | F | 4 | 100%
| Total # Predecessors | F | 8
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 25%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 25%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 0.86
| All Activities w/Successors | F | 6 | 100%
| Activities Missing Successors | F | 1 | 14%
| Total # Successors | F | 6
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 8 | 53%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 4 | 50%
| Completed Delayed - Tasks & Milestones | F | 4 | 50%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 13
| Avg Finish Variance - Tasks & Milestones | F | 6
| Actually Finished - Tasks | F | 7 | 54%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 3 | 43%
| Completed Delayed - Tasks | F | 4 | 57%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 2 | 15%
| Actually Finished - Milestones | F | 1 | 50%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 1 | 100%
| Completed Delayed - Milestones | F | 0 | 0%
| Actually Started - Tasks | F | 3 | 23%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 3 | 100%
| In-Progress Delayed Finish - Tasks | F | 3 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 44
| Avg Start Variance | F | 44
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 4 | 27%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 4 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 3 | 23%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 3 | 100%
| Planned Delayed Finish - Tasks | F | 3 | 100%
| Scheduled to Start - Milestones | F | 1 | 50%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 1 | 100%
| Planned Delayed Finish - Milestones | F | 1 | 100%
| Schedule Baseline Activities | F | 15 | 100%
| Scheduled/Baselined to Start | F | 7
| Scheduled/Baselined to Finish | F | 7
| Start/ed | F | 11
| Finish/ed | F | 8
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 1 | 20%
| Completed Delayed (>30 days) | F | 0 | 0%
| SPI(t) | F | 0.63
| Scheduled Activities | F | 15 | 100%
| Scheduled to Start | F | 7 | 47%
| Scheduled to Finish | F | 7 | 47%
| Longest Path - Critical Activities and Milestones | F | 5 | 71%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 4 | 67%
| Critical Tasks (In Progress) | F | 1 | 25%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| High Float 10% | F | 0 | 0%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 5 | 71%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 4 | 67%
| Critical Tasks (In Progress) | F | 1 | 25%
| Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| Logic Density™ | F | 2.67
| CP Logic Density™ | F | 2.6
| Critical w/Missing Logic | F | 1 | 14%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 10
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 7
| Started Delayed (<=30 days) | F | 4 | 80%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 1 | 20%
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 10
| Current Baselined to Start & Started | F | 10
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 7
| Current Baselined to Finish & Finished | F | 7
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 4 | 80%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 1 | 20%
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 13 | 100%
| Scheduled to Start - To Time Now | F | 13 | 100%
| Started | F | 10
| Started Late | F | 5
| Started Delayed (<=30 days) | F | 4 | 80%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 1 | 20%
| BEI - Value Task Starts | F | 0.77
| Baselined to Finish - To Time Now | F | 12 | 92%
| Scheduled to Finish - To Time Now | F | 12 | 92%
| Finished | F | 7
| Finished Late | F | 4
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.58
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.77
| BEI - Value Task Finishes - Cumulative | F | 0.58
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | 3
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 10
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 3
| Baselined to Start - Check | F | 13
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 7
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 6
| Baselined to Finish - Check | F | 13
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 10
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 3
| Current Baseline to Finish & Finished (BL Plan) | F | 7
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 6
| Baselined to Start | F | 13
| Scheduled to Start | F | 13 | 100%
| Started - Scheduled | F | 10 | 77%
| Started - Baseline Comparison | F | 10 | 77%
| BEI - Value Task Starts | F | 0.77
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 12
| Scheduled to Finish | F | 12
| Finished | F | 7
| BEI - Value Task Finishes | F | 0.58
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-05-29
| Started (incl. Future Baseline Starts) - Scheduled | F | 10 | 77%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 10 | 77%
| Started Late (from Baseline) | F | 5
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 7 | 54%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 7 | 54%
| Finished Late | F | 4
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 4 | 57%
| Completed On-Schedule | F | 3 | 43%
| Accelerated | F | 0 | 0%
| Days Variance | F | 50 | 714%
| Days Early | F | 0 | 0%
| Days Late | F | 50 | 714%
| Avg Days Early | F | 0
| Avg Days Late | F | 13
| Avg Variance | F | 7
| Actually Finished | F | 7 | 47%
| Took Longer than Planned | F | 3 | 38%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 7 | 54%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 7 | 58%
| Missed Durations | F | 2 | 29%
| Missed Durations & Late Actual Finish | F | 2 | 29%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 4 | 57%
| Completed On-Schedule | F | 3 | 43%
| Accelerated | F | 0 | 0%
| Days Variance | F | 50 | 714%
| Days Early | F | 0 | 0%
| Days Late | F | 50 | 714%
| Avg Days Early | F | 0
| Avg Days Late | F | 13
| Avg Variance | F | 7
| Actually Finished | F | 7 | 47%
| Took Longer than Planned | F | 3 | 38%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 7 | 54%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 7 | 58%
| Missed Durations | F | 2 | 29%
| Missed Durations & Late Actual Finish | F | 2 | 29%
| Baselined Tasks | F | 13
| Baselined to Start - TOTAL | F | 13
| Complete Task Starts - Cumulative | F | 10 | 77%
| Incomplete Task Starts - Cumulative (in work) | F | 3 | 23%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 13
| Complete Task Finishes - Cumulative (in work) | F | 7 | 58%
| Incomplete Task Finishes - Cumulative | F | 5 | 58%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.58
| BEI - Total Tasks | F | 12
| BEI - Complete Tasks | F | 7 | 58%
| BEI - Incomplete Tasks | F | 5 | 42%
| BEI - Value Tasks (adjusted) | F | 0.58
| BEI - Complete Tasks (adjusted) | F | 7 | 58%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-05-29
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| BEI - Value Milestones (adjusted) | F | 1
| BEI - Complete Milestones (adjusted) | F | 1 | 100%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-05-29
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-05-29
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-05-29
| BEI - Value Tasks | F | 0.58
| BEI - Total Tasks | F | 12
| BEI - Incomplete Tasks | F | 5 | 42%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 100%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.58
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 1
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-05-29
| Total Activities - DRM | F | 7
| Total Activities - DRM Graph | F | 7
| Status Date | F | 2026-05-29
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-05-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-05-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.77
| BEI - Value Task Finishes - Cumulative | F | 0.58
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | 3
| BEI - Value Tasks | F | 0.58
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 1
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.58
| BEI - Complete Tasks | F | 7 | 58%
| BEI - Incomplete Tasks | F | 5 | 42%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 57%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 14%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 14%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-05-29
| High Float 10% | F | 0 | 0%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 25%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 4 | 80%
| Longest Path (Tasks & Milestones) | F | 5 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| Critical Milestones (To-Go) | F | 1 | 100%
| Longest Path (Milestones) | F | 1 | 20%
| Normal Tasks | F | 13 | 87%
| Normal Tasks (To-Go) | F | 6 | 86%
| Critical Tasks (To-Go) | F | 4 | 67%
| Critical Tasks (In Progress) | F | 1 | 25%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.6
| Time Now | F | 2026-05-29
| Forecast to be Finished | F | 12 | 92%
| Completed On Time | F | 3 | 25%
| Completed Late | F | 7 | 58%
| Not Completed | F | 5 | 42%
| Baseline Finish Compliance | F | 25%
| Forecast to be Started | F | 13 | 100%
| Started On Time | F | 5 | 38%
| Started Late | F | 6 | 46%
| Not Started | F | 3 | 23%
| Baseline Start Compliance | F | 62%
1 | Completed Activities | F | 7
HSD01 | Time Now | F | 2026-05-29
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 3 | 23%
HSD04 | Started Late | F | 6 | 46%
HSD05 | Forecast to be Finished but not Finished yet | T | 5 | 38%
HSD06 | Finished Late | F | 7 | 58%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-07-17
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 0 | 0%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.58
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | T | 0
SEM06 | BEI Cumulative | T | 0.58
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 3
SEM07 | To Go - Planned Task Starts - Count | T | 2
SEM07 | To Go - BEI - Task Finishes - Count | T | 3
SEM07 | To Go - Baselined Task Starts - Count | T | 2
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 2
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 2
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 1
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 3
SEM07 | To Go - Planned Task Starts - Count | T | 2
SEM07 | To Go - BEI - Task Finishes - Count | T | 3
SEM07 | To Go - Baselined Task Starts - Count | T | 2
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | Workoff Burden - Starts To-Go (Total) | F | 2
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 2
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | 0
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | 3
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 2
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 1
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 2
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 2
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 1
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 3
SEM07 | To Go - Planned Task Starts - Count | T | 2
SEM07 | To Go - BEI - Task Finishes - Count | T | 3
SEM07 | To Go - Baselined Task Starts - Count | T | 2
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | TC-BEI | T | 3
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -1.38
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Project2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project2 (5/24/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-05-24
| Specific Task Start | F | 2027-06-17
| Specific Task Finish | F | 2027-07-14
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-05-24
| High Float 44d | F | 44 | 42%
| Zero Days Float | F | 41 | 39%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 2%
| Critical Merge Hotspot | F | 3 | 3%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 39 | 37%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 106 | 84%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 106 | 100%
| Normal Tasks (To-Go, In Progress) | F | 3 | 3%
| Critical Path (Tasks & Milestones) | F | 41 | 39%
| Critical Path (Milestones) | F | 0 | 0%
| Critical Path (Normal Tasks) | F | 41 | 100%
| Critical Path (Normal In Progress) | F | 1 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 41 | 39%
| Near-Critical (<10 Days Float) | F | 50 | 47%
| CP Logic Density™ | F | 3.2
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.74
| BEI - Total Tasks | F | 27
| BEI - Complete Tasks | F | 20 | 74%
| BEI - Incomplete Tasks | F | 7 | 26%
| Status Date | F | 2026-05-24
| Milestone #1 - 100 | F | 2027-06-17
| Float Milestone #1 - 100 | F | 0
| Milestone #2 - 101 | F | 2027-04-08
| Float to Milestone #2 - 101 | F | 15
| Milestone #3 - 102 | F | 2027-05-13
| Float to Milestone #3 - 102 | F | 10
| Milestone #4 - 103 | F | 2027-06-16
| Float to Milestone #4 - 103 | F | 10
| Milestone #5 - 104 | F | 2027-06-17
| Float to Milestone #5 - 104 | F | 30
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-05-24
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-05-24
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-05-24
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 20 | 16%
| Completed Milestones | F | 0
| Completed Tasks | F | 20 | 16%
| Total Activities (To-Go) - % of Total | F | 122 | 85%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 106 | 87%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 106 | 87%
| Summaries (To-Go) | F | 16 | 13%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 41 | 87%
| Longest Path (Normal Tasks) | F | 41 | 87%
| Longest Path (Milestones) | F | 0 | 0%
| Critical Milestones (To-Go) | F | 0 | 0%
| Critical Normal Tasks (To-Go) | F | 41 | 100%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 23
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 20
| Started Delayed (<=30 days) | F | 8 | 67%
| Started Delayed (Between 31 to 60 days) | F | 4 | 33%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 6 | 55%
| Completed Delayed (Between 31 to 60 days) | F | 5 | 45%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.79
| BEI - Value Task Finishes - Cumulative | F | 0.74
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.06
| FEI - Value Task Finish - Cumulative | F | 1.07
| Current Baseline to Start & Started (BL Plan) | F | 23
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 103
| Current Baseline to Finish & Finished (BL Plan) | F | 20
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 106
| Duration Ratio Metric (DRM) | F | 20
| DRM Graph | F | 20
| Baselined to Start | F | 106
| Scheduled to Start | F | 106
| Baselined to Finish | F | 106
| Scheduled to Finish | F | 106
| BEI - Value Activities | F | 0.74
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 106 | 87%
| Critical Path To-Go | F | 41 | 39%
| Status Date | F | 2026-05-24
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 20 | 16%
| Completed Milestones | F | 0
| Completed Tasks | F | 20 | 16%
| Total Activities (To-Go) - % of Total | F | 122 | 85%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 106 | 87%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 106 | 87%
| Summaries (To-Go) | F | 16 | 13%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 41 | 87%
| Longest Path (Normal Tasks) | F | 41 | 87%
| Longest Path (Milestones) | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-05-24
| Total Activities (To-Go) - % of Total | F | 122 | 85%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 106 | 87%
| Summary-to-Task Ratio (To-Go) | F | 1:07 | 0.15
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 41 | 39%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 106 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 106 | 87%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 9
| Avg. Remaining Duration | F | 9
| High Baseline Duration (44d) | F | 1 | 1%
| High Planned Duration (44d) | F | 1 | 1%
| Insufficient Detail™ | F | 1 | 1%
| Critical Activities (To-Go) | F | 41 | 39%
| Avg. Critical Original Duration | F | 9
| Avg. Critical Remaining Duration | F | 8
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 106 | 84%
| Total Constraints | F | 1 | 1%
| Start No Earlier Than | F | 1 | 1%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 4 | 4%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 105 | 99%
| No Constraints | F | 105 | 99%
| Logic Density™ | F | 2.81
| Logic Density™ - Predecessors | F | 1.45
| Logic Density™ - Successors | F | 1.36
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 103 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 1 | 1%
| FS Predecessors | F | 106 | 100%
| All Activities w/Successors | F | 102 | 96%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 102 | 96%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.47
| All Activities w/Predecessors | F | 103 | 100%
| Total # Predecessors | F | 151
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 2 | 2%
| Total # Predecessor Lags | F | 2
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 5
| Hidden Duration (Planned) | F | 1 | 1%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 10 | 10%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | 0 | 0%
| Critical Merge Hotspot | F | 3 | 3%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 2%
| Logic Density™ - Successors | F | 1.36
| All Activities w/Successors | F | 102 | 100%
| Activities Missing Successors | F | 4 | 4%
| Total # Successors | F | 144
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 1 | 1%
| Total# of Successor Lags | F | 1
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 11 | 10%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 2%
| Actually Finished - Tasks & Milestones | F | 20 | 16%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 9 | 45%
| Completed Delayed - Tasks & Milestones | F | 11 | 55%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 25
| Avg Finish Variance - Tasks & Milestones | F | 14
| Actually Finished - Tasks | F | 20 | 16%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 9 | 45%
| Completed Delayed - Tasks | F | 11 | 55%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 1 | 1%
| Extended Durations - Tasks | F | 4 | 3%
| Actually Finished - Milestones | F | 0
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 3 | 2%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 3 | 100%
| In-Progress Delayed Finish - Tasks | F | 3 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 24
| Avg Start Variance | F | 24
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 103 | 82%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 103 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 103 | 82%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 103 | 100%
| Planned Delayed Finish - Tasks | F | 103 | 100%
| Scheduled to Start - Milestones | F | 0
| Planned Ahead Start - Milestones | F | 0
| Planned On Schedule Start - Milestones | F | 0
| Planned Delayed Start - Milestones | F | 0
| Planned Delayed Finish - Milestones | F | 0
| Schedule Baseline Activities | F | 126 | 100%
| Scheduled/Baselined to Start | F | 106
| Scheduled/Baselined to Finish | F | 106
| Start/ed | F | 23
| Finish/ed | F | 20
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 4 | 33%
| Completed Delayed (>30 days) | F | 5 | 45%
| SPI(t) | F | 0.83
| Scheduled Activities | F | 126 | 100%
| Scheduled to Start | F | 106 | 84%
| Scheduled to Finish | F | 106 | 84%
| Longest Path - Critical Activities and Milestones | F | 41 | 39%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 41 | 39%
| Critical Tasks (In Progress) | F | 1 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| High Float 10% | F | 39 | 37%
| High Float 44d | F | 44 | 42%
| Zero Days Float | F | 41 | 39%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 41 | 39%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 41 | 39%
| Critical Tasks (In Progress) | F | 1 | 2%
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Logic Density™ | F | 2.79
| CP Logic Density™ | F | 3.2
| Critical w/Missing Logic | F | 1 | 4%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 41 | 39%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 1 | 2%
| Critical with Successor Lag | F | 1 | 2%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 1 | 2%
| Negative Float with Successor Lag | F | 1 | 2%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 23
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 20
| Started Delayed (<=30 days) | F | 8 | 67%
| Started Delayed (Between 31 to 60 days) | F | 4 | 33%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 6 | 55%
| Completed Delayed (Between 31 to 60 days) | F | 5 | 45%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 23
| Current Baselined to Start & Started | F | 23
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 20
| Current Baselined to Finish & Finished | F | 20
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 8 | 67%
| Started Delayed (Between 31 to 60 days) | F | 4 | 33%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 6 | 55%
| Completed Delayed (Between 31 to 60 days) | F | 5 | 45%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 29 | 23%
| Scheduled to Start - To Time Now | F | 29 | 23%
| Started | F | 23
| Started Late | F | 12
| Started Delayed (<=30 days) | F | 8 | 67%
| Started Delayed (Between 31 to 60 days) | F | 4 | 33%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 0.79
| Baselined to Finish - To Time Now | F | 27 | 21%
| Scheduled to Finish - To Time Now | F | 27 | 21%
| Finished | F | 20
| Finished Late | F | 11
| Completed Delayed (<=30 days) | F | 6 | 55%
| Completed Delayed (Between 31 to 60 days) | F | 5 | 45%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.74
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.79
| BEI - Value Task Finishes - Cumulative | F | 0.74
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.06
| FEI - Value Task Finish - Cumulative | F | 1.07
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 23
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 103
| Baselined to Start - Check | F | 126
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 20
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 106
| Baselined to Finish - Check | F | 126
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 23
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 103
| Current Baseline to Finish & Finished (BL Plan) | F | 20
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 106
| Baselined to Start | F | 29
| Scheduled to Start | F | 29 | 100%
| Started - Scheduled | F | 23 | 79%
| Started - Baseline Comparison | F | 23 | 79%
| BEI - Value Task Starts | F | 0.79
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 27
| Scheduled to Finish | F | 27
| Finished | F | 20
| BEI - Value Task Finishes | F | 0.74
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-05-24
| Started (incl. Future Baseline Starts) - Scheduled | F | 23 | 18%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 23 | 18%
| Started Late (from Baseline) | F | 12
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 20 | 16%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 20 | 16%
| Finished Late | F | 11
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 11 | 55%
| Completed On-Schedule | F | 9 | 45%
| Accelerated | F | 0 | 0%
| Days Variance | F | 277 | 1385%
| Days Early | F | 0 | 0%
| Days Late | F | 277 | 1385%
| Avg Days Early | F | 0
| Avg Days Late | F | 25
| Avg Variance | F | 14
| Actually Finished | F | 20 | 16%
| Took Longer than Planned | F | 4 | 20%
| Took Less Than Planned | F | 2 | 10%
| Completed (w/Baseline Duration) | F | 20 | 16%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 20 | 74%
| Missed Durations | F | 4 | 20%
| Missed Durations & Late Actual Finish | F | 4 | 20%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 11 | 55%
| Completed On-Schedule | F | 9 | 45%
| Accelerated | F | 0 | 0%
| Days Variance | F | 277 | 1385%
| Days Early | F | 0 | 0%
| Days Late | F | 277 | 1385%
| Avg Days Early | F | 0
| Avg Days Late | F | 25
| Avg Variance | F | 14
| Actually Finished | F | 20 | 16%
| Took Longer than Planned | F | 4 | 20%
| Took Less Than Planned | F | 2 | 10%
| Completed (w/Baseline Duration) | F | 20 | 16%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 20 | 74%
| Missed Durations | F | 4 | 20%
| Missed Durations & Late Actual Finish | F | 4 | 20%
| Baselined Tasks | F | 126
| Baselined to Start - TOTAL | F | 126
| Complete Task Starts - Cumulative | F | 23 | 79%
| Incomplete Task Starts - Cumulative (in work) | F | 6 | 21%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 126
| Complete Task Finishes - Cumulative (in work) | F | 20 | 74%
| Incomplete Task Finishes - Cumulative | F | 7 | 74%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.74
| BEI - Total Tasks | F | 27
| BEI - Complete Tasks | F | 20 | 74%
| BEI - Incomplete Tasks | F | 7 | 26%
| BEI - Value Tasks (adjusted) | F | 0.74
| BEI - Complete Tasks (adjusted) | F | 20 | 74%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-05-24
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-05-24
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-05-24
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-05-24
| BEI - Value Tasks | F | 0.74
| BEI - Total Tasks | F | 27
| BEI - Incomplete Tasks | F | 7 | 26%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.74
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-05-24
| Total Activities - DRM | F | 20
| Total Activities - DRM Graph | F | 20
| Status Date | F | 2026-05-24
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | 2027-05-13
| Float to Milestone #3 - 102 | F | 10
| Milestone #4 - 103 | F | 2027-06-02
| Float to Milestone #4 - 103 | F | 10
| Milestone #5 - 104 | F | 2027-07-15
| Float to Milestone #5 - 105 | F | 10
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-05-24
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-05-24
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.79
| BEI - Value Task Finishes - Cumulative | F | 0.74
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.06
| FEI - Value Task Finish - Cumulative | F | 1.07
| BEI - Value Tasks | F | 0.74
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.74
| BEI - Complete Tasks | F | 20 | 74%
| BEI - Incomplete Tasks | F | 7 | 26%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-05-24
| High Float 10% | F | 39 | 37%
| High Float 44d | F | 44 | 42%
| Zero Days Float | F | 41 | 39%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 2%
| Critical Merge Hotspot | F | 3 | 3%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 41 | 87%
| Longest Path (Tasks & Milestones) | F | 41 | 87%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestones (To-Go) | F | 0
| Longest Path (Milestones) | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Normal Tasks (To-Go) | F | 106 | 87%
| Critical Tasks (To-Go) | F | 41 | 39%
| Critical Tasks (In Progress) | F | 1 | 2%
| Zero Days Float | F | 41 | 39%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 3.2
| Time Now | F | 2026-05-24
| Forecast to be Finished | F | 27 | 21%
| Completed On Time | F | 9 | 33%
| Completed Late | F | 11 | 41%
| Not Completed | F | 7 | 26%
| Baseline Finish Compliance | F | 33%
| Forecast to be Started | F | 29 | 23%
| Started On Time | F | 11 | 38%
| Started Late | F | 12 | 41%
| Not Started | F | 6 | 21%
| Baseline Start Compliance | F | 41%
1 | Completed Activities | F | 20
HSD01 | Time Now | F | 2026-05-24
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 6 | 5%
HSD04 | Started Late | F | 12 | 41%
HSD05 | Forecast to be Finished but not Finished yet | T | 7 | 6%
HSD06 | Finished Late | F | 11 | 41%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2027-09-14
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 5 | 100%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.74
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | F | 1.25
SEM06 | BEI Cumulative | T | 0.74
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1.07
SEM07 | To Go - Planned Task Starts - Count | T | 103
SEM07 | To Go - BEI - Task Finishes - Count | T | 106
SEM07 | To Go - Baselined Task Starts - Count | T | 103
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 6
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 97
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 7
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 99
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1.07
SEM07 | To Go - Planned Task Starts - Count | T | 103
SEM07 | To Go - BEI - Task Finishes - Count | T | 106
SEM07 | To Go - Baselined Task Starts - Count | T | 103
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 103
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 6
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 97
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 106
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 7
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 99
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 6
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 97
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 7
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 99
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1.07
SEM07 | To Go - Planned Task Starts - Count | T | 103
SEM07 | To Go - BEI - Task Finishes - Count | T | 106
SEM07 | To Go - Baselined Task Starts - Count | T | 103
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | TC-BEI | F | 1.07
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.34
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Project5_TAMPERED
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED (8/27/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-08-27
| Specific Task Start | F | 2027-09-24
| Specific Task Finish | F | 2027-10-21
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 5 | 5%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 5 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-08-27
| High Float 44d | F | 44 | 44%
| Zero Days Float | F | 4 | 4%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 41 | 41%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 99 | 79%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 100%
| Normal Tasks (To-Go, In Progress) | F | 2 | 2%
| Critical Path (Tasks & Milestones) | F | 4 | 4%
| Critical Path (Milestones) | F | 0 | 0%
| Critical Path (Normal Tasks) | F | 4 | 100%
| Critical Path (Normal In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 4 | 4%
| Near-Critical (<10 Days Float) | F | 5 | 5%
| CP Logic Density™ | F | 3
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| Status Date | F | 2026-08-27
| Milestone #1 - 100 | F | 2027-09-24
| Float Milestone #1 - 100 | F | 19
| Milestone #2 - 101 | F | 2027-07-16
| Float to Milestone #2 - 101 | F | 36
| Milestone #3 - 102 | F | 2027-08-20
| Float to Milestone #3 - 102 | F | 35
| Milestone #4 - 103 | F | 2027-09-23
| Float to Milestone #4 - 103 | F | 35
| Milestone #5 - 104 | F | 2027-09-24
| Float to Milestone #5 - 104 | F | 55
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 27 | 21%
| Completed Milestones | F | 0
| Completed Tasks | F | 27 | 21%
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 88%
| Summaries (To-Go) | F | 14 | 12%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 4 | 100%
| Longest Path (Normal Tasks) | F | 4 | 100%
| Longest Path (Milestones) | F | 0 | 0%
| Critical Milestones (To-Go) | F | 0 | 0%
| Critical Normal Tasks (To-Go) | F | 4 | 100%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.24
| FEI - Value Task Finish - Cumulative | F | 1.24
| Current Baseline to Start & Started (BL Plan) | F | 29
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 97
| Current Baseline to Finish & Finished (BL Plan) | F | 27
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 99
| Duration Ratio Metric (DRM) | F | 27
| DRM Graph | F | 27
| Baselined to Start | F | 99
| Scheduled to Start | F | 99
| Baselined to Finish | F | 99
| Scheduled to Finish | F | 99
| BEI - Value Activities | F | 0.59
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Critical Path To-Go | F | 4 | 4%
| Status Date | F | 2026-08-27
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 27 | 21%
| Completed Milestones | F | 0
| Completed Tasks | F | 27 | 21%
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 88%
| Summaries (To-Go) | F | 14 | 12%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 4 | 100%
| Longest Path (Normal Tasks) | F | 4 | 100%
| Longest Path (Milestones) | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-08-27
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Summary-to-Task Ratio (To-Go) | F | 1:07 | 0.14
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 4 | 4%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 99 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 10
| Avg. Remaining Duration | F | 9
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 4 | 4%
| Avg. Critical Original Duration | F | 8
| Avg. Critical Remaining Duration | F | 8
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 99 | 79%
| Total Constraints | F | 3 | 3%
| Start No Earlier Than | F | 2 | 2%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 1 | 1%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 5 | 5%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 96 | 97%
| No Constraints | F | 96 | 97%
| Logic Density™ | F | 2.86
| Logic Density™ - Predecessors | F | 1.48
| Logic Density™ - Successors | F | 1.37
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 97 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 99 | 100%
| All Activities w/Successors | F | 94 | 95%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 94 | 95%
| Missing Logic | F | 5 | 5%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 5 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.49
| All Activities w/Predecessors | F | 97 | 100%
| Total # Predecessors | F | 145
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 1 | 1%
| Total # Predecessor Lags | F | 1
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 5
| Hidden Duration (Planned) | F | 1 | 1%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 10 | 10%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 1%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.37
| All Activities w/Successors | F | 94 | 100%
| Activities Missing Successors | F | 5 | 5%
| Total # Successors | F | 136
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 1 | 1%
| Total# of Successor Lags | F | 1
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 11 | 11%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 27 | 21%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 9 | 33%
| Completed Delayed - Tasks & Milestones | F | 18 | 67%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 39
| Avg Finish Variance - Tasks & Milestones | F | 26
| Actually Finished - Tasks | F | 27 | 21%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 9 | 33%
| Completed Delayed - Tasks | F | 18 | 67%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 2 | 2%
| Extended Durations - Tasks | F | 7 | 6%
| Actually Finished - Milestones | F | 0
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 2 | 2%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 2 | 100%
| In-Progress Delayed Finish - Tasks | F | 2 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 85
| Avg Start Variance | F | 85
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 97 | 77%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 97 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 97 | 77%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 97 | 100%
| Planned Delayed Finish - Tasks | F | 97 | 100%
| Scheduled to Start - Milestones | F | 0
| Planned Ahead Start - Milestones | F | 0
| Planned On Schedule Start - Milestones | F | 0
| Planned Delayed Start - Milestones | F | 0
| Planned Delayed Finish - Milestones | F | 0
| Schedule Baseline Activities | F | 126 | 100%
| Scheduled/Baselined to Start | F | 99
| Scheduled/Baselined to Finish | F | 99
| Start/ed | F | 29
| Finish/ed | F | 27
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 10 | 56%
| Completed Delayed (>30 days) | F | 11 | 61%
| SPI(t) | F | 0.91
| Scheduled Activities | F | 126 | 100%
| Scheduled to Start | F | 99 | 79%
| Scheduled to Finish | F | 99 | 79%
| Longest Path - Critical Activities and Milestones | F | 4 | 4%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 4 | 4%
| Critical Tasks (In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| High Float 10% | F | 41 | 41%
| High Float 44d | F | 44 | 44%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 4 | 4%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 4 | 4%
| Critical Tasks (In Progress) | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Logic Density™ | F | 2.81
| CP Logic Density™ | F | 3
| Critical w/Missing Logic | F | 1 | 5%
| Critical w/Hard Constraints | F | 1 | 1%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 1 | 1%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Current Baselined to Start & Started | F | 29
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Current Baselined to Finish & Finished | F | 27
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| Baselined to Start - To Time Now | F | 48 | 38%
| Scheduled to Start - To Time Now | F | 48 | 38%
| Started | F | 29
| Started Late | F | 18
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| BEI - Value Task Starts | F | 0.6
| Baselined to Finish - To Time Now | F | 46 | 37%
| Scheduled to Finish - To Time Now | F | 46 | 37%
| Finished | F | 27
| Finished Late | F | 18
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| BEI - Value Task Finishes | F | 0.59
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.24
| FEI - Value Task Finish - Cumulative | F | 1.24
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 29
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 97
| Baselined to Start - Check | F | 126
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 27
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 99
| Baselined to Finish - Check | F | 126
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 29
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 97
| Current Baseline to Finish & Finished (BL Plan) | F | 27
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 99
| Baselined to Start | F | 48
| Scheduled to Start | F | 48 | 100%
| Started - Scheduled | F | 29 | 60%
| Started - Baseline Comparison | F | 29 | 60%
| BEI - Value Task Starts | F | 0.6
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 46
| Scheduled to Finish | F | 46
| Finished | F | 27
| BEI - Value Task Finishes | F | 0.59
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-08-27
| Started (incl. Future Baseline Starts) - Scheduled | F | 29 | 23%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 29 | 23%
| Started Late (from Baseline) | F | 18
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 27 | 21%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 27 | 21%
| Finished Late | F | 18
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 18 | 67%
| Completed On-Schedule | F | 9 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | 705 | 2611%
| Days Early | F | 0 | 0%
| Days Late | F | 705 | 2611%
| Avg Days Early | F | 0
| Avg Days Late | F | 39
| Avg Variance | F | 26
| Actually Finished | F | 27 | 21%
| Took Longer than Planned | F | 7 | 26%
| Took Less Than Planned | F | 6 | 22%
| Completed (w/Baseline Duration) | F | 27 | 21%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 27 | 59%
| Missed Durations | F | 7 | 26%
| Missed Durations & Late Actual Finish | F | 7 | 26%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 18 | 67%
| Completed On-Schedule | F | 9 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | 705 | 2611%
| Days Early | F | 0 | 0%
| Days Late | F | 705 | 2611%
| Avg Days Early | F | 0
| Avg Days Late | F | 39
| Avg Variance | F | 26
| Actually Finished | F | 27 | 21%
| Took Longer than Planned | F | 7 | 26%
| Took Less Than Planned | F | 6 | 22%
| Completed (w/Baseline Duration) | F | 27 | 21%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 27 | 59%
| Missed Durations | F | 7 | 26%
| Missed Durations & Late Actual Finish | F | 7 | 26%
| Baselined Tasks | F | 126
| Baselined to Start - TOTAL | F | 126
| Complete Task Starts - Cumulative | F | 29 | 60%
| Incomplete Task Starts - Cumulative (in work) | F | 19 | 40%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 126
| Complete Task Finishes - Cumulative (in work) | F | 27 | 59%
| Incomplete Task Finishes - Cumulative | F | 19 | 59%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| BEI - Value Tasks (adjusted) | F | 0.59
| BEI - Complete Tasks (adjusted) | F | 27 | 59%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Incomplete Tasks | F | 19 | 41%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.59
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| Total Activities - DRM | F | 27
| Total Activities - DRM Graph | F | 27
| Status Date | F | 2026-08-27
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | 2027-08-20
| Float to Milestone #3 - 102 | F | 35
| Milestone #4 - 103 | F | 2027-09-09
| Float to Milestone #4 - 103 | F | 35
| Milestone #5 - 104 | F | 2027-10-22
| Float to Milestone #5 - 105 | F | 35
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.24
| FEI - Value Task Finish - Cumulative | F | 1.24
| BEI - Value Tasks | F | 0.59
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 5 | 5%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 5 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-08-27
| High Float 10% | F | 41 | 41%
| High Float 44d | F | 44 | 44%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 4 | 100%
| Longest Path (Tasks & Milestones) | F | 4 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestones (To-Go) | F | 0
| Longest Path (Milestones) | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Normal Tasks (To-Go) | F | 99 | 88%
| Critical Tasks (To-Go) | F | 4 | 4%
| Critical Tasks (In Progress) | F | 0 | 0%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 3
| Time Now | F | 2026-08-27
| Forecast to be Finished | F | 46 | 37%
| Completed On Time | T | 9 | 20%
| Completed Late | F | 18 | 39%
| Not Completed | F | 19 | 41%
| Baseline Finish Compliance | T | 20%
| Forecast to be Started | F | 48 | 38%
| Started On Time | T | 11 | 23%
| Started Late | F | 18 | 38%
| Not Started | F | 19 | 40%
| Baseline Start Compliance | F | 25%
1 | Completed Activities | F | 27
HSD01 | Time Now | F | 2026-08-27
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 19 | 15%
HSD04 | Started Late | F | 18 | 38%
HSD05 | Forecast to be Finished but not Finished yet | T | 19 | 15%
HSD06 | Finished Late | F | 18 | 39%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2028-01-26
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 2 | 100%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.59
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | T | 0.67
SEM06 | BEI Cumulative | T | 0.59
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.24
SEM07 | To Go - Planned Task Starts - Count | T | 97
SEM07 | To Go - BEI - Task Finishes - Count | T | 99
SEM07 | To Go - Baselined Task Starts - Count | T | 97
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 78
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 80
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.24
SEM07 | To Go - Planned Task Starts - Count | T | 97
SEM07 | To Go - BEI - Task Finishes - Count | T | 99
SEM07 | To Go - Baselined Task Starts - Count | T | 97
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 97
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 78
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 99
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 80
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 78
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 80
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.24
SEM07 | To Go - Planned Task Starts - Count | T | 97
SEM07 | To Go - BEI - Task Finishes - Count | T | 99
SEM07 | To Go - Baselined Task Starts - Count | T | 97
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | TC-BEI | T | 1.24
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.61
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Project2-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project2 2 (5/24/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-05-24
| Specific Task Start | F | 2027-06-17
| Specific Task Finish | F | 2027-07-14
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-05-24
| High Float 44d | F | 44 | 42%
| Zero Days Float | F | 41 | 39%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 2%
| Critical Merge Hotspot | F | 3 | 3%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 39 | 37%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 106 | 84%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 106 | 100%
| Normal Tasks (To-Go, In Progress) | F | 3 | 3%
| Critical Path (Tasks & Milestones) | F | 41 | 39%
| Critical Path (Milestones) | F | 0 | 0%
| Critical Path (Normal Tasks) | F | 41 | 100%
| Critical Path (Normal In Progress) | F | 1 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 41 | 39%
| Near-Critical (<10 Days Float) | F | 50 | 47%
| CP Logic Density™ | F | 3.2
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.74
| BEI - Total Tasks | F | 27
| BEI - Complete Tasks | F | 20 | 74%
| BEI - Incomplete Tasks | F | 7 | 26%
| Status Date | F | 2026-05-24
| Milestone #1 - 100 | F | 2027-06-17
| Float Milestone #1 - 100 | F | 0
| Milestone #2 - 101 | F | 2027-04-08
| Float to Milestone #2 - 101 | F | 15
| Milestone #3 - 102 | F | 2027-05-13
| Float to Milestone #3 - 102 | F | 10
| Milestone #4 - 103 | F | 2027-06-16
| Float to Milestone #4 - 103 | F | 10
| Milestone #5 - 104 | F | 2027-06-17
| Float to Milestone #5 - 104 | F | 30
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-05-24
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-05-24
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-05-24
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 20 | 16%
| Completed Milestones | F | 0
| Completed Tasks | F | 20 | 16%
| Total Activities (To-Go) - % of Total | F | 122 | 85%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 106 | 87%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 106 | 87%
| Summaries (To-Go) | F | 16 | 13%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 41 | 87%
| Longest Path (Normal Tasks) | F | 41 | 87%
| Longest Path (Milestones) | F | 0 | 0%
| Critical Milestones (To-Go) | F | 0 | 0%
| Critical Normal Tasks (To-Go) | F | 41 | 100%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 23
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 20
| Started Delayed (<=30 days) | F | 8 | 67%
| Started Delayed (Between 31 to 60 days) | F | 4 | 33%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 6 | 55%
| Completed Delayed (Between 31 to 60 days) | F | 5 | 45%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.79
| BEI - Value Task Finishes - Cumulative | F | 0.74
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.06
| FEI - Value Task Finish - Cumulative | F | 1.07
| Current Baseline to Start & Started (BL Plan) | F | 23
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 103
| Current Baseline to Finish & Finished (BL Plan) | F | 20
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 106
| Duration Ratio Metric (DRM) | F | 20
| DRM Graph | F | 20
| Baselined to Start | F | 106
| Scheduled to Start | F | 106
| Baselined to Finish | F | 106
| Scheduled to Finish | F | 106
| BEI - Value Activities | F | 0.74
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 106 | 87%
| Critical Path To-Go | F | 41 | 39%
| Status Date | F | 2026-05-24
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 20 | 16%
| Completed Milestones | F | 0
| Completed Tasks | F | 20 | 16%
| Total Activities (To-Go) - % of Total | F | 122 | 85%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 106 | 87%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 106 | 87%
| Summaries (To-Go) | F | 16 | 13%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 41 | 87%
| Longest Path (Normal Tasks) | F | 41 | 87%
| Longest Path (Milestones) | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-05-24
| Total Activities (To-Go) - % of Total | F | 122 | 85%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 106 | 87%
| Summary-to-Task Ratio (To-Go) | F | 1:07 | 0.15
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 41 | 39%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 106 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 106 | 87%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 9
| Avg. Remaining Duration | F | 9
| High Baseline Duration (44d) | F | 1 | 1%
| High Planned Duration (44d) | F | 1 | 1%
| Insufficient Detail™ | F | 1 | 1%
| Critical Activities (To-Go) | F | 41 | 39%
| Avg. Critical Original Duration | F | 9
| Avg. Critical Remaining Duration | F | 8
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 106 | 84%
| Total Constraints | F | 1 | 1%
| Start No Earlier Than | F | 1 | 1%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 4 | 4%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 105 | 99%
| No Constraints | F | 105 | 99%
| Logic Density™ | F | 2.81
| Logic Density™ - Predecessors | F | 1.45
| Logic Density™ - Successors | F | 1.36
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 103 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 1 | 1%
| FS Predecessors | F | 106 | 100%
| All Activities w/Successors | F | 102 | 96%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 102 | 96%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.47
| All Activities w/Predecessors | F | 103 | 100%
| Total # Predecessors | F | 151
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 2 | 2%
| Total # Predecessor Lags | F | 2
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 5
| Hidden Duration (Planned) | F | 1 | 1%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 10 | 10%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | 0 | 0%
| Critical Merge Hotspot | F | 3 | 3%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 2%
| Logic Density™ - Successors | F | 1.36
| All Activities w/Successors | F | 102 | 100%
| Activities Missing Successors | F | 4 | 4%
| Total # Successors | F | 144
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 1 | 1%
| Total# of Successor Lags | F | 1
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 11 | 10%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 2%
| Actually Finished - Tasks & Milestones | F | 20 | 16%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 9 | 45%
| Completed Delayed - Tasks & Milestones | F | 11 | 55%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 25
| Avg Finish Variance - Tasks & Milestones | F | 14
| Actually Finished - Tasks | F | 20 | 16%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 9 | 45%
| Completed Delayed - Tasks | F | 11 | 55%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 1 | 1%
| Extended Durations - Tasks | F | 4 | 3%
| Actually Finished - Milestones | F | 0
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 3 | 2%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 3 | 100%
| In-Progress Delayed Finish - Tasks | F | 3 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 24
| Avg Start Variance | F | 24
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 103 | 82%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 103 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 103 | 82%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 103 | 100%
| Planned Delayed Finish - Tasks | F | 103 | 100%
| Scheduled to Start - Milestones | F | 0
| Planned Ahead Start - Milestones | F | 0
| Planned On Schedule Start - Milestones | F | 0
| Planned Delayed Start - Milestones | F | 0
| Planned Delayed Finish - Milestones | F | 0
| Schedule Baseline Activities | F | 126 | 100%
| Scheduled/Baselined to Start | F | 106
| Scheduled/Baselined to Finish | F | 106
| Start/ed | F | 23
| Finish/ed | F | 20
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 4 | 33%
| Completed Delayed (>30 days) | F | 5 | 45%
| SPI(t) | F | 0.83
| Scheduled Activities | F | 126 | 100%
| Scheduled to Start | F | 106 | 84%
| Scheduled to Finish | F | 106 | 84%
| Longest Path - Critical Activities and Milestones | F | 41 | 39%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 41 | 39%
| Critical Tasks (In Progress) | F | 1 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| High Float 10% | F | 39 | 37%
| High Float 44d | F | 44 | 42%
| Zero Days Float | F | 41 | 39%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 41 | 39%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 41 | 39%
| Critical Tasks (In Progress) | F | 1 | 2%
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Logic Density™ | F | 2.79
| CP Logic Density™ | F | 3.2
| Critical w/Missing Logic | F | 1 | 4%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 41 | 39%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 1 | 2%
| Critical with Successor Lag | F | 1 | 2%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 1 | 2%
| Negative Float with Successor Lag | F | 1 | 2%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 23
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 20
| Started Delayed (<=30 days) | F | 8 | 67%
| Started Delayed (Between 31 to 60 days) | F | 4 | 33%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 6 | 55%
| Completed Delayed (Between 31 to 60 days) | F | 5 | 45%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 23
| Current Baselined to Start & Started | F | 23
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 20
| Current Baselined to Finish & Finished | F | 20
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 8 | 67%
| Started Delayed (Between 31 to 60 days) | F | 4 | 33%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 6 | 55%
| Completed Delayed (Between 31 to 60 days) | F | 5 | 45%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 29 | 23%
| Scheduled to Start - To Time Now | F | 29 | 23%
| Started | F | 23
| Started Late | F | 12
| Started Delayed (<=30 days) | F | 8 | 67%
| Started Delayed (Between 31 to 60 days) | F | 4 | 33%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 0.79
| Baselined to Finish - To Time Now | F | 27 | 21%
| Scheduled to Finish - To Time Now | F | 27 | 21%
| Finished | F | 20
| Finished Late | F | 11
| Completed Delayed (<=30 days) | F | 6 | 55%
| Completed Delayed (Between 31 to 60 days) | F | 5 | 45%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.74
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.79
| BEI - Value Task Finishes - Cumulative | F | 0.74
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.06
| FEI - Value Task Finish - Cumulative | F | 1.07
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 23
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 103
| Baselined to Start - Check | F | 126
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 20
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 106
| Baselined to Finish - Check | F | 126
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 23
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 103
| Current Baseline to Finish & Finished (BL Plan) | F | 20
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 106
| Baselined to Start | F | 29
| Scheduled to Start | F | 29 | 100%
| Started - Scheduled | F | 23 | 79%
| Started - Baseline Comparison | F | 23 | 79%
| BEI - Value Task Starts | F | 0.79
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 27
| Scheduled to Finish | F | 27
| Finished | F | 20
| BEI - Value Task Finishes | F | 0.74
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-05-24
| Started (incl. Future Baseline Starts) - Scheduled | F | 23 | 18%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 23 | 18%
| Started Late (from Baseline) | F | 12
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 20 | 16%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 20 | 16%
| Finished Late | F | 11
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 11 | 55%
| Completed On-Schedule | F | 9 | 45%
| Accelerated | F | 0 | 0%
| Days Variance | F | 277 | 1385%
| Days Early | F | 0 | 0%
| Days Late | F | 277 | 1385%
| Avg Days Early | F | 0
| Avg Days Late | F | 25
| Avg Variance | F | 14
| Actually Finished | F | 20 | 16%
| Took Longer than Planned | F | 4 | 20%
| Took Less Than Planned | F | 2 | 10%
| Completed (w/Baseline Duration) | F | 20 | 16%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 20 | 74%
| Missed Durations | F | 4 | 20%
| Missed Durations & Late Actual Finish | F | 4 | 20%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 11 | 55%
| Completed On-Schedule | F | 9 | 45%
| Accelerated | F | 0 | 0%
| Days Variance | F | 277 | 1385%
| Days Early | F | 0 | 0%
| Days Late | F | 277 | 1385%
| Avg Days Early | F | 0
| Avg Days Late | F | 25
| Avg Variance | F | 14
| Actually Finished | F | 20 | 16%
| Took Longer than Planned | F | 4 | 20%
| Took Less Than Planned | F | 2 | 10%
| Completed (w/Baseline Duration) | F | 20 | 16%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 20 | 74%
| Missed Durations | F | 4 | 20%
| Missed Durations & Late Actual Finish | F | 4 | 20%
| Baselined Tasks | F | 126
| Baselined to Start - TOTAL | F | 126
| Complete Task Starts - Cumulative | F | 23 | 79%
| Incomplete Task Starts - Cumulative (in work) | F | 6 | 21%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 126
| Complete Task Finishes - Cumulative (in work) | F | 20 | 74%
| Incomplete Task Finishes - Cumulative | F | 7 | 74%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.74
| BEI - Total Tasks | F | 27
| BEI - Complete Tasks | F | 20 | 74%
| BEI - Incomplete Tasks | F | 7 | 26%
| BEI - Value Tasks (adjusted) | F | 0.74
| BEI - Complete Tasks (adjusted) | F | 20 | 74%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-05-24
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-05-24
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-05-24
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-05-24
| BEI - Value Tasks | F | 0.74
| BEI - Total Tasks | F | 27
| BEI - Incomplete Tasks | F | 7 | 26%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.74
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-05-24
| Total Activities - DRM | F | 20
| Total Activities - DRM Graph | F | 20
| Status Date | F | 2026-05-24
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | 2027-05-13
| Float to Milestone #3 - 102 | F | 10
| Milestone #4 - 103 | F | 2027-06-02
| Float to Milestone #4 - 103 | F | 10
| Milestone #5 - 104 | F | 2027-07-15
| Float to Milestone #5 - 105 | F | 10
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-05-24
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-05-24
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.79
| BEI - Value Task Finishes - Cumulative | F | 0.74
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.06
| FEI - Value Task Finish - Cumulative | F | 1.07
| BEI - Value Tasks | F | 0.74
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.74
| BEI - Complete Tasks | F | 20 | 74%
| BEI - Incomplete Tasks | F | 7 | 26%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-05-24
| High Float 10% | F | 39 | 37%
| High Float 44d | F | 44 | 42%
| Zero Days Float | F | 41 | 39%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 2%
| Critical Merge Hotspot | F | 3 | 3%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 41 | 87%
| Longest Path (Tasks & Milestones) | F | 41 | 87%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestones (To-Go) | F | 0
| Longest Path (Milestones) | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Normal Tasks (To-Go) | F | 106 | 87%
| Critical Tasks (To-Go) | F | 41 | 39%
| Critical Tasks (In Progress) | F | 1 | 2%
| Zero Days Float | F | 41 | 39%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 3.2
| Time Now | F | 2026-05-24
| Forecast to be Finished | F | 27 | 21%
| Completed On Time | F | 9 | 33%
| Completed Late | F | 11 | 41%
| Not Completed | F | 7 | 26%
| Baseline Finish Compliance | F | 33%
| Forecast to be Started | F | 29 | 23%
| Started On Time | F | 11 | 38%
| Started Late | F | 12 | 41%
| Not Started | F | 6 | 21%
| Baseline Start Compliance | F | 41%
1 | Completed Activities | F | 20
HSD01 | Time Now | F | 2026-05-24
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 6 | 5%
HSD04 | Started Late | F | 12 | 41%
HSD05 | Forecast to be Finished but not Finished yet | T | 7 | 6%
HSD06 | Finished Late | F | 11 | 41%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2027-09-14
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 5 | 100%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.74
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | F | 1.25
SEM06 | BEI Cumulative | T | 0.74
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1.07
SEM07 | To Go - Planned Task Starts - Count | T | 103
SEM07 | To Go - BEI - Task Finishes - Count | T | 106
SEM07 | To Go - Baselined Task Starts - Count | T | 103
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 6
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 97
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 7
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 99
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1.07
SEM07 | To Go - Planned Task Starts - Count | T | 103
SEM07 | To Go - BEI - Task Finishes - Count | T | 106
SEM07 | To Go - Baselined Task Starts - Count | T | 103
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 103
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 6
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 97
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 106
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 7
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 99
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 6
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 97
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 7
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 99
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1.07
SEM07 | To Go - Planned Task Starts - Count | T | 103
SEM07 | To Go - BEI - Task Finishes - Count | T | 106
SEM07 | To Go - Baselined Task Starts - Count | T | 103
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | TC-BEI | F | 1.07
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.34
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Project3
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project3 (6/30/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-06-30
| Specific Task Start | F | 2027-08-05
| Specific Task Finish | F | 2027-09-01
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-06-30
| High Float 44d | F | 42 | 41%
| Zero Days Float | F | 40 | 39%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Critical Merge Hotspot | F | 3 | 3%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 31 | 30%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 102 | 81%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 102 | 100%
| Normal Tasks (To-Go, In Progress) | F | 1 | 1%
| Critical Path (Tasks & Milestones) | F | 40 | 39%
| Critical Path (Milestones) | F | 0 | 0%
| Critical Path (Normal Tasks) | F | 40 | 100%
| Critical Path (Normal In Progress) | F | 1 | 3%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 40 | 39%
| Near-Critical (<10 Days Float) | F | 49 | 48%
| CP Logic Density™ | F | 3.23
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.67
| BEI - Total Tasks | F | 36
| BEI - Complete Tasks | F | 24 | 67%
| BEI - Incomplete Tasks | F | 12 | 33%
| Status Date | F | 2026-06-30
| Milestone #1 - 100 | F | 2027-08-05
| Float Milestone #1 - 100 | F | 0
| Milestone #2 - 101 | F | 2027-05-27
| Float to Milestone #2 - 101 | F | 15
| Milestone #3 - 102 | F | 2027-07-01
| Float to Milestone #3 - 102 | F | 10
| Milestone #4 - 103 | F | 2027-08-04
| Float to Milestone #4 - 103 | F | 10
| Milestone #5 - 104 | F | 2027-08-05
| Float to Milestone #5 - 104 | F | 30
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-06-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-06-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-06-30
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 24 | 19%
| Completed Milestones | F | 0
| Completed Tasks | F | 24 | 19%
| Total Activities (To-Go) - % of Total | F | 117 | 81%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 102 | 87%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 102 | 87%
| Summaries (To-Go) | F | 15 | 13%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 40 | 87%
| Longest Path (Normal Tasks) | F | 40 | 87%
| Longest Path (Milestones) | F | 0 | 0%
| Critical Milestones (To-Go) | F | 0 | 0%
| Critical Normal Tasks (To-Go) | F | 40 | 100%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 25
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 24
| Started Delayed (<=30 days) | F | 8 | 57%
| Started Delayed (Between 31 to 60 days) | F | 4 | 29%
| Started Delayed (>60 days) | F | 2 | 14%
| Completed Delayed (<=30 days) | F | 7 | 47%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 40%
| Completed Delayed (>60 days) | F | 2 | 13%
| BEI - Value Task Starts - Cumulative | F | 0.66
| BEI - Value Task Finishes - Cumulative | F | 0.67
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.15
| FEI - Value Task Finish - Cumulative | F | 1.13
| Current Baseline to Start & Started (BL Plan) | F | 25
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 101
| Current Baseline to Finish & Finished (BL Plan) | F | 24
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 102
| Duration Ratio Metric (DRM) | F | 24
| DRM Graph | F | 24
| Baselined to Start | F | 102
| Scheduled to Start | F | 102
| Baselined to Finish | F | 102
| Scheduled to Finish | F | 102
| BEI - Value Activities | F | 0.67
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 102 | 87%
| Critical Path To-Go | F | 40 | 39%
| Status Date | F | 2026-06-30
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 24 | 19%
| Completed Milestones | F | 0
| Completed Tasks | F | 24 | 19%
| Total Activities (To-Go) - % of Total | F | 117 | 81%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 102 | 87%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 102 | 87%
| Summaries (To-Go) | F | 15 | 13%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 40 | 87%
| Longest Path (Normal Tasks) | F | 40 | 87%
| Longest Path (Milestones) | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-06-30
| Total Activities (To-Go) - % of Total | F | 117 | 81%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 102 | 87%
| Summary-to-Task Ratio (To-Go) | F | 1:07 | 0.15
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 40 | 39%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 102 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 102 | 87%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 9
| Avg. Remaining Duration | F | 9
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 40 | 39%
| Avg. Critical Original Duration | F | 9
| Avg. Critical Remaining Duration | F | 9
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 102 | 81%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 4 | 4%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 102 | 100%
| No Constraints | F | 102 | 100%
| Logic Density™ | F | 2.83
| Logic Density™ - Predecessors | F | 1.47
| Logic Density™ - Successors | F | 1.36
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 101 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 1 | 1%
| FS Predecessors | F | 102 | 100%
| All Activities w/Successors | F | 98 | 96%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 98 | 96%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.47
| All Activities w/Predecessors | F | 101 | 100%
| Total # Predecessors | F | 148
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 1 | 1%
| Total # Predecessor Lags | F | 1
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 5
| Hidden Duration (Planned) | F | 1 | 1%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 10 | 10%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 3 | 3%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Logic Density™ - Successors | F | 1.36
| All Activities w/Successors | F | 98 | 100%
| Activities Missing Successors | F | 4 | 4%
| Total # Successors | F | 139
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 1 | 1%
| Total# of Successor Lags | F | 1
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 11 | 11%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Actually Finished - Tasks & Milestones | F | 24 | 19%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 9 | 38%
| Completed Delayed - Tasks & Milestones | F | 15 | 63%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 32
| Avg Finish Variance - Tasks & Milestones | F | 20
| Actually Finished - Tasks | F | 24 | 19%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 9 | 38%
| Completed Delayed - Tasks | F | 15 | 63%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 1 | 1%
| Extended Durations - Tasks | F | 6 | 5%
| Actually Finished - Milestones | F | 0
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 1 | 1%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 1 | 100%
| In-Progress Delayed Finish - Tasks | F | 1 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 67
| Avg Start Variance | F | 67
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 101 | 80%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 101 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 101 | 80%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 101 | 100%
| Planned Delayed Finish - Tasks | F | 101 | 100%
| Scheduled to Start - Milestones | F | 0
| Planned Ahead Start - Milestones | F | 0
| Planned On Schedule Start - Milestones | F | 0
| Planned Delayed Start - Milestones | F | 0
| Planned Delayed Finish - Milestones | F | 0
| Schedule Baseline Activities | F | 126 | 100%
| Scheduled/Baselined to Start | F | 102
| Scheduled/Baselined to Finish | F | 102
| Start/ed | F | 25
| Finish/ed | F | 24
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 6 | 43%
| Completed Delayed (>30 days) | F | 8 | 53%
| SPI(t) | F | 0.88
| Scheduled Activities | F | 126 | 100%
| Scheduled to Start | F | 102 | 81%
| Scheduled to Finish | F | 102 | 81%
| Longest Path - Critical Activities and Milestones | F | 40 | 39%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 40 | 39%
| Critical Tasks (In Progress) | F | 1 | 3%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| High Float 10% | F | 31 | 30%
| High Float 44d | F | 42 | 41%
| Zero Days Float | F | 40 | 39%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 40 | 39%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 40 | 39%
| Critical Tasks (In Progress) | F | 1 | 3%
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Logic Density™ | F | 2.79
| CP Logic Density™ | F | 3.23
| Critical w/Missing Logic | F | 1 | 4%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 40 | 39%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 1 | 3%
| Critical with Successor Lag | F | 1 | 3%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 25
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 24
| Started Delayed (<=30 days) | F | 8 | 57%
| Started Delayed (Between 31 to 60 days) | F | 4 | 29%
| Started Delayed (>60 days) | F | 2 | 14%
| Completed Delayed (<=30 days) | F | 7 | 47%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 40%
| Completed Delayed (>60 days) | F | 2 | 13%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 25
| Current Baselined to Start & Started | F | 25
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 24
| Current Baselined to Finish & Finished | F | 24
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 8 | 57%
| Started Delayed (Between 31 to 60 days) | F | 4 | 29%
| Started Delayed (>60 days) | F | 2 | 14%
| Completed Delayed (<=30 days) | F | 7 | 47%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 40%
| Completed Delayed (>60 days) | F | 2 | 13%
| Baselined to Start - To Time Now | F | 38 | 30%
| Scheduled to Start - To Time Now | F | 38 | 30%
| Started | F | 25
| Started Late | F | 14
| Started Delayed (<=30 days) | F | 8 | 57%
| Started Delayed (Between 31 to 60 days) | F | 4 | 29%
| Started Delayed (>60 days) | F | 2 | 14%
| BEI - Value Task Starts | F | 0.66
| Baselined to Finish - To Time Now | F | 36 | 29%
| Scheduled to Finish - To Time Now | F | 36 | 29%
| Finished | F | 24
| Finished Late | F | 15
| Completed Delayed (<=30 days) | F | 7 | 47%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 40%
| Completed Delayed (>60 days) | F | 2 | 13%
| BEI - Value Task Finishes | F | 0.67
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.66
| BEI - Value Task Finishes - Cumulative | F | 0.67
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.15
| FEI - Value Task Finish - Cumulative | F | 1.13
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 25
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 101
| Baselined to Start - Check | F | 126
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 24
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 102
| Baselined to Finish - Check | F | 126
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 25
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 101
| Current Baseline to Finish & Finished (BL Plan) | F | 24
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 102
| Baselined to Start | F | 38
| Scheduled to Start | F | 38 | 100%
| Started - Scheduled | F | 25 | 66%
| Started - Baseline Comparison | F | 25 | 66%
| BEI - Value Task Starts | F | 0.66
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 36
| Scheduled to Finish | F | 36
| Finished | F | 24
| BEI - Value Task Finishes | F | 0.67
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-06-30
| Started (incl. Future Baseline Starts) - Scheduled | F | 25 | 20%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 25 | 20%
| Started Late (from Baseline) | F | 14
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 24 | 19%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 24 | 19%
| Finished Late | F | 15
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 15 | 63%
| Completed On-Schedule | F | 9 | 38%
| Accelerated | F | 0 | 0%
| Days Variance | F | 475 | 1979%
| Days Early | F | 0 | 0%
| Days Late | F | 475 | 1979%
| Avg Days Early | F | 0
| Avg Days Late | F | 32
| Avg Variance | F | 20
| Actually Finished | F | 24 | 19%
| Took Longer than Planned | F | 6 | 25%
| Took Less Than Planned | F | 4 | 17%
| Completed (w/Baseline Duration) | F | 24 | 19%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 24 | 67%
| Missed Durations | F | 6 | 25%
| Missed Durations & Late Actual Finish | F | 6 | 25%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 15 | 63%
| Completed On-Schedule | F | 9 | 38%
| Accelerated | F | 0 | 0%
| Days Variance | F | 475 | 1979%
| Days Early | F | 0 | 0%
| Days Late | F | 475 | 1979%
| Avg Days Early | F | 0
| Avg Days Late | F | 32
| Avg Variance | F | 20
| Actually Finished | F | 24 | 19%
| Took Longer than Planned | F | 6 | 25%
| Took Less Than Planned | F | 4 | 17%
| Completed (w/Baseline Duration) | F | 24 | 19%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 24 | 67%
| Missed Durations | F | 6 | 25%
| Missed Durations & Late Actual Finish | F | 6 | 25%
| Baselined Tasks | F | 126
| Baselined to Start - TOTAL | F | 126
| Complete Task Starts - Cumulative | F | 25 | 66%
| Incomplete Task Starts - Cumulative (in work) | F | 13 | 34%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 126
| Complete Task Finishes - Cumulative (in work) | F | 24 | 67%
| Incomplete Task Finishes - Cumulative | F | 12 | 67%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.67
| BEI - Total Tasks | F | 36
| BEI - Complete Tasks | F | 24 | 67%
| BEI - Incomplete Tasks | F | 12 | 33%
| BEI - Value Tasks (adjusted) | F | 0.67
| BEI - Complete Tasks (adjusted) | F | 24 | 67%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-06-30
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-06-30
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-06-30
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-06-30
| BEI - Value Tasks | F | 0.67
| BEI - Total Tasks | F | 36
| BEI - Incomplete Tasks | F | 12 | 33%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.67
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-06-30
| Total Activities - DRM | F | 24
| Total Activities - DRM Graph | F | 24
| Status Date | F | 2026-06-30
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | 2027-07-01
| Float to Milestone #3 - 102 | F | 10
| Milestone #4 - 103 | F | 2027-07-21
| Float to Milestone #4 - 103 | F | 10
| Milestone #5 - 104 | F | 2027-09-02
| Float to Milestone #5 - 105 | F | 10
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-06-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-06-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.66
| BEI - Value Task Finishes - Cumulative | F | 0.67
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.15
| FEI - Value Task Finish - Cumulative | F | 1.13
| BEI - Value Tasks | F | 0.67
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.67
| BEI - Complete Tasks | F | 24 | 67%
| BEI - Incomplete Tasks | F | 12 | 33%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-06-30
| High Float 10% | F | 31 | 30%
| High Float 44d | F | 42 | 41%
| Zero Days Float | F | 40 | 39%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Critical Merge Hotspot | F | 3 | 3%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 40 | 87%
| Longest Path (Tasks & Milestones) | F | 40 | 87%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestones (To-Go) | F | 0
| Longest Path (Milestones) | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Normal Tasks (To-Go) | F | 102 | 87%
| Critical Tasks (To-Go) | F | 40 | 39%
| Critical Tasks (In Progress) | F | 1 | 3%
| Zero Days Float | F | 40 | 39%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 3.23
| Time Now | F | 2026-06-30
| Forecast to be Finished | F | 36 | 29%
| Completed On Time | F | 9 | 25%
| Completed Late | F | 15 | 42%
| Not Completed | F | 12 | 33%
| Baseline Finish Compliance | F | 25%
| Forecast to be Started | F | 38 | 30%
| Started On Time | F | 11 | 29%
| Started Late | F | 14 | 37%
| Not Started | F | 13 | 34%
| Baseline Start Compliance | F | 32%
1 | Completed Activities | F | 24
HSD01 | Time Now | F | 2026-06-30
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 13 | 10%
HSD04 | Started Late | F | 14 | 37%
HSD05 | Forecast to be Finished but not Finished yet | T | 12 | 10%
HSD06 | Finished Late | F | 15 | 42%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2027-11-02
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 2 | 67%
SEM02 | BRI Current | T | 0.14
SEM03 | BRI Cumulative | F | 0.67
SEM04 | BPI Current | T | 0.14
SEM05 | BEI Current | T | 0.43
SEM06 | BEI Cumulative | T | 0.67
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.15
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.13
SEM07 | To Go - Planned Task Starts - Count | T | 101
SEM07 | To Go - BEI - Task Finishes - Count | T | 102
SEM07 | To Go - Baselined Task Starts - Count | T | 101
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.15
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 13
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 88
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 12
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 90
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.15
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.13
SEM07 | To Go - Planned Task Starts - Count | T | 101
SEM07 | To Go - BEI - Task Finishes - Count | T | 102
SEM07 | To Go - Baselined Task Starts - Count | T | 101
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.15
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 101
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 13
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 88
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 102
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 12
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 90
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 13
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 88
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 12
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 90
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.15
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.13
SEM07 | To Go - Planned Task Starts - Count | T | 101
SEM07 | To Go - BEI - Task Finishes - Count | T | 102
SEM07 | To Go - Baselined Task Starts - Count | T | 101
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.15
SEM07 | TC-BEI | T | 1.13
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.45
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Project4
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project4 (7/29/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-07-29
| Specific Task Start | F | 2027-08-19
| Specific Task Finish | F | 2027-09-15
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-07-29
| High Float 44d | F | 41 | 41%
| Zero Days Float | F | 37 | 37%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Critical Merge Hotspot | F | 3 | 3%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 31 | 31%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 101 | 80%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 101 | 100%
| Normal Tasks (To-Go, In Progress) | F | 1 | 1%
| Critical Path (Tasks & Milestones) | F | 37 | 37%
| Critical Path (Milestones) | F | 0 | 0%
| Critical Path (Normal Tasks) | F | 37 | 100%
| Critical Path (Normal In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 37 | 37%
| Near-Critical (<10 Days Float) | F | 48 | 48%
| CP Logic Density™ | F | 3.32
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.58
| BEI - Total Tasks | F | 43
| BEI - Complete Tasks | F | 25 | 58%
| BEI - Incomplete Tasks | F | 18 | 42%
| Status Date | F | 2026-07-29
| Milestone #1 - 100 | F | 2027-08-19
| Float Milestone #1 - 100 | F | 0
| Milestone #2 - 101 | F | 2027-06-10
| Float to Milestone #2 - 101 | F | 15
| Milestone #3 - 102 | F | 2027-07-15
| Float to Milestone #3 - 102 | F | 10
| Milestone #4 - 103 | F | 2027-08-18
| Float to Milestone #4 - 103 | F | 10
| Milestone #5 - 104 | F | 2027-08-19
| Float to Milestone #5 - 104 | F | 30
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-07-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-07-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-07-29
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 25 | 20%
| Completed Milestones | F | 0
| Completed Tasks | F | 25 | 20%
| Total Activities (To-Go) - % of Total | F | 116 | 81%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 101 | 87%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 101 | 87%
| Summaries (To-Go) | F | 15 | 13%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 37 | 90%
| Longest Path (Normal Tasks) | F | 37 | 90%
| Longest Path (Milestones) | F | 0 | 0%
| Critical Milestones (To-Go) | F | 0 | 0%
| Critical Normal Tasks (To-Go) | F | 37 | 100%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 26
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 25
| Started Delayed (<=30 days) | F | 8 | 53%
| Started Delayed (Between 31 to 60 days) | F | 4 | 27%
| Started Delayed (>60 days) | F | 3 | 20%
| Completed Delayed (<=30 days) | F | 7 | 44%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 38%
| Completed Delayed (>60 days) | F | 3 | 19%
| BEI - Value Task Starts - Cumulative | F | 0.59
| BEI - Value Task Finishes - Cumulative | F | 0.58
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.22
| FEI - Value Task Finish - Cumulative | F | 1.22
| Current Baseline to Start & Started (BL Plan) | F | 26
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 100
| Current Baseline to Finish & Finished (BL Plan) | F | 25
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 101
| Duration Ratio Metric (DRM) | F | 25
| DRM Graph | F | 25
| Baselined to Start | F | 101
| Scheduled to Start | F | 101
| Baselined to Finish | F | 101
| Scheduled to Finish | F | 101
| BEI - Value Activities | F | 0.58
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 101 | 87%
| Critical Path To-Go | F | 37 | 37%
| Status Date | F | 2026-07-29
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 25 | 20%
| Completed Milestones | F | 0
| Completed Tasks | F | 25 | 20%
| Total Activities (To-Go) - % of Total | F | 116 | 81%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 101 | 87%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 101 | 87%
| Summaries (To-Go) | F | 15 | 13%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 37 | 90%
| Longest Path (Normal Tasks) | F | 37 | 90%
| Longest Path (Milestones) | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-07-29
| Total Activities (To-Go) - % of Total | F | 116 | 81%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 101 | 87%
| Summary-to-Task Ratio (To-Go) | F | 1:07 | 0.15
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 37 | 37%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 101 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 101 | 87%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 9
| Avg. Remaining Duration | F | 9
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 37 | 37%
| Avg. Critical Original Duration | F | 9
| Avg. Critical Remaining Duration | F | 9
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 101 | 80%
| Total Constraints | F | 2 | 2%
| Start No Earlier Than | F | 2 | 2%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 4 | 4%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 99 | 98%
| No Constraints | F | 99 | 98%
| Logic Density™ | F | 2.87
| Logic Density™ - Predecessors | F | 1.49
| Logic Density™ - Successors | F | 1.39
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 100 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 101 | 100%
| All Activities w/Successors | F | 97 | 96%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 97 | 96%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.49
| All Activities w/Predecessors | F | 100 | 100%
| Total # Predecessors | F | 149
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 1 | 1%
| Total # Predecessor Lags | F | 1
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 5
| Hidden Duration (Planned) | F | 1 | 1%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 10 | 10%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 3 | 3%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Logic Density™ - Successors | F | 1.39
| All Activities w/Successors | F | 97 | 100%
| Activities Missing Successors | F | 4 | 4%
| Total # Successors | F | 140
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 1 | 1%
| Total# of Successor Lags | F | 1
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 11 | 11%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 8 | 8%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Actually Finished - Tasks & Milestones | F | 25 | 20%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 9 | 36%
| Completed Delayed - Tasks & Milestones | F | 16 | 64%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 34
| Avg Finish Variance - Tasks & Milestones | F | 22
| Actually Finished - Tasks | F | 25 | 20%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 9 | 36%
| Completed Delayed - Tasks | F | 16 | 64%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 1 | 1%
| Extended Durations - Tasks | F | 6 | 5%
| Actually Finished - Milestones | F | 0
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 1 | 1%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 1 | 100%
| In-Progress Delayed Finish - Tasks | F | 1 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 67
| Avg Start Variance | F | 67
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 100 | 79%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 100 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 100 | 79%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 100 | 100%
| Planned Delayed Finish - Tasks | F | 100 | 100%
| Scheduled to Start - Milestones | F | 0
| Planned Ahead Start - Milestones | F | 0
| Planned On Schedule Start - Milestones | F | 0
| Planned Delayed Start - Milestones | F | 0
| Planned Delayed Finish - Milestones | F | 0
| Schedule Baseline Activities | F | 126 | 100%
| Scheduled/Baselined to Start | F | 101
| Scheduled/Baselined to Finish | F | 101
| Start/ed | F | 26
| Finish/ed | F | 25
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 7 | 47%
| Completed Delayed (>30 days) | F | 9 | 56%
| SPI(t) | F | 0.89
| Scheduled Activities | F | 126 | 100%
| Scheduled to Start | F | 101 | 80%
| Scheduled to Finish | F | 101 | 80%
| Longest Path - Critical Activities and Milestones | F | 37 | 37%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 37 | 37%
| Critical Tasks (In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| High Float 10% | F | 31 | 31%
| High Float 44d | F | 41 | 41%
| Zero Days Float | F | 37 | 37%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 37 | 37%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 37 | 37%
| Critical Tasks (In Progress) | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Logic Density™ | F | 2.83
| CP Logic Density™ | F | 3.32
| Critical w/Missing Logic | F | 1 | 4%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 37 | 37%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 26
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 25
| Started Delayed (<=30 days) | F | 8 | 53%
| Started Delayed (Between 31 to 60 days) | F | 4 | 27%
| Started Delayed (>60 days) | F | 3 | 20%
| Completed Delayed (<=30 days) | F | 7 | 44%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 38%
| Completed Delayed (>60 days) | F | 3 | 19%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 26
| Current Baselined to Start & Started | F | 26
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 25
| Current Baselined to Finish & Finished | F | 25
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 8 | 53%
| Started Delayed (Between 31 to 60 days) | F | 4 | 27%
| Started Delayed (>60 days) | F | 3 | 20%
| Completed Delayed (<=30 days) | F | 7 | 44%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 38%
| Completed Delayed (>60 days) | F | 3 | 19%
| Baselined to Start - To Time Now | F | 44 | 35%
| Scheduled to Start - To Time Now | F | 44 | 35%
| Started | F | 26
| Started Late | F | 15
| Started Delayed (<=30 days) | F | 8 | 53%
| Started Delayed (Between 31 to 60 days) | F | 4 | 27%
| Started Delayed (>60 days) | F | 3 | 20%
| BEI - Value Task Starts | F | 0.59
| Baselined to Finish - To Time Now | F | 43 | 34%
| Scheduled to Finish - To Time Now | F | 43 | 34%
| Finished | F | 25
| Finished Late | F | 16
| Completed Delayed (<=30 days) | F | 7 | 44%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 38%
| Completed Delayed (>60 days) | F | 3 | 19%
| BEI - Value Task Finishes | F | 0.58
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.59
| BEI - Value Task Finishes - Cumulative | F | 0.58
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.22
| FEI - Value Task Finish - Cumulative | F | 1.22
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 26
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 100
| Baselined to Start - Check | F | 126
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 25
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 101
| Baselined to Finish - Check | F | 126
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 26
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 100
| Current Baseline to Finish & Finished (BL Plan) | F | 25
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 101
| Baselined to Start | F | 44
| Scheduled to Start | F | 44 | 100%
| Started - Scheduled | F | 26 | 59%
| Started - Baseline Comparison | F | 26 | 59%
| BEI - Value Task Starts | F | 0.59
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 43
| Scheduled to Finish | F | 43
| Finished | F | 25
| BEI - Value Task Finishes | F | 0.58
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-07-29
| Started (incl. Future Baseline Starts) - Scheduled | F | 26 | 21%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 26 | 21%
| Started Late (from Baseline) | F | 15
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 25 | 20%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 25 | 20%
| Finished Late | F | 16
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 16 | 64%
| Completed On-Schedule | F | 9 | 36%
| Accelerated | F | 0 | 0%
| Days Variance | F | 540 | 2160%
| Days Early | F | 0 | 0%
| Days Late | F | 540 | 2160%
| Avg Days Early | F | 0
| Avg Days Late | F | 34
| Avg Variance | F | 22
| Actually Finished | F | 25 | 20%
| Took Longer than Planned | F | 6 | 24%
| Took Less Than Planned | F | 5 | 20%
| Completed (w/Baseline Duration) | F | 25 | 20%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 25 | 58%
| Missed Durations | F | 6 | 24%
| Missed Durations & Late Actual Finish | F | 6 | 24%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 16 | 64%
| Completed On-Schedule | F | 9 | 36%
| Accelerated | F | 0 | 0%
| Days Variance | F | 540 | 2160%
| Days Early | F | 0 | 0%
| Days Late | F | 540 | 2160%
| Avg Days Early | F | 0
| Avg Days Late | F | 34
| Avg Variance | F | 22
| Actually Finished | F | 25 | 20%
| Took Longer than Planned | F | 6 | 24%
| Took Less Than Planned | F | 5 | 20%
| Completed (w/Baseline Duration) | F | 25 | 20%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 25 | 58%
| Missed Durations | F | 6 | 24%
| Missed Durations & Late Actual Finish | F | 6 | 24%
| Baselined Tasks | F | 126
| Baselined to Start - TOTAL | F | 126
| Complete Task Starts - Cumulative | F | 26 | 59%
| Incomplete Task Starts - Cumulative (in work) | F | 18 | 41%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 126
| Complete Task Finishes - Cumulative (in work) | F | 25 | 58%
| Incomplete Task Finishes - Cumulative | F | 18 | 58%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.58
| BEI - Total Tasks | F | 43
| BEI - Complete Tasks | F | 25 | 58%
| BEI - Incomplete Tasks | F | 18 | 42%
| BEI - Value Tasks (adjusted) | F | 0.58
| BEI - Complete Tasks (adjusted) | F | 25 | 58%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-07-29
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-07-29
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-07-29
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-07-29
| BEI - Value Tasks | F | 0.58
| BEI - Total Tasks | F | 43
| BEI - Incomplete Tasks | F | 18 | 42%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.58
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-07-29
| Total Activities - DRM | F | 25
| Total Activities - DRM Graph | F | 25
| Status Date | F | 2026-07-29
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | 2027-07-15
| Float to Milestone #3 - 102 | F | 10
| Milestone #4 - 103 | F | 2027-08-04
| Float to Milestone #4 - 103 | F | 10
| Milestone #5 - 104 | F | 2027-09-16
| Float to Milestone #5 - 105 | F | 10
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-07-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-07-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.59
| BEI - Value Task Finishes - Cumulative | F | 0.58
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.22
| FEI - Value Task Finish - Cumulative | F | 1.22
| BEI - Value Tasks | F | 0.58
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.58
| BEI - Complete Tasks | F | 25 | 58%
| BEI - Incomplete Tasks | F | 18 | 42%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-07-29
| High Float 10% | F | 31 | 31%
| High Float 44d | F | 41 | 41%
| Zero Days Float | F | 37 | 37%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Critical Merge Hotspot | F | 3 | 3%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 37 | 90%
| Longest Path (Tasks & Milestones) | F | 37 | 90%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestones (To-Go) | F | 0
| Longest Path (Milestones) | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Normal Tasks (To-Go) | F | 101 | 87%
| Critical Tasks (To-Go) | F | 37 | 37%
| Critical Tasks (In Progress) | F | 0 | 0%
| Zero Days Float | F | 37 | 37%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 3.32
| Time Now | F | 2026-07-29
| Forecast to be Finished | F | 43 | 34%
| Completed On Time | T | 9 | 21%
| Completed Late | F | 16 | 37%
| Not Completed | F | 18 | 42%
| Baseline Finish Compliance | T | 21%
| Forecast to be Started | F | 44 | 35%
| Started On Time | F | 11 | 25%
| Started Late | F | 15 | 34%
| Not Started | F | 18 | 41%
| Baseline Start Compliance | F | 27%
1 | Completed Activities | F | 25
HSD01 | Time Now | F | 2026-07-29
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 18 | 14%
HSD04 | Started Late | F | 15 | 34%
HSD05 | Forecast to be Finished but not Finished yet | T | 18 | 14%
HSD06 | Finished Late | F | 16 | 37%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2027-11-16
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 1 | 100%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.58
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | T | 0.14
SEM06 | BEI Cumulative | T | 0.58
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.22
SEM07 | To Go - Planned Task Starts - Count | T | 100
SEM07 | To Go - BEI - Task Finishes - Count | T | 101
SEM07 | To Go - Baselined Task Starts - Count | T | 100
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.22
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 18
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 82
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 18
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 83
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.22
SEM07 | To Go - Planned Task Starts - Count | T | 100
SEM07 | To Go - BEI - Task Finishes - Count | T | 101
SEM07 | To Go - Baselined Task Starts - Count | T | 100
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.22
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 100
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 18
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 82
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 101
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 18
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 83
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 18
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 82
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 18
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 83
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.22
SEM07 | To Go - Planned Task Starts - Count | T | 100
SEM07 | To Go - BEI - Task Finishes - Count | T | 101
SEM07 | To Go - Baselined Task Starts - Count | T | 100
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.22
SEM07 | TC-BEI | T | 1.22
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.63
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Project5
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5 (8/27/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-08-27
| Specific Task Start | F | 2027-09-24
| Specific Task Finish | F | 2027-10-21
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 5 | 5%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 5 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-08-27
| High Float 44d | F | 44 | 44%
| Zero Days Float | F | 4 | 4%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 41 | 41%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 99 | 79%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 100%
| Normal Tasks (To-Go, In Progress) | F | 2 | 2%
| Critical Path (Tasks & Milestones) | F | 4 | 4%
| Critical Path (Milestones) | F | 0 | 0%
| Critical Path (Normal Tasks) | F | 4 | 100%
| Critical Path (Normal In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 4 | 4%
| Near-Critical (<10 Days Float) | F | 5 | 5%
| CP Logic Density™ | F | 3
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| Status Date | F | 2026-08-27
| Milestone #1 - 100 | F | 2027-09-24
| Float Milestone #1 - 100 | F | 19
| Milestone #2 - 101 | F | 2027-07-16
| Float to Milestone #2 - 101 | F | 36
| Milestone #3 - 102 | F | 2027-08-20
| Float to Milestone #3 - 102 | F | 35
| Milestone #4 - 103 | F | 2027-09-23
| Float to Milestone #4 - 103 | F | 35
| Milestone #5 - 104 | F | 2027-09-24
| Float to Milestone #5 - 104 | F | 55
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 27 | 21%
| Completed Milestones | F | 0
| Completed Tasks | F | 27 | 21%
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 88%
| Summaries (To-Go) | F | 14 | 12%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 4 | 100%
| Longest Path (Normal Tasks) | F | 4 | 100%
| Longest Path (Milestones) | F | 0 | 0%
| Critical Milestones (To-Go) | F | 0 | 0%
| Critical Normal Tasks (To-Go) | F | 4 | 100%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.24
| FEI - Value Task Finish - Cumulative | F | 1.24
| Current Baseline to Start & Started (BL Plan) | F | 29
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 97
| Current Baseline to Finish & Finished (BL Plan) | F | 27
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 99
| Duration Ratio Metric (DRM) | F | 27
| DRM Graph | F | 27
| Baselined to Start | F | 99
| Scheduled to Start | F | 99
| Baselined to Finish | F | 99
| Scheduled to Finish | F | 99
| BEI - Value Activities | F | 0.59
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Critical Path To-Go | F | 4 | 4%
| Status Date | F | 2026-08-27
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 27 | 21%
| Completed Milestones | F | 0
| Completed Tasks | F | 27 | 21%
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 88%
| Summaries (To-Go) | F | 14 | 12%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 4 | 100%
| Longest Path (Normal Tasks) | F | 4 | 100%
| Longest Path (Milestones) | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-08-27
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Summary-to-Task Ratio (To-Go) | F | 1:07 | 0.14
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 4 | 4%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 99 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 10
| Avg. Remaining Duration | F | 9
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 4 | 4%
| Avg. Critical Original Duration | F | 8
| Avg. Critical Remaining Duration | F | 8
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 99 | 79%
| Total Constraints | F | 3 | 3%
| Start No Earlier Than | F | 2 | 2%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 1 | 1%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 5 | 5%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 96 | 97%
| No Constraints | F | 96 | 97%
| Logic Density™ | F | 2.86
| Logic Density™ - Predecessors | F | 1.48
| Logic Density™ - Successors | F | 1.37
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 97 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 99 | 100%
| All Activities w/Successors | F | 94 | 95%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 94 | 95%
| Missing Logic | F | 5 | 5%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 5 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.49
| All Activities w/Predecessors | F | 97 | 100%
| Total # Predecessors | F | 145
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 1 | 1%
| Total # Predecessor Lags | F | 1
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 5
| Hidden Duration (Planned) | F | 1 | 1%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 10 | 10%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 1%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.37
| All Activities w/Successors | F | 94 | 100%
| Activities Missing Successors | F | 5 | 5%
| Total # Successors | F | 136
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 1 | 1%
| Total# of Successor Lags | F | 1
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 11 | 11%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 27 | 21%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 9 | 33%
| Completed Delayed - Tasks & Milestones | F | 18 | 67%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 39
| Avg Finish Variance - Tasks & Milestones | F | 26
| Actually Finished - Tasks | F | 27 | 21%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 9 | 33%
| Completed Delayed - Tasks | F | 18 | 67%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 2 | 2%
| Extended Durations - Tasks | F | 7 | 6%
| Actually Finished - Milestones | F | 0
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 2 | 2%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 2 | 100%
| In-Progress Delayed Finish - Tasks | F | 2 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 85
| Avg Start Variance | F | 85
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 97 | 77%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 97 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 97 | 77%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 97 | 100%
| Planned Delayed Finish - Tasks | F | 97 | 100%
| Scheduled to Start - Milestones | F | 0
| Planned Ahead Start - Milestones | F | 0
| Planned On Schedule Start - Milestones | F | 0
| Planned Delayed Start - Milestones | F | 0
| Planned Delayed Finish - Milestones | F | 0
| Schedule Baseline Activities | F | 126 | 100%
| Scheduled/Baselined to Start | F | 99
| Scheduled/Baselined to Finish | F | 99
| Start/ed | F | 29
| Finish/ed | F | 27
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 10 | 56%
| Completed Delayed (>30 days) | F | 11 | 61%
| SPI(t) | F | 0.91
| Scheduled Activities | F | 126 | 100%
| Scheduled to Start | F | 99 | 79%
| Scheduled to Finish | F | 99 | 79%
| Longest Path - Critical Activities and Milestones | F | 4 | 4%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 4 | 4%
| Critical Tasks (In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| High Float 10% | F | 41 | 41%
| High Float 44d | F | 44 | 44%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 4 | 4%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 4 | 4%
| Critical Tasks (In Progress) | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Logic Density™ | F | 2.81
| CP Logic Density™ | F | 3
| Critical w/Missing Logic | F | 1 | 5%
| Critical w/Hard Constraints | F | 1 | 1%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 1 | 1%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Current Baselined to Start & Started | F | 29
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Current Baselined to Finish & Finished | F | 27
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| Baselined to Start - To Time Now | F | 48 | 38%
| Scheduled to Start - To Time Now | F | 48 | 38%
| Started | F | 29
| Started Late | F | 18
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| BEI - Value Task Starts | F | 0.6
| Baselined to Finish - To Time Now | F | 46 | 37%
| Scheduled to Finish - To Time Now | F | 46 | 37%
| Finished | F | 27
| Finished Late | F | 18
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| BEI - Value Task Finishes | F | 0.59
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.24
| FEI - Value Task Finish - Cumulative | F | 1.24
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 29
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 97
| Baselined to Start - Check | F | 126
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 27
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 99
| Baselined to Finish - Check | F | 126
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 29
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 97
| Current Baseline to Finish & Finished (BL Plan) | F | 27
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 99
| Baselined to Start | F | 48
| Scheduled to Start | F | 48 | 100%
| Started - Scheduled | F | 29 | 60%
| Started - Baseline Comparison | F | 29 | 60%
| BEI - Value Task Starts | F | 0.6
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 46
| Scheduled to Finish | F | 46
| Finished | F | 27
| BEI - Value Task Finishes | F | 0.59
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-08-27
| Started (incl. Future Baseline Starts) - Scheduled | F | 29 | 23%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 29 | 23%
| Started Late (from Baseline) | F | 18
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 27 | 21%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 27 | 21%
| Finished Late | F | 18
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 18 | 67%
| Completed On-Schedule | F | 9 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | 705 | 2611%
| Days Early | F | 0 | 0%
| Days Late | F | 705 | 2611%
| Avg Days Early | F | 0
| Avg Days Late | F | 39
| Avg Variance | F | 26
| Actually Finished | F | 27 | 21%
| Took Longer than Planned | F | 7 | 26%
| Took Less Than Planned | F | 6 | 22%
| Completed (w/Baseline Duration) | F | 27 | 21%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 27 | 59%
| Missed Durations | F | 7 | 26%
| Missed Durations & Late Actual Finish | F | 7 | 26%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 18 | 67%
| Completed On-Schedule | F | 9 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | 705 | 2611%
| Days Early | F | 0 | 0%
| Days Late | F | 705 | 2611%
| Avg Days Early | F | 0
| Avg Days Late | F | 39
| Avg Variance | F | 26
| Actually Finished | F | 27 | 21%
| Took Longer than Planned | F | 7 | 26%
| Took Less Than Planned | F | 6 | 22%
| Completed (w/Baseline Duration) | F | 27 | 21%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 27 | 59%
| Missed Durations | F | 7 | 26%
| Missed Durations & Late Actual Finish | F | 7 | 26%
| Baselined Tasks | F | 126
| Baselined to Start - TOTAL | F | 126
| Complete Task Starts - Cumulative | F | 29 | 60%
| Incomplete Task Starts - Cumulative (in work) | F | 19 | 40%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 126
| Complete Task Finishes - Cumulative (in work) | F | 27 | 59%
| Incomplete Task Finishes - Cumulative | F | 19 | 59%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| BEI - Value Tasks (adjusted) | F | 0.59
| BEI - Complete Tasks (adjusted) | F | 27 | 59%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Incomplete Tasks | F | 19 | 41%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.59
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| Total Activities - DRM | F | 27
| Total Activities - DRM Graph | F | 27
| Status Date | F | 2026-08-27
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | 2027-08-20
| Float to Milestone #3 - 102 | F | 35
| Milestone #4 - 103 | F | 2027-09-09
| Float to Milestone #4 - 103 | F | 35
| Milestone #5 - 104 | F | 2027-10-22
| Float to Milestone #5 - 105 | F | 35
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.24
| FEI - Value Task Finish - Cumulative | F | 1.24
| BEI - Value Tasks | F | 0.59
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 5 | 5%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 5 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-08-27
| High Float 10% | F | 41 | 41%
| High Float 44d | F | 44 | 44%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 4 | 100%
| Longest Path (Tasks & Milestones) | F | 4 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestones (To-Go) | F | 0
| Longest Path (Milestones) | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Normal Tasks (To-Go) | F | 99 | 88%
| Critical Tasks (To-Go) | F | 4 | 4%
| Critical Tasks (In Progress) | F | 0 | 0%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 3
| Time Now | F | 2026-08-27
| Forecast to be Finished | F | 46 | 37%
| Completed On Time | T | 9 | 20%
| Completed Late | F | 18 | 39%
| Not Completed | F | 19 | 41%
| Baseline Finish Compliance | T | 20%
| Forecast to be Started | F | 48 | 38%
| Started On Time | T | 11 | 23%
| Started Late | F | 18 | 38%
| Not Started | F | 19 | 40%
| Baseline Start Compliance | F | 25%
1 | Completed Activities | F | 27
HSD01 | Time Now | F | 2026-08-27
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 19 | 15%
HSD04 | Started Late | F | 18 | 38%
HSD05 | Forecast to be Finished but not Finished yet | T | 19 | 15%
HSD06 | Finished Late | F | 18 | 39%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2028-01-26
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 2 | 100%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.59
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | T | 0.67
SEM06 | BEI Cumulative | T | 0.59
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.24
SEM07 | To Go - Planned Task Starts - Count | T | 97
SEM07 | To Go - BEI - Task Finishes - Count | T | 99
SEM07 | To Go - Baselined Task Starts - Count | T | 97
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 78
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 80
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.24
SEM07 | To Go - Planned Task Starts - Count | T | 97
SEM07 | To Go - BEI - Task Finishes - Count | T | 99
SEM07 | To Go - Baselined Task Starts - Count | T | 97
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 97
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 78
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 99
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 80
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 78
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 80
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.24
SEM07 | To Go - Planned Task Starts - Count | T | 97
SEM07 | To Go - BEI - Task Finishes - Count | T | 99
SEM07 | To Go - Baselined Task Starts - Count | T | 97
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | TC-BEI | T | 1.24
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.61
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Large-Test-File
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Large Test File (2/7/2025 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2025-02-07
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 2 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 7 | 1%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 2 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 0 | 0%
| Open Finish | F | 2 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 41 | 4%
| Status Date | F | 2025-02-07
| High Float 44d | F | 898 | 88%
| Zero Days Float | F | 2 | 0%
| Hidden Duration (Planned) | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 9%
| Critical Merge Hotspot | F | 9 | 1%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Critical Diverge Hotspot | F | 11 | 1%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 467 | 46%
| Negative Float | F | 41 | 4%
| Tasks & Milestones (To Go) | F | 1024 | 59%
| Milestones (To-Go) | F | 79 | 8%
| Normal Tasks (To-Go) | F | 945 | 92%
| Normal Tasks (To-Go, In Progress) | F | 108 | 11%
| Critical Path (Tasks & Milestones) | F | 43 | 4%
| Critical Path (Milestones) | F | 8 | 19%
| Critical Path (Normal Tasks) | F | 35 | 81%
| Critical Path (Normal In Progress) | F | 1 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04
| Negative Float | F | 41 | 4%
| Zero Days Float | F | 2 | 0%
| Near-Critical (<10 Days Float) | F | 74 | 7%
| CP Logic Density™ | F | 7.58
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1205
| BEI - Complete Tasks | F | 609 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| Status Date | F | 2025-02-07
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2025-02-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2025-08-06
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2025-02-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 0
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | 279 | 36%
| Status Date | F | 2025-02-07
| Total Activities | F | 2125
| Milestones | F | 169 | 8%
| Normal Tasks | F | 1554 | 73%
| Summaries | F | 402 | 19%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 1723 | 81%
| Completed Tasks & Milestones | F | 699 | 41%
| Completed Milestones | F | 90 | 53%
| Completed Tasks | F | 609 | 39%
| Total Activities (To-Go) - % of Total | F | 1309 | 62%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78%
| Milestones (To-Go) | F | 79 | 6%
| Normal Tasks (To-Go) | F | 945 | 72%
| Summaries (To-Go) | F | 285 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 43 | 84%
| Longest Path (Normal Tasks) | F | 35 | 69%
| Longest Path (Milestones) | F | 8 | 16%
| Critical Milestones (To-Go) | F | 8 | 19%
| Critical Normal Tasks (To-Go) | F | 35 | 81%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 1544
| Scheduled to Start | F | 1554
| Actual Starts | F | 717
| Baselined to Finish | F | 1544
| Scheduled to Finish | F | 1554
| Actual Finishes | F | 609
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10%
| Started Delayed (>60 days) | F | 366 | 71%
| Completed Delayed (<=30 days) | F | 71 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11%
| Completed Delayed (>60 days) | F | 365 | 74%
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.63
| FEI - Value Task Finish - Cumulative | F | 2.75
| Current Baseline to Start & Started (BL Plan) | F | 716
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 828
| Current Baseline to Finish & Finished (BL Plan) | F | 609
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 935
| Duration Ratio Metric (DRM) | F | 584
| DRM Graph | F | 584
| Baselined to Start | F | 935
| Scheduled to Start | F | 945
| Baselined to Finish | F | 935
| Scheduled to Finish | F | 945
| BEI - Value Activities | F | 0.52
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78%
| Critical Path To-Go | F | 43 | 4%
| Status Date | F | 2025-02-07
| Total Activities | F | 2125
| Milestones | F | 169 | 8%
| Normal Tasks | F | 1554 | 73%
| Summaries | F | 402 | 19%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 1723 | 81%
| Completed Tasks & Milestones | F | 699 | 41%
| Completed Milestones | F | 90 | 53%
| Completed Tasks | F | 609 | 39%
| Total Activities (To-Go) - % of Total | F | 1309 | 62%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78%
| Milestones (To-Go) | F | 79 | 6%
| Normal Tasks (To-Go) | F | 945 | 72%
| Summaries (To-Go) | F | 285 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 43 | 84%
| Longest Path (Normal Tasks) | F | 35 | 69%
| Longest Path (Milestones) | F | 8 | 16%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2025-02-07
| Total Activities (To-Go) - % of Total | F | 1309 | 62%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78%
| Summary-to-Task Ratio (To-Go) | F | 1:03 | 0.3
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.08
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 43 | 4%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 2 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 1024 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 7 | 1%
| Avg. Original Duration | F | 41
| Avg. Remaining Duration | F | 16
| High Baseline Duration (44d) | F | 87 | 9%
| High Planned Duration (44d) | F | 124 | 13%
| Insufficient Detail™ | F | 22 | 2%
| Critical Activities (To-Go) | F | 35 | 4%
| Avg. Critical Original Duration | F | 14
| Avg. Critical Remaining Duration | F | 9
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 2 | 6%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 945 | 61%
| Total Constraints | F | 82 | 8%
| Start No Earlier Than | F | 80 | 8%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 1 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 1 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 1 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 1 | 0%
| Open Ends w/o Constraints | F | 1 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 942 | 92%
| No Constraints | F | 942 | 92%
| Logic Density™ | F | 3.14
| Logic Density™ - Predecessors | F | 1.77
| Logic Density™ - Successors | F | 1.36
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 915 | 100%
| SS Predecessors | F | 45 | 4%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 36 | 4%
| FS Predecessors | F | 1020 | 100%
| All Activities w/Successors | F | 1022 | 100%
| SS Successors | F | 47 | 5%
| FF Successors | F | 31 | 3%
| SF Successors | F | 0 | 0%
| FS Successors | F | 1014 | 99%
| Missing Logic | F | 2 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 1 | 0%
| Open Finish | F | 2 | 0%
| Logic Density™ - Predecessors | F | 1.82
| All Activities w/Predecessors | F | 915 | 100%
| Total # Predecessors | F | 1665
| Activities Missing Predecessors | F | 1 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 2 | 0%
| Total # Predecessor Lags | F | 2
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 22
| Hidden Duration (Planned) | F | 2 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 125 | 14%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 9 | 1%
| Logic Hotspot™ | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 9%
| Logic Density™ - Successors | F | 1.36
| All Activities w/Successors | F | 1022 | 100%
| Activities Missing Successors | F | 2 | 0%
| Total # Successors | F | 1395
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 8 | 1%
| Total# of Successor Lags | F | 8
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 72 | 7%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 11 | 1%
| Logic Hotspot™ | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 9%
| Actually Finished - Tasks & Milestones | F | 699 | 41%
| Completed Ahead - Tasks & Milestones | F | 55 | 8%
| Completed On-Schedule - Tasks & Milestones | F | 81 | 12%
| Completed Delayed - Tasks & Milestones | F | 562 | 80%
| Avg Days Finished Early - Tasks & Milestones | F | 24
| Avg Days Finished Late - Tasks & Milestones | F | 161
| Avg Finish Variance - Tasks & Milestones | F | 128
| Actually Finished - Tasks | F | 609 | 39%
| Completed Ahead - Tasks | F | 48 | 8%
| Completed On-Schedule - Tasks | F | 69 | 11%
| Completed Delayed - Tasks | F | 492 | 81%
| Accelerated Durations Early/On-Schedule - Tasks | F | 12 | 1%
| Accelerated Durations Late - Tasks | F | 106 | 7%
| Extended Durations - Tasks | F | 271 | 17%
| Actually Finished - Milestones | F | 90 | 53%
| Completed Ahead - Milestones | F | 7 | 8%
| Completed On-Schedule - Milestones | F | 12 | 13%
| Completed Delayed - Milestones | F | 70 | 78%
| Actually Started - Tasks | F | 108 | 7%
| In-Progress Started Ahead - Tasks | F | 10 | 9%
| In-Progress Started On-Schedule - Tasks | F | 17 | 16%
| In-Progress Started Delayed - Tasks | F | 80 | 74%
| In-Progress Delayed Finish - Tasks | F | 106 | 98%
| Avg Days Started Early | F | 15
| Avg Days Started Late | F | 121
| Avg Start Variance | F | 106
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 916 | 53%
| Planned Ahead Start - Tasks & Milestones | F | 4 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 96 | 10%
| Planned Delayed Start - Tasks & Milestones | F | 804 | 88%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 837 | 54%
| Planned Ahead Start - Tasks | F | 4 | 0%
| Planned On Schedule Start - Tasks | F | 93 | 11%
| Planned Delayed Start - Tasks | F | 731 | 87%
| Planned Delayed Finish - Tasks | F | 732 | 87%
| Scheduled to Start - Milestones | F | 79 | 47%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 3 | 4%
| Planned Delayed Start - Milestones | F | 73 | 92%
| Planned Delayed Finish - Milestones | F | 73 | 92%
| Schedule Baseline Activities | F | 1709 | 99%
| Scheduled/Baselined to Start | F | 1011
| Scheduled/Baselined to Finish | F | 1011
| Start/ed | F | 807
| Finish/ed | F | 699
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 417 | 81%
| Completed Delayed (>30 days) | F | 421 | 86%
| SPI(t) | F | 8.22
| Scheduled Activities | F | 1723 | 100%
| Scheduled to Start | F | 1024 | 59%
| Scheduled to Finish | F | 1024 | 59%
| Longest Path - Critical Activities and Milestones | F | 43 | 4%
| Critical Milestones (To-Go) | F | 8 | 10%
| Critical Tasks (To-Go) | F | 35 | 4%
| Critical Tasks (In Progress) | F | 1 | 3%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| High Float 10% | F | 467 | 46%
| High Float 44d | F | 898 | 88%
| Zero Days Float | F | 2 | 0%
| Negative Float | F | 41 | 4%
| Longest Path - Critical Activities and Milestones | F | 43 | 4%
| Critical Milestones (To-Go) | F | 8 | 10%
| Critical Tasks (To-Go) | F | 35 | 4%
| Critical Tasks (In Progress) | F | 1 | 3%
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.08
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| Logic Density™ | F | 3.14
| CP Logic Density™ | F | 7.58
| Critical w/Missing Logic | F | 1 | 0%
| Critical w/Hard Constraints | F | 1 | 0%
| Zero Days Float | F | 2 | 0%
| Negative Float | F | 41 | 4%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 2 | 6%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 1 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 1544
| Scheduled to Start | F | 1554
| Actual Starts | F | 717
| Baselined to Finish | F | 1544
| Scheduled to Finish | F | 1554
| Actual Finishes | F | 609
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10%
| Started Delayed (>60 days) | F | 366 | 71%
| Completed Delayed (<=30 days) | F | 71 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11%
| Completed Delayed (>60 days) | F | 365 | 74%
| Baselined to Start | F | 1544
| Scheduled to Start | F | 1554
| Actual Starts | F | 717
| Current Baselined to Start & Started | F | 716
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 1544
| Scheduled to Finish | F | 1554
| Actual Finishes | F | 609
| Current Baselined to Finish & Finished | F | 609
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10%
| Started Delayed (>60 days) | F | 366 | 71%
| Completed Delayed (<=30 days) | F | 71 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11%
| Completed Delayed (>60 days) | F | 365 | 74%
| Baselined to Start - To Time Now | F | 1228 | 80%
| Scheduled to Start - To Time Now | F | 1228 | 79%
| Started | F | 715
| Started Late | F | 515
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10%
| Started Delayed (>60 days) | F | 366 | 71%
| BEI - Value Task Starts | F | 0.58
| Baselined to Finish - To Time Now | F | 1205 | 78%
| Scheduled to Finish - To Time Now | F | 1205 | 78%
| Finished | F | 609
| Finished Late | F | 492
| Completed Delayed (<=30 days) | F | 71 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11%
| Completed Delayed (>60 days) | F | 365 | 74%
| BEI - Value Task Finishes | F | 0.51
| Started - Future | F | 1
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.63
| FEI - Value Task Finish - Cumulative | F | 2.75
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 716
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 828
| Baselined to Start - Check | F | 1544
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 609
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 935
| Baselined to Finish - Check | F | 1544
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 716
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 828
| Current Baseline to Finish & Finished (BL Plan) | F | 609
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 935
| Baselined to Start | F | 1228
| Scheduled to Start | F | 1228 | 100%
| Started - Scheduled | F | 715 | 58%
| Started - Baseline Comparison | F | 715 | 58%
| BEI - Value Task Starts | F | 0.58
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 1205
| Scheduled to Finish | F | 1205
| Finished | F | 609
| BEI - Value Task Finishes | F | 0.51
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2025-02-07
| Started (incl. Future Baseline Starts) - Scheduled | F | 717 | 46%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 716 | 46%
| Started Late (from Baseline) | F | 515
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 609 | 39%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 609 | 39%
| Finished Late | F | 492
| Completed Ahead | F | 48 | 8%
| Completed Delayed | F | 492 | 81%
| Completed On-Schedule | F | 69 | 11%
| Accelerated | F | 13 | 2%
| Days Variance | F | 83556 | 13720%
| Days Early | F | 1212 | 199%
| Days Late | F | 84767 | 13919%
| Avg Days Early | F | 25
| Avg Days Late | F | 172
| Avg Variance | F | 137
| Actually Finished | F | 609 | 35%
| Took Longer than Planned | F | 303 | 43%
| Took Less Than Planned | F | 157 | 22%
| Completed (w/Baseline Duration) | F | 585 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 609 | 51%
| Missed Durations | F | 271 | 44%
| Missed Durations & Late Actual Finish | F | 253 | 42%
| Completed Ahead | F | 48 | 8%
| Completed Delayed | F | 492 | 81%
| Completed On-Schedule | F | 69 | 11%
| Accelerated | F | 13 | 2%
| Days Variance | F | 83556 | 13720%
| Days Early | F | 1212 | 199%
| Days Late | F | 84767 | 13919%
| Avg Days Early | F | 25
| Avg Days Late | F | 172
| Avg Variance | F | 137
| Actually Finished | F | 609 | 35%
| Took Longer than Planned | F | 303 | 43%
| Took Less Than Planned | F | 157 | 22%
| Completed (w/Baseline Duration) | F | 585 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 609 | 51%
| Missed Durations | F | 271 | 44%
| Missed Durations & Late Actual Finish | F | 253 | 42%
| Baselined Tasks | F | 1544
| Baselined to Start - TOTAL | F | 1544
| Complete Task Starts - Cumulative | F | 715 | 58%
| Incomplete Task Starts - Cumulative (in work) | F | 513 | 42%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 1544
| Complete Task Finishes - Cumulative (in work) | F | 609 | 51%
| Incomplete Task Finishes - Cumulative | F | 596 | 51%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1205
| BEI - Complete Tasks | F | 609 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| BEI - Value Tasks (adjusted) | F | 0.51
| BEI - Complete Tasks (adjusted) | F | 609 | 51%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2025-02-07
| BEI - Value Milestones | F | 0.7
| BEI - Total Milestones | F | 128
| BEI - Complete Milestones | F | 89 | 70%
| BEI - Incomplete Milestones | F | 39 | 30%
| BEI - Value Milestones (adjusted) | F | 0.7
| BEI - Complete Milestones (adjusted) | F | 89 | 70%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2025-02-07
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2025-02-07
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2025-02-07
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1205
| BEI - Incomplete Tasks | F | 596 | 49%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 89 | 70%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0.7
| BEI - Total Milestones | F | 128
| BEI - Complete Milestones | F | 89 | 70%
| BEI - Incomplete Milestones | F | 39 | 30%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.51
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0.7
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2025-02-07
| Total Activities - DRM | F | 584
| Total Activities - DRM Graph | F | 584
| Status Date | F | 2025-02-07
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2025-02-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 0
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2025-02-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2025-08-06
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.63
| FEI - Value Task Finish - Cumulative | F | 2.75
| BEI - Value Tasks | F | 0.51
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0.7
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Complete Tasks | F | 609 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 2 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 7 | 1%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 2 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 1 | 0%
| Open Finish | F | 2 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 41 | 4%
| Status Date | F | 2025-02-07
| High Float 10% | F | 467 | 46%
| High Float 44d | F | 898 | 88%
| Zero Days Float | F | 2 | 0%
| Negative Float | F | 41 | 4%
| Hidden Duration (Planned) | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 9%
| Critical Merge Hotspot | F | 9 | 1%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Critical Diverge Hotspot | F | 11 | 1%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 35 | 69%
| Longest Path (Tasks & Milestones) | F | 43 | 84%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| Critical Milestones (To-Go) | F | 8 | 10%
| Longest Path (Milestones) | F | 8 | 16%
| Normal Tasks | F | 1554 | 73%
| Normal Tasks (To-Go) | F | 945 | 72%
| Critical Tasks (To-Go) | F | 35 | 4%
| Critical Tasks (In Progress) | F | 1 | 3%
| Zero Days Float | F | 2 | 0%
| Negative Float | F | 41 | 4%
| CP Logic Density™ | F | 7.58
| Time Now | F | 2025-02-07
| Forecast to be Finished | F | 1202 | 78%
| Completed On Time | T | 116 | 10%
| Completed Late | F | 488 | 41%
| Not Completed | F | 594 | 49%
| Baseline Finish Compliance | T | 10%
| Forecast to be Started | F | 1228 | 80%
| Started On Time | T | 200 | 16%
| Started Late | F | 515 | 42%
| Not Started | F | 513 | 42%
| Baseline Start Compliance | T | 22%
1 | Completed Activities | F | 609
HSD01 | Time Now | F | 2025-02-07
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 513 | 33%
HSD04 | Started Late | F | 515 | 42%
HSD05 | Forecast to be Finished but not Finished yet | T | 594 | 38%
HSD06 | Finished Late | F | 488 | 41%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2028-09-29
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 49 | 98%
SEM02 | BRI Current | T | 0.03
SEM03 | BRI Cumulative | F | 0.51
SEM04 | BPI Current | T | 0.03
SEM05 | BEI Current | F | 1.67
SEM06 | BEI Cumulative | T | 0.51
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.75
SEM07 | To Go - Planned Task Starts - Count | T | 836
SEM07 | To Go - BEI - Task Finishes - Count | T | 940
SEM07 | To Go - Baselined Task Starts - Count | T | 828
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 521
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 315
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 605
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 339
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.75
SEM07 | To Go - Planned Task Starts - Count | T | 836
SEM07 | To Go - BEI - Task Finishes - Count | T | 940
SEM07 | To Go - Baselined Task Starts - Count | T | 828
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 836
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 521
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 315
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 944
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 605
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 339
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 521
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 315
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 605
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 339
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.75
SEM07 | To Go - Planned Task Starts - Count | T | 836
SEM07 | To Go - BEI - Task Finishes - Count | T | 940
SEM07 | To Go - Baselined Task Starts - Count | T | 828
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | TC-BEI | T | 2.77
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -2.15
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Large-Test-File2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Large Test File2 (3/10/2025 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2025-03-10
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 1 | 0%
| Wrong Status - Actual Finishes | F | 4 | 1%
| Invalid Forecast Dates | F | 338 | 34%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 4 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 3 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 122 | 12%
| Status Date | F | 2025-03-10
| High Float 44d | F | 717 | 72%
| Zero Days Float | F | 66 | 7%
| Hidden Duration (Planned) | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 2%
| Critical Merge Hotspot | F | 35 | 4%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Critical Diverge Hotspot | F | 22 | 2%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 354 | 35%
| Negative Float | F | 122 | 12%
| Tasks & Milestones (To Go) | F | 998 | 58%
| Milestones (To-Go) | F | 79 | 8%
| Normal Tasks (To-Go) | F | 919 | 92%
| Normal Tasks (To-Go, In Progress) | F | 92 | 9%
| Critical Path (Tasks & Milestones) | F | 185 | 19%
| Critical Path (Milestones) | F | 15 | 8%
| Critical Path (Normal Tasks) | F | 170 | 92%
| Critical Path (Normal In Progress) | F | 4 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11
| Negative Float | F | 122 | 12%
| Zero Days Float | F | 66 | 7%
| Near-Critical (<10 Days Float) | F | 242 | 24%
| CP Logic Density™ | F | 4.27
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1228
| BEI - Complete Tasks | F | 632 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| Status Date | F | 2025-03-10
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2028-03-06
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 0
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | 324 | 39%
| Status Date | F | 2025-03-10
| Total Activities | F | 2124
| Milestones | F | 169 | 8%
| Normal Tasks | F | 1553 | 73%
| Summaries | F | 402 | 19%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 1722 | 81%
| Completed Tasks & Milestones | F | 724 | 42%
| Completed Milestones | F | 90 | 53%
| Completed Tasks | F | 634 | 41%
| Total Activities (To-Go) - % of Total | F | 1284 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 998 | 78%
| Milestones (To-Go) | F | 79 | 6%
| Normal Tasks (To-Go) | F | 919 | 72%
| Summaries (To-Go) | F | 286 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 185 | 82%
| Longest Path (Normal Tasks) | F | 170 | 76%
| Longest Path (Milestones) | F | 15 | 7%
| Critical Milestones (To-Go) | F | 15 | 8%
| Critical Normal Tasks (To-Go) | F | 170 | 92%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 1543
| Scheduled to Start | F | 1553
| Actual Starts | F | 726
| Baselined to Finish | F | 1543
| Scheduled to Finish | F | 1553
| Actual Finishes | F | 634
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.49
| FEI - Value Task Finish - Cumulative | F | 2.75
| Current Baseline to Start & Started (BL Plan) | F | 723
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 820
| Current Baseline to Finish & Finished (BL Plan) | F | 632
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 911
| Duration Ratio Metric (DRM) | F | 608
| DRM Graph | F | 608
| Baselined to Start | F | 911
| Scheduled to Start | F | 919
| Baselined to Finish | F | 911
| Scheduled to Finish | F | 919
| BEI - Value Activities | F | 0.53
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 998 | 78%
| Critical Path To-Go | F | 185 | 19%
| Status Date | F | 2025-03-10
| Total Activities | F | 2124
| Milestones | F | 169 | 8%
| Normal Tasks | F | 1553 | 73%
| Summaries | F | 402 | 19%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 1722 | 81%
| Completed Tasks & Milestones | F | 724 | 42%
| Completed Milestones | F | 90 | 53%
| Completed Tasks | F | 634 | 41%
| Total Activities (To-Go) - % of Total | F | 1284 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 998 | 78%
| Milestones (To-Go) | F | 79 | 6%
| Normal Tasks (To-Go) | F | 919 | 72%
| Summaries (To-Go) | F | 286 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 185 | 82%
| Longest Path (Normal Tasks) | F | 170 | 76%
| Longest Path (Milestones) | F | 15 | 7%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2025-03-10
| Total Activities (To-Go) - % of Total | F | 1284 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 998 | 78%
| Summary-to-Task Ratio (To-Go) | F | 1:03 | 0.31
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.09
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 185 | 19%
| Wrong Status (To-Go) | F | 1 | 0%
| Invalid Forecast Dates | F | 338 | 34%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 998 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 998 | 78%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 4 | 0%
| Avg. Original Duration | F | 42
| Avg. Remaining Duration | F | 19
| High Baseline Duration (44d) | F | 86 | 9%
| High Planned Duration (44d) | F | 120 | 13%
| Insufficient Detail™ | F | 21 | 2%
| Critical Activities (To-Go) | F | 170 | 18%
| Avg. Critical Original Duration | F | 18
| Avg. Critical Remaining Duration | F | 12
| Critical w/High Baseline Duration (44d) | F | 4 | 0%
| Critical w/High Planned Duration (44d) | F | 6 | 4%
| Critical w/Insufficient Detail™ | F | 2 | 0%
| Activities (To-Go) | F | 919 | 59%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 3 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 998 | 100%
| No Constraints | F | 997 | 100%
| Logic Density™ | F | 3.15
| Logic Density™ - Predecessors | F | 1.79
| Logic Density™ - Successors | F | 1.37
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 905 | 100%
| SS Predecessors | F | 42 | 4%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 36 | 4%
| FS Predecessors | F | 994 | 100%
| All Activities w/Successors | F | 996 | 100%
| SS Successors | F | 42 | 4%
| FF Successors | F | 31 | 3%
| SF Successors | F | 0 | 0%
| FS Successors | F | 990 | 99%
| Missing Logic | F | 3 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 1 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.82
| All Activities w/Predecessors | F | 905 | 100%
| Total # Predecessors | F | 1649
| Activities Missing Predecessors | F | 1 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 2 | 0%
| Total # Predecessor Lags | F | 2
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 22
| Hidden Duration (Planned) | F | 2 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 123 | 14%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 35 | 4%
| Logic Hotspot™ | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 2%
| Logic Density™ - Successors | F | 1.37
| All Activities w/Successors | F | 996 | 100%
| Activities Missing Successors | F | 2 | 0%
| Total # Successors | F | 1364
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 8 | 1%
| Total# of Successor Lags | F | 8
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 72 | 7%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 22 | 2%
| Logic Hotspot™ | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 2%
| Actually Finished - Tasks & Milestones | F | 724 | 42%
| Completed Ahead - Tasks & Milestones | F | 55 | 8%
| Completed On-Schedule - Tasks & Milestones | F | 81 | 11%
| Completed Delayed - Tasks & Milestones | F | 585 | 81%
| Avg Days Finished Early - Tasks & Milestones | F | 24
| Avg Days Finished Late - Tasks & Milestones | F | 169
| Avg Finish Variance - Tasks & Milestones | F | 134
| Actually Finished - Tasks | F | 634 | 41%
| Completed Ahead - Tasks | F | 48 | 8%
| Completed On-Schedule - Tasks | F | 69 | 11%
| Completed Delayed - Tasks | F | 515 | 81%
| Accelerated Durations Early/On-Schedule - Tasks | F | 12 | 1%
| Accelerated Durations Late - Tasks | F | 105 | 7%
| Extended Durations - Tasks | F | 285 | 18%
| Actually Finished - Milestones | F | 90 | 53%
| Completed Ahead - Milestones | F | 7 | 8%
| Completed On-Schedule - Milestones | F | 12 | 13%
| Completed Delayed - Milestones | F | 70 | 78%
| Actually Started - Tasks | F | 92 | 6%
| In-Progress Started Ahead - Tasks | F | 8 | 9%
| In-Progress Started On-Schedule - Tasks | F | 15 | 16%
| In-Progress Started Delayed - Tasks | F | 68 | 74%
| In-Progress Delayed Finish - Tasks | F | 91 | 99%
| Avg Days Started Early | F | 16
| Avg Days Started Late | F | 118
| Avg Start Variance | F | 101
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 906 | 53%
| Planned Ahead Start - Tasks & Milestones | F | 97 | 11%
| Planned On Schedule Start - Tasks & Milestones | F | 1 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 798 | 88%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 827 | 53%
| Planned Ahead Start - Tasks | F | 89 | 11%
| Planned On Schedule Start - Tasks | F | 1 | 0%
| Planned Delayed Start - Tasks | F | 730 | 88%
| Planned Delayed Finish - Tasks | F | 731 | 88%
| Scheduled to Start - Milestones | F | 79 | 47%
| Planned Ahead Start - Milestones | F | 8 | 10%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 68 | 86%
| Planned Delayed Finish - Milestones | F | 68 | 86%
| Schedule Baseline Activities | F | 1708 | 99%
| Scheduled/Baselined to Start | F | 987
| Scheduled/Baselined to Finish | F | 987
| Start/ed | F | 816
| Finish/ed | F | 724
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 424 | 81%
| Completed Delayed (>30 days) | F | 443 | 86%
| SPI(t) | F | 8.14
| Scheduled Activities | F | 1722 | 100%
| Scheduled to Start | F | 998 | 58%
| Scheduled to Finish | F | 998 | 58%
| Longest Path - Critical Activities and Milestones | F | 185 | 19%
| Critical Milestones (To-Go) | F | 15 | 19%
| Critical Tasks (To-Go) | F | 170 | 18%
| Critical Tasks (In Progress) | F | 4 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| High Float 10% | F | 354 | 35%
| High Float 44d | F | 717 | 72%
| Zero Days Float | F | 66 | 7%
| Negative Float | F | 122 | 12%
| Longest Path - Critical Activities and Milestones | F | 185 | 19%
| Critical Milestones (To-Go) | F | 15 | 19%
| Critical Tasks (To-Go) | F | 170 | 18%
| Critical Tasks (In Progress) | F | 4 | 2%
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.09
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| Logic Density™ | F | 3.13
| CP Logic Density™ | F | 4.27
| Critical w/Missing Logic | F | 1 | 0%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 66 | 7%
| Negative Float | F | 122 | 12%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 4 | 0%
| Critical w/High Planned Duration (44d) | F | 6 | 4%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 1543
| Scheduled to Start | F | 1553
| Actual Starts | F | 726
| Baselined to Finish | F | 1543
| Scheduled to Finish | F | 1553
| Actual Finishes | F | 634
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| Baselined to Start | F | 1543
| Scheduled to Start | F | 1553
| Actual Starts | F | 726
| Current Baselined to Start & Started | F | 723
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 1543
| Scheduled to Finish | F | 1553
| Actual Finishes | F | 634
| Current Baselined to Finish & Finished | F | 632
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| Baselined to Start - To Time Now | F | 1247 | 81%
| Scheduled to Start - To Time Now | F | 1247 | 80%
| Started | F | 722
| Started Late | F | 522
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| BEI - Value Task Starts | F | 0.58
| Baselined to Finish - To Time Now | F | 1228 | 80%
| Scheduled to Finish - To Time Now | F | 1228 | 80%
| Finished | F | 632
| Finished Late | F | 515
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| BEI - Value Task Finishes | F | 0.51
| Started - Future | F | 1
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.49
| FEI - Value Task Finish - Cumulative | F | 2.75
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 723
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 820
| Baselined to Start - Check | F | 1543
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 632
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 911
| Baselined to Finish - Check | F | 1543
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 723
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 820
| Current Baseline to Finish & Finished (BL Plan) | F | 632
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 911
| Baselined to Start | F | 1247
| Scheduled to Start | F | 1247 | 100%
| Started - Scheduled | F | 722 | 58%
| Started - Baseline Comparison | F | 722 | 58%
| BEI - Value Task Starts | F | 0.58
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 1228
| Scheduled to Finish | F | 1228
| Finished | F | 632
| BEI - Value Task Finishes | F | 0.51
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2025-03-10
| Started (incl. Future Baseline Starts) - Scheduled | F | 726 | 47%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 723 | 47%
| Started Late (from Baseline) | F | 522
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 632 | 41%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 632 | 41%
| Finished Late | F | 515
| Completed Ahead | F | 48 | 8%
| Completed Delayed | F | 515 | 81%
| Completed On-Schedule | F | 69 | 11%
| Accelerated | F | 13 | 2%
| Days Variance | F | 91676 | 14460%
| Days Early | F | 1212 | 191%
| Days Late | F | 92888 | 14651%
| Avg Days Early | F | 25
| Avg Days Late | F | 180
| Avg Variance | F | 145
| Actually Finished | F | 634 | 37%
| Took Longer than Planned | F | 317 | 44%
| Took Less Than Planned | F | 160 | 22%
| Completed (w/Baseline Duration) | F | 608 | 39%
| Completed (w/o Baseline Duration) | F | 2 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 632 | 51%
| Missed Durations | F | 285 | 45%
| Missed Durations & Late Actual Finish | F | 267 | 42%
| Completed Ahead | F | 48 | 8%
| Completed Delayed | F | 515 | 81%
| Completed On-Schedule | F | 69 | 11%
| Accelerated | F | 13 | 2%
| Days Variance | F | 91676 | 14460%
| Days Early | F | 1212 | 191%
| Days Late | F | 92888 | 14651%
| Avg Days Early | F | 25
| Avg Days Late | F | 180
| Avg Variance | F | 145
| Actually Finished | F | 634 | 37%
| Took Longer than Planned | F | 317 | 44%
| Took Less Than Planned | F | 160 | 22%
| Completed (w/Baseline Duration) | F | 608 | 39%
| Completed (w/o Baseline Duration) | F | 2 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 632 | 51%
| Missed Durations | F | 285 | 45%
| Missed Durations & Late Actual Finish | F | 267 | 42%
| Baselined Tasks | F | 1543
| Baselined to Start - TOTAL | F | 1543
| Complete Task Starts - Cumulative | F | 722 | 58%
| Incomplete Task Starts - Cumulative (in work) | F | 525 | 42%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 1543
| Complete Task Finishes - Cumulative (in work) | F | 632 | 51%
| Incomplete Task Finishes - Cumulative | F | 596 | 51%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1228
| BEI - Complete Tasks | F | 632 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| BEI - Value Tasks (adjusted) | F | 0.51
| BEI - Complete Tasks (adjusted) | F | 632 | 51%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| BEI - Value Milestones | F | 0.69
| BEI - Total Milestones | F | 129
| BEI - Complete Milestones | F | 89 | 69%
| BEI - Incomplete Milestones | F | 40 | 31%
| BEI - Value Milestones (adjusted) | F | 0.69
| BEI - Complete Milestones (adjusted) | F | 89 | 69%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1228
| BEI - Incomplete Tasks | F | 596 | 49%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 89 | 69%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0.69
| BEI - Total Milestones | F | 129
| BEI - Complete Milestones | F | 89 | 69%
| BEI - Incomplete Milestones | F | 40 | 31%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.51
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0.69
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| Total Activities - DRM | F | 608
| Total Activities - DRM Graph | F | 608
| Status Date | F | 2025-03-10
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 0
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2028-03-06
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.49
| FEI - Value Task Finish - Cumulative | F | 2.75
| BEI - Value Tasks | F | 0.51
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0.69
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Complete Tasks | F | 632 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 1 | 0%
| Invalid Forecast Dates | F | 338 | 34%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 4 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 3 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 1 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 122 | 12%
| Status Date | F | 2025-03-10
| High Float 10% | F | 354 | 35%
| High Float 44d | F | 717 | 72%
| Zero Days Float | F | 66 | 7%
| Negative Float | F | 122 | 12%
| Hidden Duration (Planned) | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 2%
| Critical Merge Hotspot | F | 35 | 4%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Critical Diverge Hotspot | F | 22 | 2%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 170 | 76%
| Longest Path (Tasks & Milestones) | F | 185 | 82%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| Critical Milestones (To-Go) | F | 15 | 19%
| Longest Path (Milestones) | F | 15 | 7%
| Normal Tasks | F | 1553 | 73%
| Normal Tasks (To-Go) | F | 919 | 72%
| Critical Tasks (To-Go) | F | 170 | 18%
| Critical Tasks (In Progress) | F | 4 | 2%
| Zero Days Float | F | 66 | 7%
| Negative Float | F | 122 | 12%
| CP Logic Density™ | F | 4.27
| Time Now | F | 2025-03-10
| Forecast to be Finished | F | 1227 | 80%
| Completed On Time | T | 159 | 13%
| Completed Late | F | 581 | 47%
| Not Completed | F | 595 | 48%
| Baseline Finish Compliance | T | 13%
| Forecast to be Started | F | 1247 | 81%
| Started On Time | T | 250 | 20%
| Started Late | F | 605 | 49%
| Not Started | F | 525 | 42%
| Baseline Start Compliance | F | 26%
1 | Completed Activities | F | 630
HSD01 | Time Now | F | 2025-03-10
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 525 | 34%
HSD04 | Started Late | F | 605 | 49%
HSD05 | Forecast to be Finished but not Finished yet | T | 595 | 39%
HSD06 | Finished Late | F | 581 | 47%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2029-04-20
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 24 | 100%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.51
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | F | 1
SEM06 | BEI Cumulative | T | 0.51
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.42
SEM07 | To Go - Planned Task Starts - Count | T | 662
SEM07 | To Go - BEI - Task Finishes - Count | T | 766
SEM07 | To Go - Baselined Task Starts - Count | T | 655
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 398
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 263
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 492
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 279
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.42
SEM07 | To Go - Planned Task Starts - Count | T | 662
SEM07 | To Go - BEI - Task Finishes - Count | T | 766
SEM07 | To Go - Baselined Task Starts - Count | T | 655
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 661
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 398
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 263
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 771
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 492
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 279
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 398
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 263
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 492
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 279
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.42
SEM07 | To Go - Planned Task Starts - Count | T | 662
SEM07 | To Go - BEI - Task Finishes - Count | T | 766
SEM07 | To Go - Baselined Task Starts - Count | T | 655
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | TC-BEI | T | 2.45
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -1.91
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Large-Test-File-Leveled
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Large Test File Leveled (2/7/2025 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2025-02-07
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 2 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 6 | 1%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 2 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 0 | 0%
| Open Finish | F | 2 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 47 | 5%
| Status Date | F | 2025-02-07
| High Float 44d | F | 912 | 89%
| Zero Days Float | F | 2 | 0%
| Hidden Duration (Planned) | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 8%
| Critical Merge Hotspot | F | 10 | 1%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Critical Diverge Hotspot | F | 13 | 1%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 467 | 46%
| Negative Float | F | 47 | 5%
| Tasks & Milestones (To Go) | F | 1024 | 59%
| Milestones (To-Go) | F | 79 | 8%
| Normal Tasks (To-Go) | F | 945 | 92%
| Normal Tasks (To-Go, In Progress) | F | 108 | 11%
| Critical Path (Tasks & Milestones) | F | 49 | 5%
| Critical Path (Milestones) | F | 8 | 16%
| Critical Path (Normal Tasks) | F | 41 | 84%
| Critical Path (Normal In Progress) | F | 1 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:05
| Negative Float | F | 47 | 5%
| Zero Days Float | F | 2 | 0%
| Near-Critical (<10 Days Float) | F | 49 | 5%
| CP Logic Density™ | F | 7.14
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1205
| BEI - Complete Tasks | F | 609 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| Status Date | F | 2025-02-07
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2025-02-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2025-08-06
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2025-02-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 0
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | 203 | 29%
| Status Date | F | 2025-02-07
| Total Activities | F | 2125
| Milestones | F | 169 | 8%
| Normal Tasks | F | 1554 | 73%
| Summaries | F | 402 | 19%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 1723 | 81%
| Completed Tasks & Milestones | F | 699 | 41%
| Completed Milestones | F | 90 | 53%
| Completed Tasks | F | 609 | 39%
| Total Activities (To-Go) - % of Total | F | 1309 | 62%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78%
| Milestones (To-Go) | F | 79 | 6%
| Normal Tasks (To-Go) | F | 945 | 72%
| Summaries (To-Go) | F | 285 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 49 | 84%
| Longest Path (Normal Tasks) | F | 41 | 71%
| Longest Path (Milestones) | F | 8 | 14%
| Critical Milestones (To-Go) | F | 8 | 16%
| Critical Normal Tasks (To-Go) | F | 41 | 84%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 1544
| Scheduled to Start | F | 1554
| Actual Starts | F | 717
| Baselined to Finish | F | 1544
| Scheduled to Finish | F | 1554
| Actual Finishes | F | 609
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10%
| Started Delayed (>60 days) | F | 366 | 71%
| Completed Delayed (<=30 days) | F | 71 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11%
| Completed Delayed (>60 days) | F | 365 | 74%
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.63
| FEI - Value Task Finish - Cumulative | F | 2.75
| Current Baseline to Start & Started (BL Plan) | F | 716
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 828
| Current Baseline to Finish & Finished (BL Plan) | F | 609
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 935
| Duration Ratio Metric (DRM) | F | 584
| DRM Graph | F | 584
| Baselined to Start | F | 935
| Scheduled to Start | F | 945
| Baselined to Finish | F | 935
| Scheduled to Finish | F | 945
| BEI - Value Activities | F | 0.52
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78%
| Critical Path To-Go | F | 49 | 5%
| Status Date | F | 2025-02-07
| Total Activities | F | 2125
| Milestones | F | 169 | 8%
| Normal Tasks | F | 1554 | 73%
| Summaries | F | 402 | 19%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 1723 | 81%
| Completed Tasks & Milestones | F | 699 | 41%
| Completed Milestones | F | 90 | 53%
| Completed Tasks | F | 609 | 39%
| Total Activities (To-Go) - % of Total | F | 1309 | 62%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78%
| Milestones (To-Go) | F | 79 | 6%
| Normal Tasks (To-Go) | F | 945 | 72%
| Summaries (To-Go) | F | 285 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 49 | 84%
| Longest Path (Normal Tasks) | F | 41 | 71%
| Longest Path (Milestones) | F | 8 | 14%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2025-02-07
| Total Activities (To-Go) - % of Total | F | 1309 | 62%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78%
| Summary-to-Task Ratio (To-Go) | F | 1:03 | 0.3
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.08
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:05 | 0.2
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 49 | 5%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 2 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 1024 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 6 | 1%
| Avg. Original Duration | F | 41
| Avg. Remaining Duration | F | 16
| High Baseline Duration (44d) | F | 87 | 9%
| High Planned Duration (44d) | F | 125 | 13%
| Insufficient Detail™ | F | 21 | 2%
| Critical Activities (To-Go) | F | 41 | 4%
| Avg. Critical Original Duration | F | 15
| Avg. Critical Remaining Duration | F | 10
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 2 | 5%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 945 | 61%
| Total Constraints | F | 82 | 8%
| Start No Earlier Than | F | 80 | 8%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 1 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 1 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 1 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 1 | 0%
| Open Ends w/o Constraints | F | 1 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 942 | 92%
| No Constraints | F | 942 | 92%
| Logic Density™ | F | 3.14
| Logic Density™ - Predecessors | F | 1.77
| Logic Density™ - Successors | F | 1.36
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 915 | 100%
| SS Predecessors | F | 45 | 4%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 36 | 4%
| FS Predecessors | F | 1020 | 100%
| All Activities w/Successors | F | 1022 | 100%
| SS Successors | F | 47 | 5%
| FF Successors | F | 31 | 3%
| SF Successors | F | 0 | 0%
| FS Successors | F | 1014 | 99%
| Missing Logic | F | 2 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 1 | 0%
| Open Finish | F | 2 | 0%
| Logic Density™ - Predecessors | F | 1.82
| All Activities w/Predecessors | F | 915 | 100%
| Total # Predecessors | F | 1665
| Activities Missing Predecessors | F | 1 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 2 | 0%
| Total # Predecessor Lags | F | 2
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 22
| Hidden Duration (Planned) | F | 2 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 125 | 14%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 10 | 1%
| Logic Hotspot™ | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 8%
| Logic Density™ - Successors | F | 1.36
| All Activities w/Successors | F | 1022 | 100%
| Activities Missing Successors | F | 2 | 0%
| Total # Successors | F | 1395
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 8 | 1%
| Total# of Successor Lags | F | 8
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 72 | 7%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 13 | 1%
| Logic Hotspot™ | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 8%
| Actually Finished - Tasks & Milestones | F | 699 | 41%
| Completed Ahead - Tasks & Milestones | F | 55 | 8%
| Completed On-Schedule - Tasks & Milestones | F | 81 | 12%
| Completed Delayed - Tasks & Milestones | F | 562 | 80%
| Avg Days Finished Early - Tasks & Milestones | F | 24
| Avg Days Finished Late - Tasks & Milestones | F | 161
| Avg Finish Variance - Tasks & Milestones | F | 128
| Actually Finished - Tasks | F | 609 | 39%
| Completed Ahead - Tasks | F | 48 | 8%
| Completed On-Schedule - Tasks | F | 69 | 11%
| Completed Delayed - Tasks | F | 492 | 81%
| Accelerated Durations Early/On-Schedule - Tasks | F | 12 | 1%
| Accelerated Durations Late - Tasks | F | 106 | 7%
| Extended Durations - Tasks | F | 271 | 17%
| Actually Finished - Milestones | F | 90 | 53%
| Completed Ahead - Milestones | F | 7 | 8%
| Completed On-Schedule - Milestones | F | 12 | 13%
| Completed Delayed - Milestones | F | 70 | 78%
| Actually Started - Tasks | F | 108 | 7%
| In-Progress Started Ahead - Tasks | F | 10 | 9%
| In-Progress Started On-Schedule - Tasks | F | 17 | 16%
| In-Progress Started Delayed - Tasks | F | 80 | 74%
| In-Progress Delayed Finish - Tasks | F | 106 | 98%
| Avg Days Started Early | F | 15
| Avg Days Started Late | F | 121
| Avg Start Variance | F | 106
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 916 | 53%
| Planned Ahead Start - Tasks & Milestones | F | 40 | 4%
| Planned On Schedule Start - Tasks & Milestones | F | 27 | 3%
| Planned Delayed Start - Tasks & Milestones | F | 837 | 91%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 837 | 54%
| Planned Ahead Start - Tasks | F | 40 | 5%
| Planned On Schedule Start - Tasks | F | 26 | 3%
| Planned Delayed Start - Tasks | F | 762 | 91%
| Planned Delayed Finish - Tasks | F | 776 | 93%
| Scheduled to Start - Milestones | F | 79 | 47%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 1 | 1%
| Planned Delayed Start - Milestones | F | 75 | 95%
| Planned Delayed Finish - Milestones | F | 75 | 95%
| Schedule Baseline Activities | F | 1709 | 99%
| Scheduled/Baselined to Start | F | 1011
| Scheduled/Baselined to Finish | F | 1011
| Start/ed | F | 807
| Finish/ed | F | 699
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 417 | 81%
| Completed Delayed (>30 days) | F | 421 | 86%
| SPI(t) | F | 8.22
| Scheduled Activities | F | 1723 | 100%
| Scheduled to Start | F | 1024 | 59%
| Scheduled to Finish | F | 1024 | 59%
| Longest Path - Critical Activities and Milestones | F | 49 | 5%
| Critical Milestones (To-Go) | F | 8 | 10%
| Critical Tasks (To-Go) | F | 41 | 4%
| Critical Tasks (In Progress) | F | 1 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:05 | 0.2
| High Float 10% | F | 467 | 46%
| High Float 44d | F | 912 | 89%
| Zero Days Float | F | 2 | 0%
| Negative Float | F | 47 | 5%
| Longest Path - Critical Activities and Milestones | F | 49 | 5%
| Critical Milestones (To-Go) | F | 8 | 10%
| Critical Tasks (To-Go) | F | 41 | 4%
| Critical Tasks (In Progress) | F | 1 | 2%
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.08
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:05 | 0.2
| Logic Density™ | F | 3.14
| CP Logic Density™ | F | 7.14
| Critical w/Missing Logic | F | 1 | 0%
| Critical w/Hard Constraints | F | 1 | 0%
| Zero Days Float | F | 2 | 0%
| Negative Float | F | 47 | 5%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 2 | 5%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 1 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 1544
| Scheduled to Start | F | 1554
| Actual Starts | F | 717
| Baselined to Finish | F | 1544
| Scheduled to Finish | F | 1554
| Actual Finishes | F | 609
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10%
| Started Delayed (>60 days) | F | 366 | 71%
| Completed Delayed (<=30 days) | F | 71 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11%
| Completed Delayed (>60 days) | F | 365 | 74%
| Baselined to Start | F | 1544
| Scheduled to Start | F | 1554
| Actual Starts | F | 717
| Current Baselined to Start & Started | F | 716
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 1544
| Scheduled to Finish | F | 1554
| Actual Finishes | F | 609
| Current Baselined to Finish & Finished | F | 609
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10%
| Started Delayed (>60 days) | F | 366 | 71%
| Completed Delayed (<=30 days) | F | 71 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11%
| Completed Delayed (>60 days) | F | 365 | 74%
| Baselined to Start - To Time Now | F | 1228 | 80%
| Scheduled to Start - To Time Now | F | 1228 | 79%
| Started | F | 715
| Started Late | F | 515
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10%
| Started Delayed (>60 days) | F | 366 | 71%
| BEI - Value Task Starts | F | 0.58
| Baselined to Finish - To Time Now | F | 1205 | 78%
| Scheduled to Finish - To Time Now | F | 1205 | 78%
| Finished | F | 609
| Finished Late | F | 492
| Completed Delayed (<=30 days) | F | 71 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11%
| Completed Delayed (>60 days) | F | 365 | 74%
| BEI - Value Task Finishes | F | 0.51
| Started - Future | F | 1
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.63
| FEI - Value Task Finish - Cumulative | F | 2.75
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 716
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 828
| Baselined to Start - Check | F | 1544
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 609
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 935
| Baselined to Finish - Check | F | 1544
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 716
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 828
| Current Baseline to Finish & Finished (BL Plan) | F | 609
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 935
| Baselined to Start | F | 1228
| Scheduled to Start | F | 1228 | 100%
| Started - Scheduled | F | 715 | 58%
| Started - Baseline Comparison | F | 715 | 58%
| BEI - Value Task Starts | F | 0.58
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 1205
| Scheduled to Finish | F | 1205
| Finished | F | 609
| BEI - Value Task Finishes | F | 0.51
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2025-02-07
| Started (incl. Future Baseline Starts) - Scheduled | F | 717 | 46%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 716 | 46%
| Started Late (from Baseline) | F | 515
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 609 | 39%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 609 | 39%
| Finished Late | F | 492
| Completed Ahead | F | 48 | 8%
| Completed Delayed | F | 492 | 81%
| Completed On-Schedule | F | 69 | 11%
| Accelerated | F | 13 | 2%
| Days Variance | F | 83556 | 13720%
| Days Early | F | 1212 | 199%
| Days Late | F | 84767 | 13919%
| Avg Days Early | F | 25
| Avg Days Late | F | 172
| Avg Variance | F | 137
| Actually Finished | F | 609 | 35%
| Took Longer than Planned | F | 303 | 43%
| Took Less Than Planned | F | 157 | 22%
| Completed (w/Baseline Duration) | F | 585 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 609 | 51%
| Missed Durations | F | 271 | 44%
| Missed Durations & Late Actual Finish | F | 253 | 42%
| Completed Ahead | F | 48 | 8%
| Completed Delayed | F | 492 | 81%
| Completed On-Schedule | F | 69 | 11%
| Accelerated | F | 13 | 2%
| Days Variance | F | 83556 | 13720%
| Days Early | F | 1212 | 199%
| Days Late | F | 84767 | 13919%
| Avg Days Early | F | 25
| Avg Days Late | F | 172
| Avg Variance | F | 137
| Actually Finished | F | 609 | 35%
| Took Longer than Planned | F | 303 | 43%
| Took Less Than Planned | F | 157 | 22%
| Completed (w/Baseline Duration) | F | 585 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 609 | 51%
| Missed Durations | F | 271 | 44%
| Missed Durations & Late Actual Finish | F | 253 | 42%
| Baselined Tasks | F | 1544
| Baselined to Start - TOTAL | F | 1544
| Complete Task Starts - Cumulative | F | 715 | 58%
| Incomplete Task Starts - Cumulative (in work) | F | 513 | 42%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 1544
| Complete Task Finishes - Cumulative (in work) | F | 609 | 51%
| Incomplete Task Finishes - Cumulative | F | 596 | 51%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1205
| BEI - Complete Tasks | F | 609 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| BEI - Value Tasks (adjusted) | F | 0.51
| BEI - Complete Tasks (adjusted) | F | 609 | 51%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2025-02-07
| BEI - Value Milestones | F | 0.7
| BEI - Total Milestones | F | 128
| BEI - Complete Milestones | F | 89 | 70%
| BEI - Incomplete Milestones | F | 39 | 30%
| BEI - Value Milestones (adjusted) | F | 0.7
| BEI - Complete Milestones (adjusted) | F | 89 | 70%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2025-02-07
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2025-02-07
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2025-02-07
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1205
| BEI - Incomplete Tasks | F | 596 | 49%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 89 | 70%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0.7
| BEI - Total Milestones | F | 128
| BEI - Complete Milestones | F | 89 | 70%
| BEI - Incomplete Milestones | F | 39 | 30%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.51
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0.7
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2025-02-07
| Total Activities - DRM | F | 584
| Total Activities - DRM Graph | F | 584
| Status Date | F | 2025-02-07
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2025-02-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 0
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2025-02-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2025-08-06
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.63
| FEI - Value Task Finish - Cumulative | F | 2.75
| BEI - Value Tasks | F | 0.51
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0.7
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Complete Tasks | F | 609 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 2 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 6 | 1%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 2 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 1 | 0%
| Open Finish | F | 2 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 47 | 5%
| Status Date | F | 2025-02-07
| High Float 10% | F | 467 | 46%
| High Float 44d | F | 912 | 89%
| Zero Days Float | F | 2 | 0%
| Negative Float | F | 47 | 5%
| Hidden Duration (Planned) | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 8%
| Critical Merge Hotspot | F | 10 | 1%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Critical Diverge Hotspot | F | 13 | 1%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 41 | 71%
| Longest Path (Tasks & Milestones) | F | 49 | 84%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:05 | 0.2
| Critical Milestones (To-Go) | F | 8 | 10%
| Longest Path (Milestones) | F | 8 | 14%
| Normal Tasks | F | 1554 | 73%
| Normal Tasks (To-Go) | F | 945 | 72%
| Critical Tasks (To-Go) | F | 41 | 4%
| Critical Tasks (In Progress) | F | 1 | 2%
| Zero Days Float | F | 2 | 0%
| Negative Float | F | 47 | 5%
| CP Logic Density™ | F | 7.14
| Time Now | F | 2025-02-07
| Forecast to be Finished | F | 1202 | 78%
| Completed On Time | T | 116 | 10%
| Completed Late | F | 488 | 41%
| Not Completed | F | 594 | 49%
| Baseline Finish Compliance | T | 10%
| Forecast to be Started | F | 1228 | 80%
| Started On Time | T | 200 | 16%
| Started Late | F | 515 | 42%
| Not Started | F | 513 | 42%
| Baseline Start Compliance | T | 22%
1 | Completed Activities | F | 609
HSD01 | Time Now | F | 2025-02-07
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 513 | 33%
HSD04 | Started Late | F | 515 | 42%
HSD05 | Forecast to be Finished but not Finished yet | T | 594 | 38%
HSD06 | Finished Late | F | 488 | 41%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2028-09-29
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 49 | 98%
SEM02 | BRI Current | T | 0.03
SEM03 | BRI Cumulative | F | 0.51
SEM04 | BPI Current | T | 0.03
SEM05 | BEI Current | F | 1.67
SEM06 | BEI Cumulative | T | 0.51
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.75
SEM07 | To Go - Planned Task Starts - Count | T | 836
SEM07 | To Go - BEI - Task Finishes - Count | T | 940
SEM07 | To Go - Baselined Task Starts - Count | T | 828
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 521
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 315
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 605
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 339
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.75
SEM07 | To Go - Planned Task Starts - Count | T | 836
SEM07 | To Go - BEI - Task Finishes - Count | T | 940
SEM07 | To Go - Baselined Task Starts - Count | T | 828
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 836
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 521
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 315
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 944
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 605
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 339
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 521
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 315
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 605
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 339
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.75
SEM07 | To Go - Planned Task Starts - Count | T | 836
SEM07 | To Go - BEI - Task Finishes - Count | T | 940
SEM07 | To Go - Baselined Task Starts - Count | T | 828
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | TC-BEI | T | 2.77
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -2.15
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Large-Test-File-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Large Test File 2 (2/7/2025 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2025-02-07
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 2 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 7 | 1%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 2 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 0 | 0%
| Open Finish | F | 2 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 41 | 4%
| Status Date | F | 2025-02-07
| High Float 44d | F | 898 | 88%
| Zero Days Float | F | 2 | 0%
| Hidden Duration (Planned) | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 9%
| Critical Merge Hotspot | F | 9 | 1%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Critical Diverge Hotspot | F | 11 | 1%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 467 | 46%
| Negative Float | F | 41 | 4%
| Tasks & Milestones (To Go) | F | 1024 | 59%
| Milestones (To-Go) | F | 79 | 8%
| Normal Tasks (To-Go) | F | 945 | 92%
| Normal Tasks (To-Go, In Progress) | F | 108 | 11%
| Critical Path (Tasks & Milestones) | F | 43 | 4%
| Critical Path (Milestones) | F | 8 | 19%
| Critical Path (Normal Tasks) | F | 35 | 81%
| Critical Path (Normal In Progress) | F | 1 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04
| Negative Float | F | 41 | 4%
| Zero Days Float | F | 2 | 0%
| Near-Critical (<10 Days Float) | F | 74 | 7%
| CP Logic Density™ | F | 7.58
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1205
| BEI - Complete Tasks | F | 609 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| Status Date | F | 2025-02-07
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2025-02-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2025-08-06
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2025-02-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 0
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | 279 | 36%
| Status Date | F | 2025-02-07
| Total Activities | F | 2125
| Milestones | F | 169 | 8%
| Normal Tasks | F | 1554 | 73%
| Summaries | F | 402 | 19%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 1723 | 81%
| Completed Tasks & Milestones | F | 699 | 41%
| Completed Milestones | F | 90 | 53%
| Completed Tasks | F | 609 | 39%
| Total Activities (To-Go) - % of Total | F | 1309 | 62%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78%
| Milestones (To-Go) | F | 79 | 6%
| Normal Tasks (To-Go) | F | 945 | 72%
| Summaries (To-Go) | F | 285 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 43 | 84%
| Longest Path (Normal Tasks) | F | 35 | 69%
| Longest Path (Milestones) | F | 8 | 16%
| Critical Milestones (To-Go) | F | 8 | 19%
| Critical Normal Tasks (To-Go) | F | 35 | 81%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 1544
| Scheduled to Start | F | 1554
| Actual Starts | F | 717
| Baselined to Finish | F | 1544
| Scheduled to Finish | F | 1554
| Actual Finishes | F | 609
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10%
| Started Delayed (>60 days) | F | 366 | 71%
| Completed Delayed (<=30 days) | F | 71 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11%
| Completed Delayed (>60 days) | F | 365 | 74%
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.63
| FEI - Value Task Finish - Cumulative | F | 2.75
| Current Baseline to Start & Started (BL Plan) | F | 716
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 828
| Current Baseline to Finish & Finished (BL Plan) | F | 609
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 935
| Duration Ratio Metric (DRM) | F | 584
| DRM Graph | F | 584
| Baselined to Start | F | 935
| Scheduled to Start | F | 945
| Baselined to Finish | F | 935
| Scheduled to Finish | F | 945
| BEI - Value Activities | F | 0.52
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78%
| Critical Path To-Go | F | 43 | 4%
| Status Date | F | 2025-02-07
| Total Activities | F | 2125
| Milestones | F | 169 | 8%
| Normal Tasks | F | 1554 | 73%
| Summaries | F | 402 | 19%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 1723 | 81%
| Completed Tasks & Milestones | F | 699 | 41%
| Completed Milestones | F | 90 | 53%
| Completed Tasks | F | 609 | 39%
| Total Activities (To-Go) - % of Total | F | 1309 | 62%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78%
| Milestones (To-Go) | F | 79 | 6%
| Normal Tasks (To-Go) | F | 945 | 72%
| Summaries (To-Go) | F | 285 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 43 | 84%
| Longest Path (Normal Tasks) | F | 35 | 69%
| Longest Path (Milestones) | F | 8 | 16%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2025-02-07
| Total Activities (To-Go) - % of Total | F | 1309 | 62%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78%
| Summary-to-Task Ratio (To-Go) | F | 1:03 | 0.3
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.08
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 43 | 4%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 2 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 1024 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 7 | 1%
| Avg. Original Duration | F | 41
| Avg. Remaining Duration | F | 16
| High Baseline Duration (44d) | F | 87 | 9%
| High Planned Duration (44d) | F | 124 | 13%
| Insufficient Detail™ | F | 22 | 2%
| Critical Activities (To-Go) | F | 35 | 4%
| Avg. Critical Original Duration | F | 14
| Avg. Critical Remaining Duration | F | 9
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 2 | 6%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 945 | 61%
| Total Constraints | F | 82 | 8%
| Start No Earlier Than | F | 80 | 8%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 1 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 1 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 1 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 1 | 0%
| Open Ends w/o Constraints | F | 1 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 942 | 92%
| No Constraints | F | 942 | 92%
| Logic Density™ | F | 3.14
| Logic Density™ - Predecessors | F | 1.77
| Logic Density™ - Successors | F | 1.36
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 915 | 100%
| SS Predecessors | F | 45 | 4%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 36 | 4%
| FS Predecessors | F | 1020 | 100%
| All Activities w/Successors | F | 1022 | 100%
| SS Successors | F | 47 | 5%
| FF Successors | F | 31 | 3%
| SF Successors | F | 0 | 0%
| FS Successors | F | 1014 | 99%
| Missing Logic | F | 2 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 1 | 0%
| Open Finish | F | 2 | 0%
| Logic Density™ - Predecessors | F | 1.82
| All Activities w/Predecessors | F | 915 | 100%
| Total # Predecessors | F | 1665
| Activities Missing Predecessors | F | 1 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 2 | 0%
| Total # Predecessor Lags | F | 2
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 22
| Hidden Duration (Planned) | F | 2 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 125 | 14%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 9 | 1%
| Logic Hotspot™ | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 9%
| Logic Density™ - Successors | F | 1.36
| All Activities w/Successors | F | 1022 | 100%
| Activities Missing Successors | F | 2 | 0%
| Total # Successors | F | 1395
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 8 | 1%
| Total# of Successor Lags | F | 8
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 72 | 7%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 11 | 1%
| Logic Hotspot™ | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 9%
| Actually Finished - Tasks & Milestones | F | 699 | 41%
| Completed Ahead - Tasks & Milestones | F | 55 | 8%
| Completed On-Schedule - Tasks & Milestones | F | 81 | 12%
| Completed Delayed - Tasks & Milestones | F | 562 | 80%
| Avg Days Finished Early - Tasks & Milestones | F | 24
| Avg Days Finished Late - Tasks & Milestones | F | 161
| Avg Finish Variance - Tasks & Milestones | F | 128
| Actually Finished - Tasks | F | 609 | 39%
| Completed Ahead - Tasks | F | 48 | 8%
| Completed On-Schedule - Tasks | F | 69 | 11%
| Completed Delayed - Tasks | F | 492 | 81%
| Accelerated Durations Early/On-Schedule - Tasks | F | 12 | 1%
| Accelerated Durations Late - Tasks | F | 106 | 7%
| Extended Durations - Tasks | F | 271 | 17%
| Actually Finished - Milestones | F | 90 | 53%
| Completed Ahead - Milestones | F | 7 | 8%
| Completed On-Schedule - Milestones | F | 12 | 13%
| Completed Delayed - Milestones | F | 70 | 78%
| Actually Started - Tasks | F | 108 | 7%
| In-Progress Started Ahead - Tasks | F | 10 | 9%
| In-Progress Started On-Schedule - Tasks | F | 17 | 16%
| In-Progress Started Delayed - Tasks | F | 80 | 74%
| In-Progress Delayed Finish - Tasks | F | 106 | 98%
| Avg Days Started Early | F | 15
| Avg Days Started Late | F | 121
| Avg Start Variance | F | 106
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 916 | 53%
| Planned Ahead Start - Tasks & Milestones | F | 4 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 96 | 10%
| Planned Delayed Start - Tasks & Milestones | F | 804 | 88%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 837 | 54%
| Planned Ahead Start - Tasks | F | 4 | 0%
| Planned On Schedule Start - Tasks | F | 93 | 11%
| Planned Delayed Start - Tasks | F | 731 | 87%
| Planned Delayed Finish - Tasks | F | 732 | 87%
| Scheduled to Start - Milestones | F | 79 | 47%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 3 | 4%
| Planned Delayed Start - Milestones | F | 73 | 92%
| Planned Delayed Finish - Milestones | F | 73 | 92%
| Schedule Baseline Activities | F | 1709 | 99%
| Scheduled/Baselined to Start | F | 1011
| Scheduled/Baselined to Finish | F | 1011
| Start/ed | F | 807
| Finish/ed | F | 699
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 417 | 81%
| Completed Delayed (>30 days) | F | 421 | 86%
| SPI(t) | F | 8.22
| Scheduled Activities | F | 1723 | 100%
| Scheduled to Start | F | 1024 | 59%
| Scheduled to Finish | F | 1024 | 59%
| Longest Path - Critical Activities and Milestones | F | 43 | 4%
| Critical Milestones (To-Go) | F | 8 | 10%
| Critical Tasks (To-Go) | F | 35 | 4%
| Critical Tasks (In Progress) | F | 1 | 3%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| High Float 10% | F | 467 | 46%
| High Float 44d | F | 898 | 88%
| Zero Days Float | F | 2 | 0%
| Negative Float | F | 41 | 4%
| Longest Path - Critical Activities and Milestones | F | 43 | 4%
| Critical Milestones (To-Go) | F | 8 | 10%
| Critical Tasks (To-Go) | F | 35 | 4%
| Critical Tasks (In Progress) | F | 1 | 3%
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.08
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| Logic Density™ | F | 3.14
| CP Logic Density™ | F | 7.58
| Critical w/Missing Logic | F | 1 | 0%
| Critical w/Hard Constraints | F | 1 | 0%
| Zero Days Float | F | 2 | 0%
| Negative Float | F | 41 | 4%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 2 | 6%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 1 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 1544
| Scheduled to Start | F | 1554
| Actual Starts | F | 717
| Baselined to Finish | F | 1544
| Scheduled to Finish | F | 1554
| Actual Finishes | F | 609
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10%
| Started Delayed (>60 days) | F | 366 | 71%
| Completed Delayed (<=30 days) | F | 71 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11%
| Completed Delayed (>60 days) | F | 365 | 74%
| Baselined to Start | F | 1544
| Scheduled to Start | F | 1554
| Actual Starts | F | 717
| Current Baselined to Start & Started | F | 716
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 1544
| Scheduled to Finish | F | 1554
| Actual Finishes | F | 609
| Current Baselined to Finish & Finished | F | 609
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10%
| Started Delayed (>60 days) | F | 366 | 71%
| Completed Delayed (<=30 days) | F | 71 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11%
| Completed Delayed (>60 days) | F | 365 | 74%
| Baselined to Start - To Time Now | F | 1228 | 80%
| Scheduled to Start - To Time Now | F | 1228 | 79%
| Started | F | 715
| Started Late | F | 515
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10%
| Started Delayed (>60 days) | F | 366 | 71%
| BEI - Value Task Starts | F | 0.58
| Baselined to Finish - To Time Now | F | 1205 | 78%
| Scheduled to Finish - To Time Now | F | 1205 | 78%
| Finished | F | 609
| Finished Late | F | 492
| Completed Delayed (<=30 days) | F | 71 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11%
| Completed Delayed (>60 days) | F | 365 | 74%
| BEI - Value Task Finishes | F | 0.51
| Started - Future | F | 1
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.63
| FEI - Value Task Finish - Cumulative | F | 2.75
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 716
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 828
| Baselined to Start - Check | F | 1544
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 609
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 935
| Baselined to Finish - Check | F | 1544
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 716
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 828
| Current Baseline to Finish & Finished (BL Plan) | F | 609
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 935
| Baselined to Start | F | 1228
| Scheduled to Start | F | 1228 | 100%
| Started - Scheduled | F | 715 | 58%
| Started - Baseline Comparison | F | 715 | 58%
| BEI - Value Task Starts | F | 0.58
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 1205
| Scheduled to Finish | F | 1205
| Finished | F | 609
| BEI - Value Task Finishes | F | 0.51
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2025-02-07
| Started (incl. Future Baseline Starts) - Scheduled | F | 717 | 46%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 716 | 46%
| Started Late (from Baseline) | F | 515
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 609 | 39%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 609 | 39%
| Finished Late | F | 492
| Completed Ahead | F | 48 | 8%
| Completed Delayed | F | 492 | 81%
| Completed On-Schedule | F | 69 | 11%
| Accelerated | F | 13 | 2%
| Days Variance | F | 83556 | 13720%
| Days Early | F | 1212 | 199%
| Days Late | F | 84767 | 13919%
| Avg Days Early | F | 25
| Avg Days Late | F | 172
| Avg Variance | F | 137
| Actually Finished | F | 609 | 35%
| Took Longer than Planned | F | 303 | 43%
| Took Less Than Planned | F | 157 | 22%
| Completed (w/Baseline Duration) | F | 585 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 609 | 51%
| Missed Durations | F | 271 | 44%
| Missed Durations & Late Actual Finish | F | 253 | 42%
| Completed Ahead | F | 48 | 8%
| Completed Delayed | F | 492 | 81%
| Completed On-Schedule | F | 69 | 11%
| Accelerated | F | 13 | 2%
| Days Variance | F | 83556 | 13720%
| Days Early | F | 1212 | 199%
| Days Late | F | 84767 | 13919%
| Avg Days Early | F | 25
| Avg Days Late | F | 172
| Avg Variance | F | 137
| Actually Finished | F | 609 | 35%
| Took Longer than Planned | F | 303 | 43%
| Took Less Than Planned | F | 157 | 22%
| Completed (w/Baseline Duration) | F | 585 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 609 | 51%
| Missed Durations | F | 271 | 44%
| Missed Durations & Late Actual Finish | F | 253 | 42%
| Baselined Tasks | F | 1544
| Baselined to Start - TOTAL | F | 1544
| Complete Task Starts - Cumulative | F | 715 | 58%
| Incomplete Task Starts - Cumulative (in work) | F | 513 | 42%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 1544
| Complete Task Finishes - Cumulative (in work) | F | 609 | 51%
| Incomplete Task Finishes - Cumulative | F | 596 | 51%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1205
| BEI - Complete Tasks | F | 609 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| BEI - Value Tasks (adjusted) | F | 0.51
| BEI - Complete Tasks (adjusted) | F | 609 | 51%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2025-02-07
| BEI - Value Milestones | F | 0.7
| BEI - Total Milestones | F | 128
| BEI - Complete Milestones | F | 89 | 70%
| BEI - Incomplete Milestones | F | 39 | 30%
| BEI - Value Milestones (adjusted) | F | 0.7
| BEI - Complete Milestones (adjusted) | F | 89 | 70%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2025-02-07
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2025-02-07
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2025-02-07
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1205
| BEI - Incomplete Tasks | F | 596 | 49%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 89 | 70%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0.7
| BEI - Total Milestones | F | 128
| BEI - Complete Milestones | F | 89 | 70%
| BEI - Incomplete Milestones | F | 39 | 30%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.51
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0.7
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2025-02-07
| Total Activities - DRM | F | 584
| Total Activities - DRM Graph | F | 584
| Status Date | F | 2025-02-07
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2025-02-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 0
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2025-02-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2025-08-06
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.63
| FEI - Value Task Finish - Cumulative | F | 2.75
| BEI - Value Tasks | F | 0.51
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0.7
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Complete Tasks | F | 609 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 2 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 7 | 1%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 2 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 1 | 0%
| Open Finish | F | 2 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 41 | 4%
| Status Date | F | 2025-02-07
| High Float 10% | F | 467 | 46%
| High Float 44d | F | 898 | 88%
| Zero Days Float | F | 2 | 0%
| Negative Float | F | 41 | 4%
| Hidden Duration (Planned) | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 9%
| Critical Merge Hotspot | F | 9 | 1%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Critical Diverge Hotspot | F | 11 | 1%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 35 | 69%
| Longest Path (Tasks & Milestones) | F | 43 | 84%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| Critical Milestones (To-Go) | F | 8 | 10%
| Longest Path (Milestones) | F | 8 | 16%
| Normal Tasks | F | 1554 | 73%
| Normal Tasks (To-Go) | F | 945 | 72%
| Critical Tasks (To-Go) | F | 35 | 4%
| Critical Tasks (In Progress) | F | 1 | 3%
| Zero Days Float | F | 2 | 0%
| Negative Float | F | 41 | 4%
| CP Logic Density™ | F | 7.58
| Time Now | F | 2025-02-07
| Forecast to be Finished | F | 1202 | 78%
| Completed On Time | T | 116 | 10%
| Completed Late | F | 488 | 41%
| Not Completed | F | 594 | 49%
| Baseline Finish Compliance | T | 10%
| Forecast to be Started | F | 1228 | 80%
| Started On Time | T | 200 | 16%
| Started Late | F | 515 | 42%
| Not Started | F | 513 | 42%
| Baseline Start Compliance | T | 22%
1 | Completed Activities | F | 609
HSD01 | Time Now | F | 2025-02-07
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 513 | 33%
HSD04 | Started Late | F | 515 | 42%
HSD05 | Forecast to be Finished but not Finished yet | T | 594 | 38%
HSD06 | Finished Late | F | 488 | 41%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2028-09-29
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 49 | 98%
SEM02 | BRI Current | T | 0.03
SEM03 | BRI Cumulative | F | 0.51
SEM04 | BPI Current | T | 0.03
SEM05 | BEI Current | F | 1.67
SEM06 | BEI Cumulative | T | 0.51
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.75
SEM07 | To Go - Planned Task Starts - Count | T | 836
SEM07 | To Go - BEI - Task Finishes - Count | T | 940
SEM07 | To Go - Baselined Task Starts - Count | T | 828
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 521
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 315
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 605
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 339
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.75
SEM07 | To Go - Planned Task Starts - Count | T | 836
SEM07 | To Go - BEI - Task Finishes - Count | T | 940
SEM07 | To Go - Baselined Task Starts - Count | T | 828
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 836
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 521
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 315
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 944
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 605
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 339
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 521
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 315
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 605
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 339
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.75
SEM07 | To Go - Planned Task Starts - Count | T | 836
SEM07 | To Go - BEI - Task Finishes - Count | T | 940
SEM07 | To Go - Baselined Task Starts - Count | T | 828
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63
SEM07 | TC-BEI | T | 2.77
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -2.15
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Large-Test-File2-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Large Test File2 2 (3/10/2025 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2025-03-10
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 1 | 0%
| Wrong Status - Actual Finishes | F | 4 | 1%
| Invalid Forecast Dates | F | 338 | 34%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 4 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 3 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 122 | 12%
| Status Date | F | 2025-03-10
| High Float 44d | F | 717 | 72%
| Zero Days Float | F | 66 | 7%
| Hidden Duration (Planned) | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 2%
| Critical Merge Hotspot | F | 35 | 4%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Critical Diverge Hotspot | F | 22 | 2%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 354 | 35%
| Negative Float | F | 122 | 12%
| Tasks & Milestones (To Go) | F | 998 | 58%
| Milestones (To-Go) | F | 79 | 8%
| Normal Tasks (To-Go) | F | 919 | 92%
| Normal Tasks (To-Go, In Progress) | F | 92 | 9%
| Critical Path (Tasks & Milestones) | F | 185 | 19%
| Critical Path (Milestones) | F | 15 | 8%
| Critical Path (Normal Tasks) | F | 170 | 92%
| Critical Path (Normal In Progress) | F | 4 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11
| Negative Float | F | 122 | 12%
| Zero Days Float | F | 66 | 7%
| Near-Critical (<10 Days Float) | F | 242 | 24%
| CP Logic Density™ | F | 4.27
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1228
| BEI - Complete Tasks | F | 632 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| Status Date | F | 2025-03-10
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2028-03-06
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 0
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | 324 | 39%
| Status Date | F | 2025-03-10
| Total Activities | F | 2124
| Milestones | F | 169 | 8%
| Normal Tasks | F | 1553 | 73%
| Summaries | F | 402 | 19%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 1722 | 81%
| Completed Tasks & Milestones | F | 724 | 42%
| Completed Milestones | F | 90 | 53%
| Completed Tasks | F | 634 | 41%
| Total Activities (To-Go) - % of Total | F | 1284 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 998 | 78%
| Milestones (To-Go) | F | 79 | 6%
| Normal Tasks (To-Go) | F | 919 | 72%
| Summaries (To-Go) | F | 286 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 185 | 82%
| Longest Path (Normal Tasks) | F | 170 | 76%
| Longest Path (Milestones) | F | 15 | 7%
| Critical Milestones (To-Go) | F | 15 | 8%
| Critical Normal Tasks (To-Go) | F | 170 | 92%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 1543
| Scheduled to Start | F | 1553
| Actual Starts | F | 726
| Baselined to Finish | F | 1543
| Scheduled to Finish | F | 1553
| Actual Finishes | F | 634
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.49
| FEI - Value Task Finish - Cumulative | F | 2.75
| Current Baseline to Start & Started (BL Plan) | F | 723
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 820
| Current Baseline to Finish & Finished (BL Plan) | F | 632
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 911
| Duration Ratio Metric (DRM) | F | 608
| DRM Graph | F | 608
| Baselined to Start | F | 911
| Scheduled to Start | F | 919
| Baselined to Finish | F | 911
| Scheduled to Finish | F | 919
| BEI - Value Activities | F | 0.53
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 998 | 78%
| Critical Path To-Go | F | 185 | 19%
| Status Date | F | 2025-03-10
| Total Activities | F | 2124
| Milestones | F | 169 | 8%
| Normal Tasks | F | 1553 | 73%
| Summaries | F | 402 | 19%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 1722 | 81%
| Completed Tasks & Milestones | F | 724 | 42%
| Completed Milestones | F | 90 | 53%
| Completed Tasks | F | 634 | 41%
| Total Activities (To-Go) - % of Total | F | 1284 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 998 | 78%
| Milestones (To-Go) | F | 79 | 6%
| Normal Tasks (To-Go) | F | 919 | 72%
| Summaries (To-Go) | F | 286 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 185 | 82%
| Longest Path (Normal Tasks) | F | 170 | 76%
| Longest Path (Milestones) | F | 15 | 7%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2025-03-10
| Total Activities (To-Go) - % of Total | F | 1284 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 998 | 78%
| Summary-to-Task Ratio (To-Go) | F | 1:03 | 0.31
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.09
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 185 | 19%
| Wrong Status (To-Go) | F | 1 | 0%
| Invalid Forecast Dates | F | 338 | 34%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 998 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 998 | 78%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 4 | 0%
| Avg. Original Duration | F | 42
| Avg. Remaining Duration | F | 19
| High Baseline Duration (44d) | F | 86 | 9%
| High Planned Duration (44d) | F | 120 | 13%
| Insufficient Detail™ | F | 21 | 2%
| Critical Activities (To-Go) | F | 170 | 18%
| Avg. Critical Original Duration | F | 18
| Avg. Critical Remaining Duration | F | 12
| Critical w/High Baseline Duration (44d) | F | 4 | 0%
| Critical w/High Planned Duration (44d) | F | 6 | 4%
| Critical w/Insufficient Detail™ | F | 2 | 0%
| Activities (To-Go) | F | 919 | 59%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 3 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 998 | 100%
| No Constraints | F | 997 | 100%
| Logic Density™ | F | 3.15
| Logic Density™ - Predecessors | F | 1.79
| Logic Density™ - Successors | F | 1.37
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 905 | 100%
| SS Predecessors | F | 42 | 4%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 36 | 4%
| FS Predecessors | F | 994 | 100%
| All Activities w/Successors | F | 996 | 100%
| SS Successors | F | 42 | 4%
| FF Successors | F | 31 | 3%
| SF Successors | F | 0 | 0%
| FS Successors | F | 990 | 99%
| Missing Logic | F | 3 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 1 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.82
| All Activities w/Predecessors | F | 905 | 100%
| Total # Predecessors | F | 1649
| Activities Missing Predecessors | F | 1 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 2 | 0%
| Total # Predecessor Lags | F | 2
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 22
| Hidden Duration (Planned) | F | 2 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 123 | 14%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 35 | 4%
| Logic Hotspot™ | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 2%
| Logic Density™ - Successors | F | 1.37
| All Activities w/Successors | F | 996 | 100%
| Activities Missing Successors | F | 2 | 0%
| Total # Successors | F | 1364
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 8 | 1%
| Total# of Successor Lags | F | 8
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 72 | 7%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 22 | 2%
| Logic Hotspot™ | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 2%
| Actually Finished - Tasks & Milestones | F | 724 | 42%
| Completed Ahead - Tasks & Milestones | F | 55 | 8%
| Completed On-Schedule - Tasks & Milestones | F | 81 | 11%
| Completed Delayed - Tasks & Milestones | F | 585 | 81%
| Avg Days Finished Early - Tasks & Milestones | F | 24
| Avg Days Finished Late - Tasks & Milestones | F | 169
| Avg Finish Variance - Tasks & Milestones | F | 134
| Actually Finished - Tasks | F | 634 | 41%
| Completed Ahead - Tasks | F | 48 | 8%
| Completed On-Schedule - Tasks | F | 69 | 11%
| Completed Delayed - Tasks | F | 515 | 81%
| Accelerated Durations Early/On-Schedule - Tasks | F | 12 | 1%
| Accelerated Durations Late - Tasks | F | 105 | 7%
| Extended Durations - Tasks | F | 285 | 18%
| Actually Finished - Milestones | F | 90 | 53%
| Completed Ahead - Milestones | F | 7 | 8%
| Completed On-Schedule - Milestones | F | 12 | 13%
| Completed Delayed - Milestones | F | 70 | 78%
| Actually Started - Tasks | F | 92 | 6%
| In-Progress Started Ahead - Tasks | F | 8 | 9%
| In-Progress Started On-Schedule - Tasks | F | 15 | 16%
| In-Progress Started Delayed - Tasks | F | 68 | 74%
| In-Progress Delayed Finish - Tasks | F | 91 | 99%
| Avg Days Started Early | F | 16
| Avg Days Started Late | F | 118
| Avg Start Variance | F | 101
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 906 | 53%
| Planned Ahead Start - Tasks & Milestones | F | 97 | 11%
| Planned On Schedule Start - Tasks & Milestones | F | 1 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 798 | 88%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 827 | 53%
| Planned Ahead Start - Tasks | F | 89 | 11%
| Planned On Schedule Start - Tasks | F | 1 | 0%
| Planned Delayed Start - Tasks | F | 730 | 88%
| Planned Delayed Finish - Tasks | F | 731 | 88%
| Scheduled to Start - Milestones | F | 79 | 47%
| Planned Ahead Start - Milestones | F | 8 | 10%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 68 | 86%
| Planned Delayed Finish - Milestones | F | 68 | 86%
| Schedule Baseline Activities | F | 1708 | 99%
| Scheduled/Baselined to Start | F | 987
| Scheduled/Baselined to Finish | F | 987
| Start/ed | F | 816
| Finish/ed | F | 724
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 424 | 81%
| Completed Delayed (>30 days) | F | 443 | 86%
| SPI(t) | F | 8.14
| Scheduled Activities | F | 1722 | 100%
| Scheduled to Start | F | 998 | 58%
| Scheduled to Finish | F | 998 | 58%
| Longest Path - Critical Activities and Milestones | F | 185 | 19%
| Critical Milestones (To-Go) | F | 15 | 19%
| Critical Tasks (To-Go) | F | 170 | 18%
| Critical Tasks (In Progress) | F | 4 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| High Float 10% | F | 354 | 35%
| High Float 44d | F | 717 | 72%
| Zero Days Float | F | 66 | 7%
| Negative Float | F | 122 | 12%
| Longest Path - Critical Activities and Milestones | F | 185 | 19%
| Critical Milestones (To-Go) | F | 15 | 19%
| Critical Tasks (To-Go) | F | 170 | 18%
| Critical Tasks (In Progress) | F | 4 | 2%
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.09
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| Logic Density™ | F | 3.13
| CP Logic Density™ | F | 4.27
| Critical w/Missing Logic | F | 1 | 0%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 66 | 7%
| Negative Float | F | 122 | 12%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 4 | 0%
| Critical w/High Planned Duration (44d) | F | 6 | 4%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 1543
| Scheduled to Start | F | 1553
| Actual Starts | F | 726
| Baselined to Finish | F | 1543
| Scheduled to Finish | F | 1553
| Actual Finishes | F | 634
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| Baselined to Start | F | 1543
| Scheduled to Start | F | 1553
| Actual Starts | F | 726
| Current Baselined to Start & Started | F | 723
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 1543
| Scheduled to Finish | F | 1553
| Actual Finishes | F | 634
| Current Baselined to Finish & Finished | F | 632
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| Baselined to Start - To Time Now | F | 1247 | 81%
| Scheduled to Start - To Time Now | F | 1247 | 80%
| Started | F | 722
| Started Late | F | 522
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| BEI - Value Task Starts | F | 0.58
| Baselined to Finish - To Time Now | F | 1228 | 80%
| Scheduled to Finish - To Time Now | F | 1228 | 80%
| Finished | F | 632
| Finished Late | F | 515
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| BEI - Value Task Finishes | F | 0.51
| Started - Future | F | 1
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.49
| FEI - Value Task Finish - Cumulative | F | 2.75
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 723
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 820
| Baselined to Start - Check | F | 1543
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 632
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 911
| Baselined to Finish - Check | F | 1543
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 723
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 820
| Current Baseline to Finish & Finished (BL Plan) | F | 632
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 911
| Baselined to Start | F | 1247
| Scheduled to Start | F | 1247 | 100%
| Started - Scheduled | F | 722 | 58%
| Started - Baseline Comparison | F | 722 | 58%
| BEI - Value Task Starts | F | 0.58
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 1228
| Scheduled to Finish | F | 1228
| Finished | F | 632
| BEI - Value Task Finishes | F | 0.51
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2025-03-10
| Started (incl. Future Baseline Starts) - Scheduled | F | 726 | 47%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 723 | 47%
| Started Late (from Baseline) | F | 522
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 632 | 41%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 632 | 41%
| Finished Late | F | 515
| Completed Ahead | F | 48 | 8%
| Completed Delayed | F | 515 | 81%
| Completed On-Schedule | F | 69 | 11%
| Accelerated | F | 13 | 2%
| Days Variance | F | 91676 | 14460%
| Days Early | F | 1212 | 191%
| Days Late | F | 92888 | 14651%
| Avg Days Early | F | 25
| Avg Days Late | F | 180
| Avg Variance | F | 145
| Actually Finished | F | 634 | 37%
| Took Longer than Planned | F | 317 | 44%
| Took Less Than Planned | F | 160 | 22%
| Completed (w/Baseline Duration) | F | 608 | 39%
| Completed (w/o Baseline Duration) | F | 2 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 632 | 51%
| Missed Durations | F | 285 | 45%
| Missed Durations & Late Actual Finish | F | 267 | 42%
| Completed Ahead | F | 48 | 8%
| Completed Delayed | F | 515 | 81%
| Completed On-Schedule | F | 69 | 11%
| Accelerated | F | 13 | 2%
| Days Variance | F | 91676 | 14460%
| Days Early | F | 1212 | 191%
| Days Late | F | 92888 | 14651%
| Avg Days Early | F | 25
| Avg Days Late | F | 180
| Avg Variance | F | 145
| Actually Finished | F | 634 | 37%
| Took Longer than Planned | F | 317 | 44%
| Took Less Than Planned | F | 160 | 22%
| Completed (w/Baseline Duration) | F | 608 | 39%
| Completed (w/o Baseline Duration) | F | 2 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 632 | 51%
| Missed Durations | F | 285 | 45%
| Missed Durations & Late Actual Finish | F | 267 | 42%
| Baselined Tasks | F | 1543
| Baselined to Start - TOTAL | F | 1543
| Complete Task Starts - Cumulative | F | 722 | 58%
| Incomplete Task Starts - Cumulative (in work) | F | 525 | 42%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 1543
| Complete Task Finishes - Cumulative (in work) | F | 632 | 51%
| Incomplete Task Finishes - Cumulative | F | 596 | 51%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1228
| BEI - Complete Tasks | F | 632 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| BEI - Value Tasks (adjusted) | F | 0.51
| BEI - Complete Tasks (adjusted) | F | 632 | 51%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| BEI - Value Milestones | F | 0.69
| BEI - Total Milestones | F | 129
| BEI - Complete Milestones | F | 89 | 69%
| BEI - Incomplete Milestones | F | 40 | 31%
| BEI - Value Milestones (adjusted) | F | 0.69
| BEI - Complete Milestones (adjusted) | F | 89 | 69%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1228
| BEI - Incomplete Tasks | F | 596 | 49%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 89 | 69%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0.69
| BEI - Total Milestones | F | 129
| BEI - Complete Milestones | F | 89 | 69%
| BEI - Incomplete Milestones | F | 40 | 31%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.51
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0.69
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| Total Activities - DRM | F | 608
| Total Activities - DRM Graph | F | 608
| Status Date | F | 2025-03-10
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 0
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2028-03-06
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.49
| FEI - Value Task Finish - Cumulative | F | 2.75
| BEI - Value Tasks | F | 0.51
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0.69
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Complete Tasks | F | 632 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 1 | 0%
| Invalid Forecast Dates | F | 338 | 34%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 4 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 3 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 1 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 122 | 12%
| Status Date | F | 2025-03-10
| High Float 10% | F | 354 | 35%
| High Float 44d | F | 717 | 72%
| Zero Days Float | F | 66 | 7%
| Negative Float | F | 122 | 12%
| Hidden Duration (Planned) | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 2%
| Critical Merge Hotspot | F | 35 | 4%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Critical Diverge Hotspot | F | 22 | 2%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 170 | 76%
| Longest Path (Tasks & Milestones) | F | 185 | 82%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| Critical Milestones (To-Go) | F | 15 | 19%
| Longest Path (Milestones) | F | 15 | 7%
| Normal Tasks | F | 1553 | 73%
| Normal Tasks (To-Go) | F | 919 | 72%
| Critical Tasks (To-Go) | F | 170 | 18%
| Critical Tasks (In Progress) | F | 4 | 2%
| Zero Days Float | F | 66 | 7%
| Negative Float | F | 122 | 12%
| CP Logic Density™ | F | 4.27
| Time Now | F | 2025-03-10
| Forecast to be Finished | F | 1227 | 80%
| Completed On Time | T | 159 | 13%
| Completed Late | F | 581 | 47%
| Not Completed | F | 595 | 48%
| Baseline Finish Compliance | T | 13%
| Forecast to be Started | F | 1247 | 81%
| Started On Time | T | 250 | 20%
| Started Late | F | 605 | 49%
| Not Started | F | 525 | 42%
| Baseline Start Compliance | F | 26%
1 | Completed Activities | F | 630
HSD01 | Time Now | F | 2025-03-10
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 525 | 34%
HSD04 | Started Late | F | 605 | 49%
HSD05 | Forecast to be Finished but not Finished yet | T | 595 | 39%
HSD06 | Finished Late | F | 581 | 47%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2029-04-20
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 24 | 100%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.51
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | F | 1
SEM06 | BEI Cumulative | T | 0.51
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.42
SEM07 | To Go - Planned Task Starts - Count | T | 662
SEM07 | To Go - BEI - Task Finishes - Count | T | 766
SEM07 | To Go - Baselined Task Starts - Count | T | 655
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 398
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 263
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 492
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 279
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.42
SEM07 | To Go - Planned Task Starts - Count | T | 662
SEM07 | To Go - BEI - Task Finishes - Count | T | 766
SEM07 | To Go - Baselined Task Starts - Count | T | 655
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 661
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 398
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 263
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 771
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 492
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 279
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 398
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 263
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 492
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 279
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.42
SEM07 | To Go - Planned Task Starts - Count | T | 662
SEM07 | To Go - BEI - Task Finishes - Count | T | 766
SEM07 | To Go - Baselined Task Starts - Count | T | 655
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | TC-BEI | T | 2.45
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -1.91
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## SRA-Large-Test-File2-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
SRA Large Test File2 2 (3/10/2025 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2025-03-10
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 1 | 0%
| Wrong Status - Actual Finishes | F | 4 | 1%
| Invalid Forecast Dates | F | 338 | 34%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 4 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 3 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 122 | 12%
| Status Date | F | 2025-03-10
| High Float 44d | F | 717 | 72%
| Zero Days Float | F | 66 | 7%
| Hidden Duration (Planned) | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 2%
| Critical Merge Hotspot | F | 35 | 4%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Critical Diverge Hotspot | F | 22 | 2%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 354 | 35%
| Negative Float | F | 122 | 12%
| Tasks & Milestones (To Go) | F | 998 | 58%
| Milestones (To-Go) | F | 79 | 8%
| Normal Tasks (To-Go) | F | 919 | 92%
| Normal Tasks (To-Go, In Progress) | F | 92 | 9%
| Critical Path (Tasks & Milestones) | F | 185 | 19%
| Critical Path (Milestones) | F | 15 | 8%
| Critical Path (Normal Tasks) | F | 170 | 92%
| Critical Path (Normal In Progress) | F | 4 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11
| Negative Float | F | 122 | 12%
| Zero Days Float | F | 66 | 7%
| Near-Critical (<10 Days Float) | F | 242 | 24%
| CP Logic Density™ | F | 4.27
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1228
| BEI - Complete Tasks | F | 632 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| Status Date | F | 2025-03-10
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2028-03-06
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 0
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | 324 | 39%
| Status Date | F | 2025-03-10
| Total Activities | F | 2124
| Milestones | F | 169 | 8%
| Normal Tasks | F | 1553 | 73%
| Summaries | F | 402 | 19%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 1722 | 81%
| Completed Tasks & Milestones | F | 724 | 42%
| Completed Milestones | F | 90 | 53%
| Completed Tasks | F | 634 | 41%
| Total Activities (To-Go) - % of Total | F | 1284 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 998 | 78%
| Milestones (To-Go) | F | 79 | 6%
| Normal Tasks (To-Go) | F | 919 | 72%
| Summaries (To-Go) | F | 286 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 185 | 82%
| Longest Path (Normal Tasks) | F | 170 | 76%
| Longest Path (Milestones) | F | 15 | 7%
| Critical Milestones (To-Go) | F | 15 | 8%
| Critical Normal Tasks (To-Go) | F | 170 | 92%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 1543
| Scheduled to Start | F | 1553
| Actual Starts | F | 726
| Baselined to Finish | F | 1543
| Scheduled to Finish | F | 1553
| Actual Finishes | F | 634
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.49
| FEI - Value Task Finish - Cumulative | F | 2.75
| Current Baseline to Start & Started (BL Plan) | F | 723
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 820
| Current Baseline to Finish & Finished (BL Plan) | F | 632
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 911
| Duration Ratio Metric (DRM) | F | 608
| DRM Graph | F | 608
| Baselined to Start | F | 911
| Scheduled to Start | F | 919
| Baselined to Finish | F | 911
| Scheduled to Finish | F | 919
| BEI - Value Activities | F | 0.53
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 998 | 78%
| Critical Path To-Go | F | 185 | 19%
| Status Date | F | 2025-03-10
| Total Activities | F | 2124
| Milestones | F | 169 | 8%
| Normal Tasks | F | 1553 | 73%
| Summaries | F | 402 | 19%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 1722 | 81%
| Completed Tasks & Milestones | F | 724 | 42%
| Completed Milestones | F | 90 | 53%
| Completed Tasks | F | 634 | 41%
| Total Activities (To-Go) - % of Total | F | 1284 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 998 | 78%
| Milestones (To-Go) | F | 79 | 6%
| Normal Tasks (To-Go) | F | 919 | 72%
| Summaries (To-Go) | F | 286 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 185 | 82%
| Longest Path (Normal Tasks) | F | 170 | 76%
| Longest Path (Milestones) | F | 15 | 7%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2025-03-10
| Total Activities (To-Go) - % of Total | F | 1284 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 998 | 78%
| Summary-to-Task Ratio (To-Go) | F | 1:03 | 0.31
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.09
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 185 | 19%
| Wrong Status (To-Go) | F | 1 | 0%
| Invalid Forecast Dates | F | 338 | 34%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 998 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 998 | 78%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 4 | 0%
| Avg. Original Duration | F | 42
| Avg. Remaining Duration | F | 19
| High Baseline Duration (44d) | F | 86 | 9%
| High Planned Duration (44d) | F | 120 | 13%
| Insufficient Detail™ | F | 21 | 2%
| Critical Activities (To-Go) | F | 170 | 18%
| Avg. Critical Original Duration | F | 18
| Avg. Critical Remaining Duration | F | 12
| Critical w/High Baseline Duration (44d) | F | 4 | 0%
| Critical w/High Planned Duration (44d) | F | 6 | 4%
| Critical w/Insufficient Detail™ | F | 2 | 0%
| Activities (To-Go) | F | 919 | 59%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 3 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 998 | 100%
| No Constraints | F | 997 | 100%
| Logic Density™ | F | 3.15
| Logic Density™ - Predecessors | F | 1.79
| Logic Density™ - Successors | F | 1.37
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 905 | 100%
| SS Predecessors | F | 42 | 4%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 36 | 4%
| FS Predecessors | F | 994 | 100%
| All Activities w/Successors | F | 996 | 100%
| SS Successors | F | 42 | 4%
| FF Successors | F | 31 | 3%
| SF Successors | F | 0 | 0%
| FS Successors | F | 990 | 99%
| Missing Logic | F | 3 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 1 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.82
| All Activities w/Predecessors | F | 905 | 100%
| Total # Predecessors | F | 1649
| Activities Missing Predecessors | F | 1 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 2 | 0%
| Total # Predecessor Lags | F | 2
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 22
| Hidden Duration (Planned) | F | 2 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 123 | 14%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 35 | 4%
| Logic Hotspot™ | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 2%
| Logic Density™ - Successors | F | 1.37
| All Activities w/Successors | F | 996 | 100%
| Activities Missing Successors | F | 2 | 0%
| Total # Successors | F | 1364
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 8 | 1%
| Total# of Successor Lags | F | 8
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 72 | 7%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 22 | 2%
| Logic Hotspot™ | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 2%
| Actually Finished - Tasks & Milestones | F | 724 | 42%
| Completed Ahead - Tasks & Milestones | F | 55 | 8%
| Completed On-Schedule - Tasks & Milestones | F | 81 | 11%
| Completed Delayed - Tasks & Milestones | F | 585 | 81%
| Avg Days Finished Early - Tasks & Milestones | F | 24
| Avg Days Finished Late - Tasks & Milestones | F | 169
| Avg Finish Variance - Tasks & Milestones | F | 134
| Actually Finished - Tasks | F | 634 | 41%
| Completed Ahead - Tasks | F | 48 | 8%
| Completed On-Schedule - Tasks | F | 69 | 11%
| Completed Delayed - Tasks | F | 515 | 81%
| Accelerated Durations Early/On-Schedule - Tasks | F | 12 | 1%
| Accelerated Durations Late - Tasks | F | 105 | 7%
| Extended Durations - Tasks | F | 285 | 18%
| Actually Finished - Milestones | F | 90 | 53%
| Completed Ahead - Milestones | F | 7 | 8%
| Completed On-Schedule - Milestones | F | 12 | 13%
| Completed Delayed - Milestones | F | 70 | 78%
| Actually Started - Tasks | F | 92 | 6%
| In-Progress Started Ahead - Tasks | F | 8 | 9%
| In-Progress Started On-Schedule - Tasks | F | 15 | 16%
| In-Progress Started Delayed - Tasks | F | 68 | 74%
| In-Progress Delayed Finish - Tasks | F | 91 | 99%
| Avg Days Started Early | F | 16
| Avg Days Started Late | F | 118
| Avg Start Variance | F | 101
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 906 | 53%
| Planned Ahead Start - Tasks & Milestones | F | 97 | 11%
| Planned On Schedule Start - Tasks & Milestones | F | 1 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 798 | 88%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 827 | 53%
| Planned Ahead Start - Tasks | F | 89 | 11%
| Planned On Schedule Start - Tasks | F | 1 | 0%
| Planned Delayed Start - Tasks | F | 730 | 88%
| Planned Delayed Finish - Tasks | F | 731 | 88%
| Scheduled to Start - Milestones | F | 79 | 47%
| Planned Ahead Start - Milestones | F | 8 | 10%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 68 | 86%
| Planned Delayed Finish - Milestones | F | 68 | 86%
| Schedule Baseline Activities | F | 1708 | 99%
| Scheduled/Baselined to Start | F | 987
| Scheduled/Baselined to Finish | F | 987
| Start/ed | F | 816
| Finish/ed | F | 724
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 424 | 81%
| Completed Delayed (>30 days) | F | 443 | 86%
| SPI(t) | F | 8.14
| Scheduled Activities | F | 1722 | 100%
| Scheduled to Start | F | 998 | 58%
| Scheduled to Finish | F | 998 | 58%
| Longest Path - Critical Activities and Milestones | F | 185 | 19%
| Critical Milestones (To-Go) | F | 15 | 19%
| Critical Tasks (To-Go) | F | 170 | 18%
| Critical Tasks (In Progress) | F | 4 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| High Float 10% | F | 354 | 35%
| High Float 44d | F | 717 | 72%
| Zero Days Float | F | 66 | 7%
| Negative Float | F | 122 | 12%
| Longest Path - Critical Activities and Milestones | F | 185 | 19%
| Critical Milestones (To-Go) | F | 15 | 19%
| Critical Tasks (To-Go) | F | 170 | 18%
| Critical Tasks (In Progress) | F | 4 | 2%
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.09
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| Logic Density™ | F | 3.13
| CP Logic Density™ | F | 4.27
| Critical w/Missing Logic | F | 1 | 0%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 66 | 7%
| Negative Float | F | 122 | 12%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 4 | 0%
| Critical w/High Planned Duration (44d) | F | 6 | 4%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 1543
| Scheduled to Start | F | 1553
| Actual Starts | F | 726
| Baselined to Finish | F | 1543
| Scheduled to Finish | F | 1553
| Actual Finishes | F | 634
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| Baselined to Start | F | 1543
| Scheduled to Start | F | 1553
| Actual Starts | F | 726
| Current Baselined to Start & Started | F | 723
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 1543
| Scheduled to Finish | F | 1553
| Actual Finishes | F | 634
| Current Baselined to Finish & Finished | F | 632
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| Baselined to Start - To Time Now | F | 1247 | 81%
| Scheduled to Start - To Time Now | F | 1247 | 80%
| Started | F | 722
| Started Late | F | 522
| Started Delayed (<=30 days) | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 52 | 10%
| Started Delayed (>60 days) | F | 372 | 71%
| BEI - Value Task Starts | F | 0.58
| Baselined to Finish - To Time Now | F | 1228 | 80%
| Scheduled to Finish - To Time Now | F | 1228 | 80%
| Finished | F | 632
| Finished Late | F | 515
| Completed Delayed (<=30 days) | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 58 | 11%
| Completed Delayed (>60 days) | F | 385 | 75%
| BEI - Value Task Finishes | F | 0.51
| Started - Future | F | 1
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.49
| FEI - Value Task Finish - Cumulative | F | 2.75
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 723
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 820
| Baselined to Start - Check | F | 1543
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 632
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 911
| Baselined to Finish - Check | F | 1543
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 723
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 820
| Current Baseline to Finish & Finished (BL Plan) | F | 632
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 911
| Baselined to Start | F | 1247
| Scheduled to Start | F | 1247 | 100%
| Started - Scheduled | F | 722 | 58%
| Started - Baseline Comparison | F | 722 | 58%
| BEI - Value Task Starts | F | 0.58
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 1228
| Scheduled to Finish | F | 1228
| Finished | F | 632
| BEI - Value Task Finishes | F | 0.51
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2025-03-10
| Started (incl. Future Baseline Starts) - Scheduled | F | 726 | 47%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 723 | 47%
| Started Late (from Baseline) | F | 522
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 632 | 41%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 632 | 41%
| Finished Late | F | 515
| Completed Ahead | F | 48 | 8%
| Completed Delayed | F | 515 | 81%
| Completed On-Schedule | F | 69 | 11%
| Accelerated | F | 13 | 2%
| Days Variance | F | 91676 | 14460%
| Days Early | F | 1212 | 191%
| Days Late | F | 92888 | 14651%
| Avg Days Early | F | 25
| Avg Days Late | F | 180
| Avg Variance | F | 145
| Actually Finished | F | 634 | 37%
| Took Longer than Planned | F | 317 | 44%
| Took Less Than Planned | F | 160 | 22%
| Completed (w/Baseline Duration) | F | 608 | 39%
| Completed (w/o Baseline Duration) | F | 2 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 632 | 51%
| Missed Durations | F | 285 | 45%
| Missed Durations & Late Actual Finish | F | 267 | 42%
| Completed Ahead | F | 48 | 8%
| Completed Delayed | F | 515 | 81%
| Completed On-Schedule | F | 69 | 11%
| Accelerated | F | 13 | 2%
| Days Variance | F | 91676 | 14460%
| Days Early | F | 1212 | 191%
| Days Late | F | 92888 | 14651%
| Avg Days Early | F | 25
| Avg Days Late | F | 180
| Avg Variance | F | 145
| Actually Finished | F | 634 | 37%
| Took Longer than Planned | F | 317 | 44%
| Took Less Than Planned | F | 160 | 22%
| Completed (w/Baseline Duration) | F | 608 | 39%
| Completed (w/o Baseline Duration) | F | 2 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 632 | 51%
| Missed Durations | F | 285 | 45%
| Missed Durations & Late Actual Finish | F | 267 | 42%
| Baselined Tasks | F | 1543
| Baselined to Start - TOTAL | F | 1543
| Complete Task Starts - Cumulative | F | 722 | 58%
| Incomplete Task Starts - Cumulative (in work) | F | 525 | 42%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 1543
| Complete Task Finishes - Cumulative (in work) | F | 632 | 51%
| Incomplete Task Finishes - Cumulative | F | 596 | 51%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1228
| BEI - Complete Tasks | F | 632 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| BEI - Value Tasks (adjusted) | F | 0.51
| BEI - Complete Tasks (adjusted) | F | 632 | 51%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| BEI - Value Milestones | F | 0.69
| BEI - Total Milestones | F | 129
| BEI - Complete Milestones | F | 89 | 69%
| BEI - Incomplete Milestones | F | 40 | 31%
| BEI - Value Milestones (adjusted) | F | 0.69
| BEI - Complete Milestones (adjusted) | F | 89 | 69%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| BEI - Value Tasks | F | 0.51
| BEI - Total Tasks | F | 1228
| BEI - Incomplete Tasks | F | 596 | 49%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 89 | 69%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0.69
| BEI - Total Milestones | F | 129
| BEI - Complete Milestones | F | 89 | 69%
| BEI - Incomplete Milestones | F | 40 | 31%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.51
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0.69
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2025-03-10
| Total Activities - DRM | F | 608
| Total Activities - DRM Graph | F | 608
| Status Date | F | 2025-03-10
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 0
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2028-03-06
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 2.49
| FEI - Value Task Finish - Cumulative | F | 2.75
| BEI - Value Tasks | F | 0.51
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0.69
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.51
| BEI - Complete Tasks | F | 632 | 51%
| BEI - Incomplete Tasks | F | 596 | 49%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 1 | 0%
| Invalid Forecast Dates | F | 338 | 34%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 4 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 3 | 0%
| Missing Predecessors | F | 1 | 0%
| Missing Successors | F | 2 | 0%
| Open Start | F | 1 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 122 | 12%
| Status Date | F | 2025-03-10
| High Float 10% | F | 354 | 35%
| High Float 44d | F | 717 | 72%
| Zero Days Float | F | 66 | 7%
| Negative Float | F | 122 | 12%
| Hidden Duration (Planned) | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 2%
| Critical Merge Hotspot | F | 35 | 4%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100%
| Critical Diverge Hotspot | F | 22 | 2%
| Diverge Hotspot w/Successor Lags | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 170 | 76%
| Longest Path (Tasks & Milestones) | F | 185 | 82%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:11 | 0.09
| Critical Milestones (To-Go) | F | 15 | 19%
| Longest Path (Milestones) | F | 15 | 7%
| Normal Tasks | F | 1553 | 73%
| Normal Tasks (To-Go) | F | 919 | 72%
| Critical Tasks (To-Go) | F | 170 | 18%
| Critical Tasks (In Progress) | F | 4 | 2%
| Zero Days Float | F | 66 | 7%
| Negative Float | F | 122 | 12%
| CP Logic Density™ | F | 4.27
| Time Now | F | 2025-03-10
| Forecast to be Finished | F | 1227 | 80%
| Completed On Time | T | 159 | 13%
| Completed Late | F | 581 | 47%
| Not Completed | F | 595 | 48%
| Baseline Finish Compliance | T | 13%
| Forecast to be Started | F | 1247 | 81%
| Started On Time | T | 250 | 20%
| Started Late | F | 605 | 49%
| Not Started | F | 525 | 42%
| Baseline Start Compliance | F | 26%
1 | Completed Activities | F | 630
HSD01 | Time Now | F | 2025-03-10
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 525 | 34%
HSD04 | Started Late | F | 605 | 49%
HSD05 | Forecast to be Finished but not Finished yet | T | 595 | 39%
HSD06 | Finished Late | F | 581 | 47%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2029-04-20
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 24 | 100%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.51
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | F | 1
SEM06 | BEI Cumulative | T | 0.51
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.42
SEM07 | To Go - Planned Task Starts - Count | T | 662
SEM07 | To Go - BEI - Task Finishes - Count | T | 766
SEM07 | To Go - Baselined Task Starts - Count | T | 655
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 398
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 263
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 492
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 279
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.42
SEM07 | To Go - Planned Task Starts - Count | T | 662
SEM07 | To Go - BEI - Task Finishes - Count | T | 766
SEM07 | To Go - Baselined Task Starts - Count | T | 655
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 661
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 398
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 263
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 771
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 492
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 279
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 398
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 263
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 492
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 279
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.42
SEM07 | To Go - Planned Task Starts - Count | T | 662
SEM07 | To Go - BEI - Task Finishes - Count | T | 766
SEM07 | To Go - Baselined Task Starts - Count | T | 655
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.22
SEM07 | TC-BEI | T | 2.45
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -1.91
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Jacked-Up-Schedule-1
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Jacked Up Schedule 1 (7/30/2026 8:00:00 AM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-07-30
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0
| Wrong Status - Actual Finishes | F | 0
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 3 | 20%
| Missing Predecessors | F | 1 | 7%
| Missing Successors | F | 2 | 13%
| Open Start | F | 1
| Open Finish | F | 1 | 7%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-07-30
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 9 | 60%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 7%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 1 | 7%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 2 | 13%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 3 | 20%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 15 | 100%
| Milestones (To-Go) | F | 2 | 13%
| Normal Tasks (To-Go) | F | 13 | 87%
| Normal Tasks (To-Go, In Progress) | F | 0 | 0%
| Critical Path (Tasks & Milestones) | F | 9 | 60%
| Critical Path (Milestones) | F | 2 | 22%
| Critical Path (Normal Tasks) | F | 7 | 78%
| Critical Path (Normal In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 9 | 60%
| Near-Critical (<10 Days Float) | F | 14 | 93%
| CP Logic Density™ | F | 2.33
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | 0
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | 2026-07-30
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-07-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-07-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-07-30
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 0 | 0%
| Completed Milestones | F | 0 | 0%
| Completed Tasks | F | 0 | 0%
| Total Activities (To-Go) - % of Total | F | 15 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 15 | 100%
| Milestones (To-Go) | F | 2 | 13%
| Normal Tasks (To-Go) | F | 13 | 87%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 9 | 100%
| Longest Path (Normal Tasks) | F | 7 | 78%
| Longest Path (Milestones) | F | 2 | 22%
| Critical Milestones (To-Go) | F | 2 | 22%
| Critical Normal Tasks (To-Go) | F | 7 | 78%
| Riding Data Date | F | 2 | 13%
| Baselined to Start | F | 0
| Scheduled to Start | F | 13
| Actual Starts | F | 0
| Baselined to Finish | F | 0
| Scheduled to Finish | F | 13
| Actual Finishes | F | 0
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | 0
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | 0
| Duration Ratio Metric (DRM) | F | 0
| DRM Graph | F | 0
| Baselined to Start | F | 0
| Scheduled to Start | F | 13
| Baselined to Finish | F | 0
| Scheduled to Finish | F | 13
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 15 | 100%
| Critical Path To-Go | F | 9 | 60%
| Status Date | F | 2026-07-30
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 0 | 0%
| Completed Milestones | F | 0 | 0%
| Completed Tasks | F | 0 | 0%
| Total Activities (To-Go) - % of Total | F | 15 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 15 | 100%
| Milestones (To-Go) | F | 2 | 13%
| Normal Tasks (To-Go) | F | 13 | 87%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 9 | 100%
| Longest Path (Normal Tasks) | F | 7 | 78%
| Longest Path (Milestones) | F | 2 | 22%
| Riding Data Date | F | 2 | 13%
| Status Date | F | 2026-07-30
| Total Activities (To-Go) - % of Total | F | 15 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 15 | 100%
| Summary-to-Task Ratio (To-Go) | F | N/A | 0
| Milestone-to-Task Ratio (To-Go) | F | 1:07 | 0.15
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.29
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 9 | 60%
| Wrong Status (To-Go) | F | 0
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 15 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 15 | 100%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 11
| Avg. Remaining Duration | F | 6
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 1 | 8%
| Insufficient Detail™ | F | 1 | 8%
| Critical Activities (To-Go) | F | 7 | 54%
| Avg. Critical Original Duration | F | 5
| Avg. Critical Remaining Duration | F | 5
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 13 | 100%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 3 | 13%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 15 | 100%
| No Constraints | F | 15 | 100%
| Logic Density™ | F | 2.13
| Logic Density™ - Predecessors | F | 1.07
| Logic Density™ - Successors | F | 1.07
| Summary Links | F | N/A | 0%
| All Activities w/Predecessors | F | 14 | 93%
| SS Predecessors | F | 1 | 7%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 1 | 7%
| FS Predecessors | F | 12 | 80%
| All Activities w/Successors | F | 13 | 87%
| SS Successors | F | 1 | 7%
| FF Successors | F | 1 | 7%
| SF Successors | F | 0 | 0%
| FS Successors | F | 12 | 80%
| Missing Logic | F | 3 | 20%
| Missing Predecessors | F | 1 | 7%
| Missing Successors | F | 2 | 13%
| Open Start | F | 1 | 7%
| Open Finish | F | 1 | 7%
| Logic Density™ - Predecessors | F | 1.07
| All Activities w/Predecessors | F | 14 | 100%
| Total # Predecessors | F | 16
| Activities Missing Predecessors | F | 1 | 7%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 7%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 7%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.07
| All Activities w/Successors | F | 13 | 100%
| Activities Missing Successors | F | 2 | 13%
| Total # Successors | F | 16
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 1 | 7%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 1 | 7%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 0 | 0%
| Completed Ahead - Tasks & Milestones | F | 0
| Completed On-Schedule - Tasks & Milestones | F | 0
| Completed Delayed - Tasks & Milestones | F | 0
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 0
| Avg Finish Variance - Tasks & Milestones | F | 0
| Actually Finished - Tasks | F | 0 | 0%
| Completed Ahead - Tasks | F | 0
| Completed On-Schedule - Tasks | F | 0
| Completed Delayed - Tasks | F | 0
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 0 | 0%
| Actually Finished - Milestones | F | 0 | 0%
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 0 | 0%
| In-Progress Started Ahead - Tasks | F | 0
| In-Progress Started On-Schedule - Tasks | F | 0
| In-Progress Started Delayed - Tasks | F | 0
| In-Progress Delayed Finish - Tasks | F | 0
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | 0
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 15 | 100%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 0 | 0%
| Riding Data Date - Tasks & Milestones | F | 2 | 13%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 13 | 100%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 0 | 0%
| Planned Delayed Finish - Tasks | F | 0 | 0%
| Scheduled to Start - Milestones | F | 2 | 100%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 0 | 0%
| Planned Delayed Finish - Milestones | F | 0 | 0%
| Schedule Baseline Activities | F | 0 | 0%
| Scheduled/Baselined to Start | F | 0
| Scheduled/Baselined to Finish | F | 0
| Start/ed | F | 0
| Finish/ed | F | 0
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | 15 | 100%
| Scheduled to Start | F | 15 | 100%
| Scheduled to Finish | F | 15 | 100%
| Longest Path - Critical Activities and Milestones | F | 9 | 60%
| Critical Milestones (To-Go) | F | 2 | 100%
| Critical Tasks (To-Go) | F | 7 | 54%
| Critical Tasks (In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.29
| High Float 10% | F | 3 | 20%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 9 | 60%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 9 | 60%
| Critical Milestones (To-Go) | F | 2 | 100%
| Critical Tasks (To-Go) | F | 7 | 54%
| Critical Tasks (In Progress) | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | 1:07 | 0.15
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.29
| Logic Density™ | F | 2.13
| CP Logic Density™ | F | 2.33
| Critical w/Missing Logic | F | 2 | 20%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 9 | 60%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 0
| Scheduled to Start | F | 13
| Actual Starts | F | 0
| Baselined to Finish | F | 0
| Scheduled to Finish | F | 13
| Actual Finishes | F | 0
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | 0
| Scheduled to Start | F | 13
| Actual Starts | F | 0
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | 0
| Scheduled to Finish | F | 13
| Actual Finishes | F | 0
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | 0
| Scheduled to Start - To Time Now | F | 0 | 0%
| Started | F | 0
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | 0
| Scheduled to Finish - To Time Now | F | 0
| Finished | F | 0
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | 0
| Not Baselined to Start | F | 0
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | 0
| Baselined to Start - Check | F | 0
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | 0
| Baselined to Finish - Check | F | 0
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | 0
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | 0
| Baselined to Start | F | 0
| Scheduled to Start | F | 0
| Started - Scheduled | F | 0
| Started - Baseline Comparison | F | 0
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 0
| Scheduled to Finish | F | 0
| Finished | F | 0
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-07-30
| Started (incl. Future Baseline Starts) - Scheduled | F | 0 | 0%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 0
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 0 | 0%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 0
| Finished Late | F | N/A
| Completed Ahead | F | 0
| Completed Delayed | F | 0
| Completed On-Schedule | F | 0
| Accelerated | F | 0
| Days Variance | F | 0
| Days Early | F | 0
| Days Late | F | 0
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 0 | 0%
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | 0 | 0%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | 0
| Missed Durations & Late Actual Finish | F | 0
| Completed Ahead | F | 0
| Completed Delayed | F | 0
| Completed On-Schedule | F | 0
| Accelerated | F | 0
| Days Variance | F | 0
| Days Early | F | 0
| Days Late | F | 0
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 0 | 0%
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | 0 | 0%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | 0
| Missed Durations & Late Actual Finish | F | 0
| Baselined Tasks | F | 0
| Baselined to Start - TOTAL | F | 0
| Complete Task Starts - Cumulative | F | 0
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 0
| Complete Task Finishes - Cumulative (in work) | F | 0
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | 0
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-07-30
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-07-30
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-07-30
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-07-30
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | 0
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-07-30
| Total Activities - DRM | F | 0
| Total Activities - DRM Graph | F | 0
| Status Date | F | 2026-07-30
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-07-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-07-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 3 | 20%
| Missing Predecessors | F | 1 | 7%
| Missing Successors | F | 2 | 13%
| Open Start | F | 1 | 7%
| Open Finish | F | 1 | 7%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-07-30
| High Float 10% | F | 3 | 20%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 9 | 60%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 7%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 1 | 7%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 2 | 13%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 7 | 78%
| Longest Path (Tasks & Milestones) | F | 9 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.29
| Critical Milestones (To-Go) | F | 2 | 100%
| Longest Path (Milestones) | F | 2 | 22%
| Normal Tasks | F | 13 | 87%
| Normal Tasks (To-Go) | F | 13 | 87%
| Critical Tasks (To-Go) | F | 7 | 54%
| Critical Tasks (In Progress) | F | 0 | 0%
| Zero Days Float | F | 9 | 60%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.33
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | 2026-07-30
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-10-07
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | T | 13
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 12
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 13
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | T | 13
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 12
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 12
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | 0
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 13
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 13
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 12
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 13
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | T | 13
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | 0
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | 0
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Jacked-up-Schedule-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Jacked up Schedule 2 (7/30/2026 8:00:00 AM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-07-30
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0
| Wrong Status - Actual Finishes | F | 0
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 2 | 33%
| Missing Predecessors | F | 1 | 17%
| Missing Successors | F | 1 | 17%
| Open Start | F | 0
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 1 | 17%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 2 | 33%
| Status Date | F | 2026-07-30
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 3 | 50%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 17%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 1 | 17%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 2 | 33%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 1 | 17%
| Negative Float | F | 2 | 33%
| Tasks & Milestones (To Go) | F | 6 | 100%
| Milestones (To-Go) | F | 3 | 50%
| Normal Tasks (To-Go) | F | 3 | 50%
| Normal Tasks (To-Go, In Progress) | F | 0 | 0%
| Critical Path (Tasks & Milestones) | F | 5 | 83%
| Critical Path (Milestones) | F | 3 | 60%
| Critical Path (Normal Tasks) | F | 2 | 40%
| Critical Path (Normal In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:01
| Negative Float | F | 2 | 33%
| Zero Days Float | F | 3 | 50%
| Near-Critical (<10 Days Float) | F | 5 | 83%
| CP Logic Density™ | F | 2.4
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | 0
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | 2026-07-30
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-07-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-07-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-07-30
| Total Activities | F | 6
| Milestones | F | 3 | 50%
| Normal Tasks | F | 3 | 50%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 6 | 100%
| Completed Tasks & Milestones | F | 0 | 0%
| Completed Milestones | F | 0 | 0%
| Completed Tasks | F | 0 | 0%
| Total Activities (To-Go) - % of Total | F | 6 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 6 | 100%
| Milestones (To-Go) | F | 3 | 50%
| Normal Tasks (To-Go) | F | 3 | 50%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 5 | 100%
| Longest Path (Normal Tasks) | F | 2 | 40%
| Longest Path (Milestones) | F | 3 | 60%
| Critical Milestones (To-Go) | F | 3 | 60%
| Critical Normal Tasks (To-Go) | F | 2 | 40%
| Riding Data Date | F | 2 | 33%
| Baselined to Start | F | 0
| Scheduled to Start | F | 3
| Actual Starts | F | 0
| Baselined to Finish | F | 0
| Scheduled to Finish | F | 3
| Actual Finishes | F | 0
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | 0
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | 0
| Duration Ratio Metric (DRM) | F | 0
| DRM Graph | F | 0
| Baselined to Start | F | 0
| Scheduled to Start | F | 3
| Baselined to Finish | F | 0
| Scheduled to Finish | F | 3
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 6 | 100%
| Critical Path To-Go | F | 5 | 83%
| Status Date | F | 2026-07-30
| Total Activities | F | 6
| Milestones | F | 3 | 50%
| Normal Tasks | F | 3 | 50%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 6 | 100%
| Completed Tasks & Milestones | F | 0 | 0%
| Completed Milestones | F | 0 | 0%
| Completed Tasks | F | 0 | 0%
| Total Activities (To-Go) - % of Total | F | 6 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 6 | 100%
| Milestones (To-Go) | F | 3 | 50%
| Normal Tasks (To-Go) | F | 3 | 50%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 5 | 100%
| Longest Path (Normal Tasks) | F | 2 | 40%
| Longest Path (Milestones) | F | 3 | 60%
| Riding Data Date | F | 2 | 33%
| Status Date | F | 2026-07-30
| Total Activities (To-Go) - % of Total | F | 6 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 6 | 100%
| Summary-to-Task Ratio (To-Go) | F | N/A | 0
| Milestone-to-Task Ratio (To-Go) | F | 1:01 | 1
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:01 | 1.5
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 5 | 83%
| Wrong Status (To-Go) | F | 0
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 6 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 6 | 100%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 17
| Avg. Remaining Duration | F | 17
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 3 | 100%
| Critical Activities (To-Go) | F | 2 | 67%
| Avg. Critical Original Duration | F | 20
| Avg. Critical Remaining Duration | F | 20
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 2 | 67%
| Activities (To-Go) | F | 3 | 100%
| Total Constraints | F | 3 | 50%
| Start No Earlier Than | F | 2 | 33%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 1 | 17%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 1 | 17%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 2 | 17%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 3 | 50%
| No Constraints | F | 3 | 50%
| Logic Density™ | F | 2.33
| Logic Density™ - Predecessors | F | 1.17
| Logic Density™ - Successors | F | 1.17
| Summary Links | F | N/A | 0%
| All Activities w/Predecessors | F | 5 | 83%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 5 | 83%
| All Activities w/Successors | F | 5 | 83%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 5 | 83%
| Missing Logic | F | 2 | 33%
| Missing Predecessors | F | 1 | 17%
| Missing Successors | F | 1 | 17%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.17
| All Activities w/Predecessors | F | 5 | 100%
| Total # Predecessors | F | 7
| Activities Missing Predecessors | F | 1 | 17%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 17%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 17%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.17
| All Activities w/Successors | F | 5 | 100%
| Activities Missing Successors | F | 1 | 17%
| Total # Successors | F | 7
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 1 | 17%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 1 | 17%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 0 | 0%
| Completed Ahead - Tasks & Milestones | F | 0
| Completed On-Schedule - Tasks & Milestones | F | 0
| Completed Delayed - Tasks & Milestones | F | 0
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 0
| Avg Finish Variance - Tasks & Milestones | F | 0
| Actually Finished - Tasks | F | 0 | 0%
| Completed Ahead - Tasks | F | 0
| Completed On-Schedule - Tasks | F | 0
| Completed Delayed - Tasks | F | 0
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 0 | 0%
| Actually Finished - Milestones | F | 0 | 0%
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 0 | 0%
| In-Progress Started Ahead - Tasks | F | 0
| In-Progress Started On-Schedule - Tasks | F | 0
| In-Progress Started Delayed - Tasks | F | 0
| In-Progress Delayed Finish - Tasks | F | 0
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | 0
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 6 | 100%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 0 | 0%
| Riding Data Date - Tasks & Milestones | F | 2 | 33%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 3 | 100%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 0 | 0%
| Planned Delayed Finish - Tasks | F | 0 | 0%
| Scheduled to Start - Milestones | F | 3 | 100%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 0 | 0%
| Planned Delayed Finish - Milestones | F | 0 | 0%
| Schedule Baseline Activities | F | 0 | 0%
| Scheduled/Baselined to Start | F | 0
| Scheduled/Baselined to Finish | F | 0
| Start/ed | F | 0
| Finish/ed | F | 0
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | 6 | 100%
| Scheduled to Start | F | 6 | 100%
| Scheduled to Finish | F | 6 | 100%
| Longest Path - Critical Activities and Milestones | F | 5 | 83%
| Critical Milestones (To-Go) | F | 3 | 100%
| Critical Tasks (To-Go) | F | 2 | 67%
| Critical Tasks (In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:01 | 1.5
| High Float 10% | F | 1 | 17%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 3 | 50%
| Negative Float | F | 2 | 33%
| Longest Path - Critical Activities and Milestones | F | 5 | 83%
| Critical Milestones (To-Go) | F | 3 | 100%
| Critical Tasks (To-Go) | F | 2 | 67%
| Critical Tasks (In Progress) | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | 1:01 | 1
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:01 | 1.5
| Logic Density™ | F | 2.33
| CP Logic Density™ | F | 2.4
| Critical w/Missing Logic | F | 2 | 33%
| Critical w/Hard Constraints | F | 1 | 17%
| Zero Days Float | F | 3 | 50%
| Negative Float | F | 2 | 33%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 1 | 17%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 0
| Scheduled to Start | F | 3
| Actual Starts | F | 0
| Baselined to Finish | F | 0
| Scheduled to Finish | F | 3
| Actual Finishes | F | 0
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | 0
| Scheduled to Start | F | 3
| Actual Starts | F | 0
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | 0
| Scheduled to Finish | F | 3
| Actual Finishes | F | 0
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | 0
| Scheduled to Start - To Time Now | F | 0 | 0%
| Started | F | 0
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | 0
| Scheduled to Finish - To Time Now | F | 0
| Finished | F | 0
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | 0
| Not Baselined to Start | F | 0
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | 0
| Baselined to Start - Check | F | 0
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | 0
| Baselined to Finish - Check | F | 0
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | 0
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | 0
| Baselined to Start | F | 0
| Scheduled to Start | F | 0
| Started - Scheduled | F | 0
| Started - Baseline Comparison | F | 0
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 0
| Scheduled to Finish | F | 0
| Finished | F | 0
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-07-30
| Started (incl. Future Baseline Starts) - Scheduled | F | 0 | 0%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 0
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 0 | 0%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 0
| Finished Late | F | N/A
| Completed Ahead | F | 0
| Completed Delayed | F | 0
| Completed On-Schedule | F | 0
| Accelerated | F | 0
| Days Variance | F | 0
| Days Early | F | 0
| Days Late | F | 0
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 0 | 0%
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | 0 | 0%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | 0
| Missed Durations & Late Actual Finish | F | 0
| Completed Ahead | F | 0
| Completed Delayed | F | 0
| Completed On-Schedule | F | 0
| Accelerated | F | 0
| Days Variance | F | 0
| Days Early | F | 0
| Days Late | F | 0
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 0 | 0%
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | 0 | 0%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | 0
| Missed Durations & Late Actual Finish | F | 0
| Baselined Tasks | F | 0
| Baselined to Start - TOTAL | F | 0
| Complete Task Starts - Cumulative | F | 0
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 0
| Complete Task Finishes - Cumulative (in work) | F | 0
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | 0
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-07-30
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-07-30
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-07-30
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-07-30
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | 0
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-07-30
| Total Activities - DRM | F | 0
| Total Activities - DRM Graph | F | 0
| Status Date | F | 2026-07-30
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-07-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-07-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 2 | 33%
| Missing Predecessors | F | 1 | 17%
| Missing Successors | F | 1 | 17%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 1 | 17%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 2 | 33%
| Status Date | F | 2026-07-30
| High Float 10% | F | 1 | 17%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 3 | 50%
| Negative Float | F | 2 | 33%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 17%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 1 | 17%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 2 | 33%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 2 | 40%
| Longest Path (Tasks & Milestones) | F | 5 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:01 | 1.5
| Critical Milestones (To-Go) | F | 3 | 100%
| Longest Path (Milestones) | F | 3 | 60%
| Normal Tasks | F | 3 | 50%
| Normal Tasks (To-Go) | F | 3 | 50%
| Critical Tasks (To-Go) | F | 2 | 67%
| Critical Tasks (In Progress) | F | 0 | 0%
| Zero Days Float | F | 3 | 50%
| Negative Float | F | 2 | 33%
| CP Logic Density™ | F | 2.4
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | 2026-07-30
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-10-09
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | T | 3
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 2
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 3
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | T | 3
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | 2
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 2
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | 0
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | 3
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 3
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 2
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 3
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | T | 3
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | 0
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | 0
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Hard_File_updated3
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated3 (10/12/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-10-12
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 41 | 79%
| Missing Logic | F | 6 | 9%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 6 | 9%
| Open Start | F | 0
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 49 | 72%
| Status Date | F | 2026-10-12
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 4 | 6%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 11 | 16%
| Negative Float | F | 49 | 72%
| Tasks & Milestones (To Go) | F | 68 | 62%
| Milestones (To-Go) | F | 16 | 24%
| Normal Tasks (To-Go) | F | 52 | 76%
| Normal Tasks (To-Go, In Progress) | F | 0 | 0%
| Critical Path (Tasks & Milestones) | F | 49 | 72%
| Critical Path (Milestones) | F | 9 | 18%
| Critical Path (Normal Tasks) | F | 40 | 82%
| Critical Path (Normal In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04
| Negative Float | F | 49 | 72%
| Zero Days Float | F | 0 | 0%
| Near-Critical (<10 Days Float) | F | 56 | 82%
| CP Logic Density™ | F | 2.12
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.47
| BEI - Total Tasks | F | 68
| BEI - Complete Tasks | F | 32 | 47%
| BEI - Incomplete Tasks | F | 36 | 53%
| Status Date | F | 2026-10-12
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-10-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-10-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-10-12
| Total Activities | F | 141
| Milestones | F | 26 | 18%
| Normal Tasks | F | 84 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 42 | 38%
| Completed Milestones | F | 10 | 38%
| Completed Tasks | F | 32 | 38%
| Total Activities (To-Go) - % of Total | F | 92 | 65%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 68 | 74%
| Milestones (To-Go) | F | 16 | 17%
| Normal Tasks (To-Go) | F | 52 | 57%
| Summaries (To-Go) | F | 24 | 26%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 49 | 78%
| Longest Path (Normal Tasks) | F | 40 | 63%
| Longest Path (Milestones) | F | 9 | 14%
| Critical Milestones (To-Go) | F | 9 | 18%
| Critical Normal Tasks (To-Go) | F | 40 | 82%
| Riding Data Date | F | 4 | 6%
| Baselined to Start | F | 84
| Scheduled to Start | F | 84
| Actual Starts | F | 32
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Actual Finishes | F | 32
| Started Delayed (<=30 days) | F | 24 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 24 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.46
| BEI - Value Task Finishes - Cumulative | F | 0.47
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 3.47
| FEI - Value Task Finish - Cumulative | F | 3.25
| Current Baseline to Start & Started (BL Plan) | F | 32
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 52
| Current Baseline to Finish & Finished (BL Plan) | F | 32
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 52
| Duration Ratio Metric (DRM) | F | 28
| DRM Graph | F | 28
| Baselined to Start | F | 52
| Scheduled to Start | F | 52
| Baselined to Finish | F | 52
| Scheduled to Finish | F | 52
| BEI - Value Activities | F | 0.48
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 68 | 74%
| Critical Path To-Go | F | 49 | 72%
| Status Date | F | 2026-10-12
| Total Activities | F | 141
| Milestones | F | 26 | 18%
| Normal Tasks | F | 84 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 42 | 38%
| Completed Milestones | F | 10 | 38%
| Completed Tasks | F | 32 | 38%
| Total Activities (To-Go) - % of Total | F | 92 | 65%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 68 | 74%
| Milestones (To-Go) | F | 16 | 17%
| Normal Tasks (To-Go) | F | 52 | 57%
| Summaries (To-Go) | F | 24 | 26%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 49 | 78%
| Longest Path (Normal Tasks) | F | 40 | 63%
| Longest Path (Milestones) | F | 9 | 14%
| Riding Data Date | F | 4 | 6%
| Status Date | F | 2026-10-12
| Total Activities (To-Go) - % of Total | F | 92 | 65%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 68 | 74%
| Summary-to-Task Ratio (To-Go) | F | 1:02 | 0.46
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.31
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 49 | 72%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 68 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 68 | 74%
| Estimated Duration | F | 41 | 79%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 2
| Avg. Remaining Duration | F | 2
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 40 | 77%
| Avg. Critical Original Duration | F | 2
| Avg. Critical Remaining Duration | F | 2
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 52 | 62%
| Total Constraints | F | 44 | 65%
| Start No Earlier Than | F | 44 | 65%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 4 | 6%
| Open Ends w/o Constraints | F | 2 | 3%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 24 | 35%
| No Constraints | F | 23 | 34%
| Logic Density™ | F | 2.07
| Logic Density™ - Predecessors | F | 1.09
| Logic Density™ - Successors | F | 0.99
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 68 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 68 | 100%
| All Activities w/Successors | F | 62 | 91%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 62 | 91%
| Missing Logic | F | 6 | 9%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 6 | 9%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.09
| All Activities w/Predecessors | F | 68 | 100%
| Total # Predecessors | F | 74
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 0.99
| All Activities w/Successors | F | 62 | 100%
| Activities Missing Successors | F | 6 | 9%
| Total # Successors | F | 67
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 42 | 38%
| Completed Ahead - Tasks & Milestones | F | 3 | 7%
| Completed On-Schedule - Tasks & Milestones | F | 7 | 17%
| Completed Delayed - Tasks & Milestones | F | 32 | 76%
| Avg Days Finished Early - Tasks & Milestones | F | 21
| Avg Days Finished Late - Tasks & Milestones | F | 6
| Avg Finish Variance - Tasks & Milestones | F | 3
| Actually Finished - Tasks | F | 32 | 38%
| Completed Ahead - Tasks | F | 3 | 9%
| Completed On-Schedule - Tasks | F | 5 | 16%
| Completed Delayed - Tasks | F | 24 | 75%
| Accelerated Durations Early/On-Schedule - Tasks | F | 2 | 2%
| Accelerated Durations Late - Tasks | F | 2 | 2%
| Extended Durations - Tasks | F | 5 | 6%
| Actually Finished - Milestones | F | 10 | 38%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 2 | 20%
| Completed Delayed - Milestones | F | 8 | 80%
| Actually Started - Tasks | F | 0 | 0%
| In-Progress Started Ahead - Tasks | F | 0
| In-Progress Started On-Schedule - Tasks | F | 0
| In-Progress Started Delayed - Tasks | F | 0
| In-Progress Delayed Finish - Tasks | F | 0
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | 0
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 68 | 62%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 68 | 100%
| Riding Data Date - Tasks & Milestones | F | 4 | 6%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 52 | 62%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 52 | 100%
| Planned Delayed Finish - Tasks | F | 52 | 100%
| Scheduled to Start - Milestones | F | 16 | 62%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 16 | 100%
| Planned Delayed Finish - Milestones | F | 16 | 100%
| Schedule Baseline Activities | F | 110 | 100%
| Scheduled/Baselined to Start | F | 68
| Scheduled/Baselined to Finish | F | 68
| Start/ed | F | 42
| Finish/ed | F | 42
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 0 | 0%
| Completed Delayed (>30 days) | F | 0 | 0%
| SPI(t) | F | 1.25
| Scheduled Activities | F | 110 | 100%
| Scheduled to Start | F | 68 | 62%
| Scheduled to Finish | F | 68 | 62%
| Longest Path - Critical Activities and Milestones | F | 49 | 72%
| Critical Milestones (To-Go) | F | 9 | 56%
| Critical Tasks (To-Go) | F | 40 | 77%
| Critical Tasks (In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| High Float 10% | F | 11 | 16%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 49 | 72%
| Longest Path - Critical Activities and Milestones | F | 49 | 72%
| Critical Milestones (To-Go) | F | 9 | 56%
| Critical Tasks (To-Go) | F | 40 | 77%
| Critical Tasks (In Progress) | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.31
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| Logic Density™ | F | 2.09
| CP Logic Density™ | F | 2.12
| Critical w/Missing Logic | F | 1 | 9%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 49 | 72%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 84
| Scheduled to Start | F | 84
| Actual Starts | F | 32
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Actual Finishes | F | 32
| Started Delayed (<=30 days) | F | 24 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 24 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 84
| Scheduled to Start | F | 84
| Actual Starts | F | 32
| Current Baselined to Start & Started | F | 32
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Actual Finishes | F | 32
| Current Baselined to Finish & Finished | F | 32
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 24 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 24 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 69 | 82%
| Scheduled to Start - To Time Now | F | 69 | 82%
| Started | F | 32
| Started Late | F | 24
| Started Delayed (<=30 days) | F | 24 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 0.46
| Baselined to Finish - To Time Now | F | 68 | 81%
| Scheduled to Finish - To Time Now | F | 68 | 81%
| Finished | F | 32
| Finished Late | F | 24
| Completed Delayed (<=30 days) | F | 24 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.47
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.46
| BEI - Value Task Finishes - Cumulative | F | 0.47
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 3.47
| FEI - Value Task Finish - Cumulative | F | 3.25
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 32
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 52
| Baselined to Start - Check | F | 84
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 32
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 52
| Baselined to Finish - Check | F | 84
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 32
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 52
| Current Baseline to Finish & Finished (BL Plan) | F | 32
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 52
| Baselined to Start | F | 69
| Scheduled to Start | F | 69 | 100%
| Started - Scheduled | F | 32 | 46%
| Started - Baseline Comparison | F | 32 | 46%
| BEI - Value Task Starts | F | 0.46
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 68
| Scheduled to Finish | F | 68
| Finished | F | 32
| BEI - Value Task Finishes | F | 0.47
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-10-12
| Started (incl. Future Baseline Starts) - Scheduled | F | 32 | 38%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 32 | 38%
| Started Late (from Baseline) | F | 24
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 32 | 38%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 32 | 38%
| Finished Late | F | 24
| Completed Ahead | F | 3 | 9%
| Completed Delayed | F | 24 | 75%
| Completed On-Schedule | F | 5 | 16%
| Accelerated | F | 3 | 9%
| Days Variance | F | 84 | 262%
| Days Early | F | 63 | 196%
| Days Late | F | 147 | 458%
| Avg Days Early | F | 21
| Avg Days Late | F | 6
| Avg Variance | F | 3
| Actually Finished | F | 32 | 29%
| Took Longer than Planned | F | 9 | 21%
| Took Less Than Planned | F | 7 | 17%
| Completed (w/Baseline Duration) | F | 31 | 37%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 1 | 1%
| Baseline-to-Date Completed Tasks | F | 32 | 47%
| Missed Durations | F | 5 | 16%
| Missed Durations & Late Actual Finish | F | 4 | 13%
| Completed Ahead | F | 3 | 9%
| Completed Delayed | F | 24 | 75%
| Completed On-Schedule | F | 5 | 16%
| Accelerated | F | 3 | 9%
| Days Variance | F | 84 | 262%
| Days Early | F | 63 | 196%
| Days Late | F | 147 | 458%
| Avg Days Early | F | 21
| Avg Days Late | F | 6
| Avg Variance | F | 3
| Actually Finished | F | 32 | 29%
| Took Longer than Planned | F | 9 | 21%
| Took Less Than Planned | F | 7 | 17%
| Completed (w/Baseline Duration) | F | 31 | 37%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 1 | 1%
| Baseline-to-Date Completed Tasks | F | 32 | 47%
| Missed Durations | F | 5 | 16%
| Missed Durations & Late Actual Finish | F | 4 | 13%
| Baselined Tasks | F | 84
| Baselined to Start - TOTAL | F | 84
| Complete Task Starts - Cumulative | F | 32 | 46%
| Incomplete Task Starts - Cumulative (in work) | F | 37 | 54%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 84
| Complete Task Finishes - Cumulative (in work) | F | 32 | 47%
| Incomplete Task Finishes - Cumulative | F | 36 | 47%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.47
| BEI - Total Tasks | F | 68
| BEI - Complete Tasks | F | 32 | 47%
| BEI - Incomplete Tasks | F | 36 | 53%
| BEI - Value Tasks (adjusted) | F | 0.47
| BEI - Complete Tasks (adjusted) | F | 32 | 47%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-10-12
| BEI - Value Milestones | F | 0.53
| BEI - Total Milestones | F | 19
| BEI - Complete Milestones | F | 10 | 53%
| BEI - Incomplete Milestones | F | 9 | 47%
| BEI - Value Milestones (adjusted) | F | 0.53
| BEI - Complete Milestones (adjusted) | F | 10 | 53%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-10-12
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-10-12
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-10-12
| BEI - Value Tasks | F | 0.47
| BEI - Total Tasks | F | 68
| BEI - Incomplete Tasks | F | 36 | 53%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 10 | 53%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0.53
| BEI - Total Milestones | F | 19
| BEI - Complete Milestones | F | 10 | 53%
| BEI - Incomplete Milestones | F | 9 | 47%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.47
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0.53
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-10-12
| Total Activities - DRM | F | 28
| Total Activities - DRM Graph | F | 28
| Status Date | F | 2026-10-12
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-10-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-10-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.46
| BEI - Value Task Finishes - Cumulative | F | 0.47
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 3.47
| FEI - Value Task Finish - Cumulative | F | 3.25
| BEI - Value Tasks | F | 0.47
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0.53
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.47
| BEI - Complete Tasks | F | 32 | 47%
| BEI - Incomplete Tasks | F | 36 | 53%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 41 | 79%
| Missing Logic | F | 6 | 9%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 6 | 9%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 49 | 72%
| Status Date | F | 2026-10-12
| High Float 10% | F | 11 | 16%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 49 | 72%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 4 | 6%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 40 | 63%
| Longest Path (Tasks & Milestones) | F | 49 | 78%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| Critical Milestones (To-Go) | F | 9 | 56%
| Longest Path (Milestones) | F | 9 | 14%
| Normal Tasks | F | 84 | 60%
| Normal Tasks (To-Go) | F | 52 | 57%
| Critical Tasks (To-Go) | F | 40 | 77%
| Critical Tasks (In Progress) | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 49 | 72%
| CP Logic Density™ | F | 2.12
| Time Now | F | 2026-10-12
| Forecast to be Finished | F | 68 | 81%
| Completed On Time | T | 9 | 13%
| Completed Late | F | 23 | 34%
| Not Completed | F | 36 | 53%
| Baseline Finish Compliance | T | 13%
| Forecast to be Started | F | 69 | 82%
| Started On Time | T | 9 | 13%
| Started Late | F | 23 | 33%
| Not Started | F | 37 | 54%
| Baseline Start Compliance | T | 17%
1 | Completed Activities | F | 32
HSD01 | Time Now | F | 2026-10-12
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 37 | 44%
HSD04 | Started Late | F | 23 | 33%
HSD05 | Forecast to be Finished but not Finished yet | T | 36 | 43%
HSD06 | Finished Late | F | 23 | 34%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-12-12
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 1 | 50%
SEM02 | BRI Current | T | 0.04
SEM03 | BRI Cumulative | F | 0.47
SEM04 | BPI Current | T | 0.04
SEM05 | BEI Current | T | 0.09
SEM06 | BEI Cumulative | T | 0.47
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 3.47
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 3.25
SEM07 | To Go - Planned Task Starts - Count | T | 52
SEM07 | To Go - BEI - Task Finishes - Count | T | 52
SEM07 | To Go - Baselined Task Starts - Count | T | 52
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 3.47
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 33
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 15
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 36
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 16
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 3.47
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 3.25
SEM07 | To Go - Planned Task Starts - Count | T | 52
SEM07 | To Go - BEI - Task Finishes - Count | T | 52
SEM07 | To Go - Baselined Task Starts - Count | T | 52
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 3.47
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 48
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 33
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 15
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 52
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 36
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 16
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 33
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 15
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 36
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 16
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 3.47
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 3.25
SEM07 | To Go - Planned Task Starts - Count | T | 52
SEM07 | To Go - BEI - Task Finishes - Count | T | 52
SEM07 | To Go - Baselined Task Starts - Count | T | 52
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 3.47
SEM07 | TC-BEI | T | 3.25
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -2.52
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Hard_File_updated4-24-hour-cal
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated4 24 hour calendar (11/12/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-11-12
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 3 | 16%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 9 | 64%
| Missing Logic | F | 2 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 2 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 15 | 79%
| Status Date | F | 2026-11-12
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 3 | 16%
| Negative Float | F | 15 | 79%
| Tasks & Milestones (To Go) | F | 19 | 17%
| Milestones (To-Go) | F | 5 | 26%
| Normal Tasks (To-Go) | F | 14 | 74%
| Normal Tasks (To-Go, In Progress) | F | 4 | 21%
| Critical Path (Tasks & Milestones) | F | 15 | 79%
| Critical Path (Milestones) | F | 4 | 27%
| Critical Path (Normal Tasks) | F | 11 | 73%
| Critical Path (Normal In Progress) | F | 1 | 7%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:03
| Negative Float | F | 15 | 79%
| Zero Days Float | F | 0 | 0%
| Near-Critical (<10 Days Float) | F | 16 | 84%
| CP Logic Density™ | F | 2.07
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.83
| BEI - Total Tasks | F | 84
| BEI - Complete Tasks | F | 70 | 83%
| BEI - Incomplete Tasks | F | 14 | 17%
| Status Date | F | 2026-11-12
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-11-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-11-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-11-12
| Total Activities | F | 141
| Milestones | F | 26 | 18%
| Normal Tasks | F | 84 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 91 | 83%
| Completed Milestones | F | 21 | 81%
| Completed Tasks | F | 70 | 83%
| Total Activities (To-Go) - % of Total | F | 30 | 21%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 19 | 63%
| Milestones (To-Go) | F | 5 | 17%
| Normal Tasks (To-Go) | F | 14 | 47%
| Summaries (To-Go) | F | 11 | 37%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 15 | 83%
| Longest Path (Normal Tasks) | F | 11 | 61%
| Longest Path (Milestones) | F | 4 | 22%
| Critical Milestones (To-Go) | F | 4 | 27%
| Critical Normal Tasks (To-Go) | F | 11 | 73%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 84
| Scheduled to Start | F | 84
| Actual Starts | F | 74
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Actual Finishes | F | 70
| Started Delayed (<=30 days) | F | 51 | 77%
| Started Delayed (Between 31 to 60 days) | F | 9 | 14%
| Started Delayed (>60 days) | F | 6 | 9%
| Completed Delayed (<=30 days) | F | 49 | 79%
| Completed Delayed (Between 31 to 60 days) | F | 7 | 11%
| Completed Delayed (>60 days) | F | 6 | 10%
| BEI - Value Task Starts - Cumulative | F | 0.88
| BEI - Value Task Finishes - Cumulative | F | 0.83
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | 74
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 10
| Current Baseline to Finish & Finished (BL Plan) | F | 70
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 14
| Duration Ratio Metric (DRM) | F | 66
| DRM Graph | F | 66
| Baselined to Start | F | 14
| Scheduled to Start | F | 14
| Baselined to Finish | F | 14
| Scheduled to Finish | F | 14
| BEI - Value Activities | F | 0.83
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 19 | 63%
| Critical Path To-Go | F | 15 | 79%
| Status Date | F | 2026-11-12
| Total Activities | F | 141
| Milestones | F | 26 | 18%
| Normal Tasks | F | 84 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 91 | 83%
| Completed Milestones | F | 21 | 81%
| Completed Tasks | F | 70 | 83%
| Total Activities (To-Go) - % of Total | F | 30 | 21%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 19 | 63%
| Milestones (To-Go) | F | 5 | 17%
| Normal Tasks (To-Go) | F | 14 | 47%
| Summaries (To-Go) | F | 11 | 37%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 15 | 83%
| Longest Path (Normal Tasks) | F | 11 | 61%
| Longest Path (Milestones) | F | 4 | 22%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-11-12
| Total Activities (To-Go) - % of Total | F | 30 | 21%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 19 | 63%
| Summary-to-Task Ratio (To-Go) | F | 1:01 | 0.79
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.36
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.36
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 15 | 79%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 3 | 16%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 19 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 19 | 63%
| Estimated Duration | F | 9 | 64%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 2
| Avg. Remaining Duration | F | 1
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 11 | 79%
| Avg. Critical Original Duration | F | 1
| Avg. Critical Remaining Duration | F | 1
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 14 | 17%
| Total Constraints | F | 3 | 16%
| Start No Earlier Than | F | 3 | 16%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 1 | 5%
| Open Ends w/o Constraints | F | 1 | 5%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 16 | 84%
| No Constraints | F | 15 | 79%
| Logic Density™ | F | 2
| Logic Density™ - Predecessors | F | 1.05
| Logic Density™ - Successors | F | 0.95
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 15 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 19 | 100%
| All Activities w/Successors | F | 17 | 89%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 17 | 89%
| Missing Logic | F | 2 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 2 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.07
| All Activities w/Predecessors | F | 15 | 100%
| Total # Predecessors | F | 16
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 0.95
| All Activities w/Successors | F | 17 | 100%
| Activities Missing Successors | F | 2 | 11%
| Total # Successors | F | 18
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 91 | 83%
| Completed Ahead - Tasks & Milestones | F | 3 | 3%
| Completed On-Schedule - Tasks & Milestones | F | 7 | 8%
| Completed Delayed - Tasks & Milestones | F | 81 | 89%
| Avg Days Finished Early - Tasks & Milestones | F | 21
| Avg Days Finished Late - Tasks & Milestones | F | 25
| Avg Finish Variance - Tasks & Milestones | F | 21
| Actually Finished - Tasks | F | 70 | 83%
| Completed Ahead - Tasks | F | 3 | 4%
| Completed On-Schedule - Tasks | F | 5 | 7%
| Completed Delayed - Tasks | F | 62 | 89%
| Accelerated Durations Early/On-Schedule - Tasks | F | 2 | 2%
| Accelerated Durations Late - Tasks | F | 2 | 2%
| Extended Durations - Tasks | F | 8 | 10%
| Actually Finished - Milestones | F | 21 | 81%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 2 | 10%
| Completed Delayed - Milestones | F | 19 | 90%
| Actually Started - Tasks | F | 4 | 5%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 4 | 100%
| In-Progress Delayed Finish - Tasks | F | 4 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 35
| Avg Start Variance | F | 35
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 15 | 14%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 15 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 10 | 12%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 10 | 100%
| Planned Delayed Finish - Tasks | F | 10 | 100%
| Scheduled to Start - Milestones | F | 5 | 19%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 5 | 100%
| Planned Delayed Finish - Milestones | F | 5 | 100%
| Schedule Baseline Activities | F | 110 | 100%
| Scheduled/Baselined to Start | F | 19
| Scheduled/Baselined to Finish | F | 19
| Start/ed | F | 95
| Finish/ed | F | 91
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 15 | 23%
| Completed Delayed (>30 days) | F | 13 | 21%
| SPI(t) | F | 1.31
| Scheduled Activities | F | 110 | 100%
| Scheduled to Start | F | 19 | 17%
| Scheduled to Finish | F | 19 | 17%
| Longest Path - Critical Activities and Milestones | F | 15 | 79%
| Critical Milestones (To-Go) | F | 4 | 80%
| Critical Tasks (To-Go) | F | 11 | 79%
| Critical Tasks (In Progress) | F | 1 | 9%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.36
| High Float 10% | F | 3 | 16%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 15 | 79%
| Longest Path - Critical Activities and Milestones | F | 15 | 79%
| Critical Milestones (To-Go) | F | 4 | 80%
| Critical Tasks (To-Go) | F | 11 | 79%
| Critical Tasks (In Progress) | F | 1 | 9%
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.36
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.36
| Logic Density™ | F | 2.09
| CP Logic Density™ | F | 2.07
| Critical w/Missing Logic | F | 1 | 11%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 15 | 79%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 84
| Scheduled to Start | F | 84
| Actual Starts | F | 74
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Actual Finishes | F | 70
| Started Delayed (<=30 days) | F | 51 | 77%
| Started Delayed (Between 31 to 60 days) | F | 9 | 14%
| Started Delayed (>60 days) | F | 6 | 9%
| Completed Delayed (<=30 days) | F | 49 | 79%
| Completed Delayed (Between 31 to 60 days) | F | 7 | 11%
| Completed Delayed (>60 days) | F | 6 | 10%
| Baselined to Start | F | 84
| Scheduled to Start | F | 84
| Actual Starts | F | 74
| Current Baselined to Start & Started | F | 74
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Actual Finishes | F | 70
| Current Baselined to Finish & Finished | F | 70
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 51 | 77%
| Started Delayed (Between 31 to 60 days) | F | 9 | 14%
| Started Delayed (>60 days) | F | 6 | 9%
| Completed Delayed (<=30 days) | F | 49 | 79%
| Completed Delayed (Between 31 to 60 days) | F | 7 | 11%
| Completed Delayed (>60 days) | F | 6 | 10%
| Baselined to Start - To Time Now | F | 84 | 100%
| Scheduled to Start - To Time Now | F | 84 | 100%
| Started | F | 74
| Started Late | F | 66
| Started Delayed (<=30 days) | F | 51 | 77%
| Started Delayed (Between 31 to 60 days) | F | 9 | 14%
| Started Delayed (>60 days) | F | 6 | 9%
| BEI - Value Task Starts | F | 0.88
| Baselined to Finish - To Time Now | F | 84 | 100%
| Scheduled to Finish - To Time Now | F | 84 | 100%
| Finished | F | 70
| Finished Late | F | 62
| Completed Delayed (<=30 days) | F | 49 | 79%
| Completed Delayed (Between 31 to 60 days) | F | 7 | 11%
| Completed Delayed (>60 days) | F | 6 | 10%
| BEI - Value Task Finishes | F | 0.83
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.88
| BEI - Value Task Finishes - Cumulative | F | 0.83
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 74
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 10
| Baselined to Start - Check | F | 84
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 70
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 14
| Baselined to Finish - Check | F | 84
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 74
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 10
| Current Baseline to Finish & Finished (BL Plan) | F | 70
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 14
| Baselined to Start | F | 84
| Scheduled to Start | F | 84 | 100%
| Started - Scheduled | F | 74 | 88%
| Started - Baseline Comparison | F | 74 | 88%
| BEI - Value Task Starts | F | 0.88
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Finished | F | 70
| BEI - Value Task Finishes | F | 0.83
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-11-12
| Started (incl. Future Baseline Starts) - Scheduled | F | 74 | 88%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 74 | 88%
| Started Late (from Baseline) | F | 66
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 70 | 83%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 70 | 83%
| Finished Late | F | 62
| Completed Ahead | F | 3 | 4%
| Completed Delayed | F | 62 | 89%
| Completed On-Schedule | F | 5 | 7%
| Accelerated | F | 3 | 4%
| Days Variance | F | 1483 | 2118%
| Days Early | F | 63 | 89%
| Days Late | F | 1545 | 2208%
| Avg Days Early | F | 21
| Avg Days Late | F | 25
| Avg Variance | F | 21
| Actually Finished | F | 70 | 64%
| Took Longer than Planned | F | 15 | 16%
| Took Less Than Planned | F | 23 | 25%
| Completed (w/Baseline Duration) | F | 69 | 82%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 1 | 1%
| Baseline-to-Date Completed Tasks | F | 70 | 83%
| Missed Durations | F | 8 | 11%
| Missed Durations & Late Actual Finish | F | 7 | 10%
| Completed Ahead | F | 3 | 4%
| Completed Delayed | F | 62 | 89%
| Completed On-Schedule | F | 5 | 7%
| Accelerated | F | 3 | 4%
| Days Variance | F | 1483 | 2118%
| Days Early | F | 63 | 89%
| Days Late | F | 1545 | 2208%
| Avg Days Early | F | 21
| Avg Days Late | F | 25
| Avg Variance | F | 21
| Actually Finished | F | 70 | 64%
| Took Longer than Planned | F | 15 | 16%
| Took Less Than Planned | F | 23 | 25%
| Completed (w/Baseline Duration) | F | 69 | 82%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 1 | 1%
| Baseline-to-Date Completed Tasks | F | 70 | 83%
| Missed Durations | F | 8 | 11%
| Missed Durations & Late Actual Finish | F | 7 | 10%
| Baselined Tasks | F | 84
| Baselined to Start - TOTAL | F | 84
| Complete Task Starts - Cumulative | F | 74 | 88%
| Incomplete Task Starts - Cumulative (in work) | F | 10 | 12%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 84
| Complete Task Finishes - Cumulative (in work) | F | 70 | 83%
| Incomplete Task Finishes - Cumulative | F | 14 | 83%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.83
| BEI - Total Tasks | F | 84
| BEI - Complete Tasks | F | 70 | 83%
| BEI - Incomplete Tasks | F | 14 | 17%
| BEI - Value Tasks (adjusted) | F | 0.83
| BEI - Complete Tasks (adjusted) | F | 70 | 83%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-11-12
| BEI - Value Milestones | F | 0.81
| BEI - Total Milestones | F | 26
| BEI - Complete Milestones | F | 21 | 81%
| BEI - Incomplete Milestones | F | 5 | 19%
| BEI - Value Milestones (adjusted) | F | 0.81
| BEI - Complete Milestones (adjusted) | F | 21 | 81%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-11-12
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-11-12
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-11-12
| BEI - Value Tasks | F | 0.83
| BEI - Total Tasks | F | 84
| BEI - Incomplete Tasks | F | 14 | 17%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 21 | 81%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0.81
| BEI - Total Milestones | F | 26
| BEI - Complete Milestones | F | 21 | 81%
| BEI - Incomplete Milestones | F | 5 | 19%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.83
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0.81
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-11-12
| Total Activities - DRM | F | 66
| Total Activities - DRM Graph | F | 66
| Status Date | F | 2026-11-12
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-11-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-11-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.88
| BEI - Value Task Finishes - Cumulative | F | 0.83
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | 0.83
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0.81
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.83
| BEI - Complete Tasks | F | 70 | 83%
| BEI - Incomplete Tasks | F | 14 | 17%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 3 | 16%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 9 | 64%
| Missing Logic | F | 2 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 2 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 15 | 79%
| Status Date | F | 2026-11-12
| High Float 10% | F | 3 | 16%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 15 | 79%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 11 | 61%
| Longest Path (Tasks & Milestones) | F | 15 | 83%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.36
| Critical Milestones (To-Go) | F | 4 | 80%
| Longest Path (Milestones) | F | 4 | 22%
| Normal Tasks | F | 84 | 60%
| Normal Tasks (To-Go) | F | 14 | 47%
| Critical Tasks (To-Go) | F | 11 | 79%
| Critical Tasks (In Progress) | F | 1 | 9%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 15 | 79%
| CP Logic Density™ | F | 2.07
| Time Now | F | 2026-11-12
| Forecast to be Finished | F | 84 | 100%
| Completed On Time | T | 9 | 11%
| Completed Late | T | 64 | 76%
| Not Completed | F | 14 | 17%
| Baseline Finish Compliance | T | 11%
| Forecast to be Started | F | 84 | 100%
| Started On Time | T | 9 | 11%
| Started Late | T | 65 | 77%
| Not Started | F | 10 | 12%
| Baseline Start Compliance | T | 14%
1 | Completed Activities | F | 70
HSD01 | Time Now | F | 2026-11-12
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 10 | 12%
HSD04 | Started Late | T | 65 | 77%
HSD05 | Forecast to be Finished but not Finished yet | T | 14 | 17%
HSD06 | Finished Late | T | 64 | 76%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-11-19
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 29 | 85%
SEM02 | BRI Current | F | 0.31
SEM03 | BRI Cumulative | F | 0.83
SEM04 | BPI Current | F | 0.31
SEM05 | BEI Current | F | 2.13
SEM06 | BEI Cumulative | T | 0.83
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 0
SEM07 | To Go - Planned Task Starts - Count | T | 10
SEM07 | To Go - BEI - Task Finishes - Count | T | FALSE
SEM07 | To Go - Baselined Task Starts - Count | T | 10
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 10
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 11
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 0
SEM07 | To Go - Planned Task Starts - Count | T | 10
SEM07 | To Go - BEI - Task Finishes - Count | T | FALSE
SEM07 | To Go - Baselined Task Starts - Count | T | 10
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 10
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 10
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | 0
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 11
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 11
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 10
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 11
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 0
SEM07 | To Go - Planned Task Starts - Count | T | 10
SEM07 | To Go - BEI - Task Finishes - Count | T | FALSE
SEM07 | To Go - Baselined Task Starts - Count | T | 10
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | TC-BEI | F | 0
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | 0.79
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Hard_File
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File (7/7/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-07-07
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0
| Wrong Status - Actual Finishes | F | 0
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 1 | 1%
| Estimated Duration | F | 68 | 80%
| Missing Logic | F | 7 | 6%
| Missing Predecessors | F | 1 | 1%
| Missing Successors | F | 6 | 5%
| Open Start | F | 0
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-07-07
| High Float 44d | F | 2 | 2%
| Zero Days Float | F | 78 | 71%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 1 | 1%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 20 | 18%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 110 | 100%
| Milestones (To-Go) | F | 25 | 23%
| Normal Tasks (To-Go) | F | 85 | 77%
| Normal Tasks (To-Go, In Progress) | F | 0 | 0%
| Critical Path (Tasks & Milestones) | F | 34 | 31%
| Critical Path (Milestones) | F | 7 | 21%
| Critical Path (Normal Tasks) | F | 27 | 79%
| Critical Path (Normal In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 78 | 71%
| Near-Critical (<10 Days Float) | F | 90 | 82%
| CP Logic Density™ | F | 2.21
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | 0
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | 2026-07-07
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-07-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2026-08-20
| Margin - Margin Task Name #3 | F | 2026-08-26
| Margin - Margin Task Name #4 | F | 2026-08-18
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-07-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 1 | 100%
| Margin - Margin Task Name #3 | F | 0
| Margin - Margin Task Name #4 | F | 1 | 100%
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-07-07
| Total Activities | F | 141
| Milestones | F | 25 | 18%
| Normal Tasks | F | 85 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 0 | 0%
| Completed Milestones | F | 0 | 0%
| Completed Tasks | F | 0 | 0%
| Total Activities (To-Go) - % of Total | F | 141 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 110 | 78%
| Milestones (To-Go) | F | 25 | 18%
| Normal Tasks (To-Go) | F | 85 | 60%
| Summaries (To-Go) | F | 31 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 34 | 79%
| Longest Path (Normal Tasks) | F | 27 | 63%
| Longest Path (Milestones) | F | 7 | 16%
| Critical Milestones (To-Go) | F | 7 | 21%
| Critical Normal Tasks (To-Go) | F | 27 | 79%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 85
| Scheduled to Start | F | 85
| Actual Starts | F | 0
| Baselined to Finish | F | 85
| Scheduled to Finish | F | 85
| Actual Finishes | F | 0
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | 85
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | 85
| Duration Ratio Metric (DRM) | F | 0
| DRM Graph | F | 0
| Baselined to Start | F | 85
| Scheduled to Start | F | 85
| Baselined to Finish | F | 85
| Scheduled to Finish | F | 85
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 110 | 78%
| Critical Path To-Go | F | 34 | 31%
| Status Date | F | 2026-07-07
| Total Activities | F | 141
| Milestones | F | 25 | 18%
| Normal Tasks | F | 85 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 0 | 0%
| Completed Milestones | F | 0 | 0%
| Completed Tasks | F | 0 | 0%
| Total Activities (To-Go) - % of Total | F | 141 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 110 | 78%
| Milestones (To-Go) | F | 25 | 18%
| Normal Tasks (To-Go) | F | 85 | 60%
| Summaries (To-Go) | F | 31 | 22%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 34 | 79%
| Longest Path (Normal Tasks) | F | 27 | 63%
| Longest Path (Milestones) | F | 7 | 16%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-07-07
| Total Activities (To-Go) - % of Total | F | 141 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 110 | 78%
| Summary-to-Task Ratio (To-Go) | F | 1:03 | 0.36
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.29
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.26
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 34 | 31%
| Wrong Status (To-Go) | F | 0
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 110 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 110 | 78%
| Estimated Duration | F | 68 | 80%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 1 | 1%
| Avg. Original Duration | F | 2
| Avg. Remaining Duration | F | 2
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 2 | 2%
| Critical Activities (To-Go) | F | 27 | 32%
| Avg. Critical Original Duration | F | 1
| Avg. Critical Remaining Duration | F | 1
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 85 | 100%
| Total Constraints | F | 2 | 2%
| Start No Earlier Than | F | 1 | 1%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 1 | 1%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 1 | 1%
| Open Ends w/o Constraints | F | 6 | 5%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 108 | 98%
| No Constraints | F | 107 | 97%
| Logic Density™ | F | 2.07
| Logic Density™ - Predecessors | F | 1.04
| Logic Density™ - Successors | F | 1.04
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 109 | 99%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 109 | 99%
| All Activities w/Successors | F | 104 | 95%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 104 | 95%
| Missing Logic | F | 7 | 6%
| Missing Predecessors | F | 1 | 1%
| Missing Successors | F | 6 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.04
| All Activities w/Predecessors | F | 109 | 100%
| Total # Predecessors | F | 114
| Activities Missing Predecessors | F | 1 | 1%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.04
| All Activities w/Successors | F | 104 | 100%
| Activities Missing Successors | F | 6 | 5%
| Total # Successors | F | 114
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 1 | 1%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 1 | 1%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 0 | 0%
| Completed Ahead - Tasks & Milestones | F | 0
| Completed On-Schedule - Tasks & Milestones | F | 0
| Completed Delayed - Tasks & Milestones | F | 0
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 0
| Avg Finish Variance - Tasks & Milestones | F | 0
| Actually Finished - Tasks | F | 0 | 0%
| Completed Ahead - Tasks | F | 0
| Completed On-Schedule - Tasks | F | 0
| Completed Delayed - Tasks | F | 0
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 0 | 0%
| Actually Finished - Milestones | F | 0 | 0%
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 0 | 0%
| In-Progress Started Ahead - Tasks | F | 0
| In-Progress Started On-Schedule - Tasks | F | 0
| In-Progress Started Delayed - Tasks | F | 0
| In-Progress Delayed Finish - Tasks | F | 0
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | 0
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 110 | 100%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 110 | 100%
| Planned Delayed Start - Tasks & Milestones | F | 0 | 0%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 85 | 100%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 85 | 100%
| Planned Delayed Start - Tasks | F | 0 | 0%
| Planned Delayed Finish - Tasks | F | 0 | 0%
| Scheduled to Start - Milestones | F | 25 | 100%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 25 | 100%
| Planned Delayed Start - Milestones | F | 0 | 0%
| Planned Delayed Finish - Milestones | F | 0 | 0%
| Schedule Baseline Activities | F | 110 | 100%
| Scheduled/Baselined to Start | F | 110
| Scheduled/Baselined to Finish | F | 110
| Start/ed | F | 0
| Finish/ed | F | 0
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | 110 | 100%
| Scheduled to Start | F | 110 | 100%
| Scheduled to Finish | F | 110 | 100%
| Longest Path - Critical Activities and Milestones | F | 34 | 31%
| Critical Milestones (To-Go) | F | 7 | 28%
| Critical Tasks (To-Go) | F | 27 | 32%
| Critical Tasks (In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.26
| High Float 10% | F | 20 | 18%
| High Float 44d | F | 2 | 2%
| Zero Days Float | F | 78 | 71%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 34 | 31%
| Critical Milestones (To-Go) | F | 7 | 28%
| Critical Tasks (To-Go) | F | 27 | 32%
| Critical Tasks (In Progress) | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.29
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.26
| Logic Density™ | F | 2.07
| CP Logic Density™ | F | 2.21
| Critical w/Missing Logic | F | 1 | 6%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 78 | 71%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 85
| Scheduled to Start | F | 85
| Actual Starts | F | 0
| Baselined to Finish | F | 85
| Scheduled to Finish | F | 85
| Actual Finishes | F | 0
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | 85
| Scheduled to Start | F | 85
| Actual Starts | F | 0
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | 85
| Scheduled to Finish | F | 85
| Actual Finishes | F | 0
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | 0 | 0%
| Scheduled to Start - To Time Now | F | 0 | 0%
| Started | F | 0
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | 0 | 0%
| Scheduled to Finish - To Time Now | F | 0 | 0%
| Finished | F | 0
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | 85
| Baselined to Start - Check | F | 85
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | 85
| Baselined to Finish - Check | F | 85
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | 85
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | 85
| Baselined to Start | F | 0
| Scheduled to Start | F | 0
| Started - Scheduled | F | 0
| Started - Baseline Comparison | F | 0
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 0
| Scheduled to Finish | F | 0
| Finished | F | 0
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-07-07
| Started (incl. Future Baseline Starts) - Scheduled | F | 0 | 0%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 0 | 0%
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 0 | 0%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 0 | 0%
| Finished Late | F | N/A
| Completed Ahead | F | 0
| Completed Delayed | F | 0
| Completed On-Schedule | F | 0
| Accelerated | F | 0
| Days Variance | F | 0
| Days Early | F | 0
| Days Late | F | 0
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 0 | 0%
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | 0 | 0%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | 0
| Missed Durations & Late Actual Finish | F | 0
| Completed Ahead | F | 0
| Completed Delayed | F | 0
| Completed On-Schedule | F | 0
| Accelerated | F | 0
| Days Variance | F | 0
| Days Early | F | 0
| Days Late | F | 0
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 0 | 0%
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | 0 | 0%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | 0
| Missed Durations & Late Actual Finish | F | 0
| Baselined Tasks | F | 85
| Baselined to Start - TOTAL | F | 85
| Complete Task Starts - Cumulative | F | 0
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 85
| Complete Task Finishes - Cumulative (in work) | F | 0
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | 0
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | 0
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-07-07
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | 0
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-07-07
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-07-07
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-07-07
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | 0
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-07-07
| Total Activities - DRM | F | 0
| Total Activities - DRM Graph | F | 0
| Status Date | F | 2026-07-07
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-07-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 1
| Margin - Margin Task Name #3 | F | 0
| Margin - Margin Task Name #4 | F | 1
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-07-07
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2026-08-20
| Margin - Margin Task Name #3 | F | 2026-08-26
| Margin - Margin Task Name #4 | F | 2026-08-18
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 1 | 1%
| Estimated Duration | F | 68 | 80%
| Missing Logic | F | 7 | 6%
| Missing Predecessors | F | 1 | 1%
| Missing Successors | F | 6 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-07-07
| High Float 10% | F | 20 | 18%
| High Float 44d | F | 2 | 2%
| Zero Days Float | F | 78 | 71%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 1 | 1%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 27 | 63%
| Longest Path (Tasks & Milestones) | F | 34 | 79%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.26
| Critical Milestones (To-Go) | F | 7 | 28%
| Longest Path (Milestones) | F | 7 | 16%
| Normal Tasks | F | 85 | 60%
| Normal Tasks (To-Go) | F | 85 | 60%
| Critical Tasks (To-Go) | F | 27 | 32%
| Critical Tasks (In Progress) | F | 0 | 0%
| Zero Days Float | F | 78 | 71%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.21
| Time Now | F | 2026-07-07
| Forecast to be Finished | F | 0 | 0%
| Completed On Time | F | 0
| Completed Late | F | 0
| Not Completed | F | 0
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | 0 | 0%
| Started On Time | F | 0
| Started Late | F | 0
| Not Started | F | 0
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | 2026-07-07
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | 0 | 0%
HSD04 | Started Late | F | 0
HSD05 | Forecast to be Finished but not Finished yet | F | 0 | 0%
HSD06 | Finished Late | F | 0
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-11-05
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 85
SEM07 | To Go - BEI - Task Finishes - Count | T | 85
SEM07 | To Go - Baselined Task Starts - Count | T | 85
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 85
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 85
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 85
SEM07 | To Go - BEI - Task Finishes - Count | T | 85
SEM07 | To Go - Baselined Task Starts - Count | T | 85
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 85
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 85
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 85
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 85
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 85
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 85
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 85
SEM07 | To Go - BEI - Task Finishes - Count | T | 85
SEM07 | To Go - Baselined Task Starts - Count | T | 85
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | TC-BEI | F | 1
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -1
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Hard_File_updated
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated (8/11/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-08-11
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 1 | 1%
| Estimated Duration | F | 65 | 82%
| Missing Logic | F | 8 | 8%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 7 | 7%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-08-11
| High Float 44d | F | 6 | 6%
| Zero Days Float | F | 74 | 72%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 17 | 17%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 103 | 94%
| Milestones (To-Go) | F | 24 | 23%
| Normal Tasks (To-Go) | F | 79 | 77%
| Normal Tasks (To-Go, In Progress) | F | 1 | 1%
| Critical Path (Tasks & Milestones) | F | 33 | 32%
| Critical Path (Milestones) | F | 6 | 18%
| Critical Path (Normal Tasks) | F | 27 | 82%
| Critical Path (Normal In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:05
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 74 | 72%
| Near-Critical (<10 Days Float) | F | 81 | 79%
| CP Logic Density™ | F | 2.12
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.27
| BEI - Total Tasks | F | 11
| BEI - Complete Tasks | F | 3 | 27%
| BEI - Incomplete Tasks | F | 8 | 73%
| Status Date | F | 2026-08-11
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-11
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2026-08-20
| Margin - Margin Task Name #3 | F | 2026-08-26
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-11
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 1 | 100%
| Margin - Margin Task Name #3 | F | 0
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-11
| Total Activities | F | 141
| Milestones | F | 25 | 18%
| Normal Tasks | F | 85 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 7 | 6%
| Completed Milestones | F | 1 | 4%
| Completed Tasks | F | 6 | 7%
| Total Activities (To-Go) - % of Total | F | 134 | 95%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 103 | 77%
| Milestones (To-Go) | F | 24 | 18%
| Normal Tasks (To-Go) | F | 79 | 59%
| Summaries (To-Go) | F | 31 | 23%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 33 | 83%
| Longest Path (Normal Tasks) | F | 27 | 68%
| Longest Path (Milestones) | F | 6 | 15%
| Critical Milestones (To-Go) | F | 6 | 18%
| Critical Normal Tasks (To-Go) | F | 27 | 82%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 85
| Scheduled to Start | F | 85
| Actual Starts | F | 7
| Baselined to Finish | F | 85
| Scheduled to Finish | F | 85
| Actual Finishes | F | 6
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.33
| BEI - Value Task Finishes - Cumulative | F | 0.27
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.11
| FEI - Value Task Finish - Cumulative | F | 1.11
| Current Baseline to Start & Started (BL Plan) | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 78
| Current Baseline to Finish & Finished (BL Plan) | F | 6
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 79
| Duration Ratio Metric (DRM) | F | 6
| DRM Graph | F | 6
| Baselined to Start | F | 79
| Scheduled to Start | F | 79
| Baselined to Finish | F | 79
| Scheduled to Finish | F | 79
| BEI - Value Activities | F | 0.29
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 103 | 77%
| Critical Path To-Go | F | 33 | 32%
| Status Date | F | 2026-08-11
| Total Activities | F | 141
| Milestones | F | 25 | 18%
| Normal Tasks | F | 85 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 7 | 6%
| Completed Milestones | F | 1 | 4%
| Completed Tasks | F | 6 | 7%
| Total Activities (To-Go) - % of Total | F | 134 | 95%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 103 | 77%
| Milestones (To-Go) | F | 24 | 18%
| Normal Tasks (To-Go) | F | 79 | 59%
| Summaries (To-Go) | F | 31 | 23%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 33 | 83%
| Longest Path (Normal Tasks) | F | 27 | 68%
| Longest Path (Milestones) | F | 6 | 15%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-08-11
| Total Activities (To-Go) - % of Total | F | 134 | 95%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 103 | 77%
| Summary-to-Task Ratio (To-Go) | F | 1:03 | 0.39
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.3
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:05 | 0.22
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 33 | 32%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 103 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 103 | 77%
| Estimated Duration | F | 65 | 82%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 1 | 1%
| Avg. Original Duration | F | 1
| Avg. Remaining Duration | F | 1
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 1 | 1%
| Critical Activities (To-Go) | F | 27 | 34%
| Avg. Critical Original Duration | F | 1
| Avg. Critical Remaining Duration | F | 1
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 79 | 93%
| Total Constraints | F | 3 | 3%
| Start No Earlier Than | F | 2 | 2%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 1 | 1%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 1 | 1%
| Open Ends w/o Constraints | F | 7 | 6%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 100 | 97%
| No Constraints | F | 99 | 96%
| Logic Density™ | F | 2.08
| Logic Density™ - Predecessors | F | 1.05
| Logic Density™ - Successors | F | 1.03
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 102 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 102 | 99%
| All Activities w/Successors | F | 96 | 93%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 96 | 93%
| Missing Logic | F | 8 | 8%
| Missing Predecessors | F | 1 | 1%
| Missing Successors | F | 7 | 7%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.06
| All Activities w/Predecessors | F | 102 | 100%
| Total # Predecessors | F | 108
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.03
| All Activities w/Successors | F | 96 | 100%
| Activities Missing Successors | F | 7 | 7%
| Total # Successors | F | 106
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 1 | 1%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 7 | 6%
| Completed Ahead - Tasks & Milestones | F | 3 | 43%
| Completed On-Schedule - Tasks & Milestones | F | 3 | 43%
| Completed Delayed - Tasks & Milestones | F | 1 | 14%
| Avg Days Finished Early - Tasks & Milestones | F | 21
| Avg Days Finished Late - Tasks & Milestones | F | 5
| Avg Finish Variance - Tasks & Milestones | F | -8
| Actually Finished - Tasks | F | 6 | 7%
| Completed Ahead - Tasks | F | 3 | 50%
| Completed On-Schedule - Tasks | F | 2 | 33%
| Completed Delayed - Tasks | F | 1 | 17%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 2 | 2%
| Actually Finished - Milestones | F | 1 | 4%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 1 | 100%
| Completed Delayed - Milestones | F | 0 | 0%
| Actually Started - Tasks | F | 1 | 1%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 1 | 100%
| In-Progress Started Delayed - Tasks | F | 0 | 0%
| In-Progress Delayed Finish - Tasks | F | 1 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 0
| Avg Start Variance | F | 0
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 102 | 93%
| Planned Ahead Start - Tasks & Milestones | F | 3 | 3%
| Planned On Schedule Start - Tasks & Milestones | F | 84 | 82%
| Planned Delayed Start - Tasks & Milestones | F | 15 | 15%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 78 | 92%
| Planned Ahead Start - Tasks | F | 2 | 3%
| Planned On Schedule Start - Tasks | F | 66 | 85%
| Planned Delayed Start - Tasks | F | 10 | 13%
| Planned Delayed Finish - Tasks | F | 10 | 13%
| Scheduled to Start - Milestones | F | 24 | 96%
| Planned Ahead Start - Milestones | F | 1 | 4%
| Planned On Schedule Start - Milestones | F | 18 | 75%
| Planned Delayed Start - Milestones | F | 5 | 21%
| Planned Delayed Finish - Milestones | F | 5 | 21%
| Schedule Baseline Activities | F | 110 | 100%
| Scheduled/Baselined to Start | F | 103
| Scheduled/Baselined to Finish | F | 103
| Start/ed | F | 8
| Finish/ed | F | 7
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | 0 | 0%
| SPI(t) | F | 0.8
| Scheduled Activities | F | 110 | 100%
| Scheduled to Start | F | 103 | 94%
| Scheduled to Finish | F | 103 | 94%
| Longest Path - Critical Activities and Milestones | F | 33 | 32%
| Critical Milestones (To-Go) | F | 6 | 25%
| Critical Tasks (To-Go) | F | 27 | 34%
| Critical Tasks (In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:05 | 0.22
| High Float 10% | F | 17 | 17%
| High Float 44d | F | 6 | 6%
| Zero Days Float | F | 74 | 72%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 33 | 32%
| Critical Milestones (To-Go) | F | 6 | 25%
| Critical Tasks (To-Go) | F | 27 | 34%
| Critical Tasks (In Progress) | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.3
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:05 | 0.22
| Logic Density™ | F | 2.05
| CP Logic Density™ | F | 2.12
| Critical w/Missing Logic | F | 1 | 8%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 74 | 72%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 85
| Scheduled to Start | F | 85
| Actual Starts | F | 7
| Baselined to Finish | F | 85
| Scheduled to Finish | F | 85
| Actual Finishes | F | 6
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 85
| Scheduled to Start | F | 85
| Actual Starts | F | 7
| Current Baselined to Start & Started | F | 7
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 85
| Scheduled to Finish | F | 85
| Actual Finishes | F | 6
| Current Baselined to Finish & Finished | F | 6
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 12 | 14%
| Scheduled to Start - To Time Now | F | 12 | 14%
| Started | F | 4
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | 0.33
| Baselined to Finish - To Time Now | F | 11 | 13%
| Scheduled to Finish - To Time Now | F | 11 | 13%
| Finished | F | 3
| Finished Late | F | 1
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.27
| Started - Future | F | 3
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.33
| BEI - Value Task Finishes - Cumulative | F | 0.27
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.11
| FEI - Value Task Finish - Cumulative | F | 1.11
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 7
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 78
| Baselined to Start - Check | F | 85
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 6
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 79
| Baselined to Finish - Check | F | 85
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 78
| Current Baseline to Finish & Finished (BL Plan) | F | 6
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 79
| Baselined to Start | F | 12
| Scheduled to Start | F | 12 | 100%
| Started - Scheduled | F | 4 | 33%
| Started - Baseline Comparison | F | 4 | 33%
| BEI - Value Task Starts | F | 0.33
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 11
| Scheduled to Finish | F | 11
| Finished | F | 3
| BEI - Value Task Finishes | F | 0.27
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-08-11
| Started (incl. Future Baseline Starts) - Scheduled | F | 7 | 8%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 7 | 8%
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 6 | 7%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 6 | 7%
| Finished Late | F | 1
| Completed Ahead | F | 3 | 50%
| Completed Delayed | F | 1 | 17%
| Completed On-Schedule | F | 2 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | -57 | -954%
| Days Early | F | 63 | 1044%
| Days Late | F | 5 | 90%
| Avg Days Early | F | 21
| Avg Days Late | F | 5
| Avg Variance | F | -10
| Actually Finished | F | 6 | 5%
| Took Longer than Planned | F | 2 | 29%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 6 | 7%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 3 | 27%
| Missed Durations | F | 2 | 33%
| Missed Durations & Late Actual Finish | F | 1 | 17%
| Completed Ahead | F | 3 | 50%
| Completed Delayed | F | 1 | 17%
| Completed On-Schedule | F | 2 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | -57 | -954%
| Days Early | F | 63 | 1044%
| Days Late | F | 5 | 90%
| Avg Days Early | F | 21
| Avg Days Late | F | 5
| Avg Variance | F | -10
| Actually Finished | F | 6 | 5%
| Took Longer than Planned | F | 2 | 29%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 6 | 7%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 3 | 27%
| Missed Durations | F | 2 | 33%
| Missed Durations & Late Actual Finish | F | 1 | 17%
| Baselined Tasks | F | 85
| Baselined to Start - TOTAL | F | 85
| Complete Task Starts - Cumulative | F | 4 | 33%
| Incomplete Task Starts - Cumulative (in work) | F | 8 | 67%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 85
| Complete Task Finishes - Cumulative (in work) | F | 3 | 27%
| Incomplete Task Finishes - Cumulative | F | 8 | 27%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.27
| BEI - Total Tasks | F | 11
| BEI - Complete Tasks | F | 3 | 27%
| BEI - Incomplete Tasks | F | 8 | 73%
| BEI - Value Tasks (adjusted) | F | 0.55
| BEI - Complete Tasks (adjusted) | F | 6 | 55%
| BEI - Complete Future Tasks (adjusted) | F | 3
| Status Date | F | 2026-08-11
| BEI - Value Milestones | F | 0.33
| BEI - Total Milestones | F | 3
| BEI - Complete Milestones | F | 1 | 33%
| BEI - Incomplete Milestones | F | 2 | 67%
| BEI - Value Milestones (adjusted) | F | 0.33
| BEI - Complete Milestones (adjusted) | F | 1 | 33%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-11
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | 3
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | 3
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-08-11
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-11
| BEI - Value Tasks | F | 0.27
| BEI - Total Tasks | F | 11
| BEI - Incomplete Tasks | F | 8 | 73%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 33%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0.33
| BEI - Total Milestones | F | 3
| BEI - Complete Milestones | F | 1 | 33%
| BEI - Incomplete Milestones | F | 2 | 67%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.55
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0.33
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-11
| Total Activities - DRM | F | 6
| Total Activities - DRM Graph | F | 6
| Status Date | F | 2026-08-11
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-11
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 1
| Margin - Margin Task Name #3 | F | 0
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-11
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2026-08-20
| Margin - Margin Task Name #3 | F | 2026-08-26
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.33
| BEI - Value Task Finishes - Cumulative | F | 0.27
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.11
| FEI - Value Task Finish - Cumulative | F | 1.11
| BEI - Value Tasks | F | 0.27
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0.33
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.27
| BEI - Complete Tasks | F | 3 | 27%
| BEI - Incomplete Tasks | F | 8 | 73%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 1 | 1%
| Estimated Duration | F | 65 | 82%
| Missing Logic | F | 8 | 8%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 7 | 7%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-08-11
| High Float 10% | F | 17 | 17%
| High Float 44d | F | 6 | 6%
| Zero Days Float | F | 74 | 72%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 27 | 68%
| Longest Path (Tasks & Milestones) | F | 33 | 83%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:05 | 0.22
| Critical Milestones (To-Go) | F | 6 | 25%
| Longest Path (Milestones) | F | 6 | 15%
| Normal Tasks | F | 85 | 60%
| Normal Tasks (To-Go) | F | 79 | 59%
| Critical Tasks (To-Go) | F | 27 | 34%
| Critical Tasks (In Progress) | F | 0 | 0%
| Zero Days Float | F | 74 | 72%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.12
| Time Now | F | 2026-08-11
| Forecast to be Finished | F | 11 | 13%
| Completed On Time | T | 2 | 18%
| Completed Late | F | 1 | 9%
| Not Completed | F | 8 | 73%
| Baseline Finish Compliance | T | 18%
| Forecast to be Started | F | 12 | 14%
| Started On Time | F | 4 | 33%
| Started Late | F | 0 | 0%
| Not Started | F | 8 | 67%
| Baseline Start Compliance | F | 33%
1 | Completed Activities | F | 6
HSD01 | Time Now | F | 2026-08-11
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 8 | 9%
HSD04 | Started Late | F | 0 | 0%
HSD05 | Forecast to be Finished but not Finished yet | T | 8 | 9%
HSD06 | Finished Late | F | 1 | 9%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-11-05
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 0 | 0%
SEM02 | BRI Current | T | 0.11
SEM03 | BRI Cumulative | F | 0.27
SEM04 | BPI Current | T | 0.11
SEM05 | BEI Current | T | 0.11
SEM06 | BEI Cumulative | T | 0.27
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.11
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.11
SEM07 | To Go - Planned Task Starts - Count | T | 78
SEM07 | To Go - BEI - Task Finishes - Count | T | 79
SEM07 | To Go - Baselined Task Starts - Count | T | 78
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.11
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 8
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 70
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 8
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 71
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.11
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.11
SEM07 | To Go - Planned Task Starts - Count | T | 78
SEM07 | To Go - BEI - Task Finishes - Count | T | 79
SEM07 | To Go - Baselined Task Starts - Count | T | 78
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.11
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 78
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 8
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 70
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 79
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 8
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 71
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 8
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 70
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 8
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 71
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.11
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.11
SEM07 | To Go - Planned Task Starts - Count | T | 78
SEM07 | To Go - BEI - Task Finishes - Count | T | 79
SEM07 | To Go - Baselined Task Starts - Count | T | 78
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.11
SEM07 | TC-BEI | T | 1.11
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.67
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Hard_File_updated_with_logic_r
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated_with_logic_reestablished (8/11/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-08-11
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 1 | 1%
| Estimated Duration | F | 65 | 82%
| Missing Logic | F | 7 | 7%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 7 | 7%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 76 | 74%
| Status Date | F | 2026-08-11
| High Float 44d | F | 9 | 9%
| Zero Days Float | F | 8 | 8%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 1 | 1%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 1 | 1%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 16 | 16%
| Negative Float | F | 76 | 74%
| Tasks & Milestones (To Go) | F | 103 | 94%
| Milestones (To-Go) | F | 24 | 23%
| Normal Tasks (To-Go) | F | 79 | 77%
| Normal Tasks (To-Go, In Progress) | F | 1 | 1%
| Critical Path (Tasks & Milestones) | F | 84 | 82%
| Critical Path (Milestones) | F | 17 | 20%
| Critical Path (Normal Tasks) | F | 67 | 80%
| Critical Path (Normal In Progress) | F | 1 | 1%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04
| Negative Float | F | 76 | 74%
| Zero Days Float | F | 8 | 8%
| Near-Critical (<10 Days Float) | F | 87 | 84%
| CP Logic Density™ | F | 2.17
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.27
| BEI - Total Tasks | F | 11
| BEI - Complete Tasks | F | 3 | 27%
| BEI - Incomplete Tasks | F | 8 | 73%
| Status Date | F | 2026-08-11
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-11
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2026-08-26
| Margin - Margin Task Name #3 | F | 2026-09-02
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-11
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 1 | 100%
| Margin - Margin Task Name #3 | F | 0
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-11
| Total Activities | F | 141
| Milestones | F | 25 | 18%
| Normal Tasks | F | 85 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 7 | 6%
| Completed Milestones | F | 1 | 4%
| Completed Tasks | F | 6 | 7%
| Total Activities (To-Go) - % of Total | F | 134 | 95%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 103 | 77%
| Milestones (To-Go) | F | 24 | 18%
| Normal Tasks (To-Go) | F | 79 | 59%
| Summaries (To-Go) | F | 31 | 23%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 84 | 78%
| Longest Path (Normal Tasks) | F | 67 | 62%
| Longest Path (Milestones) | F | 17 | 16%
| Critical Milestones (To-Go) | F | 17 | 20%
| Critical Normal Tasks (To-Go) | F | 67 | 80%
| Riding Data Date | F | 1 | 1%
| Baselined to Start | F | 85
| Scheduled to Start | F | 85
| Actual Starts | F | 7
| Baselined to Finish | F | 85
| Scheduled to Finish | F | 85
| Actual Finishes | F | 6
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.33
| BEI - Value Task Finishes - Cumulative | F | 0.27
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.11
| FEI - Value Task Finish - Cumulative | F | 1.11
| Current Baseline to Start & Started (BL Plan) | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 78
| Current Baseline to Finish & Finished (BL Plan) | F | 6
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 79
| Duration Ratio Metric (DRM) | F | 6
| DRM Graph | F | 6
| Baselined to Start | F | 79
| Scheduled to Start | F | 79
| Baselined to Finish | F | 79
| Scheduled to Finish | F | 79
| BEI - Value Activities | F | 0.29
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 103 | 77%
| Critical Path To-Go | F | 84 | 82%
| Status Date | F | 2026-08-11
| Total Activities | F | 141
| Milestones | F | 25 | 18%
| Normal Tasks | F | 85 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 7 | 6%
| Completed Milestones | F | 1 | 4%
| Completed Tasks | F | 6 | 7%
| Total Activities (To-Go) - % of Total | F | 134 | 95%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 103 | 77%
| Milestones (To-Go) | F | 24 | 18%
| Normal Tasks (To-Go) | F | 79 | 59%
| Summaries (To-Go) | F | 31 | 23%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 84 | 78%
| Longest Path (Normal Tasks) | F | 67 | 62%
| Longest Path (Milestones) | F | 17 | 16%
| Riding Data Date | F | 1 | 1%
| Status Date | F | 2026-08-11
| Total Activities (To-Go) - % of Total | F | 134 | 95%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 103 | 77%
| Summary-to-Task Ratio (To-Go) | F | 1:03 | 0.39
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.3
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 84 | 82%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 103 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 103 | 77%
| Estimated Duration | F | 65 | 82%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 1 | 1%
| Avg. Original Duration | F | 1
| Avg. Remaining Duration | F | 1
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 1 | 1%
| Critical Activities (To-Go) | F | 67 | 85%
| Avg. Critical Original Duration | F | 1
| Avg. Critical Remaining Duration | F | 1
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 1 | 1%
| Activities (To-Go) | F | 79 | 93%
| Total Constraints | F | 3 | 3%
| Start No Earlier Than | F | 2 | 2%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 1 | 1%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 1 | 1%
| Open Ends w/o Constraints | F | 6 | 6%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 100 | 97%
| No Constraints | F | 99 | 96%
| Logic Density™ | F | 2.1
| Logic Density™ - Predecessors | F | 1.06
| Logic Density™ - Successors | F | 1.04
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 102 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 103 | 100%
| All Activities w/Successors | F | 96 | 93%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 96 | 93%
| Missing Logic | F | 7 | 7%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 7 | 7%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.06
| All Activities w/Predecessors | F | 102 | 100%
| Total # Predecessors | F | 108
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 1%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.04
| All Activities w/Successors | F | 96 | 100%
| Activities Missing Successors | F | 7 | 7%
| Total # Successors | F | 107
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 1 | 1%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 1 | 1%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 7 | 6%
| Completed Ahead - Tasks & Milestones | F | 3 | 43%
| Completed On-Schedule - Tasks & Milestones | F | 3 | 43%
| Completed Delayed - Tasks & Milestones | F | 1 | 14%
| Avg Days Finished Early - Tasks & Milestones | F | 21
| Avg Days Finished Late - Tasks & Milestones | F | 5
| Avg Finish Variance - Tasks & Milestones | F | -8
| Actually Finished - Tasks | F | 6 | 7%
| Completed Ahead - Tasks | F | 3 | 50%
| Completed On-Schedule - Tasks | F | 2 | 33%
| Completed Delayed - Tasks | F | 1 | 17%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 2 | 2%
| Actually Finished - Milestones | F | 1 | 4%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 1 | 100%
| Completed Delayed - Milestones | F | 0 | 0%
| Actually Started - Tasks | F | 1 | 1%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 1 | 100%
| In-Progress Started Delayed - Tasks | F | 0 | 0%
| In-Progress Delayed Finish - Tasks | F | 1 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 0
| Avg Start Variance | F | 0
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 102 | 93%
| Planned Ahead Start - Tasks & Milestones | F | 3 | 3%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 99 | 97%
| Riding Data Date - Tasks & Milestones | F | 1 | 1%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 78 | 92%
| Planned Ahead Start - Tasks | F | 2 | 3%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 76 | 97%
| Planned Delayed Finish - Tasks | F | 76 | 97%
| Scheduled to Start - Milestones | F | 24 | 96%
| Planned Ahead Start - Milestones | F | 1 | 4%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 23 | 96%
| Planned Delayed Finish - Milestones | F | 23 | 96%
| Schedule Baseline Activities | F | 110 | 100%
| Scheduled/Baselined to Start | F | 103
| Scheduled/Baselined to Finish | F | 103
| Start/ed | F | 8
| Finish/ed | F | 7
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | 0 | 0%
| SPI(t) | F | 0.8
| Scheduled Activities | F | 110 | 100%
| Scheduled to Start | F | 103 | 94%
| Scheduled to Finish | F | 103 | 94%
| Longest Path - Critical Activities and Milestones | F | 84 | 82%
| Critical Milestones (To-Go) | F | 17 | 71%
| Critical Tasks (To-Go) | F | 67 | 85%
| Critical Tasks (In Progress) | F | 1 | 1%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| High Float 10% | F | 16 | 16%
| High Float 44d | F | 9 | 9%
| Zero Days Float | F | 8 | 8%
| Negative Float | F | 76 | 74%
| Longest Path - Critical Activities and Milestones | F | 84 | 82%
| Critical Milestones (To-Go) | F | 17 | 71%
| Critical Tasks (To-Go) | F | 67 | 85%
| Critical Tasks (In Progress) | F | 1 | 1%
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.3
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| Logic Density™ | F | 2.07
| CP Logic Density™ | F | 2.17
| Critical w/Missing Logic | F | 1 | 7%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 8 | 8%
| Negative Float | F | 76 | 74%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 85
| Scheduled to Start | F | 85
| Actual Starts | F | 7
| Baselined to Finish | F | 85
| Scheduled to Finish | F | 85
| Actual Finishes | F | 6
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 85
| Scheduled to Start | F | 85
| Actual Starts | F | 7
| Current Baselined to Start & Started | F | 7
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 85
| Scheduled to Finish | F | 85
| Actual Finishes | F | 6
| Current Baselined to Finish & Finished | F | 6
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 12 | 14%
| Scheduled to Start - To Time Now | F | 12 | 14%
| Started | F | 4
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | 0.33
| Baselined to Finish - To Time Now | F | 11 | 13%
| Scheduled to Finish - To Time Now | F | 11 | 13%
| Finished | F | 3
| Finished Late | F | 1
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.27
| Started - Future | F | 3
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.33
| BEI - Value Task Finishes - Cumulative | F | 0.27
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.11
| FEI - Value Task Finish - Cumulative | F | 1.11
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 7
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 78
| Baselined to Start - Check | F | 85
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 6
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 79
| Baselined to Finish - Check | F | 85
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 78
| Current Baseline to Finish & Finished (BL Plan) | F | 6
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 79
| Baselined to Start | F | 12
| Scheduled to Start | F | 12 | 100%
| Started - Scheduled | F | 4 | 33%
| Started - Baseline Comparison | F | 4 | 33%
| BEI - Value Task Starts | F | 0.33
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 11
| Scheduled to Finish | F | 11
| Finished | F | 3
| BEI - Value Task Finishes | F | 0.27
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-08-11
| Started (incl. Future Baseline Starts) - Scheduled | F | 7 | 8%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 7 | 8%
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 6 | 7%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 6 | 7%
| Finished Late | F | 1
| Completed Ahead | F | 3 | 50%
| Completed Delayed | F | 1 | 17%
| Completed On-Schedule | F | 2 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | -57 | -954%
| Days Early | F | 63 | 1044%
| Days Late | F | 5 | 90%
| Avg Days Early | F | 21
| Avg Days Late | F | 5
| Avg Variance | F | -10
| Actually Finished | F | 6 | 5%
| Took Longer than Planned | F | 2 | 29%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 6 | 7%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 3 | 27%
| Missed Durations | F | 2 | 33%
| Missed Durations & Late Actual Finish | F | 1 | 17%
| Completed Ahead | F | 3 | 50%
| Completed Delayed | F | 1 | 17%
| Completed On-Schedule | F | 2 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | -57 | -954%
| Days Early | F | 63 | 1044%
| Days Late | F | 5 | 90%
| Avg Days Early | F | 21
| Avg Days Late | F | 5
| Avg Variance | F | -10
| Actually Finished | F | 6 | 5%
| Took Longer than Planned | F | 2 | 29%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 6 | 7%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 3 | 27%
| Missed Durations | F | 2 | 33%
| Missed Durations & Late Actual Finish | F | 1 | 17%
| Baselined Tasks | F | 85
| Baselined to Start - TOTAL | F | 85
| Complete Task Starts - Cumulative | F | 4 | 33%
| Incomplete Task Starts - Cumulative (in work) | F | 8 | 67%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 85
| Complete Task Finishes - Cumulative (in work) | F | 3 | 27%
| Incomplete Task Finishes - Cumulative | F | 8 | 27%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.27
| BEI - Total Tasks | F | 11
| BEI - Complete Tasks | F | 3 | 27%
| BEI - Incomplete Tasks | F | 8 | 73%
| BEI - Value Tasks (adjusted) | F | 0.55
| BEI - Complete Tasks (adjusted) | F | 6 | 55%
| BEI - Complete Future Tasks (adjusted) | F | 3
| Status Date | F | 2026-08-11
| BEI - Value Milestones | F | 0.33
| BEI - Total Milestones | F | 3
| BEI - Complete Milestones | F | 1 | 33%
| BEI - Incomplete Milestones | F | 2 | 67%
| BEI - Value Milestones (adjusted) | F | 0.33
| BEI - Complete Milestones (adjusted) | F | 1 | 33%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-11
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | 3
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | 3
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-08-11
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-11
| BEI - Value Tasks | F | 0.27
| BEI - Total Tasks | F | 11
| BEI - Incomplete Tasks | F | 8 | 73%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 33%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0.33
| BEI - Total Milestones | F | 3
| BEI - Complete Milestones | F | 1 | 33%
| BEI - Incomplete Milestones | F | 2 | 67%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.55
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0.33
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-11
| Total Activities - DRM | F | 6
| Total Activities - DRM Graph | F | 6
| Status Date | F | 2026-08-11
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-11
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 1
| Margin - Margin Task Name #3 | F | 0
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-11
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | 2026-08-26
| Margin - Margin Task Name #3 | F | 2026-09-02
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.33
| BEI - Value Task Finishes - Cumulative | F | 0.27
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.11
| FEI - Value Task Finish - Cumulative | F | 1.11
| BEI - Value Tasks | F | 0.27
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0.33
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.27
| BEI - Complete Tasks | F | 3 | 27%
| BEI - Incomplete Tasks | F | 8 | 73%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 1 | 1%
| Estimated Duration | F | 65 | 82%
| Missing Logic | F | 7 | 7%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 7 | 7%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 76 | 74%
| Status Date | F | 2026-08-11
| High Float 10% | F | 16 | 16%
| High Float 44d | F | 9 | 9%
| Zero Days Float | F | 8 | 8%
| Negative Float | F | 76 | 74%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 1 | 1%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 1 | 1%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 67 | 62%
| Longest Path (Tasks & Milestones) | F | 84 | 78%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| Critical Milestones (To-Go) | F | 17 | 71%
| Longest Path (Milestones) | F | 17 | 16%
| Normal Tasks | F | 85 | 60%
| Normal Tasks (To-Go) | F | 79 | 59%
| Critical Tasks (To-Go) | F | 67 | 85%
| Critical Tasks (In Progress) | F | 1 | 1%
| Zero Days Float | F | 8 | 8%
| Negative Float | F | 76 | 74%
| CP Logic Density™ | F | 2.17
| Time Now | F | 2026-08-11
| Forecast to be Finished | F | 11 | 13%
| Completed On Time | T | 2 | 18%
| Completed Late | F | 1 | 9%
| Not Completed | F | 8 | 73%
| Baseline Finish Compliance | T | 18%
| Forecast to be Started | F | 12 | 14%
| Started On Time | F | 4 | 33%
| Started Late | F | 0 | 0%
| Not Started | F | 8 | 67%
| Baseline Start Compliance | F | 33%
1 | Completed Activities | F | 6
HSD01 | Time Now | F | 2026-08-11
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 8 | 9%
HSD04 | Started Late | F | 0 | 0%
HSD05 | Forecast to be Finished but not Finished yet | T | 8 | 9%
HSD06 | Finished Late | F | 1 | 9%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-11-12
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 0 | 0%
SEM02 | BRI Current | T | 0.11
SEM03 | BRI Cumulative | F | 0.27
SEM04 | BPI Current | T | 0.11
SEM05 | BEI Current | T | 0.11
SEM06 | BEI Cumulative | T | 0.27
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.11
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.11
SEM07 | To Go - Planned Task Starts - Count | T | 78
SEM07 | To Go - BEI - Task Finishes - Count | T | 79
SEM07 | To Go - Baselined Task Starts - Count | T | 78
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.11
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 8
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 69
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 8
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 71
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.11
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.11
SEM07 | To Go - Planned Task Starts - Count | T | 78
SEM07 | To Go - BEI - Task Finishes - Count | T | 79
SEM07 | To Go - Baselined Task Starts - Count | T | 78
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.11
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 77
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 8
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 69
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 79
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 8
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 71
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 8
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 69
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 8
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 71
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.11
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.11
SEM07 | To Go - Planned Task Starts - Count | T | 78
SEM07 | To Go - BEI - Task Finishes - Count | T | 79
SEM07 | To Go - Baselined Task Starts - Count | T | 78
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.11
SEM07 | TC-BEI | T | 1.11
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.67
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Hard_File_updated2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated2 (9/10/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-09-10
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 42 | 55%
| Expected Finish But Still In-Progress | F | 0
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 47 | 81%
| Missing Logic | F | 6 | 8%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 6 | 8%
| Open Start | F | 0
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-09-10
| High Float 44d | F | 5 | 7%
| Zero Days Float | F | 25 | 33%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 22 | 29%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 76 | 69%
| Milestones (To-Go) | F | 18 | 24%
| Normal Tasks (To-Go) | F | 58 | 76%
| Normal Tasks (To-Go, In Progress) | F | 0 | 0%
| Critical Path (Tasks & Milestones) | F | 24 | 32%
| Critical Path (Milestones) | F | 5 | 21%
| Critical Path (Normal Tasks) | F | 19 | 79%
| Critical Path (Normal In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 25 | 33%
| Near-Critical (<10 Days Float) | F | 54 | 71%
| CP Logic Density™ | F | 2.13
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 44
| BEI - Complete Tasks | F | 26 | 59%
| BEI - Incomplete Tasks | F | 18 | 41%
| Status Date | F | 2026-09-10
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-09-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-09-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-09-10
| Total Activities | F | 141
| Milestones | F | 26 | 18%
| Normal Tasks | F | 84 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 34 | 31%
| Completed Milestones | F | 8 | 31%
| Completed Tasks | F | 26 | 31%
| Total Activities (To-Go) - % of Total | F | 102 | 72%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 76 | 75%
| Milestones (To-Go) | F | 18 | 18%
| Normal Tasks (To-Go) | F | 58 | 57%
| Summaries (To-Go) | F | 26 | 25%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 24 | 83%
| Longest Path (Normal Tasks) | F | 19 | 66%
| Longest Path (Milestones) | F | 5 | 17%
| Critical Milestones (To-Go) | F | 5 | 21%
| Critical Normal Tasks (To-Go) | F | 19 | 79%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 84
| Scheduled to Start | F | 84
| Actual Starts | F | 26
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Actual Finishes | F | 26
| Started Delayed (<=30 days) | F | 18 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 20 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.59
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.1
| FEI - Value Task Finish - Cumulative | F | 1.1
| Current Baseline to Start & Started (BL Plan) | F | 26
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 58
| Current Baseline to Finish & Finished (BL Plan) | F | 26
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 58
| Duration Ratio Metric (DRM) | F | 22
| DRM Graph | F | 22
| Baselined to Start | F | 58
| Scheduled to Start | F | 58
| Baselined to Finish | F | 58
| Scheduled to Finish | F | 58
| BEI - Value Activities | F | 0.6
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 76 | 75%
| Critical Path To-Go | F | 24 | 32%
| Status Date | F | 2026-09-10
| Total Activities | F | 141
| Milestones | F | 26 | 18%
| Normal Tasks | F | 84 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 34 | 31%
| Completed Milestones | F | 8 | 31%
| Completed Tasks | F | 26 | 31%
| Total Activities (To-Go) - % of Total | F | 102 | 72%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 76 | 75%
| Milestones (To-Go) | F | 18 | 18%
| Normal Tasks (To-Go) | F | 58 | 57%
| Summaries (To-Go) | F | 26 | 25%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 24 | 83%
| Longest Path (Normal Tasks) | F | 19 | 66%
| Longest Path (Milestones) | F | 5 | 17%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-09-10
| Total Activities (To-Go) - % of Total | F | 102 | 72%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 76 | 75%
| Summary-to-Task Ratio (To-Go) | F | 1:02 | 0.45
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.31
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.26
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 24 | 32%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 42 | 55%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 76 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 76 | 75%
| Estimated Duration | F | 47 | 81%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 1
| Avg. Remaining Duration | F | 1
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 19 | 33%
| Avg. Critical Original Duration | F | 2
| Avg. Critical Remaining Duration | F | 1
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 58 | 69%
| Total Constraints | F | 1 | 1%
| Start No Earlier Than | F | 1 | 1%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 1 | 1%
| Open Ends w/o Constraints | F | 5 | 7%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 75 | 99%
| No Constraints | F | 74 | 97%
| Logic Density™ | F | 2.07
| Logic Density™ - Predecessors | F | 1.08
| Logic Density™ - Successors | F | 0.99
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 76 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 76 | 100%
| All Activities w/Successors | F | 70 | 92%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 70 | 92%
| Missing Logic | F | 6 | 8%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 6 | 8%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.08
| All Activities w/Predecessors | F | 76 | 100%
| Total # Predecessors | F | 82
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 0.99
| All Activities w/Successors | F | 70 | 100%
| Activities Missing Successors | F | 6 | 8%
| Total # Successors | F | 75
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 34 | 31%
| Completed Ahead - Tasks & Milestones | F | 3 | 9%
| Completed On-Schedule - Tasks & Milestones | F | 5 | 15%
| Completed Delayed - Tasks & Milestones | F | 26 | 76%
| Avg Days Finished Early - Tasks & Milestones | F | 21
| Avg Days Finished Late - Tasks & Milestones | F | 7
| Avg Finish Variance - Tasks & Milestones | F | 3
| Actually Finished - Tasks | F | 26 | 31%
| Completed Ahead - Tasks | F | 3 | 12%
| Completed On-Schedule - Tasks | F | 3 | 12%
| Completed Delayed - Tasks | F | 20 | 77%
| Accelerated Durations Early/On-Schedule - Tasks | F | 1 | 1%
| Accelerated Durations Late - Tasks | F | 2 | 2%
| Extended Durations - Tasks | F | 5 | 6%
| Actually Finished - Milestones | F | 8 | 31%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 2 | 25%
| Completed Delayed - Milestones | F | 6 | 75%
| Actually Started - Tasks | F | 0 | 0%
| In-Progress Started Ahead - Tasks | F | 0
| In-Progress Started On-Schedule - Tasks | F | 0
| In-Progress Started Delayed - Tasks | F | 0
| In-Progress Delayed Finish - Tasks | F | 0
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | 0
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 76 | 69%
| Planned Ahead Start - Tasks & Milestones | F | 9 | 12%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 67 | 88%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 58 | 69%
| Planned Ahead Start - Tasks | F | 5 | 9%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 53 | 91%
| Planned Delayed Finish - Tasks | F | 52 | 90%
| Scheduled to Start - Milestones | F | 18 | 69%
| Planned Ahead Start - Milestones | F | 4 | 22%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 14 | 78%
| Planned Delayed Finish - Milestones | F | 14 | 78%
| Schedule Baseline Activities | F | 110 | 100%
| Scheduled/Baselined to Start | F | 76
| Scheduled/Baselined to Finish | F | 76
| Start/ed | F | 34
| Finish/ed | F | 34
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 0 | 0%
| Completed Delayed (>30 days) | F | 0 | 0%
| SPI(t) | F | 1.14
| Scheduled Activities | F | 110 | 100%
| Scheduled to Start | F | 76 | 69%
| Scheduled to Finish | F | 76 | 69%
| Longest Path - Critical Activities and Milestones | F | 24 | 32%
| Critical Milestones (To-Go) | F | 5 | 28%
| Critical Tasks (To-Go) | F | 19 | 33%
| Critical Tasks (In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.26
| High Float 10% | F | 22 | 29%
| High Float 44d | F | 5 | 7%
| Zero Days Float | F | 25 | 33%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 24 | 32%
| Critical Milestones (To-Go) | F | 5 | 28%
| Critical Tasks (To-Go) | F | 19 | 33%
| Critical Tasks (In Progress) | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.31
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.26
| Logic Density™ | F | 2.07
| CP Logic Density™ | F | 2.13
| Critical w/Missing Logic | F | 1 | 8%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 25 | 33%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 84
| Scheduled to Start | F | 84
| Actual Starts | F | 26
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Actual Finishes | F | 26
| Started Delayed (<=30 days) | F | 18 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 20 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 84
| Scheduled to Start | F | 84
| Actual Starts | F | 26
| Current Baselined to Start & Started | F | 26
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Actual Finishes | F | 26
| Current Baselined to Finish & Finished | F | 26
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 18 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 20 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 44 | 52%
| Scheduled to Start - To Time Now | F | 44 | 52%
| Started | F | 26
| Started Late | F | 18
| Started Delayed (<=30 days) | F | 18 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 0.59
| Baselined to Finish - To Time Now | F | 44 | 52%
| Scheduled to Finish - To Time Now | F | 44 | 52%
| Finished | F | 26
| Finished Late | F | 20
| Completed Delayed (<=30 days) | F | 20 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.59
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.59
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.1
| FEI - Value Task Finish - Cumulative | F | 1.1
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 26
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 58
| Baselined to Start - Check | F | 84
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 26
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 58
| Baselined to Finish - Check | F | 84
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 26
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 58
| Current Baseline to Finish & Finished (BL Plan) | F | 26
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 58
| Baselined to Start | F | 44
| Scheduled to Start | F | 44 | 100%
| Started - Scheduled | F | 26 | 59%
| Started - Baseline Comparison | F | 26 | 59%
| BEI - Value Task Starts | F | 0.59
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 44
| Scheduled to Finish | F | 44
| Finished | F | 26
| BEI - Value Task Finishes | F | 0.59
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-09-10
| Started (incl. Future Baseline Starts) - Scheduled | F | 26 | 31%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 26 | 31%
| Started Late (from Baseline) | F | 18
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 26 | 31%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 26 | 31%
| Finished Late | F | 20
| Completed Ahead | F | 3 | 12%
| Completed Delayed | F | 20 | 77%
| Completed On-Schedule | F | 3 | 12%
| Accelerated | F | 1 | 4%
| Days Variance | F | 73 | 280%
| Days Early | F | 63 | 241%
| Days Late | F | 136 | 521%
| Avg Days Early | F | 21
| Avg Days Late | F | 7
| Avg Variance | F | 3
| Actually Finished | F | 26 | 24%
| Took Longer than Planned | F | 10 | 29%
| Took Less Than Planned | F | 5 | 15%
| Completed (w/Baseline Duration) | F | 25 | 30%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 1 | 1%
| Baseline-to-Date Completed Tasks | F | 26 | 59%
| Missed Durations | F | 5 | 19%
| Missed Durations & Late Actual Finish | F | 4 | 15%
| Completed Ahead | F | 3 | 12%
| Completed Delayed | F | 20 | 77%
| Completed On-Schedule | F | 3 | 12%
| Accelerated | F | 1 | 4%
| Days Variance | F | 73 | 280%
| Days Early | F | 63 | 241%
| Days Late | F | 136 | 521%
| Avg Days Early | F | 21
| Avg Days Late | F | 7
| Avg Variance | F | 3
| Actually Finished | F | 26 | 24%
| Took Longer than Planned | F | 10 | 29%
| Took Less Than Planned | F | 5 | 15%
| Completed (w/Baseline Duration) | F | 25 | 30%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 1 | 1%
| Baseline-to-Date Completed Tasks | F | 26 | 59%
| Missed Durations | F | 5 | 19%
| Missed Durations & Late Actual Finish | F | 4 | 15%
| Baselined Tasks | F | 84
| Baselined to Start - TOTAL | F | 84
| Complete Task Starts - Cumulative | F | 26 | 59%
| Incomplete Task Starts - Cumulative (in work) | F | 18 | 41%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 84
| Complete Task Finishes - Cumulative (in work) | F | 26 | 59%
| Incomplete Task Finishes - Cumulative | F | 18 | 59%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 44
| BEI - Complete Tasks | F | 26 | 59%
| BEI - Incomplete Tasks | F | 18 | 41%
| BEI - Value Tasks (adjusted) | F | 0.59
| BEI - Complete Tasks (adjusted) | F | 26 | 59%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-09-10
| BEI - Value Milestones | F | 0.62
| BEI - Total Milestones | F | 13
| BEI - Complete Milestones | F | 8 | 62%
| BEI - Incomplete Milestones | F | 5 | 38%
| BEI - Value Milestones (adjusted) | F | 0.62
| BEI - Complete Milestones (adjusted) | F | 8 | 62%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-09-10
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-09-10
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-09-10
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 44
| BEI - Incomplete Tasks | F | 18 | 41%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 8 | 62%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0.62
| BEI - Total Milestones | F | 13
| BEI - Complete Milestones | F | 8 | 62%
| BEI - Incomplete Milestones | F | 5 | 38%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.59
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0.62
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-09-10
| Total Activities - DRM | F | 22
| Total Activities - DRM Graph | F | 22
| Status Date | F | 2026-09-10
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-09-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-09-10
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.59
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.1
| FEI - Value Task Finish - Cumulative | F | 1.1
| BEI - Value Tasks | F | 0.59
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0.62
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Complete Tasks | F | 26 | 59%
| BEI - Incomplete Tasks | F | 18 | 41%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 42 | 55%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 47 | 81%
| Missing Logic | F | 6 | 8%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 6 | 8%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-09-10
| High Float 10% | F | 22 | 29%
| High Float 44d | F | 5 | 7%
| Zero Days Float | F | 25 | 33%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 19 | 66%
| Longest Path (Tasks & Milestones) | F | 24 | 83%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.26
| Critical Milestones (To-Go) | F | 5 | 28%
| Longest Path (Milestones) | F | 5 | 17%
| Normal Tasks | F | 84 | 60%
| Normal Tasks (To-Go) | F | 58 | 57%
| Critical Tasks (To-Go) | F | 19 | 33%
| Critical Tasks (In Progress) | F | 0 | 0%
| Zero Days Float | F | 25 | 33%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.13
| Time Now | F | 2026-09-10
| Forecast to be Finished | F | 43 | 51%
| Completed On Time | F | 13 | 30%
| Completed Late | F | 26 | 60%
| Not Completed | F | 17 | 40%
| Baseline Finish Compliance | F | 30%
| Forecast to be Started | F | 44 | 52%
| Started On Time | F | 13 | 30%
| Started Late | F | 27 | 61%
| Not Started | F | 18 | 41%
| Baseline Start Compliance | F | 39%
1 | Completed Activities | F | 26
HSD01 | Time Now | F | 2026-09-10
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 18 | 21%
HSD04 | Started Late | F | 27 | 61%
HSD05 | Forecast to be Finished but not Finished yet | T | 17 | 20%
HSD06 | Finished Late | F | 26 | 60%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-11-05
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 3 | 15%
SEM02 | BRI Current | F | 0.52
SEM03 | BRI Cumulative | F | 0.59
SEM04 | BPI Current | F | 0.61
SEM05 | BEI Current | T | 0.61
SEM06 | BEI Cumulative | T | 0.59
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.08
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1.07
SEM07 | To Go - Planned Task Starts - Count | T | 43
SEM07 | To Go - BEI - Task Finishes - Count | T | 44
SEM07 | To Go - Baselined Task Starts - Count | T | 43
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.08
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 4
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 39
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 4
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 39
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.08
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1.07
SEM07 | To Go - Planned Task Starts - Count | T | 43
SEM07 | To Go - BEI - Task Finishes - Count | T | 44
SEM07 | To Go - Baselined Task Starts - Count | T | 43
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.08
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 43
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 4
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 39
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 43
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 4
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 39
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 4
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 39
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 4
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 39
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.08
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1.07
SEM07 | To Go - Planned Task Starts - Count | T | 43
SEM07 | To Go - BEI - Task Finishes - Count | T | 44
SEM07 | To Go - Baselined Task Starts - Count | T | 43
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.08
SEM07 | TC-BEI | F | 1.07
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.45
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Hard_File_updated3-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated3 2 (10/12/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-10-12
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 41 | 79%
| Missing Logic | F | 6 | 9%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 6 | 9%
| Open Start | F | 0
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 49 | 72%
| Status Date | F | 2026-10-12
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 4 | 6%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 11 | 16%
| Negative Float | F | 49 | 72%
| Tasks & Milestones (To Go) | F | 68 | 62%
| Milestones (To-Go) | F | 16 | 24%
| Normal Tasks (To-Go) | F | 52 | 76%
| Normal Tasks (To-Go, In Progress) | F | 0 | 0%
| Critical Path (Tasks & Milestones) | F | 49 | 72%
| Critical Path (Milestones) | F | 9 | 18%
| Critical Path (Normal Tasks) | F | 40 | 82%
| Critical Path (Normal In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04
| Negative Float | F | 49 | 72%
| Zero Days Float | F | 0 | 0%
| Near-Critical (<10 Days Float) | F | 56 | 82%
| CP Logic Density™ | F | 2.12
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.47
| BEI - Total Tasks | F | 68
| BEI - Complete Tasks | F | 32 | 47%
| BEI - Incomplete Tasks | F | 36 | 53%
| Status Date | F | 2026-10-12
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-10-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-10-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-10-12
| Total Activities | F | 141
| Milestones | F | 26 | 18%
| Normal Tasks | F | 84 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 42 | 38%
| Completed Milestones | F | 10 | 38%
| Completed Tasks | F | 32 | 38%
| Total Activities (To-Go) - % of Total | F | 92 | 65%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 68 | 74%
| Milestones (To-Go) | F | 16 | 17%
| Normal Tasks (To-Go) | F | 52 | 57%
| Summaries (To-Go) | F | 24 | 26%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 49 | 78%
| Longest Path (Normal Tasks) | F | 40 | 63%
| Longest Path (Milestones) | F | 9 | 14%
| Critical Milestones (To-Go) | F | 9 | 18%
| Critical Normal Tasks (To-Go) | F | 40 | 82%
| Riding Data Date | F | 4 | 6%
| Baselined to Start | F | 84
| Scheduled to Start | F | 84
| Actual Starts | F | 32
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Actual Finishes | F | 32
| Started Delayed (<=30 days) | F | 24 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 24 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.46
| BEI - Value Task Finishes - Cumulative | F | 0.47
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 3.47
| FEI - Value Task Finish - Cumulative | F | 3.25
| Current Baseline to Start & Started (BL Plan) | F | 32
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 52
| Current Baseline to Finish & Finished (BL Plan) | F | 32
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 52
| Duration Ratio Metric (DRM) | F | 28
| DRM Graph | F | 28
| Baselined to Start | F | 52
| Scheduled to Start | F | 52
| Baselined to Finish | F | 52
| Scheduled to Finish | F | 52
| BEI - Value Activities | F | 0.48
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 68 | 74%
| Critical Path To-Go | F | 49 | 72%
| Status Date | F | 2026-10-12
| Total Activities | F | 141
| Milestones | F | 26 | 18%
| Normal Tasks | F | 84 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 42 | 38%
| Completed Milestones | F | 10 | 38%
| Completed Tasks | F | 32 | 38%
| Total Activities (To-Go) - % of Total | F | 92 | 65%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 68 | 74%
| Milestones (To-Go) | F | 16 | 17%
| Normal Tasks (To-Go) | F | 52 | 57%
| Summaries (To-Go) | F | 24 | 26%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 49 | 78%
| Longest Path (Normal Tasks) | F | 40 | 63%
| Longest Path (Milestones) | F | 9 | 14%
| Riding Data Date | F | 4 | 6%
| Status Date | F | 2026-10-12
| Total Activities (To-Go) - % of Total | F | 92 | 65%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 68 | 74%
| Summary-to-Task Ratio (To-Go) | F | 1:02 | 0.46
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.31
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 49 | 72%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 68 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 68 | 74%
| Estimated Duration | F | 41 | 79%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 2
| Avg. Remaining Duration | F | 2
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 40 | 77%
| Avg. Critical Original Duration | F | 2
| Avg. Critical Remaining Duration | F | 2
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 52 | 62%
| Total Constraints | F | 44 | 65%
| Start No Earlier Than | F | 44 | 65%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 4 | 6%
| Open Ends w/o Constraints | F | 2 | 3%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 24 | 35%
| No Constraints | F | 23 | 34%
| Logic Density™ | F | 2.07
| Logic Density™ - Predecessors | F | 1.09
| Logic Density™ - Successors | F | 0.99
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 68 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 68 | 100%
| All Activities w/Successors | F | 62 | 91%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 62 | 91%
| Missing Logic | F | 6 | 9%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 6 | 9%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.09
| All Activities w/Predecessors | F | 68 | 100%
| Total # Predecessors | F | 74
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 0.99
| All Activities w/Successors | F | 62 | 100%
| Activities Missing Successors | F | 6 | 9%
| Total # Successors | F | 67
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 42 | 38%
| Completed Ahead - Tasks & Milestones | F | 3 | 7%
| Completed On-Schedule - Tasks & Milestones | F | 7 | 17%
| Completed Delayed - Tasks & Milestones | F | 32 | 76%
| Avg Days Finished Early - Tasks & Milestones | F | 21
| Avg Days Finished Late - Tasks & Milestones | F | 6
| Avg Finish Variance - Tasks & Milestones | F | 3
| Actually Finished - Tasks | F | 32 | 38%
| Completed Ahead - Tasks | F | 3 | 9%
| Completed On-Schedule - Tasks | F | 5 | 16%
| Completed Delayed - Tasks | F | 24 | 75%
| Accelerated Durations Early/On-Schedule - Tasks | F | 2 | 2%
| Accelerated Durations Late - Tasks | F | 2 | 2%
| Extended Durations - Tasks | F | 5 | 6%
| Actually Finished - Milestones | F | 10 | 38%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 2 | 20%
| Completed Delayed - Milestones | F | 8 | 80%
| Actually Started - Tasks | F | 0 | 0%
| In-Progress Started Ahead - Tasks | F | 0
| In-Progress Started On-Schedule - Tasks | F | 0
| In-Progress Started Delayed - Tasks | F | 0
| In-Progress Delayed Finish - Tasks | F | 0
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | 0
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 68 | 62%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 68 | 100%
| Riding Data Date - Tasks & Milestones | F | 4 | 6%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 52 | 62%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 52 | 100%
| Planned Delayed Finish - Tasks | F | 52 | 100%
| Scheduled to Start - Milestones | F | 16 | 62%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 16 | 100%
| Planned Delayed Finish - Milestones | F | 16 | 100%
| Schedule Baseline Activities | F | 110 | 100%
| Scheduled/Baselined to Start | F | 68
| Scheduled/Baselined to Finish | F | 68
| Start/ed | F | 42
| Finish/ed | F | 42
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 0 | 0%
| Completed Delayed (>30 days) | F | 0 | 0%
| SPI(t) | F | 1.25
| Scheduled Activities | F | 110 | 100%
| Scheduled to Start | F | 68 | 62%
| Scheduled to Finish | F | 68 | 62%
| Longest Path - Critical Activities and Milestones | F | 49 | 72%
| Critical Milestones (To-Go) | F | 9 | 56%
| Critical Tasks (To-Go) | F | 40 | 77%
| Critical Tasks (In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| High Float 10% | F | 11 | 16%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 49 | 72%
| Longest Path - Critical Activities and Milestones | F | 49 | 72%
| Critical Milestones (To-Go) | F | 9 | 56%
| Critical Tasks (To-Go) | F | 40 | 77%
| Critical Tasks (In Progress) | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.31
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| Logic Density™ | F | 2.09
| CP Logic Density™ | F | 2.12
| Critical w/Missing Logic | F | 1 | 9%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 49 | 72%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 84
| Scheduled to Start | F | 84
| Actual Starts | F | 32
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Actual Finishes | F | 32
| Started Delayed (<=30 days) | F | 24 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 24 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 84
| Scheduled to Start | F | 84
| Actual Starts | F | 32
| Current Baselined to Start & Started | F | 32
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Actual Finishes | F | 32
| Current Baselined to Finish & Finished | F | 32
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 24 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 24 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 69 | 82%
| Scheduled to Start - To Time Now | F | 69 | 82%
| Started | F | 32
| Started Late | F | 24
| Started Delayed (<=30 days) | F | 24 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 0.46
| Baselined to Finish - To Time Now | F | 68 | 81%
| Scheduled to Finish - To Time Now | F | 68 | 81%
| Finished | F | 32
| Finished Late | F | 24
| Completed Delayed (<=30 days) | F | 24 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.47
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.46
| BEI - Value Task Finishes - Cumulative | F | 0.47
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 3.47
| FEI - Value Task Finish - Cumulative | F | 3.25
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 32
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 52
| Baselined to Start - Check | F | 84
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 32
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 52
| Baselined to Finish - Check | F | 84
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 32
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 52
| Current Baseline to Finish & Finished (BL Plan) | F | 32
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 52
| Baselined to Start | F | 69
| Scheduled to Start | F | 69 | 100%
| Started - Scheduled | F | 32 | 46%
| Started - Baseline Comparison | F | 32 | 46%
| BEI - Value Task Starts | F | 0.46
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 68
| Scheduled to Finish | F | 68
| Finished | F | 32
| BEI - Value Task Finishes | F | 0.47
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-10-12
| Started (incl. Future Baseline Starts) - Scheduled | F | 32 | 38%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 32 | 38%
| Started Late (from Baseline) | F | 24
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 32 | 38%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 32 | 38%
| Finished Late | F | 24
| Completed Ahead | F | 3 | 9%
| Completed Delayed | F | 24 | 75%
| Completed On-Schedule | F | 5 | 16%
| Accelerated | F | 3 | 9%
| Days Variance | F | 84 | 262%
| Days Early | F | 63 | 196%
| Days Late | F | 147 | 458%
| Avg Days Early | F | 21
| Avg Days Late | F | 6
| Avg Variance | F | 3
| Actually Finished | F | 32 | 29%
| Took Longer than Planned | F | 9 | 21%
| Took Less Than Planned | F | 7 | 17%
| Completed (w/Baseline Duration) | F | 31 | 37%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 1 | 1%
| Baseline-to-Date Completed Tasks | F | 32 | 47%
| Missed Durations | F | 5 | 16%
| Missed Durations & Late Actual Finish | F | 4 | 13%
| Completed Ahead | F | 3 | 9%
| Completed Delayed | F | 24 | 75%
| Completed On-Schedule | F | 5 | 16%
| Accelerated | F | 3 | 9%
| Days Variance | F | 84 | 262%
| Days Early | F | 63 | 196%
| Days Late | F | 147 | 458%
| Avg Days Early | F | 21
| Avg Days Late | F | 6
| Avg Variance | F | 3
| Actually Finished | F | 32 | 29%
| Took Longer than Planned | F | 9 | 21%
| Took Less Than Planned | F | 7 | 17%
| Completed (w/Baseline Duration) | F | 31 | 37%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 1 | 1%
| Baseline-to-Date Completed Tasks | F | 32 | 47%
| Missed Durations | F | 5 | 16%
| Missed Durations & Late Actual Finish | F | 4 | 13%
| Baselined Tasks | F | 84
| Baselined to Start - TOTAL | F | 84
| Complete Task Starts - Cumulative | F | 32 | 46%
| Incomplete Task Starts - Cumulative (in work) | F | 37 | 54%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 84
| Complete Task Finishes - Cumulative (in work) | F | 32 | 47%
| Incomplete Task Finishes - Cumulative | F | 36 | 47%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.47
| BEI - Total Tasks | F | 68
| BEI - Complete Tasks | F | 32 | 47%
| BEI - Incomplete Tasks | F | 36 | 53%
| BEI - Value Tasks (adjusted) | F | 0.47
| BEI - Complete Tasks (adjusted) | F | 32 | 47%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-10-12
| BEI - Value Milestones | F | 0.53
| BEI - Total Milestones | F | 19
| BEI - Complete Milestones | F | 10 | 53%
| BEI - Incomplete Milestones | F | 9 | 47%
| BEI - Value Milestones (adjusted) | F | 0.53
| BEI - Complete Milestones (adjusted) | F | 10 | 53%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-10-12
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-10-12
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-10-12
| BEI - Value Tasks | F | 0.47
| BEI - Total Tasks | F | 68
| BEI - Incomplete Tasks | F | 36 | 53%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 10 | 53%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0.53
| BEI - Total Milestones | F | 19
| BEI - Complete Milestones | F | 10 | 53%
| BEI - Incomplete Milestones | F | 9 | 47%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.47
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0.53
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-10-12
| Total Activities - DRM | F | 28
| Total Activities - DRM Graph | F | 28
| Status Date | F | 2026-10-12
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-10-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-10-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.46
| BEI - Value Task Finishes - Cumulative | F | 0.47
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 3.47
| FEI - Value Task Finish - Cumulative | F | 3.25
| BEI - Value Tasks | F | 0.47
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0.53
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.47
| BEI - Complete Tasks | F | 32 | 47%
| BEI - Incomplete Tasks | F | 36 | 53%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 41 | 79%
| Missing Logic | F | 6 | 9%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 6 | 9%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 49 | 72%
| Status Date | F | 2026-10-12
| High Float 10% | F | 11 | 16%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 49 | 72%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 4 | 6%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 40 | 63%
| Longest Path (Tasks & Milestones) | F | 49 | 78%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23
| Critical Milestones (To-Go) | F | 9 | 56%
| Longest Path (Milestones) | F | 9 | 14%
| Normal Tasks | F | 84 | 60%
| Normal Tasks (To-Go) | F | 52 | 57%
| Critical Tasks (To-Go) | F | 40 | 77%
| Critical Tasks (In Progress) | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 49 | 72%
| CP Logic Density™ | F | 2.12
| Time Now | F | 2026-10-12
| Forecast to be Finished | F | 68 | 81%
| Completed On Time | T | 9 | 13%
| Completed Late | F | 23 | 34%
| Not Completed | F | 36 | 53%
| Baseline Finish Compliance | T | 13%
| Forecast to be Started | F | 69 | 82%
| Started On Time | T | 9 | 13%
| Started Late | F | 23 | 33%
| Not Started | F | 37 | 54%
| Baseline Start Compliance | T | 17%
1 | Completed Activities | F | 32
HSD01 | Time Now | F | 2026-10-12
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 37 | 44%
HSD04 | Started Late | F | 23 | 33%
HSD05 | Forecast to be Finished but not Finished yet | T | 36 | 43%
HSD06 | Finished Late | F | 23 | 34%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-12-12
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 1 | 50%
SEM02 | BRI Current | T | 0.04
SEM03 | BRI Cumulative | F | 0.47
SEM04 | BPI Current | T | 0.04
SEM05 | BEI Current | T | 0.09
SEM06 | BEI Cumulative | T | 0.47
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 3.47
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 3.25
SEM07 | To Go - Planned Task Starts - Count | T | 52
SEM07 | To Go - BEI - Task Finishes - Count | T | 52
SEM07 | To Go - Baselined Task Starts - Count | T | 52
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 3.47
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 33
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 15
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 36
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 16
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 3.47
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 3.25
SEM07 | To Go - Planned Task Starts - Count | T | 52
SEM07 | To Go - BEI - Task Finishes - Count | T | 52
SEM07 | To Go - Baselined Task Starts - Count | T | 52
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 3.47
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 48
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 33
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 15
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 52
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 36
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 16
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 33
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 15
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 36
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 16
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 3.47
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 3.25
SEM07 | To Go - Planned Task Starts - Count | T | 52
SEM07 | To Go - BEI - Task Finishes - Count | T | 52
SEM07 | To Go - Baselined Task Starts - Count | T | 52
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 3.47
SEM07 | TC-BEI | T | 3.25
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -2.52
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Hard_File_updated4-24-hour-cal2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated4 24 hour calendar 2 (11/12/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-11-12
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 3 | 16%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 9 | 64%
| Missing Logic | F | 2 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 2 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 15 | 79%
| Status Date | F | 2026-11-12
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 3 | 16%
| Negative Float | F | 15 | 79%
| Tasks & Milestones (To Go) | F | 19 | 17%
| Milestones (To-Go) | F | 5 | 26%
| Normal Tasks (To-Go) | F | 14 | 74%
| Normal Tasks (To-Go, In Progress) | F | 4 | 21%
| Critical Path (Tasks & Milestones) | F | 15 | 79%
| Critical Path (Milestones) | F | 4 | 27%
| Critical Path (Normal Tasks) | F | 11 | 73%
| Critical Path (Normal In Progress) | F | 1 | 7%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:03
| Negative Float | F | 15 | 79%
| Zero Days Float | F | 0 | 0%
| Near-Critical (<10 Days Float) | F | 16 | 84%
| CP Logic Density™ | F | 2.07
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.83
| BEI - Total Tasks | F | 84
| BEI - Complete Tasks | F | 70 | 83%
| BEI - Incomplete Tasks | F | 14 | 17%
| Status Date | F | 2026-11-12
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-11-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-11-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-11-12
| Total Activities | F | 141
| Milestones | F | 26 | 18%
| Normal Tasks | F | 84 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 91 | 83%
| Completed Milestones | F | 21 | 81%
| Completed Tasks | F | 70 | 83%
| Total Activities (To-Go) - % of Total | F | 30 | 21%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 19 | 63%
| Milestones (To-Go) | F | 5 | 17%
| Normal Tasks (To-Go) | F | 14 | 47%
| Summaries (To-Go) | F | 11 | 37%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 15 | 83%
| Longest Path (Normal Tasks) | F | 11 | 61%
| Longest Path (Milestones) | F | 4 | 22%
| Critical Milestones (To-Go) | F | 4 | 27%
| Critical Normal Tasks (To-Go) | F | 11 | 73%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 84
| Scheduled to Start | F | 84
| Actual Starts | F | 74
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Actual Finishes | F | 70
| Started Delayed (<=30 days) | F | 51 | 77%
| Started Delayed (Between 31 to 60 days) | F | 9 | 14%
| Started Delayed (>60 days) | F | 6 | 9%
| Completed Delayed (<=30 days) | F | 49 | 79%
| Completed Delayed (Between 31 to 60 days) | F | 7 | 11%
| Completed Delayed (>60 days) | F | 6 | 10%
| BEI - Value Task Starts - Cumulative | F | 0.88
| BEI - Value Task Finishes - Cumulative | F | 0.83
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | 74
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 10
| Current Baseline to Finish & Finished (BL Plan) | F | 70
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 14
| Duration Ratio Metric (DRM) | F | 66
| DRM Graph | F | 66
| Baselined to Start | F | 14
| Scheduled to Start | F | 14
| Baselined to Finish | F | 14
| Scheduled to Finish | F | 14
| BEI - Value Activities | F | 0.83
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 19 | 63%
| Critical Path To-Go | F | 15 | 79%
| Status Date | F | 2026-11-12
| Total Activities | F | 141
| Milestones | F | 26 | 18%
| Normal Tasks | F | 84 | 60%
| Summaries | F | 31 | 22%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78%
| Completed Tasks & Milestones | F | 91 | 83%
| Completed Milestones | F | 21 | 81%
| Completed Tasks | F | 70 | 83%
| Total Activities (To-Go) - % of Total | F | 30 | 21%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 19 | 63%
| Milestones (To-Go) | F | 5 | 17%
| Normal Tasks (To-Go) | F | 14 | 47%
| Summaries (To-Go) | F | 11 | 37%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 15 | 83%
| Longest Path (Normal Tasks) | F | 11 | 61%
| Longest Path (Milestones) | F | 4 | 22%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-11-12
| Total Activities (To-Go) - % of Total | F | 30 | 21%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 19 | 63%
| Summary-to-Task Ratio (To-Go) | F | 1:01 | 0.79
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.36
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.36
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 15 | 79%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 3 | 16%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 19 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 19 | 63%
| Estimated Duration | F | 9 | 64%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 2
| Avg. Remaining Duration | F | 1
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 11 | 79%
| Avg. Critical Original Duration | F | 1
| Avg. Critical Remaining Duration | F | 1
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 14 | 17%
| Total Constraints | F | 3 | 16%
| Start No Earlier Than | F | 3 | 16%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 1 | 5%
| Open Ends w/o Constraints | F | 1 | 5%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 16 | 84%
| No Constraints | F | 15 | 79%
| Logic Density™ | F | 2
| Logic Density™ - Predecessors | F | 1.05
| Logic Density™ - Successors | F | 0.95
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 15 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 19 | 100%
| All Activities w/Successors | F | 17 | 89%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 17 | 89%
| Missing Logic | F | 2 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 2 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.07
| All Activities w/Predecessors | F | 15 | 100%
| Total # Predecessors | F | 16
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 0.95
| All Activities w/Successors | F | 17 | 100%
| Activities Missing Successors | F | 2 | 11%
| Total # Successors | F | 18
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 91 | 83%
| Completed Ahead - Tasks & Milestones | F | 3 | 3%
| Completed On-Schedule - Tasks & Milestones | F | 7 | 8%
| Completed Delayed - Tasks & Milestones | F | 81 | 89%
| Avg Days Finished Early - Tasks & Milestones | F | 21
| Avg Days Finished Late - Tasks & Milestones | F | 25
| Avg Finish Variance - Tasks & Milestones | F | 21
| Actually Finished - Tasks | F | 70 | 83%
| Completed Ahead - Tasks | F | 3 | 4%
| Completed On-Schedule - Tasks | F | 5 | 7%
| Completed Delayed - Tasks | F | 62 | 89%
| Accelerated Durations Early/On-Schedule - Tasks | F | 2 | 2%
| Accelerated Durations Late - Tasks | F | 2 | 2%
| Extended Durations - Tasks | F | 8 | 10%
| Actually Finished - Milestones | F | 21 | 81%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 2 | 10%
| Completed Delayed - Milestones | F | 19 | 90%
| Actually Started - Tasks | F | 4 | 5%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 4 | 100%
| In-Progress Delayed Finish - Tasks | F | 4 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 35
| Avg Start Variance | F | 35
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 15 | 14%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 15 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 10 | 12%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 10 | 100%
| Planned Delayed Finish - Tasks | F | 10 | 100%
| Scheduled to Start - Milestones | F | 5 | 19%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 5 | 100%
| Planned Delayed Finish - Milestones | F | 5 | 100%
| Schedule Baseline Activities | F | 110 | 100%
| Scheduled/Baselined to Start | F | 19
| Scheduled/Baselined to Finish | F | 19
| Start/ed | F | 95
| Finish/ed | F | 91
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 15 | 23%
| Completed Delayed (>30 days) | F | 13 | 21%
| SPI(t) | F | 1.31
| Scheduled Activities | F | 110 | 100%
| Scheduled to Start | F | 19 | 17%
| Scheduled to Finish | F | 19 | 17%
| Longest Path - Critical Activities and Milestones | F | 15 | 79%
| Critical Milestones (To-Go) | F | 4 | 80%
| Critical Tasks (To-Go) | F | 11 | 79%
| Critical Tasks (In Progress) | F | 1 | 9%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.36
| High Float 10% | F | 3 | 16%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 15 | 79%
| Longest Path - Critical Activities and Milestones | F | 15 | 79%
| Critical Milestones (To-Go) | F | 4 | 80%
| Critical Tasks (To-Go) | F | 11 | 79%
| Critical Tasks (In Progress) | F | 1 | 9%
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.36
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.36
| Logic Density™ | F | 2.09
| CP Logic Density™ | F | 2.07
| Critical w/Missing Logic | F | 1 | 11%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 15 | 79%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 84
| Scheduled to Start | F | 84
| Actual Starts | F | 74
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Actual Finishes | F | 70
| Started Delayed (<=30 days) | F | 51 | 77%
| Started Delayed (Between 31 to 60 days) | F | 9 | 14%
| Started Delayed (>60 days) | F | 6 | 9%
| Completed Delayed (<=30 days) | F | 49 | 79%
| Completed Delayed (Between 31 to 60 days) | F | 7 | 11%
| Completed Delayed (>60 days) | F | 6 | 10%
| Baselined to Start | F | 84
| Scheduled to Start | F | 84
| Actual Starts | F | 74
| Current Baselined to Start & Started | F | 74
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Actual Finishes | F | 70
| Current Baselined to Finish & Finished | F | 70
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 51 | 77%
| Started Delayed (Between 31 to 60 days) | F | 9 | 14%
| Started Delayed (>60 days) | F | 6 | 9%
| Completed Delayed (<=30 days) | F | 49 | 79%
| Completed Delayed (Between 31 to 60 days) | F | 7 | 11%
| Completed Delayed (>60 days) | F | 6 | 10%
| Baselined to Start - To Time Now | F | 84 | 100%
| Scheduled to Start - To Time Now | F | 84 | 100%
| Started | F | 74
| Started Late | F | 66
| Started Delayed (<=30 days) | F | 51 | 77%
| Started Delayed (Between 31 to 60 days) | F | 9 | 14%
| Started Delayed (>60 days) | F | 6 | 9%
| BEI - Value Task Starts | F | 0.88
| Baselined to Finish - To Time Now | F | 84 | 100%
| Scheduled to Finish - To Time Now | F | 84 | 100%
| Finished | F | 70
| Finished Late | F | 62
| Completed Delayed (<=30 days) | F | 49 | 79%
| Completed Delayed (Between 31 to 60 days) | F | 7 | 11%
| Completed Delayed (>60 days) | F | 6 | 10%
| BEI - Value Task Finishes | F | 0.83
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.88
| BEI - Value Task Finishes - Cumulative | F | 0.83
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 74
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 10
| Baselined to Start - Check | F | 84
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 70
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 14
| Baselined to Finish - Check | F | 84
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 74
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 10
| Current Baseline to Finish & Finished (BL Plan) | F | 70
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 14
| Baselined to Start | F | 84
| Scheduled to Start | F | 84 | 100%
| Started - Scheduled | F | 74 | 88%
| Started - Baseline Comparison | F | 74 | 88%
| BEI - Value Task Starts | F | 0.88
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 84
| Scheduled to Finish | F | 84
| Finished | F | 70
| BEI - Value Task Finishes | F | 0.83
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-11-12
| Started (incl. Future Baseline Starts) - Scheduled | F | 74 | 88%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 74 | 88%
| Started Late (from Baseline) | F | 66
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 70 | 83%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 70 | 83%
| Finished Late | F | 62
| Completed Ahead | F | 3 | 4%
| Completed Delayed | F | 62 | 89%
| Completed On-Schedule | F | 5 | 7%
| Accelerated | F | 3 | 4%
| Days Variance | F | 1483 | 2118%
| Days Early | F | 63 | 89%
| Days Late | F | 1545 | 2208%
| Avg Days Early | F | 21
| Avg Days Late | F | 25
| Avg Variance | F | 21
| Actually Finished | F | 70 | 64%
| Took Longer than Planned | F | 15 | 16%
| Took Less Than Planned | F | 23 | 25%
| Completed (w/Baseline Duration) | F | 69 | 82%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 1 | 1%
| Baseline-to-Date Completed Tasks | F | 70 | 83%
| Missed Durations | F | 8 | 11%
| Missed Durations & Late Actual Finish | F | 7 | 10%
| Completed Ahead | F | 3 | 4%
| Completed Delayed | F | 62 | 89%
| Completed On-Schedule | F | 5 | 7%
| Accelerated | F | 3 | 4%
| Days Variance | F | 1483 | 2118%
| Days Early | F | 63 | 89%
| Days Late | F | 1545 | 2208%
| Avg Days Early | F | 21
| Avg Days Late | F | 25
| Avg Variance | F | 21
| Actually Finished | F | 70 | 64%
| Took Longer than Planned | F | 15 | 16%
| Took Less Than Planned | F | 23 | 25%
| Completed (w/Baseline Duration) | F | 69 | 82%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 1 | 1%
| Baseline-to-Date Completed Tasks | F | 70 | 83%
| Missed Durations | F | 8 | 11%
| Missed Durations & Late Actual Finish | F | 7 | 10%
| Baselined Tasks | F | 84
| Baselined to Start - TOTAL | F | 84
| Complete Task Starts - Cumulative | F | 74 | 88%
| Incomplete Task Starts - Cumulative (in work) | F | 10 | 12%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 84
| Complete Task Finishes - Cumulative (in work) | F | 70 | 83%
| Incomplete Task Finishes - Cumulative | F | 14 | 83%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.83
| BEI - Total Tasks | F | 84
| BEI - Complete Tasks | F | 70 | 83%
| BEI - Incomplete Tasks | F | 14 | 17%
| BEI - Value Tasks (adjusted) | F | 0.83
| BEI - Complete Tasks (adjusted) | F | 70 | 83%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-11-12
| BEI - Value Milestones | F | 0.81
| BEI - Total Milestones | F | 26
| BEI - Complete Milestones | F | 21 | 81%
| BEI - Incomplete Milestones | F | 5 | 19%
| BEI - Value Milestones (adjusted) | F | 0.81
| BEI - Complete Milestones (adjusted) | F | 21 | 81%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-11-12
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-11-12
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-11-12
| BEI - Value Tasks | F | 0.83
| BEI - Total Tasks | F | 84
| BEI - Incomplete Tasks | F | 14 | 17%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 21 | 81%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0.81
| BEI - Total Milestones | F | 26
| BEI - Complete Milestones | F | 21 | 81%
| BEI - Incomplete Milestones | F | 5 | 19%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.83
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0.81
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-11-12
| Total Activities - DRM | F | 66
| Total Activities - DRM Graph | F | 66
| Status Date | F | 2026-11-12
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-11-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-11-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.88
| BEI - Value Task Finishes - Cumulative | F | 0.83
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | 0.83
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0.81
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.83
| BEI - Complete Tasks | F | 70 | 83%
| BEI - Incomplete Tasks | F | 14 | 17%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 3 | 16%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 9 | 64%
| Missing Logic | F | 2 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 2 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 15 | 79%
| Status Date | F | 2026-11-12
| High Float 10% | F | 3 | 16%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 15 | 79%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 11 | 61%
| Longest Path (Tasks & Milestones) | F | 15 | 83%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.36
| Critical Milestones (To-Go) | F | 4 | 80%
| Longest Path (Milestones) | F | 4 | 22%
| Normal Tasks | F | 84 | 60%
| Normal Tasks (To-Go) | F | 14 | 47%
| Critical Tasks (To-Go) | F | 11 | 79%
| Critical Tasks (In Progress) | F | 1 | 9%
| Zero Days Float | F | 0 | 0%
| Negative Float | F | 15 | 79%
| CP Logic Density™ | F | 2.07
| Time Now | F | 2026-11-12
| Forecast to be Finished | F | 84 | 100%
| Completed On Time | T | 9 | 11%
| Completed Late | T | 64 | 76%
| Not Completed | F | 14 | 17%
| Baseline Finish Compliance | T | 11%
| Forecast to be Started | F | 84 | 100%
| Started On Time | T | 9 | 11%
| Started Late | T | 65 | 77%
| Not Started | F | 10 | 12%
| Baseline Start Compliance | T | 14%
1 | Completed Activities | F | 70
HSD01 | Time Now | F | 2026-11-12
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 10 | 12%
HSD04 | Started Late | T | 65 | 77%
HSD05 | Forecast to be Finished but not Finished yet | T | 14 | 17%
HSD06 | Finished Late | T | 64 | 76%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-11-19
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 29 | 85%
SEM02 | BRI Current | F | 0.31
SEM03 | BRI Cumulative | F | 0.83
SEM04 | BPI Current | F | 0.31
SEM05 | BEI Current | F | 2.13
SEM06 | BEI Cumulative | T | 0.83
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 0
SEM07 | To Go - Planned Task Starts - Count | T | 10
SEM07 | To Go - BEI - Task Finishes - Count | T | FALSE
SEM07 | To Go - Baselined Task Starts - Count | T | 10
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 10
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 11
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 0
SEM07 | To Go - Planned Task Starts - Count | T | 10
SEM07 | To Go - BEI - Task Finishes - Count | T | FALSE
SEM07 | To Go - Baselined Task Starts - Count | T | 10
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 10
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 10
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | 0
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 11
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 11
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 10
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 11
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 0
SEM07 | To Go - Planned Task Starts - Count | T | 10
SEM07 | To Go - BEI - Task Finishes - Count | T | FALSE
SEM07 | To Go - Baselined Task Starts - Count | T | 10
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | TC-BEI | F | 0
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | 0.79
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## EVM1
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
EVM1 (9/1/2012 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2012-09-01
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0
| Invalid Forecast Dates | F | 12 | 109%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 2 | 18%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 9%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2012-09-01
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 10 | 91%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 11 | 100%
| Milestones (To-Go) | F | 3 | 27%
| Normal Tasks (To-Go) | F | 8 | 73%
| Normal Tasks (To-Go, In Progress) | F | 2 | 18%
| Critical Path (Tasks & Milestones) | F | 10 | 91%
| Critical Path (Milestones) | F | 3 | 30%
| Critical Path (Normal Tasks) | F | 7 | 70%
| Critical Path (Normal In Progress) | F | 1 | 10%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:02
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 10 | 91%
| Near-Critical (<10 Days Float) | F | 11 | 100%
| CP Logic Density™ | F | 1.9
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0
| BEI - Total Tasks | F | 5
| BEI - Complete Tasks | F | 0 | 0%
| BEI - Incomplete Tasks | F | 5 | 100%
| Status Date | F | 2012-09-01
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2012-09-01
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2012-09-01
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2012-09-01
| Total Activities | F | 14
| Milestones | F | 3 | 21%
| Normal Tasks | F | 8 | 57%
| Summaries | F | 3 | 21%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 11 | 79%
| Completed Tasks & Milestones | F | 0 | 0%
| Completed Milestones | F | 0 | 0%
| Completed Tasks | F | 0 | 0%
| Total Activities (To-Go) - % of Total | F | 14 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 11 | 79%
| Milestones (To-Go) | F | 3 | 21%
| Normal Tasks (To-Go) | F | 8 | 57%
| Summaries (To-Go) | F | 3 | 21%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 10 | 77%
| Longest Path (Normal Tasks) | F | 7 | 54%
| Longest Path (Milestones) | F | 3 | 23%
| Critical Milestones (To-Go) | F | 3 | 30%
| Critical Normal Tasks (To-Go) | F | 7 | 70%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 8
| Scheduled to Start | F | 8
| Actual Starts | F | 2
| Baselined to Finish | F | 8
| Scheduled to Finish | F | 8
| Actual Finishes | F | 0
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.4
| BEI - Value Task Finishes - Cumulative | F | 0
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Current Baseline to Start & Started (BL Plan) | F | 2
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 6
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | 8
| Duration Ratio Metric (DRM) | F | 0
| DRM Graph | F | 0
| Baselined to Start | F | 8
| Scheduled to Start | F | 8
| Baselined to Finish | F | 8
| Scheduled to Finish | F | 8
| BEI - Value Activities | F | 0
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 11 | 79%
| Critical Path To-Go | F | 10 | 91%
| Status Date | F | 2012-09-01
| Total Activities | F | 14
| Milestones | F | 3 | 21%
| Normal Tasks | F | 8 | 57%
| Summaries | F | 3 | 21%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 11 | 79%
| Completed Tasks & Milestones | F | 0 | 0%
| Completed Milestones | F | 0 | 0%
| Completed Tasks | F | 0 | 0%
| Total Activities (To-Go) - % of Total | F | 14 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 11 | 79%
| Milestones (To-Go) | F | 3 | 21%
| Normal Tasks (To-Go) | F | 8 | 57%
| Summaries (To-Go) | F | 3 | 21%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 10 | 77%
| Longest Path (Normal Tasks) | F | 7 | 54%
| Longest Path (Milestones) | F | 3 | 23%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2012-09-01
| Total Activities (To-Go) - % of Total | F | 14 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 11 | 79%
| Summary-to-Task Ratio (To-Go) | F | 1:03 | 0.38
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.38
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:02 | 0.43
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 10 | 91%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 12 | 109%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 11 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 11 | 79%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 3
| Avg. Remaining Duration | F | 2
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 6 | 75%
| Critical Activities (To-Go) | F | 7 | 88%
| Avg. Critical Original Duration | F | 3
| Avg. Critical Remaining Duration | F | 3
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 5 | 63%
| Activities (To-Go) | F | 8 | 100%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 2 | 9%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 11 | 100%
| No Constraints | F | 11 | 100%
| Logic Density™ | F | 1.82
| Logic Density™ - Predecessors | F | 0.91
| Logic Density™ - Successors | F | 0.91
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 9 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 10 | 91%
| All Activities w/Successors | F | 10 | 91%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 10 | 91%
| Missing Logic | F | 2 | 18%
| Missing Predecessors | F | 1 | 9%
| Missing Successors | F | 1 | 9%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1
| All Activities w/Predecessors | F | 9 | 100%
| Total # Predecessors | F | 9
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 0.91
| All Activities w/Successors | F | 10 | 100%
| Activities Missing Successors | F | 1 | 9%
| Total # Successors | F | 10
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 0 | 0%
| Completed Ahead - Tasks & Milestones | F | 0
| Completed On-Schedule - Tasks & Milestones | F | 0
| Completed Delayed - Tasks & Milestones | F | 0
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 0
| Avg Finish Variance - Tasks & Milestones | F | 0
| Actually Finished - Tasks | F | 0 | 0%
| Completed Ahead - Tasks | F | 0
| Completed On-Schedule - Tasks | F | 0
| Completed Delayed - Tasks | F | 0
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 0 | 0%
| Actually Finished - Milestones | F | 0 | 0%
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 2 | 25%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 2 | 100%
| In-Progress Started Delayed - Tasks | F | 0 | 0%
| In-Progress Delayed Finish - Tasks | F | 0 | 0%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 0
| Avg Start Variance | F | 0
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 9 | 82%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 9 | 100%
| Planned Delayed Start - Tasks & Milestones | F | 0 | 0%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 6 | 75%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 6 | 100%
| Planned Delayed Start - Tasks | F | 0 | 0%
| Planned Delayed Finish - Tasks | F | 0 | 0%
| Scheduled to Start - Milestones | F | 3 | 100%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 3 | 100%
| Planned Delayed Start - Milestones | F | 0 | 0%
| Planned Delayed Finish - Milestones | F | 0 | 0%
| Schedule Baseline Activities | F | 11 | 100%
| Scheduled/Baselined to Start | F | 11
| Scheduled/Baselined to Finish | F | 11
| Start/ed | F | 2
| Finish/ed | F | 0
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | 0
| Scheduled Activities | F | 11 | 100%
| Scheduled to Start | F | 11 | 100%
| Scheduled to Finish | F | 11 | 100%
| Longest Path - Critical Activities and Milestones | F | 10 | 91%
| Critical Milestones (To-Go) | F | 3 | 100%
| Critical Tasks (To-Go) | F | 7 | 88%
| Critical Tasks (In Progress) | F | 1 | 14%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:02 | 0.43
| High Float 10% | F | 0 | 0%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 10 | 91%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 10 | 91%
| Critical Milestones (To-Go) | F | 3 | 100%
| Critical Tasks (To-Go) | F | 7 | 88%
| Critical Tasks (In Progress) | F | 1 | 14%
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.38
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:02 | 0.43
| Logic Density™ | F | 1.82
| CP Logic Density™ | F | 1.9
| Critical w/Missing Logic | F | 1 | 18%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 10 | 91%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 8
| Scheduled to Start | F | 8
| Actual Starts | F | 2
| Baselined to Finish | F | 8
| Scheduled to Finish | F | 8
| Actual Finishes | F | 0
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | 8
| Scheduled to Start | F | 8
| Actual Starts | F | 2
| Current Baselined to Start & Started | F | 2
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 8
| Scheduled to Finish | F | 8
| Actual Finishes | F | 0
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | 5 | 63%
| Scheduled to Start - To Time Now | F | 5 | 63%
| Started | F | 2
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | 0.4
| Baselined to Finish - To Time Now | F | 5 | 63%
| Scheduled to Finish - To Time Now | F | 5 | 63%
| Finished | F | 0
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | 0
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.4
| BEI - Value Task Finishes - Cumulative | F | 0
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 2
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 6
| Baselined to Start - Check | F | 8
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | 8
| Baselined to Finish - Check | F | 8
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | 2
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 6
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | 8
| Baselined to Start | F | 5
| Scheduled to Start | F | 5 | 100%
| Started - Scheduled | F | 2 | 40%
| Started - Baseline Comparison | F | 2 | 40%
| BEI - Value Task Starts | F | 0.4
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 5
| Scheduled to Finish | F | 5
| Finished | F | 0
| BEI - Value Task Finishes | F | 0
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2012-09-01
| Started (incl. Future Baseline Starts) - Scheduled | F | 2 | 25%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 2 | 25%
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 0 | 0%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 0 | 0%
| Finished Late | F | N/A
| Completed Ahead | F | 0
| Completed Delayed | F | 0
| Completed On-Schedule | F | 0
| Accelerated | F | 0
| Days Variance | F | 0
| Days Early | F | 0
| Days Late | F | 0
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 0 | 0%
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | 0 | 0%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 0 | 0%
| Missed Durations | F | 0
| Missed Durations & Late Actual Finish | F | 0
| Completed Ahead | F | 0
| Completed Delayed | F | 0
| Completed On-Schedule | F | 0
| Accelerated | F | 0
| Days Variance | F | 0
| Days Early | F | 0
| Days Late | F | 0
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 0 | 0%
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | 0 | 0%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 0 | 0%
| Missed Durations | F | 0
| Missed Durations & Late Actual Finish | F | 0
| Baselined Tasks | F | 8
| Baselined to Start - TOTAL | F | 8
| Complete Task Starts - Cumulative | F | 2 | 40%
| Incomplete Task Starts - Cumulative (in work) | F | 3 | 60%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 8
| Complete Task Finishes - Cumulative (in work) | F | 0 | 0%
| Incomplete Task Finishes - Cumulative | F | 5 | 0%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0
| BEI - Total Tasks | F | 5
| BEI - Complete Tasks | F | 0 | 0%
| BEI - Incomplete Tasks | F | 5 | 100%
| BEI - Value Tasks (adjusted) | F | 0
| BEI - Complete Tasks (adjusted) | F | 0 | 0%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2012-09-01
| BEI - Value Milestones | F | 0
| BEI - Total Milestones | F | 2
| BEI - Complete Milestones | F | 0 | 0%
| BEI - Incomplete Milestones | F | 2 | 100%
| BEI - Value Milestones (adjusted) | F | 0
| BEI - Complete Milestones (adjusted) | F | 0 | 0%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2012-09-01
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2012-09-01
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2012-09-01
| BEI - Value Tasks | F | 0
| BEI - Total Tasks | F | 5
| BEI - Incomplete Tasks | F | 5 | 100%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 0 | 0%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0
| BEI - Total Milestones | F | 2
| BEI - Complete Milestones | F | 0 | 0%
| BEI - Incomplete Milestones | F | 2 | 100%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2012-09-01
| Total Activities - DRM | F | 0
| Total Activities - DRM Graph | F | 0
| Status Date | F | 2012-09-01
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2012-09-01
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2012-09-01
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.4
| BEI - Value Task Finishes - Cumulative | F | 0
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| BEI - Value Tasks | F | 0
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0
| BEI - Complete Tasks | F | 0 | 0%
| BEI - Incomplete Tasks | F | 5 | 100%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 12 | 109%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 2 | 18%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 9%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2012-09-01
| High Float 10% | F | 0 | 0%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 10 | 91%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 7 | 54%
| Longest Path (Tasks & Milestones) | F | 10 | 77%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:02 | 0.43
| Critical Milestones (To-Go) | F | 3 | 100%
| Longest Path (Milestones) | F | 3 | 23%
| Normal Tasks | F | 8 | 57%
| Normal Tasks (To-Go) | F | 8 | 57%
| Critical Tasks (To-Go) | F | 7 | 88%
| Critical Tasks (In Progress) | F | 1 | 14%
| Zero Days Float | F | 10 | 91%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 1.9
| Time Now | F | 2012-09-01
| Forecast to be Finished | F | 5 | 63%
| Completed On Time | F | 5 | 100%
| Completed Late | F | 0 | 0%
| Not Completed | F | 5 | 100%
| Baseline Finish Compliance | F | 100%
| Forecast to be Started | F | 5 | 63%
| Started On Time | F | 5 | 100%
| Started Late | F | 0 | 0%
| Not Started | F | 3 | 60%
| Baseline Start Compliance | F | 100%
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | 2012-09-01
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 3 | 38%
HSD04 | Started Late | F | 0 | 0%
HSD05 | Forecast to be Finished but not Finished yet | T | 5 | 63%
HSD06 | Finished Late | F | 0 | 0%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2012-09-12
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | T | 0
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | T | 0
SEM06 | BEI Cumulative | T | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 3
SEM07 | To Go - BEI - Task Finishes - Count | T | 3
SEM07 | To Go - Baselined Task Starts - Count | T | 3
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 3
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 3
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 3
SEM07 | To Go - BEI - Task Finishes - Count | T | 3
SEM07 | To Go - Baselined Task Starts - Count | T | 3
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Workoff Burden - Starts To-Go (Total) | F | 3
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | 3
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | 3
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 3
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 3
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 3
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 3
SEM07 | To Go - BEI - Task Finishes - Count | T | 3
SEM07 | To Go - Baselined Task Starts - Count | T | 3
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | TC-BEI | F | 1
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -1
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## EVM2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
EVM2 (9/12/2012 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2012-09-12
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 13%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 13%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2012-09-12
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 8 | 100%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 8 | 73%
| Milestones (To-Go) | F | 2 | 25%
| Normal Tasks (To-Go) | F | 6 | 75%
| Normal Tasks (To-Go, In Progress) | F | 1 | 13%
| Critical Path (Tasks & Milestones) | F | 8 | 100%
| Critical Path (Milestones) | F | 2 | 25%
| Critical Path (Normal Tasks) | F | 6 | 75%
| Critical Path (Normal In Progress) | F | 1 | 13%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:03
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 8 | 100%
| Near-Critical (<10 Days Float) | F | 8 | 100%
| CP Logic Density™ | F | 2.13
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.25
| BEI - Total Tasks | F | 8
| BEI - Complete Tasks | F | 2 | 25%
| BEI - Incomplete Tasks | F | 6 | 75%
| Status Date | F | 2012-09-12
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2012-09-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2012-09-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2012-09-12
| Total Activities | F | 14
| Milestones | F | 3 | 21%
| Normal Tasks | F | 8 | 57%
| Summaries | F | 3 | 21%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 11 | 79%
| Completed Tasks & Milestones | F | 3 | 27%
| Completed Milestones | F | 1 | 33%
| Completed Tasks | F | 2 | 25%
| Total Activities (To-Go) - % of Total | F | 11 | 79%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 8 | 73%
| Milestones (To-Go) | F | 2 | 18%
| Normal Tasks (To-Go) | F | 6 | 55%
| Summaries (To-Go) | F | 3 | 27%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 8 | 73%
| Longest Path (Normal Tasks) | F | 6 | 55%
| Longest Path (Milestones) | F | 2 | 18%
| Critical Milestones (To-Go) | F | 2 | 25%
| Critical Normal Tasks (To-Go) | F | 6 | 75%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 8
| Scheduled to Start | F | 8
| Actual Starts | F | 3
| Baselined to Finish | F | 8
| Scheduled to Finish | F | 8
| Actual Finishes | F | 2
| Started Delayed (<=30 days) | F | 1 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.38
| BEI - Value Task Finishes - Cumulative | F | 0.25
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | 6
| Current Baseline to Start & Started (BL Plan) | F | 3
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 5
| Current Baseline to Finish & Finished (BL Plan) | F | 2
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 6
| Duration Ratio Metric (DRM) | F | 2
| DRM Graph | F | 2
| Baselined to Start | F | 6
| Scheduled to Start | F | 6
| Baselined to Finish | F | 6
| Scheduled to Finish | F | 6
| BEI - Value Activities | F | 0.27
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 8 | 73%
| Critical Path To-Go | F | 8 | 100%
| Status Date | F | 2012-09-12
| Total Activities | F | 14
| Milestones | F | 3 | 21%
| Normal Tasks | F | 8 | 57%
| Summaries | F | 3 | 21%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 11 | 79%
| Completed Tasks & Milestones | F | 3 | 27%
| Completed Milestones | F | 1 | 33%
| Completed Tasks | F | 2 | 25%
| Total Activities (To-Go) - % of Total | F | 11 | 79%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 8 | 73%
| Milestones (To-Go) | F | 2 | 18%
| Normal Tasks (To-Go) | F | 6 | 55%
| Summaries (To-Go) | F | 3 | 27%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 8 | 73%
| Longest Path (Normal Tasks) | F | 6 | 55%
| Longest Path (Milestones) | F | 2 | 18%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2012-09-12
| Total Activities (To-Go) - % of Total | F | 11 | 79%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 8 | 73%
| Summary-to-Task Ratio (To-Go) | F | 1:02 | 0.5
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.33
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.33
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 8 | 100%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 8 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 8 | 73%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 3
| Avg. Remaining Duration | F | 2
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 6 | 100%
| Avg. Critical Original Duration | F | 3
| Avg. Critical Remaining Duration | F | 2
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 6 | 75%
| Total Constraints | F | 4 | 50%
| Start No Earlier Than | F | 4 | 50%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 1 | 13%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 4 | 50%
| No Constraints | F | 4 | 50%
| Logic Density™ | F | 2.13
| Logic Density™ - Predecessors | F | 1.13
| Logic Density™ - Successors | F | 1
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 7 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 8 | 100%
| All Activities w/Successors | F | 7 | 88%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 7 | 88%
| Missing Logic | F | 1 | 13%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 13%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.14
| All Activities w/Predecessors | F | 7 | 100%
| Total # Predecessors | F | 8
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1
| All Activities w/Successors | F | 7 | 100%
| Activities Missing Successors | F | 1 | 13%
| Total # Successors | F | 8
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 3 | 27%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 1 | 33%
| Completed Delayed - Tasks & Milestones | F | 2 | 67%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 2
| Avg Finish Variance - Tasks & Milestones | F | 1
| Actually Finished - Tasks | F | 2 | 25%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 1 | 50%
| Completed Delayed - Tasks | F | 1 | 50%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 1 | 13%
| Actually Finished - Milestones | F | 1 | 33%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 0 | 0%
| Completed Delayed - Milestones | F | 1 | 100%
| Actually Started - Tasks | F | 1 | 13%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 1 | 100%
| In-Progress Delayed Finish - Tasks | F | 1 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 2
| Avg Start Variance | F | 2
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 7 | 64%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 7 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 5 | 63%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 5 | 100%
| Planned Delayed Finish - Tasks | F | 5 | 100%
| Scheduled to Start - Milestones | F | 2 | 67%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 2 | 100%
| Planned Delayed Finish - Milestones | F | 2 | 100%
| Schedule Baseline Activities | F | 11 | 100%
| Scheduled/Baselined to Start | F | 8
| Scheduled/Baselined to Finish | F | 8
| Start/ed | F | 4
| Finish/ed | F | 3
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 0 | 0%
| Completed Delayed (>30 days) | F | 0 | 0%
| SPI(t) | F | 0.56
| Scheduled Activities | F | 11 | 100%
| Scheduled to Start | F | 8 | 73%
| Scheduled to Finish | F | 8 | 73%
| Longest Path - Critical Activities and Milestones | F | 8 | 100%
| Critical Milestones (To-Go) | F | 2 | 100%
| Critical Tasks (To-Go) | F | 6 | 100%
| Critical Tasks (In Progress) | F | 1 | 17%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.33
| High Float 10% | F | 0 | 0%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 8 | 100%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 8 | 100%
| Critical Milestones (To-Go) | F | 2 | 100%
| Critical Tasks (To-Go) | F | 6 | 100%
| Critical Tasks (In Progress) | F | 1 | 17%
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.33
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.33
| Logic Density™ | F | 2
| CP Logic Density™ | F | 2.13
| Critical w/Missing Logic | F | 1 | 13%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 8 | 100%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 8
| Scheduled to Start | F | 8
| Actual Starts | F | 3
| Baselined to Finish | F | 8
| Scheduled to Finish | F | 8
| Actual Finishes | F | 2
| Started Delayed (<=30 days) | F | 1 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 8
| Scheduled to Start | F | 8
| Actual Starts | F | 3
| Current Baselined to Start & Started | F | 3
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 8
| Scheduled to Finish | F | 8
| Actual Finishes | F | 2
| Current Baselined to Finish & Finished | F | 2
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 1 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 8 | 100%
| Scheduled to Start - To Time Now | F | 8 | 100%
| Started | F | 3
| Started Late | F | 1
| Started Delayed (<=30 days) | F | 1 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 0.38
| Baselined to Finish - To Time Now | F | 8 | 100%
| Scheduled to Finish - To Time Now | F | 8 | 100%
| Finished | F | 2
| Finished Late | F | 1
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.25
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.38
| BEI - Value Task Finishes - Cumulative | F | 0.25
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | 6
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 3
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 5
| Baselined to Start - Check | F | 8
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 2
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 6
| Baselined to Finish - Check | F | 8
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 3
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 5
| Current Baseline to Finish & Finished (BL Plan) | F | 2
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 6
| Baselined to Start | F | 8
| Scheduled to Start | F | 8 | 100%
| Started - Scheduled | F | 3 | 38%
| Started - Baseline Comparison | F | 3 | 38%
| BEI - Value Task Starts | F | 0.38
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 8
| Scheduled to Finish | F | 8
| Finished | F | 2
| BEI - Value Task Finishes | F | 0.25
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2012-09-12
| Started (incl. Future Baseline Starts) - Scheduled | F | 3 | 38%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 3 | 38%
| Started Late (from Baseline) | F | 1
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 2 | 25%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 2 | 25%
| Finished Late | F | 1
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 1 | 50%
| Completed On-Schedule | F | 1 | 50%
| Accelerated | F | 0 | 0%
| Days Variance | F | 2 | 100%
| Days Early | F | 0 | 0%
| Days Late | F | 2 | 100%
| Avg Days Early | F | 0
| Avg Days Late | F | 2
| Avg Variance | F | 1
| Actually Finished | F | 2 | 18%
| Took Longer than Planned | F | 1 | 33%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 2 | 25%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 2 | 25%
| Missed Durations | F | 1 | 50%
| Missed Durations & Late Actual Finish | F | 1 | 50%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 1 | 50%
| Completed On-Schedule | F | 1 | 50%
| Accelerated | F | 0 | 0%
| Days Variance | F | 2 | 100%
| Days Early | F | 0 | 0%
| Days Late | F | 2 | 100%
| Avg Days Early | F | 0
| Avg Days Late | F | 2
| Avg Variance | F | 1
| Actually Finished | F | 2 | 18%
| Took Longer than Planned | F | 1 | 33%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 2 | 25%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 2 | 25%
| Missed Durations | F | 1 | 50%
| Missed Durations & Late Actual Finish | F | 1 | 50%
| Baselined Tasks | F | 8
| Baselined to Start - TOTAL | F | 8
| Complete Task Starts - Cumulative | F | 3 | 38%
| Incomplete Task Starts - Cumulative (in work) | F | 5 | 63%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 8
| Complete Task Finishes - Cumulative (in work) | F | 2 | 25%
| Incomplete Task Finishes - Cumulative | F | 6 | 25%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.25
| BEI - Total Tasks | F | 8
| BEI - Complete Tasks | F | 2 | 25%
| BEI - Incomplete Tasks | F | 6 | 75%
| BEI - Value Tasks (adjusted) | F | 0.25
| BEI - Complete Tasks (adjusted) | F | 2 | 25%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2012-09-12
| BEI - Value Milestones | F | 0.33
| BEI - Total Milestones | F | 3
| BEI - Complete Milestones | F | 1 | 33%
| BEI - Incomplete Milestones | F | 2 | 67%
| BEI - Value Milestones (adjusted) | F | 0.33
| BEI - Complete Milestones (adjusted) | F | 1 | 33%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2012-09-12
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2012-09-12
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2012-09-12
| BEI - Value Tasks | F | 0.25
| BEI - Total Tasks | F | 8
| BEI - Incomplete Tasks | F | 6 | 75%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 33%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 0.33
| BEI - Total Milestones | F | 3
| BEI - Complete Milestones | F | 1 | 33%
| BEI - Incomplete Milestones | F | 2 | 67%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.25
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 0.33
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2012-09-12
| Total Activities - DRM | F | 2
| Total Activities - DRM Graph | F | 2
| Status Date | F | 2012-09-12
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2012-09-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2012-09-12
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.38
| BEI - Value Task Finishes - Cumulative | F | 0.25
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | 6
| BEI - Value Tasks | F | 0.25
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 0.33
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.25
| BEI - Complete Tasks | F | 2 | 25%
| BEI - Incomplete Tasks | F | 6 | 75%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 13%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 13%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2012-09-12
| High Float 10% | F | 0 | 0%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 8 | 100%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 6 | 55%
| Longest Path (Tasks & Milestones) | F | 8 | 73%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.33
| Critical Milestones (To-Go) | F | 2 | 100%
| Longest Path (Milestones) | F | 2 | 18%
| Normal Tasks | F | 8 | 57%
| Normal Tasks (To-Go) | F | 6 | 55%
| Critical Tasks (To-Go) | F | 6 | 100%
| Critical Tasks (In Progress) | F | 1 | 17%
| Zero Days Float | F | 8 | 100%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.13
| Time Now | F | 2012-09-12
| Forecast to be Finished | F | 7 | 88%
| Completed On Time | T | 1 | 14%
| Completed Late | F | 1 | 14%
| Not Completed | F | 5 | 71%
| Baseline Finish Compliance | T | 14%
| Forecast to be Started | F | 8 | 100%
| Started On Time | F | 2 | 25%
| Started Late | F | 1 | 13%
| Not Started | F | 5 | 63%
| Baseline Start Compliance | F | 25%
1 | Completed Activities | F | 2
HSD01 | Time Now | F | 2012-09-12
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 5 | 63%
HSD04 | Started Late | F | 1 | 13%
HSD05 | Forecast to be Finished but not Finished yet | T | 5 | 63%
HSD06 | Finished Late | F | 1 | 14%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2012-10-04
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 0 | 0%
SEM02 | BRI Current | F | 0.25
SEM03 | BRI Cumulative | F | 0.25
SEM04 | BPI Current | F | 0.25
SEM05 | BEI Current | T | 0.25
SEM06 | BEI Cumulative | T | 0.25
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 6
SEM07 | To Go - Planned Task Starts - Count | T | 5
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 5
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 5
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 6
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 6
SEM07 | To Go - Planned Task Starts - Count | T | 5
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 5
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | Workoff Burden - Starts To-Go (Total) | F | 5
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 5
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | 0
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 6
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 6
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 5
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 6
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 0
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 6
SEM07 | To Go - Planned Task Starts - Count | T | 5
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 5
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | TC-BEI | T | 6
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -3.45
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Project2-3
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project2 3 (5/24/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-05-24
| Specific Task Start | F | 2027-06-17
| Specific Task Finish | F | 2027-07-14
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-05-24
| High Float 44d | F | 44 | 42%
| Zero Days Float | F | 41 | 39%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 2%
| Critical Merge Hotspot | F | 3 | 3%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 39 | 37%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 106 | 84%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 106 | 100%
| Normal Tasks (To-Go, In Progress) | F | 3 | 3%
| Critical Path (Tasks & Milestones) | F | 41 | 39%
| Critical Path (Milestones) | F | 0 | 0%
| Critical Path (Normal Tasks) | F | 41 | 100%
| Critical Path (Normal In Progress) | F | 1 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 41 | 39%
| Near-Critical (<10 Days Float) | F | 50 | 47%
| CP Logic Density™ | F | 3.2
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.74
| BEI - Total Tasks | F | 27
| BEI - Complete Tasks | F | 20 | 74%
| BEI - Incomplete Tasks | F | 7 | 26%
| Status Date | F | 2026-05-24
| Milestone #1 - 100 | F | 2027-06-17
| Float Milestone #1 - 100 | F | 0
| Milestone #2 - 101 | F | 2027-04-08
| Float to Milestone #2 - 101 | F | 15
| Milestone #3 - 102 | F | 2027-05-13
| Float to Milestone #3 - 102 | F | 10
| Milestone #4 - 103 | F | 2027-06-16
| Float to Milestone #4 - 103 | F | 10
| Milestone #5 - 104 | F | 2027-06-17
| Float to Milestone #5 - 104 | F | 30
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-05-24
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-05-24
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-05-24
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 20 | 16%
| Completed Milestones | F | 0
| Completed Tasks | F | 20 | 16%
| Total Activities (To-Go) - % of Total | F | 122 | 85%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 106 | 87%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 106 | 87%
| Summaries (To-Go) | F | 16 | 13%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 41 | 87%
| Longest Path (Normal Tasks) | F | 41 | 87%
| Longest Path (Milestones) | F | 0 | 0%
| Critical Milestones (To-Go) | F | 0 | 0%
| Critical Normal Tasks (To-Go) | F | 41 | 100%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 23
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 20
| Started Delayed (<=30 days) | F | 8 | 67%
| Started Delayed (Between 31 to 60 days) | F | 4 | 33%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 6 | 55%
| Completed Delayed (Between 31 to 60 days) | F | 5 | 45%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.79
| BEI - Value Task Finishes - Cumulative | F | 0.74
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.06
| FEI - Value Task Finish - Cumulative | F | 1.07
| Current Baseline to Start & Started (BL Plan) | F | 23
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 103
| Current Baseline to Finish & Finished (BL Plan) | F | 20
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 106
| Duration Ratio Metric (DRM) | F | 20
| DRM Graph | F | 20
| Baselined to Start | F | 106
| Scheduled to Start | F | 106
| Baselined to Finish | F | 106
| Scheduled to Finish | F | 106
| BEI - Value Activities | F | 0.74
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 106 | 87%
| Critical Path To-Go | F | 41 | 39%
| Status Date | F | 2026-05-24
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 20 | 16%
| Completed Milestones | F | 0
| Completed Tasks | F | 20 | 16%
| Total Activities (To-Go) - % of Total | F | 122 | 85%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 106 | 87%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 106 | 87%
| Summaries (To-Go) | F | 16 | 13%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 41 | 87%
| Longest Path (Normal Tasks) | F | 41 | 87%
| Longest Path (Milestones) | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-05-24
| Total Activities (To-Go) - % of Total | F | 122 | 85%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 106 | 87%
| Summary-to-Task Ratio (To-Go) | F | 1:07 | 0.15
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 41 | 39%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 106 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 106 | 87%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 9
| Avg. Remaining Duration | F | 9
| High Baseline Duration (44d) | F | 1 | 1%
| High Planned Duration (44d) | F | 1 | 1%
| Insufficient Detail™ | F | 1 | 1%
| Critical Activities (To-Go) | F | 41 | 39%
| Avg. Critical Original Duration | F | 9
| Avg. Critical Remaining Duration | F | 8
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 106 | 84%
| Total Constraints | F | 1 | 1%
| Start No Earlier Than | F | 1 | 1%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 4 | 4%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 105 | 99%
| No Constraints | F | 105 | 99%
| Logic Density™ | F | 2.81
| Logic Density™ - Predecessors | F | 1.45
| Logic Density™ - Successors | F | 1.36
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 103 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 1 | 1%
| FS Predecessors | F | 106 | 100%
| All Activities w/Successors | F | 102 | 96%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 102 | 96%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.47
| All Activities w/Predecessors | F | 103 | 100%
| Total # Predecessors | F | 151
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 2 | 2%
| Total # Predecessor Lags | F | 2
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 5
| Hidden Duration (Planned) | F | 1 | 1%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 10 | 10%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | 0 | 0%
| Critical Merge Hotspot | F | 3 | 3%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 2%
| Logic Density™ - Successors | F | 1.36
| All Activities w/Successors | F | 102 | 100%
| Activities Missing Successors | F | 4 | 4%
| Total # Successors | F | 144
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 1 | 1%
| Total# of Successor Lags | F | 1
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 11 | 10%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 2%
| Actually Finished - Tasks & Milestones | F | 20 | 16%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 9 | 45%
| Completed Delayed - Tasks & Milestones | F | 11 | 55%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 25
| Avg Finish Variance - Tasks & Milestones | F | 14
| Actually Finished - Tasks | F | 20 | 16%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 9 | 45%
| Completed Delayed - Tasks | F | 11 | 55%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 1 | 1%
| Extended Durations - Tasks | F | 4 | 3%
| Actually Finished - Milestones | F | 0
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 3 | 2%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 3 | 100%
| In-Progress Delayed Finish - Tasks | F | 3 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 24
| Avg Start Variance | F | 24
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 103 | 82%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 103 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 103 | 82%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 103 | 100%
| Planned Delayed Finish - Tasks | F | 103 | 100%
| Scheduled to Start - Milestones | F | 0
| Planned Ahead Start - Milestones | F | 0
| Planned On Schedule Start - Milestones | F | 0
| Planned Delayed Start - Milestones | F | 0
| Planned Delayed Finish - Milestones | F | 0
| Schedule Baseline Activities | F | 126 | 100%
| Scheduled/Baselined to Start | F | 106
| Scheduled/Baselined to Finish | F | 106
| Start/ed | F | 23
| Finish/ed | F | 20
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 4 | 33%
| Completed Delayed (>30 days) | F | 5 | 45%
| SPI(t) | F | 0.83
| Scheduled Activities | F | 126 | 100%
| Scheduled to Start | F | 106 | 84%
| Scheduled to Finish | F | 106 | 84%
| Longest Path - Critical Activities and Milestones | F | 41 | 39%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 41 | 39%
| Critical Tasks (In Progress) | F | 1 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| High Float 10% | F | 39 | 37%
| High Float 44d | F | 44 | 42%
| Zero Days Float | F | 41 | 39%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 41 | 39%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 41 | 39%
| Critical Tasks (In Progress) | F | 1 | 2%
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Logic Density™ | F | 2.79
| CP Logic Density™ | F | 3.2
| Critical w/Missing Logic | F | 1 | 4%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 41 | 39%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 1 | 2%
| Critical with Successor Lag | F | 1 | 2%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 1 | 2%
| Negative Float with Successor Lag | F | 1 | 2%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 23
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 20
| Started Delayed (<=30 days) | F | 8 | 67%
| Started Delayed (Between 31 to 60 days) | F | 4 | 33%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 6 | 55%
| Completed Delayed (Between 31 to 60 days) | F | 5 | 45%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 23
| Current Baselined to Start & Started | F | 23
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 20
| Current Baselined to Finish & Finished | F | 20
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 8 | 67%
| Started Delayed (Between 31 to 60 days) | F | 4 | 33%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 6 | 55%
| Completed Delayed (Between 31 to 60 days) | F | 5 | 45%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 29 | 23%
| Scheduled to Start - To Time Now | F | 29 | 23%
| Started | F | 23
| Started Late | F | 12
| Started Delayed (<=30 days) | F | 8 | 67%
| Started Delayed (Between 31 to 60 days) | F | 4 | 33%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 0.79
| Baselined to Finish - To Time Now | F | 27 | 21%
| Scheduled to Finish - To Time Now | F | 27 | 21%
| Finished | F | 20
| Finished Late | F | 11
| Completed Delayed (<=30 days) | F | 6 | 55%
| Completed Delayed (Between 31 to 60 days) | F | 5 | 45%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.74
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.79
| BEI - Value Task Finishes - Cumulative | F | 0.74
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.06
| FEI - Value Task Finish - Cumulative | F | 1.07
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 23
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 103
| Baselined to Start - Check | F | 126
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 20
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 106
| Baselined to Finish - Check | F | 126
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 23
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 103
| Current Baseline to Finish & Finished (BL Plan) | F | 20
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 106
| Baselined to Start | F | 29
| Scheduled to Start | F | 29 | 100%
| Started - Scheduled | F | 23 | 79%
| Started - Baseline Comparison | F | 23 | 79%
| BEI - Value Task Starts | F | 0.79
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 27
| Scheduled to Finish | F | 27
| Finished | F | 20
| BEI - Value Task Finishes | F | 0.74
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-05-24
| Started (incl. Future Baseline Starts) - Scheduled | F | 23 | 18%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 23 | 18%
| Started Late (from Baseline) | F | 12
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 20 | 16%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 20 | 16%
| Finished Late | F | 11
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 11 | 55%
| Completed On-Schedule | F | 9 | 45%
| Accelerated | F | 0 | 0%
| Days Variance | F | 277 | 1385%
| Days Early | F | 0 | 0%
| Days Late | F | 277 | 1385%
| Avg Days Early | F | 0
| Avg Days Late | F | 25
| Avg Variance | F | 14
| Actually Finished | F | 20 | 16%
| Took Longer than Planned | F | 4 | 20%
| Took Less Than Planned | F | 2 | 10%
| Completed (w/Baseline Duration) | F | 20 | 16%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 20 | 74%
| Missed Durations | F | 4 | 20%
| Missed Durations & Late Actual Finish | F | 4 | 20%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 11 | 55%
| Completed On-Schedule | F | 9 | 45%
| Accelerated | F | 0 | 0%
| Days Variance | F | 277 | 1385%
| Days Early | F | 0 | 0%
| Days Late | F | 277 | 1385%
| Avg Days Early | F | 0
| Avg Days Late | F | 25
| Avg Variance | F | 14
| Actually Finished | F | 20 | 16%
| Took Longer than Planned | F | 4 | 20%
| Took Less Than Planned | F | 2 | 10%
| Completed (w/Baseline Duration) | F | 20 | 16%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 20 | 74%
| Missed Durations | F | 4 | 20%
| Missed Durations & Late Actual Finish | F | 4 | 20%
| Baselined Tasks | F | 126
| Baselined to Start - TOTAL | F | 126
| Complete Task Starts - Cumulative | F | 23 | 79%
| Incomplete Task Starts - Cumulative (in work) | F | 6 | 21%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 126
| Complete Task Finishes - Cumulative (in work) | F | 20 | 74%
| Incomplete Task Finishes - Cumulative | F | 7 | 74%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.74
| BEI - Total Tasks | F | 27
| BEI - Complete Tasks | F | 20 | 74%
| BEI - Incomplete Tasks | F | 7 | 26%
| BEI - Value Tasks (adjusted) | F | 0.74
| BEI - Complete Tasks (adjusted) | F | 20 | 74%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-05-24
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-05-24
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-05-24
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-05-24
| BEI - Value Tasks | F | 0.74
| BEI - Total Tasks | F | 27
| BEI - Incomplete Tasks | F | 7 | 26%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.74
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-05-24
| Total Activities - DRM | F | 20
| Total Activities - DRM Graph | F | 20
| Status Date | F | 2026-05-24
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | 2027-05-13
| Float to Milestone #3 - 102 | F | 10
| Milestone #4 - 103 | F | 2027-06-02
| Float to Milestone #4 - 103 | F | 10
| Milestone #5 - 104 | F | 2027-07-15
| Float to Milestone #5 - 105 | F | 10
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-05-24
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-05-24
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.79
| BEI - Value Task Finishes - Cumulative | F | 0.74
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.06
| FEI - Value Task Finish - Cumulative | F | 1.07
| BEI - Value Tasks | F | 0.74
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.74
| BEI - Complete Tasks | F | 20 | 74%
| BEI - Incomplete Tasks | F | 7 | 26%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-05-24
| High Float 10% | F | 39 | 37%
| High Float 44d | F | 44 | 42%
| Zero Days Float | F | 41 | 39%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 2%
| Critical Merge Hotspot | F | 3 | 3%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 41 | 87%
| Longest Path (Tasks & Milestones) | F | 41 | 87%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestones (To-Go) | F | 0
| Longest Path (Milestones) | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Normal Tasks (To-Go) | F | 106 | 87%
| Critical Tasks (To-Go) | F | 41 | 39%
| Critical Tasks (In Progress) | F | 1 | 2%
| Zero Days Float | F | 41 | 39%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 3.2
| Time Now | F | 2026-05-24
| Forecast to be Finished | F | 27 | 21%
| Completed On Time | F | 9 | 33%
| Completed Late | F | 11 | 41%
| Not Completed | F | 7 | 26%
| Baseline Finish Compliance | F | 33%
| Forecast to be Started | F | 29 | 23%
| Started On Time | F | 11 | 38%
| Started Late | F | 12 | 41%
| Not Started | F | 6 | 21%
| Baseline Start Compliance | F | 41%
1 | Completed Activities | F | 20
HSD01 | Time Now | F | 2026-05-24
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 6 | 5%
HSD04 | Started Late | F | 12 | 41%
HSD05 | Forecast to be Finished but not Finished yet | T | 7 | 6%
HSD06 | Finished Late | F | 11 | 41%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2027-09-14
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 5 | 100%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.74
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | F | 1.25
SEM06 | BEI Cumulative | T | 0.74
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1.07
SEM07 | To Go - Planned Task Starts - Count | T | 103
SEM07 | To Go - BEI - Task Finishes - Count | T | 106
SEM07 | To Go - Baselined Task Starts - Count | T | 103
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 6
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 97
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 7
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 99
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1.07
SEM07 | To Go - Planned Task Starts - Count | T | 103
SEM07 | To Go - BEI - Task Finishes - Count | T | 106
SEM07 | To Go - Baselined Task Starts - Count | T | 103
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 103
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 6
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 97
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 106
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 7
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 99
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 6
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 97
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 7
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 99
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1.07
SEM07 | To Go - Planned Task Starts - Count | T | 103
SEM07 | To Go - BEI - Task Finishes - Count | T | 106
SEM07 | To Go - Baselined Task Starts - Count | T | 103
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1.06
SEM07 | TC-BEI | F | 1.07
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.34
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Project3-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project3 2 (6/30/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-06-30
| Specific Task Start | F | 2027-08-05
| Specific Task Finish | F | 2027-09-01
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-06-30
| High Float 44d | F | 42 | 41%
| Zero Days Float | F | 40 | 39%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Critical Merge Hotspot | F | 3 | 3%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 31 | 30%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 102 | 81%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 102 | 100%
| Normal Tasks (To-Go, In Progress) | F | 1 | 1%
| Critical Path (Tasks & Milestones) | F | 40 | 39%
| Critical Path (Milestones) | F | 0 | 0%
| Critical Path (Normal Tasks) | F | 40 | 100%
| Critical Path (Normal In Progress) | F | 1 | 3%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 40 | 39%
| Near-Critical (<10 Days Float) | F | 49 | 48%
| CP Logic Density™ | F | 3.23
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.67
| BEI - Total Tasks | F | 36
| BEI - Complete Tasks | F | 24 | 67%
| BEI - Incomplete Tasks | F | 12 | 33%
| Status Date | F | 2026-06-30
| Milestone #1 - 100 | F | 2027-08-05
| Float Milestone #1 - 100 | F | 0
| Milestone #2 - 101 | F | 2027-05-27
| Float to Milestone #2 - 101 | F | 15
| Milestone #3 - 102 | F | 2027-07-01
| Float to Milestone #3 - 102 | F | 10
| Milestone #4 - 103 | F | 2027-08-04
| Float to Milestone #4 - 103 | F | 10
| Milestone #5 - 104 | F | 2027-08-05
| Float to Milestone #5 - 104 | F | 30
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-06-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-06-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-06-30
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 24 | 19%
| Completed Milestones | F | 0
| Completed Tasks | F | 24 | 19%
| Total Activities (To-Go) - % of Total | F | 117 | 81%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 102 | 87%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 102 | 87%
| Summaries (To-Go) | F | 15 | 13%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 40 | 87%
| Longest Path (Normal Tasks) | F | 40 | 87%
| Longest Path (Milestones) | F | 0 | 0%
| Critical Milestones (To-Go) | F | 0 | 0%
| Critical Normal Tasks (To-Go) | F | 40 | 100%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 25
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 24
| Started Delayed (<=30 days) | F | 8 | 57%
| Started Delayed (Between 31 to 60 days) | F | 4 | 29%
| Started Delayed (>60 days) | F | 2 | 14%
| Completed Delayed (<=30 days) | F | 7 | 47%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 40%
| Completed Delayed (>60 days) | F | 2 | 13%
| BEI - Value Task Starts - Cumulative | F | 0.66
| BEI - Value Task Finishes - Cumulative | F | 0.67
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.15
| FEI - Value Task Finish - Cumulative | F | 1.13
| Current Baseline to Start & Started (BL Plan) | F | 25
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 101
| Current Baseline to Finish & Finished (BL Plan) | F | 24
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 102
| Duration Ratio Metric (DRM) | F | 24
| DRM Graph | F | 24
| Baselined to Start | F | 102
| Scheduled to Start | F | 102
| Baselined to Finish | F | 102
| Scheduled to Finish | F | 102
| BEI - Value Activities | F | 0.67
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 102 | 87%
| Critical Path To-Go | F | 40 | 39%
| Status Date | F | 2026-06-30
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 24 | 19%
| Completed Milestones | F | 0
| Completed Tasks | F | 24 | 19%
| Total Activities (To-Go) - % of Total | F | 117 | 81%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 102 | 87%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 102 | 87%
| Summaries (To-Go) | F | 15 | 13%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 40 | 87%
| Longest Path (Normal Tasks) | F | 40 | 87%
| Longest Path (Milestones) | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-06-30
| Total Activities (To-Go) - % of Total | F | 117 | 81%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 102 | 87%
| Summary-to-Task Ratio (To-Go) | F | 1:07 | 0.15
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 40 | 39%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 102 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 102 | 87%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 9
| Avg. Remaining Duration | F | 9
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 40 | 39%
| Avg. Critical Original Duration | F | 9
| Avg. Critical Remaining Duration | F | 9
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 102 | 81%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 4 | 4%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 102 | 100%
| No Constraints | F | 102 | 100%
| Logic Density™ | F | 2.83
| Logic Density™ - Predecessors | F | 1.47
| Logic Density™ - Successors | F | 1.36
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 101 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 1 | 1%
| FS Predecessors | F | 102 | 100%
| All Activities w/Successors | F | 98 | 96%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 98 | 96%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.47
| All Activities w/Predecessors | F | 101 | 100%
| Total # Predecessors | F | 148
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 1 | 1%
| Total # Predecessor Lags | F | 1
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 5
| Hidden Duration (Planned) | F | 1 | 1%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 10 | 10%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 3 | 3%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Logic Density™ - Successors | F | 1.36
| All Activities w/Successors | F | 98 | 100%
| Activities Missing Successors | F | 4 | 4%
| Total # Successors | F | 139
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 1 | 1%
| Total# of Successor Lags | F | 1
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 11 | 11%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Actually Finished - Tasks & Milestones | F | 24 | 19%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 9 | 38%
| Completed Delayed - Tasks & Milestones | F | 15 | 63%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 32
| Avg Finish Variance - Tasks & Milestones | F | 20
| Actually Finished - Tasks | F | 24 | 19%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 9 | 38%
| Completed Delayed - Tasks | F | 15 | 63%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 1 | 1%
| Extended Durations - Tasks | F | 6 | 5%
| Actually Finished - Milestones | F | 0
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 1 | 1%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 1 | 100%
| In-Progress Delayed Finish - Tasks | F | 1 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 67
| Avg Start Variance | F | 67
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 101 | 80%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 101 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 101 | 80%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 101 | 100%
| Planned Delayed Finish - Tasks | F | 101 | 100%
| Scheduled to Start - Milestones | F | 0
| Planned Ahead Start - Milestones | F | 0
| Planned On Schedule Start - Milestones | F | 0
| Planned Delayed Start - Milestones | F | 0
| Planned Delayed Finish - Milestones | F | 0
| Schedule Baseline Activities | F | 126 | 100%
| Scheduled/Baselined to Start | F | 102
| Scheduled/Baselined to Finish | F | 102
| Start/ed | F | 25
| Finish/ed | F | 24
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 6 | 43%
| Completed Delayed (>30 days) | F | 8 | 53%
| SPI(t) | F | 0.88
| Scheduled Activities | F | 126 | 100%
| Scheduled to Start | F | 102 | 81%
| Scheduled to Finish | F | 102 | 81%
| Longest Path - Critical Activities and Milestones | F | 40 | 39%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 40 | 39%
| Critical Tasks (In Progress) | F | 1 | 3%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| High Float 10% | F | 31 | 30%
| High Float 44d | F | 42 | 41%
| Zero Days Float | F | 40 | 39%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 40 | 39%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 40 | 39%
| Critical Tasks (In Progress) | F | 1 | 3%
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Logic Density™ | F | 2.79
| CP Logic Density™ | F | 3.23
| Critical w/Missing Logic | F | 1 | 4%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 40 | 39%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 1 | 3%
| Critical with Successor Lag | F | 1 | 3%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 25
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 24
| Started Delayed (<=30 days) | F | 8 | 57%
| Started Delayed (Between 31 to 60 days) | F | 4 | 29%
| Started Delayed (>60 days) | F | 2 | 14%
| Completed Delayed (<=30 days) | F | 7 | 47%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 40%
| Completed Delayed (>60 days) | F | 2 | 13%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 25
| Current Baselined to Start & Started | F | 25
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 24
| Current Baselined to Finish & Finished | F | 24
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 8 | 57%
| Started Delayed (Between 31 to 60 days) | F | 4 | 29%
| Started Delayed (>60 days) | F | 2 | 14%
| Completed Delayed (<=30 days) | F | 7 | 47%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 40%
| Completed Delayed (>60 days) | F | 2 | 13%
| Baselined to Start - To Time Now | F | 38 | 30%
| Scheduled to Start - To Time Now | F | 38 | 30%
| Started | F | 25
| Started Late | F | 14
| Started Delayed (<=30 days) | F | 8 | 57%
| Started Delayed (Between 31 to 60 days) | F | 4 | 29%
| Started Delayed (>60 days) | F | 2 | 14%
| BEI - Value Task Starts | F | 0.66
| Baselined to Finish - To Time Now | F | 36 | 29%
| Scheduled to Finish - To Time Now | F | 36 | 29%
| Finished | F | 24
| Finished Late | F | 15
| Completed Delayed (<=30 days) | F | 7 | 47%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 40%
| Completed Delayed (>60 days) | F | 2 | 13%
| BEI - Value Task Finishes | F | 0.67
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.66
| BEI - Value Task Finishes - Cumulative | F | 0.67
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.15
| FEI - Value Task Finish - Cumulative | F | 1.13
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 25
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 101
| Baselined to Start - Check | F | 126
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 24
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 102
| Baselined to Finish - Check | F | 126
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 25
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 101
| Current Baseline to Finish & Finished (BL Plan) | F | 24
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 102
| Baselined to Start | F | 38
| Scheduled to Start | F | 38 | 100%
| Started - Scheduled | F | 25 | 66%
| Started - Baseline Comparison | F | 25 | 66%
| BEI - Value Task Starts | F | 0.66
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 36
| Scheduled to Finish | F | 36
| Finished | F | 24
| BEI - Value Task Finishes | F | 0.67
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-06-30
| Started (incl. Future Baseline Starts) - Scheduled | F | 25 | 20%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 25 | 20%
| Started Late (from Baseline) | F | 14
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 24 | 19%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 24 | 19%
| Finished Late | F | 15
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 15 | 63%
| Completed On-Schedule | F | 9 | 38%
| Accelerated | F | 0 | 0%
| Days Variance | F | 475 | 1979%
| Days Early | F | 0 | 0%
| Days Late | F | 475 | 1979%
| Avg Days Early | F | 0
| Avg Days Late | F | 32
| Avg Variance | F | 20
| Actually Finished | F | 24 | 19%
| Took Longer than Planned | F | 6 | 25%
| Took Less Than Planned | F | 4 | 17%
| Completed (w/Baseline Duration) | F | 24 | 19%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 24 | 67%
| Missed Durations | F | 6 | 25%
| Missed Durations & Late Actual Finish | F | 6 | 25%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 15 | 63%
| Completed On-Schedule | F | 9 | 38%
| Accelerated | F | 0 | 0%
| Days Variance | F | 475 | 1979%
| Days Early | F | 0 | 0%
| Days Late | F | 475 | 1979%
| Avg Days Early | F | 0
| Avg Days Late | F | 32
| Avg Variance | F | 20
| Actually Finished | F | 24 | 19%
| Took Longer than Planned | F | 6 | 25%
| Took Less Than Planned | F | 4 | 17%
| Completed (w/Baseline Duration) | F | 24 | 19%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 24 | 67%
| Missed Durations | F | 6 | 25%
| Missed Durations & Late Actual Finish | F | 6 | 25%
| Baselined Tasks | F | 126
| Baselined to Start - TOTAL | F | 126
| Complete Task Starts - Cumulative | F | 25 | 66%
| Incomplete Task Starts - Cumulative (in work) | F | 13 | 34%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 126
| Complete Task Finishes - Cumulative (in work) | F | 24 | 67%
| Incomplete Task Finishes - Cumulative | F | 12 | 67%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.67
| BEI - Total Tasks | F | 36
| BEI - Complete Tasks | F | 24 | 67%
| BEI - Incomplete Tasks | F | 12 | 33%
| BEI - Value Tasks (adjusted) | F | 0.67
| BEI - Complete Tasks (adjusted) | F | 24 | 67%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-06-30
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-06-30
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-06-30
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-06-30
| BEI - Value Tasks | F | 0.67
| BEI - Total Tasks | F | 36
| BEI - Incomplete Tasks | F | 12 | 33%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.67
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-06-30
| Total Activities - DRM | F | 24
| Total Activities - DRM Graph | F | 24
| Status Date | F | 2026-06-30
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | 2027-07-01
| Float to Milestone #3 - 102 | F | 10
| Milestone #4 - 103 | F | 2027-07-21
| Float to Milestone #4 - 103 | F | 10
| Milestone #5 - 104 | F | 2027-09-02
| Float to Milestone #5 - 105 | F | 10
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-06-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-06-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.66
| BEI - Value Task Finishes - Cumulative | F | 0.67
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.15
| FEI - Value Task Finish - Cumulative | F | 1.13
| BEI - Value Tasks | F | 0.67
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.67
| BEI - Complete Tasks | F | 24 | 67%
| BEI - Incomplete Tasks | F | 12 | 33%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-06-30
| High Float 10% | F | 31 | 30%
| High Float 44d | F | 42 | 41%
| Zero Days Float | F | 40 | 39%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Critical Merge Hotspot | F | 3 | 3%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 40 | 87%
| Longest Path (Tasks & Milestones) | F | 40 | 87%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestones (To-Go) | F | 0
| Longest Path (Milestones) | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Normal Tasks (To-Go) | F | 102 | 87%
| Critical Tasks (To-Go) | F | 40 | 39%
| Critical Tasks (In Progress) | F | 1 | 3%
| Zero Days Float | F | 40 | 39%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 3.23
| Time Now | F | 2026-06-30
| Forecast to be Finished | F | 36 | 29%
| Completed On Time | F | 9 | 25%
| Completed Late | F | 15 | 42%
| Not Completed | F | 12 | 33%
| Baseline Finish Compliance | F | 25%
| Forecast to be Started | F | 38 | 30%
| Started On Time | F | 11 | 29%
| Started Late | F | 14 | 37%
| Not Started | F | 13 | 34%
| Baseline Start Compliance | F | 32%
1 | Completed Activities | F | 24
HSD01 | Time Now | F | 2026-06-30
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 13 | 10%
HSD04 | Started Late | F | 14 | 37%
HSD05 | Forecast to be Finished but not Finished yet | T | 12 | 10%
HSD06 | Finished Late | F | 15 | 42%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2027-11-02
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 2 | 67%
SEM02 | BRI Current | T | 0.14
SEM03 | BRI Cumulative | F | 0.67
SEM04 | BPI Current | T | 0.14
SEM05 | BEI Current | T | 0.43
SEM06 | BEI Cumulative | T | 0.67
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.15
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.13
SEM07 | To Go - Planned Task Starts - Count | T | 101
SEM07 | To Go - BEI - Task Finishes - Count | T | 102
SEM07 | To Go - Baselined Task Starts - Count | T | 101
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.15
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 13
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 88
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 12
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 90
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.15
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.13
SEM07 | To Go - Planned Task Starts - Count | T | 101
SEM07 | To Go - BEI - Task Finishes - Count | T | 102
SEM07 | To Go - Baselined Task Starts - Count | T | 101
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.15
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 101
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 13
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 88
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 102
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 12
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 90
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 13
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 88
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 12
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 90
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.15
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.13
SEM07 | To Go - Planned Task Starts - Count | T | 101
SEM07 | To Go - BEI - Task Finishes - Count | T | 102
SEM07 | To Go - Baselined Task Starts - Count | T | 101
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.15
SEM07 | TC-BEI | T | 1.13
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.45
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Project4-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project4 2 (7/29/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-07-29
| Specific Task Start | F | 2027-08-19
| Specific Task Finish | F | 2027-09-15
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-07-29
| High Float 44d | F | 41 | 41%
| Zero Days Float | F | 37 | 37%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Critical Merge Hotspot | F | 3 | 3%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 31 | 31%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 101 | 80%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 101 | 100%
| Normal Tasks (To-Go, In Progress) | F | 1 | 1%
| Critical Path (Tasks & Milestones) | F | 37 | 37%
| Critical Path (Milestones) | F | 0 | 0%
| Critical Path (Normal Tasks) | F | 37 | 100%
| Critical Path (Normal In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 37 | 37%
| Near-Critical (<10 Days Float) | F | 48 | 48%
| CP Logic Density™ | F | 3.32
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.58
| BEI - Total Tasks | F | 43
| BEI - Complete Tasks | F | 25 | 58%
| BEI - Incomplete Tasks | F | 18 | 42%
| Status Date | F | 2026-07-29
| Milestone #1 - 100 | F | 2027-08-19
| Float Milestone #1 - 100 | F | 0
| Milestone #2 - 101 | F | 2027-06-10
| Float to Milestone #2 - 101 | F | 15
| Milestone #3 - 102 | F | 2027-07-15
| Float to Milestone #3 - 102 | F | 10
| Milestone #4 - 103 | F | 2027-08-18
| Float to Milestone #4 - 103 | F | 10
| Milestone #5 - 104 | F | 2027-08-19
| Float to Milestone #5 - 104 | F | 30
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-07-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-07-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-07-29
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 25 | 20%
| Completed Milestones | F | 0
| Completed Tasks | F | 25 | 20%
| Total Activities (To-Go) - % of Total | F | 116 | 81%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 101 | 87%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 101 | 87%
| Summaries (To-Go) | F | 15 | 13%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 37 | 90%
| Longest Path (Normal Tasks) | F | 37 | 90%
| Longest Path (Milestones) | F | 0 | 0%
| Critical Milestones (To-Go) | F | 0 | 0%
| Critical Normal Tasks (To-Go) | F | 37 | 100%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 26
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 25
| Started Delayed (<=30 days) | F | 8 | 53%
| Started Delayed (Between 31 to 60 days) | F | 4 | 27%
| Started Delayed (>60 days) | F | 3 | 20%
| Completed Delayed (<=30 days) | F | 7 | 44%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 38%
| Completed Delayed (>60 days) | F | 3 | 19%
| BEI - Value Task Starts - Cumulative | F | 0.59
| BEI - Value Task Finishes - Cumulative | F | 0.58
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.22
| FEI - Value Task Finish - Cumulative | F | 1.22
| Current Baseline to Start & Started (BL Plan) | F | 26
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 100
| Current Baseline to Finish & Finished (BL Plan) | F | 25
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 101
| Duration Ratio Metric (DRM) | F | 25
| DRM Graph | F | 25
| Baselined to Start | F | 101
| Scheduled to Start | F | 101
| Baselined to Finish | F | 101
| Scheduled to Finish | F | 101
| BEI - Value Activities | F | 0.58
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 101 | 87%
| Critical Path To-Go | F | 37 | 37%
| Status Date | F | 2026-07-29
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 25 | 20%
| Completed Milestones | F | 0
| Completed Tasks | F | 25 | 20%
| Total Activities (To-Go) - % of Total | F | 116 | 81%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 101 | 87%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 101 | 87%
| Summaries (To-Go) | F | 15 | 13%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 37 | 90%
| Longest Path (Normal Tasks) | F | 37 | 90%
| Longest Path (Milestones) | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-07-29
| Total Activities (To-Go) - % of Total | F | 116 | 81%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 101 | 87%
| Summary-to-Task Ratio (To-Go) | F | 1:07 | 0.15
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 37 | 37%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 101 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 101 | 87%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 9
| Avg. Remaining Duration | F | 9
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 37 | 37%
| Avg. Critical Original Duration | F | 9
| Avg. Critical Remaining Duration | F | 9
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 101 | 80%
| Total Constraints | F | 2 | 2%
| Start No Earlier Than | F | 2 | 2%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 4 | 4%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 99 | 98%
| No Constraints | F | 99 | 98%
| Logic Density™ | F | 2.87
| Logic Density™ - Predecessors | F | 1.49
| Logic Density™ - Successors | F | 1.39
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 100 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 101 | 100%
| All Activities w/Successors | F | 97 | 96%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 97 | 96%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.49
| All Activities w/Predecessors | F | 100 | 100%
| Total # Predecessors | F | 149
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 1 | 1%
| Total # Predecessor Lags | F | 1
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 5
| Hidden Duration (Planned) | F | 1 | 1%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 10 | 10%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 3 | 3%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Logic Density™ - Successors | F | 1.39
| All Activities w/Successors | F | 97 | 100%
| Activities Missing Successors | F | 4 | 4%
| Total # Successors | F | 140
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 1 | 1%
| Total# of Successor Lags | F | 1
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 11 | 11%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 8 | 8%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Actually Finished - Tasks & Milestones | F | 25 | 20%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 9 | 36%
| Completed Delayed - Tasks & Milestones | F | 16 | 64%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 34
| Avg Finish Variance - Tasks & Milestones | F | 22
| Actually Finished - Tasks | F | 25 | 20%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 9 | 36%
| Completed Delayed - Tasks | F | 16 | 64%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 1 | 1%
| Extended Durations - Tasks | F | 6 | 5%
| Actually Finished - Milestones | F | 0
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 1 | 1%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 1 | 100%
| In-Progress Delayed Finish - Tasks | F | 1 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 67
| Avg Start Variance | F | 67
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 100 | 79%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 100 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 100 | 79%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 100 | 100%
| Planned Delayed Finish - Tasks | F | 100 | 100%
| Scheduled to Start - Milestones | F | 0
| Planned Ahead Start - Milestones | F | 0
| Planned On Schedule Start - Milestones | F | 0
| Planned Delayed Start - Milestones | F | 0
| Planned Delayed Finish - Milestones | F | 0
| Schedule Baseline Activities | F | 126 | 100%
| Scheduled/Baselined to Start | F | 101
| Scheduled/Baselined to Finish | F | 101
| Start/ed | F | 26
| Finish/ed | F | 25
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 7 | 47%
| Completed Delayed (>30 days) | F | 9 | 56%
| SPI(t) | F | 0.89
| Scheduled Activities | F | 126 | 100%
| Scheduled to Start | F | 101 | 80%
| Scheduled to Finish | F | 101 | 80%
| Longest Path - Critical Activities and Milestones | F | 37 | 37%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 37 | 37%
| Critical Tasks (In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| High Float 10% | F | 31 | 31%
| High Float 44d | F | 41 | 41%
| Zero Days Float | F | 37 | 37%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 37 | 37%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 37 | 37%
| Critical Tasks (In Progress) | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Logic Density™ | F | 2.83
| CP Logic Density™ | F | 3.32
| Critical w/Missing Logic | F | 1 | 4%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 37 | 37%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 26
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 25
| Started Delayed (<=30 days) | F | 8 | 53%
| Started Delayed (Between 31 to 60 days) | F | 4 | 27%
| Started Delayed (>60 days) | F | 3 | 20%
| Completed Delayed (<=30 days) | F | 7 | 44%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 38%
| Completed Delayed (>60 days) | F | 3 | 19%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 26
| Current Baselined to Start & Started | F | 26
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 25
| Current Baselined to Finish & Finished | F | 25
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 8 | 53%
| Started Delayed (Between 31 to 60 days) | F | 4 | 27%
| Started Delayed (>60 days) | F | 3 | 20%
| Completed Delayed (<=30 days) | F | 7 | 44%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 38%
| Completed Delayed (>60 days) | F | 3 | 19%
| Baselined to Start - To Time Now | F | 44 | 35%
| Scheduled to Start - To Time Now | F | 44 | 35%
| Started | F | 26
| Started Late | F | 15
| Started Delayed (<=30 days) | F | 8 | 53%
| Started Delayed (Between 31 to 60 days) | F | 4 | 27%
| Started Delayed (>60 days) | F | 3 | 20%
| BEI - Value Task Starts | F | 0.59
| Baselined to Finish - To Time Now | F | 43 | 34%
| Scheduled to Finish - To Time Now | F | 43 | 34%
| Finished | F | 25
| Finished Late | F | 16
| Completed Delayed (<=30 days) | F | 7 | 44%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 38%
| Completed Delayed (>60 days) | F | 3 | 19%
| BEI - Value Task Finishes | F | 0.58
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.59
| BEI - Value Task Finishes - Cumulative | F | 0.58
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.22
| FEI - Value Task Finish - Cumulative | F | 1.22
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 26
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 100
| Baselined to Start - Check | F | 126
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 25
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 101
| Baselined to Finish - Check | F | 126
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 26
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 100
| Current Baseline to Finish & Finished (BL Plan) | F | 25
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 101
| Baselined to Start | F | 44
| Scheduled to Start | F | 44 | 100%
| Started - Scheduled | F | 26 | 59%
| Started - Baseline Comparison | F | 26 | 59%
| BEI - Value Task Starts | F | 0.59
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 43
| Scheduled to Finish | F | 43
| Finished | F | 25
| BEI - Value Task Finishes | F | 0.58
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-07-29
| Started (incl. Future Baseline Starts) - Scheduled | F | 26 | 21%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 26 | 21%
| Started Late (from Baseline) | F | 15
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 25 | 20%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 25 | 20%
| Finished Late | F | 16
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 16 | 64%
| Completed On-Schedule | F | 9 | 36%
| Accelerated | F | 0 | 0%
| Days Variance | F | 540 | 2160%
| Days Early | F | 0 | 0%
| Days Late | F | 540 | 2160%
| Avg Days Early | F | 0
| Avg Days Late | F | 34
| Avg Variance | F | 22
| Actually Finished | F | 25 | 20%
| Took Longer than Planned | F | 6 | 24%
| Took Less Than Planned | F | 5 | 20%
| Completed (w/Baseline Duration) | F | 25 | 20%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 25 | 58%
| Missed Durations | F | 6 | 24%
| Missed Durations & Late Actual Finish | F | 6 | 24%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 16 | 64%
| Completed On-Schedule | F | 9 | 36%
| Accelerated | F | 0 | 0%
| Days Variance | F | 540 | 2160%
| Days Early | F | 0 | 0%
| Days Late | F | 540 | 2160%
| Avg Days Early | F | 0
| Avg Days Late | F | 34
| Avg Variance | F | 22
| Actually Finished | F | 25 | 20%
| Took Longer than Planned | F | 6 | 24%
| Took Less Than Planned | F | 5 | 20%
| Completed (w/Baseline Duration) | F | 25 | 20%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 25 | 58%
| Missed Durations | F | 6 | 24%
| Missed Durations & Late Actual Finish | F | 6 | 24%
| Baselined Tasks | F | 126
| Baselined to Start - TOTAL | F | 126
| Complete Task Starts - Cumulative | F | 26 | 59%
| Incomplete Task Starts - Cumulative (in work) | F | 18 | 41%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 126
| Complete Task Finishes - Cumulative (in work) | F | 25 | 58%
| Incomplete Task Finishes - Cumulative | F | 18 | 58%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.58
| BEI - Total Tasks | F | 43
| BEI - Complete Tasks | F | 25 | 58%
| BEI - Incomplete Tasks | F | 18 | 42%
| BEI - Value Tasks (adjusted) | F | 0.58
| BEI - Complete Tasks (adjusted) | F | 25 | 58%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-07-29
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-07-29
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-07-29
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-07-29
| BEI - Value Tasks | F | 0.58
| BEI - Total Tasks | F | 43
| BEI - Incomplete Tasks | F | 18 | 42%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.58
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-07-29
| Total Activities - DRM | F | 25
| Total Activities - DRM Graph | F | 25
| Status Date | F | 2026-07-29
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | 2027-07-15
| Float to Milestone #3 - 102 | F | 10
| Milestone #4 - 103 | F | 2027-08-04
| Float to Milestone #4 - 103 | F | 10
| Milestone #5 - 104 | F | 2027-09-16
| Float to Milestone #5 - 105 | F | 10
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-07-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-07-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.59
| BEI - Value Task Finishes - Cumulative | F | 0.58
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.22
| FEI - Value Task Finish - Cumulative | F | 1.22
| BEI - Value Tasks | F | 0.58
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.58
| BEI - Complete Tasks | F | 25 | 58%
| BEI - Incomplete Tasks | F | 18 | 42%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 4 | 4%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 4 | 4%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-07-29
| High Float 10% | F | 31 | 31%
| High Float 44d | F | 41 | 41%
| Zero Days Float | F | 37 | 37%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 1 | 3%
| Critical Merge Hotspot | F | 3 | 3%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 8 | 8%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 37 | 90%
| Longest Path (Tasks & Milestones) | F | 37 | 90%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestones (To-Go) | F | 0
| Longest Path (Milestones) | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Normal Tasks (To-Go) | F | 101 | 87%
| Critical Tasks (To-Go) | F | 37 | 37%
| Critical Tasks (In Progress) | F | 0 | 0%
| Zero Days Float | F | 37 | 37%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 3.32
| Time Now | F | 2026-07-29
| Forecast to be Finished | F | 43 | 34%
| Completed On Time | T | 9 | 21%
| Completed Late | F | 16 | 37%
| Not Completed | F | 18 | 42%
| Baseline Finish Compliance | T | 21%
| Forecast to be Started | F | 44 | 35%
| Started On Time | F | 11 | 25%
| Started Late | F | 15 | 34%
| Not Started | F | 18 | 41%
| Baseline Start Compliance | F | 27%
1 | Completed Activities | F | 25
HSD01 | Time Now | F | 2026-07-29
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 18 | 14%
HSD04 | Started Late | F | 15 | 34%
HSD05 | Forecast to be Finished but not Finished yet | T | 18 | 14%
HSD06 | Finished Late | F | 16 | 37%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2027-11-16
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 1 | 100%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.58
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | T | 0.14
SEM06 | BEI Cumulative | T | 0.58
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.22
SEM07 | To Go - Planned Task Starts - Count | T | 100
SEM07 | To Go - BEI - Task Finishes - Count | T | 101
SEM07 | To Go - Baselined Task Starts - Count | T | 100
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.22
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 18
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 82
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 18
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 83
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.22
SEM07 | To Go - Planned Task Starts - Count | T | 100
SEM07 | To Go - BEI - Task Finishes - Count | T | 101
SEM07 | To Go - Baselined Task Starts - Count | T | 100
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.22
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 100
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 18
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 82
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 101
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 18
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 83
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 18
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 82
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 18
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 83
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.22
SEM07 | To Go - Planned Task Starts - Count | T | 100
SEM07 | To Go - BEI - Task Finishes - Count | T | 101
SEM07 | To Go - Baselined Task Starts - Count | T | 100
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.22
SEM07 | TC-BEI | T | 1.22
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.63
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Project5_TAMPERED-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED 2 (8/27/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-08-27
| Specific Task Start | F | 2027-09-24
| Specific Task Finish | F | 2027-10-21
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 5 | 5%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 5 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-08-27
| High Float 44d | F | 44 | 44%
| Zero Days Float | F | 4 | 4%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 41 | 41%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 99 | 79%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 100%
| Normal Tasks (To-Go, In Progress) | F | 2 | 2%
| Critical Path (Tasks & Milestones) | F | 4 | 4%
| Critical Path (Milestones) | F | 0 | 0%
| Critical Path (Normal Tasks) | F | 4 | 100%
| Critical Path (Normal In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 4 | 4%
| Near-Critical (<10 Days Float) | F | 5 | 5%
| CP Logic Density™ | F | 3
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| Status Date | F | 2026-08-27
| Milestone #1 - 100 | F | 2027-09-24
| Float Milestone #1 - 100 | F | 19
| Milestone #2 - 101 | F | 2027-07-16
| Float to Milestone #2 - 101 | F | 36
| Milestone #3 - 102 | F | 2027-08-20
| Float to Milestone #3 - 102 | F | 35
| Milestone #4 - 103 | F | 2027-09-23
| Float to Milestone #4 - 103 | F | 35
| Milestone #5 - 104 | F | 2027-09-24
| Float to Milestone #5 - 104 | F | 55
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 27 | 21%
| Completed Milestones | F | 0
| Completed Tasks | F | 27 | 21%
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 88%
| Summaries (To-Go) | F | 14 | 12%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 4 | 100%
| Longest Path (Normal Tasks) | F | 4 | 100%
| Longest Path (Milestones) | F | 0 | 0%
| Critical Milestones (To-Go) | F | 0 | 0%
| Critical Normal Tasks (To-Go) | F | 4 | 100%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.24
| FEI - Value Task Finish - Cumulative | F | 1.24
| Current Baseline to Start & Started (BL Plan) | F | 29
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 97
| Current Baseline to Finish & Finished (BL Plan) | F | 27
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 99
| Duration Ratio Metric (DRM) | F | 27
| DRM Graph | F | 27
| Baselined to Start | F | 99
| Scheduled to Start | F | 99
| Baselined to Finish | F | 99
| Scheduled to Finish | F | 99
| BEI - Value Activities | F | 0.59
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Critical Path To-Go | F | 4 | 4%
| Status Date | F | 2026-08-27
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 27 | 21%
| Completed Milestones | F | 0
| Completed Tasks | F | 27 | 21%
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 88%
| Summaries (To-Go) | F | 14 | 12%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 4 | 100%
| Longest Path (Normal Tasks) | F | 4 | 100%
| Longest Path (Milestones) | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-08-27
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Summary-to-Task Ratio (To-Go) | F | 1:07 | 0.14
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 4 | 4%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 99 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 10
| Avg. Remaining Duration | F | 9
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 4 | 4%
| Avg. Critical Original Duration | F | 8
| Avg. Critical Remaining Duration | F | 8
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 99 | 79%
| Total Constraints | F | 3 | 3%
| Start No Earlier Than | F | 2 | 2%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 1 | 1%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 5 | 5%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 96 | 97%
| No Constraints | F | 96 | 97%
| Logic Density™ | F | 2.86
| Logic Density™ - Predecessors | F | 1.48
| Logic Density™ - Successors | F | 1.37
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 97 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 99 | 100%
| All Activities w/Successors | F | 94 | 95%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 94 | 95%
| Missing Logic | F | 5 | 5%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 5 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.49
| All Activities w/Predecessors | F | 97 | 100%
| Total # Predecessors | F | 145
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 1 | 1%
| Total # Predecessor Lags | F | 1
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 5
| Hidden Duration (Planned) | F | 1 | 1%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 10 | 10%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 1%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.37
| All Activities w/Successors | F | 94 | 100%
| Activities Missing Successors | F | 5 | 5%
| Total # Successors | F | 136
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 1 | 1%
| Total# of Successor Lags | F | 1
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 11 | 11%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 27 | 21%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 9 | 33%
| Completed Delayed - Tasks & Milestones | F | 18 | 67%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 39
| Avg Finish Variance - Tasks & Milestones | F | 26
| Actually Finished - Tasks | F | 27 | 21%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 9 | 33%
| Completed Delayed - Tasks | F | 18 | 67%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 2 | 2%
| Extended Durations - Tasks | F | 7 | 6%
| Actually Finished - Milestones | F | 0
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 2 | 2%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 2 | 100%
| In-Progress Delayed Finish - Tasks | F | 2 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 85
| Avg Start Variance | F | 85
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 97 | 77%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 97 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 97 | 77%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 97 | 100%
| Planned Delayed Finish - Tasks | F | 97 | 100%
| Scheduled to Start - Milestones | F | 0
| Planned Ahead Start - Milestones | F | 0
| Planned On Schedule Start - Milestones | F | 0
| Planned Delayed Start - Milestones | F | 0
| Planned Delayed Finish - Milestones | F | 0
| Schedule Baseline Activities | F | 126 | 100%
| Scheduled/Baselined to Start | F | 99
| Scheduled/Baselined to Finish | F | 99
| Start/ed | F | 29
| Finish/ed | F | 27
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 10 | 56%
| Completed Delayed (>30 days) | F | 11 | 61%
| SPI(t) | F | 0.91
| Scheduled Activities | F | 126 | 100%
| Scheduled to Start | F | 99 | 79%
| Scheduled to Finish | F | 99 | 79%
| Longest Path - Critical Activities and Milestones | F | 4 | 4%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 4 | 4%
| Critical Tasks (In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| High Float 10% | F | 41 | 41%
| High Float 44d | F | 44 | 44%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 4 | 4%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 4 | 4%
| Critical Tasks (In Progress) | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Logic Density™ | F | 2.81
| CP Logic Density™ | F | 3
| Critical w/Missing Logic | F | 1 | 5%
| Critical w/Hard Constraints | F | 1 | 1%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 1 | 1%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Current Baselined to Start & Started | F | 29
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Current Baselined to Finish & Finished | F | 27
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| Baselined to Start - To Time Now | F | 48 | 38%
| Scheduled to Start - To Time Now | F | 48 | 38%
| Started | F | 29
| Started Late | F | 18
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| BEI - Value Task Starts | F | 0.6
| Baselined to Finish - To Time Now | F | 46 | 37%
| Scheduled to Finish - To Time Now | F | 46 | 37%
| Finished | F | 27
| Finished Late | F | 18
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| BEI - Value Task Finishes | F | 0.59
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.24
| FEI - Value Task Finish - Cumulative | F | 1.24
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 29
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 97
| Baselined to Start - Check | F | 126
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 27
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 99
| Baselined to Finish - Check | F | 126
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 29
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 97
| Current Baseline to Finish & Finished (BL Plan) | F | 27
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 99
| Baselined to Start | F | 48
| Scheduled to Start | F | 48 | 100%
| Started - Scheduled | F | 29 | 60%
| Started - Baseline Comparison | F | 29 | 60%
| BEI - Value Task Starts | F | 0.6
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 46
| Scheduled to Finish | F | 46
| Finished | F | 27
| BEI - Value Task Finishes | F | 0.59
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-08-27
| Started (incl. Future Baseline Starts) - Scheduled | F | 29 | 23%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 29 | 23%
| Started Late (from Baseline) | F | 18
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 27 | 21%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 27 | 21%
| Finished Late | F | 18
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 18 | 67%
| Completed On-Schedule | F | 9 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | 705 | 2611%
| Days Early | F | 0 | 0%
| Days Late | F | 705 | 2611%
| Avg Days Early | F | 0
| Avg Days Late | F | 39
| Avg Variance | F | 26
| Actually Finished | F | 27 | 21%
| Took Longer than Planned | F | 7 | 26%
| Took Less Than Planned | F | 6 | 22%
| Completed (w/Baseline Duration) | F | 27 | 21%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 27 | 59%
| Missed Durations | F | 7 | 26%
| Missed Durations & Late Actual Finish | F | 7 | 26%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 18 | 67%
| Completed On-Schedule | F | 9 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | 705 | 2611%
| Days Early | F | 0 | 0%
| Days Late | F | 705 | 2611%
| Avg Days Early | F | 0
| Avg Days Late | F | 39
| Avg Variance | F | 26
| Actually Finished | F | 27 | 21%
| Took Longer than Planned | F | 7 | 26%
| Took Less Than Planned | F | 6 | 22%
| Completed (w/Baseline Duration) | F | 27 | 21%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 27 | 59%
| Missed Durations | F | 7 | 26%
| Missed Durations & Late Actual Finish | F | 7 | 26%
| Baselined Tasks | F | 126
| Baselined to Start - TOTAL | F | 126
| Complete Task Starts - Cumulative | F | 29 | 60%
| Incomplete Task Starts - Cumulative (in work) | F | 19 | 40%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 126
| Complete Task Finishes - Cumulative (in work) | F | 27 | 59%
| Incomplete Task Finishes - Cumulative | F | 19 | 59%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| BEI - Value Tasks (adjusted) | F | 0.59
| BEI - Complete Tasks (adjusted) | F | 27 | 59%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Incomplete Tasks | F | 19 | 41%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.59
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| Total Activities - DRM | F | 27
| Total Activities - DRM Graph | F | 27
| Status Date | F | 2026-08-27
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | 2027-08-20
| Float to Milestone #3 - 102 | F | 35
| Milestone #4 - 103 | F | 2027-09-09
| Float to Milestone #4 - 103 | F | 35
| Milestone #5 - 104 | F | 2027-10-22
| Float to Milestone #5 - 105 | F | 35
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.24
| FEI - Value Task Finish - Cumulative | F | 1.24
| BEI - Value Tasks | F | 0.59
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 5 | 5%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 5 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-08-27
| High Float 10% | F | 41 | 41%
| High Float 44d | F | 44 | 44%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 4 | 100%
| Longest Path (Tasks & Milestones) | F | 4 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestones (To-Go) | F | 0
| Longest Path (Milestones) | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Normal Tasks (To-Go) | F | 99 | 88%
| Critical Tasks (To-Go) | F | 4 | 4%
| Critical Tasks (In Progress) | F | 0 | 0%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 3
| Time Now | F | 2026-08-27
| Forecast to be Finished | F | 46 | 37%
| Completed On Time | T | 9 | 20%
| Completed Late | F | 18 | 39%
| Not Completed | F | 19 | 41%
| Baseline Finish Compliance | T | 20%
| Forecast to be Started | F | 48 | 38%
| Started On Time | T | 11 | 23%
| Started Late | F | 18 | 38%
| Not Started | F | 19 | 40%
| Baseline Start Compliance | F | 25%
1 | Completed Activities | F | 27
HSD01 | Time Now | F | 2026-08-27
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 19 | 15%
HSD04 | Started Late | F | 18 | 38%
HSD05 | Forecast to be Finished but not Finished yet | T | 19 | 15%
HSD06 | Finished Late | F | 18 | 39%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2028-01-26
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 2 | 100%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.59
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | T | 0.67
SEM06 | BEI Cumulative | T | 0.59
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.24
SEM07 | To Go - Planned Task Starts - Count | T | 97
SEM07 | To Go - BEI - Task Finishes - Count | T | 99
SEM07 | To Go - Baselined Task Starts - Count | T | 97
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 78
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 80
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.24
SEM07 | To Go - Planned Task Starts - Count | T | 97
SEM07 | To Go - BEI - Task Finishes - Count | T | 99
SEM07 | To Go - Baselined Task Starts - Count | T | 97
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 97
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 78
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 99
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 80
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 78
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 80
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.24
SEM07 | To Go - Planned Task Starts - Count | T | 97
SEM07 | To Go - BEI - Task Finishes - Count | T | 99
SEM07 | To Go - Baselined Task Starts - Count | T | 97
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | TC-BEI | T | 1.24
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.61
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## TP4_DataCenter_v1-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v1 2 (1/30/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-01-30
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 1 | 8%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 8%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 8%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-01-30
| High Float 44d | F | 1 | 8%
| Zero Days Float | F | 8 | 62%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 8%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 1 | 8%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 2 | 15%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 13 | 87%
| Milestones (To-Go) | F | 1 | 8%
| Normal Tasks (To-Go) | F | 12 | 92%
| Normal Tasks (To-Go, In Progress) | F | 1 | 8%
| Critical Path (Tasks & Milestones) | F | 8 | 62%
| Critical Path (Milestones) | F | 1 | 13%
| Critical Path (Normal Tasks) | F | 7 | 88%
| Critical Path (Normal In Progress) | F | 1 | 13%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:07
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 8 | 62%
| Near-Critical (<10 Days Float) | F | 9 | 69%
| CP Logic Density™ | F | 3
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 1
| BEI - Total Tasks | F | 1
| BEI - Complete Tasks | F | 1 | 100%
| BEI - Incomplete Tasks | F | 0 | 0%
| Status Date | F | 2026-01-30
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-01-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-01-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-01-30
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 2 | 13%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 1 | 8%
| Total Activities (To-Go) - % of Total | F | 13 | 87%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 13 | 100%
| Milestones (To-Go) | F | 1 | 8%
| Normal Tasks (To-Go) | F | 12 | 92%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 8 | 100%
| Longest Path (Normal Tasks) | F | 7 | 88%
| Longest Path (Milestones) | F | 1 | 13%
| Critical Milestones (To-Go) | F | 1 | 13%
| Critical Normal Tasks (To-Go) | F | 7 | 88%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 2
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 1
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.67
| BEI - Value Task Finishes - Cumulative | F | 1
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Current Baseline to Start & Started (BL Plan) | F | 2
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 11
| Current Baseline to Finish & Finished (BL Plan) | F | 1
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 12
| Duration Ratio Metric (DRM) | F | 1
| DRM Graph | F | 1
| Baselined to Start | F | 12
| Scheduled to Start | F | 12
| Baselined to Finish | F | 12
| Scheduled to Finish | F | 12
| BEI - Value Activities | F | 1
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 13 | 100%
| Critical Path To-Go | F | 8 | 62%
| Status Date | F | 2026-01-30
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 2 | 13%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 1 | 8%
| Total Activities (To-Go) - % of Total | F | 13 | 87%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 13 | 100%
| Milestones (To-Go) | F | 1 | 8%
| Normal Tasks (To-Go) | F | 12 | 92%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 8 | 100%
| Longest Path (Normal Tasks) | F | 7 | 88%
| Longest Path (Milestones) | F | 1 | 13%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-01-30
| Total Activities (To-Go) - % of Total | F | 13 | 87%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 13 | 100%
| Summary-to-Task Ratio (To-Go) | F | N/A | 0
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.08
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:07 | 0.14
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 8 | 62%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 1 | 8%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 13 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 13 | 100%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 16
| Avg. Remaining Duration | F | 16
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 5 | 42%
| Critical Activities (To-Go) | F | 7 | 58%
| Avg. Critical Original Duration | F | 16
| Avg. Critical Remaining Duration | F | 16
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 3 | 25%
| Activities (To-Go) | F | 12 | 92%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 1 | 8%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 13 | 100%
| No Constraints | F | 13 | 100%
| Logic Density™ | F | 2.77
| Logic Density™ - Predecessors | F | 1.46
| Logic Density™ - Successors | F | 1.31
| Summary Links | F | N/A | 0%
| All Activities w/Predecessors | F | 12 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 13 | 100%
| All Activities w/Successors | F | 12 | 92%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 12 | 92%
| Missing Logic | F | 1 | 8%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 8%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.5
| All Activities w/Predecessors | F | 12 | 100%
| Total # Predecessors | F | 18
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 8%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 8%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.31
| All Activities w/Successors | F | 12 | 100%
| Activities Missing Successors | F | 1 | 8%
| Total # Successors | F | 17
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 1 | 8%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 1 | 8%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 2 | 13%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 2 | 100%
| Completed Delayed - Tasks & Milestones | F | 0 | 0%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 0
| Avg Finish Variance - Tasks & Milestones | F | 0
| Actually Finished - Tasks | F | 1 | 8%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 1 | 100%
| Completed Delayed - Tasks | F | 0 | 0%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 0 | 0%
| Actually Finished - Milestones | F | 1 | 50%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 1 | 100%
| Completed Delayed - Milestones | F | 0 | 0%
| Actually Started - Tasks | F | 1 | 8%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 1 | 100%
| In-Progress Started Delayed - Tasks | F | 0 | 0%
| In-Progress Delayed Finish - Tasks | F | 0 | 0%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 0
| Avg Start Variance | F | 0
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 12 | 80%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 12 | 100%
| Planned Delayed Start - Tasks & Milestones | F | 0 | 0%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 11 | 85%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 11 | 100%
| Planned Delayed Start - Tasks | F | 0 | 0%
| Planned Delayed Finish - Tasks | F | 0 | 0%
| Scheduled to Start - Milestones | F | 1 | 50%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 1 | 100%
| Planned Delayed Start - Milestones | F | 0 | 0%
| Planned Delayed Finish - Milestones | F | 0 | 0%
| Schedule Baseline Activities | F | 15 | 100%
| Scheduled/Baselined to Start | F | 13
| Scheduled/Baselined to Finish | F | 13
| Start/ed | F | 3
| Finish/ed | F | 2
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | 0.5
| Scheduled Activities | F | 15 | 100%
| Scheduled to Start | F | 13 | 87%
| Scheduled to Finish | F | 13 | 87%
| Longest Path - Critical Activities and Milestones | F | 8 | 62%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 7 | 58%
| Critical Tasks (In Progress) | F | 1 | 14%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:07 | 0.14
| High Float 10% | F | 2 | 15%
| High Float 44d | F | 1 | 8%
| Zero Days Float | F | 8 | 62%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 8 | 62%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 7 | 58%
| Critical Tasks (In Progress) | F | 1 | 14%
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.08
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:07 | 0.14
| Logic Density™ | F | 2.67
| CP Logic Density™ | F | 3
| Critical w/Missing Logic | F | 1 | 8%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 8 | 62%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 2
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 1
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 2
| Current Baselined to Start & Started | F | 2
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 1
| Current Baselined to Finish & Finished | F | 1
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | 3 | 23%
| Scheduled to Start - To Time Now | F | 3 | 23%
| Started | F | 2
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | 0.67
| Baselined to Finish - To Time Now | F | 1 | 8%
| Scheduled to Finish - To Time Now | F | 1 | 8%
| Finished | F | 1
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | 1
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.67
| BEI - Value Task Finishes - Cumulative | F | 1
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 2
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 11
| Baselined to Start - Check | F | 13
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 1
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 12
| Baselined to Finish - Check | F | 13
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 2
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 11
| Current Baseline to Finish & Finished (BL Plan) | F | 1
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 12
| Baselined to Start | F | 3
| Scheduled to Start | F | 3 | 100%
| Started - Scheduled | F | 2 | 67%
| Started - Baseline Comparison | F | 2 | 67%
| BEI - Value Task Starts | F | 0.67
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 1
| Scheduled to Finish | F | 1
| Finished | F | 1
| BEI - Value Task Finishes | F | 1
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-01-30
| Started (incl. Future Baseline Starts) - Scheduled | F | 2 | 15%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 2 | 15%
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 1 | 8%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 1 | 8%
| Finished Late | F | N/A
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 0 | 0%
| Completed On-Schedule | F | 1 | 100%
| Accelerated | F | 0 | 0%
| Days Variance | F | 0 | 0%
| Days Early | F | 0 | 0%
| Days Late | F | 0 | 0%
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 1 | 7%
| Took Longer than Planned | F | 0 | 0%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 1 | 8%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 1 | 100%
| Missed Durations | F | 0 | 0%
| Missed Durations & Late Actual Finish | F | 0 | 0%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 0 | 0%
| Completed On-Schedule | F | 1 | 100%
| Accelerated | F | 0 | 0%
| Days Variance | F | 0 | 0%
| Days Early | F | 0 | 0%
| Days Late | F | 0 | 0%
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 1 | 7%
| Took Longer than Planned | F | 0 | 0%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 1 | 8%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 1 | 100%
| Missed Durations | F | 0 | 0%
| Missed Durations & Late Actual Finish | F | 0 | 0%
| Baselined Tasks | F | 13
| Baselined to Start - TOTAL | F | 13
| Complete Task Starts - Cumulative | F | 2 | 67%
| Incomplete Task Starts - Cumulative (in work) | F | 1 | 33%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 13
| Complete Task Finishes - Cumulative (in work) | F | 1 | 100%
| Incomplete Task Finishes - Cumulative | F | 0 | 100%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 1
| BEI - Total Tasks | F | 1
| BEI - Complete Tasks | F | 1 | 100%
| BEI - Incomplete Tasks | F | 0 | 0%
| BEI - Value Tasks (adjusted) | F | 1
| BEI - Complete Tasks (adjusted) | F | 1 | 100%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-01-30
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| BEI - Value Milestones (adjusted) | F | 1
| BEI - Complete Milestones (adjusted) | F | 1 | 100%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-01-30
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-01-30
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-01-30
| BEI - Value Tasks | F | 1
| BEI - Total Tasks | F | 1
| BEI - Incomplete Tasks | F | 0 | 0%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 100%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 1
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 1
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-01-30
| Total Activities - DRM | F | 1
| Total Activities - DRM Graph | F | 1
| Status Date | F | 2026-01-30
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-01-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-01-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.67
| BEI - Value Task Finishes - Cumulative | F | 1
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| BEI - Value Tasks | F | 1
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 1
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 1
| BEI - Complete Tasks | F | 1 | 100%
| BEI - Incomplete Tasks | F | 0 | 0%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 1 | 8%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 8%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 8%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-01-30
| High Float 10% | F | 2 | 15%
| High Float 44d | F | 1 | 8%
| Zero Days Float | F | 8 | 62%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 8%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 1 | 8%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 7 | 88%
| Longest Path (Tasks & Milestones) | F | 8 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:07 | 0.14
| Critical Milestones (To-Go) | F | 1 | 100%
| Longest Path (Milestones) | F | 1 | 13%
| Normal Tasks | F | 13 | 87%
| Normal Tasks (To-Go) | F | 12 | 92%
| Critical Tasks (To-Go) | F | 7 | 58%
| Critical Tasks (In Progress) | F | 1 | 14%
| Zero Days Float | F | 8 | 62%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 3
| Time Now | F | 2026-01-30
| Forecast to be Finished | F | 1 | 8%
| Completed On Time | F | 1 | 100%
| Completed Late | F | 0 | 0%
| Not Completed | F | 0 | 0%
| Baseline Finish Compliance | F | 100%
| Forecast to be Started | F | 3 | 23%
| Started On Time | F | 3 | 100%
| Started Late | F | 0 | 0%
| Not Started | F | 1 | 33%
| Baseline Start Compliance | F | 100%
1 | Completed Activities | F | 1
HSD01 | Time Now | F | 2026-01-30
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 1 | 8%
HSD04 | Started Late | F | 0 | 0%
HSD05 | Forecast to be Finished but not Finished yet | F | 0 | 0%
HSD06 | Finished Late | F | 0 | 0%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-06-05
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 0 | 0%
SEM02 | BRI Current | F | 1
SEM03 | BRI Cumulative | F | 1
SEM04 | BPI Current | F | 1
SEM05 | BEI Current | F | 1
SEM06 | BEI Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 10
SEM07 | To Go - BEI - Task Finishes - Count | T | 12
SEM07 | To Go - Baselined Task Starts - Count | T | 10
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 10
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 12
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 10
SEM07 | To Go - BEI - Task Finishes - Count | T | 12
SEM07 | To Go - Baselined Task Starts - Count | T | 10
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 10
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 10
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 12
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 12
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 10
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 12
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 10
SEM07 | To Go - BEI - Task Finishes - Count | T | 12
SEM07 | To Go - Baselined Task Starts - Count | T | 10
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | TC-BEI | F | 1
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | 0
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## TP4_DataCenter_v2-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v2 2 (2/27/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-02-27
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 9%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 9%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-02-27
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 64%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 13%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 1 | 9%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 11 | 73%
| Milestones (To-Go) | F | 1 | 9%
| Normal Tasks (To-Go) | F | 10 | 91%
| Normal Tasks (To-Go, In Progress) | F | 3 | 27%
| Critical Path (Tasks & Milestones) | F | 7 | 64%
| Critical Path (Milestones) | F | 1 | 14%
| Critical Path (Normal Tasks) | F | 6 | 86%
| Critical Path (Normal In Progress) | F | 1 | 14%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 7 | 64%
| Near-Critical (<10 Days Float) | F | 8 | 73%
| CP Logic Density™ | F | 2.86
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.75
| BEI - Total Tasks | F | 4
| BEI - Complete Tasks | F | 3 | 75%
| BEI - Incomplete Tasks | F | 1 | 25%
| Status Date | F | 2026-02-27
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-02-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-02-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-02-27
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 4 | 27%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 3 | 23%
| Total Activities (To-Go) - % of Total | F | 11 | 73%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 11 | 100%
| Milestones (To-Go) | F | 1 | 9%
| Normal Tasks (To-Go) | F | 10 | 91%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Milestones) | F | 1 | 14%
| Critical Milestones (To-Go) | F | 1 | 14%
| Critical Normal Tasks (To-Go) | F | 6 | 86%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 6
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 3
| Started Delayed (<=30 days) | F | 1 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | 1
| BEI - Value Task Finishes - Cumulative | F | 0.75
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1.1
| Current Baseline to Start & Started (BL Plan) | F | 6
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 7
| Current Baseline to Finish & Finished (BL Plan) | F | 3
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 10
| Duration Ratio Metric (DRM) | F | 3
| DRM Graph | F | 3
| Baselined to Start | F | 10
| Scheduled to Start | F | 10
| Baselined to Finish | F | 10
| Scheduled to Finish | F | 10
| BEI - Value Activities | F | 0.8
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 11 | 100%
| Critical Path To-Go | F | 7 | 64%
| Status Date | F | 2026-02-27
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 4 | 27%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 3 | 23%
| Total Activities (To-Go) - % of Total | F | 11 | 73%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 11 | 100%
| Milestones (To-Go) | F | 1 | 9%
| Normal Tasks (To-Go) | F | 10 | 91%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Milestones) | F | 1 | 14%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-02-27
| Total Activities (To-Go) - % of Total | F | 11 | 73%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 11 | 100%
| Summary-to-Task Ratio (To-Go) | F | N/A | 0
| Milestone-to-Task Ratio (To-Go) | F | 1:10 | 0.1
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 7 | 64%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 11 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 11 | 100%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 17
| Avg. Remaining Duration | F | 16
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 5 | 50%
| Critical Activities (To-Go) | F | 6 | 60%
| Avg. Critical Original Duration | F | 18
| Avg. Critical Remaining Duration | F | 17
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 3 | 30%
| Activities (To-Go) | F | 10 | 77%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 1 | 9%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 11 | 100%
| No Constraints | F | 11 | 100%
| Logic Density™ | F | 2.73
| Logic Density™ - Predecessors | F | 1.55
| Logic Density™ - Successors | F | 1.18
| Summary Links | F | N/A | 0%
| All Activities w/Predecessors | F | 8 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 11 | 100%
| All Activities w/Successors | F | 10 | 91%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 10 | 91%
| Missing Logic | F | 1 | 9%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 9%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.75
| All Activities w/Predecessors | F | 8 | 100%
| Total # Predecessors | F | 14
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 13%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 13%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.18
| All Activities w/Successors | F | 10 | 100%
| Activities Missing Successors | F | 1 | 9%
| Total # Successors | F | 13
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 4 | 27%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 4 | 100%
| Completed Delayed - Tasks & Milestones | F | 0 | 0%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 0
| Avg Finish Variance - Tasks & Milestones | F | 0
| Actually Finished - Tasks | F | 3 | 23%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 3 | 100%
| Completed Delayed - Tasks | F | 0 | 0%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 0 | 0%
| Actually Finished - Milestones | F | 1 | 50%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 1 | 100%
| Completed Delayed - Milestones | F | 0 | 0%
| Actually Started - Tasks | F | 3 | 23%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 2 | 67%
| In-Progress Started Delayed - Tasks | F | 1 | 33%
| In-Progress Delayed Finish - Tasks | F | 1 | 33%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 2
| Avg Start Variance | F | 2
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 8 | 53%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 8 | 100%
| Planned Delayed Start - Tasks & Milestones | F | 0 | 0%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 7 | 54%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 7 | 100%
| Planned Delayed Start - Tasks | F | 0 | 0%
| Planned Delayed Finish - Tasks | F | 0 | 0%
| Scheduled to Start - Milestones | F | 1 | 50%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 1 | 100%
| Planned Delayed Start - Milestones | F | 0 | 0%
| Planned Delayed Finish - Milestones | F | 0 | 0%
| Schedule Baseline Activities | F | 15 | 100%
| Scheduled/Baselined to Start | F | 11
| Scheduled/Baselined to Finish | F | 11
| Start/ed | F | 7
| Finish/ed | F | 4
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 0 | 0%
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | 0.5
| Scheduled Activities | F | 15 | 100%
| Scheduled to Start | F | 11 | 73%
| Scheduled to Finish | F | 11 | 73%
| Longest Path - Critical Activities and Milestones | F | 7 | 64%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 6 | 60%
| Critical Tasks (In Progress) | F | 1 | 17%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| High Float 10% | F | 1 | 9%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 64%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 7 | 64%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 6 | 60%
| Critical Tasks (In Progress) | F | 1 | 17%
| Milestone-to-Task Ratio (To-Go) | F | 1:10 | 0.1
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Logic Density™ | F | 2.67
| CP Logic Density™ | F | 2.86
| Critical w/Missing Logic | F | 1 | 9%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 7 | 64%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 6
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 3
| Started Delayed (<=30 days) | F | 1 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 6
| Current Baselined to Start & Started | F | 6
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 3
| Current Baselined to Finish & Finished | F | 3
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 1 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | 6 | 46%
| Scheduled to Start - To Time Now | F | 6 | 46%
| Started | F | 6
| Started Late | F | 1
| Started Delayed (<=30 days) | F | 1 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 1
| Baselined to Finish - To Time Now | F | 4 | 31%
| Scheduled to Finish - To Time Now | F | 4 | 31%
| Finished | F | 3
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | 0.75
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 1
| BEI - Value Task Finishes - Cumulative | F | 0.75
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1.1
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 6
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 7
| Baselined to Start - Check | F | 13
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 3
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 10
| Baselined to Finish - Check | F | 13
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 6
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 7
| Current Baseline to Finish & Finished (BL Plan) | F | 3
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 10
| Baselined to Start | F | 6
| Scheduled to Start | F | 6 | 100%
| Started - Scheduled | F | 6 | 100%
| Started - Baseline Comparison | F | 6 | 100%
| BEI - Value Task Starts | F | 1
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 4
| Scheduled to Finish | F | 4
| Finished | F | 3
| BEI - Value Task Finishes | F | 0.75
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-02-27
| Started (incl. Future Baseline Starts) - Scheduled | F | 6 | 46%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 6 | 46%
| Started Late (from Baseline) | F | 1
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 3 | 23%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 3 | 23%
| Finished Late | F | N/A
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 0 | 0%
| Completed On-Schedule | F | 3 | 100%
| Accelerated | F | 0 | 0%
| Days Variance | F | 0 | 0%
| Days Early | F | 0 | 0%
| Days Late | F | 0 | 0%
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 3 | 20%
| Took Longer than Planned | F | 0 | 0%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 3 | 23%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 3 | 75%
| Missed Durations | F | 0 | 0%
| Missed Durations & Late Actual Finish | F | 0 | 0%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 0 | 0%
| Completed On-Schedule | F | 3 | 100%
| Accelerated | F | 0 | 0%
| Days Variance | F | 0 | 0%
| Days Early | F | 0 | 0%
| Days Late | F | 0 | 0%
| Avg Days Early | F | 0
| Avg Days Late | F | 0
| Avg Variance | F | 0
| Actually Finished | F | 3 | 20%
| Took Longer than Planned | F | 0 | 0%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 3 | 23%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 3 | 75%
| Missed Durations | F | 0 | 0%
| Missed Durations & Late Actual Finish | F | 0 | 0%
| Baselined Tasks | F | 13
| Baselined to Start - TOTAL | F | 13
| Complete Task Starts - Cumulative | F | 6 | 100%
| Incomplete Task Starts - Cumulative (in work) | F | 0 | 0%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 13
| Complete Task Finishes - Cumulative (in work) | F | 3 | 75%
| Incomplete Task Finishes - Cumulative | F | 1 | 75%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.75
| BEI - Total Tasks | F | 4
| BEI - Complete Tasks | F | 3 | 75%
| BEI - Incomplete Tasks | F | 1 | 25%
| BEI - Value Tasks (adjusted) | F | 0.75
| BEI - Complete Tasks (adjusted) | F | 3 | 75%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-02-27
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| BEI - Value Milestones (adjusted) | F | 1
| BEI - Complete Milestones (adjusted) | F | 1 | 100%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-02-27
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-02-27
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-02-27
| BEI - Value Tasks | F | 0.75
| BEI - Total Tasks | F | 4
| BEI - Incomplete Tasks | F | 1 | 25%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 100%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.75
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 1
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-02-27
| Total Activities - DRM | F | 3
| Total Activities - DRM Graph | F | 3
| Status Date | F | 2026-02-27
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-02-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-02-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 1
| BEI - Value Task Finishes - Cumulative | F | 0.75
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1.1
| BEI - Value Tasks | F | 0.75
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 1
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.75
| BEI - Complete Tasks | F | 3 | 75%
| BEI - Incomplete Tasks | F | 1 | 25%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 9%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 9%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-02-27
| High Float 10% | F | 1 | 9%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 64%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 13%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Critical Milestones (To-Go) | F | 1 | 100%
| Longest Path (Milestones) | F | 1 | 14%
| Normal Tasks | F | 13 | 87%
| Normal Tasks (To-Go) | F | 10 | 91%
| Critical Tasks (To-Go) | F | 6 | 60%
| Critical Tasks (In Progress) | F | 1 | 17%
| Zero Days Float | F | 7 | 64%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.86
| Time Now | F | 2026-02-27
| Forecast to be Finished | F | 3 | 23%
| Completed On Time | F | 2 | 67%
| Completed Late | F | 0 | 0%
| Not Completed | F | 1 | 33%
| Baseline Finish Compliance | F | 67%
| Forecast to be Started | F | 6 | 46%
| Started On Time | F | 5 | 83%
| Started Late | F | 1 | 17%
| Not Started | F | 0 | 0%
| Baseline Start Compliance | F | 100%
1 | Completed Activities | F | 3
HSD01 | Time Now | F | 2026-02-27
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | 0 | 0%
HSD04 | Started Late | F | 1 | 17%
HSD05 | Forecast to be Finished but not Finished yet | T | 1 | 8%
HSD06 | Finished Late | F | 0 | 0%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-06-05
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 0 | 0%
SEM02 | BRI Current | F | 0.67
SEM03 | BRI Cumulative | F | 0.75
SEM04 | BPI Current | F | 0.67
SEM05 | BEI Current | T | 0.67
SEM06 | BEI Cumulative | T | 0.75
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.1
SEM07 | To Go - Planned Task Starts - Count | T | 7
SEM07 | To Go - BEI - Task Finishes - Count | T | 11
SEM07 | To Go - Baselined Task Starts - Count | T | 7
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 7
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 9
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.1
SEM07 | To Go - Planned Task Starts - Count | T | 7
SEM07 | To Go - BEI - Task Finishes - Count | T | 11
SEM07 | To Go - Baselined Task Starts - Count | T | 7
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 7
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 7
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 9
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 9
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 7
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 9
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.1
SEM07 | To Go - Planned Task Starts - Count | T | 7
SEM07 | To Go - BEI - Task Finishes - Count | T | 11
SEM07 | To Go - Baselined Task Starts - Count | T | 7
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | TC-BEI | T | 1.1
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.29
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## TP4_DataCenter_v3-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v3 2 (3/31/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-03-31
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 44%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-03-31
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 14%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 1 | 11%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 9 | 60%
| Milestones (To-Go) | F | 1 | 11%
| Normal Tasks (To-Go) | F | 8 | 89%
| Normal Tasks (To-Go, In Progress) | F | 2 | 22%
| Critical Path (Tasks & Milestones) | F | 7 | 78%
| Critical Path (Milestones) | F | 1 | 14%
| Critical Path (Normal Tasks) | F | 6 | 86%
| Critical Path (Normal In Progress) | F | 1 | 14%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Near-Critical (<10 Days Float) | F | 7 | 78%
| CP Logic Density™ | F | 2.86
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.71
| BEI - Total Tasks | F | 7
| BEI - Complete Tasks | F | 5 | 71%
| BEI - Incomplete Tasks | F | 2 | 29%
| Status Date | F | 2026-03-31
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-03-31
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 6 | 40%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 5 | 38%
| Total Activities (To-Go) - % of Total | F | 9 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Milestones (To-Go) | F | 1 | 11%
| Normal Tasks (To-Go) | F | 8 | 89%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Milestones) | F | 1 | 14%
| Critical Milestones (To-Go) | F | 1 | 14%
| Critical Normal Tasks (To-Go) | F | 6 | 86%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 7
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 5
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.78
| BEI - Value Task Finishes - Cumulative | F | 0.71
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Current Baseline to Start & Started (BL Plan) | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 6
| Current Baseline to Finish & Finished (BL Plan) | F | 5
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 8
| Duration Ratio Metric (DRM) | F | 5
| DRM Graph | F | 5
| Baselined to Start | F | 8
| Scheduled to Start | F | 8
| Baselined to Finish | F | 8
| Scheduled to Finish | F | 8
| BEI - Value Activities | F | 0.75
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Critical Path To-Go | F | 7 | 78%
| Status Date | F | 2026-03-31
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 6 | 40%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 5 | 38%
| Total Activities (To-Go) - % of Total | F | 9 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Milestones (To-Go) | F | 1 | 11%
| Normal Tasks (To-Go) | F | 8 | 89%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Milestones) | F | 1 | 14%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-03-31
| Total Activities (To-Go) - % of Total | F | 9 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Summary-to-Task Ratio (To-Go) | F | N/A | 0
| Milestone-to-Task Ratio (To-Go) | F | 1:08 | 0.13
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 7 | 78%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 44%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 9 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 18
| Avg. Remaining Duration | F | 16
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 4 | 50%
| Critical Activities (To-Go) | F | 6 | 75%
| Avg. Critical Original Duration | F | 18
| Avg. Critical Remaining Duration | F | 17
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 3 | 38%
| Activities (To-Go) | F | 8 | 62%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 1 | 11%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 9 | 100%
| No Constraints | F | 9 | 100%
| Logic Density™ | F | 2.78
| Logic Density™ - Predecessors | F | 1.67
| Logic Density™ - Successors | F | 1.11
| Summary Links | F | N/A | 0%
| All Activities w/Predecessors | F | 7 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 9 | 100%
| All Activities w/Successors | F | 8 | 89%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 8 | 89%
| Missing Logic | F | 1 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.86
| All Activities w/Predecessors | F | 7 | 100%
| Total # Predecessors | F | 13
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 14%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 14%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.11
| All Activities w/Successors | F | 8 | 100%
| Activities Missing Successors | F | 1 | 11%
| Total # Successors | F | 10
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 6 | 40%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 4 | 67%
| Completed Delayed - Tasks & Milestones | F | 2 | 33%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 4
| Avg Finish Variance - Tasks & Milestones | F | 1
| Actually Finished - Tasks | F | 5 | 38%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 3 | 60%
| Completed Delayed - Tasks | F | 2 | 40%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 1 | 8%
| Actually Finished - Milestones | F | 1 | 50%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 1 | 100%
| Completed Delayed - Milestones | F | 0 | 0%
| Actually Started - Tasks | F | 2 | 15%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 1 | 50%
| In-Progress Started Delayed - Tasks | F | 1 | 50%
| In-Progress Delayed Finish - Tasks | F | 1 | 50%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 4
| Avg Start Variance | F | 4
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 7 | 47%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 6 | 86%
| Planned Delayed Start - Tasks & Milestones | F | 1 | 14%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 6 | 46%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 5 | 83%
| Planned Delayed Start - Tasks | F | 1 | 17%
| Planned Delayed Finish - Tasks | F | 1 | 17%
| Scheduled to Start - Milestones | F | 1 | 50%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 1 | 100%
| Planned Delayed Start - Milestones | F | 0 | 0%
| Planned Delayed Finish - Milestones | F | 0 | 0%
| Schedule Baseline Activities | F | 15 | 100%
| Scheduled/Baselined to Start | F | 9
| Scheduled/Baselined to Finish | F | 9
| Start/ed | F | 8
| Finish/ed | F | 6
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 0 | 0%
| Completed Delayed (>30 days) | F | 0 | 0%
| SPI(t) | F | 0.67
| Scheduled Activities | F | 15 | 100%
| Scheduled to Start | F | 9 | 60%
| Scheduled to Finish | F | 9 | 60%
| Longest Path - Critical Activities and Milestones | F | 7 | 78%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 6 | 75%
| Critical Tasks (In Progress) | F | 1 | 17%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| High Float 10% | F | 1 | 11%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 7 | 78%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 6 | 75%
| Critical Tasks (In Progress) | F | 1 | 17%
| Milestone-to-Task Ratio (To-Go) | F | 1:08 | 0.13
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Logic Density™ | F | 2.67
| CP Logic Density™ | F | 2.86
| Critical w/Missing Logic | F | 1 | 11%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 7
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 5
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 7
| Current Baselined to Start & Started | F | 7
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 5
| Current Baselined to Finish & Finished | F | 5
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 9 | 69%
| Scheduled to Start - To Time Now | F | 9 | 69%
| Started | F | 7
| Started Late | F | 2
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 0.78
| Baselined to Finish - To Time Now | F | 7 | 54%
| Scheduled to Finish - To Time Now | F | 7 | 54%
| Finished | F | 5
| Finished Late | F | 2
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.71
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.78
| BEI - Value Task Finishes - Cumulative | F | 0.71
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 7
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 6
| Baselined to Start - Check | F | 13
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 5
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 8
| Baselined to Finish - Check | F | 13
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 6
| Current Baseline to Finish & Finished (BL Plan) | F | 5
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 8
| Baselined to Start | F | 9
| Scheduled to Start | F | 9 | 100%
| Started - Scheduled | F | 7 | 78%
| Started - Baseline Comparison | F | 7 | 78%
| BEI - Value Task Starts | F | 0.78
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 7
| Scheduled to Finish | F | 7
| Finished | F | 5
| BEI - Value Task Finishes | F | 0.71
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-03-31
| Started (incl. Future Baseline Starts) - Scheduled | F | 7 | 54%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 7 | 54%
| Started Late (from Baseline) | F | 2
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 5 | 38%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 5 | 38%
| Finished Late | F | 2
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 2 | 40%
| Completed On-Schedule | F | 3 | 60%
| Accelerated | F | 0 | 0%
| Days Variance | F | 8 | 160%
| Days Early | F | 0 | 0%
| Days Late | F | 8 | 160%
| Avg Days Early | F | 0
| Avg Days Late | F | 4
| Avg Variance | F | 2
| Actually Finished | F | 5 | 33%
| Took Longer than Planned | F | 2 | 33%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 5 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 5 | 71%
| Missed Durations | F | 1 | 20%
| Missed Durations & Late Actual Finish | F | 1 | 20%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 2 | 40%
| Completed On-Schedule | F | 3 | 60%
| Accelerated | F | 0 | 0%
| Days Variance | F | 8 | 160%
| Days Early | F | 0 | 0%
| Days Late | F | 8 | 160%
| Avg Days Early | F | 0
| Avg Days Late | F | 4
| Avg Variance | F | 2
| Actually Finished | F | 5 | 33%
| Took Longer than Planned | F | 2 | 33%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 5 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 5 | 71%
| Missed Durations | F | 1 | 20%
| Missed Durations & Late Actual Finish | F | 1 | 20%
| Baselined Tasks | F | 13
| Baselined to Start - TOTAL | F | 13
| Complete Task Starts - Cumulative | F | 7 | 78%
| Incomplete Task Starts - Cumulative (in work) | F | 2 | 22%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 13
| Complete Task Finishes - Cumulative (in work) | F | 5 | 71%
| Incomplete Task Finishes - Cumulative | F | 2 | 71%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.71
| BEI - Total Tasks | F | 7
| BEI - Complete Tasks | F | 5 | 71%
| BEI - Incomplete Tasks | F | 2 | 29%
| BEI - Value Tasks (adjusted) | F | 0.71
| BEI - Complete Tasks (adjusted) | F | 5 | 71%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| BEI - Value Milestones (adjusted) | F | 1
| BEI - Complete Milestones (adjusted) | F | 1 | 100%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| BEI - Value Tasks | F | 0.71
| BEI - Total Tasks | F | 7
| BEI - Incomplete Tasks | F | 2 | 29%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 100%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.71
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 1
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| Total Activities - DRM | F | 5
| Total Activities - DRM Graph | F | 5
| Status Date | F | 2026-03-31
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.78
| BEI - Value Task Finishes - Cumulative | F | 0.71
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| BEI - Value Tasks | F | 0.71
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 1
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.71
| BEI - Complete Tasks | F | 5 | 71%
| BEI - Incomplete Tasks | F | 2 | 29%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 44%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-03-31
| High Float 10% | F | 1 | 11%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 14%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Critical Milestones (To-Go) | F | 1 | 100%
| Longest Path (Milestones) | F | 1 | 14%
| Normal Tasks | F | 13 | 87%
| Normal Tasks (To-Go) | F | 8 | 89%
| Critical Tasks (To-Go) | F | 6 | 75%
| Critical Tasks (In Progress) | F | 1 | 17%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.86
| Time Now | F | 2026-03-31
| Forecast to be Finished | F | 7 | 54%
| Completed On Time | F | 4 | 57%
| Completed Late | F | 3 | 43%
| Not Completed | F | 2 | 29%
| Baseline Finish Compliance | F | 57%
| Forecast to be Started | F | 9 | 69%
| Started On Time | F | 6 | 67%
| Started Late | F | 3 | 33%
| Not Started | F | 2 | 22%
| Baseline Start Compliance | F | 100%
1 | Completed Activities | F | 5
HSD01 | Time Now | F | 2026-03-31
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 2 | 15%
HSD04 | Started Late | F | 3 | 33%
HSD05 | Forecast to be Finished but not Finished yet | T | 2 | 15%
HSD06 | Finished Late | F | 3 | 43%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-06-05
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 0 | 0%
SEM02 | BRI Current | F | 0.67
SEM03 | BRI Cumulative | F | 0.71
SEM04 | BPI Current | F | 0.67
SEM05 | BEI Current | T | 0.67
SEM06 | BEI Cumulative | T | 0.71
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 4
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 4
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 6
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 4
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Workoff Burden - Starts To-Go (Total) | F | 4
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | 4
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 6
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 6
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 4
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 6
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 4
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | TC-BEI | F | 1
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.25
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## TP4_DataCenter_v4-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v4 2 (4/30/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-04-30
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 57%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 14%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 14%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-04-30
| High Float 44d | F | 1 | 14%
| Zero Days Float | F | 5 | 71%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 20%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 2 | 29%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 7 | 47%
| Milestones (To-Go) | F | 1 | 14%
| Normal Tasks (To-Go) | F | 6 | 86%
| Normal Tasks (To-Go, In Progress) | F | 2 | 29%
| Critical Path (Tasks & Milestones) | F | 5 | 71%
| Critical Path (Milestones) | F | 1 | 20%
| Critical Path (Normal Tasks) | F | 4 | 80%
| Critical Path (Normal In Progress) | F | 2 | 40%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 5 | 71%
| Near-Critical (<10 Days Float) | F | 5 | 71%
| CP Logic Density™ | F | 2.6
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.78
| BEI - Total Tasks | F | 9
| BEI - Complete Tasks | F | 7 | 78%
| BEI - Incomplete Tasks | F | 2 | 22%
| Status Date | F | 2026-04-30
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-04-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-04-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-04-30
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 8 | 53%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 7 | 54%
| Total Activities (To-Go) - % of Total | F | 7 | 47%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Milestones (To-Go) | F | 1 | 14%
| Normal Tasks (To-Go) | F | 6 | 86%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 5 | 100%
| Longest Path (Normal Tasks) | F | 4 | 80%
| Longest Path (Milestones) | F | 1 | 20%
| Critical Milestones (To-Go) | F | 1 | 20%
| Critical Normal Tasks (To-Go) | F | 4 | 80%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 9
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 7
| Started Delayed (<=30 days) | F | 4 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.82
| BEI - Value Task Finishes - Cumulative | F | 0.78
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Current Baseline to Start & Started (BL Plan) | F | 9
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 4
| Current Baseline to Finish & Finished (BL Plan) | F | 7
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 6
| Duration Ratio Metric (DRM) | F | 7
| DRM Graph | F | 7
| Baselined to Start | F | 6
| Scheduled to Start | F | 6
| Baselined to Finish | F | 6
| Scheduled to Finish | F | 6
| BEI - Value Activities | F | 0.8
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Critical Path To-Go | F | 5 | 71%
| Status Date | F | 2026-04-30
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 8 | 53%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 7 | 54%
| Total Activities (To-Go) - % of Total | F | 7 | 47%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Milestones (To-Go) | F | 1 | 14%
| Normal Tasks (To-Go) | F | 6 | 86%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 5 | 100%
| Longest Path (Normal Tasks) | F | 4 | 80%
| Longest Path (Milestones) | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-04-30
| Total Activities (To-Go) - % of Total | F | 7 | 47%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Summary-to-Task Ratio (To-Go) | F | N/A | 0
| Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 5 | 71%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 57%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 7 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 17
| Avg. Remaining Duration | F | 16
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 3 | 50%
| Critical Activities (To-Go) | F | 4 | 67%
| Avg. Critical Original Duration | F | 16
| Avg. Critical Remaining Duration | F | 15
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 2 | 33%
| Activities (To-Go) | F | 6 | 46%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 1 | 14%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 7 | 100%
| No Constraints | F | 7 | 100%
| Logic Density™ | F | 2.57
| Logic Density™ - Predecessors | F | 1.71
| Logic Density™ - Successors | F | 0.86
| Summary Links | F | N/A | 0%
| All Activities w/Predecessors | F | 5 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 7 | 100%
| All Activities w/Successors | F | 6 | 86%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 6 | 86%
| Missing Logic | F | 1 | 14%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 14%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.8
| All Activities w/Predecessors | F | 5 | 100%
| Total # Predecessors | F | 9
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 20%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 20%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 0.86
| All Activities w/Successors | F | 6 | 100%
| Activities Missing Successors | F | 1 | 14%
| Total # Successors | F | 6
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 8 | 53%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 4 | 50%
| Completed Delayed - Tasks & Milestones | F | 4 | 50%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 13
| Avg Finish Variance - Tasks & Milestones | F | 6
| Actually Finished - Tasks | F | 7 | 54%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 3 | 43%
| Completed Delayed - Tasks | F | 4 | 57%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 2 | 15%
| Actually Finished - Milestones | F | 1 | 50%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 1 | 100%
| Completed Delayed - Milestones | F | 0 | 0%
| Actually Started - Tasks | F | 2 | 15%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 2 | 100%
| In-Progress Delayed Finish - Tasks | F | 2 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 21
| Avg Start Variance | F | 21
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 5 | 33%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 1 | 20%
| Planned Delayed Start - Tasks & Milestones | F | 4 | 80%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 4 | 31%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 1 | 25%
| Planned Delayed Start - Tasks | F | 3 | 75%
| Planned Delayed Finish - Tasks | F | 3 | 75%
| Scheduled to Start - Milestones | F | 1 | 50%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 1 | 100%
| Planned Delayed Finish - Milestones | F | 1 | 100%
| Schedule Baseline Activities | F | 15 | 100%
| Scheduled/Baselined to Start | F | 7
| Scheduled/Baselined to Finish | F | 7
| Start/ed | F | 10
| Finish/ed | F | 8
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 0 | 0%
| Completed Delayed (>30 days) | F | 0 | 0%
| SPI(t) | F | 0.7
| Scheduled Activities | F | 15 | 100%
| Scheduled to Start | F | 7 | 47%
| Scheduled to Finish | F | 7 | 47%
| Longest Path - Critical Activities and Milestones | F | 5 | 71%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 4 | 67%
| Critical Tasks (In Progress) | F | 2 | 50%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| High Float 10% | F | 2 | 29%
| High Float 44d | F | 1 | 14%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 5 | 71%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 4 | 67%
| Critical Tasks (In Progress) | F | 2 | 50%
| Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| Logic Density™ | F | 2.67
| CP Logic Density™ | F | 2.6
| Critical w/Missing Logic | F | 1 | 14%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 9
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 7
| Started Delayed (<=30 days) | F | 4 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 9
| Current Baselined to Start & Started | F | 9
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 7
| Current Baselined to Finish & Finished | F | 7
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 4 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 11 | 85%
| Scheduled to Start - To Time Now | F | 11 | 85%
| Started | F | 9
| Started Late | F | 4
| Started Delayed (<=30 days) | F | 4 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 0.82
| Baselined to Finish - To Time Now | F | 9 | 69%
| Scheduled to Finish - To Time Now | F | 9 | 69%
| Finished | F | 7
| Finished Late | F | 4
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.78
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.82
| BEI - Value Task Finishes - Cumulative | F | 0.78
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 9
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 4
| Baselined to Start - Check | F | 13
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 7
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 6
| Baselined to Finish - Check | F | 13
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 9
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 4
| Current Baseline to Finish & Finished (BL Plan) | F | 7
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 6
| Baselined to Start | F | 11
| Scheduled to Start | F | 11 | 100%
| Started - Scheduled | F | 9 | 82%
| Started - Baseline Comparison | F | 9 | 82%
| BEI - Value Task Starts | F | 0.82
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 9
| Scheduled to Finish | F | 9
| Finished | F | 7
| BEI - Value Task Finishes | F | 0.78
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-04-30
| Started (incl. Future Baseline Starts) - Scheduled | F | 9 | 69%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 9 | 69%
| Started Late (from Baseline) | F | 4
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 7 | 54%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 7 | 54%
| Finished Late | F | 4
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 4 | 57%
| Completed On-Schedule | F | 3 | 43%
| Accelerated | F | 0 | 0%
| Days Variance | F | 50 | 714%
| Days Early | F | 0 | 0%
| Days Late | F | 50 | 714%
| Avg Days Early | F | 0
| Avg Days Late | F | 13
| Avg Variance | F | 7
| Actually Finished | F | 7 | 47%
| Took Longer than Planned | F | 3 | 38%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 7 | 54%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 7 | 78%
| Missed Durations | F | 2 | 29%
| Missed Durations & Late Actual Finish | F | 2 | 29%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 4 | 57%
| Completed On-Schedule | F | 3 | 43%
| Accelerated | F | 0 | 0%
| Days Variance | F | 50 | 714%
| Days Early | F | 0 | 0%
| Days Late | F | 50 | 714%
| Avg Days Early | F | 0
| Avg Days Late | F | 13
| Avg Variance | F | 7
| Actually Finished | F | 7 | 47%
| Took Longer than Planned | F | 3 | 38%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 7 | 54%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 7 | 78%
| Missed Durations | F | 2 | 29%
| Missed Durations & Late Actual Finish | F | 2 | 29%
| Baselined Tasks | F | 13
| Baselined to Start - TOTAL | F | 13
| Complete Task Starts - Cumulative | F | 9 | 82%
| Incomplete Task Starts - Cumulative (in work) | F | 2 | 18%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 13
| Complete Task Finishes - Cumulative (in work) | F | 7 | 78%
| Incomplete Task Finishes - Cumulative | F | 2 | 78%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.78
| BEI - Total Tasks | F | 9
| BEI - Complete Tasks | F | 7 | 78%
| BEI - Incomplete Tasks | F | 2 | 22%
| BEI - Value Tasks (adjusted) | F | 0.78
| BEI - Complete Tasks (adjusted) | F | 7 | 78%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-04-30
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| BEI - Value Milestones (adjusted) | F | 1
| BEI - Complete Milestones (adjusted) | F | 1 | 100%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-04-30
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-04-30
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-04-30
| BEI - Value Tasks | F | 0.78
| BEI - Total Tasks | F | 9
| BEI - Incomplete Tasks | F | 2 | 22%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 100%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.78
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 1
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-04-30
| Total Activities - DRM | F | 7
| Total Activities - DRM Graph | F | 7
| Status Date | F | 2026-04-30
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-04-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-04-30
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.82
| BEI - Value Task Finishes - Cumulative | F | 0.78
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| BEI - Value Tasks | F | 0.78
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 1
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.78
| BEI - Complete Tasks | F | 7 | 78%
| BEI - Incomplete Tasks | F | 2 | 22%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 57%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 14%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 14%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-04-30
| High Float 10% | F | 2 | 29%
| High Float 44d | F | 1 | 14%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 20%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 4 | 80%
| Longest Path (Tasks & Milestones) | F | 5 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| Critical Milestones (To-Go) | F | 1 | 100%
| Longest Path (Milestones) | F | 1 | 20%
| Normal Tasks | F | 13 | 87%
| Normal Tasks (To-Go) | F | 6 | 86%
| Critical Tasks (To-Go) | F | 4 | 67%
| Critical Tasks (In Progress) | F | 2 | 50%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.6
| Time Now | F | 2026-04-30
| Forecast to be Finished | F | 9 | 69%
| Completed On Time | F | 4 | 44%
| Completed Late | F | 5 | 56%
| Not Completed | F | 2 | 22%
| Baseline Finish Compliance | F | 44%
| Forecast to be Started | F | 11 | 85%
| Started On Time | F | 6 | 55%
| Started Late | F | 5 | 45%
| Not Started | F | 2 | 18%
| Baseline Start Compliance | F | 91%
1 | Completed Activities | F | 7
HSD01 | Time Now | F | 2026-04-30
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 2 | 15%
HSD04 | Started Late | F | 5 | 45%
HSD05 | Forecast to be Finished but not Finished yet | T | 2 | 15%
HSD06 | Finished Late | F | 5 | 56%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-06-26
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 1 | 50%
SEM02 | BRI Current | F | 0.33
SEM03 | BRI Cumulative | F | 0.78
SEM04 | BPI Current | F | 0.33
SEM05 | BEI Current | T | 0.67
SEM06 | BEI Cumulative | T | 0.78
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 2
SEM07 | To Go - BEI - Task Finishes - Count | T | 4
SEM07 | To Go - Baselined Task Starts - Count | T | 2
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 2
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 2
SEM07 | To Go - BEI - Task Finishes - Count | T | 4
SEM07 | To Go - Baselined Task Starts - Count | T | 2
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Workoff Burden - Starts To-Go (Total) | F | 2
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | 2
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | 4
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 4
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 2
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 2
SEM07 | To Go - BEI - Task Finishes - Count | T | 4
SEM07 | To Go - Baselined Task Starts - Count | T | 2
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | TC-BEI | F | 1
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.2
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## TP4_DataCenter_v5-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities | AlltheProjects - 17639 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v5 2 (5/29/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-05-29
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 57%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 14%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 14%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-05-29
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 5 | 71%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 25%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 7 | 47%
| Milestones (To-Go) | F | 1 | 14%
| Normal Tasks (To-Go) | F | 6 | 86%
| Normal Tasks (To-Go, In Progress) | F | 3 | 43%
| Critical Path (Tasks & Milestones) | F | 5 | 71%
| Critical Path (Milestones) | F | 1 | 20%
| Critical Path (Normal Tasks) | F | 4 | 80%
| Critical Path (Normal In Progress) | F | 1 | 20%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 5 | 71%
| Near-Critical (<10 Days Float) | F | 5 | 71%
| CP Logic Density™ | F | 2.6
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.58
| BEI - Total Tasks | F | 12
| BEI - Complete Tasks | F | 7 | 58%
| BEI - Incomplete Tasks | F | 5 | 42%
| Status Date | F | 2026-05-29
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-05-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-05-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-05-29
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 8 | 53%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 7 | 54%
| Total Activities (To-Go) - % of Total | F | 7 | 47%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Milestones (To-Go) | F | 1 | 14%
| Normal Tasks (To-Go) | F | 6 | 86%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 5 | 100%
| Longest Path (Normal Tasks) | F | 4 | 80%
| Longest Path (Milestones) | F | 1 | 20%
| Critical Milestones (To-Go) | F | 1 | 20%
| Critical Normal Tasks (To-Go) | F | 4 | 80%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 10
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 7
| Started Delayed (<=30 days) | F | 4 | 80%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 1 | 20%
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.77
| BEI - Value Task Finishes - Cumulative | F | 0.58
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | 3
| Current Baseline to Start & Started (BL Plan) | F | 10
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 3
| Current Baseline to Finish & Finished (BL Plan) | F | 7
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 6
| Duration Ratio Metric (DRM) | F | 7
| DRM Graph | F | 7
| Baselined to Start | F | 6
| Scheduled to Start | F | 6
| Baselined to Finish | F | 6
| Scheduled to Finish | F | 6
| BEI - Value Activities | F | 0.62
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Critical Path To-Go | F | 5 | 71%
| Status Date | F | 2026-05-29
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 8 | 53%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 7 | 54%
| Total Activities (To-Go) - % of Total | F | 7 | 47%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Milestones (To-Go) | F | 1 | 14%
| Normal Tasks (To-Go) | F | 6 | 86%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 5 | 100%
| Longest Path (Normal Tasks) | F | 4 | 80%
| Longest Path (Milestones) | F | 1 | 20%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-05-29
| Total Activities (To-Go) - % of Total | F | 7 | 47%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Summary-to-Task Ratio (To-Go) | F | N/A | 0
| Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 5 | 71%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 57%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 7 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 7 | 100%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 17
| Avg. Remaining Duration | F | 14
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 3 | 50%
| Critical Activities (To-Go) | F | 4 | 67%
| Avg. Critical Original Duration | F | 15
| Avg. Critical Remaining Duration | F | 14
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 1 | 17%
| Activities (To-Go) | F | 6 | 46%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 1 | 14%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 7 | 100%
| No Constraints | F | 7 | 100%
| Logic Density™ | F | 2.57
| Logic Density™ - Predecessors | F | 1.71
| Logic Density™ - Successors | F | 0.86
| Summary Links | F | N/A | 0%
| All Activities w/Predecessors | F | 4 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 7 | 100%
| All Activities w/Successors | F | 6 | 86%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 6 | 86%
| Missing Logic | F | 1 | 14%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 14%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 2
| All Activities w/Predecessors | F | 4 | 100%
| Total # Predecessors | F | 8
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 25%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 25%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 0.86
| All Activities w/Successors | F | 6 | 100%
| Activities Missing Successors | F | 1 | 14%
| Total # Successors | F | 6
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 8 | 53%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 4 | 50%
| Completed Delayed - Tasks & Milestones | F | 4 | 50%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 13
| Avg Finish Variance - Tasks & Milestones | F | 6
| Actually Finished - Tasks | F | 7 | 54%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 3 | 43%
| Completed Delayed - Tasks | F | 4 | 57%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 2 | 15%
| Actually Finished - Milestones | F | 1 | 50%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 1 | 100%
| Completed Delayed - Milestones | F | 0 | 0%
| Actually Started - Tasks | F | 3 | 23%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 3 | 100%
| In-Progress Delayed Finish - Tasks | F | 3 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 44
| Avg Start Variance | F | 44
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 4 | 27%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 4 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 3 | 23%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 3 | 100%
| Planned Delayed Finish - Tasks | F | 3 | 100%
| Scheduled to Start - Milestones | F | 1 | 50%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 1 | 100%
| Planned Delayed Finish - Milestones | F | 1 | 100%
| Schedule Baseline Activities | F | 15 | 100%
| Scheduled/Baselined to Start | F | 7
| Scheduled/Baselined to Finish | F | 7
| Start/ed | F | 11
| Finish/ed | F | 8
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 1 | 20%
| Completed Delayed (>30 days) | F | 0 | 0%
| SPI(t) | F | 0.63
| Scheduled Activities | F | 15 | 100%
| Scheduled to Start | F | 7 | 47%
| Scheduled to Finish | F | 7 | 47%
| Longest Path - Critical Activities and Milestones | F | 5 | 71%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 4 | 67%
| Critical Tasks (In Progress) | F | 1 | 25%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| High Float 10% | F | 0 | 0%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 5 | 71%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 4 | 67%
| Critical Tasks (In Progress) | F | 1 | 25%
| Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| Logic Density™ | F | 2.67
| CP Logic Density™ | F | 2.6
| Critical w/Missing Logic | F | 1 | 14%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 10
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 7
| Started Delayed (<=30 days) | F | 4 | 80%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 1 | 20%
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 10
| Current Baselined to Start & Started | F | 10
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 7
| Current Baselined to Finish & Finished | F | 7
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 4 | 80%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 1 | 20%
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 13 | 100%
| Scheduled to Start - To Time Now | F | 13 | 100%
| Started | F | 10
| Started Late | F | 5
| Started Delayed (<=30 days) | F | 4 | 80%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 1 | 20%
| BEI - Value Task Starts | F | 0.77
| Baselined to Finish - To Time Now | F | 12 | 92%
| Scheduled to Finish - To Time Now | F | 12 | 92%
| Finished | F | 7
| Finished Late | F | 4
| Completed Delayed (<=30 days) | F | 4 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.58
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.77
| BEI - Value Task Finishes - Cumulative | F | 0.58
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | 3
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 10
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 3
| Baselined to Start - Check | F | 13
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 7
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 6
| Baselined to Finish - Check | F | 13
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 10
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 3
| Current Baseline to Finish & Finished (BL Plan) | F | 7
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 6
| Baselined to Start | F | 13
| Scheduled to Start | F | 13 | 100%
| Started - Scheduled | F | 10 | 77%
| Started - Baseline Comparison | F | 10 | 77%
| BEI - Value Task Starts | F | 0.77
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 12
| Scheduled to Finish | F | 12
| Finished | F | 7
| BEI - Value Task Finishes | F | 0.58
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-05-29
| Started (incl. Future Baseline Starts) - Scheduled | F | 10 | 77%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 10 | 77%
| Started Late (from Baseline) | F | 5
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 7 | 54%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 7 | 54%
| Finished Late | F | 4
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 4 | 57%
| Completed On-Schedule | F | 3 | 43%
| Accelerated | F | 0 | 0%
| Days Variance | F | 50 | 714%
| Days Early | F | 0 | 0%
| Days Late | F | 50 | 714%
| Avg Days Early | F | 0
| Avg Days Late | F | 13
| Avg Variance | F | 7
| Actually Finished | F | 7 | 47%
| Took Longer than Planned | F | 3 | 38%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 7 | 54%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 7 | 58%
| Missed Durations | F | 2 | 29%
| Missed Durations & Late Actual Finish | F | 2 | 29%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 4 | 57%
| Completed On-Schedule | F | 3 | 43%
| Accelerated | F | 0 | 0%
| Days Variance | F | 50 | 714%
| Days Early | F | 0 | 0%
| Days Late | F | 50 | 714%
| Avg Days Early | F | 0
| Avg Days Late | F | 13
| Avg Variance | F | 7
| Actually Finished | F | 7 | 47%
| Took Longer than Planned | F | 3 | 38%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 7 | 54%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 7 | 58%
| Missed Durations | F | 2 | 29%
| Missed Durations & Late Actual Finish | F | 2 | 29%
| Baselined Tasks | F | 13
| Baselined to Start - TOTAL | F | 13
| Complete Task Starts - Cumulative | F | 10 | 77%
| Incomplete Task Starts - Cumulative (in work) | F | 3 | 23%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 13
| Complete Task Finishes - Cumulative (in work) | F | 7 | 58%
| Incomplete Task Finishes - Cumulative | F | 5 | 58%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.58
| BEI - Total Tasks | F | 12
| BEI - Complete Tasks | F | 7 | 58%
| BEI - Incomplete Tasks | F | 5 | 42%
| BEI - Value Tasks (adjusted) | F | 0.58
| BEI - Complete Tasks (adjusted) | F | 7 | 58%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-05-29
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| BEI - Value Milestones (adjusted) | F | 1
| BEI - Complete Milestones (adjusted) | F | 1 | 100%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-05-29
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-05-29
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-05-29
| BEI - Value Tasks | F | 0.58
| BEI - Total Tasks | F | 12
| BEI - Incomplete Tasks | F | 5 | 42%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 100%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.58
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 1
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-05-29
| Total Activities - DRM | F | 7
| Total Activities - DRM Graph | F | 7
| Status Date | F | 2026-05-29
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-05-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-05-29
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.77
| BEI - Value Task Finishes - Cumulative | F | 0.58
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | 3
| BEI - Value Tasks | F | 0.58
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 1
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.58
| BEI - Complete Tasks | F | 7 | 58%
| BEI - Incomplete Tasks | F | 5 | 42%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 57%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 14%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 14%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-05-29
| High Float 10% | F | 0 | 0%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 25%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 4 | 80%
| Longest Path (Tasks & Milestones) | F | 5 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.25
| Critical Milestones (To-Go) | F | 1 | 100%
| Longest Path (Milestones) | F | 1 | 20%
| Normal Tasks | F | 13 | 87%
| Normal Tasks (To-Go) | F | 6 | 86%
| Critical Tasks (To-Go) | F | 4 | 67%
| Critical Tasks (In Progress) | F | 1 | 25%
| Zero Days Float | F | 5 | 71%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.6
| Time Now | F | 2026-05-29
| Forecast to be Finished | F | 12 | 92%
| Completed On Time | F | 3 | 25%
| Completed Late | F | 7 | 58%
| Not Completed | F | 5 | 42%
| Baseline Finish Compliance | F | 25%
| Forecast to be Started | F | 13 | 100%
| Started On Time | F | 5 | 38%
| Started Late | F | 6 | 46%
| Not Started | F | 3 | 23%
| Baseline Start Compliance | F | 62%
1 | Completed Activities | F | 7
HSD01 | Time Now | F | 2026-05-29
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 3 | 23%
HSD04 | Started Late | F | 6 | 46%
HSD05 | Forecast to be Finished but not Finished yet | T | 5 | 38%
HSD06 | Finished Late | F | 7 | 58%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-07-17
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 0 | 0%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.58
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | T | 0
SEM06 | BEI Cumulative | T | 0.58
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 3
SEM07 | To Go - Planned Task Starts - Count | T | 2
SEM07 | To Go - BEI - Task Finishes - Count | T | 3
SEM07 | To Go - Baselined Task Starts - Count | T | 2
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 2
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 2
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 1
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 3
SEM07 | To Go - Planned Task Starts - Count | T | 2
SEM07 | To Go - BEI - Task Finishes - Count | T | 3
SEM07 | To Go - Baselined Task Starts - Count | T | 2
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | Workoff Burden - Starts To-Go (Total) | F | 2
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 2
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | 0
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | 3
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 2
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 1
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 2
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 0
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 2
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | 1
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 3
SEM07 | To Go - Planned Task Starts - Count | T | 2
SEM07 | To Go - BEI - Task Finishes - Count | T | 3
SEM07 | To Go - Baselined Task Starts - Count | T | 2
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 0
SEM07 | TC-BEI | T | 3
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -1.38
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%