## Ribbon View
Deltek Acumen Fuse® Ribbon View Report
Workbook: Workbook1 - 17639 Activities
Quick Add Metrics
Created on: 8/7/2026
Created by: dpolitte
Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
[404 empty] | Wrong Status - Actual Starts | Wrong Status - Actual Finishes | Invalid Forecast Dates | Expected Finish But Still In-Progress | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | SF Relations | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Missing Baseline Starts | Missing Baseline Finishes | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | High Float 10% of Rem Project Duration | High Float 44d | Zero Days Float | Number of Leads | Number of Lags | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | New To-Go Tasks in Status Period | New Completed Tasks in Status Period | New Critical Tasks in Status Period | Riding Data Date | Deadlines | Missed Activities | High Float 10% | Negative Float | Max Float | Tasks & Milestones (To Go) | Milestones (To-Go) | Normal Tasks (To-Go) | Normal Tasks (To-Go, In Progress) | Milestone-to-Task Ratio (To-Go) | Float Ratio™ | Critical Path (Tasks & Milestones) | Critical Path (Milestones) | Critical Path (Normal Tasks) | Critical Path (Normal In Progress) | Critical Milestone-to-Task Ratio (To-Go) | Negative Float | Zero Days Float | Near-Critical (<10 Days Float) | Near CP - Float Ratio™ | CP Logic Density™ | Critical Tasks Created in Status Period | Critical CEI - Value Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | Status Date | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Status Date | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Status Date | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | New Activity - Created | New Activity - Already Finished | New Activity - Finished in Status Period | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Max Float | Newly Created Activity & Critical - Created (Snapshot) | Number of Leads | Number of Lags | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Total New Completed Tasks & Milestones in Status Period | Total New Tasks & Milestones in Status Period | Riding Data Date | Deadlines | Missed Activities | Wrong Status | Invalid Forecast Dates | Expected Finish | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | SF Relations | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Missing Baseline Starts | Missing Baseline Finishes | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | SV(t) | SPI(t) | Missing Predecessors | Missing Successors | Activities with Lags | SS Predecessors | SF Predecessors | FF Predecessors | FS Predecessors | Logic Density™ | Merge Hotspot | Diverge Hotspot | Logic Hotspot™ | Summary Links | Open Start | Open Finish | Open Ends with Constraints | Open Ends w/o Constraints | Open Ends | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Score | time axis 2012-08-01 to 2029-04-01
Ribbons | SRA Large Test File2 | [402 empty] | 1 | 4 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 11 | 12 | 0 | 0 | 122 | 2025-03-10 | 623 | 717 | 67 | 1 | 5 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 0 | 1363 | 354 | 122 | 2196 | 999 | 80 | 919 | 92 | 1:11 | N/A | 186 | 16 | 170 | 4 | 1:11 | 122 | 67 | 243 | N/A | 4.26 | 0 | N/A | N/A | N/A | 0 | 0 | 0.51 | 1228 | 632 | 596 | 2025-03-10 | 0.51 | 1228 | 632 | 596 | 0.51 | 632 | N/A | 2025-03-10 | 0.69 | 129 | 89 | 40 | 0.69 | 89 | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 354 | 717 | 67 | 122 | 2196 | 0 | 1 | 8 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 1095 | 1 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 11 | 12 | 0 | 0 | 122 | 2025-03-10 | -270791 | 8.14 | 12 | 18 | 8 | 70 | 0 | 43 | 1704 | 3.13 | 155 | 141 | 14 | 0 | 3 | 11 | 0 | 25 | 25 | 2 | 0 | 8 | 90 | 0 | 0 | 660 | 112 | 86 | 322 | 4 | 842 | 1095 | x | 0.59 | 0.53 | 0
Ribbons | SRA Large Test File2 | [402 empty] | 0% | 1% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  | 62% | 72% | 7% | 0% | 1% | 0% | 2% | 4% | 100% | 2% | 20% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 87% | 35% | 12% |  | 58% | 8% | 92% | 9% |  |  | 19% | 9% | 91% | 2% |  | 12% | 7% | 24% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 51% | 49% |  |  |  | 51% | 49% |  | 51% |  |  |  |  | 69% | 31% |  | 69% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 35% | 72% | 7% | 12% |  |  | 0% | 0% | 0% | 2% | 4% | 100% | 2% | 20% |  |  | 0% | 0% | 87% | 0% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  |  |  | 1% | 1% | 0% | 4% | 0% | 2% | 99% |  | 9% | 8% | 1% | 0% | 0% | 1% | 0% | 1% | 1% | 0% | 0% | 1% | 6% | 0% | 0% | 73% | 12% | 10% | 36% | 1% | 94% | 87%
Ribbons | TP4_DataCenter_v1 | [402 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-01-30 | 4 | 1 | 8 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 45 | 13 | 1 | 12 | 1 | 1:12 | 0.63 | 8 | 1 | 7 | 1 | 1:07 | 0 | 8 | 9 | 0.03 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 1 | 1 | 1 | 0 | 2026-01-30 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-01-30 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-01-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | 2 | 1 | 8 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-01-30 | -4 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 12 | 0 | ✓ | 1 | 1 | 0
Ribbons | TP4_DataCenter_v1 | [402 empty] | 0% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 31% | 8% | 62% | 0% | 0% | 0% | 0% | 8% | ( N/A ) | 8% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 15% | 0% |  | 87% | 8% | 92% | 8% |  |  | 62% | 13% | 88% | 13% |  | 0% | 62% | 69% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 100% | 0% |  |  |  | 100% | 0% |  | 100% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 15% | 8% | 62% | 0% |  |  | 0% | 0% | 0% | 0% | 8% | ( N/A ) | 8% | ( N/A ) |  |  | 0% | 0% | 0% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 0% | 0% | 8% | 0% | 100% | 0%
Ribbons | TP4_DataCenter_v2 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-02-27 | 3 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 30 | 11 | 1 | 10 | 3 | 1:10 | 0.47 | 7 | 1 | 6 | 1 | 1:06 | 0 | 7 | 8 | 0.04 | 2.86 | 0 | N/A | N/A | N/A | 0 | 0 | 0.75 | 4 | 3 | 1 | 2026-02-27 | 0.75 | 4 | 3 | 1 | 0.75 | 3 | N/A | 2026-02-27 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-02-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | 1 | 0 | 7 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-02-27 | -69 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | ✓ | 1 | 0.75 | 0
Ribbons | TP4_DataCenter_v2 | [402 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 27% | 0% | 64% | 0% | 0% | 0% | 0% | 13% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 8% | 9% | 0% |  | 73% | 9% | 91% | 27% |  |  | 64% | 14% | 86% | 14% |  | 0% | 64% | 73% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 75% | 25% |  |  |  | 75% | 25% |  | 75% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 9% | 0% | 64% | 0% |  |  | 0% | 0% | 0% | 0% | 13% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 25%
Ribbons | TP4_DataCenter_v3 | [402 empty] | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | 2 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 30 | 9 | 1 | 8 | 2 | 1:08 | 0.34 | 7 | 1 | 6 | 1 | 1:06 | 0 | 7 | 7 | 0 | 2.86 | 0 | N/A | N/A | N/A | 0 | 0 | 0.71 | 7 | 5 | 2 | 2026-03-31 | 0.71 | 7 | 5 | 2 | 0.71 | 5 | N/A | 2026-03-31 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 1 | 0 | 7 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | -123 | 0.67 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 8 | 3 | ✓ | 1 | 0.71 | 0
Ribbons | TP4_DataCenter_v3 | [402 empty] | 0% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 22% | 0% | 78% | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 31% | 11% | 0% |  | 60% | 11% | 89% | 22% |  |  | 78% | 14% | 86% | 14% |  | 0% | 78% | 78% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 71% | 29% |  |  |  | 71% | 29% |  | 71% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 11% | 0% | 78% | 0% |  |  | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 43% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 100% | 43%
Ribbons | TP4_DataCenter_v4 | [402 empty] | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-04-30 | 2 | 1 | 5 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0 | 50 | 7 | 1 | 6 | 2 | 1:06 | 0.73 | 5 | 1 | 4 | 2 | 1:04 | 0 | 5 | 5 | 0 | 2.6 | 0 | N/A | N/A | N/A | 0 | 0 | 0.78 | 9 | 7 | 2 | 2026-04-30 | 0.78 | 9 | 7 | 2 | 0.78 | 7 | N/A | 2026-04-30 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-04-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | 2 | 1 | 5 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-04-30 | -99 | 0.7 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 6 | 5 | ✓ | 1 | 0.78 | 0
Ribbons | TP4_DataCenter_v4 | [402 empty] | 0% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 29% | 14% | 71% | 0% | 0% | 0% | 0% | 20% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 69% | 29% | 0% |  | 47% | 14% | 86% | 29% |  |  | 71% | 20% | 80% | 40% |  | 0% | 71% | 71% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 78% | 22% |  |  |  | 78% | 22% |  | 78% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 29% | 14% | 71% | 0% |  |  | 0% | 0% | 0% | 0% | 20% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 56% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 17% | 0% | 0% | 67% | 0% | 100% | 56%
Ribbons | TP4_DataCenter_v5 | [402 empty] | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-05-29 | 2 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 15 | 7 | 1 | 6 | 3 | 1:06 | 0.32 | 5 | 1 | 4 | 1 | 1:04 | 0 | 5 | 5 | 0 | 2.6 | 0 | N/A | N/A | N/A | 0 | 0 | 0.58 | 12 | 7 | 5 | 2026-05-29 | 0.58 | 12 | 7 | 5 | 0.58 | 7 | N/A | 2026-05-29 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-05-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | 0 | 0 | 5 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 9 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-05-29 | -280 | 0.63 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 6 | 9 | ✓ | 1 | 0.58 | 0
Ribbons | TP4_DataCenter_v5 | [402 empty] | 0% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 29% | 0% | 71% | 0% | 0% | 0% | 0% | 25% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 77% | 0% | 0% |  | 47% | 14% | 86% | 43% |  |  | 71% | 20% | 80% | 20% |  | 0% | 71% | 71% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 58% | 42% |  |  |  | 58% | 42% |  | 58% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 0% | 0% | 71% | 0% |  |  | 0% | 0% | 0% | 0% | 25% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 75% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 67% | 0% | 100% | 75%
Ribbons | Project2 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-24 | 42 | 44 | 41 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 39 | 0 | 263 | 106 | 0 | 106 | 3 | N/A | 14.01 | 41 | 0 | 41 | 1 | N/A | 0 | 41 | 50 | 0.05 | 3.2 | 0 | N/A | N/A | N/A | 0 | 0 | 0.74 | 27 | 20 | 7 | 2026-05-24 | 0.74 | 27 | 20 | 7 | 0.74 | 20 | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 39 | 44 | 41 | 0 | 263 | 0 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-24 | -454 | 0.83 | 1 | 5 | 2 | 0 | 0 | 1 | 125 | 2.79 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 0 | 2 | 1 | 0 | 0 | 44 | 0 | 1 | 0 | 0 | 0 | 18 | ✓ | 1 | 0.74 | 0
Ribbons | Project2 | [402 empty] | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 40% | 42% | 39% | 0% | 2% | 1% | 2% | 3% | 0% | 8% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 37% | 0% |  | 84% | 0% | 100% | 3% |  |  | 39% | 0% | 100% | 2% |  | 0% | 39% | 47% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 74% | 26% |  |  |  | 74% | 26% |  | 74% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 37% | 42% | 39% | 0% |  |  | 0% | 2% | 1% | 2% | 3% | 0% | 8% | 0% |  |  | 0% | 0% | 67% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 4% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 4% | 5% | 4% | 0% | 1% | 1% | 0% | 0% | 42% | 0% | 1% | 0% | 0% | 0% | 67%
Ribbons | Project5_TAMPERED | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 43 | 44 | 4 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 41 | 0 | 275 | 99 | 0 | 99 | 2 | N/A | 22.02 | 4 | 0 | 4 | 0 | N/A | 0 | 4 | 5 | 0.1 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 0.59 | 46 | 27 | 19 | 2026-08-27 | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 41 | 44 | 4 | 0 | 275 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | -902 | 0.91 | 1 | 6 | 2 | 0 | 0 | 1 | 125 | 2.81 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 7 | 7 | 5 | 0 | 1 | 0 | 0 | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 37 | x | 1 | 0.59 | 0
Ribbons | Project5_TAMPERED | [402 empty] | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  | 43% | 44% | 4% | 0% | 1% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 41% | 0% |  | 79% | 0% | 100% | 2% |  |  | 4% | 0% | 100% | 0% |  | 0% | 4% | 5% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 59% | 41% |  |  |  | 59% | 41% |  | 59% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 41% | 44% | 4% | 0% |  |  | 0% | 2% | 1% | 0% | 1% | 0% | 0% | 0% |  |  | 0% | 0% | 80% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  |  |  | 1% | 5% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 5% | 6% | 5% | 0% | 1% | 0% | 0% | 1% | 44% | 0% | 0% | 0% | 0% | 0% | 80%
Ribbons | Project2 2 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-24 | 42 | 44 | 41 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 39 | 0 | 263 | 106 | 0 | 106 | 3 | N/A | 14.01 | 41 | 0 | 41 | 1 | N/A | 0 | 41 | 50 | 0.05 | 3.2 | 0 | N/A | N/A | N/A | 0 | 0 | 0.74 | 27 | 20 | 7 | 2026-05-24 | 0.74 | 27 | 20 | 7 | 0.74 | 20 | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 39 | 44 | 41 | 0 | 263 | 0 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-24 | -454 | 0.83 | 1 | 5 | 2 | 0 | 0 | 1 | 125 | 2.79 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 0 | 2 | 1 | 0 | 0 | 44 | 0 | 1 | 0 | 0 | 0 | 18 | ✓ | 1 | 0.74 | 0
Ribbons | Project2 2 | [402 empty] | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 40% | 42% | 39% | 0% | 2% | 1% | 2% | 3% | 0% | 8% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 37% | 0% |  | 84% | 0% | 100% | 3% |  |  | 39% | 0% | 100% | 2% |  | 0% | 39% | 47% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 74% | 26% |  |  |  | 74% | 26% |  | 74% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 37% | 42% | 39% | 0% |  |  | 0% | 2% | 1% | 2% | 3% | 0% | 8% | 0% |  |  | 0% | 0% | 67% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 4% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 4% | 5% | 4% | 0% | 1% | 1% | 0% | 0% | 42% | 0% | 1% | 0% | 0% | 0% | 67%
Ribbons | Project3 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-30 | 40 | 42 | 40 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 31 | 0 | 223 | 102 | 0 | 102 | 1 | N/A | 13.83 | 40 | 0 | 40 | 1 | N/A | 0 | 40 | 49 | 0.05 | 3.23 | 0 | N/A | N/A | N/A | 0 | 0 | 0.67 | 36 | 24 | 12 | 2026-06-30 | 0.67 | 36 | 24 | 12 | 0.67 | 24 | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | 31 | 42 | 40 | 0 | 223 | 0 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-30 | -550 | 0.88 | 1 | 5 | 2 | 0 | 0 | 1 | 125 | 2.79 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 0 | 2 | 1 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 27 | ✓ | 1 | 0.67 | 0
Ribbons | Project3 | [402 empty] | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 39% | 41% | 39% | 0% | 2% | 1% | 3% | 3% | 0% | 8% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 30% | 0% |  | 81% | 0% | 100% | 1% |  |  | 39% | 0% | 100% | 3% |  | 0% | 39% | 48% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 67% | 33% |  |  |  | 67% | 33% |  | 67% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 30% | 41% | 39% | 0% |  |  | 0% | 2% | 1% | 3% | 3% | 0% | 8% | 0% |  |  | 0% | 0% | 75% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 4% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 4% | 5% | 4% | 0% | 1% | 1% | 0% | 0% | 41% | 0% | 0% | 0% | 0% | 0% | 75%
Ribbons | Project4 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-29 | 39 | 41 | 37 | 0 | 1 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 31 | 0 | 230 | 101 | 0 | 101 | 1 | N/A | 13.76 | 37 | 0 | 37 | 0 | N/A | 0 | 37 | 48 | 0.13 | 3.32 | 0 | N/A | N/A | N/A | 0 | 0 | 0.58 | 43 | 25 | 18 | 2026-07-29 | 0.58 | 43 | 25 | 18 | 0.58 | 25 | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | 31 | 41 | 37 | 0 | 230 | 0 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-29 | -630 | 0.89 | 1 | 5 | 2 | 0 | 0 | 1 | 125 | 2.83 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 0 | 1 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 34 | ✓ | 1 | 0.58 | 0
Ribbons | Project4 | [402 empty] | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 39% | 41% | 37% | 0% | 1% | 1% | 3% | 3% | 0% | 8% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 31% | 0% |  | 80% | 0% | 100% | 1% |  |  | 37% | 0% | 100% | 0% |  | 0% | 37% | 48% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 58% | 42% |  |  |  | 58% | 42% |  | 58% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 31% | 41% | 37% | 0% |  |  | 0% | 2% | 1% | 3% | 3% | 0% | 8% | 0% |  |  | 0% | 0% | 79% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 4% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 4% | 5% | 4% | 0% | 1% | 0% | 0% | 0% | 41% | 0% | 0% | 0% | 0% | 0% | 79%
Ribbons | Project5 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 43 | 44 | 4 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 41 | 0 | 275 | 99 | 0 | 99 | 2 | N/A | 22.02 | 4 | 0 | 4 | 0 | N/A | 0 | 4 | 5 | 0.1 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 0.59 | 46 | 27 | 19 | 2026-08-27 | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 41 | 44 | 4 | 0 | 275 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | -902 | 0.91 | 1 | 6 | 2 | 0 | 0 | 1 | 125 | 2.81 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 7 | 7 | 5 | 0 | 1 | 0 | 0 | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 37 | ✓ | 1 | 0.59 | 0
Ribbons | Project5 | [402 empty] | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  | 43% | 44% | 4% | 0% | 1% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 41% | 0% |  | 79% | 0% | 100% | 2% |  |  | 4% | 0% | 100% | 0% |  | 0% | 4% | 5% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 59% | 41% |  |  |  | 59% | 41% |  | 59% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 41% | 44% | 4% | 0% |  |  | 0% | 2% | 1% | 0% | 1% | 0% | 0% | 0% |  |  | 0% | 0% | 80% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  |  |  | 1% | 5% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 5% | 6% | 5% | 0% | 1% | 0% | 0% | 1% | 44% | 0% | 0% | 0% | 0% | 0% | 80%
Ribbons | Large Test File | [402 empty] | 0 | 0 | 2 | 0 | 0 | 0 | 7 | 0 | 0 | 2 | 1 | 2 | 0 | 2 | 0 | 0 | 12 | 13 | 1 | 0 | 41 | 2025-02-07 | 804 | 898 | 2 | 1 | 5 | 2 | 4 | 9 | 2 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 1356 | 467 | 41 | 2873 | 1024 | 79 | 945 | 108 | 1:12 | N/A | 43 | 8 | 35 | 1 | 1:04 | 41 | 2 | 74 | -4.26 | 7.58 | 0 | N/A | N/A | N/A | 0 | 0 | 0.51 | 1205 | 609 | 596 | 2025-02-07 | 0.51 | 1205 | 609 | 596 | 0.51 | 609 | N/A | 2025-02-07 | 0.7 | 128 | 89 | 39 | 0.7 | 89 | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 467 | 898 | 2 | 41 | 2873 | 0 | 1 | 8 | 2 | 4 | 9 | 2 | 11 | 1 | 0 | 0 | 0 | 0 | 1115 | 0 | 2 | 0 | 0 | 0 | 7 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 12 | 13 | 1 | 0 | 41 | 2025-02-07 | -175932 | 8.22 | 11 | 16 | 8 | 71 | 0 | 43 | 1705 | 3.14 | 156 | 141 | 14 | 0 | 3 | 11 | 1 | 21 | 22 | 0 | 0 | 8 | 93 | 0 | 0 | 814 | 35 | 87 | 0 | 0 | 866 | 1115 | ✓ | 0.97 | 0.52 | 0
Ribbons | Large Test File | [402 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 4% |  | 79% | 88% | 0% | 0% | 0% | 0% | 9% | 1% | 100% | 1% | 20% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 86% | 46% | 4% |  | 59% | 8% | 92% | 11% |  |  | 4% | 19% | 81% | 2% |  | 4% | 0% | 7% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 51% | 49% |  |  |  | 51% | 49% |  | 51% |  |  |  |  | 70% | 30% |  | 70% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 46% | 88% | 0% | 4% |  |  | 0% | 0% | 0% | 9% | 1% | 100% | 1% | 20% |  |  | 0% | 0% | 91% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 4% |  |  |  | 1% | 1% | 0% | 4% | 0% | 2% | 99% |  | 9% | 8% | 1% | 0% | 0% | 1% | 0% | 1% | 1% | 0% | 0% | 1% | 6% | 0% | 0% | 88% | 4% | 9% | 0% | 0% | 94% | 91%
Ribbons | Large Test File2 | [402 empty] | 1 | 4 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 10 | 11 | 0 | 0 | 122 | 2025-03-10 | 623 | 717 | 66 | 1 | 5 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 0 | 1363 | 354 | 122 | 2196 | 998 | 79 | 919 | 92 | 1:12 | N/A | 185 | 15 | 170 | 4 | 1:11 | 122 | 66 | 242 | N/A | 4.27 | 0 | N/A | N/A | N/A | 0 | 0 | 0.51 | 1228 | 632 | 596 | 2025-03-10 | 0.51 | 1228 | 632 | 596 | 0.51 | 632 | N/A | 2025-03-10 | 0.69 | 129 | 89 | 40 | 0.69 | 89 | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 354 | 717 | 66 | 122 | 2196 | 0 | 1 | 8 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 1095 | 1 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 10 | 11 | 0 | 0 | 122 | 2025-03-10 | -270791 | 8.14 | 12 | 18 | 8 | 70 | 0 | 43 | 1703 | 3.13 | 155 | 141 | 14 | 0 | 3 | 11 | 0 | 25 | 25 | 2 | 0 | 8 | 90 | 0 | 0 | 660 | 112 | 86 | 322 | 4 | 842 | 1095 | x | 0.59 | 0.53 | 0
Ribbons | Large Test File2 | [402 empty] | 0% | 1% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  | 62% | 72% | 7% | 0% | 1% | 0% | 2% | 4% | 100% | 2% | 20% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 87% | 35% | 12% |  | 58% | 8% | 92% | 9% |  |  | 19% | 8% | 92% | 2% |  | 12% | 7% | 24% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 51% | 49% |  |  |  | 51% | 49% |  | 51% |  |  |  |  | 69% | 31% |  | 69% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 35% | 72% | 7% | 12% |  |  | 0% | 0% | 0% | 2% | 4% | 100% | 2% | 20% |  |  | 0% | 0% | 87% | 0% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  |  |  | 1% | 1% | 0% | 4% | 0% | 2% | 99% |  | 9% | 8% | 1% | 0% | 0% | 1% | 0% | 1% | 1% | 0% | 0% | 1% | 6% | 0% | 0% | 73% | 12% | 10% | 36% | 1% | 94% | 87%
Ribbons | Large Test File Leveled | [402 empty] | 0 | 0 | 2 | 0 | 0 | 0 | 6 | 0 | 0 | 2 | 1 | 2 | 0 | 2 | 0 | 0 | 12 | 13 | 1 | 0 | 47 | 2025-02-07 | 803 | 912 | 2 | 1 | 5 | 2 | 4 | 10 | 2 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 1400 | 467 | 47 | 2873 | 1024 | 79 | 945 | 108 | 1:12 | N/A | 49 | 8 | 41 | 1 | 1:05 | 47 | 2 | 49 | -6.67 | 7.14 | 0 | N/A | N/A | N/A | 0 | 0 | 0.51 | 1205 | 609 | 596 | 2025-02-07 | 0.51 | 1205 | 609 | 596 | 0.51 | 609 | N/A | 2025-02-07 | 0.7 | 128 | 89 | 39 | 0.7 | 89 | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 467 | 912 | 2 | 47 | 2873 | 0 | 1 | 8 | 2 | 4 | 10 | 2 | 13 | 1 | 0 | 0 | 0 | 0 | 1115 | 0 | 2 | 0 | 0 | 0 | 6 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 12 | 13 | 1 | 0 | 47 | 2025-02-07 | -175932 | 8.22 | 11 | 16 | 8 | 71 | 0 | 43 | 1705 | 3.14 | 156 | 141 | 14 | 0 | 3 | 11 | 1 | 21 | 22 | 0 | 0 | 8 | 93 | 0 | 0 | 827 | 41 | 87 | 0 | 0 | 866 | 1115 | x | 0.95 | 0.52 | 0
Ribbons | Large Test File Leveled | [402 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 5% |  | 78% | 89% | 0% | 0% | 0% | 0% | 8% | 1% | 100% | 1% | 20% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 89% | 46% | 5% |  | 59% | 8% | 92% | 11% |  |  | 5% | 16% | 84% | 2% |  | 5% | 0% | 5% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 51% | 49% |  |  |  | 51% | 49% |  | 51% |  |  |  |  | 70% | 30% |  | 70% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 46% | 89% | 0% | 5% |  |  | 0% | 0% | 0% | 8% | 1% | 100% | 1% | 20% |  |  | 0% | 0% | 91% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 5% |  |  |  | 1% | 1% | 0% | 4% | 0% | 2% | 99% |  | 9% | 8% | 1% | 0% | 0% | 1% | 0% | 1% | 1% | 0% | 0% | 1% | 6% | 0% | 0% | 89% | 4% | 9% | 0% | 0% | 94% | 91%
Ribbons | Large Test File 2 | [402 empty] | 0 | 0 | 2 | 0 | 0 | 0 | 7 | 0 | 0 | 2 | 1 | 2 | 0 | 2 | 0 | 0 | 12 | 13 | 1 | 0 | 41 | 2025-02-07 | 804 | 898 | 2 | 1 | 5 | 2 | 4 | 9 | 2 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 1356 | 467 | 41 | 2873 | 1024 | 79 | 945 | 108 | 1:12 | N/A | 43 | 8 | 35 | 1 | 1:04 | 41 | 2 | 74 | -4.26 | 7.58 | 0 | N/A | N/A | N/A | 0 | 0 | 0.51 | 1205 | 609 | 596 | 2025-02-07 | 0.51 | 1205 | 609 | 596 | 0.51 | 609 | N/A | 2025-02-07 | 0.7 | 128 | 89 | 39 | 0.7 | 89 | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 467 | 898 | 2 | 41 | 2873 | 0 | 1 | 8 | 2 | 4 | 9 | 2 | 11 | 1 | 0 | 0 | 0 | 0 | 1115 | 0 | 2 | 0 | 0 | 0 | 7 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 12 | 13 | 1 | 0 | 41 | 2025-02-07 | -175932 | 8.22 | 11 | 16 | 8 | 71 | 0 | 43 | 1705 | 3.14 | 156 | 141 | 14 | 0 | 3 | 11 | 1 | 21 | 22 | 0 | 0 | 8 | 93 | 0 | 0 | 814 | 35 | 87 | 0 | 0 | 866 | 1115 | ✓ | 0.97 | 0.52 | 0
Ribbons | Large Test File 2 | [402 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 4% |  | 79% | 88% | 0% | 0% | 0% | 0% | 9% | 1% | 100% | 1% | 20% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 86% | 46% | 4% |  | 59% | 8% | 92% | 11% |  |  | 4% | 19% | 81% | 2% |  | 4% | 0% | 7% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 51% | 49% |  |  |  | 51% | 49% |  | 51% |  |  |  |  | 70% | 30% |  | 70% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 46% | 88% | 0% | 4% |  |  | 0% | 0% | 0% | 9% | 1% | 100% | 1% | 20% |  |  | 0% | 0% | 91% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 4% |  |  |  | 1% | 1% | 0% | 4% | 0% | 2% | 99% |  | 9% | 8% | 1% | 0% | 0% | 1% | 0% | 1% | 1% | 0% | 0% | 1% | 6% | 0% | 0% | 88% | 4% | 9% | 0% | 0% | 94% | 91%
Ribbons | Large Test File2 2 | [402 empty] | 1 | 4 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 10 | 11 | 0 | 0 | 122 | 2025-03-10 | 623 | 717 | 66 | 1 | 5 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 0 | 1363 | 354 | 122 | 2196 | 998 | 79 | 919 | 92 | 1:12 | N/A | 185 | 15 | 170 | 4 | 1:11 | 122 | 66 | 242 | N/A | 4.27 | 0 | N/A | N/A | N/A | 0 | 0 | 0.51 | 1228 | 632 | 596 | 2025-03-10 | 0.51 | 1228 | 632 | 596 | 0.51 | 632 | N/A | 2025-03-10 | 0.69 | 129 | 89 | 40 | 0.69 | 89 | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 354 | 717 | 66 | 122 | 2196 | 0 | 1 | 8 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 1095 | 1 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 10 | 11 | 0 | 0 | 122 | 2025-03-10 | -270791 | 8.14 | 12 | 18 | 8 | 70 | 0 | 43 | 1703 | 3.13 | 155 | 141 | 14 | 0 | 3 | 11 | 0 | 25 | 25 | 2 | 0 | 8 | 90 | 0 | 0 | 660 | 112 | 86 | 322 | 4 | 842 | 1095 | ✓ | 0.59 | 0.53 | 0
Ribbons | Large Test File2 2 | [402 empty] | 0% | 1% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  | 62% | 72% | 7% | 0% | 1% | 0% | 2% | 4% | 100% | 2% | 20% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 87% | 35% | 12% |  | 58% | 8% | 92% | 9% |  |  | 19% | 8% | 92% | 2% |  | 12% | 7% | 24% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 51% | 49% |  |  |  | 51% | 49% |  | 51% |  |  |  |  | 69% | 31% |  | 69% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 35% | 72% | 7% | 12% |  |  | 0% | 0% | 0% | 2% | 4% | 100% | 2% | 20% |  |  | 0% | 0% | 87% | 0% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  |  |  | 1% | 1% | 0% | 4% | 0% | 2% | 99% |  | 9% | 8% | 1% | 0% | 0% | 1% | 0% | 1% | 1% | 0% | 0% | 1% | 6% | 0% | 0% | 73% | 12% | 10% | 36% | 1% | 94% | 87%
Ribbons | SRA Large Test File2 2 | [402 empty] | 1 | 4 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 10 | 11 | 0 | 0 | 122 | 2025-03-10 | 623 | 717 | 66 | 1 | 5 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 0 | 1363 | 354 | 122 | 2196 | 998 | 79 | 919 | 92 | 1:12 | N/A | 185 | 15 | 170 | 4 | 1:11 | 122 | 66 | 242 | N/A | 4.27 | 0 | N/A | N/A | N/A | 0 | 0 | 0.51 | 1228 | 632 | 596 | 2025-03-10 | 0.51 | 1228 | 632 | 596 | 0.51 | 632 | N/A | 2025-03-10 | 0.69 | 129 | 89 | 40 | 0.69 | 89 | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 354 | 717 | 66 | 122 | 2196 | 0 | 1 | 8 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 1095 | 1 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 10 | 11 | 0 | 0 | 122 | 2025-03-10 | -270791 | 8.14 | 12 | 18 | 8 | 70 | 0 | 43 | 1703 | 3.13 | 155 | 141 | 14 | 0 | 3 | 11 | 0 | 25 | 25 | 2 | 0 | 8 | 90 | 0 | 0 | 660 | 112 | 86 | 322 | 4 | 842 | 1095 | x | 0.59 | 0.53 | 0
Ribbons | SRA Large Test File2 2 | [402 empty] | 0% | 1% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  | 62% | 72% | 7% | 0% | 1% | 0% | 2% | 4% | 100% | 2% | 20% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 87% | 35% | 12% |  | 58% | 8% | 92% | 9% |  |  | 19% | 8% | 92% | 2% |  | 12% | 7% | 24% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 51% | 49% |  |  |  | 51% | 49% |  | 51% |  |  |  |  | 69% | 31% |  | 69% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 35% | 72% | 7% | 12% |  |  | 0% | 0% | 0% | 2% | 4% | 100% | 2% | 20% |  |  | 0% | 0% | 87% | 0% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  |  |  | 1% | 1% | 0% | 4% | 0% | 2% | 99% |  | 9% | 8% | 1% | 0% | 0% | 1% | 0% | 1% | 1% | 0% | 0% | 1% | 6% | 0% | 0% | 73% | 12% | 10% | 36% | 1% | 94% | 87%
Ribbons | Jacked Up Schedule 1 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 3 | 1 | 2 | 1 | 1 | 0 | N/A | 15 | 15 | 0 | 0 | 0 | 2026-07-30 | 3 | 0 | 9 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 26 | 15 | 2 | 13 | 0 | 1:07 | 0.77 | 9 | 2 | 7 | 0 | 1:04 | 0 | 9 | 14 | 0.4 | 2.33 | 0 | N/A | N/A | N/A | 0 | 0 | N/A | 0 | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | 3 | 0 | 9 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 3 | 1 | 2 | 1 | 1 | 0 | N/A | 15 | 15 | 0 | 0 | 0 | 2026-07-30 | 0 | N/A | 1 | 2 | 0 | 1 | 0 | 1 | 12 | 2.13 | 1 | 1 | 0 | N/A | 1 | 1 | 0 | 3 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | 0 | 0 | ✓ | N/A | 0 | 0
Ribbons | Jacked Up Schedule 1 | [402 empty] | ( N/A ) | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 0% | 0% | N/A | 20% | 7% | 13% | ( N/A ) | 7% | 0% | 0% | 100% | 100% | 0% | 0% | 0% |  | 20% | 0% | 60% | 0% | 0% | 0% | 0% | 7% | ( N/A ) | 7% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 13% | 0% | ( N/A ) | 20% | 0% |  | 100% | 13% | 87% | 0% |  |  | 60% | 22% | 78% | 0% |  | 0% | 60% | 93% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | N/A | N/A |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 20% | 0% | 60% | 0% |  |  | 0% | 0% | 0% | 0% | 7% | ( N/A ) | 7% | ( N/A ) |  |  | 13% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | N/A | 20% | 7% | 13% | 7% | 7% | 0% | 0% | 100% | 100% | 0% | 0% | 0% |  |  |  | 7% | 13% | 0% | 7% | 0% | 7% | 80% |  | 7% | 7% | 0% | N/A | 7% | 7% | 0% | 13% | 20% | N/A | N/A | N/A | N/A | N/A | N/A | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Ribbons | Jacked up Schedule 2 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 2 | 1 | 1 | 0 | 0 | 0 | N/A | 6 | 6 | 1 | 0 | 2 | 2026-07-30 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 2 | 13 | 6 | 3 | 3 | 0 | 1:01 | 0.27 | 5 | 3 | 2 | 0 | 1:01 | 2 | 3 | 5 | -0.25 | 2.4 | 0 | N/A | N/A | N/A | 0 | 0 | N/A | 0 | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | 1 | 0 | 3 | 2 | 13 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 2 | 1 | 1 | 0 | 0 | 0 | N/A | 6 | 6 | 1 | 0 | 2 | 2026-07-30 | 0 | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 5 | 2.33 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | 0 | 0 | ✓ | N/A | 0 | 0
Ribbons | Jacked up Schedule 2 | [402 empty] | ( N/A ) | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 0% | 0% | N/A | 33% | 17% | 17% | ( N/A ) | 0% | 0% | 0% | 100% | 100% | 17% | 0% | 33% |  | 17% | 0% | 50% | 0% | 0% | 0% | 0% | 17% | ( N/A ) | 17% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 33% | 0% | ( N/A ) | 17% | 33% |  | 100% | 50% | 50% | 0% |  |  | 83% | 60% | 40% | 0% |  | 33% | 50% | 83% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | N/A | N/A |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 17% | 0% | 50% | 33% |  |  | 0% | 0% | 0% | 0% | 17% | ( N/A ) | 17% | ( N/A ) |  |  | 33% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | N/A | 33% | 17% | 17% | 0% | 0% | 0% | 0% | 100% | 100% | 17% | 0% | 33% |  |  |  | 17% | 17% | 0% | 0% | 0% | 0% | 83% |  | 17% | 17% | 0% | N/A | 0% | 0% | 0% | 17% | 33% | N/A | N/A | N/A | N/A | N/A | N/A | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Ribbons | Hard_File_updated3 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 2026-10-12 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 76 | 11 | 49 | 43 | 68 | 16 | 52 | 0 | 1:03 | -10.94 | 49 | 9 | 40 | 0 | 1:04 | 49 | 0 | 56 | -18.17 | 2.12 | 0 | N/A | N/A | N/A | 0 | 0 | 0.47 | 68 | 32 | 36 | 2026-10-12 | 0.47 | 68 | 32 | 36 | 0.47 | 32 | N/A | 2026-10-12 | 0.53 | 19 | 10 | 9 | 0.53 | 10 | N/A | 2026-10-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | 11 | 0 | 0 | 49 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 4 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 2026-10-12 | -84 | 1.25 | 3 | 6 | 0 | 0 | 0 | 0 | 107 | 2.09 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 1 | 60 | ✓ | 0.11 | 0.47 | 0
Ribbons | Hard_File_updated3 | [402 empty] | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 79% | 0% | 9% | 0% | 9% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 72% |  | 19% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 6% | 0% | 90% | 16% | 72% |  | 62% | 24% | 76% | 0% |  |  | 72% | 18% | 82% | 0% |  | 72% | 0% | 82% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 47% | 53% |  |  |  | 47% | 53% |  | 47% |  |  |  |  | 53% | 47% |  | 53% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 16% | 0% | 0% | 72% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 6% | 0% | 88% | 0% | 0% | 0% | 0% | 0% | 0% | 79% | 0% | 9% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 72% |  |  |  | 3% | 5% | 0% | 0% | 0% | 0% | 97% |  | 1% | 1% | 0% | 0% | 0% | 0% | 4% | 2% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 77% | 0% | 0% | 0% | 2% | 88%
Ribbons | Hard_File_updated4 24 hour calendar | [402 empty] | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2026-11-12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 74 | 3 | 15 | 34 | 19 | 5 | 14 | 4 | 1:03 | N/A | 15 | 4 | 11 | 1 | 1:03 | 15 | 0 | 16 | N/A | 2.07 | 0 | N/A | N/A | N/A | 0 | 0 | 0.83 | 84 | 70 | 14 | 2026-11-12 | 0.83 | 84 | 70 | 14 | 0.83 | 70 | N/A | 2026-11-12 | 0.81 | 26 | 21 | 5 | 0.81 | 21 | N/A | 2026-11-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | 3 | 0 | 0 | 15 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 74 | 0 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2026-11-12 | -1700 | 1.31 | 3 | 6 | 0 | 0 | 0 | 0 | 107 | 2.09 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 1 | 0 | 0 | 74 | ✓ | -2.5 | 0.85 | 0
Ribbons | Hard_File_updated4 24 hour calendar | [402 empty] | 0% | 0% | 16% | 0% | 0% | 0% | 0% | 64% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 79% |  | 21% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 90% | 16% | 79% |  | 17% | 26% | 74% | 21% |  |  | 79% | 27% | 73% | 7% |  | 79% | 0% | 84% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 83% | 17% |  |  |  | 83% | 17% |  | 83% |  |  |  |  | 81% | 19% |  | 81% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 16% | 0% | 0% | 79% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 90% | 0% | 16% | 0% | 0% | 0% | 0% | 64% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 79% |  |  |  | 3% | 5% | 0% | 0% | 0% | 0% | 97% |  | 1% | 1% | 0% | 0% | 0% | 0% | 4% | 2% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 92% | 0% | 8% | 0% | 0% | 90%
Ribbons | Hard_File | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 68 | 0 | 7 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-07 | 20 | 2 | 78 | 0 | 0 | 0 | 0 | 0 | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 54 | 110 | 25 | 85 | 0 | 1:03 | N/A | 34 | 7 | 27 | 0 | 1:04 | 0 | 78 | 90 | N/A | 2.21 | 0 | N/A | N/A | N/A | 0 | 0 | N/A | 0 | N/A | N/A | 2026-07-07 | N/A | 0 | N/A | N/A | N/A | 0 | N/A | 2026-07-07 | N/A | 0 | N/A | N/A | N/A | 0 | N/A | 2026-07-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-07 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-07 | 20 | 2 | 78 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 68 | 0 | 7 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-07 | 0 | N/A | 1 | 6 | 0 | 0 | 0 | 0 | 109 | 2.07 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 2 | 0 | ✓ | 1 | N/A | 0
Ribbons | Hard_File | [402 empty] | ( N/A ) | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 1% | 80% | 0% | 6% | 1% | 5% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 18% | 2% | 71% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 1% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 18% | 0% |  | 100% | 23% | 77% | 0% |  |  | 31% | 21% | 79% | 0% |  | 0% | 71% | 82% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | N/A | N/A |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 18% | 2% | 71% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 1% | ( N/A ) |  |  | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 0% | 1% | 80% | 0% | 6% | 1% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 5% | 0% | 0% | 0% | 0% | 99% |  | 1% | 1% | 0% | 0% | 0% | 0% | 1% | 5% | 6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 2% | ( N/A )
Ribbons | Hard_File_updated | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 65 | 0 | 8 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-08-11 | 23 | 6 | 74 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 12 | 17 | 0 | 54 | 103 | 24 | 79 | 1 | 1:03 | N/A | 33 | 6 | 27 | 0 | 1:05 | 0 | 74 | 81 | N/A | 2.12 | 0 | N/A | N/A | N/A | 0 | 0 | 0.27 | 11 | 3 | 8 | 2026-08-11 | 0.27 | 11 | 3 | 8 | 0.55 | 6 | 3 | 2026-08-11 | 0.33 | 3 | 1 | 2 | 0.33 | 1 | N/A | 2026-08-11 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 3 | 2026-08-11 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 3 | 2026-08-11 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-11 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-11 | 17 | 6 | 74 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 1 | 65 | 0 | 8 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-08-11 | 51 | 0.8 | 3 | 7 | 0 | 0 | 0 | 0 | 107 | 2.05 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 9 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 9 | ✓ | 1 | 0.55 | 0
Ribbons | Hard_File_updated | [402 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 82% | 0% | 8% | 0% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 22% | 6% | 72% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 14% | 17% | 0% |  | 94% | 23% | 77% | 1% |  |  | 32% | 18% | 82% | 0% |  | 0% | 72% | 79% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 27% | 73% |  |  |  | 27% | 73% |  | 55% |  |  |  |  | 33% | 67% |  | 33% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 17% | 6% | 72% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 82% | 0% | 0% | 0% | 0% | 0% | 1% | 82% | 0% | 8% | 0% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 3% | 6% | 0% | 0% | 0% | 0% | 97% |  | 1% | 1% | 0% | 0% | 0% | 0% | 1% | 5% | 9% | 1% | 0% | 0% | 0% | 0% | 0% | 4% | 0% | 0% | 0% | 0% | 3% | 82%
Ribbons | Hard_File_updated_with_logic_reestablished | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 65 | 0 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 2026-08-11 | 17 | 9 | 8 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 0 | 1 | 0 | 77 | 16 | 76 | 62 | 103 | 24 | 79 | 1 | 1:03 | N/A | 84 | 17 | 67 | 1 | 1:04 | 76 | 8 | 87 | N/A | 2.17 | 0 | N/A | N/A | N/A | 0 | 0 | 0.27 | 11 | 3 | 8 | 2026-08-11 | 0.27 | 11 | 3 | 8 | 0.55 | 6 | 3 | 2026-08-11 | 0.33 | 3 | 1 | 2 | 0.33 | 1 | N/A | 2026-08-11 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 3 | 2026-08-11 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 3 | 2026-08-11 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-11 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-11 | 16 | 9 | 8 | 76 | 62 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 1 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 1 | 65 | 0 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 2026-08-11 | 51 | 0.8 | 2 | 7 | 0 | 0 | 0 | 0 | 108 | 2.07 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 8 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 60 | 0 | 0 | 0 | 2 | 9 | ✓ | 0.89 | 0.55 | 0
Ribbons | Hard_File_updated_with_logic_reestablished | [402 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 82% | 0% | 7% | 0% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 74% |  | 17% | 9% | 8% | 0% | 0% | 0% | 0% | 1% | ( N/A ) | 1% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 1% | 0% | 92% | 16% | 74% |  | 94% | 23% | 77% | 1% |  |  | 82% | 20% | 80% | 1% |  | 74% | 8% | 84% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 27% | 73% |  |  |  | 27% | 73% |  | 55% |  |  |  |  | 33% | 67% |  | 33% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 16% | 9% | 8% | 74% |  |  | 0% | 0% | 0% | 0% | 1% | ( N/A ) | 1% | ( N/A ) |  |  | 1% | 0% | 82% | 0% | 0% | 0% | 0% | 0% | 1% | 82% | 0% | 7% | 0% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 74% |  |  |  | 2% | 6% | 0% | 0% | 0% | 0% | 98% |  | 1% | 1% | 0% | 0% | 0% | 0% | 1% | 5% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 6% | 77% | 0% | 0% | 0% | 3% | 82%
Ribbons | Hard_File_updated2 | [402 empty] | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 47 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-09-10 | 23 | 5 | 25 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 72 | 22 | 0 | 61 | 76 | 18 | 58 | 0 | 1:03 | 7.68 | 24 | 5 | 19 | 0 | 1:04 | 0 | 25 | 54 | 0.52 | 2.13 | 0 | N/A | N/A | N/A | 0 | 0 | 0.59 | 44 | 26 | 18 | 2026-09-10 | 0.59 | 44 | 26 | 18 | 0.59 | 26 | N/A | 2026-09-10 | 0.62 | 13 | 8 | 5 | 0.62 | 8 | N/A | 2026-09-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | 22 | 5 | 25 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 33 | 0 | 42 | 0 | 0 | 0 | 0 | 47 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-09-10 | -73 | 1.14 | 3 | 6 | 0 | 0 | 0 | 0 | 107 | 2.07 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 8 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 30 | 0 | 1 | 33 | ✓ | 1 | 0.59 | 0
Ribbons | Hard_File_updated2 | [402 empty] | 0% | 0% | 55% | ( N/A ) | 0% | 0% | 0% | 81% | 0% | 8% | 0% | 8% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 30% | 7% | 33% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 86% | 29% | 0% |  | 69% | 24% | 76% | 0% |  |  | 32% | 21% | 79% | 0% |  | 0% | 33% | 71% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 59% | 41% |  |  |  | 59% | 41% |  | 59% |  |  |  |  | 62% | 38% |  | 62% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 29% | 7% | 33% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 75% | 0% | 55% | 0% | 0% | 0% | 0% | 81% | 0% | 8% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 3% | 5% | 0% | 0% | 0% | 0% | 97% |  | 1% | 1% | 0% | 0% | 0% | 0% | 1% | 5% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 3% | 0% | 0% | 52% | 0% | 2% | 75%
Ribbons | Hard_File_updated3 2 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 2026-10-12 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 76 | 11 | 49 | 43 | 68 | 16 | 52 | 0 | 1:03 | -10.94 | 49 | 9 | 40 | 0 | 1:04 | 49 | 0 | 56 | -18.17 | 2.12 | 0 | N/A | N/A | N/A | 0 | 0 | 0.47 | 68 | 32 | 36 | 2026-10-12 | 0.47 | 68 | 32 | 36 | 0.47 | 32 | N/A | 2026-10-12 | 0.53 | 19 | 10 | 9 | 0.53 | 10 | N/A | 2026-10-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | 11 | 0 | 0 | 49 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 4 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 2026-10-12 | -84 | 1.25 | 3 | 6 | 0 | 0 | 0 | 0 | 107 | 2.09 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 1 | 60 | ✓ | 0.11 | 0.47 | 0
Ribbons | Hard_File_updated3 2 | [402 empty] | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 79% | 0% | 9% | 0% | 9% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 72% |  | 19% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 6% | 0% | 90% | 16% | 72% |  | 62% | 24% | 76% | 0% |  |  | 72% | 18% | 82% | 0% |  | 72% | 0% | 82% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 47% | 53% |  |  |  | 47% | 53% |  | 47% |  |  |  |  | 53% | 47% |  | 53% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 16% | 0% | 0% | 72% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 6% | 0% | 88% | 0% | 0% | 0% | 0% | 0% | 0% | 79% | 0% | 9% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 72% |  |  |  | 3% | 5% | 0% | 0% | 0% | 0% | 97% |  | 1% | 1% | 0% | 0% | 0% | 0% | 4% | 2% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 77% | 0% | 0% | 0% | 2% | 88%
Ribbons | Hard_File_updated4 24 hour calendar 2 | [402 empty] | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2026-11-12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 74 | 3 | 15 | 34 | 19 | 5 | 14 | 4 | 1:03 | N/A | 15 | 4 | 11 | 1 | 1:03 | 15 | 0 | 16 | N/A | 2.07 | 0 | N/A | N/A | N/A | 0 | 0 | 0.83 | 84 | 70 | 14 | 2026-11-12 | 0.83 | 84 | 70 | 14 | 0.83 | 70 | N/A | 2026-11-12 | 0.81 | 26 | 21 | 5 | 0.81 | 21 | N/A | 2026-11-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | 3 | 0 | 0 | 15 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 74 | 0 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2026-11-12 | -1700 | 1.31 | 3 | 6 | 0 | 0 | 0 | 0 | 107 | 2.09 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 1 | 0 | 0 | 74 | ✓ | -2.5 | 0.85 | 0
Ribbons | Hard_File_updated4 24 hour calendar 2 | [402 empty] | 0% | 0% | 16% | 0% | 0% | 0% | 0% | 64% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 79% |  | 21% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 90% | 16% | 79% |  | 17% | 26% | 74% | 21% |  |  | 79% | 27% | 73% | 7% |  | 79% | 0% | 84% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 83% | 17% |  |  |  | 83% | 17% |  | 83% |  |  |  |  | 81% | 19% |  | 81% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 16% | 0% | 0% | 79% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 90% | 0% | 16% | 0% | 0% | 0% | 0% | 64% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 79% |  |  |  | 3% | 5% | 0% | 0% | 0% | 0% | 97% |  | 1% | 1% | 0% | 0% | 0% | 0% | 4% | 2% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 92% | 0% | 8% | 0% | 0% | 90%
Ribbons | EVM1 | [402 empty] | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2012-09-01 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 3 | 8 | 2 | 1:03 | N/A | 10 | 3 | 7 | 1 | 1:02 | 0 | 10 | 11 | N/A | 1.9 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 5 | 0 | 5 | 2012-09-01 | 0 | 5 | 0 | 5 | 0 | 0 | N/A | 2012-09-01 | 0 | 2 | 0 | 2 | 0 | 0 | N/A | 2012-09-01 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2012-09-01 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2012-09-01 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2012-09-01 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2012-09-01 | 0 | 0 | 10 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2012-09-01 | -34 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 10 | 1.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | ✓ | 1 | 0 | 0
Ribbons | EVM1 | [402 empty] | 0% | ( N/A ) | 109% | 0% | 0% | 0% | 0% | 0% | 0% | 18% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 91% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 0% | 0% |  | 100% | 27% | 73% | 18% |  |  | 91% | 30% | 70% | 10% |  | 0% | 91% | 100% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 0% | 100% |  |  |  | 0% | 100% |  | 0% |  |  |  |  | 0% | 100% |  | 0% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 0% | 0% | 91% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 0% | 0% | 109% | 0% | 0% | 0% | 0% | 0% | 0% | 18% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 9% | 9% | 0% | 0% | 0% | 0% | 91% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9% | 18% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0%
Ribbons | EVM2 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2012-09-12 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 8 | 2 | 6 | 1 | 1:03 | 0 | 8 | 2 | 6 | 1 | 1:03 | 0 | 8 | 8 | 0 | 2.13 | 0 | N/A | N/A | N/A | 0 | 0 | 0.25 | 8 | 2 | 6 | 2012-09-12 | 0.25 | 8 | 2 | 6 | 0.25 | 2 | N/A | 2012-09-12 | 0.33 | 3 | 1 | 2 | 0.33 | 1 | N/A | 2012-09-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2012-09-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2012-09-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2012-09-12 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2012-09-12 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2012-09-12 | -23 | 0.56 | 1 | 1 | 0 | 0 | 0 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | ✓ | 1 | 0.25 | 0
Ribbons | EVM2 | [402 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13% | 0% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 88% | 0% | 0% |  | 73% | 25% | 75% | 13% |  |  | 100% | 25% | 75% | 13% |  | 0% | 100% | 100% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 25% | 75% |  |  |  | 25% | 75% |  | 25% |  |  |  |  | 33% | 67% |  | 33% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 0% | 0% | 100% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 88% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13% | 0% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 9% | 9% | 0% | 0% | 0% | 0% | 91% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9% | 18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 88%
Ribbons | Project2 3 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-24 | 42 | 44 | 41 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 39 | 0 | 263 | 106 | 0 | 106 | 3 | N/A | 14.01 | 41 | 0 | 41 | 1 | N/A | 0 | 41 | 50 | 0.05 | 3.2 | 0 | N/A | N/A | N/A | 0 | 0 | 0.74 | 27 | 20 | 7 | 2026-05-24 | 0.74 | 27 | 20 | 7 | 0.74 | 20 | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 39 | 44 | 41 | 0 | 263 | 0 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-24 | -454 | 0.83 | 1 | 5 | 2 | 0 | 0 | 1 | 125 | 2.79 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 0 | 2 | 1 | 0 | 0 | 44 | 0 | 1 | 0 | 0 | 0 | 18 | ✓ | 1 | 0.74 | 0
Ribbons | Project2 3 | [402 empty] | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 40% | 42% | 39% | 0% | 2% | 1% | 2% | 3% | 0% | 8% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 37% | 0% |  | 84% | 0% | 100% | 3% |  |  | 39% | 0% | 100% | 2% |  | 0% | 39% | 47% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 74% | 26% |  |  |  | 74% | 26% |  | 74% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 37% | 42% | 39% | 0% |  |  | 0% | 2% | 1% | 2% | 3% | 0% | 8% | 0% |  |  | 0% | 0% | 67% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 4% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 4% | 5% | 4% | 0% | 1% | 1% | 0% | 0% | 42% | 0% | 1% | 0% | 0% | 0% | 67%
Ribbons | Project3 2 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-30 | 40 | 42 | 40 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 31 | 0 | 223 | 102 | 0 | 102 | 1 | N/A | 13.83 | 40 | 0 | 40 | 1 | N/A | 0 | 40 | 49 | 0.05 | 3.23 | 0 | N/A | N/A | N/A | 0 | 0 | 0.67 | 36 | 24 | 12 | 2026-06-30 | 0.67 | 36 | 24 | 12 | 0.67 | 24 | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | 31 | 42 | 40 | 0 | 223 | 0 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-30 | -550 | 0.88 | 1 | 5 | 2 | 0 | 0 | 1 | 125 | 2.79 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 0 | 2 | 1 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 27 | x | 1 | 0.67 | 0
Ribbons | Project3 2 | [402 empty] | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 39% | 41% | 39% | 0% | 2% | 1% | 3% | 3% | 0% | 8% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 30% | 0% |  | 81% | 0% | 100% | 1% |  |  | 39% | 0% | 100% | 3% |  | 0% | 39% | 48% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 67% | 33% |  |  |  | 67% | 33% |  | 67% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 30% | 41% | 39% | 0% |  |  | 0% | 2% | 1% | 3% | 3% | 0% | 8% | 0% |  |  | 0% | 0% | 75% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 4% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 4% | 5% | 4% | 0% | 1% | 1% | 0% | 0% | 41% | 0% | 0% | 0% | 0% | 0% | 75%
Ribbons | Project4 2 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-29 | 39 | 41 | 37 | 0 | 1 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 31 | 0 | 230 | 101 | 0 | 101 | 1 | N/A | 13.76 | 37 | 0 | 37 | 0 | N/A | 0 | 37 | 48 | 0.13 | 3.32 | 0 | N/A | N/A | N/A | 0 | 0 | 0.58 | 43 | 25 | 18 | 2026-07-29 | 0.58 | 43 | 25 | 18 | 0.58 | 25 | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | 31 | 41 | 37 | 0 | 230 | 0 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-29 | -630 | 0.89 | 1 | 5 | 2 | 0 | 0 | 1 | 125 | 2.83 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 0 | 1 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 34 | ✓ | 1 | 0.58 | 0
Ribbons | Project4 2 | [402 empty] | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 39% | 41% | 37% | 0% | 1% | 1% | 3% | 3% | 0% | 8% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 31% | 0% |  | 80% | 0% | 100% | 1% |  |  | 37% | 0% | 100% | 0% |  | 0% | 37% | 48% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 58% | 42% |  |  |  | 58% | 42% |  | 58% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 31% | 41% | 37% | 0% |  |  | 0% | 2% | 1% | 3% | 3% | 0% | 8% | 0% |  |  | 0% | 0% | 79% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 4% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 4% | 5% | 4% | 0% | 1% | 0% | 0% | 0% | 41% | 0% | 0% | 0% | 0% | 0% | 79%
Ribbons | Project5_TAMPERED 2 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 43 | 44 | 4 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 41 | 0 | 275 | 99 | 0 | 99 | 2 | N/A | 22.02 | 4 | 0 | 4 | 0 | N/A | 0 | 4 | 5 | 0.1 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 0.59 | 46 | 27 | 19 | 2026-08-27 | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 41 | 44 | 4 | 0 | 275 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | -902 | 0.91 | 1 | 6 | 2 | 0 | 0 | 1 | 125 | 2.81 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 7 | 7 | 5 | 0 | 1 | 0 | 0 | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 37 | ✓ | 1 | 0.59 | 0
Ribbons | Project5_TAMPERED 2 | [402 empty] | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  | 43% | 44% | 4% | 0% | 1% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 41% | 0% |  | 79% | 0% | 100% | 2% |  |  | 4% | 0% | 100% | 0% |  | 0% | 4% | 5% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 59% | 41% |  |  |  | 59% | 41% |  | 59% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 41% | 44% | 4% | 0% |  |  | 0% | 2% | 1% | 0% | 1% | 0% | 0% | 0% |  |  | 0% | 0% | 80% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  |  |  | 1% | 5% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 5% | 6% | 5% | 0% | 1% | 0% | 0% | 1% | 44% | 0% | 0% | 0% | 0% | 0% | 80%
Ribbons | TP4_DataCenter_v1 2 | [402 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-01-30 | 4 | 1 | 8 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 45 | 13 | 1 | 12 | 1 | 1:12 | 0.63 | 8 | 1 | 7 | 1 | 1:07 | 0 | 8 | 9 | 0.03 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 1 | 1 | 1 | 0 | 2026-01-30 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-01-30 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-01-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | 2 | 1 | 8 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-01-30 | -4 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 12 | 0 | ✓ | 1 | 1 | 0
Ribbons | TP4_DataCenter_v1 2 | [402 empty] | 0% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 31% | 8% | 62% | 0% | 0% | 0% | 0% | 8% | ( N/A ) | 8% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 15% | 0% |  | 87% | 8% | 92% | 8% |  |  | 62% | 13% | 88% | 13% |  | 0% | 62% | 69% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 100% | 0% |  |  |  | 100% | 0% |  | 100% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 15% | 8% | 62% | 0% |  |  | 0% | 0% | 0% | 0% | 8% | ( N/A ) | 8% | ( N/A ) |  |  | 0% | 0% | 0% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 0% | 0% | 8% | 0% | 100% | 0%
Ribbons | TP4_DataCenter_v2 2 | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-02-27 | 3 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 30 | 11 | 1 | 10 | 3 | 1:10 | 0.47 | 7 | 1 | 6 | 1 | 1:06 | 0 | 7 | 8 | 0.04 | 2.86 | 0 | N/A | N/A | N/A | 0 | 0 | 0.75 | 4 | 3 | 1 | 2026-02-27 | 0.75 | 4 | 3 | 1 | 0.75 | 3 | N/A | 2026-02-27 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-02-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | 1 | 0 | 7 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-02-27 | -69 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | ✓ | 1 | 0.75 | 0
Ribbons | TP4_DataCenter_v2 2 | [402 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 27% | 0% | 64% | 0% | 0% | 0% | 0% | 13% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 8% | 9% | 0% |  | 73% | 9% | 91% | 27% |  |  | 64% | 14% | 86% | 14% |  | 0% | 64% | 73% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 75% | 25% |  |  |  | 75% | 25% |  | 75% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 9% | 0% | 64% | 0% |  |  | 0% | 0% | 0% | 0% | 13% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 25%
Ribbons | TP4_DataCenter_v3 2 | [402 empty] | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | 2 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 30 | 9 | 1 | 8 | 2 | 1:08 | 0.34 | 7 | 1 | 6 | 1 | 1:06 | 0 | 7 | 7 | 0 | 2.86 | 0 | N/A | N/A | N/A | 0 | 0 | 0.71 | 7 | 5 | 2 | 2026-03-31 | 0.71 | 7 | 5 | 2 | 0.71 | 5 | N/A | 2026-03-31 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 1 | 0 | 7 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | -123 | 0.67 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 8 | 3 | ✓ | 1 | 0.71 | 0
Ribbons | TP4_DataCenter_v3 2 | [402 empty] | 0% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 22% | 0% | 78% | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 31% | 11% | 0% |  | 60% | 11% | 89% | 22% |  |  | 78% | 14% | 86% | 14% |  | 0% | 78% | 78% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 71% | 29% |  |  |  | 71% | 29% |  | 71% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 11% | 0% | 78% | 0% |  |  | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 43% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 100% | 43%
Ribbons | TP4_DataCenter_v4 2 | [402 empty] | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-04-30 | 2 | 1 | 5 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0 | 50 | 7 | 1 | 6 | 2 | 1:06 | 0.73 | 5 | 1 | 4 | 2 | 1:04 | 0 | 5 | 5 | 0 | 2.6 | 0 | N/A | N/A | N/A | 0 | 0 | 0.78 | 9 | 7 | 2 | 2026-04-30 | 0.78 | 9 | 7 | 2 | 0.78 | 7 | N/A | 2026-04-30 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-04-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | 2 | 1 | 5 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-04-30 | -99 | 0.7 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 6 | 5 | ✓ | 1 | 0.78 | 0
Ribbons | TP4_DataCenter_v4 2 | [402 empty] | 0% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 29% | 14% | 71% | 0% | 0% | 0% | 0% | 20% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 69% | 29% | 0% |  | 47% | 14% | 86% | 29% |  |  | 71% | 20% | 80% | 40% |  | 0% | 71% | 71% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 78% | 22% |  |  |  | 78% | 22% |  | 78% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 29% | 14% | 71% | 0% |  |  | 0% | 0% | 0% | 0% | 20% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 56% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 17% | 0% | 0% | 67% | 0% | 100% | 56%
Ribbons | TP4_DataCenter_v5 2 | [402 empty] | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-05-29 | 2 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 15 | 7 | 1 | 6 | 3 | 1:06 | 0.32 | 5 | 1 | 4 | 1 | 1:04 | 0 | 5 | 5 | 0 | 2.6 | 0 | N/A | N/A | N/A | 0 | 0 | 0.58 | 12 | 7 | 5 | 2026-05-29 | 0.58 | 12 | 7 | 5 | 0.58 | 7 | N/A | 2026-05-29 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-05-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | 0 | 0 | 5 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 9 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-05-29 | -280 | 0.63 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 6 | 9 | ✓ | 1 | 0.58 | 0
Ribbons | TP4_DataCenter_v5 2 | [402 empty] | 0% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 29% | 0% | 71% | 0% | 0% | 0% | 0% | 25% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 77% | 0% | 0% |  | 47% | 14% | 86% | 43% |  |  | 71% | 20% | 80% | 20% |  | 0% | 71% | 71% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 58% | 42% |  |  |  | 58% | 42% |  | 58% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 0% | 0% | 71% | 0% |  |  | 0% | 0% | 0% | 0% | 25% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 75% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 67% | 0% | 100% | 75%
Phase Analyzer | Status Date | 2012-08-01: 2012-09-01; 2012-09-01: 2012-09-12; 2012-10-01: 2012-09-12; 2012-11-01: N/A; 2012-12-01: N/A; 2013-01-01: N/A; 2013-02-01: N/A; 2013-03-01: N/A; 2013-04-01: N/A; 2013-05-01: N/A; 2013-06-01: N/A; 2013-07-01: N/A; 2013-08-01: N/A; 2013-09-01: N/A; 2013-10-01: N/A; 2013-11-01: N/A; 2013-12-01: N/A; 2014-01-01: N/A; 2014-02-01: N/A; 2014-03-01: N/A; 2014-04-01: N/A; 2014-05-01: N/A; 2014-06-01: N/A; 2014-07-01: N/A; 2014-08-01: N/A; 2014-09-01: N/A; 2014-10-01: N/A; 2014-11-01: N/A; 2014-12-01: N/A; 2015-01-01: N/A; 2015-02-01: N/A; 2015-03-01: N/A; 2015-04-01: N/A; 2015-05-01: N/A; 2015-06-01: N/A; 2015-07-01: N/A; 2015-08-01: N/A; 2015-09-01: N/A; 2015-10-01: N/A; 2015-11-01: N/A; 2015-12-01: N/A; 2016-01-01: N/A; 2016-02-01: N/A; 2016-03-01: N/A; 2016-04-01: N/A; 2016-05-01: N/A; 2016-06-01: N/A; 2016-07-01: N/A; 2016-08-01: N/A; 2016-09-01: N/A; 2016-10-01: N/A; 2016-11-01: N/A; 2016-12-01: N/A; 2017-01-01: N/A; 2017-02-01: N/A; 2017-03-01: N/A; 2017-04-01: N/A; 2017-05-01: N/A; 2017-06-01: 2025-03-10; 2017-07-01: 2025-03-10; 2017-08-01: 2025-03-10; 2017-09-01: 2025-03-10; 2017-10-01: 2025-03-10; 2017-11-01: 2025-03-10; 2017-12-01: 2025-03-10; 2018-01-01: 2025-03-10; 2018-02-01: 2025-03-10; 2018-03-01: 2025-03-10; 2018-04-01: 2025-03-10; 2018-05-01: 2025-03-10; 2018-06-01: 2025-03-10; 2018-07-01: 2025-03-10; 2018-08-01: 2025-03-10; 2018-09-01: 2025-03-10; 2018-10-01: 2025-03-10; 2018-11-01: 2025-03-10; 2018-12-01: 2025-03-10; 2019-01-01: 2025-03-10; 2019-02-01: 2025-03-10; 2019-03-01: 2025-03-10; 2019-04-01: 2025-03-10; 2019-05-01: 2025-03-10; 2019-06-01: 2025-03-10; 2019-07-01: 2025-03-10; 2019-08-01: 2025-03-10; 2019-09-01: 2025-03-10; 2019-10-01: 2025-03-10; 2019-11-01: 2025-03-10; 2019-12-01: 2025-03-10; 2020-01-01: 2025-03-10; 2020-02-01: 2025-03-10; 2020-03-01: 2025-03-10; 2020-04-01: 2025-03-10; 2020-05-01: 2025-03-10; 2020-06-01: 2025-03-10; 2020-07-01: 2025-03-10; 2020-08-01: 2025-03-10; 2020-09-01: 2025-03-10; 2020-10-01: 2025-03-10; 2020-11-01: 2025-03-10; 2020-12-01: 2025-03-10; 2021-01-01: 2025-03-10; 2021-02-01: 2025-03-10; 2021-03-01: 2025-03-10; 2021-04-01: 2025-03-10; 2021-05-01: 2025-03-10; 2021-06-01: 2025-03-10; 2021-07-01: 2025-03-10; 2021-08-01: 2025-03-10; 2021-09-01: 2025-03-10; 2021-10-01: 2025-03-10; 2021-11-01: 2025-03-10; 2021-12-01: 2025-03-10; 2022-01-01: 2025-03-10; 2022-02-01: 2025-03-10; 2022-03-01: 2025-03-10; 2022-04-01: 2025-03-10; 2022-05-01: 2025-03-10; 2022-06-01: 2025-03-10; 2022-07-01: 2025-03-10; 2022-08-01: 2025-03-10; 2022-09-01: 2025-03-10; 2022-10-01: 2025-03-10; 2022-11-01: 2025-03-10; 2022-12-01: 2025-03-10; 2023-01-01: 2025-03-10; 2023-02-01: 2025-03-10; 2023-03-01: 2025-03-10; 2023-04-01: 2025-03-10; 2023-05-01: 2025-03-10; 2023-06-01: 2025-03-10; 2023-07-01: 2025-03-10; 2023-08-01: 2025-03-10; 2023-09-01: 2025-03-10; 2023-10-01: 2025-03-10; 2023-11-01: 2025-03-10; 2023-12-01: 2025-03-10; 2024-01-01: 2025-03-10; 2024-02-01: 2025-03-10; 2024-03-01: 2025-03-10; 2024-04-01: 2025-03-10; 2024-05-01: 2025-03-10; 2024-06-01: 2025-03-10; 2024-07-01: 2025-03-10; 2024-08-01: 2025-03-10; 2024-09-01: 2025-03-10; 2024-10-01: 2025-03-10; 2024-11-01: 2025-03-10; 2024-12-01: 2025-03-10; 2025-01-01: 2025-03-10; 2025-02-01: 2025-03-10; 2025-03-01: 2025-03-10; 2025-04-01: 2025-03-10; 2025-05-01: 2025-03-10; 2025-06-01: 2025-03-10; 2025-07-01: 2025-03-10; 2025-08-01: 2025-03-10; 2025-09-01: 2025-03-10; 2025-10-01: 2025-03-10; 2025-11-01: 2025-03-10; 2025-12-01: 2025-03-10; 2026-01-01: 2025-03-10; 2026-02-01: 2025-03-10; 2026-03-01: 2025-03-10; 2026-04-01: 2025-03-10; 2026-05-01: 2025-03-10; 2026-06-01: 2025-03-10; 2026-07-01: 2025-03-10; 2026-08-01: 2025-03-10; 2026-09-01: 2025-03-10; 2026-10-01: 2025-03-10; 2026-11-01: 2025-03-10; 2026-12-01: 2025-03-10; 2027-01-01: 2025-03-10; 2027-02-01: 2025-03-10; 2027-03-01: 2025-03-10; 2027-04-01: 2025-03-10; 2027-05-01: 2025-03-10; 2027-06-01: 2025-03-10; 2027-07-01: 2025-03-10; 2027-08-01: 2025-03-10; 2027-09-01: 2025-03-10; 2027-10-01: 2025-03-10; 2027-11-01: 2025-03-10; 2027-12-01: 2025-03-10; 2028-01-01: 2025-03-10; 2028-02-01: 2025-03-10; 2028-03-01: 2025-03-10; 2028-04-01: 2025-03-10; 2028-05-01: 2025-03-10; 2028-06-01: 2025-03-10; 2028-07-01: 2025-03-10; 2028-08-01: 2025-03-10; 2028-09-01: 2025-03-10; 2028-10-01: 2025-03-10; 2028-11-01: 2025-03-10; 2028-12-01: 2025-03-10; 2029-01-01: 2025-03-10; 2029-02-01: 2025-03-10; 2029-03-01: 2025-03-10; 2029-04-01: 2025-03-10
Phase Analyzer | WBS | 2012-08-01: 1; 2012-09-01: 1; 2012-10-01: 3; 2012-11-01: N/A; 2012-12-01: N/A; 2013-01-01: N/A; 2013-02-01: N/A; 2013-03-01: N/A; 2013-04-01: N/A; 2013-05-01: N/A; 2013-06-01: N/A; 2013-07-01: N/A; 2013-08-01: N/A; 2013-09-01: N/A; 2013-10-01: N/A; 2013-11-01: N/A; 2013-12-01: N/A; 2014-01-01: N/A; 2014-02-01: N/A; 2014-03-01: N/A; 2014-04-01: N/A; 2014-05-01: N/A; 2014-06-01: N/A; 2014-07-01: N/A; 2014-08-01: N/A; 2014-09-01: N/A; 2014-10-01: N/A; 2014-11-01: N/A; 2014-12-01: N/A; 2015-01-01: N/A; 2015-02-01: N/A; 2015-03-01: N/A; 2015-04-01: N/A; 2015-05-01: N/A; 2015-06-01: N/A; 2015-07-01: N/A; 2015-08-01: N/A; 2015-09-01: N/A; 2015-10-01: N/A; 2015-11-01: N/A; 2015-12-01: N/A; 2016-01-01: N/A; 2016-02-01: N/A; 2016-03-01: N/A; 2016-04-01: N/A; 2016-05-01: N/A; 2016-06-01: N/A; 2016-07-01: N/A; 2016-08-01: N/A; 2016-09-01: N/A; 2016-10-01: N/A; 2016-11-01: N/A; 2016-12-01: N/A; 2017-01-01: N/A; 2017-02-01: N/A; 2017-03-01: N/A; 2017-04-01: N/A; 2017-05-01: N/A; 2017-06-01: 1; 2017-07-01: 1; 2017-08-01: 1; 2017-09-01: 1; 2017-10-01: 1; 2017-11-01: 1; 2017-12-01: 1; 2018-01-01: 1; 2018-02-01: 1; 2018-03-01: 1; 2018-04-01: 1; 2018-05-01: 1; 2018-06-01: 1; 2018-07-01: 1; 2018-08-01: 1; 2018-09-01: 1; 2018-10-01: 1; 2018-11-01: 1; 2018-12-01: 1; 2019-01-01: 1; 2019-02-01: 1; 2019-03-01: 1; 2019-04-01: 1; 2019-05-01: 1; 2019-06-01: 1; 2019-07-01: 1; 2019-08-01: 1; 2019-09-01: 1; 2019-10-01: 1; 2019-11-01: 1; 2019-12-01: 1; 2020-01-01: 1; 2020-02-01: 1; 2020-03-01: 1; 2020-04-01: 1; 2020-05-01: 1; 2020-06-01: 1; 2020-07-01: 1; 2020-08-01: 1; 2020-09-01: 1; 2020-10-01: 1; 2020-11-01: 1; 2020-12-01: 1; 2021-01-01: 1; 2021-02-01: 1; 2021-03-01: 1; 2021-04-01: 1; 2021-05-01: 1; 2021-06-01: 1; 2021-07-01: 1; 2021-08-01: 1; 2021-09-01: 1; 2021-10-01: 1; 2021-11-01: 1; 2021-12-01: 1; 2022-01-01: 1; 2022-02-01: 1; 2022-03-01: 1; 2022-04-01: 1; 2022-05-01: 1; 2022-06-01: 1; 2022-07-01: 1; 2022-08-01: 1; 2022-09-01: 1; 2022-10-01: 1; 2022-11-01: 1; 2022-12-01: 1; 2023-01-01: 1; 2023-02-01: 1; 2023-03-01: 1; 2023-04-01: 1; 2023-05-01: 1; 2023-06-01: 1; 2023-07-01: 1; 2023-08-01: 1; 2023-09-01: 1; 2023-10-01: 1; 2023-11-01: 1; 2023-12-01: 1; 2024-01-01: 1; 2024-02-01: 1; 2024-03-01: 1; 2024-04-01: 1; 2024-05-01: 1; 2024-06-01: 1; 2024-07-01: 1; 2024-08-01: 1; 2024-09-01: 1; 2024-10-01: 1; 2024-11-01: 1; 2024-12-01: 1; 2025-01-01: 1; 2025-02-01: 1; 2025-03-01: 1; 2025-04-01: 1; 2025-05-01: 1; 2025-06-01: 1; 2025-07-01: 1; 2025-08-01: 1; 2025-09-01: 1; 2025-10-01: 1; 2025-11-01: 1; 2025-12-01: 1; 2026-01-01: 1; 2026-02-01: 1; 2026-03-01: 1; 2026-04-01: 1; 2026-05-01: 1; 2026-06-01: 1; 2026-07-01: 1; 2026-08-01: 1; 2026-09-01: 1; 2026-10-01: 1; 2026-11-01: 1; 2026-12-01: 1; 2027-01-01: 1; 2027-02-01: 1; 2027-03-01: 1; 2027-04-01: 1; 2027-05-01: 1; 2027-06-01: 1; 2027-07-01: 1; 2027-08-01: 1; 2027-09-01: 1; 2027-10-01: 1; 2027-11-01: 1; 2027-12-01: 1; 2028-01-01: 1; 2028-02-01: 1; 2028-03-01: 1; 2028-04-01: 1; 2028-05-01: 1; 2028-06-01: 1; 2028-07-01: 1; 2028-08-01: 1; 2028-09-01: 1; 2028-10-01: 1; 2028-11-01: 1; 2028-12-01: 1; 2029-01-01: 1; 2029-02-01: 1; 2029-03-01: 1; 2029-04-01: 1
Phase Analyzer | New Activity - Created (Snapshot) | 2012-08-01: 0; 2012-09-01: 0; 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0; 2013-06-01: 0; 2013-07-01: 0; 2013-08-01: 0; 2013-09-01: 0; 2013-10-01: 0; 2013-11-01: 0; 2013-12-01: 0; 2014-01-01: 0; 2014-02-01: 0; 2014-03-01: 0; 2014-04-01: 0; 2014-05-01: 0; 2014-06-01: 0; 2014-07-01: 0; 2014-08-01: 0; 2014-09-01: 0; 2014-10-01: 0; 2014-11-01: 0; 2014-12-01: 0; 2015-01-01: 0; 2015-02-01: 0; 2015-03-01: 0; 2015-04-01: 0; 2015-05-01: 0; 2015-06-01: 0; 2015-07-01: 0; 2015-08-01: 0; 2015-09-01: 0; 2015-10-01: 0; 2015-11-01: 0; 2015-12-01: 0; 2016-01-01: 0; 2016-02-01: 0; 2016-03-01: 0; 2016-04-01: 0; 2016-05-01: 0; 2016-06-01: 0; 2016-07-01: 0; 2016-08-01: 0; 2016-09-01: 0; 2016-10-01: 0; 2016-11-01: 0; 2016-12-01: 0; 2017-01-01: 0; 2017-02-01: 0; 2017-03-01: 0; 2017-04-01: 0; 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0; 2018-01-01: 0; 2018-02-01: 0; 2018-03-01: 0; 2018-04-01: 0; 2018-05-01: 0; 2018-06-01: 0; 2018-07-01: 0; 2018-08-01: 0; 2018-09-01: 0; 2018-10-01: 0; 2018-11-01: 0; 2018-12-01: 0; 2019-01-01: 0; 2019-02-01: 0; 2019-03-01: 0; 2019-04-01: 0; 2019-05-01: 0; 2019-06-01: 0; 2019-07-01: 0; 2019-08-01: 0; 2019-09-01: 0; 2019-10-01: 0; 2019-11-01: 0; 2019-12-01: 0; 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0; 2023-09-01: 0; 2023-10-01: 0; 2023-11-01: 0; 2023-12-01: 0; 2024-01-01: 0; 2024-02-01: 0; 2024-03-01: 0; 2024-04-01: 0; 2024-05-01: 0; 2024-06-01: 0; 2024-07-01: 0; 2024-08-01: 0; 2024-09-01: 0; 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 0; 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 0; 2025-12-01: 0; 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0; 2026-11-01: 0; 2026-12-01: 0; 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0; 2027-06-01: 0; 2027-07-01: 0; 2027-08-01: 0; 2027-09-01: 0; 2027-10-01: 0; 2027-11-01: 0; 2027-12-01: 0; 2028-01-01: 0; 2028-02-01: 0; 2028-03-01: 0; 2028-04-01: 0; 2028-05-01: 0; 2028-06-01: 0; 2028-07-01: 0; 2028-08-01: 0; 2028-09-01: 0; 2028-10-01: 0; 2028-11-01: 0; 2028-12-01: 0; 2029-01-01: 0; 2029-02-01: 0; 2029-03-01: 0; 2029-04-01: 0
Phase Analyzer | New Activity - Already Finished (Snapshot) - check/compare | 2012-08-01: 0; 2012-09-01: 0; 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0; 2013-06-01: 0; 2013-07-01: 0; 2013-08-01: 0; 2013-09-01: 0; 2013-10-01: 0; 2013-11-01: 0; 2013-12-01: 0; 2014-01-01: 0; 2014-02-01: 0; 2014-03-01: 0; 2014-04-01: 0; 2014-05-01: 0; 2014-06-01: 0; 2014-07-01: 0; 2014-08-01: 0; 2014-09-01: 0; 2014-10-01: 0; 2014-11-01: 0; 2014-12-01: 0; 2015-01-01: 0; 2015-02-01: 0; 2015-03-01: 0; 2015-04-01: 0; 2015-05-01: 0; 2015-06-01: 0; 2015-07-01: 0; 2015-08-01: 0; 2015-09-01: 0; 2015-10-01: 0; 2015-11-01: 0; 2015-12-01: 0; 2016-01-01: 0; 2016-02-01: 0; 2016-03-01: 0; 2016-04-01: 0; 2016-05-01: 0; 2016-06-01: 0; 2016-07-01: 0; 2016-08-01: 0; 2016-09-01: 0; 2016-10-01: 0; 2016-11-01: 0; 2016-12-01: 0; 2017-01-01: 0; 2017-02-01: 0; 2017-03-01: 0; 2017-04-01: 0; 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0; 2018-01-01: 0; 2018-02-01: 0; 2018-03-01: 0; 2018-04-01: 0; 2018-05-01: 0; 2018-06-01: 0; 2018-07-01: 0; 2018-08-01: 0; 2018-09-01: 0; 2018-10-01: 0; 2018-11-01: 0; 2018-12-01: 0; 2019-01-01: 0; 2019-02-01: 0; 2019-03-01: 0; 2019-04-01: 0; 2019-05-01: 0; 2019-06-01: 0; 2019-07-01: 0; 2019-08-01: 0; 2019-09-01: 0; 2019-10-01: 0; 2019-11-01: 0; 2019-12-01: 0; 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0; 2023-09-01: 0; 2023-10-01: 0; 2023-11-01: 0; 2023-12-01: 0; 2024-01-01: 0; 2024-02-01: 0; 2024-03-01: 0; 2024-04-01: 0; 2024-05-01: 0; 2024-06-01: 0; 2024-07-01: 0; 2024-08-01: 0; 2024-09-01: 0; 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 0; 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 0; 2025-12-01: 0; 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0; 2026-11-01: 0; 2026-12-01: 0; 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0; 2027-06-01: 0; 2027-07-01: 0; 2027-08-01: 0; 2027-09-01: 0; 2027-10-01: 0; 2027-11-01: 0; 2027-12-01: 0; 2028-01-01: 0; 2028-02-01: 0; 2028-03-01: 0; 2028-04-01: 0; 2028-05-01: 0; 2028-06-01: 0; 2028-07-01: 0; 2028-08-01: 0; 2028-09-01: 0; 2028-10-01: 0; 2028-11-01: 0; 2028-12-01: 0; 2029-01-01: 0; 2029-02-01: 0; 2029-03-01: 0; 2029-04-01: 0
Phase Analyzer | New Activity - Finished in Status Period (Snapshot) - check/compare | 2012-08-01: N/A; 2012-09-01: N/A; 2012-10-01: N/A; 2012-11-01: N/A; 2012-12-01: N/A; 2013-01-01: N/A; 2013-02-01: N/A; 2013-03-01: N/A; 2013-04-01: N/A; 2013-05-01: N/A; 2013-06-01: N/A; 2013-07-01: N/A; 2013-08-01: N/A; 2013-09-01: N/A; 2013-10-01: N/A; 2013-11-01: N/A; 2013-12-01: N/A; 2014-01-01: N/A; 2014-02-01: N/A; 2014-03-01: N/A; 2014-04-01: N/A; 2014-05-01: N/A; 2014-06-01: N/A; 2014-07-01: N/A; 2014-08-01: N/A; 2014-09-01: N/A; 2014-10-01: N/A; 2014-11-01: N/A; 2014-12-01: N/A; 2015-01-01: N/A; 2015-02-01: N/A; 2015-03-01: N/A; 2015-04-01: N/A; 2015-05-01: N/A; 2015-06-01: N/A; 2015-07-01: N/A; 2015-08-01: N/A; 2015-09-01: N/A; 2015-10-01: N/A; 2015-11-01: N/A; 2015-12-01: N/A; 2016-01-01: N/A; 2016-02-01: N/A; 2016-03-01: N/A; 2016-04-01: N/A; 2016-05-01: N/A; 2016-06-01: N/A; 2016-07-01: N/A; 2016-08-01: N/A; 2016-09-01: N/A; 2016-10-01: N/A; 2016-11-01: N/A; 2016-12-01: N/A; 2017-01-01: N/A; 2017-02-01: N/A; 2017-03-01: N/A; 2017-04-01: N/A; 2017-05-01: N/A; 2017-06-01: N/A; 2017-07-01: N/A; 2017-08-01: N/A; 2017-09-01: N/A; 2017-10-01: N/A; 2017-11-01: N/A; 2017-12-01: N/A; 2018-01-01: N/A; 2018-02-01: N/A; 2018-03-01: N/A; 2018-04-01: N/A; 2018-05-01: N/A; 2018-06-01: N/A; 2018-07-01: N/A; 2018-08-01: N/A; 2018-09-01: N/A; 2018-10-01: N/A; 2018-11-01: N/A; 2018-12-01: N/A; 2019-01-01: N/A; 2019-02-01: N/A; 2019-03-01: N/A; 2019-04-01: N/A; 2019-05-01: N/A; 2019-06-01: N/A; 2019-07-01: N/A; 2019-08-01: N/A; 2019-09-01: N/A; 2019-10-01: N/A; 2019-11-01: N/A; 2019-12-01: N/A; 2020-01-01: N/A; 2020-02-01: N/A; 2020-03-01: N/A; 2020-04-01: N/A; 2020-05-01: N/A; 2020-06-01: N/A; 2020-07-01: N/A; 2020-08-01: N/A; 2020-09-01: N/A; 2020-10-01: N/A; 2020-11-01: N/A; 2020-12-01: N/A; 2021-01-01: N/A; 2021-02-01: N/A; 2021-03-01: N/A; 2021-04-01: N/A; 2021-05-01: N/A; 2021-06-01: N/A; 2021-07-01: N/A; 2021-08-01: N/A; 2021-09-01: N/A; 2021-10-01: N/A; 2021-11-01: N/A; 2021-12-01: N/A; 2022-01-01: N/A; 2022-02-01: N/A; 2022-03-01: N/A; 2022-04-01: N/A; 2022-05-01: N/A; 2022-06-01: N/A; 2022-07-01: N/A; 2022-08-01: N/A; 2022-09-01: N/A; 2022-10-01: N/A; 2022-11-01: N/A; 2022-12-01: N/A; 2023-01-01: N/A; 2023-02-01: N/A; 2023-03-01: N/A; 2023-04-01: N/A; 2023-05-01: N/A; 2023-06-01: N/A; 2023-07-01: N/A; 2023-08-01: N/A; 2023-09-01: N/A; 2023-10-01: N/A; 2023-11-01: N/A; 2023-12-01: N/A; 2024-01-01: N/A; 2024-02-01: N/A; 2024-03-01: N/A; 2024-04-01: N/A; 2024-05-01: N/A; 2024-06-01: N/A; 2024-07-01: N/A; 2024-08-01: N/A; 2024-09-01: N/A; 2024-10-01: N/A; 2024-11-01: N/A; 2024-12-01: N/A; 2025-01-01: N/A; 2025-02-01: N/A; 2025-03-01: N/A; 2025-04-01: N/A; 2025-05-01: N/A; 2025-06-01: N/A; 2025-07-01: N/A; 2025-08-01: N/A; 2025-09-01: N/A; 2025-10-01: N/A; 2025-11-01: N/A; 2025-12-01: N/A; 2026-01-01: N/A; 2026-02-01: N/A; 2026-03-01: N/A; 2026-04-01: N/A; 2026-05-01: N/A; 2026-06-01: N/A; 2026-07-01: N/A; 2026-08-01: N/A; 2026-09-01: N/A; 2026-10-01: N/A; 2026-11-01: N/A; 2026-12-01: N/A; 2027-01-01: N/A; 2027-02-01: N/A; 2027-03-01: N/A; 2027-04-01: N/A; 2027-05-01: N/A; 2027-06-01: N/A; 2027-07-01: N/A; 2027-08-01: N/A; 2027-09-01: N/A; 2027-10-01: N/A; 2027-11-01: N/A; 2027-12-01: N/A; 2028-01-01: N/A; 2028-02-01: N/A; 2028-03-01: N/A; 2028-04-01: N/A; 2028-05-01: N/A; 2028-06-01: N/A; 2028-07-01: N/A; 2028-08-01: N/A; 2028-09-01: N/A; 2028-10-01: N/A; 2028-11-01: N/A; 2028-12-01: N/A; 2029-01-01: N/A; 2029-02-01: N/A; 2029-03-01: N/A; 2029-04-01: N/A
Phase Analyzer | Specific Task Start | 2012-08-01: N/A; 2012-09-01: N/A; 2012-10-01: N/A; 2012-11-01: N/A; 2012-12-01: N/A; 2013-01-01: N/A; 2013-02-01: N/A; 2013-03-01: N/A; 2013-04-01: N/A; 2013-05-01: N/A; 2013-06-01: N/A; 2013-07-01: N/A; 2013-08-01: N/A; 2013-09-01: N/A; 2013-10-01: N/A; 2013-11-01: N/A; 2013-12-01: N/A; 2014-01-01: N/A; 2014-02-01: N/A; 2014-03-01: N/A; 2014-04-01: N/A; 2014-05-01: N/A; 2014-06-01: N/A; 2014-07-01: N/A; 2014-08-01: N/A; 2014-09-01: N/A; 2014-10-01: N/A; 2014-11-01: N/A; 2014-12-01: N/A; 2015-01-01: N/A; 2015-02-01: N/A; 2015-03-01: N/A; 2015-04-01: N/A; 2015-05-01: N/A; 2015-06-01: N/A; 2015-07-01: N/A; 2015-08-01: N/A; 2015-09-01: N/A; 2015-10-01: N/A; 2015-11-01: N/A; 2015-12-01: N/A; 2016-01-01: N/A; 2016-02-01: N/A; 2016-03-01: N/A; 2016-04-01: N/A; 2016-05-01: N/A; 2016-06-01: N/A; 2016-07-01: N/A; 2016-08-01: N/A; 2016-09-01: N/A; 2016-10-01: N/A; 2016-11-01: N/A; 2016-12-01: N/A; 2017-01-01: N/A; 2017-02-01: N/A; 2017-03-01: N/A; 2017-04-01: N/A; 2017-05-01: N/A; 2017-06-01: N/A; 2017-07-01: N/A; 2017-08-01: N/A; 2017-09-01: N/A; 2017-10-01: N/A; 2017-11-01: N/A; 2017-12-01: N/A; 2018-01-01: N/A; 2018-02-01: N/A; 2018-03-01: N/A; 2018-04-01: N/A; 2018-05-01: N/A; 2018-06-01: N/A; 2018-07-01: N/A; 2018-08-01: N/A; 2018-09-01: N/A; 2018-10-01: N/A; 2018-11-01: N/A; 2018-12-01: N/A; 2019-01-01: N/A; 2019-02-01: N/A; 2019-03-01: N/A; 2019-04-01: N/A; 2019-05-01: N/A; 2019-06-01: N/A; 2019-07-01: N/A; 2019-08-01: N/A; 2019-09-01: N/A; 2019-10-01: N/A; 2019-11-01: N/A; 2019-12-01: N/A; 2020-01-01: N/A; 2020-02-01: N/A; 2020-03-01: N/A; 2020-04-01: N/A; 2020-05-01: N/A; 2020-06-01: N/A; 2020-07-01: N/A; 2020-08-01: N/A; 2020-09-01: N/A; 2020-10-01: N/A; 2020-11-01: N/A; 2020-12-01: N/A; 2021-01-01: N/A; 2021-02-01: N/A; 2021-03-01: N/A; 2021-04-01: N/A; 2021-05-01: N/A; 2021-06-01: N/A; 2021-07-01: N/A; 2021-08-01: N/A; 2021-09-01: N/A; 2021-10-01: N/A; 2021-11-01: N/A; 2021-12-01: N/A; 2022-01-01: N/A; 2022-02-01: N/A; 2022-03-01: N/A; 2022-04-01: N/A; 2022-05-01: N/A; 2022-06-01: N/A; 2022-07-01: N/A; 2022-08-01: N/A; 2022-09-01: N/A; 2022-10-01: N/A; 2022-11-01: N/A; 2022-12-01: N/A; 2023-01-01: N/A; 2023-02-01: N/A; 2023-03-01: N/A; 2023-04-01: N/A; 2023-05-01: N/A; 2023-06-01: N/A; 2023-07-01: N/A; 2023-08-01: N/A; 2023-09-01: N/A; 2023-10-01: N/A; 2023-11-01: N/A; 2023-12-01: N/A; 2024-01-01: N/A; 2024-02-01: N/A; 2024-03-01: N/A; 2024-04-01: N/A; 2024-05-01: N/A; 2024-06-01: N/A; 2024-07-01: N/A; 2024-08-01: N/A; 2024-09-01: N/A; 2024-10-01: N/A; 2024-11-01: N/A; 2024-12-01: N/A; 2025-01-01: N/A; 2025-02-01: N/A; 2025-03-01: N/A; 2025-04-01: N/A; 2025-05-01: N/A; 2025-06-01: N/A; 2025-07-01: N/A; 2025-08-01: N/A; 2025-09-01: N/A; 2025-10-01: N/A; 2025-11-01: N/A; 2025-12-01: N/A; 2026-01-01: N/A; 2026-02-01: N/A; 2026-03-01: N/A; 2026-04-01: N/A; 2026-05-01: N/A; 2026-06-01: N/A; 2026-07-01: N/A; 2026-08-01: N/A; 2026-09-01: N/A; 2026-10-01: N/A; 2026-11-01: N/A; 2026-12-01: N/A; 2027-01-01: N/A; 2027-02-01: N/A; 2027-03-01: N/A; 2027-04-01: N/A; 2027-05-01: N/A; 2027-06-01: 2027-06-17; 2027-07-01: 2027-06-17; 2027-08-01: 2027-08-05; 2027-09-01: 2027-08-05; 2027-10-01: 2027-09-24; 2027-11-01: N/A; 2027-12-01: N/A; 2028-01-01: N/A; 2028-02-01: N/A; 2028-03-01: N/A; 2028-04-01: N/A; 2028-05-01: N/A; 2028-06-01: N/A; 2028-07-01: N/A; 2028-08-01: N/A; 2028-09-01: N/A; 2028-10-01: N/A; 2028-11-01: N/A; 2028-12-01: N/A; 2029-01-01: N/A; 2029-02-01: N/A; 2029-03-01: N/A; 2029-04-01: N/A
Phase Analyzer | Specific Task Finish | 2012-08-01: N/A; 2012-09-01: N/A; 2012-10-01: N/A; 2012-11-01: N/A; 2012-12-01: N/A; 2013-01-01: N/A; 2013-02-01: N/A; 2013-03-01: N/A; 2013-04-01: N/A; 2013-05-01: N/A; 2013-06-01: N/A; 2013-07-01: N/A; 2013-08-01: N/A; 2013-09-01: N/A; 2013-10-01: N/A; 2013-11-01: N/A; 2013-12-01: N/A; 2014-01-01: N/A; 2014-02-01: N/A; 2014-03-01: N/A; 2014-04-01: N/A; 2014-05-01: N/A; 2014-06-01: N/A; 2014-07-01: N/A; 2014-08-01: N/A; 2014-09-01: N/A; 2014-10-01: N/A; 2014-11-01: N/A; 2014-12-01: N/A; 2015-01-01: N/A; 2015-02-01: N/A; 2015-03-01: N/A; 2015-04-01: N/A; 2015-05-01: N/A; 2015-06-01: N/A; 2015-07-01: N/A; 2015-08-01: N/A; 2015-09-01: N/A; 2015-10-01: N/A; 2015-11-01: N/A; 2015-12-01: N/A; 2016-01-01: N/A; 2016-02-01: N/A; 2016-03-01: N/A; 2016-04-01: N/A; 2016-05-01: N/A; 2016-06-01: N/A; 2016-07-01: N/A; 2016-08-01: N/A; 2016-09-01: N/A; 2016-10-01: N/A; 2016-11-01: N/A; 2016-12-01: N/A; 2017-01-01: N/A; 2017-02-01: N/A; 2017-03-01: N/A; 2017-04-01: N/A; 2017-05-01: N/A; 2017-06-01: N/A; 2017-07-01: N/A; 2017-08-01: N/A; 2017-09-01: N/A; 2017-10-01: N/A; 2017-11-01: N/A; 2017-12-01: N/A; 2018-01-01: N/A; 2018-02-01: N/A; 2018-03-01: N/A; 2018-04-01: N/A; 2018-05-01: N/A; 2018-06-01: N/A; 2018-07-01: N/A; 2018-08-01: N/A; 2018-09-01: N/A; 2018-10-01: N/A; 2018-11-01: N/A; 2018-12-01: N/A; 2019-01-01: N/A; 2019-02-01: N/A; 2019-03-01: N/A; 2019-04-01: N/A; 2019-05-01: N/A; 2019-06-01: N/A; 2019-07-01: N/A; 2019-08-01: N/A; 2019-09-01: N/A; 2019-10-01: N/A; 2019-11-01: N/A; 2019-12-01: N/A; 2020-01-01: N/A; 2020-02-01: N/A; 2020-03-01: N/A; 2020-04-01: N/A; 2020-05-01: N/A; 2020-06-01: N/A; 2020-07-01: N/A; 2020-08-01: N/A; 2020-09-01: N/A; 2020-10-01: N/A; 2020-11-01: N/A; 2020-12-01: N/A; 2021-01-01: N/A; 2021-02-01: N/A; 2021-03-01: N/A; 2021-04-01: N/A; 2021-05-01: N/A; 2021-06-01: N/A; 2021-07-01: N/A; 2021-08-01: N/A; 2021-09-01: N/A; 2021-10-01: N/A; 2021-11-01: N/A; 2021-12-01: N/A; 2022-01-01: N/A; 2022-02-01: N/A; 2022-03-01: N/A; 2022-04-01: N/A; 2022-05-01: N/A; 2022-06-01: N/A; 2022-07-01: N/A; 2022-08-01: N/A; 2022-09-01: N/A; 2022-10-01: N/A; 2022-11-01: N/A; 2022-12-01: N/A; 2023-01-01: N/A; 2023-02-01: N/A; 2023-03-01: N/A; 2023-04-01: N/A; 2023-05-01: N/A; 2023-06-01: N/A; 2023-07-01: N/A; 2023-08-01: N/A; 2023-09-01: N/A; 2023-10-01: N/A; 2023-11-01: N/A; 2023-12-01: N/A; 2024-01-01: N/A; 2024-02-01: N/A; 2024-03-01: N/A; 2024-04-01: N/A; 2024-05-01: N/A; 2024-06-01: N/A; 2024-07-01: N/A; 2024-08-01: N/A; 2024-09-01: N/A; 2024-10-01: N/A; 2024-11-01: N/A; 2024-12-01: N/A; 2025-01-01: N/A; 2025-02-01: N/A; 2025-03-01: N/A; 2025-04-01: N/A; 2025-05-01: N/A; 2025-06-01: N/A; 2025-07-01: N/A; 2025-08-01: N/A; 2025-09-01: N/A; 2025-10-01: N/A; 2025-11-01: N/A; 2025-12-01: N/A; 2026-01-01: N/A; 2026-02-01: N/A; 2026-03-01: N/A; 2026-04-01: N/A; 2026-05-01: N/A; 2026-06-01: N/A; 2026-07-01: N/A; 2026-08-01: N/A; 2026-09-01: N/A; 2026-10-01: N/A; 2026-11-01: N/A; 2026-12-01: N/A; 2027-01-01: N/A; 2027-02-01: N/A; 2027-03-01: N/A; 2027-04-01: N/A; 2027-05-01: N/A; 2027-06-01: N/A; 2027-07-01: 2027-07-14; 2027-08-01: N/A; 2027-09-01: 2027-09-01; 2027-10-01: 2027-10-21; 2027-11-01: N/A; 2027-12-01: N/A; 2028-01-01: N/A; 2028-02-01: N/A; 2028-03-01: N/A; 2028-04-01: N/A; 2028-05-01: N/A; 2028-06-01: N/A; 2028-07-01: N/A; 2028-08-01: N/A; 2028-09-01: N/A; 2028-10-01: N/A; 2028-11-01: N/A; 2028-12-01: N/A; 2029-01-01: N/A; 2029-02-01: N/A; 2029-03-01: N/A; 2029-04-01: N/A
Phase Analyzer | Score | 2012-08-01: 100; 2012-09-01: 100; 2012-10-01: 100; 2012-11-01: N/A; 2012-12-01: N/A; 2013-01-01: N/A; 2013-02-01: N/A; 2013-03-01: N/A; 2013-04-01: N/A; 2013-05-01: N/A; 2013-06-01: N/A; 2013-07-01: N/A; 2013-08-01: N/A; 2013-09-01: N/A; 2013-10-01: N/A; 2013-11-01: N/A; 2013-12-01: N/A; 2014-01-01: N/A; 2014-02-01: N/A; 2014-03-01: N/A; 2014-04-01: N/A; 2014-05-01: N/A; 2014-06-01: N/A; 2014-07-01: N/A; 2014-08-01: N/A; 2014-09-01: N/A; 2014-10-01: N/A; 2014-11-01: N/A; 2014-12-01: N/A; 2015-01-01: N/A; 2015-02-01: N/A; 2015-03-01: N/A; 2015-04-01: N/A; 2015-05-01: N/A; 2015-06-01: N/A; 2015-07-01: N/A; 2015-08-01: N/A; 2015-09-01: N/A; 2015-10-01: N/A; 2015-11-01: N/A; 2015-12-01: N/A; 2016-01-01: N/A; 2016-02-01: N/A; 2016-03-01: N/A; 2016-04-01: N/A; 2016-05-01: N/A; 2016-06-01: N/A; 2016-07-01: N/A; 2016-08-01: N/A; 2016-09-01: N/A; 2016-10-01: N/A; 2016-11-01: N/A; 2016-12-01: N/A; 2017-01-01: N/A; 2017-02-01: N/A; 2017-03-01: N/A; 2017-04-01: N/A; 2017-05-01: N/A; 2017-06-01: 100; 2017-07-01: 100; 2017-08-01: 100; 2017-09-01: 100; 2017-10-01: 100; 2017-11-01: 100; 2017-12-01: 100; 2018-01-01: 100; 2018-02-01: 100; 2018-03-01: 100; 2018-04-01: 100; 2018-05-01: 100; 2018-06-01: 100; 2018-07-01: 100; 2018-08-01: 100; 2018-09-01: 100; 2018-10-01: 100; 2018-11-01: 100; 2018-12-01: 100; 2019-01-01: 100; 2019-02-01: 100; 2019-03-01: 100; 2019-04-01: 100; 2019-05-01: 100; 2019-06-01: 100; 2019-07-01: 100; 2019-08-01: 100; 2019-09-01: 100; 2019-10-01: 100; 2019-11-01: 100; 2019-12-01: 100; 2020-01-01: 100; 2020-02-01: 100; 2020-03-01: 100; 2020-04-01: 100; 2020-05-01: 100; 2020-06-01: 100; 2020-07-01: 100; 2020-08-01: 100; 2020-09-01: 100; 2020-10-01: 100; 2020-11-01: 100; 2020-12-01: 100; 2021-01-01: 100; 2021-02-01: 100; 2021-03-01: 100; 2021-04-01: 100; 2021-05-01: 100; 2021-06-01: 100; 2021-07-01: 100; 2021-08-01: 100; 2021-09-01: 100; 2021-10-01: 100; 2021-11-01: 100; 2021-12-01: 100; 2022-01-01: 100; 2022-02-01: 100; 2022-03-01: 100; 2022-04-01: 100; 2022-05-01: 100; 2022-06-01: 100; 2022-07-01: 100; 2022-08-01: 100; 2022-09-01: 100; 2022-10-01: 100; 2022-11-01: 100; 2022-12-01: 100; 2023-01-01: 100; 2023-02-01: 100; 2023-03-01: 100; 2023-04-01: 100; 2023-05-01: 100; 2023-06-01: 100; 2023-07-01: 100; 2023-08-01: 100; 2023-09-01: 100; 2023-10-01: 100; 2023-11-01: 100; 2023-12-01: 100; 2024-01-01: 100; 2024-02-01: 100; 2024-03-01: 100; 2024-04-01: 100; 2024-05-01: 100; 2024-06-01: 100; 2024-07-01: 100; 2024-08-01: 100; 2024-09-01: 100; 2024-10-01: 100; 2024-11-01: 100; 2024-12-01: 100; 2025-01-01: 100; 2025-02-01: 100; 2025-03-01: 100; 2025-04-01: 100; 2025-05-01: 100; 2025-06-01: 100; 2025-07-01: 100; 2025-08-01: 100; 2025-09-01: 100; 2025-10-01: 100; 2025-11-01: 100; 2025-12-01: 100; 2026-01-01: 100; 2026-02-01: 100; 2026-03-01: 100; 2026-04-01: 100; 2026-05-01: 100; 2026-06-01: 100; 2026-07-01: 100; 2026-08-01: 100; 2026-09-01: 100; 2026-10-01: 100; 2026-11-01: 100; 2026-12-01: 100; 2027-01-01: 100; 2027-02-01: 100; 2027-03-01: 100; 2027-04-01: 100; 2027-05-01: 100; 2027-06-01: 100; 2027-07-01: 100; 2027-08-01: 100; 2027-09-01: 100; 2027-10-01: 100; 2027-11-01: 100; 2027-12-01: 100; 2028-01-01: 100; 2028-02-01: 100; 2028-03-01: 100; 2028-04-01: 100; 2028-05-01: 100; 2028-06-01: 100; 2028-07-01: 100; 2028-08-01: 100; 2028-09-01: 100; 2028-10-01: 100; 2028-11-01: 100; 2028-12-01: 100; 2029-01-01: 100; 2029-02-01: 100; 2029-03-01: 100; 2029-04-01: 100

## Ribbon Analysis
Deltek Acumen Fuse® Ribbon View Report
Workbook: Workbook1 - 17639 Activities
Quick Add Metrics
Created on: 8/7/2026
Created by: dpolitte
Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Wrong Status - Actual Starts | Wrong Status - Actual Finishes | Invalid Forecast Dates | Expected Finish But Still In-Progress | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | SF Relations | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Missing Baseline Starts | Missing Baseline Finishes | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | High Float 10% of Rem Project Duration | High Float 44d | Zero Days Float | Number of Leads | Number of Lags | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | New To-Go Tasks in Status Period | New Completed Tasks in Status Period | New Critical Tasks in Status Period | Riding Data Date | Deadlines | Missed Activities | High Float 10% | Negative Float | Max Float | Tasks & Milestones (To Go) | Milestones (To-Go) | Normal Tasks (To-Go) | Normal Tasks (To-Go, In Progress) | Milestone-to-Task Ratio (To-Go) | Float Ratio™ | Critical Path (Tasks & Milestones) | Critical Path (Milestones) | Critical Path (Normal Tasks) | Critical Path (Normal In Progress) | Critical Milestone-to-Task Ratio (To-Go) | Negative Float | Zero Days Float | Near-Critical (<10 Days Float) | Near CP - Float Ratio™ | CP Logic Density™ | Critical Tasks Created in Status Period | Critical CEI - Value Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | Status Date | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Status Date | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Status Date | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | New Activity - Created | New Activity - Already Finished | New Activity - Finished in Status Period | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Max Float | Newly Created Activity & Critical - Created (Snapshot) | Number of Leads | Number of Lags | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Total New Completed Tasks & Milestones in Status Period | Total New Tasks & Milestones in Status Period | Riding Data Date | Deadlines | Missed Activities | Wrong Status | Invalid Forecast Dates | Expected Finish | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | SF Relations | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Missing Baseline Starts | Missing Baseline Finishes | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | SV(t) | SPI(t) | Missing Predecessors | Missing Successors | Activities with Lags | SS Predecessors | SF Predecessors | FF Predecessors | FS Predecessors | Logic Density™ | Merge Hotspot | Diverge Hotspot | Logic Hotspot™ | Summary Links | Open Start | Open Finish | Open Ends with Constraints | Open Ends w/o Constraints | Open Ends | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Score
Ribbons | SRA Large Test File2 | 1 | 4 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 11 | 12 | 0 | 0 | 122 | 2025-03-10 | 623 | 717 | 67 | 1 | 5 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 0 | 1363 | 354 | 122 | 2196 | 999 | 80 | 919 | 92 | 1:11 | N/A | 186 | 16 | 170 | 4 | 1:11 | 122 | 67 | 243 | N/A | 4.26 | 0 | N/A | N/A | N/A | 0 | 0 | 0.51 | 1228 | 632 | 596 | 2025-03-10 | 0.51 | 1228 | 632 | 596 | 0.51 | 632 | N/A | 2025-03-10 | 0.69 | 129 | 89 | 40 | 0.69 | 89 | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 354 | 717 | 67 | 122 | 2196 | 0 | 1 | 8 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 1095 | 1 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 11 | 12 | 0 | 0 | 122 | 2025-03-10 | -270791 | 8.14 | 12 | 18 | 8 | 70 | 0 | 43 | 1704 | 3.13 | 155 | 141 | 14 | 0 | 3 | 11 | 0 | 25 | 25 | 2 | 0 | 8 | 90 | 0 | 0 | 660 | 112 | 86 | 322 | 4 | 842 | 1095 | x | 0.59 | 0.53 | 0
Ribbons | TP4_DataCenter_v1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-01-30 | 4 | 1 | 8 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 45 | 13 | 1 | 12 | 1 | 1:12 | 0.63 | 8 | 1 | 7 | 1 | 1:07 | 0 | 8 | 9 | 0.03 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 1 | 1 | 1 | 0 | 2026-01-30 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-01-30 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-01-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | 2 | 1 | 8 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-01-30 | -4 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 12 | 0 | ✓ | 1 | 1 | 0
Ribbons | TP4_DataCenter_v2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-02-27 | 3 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 30 | 11 | 1 | 10 | 3 | 1:10 | 0.47 | 7 | 1 | 6 | 1 | 1:06 | 0 | 7 | 8 | 0.04 | 2.86 | 0 | N/A | N/A | N/A | 0 | 0 | 0.75 | 4 | 3 | 1 | 2026-02-27 | 0.75 | 4 | 3 | 1 | 0.75 | 3 | N/A | 2026-02-27 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-02-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | 1 | 0 | 7 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-02-27 | -69 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | ✓ | 1 | 0.75 | 0
Ribbons | TP4_DataCenter_v3 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | 2 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 30 | 9 | 1 | 8 | 2 | 1:08 | 0.34 | 7 | 1 | 6 | 1 | 1:06 | 0 | 7 | 7 | 0 | 2.86 | 0 | N/A | N/A | N/A | 0 | 0 | 0.71 | 7 | 5 | 2 | 2026-03-31 | 0.71 | 7 | 5 | 2 | 0.71 | 5 | N/A | 2026-03-31 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 1 | 0 | 7 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | -123 | 0.67 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 8 | 3 | ✓ | 1 | 0.71 | 0
Ribbons | TP4_DataCenter_v4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-04-30 | 2 | 1 | 5 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0 | 50 | 7 | 1 | 6 | 2 | 1:06 | 0.73 | 5 | 1 | 4 | 2 | 1:04 | 0 | 5 | 5 | 0 | 2.6 | 0 | N/A | N/A | N/A | 0 | 0 | 0.78 | 9 | 7 | 2 | 2026-04-30 | 0.78 | 9 | 7 | 2 | 0.78 | 7 | N/A | 2026-04-30 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-04-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | 2 | 1 | 5 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-04-30 | -99 | 0.7 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 6 | 5 | ✓ | 1 | 0.78 | 0
Ribbons | TP4_DataCenter_v5 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-05-29 | 2 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 15 | 7 | 1 | 6 | 3 | 1:06 | 0.32 | 5 | 1 | 4 | 1 | 1:04 | 0 | 5 | 5 | 0 | 2.6 | 0 | N/A | N/A | N/A | 0 | 0 | 0.58 | 12 | 7 | 5 | 2026-05-29 | 0.58 | 12 | 7 | 5 | 0.58 | 7 | N/A | 2026-05-29 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-05-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | 0 | 0 | 5 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 9 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-05-29 | -280 | 0.63 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 6 | 9 | ✓ | 1 | 0.58 | 0
Ribbons | Project2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-24 | 42 | 44 | 41 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 39 | 0 | 263 | 106 | 0 | 106 | 3 | N/A | 14.01 | 41 | 0 | 41 | 1 | N/A | 0 | 41 | 50 | 0.05 | 3.2 | 0 | N/A | N/A | N/A | 0 | 0 | 0.74 | 27 | 20 | 7 | 2026-05-24 | 0.74 | 27 | 20 | 7 | 0.74 | 20 | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 39 | 44 | 41 | 0 | 263 | 0 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-24 | -454 | 0.83 | 1 | 5 | 2 | 0 | 0 | 1 | 125 | 2.79 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 0 | 2 | 1 | 0 | 0 | 44 | 0 | 1 | 0 | 0 | 0 | 18 | ✓ | 1 | 0.74 | 0
Ribbons | Project5_TAMPERED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 43 | 44 | 4 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 41 | 0 | 275 | 99 | 0 | 99 | 2 | N/A | 22.02 | 4 | 0 | 4 | 0 | N/A | 0 | 4 | 5 | 0.1 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 0.59 | 46 | 27 | 19 | 2026-08-27 | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 41 | 44 | 4 | 0 | 275 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | -902 | 0.91 | 1 | 6 | 2 | 0 | 0 | 1 | 125 | 2.81 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 7 | 7 | 5 | 0 | 1 | 0 | 0 | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 37 | x | 1 | 0.59 | 0
Ribbons | Project2 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-24 | 42 | 44 | 41 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 39 | 0 | 263 | 106 | 0 | 106 | 3 | N/A | 14.01 | 41 | 0 | 41 | 1 | N/A | 0 | 41 | 50 | 0.05 | 3.2 | 0 | N/A | N/A | N/A | 0 | 0 | 0.74 | 27 | 20 | 7 | 2026-05-24 | 0.74 | 27 | 20 | 7 | 0.74 | 20 | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 39 | 44 | 41 | 0 | 263 | 0 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-24 | -454 | 0.83 | 1 | 5 | 2 | 0 | 0 | 1 | 125 | 2.79 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 0 | 2 | 1 | 0 | 0 | 44 | 0 | 1 | 0 | 0 | 0 | 18 | ✓ | 1 | 0.74 | 0
Ribbons | Project3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-30 | 40 | 42 | 40 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 31 | 0 | 223 | 102 | 0 | 102 | 1 | N/A | 13.83 | 40 | 0 | 40 | 1 | N/A | 0 | 40 | 49 | 0.05 | 3.23 | 0 | N/A | N/A | N/A | 0 | 0 | 0.67 | 36 | 24 | 12 | 2026-06-30 | 0.67 | 36 | 24 | 12 | 0.67 | 24 | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | 31 | 42 | 40 | 0 | 223 | 0 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-30 | -550 | 0.88 | 1 | 5 | 2 | 0 | 0 | 1 | 125 | 2.79 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 0 | 2 | 1 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 27 | ✓ | 1 | 0.67 | 0
Ribbons | Project4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-29 | 39 | 41 | 37 | 0 | 1 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 31 | 0 | 230 | 101 | 0 | 101 | 1 | N/A | 13.76 | 37 | 0 | 37 | 0 | N/A | 0 | 37 | 48 | 0.13 | 3.32 | 0 | N/A | N/A | N/A | 0 | 0 | 0.58 | 43 | 25 | 18 | 2026-07-29 | 0.58 | 43 | 25 | 18 | 0.58 | 25 | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | 31 | 41 | 37 | 0 | 230 | 0 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-29 | -630 | 0.89 | 1 | 5 | 2 | 0 | 0 | 1 | 125 | 2.83 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 0 | 1 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 34 | ✓ | 1 | 0.58 | 0
Ribbons | Project5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 43 | 44 | 4 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 41 | 0 | 275 | 99 | 0 | 99 | 2 | N/A | 22.02 | 4 | 0 | 4 | 0 | N/A | 0 | 4 | 5 | 0.1 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 0.59 | 46 | 27 | 19 | 2026-08-27 | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 41 | 44 | 4 | 0 | 275 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | -902 | 0.91 | 1 | 6 | 2 | 0 | 0 | 1 | 125 | 2.81 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 7 | 7 | 5 | 0 | 1 | 0 | 0 | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 37 | ✓ | 1 | 0.59 | 0
Ribbons | Large Test File | 0 | 0 | 2 | 0 | 0 | 0 | 7 | 0 | 0 | 2 | 1 | 2 | 0 | 2 | 0 | 0 | 12 | 13 | 1 | 0 | 41 | 2025-02-07 | 804 | 898 | 2 | 1 | 5 | 2 | 4 | 9 | 2 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 1356 | 467 | 41 | 2873 | 1024 | 79 | 945 | 108 | 1:12 | N/A | 43 | 8 | 35 | 1 | 1:04 | 41 | 2 | 74 | -4.26 | 7.58 | 0 | N/A | N/A | N/A | 0 | 0 | 0.51 | 1205 | 609 | 596 | 2025-02-07 | 0.51 | 1205 | 609 | 596 | 0.51 | 609 | N/A | 2025-02-07 | 0.7 | 128 | 89 | 39 | 0.7 | 89 | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 467 | 898 | 2 | 41 | 2873 | 0 | 1 | 8 | 2 | 4 | 9 | 2 | 11 | 1 | 0 | 0 | 0 | 0 | 1115 | 0 | 2 | 0 | 0 | 0 | 7 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 12 | 13 | 1 | 0 | 41 | 2025-02-07 | -175932 | 8.22 | 11 | 16 | 8 | 71 | 0 | 43 | 1705 | 3.14 | 156 | 141 | 14 | 0 | 3 | 11 | 1 | 21 | 22 | 0 | 0 | 8 | 93 | 0 | 0 | 814 | 35 | 87 | 0 | 0 | 866 | 1115 | ✓ | 0.97 | 0.52 | 0
Ribbons | Large Test File2 | 1 | 4 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 10 | 11 | 0 | 0 | 122 | 2025-03-10 | 623 | 717 | 66 | 1 | 5 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 0 | 1363 | 354 | 122 | 2196 | 998 | 79 | 919 | 92 | 1:12 | N/A | 185 | 15 | 170 | 4 | 1:11 | 122 | 66 | 242 | N/A | 4.27 | 0 | N/A | N/A | N/A | 0 | 0 | 0.51 | 1228 | 632 | 596 | 2025-03-10 | 0.51 | 1228 | 632 | 596 | 0.51 | 632 | N/A | 2025-03-10 | 0.69 | 129 | 89 | 40 | 0.69 | 89 | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 354 | 717 | 66 | 122 | 2196 | 0 | 1 | 8 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 1095 | 1 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 10 | 11 | 0 | 0 | 122 | 2025-03-10 | -270791 | 8.14 | 12 | 18 | 8 | 70 | 0 | 43 | 1703 | 3.13 | 155 | 141 | 14 | 0 | 3 | 11 | 0 | 25 | 25 | 2 | 0 | 8 | 90 | 0 | 0 | 660 | 112 | 86 | 322 | 4 | 842 | 1095 | x | 0.59 | 0.53 | 0
Ribbons | Large Test File Leveled | 0 | 0 | 2 | 0 | 0 | 0 | 6 | 0 | 0 | 2 | 1 | 2 | 0 | 2 | 0 | 0 | 12 | 13 | 1 | 0 | 47 | 2025-02-07 | 803 | 912 | 2 | 1 | 5 | 2 | 4 | 10 | 2 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 1400 | 467 | 47 | 2873 | 1024 | 79 | 945 | 108 | 1:12 | N/A | 49 | 8 | 41 | 1 | 1:05 | 47 | 2 | 49 | -6.67 | 7.14 | 0 | N/A | N/A | N/A | 0 | 0 | 0.51 | 1205 | 609 | 596 | 2025-02-07 | 0.51 | 1205 | 609 | 596 | 0.51 | 609 | N/A | 2025-02-07 | 0.7 | 128 | 89 | 39 | 0.7 | 89 | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 467 | 912 | 2 | 47 | 2873 | 0 | 1 | 8 | 2 | 4 | 10 | 2 | 13 | 1 | 0 | 0 | 0 | 0 | 1115 | 0 | 2 | 0 | 0 | 0 | 6 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 12 | 13 | 1 | 0 | 47 | 2025-02-07 | -175932 | 8.22 | 11 | 16 | 8 | 71 | 0 | 43 | 1705 | 3.14 | 156 | 141 | 14 | 0 | 3 | 11 | 1 | 21 | 22 | 0 | 0 | 8 | 93 | 0 | 0 | 827 | 41 | 87 | 0 | 0 | 866 | 1115 | x | 0.95 | 0.52 | 0
Ribbons | Large Test File 2 | 0 | 0 | 2 | 0 | 0 | 0 | 7 | 0 | 0 | 2 | 1 | 2 | 0 | 2 | 0 | 0 | 12 | 13 | 1 | 0 | 41 | 2025-02-07 | 804 | 898 | 2 | 1 | 5 | 2 | 4 | 9 | 2 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 1356 | 467 | 41 | 2873 | 1024 | 79 | 945 | 108 | 1:12 | N/A | 43 | 8 | 35 | 1 | 1:04 | 41 | 2 | 74 | -4.26 | 7.58 | 0 | N/A | N/A | N/A | 0 | 0 | 0.51 | 1205 | 609 | 596 | 2025-02-07 | 0.51 | 1205 | 609 | 596 | 0.51 | 609 | N/A | 2025-02-07 | 0.7 | 128 | 89 | 39 | 0.7 | 89 | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 467 | 898 | 2 | 41 | 2873 | 0 | 1 | 8 | 2 | 4 | 9 | 2 | 11 | 1 | 0 | 0 | 0 | 0 | 1115 | 0 | 2 | 0 | 0 | 0 | 7 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 12 | 13 | 1 | 0 | 41 | 2025-02-07 | -175932 | 8.22 | 11 | 16 | 8 | 71 | 0 | 43 | 1705 | 3.14 | 156 | 141 | 14 | 0 | 3 | 11 | 1 | 21 | 22 | 0 | 0 | 8 | 93 | 0 | 0 | 814 | 35 | 87 | 0 | 0 | 866 | 1115 | ✓ | 0.97 | 0.52 | 0
Ribbons | Large Test File2 2 | 1 | 4 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 10 | 11 | 0 | 0 | 122 | 2025-03-10 | 623 | 717 | 66 | 1 | 5 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 0 | 1363 | 354 | 122 | 2196 | 998 | 79 | 919 | 92 | 1:12 | N/A | 185 | 15 | 170 | 4 | 1:11 | 122 | 66 | 242 | N/A | 4.27 | 0 | N/A | N/A | N/A | 0 | 0 | 0.51 | 1228 | 632 | 596 | 2025-03-10 | 0.51 | 1228 | 632 | 596 | 0.51 | 632 | N/A | 2025-03-10 | 0.69 | 129 | 89 | 40 | 0.69 | 89 | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 354 | 717 | 66 | 122 | 2196 | 0 | 1 | 8 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 1095 | 1 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 10 | 11 | 0 | 0 | 122 | 2025-03-10 | -270791 | 8.14 | 12 | 18 | 8 | 70 | 0 | 43 | 1703 | 3.13 | 155 | 141 | 14 | 0 | 3 | 11 | 0 | 25 | 25 | 2 | 0 | 8 | 90 | 0 | 0 | 660 | 112 | 86 | 322 | 4 | 842 | 1095 | ✓ | 0.59 | 0.53 | 0
Ribbons | SRA Large Test File2 2 | 1 | 4 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 10 | 11 | 0 | 0 | 122 | 2025-03-10 | 623 | 717 | 66 | 1 | 5 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 0 | 1363 | 354 | 122 | 2196 | 998 | 79 | 919 | 92 | 1:12 | N/A | 185 | 15 | 170 | 4 | 1:11 | 122 | 66 | 242 | N/A | 4.27 | 0 | N/A | N/A | N/A | 0 | 0 | 0.51 | 1228 | 632 | 596 | 2025-03-10 | 0.51 | 1228 | 632 | 596 | 0.51 | 632 | N/A | 2025-03-10 | 0.69 | 129 | 89 | 40 | 0.69 | 89 | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 354 | 717 | 66 | 122 | 2196 | 0 | 1 | 8 | 2 | 4 | 35 | 2 | 22 | 1 | 0 | 0 | 0 | 0 | 1095 | 1 | 338 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 10 | 11 | 0 | 0 | 122 | 2025-03-10 | -270791 | 8.14 | 12 | 18 | 8 | 70 | 0 | 43 | 1703 | 3.13 | 155 | 141 | 14 | 0 | 3 | 11 | 0 | 25 | 25 | 2 | 0 | 8 | 90 | 0 | 0 | 660 | 112 | 86 | 322 | 4 | 842 | 1095 | x | 0.59 | 0.53 | 0
Ribbons | Jacked Up Schedule 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 3 | 1 | 2 | 1 | 1 | 0 | N/A | 15 | 15 | 0 | 0 | 0 | 2026-07-30 | 3 | 0 | 9 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 26 | 15 | 2 | 13 | 0 | 1:07 | 0.77 | 9 | 2 | 7 | 0 | 1:04 | 0 | 9 | 14 | 0.4 | 2.33 | 0 | N/A | N/A | N/A | 0 | 0 | N/A | 0 | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | 3 | 0 | 9 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 3 | 1 | 2 | 1 | 1 | 0 | N/A | 15 | 15 | 0 | 0 | 0 | 2026-07-30 | 0 | N/A | 1 | 2 | 0 | 1 | 0 | 1 | 12 | 2.13 | 1 | 1 | 0 | N/A | 1 | 1 | 0 | 3 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | 0 | 0 | ✓ | N/A | 0 | 0
Ribbons | Jacked up Schedule 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 2 | 1 | 1 | 0 | 0 | 0 | N/A | 6 | 6 | 1 | 0 | 2 | 2026-07-30 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 2 | 13 | 6 | 3 | 3 | 0 | 1:01 | 0.27 | 5 | 3 | 2 | 0 | 1:01 | 2 | 3 | 5 | -0.25 | 2.4 | 0 | N/A | N/A | N/A | 0 | 0 | N/A | 0 | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-30 | 1 | 0 | 3 | 2 | 13 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 2 | 1 | 1 | 0 | 0 | 0 | N/A | 6 | 6 | 1 | 0 | 2 | 2026-07-30 | 0 | N/A | 1 | 1 | 0 | 0 | 0 | 0 | 5 | 2.33 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | 0 | 0 | ✓ | N/A | 0 | 0
Ribbons | Hard_File_updated3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 2026-10-12 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 76 | 11 | 49 | 43 | 68 | 16 | 52 | 0 | 1:03 | -10.94 | 49 | 9 | 40 | 0 | 1:04 | 49 | 0 | 56 | -18.17 | 2.12 | 0 | N/A | N/A | N/A | 0 | 0 | 0.47 | 68 | 32 | 36 | 2026-10-12 | 0.47 | 68 | 32 | 36 | 0.47 | 32 | N/A | 2026-10-12 | 0.53 | 19 | 10 | 9 | 0.53 | 10 | N/A | 2026-10-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | 11 | 0 | 0 | 49 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 4 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 2026-10-12 | -84 | 1.25 | 3 | 6 | 0 | 0 | 0 | 0 | 107 | 2.09 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 1 | 60 | ✓ | 0.11 | 0.47 | 0
Ribbons | Hard_File_updated4 24 hour calendar | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2026-11-12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 74 | 3 | 15 | 34 | 19 | 5 | 14 | 4 | 1:03 | N/A | 15 | 4 | 11 | 1 | 1:03 | 15 | 0 | 16 | N/A | 2.07 | 0 | N/A | N/A | N/A | 0 | 0 | 0.83 | 84 | 70 | 14 | 2026-11-12 | 0.83 | 84 | 70 | 14 | 0.83 | 70 | N/A | 2026-11-12 | 0.81 | 26 | 21 | 5 | 0.81 | 21 | N/A | 2026-11-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | 3 | 0 | 0 | 15 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 74 | 0 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2026-11-12 | -1700 | 1.31 | 3 | 6 | 0 | 0 | 0 | 0 | 107 | 2.09 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 1 | 0 | 0 | 74 | ✓ | -2.5 | 0.85 | 0
Ribbons | Hard_File | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 68 | 0 | 7 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-07 | 20 | 2 | 78 | 0 | 0 | 0 | 0 | 0 | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 54 | 110 | 25 | 85 | 0 | 1:03 | N/A | 34 | 7 | 27 | 0 | 1:04 | 0 | 78 | 90 | N/A | 2.21 | 0 | N/A | N/A | N/A | 0 | 0 | N/A | 0 | N/A | N/A | 2026-07-07 | N/A | 0 | N/A | N/A | N/A | 0 | N/A | 2026-07-07 | N/A | 0 | N/A | N/A | N/A | 0 | N/A | 2026-07-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-07 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-07 | 20 | 2 | 78 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 68 | 0 | 7 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-07 | 0 | N/A | 1 | 6 | 0 | 0 | 0 | 0 | 109 | 2.07 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 2 | 0 | ✓ | 1 | N/A | 0
Ribbons | Hard_File_updated | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 65 | 0 | 8 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-08-11 | 23 | 6 | 74 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 12 | 17 | 0 | 54 | 103 | 24 | 79 | 1 | 1:03 | N/A | 33 | 6 | 27 | 0 | 1:05 | 0 | 74 | 81 | N/A | 2.12 | 0 | N/A | N/A | N/A | 0 | 0 | 0.27 | 11 | 3 | 8 | 2026-08-11 | 0.27 | 11 | 3 | 8 | 0.55 | 6 | 3 | 2026-08-11 | 0.33 | 3 | 1 | 2 | 0.33 | 1 | N/A | 2026-08-11 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 3 | 2026-08-11 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 3 | 2026-08-11 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-11 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-11 | 17 | 6 | 74 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 1 | 65 | 0 | 8 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-08-11 | 51 | 0.8 | 3 | 7 | 0 | 0 | 0 | 0 | 107 | 2.05 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 9 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 9 | ✓ | 1 | 0.55 | 0
Ribbons | Hard_File_updated_with_logic_reestablished | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 65 | 0 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 2026-08-11 | 17 | 9 | 8 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 0 | 1 | 0 | 77 | 16 | 76 | 62 | 103 | 24 | 79 | 1 | 1:03 | N/A | 84 | 17 | 67 | 1 | 1:04 | 76 | 8 | 87 | N/A | 2.17 | 0 | N/A | N/A | N/A | 0 | 0 | 0.27 | 11 | 3 | 8 | 2026-08-11 | 0.27 | 11 | 3 | 8 | 0.55 | 6 | 3 | 2026-08-11 | 0.33 | 3 | 1 | 2 | 0.33 | 1 | N/A | 2026-08-11 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 3 | 2026-08-11 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 3 | 2026-08-11 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-11 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-11 | 16 | 9 | 8 | 76 | 62 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 1 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 1 | 65 | 0 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 2026-08-11 | 51 | 0.8 | 2 | 7 | 0 | 0 | 0 | 0 | 108 | 2.07 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 8 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 60 | 0 | 0 | 0 | 2 | 9 | ✓ | 0.89 | 0.55 | 0
Ribbons | Hard_File_updated2 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 47 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-09-10 | 23 | 5 | 25 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 72 | 22 | 0 | 61 | 76 | 18 | 58 | 0 | 1:03 | 7.68 | 24 | 5 | 19 | 0 | 1:04 | 0 | 25 | 54 | 0.52 | 2.13 | 0 | N/A | N/A | N/A | 0 | 0 | 0.59 | 44 | 26 | 18 | 2026-09-10 | 0.59 | 44 | 26 | 18 | 0.59 | 26 | N/A | 2026-09-10 | 0.62 | 13 | 8 | 5 | 0.62 | 8 | N/A | 2026-09-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | 22 | 5 | 25 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 33 | 0 | 42 | 0 | 0 | 0 | 0 | 47 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-09-10 | -73 | 1.14 | 3 | 6 | 0 | 0 | 0 | 0 | 107 | 2.07 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 8 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 30 | 0 | 1 | 33 | ✓ | 1 | 0.59 | 0
Ribbons | Hard_File_updated3 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 2026-10-12 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 4 | 0 | 76 | 11 | 49 | 43 | 68 | 16 | 52 | 0 | 1:03 | -10.94 | 49 | 9 | 40 | 0 | 1:04 | 49 | 0 | 56 | -18.17 | 2.12 | 0 | N/A | N/A | N/A | 0 | 0 | 0.47 | 68 | 32 | 36 | 2026-10-12 | 0.47 | 68 | 32 | 36 | 0.47 | 32 | N/A | 2026-10-12 | 0.53 | 19 | 10 | 9 | 0.53 | 10 | N/A | 2026-10-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-10-12 | 11 | 0 | 0 | 49 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 4 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 2026-10-12 | -84 | 1.25 | 3 | 6 | 0 | 0 | 0 | 0 | 107 | 2.09 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 1 | 60 | ✓ | 0.11 | 0.47 | 0
Ribbons | Hard_File_updated4 24 hour calendar 2 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2026-11-12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 74 | 3 | 15 | 34 | 19 | 5 | 14 | 4 | 1:03 | N/A | 15 | 4 | 11 | 1 | 1:03 | 15 | 0 | 16 | N/A | 2.07 | 0 | N/A | N/A | N/A | 0 | 0 | 0.83 | 84 | 70 | 14 | 2026-11-12 | 0.83 | 84 | 70 | 14 | 0.83 | 70 | N/A | 2026-11-12 | 0.81 | 26 | 21 | 5 | 0.81 | 21 | N/A | 2026-11-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-11-12 | 3 | 0 | 0 | 15 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 74 | 0 | 3 | 0 | 0 | 0 | 0 | 9 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2026-11-12 | -1700 | 1.31 | 3 | 6 | 0 | 0 | 0 | 0 | 107 | 2.09 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 1 | 0 | 0 | 74 | ✓ | -2.5 | 0.85 | 0
Ribbons | EVM1 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2012-09-01 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 3 | 8 | 2 | 1:03 | N/A | 10 | 3 | 7 | 1 | 1:02 | 0 | 10 | 11 | N/A | 1.9 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | 5 | 0 | 5 | 2012-09-01 | 0 | 5 | 0 | 5 | 0 | 0 | N/A | 2012-09-01 | 0 | 2 | 0 | 2 | 0 | 0 | N/A | 2012-09-01 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2012-09-01 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2012-09-01 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2012-09-01 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2012-09-01 | 0 | 0 | 10 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2012-09-01 | -34 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 10 | 1.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | ✓ | 1 | 0 | 0
Ribbons | EVM2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2012-09-12 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 8 | 2 | 6 | 1 | 1:03 | 0 | 8 | 2 | 6 | 1 | 1:03 | 0 | 8 | 8 | 0 | 2.13 | 0 | N/A | N/A | N/A | 0 | 0 | 0.25 | 8 | 2 | 6 | 2012-09-12 | 0.25 | 8 | 2 | 6 | 0.25 | 2 | N/A | 2012-09-12 | 0.33 | 3 | 1 | 2 | 0.33 | 1 | N/A | 2012-09-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2012-09-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2012-09-12 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2012-09-12 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2012-09-12 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2012-09-12 | -23 | 0.56 | 1 | 1 | 0 | 0 | 0 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | ✓ | 1 | 0.25 | 0
Ribbons | Project2 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-24 | 42 | 44 | 41 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 39 | 0 | 263 | 106 | 0 | 106 | 3 | N/A | 14.01 | 41 | 0 | 41 | 1 | N/A | 0 | 41 | 50 | 0.05 | 3.2 | 0 | N/A | N/A | N/A | 0 | 0 | 0.74 | 27 | 20 | 7 | 2026-05-24 | 0.74 | 27 | 20 | 7 | 0.74 | 20 | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 39 | 44 | 41 | 0 | 263 | 0 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-24 | -454 | 0.83 | 1 | 5 | 2 | 0 | 0 | 1 | 125 | 2.79 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 0 | 2 | 1 | 0 | 0 | 44 | 0 | 1 | 0 | 0 | 0 | 18 | ✓ | 1 | 0.74 | 0
Ribbons | Project3 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-30 | 40 | 42 | 40 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 31 | 0 | 223 | 102 | 0 | 102 | 1 | N/A | 13.83 | 40 | 0 | 40 | 1 | N/A | 0 | 40 | 49 | 0.05 | 3.23 | 0 | N/A | N/A | N/A | 0 | 0 | 0.67 | 36 | 24 | 12 | 2026-06-30 | 0.67 | 36 | 24 | 12 | 0.67 | 24 | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | 31 | 42 | 40 | 0 | 223 | 0 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-30 | -550 | 0.88 | 1 | 5 | 2 | 0 | 0 | 1 | 125 | 2.79 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 0 | 2 | 1 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 27 | x | 1 | 0.67 | 0
Ribbons | Project4 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-29 | 39 | 41 | 37 | 0 | 1 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 31 | 0 | 230 | 101 | 0 | 101 | 1 | N/A | 13.76 | 37 | 0 | 37 | 0 | N/A | 0 | 37 | 48 | 0.13 | 3.32 | 0 | N/A | N/A | N/A | 0 | 0 | 0.58 | 43 | 25 | 18 | 2026-07-29 | 0.58 | 43 | 25 | 18 | 0.58 | 25 | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-29 | 31 | 41 | 37 | 0 | 230 | 0 | 0 | 2 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-29 | -630 | 0.89 | 1 | 5 | 2 | 0 | 0 | 1 | 125 | 2.83 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 0 | 1 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 34 | ✓ | 1 | 0.58 | 0
Ribbons | Project5_TAMPERED 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 43 | 44 | 4 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 41 | 0 | 275 | 99 | 0 | 99 | 2 | N/A | 22.02 | 4 | 0 | 4 | 0 | N/A | 0 | 4 | 5 | 0.1 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 0.59 | 46 | 27 | 19 | 2026-08-27 | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 41 | 44 | 4 | 0 | 275 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | -902 | 0.91 | 1 | 6 | 2 | 0 | 0 | 1 | 125 | 2.81 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 7 | 7 | 5 | 0 | 1 | 0 | 0 | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 37 | ✓ | 1 | 0.59 | 0
Ribbons | TP4_DataCenter_v1 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-01-30 | 4 | 1 | 8 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 45 | 13 | 1 | 12 | 1 | 1:12 | 0.63 | 8 | 1 | 7 | 1 | 1:07 | 0 | 8 | 9 | 0.03 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 1 | 1 | 1 | 0 | 2026-01-30 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-01-30 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-01-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-01-30 | 2 | 1 | 8 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 1 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-01-30 | -4 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 12 | 0 | ✓ | 1 | 1 | 0
Ribbons | TP4_DataCenter_v2 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-02-27 | 3 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 30 | 11 | 1 | 10 | 3 | 1:10 | 0.47 | 7 | 1 | 6 | 1 | 1:06 | 0 | 7 | 8 | 0.04 | 2.86 | 0 | N/A | N/A | N/A | 0 | 0 | 0.75 | 4 | 3 | 1 | 2026-02-27 | 0.75 | 4 | 3 | 1 | 0.75 | 3 | N/A | 2026-02-27 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-02-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-02-27 | 1 | 0 | 7 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-02-27 | -69 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | ✓ | 1 | 0.75 | 0
Ribbons | TP4_DataCenter_v3 2 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | 2 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 30 | 9 | 1 | 8 | 2 | 1:08 | 0.34 | 7 | 1 | 6 | 1 | 1:06 | 0 | 7 | 7 | 0 | 2.86 | 0 | N/A | N/A | N/A | 0 | 0 | 0.71 | 7 | 5 | 2 | 2026-03-31 | 0.71 | 7 | 5 | 2 | 0.71 | 5 | N/A | 2026-03-31 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 1 | 0 | 7 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | -123 | 0.67 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 8 | 3 | ✓ | 1 | 0.71 | 0
Ribbons | TP4_DataCenter_v4 2 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-04-30 | 2 | 1 | 5 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0 | 50 | 7 | 1 | 6 | 2 | 1:06 | 0.73 | 5 | 1 | 4 | 2 | 1:04 | 0 | 5 | 5 | 0 | 2.6 | 0 | N/A | N/A | N/A | 0 | 0 | 0.78 | 9 | 7 | 2 | 2026-04-30 | 0.78 | 9 | 7 | 2 | 0.78 | 7 | N/A | 2026-04-30 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-04-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | 2 | 1 | 5 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-04-30 | -99 | 0.7 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 6 | 5 | ✓ | 1 | 0.78 | 0
Ribbons | TP4_DataCenter_v5 2 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-05-29 | 2 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 15 | 7 | 1 | 6 | 3 | 1:06 | 0.32 | 5 | 1 | 4 | 1 | 1:04 | 0 | 5 | 5 | 0 | 2.6 | 0 | N/A | N/A | N/A | 0 | 0 | 0.58 | 12 | 7 | 5 | 2026-05-29 | 0.58 | 12 | 7 | 5 | 0.58 | 7 | N/A | 2026-05-29 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-05-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | 0 | 0 | 5 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 9 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-05-29 | -280 | 0.63 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 6 | 9 | ✓ | 1 | 0.58 | 0
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Wrong Status - Actual Starts | Wrong Status - Actual Finishes | Invalid Forecast Dates | Expected Finish But Still In-Progress | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | SF Relations | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Missing Baseline Starts | Missing Baseline Finishes | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | High Float 10% of Rem Project Duration | High Float 44d | Zero Days Float | Number of Leads | Number of Lags | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | New To-Go Tasks in Status Period | New Completed Tasks in Status Period | New Critical Tasks in Status Period | Riding Data Date | Deadlines | Missed Activities | High Float 10% | Negative Float | Max Float | Tasks & Milestones (To Go) | Milestones (To-Go) | Normal Tasks (To-Go) | Normal Tasks (To-Go, In Progress) | Milestone-to-Task Ratio (To-Go) | Float Ratio™ | Critical Path (Tasks & Milestones) | Critical Path (Milestones) | Critical Path (Normal Tasks) | Critical Path (Normal In Progress) | Critical Milestone-to-Task Ratio (To-Go) | Negative Float | Zero Days Float | Near-Critical (<10 Days Float) | Near CP - Float Ratio™ | CP Logic Density™ | Critical Tasks Created in Status Period | Critical CEI - Value Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | Status Date | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Status Date | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Status Date | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | New Activity - Created | New Activity - Already Finished | New Activity - Finished in Status Period | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Max Float | Newly Created Activity & Critical - Created (Snapshot) | Number of Leads | Number of Lags | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Total New Completed Tasks & Milestones in Status Period | Total New Tasks & Milestones in Status Period | Riding Data Date | Deadlines | Missed Activities | Wrong Status | Invalid Forecast Dates | Expected Finish | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | SF Relations | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Missing Baseline Starts | Missing Baseline Finishes | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | SV(t) | SPI(t) | Missing Predecessors | Missing Successors | Activities with Lags | SS Predecessors | SF Predecessors | FF Predecessors | FS Predecessors | Logic Density™ | Merge Hotspot | Diverge Hotspot | Logic Hotspot™ | Summary Links | Open Start | Open Finish | Open Ends with Constraints | Open Ends w/o Constraints | Open Ends | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Score
Ribbons | SRA Large Test File2 | 0% | 1% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  | 62% | 72% | 7% | 0% | 1% | 0% | 2% | 4% | 100% | 2% | 20% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 87% | 35% | 12% |  | 58% | 8% | 92% | 9% |  |  | 19% | 9% | 91% | 2% |  | 12% | 7% | 24% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 51% | 49% |  |  |  | 51% | 49% |  | 51% |  |  |  |  | 69% | 31% |  | 69% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 35% | 72% | 7% | 12% |  |  | 0% | 0% | 0% | 2% | 4% | 100% | 2% | 20% |  |  | 0% | 0% | 87% | 0% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  |  |  | 1% | 1% | 0% | 4% | 0% | 2% | 99% |  | 9% | 8% | 1% | 0% | 0% | 1% | 0% | 1% | 1% | 0% | 0% | 1% | 6% | 0% | 0% | 73% | 12% | 10% | 36% | 1% | 94% | 87%
Ribbons | TP4_DataCenter_v1 | 0% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 31% | 8% | 62% | 0% | 0% | 0% | 0% | 8% | ( N/A ) | 8% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 15% | 0% |  | 87% | 8% | 92% | 8% |  |  | 62% | 13% | 88% | 13% |  | 0% | 62% | 69% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 100% | 0% |  |  |  | 100% | 0% |  | 100% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 15% | 8% | 62% | 0% |  |  | 0% | 0% | 0% | 0% | 8% | ( N/A ) | 8% | ( N/A ) |  |  | 0% | 0% | 0% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 0% | 0% | 8% | 0% | 100% | 0%
Ribbons | TP4_DataCenter_v2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 27% | 0% | 64% | 0% | 0% | 0% | 0% | 13% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 8% | 9% | 0% |  | 73% | 9% | 91% | 27% |  |  | 64% | 14% | 86% | 14% |  | 0% | 64% | 73% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 75% | 25% |  |  |  | 75% | 25% |  | 75% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 9% | 0% | 64% | 0% |  |  | 0% | 0% | 0% | 0% | 13% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 25%
Ribbons | TP4_DataCenter_v3 | 0% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 22% | 0% | 78% | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 31% | 11% | 0% |  | 60% | 11% | 89% | 22% |  |  | 78% | 14% | 86% | 14% |  | 0% | 78% | 78% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 71% | 29% |  |  |  | 71% | 29% |  | 71% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 11% | 0% | 78% | 0% |  |  | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 43% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 100% | 43%
Ribbons | TP4_DataCenter_v4 | 0% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 29% | 14% | 71% | 0% | 0% | 0% | 0% | 20% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 69% | 29% | 0% |  | 47% | 14% | 86% | 29% |  |  | 71% | 20% | 80% | 40% |  | 0% | 71% | 71% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 78% | 22% |  |  |  | 78% | 22% |  | 78% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 29% | 14% | 71% | 0% |  |  | 0% | 0% | 0% | 0% | 20% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 56% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 17% | 0% | 0% | 67% | 0% | 100% | 56%
Ribbons | TP4_DataCenter_v5 | 0% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 29% | 0% | 71% | 0% | 0% | 0% | 0% | 25% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 77% | 0% | 0% |  | 47% | 14% | 86% | 43% |  |  | 71% | 20% | 80% | 20% |  | 0% | 71% | 71% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 58% | 42% |  |  |  | 58% | 42% |  | 58% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 0% | 0% | 71% | 0% |  |  | 0% | 0% | 0% | 0% | 25% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 75% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 67% | 0% | 100% | 75%
Ribbons | Project2 | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 40% | 42% | 39% | 0% | 2% | 1% | 2% | 3% | 0% | 8% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 37% | 0% |  | 84% | 0% | 100% | 3% |  |  | 39% | 0% | 100% | 2% |  | 0% | 39% | 47% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 74% | 26% |  |  |  | 74% | 26% |  | 74% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 37% | 42% | 39% | 0% |  |  | 0% | 2% | 1% | 2% | 3% | 0% | 8% | 0% |  |  | 0% | 0% | 67% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 4% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 4% | 5% | 4% | 0% | 1% | 1% | 0% | 0% | 42% | 0% | 1% | 0% | 0% | 0% | 67%
Ribbons | Project5_TAMPERED | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  | 43% | 44% | 4% | 0% | 1% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 41% | 0% |  | 79% | 0% | 100% | 2% |  |  | 4% | 0% | 100% | 0% |  | 0% | 4% | 5% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 59% | 41% |  |  |  | 59% | 41% |  | 59% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 41% | 44% | 4% | 0% |  |  | 0% | 2% | 1% | 0% | 1% | 0% | 0% | 0% |  |  | 0% | 0% | 80% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  |  |  | 1% | 5% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 5% | 6% | 5% | 0% | 1% | 0% | 0% | 1% | 44% | 0% | 0% | 0% | 0% | 0% | 80%
Ribbons | Project2 2 | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 40% | 42% | 39% | 0% | 2% | 1% | 2% | 3% | 0% | 8% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 37% | 0% |  | 84% | 0% | 100% | 3% |  |  | 39% | 0% | 100% | 2% |  | 0% | 39% | 47% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 74% | 26% |  |  |  | 74% | 26% |  | 74% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 37% | 42% | 39% | 0% |  |  | 0% | 2% | 1% | 2% | 3% | 0% | 8% | 0% |  |  | 0% | 0% | 67% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 4% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 4% | 5% | 4% | 0% | 1% | 1% | 0% | 0% | 42% | 0% | 1% | 0% | 0% | 0% | 67%
Ribbons | Project3 | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 39% | 41% | 39% | 0% | 2% | 1% | 3% | 3% | 0% | 8% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 30% | 0% |  | 81% | 0% | 100% | 1% |  |  | 39% | 0% | 100% | 3% |  | 0% | 39% | 48% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 67% | 33% |  |  |  | 67% | 33% |  | 67% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 30% | 41% | 39% | 0% |  |  | 0% | 2% | 1% | 3% | 3% | 0% | 8% | 0% |  |  | 0% | 0% | 75% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 4% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 4% | 5% | 4% | 0% | 1% | 1% | 0% | 0% | 41% | 0% | 0% | 0% | 0% | 0% | 75%
Ribbons | Project4 | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 39% | 41% | 37% | 0% | 1% | 1% | 3% | 3% | 0% | 8% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 31% | 0% |  | 80% | 0% | 100% | 1% |  |  | 37% | 0% | 100% | 0% |  | 0% | 37% | 48% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 58% | 42% |  |  |  | 58% | 42% |  | 58% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 31% | 41% | 37% | 0% |  |  | 0% | 2% | 1% | 3% | 3% | 0% | 8% | 0% |  |  | 0% | 0% | 79% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 4% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 4% | 5% | 4% | 0% | 1% | 0% | 0% | 0% | 41% | 0% | 0% | 0% | 0% | 0% | 79%
Ribbons | Project5 | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  | 43% | 44% | 4% | 0% | 1% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 41% | 0% |  | 79% | 0% | 100% | 2% |  |  | 4% | 0% | 100% | 0% |  | 0% | 4% | 5% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 59% | 41% |  |  |  | 59% | 41% |  | 59% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 41% | 44% | 4% | 0% |  |  | 0% | 2% | 1% | 0% | 1% | 0% | 0% | 0% |  |  | 0% | 0% | 80% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  |  |  | 1% | 5% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 5% | 6% | 5% | 0% | 1% | 0% | 0% | 1% | 44% | 0% | 0% | 0% | 0% | 0% | 80%
Ribbons | Large Test File | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 4% |  | 79% | 88% | 0% | 0% | 0% | 0% | 9% | 1% | 100% | 1% | 20% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 86% | 46% | 4% |  | 59% | 8% | 92% | 11% |  |  | 4% | 19% | 81% | 2% |  | 4% | 0% | 7% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 51% | 49% |  |  |  | 51% | 49% |  | 51% |  |  |  |  | 70% | 30% |  | 70% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 46% | 88% | 0% | 4% |  |  | 0% | 0% | 0% | 9% | 1% | 100% | 1% | 20% |  |  | 0% | 0% | 91% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 4% |  |  |  | 1% | 1% | 0% | 4% | 0% | 2% | 99% |  | 9% | 8% | 1% | 0% | 0% | 1% | 0% | 1% | 1% | 0% | 0% | 1% | 6% | 0% | 0% | 88% | 4% | 9% | 0% | 0% | 94% | 91%
Ribbons | Large Test File2 | 0% | 1% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  | 62% | 72% | 7% | 0% | 1% | 0% | 2% | 4% | 100% | 2% | 20% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 87% | 35% | 12% |  | 58% | 8% | 92% | 9% |  |  | 19% | 8% | 92% | 2% |  | 12% | 7% | 24% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 51% | 49% |  |  |  | 51% | 49% |  | 51% |  |  |  |  | 69% | 31% |  | 69% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 35% | 72% | 7% | 12% |  |  | 0% | 0% | 0% | 2% | 4% | 100% | 2% | 20% |  |  | 0% | 0% | 87% | 0% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  |  |  | 1% | 1% | 0% | 4% | 0% | 2% | 99% |  | 9% | 8% | 1% | 0% | 0% | 1% | 0% | 1% | 1% | 0% | 0% | 1% | 6% | 0% | 0% | 73% | 12% | 10% | 36% | 1% | 94% | 87%
Ribbons | Large Test File Leveled | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 5% |  | 78% | 89% | 0% | 0% | 0% | 0% | 8% | 1% | 100% | 1% | 20% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 89% | 46% | 5% |  | 59% | 8% | 92% | 11% |  |  | 5% | 16% | 84% | 2% |  | 5% | 0% | 5% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 51% | 49% |  |  |  | 51% | 49% |  | 51% |  |  |  |  | 70% | 30% |  | 70% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 46% | 89% | 0% | 5% |  |  | 0% | 0% | 0% | 8% | 1% | 100% | 1% | 20% |  |  | 0% | 0% | 91% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 5% |  |  |  | 1% | 1% | 0% | 4% | 0% | 2% | 99% |  | 9% | 8% | 1% | 0% | 0% | 1% | 0% | 1% | 1% | 0% | 0% | 1% | 6% | 0% | 0% | 89% | 4% | 9% | 0% | 0% | 94% | 91%
Ribbons | Large Test File 2 | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 4% |  | 79% | 88% | 0% | 0% | 0% | 0% | 9% | 1% | 100% | 1% | 20% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 86% | 46% | 4% |  | 59% | 8% | 92% | 11% |  |  | 4% | 19% | 81% | 2% |  | 4% | 0% | 7% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 51% | 49% |  |  |  | 51% | 49% |  | 51% |  |  |  |  | 70% | 30% |  | 70% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 46% | 88% | 0% | 4% |  |  | 0% | 0% | 0% | 9% | 1% | 100% | 1% | 20% |  |  | 0% | 0% | 91% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 4% |  |  |  | 1% | 1% | 0% | 4% | 0% | 2% | 99% |  | 9% | 8% | 1% | 0% | 0% | 1% | 0% | 1% | 1% | 0% | 0% | 1% | 6% | 0% | 0% | 88% | 4% | 9% | 0% | 0% | 94% | 91%
Ribbons | Large Test File2 2 | 0% | 1% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  | 62% | 72% | 7% | 0% | 1% | 0% | 2% | 4% | 100% | 2% | 20% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 87% | 35% | 12% |  | 58% | 8% | 92% | 9% |  |  | 19% | 8% | 92% | 2% |  | 12% | 7% | 24% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 51% | 49% |  |  |  | 51% | 49% |  | 51% |  |  |  |  | 69% | 31% |  | 69% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 35% | 72% | 7% | 12% |  |  | 0% | 0% | 0% | 2% | 4% | 100% | 2% | 20% |  |  | 0% | 0% | 87% | 0% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  |  |  | 1% | 1% | 0% | 4% | 0% | 2% | 99% |  | 9% | 8% | 1% | 0% | 0% | 1% | 0% | 1% | 1% | 0% | 0% | 1% | 6% | 0% | 0% | 73% | 12% | 10% | 36% | 1% | 94% | 87%
Ribbons | SRA Large Test File2 2 | 0% | 1% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  | 62% | 72% | 7% | 0% | 1% | 0% | 2% | 4% | 100% | 2% | 20% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 87% | 35% | 12% |  | 58% | 8% | 92% | 9% |  |  | 19% | 8% | 92% | 2% |  | 12% | 7% | 24% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 51% | 49% |  |  |  | 51% | 49% |  | 51% |  |  |  |  | 69% | 31% |  | 69% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 35% | 72% | 7% | 12% |  |  | 0% | 0% | 0% | 2% | 4% | 100% | 2% | 20% |  |  | 0% | 0% | 87% | 0% | 34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 1% | 0% | 0% | 12% |  |  |  | 1% | 1% | 0% | 4% | 0% | 2% | 99% |  | 9% | 8% | 1% | 0% | 0% | 1% | 0% | 1% | 1% | 0% | 0% | 1% | 6% | 0% | 0% | 73% | 12% | 10% | 36% | 1% | 94% | 87%
Ribbons | Jacked Up Schedule 1 | ( N/A ) | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 0% | 0% | N/A | 20% | 7% | 13% | ( N/A ) | 7% | 0% | 0% | 100% | 100% | 0% | 0% | 0% |  | 20% | 0% | 60% | 0% | 0% | 0% | 0% | 7% | ( N/A ) | 7% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 13% | 0% | ( N/A ) | 20% | 0% |  | 100% | 13% | 87% | 0% |  |  | 60% | 22% | 78% | 0% |  | 0% | 60% | 93% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | N/A | N/A |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 20% | 0% | 60% | 0% |  |  | 0% | 0% | 0% | 0% | 7% | ( N/A ) | 7% | ( N/A ) |  |  | 13% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | N/A | 20% | 7% | 13% | 7% | 7% | 0% | 0% | 100% | 100% | 0% | 0% | 0% |  |  |  | 7% | 13% | 0% | 7% | 0% | 7% | 80% |  | 7% | 7% | 0% | N/A | 7% | 7% | 0% | 13% | 20% | N/A | N/A | N/A | N/A | N/A | N/A | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Ribbons | Jacked up Schedule 2 | ( N/A ) | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 0% | 0% | N/A | 33% | 17% | 17% | ( N/A ) | 0% | 0% | 0% | 100% | 100% | 17% | 0% | 33% |  | 17% | 0% | 50% | 0% | 0% | 0% | 0% | 17% | ( N/A ) | 17% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 33% | 0% | ( N/A ) | 17% | 33% |  | 100% | 50% | 50% | 0% |  |  | 83% | 60% | 40% | 0% |  | 33% | 50% | 83% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | N/A | N/A |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 17% | 0% | 50% | 33% |  |  | 0% | 0% | 0% | 0% | 17% | ( N/A ) | 17% | ( N/A ) |  |  | 33% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | N/A | 33% | 17% | 17% | 0% | 0% | 0% | 0% | 100% | 100% | 17% | 0% | 33% |  |  |  | 17% | 17% | 0% | 0% | 0% | 0% | 83% |  | 17% | 17% | 0% | N/A | 0% | 0% | 0% | 17% | 33% | N/A | N/A | N/A | N/A | N/A | N/A | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Ribbons | Hard_File_updated3 | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 79% | 0% | 9% | 0% | 9% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 72% |  | 19% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 6% | 0% | 90% | 16% | 72% |  | 62% | 24% | 76% | 0% |  |  | 72% | 18% | 82% | 0% |  | 72% | 0% | 82% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 47% | 53% |  |  |  | 47% | 53% |  | 47% |  |  |  |  | 53% | 47% |  | 53% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 16% | 0% | 0% | 72% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 6% | 0% | 88% | 0% | 0% | 0% | 0% | 0% | 0% | 79% | 0% | 9% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 72% |  |  |  | 3% | 5% | 0% | 0% | 0% | 0% | 97% |  | 1% | 1% | 0% | 0% | 0% | 0% | 4% | 2% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 77% | 0% | 0% | 0% | 2% | 88%
Ribbons | Hard_File_updated4 24 hour calendar | 0% | 0% | 16% | 0% | 0% | 0% | 0% | 64% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 79% |  | 21% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 90% | 16% | 79% |  | 17% | 26% | 74% | 21% |  |  | 79% | 27% | 73% | 7% |  | 79% | 0% | 84% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 83% | 17% |  |  |  | 83% | 17% |  | 83% |  |  |  |  | 81% | 19% |  | 81% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 16% | 0% | 0% | 79% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 90% | 0% | 16% | 0% | 0% | 0% | 0% | 64% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 79% |  |  |  | 3% | 5% | 0% | 0% | 0% | 0% | 97% |  | 1% | 1% | 0% | 0% | 0% | 0% | 4% | 2% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 92% | 0% | 8% | 0% | 0% | 90%
Ribbons | Hard_File | ( N/A ) | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 1% | 80% | 0% | 6% | 1% | 5% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 18% | 2% | 71% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 1% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 18% | 0% |  | 100% | 23% | 77% | 0% |  |  | 31% | 21% | 79% | 0% |  | 0% | 71% | 82% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | N/A | N/A |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 18% | 2% | 71% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 1% | ( N/A ) |  |  | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 0% | 1% | 80% | 0% | 6% | 1% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 5% | 0% | 0% | 0% | 0% | 99% |  | 1% | 1% | 0% | 0% | 0% | 0% | 1% | 5% | 6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 2% | ( N/A )
Ribbons | Hard_File_updated | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 82% | 0% | 8% | 0% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 22% | 6% | 72% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 14% | 17% | 0% |  | 94% | 23% | 77% | 1% |  |  | 32% | 18% | 82% | 0% |  | 0% | 72% | 79% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 27% | 73% |  |  |  | 27% | 73% |  | 55% |  |  |  |  | 33% | 67% |  | 33% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 17% | 6% | 72% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 82% | 0% | 0% | 0% | 0% | 0% | 1% | 82% | 0% | 8% | 0% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 3% | 6% | 0% | 0% | 0% | 0% | 97% |  | 1% | 1% | 0% | 0% | 0% | 0% | 1% | 5% | 9% | 1% | 0% | 0% | 0% | 0% | 0% | 4% | 0% | 0% | 0% | 0% | 3% | 82%
Ribbons | Hard_File_updated_with_logic_reestablished | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 82% | 0% | 7% | 0% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 74% |  | 17% | 9% | 8% | 0% | 0% | 0% | 0% | 1% | ( N/A ) | 1% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 1% | 0% | 92% | 16% | 74% |  | 94% | 23% | 77% | 1% |  |  | 82% | 20% | 80% | 1% |  | 74% | 8% | 84% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 27% | 73% |  |  |  | 27% | 73% |  | 55% |  |  |  |  | 33% | 67% |  | 33% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 16% | 9% | 8% | 74% |  |  | 0% | 0% | 0% | 0% | 1% | ( N/A ) | 1% | ( N/A ) |  |  | 1% | 0% | 82% | 0% | 0% | 0% | 0% | 0% | 1% | 82% | 0% | 7% | 0% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 74% |  |  |  | 2% | 6% | 0% | 0% | 0% | 0% | 98% |  | 1% | 1% | 0% | 0% | 0% | 0% | 1% | 5% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 6% | 77% | 0% | 0% | 0% | 3% | 82%
Ribbons | Hard_File_updated2 | 0% | 0% | 55% | ( N/A ) | 0% | 0% | 0% | 81% | 0% | 8% | 0% | 8% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 30% | 7% | 33% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 86% | 29% | 0% |  | 69% | 24% | 76% | 0% |  |  | 32% | 21% | 79% | 0% |  | 0% | 33% | 71% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 59% | 41% |  |  |  | 59% | 41% |  | 59% |  |  |  |  | 62% | 38% |  | 62% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 29% | 7% | 33% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 75% | 0% | 55% | 0% | 0% | 0% | 0% | 81% | 0% | 8% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 3% | 5% | 0% | 0% | 0% | 0% | 97% |  | 1% | 1% | 0% | 0% | 0% | 0% | 1% | 5% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 3% | 0% | 0% | 52% | 0% | 2% | 75%
Ribbons | Hard_File_updated3 2 | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 79% | 0% | 9% | 0% | 9% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 72% |  | 19% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 6% | 0% | 90% | 16% | 72% |  | 62% | 24% | 76% | 0% |  |  | 72% | 18% | 82% | 0% |  | 72% | 0% | 82% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 47% | 53% |  |  |  | 47% | 53% |  | 47% |  |  |  |  | 53% | 47% |  | 53% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 16% | 0% | 0% | 72% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 6% | 0% | 88% | 0% | 0% | 0% | 0% | 0% | 0% | 79% | 0% | 9% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 72% |  |  |  | 3% | 5% | 0% | 0% | 0% | 0% | 97% |  | 1% | 1% | 0% | 0% | 0% | 0% | 4% | 2% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 77% | 0% | 0% | 0% | 2% | 88%
Ribbons | Hard_File_updated4 24 hour calendar 2 | 0% | 0% | 16% | 0% | 0% | 0% | 0% | 64% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 79% |  | 21% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 90% | 16% | 79% |  | 17% | 26% | 74% | 21% |  |  | 79% | 27% | 73% | 7% |  | 79% | 0% | 84% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 83% | 17% |  |  |  | 83% | 17% |  | 83% |  |  |  |  | 81% | 19% |  | 81% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 16% | 0% | 0% | 79% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 90% | 0% | 16% | 0% | 0% | 0% | 0% | 64% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 79% |  |  |  | 3% | 5% | 0% | 0% | 0% | 0% | 97% |  | 1% | 1% | 0% | 0% | 0% | 0% | 4% | 2% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 92% | 0% | 8% | 0% | 0% | 90%
Ribbons | EVM1 | 0% | ( N/A ) | 109% | 0% | 0% | 0% | 0% | 0% | 0% | 18% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 91% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 0% | 0% |  | 100% | 27% | 73% | 18% |  |  | 91% | 30% | 70% | 10% |  | 0% | 91% | 100% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 0% | 100% |  |  |  | 0% | 100% |  | 0% |  |  |  |  | 0% | 100% |  | 0% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 0% | 0% | 91% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 0% | 0% | 109% | 0% | 0% | 0% | 0% | 0% | 0% | 18% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 9% | 9% | 0% | 0% | 0% | 0% | 91% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9% | 18% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0%
Ribbons | EVM2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13% | 0% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 88% | 0% | 0% |  | 73% | 25% | 75% | 13% |  |  | 100% | 25% | 75% | 13% |  | 0% | 100% | 100% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 25% | 75% |  |  |  | 25% | 75% |  | 25% |  |  |  |  | 33% | 67% |  | 33% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 0% | 0% | 100% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 88% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13% | 0% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 9% | 9% | 0% | 0% | 0% | 0% | 91% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9% | 18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 88%
Ribbons | Project2 3 | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 40% | 42% | 39% | 0% | 2% | 1% | 2% | 3% | 0% | 8% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 37% | 0% |  | 84% | 0% | 100% | 3% |  |  | 39% | 0% | 100% | 2% |  | 0% | 39% | 47% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 74% | 26% |  |  |  | 74% | 26% |  | 74% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 37% | 42% | 39% | 0% |  |  | 0% | 2% | 1% | 2% | 3% | 0% | 8% | 0% |  |  | 0% | 0% | 67% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 4% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 4% | 5% | 4% | 0% | 1% | 1% | 0% | 0% | 42% | 0% | 1% | 0% | 0% | 0% | 67%
Ribbons | Project3 2 | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 39% | 41% | 39% | 0% | 2% | 1% | 3% | 3% | 0% | 8% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 30% | 0% |  | 81% | 0% | 100% | 1% |  |  | 39% | 0% | 100% | 3% |  | 0% | 39% | 48% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 67% | 33% |  |  |  | 67% | 33% |  | 67% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 30% | 41% | 39% | 0% |  |  | 0% | 2% | 1% | 3% | 3% | 0% | 8% | 0% |  |  | 0% | 0% | 75% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 4% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 4% | 5% | 4% | 0% | 1% | 1% | 0% | 0% | 41% | 0% | 0% | 0% | 0% | 0% | 75%
Ribbons | Project4 2 | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 39% | 41% | 37% | 0% | 1% | 1% | 3% | 3% | 0% | 8% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 31% | 0% |  | 80% | 0% | 100% | 1% |  |  | 37% | 0% | 100% | 0% |  | 0% | 37% | 48% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 58% | 42% |  |  |  | 58% | 42% |  | 58% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 31% | 41% | 37% | 0% |  |  | 0% | 2% | 1% | 3% | 3% | 0% | 8% | 0% |  |  | 0% | 0% | 79% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 1% | 4% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 4% | 5% | 4% | 0% | 1% | 0% | 0% | 0% | 41% | 0% | 0% | 0% | 0% | 0% | 79%
Ribbons | Project5_TAMPERED 2 | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  | 43% | 44% | 4% | 0% | 1% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 41% | 0% |  | 79% | 0% | 100% | 2% |  |  | 4% | 0% | 100% | 0% |  | 0% | 4% | 5% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 59% | 41% |  |  |  | 59% | 41% |  | 59% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 41% | 44% | 4% | 0% |  |  | 0% | 2% | 1% | 0% | 1% | 0% | 0% | 0% |  |  | 0% | 0% | 80% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  |  |  | 1% | 5% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 5% | 6% | 5% | 0% | 1% | 0% | 0% | 1% | 44% | 0% | 0% | 0% | 0% | 0% | 80%
Ribbons | TP4_DataCenter_v1 2 | 0% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 31% | 8% | 62% | 0% | 0% | 0% | 0% | 8% | ( N/A ) | 8% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 15% | 0% |  | 87% | 8% | 92% | 8% |  |  | 62% | 13% | 88% | 13% |  | 0% | 62% | 69% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 100% | 0% |  |  |  | 100% | 0% |  | 100% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 15% | 8% | 62% | 0% |  |  | 0% | 0% | 0% | 0% | 8% | ( N/A ) | 8% | ( N/A ) |  |  | 0% | 0% | 0% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 0% | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 0% | 0% | 8% | 0% | 100% | 0%
Ribbons | TP4_DataCenter_v2 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 27% | 0% | 64% | 0% | 0% | 0% | 0% | 13% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 8% | 9% | 0% |  | 73% | 9% | 91% | 27% |  |  | 64% | 14% | 86% | 14% |  | 0% | 64% | 73% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 75% | 25% |  |  |  | 75% | 25% |  | 75% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 9% | 0% | 64% | 0% |  |  | 0% | 0% | 0% | 0% | 13% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9% | 0% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 25%
Ribbons | TP4_DataCenter_v3 2 | 0% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 22% | 0% | 78% | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 31% | 11% | 0% |  | 60% | 11% | 89% | 22% |  |  | 78% | 14% | 86% | 14% |  | 0% | 78% | 78% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 71% | 29% |  |  |  | 71% | 29% |  | 71% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 11% | 0% | 78% | 0% |  |  | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 43% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 100% | 43%
Ribbons | TP4_DataCenter_v4 2 | 0% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 29% | 14% | 71% | 0% | 0% | 0% | 0% | 20% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 69% | 29% | 0% |  | 47% | 14% | 86% | 29% |  |  | 71% | 20% | 80% | 40% |  | 0% | 71% | 71% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 78% | 22% |  |  |  | 78% | 22% |  | 78% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 29% | 14% | 71% | 0% |  |  | 0% | 0% | 0% | 0% | 20% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 56% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 17% | 0% | 0% | 67% | 0% | 100% | 56%
Ribbons | TP4_DataCenter_v5 2 | 0% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 29% | 0% | 71% | 0% | 0% | 0% | 0% | 25% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 77% | 0% | 0% |  | 47% | 14% | 86% | 43% |  |  | 71% | 20% | 80% | 20% |  | 0% | 71% | 71% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 58% | 42% |  |  |  | 58% | 42% |  | 58% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 0% | 0% | 71% | 0% |  |  | 0% | 0% | 0% | 0% | 25% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 75% | 0% | 57% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 67% | 0% | 100% | 75%

## Phase Analysis
Deltek Acumen Fuse® Ribbon View Report
Workbook: Workbook1 - 17639 Activities
Quick Add Metrics
Created on: 8/7/2026
Created by: dpolitte
Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
 | time axis 2012-08-01 to 2029-04-01
Phase Analyzer | Status Date | 2012-09-01 | 2012-09-12 | 2012-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10 | 2025-03-10
Phase Analyzer | WBS | 1 | 1 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Phase Analyzer | New Activity - Created (Snapshot) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | New Activity - Already Finished (Snapshot) - check/compare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | New Activity - Finished in Status Period (Snapshot) - check/compare | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Specific Task Start | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-06-17 | 2027-06-17 | 2027-08-05 | 2027-08-05 | 2027-09-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Specific Task Finish | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-07-14 | N/A | 2027-09-01 | 2027-10-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Score | 100 | 100 | 100 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
 | time axis 2012-08-01 to 2029-04-01
Phase Analyzer | Status Date
Phase Analyzer | WBS
Phase Analyzer | New Activity - Created (Snapshot)
Phase Analyzer | New Activity - Already Finished (Snapshot) - check/compare
Phase Analyzer | New Activity - Finished in Status Period (Snapshot) - check/compare
Phase Analyzer | Specific Task Start
Phase Analyzer | Specific Task Finish
Phase Analyzer | Score