## Large-Test-File
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
Large Test File vs Large Test File2 - 4249 Activities | Large Test File vs Large Test File2 - 4249 Activities | Large Test File vs Large Test File2 - 4249 Activities | Large Test File vs Large Test File2 - 4249 Activities
Metric History
Created on: 7/15/2026 | Created on: 7/15/2026 | Created on: 7/15/2026 | Created on: 7/15/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
|  | Large Test File (2/7/2025 5:00:00 PM) |  |  | Large Test File2 (3/10/2025 5:00:00 PM)
Metric ID | Metric Name | Failed | X | % | Failed | X | %
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| Specific Task Start | F | N/A |  | F | N/A
| Specific Task Finish | F | N/A |  | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0% | F | 1 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0% | F | 4 | 1%
| Invalid Forecast Dates | F | 2 | 0% | F | 338 | 34%
| Expected Finish But Still In-Progress | F | 0 | 0% | F | 0 | 0%
| Missing WBS | F | 0 | 0% | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0% | F | 0 | 0%
| Activities with Duration=0 | F | 7 | 1% | F | 4 | 0%
| Estimated Duration | F | 0 | 0% | F | 0 | 0%
| Missing Logic | F | 2 | 0% | F | 3 | 0%
| Missing Predecessors | F | 1 | 0% | F | 1 | 0%
| Missing Successors | F | 2 | 0% | F | 2 | 0%
| Open Start | F | 0 | 0% | F | 0 | 0%
| Open Finish | F | 2 | 0% | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0% | F | 0 | 0%
| Summary Links | F | 0 | 0% | F | 0 | 0%
| Hard Constraints | F | 1 | 0% | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0% | F | 0 | 0%
| Negative Float | F | 41 | 4% | F | 122 | 12%
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| High Float 44d | F | 898 | 88% | F | 717 | 72%
| Zero Days Float | F | 2 | 0% | F | 66 | 7%
| Hidden Duration (Planned) | F | 2 | 0% | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 9% | F | 4 | 2%
| Critical Merge Hotspot | F | 9 | 1% | F | 35 | 4%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100% | F | 2 | 100%
| Critical Diverge Hotspot | F | 11 | 1% | F | 22 | 2%
| Diverge Hotspot w/Successor Lags | F | 1 | 20% | F | 1 | 20%
| Riding Data Date | F | 0 | 0% | F | 0 | 0%
| Deadlines | F | 0 | 0% | F | 0 | 0%
| High Float 10% | F | 467 | 46% | F | 354 | 35%
| Negative Float | F | 41 | 4% | F | 122 | 12%
| Tasks & Milestones (To Go) | F | 1024 | 59% | F | 998 | 58%
| Milestones (To-Go) | F | 79 | 8% | F | 79 | 8%
| Normal Tasks (To-Go) | F | 945 | 92% | F | 919 | 92%
| Normal Tasks (To-Go, In Progress) | F | 108 | 11% | F | 92 | 9%
| Critical Path (Tasks & Milestones) | F | 43 | 4% | F | 185 | 19%
| Critical Path (Milestones) | F | 8 | 19% | F | 15 | 8%
| Critical Path (Normal Tasks) | F | 35 | 81% | F | 170 | 92%
| Critical Path (Normal In Progress) | F | 1 | 2% | F | 4 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 |  | F | 1:11
| Negative Float | F | 41 | 4% | F | 122 | 12%
| Zero Days Float | F | 2 | 0% | F | 66 | 7%
| Near-Critical (<10 Days Float) | F | 74 | 7% | F | 242 | 24%
| CP Logic Density™ | F | 7.58 |  | F | 4.27
| Critical CEI - Value Tasks | F | N/A |  | F | 0
| Critical CEI - Complete Tasks | F | N/A |  | F | 0 | 19%
| Critical CEI - Incomplete Tasks | F | N/A |  | F | 3 | 81%
| BEI - Value Tasks | F | 0.51 |  | F | 0.51
| BEI - Total Tasks | F | 1205 |  | F | 1228
| BEI - Complete Tasks | F | 609 | 51% | F | 632 | 51%
| BEI - Incomplete Tasks | F | 596 | 49% | F | 596 | 49%
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| Milestone #1 - 100 | F | N/A |  | F | N/A
| Float Milestone #1 - 100 | F | N/A |  | F | N/A
| Milestone #2 - 101 | F | N/A |  | F | N/A
| Float to Milestone #2 - 101 | F | N/A |  | F | N/A
| Milestone #3 - 102 | F | N/A |  | F | N/A
| Float to Milestone #3 - 102 | F | N/A |  | F | N/A
| Milestone #4 - 103 | F | N/A |  | F | N/A
| Float to Milestone #4 - 103 | F | N/A |  | F | N/A
| Milestone #5 - 104 | F | N/A |  | F | N/A
| Float to Milestone #5 - 104 | F | N/A |  | F | N/A
| New Activities Since Previous Status Date | F | 0 |  | F | 0
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A |  | F | N/A
| Margin - Margin Task Name #2 | F | 2025-08-06 |  | F | 2028-03-06
| Margin - Margin Task Name #3 | F | N/A |  | F | N/A
| Margin - Margin Task Name #4 | F | N/A |  | F | N/A
| Margin - Margin Task Name #5 | F | N/A |  | F | N/A
| Margin - Margin Task Name #6 | F | N/A |  | F | N/A
| Margin - Margin Task Name #7 | F | N/A |  | F | N/A
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A |  | F | N/A
| Margin - Margin Task Name #2 | F | 0 |  | F | 0
| Margin - Margin Task Name #3 | F | N/A |  | F | N/A
| Margin - Margin Task Name #4 | F | N/A |  | F | N/A
| Margin - Margin Task Name #5 | F | N/A |  | F | N/A
| Margin - Margin Task Name #6 | F | N/A |  | F | N/A
| Margin - Margin Task Name #7 | F | 279 | 36% | F | 324 | 39%
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| Total Activities | F | 2125 |  | F | 2124
| Milestones | F | 169 | 8% | F | 169 | 8%
| Normal Tasks | F | 1554 | 73% | F | 1553 | 73%
| Summaries | F | 402 | 19% | F | 402 | 19%
| Hammocks | F | 0 | 0% | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0% | F | 0 | 0%
| Total Tasks & Milestones | F | 1723 | 81% | F | 1722 | 81%
| Completed Tasks & Milestones | F | 699 | 41% | F | 724 | 42%
| Completed Milestones | F | 90 | 53% | F | 90 | 53%
| Completed Tasks | F | 609 | 39% | F | 634 | 41%
| Total Activities (To-Go) - % of Total | F | 1309 | 62% | F | 1284 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78% | F | 998 | 78%
| Milestones (To-Go) | F | 79 | 6% | F | 79 | 6%
| Normal Tasks (To-Go) | F | 945 | 72% | F | 919 | 72%
| Summaries (To-Go) | F | 285 | 22% | F | 286 | 22%
| Hammocks (To-Go) | F | 0 | 0% | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0% | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 43 | 84% | F | 185 | 82%
| Longest Path (Normal Tasks) | F | 35 | 69% | F | 170 | 76%
| Longest Path (Milestones) | F | 8 | 16% | F | 15 | 7%
| Critical Milestones (To-Go) | F | 8 | 19% | F | 15 | 8%
| Critical Normal Tasks (To-Go) | F | 35 | 81% | F | 170 | 92%
| Riding Data Date | F | 0 | 0% | F | 0 | 0%
| Baselined to Start | F | 1544 |  | F | 1543
| Scheduled to Start | F | 1554 |  | F | 1553
| Actual Starts | F | 717 |  | F | 726
| Baselined to Finish | F | 1544 |  | F | 1543
| Scheduled to Finish | F | 1554 |  | F | 1553
| Actual Finishes | F | 609 |  | F | 634
| Started Delayed (<=30 days) | F | 98 | 19% | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10% | F | 52 | 10%
| Started Delayed (>60 days) | F | 366 | 71% | F | 372 | 71%
| Completed Delayed (<=30 days) | F | 71 | 14% | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11% | F | 58 | 11%
| Completed Delayed (>60 days) | F | 365 | 74% | F | 385 | 75%
| BEI - Value Task Starts - Cumulative | F | 0.58 |  | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51 |  | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A |  | F | 0
| HMI - Value Task Finishes - by Status Dates | F | N/A |  | F | 0
| CEI - Value Task Starts - by Status Dates | F | N/A |  | F | 0.1
| CEI - Value Task Finishes - by Status Dates | F | N/A |  | F | 0.19
| FEI - Value Task Starts - Cumulative | F | 2.63 |  | F | 2.49
| FEI - Value Task Finish - Cumulative | F | 2.75 |  | F | 2.75
| Current Baseline to Start & Started (BL Plan) | F | 716 |  | F | 723
| Future Baseline to Start & Started (Early Starts) | F | N/A |  | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0 |  | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 828 |  | F | 820
| Current Baseline to Finish & Finished (BL Plan) | F | 609 |  | F | 632
| Future Baseline to Finish & Finished (Early Finishes) | F | 0 |  | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0 |  | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 935 |  | F | 911
| Duration Ratio Metric (DRM) | F | 584 |  | F | 608
| DRM Graph | F | 584 |  | F | 608
| Baselined to Start | F | 935 |  | F | 911
| Scheduled to Start | F | 945 |  | F | 919
| Baselined to Finish | F | 935 |  | F | 911
| Scheduled to Finish | F | 945 |  | F | 919
| BEI - Value Activities | F | 0.52 |  | F | 0.53
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78% | F | 998 | 78%
| Critical Path To-Go | F | 43 | 4% | F | 185 | 19%
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| Total Activities | F | 2125 |  | F | 2124
| Milestones | F | 169 | 8% | F | 169 | 8%
| Normal Tasks | F | 1554 | 73% | F | 1553 | 73%
| Summaries | F | 402 | 19% | F | 402 | 19%
| Hammocks | F | 0 | 0% | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0% | F | 0 | 0%
| Total Tasks & Milestones | F | 1723 | 81% | F | 1722 | 81%
| Completed Tasks & Milestones | F | 699 | 41% | F | 724 | 42%
| Completed Milestones | F | 90 | 53% | F | 90 | 53%
| Completed Tasks | F | 609 | 39% | F | 634 | 41%
| Total Activities (To-Go) - % of Total | F | 1309 | 62% | F | 1284 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78% | F | 998 | 78%
| Milestones (To-Go) | F | 79 | 6% | F | 79 | 6%
| Normal Tasks (To-Go) | F | 945 | 72% | F | 919 | 72%
| Summaries (To-Go) | F | 285 | 22% | F | 286 | 22%
| Hammocks (To-Go) | F | 0 | 0% | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0% | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 43 | 84% | F | 185 | 82%
| Longest Path (Normal Tasks) | F | 35 | 69% | F | 170 | 76%
| Longest Path (Milestones) | F | 8 | 16% | F | 15 | 7%
| Riding Data Date | F | 0 | 0% | F | 0 | 0%
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| Total Activities (To-Go) - % of Total | F | 1309 | 62% | F | 1284 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78% | F | 998 | 78%
| Summary-to-Task Ratio (To-Go) | F | 1:03 | 0.3 | F | 1:03 | 0.31
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.08 | F | 1:12 | 0.09
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23 | F | 1:11 | 0.09
| Manual Tasks (To-Go) | F | 0 | 0% | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 43 | 4% | F | 185 | 19%
| Wrong Status (To-Go) | F | 0 | 0% | F | 1 | 0%
| Invalid Forecast Dates | F | 2 | 0% | F | 338 | 34%
| Missing WBS (To-Go) | F | 0 | 0% | F | 0 | 0%
| All Activities (To Go) | F | 1024 | 100% | F | 998 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 1024 | 78% | F | 998 | 78%
| Estimated Duration | F | 0 | 0% | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0% | F | 0 | 0%
| Activities with Duration=0 | F | 7 | 1% | F | 4 | 0%
| Avg. Original Duration | F | 41 |  | F | 42
| Avg. Remaining Duration | F | 16 |  | F | 19
| High Baseline Duration (44d) | F | 87 | 9% | F | 86 | 9%
| High Planned Duration (44d) | F | 124 | 13% | F | 120 | 13%
| Insufficient Detail™ | F | 22 | 2% | F | 21 | 2%
| Critical Activities (To-Go) | F | 35 | 4% | F | 170 | 18%
| Avg. Critical Original Duration | F | 14 |  | F | 18
| Avg. Critical Remaining Duration | F | 9 |  | F | 12
| Critical w/High Baseline Duration (44d) | F | 0 | 0% | F | 4 | 0%
| Critical w/High Planned Duration (44d) | F | 2 | 6% | F | 6 | 4%
| Critical w/Insufficient Detail™ | F | 0 | 0% | F | 2 | 0%
| Activities (To-Go) | F | 945 | 61% | F | 919 | 59%
| Total Constraints | F | 82 | 8% | F | 0 | 0%
| Start No Earlier Than | F | 80 | 8% | F | 0 | 0%
| Start No Later Than | F | 0 | 0% | F | 0 | 0%
| Finish No Earlier Than | F | 1 | 0% | F | 0 | 0%
| Finish No Later Than | F | 0 | 0% | F | 0 | 0%
| Hard Constraints | F | 1 | 0% | F | 0 | 0%
| Must Start On | F | 0 | 0% | F | 0 | 0%
| Must Finish On | F | 0 | 0% | F | 0 | 0%
| As Late As Possible | F | 0 | 0% | F | 0 | 0%
| Deadlines | F | 0 | 0% | F | 0 | 0%
| Mandatory Start | F | 1 | 0% | F | 0 | 0%
| Mandatory Finish | F | 0 | 0% | F | 0 | 0%
| Open Ends with Constraints | F | 1 | 0% | F | 0 | 0%
| Open Ends w/o Constraints | F | 1 | 0% | F | 3 | 0%
| Unsatisfied Constraints | F | 0 | 0% | F | 0 | 0%
| No Constraints | F | 942 | 92% | F | 998 | 100%
| No Constraints | F | 942 | 92% | F | 997 | 100%
| Logic Density™ | F | 3.14 |  | F | 3.15
| Logic Density™ - Predecessors | F | 1.77 |  | F | 1.79
| Logic Density™ - Successors | F | 1.36 |  | F | 1.37
| Summary Links | F | 0 | 0% | F | 0 | 0%
| All Activities w/Predecessors | F | 915 | 100% | F | 905 | 100%
| SS Predecessors | F | 45 | 4% | F | 42 | 4%
| SF Predecessors | F | 0 | 0% | F | 0 | 0%
| FF Predecessors | F | 36 | 4% | F | 36 | 4%
| FS Predecessors | F | 1020 | 100% | F | 994 | 100%
| All Activities w/Successors | F | 1022 | 100% | F | 996 | 100%
| SS Successors | F | 47 | 5% | F | 42 | 4%
| FF Successors | F | 31 | 3% | F | 31 | 3%
| SF Successors | F | 0 | 0% | F | 0 | 0%
| FS Successors | F | 1014 | 99% | F | 990 | 99%
| Missing Logic | F | 2 | 0% | F | 3 | 0%
| Missing Predecessors | F | 1 | 0% | F | 1 | 0%
| Missing Successors | F | 2 | 0% | F | 2 | 0%
| Open Start | F | 1 | 0% | F | 1 | 0%
| Open Finish | F | 2 | 0% | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.82 |  | F | 1.82
| All Activities w/Predecessors | F | 915 | 100% | F | 905 | 100%
| Total # Predecessors | F | 1665 |  | F | 1649
| Activities Missing Predecessors | F | 1 | 0% | F | 1 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0% | F | 0 | 0%
| Total # Predecessor Leads | F | N/A |  | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A |  | F | N/A
| Activities w/Lags on Predecessor | F | 2 | 0% | F | 2 | 0%
| Total # Predecessor Lags | F | 2 |  | F | 2
| Max # of Predecessor Lags on an Activity | F | 1 |  | F | 1
| Min Predecessor Lag (days) | F | 0 |  | F | 0
| Max Predecessor Lag (days) | F | 22 |  | F | 22
| Hidden Duration (Planned) | F | 2 | 0% | F | 2 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0% | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 125 | 14% | F | 123 | 14%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100% | F | 2 | 100%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A |  | F | N/A
| Critical Merge Hotspot | F | 9 | 1% | F | 35 | 4%
| Logic Hotspot™ | F | 10 | 1% | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 9% | F | 4 | 2%
| Logic Density™ - Successors | F | 1.36 |  | F | 1.37
| All Activities w/Successors | F | 1022 | 100% | F | 996 | 100%
| Activities Missing Successors | F | 2 | 0% | F | 2 | 0%
| Total # Successors | F | 1395 |  | F | 1364
| Activities w/Leads on Successor | F | 0 | 0% | F | 0 | 0%
| Total# of Successor Leads | F | N/A |  | F | N/A
| Max # of Successor Leads on Activity | F | N/A |  | F | N/A
| Activities w/Lags on Successor | F | 8 | 1% | F | 8 | 1%
| Total# of Successor Lags | F | 8 |  | F | 8
| Max # of Successor Lags on Activity | F | 1 |  | F | 1
| Diverge Hotspot (Successors >2) | F | 72 | 7% | F | 72 | 7%
| Diverge Hotspot w/Successor Lags | F | 1 | 20% | F | 1 | 20%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A |  | F | N/A
| Critical Diverge Hotspot | F | 11 | 1% | F | 22 | 2%
| Logic Hotspot™ | F | 10 | 1% | F | 10 | 1%
| Critical Logic Hotspot™ | F | 4 | 9% | F | 4 | 2%
| Actually Finished - Tasks & Milestones | F | 699 | 41% | F | 724 | 42%
| Completed Ahead - Tasks & Milestones | F | 55 | 8% | F | 55 | 8%
| Completed On-Schedule - Tasks & Milestones | F | 81 | 12% | F | 81 | 11%
| Completed Delayed - Tasks & Milestones | F | 562 | 80% | F | 585 | 81%
| Avg Days Finished Early - Tasks & Milestones | F | 24 |  | F | 24
| Avg Days Finished Late - Tasks & Milestones | F | 161 |  | F | 169
| Avg Finish Variance - Tasks & Milestones | F | 128 |  | F | 134
| Actually Finished - Tasks | F | 609 | 39% | F | 634 | 41%
| Completed Ahead - Tasks | F | 48 | 8% | F | 48 | 8%
| Completed On-Schedule - Tasks | F | 69 | 11% | F | 69 | 11%
| Completed Delayed - Tasks | F | 492 | 81% | F | 515 | 81%
| Accelerated Durations Early/On-Schedule - Tasks | F | 12 | 1% | F | 12 | 1%
| Accelerated Durations Late - Tasks | F | 106 | 7% | F | 105 | 7%
| Extended Durations - Tasks | F | 271 | 17% | F | 285 | 18%
| Actually Finished - Milestones | F | 90 | 53% | F | 90 | 53%
| Completed Ahead - Milestones | F | 7 | 8% | F | 7 | 8%
| Completed On-Schedule - Milestones | F | 12 | 13% | F | 12 | 13%
| Completed Delayed - Milestones | F | 70 | 78% | F | 70 | 78%
| Actually Started - Tasks | F | 108 | 7% | F | 92 | 6%
| In-Progress Started Ahead - Tasks | F | 10 | 9% | F | 8 | 9%
| In-Progress Started On-Schedule - Tasks | F | 17 | 16% | F | 15 | 16%
| In-Progress Started Delayed - Tasks | F | 80 | 74% | F | 68 | 74%
| In-Progress Delayed Finish - Tasks | F | 106 | 98% | F | 91 | 99%
| Avg Days Started Early | F | 15 |  | F | 16
| Avg Days Started Late | F | 121 |  | F | 118
| Avg Start Variance | F | 106 |  | F | 101
| Expected Finish | F | 0 | 0% | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0% | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 916 | 53% | F | 906 | 53%
| Planned Ahead Start - Tasks & Milestones | F | 4 | 0% | F | 97 | 11%
| Planned On Schedule Start - Tasks & Milestones | F | 96 | 10% | F | 1 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 804 | 88% | F | 798 | 88%
| Riding Data Date - Tasks & Milestones | F | 0 | 0% | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0% | F | 0 | 0%
| Scheduled to Start - Tasks | F | 837 | 54% | F | 827 | 53%
| Planned Ahead Start - Tasks | F | 4 | 0% | F | 89 | 11%
| Planned On Schedule Start - Tasks | F | 93 | 11% | F | 1 | 0%
| Planned Delayed Start - Tasks | F | 731 | 87% | F | 730 | 88%
| Planned Delayed Finish - Tasks | F | 732 | 87% | F | 731 | 88%
| Scheduled to Start - Milestones | F | 79 | 47% | F | 79 | 47%
| Planned Ahead Start - Milestones | F | 0 | 0% | F | 8 | 10%
| Planned On Schedule Start - Milestones | F | 3 | 4% | F | 0 | 0%
| Planned Delayed Start - Milestones | F | 73 | 92% | F | 68 | 86%
| Planned Delayed Finish - Milestones | F | 73 | 92% | F | 68 | 86%
| Schedule Baseline Activities | F | 1709 | 99% | F | 1708 | 99%
| Scheduled/Baselined to Start | F | 1011 |  | F | 987
| Scheduled/Baselined to Finish | F | 1011 |  | F | 987
| Start/ed | F | 807 |  | F | 816
| Finish/ed | F | 699 |  | F | 724
| Start Variance (Phase) | F | 0 | 0% | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100% |  | F | 100%
| Finish Variance (Phase) | F | 0 | 0% | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100% |  | F | 100%
| Started Delayed (>30 days) | F | 417 | 81% | F | 424 | 81%
| Completed Delayed (>30 days) | F | 421 | 86% | F | 443 | 86%
| SPI(t) | F | 8.22 |  | F | 8.14
| Scheduled Activities | F | 1723 | 100% | F | 1722 | 100%
| Scheduled to Start | F | 1024 | 59% | F | 998 | 58%
| Scheduled to Finish | F | 1024 | 59% | F | 998 | 58%
| Longest Path - Critical Activities and Milestones | F | 43 | 4% | F | 185 | 19%
| Critical Milestones (To-Go) | F | 8 | 10% | F | 15 | 19%
| Critical Tasks (To-Go) | F | 35 | 4% | F | 170 | 18%
| Critical Tasks (In Progress) | F | 1 | 3% | F | 4 | 2%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23 | F | 1:11 | 0.09
| High Float 10% | F | 467 | 46% | F | 354 | 35%
| High Float 44d | F | 898 | 88% | F | 717 | 72%
| Zero Days Float | F | 2 | 0% | F | 66 | 7%
| Negative Float | F | 41 | 4% | F | 122 | 12%
| Longest Path - Critical Activities and Milestones | F | 43 | 4% | F | 185 | 19%
| Critical Milestones (To-Go) | F | 8 | 10% | F | 15 | 19%
| Critical Tasks (To-Go) | F | 35 | 4% | F | 170 | 18%
| Critical Tasks (In Progress) | F | 1 | 3% | F | 4 | 2%
| Milestone-to-Task Ratio (To-Go) | F | 1:12 | 0.08 | F | 1:12 | 0.09
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23 | F | 1:11 | 0.09
| Logic Density™ | F | 3.14 |  | F | 3.13
| CP Logic Density™ | F | 7.58 |  | F | 4.27
| Critical w/Missing Logic | F | 1 | 0% | F | 1 | 0%
| Critical w/Hard Constraints | F | 1 | 0% | F | 0 | 0%
| Zero Days Float | F | 2 | 0% | F | 66 | 7%
| Negative Float | F | 41 | 4% | F | 122 | 12%
| Critical LOE | F | N/A | 0% | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0% | F | 4 | 0%
| Critical w/High Planned Duration (44d) | F | 2 | 6% | F | 6 | 4%
| Critical with Predecessor Lag | F | 0 | 0% | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0% | F | 0 | 0%
| Critical with Hard Constraints | F | 1 | 0% | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0% | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0% | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A |  | F | 0
| Critical CEI - Total Tasks | F | 0 |  | F | 3
| Critical CEI - Complete Tasks | F | N/A |  | F | 0 | 19%
| Critical CEI - Incomplete Tasks | F | N/A |  | F | 3 | 81%
| Baselined to Start | F | 1544 |  | F | 1543
| Scheduled to Start | F | 1554 |  | F | 1553
| Actual Starts | F | 717 |  | F | 726
| Baselined to Finish | F | 1544 |  | F | 1543
| Scheduled to Finish | F | 1554 |  | F | 1553
| Actual Finishes | F | 609 |  | F | 634
| Started Delayed (<=30 days) | F | 98 | 19% | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10% | F | 52 | 10%
| Started Delayed (>60 days) | F | 366 | 71% | F | 372 | 71%
| Completed Delayed (<=30 days) | F | 71 | 14% | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11% | F | 58 | 11%
| Completed Delayed (>60 days) | F | 365 | 74% | F | 385 | 75%
| Baselined to Start | F | 1544 |  | F | 1543
| Scheduled to Start | F | 1554 |  | F | 1553
| Actual Starts | F | 717 |  | F | 726
| Current Baselined to Start & Started | F | 716 |  | F | 723
| Past Baselined to Start & Started | F | 0 |  | F | 0
| Future Baseline to Start & Started | F | 0 |  | F | 0
| Baselined to Finish | F | 1544 |  | F | 1543
| Scheduled to Finish | F | 1554 |  | F | 1553
| Actual Finishes | F | 609 |  | F | 634
| Current Baselined to Finish & Finished | F | 609 |  | F | 632
| Past Baselined to Finish & Finished | F | 0 |  | F | 0
| Future Baselined to Finish & Finished | F | 0 |  | F | 0
| Started Delayed (<=30 days) | F | 98 | 19% | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10% | F | 52 | 10%
| Started Delayed (>60 days) | F | 366 | 71% | F | 372 | 71%
| Completed Delayed (<=30 days) | F | 71 | 14% | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11% | F | 58 | 11%
| Completed Delayed (>60 days) | F | 365 | 74% | F | 385 | 75%
| Baselined to Start - To Time Now | F | 1228 | 80% | F | 1247 | 81%
| Scheduled to Start - To Time Now | F | 1228 | 79% | F | 1247 | 80%
| Started | F | 715 |  | F | 722
| Started Late | F | 515 |  | F | 522
| Started Delayed (<=30 days) | F | 98 | 19% | F | 98 | 19%
| Started Delayed (Between 31 to 60 days) | F | 51 | 10% | F | 52 | 10%
| Started Delayed (>60 days) | F | 366 | 71% | F | 372 | 71%
| BEI - Value Task Starts | F | 0.58 |  | F | 0.58
| Baselined to Finish - To Time Now | F | 1205 | 78% | F | 1228 | 80%
| Scheduled to Finish - To Time Now | F | 1205 | 78% | F | 1228 | 80%
| Finished | F | 609 |  | F | 632
| Finished Late | F | 492 |  | F | 515
| Completed Delayed (<=30 days) | F | 71 | 14% | F | 72 | 14%
| Completed Delayed (Between 31 to 60 days) | F | 56 | 11% | F | 58 | 11%
| Completed Delayed (>60 days) | F | 365 | 74% | F | 385 | 75%
| BEI - Value Task Finishes | F | 0.51 |  | F | 0.51
| Started - Future | F | 1 |  | F | 1
| Not Baselined to Start | F | 0 | 0% | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.58 |  | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51 |  | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A |  | F | 0
| HMI - Value Task Finishes - by Status Dates | F | N/A |  | F | 0
| CEI - Value Task Starts - by Status Dates | F | N/A |  | F | 0.1
| CEI - Value Task Finishes - by Status Dates | F | N/A |  | F | 0.19
| FEI - Value Task Starts - Cumulative | F | 2.63 |  | F | 2.49
| FEI - Value Task Finish - Cumulative | F | 2.75 |  | F | 2.75
| Past Baseline to Start & Started (Workoff Burden) | F | 0 |  | F | 0
| Current Baseline to Start & Started | F | 716 |  | F | 723
| Current Baseline to Start & Started Past (Early Starts) | F | 0 |  | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0 |  | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 828 |  | F | 820
| Baselined to Start - Check | F | 1544 |  | F | 1543
| Future Baseline to Start & Started (Early Starts) | F | N/A |  | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0 |  | F | 0
| Current Baseline to Finish & Finished - Check | F | 609 |  | F | 632
| Current Baseline to Finish & Finished Past - Check | F | 0 |  | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0 |  | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 935 |  | F | 911
| Baselined to Finish - Check | F | 1544 |  | F | 1543
| Future Baseline to Finish & Finished - Check | F | 0 |  | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 716 |  | F | 723
| Future Baseline to Start & Started (Early Starts) | F | N/A |  | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0 |  | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 828 |  | F | 820
| Current Baseline to Finish & Finished (BL Plan) | F | 609 |  | F | 632
| Future Baseline to Finish & Finished (Early Finishes) | F | 0 |  | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0 |  | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 935 |  | F | 911
| Baselined to Start | F | 1228 |  | F | 1247
| Scheduled to Start | F | 1228 | 100% | F | 1247 | 100%
| Started - Scheduled | F | 715 | 58% | F | 722 | 58%
| Started - Baseline Comparison | F | 715 | 58% | F | 722 | 58%
| BEI - Value Task Starts | F | 0.58 |  | F | 0.58
| HMI - Value Task Starts | F | N/A |  | F | 0
| CEI - Value Task Starts | F | N/A |  | F | 0.11
| Baselined to Finish | F | 1205 |  | F | 1228
| Scheduled to Finish | F | 1205 |  | F | 1228
| Finished | F | 609 |  | F | 632
| BEI - Value Task Finishes | F | 0.51 |  | F | 0.51
| HMI - Value Task Finishes | F | N/A |  | F | 0
| CEI - Value Task Finishes | F | N/A |  | F | 0.19
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| Started (incl. Future Baseline Starts) - Scheduled | F | 717 | 46% | F | 726 | 47%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 716 | 46% | F | 723 | 47%
| Started Late (from Baseline) | F | 515 |  | F | 522
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 609 | 39% | F | 632 | 41%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 609 | 39% | F | 632 | 41%
| Finished Late | F | 492 |  | F | 515
| Completed Ahead | F | 48 | 8% | F | 48 | 8%
| Completed Delayed | F | 492 | 81% | F | 515 | 81%
| Completed On-Schedule | F | 69 | 11% | F | 69 | 11%
| Accelerated | F | 13 | 2% | F | 13 | 2%
| Days Variance | F | 83556 | 13720% | F | 91676 | 14460%
| Days Early | F | 1212 | 199% | F | 1212 | 191%
| Days Late | F | 84767 | 13919% | F | 92888 | 14651%
| Avg Days Early | F | 25 |  | F | 25
| Avg Days Late | F | 172 |  | F | 180
| Avg Variance | F | 137 |  | F | 145
| Actually Finished | F | 609 | 35% | F | 634 | 37%
| Took Longer than Planned | F | 303 | 43% | F | 317 | 44%
| Took Less Than Planned | F | 157 | 22% | F | 160 | 22%
| Completed (w/Baseline Duration) | F | 585 | 38% | F | 608 | 39%
| Completed (w/o Baseline Duration) | F | 0 | 0% | F | 2 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2% | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 609 | 51% | F | 632 | 51%
| Missed Durations | F | 271 | 44% | F | 285 | 45%
| Missed Durations & Late Actual Finish | F | 253 | 42% | F | 267 | 42%
| Completed Ahead | F | 48 | 8% | F | 48 | 8%
| Completed Delayed | F | 492 | 81% | F | 515 | 81%
| Completed On-Schedule | F | 69 | 11% | F | 69 | 11%
| Accelerated | F | 13 | 2% | F | 13 | 2%
| Days Variance | F | 83556 | 13720% | F | 91676 | 14460%
| Days Early | F | 1212 | 199% | F | 1212 | 191%
| Days Late | F | 84767 | 13919% | F | 92888 | 14651%
| Avg Days Early | F | 25 |  | F | 25
| Avg Days Late | F | 172 |  | F | 180
| Avg Variance | F | 137 |  | F | 145
| Actually Finished | F | 609 | 35% | F | 634 | 37%
| Took Longer than Planned | F | 303 | 43% | F | 317 | 44%
| Took Less Than Planned | F | 157 | 22% | F | 160 | 22%
| Completed (w/Baseline Duration) | F | 585 | 38% | F | 608 | 39%
| Completed (w/o Baseline Duration) | F | 0 | 0% | F | 2 | 0%
| Completed (w/Baseline Dur=0) | F | 24 | 2% | F | 24 | 2%
| Baseline-to-Date Completed Tasks | F | 609 | 51% | F | 632 | 51%
| Missed Durations | F | 271 | 44% | F | 285 | 45%
| Missed Durations & Late Actual Finish | F | 253 | 42% | F | 267 | 42%
| Baselined Tasks | F | 1544 |  | F | 1543
| Baselined to Start - TOTAL | F | 1544 |  | F | 1543
| Complete Task Starts - Cumulative | F | 715 | 58% | F | 722 | 58%
| Incomplete Task Starts - Cumulative (in work) | F | 513 | 42% | F | 525 | 42%
| Old Incomplete Task Starts in Status Period | F | N/A |  | F | N/A
| Baselined to Finish | F | 1544 |  | F | 1543
| Complete Task Finishes - Cumulative (in work) | F | 609 | 51% | F | 632 | 51%
| Incomplete Task Finishes - Cumulative | F | 596 | 51% | F | 596 | 51%
| Old Incomplete Task Finishes in Status Period | F | N/A |  | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A |  | F | N/A
| BEI - Value Tasks | F | 0.51 |  | F | 0.51
| BEI - Total Tasks | F | 1205 |  | F | 1228
| BEI - Complete Tasks | F | 609 | 51% | F | 632 | 51%
| BEI - Incomplete Tasks | F | 596 | 49% | F | 596 | 49%
| BEI - Value Tasks (adjusted) | F | 0.51 |  | F | 0.51
| BEI - Complete Tasks (adjusted) | F | 609 | 51% | F | 632 | 51%
| BEI - Complete Future Tasks (adjusted) | F | N/A |  | F | N/A
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| BEI - Value Milestones | F | 0.7 |  | F | 0.69
| BEI - Total Milestones | F | 128 |  | F | 129
| BEI - Complete Milestones | F | 89 | 70% | F | 89 | 69%
| BEI - Incomplete Milestones | F | 39 | 30% | F | 40 | 31%
| BEI - Value Milestones (adjusted) | F | 0.7 |  | F | 0.69
| BEI - Complete Milestones (adjusted) | F | 89 | 70% | F | 89 | 69%
| BEI - Complete Future Milestones (adjusted) | F | N/A |  | F | N/A
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| HMI - Value Tasks | F | N/A |  | F | 0
| HMI - Total Tasks | F | 0 |  | F | 24
| HMI - Complete Tasks | F | N/A |  | F | N/A | 0%
| HMI - Completed Early Tasks | F | N/A |  | F | N/A | 29%
| HMI - Incomplete Tasks | F | N/A |  | F | 24 | 100%
| HMI - Value Tasks (adjusted) | F | N/A |  | F | 0
| HMI - Complete Tasks (adjusted) | F | N/A |  | F | N/A | 0%
| HMI - Complete Future Tasks (adjusted) | F | N/A |  | F | N/A
| HMI - Value Milestones | F | N/A |  | F | 0
| HMI - Total Milestones | F | 0 |  | F | 1
| HMI - Complete Milestones | F | N/A |  | F | N/A | 0%
| HMI - Completed Early Milestones | F | N/A |  | F | N/A | 0%
| HMI - Incomplete Milestones | F | N/A |  | F | 1 | 100%
| HMI - Value Milestones (adjusted) | F | N/A |  | F | 0
| HMI - Complete Milestones (adjusted) | F | N/A |  | F | N/A | 0%
| HMI - Complete Future Milestones (adjusted) | F | N/A |  | F | N/A
| CEI - Value Tasks | F | N/A |  | F | 0.19
| CEI - Total Tasks | F | 0 |  | F | 129
| CEI - Complete Tasks | F | N/A |  | F | 24 | 19%
| CEI - Incomplete Tasks | F | N/A |  | F | 105 | 81%
| CEI - Value Tasks (adjusted) | F | N/A |  | F | 0.22
| CEI - Complete Tasks (adjusted) | F | N/A |  | F | 28 | 22%
| CEI - Complete Future Tasks (adjusted) | F | N/A |  | F | 4
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| CEI - Value Milestones | F | N/A |  | F | 0.17
| CEI - Total Milestones | F | 0 |  | F | 6
| CEI - Complete Milestones | F | N/A |  | F | 1 | 17%
| CEI - Incomplete Milestones | F | N/A |  | F | 5 | 83%
| CEI - Value Milestones (adjusted) | F | N/A |  | F | 0.17
| CEI - Complete Milestones (adjusted) | F | N/A |  | F | 1 | 17%
| CEI - Complete Future Milestones (adjusted) | F | N/A |  | F | 0
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| BEI - Value Tasks | F | 0.51 |  | F | 0.51
| BEI - Total Tasks | F | 1205 |  | F | 1228
| BEI - Incomplete Tasks | F | 596 | 49% | F | 596 | 49%
| HMI - Value Tasks | F | N/A |  | F | 0
| HMI - Total Tasks | F | 0 |  | F | 24
| HMI - Incomplete Tasks | F | N/A |  | F | 24 | 100%
| CEI - Value Tasks | F | N/A |  | F | 0.19
| CEI - Total Tasks | F | 0 |  | F | 129
| CEI - Incomplete Tasks | F | N/A |  | F | 105 | 81%
| BEI - Complete Milestones | F | 89 | 70% | F | 89 | 69%
| HMI - Complete Tasks | F | N/A |  | F | N/A | 0%
| CEI - Complete Tasks | F | N/A |  | F | 24 | 19%
| BEI - Value Milestones | F | 0.7 |  | F | 0.69
| BEI - Total Milestones | F | 128 |  | F | 129
| BEI - Complete Milestones | F | 89 | 70% | F | 89 | 69%
| BEI - Incomplete Milestones | F | 39 | 30% | F | 40 | 31%
| HMI - Value Milestones | F | N/A |  | F | 0
| HMI - Total Milestones | F | 0 |  | F | 1
| HMI - Complete Milestones | F | N/A |  | F | N/A | 0%
| HMI - Incomplete Milestones | F | N/A |  | F | 1 | 100%
| CEI - Value Milestones | F | N/A |  | F | 0.17
| CEI - Total Milestones | F | 0 |  | F | 6
| CEI - Complete Milestones | F | N/A |  | F | 1 | 17%
| CEI - Incomplete Milestones | F | N/A |  | F | 5 | 83%
| BEI - Value Tasks (adjusted) | F | 0.51 |  | F | 0.51
| HMI - Value Tasks (adjusted) | F | N/A |  | F | 0
| CEI - Value Tasks (adjusted) | F | N/A |  | F | 0.22
| BEI - Value Milestones (adjusted) | F | 0.7 |  | F | 0.69
| HMI - Value Milestones (adjusted) | F | N/A |  | F | 0
| CEI - Value Milestones (adjusted) | F | N/A |  | F | 0.17
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| Total Activities - DRM | F | 584 |  | F | 608
| Total Activities - DRM Graph | F | 584 |  | F | 608
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| Milestone #1 - 5158 | F | N/A |  | F | N/A
| Float Milestone #1 - 5158 | F | N/A |  | F | N/A
| Milestone #2 - 4786 | F | N/A |  | F | N/A
| Float to Milestone #2 - 4786 | F | N/A |  | F | N/A
| Milestone #3 - 102 | F | N/A |  | F | N/A
| Float to Milestone #3 - 102 | F | N/A |  | F | N/A
| Milestone #4 - 103 | F | N/A |  | F | N/A
| Float to Milestone #4 - 103 | F | N/A |  | F | N/A
| Milestone #5 - 104 | F | N/A |  | F | N/A
| Float to Milestone #5 - 105 | F | N/A |  | F | N/A
| New Activities Since Previous Status Date | F | 0 |  | F | 0
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A |  | F | N/A
| Margin - Margin Task Name #2 | F | 0 |  | F | 0
| Margin - Margin Task Name #3 | F | N/A |  | F | N/A
| Margin - Margin Task Name #4 | F | N/A |  | F | N/A
| Margin - Margin Task Name #5 | F | N/A |  | F | N/A
| Margin - Margin Task Name #6 | F | N/A |  | F | N/A
| Margin - Margin Task Name #7 | F | N/A |  | F | N/A
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| Margin - Margin Task Name #1 | F | N/A |  | F | N/A
| Margin - Margin Task Name #2 | F | 2025-08-06 |  | F | 2028-03-06
| Margin - Margin Task Name #3 | F | N/A |  | F | N/A
| Margin - Margin Task Name #4 | F | N/A |  | F | N/A
| Margin - Margin Task Name #5 | F | N/A |  | F | N/A
| Margin - Margin Task Name #6 | F | N/A |  | F | N/A
| Margin - Margin Task Name #7 | F | N/A |  | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.58 |  | F | 0.58
| BEI - Value Task Finishes - Cumulative | F | 0.51 |  | F | 0.51
| HMI - Value Task Starts - by Status Dates | F | N/A |  | F | 0
| HMI - Value Task Finishes - by Status Dates | F | N/A |  | F | 0
| CEI - Value Task Starts - by Status Dates | F | N/A |  | F | 0.1
| CEI - Value Task Finishes - by Status Dates | F | N/A |  | F | 0.19
| FEI - Value Task Starts - Cumulative | F | 2.63 |  | F | 2.49
| FEI - Value Task Finish - Cumulative | F | 2.75 |  | F | 2.75
| BEI - Value Tasks | F | 0.51 |  | F | 0.51
| HMI - Value Tasks | F | N/A |  | F | 0
| CEI - Value Tasks | F | N/A |  | F | 0.19
| BEI - Value Milestones | F | 0.7 |  | F | 0.69
| HMI - Value Milestones | F | N/A |  | F | 0
| CEI - Value Milestones | F | N/A |  | F | 0.17
| BEI - Value Tasks | F | 0.51 |  | F | 0.51
| BEI - Complete Tasks | F | 609 | 51% | F | 632 | 51%
| BEI - Incomplete Tasks | F | 596 | 49% | F | 596 | 49%
| BEI - CP Tasks - Planned Cumulative | F | 0 |  | F | 29
| BEI - CP Value Tasks | F | N/A |  | F | 0
| HMI - Value Tasks | F | N/A |  | F | 0
| HMI - Complete Tasks | F | N/A |  | F | N/A | 0%
| HMI - Incomplete Tasks | F | N/A |  | F | 24 | 100%
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A |  | F | 0
| HMI - CP Value Tasks | F | N/A |  | F | N/A
| CEI - Value Tasks | F | N/A |  | F | 0.19
| CEI - Complete Tasks | F | N/A |  | F | 24 | 19%
| CEI - Incomplete Tasks | F | N/A |  | F | 105 | 81%
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A |  | F | 0
| CEI - CP Value Tasks | F | N/A |  | F | N/A
| Wrong Status | F | 0 | 0% | F | 1 | 0%
| Invalid Forecast Dates | F | 2 | 0% | F | 338 | 34%
| Expected Finish | F | 0 | 0% | F | 0 | 0%
| Missing WBS | F | 0 | 0% | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0% | F | 0 | 0%
| Activities with Duration=0 | F | 7 | 1% | F | 4 | 0%
| Estimated Duration | F | 0 | 0% | F | 0 | 0%
| Missing Logic | F | 2 | 0% | F | 3 | 0%
| Missing Predecessors | F | 1 | 0% | F | 1 | 0%
| Missing Successors | F | 2 | 0% | F | 2 | 0%
| Open Start | F | 1 | 0% | F | 1 | 0%
| Open Finish | F | 2 | 0% | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0% | F | 0 | 0%
| Summary Links | F | 0 | 0% | F | 0 | 0%
| Hard Constraints | F | 1 | 0% | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0% | F | 0 | 0%
| Negative Float | F | 41 | 4% | F | 122 | 12%
| Status Date | F | 2025-02-07 |  | F | 2025-03-10
| High Float 10% | F | 467 | 46% | F | 354 | 35%
| High Float 44d | F | 898 | 88% | F | 717 | 72%
| Zero Days Float | F | 2 | 0% | F | 66 | 7%
| Negative Float | F | 41 | 4% | F | 122 | 12%
| Hidden Duration (Planned) | F | 2 | 0% | F | 2 | 0%
| Critical Logic Hotspot™ | F | 4 | 9% | F | 4 | 2%
| Critical Merge Hotspot | F | 9 | 1% | F | 35 | 4%
| Merge Hotspot w/Predecessor Lags | F | 2 | 100% | F | 2 | 100%
| Critical Diverge Hotspot | F | 11 | 1% | F | 22 | 2%
| Diverge Hotspot w/Successor Lags | F | 1 | 20% | F | 1 | 20%
| Riding Data Date | F | 0 | 0% | F | 0 | 0%
| Deadlines | F | 0 | 0% | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 35 | 69% | F | 170 | 76%
| Longest Path (Tasks & Milestones) | F | 43 | 84% | F | 185 | 82%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.23 | F | 1:11 | 0.09
| Critical Milestones (To-Go) | F | 8 | 10% | F | 15 | 19%
| Longest Path (Milestones) | F | 8 | 16% | F | 15 | 7%
| Normal Tasks | F | 1554 | 73% | F | 1553 | 73%
| Normal Tasks (To-Go) | F | 945 | 72% | F | 919 | 72%
| Critical Tasks (To-Go) | F | 35 | 4% | F | 170 | 18%
| Critical Tasks (In Progress) | F | 1 | 3% | F | 4 | 2%
| Zero Days Float | F | 2 | 0% | F | 66 | 7%
| Negative Float | F | 41 | 4% | F | 122 | 12%
| CP Logic Density™ | F | 7.58 |  | F | 4.27
| Time Now | F | 2025-02-07 |  | F | 2025-03-10
| Forecast to be Finished | F | 1202 | 78% | F | 1227 | 80%
| Completed On Time | T | 116 | 10% | T | 159 | 13%
| Completed Late | F | 488 | 41% | F | 581 | 47%
| Not Completed | F | 594 | 49% | F | 595 | 48%
| Baseline Finish Compliance | T | 10% |  | T | 13%
| Forecast to be Started | F | 1228 | 80% | F | 1247 | 81%
| Started On Time | T | 200 | 16% | T | 250 | 20%
| Started Late | F | 515 | 42% | F | 605 | 49%
| Not Started | F | 513 | 42% | F | 525 | 42%
| Baseline Start Compliance | T | 22% |  | F | 26%
1 | Completed Activities | F | 609 |  | F | 630
HSD01 | Time Now | F | 2025-02-07 |  | F | 2025-03-10
HSD02 | Label | F | N/A |  | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 513 | 33% | T | 525 | 34%
HSD04 | Started Late | F | 515 | 42% | F | 605 | 49%
HSD05 | Forecast to be Finished but not Finished yet | T | 594 | 38% | T | 595 | 39%
HSD06 | Finished Late | F | 488 | 41% | F | 581 | 47%
HSD06 | Total days delay in the half step (Days) | F | N/A |  | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0 |  | T | 202538
HSD08 | Total days ahead in the half step (Days) | F | N/A |  | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0 |  | F | 82834
HSD10 | Cumulative Finish Impact (Days) | F | 0 |  | F | -119704
HSD10 | Net Finish Impact (Days) | F | 0 |  | F | -203
HSD20 | Project Finish | F | 2028-09-29 |  | F | 2029-04-20
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0% | T | 28 | 97%
SEM01 | Workoff Burden | T | 49 | 98% | T | 24 | 100%
SEM02 | BRI Current | T | 0.03 |  | T | 0
SEM03 | BRI Cumulative | F | 0.51 |  | F | 0.51
SEM04 | BPI Current | T | 0.03 |  | T | 0
SEM05 | BEI Current | F | 1.67 |  | F | 1
SEM06 | BEI Cumulative | T | 0.51 |  | T | 0.51
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63 |  | T | 2.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.75 |  | T | 2.42
SEM07 | To Go - Planned Task Starts - Count | T | 836 |  | T | 662
SEM07 | To Go - BEI - Task Finishes - Count | T | 940 |  | T | 766
SEM07 | To Go - Baselined Task Starts - Count | T | 828 |  | T | 273
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63 |  | T | 2.22
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 521 |  | T | 398
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 315 |  | T | 263
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 605 |  | T | 492
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 339 |  | T | 279
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63 |  | T | 2.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.75 |  | T | 2.42
SEM07 | To Go - Planned Task Starts - Count | T | 836 |  | T | 662
SEM07 | To Go - BEI - Task Finishes - Count | T | 940 |  | T | 766
SEM07 | To Go - Baselined Task Starts - Count | T | 828 |  | T | 273
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63 |  | T | 2.22
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 836 |  | T | 661
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 521 |  | T | 398
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 315 |  | T | 263
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 944 |  | T | 771
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 605 |  | T | 492
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 339 |  | T | 279
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 521 |  | T | 398
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 315 |  | T | 263
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 605 |  | T | 492
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 339 |  | T | 279
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63 |  | T | 2.22
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 2.75 |  | T | 2.42
SEM07 | To Go - Planned Task Starts - Count | T | 836 |  | T | 662
SEM07 | To Go - BEI - Task Finishes - Count | T | 940 |  | T | 766
SEM07 | To Go - Baselined Task Starts - Count | T | 828 |  | T | 273
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 2.63 |  | T | 2.22
SEM07 | TC-BEI | T | 2.77 |  | T | 2.45
SEM08 | FRI Current | F | N/A |  | F | 0.19
SEM09 | Delta (BEI vs TC-BEI) | T | -2.15 |  | T | -1.91
SN05 | Newly Critical Activities | F | 0 | 0% | F | 143 | 77%
SN05 | Newly Critical Activities | F | 0 | 0% | T | 143 | 7%
SN05 | Newly Critical Activities | F | 0 | 0% | T | 143 | 7%
SN06 | Activities No Longer Critical | F | 0 | 0% | F | 1 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0% | F | 1 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0% | F | 1 | 0%