## Ribbon View
Fuse® Analyst Report
Workbook: Large Test File vs Large Test File2 - 4249 Activities
Quick Add Metrics
Created on: 7/15/2026
Created by: dpolitte
Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
|  | 2026-07-01 | 2026-07-01 | 2026-08-01 | 2026-08-01 | 2026-09-01 | 2026-09-01 | 2026-10-01 | 2026-10-01 | 2026-11-01 | 2026-11-01 | 2026-12-01 | 2026-12-01 | Status Date | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Overrun | Work Underrun | Work Overrun | Total Work | Actual Work | Remaining Work | Work Discrepancy | Baseline Work | Summarized Work | Work per Day | Missing Resources | Resources | SV(t) | SPI(t) | WV | SV | SPI | CPI | EAC | EAC(CPI) | EAC(Composite) | TCPI(BAC) | TCPI(EAC) | TCPI(EAC) to CPI | PV (BCWS) | EV (BCWP) | AC (ACWP) | %Schedule | %Spent | %Complete | %Spent (EAC) | VAC | BAC | CV | SV | SPI | CPI | EAC | EAC(CPI) | EAC(Composite) | TCPI(BAC) | TCPI(EAC) | TCPI(EAC) to CPI | PV (BCWS) | EV (BCWP) | AC (ACWP) | %Schedule | %Spent | %Complete | %Spent (EAC) | VAC | BAC | Overrun | $ Cost Underrun | $ Cost Overrun | $ Total Cost | $ Actual Cost | $ Remaining Cost | $ Cost Discrepancy | $ Budget Cost | $ Cost per Day | Negative Planned Cost | Negative Actual Cost | Critical | Soft Constraints | Hard Constraints | Remaining Duration | Rem. Critical Duration | Ribbon Length | Avg Float | Float Ratio™ | Longest Path | Time Now | Forecast to be Finished | Completed On Time | Completed Late | Not Completed | Baseline Finish Compliance | Forecast to be Started | Started On Time | Started Late | Not Started | Baseline Start Compliance | Completed Ahead | Completed Delayed | Completed On-Schedule | Accelerated | Days Variance | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Variance | Actually Finished | Took Longer than Planned | Took Less Than Planned | Started Ahead | Started Delayed | In-Progress On Schedule | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Start Variance | Discrepancy | Actually Started | Expected Finish | Planned Ahead | Planned Delayed | Planned On Schedule | Scheduled to Start | Scheduled to Finish | Underway | Planned | Completed | Days Remaining | Days Completed | Completed Milestones | Planned Milestones | Not Completed | Physical Percent Complete | Duration Percent Complete | Units Percent Complete | Wrong Status | Critical | Non-Critical | Negative Float | Zero Days Float | 0 to 20 Days Float | 20 to 30 days float | More than 30 days float | High Float | Avg Float | Max Float | Float Ratio™ | Total Activities | Milestones | Normal | Summaries | Hammocks | Milestone Ratio | Detail Level | Missing WBS | Longest Path | Riding Data Date | Activities per million | Missing Logic | Logic Density™ | Critical | Hard Constraints | Negative Float | Insufficient Detail™ | Number of Lags | Number of Leads | Merge Hotspot | Longest Path (Normal Tasks) | Newly Created Activity & Critical - Created (Snapshot) | Longest Path (Tasks & Milestones) | Critical Milestone-to-Task Ratio (To-Go) | Critical Milestones (To-Go) | Longest Path (Milestones) | Normal Tasks | Normal Tasks (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Zero Days Float | Negative Float | Float Ratio™ | CP - Float Ratio™ | CP Logic Density™ | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Max Float | Newly Created Activity & Critical - Created (Snapshot) | Number of Leads | Number of Lags | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Total New Completed Tasks & Milestones in Status Period | Total New Tasks & Milestones in Status Period | Riding Data Date | Deadlines | Missed Activities | Wrong Status | Invalid Forecast Dates | Expected Finish | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | SF Relations | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Missing Baseline Starts | Missing Baseline Finishes | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Status Date | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Status Date | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | New Activity - Created | New Activity - Already Finished | New Activity - Finished in Status Period | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | Logic Density™ | CP Logic Density™ | Critical w/Missing Logic | Critical w/Hard Constraints | Zero Days Float | Negative Float | Float Ratio™ | CP - Float Ratio™ | Critical LOE | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical with Predecessor Lag | Critical with Successor Lag | Critical with Hard Constraints | Negative Float with Predecessor Lag | Negative Float with Successor Lag | New Activity & Critical - Created (Snapshot) | Critical CEI - Value Tasks | Critical CEI - Total Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Critical Milestone-to-Task Ratio (To-Go) | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Avg Float | Max Float | Float Ratio™ | New Activity & Critical - Created (Snapshot) | Critical | Non-Critical | CP - Float Ratio™ | 0 to 20 Days Float | 20 to 30 days float | More than 30 days float | Schedule Baseline Activities | Scheduled/Baselined to Start | Scheduled/Baselined to Finish | Start/ed | Finish/ed | Start Variance (Phase) | Start Compliance™ (Phase) | Finish Variance (Phase) | Finish Compliance™ (Phase) | Started Delayed (>30 days) | Completed Delayed (>30 days) | SPI(t) | Duration Variance (Original & Actual) | Duration Variance (Actual) | Scheduled Activities | Scheduled to Start | Scheduled to Finish | Scheduled to Start - Tasks & Milestones | Planned Ahead Start - Tasks & Milestones | Planned On Schedule Start - Tasks & Milestones | Planned Delayed Start - Tasks & Milestones | Riding Data Date - Tasks & Milestones | Planned Schedule Overrun - Tasks & Milestones | Scheduled to Start - Tasks | Planned Ahead Start - Tasks | Planned On Schedule Start - Tasks | Planned Delayed Start - Tasks | Planned Delayed Finish - Tasks | Scheduled to Start - Milestones | Planned Ahead Start - Milestones | Planned On Schedule Start - Milestones | Planned Delayed Start - Milestones | Planned Delayed Finish - Milestones | Actually Started - Tasks | In-Progress Started Ahead - Tasks | In-Progress Started On-Schedule - Tasks | In-Progress Started Delayed - Tasks | In-Progress Delayed Finish - Tasks | Avg Days Started Early | Avg Days Started Late | Avg Start Variance | Expected Finish | In-Progress Schedule Overrun - Tasks & Milestones | Actually Finished - Tasks & Milestones | Completed Ahead - Tasks & Milestones | Completed On-Schedule - Tasks & Milestones | Completed Delayed - Tasks & Milestones | Avg Days Finished Early - Tasks & Milestones | Avg Days Finished Late - Tasks & Milestones | Avg Finish Variance - Tasks & Milestones | Actually Finished - Tasks | Completed Ahead - Tasks | Completed On-Schedule - Tasks | Completed Delayed - Tasks | Accelerated Durations Early/On-Schedule - Tasks | Accelerated Durations Late - Tasks | Extended Durations - Tasks | Actually Finished - Milestones | Completed Ahead - Milestones | Completed On-Schedule - Milestones | Completed Delayed - Milestones | Logic Density™ - Successors | All Activities w/Successors | Activities Missing Successors | Total # Successors | Max # Successors on an Activity | Activities w/Leads on Successor | Total# of Successor Leads | Max # of Successor Leads on Activity | Activities w/Lags on Successor | Total# of Successor Lags | Max # of Successor Lags on Activity | Diverge Hotspot (Successors >2) | Diverge Hotspot w/Successor Lags | Diverge Hotspot w/Successor Lags & Low Total Float | Critical Diverge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Logic Density™ - Predecessors | All Activities w/Predecessors | Total # Predecessors | Activities Missing Predecessors | Max # Predecessors on an Activity | Activities w/Leads on Predecessor | Total # Predecessor Leads | Max # Predecessor Leads on an Activity | Activities w/Lags on Predecessor | Total # Predecessor Lags | Max # of Predecessor Lags on an Activity | Min Predecessor Lag (days) | Max Predecessor Lag (days) | Hidden Duration (Planned) | Critical w/Hidden Duration (Planned) | Merge Hotspot (Predecessors >2) | Merge Hotspot w/Predecessor Lags | Merge Hotspot w/Predecessor Lags & Low Total Float | Critical Merge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Logic Density™ | Logic Density™ - Predecessors | Logic Density™ - Successors | Summary Links | All Activities w/Predecessors | SS Predecessors | SF Predecessors | FF Predecessors | FS Predecessors | All Activities w/Successors | SS Successors | FF Successors | SF Successors | FS Successors | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Total Constraints | Start No Earlier Than | Start No Later Than | Finish No Earlier Than | Finish No Later Than | Hard Constraints | Must Start On | Must Finish On | As Late As Possible | Deadlines | Mandatory Start | Mandatory Finish | Open Ends with Constraints | Open Ends w/o Constraints | Unsatisfied Constraints | No Constraints | No Constraints | Tasks & Milestones (To-Go) - % of Total To-Go | Estimated Duration | Milestones with Duration>0 | Activities with Duration=0 | Avg. Original Duration | Avg. Remaining Duration | High Baseline Duration (44d) | High Planned Duration (44d) | Insufficient Detail™ | Critical Activities (To-Go) | Avg. Critical Original Duration | Avg. Critical Remaining Duration | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical w/Insufficient Detail™ | Activities (To-Go) | Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Total New Tasks & Milestones in Status Period | Total New Completed Tasks & Milestones in Status Period | Riding Data Date | Remaining Days | Approx Rem Work Days | Score
Ribbons | Large Test File | [12 empty] | 2025-02-07 | 0 | 0 | 0 | 5 | 0 | 0 | 66 | 9 | 6 | 0 | 0 | 66 | 4 | x | 0.97 | 0 | 0 | 0 | 0 | 1851 | 0 | 1851 | 0 | 1851 | 0 | 0 | 81 | 16 | -2600 | -0.02 | N/A | N/A | N/A | N/A | 1851 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | 0% | N/A | 0% | 0 | 1851 | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 7 | 0 | 2442 | 78 | 4132 | 380 | 13.24 | 13 | 2025-02-07 | 4 | 0 | 0 | 4 | 0% | 7 | 3 | 0 | 4 | 43% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 79 | 15 | 94 | 94 | 3 | 94 | 0 | 2442 | 1824 | 0 | 15 | 97 | 0 | 0 | 0 | 0 | 13 | 84 | 13 | 0 | 4 | 5 | 75 | 75 | 380 | 539 | 13.24 | 151 | 15 | 82 | 54 | 0 | 1:05 | 1:02 | 0 | 13 | 0 | N/A | 0 | 4.49 | 13 | 0 | 13 | 4 | 0 | 0 | 13 | 9 | 0 | 13 | 1:02 | 4 | 4 | 82 | 82 | 9 | 0 | 0 | 13 | 13.24 | -3.17 | 14.23 | 0 | 0 | 75 | 75 | 0 | 13 | 539 | 0 | 0 | 0 | 0 | 3 | 3 | N/A | 5 | N/A | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 2025-02-07 | 0 | 4 | 0 | 4 | 0 | 0 | N/A | 2025-02-07 | 0 | 2 | 0 | 2 | 0 | 0 | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 13 | 4 | 9 | 0 | 1:05 | 1:02 | 4.49 | 14.23 | 0 | 0 | 0 | 13 | 13.24 | -3.17 | N/A | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | 0 | 0 | 13 | 4 | 9 | 0 | 1:02 | 75 | 75 | 0 | 13 | 380 | 539 | 13.24 | 0 | 13 | 84 | -3.17 | 4 | 5 | 75 | 97 | 97 | 97 | 3 | 0 | 0 | 100% | 0 | 100% | N/A | N/A | -0.02 | 5 | 0 | 97 | 97 | 97 | 94 | 0 | 15 | 79 | 0 | 0 | 79 | 0 | 13 | 66 | 66 | 15 | 0 | 2 | 13 | 13 | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 97 | 0 | 130 | 5 | 0 | N/A | N/A | 0 | N/A | N/A | 7 | N/A | N/A | 5 | 3 | 3 | 3.22 | 94 | 303 | 0 | 137 | 0 | N/A | N/A | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 13 | N/A | N/A | 3 | 3 | 3 | 4.49 | 3.15 | 1.34 | 0 | 94 | 5 | 0 | 5 | 97 | 97 | 5 | 2 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 97 | 0 | 0 | 0 | 52 | 30 | 6 | 7 | 4 | 9 | 9 | 9 | 0 | 1 | 0 | 82 | 2025-02-07 | 151 | 15 | 82 | 54 | 0 | 0 | 97 | 0 | 0 | 0 | 151 | 97 | 15 | 82 | 54 | 0 | 0 | 13 | 9 | 4 | 0 | 0 | 0 | 1330 | 910 | 0
Ribbons | Large Test File | [13 empty] | 0% | 0% | 0% | 4% | 0% | 0% | 80% | 11% | 7% | 0% | 0% | 81% | 100% |  |  |  | 0% | 0% | 0% | N/A | 0% | 100% | 0% |  |  |  | 84% | 16% |  |  | N/A | N/A | [15 empty] | 0% |  | N/A | N/A | [15 empty] | N/A |  | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0% | 0% | 13% | 7% | 0% | 263% | 263% |  |  |  | 13% |  | 5% | 0% | 0% | 100% |  | 9% | 43% | 0% | 57% |  | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) |  |  |  | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 100% | 0% | 0% |  |  |  | 0% | 3% | 0% | 0% | 84% | 16% | 97% | 100% | 3% | 97% | 0% | 57% | 43% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 13% | 87% | 13% | 0% | 4% | 5% | 77% | 77% |  |  |  | 7% | 10% | 54% | 36% | 0% | 0.18 | 0.66 | 0% | 13% | 0% |  | 0% |  | 13% | 0% | 13% | 5% | 0% | 0% | 13% | 47% |  | 68% | 0.44 | 27% | 21% | 54% | 54% | 11% | 0% | 0% | 13% |  |  |  | 0% | 0% | 77% | 77% | 0% | 13% |  |  | 0% | 0% | 0% | 23% | 3% | ( N/A ) | 5% | ( N/A ) |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13% |  |  |  | 0% | 100% |  | 0% |  |  |  |  | 0% | 100% |  | 0% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 13% | 27% | 11% | 0% | 0.18 | 0.44 |  |  | 0% | 0% | 0% | 13% |  |  | 0% | 0% | 11% | 0% | 0% | 0% | 0% | 0% |  |  |  | N/A | N/A | 0% | 0% | 13% | 27% | 11% | 0% | 0.44 | 77% | 77% | 0% | 13% |  |  |  |  | 13% | 87% |  | 4% | 5% | 77% | 100% |  |  |  |  | 0% |  | 0% |  | ( N/A ) | ( N/A ) |  | 6% | 0% | 100% | 100% | 100% | 97% | 0% | 16% | 84% | 0% | 0% | 96% | 0% | 16% | 84% | 84% | 100% | 0% | 13% | 87% | 87% | 4% | 0% | 100% | 0% | 100% |  |  |  | 0% | 0% | 0% | ( N/A ) | ( N/A ) | ( N/A ) |  |  |  | 0% | ( N/A ) | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | ( N/A ) |  | 100% | 0% |  |  | 0% |  |  | 0% |  |  | 7% | ( N/A ) | ( N/A ) | 5% | 3% | 23% |  | 100% |  | 0% |  | 0% |  |  | 0% |  |  |  |  | 0% | 0% | 14% | ( N/A ) | ( N/A ) | 3% | 3% | 23% |  |  |  | 0% | 100% | 5% | 0% | 5% | 100% | 100% | 5% | 2% | 0% | 99% | 0% | 0% | 0% | 0% | 0% | 7% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 93% | 93% | 64% | 0% | 0% | 0% |  |  | 7% | 9% | 5% | 11% |  |  | 0% | 11% | 0% | 100% |  |  | 10% | 54% | 36% | 0% | 0% | 64% | 0% | 0% | 0% | 100% | 64% | 10% | 54% | 36% | 0% | 0% | 68% | 47% | 21% |  |  | 0%
Ribbons | Large Test File2 | [12 empty] | 2025-03-10 | 0 | 0 | 0 | 9 | 0 | 0 | 38 | 10 | 4 | 0 | 0 | 42 | 7 | x | 0.59 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 0 | 45 | 15 | -51490 | 0 | N/A | N/A | N/A | N/A | 2000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | 0% | N/A | 0% | 0 | 2000 | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 11 | 0 | 0 | 3005 | 757 | 4335 | 362 | 7.22 | 11 | 2025-03-10 | 7 | 0 | 0 | 7 | 0% | 9 | 4 | 2 | 3 | 56% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | 2 | 2 | 3 | 897 | 265 | 112 | 33 | 79 | 632 | 8 | 0 | 0 | 51 | 0 | 52 | 52 | 8 | 52 | 0 | 3005 | 3809 | 0 | 2 | 60 | 0 | 0 | 0 | 0 | 11 | 49 | 10 | 1 | 7 | 2 | 40 | 40 | 362 | 689 | 7.22 | 114 | 2 | 58 | 54 | 0 | 1:29 | 1:01 | 0 | 11 | 0 | N/A | 0 | 2.83 | 11 | 0 | 10 | 5 | 0 | 0 | 9 | 11 | 0 | 11 | N/A | 0 | 0 | 58 | 58 | 11 | 2 | 1 | 10 | 7.22 | -1 | 3.73 | 4 | 0 | 39 | 40 | 1 | 10 | 689 | 0 | 0 | 0 | 0 | 1 | 1 | N/A | 4 | N/A | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 10 | 2025-03-10 | 0 | 7 | 0 | 7 | 0 | 0 | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | 0 | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 2025-03-10 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | 0 | 2025-03-10 | 11 | 0 | 11 | 2 | 1:29 | N/A | 2.83 | 3.73 | 0 | 0 | 1 | 10 | 7.22 | -1 | N/A | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 4 | 0 | 11 | 0 | 11 | 2 | N/A | 39 | 40 | 1 | 10 | 362 | 689 | 7.22 | 0 | 11 | 49 | -1 | 7 | 2 | 40 | 58 | 58 | 58 | 8 | 0 | 0 | 100% | 0 | 100% | 2 | N/A | 0 | 26 | 3 | 60 | 60 | 60 | 52 | 0 | 0 | 51 | 0 | 0 | 50 | 0 | 0 | 49 | 49 | 2 | 0 | 0 | 2 | 2 | 8 | 2 | 3 | 2 | 7 | 112 | 33 | -79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.32 | 60 | 0 | 79 | 4 | 0 | N/A | N/A | 1 | 1 | 1 | 4 | N/A | N/A | 4 | 1 | 1 | 1.52 | 52 | 79 | 0 | 7 | 0 | N/A | N/A | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 8 | N/A | N/A | 1 | 1 | 1 | 2.83 | 1.52 | 1.32 | 0 | 52 | 3 | 0 | 4 | 59 | 60 | 4 | 4 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 60 | 0 | 0 | 0 | 117 | 52 | 4 | 11 | 4 | 11 | 105 | 69 | 0 | 3 | 1 | 58 | 2025-03-10 | 114 | 2 | 58 | 54 | 0 | 0 | 60 | 0 | 0 | 0 | 114 | 60 | 2 | 58 | 54 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 1502 | 1028 | 0
Ribbons | Large Test File2 | [13 empty] | 0% | 0% | 0% | 11% | 0% | 0% | 68% | 18% | 7% | 0% | 0% | 75% | 100% |  |  |  | 0% | 0% | 0% | N/A | 0% | 100% | 0% |  |  |  | 75% | 25% |  |  | N/A | N/A | [15 empty] | 0% |  | N/A | N/A | [15 empty] | N/A |  | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 3% | 0% | 18% | 0% | 0% | 324% | 324% |  |  |  | 18% |  | 13% | 0% | 0% | 100% |  | 16% | 44% | 22% | 33% |  | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) |  |  |  | 0% | ( N/A ) | ( N/A ) | 25% | 25% | 38% | 11213% | 3313% |  |  |  | 11% | 13% | 0% | 0% | 98% | 0% | 87% | 100% | 13% | 87% | 0% | 44% | 56% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 18% | 82% | 17% | 2% | 12% | 3% | 67% | 67% |  |  |  | 5% | 2% | 51% | 47% | 0% | 0.03 | 0.93 | 0% | 18% | 0% |  | 0% |  | 18% | 0% | 17% | 9% | 0% | 0% | 15% | 52% |  | 52% | 0 | 0% | 0% | 51% | 51% | 19% | 18% | 2% | 17% |  |  |  | 4% | 0% | 65% | 67% | 2% | 17% |  |  | 0% | 0% | 0% | 9% | 2% | ( N/A ) | 7% | ( N/A ) |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 2% | 0% | 0% | 17% |  |  |  | 0% | 100% |  | 0% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | 0% | 100% |  | 0% | [7 empty] | N/A | N/A |  | N/A |  |  | 18% | 0% | 19% | 18% | 0.03 | 0 |  |  | 0% | 0% | 2% | 17% |  |  | 0% | 0% | 27% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0% | 100% | 4% | 0% | 18% | 0% | 19% | 18% | 0 | 65% | 67% | 2% | 17% |  |  |  |  | 18% | 82% |  | 12% | 3% | 67% | 97% |  |  |  |  | 0% |  | 0% |  | 100% | ( N/A ) |  | 46% | 5% | 100% | 100% | 100% | 87% | 0% | 0% | 98% | 0% | 0% | 86% | 0% | 0% | 98% | 98% | 100% | 0% | 0% | 100% | 100% | 14% | 25% | 38% | 25% | 88% |  |  |  | 0% | 0% | 0% | ( N/A ) | ( N/A ) | ( N/A ) |  |  |  | 0% | ( N/A ) | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | ( N/A ) |  | 100% | 0% |  |  | 0% |  |  | 2% |  |  | 7% | ( N/A ) | ( N/A ) | 7% | 2% | 9% |  | 100% |  | 0% |  | 0% |  |  | 0% |  |  |  |  | 0% | 0% | 15% | ( N/A ) | ( N/A ) | 2% | 2% | 9% |  |  |  | 0% | 100% | 5% | 0% | 7% | 98% | 100% | 7% | 7% | 0% | 97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 53% | 0% | 0% | 0% |  |  | 7% | 19% | 7% | 19% |  |  | 0% | 27% | 2% | 100% |  |  | 2% | 51% | 47% | 0% | 0% | 53% | 0% | 0% | 0% | 100% | 53% | 2% | 51% | 47% | 0% | 0% | 52% | 52% | 0% |  |  | 0%
Phase Analyzer | Status Date | 2026-07-01: 2025-02-07; 2026-08-01: 2025-02-07; 2026-09-01: 2025-02-07; 2026-10-01: 2025-02-07; 2026-11-01: 2025-02-07; 2026-12-01: 2025-02-07
Phase Analyzer | WBS | bar: 2026-07-01; 2026-08-01; 2026-09-01; 2026-10-01; 2026-11-01; 2026-12-01
Phase Analyzer | New Activity - Created (Snapshot) | 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0; 2026-11-01: 0; 2026-12-01: 0
Phase Analyzer | New Activity - Already Finished (Snapshot) - check/compare | 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0; 2026-11-01: 0; 2026-12-01: 0
Phase Analyzer | New Activity - Finished in Status Period (Snapshot) - check/compare | 2026-07-01: N/A; 2026-08-01: N/A; 2026-09-01: N/A; 2026-10-01: N/A; 2026-11-01: N/A; 2026-12-01: N/A
Phase Analyzer | Specific Task Start | 2026-07-01: N/A; 2026-08-01: N/A; 2026-09-01: N/A; 2026-10-01: N/A; 2026-11-01: N/A; 2026-12-01: N/A
Phase Analyzer | Specific Task Finish | 2026-07-01: N/A; 2026-08-01: N/A; 2026-09-01: N/A; 2026-10-01: N/A; 2026-11-01: N/A; 2026-12-01: N/A
Phase Analyzer | Score | 2026-07-01: 100; 2026-08-01: 100; 2026-09-01: 100; 2026-10-01: 100; 2026-11-01: 100; 2026-12-01: 100

## Ribbon Analysis
Fuse® Analyst Report
Workbook: Large Test File vs Large Test File2 - 4249 Activities
Quick Add Metrics
Created on: 7/15/2026
Created by: dpolitte
Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Status Date | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Overrun | Work Underrun | Work Overrun | Total Work | Actual Work | Remaining Work | Work Discrepancy | Baseline Work | Summarized Work | Work per Day | Missing Resources | Resources | SV(t) | SPI(t) | WV | SV | SPI | CPI | EAC | EAC(CPI) | EAC(Composite) | TCPI(BAC) | TCPI(EAC) | TCPI(EAC) to CPI | PV (BCWS) | EV (BCWP) | AC (ACWP) | %Schedule | %Spent | %Complete | %Spent (EAC) | VAC | BAC | CV | SV | SPI | CPI | EAC | EAC(CPI) | EAC(Composite) | TCPI(BAC) | TCPI(EAC) | TCPI(EAC) to CPI | PV (BCWS) | EV (BCWP) | AC (ACWP) | %Schedule | %Spent | %Complete | %Spent (EAC) | VAC | BAC | Overrun | $ Cost Underrun | $ Cost Overrun | $ Total Cost | $ Actual Cost | $ Remaining Cost | $ Cost Discrepancy | $ Budget Cost | $ Cost per Day | Negative Planned Cost | Negative Actual Cost | Critical | Soft Constraints | Hard Constraints | Remaining Duration | Rem. Critical Duration | Ribbon Length | Avg Float | Float Ratio™ | Longest Path | Time Now | Forecast to be Finished | Completed On Time | Completed Late | Not Completed | Baseline Finish Compliance | Forecast to be Started | Started On Time | Started Late | Not Started | Baseline Start Compliance | Completed Ahead | Completed Delayed | Completed On-Schedule | Accelerated | Days Variance | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Variance | Actually Finished | Took Longer than Planned | Took Less Than Planned | Started Ahead | Started Delayed | In-Progress On Schedule | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Start Variance | Discrepancy | Actually Started | Expected Finish | Planned Ahead | Planned Delayed | Planned On Schedule | Scheduled to Start | Scheduled to Finish | Underway | Planned | Completed | Days Remaining | Days Completed | Completed Milestones | Planned Milestones | Not Completed | Physical Percent Complete | Duration Percent Complete | Units Percent Complete | Wrong Status | Critical | Non-Critical | Negative Float | Zero Days Float | 0 to 20 Days Float | 20 to 30 days float | More than 30 days float | High Float | Avg Float | Max Float | Float Ratio™ | Total Activities | Milestones | Normal | Summaries | Hammocks | Milestone Ratio | Detail Level | Missing WBS | Longest Path | Riding Data Date | Activities per million | Missing Logic | Logic Density™ | Critical | Hard Constraints | Negative Float | Insufficient Detail™ | Number of Lags | Number of Leads | Merge Hotspot | Longest Path (Normal Tasks) | Newly Created Activity & Critical - Created (Snapshot) | Longest Path (Tasks & Milestones) | Critical Milestone-to-Task Ratio (To-Go) | Critical Milestones (To-Go) | Longest Path (Milestones) | Normal Tasks | Normal Tasks (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Zero Days Float | Negative Float | Float Ratio™ | CP - Float Ratio™ | CP Logic Density™ | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Max Float | Newly Created Activity & Critical - Created (Snapshot) | Number of Leads | Number of Lags | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Total New Completed Tasks & Milestones in Status Period | Total New Tasks & Milestones in Status Period | Riding Data Date | Deadlines | Missed Activities | Wrong Status | Invalid Forecast Dates | Expected Finish | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | SF Relations | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Missing Baseline Starts | Missing Baseline Finishes | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Status Date | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Status Date | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | New Activity - Created | New Activity - Already Finished | New Activity - Finished in Status Period | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | Logic Density™ | CP Logic Density™ | Critical w/Missing Logic | Critical w/Hard Constraints | Zero Days Float | Negative Float | Float Ratio™ | CP - Float Ratio™ | Critical LOE | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical with Predecessor Lag | Critical with Successor Lag | Critical with Hard Constraints | Negative Float with Predecessor Lag | Negative Float with Successor Lag | New Activity & Critical - Created (Snapshot) | Critical CEI - Value Tasks | Critical CEI - Total Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Critical Milestone-to-Task Ratio (To-Go) | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Avg Float | Max Float | Float Ratio™ | New Activity & Critical - Created (Snapshot) | Critical | Non-Critical | CP - Float Ratio™ | 0 to 20 Days Float | 20 to 30 days float | More than 30 days float | Schedule Baseline Activities | Scheduled/Baselined to Start | Scheduled/Baselined to Finish | Start/ed | Finish/ed | Start Variance (Phase) | Start Compliance™ (Phase) | Finish Variance (Phase) | Finish Compliance™ (Phase) | Started Delayed (>30 days) | Completed Delayed (>30 days) | SPI(t) | Duration Variance (Original & Actual) | Duration Variance (Actual) | Scheduled Activities | Scheduled to Start | Scheduled to Finish | Scheduled to Start - Tasks & Milestones | Planned Ahead Start - Tasks & Milestones | Planned On Schedule Start - Tasks & Milestones | Planned Delayed Start - Tasks & Milestones | Riding Data Date - Tasks & Milestones | Planned Schedule Overrun - Tasks & Milestones | Scheduled to Start - Tasks | Planned Ahead Start - Tasks | Planned On Schedule Start - Tasks | Planned Delayed Start - Tasks | Planned Delayed Finish - Tasks | Scheduled to Start - Milestones | Planned Ahead Start - Milestones | Planned On Schedule Start - Milestones | Planned Delayed Start - Milestones | Planned Delayed Finish - Milestones | Actually Started - Tasks | In-Progress Started Ahead - Tasks | In-Progress Started On-Schedule - Tasks | In-Progress Started Delayed - Tasks | In-Progress Delayed Finish - Tasks | Avg Days Started Early | Avg Days Started Late | Avg Start Variance | Expected Finish | In-Progress Schedule Overrun - Tasks & Milestones | Actually Finished - Tasks & Milestones | Completed Ahead - Tasks & Milestones | Completed On-Schedule - Tasks & Milestones | Completed Delayed - Tasks & Milestones | Avg Days Finished Early - Tasks & Milestones | Avg Days Finished Late - Tasks & Milestones | Avg Finish Variance - Tasks & Milestones | Actually Finished - Tasks | Completed Ahead - Tasks | Completed On-Schedule - Tasks | Completed Delayed - Tasks | Accelerated Durations Early/On-Schedule - Tasks | Accelerated Durations Late - Tasks | Extended Durations - Tasks | Actually Finished - Milestones | Completed Ahead - Milestones | Completed On-Schedule - Milestones | Completed Delayed - Milestones | Logic Density™ - Successors | All Activities w/Successors | Activities Missing Successors | Total # Successors | Max # Successors on an Activity | Activities w/Leads on Successor | Total# of Successor Leads | Max # of Successor Leads on Activity | Activities w/Lags on Successor | Total# of Successor Lags | Max # of Successor Lags on Activity | Diverge Hotspot (Successors >2) | Diverge Hotspot w/Successor Lags | Diverge Hotspot w/Successor Lags & Low Total Float | Critical Diverge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Logic Density™ - Predecessors | All Activities w/Predecessors | Total # Predecessors | Activities Missing Predecessors | Max # Predecessors on an Activity | Activities w/Leads on Predecessor | Total # Predecessor Leads | Max # Predecessor Leads on an Activity | Activities w/Lags on Predecessor | Total # Predecessor Lags | Max # of Predecessor Lags on an Activity | Min Predecessor Lag (days) | Max Predecessor Lag (days) | Hidden Duration (Planned) | Critical w/Hidden Duration (Planned) | Merge Hotspot (Predecessors >2) | Merge Hotspot w/Predecessor Lags | Merge Hotspot w/Predecessor Lags & Low Total Float | Critical Merge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Logic Density™ | Logic Density™ - Predecessors | Logic Density™ - Successors | Summary Links | All Activities w/Predecessors | SS Predecessors | SF Predecessors | FF Predecessors | FS Predecessors | All Activities w/Successors | SS Successors | FF Successors | SF Successors | FS Successors | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Total Constraints | Start No Earlier Than | Start No Later Than | Finish No Earlier Than | Finish No Later Than | Hard Constraints | Must Start On | Must Finish On | As Late As Possible | Deadlines | Mandatory Start | Mandatory Finish | Open Ends with Constraints | Open Ends w/o Constraints | Unsatisfied Constraints | No Constraints | No Constraints | Tasks & Milestones (To-Go) - % of Total To-Go | Estimated Duration | Milestones with Duration>0 | Activities with Duration=0 | Avg. Original Duration | Avg. Remaining Duration | High Baseline Duration (44d) | High Planned Duration (44d) | Insufficient Detail™ | Critical Activities (To-Go) | Avg. Critical Original Duration | Avg. Critical Remaining Duration | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical w/Insufficient Detail™ | Activities (To-Go) | Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Total New Tasks & Milestones in Status Period | Total New Completed Tasks & Milestones in Status Period | Riding Data Date | Remaining Days | Approx Rem Work Days | Score
Ribbons | Large Test File | 2025-02-07 | 0 | 0 | 0 | 5 | 0 | 0 | 66 | 9 | 6 | 0 | 0 | 66 | 4 | x | 0.97 | 0 | 0 | 0 | 0 | 1851 | 0 | 1851 | 0 | 1851 | 0 | 0 | 81 | 16 | -2600 | -0.02 | N/A | N/A | N/A | N/A | 1851 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | 0% | N/A | 0% | 0 | 1851 | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 7 | 0 | 2442 | 78 | 4132 | 380 | 13.24 | 13 | 2025-02-07 | 4 | 0 | 0 | 4 | 0% | 7 | 3 | 0 | 4 | 43% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 79 | 15 | 94 | 94 | 3 | 94 | 0 | 2442 | 1824 | 0 | 15 | 97 | 0 | 0 | 0 | 0 | 13 | 84 | 13 | 0 | 4 | 5 | 75 | 75 | 380 | 539 | 13.24 | 151 | 15 | 82 | 54 | 0 | 1:05 | 1:02 | 0 | 13 | 0 | N/A | 0 | 4.49 | 13 | 0 | 13 | 4 | 0 | 0 | 13 | 9 | 0 | 13 | 1:02 | 4 | 4 | 82 | 82 | 9 | 0 | 0 | 13 | 13.24 | -3.17 | 14.23 | 0 | 0 | 75 | 75 | 0 | 13 | 539 | 0 | 0 | 0 | 0 | 3 | 3 | N/A | 5 | N/A | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 2025-02-07 | 0 | 4 | 0 | 4 | 0 | 0 | N/A | 2025-02-07 | 0 | 2 | 0 | 2 | 0 | 0 | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 13 | 4 | 9 | 0 | 1:05 | 1:02 | 4.49 | 14.23 | 0 | 0 | 0 | 13 | 13.24 | -3.17 | N/A | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | 0 | 0 | 13 | 4 | 9 | 0 | 1:02 | 75 | 75 | 0 | 13 | 380 | 539 | 13.24 | 0 | 13 | 84 | -3.17 | 4 | 5 | 75 | 97 | 97 | 97 | 3 | 0 | 0 | 100% | 0 | 100% | N/A | N/A | -0.02 | 5 | 0 | 97 | 97 | 97 | 94 | 0 | 15 | 79 | 0 | 0 | 79 | 0 | 13 | 66 | 66 | 15 | 0 | 2 | 13 | 13 | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 97 | 0 | 130 | 5 | 0 | N/A | N/A | 0 | N/A | N/A | 7 | N/A | N/A | 5 | 3 | 3 | 3.22 | 94 | 303 | 0 | 137 | 0 | N/A | N/A | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 13 | N/A | N/A | 3 | 3 | 3 | 4.49 | 3.15 | 1.34 | 0 | 94 | 5 | 0 | 5 | 97 | 97 | 5 | 2 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 97 | 0 | 0 | 0 | 52 | 30 | 6 | 7 | 4 | 9 | 9 | 9 | 0 | 1 | 0 | 82 | 2025-02-07 | 151 | 15 | 82 | 54 | 0 | 0 | 97 | 0 | 0 | 0 | 151 | 97 | 15 | 82 | 54 | 0 | 0 | 13 | 9 | 4 | 0 | 0 | 0 | 1330 | 910 | 0
Ribbons | Large Test File2 | 2025-03-10 | 0 | 0 | 0 | 9 | 0 | 0 | 38 | 10 | 4 | 0 | 0 | 42 | 7 | x | 0.59 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 2000 | 0 | 0 | 45 | 15 | -51490 | 0 | N/A | N/A | N/A | N/A | 2000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | 0% | N/A | 0% | 0 | 2000 | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 11 | 0 | 0 | 3005 | 757 | 4335 | 362 | 7.22 | 11 | 2025-03-10 | 7 | 0 | 0 | 7 | 0% | 9 | 4 | 2 | 3 | 56% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | 2 | 2 | 3 | 897 | 265 | 112 | 33 | 79 | 632 | 8 | 0 | 0 | 51 | 0 | 52 | 52 | 8 | 52 | 0 | 3005 | 3809 | 0 | 2 | 60 | 0 | 0 | 0 | 0 | 11 | 49 | 10 | 1 | 7 | 2 | 40 | 40 | 362 | 689 | 7.22 | 114 | 2 | 58 | 54 | 0 | 1:29 | 1:01 | 0 | 11 | 0 | N/A | 0 | 2.83 | 11 | 0 | 10 | 5 | 0 | 0 | 9 | 11 | 0 | 11 | N/A | 0 | 0 | 58 | 58 | 11 | 2 | 1 | 10 | 7.22 | -1 | 3.73 | 4 | 0 | 39 | 40 | 1 | 10 | 689 | 0 | 0 | 0 | 0 | 1 | 1 | N/A | 4 | N/A | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 10 | 2025-03-10 | 0 | 7 | 0 | 7 | 0 | 0 | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | 0 | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 2025-03-10 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | 0 | 2025-03-10 | 11 | 0 | 11 | 2 | 1:29 | N/A | 2.83 | 3.73 | 0 | 0 | 1 | 10 | 7.22 | -1 | N/A | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 4 | 0 | 11 | 0 | 11 | 2 | N/A | 39 | 40 | 1 | 10 | 362 | 689 | 7.22 | 0 | 11 | 49 | -1 | 7 | 2 | 40 | 58 | 58 | 58 | 8 | 0 | 0 | 100% | 0 | 100% | 2 | N/A | 0 | 26 | 3 | 60 | 60 | 60 | 52 | 0 | 0 | 51 | 0 | 0 | 50 | 0 | 0 | 49 | 49 | 2 | 0 | 0 | 2 | 2 | 8 | 2 | 3 | 2 | 7 | 112 | 33 | -79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.32 | 60 | 0 | 79 | 4 | 0 | N/A | N/A | 1 | 1 | 1 | 4 | N/A | N/A | 4 | 1 | 1 | 1.52 | 52 | 79 | 0 | 7 | 0 | N/A | N/A | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 8 | N/A | N/A | 1 | 1 | 1 | 2.83 | 1.52 | 1.32 | 0 | 52 | 3 | 0 | 4 | 59 | 60 | 4 | 4 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 60 | 0 | 0 | 0 | 117 | 52 | 4 | 11 | 4 | 11 | 105 | 69 | 0 | 3 | 1 | 58 | 2025-03-10 | 114 | 2 | 58 | 54 | 0 | 0 | 60 | 0 | 0 | 0 | 114 | 60 | 2 | 58 | 54 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 1502 | 1028 | 0
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Status Date | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Overrun | Work Underrun | Work Overrun | Total Work | Actual Work | Remaining Work | Work Discrepancy | Baseline Work | Summarized Work | Work per Day | Missing Resources | Resources | SV(t) | SPI(t) | WV | SV | SPI | CPI | EAC | EAC(CPI) | EAC(Composite) | TCPI(BAC) | TCPI(EAC) | TCPI(EAC) to CPI | PV (BCWS) | EV (BCWP) | AC (ACWP) | %Schedule | %Spent | %Complete | %Spent (EAC) | VAC | BAC | CV | SV | SPI | CPI | EAC | EAC(CPI) | EAC(Composite) | TCPI(BAC) | TCPI(EAC) | TCPI(EAC) to CPI | PV (BCWS) | EV (BCWP) | AC (ACWP) | %Schedule | %Spent | %Complete | %Spent (EAC) | VAC | BAC | Overrun | $ Cost Underrun | $ Cost Overrun | $ Total Cost | $ Actual Cost | $ Remaining Cost | $ Cost Discrepancy | $ Budget Cost | $ Cost per Day | Negative Planned Cost | Negative Actual Cost | Critical | Soft Constraints | Hard Constraints | Remaining Duration | Rem. Critical Duration | Ribbon Length | Avg Float | Float Ratio™ | Longest Path | Time Now | Forecast to be Finished | Completed On Time | Completed Late | Not Completed | Baseline Finish Compliance | Forecast to be Started | Started On Time | Started Late | Not Started | Baseline Start Compliance | Completed Ahead | Completed Delayed | Completed On-Schedule | Accelerated | Days Variance | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Variance | Actually Finished | Took Longer than Planned | Took Less Than Planned | Started Ahead | Started Delayed | In-Progress On Schedule | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Start Variance | Discrepancy | Actually Started | Expected Finish | Planned Ahead | Planned Delayed | Planned On Schedule | Scheduled to Start | Scheduled to Finish | Underway | Planned | Completed | Days Remaining | Days Completed | Completed Milestones | Planned Milestones | Not Completed | Physical Percent Complete | Duration Percent Complete | Units Percent Complete | Wrong Status | Critical | Non-Critical | Negative Float | Zero Days Float | 0 to 20 Days Float | 20 to 30 days float | More than 30 days float | High Float | Avg Float | Max Float | Float Ratio™ | Total Activities | Milestones | Normal | Summaries | Hammocks | Milestone Ratio | Detail Level | Missing WBS | Longest Path | Riding Data Date | Activities per million | Missing Logic | Logic Density™ | Critical | Hard Constraints | Negative Float | Insufficient Detail™ | Number of Lags | Number of Leads | Merge Hotspot | Longest Path (Normal Tasks) | Newly Created Activity & Critical - Created (Snapshot) | Longest Path (Tasks & Milestones) | Critical Milestone-to-Task Ratio (To-Go) | Critical Milestones (To-Go) | Longest Path (Milestones) | Normal Tasks | Normal Tasks (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Zero Days Float | Negative Float | Float Ratio™ | CP - Float Ratio™ | CP Logic Density™ | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Max Float | Newly Created Activity & Critical - Created (Snapshot) | Number of Leads | Number of Lags | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Total New Completed Tasks & Milestones in Status Period | Total New Tasks & Milestones in Status Period | Riding Data Date | Deadlines | Missed Activities | Wrong Status | Invalid Forecast Dates | Expected Finish | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | SF Relations | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Missing Baseline Starts | Missing Baseline Finishes | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Status Date | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Status Date | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | New Activity - Created | New Activity - Already Finished | New Activity - Finished in Status Period | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | Logic Density™ | CP Logic Density™ | Critical w/Missing Logic | Critical w/Hard Constraints | Zero Days Float | Negative Float | Float Ratio™ | CP - Float Ratio™ | Critical LOE | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical with Predecessor Lag | Critical with Successor Lag | Critical with Hard Constraints | Negative Float with Predecessor Lag | Negative Float with Successor Lag | New Activity & Critical - Created (Snapshot) | Critical CEI - Value Tasks | Critical CEI - Total Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Critical Milestone-to-Task Ratio (To-Go) | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Avg Float | Max Float | Float Ratio™ | New Activity & Critical - Created (Snapshot) | Critical | Non-Critical | CP - Float Ratio™ | 0 to 20 Days Float | 20 to 30 days float | More than 30 days float | Schedule Baseline Activities | Scheduled/Baselined to Start | Scheduled/Baselined to Finish | Start/ed | Finish/ed | Start Variance (Phase) | Start Compliance™ (Phase) | Finish Variance (Phase) | Finish Compliance™ (Phase) | Started Delayed (>30 days) | Completed Delayed (>30 days) | SPI(t) | Duration Variance (Original & Actual) | Duration Variance (Actual) | Scheduled Activities | Scheduled to Start | Scheduled to Finish | Scheduled to Start - Tasks & Milestones | Planned Ahead Start - Tasks & Milestones | Planned On Schedule Start - Tasks & Milestones | Planned Delayed Start - Tasks & Milestones | Riding Data Date - Tasks & Milestones | Planned Schedule Overrun - Tasks & Milestones | Scheduled to Start - Tasks | Planned Ahead Start - Tasks | Planned On Schedule Start - Tasks | Planned Delayed Start - Tasks | Planned Delayed Finish - Tasks | Scheduled to Start - Milestones | Planned Ahead Start - Milestones | Planned On Schedule Start - Milestones | Planned Delayed Start - Milestones | Planned Delayed Finish - Milestones | Actually Started - Tasks | In-Progress Started Ahead - Tasks | In-Progress Started On-Schedule - Tasks | In-Progress Started Delayed - Tasks | In-Progress Delayed Finish - Tasks | Avg Days Started Early | Avg Days Started Late | Avg Start Variance | Expected Finish | In-Progress Schedule Overrun - Tasks & Milestones | Actually Finished - Tasks & Milestones | Completed Ahead - Tasks & Milestones | Completed On-Schedule - Tasks & Milestones | Completed Delayed - Tasks & Milestones | Avg Days Finished Early - Tasks & Milestones | Avg Days Finished Late - Tasks & Milestones | Avg Finish Variance - Tasks & Milestones | Actually Finished - Tasks | Completed Ahead - Tasks | Completed On-Schedule - Tasks | Completed Delayed - Tasks | Accelerated Durations Early/On-Schedule - Tasks | Accelerated Durations Late - Tasks | Extended Durations - Tasks | Actually Finished - Milestones | Completed Ahead - Milestones | Completed On-Schedule - Milestones | Completed Delayed - Milestones | Logic Density™ - Successors | All Activities w/Successors | Activities Missing Successors | Total # Successors | Max # Successors on an Activity | Activities w/Leads on Successor | Total# of Successor Leads | Max # of Successor Leads on Activity | Activities w/Lags on Successor | Total# of Successor Lags | Max # of Successor Lags on Activity | Diverge Hotspot (Successors >2) | Diverge Hotspot w/Successor Lags | Diverge Hotspot w/Successor Lags & Low Total Float | Critical Diverge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Logic Density™ - Predecessors | All Activities w/Predecessors | Total # Predecessors | Activities Missing Predecessors | Max # Predecessors on an Activity | Activities w/Leads on Predecessor | Total # Predecessor Leads | Max # Predecessor Leads on an Activity | Activities w/Lags on Predecessor | Total # Predecessor Lags | Max # of Predecessor Lags on an Activity | Min Predecessor Lag (days) | Max Predecessor Lag (days) | Hidden Duration (Planned) | Critical w/Hidden Duration (Planned) | Merge Hotspot (Predecessors >2) | Merge Hotspot w/Predecessor Lags | Merge Hotspot w/Predecessor Lags & Low Total Float | Critical Merge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Logic Density™ | Logic Density™ - Predecessors | Logic Density™ - Successors | Summary Links | All Activities w/Predecessors | SS Predecessors | SF Predecessors | FF Predecessors | FS Predecessors | All Activities w/Successors | SS Successors | FF Successors | SF Successors | FS Successors | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Total Constraints | Start No Earlier Than | Start No Later Than | Finish No Earlier Than | Finish No Later Than | Hard Constraints | Must Start On | Must Finish On | As Late As Possible | Deadlines | Mandatory Start | Mandatory Finish | Open Ends with Constraints | Open Ends w/o Constraints | Unsatisfied Constraints | No Constraints | No Constraints | Tasks & Milestones (To-Go) - % of Total To-Go | Estimated Duration | Milestones with Duration>0 | Activities with Duration=0 | Avg. Original Duration | Avg. Remaining Duration | High Baseline Duration (44d) | High Planned Duration (44d) | Insufficient Detail™ | Critical Activities (To-Go) | Avg. Critical Original Duration | Avg. Critical Remaining Duration | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical w/Insufficient Detail™ | Activities (To-Go) | Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Total New Tasks & Milestones in Status Period | Total New Completed Tasks & Milestones in Status Period | Riding Data Date | Remaining Days | Approx Rem Work Days | Score
Ribbons | Large Test File |  | 0% | 0% | 0% | 4% | 0% | 0% | 80% | 11% | 7% | 0% | 0% | 81% | 100% |  |  |  | 0% | 0% | 0% | N/A | 0% | 100% | 0% |  |  |  | 84% | 16% |  |  | N/A | N/A | [15 empty] | 0% |  | N/A | N/A | [15 empty] | N/A |  | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 0% | 0% | 13% | 7% | 0% | 263% | 263% |  |  |  | 13% |  | 5% | 0% | 0% | 100% |  | 9% | 43% | 0% | 57% |  | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) |  |  |  | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 100% | 0% | 0% |  |  |  | 0% | 3% | 0% | 0% | 84% | 16% | 97% | 100% | 3% | 97% | 0% | 57% | 43% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 13% | 87% | 13% | 0% | 4% | 5% | 77% | 77% |  |  |  | 7% | 10% | 54% | 36% | 0% | 0.18 | 0.66 | 0% | 13% | 0% |  | 0% |  | 13% | 0% | 13% | 5% | 0% | 0% | 13% | 47% |  | 68% | 0.44 | 27% | 21% | 54% | 54% | 11% | 0% | 0% | 13% |  |  |  | 0% | 0% | 77% | 77% | 0% | 13% |  |  | 0% | 0% | 0% | 23% | 3% | ( N/A ) | 5% | ( N/A ) |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13% |  |  |  | 0% | 100% |  | 0% |  |  |  |  | 0% | 100% |  | 0% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 13% | 27% | 11% | 0% | 0.18 | 0.44 |  |  | 0% | 0% | 0% | 13% |  |  | 0% | 0% | 11% | 0% | 0% | 0% | 0% | 0% |  |  |  | N/A | N/A | 0% | 0% | 13% | 27% | 11% | 0% | 0.44 | 77% | 77% | 0% | 13% |  |  |  |  | 13% | 87% |  | 4% | 5% | 77% | 100% |  |  |  |  | 0% |  | 0% |  | ( N/A ) | ( N/A ) |  | 6% | 0% | 100% | 100% | 100% | 97% | 0% | 16% | 84% | 0% | 0% | 96% | 0% | 16% | 84% | 84% | 100% | 0% | 13% | 87% | 87% | 4% | 0% | 100% | 0% | 100% |  |  |  | 0% | 0% | 0% | ( N/A ) | ( N/A ) | ( N/A ) |  |  |  | 0% | ( N/A ) | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | ( N/A ) |  | 100% | 0% |  |  | 0% |  |  | 0% |  |  | 7% | ( N/A ) | ( N/A ) | 5% | 3% | 23% |  | 100% |  | 0% |  | 0% |  |  | 0% |  |  |  |  | 0% | 0% | 14% | ( N/A ) | ( N/A ) | 3% | 3% | 23% |  |  |  | 0% | 100% | 5% | 0% | 5% | 100% | 100% | 5% | 2% | 0% | 99% | 0% | 0% | 0% | 0% | 0% | 7% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 93% | 93% | 64% | 0% | 0% | 0% |  |  | 7% | 9% | 5% | 11% |  |  | 0% | 11% | 0% | 100% |  |  | 10% | 54% | 36% | 0% | 0% | 64% | 0% | 0% | 0% | 100% | 64% | 10% | 54% | 36% | 0% | 0% | 68% | 47% | 21% |  |  | 0%
Ribbons | Large Test File2 |  | 0% | 0% | 0% | 11% | 0% | 0% | 68% | 18% | 7% | 0% | 0% | 75% | 100% |  |  |  | 0% | 0% | 0% | N/A | 0% | 100% | 0% |  |  |  | 75% | 25% |  |  | N/A | N/A | [15 empty] | 0% |  | N/A | N/A | [15 empty] | N/A |  | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 3% | 0% | 18% | 0% | 0% | 324% | 324% |  |  |  | 18% |  | 13% | 0% | 0% | 100% |  | 16% | 44% | 22% | 33% |  | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) |  |  |  | 0% | ( N/A ) | ( N/A ) | 25% | 25% | 38% | 11213% | 3313% |  |  |  | 11% | 13% | 0% | 0% | 98% | 0% | 87% | 100% | 13% | 87% | 0% | 44% | 56% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 18% | 82% | 17% | 2% | 12% | 3% | 67% | 67% |  |  |  | 5% | 2% | 51% | 47% | 0% | 0.03 | 0.93 | 0% | 18% | 0% |  | 0% |  | 18% | 0% | 17% | 9% | 0% | 0% | 15% | 52% |  | 52% | 0 | 0% | 0% | 51% | 51% | 19% | 18% | 2% | 17% |  |  |  | 4% | 0% | 65% | 67% | 2% | 17% |  |  | 0% | 0% | 0% | 9% | 2% | ( N/A ) | 7% | ( N/A ) |  |  | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 2% | 0% | 0% | 17% |  |  |  | 0% | 100% |  | 0% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | 0% | 100% |  | 0% | [7 empty] | N/A | N/A |  | N/A |  |  | 18% | 0% | 19% | 18% | 0.03 | 0 |  |  | 0% | 0% | 2% | 17% |  |  | 0% | 0% | 27% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0% | 100% | 4% | 0% | 18% | 0% | 19% | 18% | 0 | 65% | 67% | 2% | 17% |  |  |  |  | 18% | 82% |  | 12% | 3% | 67% | 97% |  |  |  |  | 0% |  | 0% |  | 100% | ( N/A ) |  | 46% | 5% | 100% | 100% | 100% | 87% | 0% | 0% | 98% | 0% | 0% | 86% | 0% | 0% | 98% | 98% | 100% | 0% | 0% | 100% | 100% | 14% | 25% | 38% | 25% | 88% |  |  |  | 0% | 0% | 0% | ( N/A ) | ( N/A ) | ( N/A ) |  |  |  | 0% | ( N/A ) | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | ( N/A ) |  | 100% | 0% |  |  | 0% |  |  | 2% |  |  | 7% | ( N/A ) | ( N/A ) | 7% | 2% | 9% |  | 100% |  | 0% |  | 0% |  |  | 0% |  |  |  |  | 0% | 0% | 15% | ( N/A ) | ( N/A ) | 2% | 2% | 9% |  |  |  | 0% | 100% | 5% | 0% | 7% | 98% | 100% | 7% | 7% | 0% | 97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 53% | 0% | 0% | 0% |  |  | 7% | 19% | 7% | 19% |  |  | 0% | 27% | 2% | 100% |  |  | 2% | 51% | 47% | 0% | 0% | 53% | 0% | 0% | 0% | 100% | 53% | 2% | 51% | 47% | 0% | 0% | 52% | 52% | 0% |  |  | 0%

## Large-Test-File1
Fuse® Analyst Report
Workbook: Large Test File vs Large Test File2 - 4249 Activities
Quick Add Metrics
Created on: 7/15/2026
Created by: dpolitte
Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View | Large Test File: Detailed View
4. SS/FF Relations
Number of Start to Start (SS) and Finish to Finish (FF) logic links. Should be lower than 10%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
6. High Float
Number of activities with total float greater than 2 months. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
7. Negative Float
Activities that are incomplete and have total float less than 0 working days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
8. High Duration
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
10. Resources
Number of activities that do not have resources/costs assigned
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
11. Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
Remaining Work
Calculation of total remaining work for all activities within a grouping
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
Missing Resources
Number of activities that are not carrying resources
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Resources
Number of activities that are carrying resources
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
Critical
Number of critical activities
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Soft Constraints
Number of activities with soft or one-way constraints.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Rem. Critical Duration
The amount of remaining time planned in order to complete all critical normal activities and milestones within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File | 2874 | 611 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 79 | 0
FALSE |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File | 2874 | 1132 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 61 | 0
FALSE |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File | 2873 | 911 | 2017-06-07 | 2028-09-27 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 68 | 1
FALSE |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File | 1928 | 315 | 2019-04-01 | 2026-11-10 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 84 | 488
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File | 1454 | 263 | 2021-01-04 | 2026-10-05 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 82 | 514
FALSE |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File | 1390 | 288 | 2021-04-05 | 2026-10-05 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 79 | 514
FALSE |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File | 1198 | 222 | 2022-01-06 | 2026-10-05 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 82 | 514
FALSE |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File | 1144 | 274 | 2022-03-07 | 2026-09-16 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 76 | 526
FALSE |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File | 1134 | 264 | 2022-04-04 | 2026-09-29 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 77 | 512
FALSE |  | 6297 | AqdIsKbIPOfZJkjKYjnG | Large Test File | 928 | 118 | 2022-12-21 | 2026-08-26 | 2022-11-15 | 2026-08-26 | Summary | InProgress | 87 | 539
FALSE |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File | 931 | 163 | 2023-01-03 | 2026-09-10 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 83 | 530
FALSE |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 85 | -26
FALSE |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 85 | -26
FALSE |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File | 975 | 288 | 2023-02-23 | 2027-01-07 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 70 | 450
FALSE |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 17 | 30
FALSE |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File | 972 | 309 | 2023-03-06 | 2027-01-01 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 68 | 455
FALSE |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File | 823 | 172 | 2023-08-04 | 2026-11-10 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 79 | 488
FALSE |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File | 800 | 552 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 31 | 510
FALSE |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File | 800 | 277 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2025-05-30 | Summary | InProgress | 65 | -26
FALSE |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File | 860 | 297 | 2023-08-07 | 2027-01-07 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 65 | 450
FALSE |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File | 760 | 466 | 2023-09-05 | 2026-09-10 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 39 | 530
FALSE |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File | 712 | 322 | 2023-09-05 | 2026-07-02 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 55 | 530
FALSE |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File | 808 | 0 | 2023-10-12 | 2027-01-01 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 99 | 454
FALSE |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File | 703 | 703 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 0 | 19
FALSE |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File | 739 | 554 | 2023-10-18 | 2026-09-25 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 25 | 512
FALSE |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File | 655 | 255 | 2024-03-04 | 2026-10-08 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 61 | 510
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File | 571 | 554 | 2024-08-01 | 2026-11-10 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 3 | 488
FALSE |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 325
FALSE |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 325
FALSE |  | 7388 | subTjNOw9tjXphx2xXzW | Large Test File | 324 | 324 | 2025-06-18 | 2026-10-02 | 2025-06-18 | 2026-10-02 | Summary | Planned | 0 | 514
FALSE |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File | 276 | 276 | 2025-06-23 | 2026-07-31 | 2024-09-26 | 2026-01-30 | Summary | Planned | 0 | 514
FALSE |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File | 272 | 272 | 2025-06-27 | 2026-07-29 | 2025-06-27 | 2026-01-23 | Summary | Planned | 0 | 24
FALSE |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File | 319 | 319 | 2025-10-07 | 2027-01-01 | 2025-06-24 | 2026-08-14 | Summary | Planned | 0 | 80
FALSE |  | 5277 | TgmqG1sR4A60sNmMtPcE | Large Test File | 193 | 193 | 2025-10-07 | 2026-07-09 | 2024-04-30 | 2024-10-04 | Summary | Planned | 0 | -28
FALSE |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File | 144 | 144 | 2026-01-15 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 0 | 11
FALSE |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File | 126 | 126 | 2026-04-01 | 2026-09-29 | 2026-01-07 | 2026-07-07 | Summary | Planned | 0 | 512
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4538 | aTyUglf0WPX6H8Zd17Iq | Large Test File | 71 | 71 | 2026-04-20 | 2026-07-31 | 2025-12-18 | 2026-07-03 | Summary | Planned | 0 | 514
FALSE |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File | 127 | 127 | 2026-04-23 | 2026-10-23 | 2025-06-26 | 2025-11-11 | Summary | Planned | 0 | 488
FALSE |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File | 160 | 160 | 2026-05-15 | 2027-01-07 | 2026-04-07 | 2026-07-27 | Summary | Planned | 0 | 450
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4140 | Lk7gef35zB3WaxM8Xyxe | Large Test File | 48 | 48 | 2026-07-06 | 2026-09-10 | 2025-09-11 | 2026-01-13 | Summary | Planned | 0 | 530
FALSE |  | 4141 | HGo5Ep3pqhcsiM5K4QjA | Large Test File | 23 | 23 | 2026-07-06 | 2026-08-05 | 2025-09-11 | 2025-10-13 | Summary | Planned | 0 | 530
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7435 | nSo6tYchIu2Aw4YtE45u | Large Test File | 44 | 44 | 2026-07-31 | 2026-10-02 | 2026-07-31 | 2026-10-02 | Summary | Planned | 0 | 514
FALSE |  | 7436 | Y83lvWkQwfsc3dMGwfVN | Large Test File | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE |  | 7437 | E8EwVgjFQaEPGP66WsCb | Large Test File | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7441 | IcgrxiRjEYJLwuugm8N7 | Large Test File | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File | 106 | 106 | 2026-08-05 | 2027-01-01 | 2026-05-01 | 2026-08-14 | Summary | Planned | 0 | 455
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4144 | zaFQ6K5wegGvKt6DGuoz | Large Test File | 25 | 25 | 2026-08-06 | 2026-09-10 | 2025-10-14 | 2026-01-13 | Summary | Planned | 0 | 530
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7446 | NnBZUSVumxDXwVdCLN8g | Large Test File | 12 | 12 | 2026-09-14 | 2026-09-30 | 2026-09-14 | 2026-09-30 | Summary | Planned | 0 | 514
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 4590 | 21lrGsmJiPqRYOd4yY3H | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Summary | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File | 37 | 37 | 2026-09-18 | 2026-11-10 | 2025-10-08 | 2026-01-23 | Summary | Planned | 0 | 488
FALSE |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File | 32 | 32 | 2026-09-18 | 2026-11-03 | 2025-10-08 | 2025-12-17 | Summary | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Summary | Planned | 0 | 510
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4059 | sH9kz6O2EFda2hu4x8Kx | Large Test File | 12 | 12 | 2026-10-26 | 2026-11-10 | 2025-11-12 | 2026-01-16 | Summary | Planned | 0 | 488
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4054 | WhXMUGkGRid5sulqMW8S | Large Test File | 5 | 5 | 2026-11-04 | 2026-11-10 | 2025-12-18 | 2026-01-23 | Summary | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Longest Path
Activities that together form the longest path through to project completion.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Forecast to be Finished
Forecast to be finished before time now
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Project Time Now | Type | Status | Percent Complete
5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 2026-06-25 | 2024-09-20 | 2026-07-02 | 2024-09-27 | 2025-02-07 | Normal | Planned | 0
5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 2026-07-02 | 2024-09-27 | 2026-07-09 | 2024-10-04 | 2025-02-07 | Normal | Planned | 0
5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 2026-07-20 | 2024-05-03 | 2026-07-21 | 2024-05-03 | 2025-02-07 | Normal | Planned | 0
5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 2026-07-30 | 2024-12-26 | 2026-10-08 | 2025-01-24 | 2025-02-07 | Normal | Planned | 0
Not Completed
Activities that were planned to be complete by now that are not complete.
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Type | Activity Status
5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 2026-06-25 | 2024-09-20 | 2026-07-02 | 2024-09-27 | Normal | Planned
5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 2026-07-02 | 2024-09-27 | 2026-07-09 | 2024-10-04 | Normal | Planned
5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 2026-07-20 | 2024-05-03 | 2026-07-21 | 2024-05-03 | Normal | Planned
5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 2026-07-30 | 2024-12-26 | 2026-10-08 | 2025-01-24 | Normal | Planned
Baseline Finish Compliance
Percentage of those activities forecast to be finished before time now that were finished on time.
Id | Description | Project | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Project Time Now | Type | Status | Percent Complete
5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | 2025-02-07 | Normal | Planned | 0
5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | 2025-02-07 | Normal | Planned | 0
5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | 2025-02-07 | Normal | Planned | 0
5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | 2025-02-07 | Normal | Planned | 0
Forecast to be Started
Forecast to be started before time now
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Project Time Now | Type | Status | Percent Complete
7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 396 | 2019-04-15 | 2019-04-15 | 2026-09-08 | 2026-09-04 | 2025-02-07 | Normal | InProgress | 79
6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 396 | 2024-06-03 | 2024-06-03 | 2026-09-08 | 2025-11-25 | 2025-02-07 | Normal | InProgress | 30
6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 396 | 2024-06-03 | 2024-06-03 | 2026-09-08 | 2025-11-21 | 2025-02-07 | Normal | InProgress | 30
5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 2026-06-25 | 2024-09-20 | 2026-07-02 | 2024-09-27 | 2025-02-07 | Normal | Planned | 0
5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 2026-07-02 | 2024-09-27 | 2026-07-09 | 2024-10-04 | 2025-02-07 | Normal | Planned | 0
5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 2026-07-20 | 2024-05-03 | 2026-07-21 | 2024-05-03 | 2025-02-07 | Normal | Planned | 0
5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 2026-07-30 | 2024-12-26 | 2026-10-08 | 2025-01-24 | 2025-02-07 | Normal | Planned | 0
Started On Time
Activities actually started on time, by their baseline start date.
Id | Description | Project | Start | Baseline Start | Finish | Baseline Finish | Type | Status
7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 2019-04-15 | 2019-04-15 | 2026-09-08 | 2026-09-04 | Normal | InProgress
6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 2024-06-03 | 2024-06-03 | 2026-09-08 | 2025-11-25 | Normal | InProgress
6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 2024-06-03 | 2024-06-03 | 2026-09-08 | 2025-11-21 | Normal | InProgress
Not Started
Activities that were planned to be start by now that are not started.
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Type | Activity Status
5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 2026-06-25 | 2024-09-20 | 2026-07-02 | 2024-09-27 | Normal | Planned
5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 2026-07-02 | 2024-09-27 | 2026-07-09 | 2024-10-04 | Normal | Planned
5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 2026-07-20 | 2024-05-03 | 2026-07-21 | 2024-05-03 | Normal | Planned
5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 2026-07-30 | 2024-12-26 | 2026-10-08 | 2025-01-24 | Normal | Planned
Baseline Start Compliance
Percentage of those activities forecast to be started before time now that were started on time.
Id | Description | Project | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Project Time Now | Type | Status | Percent Complete
5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | 2025-02-07 | Normal | Planned | 0
5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | 2025-02-07 | Normal | Planned | 0
5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | 2025-02-07 | Normal | Planned | 0
5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | 2025-02-07 | Normal | Planned | 0
In-Progress On Schedule
Number of activities that are currently underway and started on time.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
Actually Started
Total number of activities that have started.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
Planned Delayed
Number of activities that are currently planned to start after their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Planned On Schedule
Number of activities that are planned to start on time.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
Scheduled to Start
Number of activities that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Scheduled to Finish
Number of activities within that are planned to finish.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Underway
Number of activities that are in-progress.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
Planned
Number of activities that have yet to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Planned Milestones
Number of milestones that are planned but not yet in-progress or complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Not Completed
Total number of activities that have not been completed.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Negative Float
Number of activities with total float of less than 0 working days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
20 to 30 days float
Total number of activities with positive float of more than 20 and less than or equal to 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
Total Activities
The total number of activities within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File | 2874 | 611 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 79 | 0
FALSE |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File | 2874 | 1132 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 61 | 0
FALSE |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File | 2873 | 911 | 2017-06-07 | 2028-09-27 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 68 | 1
FALSE |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File | 1928 | 315 | 2019-04-01 | 2026-11-10 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 84 | 488
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File | 1454 | 263 | 2021-01-04 | 2026-10-05 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 82 | 514
FALSE |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File | 1390 | 288 | 2021-04-05 | 2026-10-05 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 79 | 514
FALSE |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File | 1198 | 222 | 2022-01-06 | 2026-10-05 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 82 | 514
FALSE |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File | 1144 | 274 | 2022-03-07 | 2026-09-16 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 76 | 526
FALSE |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File | 1134 | 264 | 2022-04-04 | 2026-09-29 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 77 | 512
FALSE |  | 6297 | AqdIsKbIPOfZJkjKYjnG | Large Test File | 928 | 118 | 2022-12-21 | 2026-08-26 | 2022-11-15 | 2026-08-26 | Summary | InProgress | 87 | 539
FALSE |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File | 931 | 163 | 2023-01-03 | 2026-09-10 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 83 | 530
FALSE |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 85 | -26
FALSE |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 85 | -26
FALSE |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File | 975 | 288 | 2023-02-23 | 2027-01-07 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 70 | 450
FALSE |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 17 | 30
FALSE |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File | 972 | 309 | 2023-03-06 | 2027-01-01 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 68 | 455
FALSE |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File | 823 | 172 | 2023-08-04 | 2026-11-10 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 79 | 488
FALSE |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File | 800 | 552 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 31 | 510
FALSE |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File | 800 | 277 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2025-05-30 | Summary | InProgress | 65 | -26
FALSE |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File | 860 | 297 | 2023-08-07 | 2027-01-07 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 65 | 450
FALSE |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File | 760 | 466 | 2023-09-05 | 2026-09-10 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 39 | 530
FALSE |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File | 712 | 322 | 2023-09-05 | 2026-07-02 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 55 | 530
FALSE |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File | 808 | 0 | 2023-10-12 | 2027-01-01 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 99 | 454
FALSE |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File | 703 | 703 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 0 | 19
FALSE |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File | 739 | 554 | 2023-10-18 | 2026-09-25 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 25 | 512
FALSE |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File | 655 | 255 | 2024-03-04 | 2026-10-08 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 61 | 510
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File | 571 | 554 | 2024-08-01 | 2026-11-10 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 3 | 488
FALSE |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 325
FALSE |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 325
FALSE |  | 7388 | subTjNOw9tjXphx2xXzW | Large Test File | 324 | 324 | 2025-06-18 | 2026-10-02 | 2025-06-18 | 2026-10-02 | Summary | Planned | 0 | 514
FALSE |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File | 276 | 276 | 2025-06-23 | 2026-07-31 | 2024-09-26 | 2026-01-30 | Summary | Planned | 0 | 514
FALSE |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File | 272 | 272 | 2025-06-27 | 2026-07-29 | 2025-06-27 | 2026-01-23 | Summary | Planned | 0 | 24
FALSE |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File | 319 | 319 | 2025-10-07 | 2027-01-01 | 2025-06-24 | 2026-08-14 | Summary | Planned | 0 | 80
FALSE |  | 5277 | TgmqG1sR4A60sNmMtPcE | Large Test File | 193 | 193 | 2025-10-07 | 2026-07-09 | 2024-04-30 | 2024-10-04 | Summary | Planned | 0 | -28
FALSE |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File | 144 | 144 | 2026-01-15 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 0 | 11
FALSE |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File | 126 | 126 | 2026-04-01 | 2026-09-29 | 2026-01-07 | 2026-07-07 | Summary | Planned | 0 | 512
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4538 | aTyUglf0WPX6H8Zd17Iq | Large Test File | 71 | 71 | 2026-04-20 | 2026-07-31 | 2025-12-18 | 2026-07-03 | Summary | Planned | 0 | 514
FALSE |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File | 127 | 127 | 2026-04-23 | 2026-10-23 | 2025-06-26 | 2025-11-11 | Summary | Planned | 0 | 488
FALSE |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File | 160 | 160 | 2026-05-15 | 2027-01-07 | 2026-04-07 | 2026-07-27 | Summary | Planned | 0 | 450
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4140 | Lk7gef35zB3WaxM8Xyxe | Large Test File | 48 | 48 | 2026-07-06 | 2026-09-10 | 2025-09-11 | 2026-01-13 | Summary | Planned | 0 | 530
FALSE |  | 4141 | HGo5Ep3pqhcsiM5K4QjA | Large Test File | 23 | 23 | 2026-07-06 | 2026-08-05 | 2025-09-11 | 2025-10-13 | Summary | Planned | 0 | 530
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7435 | nSo6tYchIu2Aw4YtE45u | Large Test File | 44 | 44 | 2026-07-31 | 2026-10-02 | 2026-07-31 | 2026-10-02 | Summary | Planned | 0 | 514
FALSE |  | 7436 | Y83lvWkQwfsc3dMGwfVN | Large Test File | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE |  | 7437 | E8EwVgjFQaEPGP66WsCb | Large Test File | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7441 | IcgrxiRjEYJLwuugm8N7 | Large Test File | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File | 106 | 106 | 2026-08-05 | 2027-01-01 | 2026-05-01 | 2026-08-14 | Summary | Planned | 0 | 455
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4144 | zaFQ6K5wegGvKt6DGuoz | Large Test File | 25 | 25 | 2026-08-06 | 2026-09-10 | 2025-10-14 | 2026-01-13 | Summary | Planned | 0 | 530
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7446 | NnBZUSVumxDXwVdCLN8g | Large Test File | 12 | 12 | 2026-09-14 | 2026-09-30 | 2026-09-14 | 2026-09-30 | Summary | Planned | 0 | 514
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 4590 | 21lrGsmJiPqRYOd4yY3H | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Summary | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File | 37 | 37 | 2026-09-18 | 2026-11-10 | 2025-10-08 | 2026-01-23 | Summary | Planned | 0 | 488
FALSE |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File | 32 | 32 | 2026-09-18 | 2026-11-03 | 2025-10-08 | 2025-12-17 | Summary | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Summary | Planned | 0 | 510
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4059 | sH9kz6O2EFda2hu4x8Kx | Large Test File | 12 | 12 | 2026-10-26 | 2026-11-10 | 2025-11-12 | 2026-01-16 | Summary | Planned | 0 | 488
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4054 | WhXMUGkGRid5sulqMW8S | Large Test File | 5 | 5 | 2026-11-04 | 2026-11-10 | 2025-12-18 | 2026-01-23 | Summary | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Milestones
Number of milestones within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Normal
Number of normal activities within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Summaries
Number of summary activities within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File | 2874 | 611 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 79 | 0
FALSE |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File | 2874 | 1132 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 61 | 0
FALSE |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File | 2873 | 911 | 2017-06-07 | 2028-09-27 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 68 | 1
FALSE |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File | 1928 | 315 | 2019-04-01 | 2026-11-10 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 84 | 488
FALSE |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File | 1454 | 263 | 2021-01-04 | 2026-10-05 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 82 | 514
FALSE |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File | 1390 | 288 | 2021-04-05 | 2026-10-05 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 79 | 514
FALSE |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File | 1198 | 222 | 2022-01-06 | 2026-10-05 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 82 | 514
FALSE |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File | 1144 | 274 | 2022-03-07 | 2026-09-16 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 76 | 526
FALSE |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File | 1134 | 264 | 2022-04-04 | 2026-09-29 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 77 | 512
FALSE |  | 6297 | AqdIsKbIPOfZJkjKYjnG | Large Test File | 928 | 118 | 2022-12-21 | 2026-08-26 | 2022-11-15 | 2026-08-26 | Summary | InProgress | 87 | 539
FALSE |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File | 931 | 163 | 2023-01-03 | 2026-09-10 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 83 | 530
FALSE |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 85 | -26
FALSE |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 85 | -26
FALSE |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File | 975 | 288 | 2023-02-23 | 2027-01-07 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 70 | 450
FALSE |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 17 | 30
FALSE |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File | 972 | 309 | 2023-03-06 | 2027-01-01 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 68 | 455
FALSE |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File | 823 | 172 | 2023-08-04 | 2026-11-10 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 79 | 488
FALSE |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File | 800 | 552 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 31 | 510
FALSE |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File | 800 | 277 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2025-05-30 | Summary | InProgress | 65 | -26
FALSE |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File | 860 | 297 | 2023-08-07 | 2027-01-07 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 65 | 450
FALSE |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File | 760 | 466 | 2023-09-05 | 2026-09-10 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 39 | 530
FALSE |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File | 712 | 322 | 2023-09-05 | 2026-07-02 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 55 | 530
FALSE |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File | 808 | 0 | 2023-10-12 | 2027-01-01 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 99 | 454
FALSE |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File | 703 | 703 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 0 | 19
FALSE |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File | 739 | 554 | 2023-10-18 | 2026-09-25 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 25 | 512
FALSE |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File | 655 | 255 | 2024-03-04 | 2026-10-08 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 61 | 510
FALSE |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File | 571 | 554 | 2024-08-01 | 2026-11-10 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 3 | 488
FALSE |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 325
FALSE |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 325
FALSE |  | 7388 | subTjNOw9tjXphx2xXzW | Large Test File | 324 | 324 | 2025-06-18 | 2026-10-02 | 2025-06-18 | 2026-10-02 | Summary | Planned | 0 | 514
FALSE |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File | 276 | 276 | 2025-06-23 | 2026-07-31 | 2024-09-26 | 2026-01-30 | Summary | Planned | 0 | 514
FALSE |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File | 272 | 272 | 2025-06-27 | 2026-07-29 | 2025-06-27 | 2026-01-23 | Summary | Planned | 0 | 24
FALSE |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File | 319 | 319 | 2025-10-07 | 2027-01-01 | 2025-06-24 | 2026-08-14 | Summary | Planned | 0 | 80
FALSE |  | 5277 | TgmqG1sR4A60sNmMtPcE | Large Test File | 193 | 193 | 2025-10-07 | 2026-07-09 | 2024-04-30 | 2024-10-04 | Summary | Planned | 0 | -28
FALSE |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File | 144 | 144 | 2026-01-15 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 0 | 11
FALSE |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File | 126 | 126 | 2026-04-01 | 2026-09-29 | 2026-01-07 | 2026-07-07 | Summary | Planned | 0 | 512
FALSE |  | 4538 | aTyUglf0WPX6H8Zd17Iq | Large Test File | 71 | 71 | 2026-04-20 | 2026-07-31 | 2025-12-18 | 2026-07-03 | Summary | Planned | 0 | 514
FALSE |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File | 127 | 127 | 2026-04-23 | 2026-10-23 | 2025-06-26 | 2025-11-11 | Summary | Planned | 0 | 488
FALSE |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File | 160 | 160 | 2026-05-15 | 2027-01-07 | 2026-04-07 | 2026-07-27 | Summary | Planned | 0 | 450
FALSE |  | 4140 | Lk7gef35zB3WaxM8Xyxe | Large Test File | 48 | 48 | 2026-07-06 | 2026-09-10 | 2025-09-11 | 2026-01-13 | Summary | Planned | 0 | 530
FALSE |  | 4141 | HGo5Ep3pqhcsiM5K4QjA | Large Test File | 23 | 23 | 2026-07-06 | 2026-08-05 | 2025-09-11 | 2025-10-13 | Summary | Planned | 0 | 530
FALSE |  | 7435 | nSo6tYchIu2Aw4YtE45u | Large Test File | 44 | 44 | 2026-07-31 | 2026-10-02 | 2026-07-31 | 2026-10-02 | Summary | Planned | 0 | 514
FALSE |  | 7436 | Y83lvWkQwfsc3dMGwfVN | Large Test File | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE |  | 7437 | E8EwVgjFQaEPGP66WsCb | Large Test File | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE |  | 7441 | IcgrxiRjEYJLwuugm8N7 | Large Test File | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File | 106 | 106 | 2026-08-05 | 2027-01-01 | 2026-05-01 | 2026-08-14 | Summary | Planned | 0 | 455
FALSE |  | 4144 | zaFQ6K5wegGvKt6DGuoz | Large Test File | 25 | 25 | 2026-08-06 | 2026-09-10 | 2025-10-14 | 2026-01-13 | Summary | Planned | 0 | 530
FALSE |  | 7446 | NnBZUSVumxDXwVdCLN8g | Large Test File | 12 | 12 | 2026-09-14 | 2026-09-30 | 2026-09-14 | 2026-09-30 | Summary | Planned | 0 | 514
FALSE |  | 4590 | 21lrGsmJiPqRYOd4yY3H | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Summary | Planned | 0 | 514
FALSE |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File | 37 | 37 | 2026-09-18 | 2026-11-10 | 2025-10-08 | 2026-01-23 | Summary | Planned | 0 | 488
FALSE |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File | 32 | 32 | 2026-09-18 | 2026-11-03 | 2025-10-08 | 2025-12-17 | Summary | Planned | 0 | 488
FALSE |  | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Summary | Planned | 0 | 510
FALSE |  | 4059 | sH9kz6O2EFda2hu4x8Kx | Large Test File | 12 | 12 | 2026-10-26 | 2026-11-10 | 2025-11-12 | 2026-01-16 | Summary | Planned | 0 | 488
FALSE |  | 4054 | WhXMUGkGRid5sulqMW8S | Large Test File | 5 | 5 | 2026-11-04 | 2026-11-10 | 2025-12-18 | 2026-01-23 | Summary | Planned | 0 | 488
Longest Path
Activities that together form the longest path through to project completion.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Critical
Number of critical activities
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Insufficient Detail™
Number of activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Notes | Id | Description | Project | Original Duration | Number of Predecessors | Number of Successors | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 3 | 2 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 3 | 3 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 9 | 1 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 10 | 1 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 3 | 2 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 3 | 1 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 1 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 3 | 1 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 15 | 1 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 8 | 2 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 137 | 5 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 4 | 3 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Longest Path (Normal Tasks)
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
Longest Path (Tasks & Milestones)
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE |  | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE |  | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26
Critical Milestones (To-Go)
Number of critical milestones to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE | TRUE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Longest Path (Milestones)
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE |  | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE |  | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE |  | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26
Normal Tasks
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 79 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | Aspose.Tasks.Calendar | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 532
FALSE |  | 30 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 532
FALSE |  | 30 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 532
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE |  | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE |  | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE |  | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE |  | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE |  | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE |  | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE |  | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE |  | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE |  | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE |  | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE |  | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE |  | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE |  | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE |  | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE |  | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE |  | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE |  | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE |  | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE |  | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE |  | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE |  | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE |  | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE |  | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE |  | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE |  | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE |  | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE |  | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE |  | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE |  | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE |  | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE |  | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
Normal Tasks (To-Go)
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 79 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | Aspose.Tasks.Calendar | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 532
FALSE |  | 30 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 532
FALSE |  | 30 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 532
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE |  | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE |  | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE |  | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE |  | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE |  | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE |  | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE |  | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE |  | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE |  | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE |  | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE |  | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE |  | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE |  | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE |  | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE |  | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE |  | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE |  | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE |  | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE |  | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE |  | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE |  | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE |  | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE |  | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE |  | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE |  | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE |  | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE |  | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE |  | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE |  | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE |  | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE |  | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
Critical Tasks (To-Go)
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
CP - Float Ratio™
Average float divided by average remaining duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE | FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE | FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE | FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE | FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE | FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE | FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE | FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE | FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE | FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE | FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE | FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE | FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE | FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE | FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
High Float 44d
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE | FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE | FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE | FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE | FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE | FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE | FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE | FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE | FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE | FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE | FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE | FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE | FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE | FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE | FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
Critical Logic Hotspot™
Number of activities with a high number of predecessors as well as a high number of successors.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 3 | TRUE | -26 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE | 137 | 5 | TRUE | -26 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0
FALSE | 4 | 3 | TRUE | -26 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0
Critical Merge Hotspot
The total number of activities with a high number of predecessor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 3 | 0 | 0 | 0 | TRUE | -26 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE | 137 | 5 | 0 | 0 | 0 | TRUE | -26 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0
FALSE | 4 | 3 | 0 | 0 | 0 | TRUE | -26 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0
Critical Diverge Hotspot
Number of activities with a high number of successor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Successor Leads | Number of Successor Lags | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 3 | 0 | 0 | TRUE | -28 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0
FALSE | 3 | 3 | 0 | 0 | TRUE | -26 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE | 1 | 4 | 0 | 0 | TRUE | -27 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0
FALSE | 137 | 5 | 0 | 0 | TRUE | -26 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0
FALSE | 4 | 3 | 0 | 0 | TRUE | -26 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0
Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
BEI - Total Milestones
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
BEI - Incomplete Milestones
The total number (cumulative) of milestones that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
Longest Path - Critical Activities and Milestones
Activities that together form the longest path through to project completion. (Number of critical activities.)
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Critical Milestones (To-Go)
Number of critical milestones to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE | TRUE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Critical Tasks (To-Go)
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Float Ratio™
Average float divided by average remaining duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File | 2874 | 611 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 79 | 0
FALSE |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File | 2874 | 1132 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 61 | 0
FALSE |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File | 2873 | 911 | 2017-06-07 | 2028-09-27 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 68 | 1
FALSE |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File | 1928 | 315 | 2019-04-01 | 2026-11-10 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 84 | 488
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File | 1454 | 263 | 2021-01-04 | 2026-10-05 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 82 | 514
FALSE |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File | 1390 | 288 | 2021-04-05 | 2026-10-05 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 79 | 514
FALSE |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File | 1198 | 222 | 2022-01-06 | 2026-10-05 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 82 | 514
FALSE |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File | 1144 | 274 | 2022-03-07 | 2026-09-16 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 76 | 526
FALSE |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File | 1134 | 264 | 2022-04-04 | 2026-09-29 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 77 | 512
FALSE |  | 6297 | AqdIsKbIPOfZJkjKYjnG | Large Test File | 928 | 118 | 2022-12-21 | 2026-08-26 | 2022-11-15 | 2026-08-26 | Summary | InProgress | 87 | 539
FALSE |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File | 931 | 163 | 2023-01-03 | 2026-09-10 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 83 | 530
FALSE |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 85 | -26
FALSE |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 85 | -26
FALSE |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File | 975 | 288 | 2023-02-23 | 2027-01-07 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 70 | 450
FALSE |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 17 | 30
FALSE |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File | 972 | 309 | 2023-03-06 | 2027-01-01 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 68 | 455
FALSE |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File | 823 | 172 | 2023-08-04 | 2026-11-10 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 79 | 488
FALSE |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File | 800 | 552 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 31 | 510
FALSE |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File | 800 | 277 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2025-05-30 | Summary | InProgress | 65 | -26
FALSE |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File | 860 | 297 | 2023-08-07 | 2027-01-07 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 65 | 450
FALSE |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File | 760 | 466 | 2023-09-05 | 2026-09-10 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 39 | 530
FALSE |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File | 712 | 322 | 2023-09-05 | 2026-07-02 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 55 | 530
FALSE |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File | 808 | 0 | 2023-10-12 | 2027-01-01 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 99 | 454
FALSE |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File | 703 | 703 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 0 | 19
FALSE |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File | 739 | 554 | 2023-10-18 | 2026-09-25 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 25 | 512
FALSE |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File | 655 | 255 | 2024-03-04 | 2026-10-08 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 61 | 510
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File | 571 | 554 | 2024-08-01 | 2026-11-10 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 3 | 488
FALSE |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 325
FALSE |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 325
FALSE |  | 7388 | subTjNOw9tjXphx2xXzW | Large Test File | 324 | 324 | 2025-06-18 | 2026-10-02 | 2025-06-18 | 2026-10-02 | Summary | Planned | 0 | 514
FALSE |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File | 276 | 276 | 2025-06-23 | 2026-07-31 | 2024-09-26 | 2026-01-30 | Summary | Planned | 0 | 514
FALSE |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File | 272 | 272 | 2025-06-27 | 2026-07-29 | 2025-06-27 | 2026-01-23 | Summary | Planned | 0 | 24
FALSE |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File | 319 | 319 | 2025-10-07 | 2027-01-01 | 2025-06-24 | 2026-08-14 | Summary | Planned | 0 | 80
FALSE |  | 5277 | TgmqG1sR4A60sNmMtPcE | Large Test File | 193 | 193 | 2025-10-07 | 2026-07-09 | 2024-04-30 | 2024-10-04 | Summary | Planned | 0 | -28
FALSE |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File | 144 | 144 | 2026-01-15 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 0 | 11
FALSE |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File | 126 | 126 | 2026-04-01 | 2026-09-29 | 2026-01-07 | 2026-07-07 | Summary | Planned | 0 | 512
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4538 | aTyUglf0WPX6H8Zd17Iq | Large Test File | 71 | 71 | 2026-04-20 | 2026-07-31 | 2025-12-18 | 2026-07-03 | Summary | Planned | 0 | 514
FALSE |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File | 127 | 127 | 2026-04-23 | 2026-10-23 | 2025-06-26 | 2025-11-11 | Summary | Planned | 0 | 488
FALSE |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File | 160 | 160 | 2026-05-15 | 2027-01-07 | 2026-04-07 | 2026-07-27 | Summary | Planned | 0 | 450
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4140 | Lk7gef35zB3WaxM8Xyxe | Large Test File | 48 | 48 | 2026-07-06 | 2026-09-10 | 2025-09-11 | 2026-01-13 | Summary | Planned | 0 | 530
FALSE |  | 4141 | HGo5Ep3pqhcsiM5K4QjA | Large Test File | 23 | 23 | 2026-07-06 | 2026-08-05 | 2025-09-11 | 2025-10-13 | Summary | Planned | 0 | 530
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7435 | nSo6tYchIu2Aw4YtE45u | Large Test File | 44 | 44 | 2026-07-31 | 2026-10-02 | 2026-07-31 | 2026-10-02 | Summary | Planned | 0 | 514
FALSE |  | 7436 | Y83lvWkQwfsc3dMGwfVN | Large Test File | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE |  | 7437 | E8EwVgjFQaEPGP66WsCb | Large Test File | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7441 | IcgrxiRjEYJLwuugm8N7 | Large Test File | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File | 106 | 106 | 2026-08-05 | 2027-01-01 | 2026-05-01 | 2026-08-14 | Summary | Planned | 0 | 455
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4144 | zaFQ6K5wegGvKt6DGuoz | Large Test File | 25 | 25 | 2026-08-06 | 2026-09-10 | 2025-10-14 | 2026-01-13 | Summary | Planned | 0 | 530
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7446 | NnBZUSVumxDXwVdCLN8g | Large Test File | 12 | 12 | 2026-09-14 | 2026-09-30 | 2026-09-14 | 2026-09-30 | Summary | Planned | 0 | 514
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 4590 | 21lrGsmJiPqRYOd4yY3H | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Summary | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File | 37 | 37 | 2026-09-18 | 2026-11-10 | 2025-10-08 | 2026-01-23 | Summary | Planned | 0 | 488
FALSE |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File | 32 | 32 | 2026-09-18 | 2026-11-03 | 2025-10-08 | 2025-12-17 | Summary | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Summary | Planned | 0 | 510
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4059 | sH9kz6O2EFda2hu4x8Kx | Large Test File | 12 | 12 | 2026-10-26 | 2026-11-10 | 2025-11-12 | 2026-01-16 | Summary | Planned | 0 | 488
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4054 | WhXMUGkGRid5sulqMW8S | Large Test File | 5 | 5 | 2026-11-04 | 2026-11-10 | 2025-12-18 | 2026-01-23 | Summary | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
CP - Float Ratio™
Average float divided by average remaining duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
Critical w/High Baseline Duration (44d)
Total number of critical activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Critical | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File | 2875 | 2874 | 611 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 79 | 0
FALSE | TRUE |  |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File | 2388 | 2874 | 1132 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 61 | 0
FALSE | FALSE |  |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File | 2478 | 2873 | 911 | 2017-06-07 | 2028-09-27 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 68 | 1
FALSE | FALSE |  |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File | 1877 | 1928 | 315 | 2019-04-01 | 2026-11-10 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 84 | 488
FALSE | FALSE |  |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE | FALSE |  |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File | 1454 | 1454 | 263 | 2021-01-04 | 2026-10-05 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 82 | 514
FALSE | FALSE |  |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File | 1410 | 1390 | 288 | 2021-04-05 | 2026-10-05 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 79 | 514
FALSE | FALSE |  |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File | 1185 | 1198 | 222 | 2022-01-06 | 2026-10-05 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 82 | 514
FALSE | FALSE |  |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File | 1125 | 1144 | 274 | 2022-03-07 | 2026-09-16 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 76 | 526
FALSE | FALSE |  |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File | 1189 | 1134 | 264 | 2022-04-04 | 2026-09-29 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 77 | 512
FALSE | FALSE |  |  | 6297 | AqdIsKbIPOfZJkjKYjnG | Large Test File | 954 | 928 | 118 | 2022-12-21 | 2026-08-26 | 2022-11-15 | 2026-08-26 | Summary | InProgress | 87 | 539
FALSE | FALSE |  |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File | 621 | 931 | 163 | 2023-01-03 | 2026-09-10 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 83 | 530
FALSE | TRUE |  |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File | 516 | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 85 | -26
FALSE | TRUE |  |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File | 516 | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 85 | -26
FALSE | FALSE |  |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File | 906 | 975 | 288 | 2023-02-23 | 2027-01-07 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 70 | 450
FALSE | FALSE |  |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File | 402 | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 17 | 30
FALSE | FALSE |  |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File | 873 | 972 | 309 | 2023-03-06 | 2027-01-01 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 68 | 455
FALSE | FALSE |  |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File | 632 | 823 | 172 | 2023-08-04 | 2026-11-10 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 79 | 488
FALSE | FALSE |  |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File | 775 | 800 | 552 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 31 | 510
FALSE | TRUE |  |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File | 462 | 800 | 277 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2025-05-30 | Summary | InProgress | 65 | -26
FALSE | FALSE |  |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File | 748 | 860 | 297 | 2023-08-07 | 2027-01-07 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 65 | 450
FALSE | FALSE |  |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File | 137 | 760 | 466 | 2023-09-05 | 2026-09-10 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 39 | 530
FALSE | FALSE |  |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File | 51 | 712 | 322 | 2023-09-05 | 2026-07-02 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 55 | 530
FALSE | FALSE |  |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File | 688 | 808 | 0 | 2023-10-12 | 2027-01-01 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 99 | 454
FALSE | FALSE |  |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File | 190 | 703 | 703 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 0 | 19
FALSE | FALSE |  |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File | 396 | 739 | 554 | 2023-10-18 | 2026-09-25 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 25 | 512
FALSE | FALSE |  |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File | 512 | 655 | 255 | 2024-03-04 | 2026-10-08 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 61 | 510
FALSE | FALSE |  |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 378 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE | FALSE |  |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 376 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE | FALSE |  |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File | 375 | 571 | 554 | 2024-08-01 | 2026-11-10 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 3 | 488
FALSE | FALSE |  |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File | 366 | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 325
FALSE | FALSE |  |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File | 366 | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 325
FALSE | FALSE |  |  | 7388 | subTjNOw9tjXphx2xXzW | Large Test File | 324 | 324 | 324 | 2025-06-18 | 2026-10-02 | 2025-06-18 | 2026-10-02 | Summary | Planned | 0 | 514
FALSE | FALSE |  |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File | 340 | 276 | 276 | 2025-06-23 | 2026-07-31 | 2024-09-26 | 2026-01-30 | Summary | Planned | 0 | 514
FALSE | FALSE |  |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File | 145 | 272 | 272 | 2025-06-27 | 2026-07-29 | 2025-06-27 | 2026-01-23 | Summary | Planned | 0 | 24
FALSE | FALSE |  |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File | 293 | 319 | 319 | 2025-10-07 | 2027-01-01 | 2025-06-24 | 2026-08-14 | Summary | Planned | 0 | 80
FALSE | TRUE |  |  | 5277 | TgmqG1sR4A60sNmMtPcE | Large Test File | 111 | 193 | 193 | 2025-10-07 | 2026-07-09 | 2024-04-30 | 2024-10-04 | Summary | Planned | 0 | -28
FALSE | FALSE |  |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File | 105 | 144 | 144 | 2026-01-15 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 0 | 11
FALSE | FALSE |  |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File | 126 | 126 | 126 | 2026-04-01 | 2026-09-29 | 2026-01-07 | 2026-07-07 | Summary | Planned | 0 | 512
FALSE | FALSE |  |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE | FALSE |  |  | 4538 | aTyUglf0WPX6H8Zd17Iq | Large Test File | 136 | 71 | 71 | 2026-04-20 | 2026-07-31 | 2025-12-18 | 2026-07-03 | Summary | Planned | 0 | 514
FALSE | FALSE |  |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File | 97 | 127 | 127 | 2026-04-23 | 2026-10-23 | 2025-06-26 | 2025-11-11 | Summary | Planned | 0 | 488
FALSE | FALSE |  |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File | 77 | 160 | 160 | 2026-05-15 | 2027-01-07 | 2026-04-07 | 2026-07-27 | Summary | Planned | 0 | 450
FALSE | FALSE |  |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 42 | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE | FALSE |  |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE | TRUE |  |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE | FALSE |  |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE | FALSE |  |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE | TRUE |  |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE | FALSE |  |  | 4140 | Lk7gef35zB3WaxM8Xyxe | Large Test File | 86 | 48 | 48 | 2026-07-06 | 2026-09-10 | 2025-09-11 | 2026-01-13 | Summary | Planned | 0 | 530
FALSE | FALSE |  |  | 4141 | HGo5Ep3pqhcsiM5K4QjA | Large Test File | 23 | 23 | 23 | 2026-07-06 | 2026-08-05 | 2025-09-11 | 2025-10-13 | Summary | Planned | 0 | 530
FALSE | FALSE |  |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE | FALSE |  |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE | TRUE |  |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE | TRUE |  |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE | FALSE |  |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE | TRUE |  |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE | FALSE |  |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE | TRUE |  |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE | FALSE |  |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE | FALSE |  |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE | TRUE |  |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE | TRUE |  |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE | TRUE |  |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | FALSE |  |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE | TRUE |  |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE | FALSE |  |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE | FALSE |  |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE | FALSE |  |  | 7435 | nSo6tYchIu2Aw4YtE45u | Large Test File | 44 | 44 | 44 | 2026-07-31 | 2026-10-02 | 2026-07-31 | 2026-10-02 | Summary | Planned | 0 | 514
FALSE | FALSE |  |  | 7436 | Y83lvWkQwfsc3dMGwfVN | Large Test File | 30 | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE | FALSE |  |  | 7437 | E8EwVgjFQaEPGP66WsCb | Large Test File | 30 | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE | FALSE |  |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | FALSE |  |  | 7441 | IcgrxiRjEYJLwuugm8N7 | Large Test File | 30 | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE | FALSE |  |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | FALSE |  |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE | FALSE |  |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE | FALSE |  |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE | FALSE |  |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File | 76 | 106 | 106 | 2026-08-05 | 2027-01-01 | 2026-05-01 | 2026-08-14 | Summary | Planned | 0 | 455
FALSE | FALSE |  |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE | FALSE |  |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE | FALSE |  |  | 4144 | zaFQ6K5wegGvKt6DGuoz | Large Test File | 63 | 25 | 25 | 2026-08-06 | 2026-09-10 | 2025-10-14 | 2026-01-13 | Summary | Planned | 0 | 530
FALSE | FALSE |  |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE | FALSE |  |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE | FALSE |  |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE | FALSE |  |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE | FALSE |  |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | FALSE |  |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE | FALSE |  |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 48 | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE | FALSE |  |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | FALSE |  |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 539 | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE | FALSE |  |  | 7446 | NnBZUSVumxDXwVdCLN8g | Large Test File | 12 | 12 | 12 | 2026-09-14 | 2026-09-30 | 2026-09-14 | 2026-09-30 | Summary | Planned | 0 | 514
FALSE | FALSE |  |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE | FALSE |  |  | 4590 | 21lrGsmJiPqRYOd4yY3H | Large Test File | 2 | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Summary | Planned | 0 | 514
FALSE | FALSE |  |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE | FALSE |  |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE | FALSE |  |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE | FALSE |  |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE | FALSE |  |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | FALSE |  |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File | 74 | 37 | 37 | 2026-09-18 | 2026-11-10 | 2025-10-08 | 2026-01-23 | Summary | Planned | 0 | 488
FALSE | FALSE |  |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File | 50 | 32 | 32 | 2026-09-18 | 2026-11-03 | 2025-10-08 | 2025-12-17 | Summary | Planned | 0 | 488
FALSE | FALSE |  |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | FALSE |  |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE | FALSE |  |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE | FALSE |  |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE | FALSE |  |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE | FALSE |  |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE | FALSE |  |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 30 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE | FALSE |  |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE | FALSE |  |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 0 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE | FALSE |  |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE | FALSE |  |  | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Large Test File | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Summary | Planned | 0 | 510
FALSE | FALSE |  |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE | FALSE |  |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE | FALSE |  |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE | TRUE |  |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE | FALSE |  |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | FALSE |  |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | TRUE |  |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE | TRUE |  |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE | FALSE |  |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE | FALSE |  |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE | FALSE |  |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE | FALSE |  |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE | FALSE |  |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 30 | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE | FALSE |  |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE | FALSE |  |  | 4059 | sH9kz6O2EFda2hu4x8Kx | Large Test File | 45 | 12 | 12 | 2026-10-26 | 2026-11-10 | 2025-11-12 | 2026-01-16 | Summary | Planned | 0 | 488
FALSE | FALSE |  |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 15 | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE | FALSE |  |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 20 | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE | FALSE |  |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE | FALSE |  |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE | FALSE |  |  | 4054 | WhXMUGkGRid5sulqMW8S | Large Test File | 24 | 5 | 5 | 2026-11-04 | 2026-11-10 | 2025-12-18 | 2026-01-23 | Summary | Planned | 0 | 488
FALSE | FALSE |  |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 14 | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE | FALSE |  |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 6 | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE | FALSE |  |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 2 | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE | FALSE |  |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE | FALSE |  |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE | FALSE |  |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 6 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE | FALSE |  |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE | FALSE |  |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE | FALSE |  |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE | FALSE |  |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE | FALSE |  |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE | FALSE |  |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE | FALSE |  |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE | FALSE |  |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE | FALSE |  |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE | FALSE |  |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE | FALSE |  |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE | FALSE |  |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE | FALSE |  |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Critical w/High Planned Duration (44d)
Number of critical activities with a duration longer than 44 days.
Excluded | Critical | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
Longest Path - Critical Activities and Milestones
Activities that together form the longest path through to project completion. (Number of critical activities.)
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Critical Milestones (To-Go)
Number of critical milestones to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE | TRUE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Critical Tasks (To-Go)
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE | FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE | FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE | FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE | FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE | FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE | FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE | FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE | FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE | FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE | FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE | FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE | FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE | FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE | FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
High Float 44d
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE | FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE | FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE | FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE | FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE | FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE | FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE | FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE | FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE | FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE | FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE | FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE | FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE | FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE | FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE | FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE | FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE | FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE | FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE | FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE | FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE | TRUE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
CP - Float Ratio™
Average float divided by average remaining duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
20 to 30 days float
Total number of activities with positive float of more than 20 and less than or equal to 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Schedule Baseline Activities
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Scheduled/Baselined to Start
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Scheduled/Baselined to Finish
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Start/ed
Number of activities starting or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
Duration Variance (Original & Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 378 | 173 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE | 376 | 173 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE | 42 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE | 20 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | 0 | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
Scheduled Activities
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Scheduled to Start
Number of activities that are scheduled to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Scheduled to Finish
Number of activities that are scheduled to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Scheduled to Start - Tasks & Milestones
Number of activities and milestones that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Planned On Schedule Start - Tasks & Milestones
Number of activities and milestones that are planned to start on time.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
Planned Delayed Start - Tasks & Milestones
Number of activities and milestones that are currently planned to start after their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Scheduled to Start - Tasks
Number of activities that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Planned On Schedule Start - Tasks
Number of activities that are planned to start on time.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
Planned Delayed Start - Tasks
Number of activities that are currently planned to start after their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Planned Delayed Finish - Tasks
Number of planned/future activities that are schedule to slip from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Scheduled to Start - Milestones
Number of milestones that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Planned On Schedule Start - Milestones
Number of milestones that are planned to start on time.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
Planned Delayed Start - Milestones
Number of milestones that are currently planned to start after their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Planned Delayed Finish - Milestones
Number of planned/future activities that are schedule to slip from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
Actually Started - Tasks
Total number of activities that have started.
Excluded | Actual Start | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2019-04-15 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE | 2024-06-03 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE | 2024-06-03 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
In-Progress Started On-Schedule - Tasks
Number of activities that are currently underway and started on time.
Excluded | Actual Start | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2019-04-15 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE | 2024-06-03 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE | 2024-06-03 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
In-Progress Delayed Finish - Tasks
Number of in-progress activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
All Activities w/Successors
The total number of activities within a grouping.
Excluded | Created | Percent Complete | Number of Successors | Number of Successor Leads | Number of Successor Lags | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 79 | 1 | 0 | 0 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | Aspose.Tasks.Calendar | 1874 | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 532
FALSE |  | 30 | 1 | 0 | 0 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | Aspose.Tasks.Calendar | 378 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 532
FALSE |  | 30 | 1 | 0 | 0 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | Aspose.Tasks.Calendar | 376 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 532
FALSE |  | 0 | 2 | 0 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE |  | 0 | 2 | 0 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 42 | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE |  | 0 | 2 | 0 | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE |  | 0 | 1 | 0 | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE |  | 0 | 1 | 0 | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE |  | 0 | 2 | 0 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 | 1 | 0 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 | 3 | 0 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE |  | 0 | 2 | 0 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE |  | 0 | 2 | 0 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 | 3 | 0 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 | 1 | 0 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE |  | 0 | 4 | 0 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 | 1 | 0 | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 514
FALSE |  | 0 | 5 | 0 | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE |  | 0 | 1 | 0 | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE |  | 0 | 1 | 0 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE |  | 0 | 2 | 0 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE |  | 0 | 2 | 0 | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE |  | 0 | 1 | 0 | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 48 | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 539 | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE |  | 0 | 1 | 0 | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE |  | 0 | 2 | 0 | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE |  | 0 | 2 | 0 | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 512
FALSE |  | 0 | 1 | 0 | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE |  | 0 | 2 | 0 | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE |  | 0 | 3 | 0 | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | Aspose.Tasks.Calendar | 30 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 0 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE |  | 0 | 2 | 0 | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 510
FALSE |  | 0 | 1 | 0 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE |  | 0 | 1 | 0 | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 | 1 | 0 | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 | 5 | 0 | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE |  | 0 | 3 | 0 | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26
FALSE |  | 0 | 1 | 0 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 30 | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 15 | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 20 | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 14 | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 6 | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 6 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE |  | 0 | 2 | 0 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE |  | 0 | 2 | 0 | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
Total # Successors
The total number of successors on all activities within a grouping.
Excluded | Created | Percent Complete | Number of Successors | Number of Successor Leads | Number of Successor Lags | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 79 | 1 | 0 | 0 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | Aspose.Tasks.Calendar | 1874 | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 532
FALSE |  | 30 | 1 | 0 | 0 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | Aspose.Tasks.Calendar | 378 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 532
FALSE |  | 30 | 1 | 0 | 0 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | Aspose.Tasks.Calendar | 376 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 532
FALSE |  | 0 | 2 | 0 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE |  | 0 | 2 | 0 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 42 | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE |  | 0 | 2 | 0 | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE |  | 0 | 1 | 0 | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE |  | 0 | 1 | 0 | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE |  | 0 | 2 | 0 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 | 1 | 0 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 | 3 | 0 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE |  | 0 | 2 | 0 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE |  | 0 | 2 | 0 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 | 3 | 0 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 | 1 | 0 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE |  | 0 | 4 | 0 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 | 1 | 0 | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 514
FALSE |  | 0 | 5 | 0 | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE |  | 0 | 1 | 0 | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE |  | 0 | 1 | 0 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE |  | 0 | 2 | 0 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE |  | 0 | 2 | 0 | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE |  | 0 | 1 | 0 | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 48 | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 539 | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE |  | 0 | 1 | 0 | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE |  | 0 | 2 | 0 | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE |  | 0 | 2 | 0 | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 512
FALSE |  | 0 | 1 | 0 | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE |  | 0 | 2 | 0 | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE |  | 0 | 3 | 0 | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | Aspose.Tasks.Calendar | 30 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 0 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE |  | 0 | 2 | 0 | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 510
FALSE |  | 0 | 1 | 0 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE |  | 0 | 1 | 0 | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 | 1 | 0 | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 | 5 | 0 | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE |  | 0 | 3 | 0 | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26
FALSE |  | 0 | 1 | 0 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 30 | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 15 | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 20 | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 14 | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 6 | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 6 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE |  | 0 | 2 | 0 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE |  | 0 | 2 | 0 | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
Max # Successors on an Activity
Excluded | Number of Successors | Number of Successor Leads | Number of Successor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 | 0 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE | 1 | 0 | 0 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE | 1 | 0 | 0 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE | 2 | 0 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE | 2 | 0 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE | 2 | 0 | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE | 1 | 0 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE | 1 | 0 | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE | 1 | 0 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE | 1 | 0 | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE | 2 | 0 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE | 1 | 0 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE | 3 | 0 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE | 2 | 0 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE | 2 | 0 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE | 3 | 0 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | 1 | 0 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE | 4 | 0 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE | 1 | 0 | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE | 5 | 0 | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE | 1 | 0 | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE | 1 | 0 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE | 1 | 0 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE | 2 | 0 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE | 1 | 0 | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE | 1 | 0 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE | 1 | 0 | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE | 2 | 0 | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE | 1 | 0 | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE | 1 | 0 | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE | 1 | 0 | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE | 2 | 0 | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE | 2 | 0 | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE | 1 | 0 | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE | 2 | 0 | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE | 3 | 0 | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE | 2 | 0 | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE | 1 | 0 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE | 1 | 0 | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | 1 | 0 | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | 5 | 0 | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE | 3 | 0 | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE | 1 | 0 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE | 2 | 0 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE | 2 | 0 | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Diverge Hotspot (Successors >2)
Number of activities with a high number of successor links.
Excluded | Number of Predecessors | Number of Successors | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 3 | 0 | 0 | TRUE | -28 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0
FALSE | 3 | 3 | 0 | 0 | TRUE | -26 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE | 1 | 4 | 0 | 0 | TRUE | -27 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0
FALSE | 1 | 5 | 0 | 0 | FALSE | 514 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0
FALSE | 1 | 3 | 0 | 0 | FALSE | 514 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0
FALSE | 137 | 5 | 0 | 0 | TRUE | -26 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0
FALSE | 4 | 3 | 0 | 0 | TRUE | -26 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0
Critical Diverge Hotspot
Number of activities with a high number of successor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Successor Leads | Number of Successor Lags | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 3 | 0 | 0 | TRUE | -28 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0
FALSE | 3 | 3 | 0 | 0 | TRUE | -26 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE | 1 | 4 | 0 | 0 | TRUE | -27 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0
FALSE | 137 | 5 | 0 | 0 | TRUE | -26 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0
FALSE | 4 | 3 | 0 | 0 | TRUE | -26 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0
Logic Hotspot™
Number of activities with a high number of predecessors as well as a high number of successors.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 3 | TRUE | -26 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE | 137 | 5 | TRUE | -26 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0
FALSE | 4 | 3 | TRUE | -26 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0
Critical Logic Hotspot™
Number of activities with a high number of predecessors as well as a high number of successors.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 3 | TRUE | -26 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE | 137 | 5 | TRUE | -26 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0
FALSE | 4 | 3 | TRUE | -26 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0
All Activities w/Predecessors
The total number of activities within a grouping that have predecessors. Includes normal activities and milestones that are planned.
Excluded | Created | Percent Complete | Number of Predecessors | Number of Leads | Number of Lags | Minimum Lag | Maximum Lag | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 42 | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 514
FALSE |  | 0 | 9 | 0 | 0 | 0 | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 | 10 | 0 | 0 | 0 | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 48 | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 539 | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE |  | 0 | 4 | 0 | 0 | 0 | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 512
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | Aspose.Tasks.Calendar | 30 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 514
FALSE |  | 0 | 15 | 0 | 0 | 0 | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 514
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 0 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE |  | 0 | 8 | 0 | 0 | 0 | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 510
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 | 137 | 0 | 0 | 0 | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE |  | 0 | 4 | 0 | 0 | 0 | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 30 | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 15 | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 20 | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 14 | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 6 | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 6 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
Total # Predecessors
The total number of successors on all activities within a grouping that have predecessors. Includes normal activities and milestones that are planned.
Excluded | Created | Percent Complete | Number of Predecessors | Number of Leads | Number of Lags | Minimum Lag | Maximum Lag | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 42 | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 514
FALSE |  | 0 | 9 | 0 | 0 | 0 | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 | 10 | 0 | 0 | 0 | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 48 | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 539 | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE |  | 0 | 4 | 0 | 0 | 0 | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 512
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 514
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | Aspose.Tasks.Calendar | 30 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 514
FALSE |  | 0 | 15 | 0 | 0 | 0 | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 514
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 0 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE |  | 0 | 8 | 0 | 0 | 0 | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 510
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 | 137 | 0 | 0 | 0 | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE |  | 0 | 4 | 0 | 0 | 0 | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 30 | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 15 | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 20 | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 14 | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 6 | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 6 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
Max # Predecessors on an Activity
The max number of predecessor links on an activity. Includes normal activities and milestones that are planned.
Excluded | Number of Predecessors | Number of Leads | Number of Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 3 | 0 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE | 1 | 0 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE | 2 | 0 | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE | 1 | 0 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE | 1 | 0 | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE | 1 | 0 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE | 1 | 0 | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE | 2 | 0 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE | 1 | 0 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE | 1 | 0 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE | 1 | 0 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE | 1 | 0 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE | 2 | 0 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE | 3 | 0 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | 2 | 0 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE | 1 | 0 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE | 2 | 0 | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE | 9 | 0 | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | 10 | 0 | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE | 2 | 0 | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE | 1 | 0 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE | 1 | 0 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE | 3 | 0 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE | 1 | 0 | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE | 3 | 0 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE | 1 | 0 | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE | 1 | 0 | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE | 1 | 0 | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE | 4 | 0 | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE | 2 | 0 | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE | 3 | 0 | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | 3 | 0 | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE | 2 | 0 | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE | 1 | 0 | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE | 1 | 0 | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE | 15 | 0 | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE | 2 | 0 | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE | 2 | 0 | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE | 2 | 0 | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE | 8 | 0 | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE | 2 | 0 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE | 2 | 0 | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE | 2 | 0 | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | 2 | 0 | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | 137 | 0 | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE | 4 | 0 | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE | 1 | 0 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE | 2 | 0 | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE | 2 | 0 | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Max Predecessor Lag (days)
The largest predecessor lag value for the selected activity grouping.
Excluded | Number of Predecessors | Number of Lags | Minimum Lag | Maximum Lag | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 3 | 0 | 0 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE | 1 | 0 | 0 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE | 2 | 0 | 0 | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE | 1 | 0 | 0 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE | 1 | 0 | 0 | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE | 1 | 0 | 0 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE | 1 | 0 | 0 | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE | 2 | 0 | 0 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE | 1 | 0 | 0 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE | 1 | 0 | 0 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE | 1 | 0 | 0 | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE | 1 | 0 | 0 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE | 1 | 0 | 0 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE | 2 | 0 | 0 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE | 3 | 0 | 0 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | 2 | 0 | 0 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE | 1 | 0 | 0 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE | 2 | 0 | 0 | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE | 1 | 0 | 0 | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE | 9 | 0 | 0 | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | 10 | 0 | 0 | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE | 2 | 0 | 0 | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE | 1 | 0 | 0 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE | 3 | 0 | 0 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE | 3 | 0 | 0 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE | 1 | 0 | 0 | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE | 1 | 0 | 0 | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE | 1 | 0 | 0 | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE | 4 | 0 | 0 | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE | 2 | 0 | 0 | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE | 3 | 0 | 0 | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | 3 | 0 | 0 | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE | 2 | 0 | 0 | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE | 1 | 0 | 0 | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE | 1 | 0 | 0 | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE | 1 | 0 | 0 | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE | 15 | 0 | 0 | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE | 2 | 0 | 0 | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE | 2 | 0 | 0 | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE | 2 | 0 | 0 | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE | 8 | 0 | 0 | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE | 2 | 0 | 0 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE | 2 | 0 | 0 | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE | 2 | 0 | 0 | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | 2 | 0 | 0 | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | 137 | 0 | 0 | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE | 4 | 0 | 0 | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE | 1 | 0 | 0 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE | 2 | 0 | 0 | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE | 1 | 0 | 0 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE | 1 | 0 | 0 | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE | 1 | 0 | 0 | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE | 2 | 0 | 0 | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Merge Hotspot (Predecessors >2)
The total number of activities with a high number of predecessor links.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 2 | FALSE | 512 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0
FALSE | 3 | 3 | TRUE | -26 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE | 9 | 1 | FALSE | 514 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0
FALSE | 10 | 1 | FALSE | 514 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0
FALSE | 3 | 2 | FALSE | 19 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0
FALSE | 3 | 1 | FALSE | 455 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0
FALSE | 4 | 1 | FALSE | 514 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0
FALSE | 3 | 2 | FALSE | 514 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0
FALSE | 3 | 1 | FALSE | 514 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0
FALSE | 15 | 1 | FALSE | 514 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0
FALSE | 8 | 2 | FALSE | 510 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0
FALSE | 137 | 5 | TRUE | -26 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0
FALSE | 4 | 3 | TRUE | -26 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0
Critical Merge Hotspot
The total number of activities with a high number of predecessor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 3 | 0 | 0 | 0 | TRUE | -26 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE | 137 | 5 | 0 | 0 | 0 | TRUE | -26 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0
FALSE | 4 | 3 | 0 | 0 | 0 | TRUE | -26 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0
Logic Hotspot™
Number of activities with a high number of predecessors as well as a high number of successors.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 3 | TRUE | -26 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE | 137 | 5 | TRUE | -26 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0
FALSE | 4 | 3 | TRUE | -26 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0
Critical Logic Hotspot™
Number of activities with a high number of predecessors as well as a high number of successors.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 3 | TRUE | -26 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE | 137 | 5 | TRUE | -26 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0
FALSE | 4 | 3 | TRUE | -26 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0
All Activities w/Predecessors
The total number of activities within a grouping that have predecessors. Includes normal activities and milestones that are planned or in-progress.
Excluded | Number of Predecessors | Number of Leads | Number of Lags | Maximum Lag | Minimum Lag | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 42 | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 514
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 514
FALSE | 9 | 0 | 0 | 0 | 0 |  | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE | 10 | 0 | 0 | 0 | 0 |  | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 48 | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 539 | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE | 4 | 0 | 0 | 0 | 0 |  | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 512
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 514
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | Aspose.Tasks.Calendar | 30 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 514
FALSE | 15 | 0 | 0 | 0 | 0 |  | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 514
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 0 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE | 8 | 0 | 0 | 0 | 0 |  | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 510
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE | 137 | 0 | 0 | 0 | 0 |  | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE | 4 | 0 | 0 | 0 | 0 |  | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 30 | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 15 | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 20 | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 14 | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 6 | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 6 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
SS Predecessors
Number of activities with Start-to-Start (SS) logic links.
Excluded | Number of SS Predecessors | Number Of SS Predecessor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | 1 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE | 1 | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE | 1 | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE | 1 | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FF Predecessors
Number of activities with Finish-to-Finish (FF) logic links.
Excluded | Number of FF Predecessors | Number Of FF Predecessor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE | 1 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE | 1 | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE | 1 | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE | 1 | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FS Predecessors
Number of activities with Finish-to-Start (FS) logic links. Should be at least 90%.
Excluded | Number of FS Predecessors | Number Of FS Predecessor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE | 1 | 0 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE | 1 | 0 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE | 3 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE | 1 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE | 2 | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE | 1 | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE | 1 | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE | 1 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE | 1 | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE | 1 | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE | 1 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE | 1 | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE | 2 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE | 1 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE | 1 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE | 1 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE | 1 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE | 1 | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE | 1 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE | 1 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE | 2 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE | 2 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | 1 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE | 1 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE | 1 | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE | 9 | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | 10 | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE | 1 | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE | 2 | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE | 1 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE | 1 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE | 3 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE | 1 | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE | 2 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE | 1 | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE | 1 | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE | 1 | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | 1 | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE | 1 | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE | 1 | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE | 1 | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE | 4 | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE | 1 | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE | 1 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE | 1 | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE | 3 | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE | 1 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | 1 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE | 3 | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE | 1 | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE | 2 | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE | 1 | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE | 1 | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE | 1 | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE | 15 | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE | 1 | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE | 2 | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE | 1 | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE | 8 | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE | 2 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE | 1 | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE | 1 | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | 2 | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE | 137 | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE | 3 | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE | 1 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE | 1 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE | 1 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE | 1 | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE | 1 | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE | 1 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE | 1 | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE | 1 | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE | 1 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE | 1 | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE | 2 | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE | 1 | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE | 1 | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE | 1 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE | 1 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE | 1 | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE | 1 | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE | 1 | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE | 1 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE | 1 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE | 1 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE | 1 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE | 1 | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE | 1 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE | 1 | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE | 1 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE | 1 | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE | 1 | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE | 2 | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
All Activities w/Successors
The total number of activities within a grouping. Includes normal activities and milestones that are planned or in-progress.
Excluded | Number of Successors | Number of Successor Leads | Number of Successor Lags | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 1 | 0 | 0 |  | 79 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | Aspose.Tasks.Calendar | 1874 | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 532
FALSE | 1 | 0 | 0 |  | 30 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | Aspose.Tasks.Calendar | 378 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 532
FALSE | 1 | 0 | 0 |  | 30 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | Aspose.Tasks.Calendar | 376 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 532
FALSE | 2 | 0 | 0 |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE | 2 | 0 | 0 |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 42 | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE | 2 | 0 | 0 |  | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE | 1 | 0 | 0 |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE | 1 | 0 | 0 |  | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE | 1 | 0 | 0 |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE | 1 | 0 | 0 |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE | 1 | 0 | 0 |  | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE | 1 | 0 | 0 |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE | 1 | 0 | 0 |  | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE | 2 | 0 | 0 |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE | 1 | 0 | 0 |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE | 1 | 0 | 0 |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE | 1 | 0 | 0 |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE | 3 | 0 | 0 |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE | 1 | 0 | 0 |  | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE | 2 | 0 | 0 |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE | 2 | 0 | 0 |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE | 1 | 0 | 0 |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE | 3 | 0 | 0 |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE | 1 | 0 | 0 |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE | 4 | 0 | 0 |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE | 1 | 0 | 0 |  | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 514
FALSE | 5 | 0 | 0 |  | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 514
FALSE | 1 | 0 | 0 |  | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE | 1 | 0 | 0 |  | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE | 1 | 0 | 0 |  | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE | 1 | 0 | 0 |  | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE | 1 | 0 | 0 |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE | 2 | 0 | 0 |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE | 1 | 0 | 0 |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE | 1 | 0 | 0 |  | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE | 1 | 0 | 0 |  | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE | 2 | 0 | 0 |  | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE | 1 | 0 | 0 |  | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE | 1 | 0 | 0 |  | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 48 | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE | 1 | 0 | 0 |  | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE | 1 | 0 | 0 |  | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 539 | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE | 1 | 0 | 0 |  | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE | 2 | 0 | 0 |  | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE | 1 | 0 | 0 |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE | 1 | 0 | 0 |  | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE | 2 | 0 | 0 |  | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE | 1 | 0 | 0 |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE | 1 | 0 | 0 |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE | 1 | 0 | 0 |  | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE | 1 | 0 | 0 |  | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 512
FALSE | 1 | 0 | 0 |  | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE | 2 | 0 | 0 |  | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE | 3 | 0 | 0 |  | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 514
FALSE | 1 | 0 | 0 |  | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | Aspose.Tasks.Calendar | 30 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 514
FALSE | 1 | 0 | 0 |  | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 514
FALSE | 1 | 0 | 0 |  | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 0 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE | 1 | 0 | 0 |  | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE | 1 | 0 | 0 |  | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE | 2 | 0 | 0 |  | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 510
FALSE | 1 | 0 | 0 |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE | 1 | 0 | 0 |  | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE | 1 | 0 | 0 |  | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE | 1 | 0 | 0 |  | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE | 5 | 0 | 0 |  | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE | 3 | 0 | 0 |  | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26
FALSE | 1 | 0 | 0 |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE | 1 | 0 | 0 |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE | 1 | 0 | 0 |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE | 1 | 0 | 0 |  | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE | 1 | 0 | 0 |  | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 30 | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE | 1 | 0 | 0 |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE | 1 | 0 | 0 |  | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 15 | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE | 1 | 0 | 0 |  | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 20 | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE | 1 | 0 | 0 |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE | 1 | 0 | 0 |  | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE | 1 | 0 | 0 |  | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 14 | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE | 1 | 0 | 0 |  | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 6 | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE | 1 | 0 | 0 |  | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE | 1 | 0 | 0 |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE | 1 | 0 | 0 |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE | 1 | 0 | 0 |  | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 6 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE | 1 | 0 | 0 |  | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE | 1 | 0 | 0 |  | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE | 1 | 0 | 0 |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE | 2 | 0 | 0 |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE | 1 | 0 | 0 |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE | 1 | 0 | 0 |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE | 1 | 0 | 0 |  | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE | 1 | 0 | 0 |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE | 1 | 0 | 0 |  | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE | 1 | 0 | 0 |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE | 1 | 0 | 0 |  | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE | 1 | 0 | 0 |  | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE | 2 | 0 | 0 |  | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
SS Successors
Number of activities with Start-to-Start (SS) logic links.
Excluded | Number of SS Successors | Number of Successor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE | 1 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE | 1 | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE | 1 | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FF Successors
Number of activities with Finish-to-Finish (FF) logic links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FS Successors
Number of activities with Finish-to-Start (FS) logic links. Should be at least 90%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Total Constraints
Number of activities with certain constraint types.
Excluded | Created | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | StartOnOrAfter | 2026-08-26 | None |  | FALSE | 539 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | StartOnOrAfter | 2026-09-08 | None |  | FALSE | 1 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0
FALSE |  | StartOnOrAfter | 2026-10-02 | None |  | FALSE | 514 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0
FALSE |  | StartOnOrAfter | 2026-09-15 | None |  | FALSE | 514 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | StartOnOrAfter | 2026-10-01 | None |  | FALSE | 510 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0
FALSE |  | StartOnOrAfter | 2026-08-17 | None |  | TRUE | -26 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0
FALSE |  | StartOnOrAfter | 2026-09-01 | Deadline | 2026-09-01 | TRUE | -26 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0
Start No Earlier Than
Number of activities with a soft (one-way) constraint that forces the activity to start on or after a given date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
No Constraints
Number of activities with no constraints.
Excluded | Created | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | None |  | None |  | FALSE | 532 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79
FALSE |  | None |  | None |  | FALSE | 532 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30
FALSE |  | None |  | None |  | FALSE | 532 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30
FALSE |  | None |  | None |  | FALSE | 512 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -28 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 530 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 24 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -28 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 530 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 24 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -28 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | -28 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 30 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -28 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 30 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -28 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 530 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 24 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -28 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -26 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -26 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 496 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -27 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 524 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 534 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 463 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 530 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 530 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 530 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 524 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 512 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 512 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 510 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 450 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -26 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 510 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 510 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 450 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 450 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 450 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 450 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 450 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 450 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0
No Constraints
Number of activities with no constraints.
Excluded | Created | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | None |  | None |  | FALSE | 532 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79
FALSE |  | None |  | None |  | FALSE | 532 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30
FALSE |  | None |  | None |  | FALSE | 532 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30
FALSE |  | None |  | None |  | FALSE | 512 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -28 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 530 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 24 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -28 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 530 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 24 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -28 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | -28 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 30 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -28 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 30 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -28 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 530 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 24 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -28 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -26 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -26 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 496 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -27 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 524 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 534 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 463 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 530 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 530 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 530 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 524 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 512 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 512 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 514 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 510 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 450 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -26 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 510 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 510 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 450 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 450 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 488 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 450 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 450 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 450 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 450 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 455 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0
Tasks & Milestones (To-Go) - % of Total To-Go
The total number of activities within a grouping. Percentage shows total to-go (planned and in-progress) tasks and milestones out of all activities (normal, milestone, summary, and LOE).
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 79 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | Aspose.Tasks.Calendar | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 532
FALSE |  | 30 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 532
FALSE |  | 30 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 532
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE |  | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE |  | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 514
FALSE |  | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 514
FALSE |  | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE |  | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 19
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 19
FALSE |  | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE |  | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE |  | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE |  | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE |  | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE |  | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE |  | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE |  | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE |  | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE |  | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE |  | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 512
FALSE |  | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE |  | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE |  | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 514
FALSE |  | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 514
FALSE |  | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 514
FALSE |  | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE |  | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE |  | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE |  | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 510
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE |  | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE |  | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE |  | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE |  | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE |  | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE |  | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE |  | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE |  | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE |  | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE |  | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE |  | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE |  | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE |  | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE |  | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE |  | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE |  | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE |  | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
High Baseline Duration (44d)
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 378 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 376 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 48 | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 539 | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
High Planned Duration (44d)
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 378 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 376 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 42 | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 539 | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
Insufficient Detail™
Number of activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 378 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 376 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 539 | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
Critical Activities (To-Go)
Number of critical activities
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
Critical w/High Baseline Duration (44d)
Total number of critical activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File | 2875 | 2874 | 611 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 79 | 0
FALSE |  |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File | 2388 | 2874 | 1132 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 61 | 0
FALSE |  |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File | 2478 | 2873 | 911 | 2017-06-07 | 2028-09-27 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 68 | 1
FALSE |  |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File | 1877 | 1928 | 315 | 2019-04-01 | 2026-11-10 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 84 | 488
FALSE |  |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File | 1454 | 1454 | 263 | 2021-01-04 | 2026-10-05 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 82 | 514
FALSE |  |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File | 1410 | 1390 | 288 | 2021-04-05 | 2026-10-05 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 79 | 514
FALSE |  |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File | 1185 | 1198 | 222 | 2022-01-06 | 2026-10-05 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 82 | 514
FALSE |  |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File | 1125 | 1144 | 274 | 2022-03-07 | 2026-09-16 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 76 | 526
FALSE |  |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File | 1189 | 1134 | 264 | 2022-04-04 | 2026-09-29 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 77 | 512
FALSE |  |  | 6297 | AqdIsKbIPOfZJkjKYjnG | Large Test File | 954 | 928 | 118 | 2022-12-21 | 2026-08-26 | 2022-11-15 | 2026-08-26 | Summary | InProgress | 87 | 539
FALSE |  |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File | 621 | 931 | 163 | 2023-01-03 | 2026-09-10 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 83 | 530
FALSE |  |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File | 516 | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 85 | -26
FALSE |  |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File | 516 | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 85 | -26
FALSE |  |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File | 906 | 975 | 288 | 2023-02-23 | 2027-01-07 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 70 | 450
FALSE |  |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File | 402 | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 17 | 30
FALSE |  |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File | 873 | 972 | 309 | 2023-03-06 | 2027-01-01 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 68 | 455
FALSE |  |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File | 632 | 823 | 172 | 2023-08-04 | 2026-11-10 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 79 | 488
FALSE |  |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File | 775 | 800 | 552 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 31 | 510
FALSE |  |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File | 462 | 800 | 277 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2025-05-30 | Summary | InProgress | 65 | -26
FALSE |  |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File | 748 | 860 | 297 | 2023-08-07 | 2027-01-07 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 65 | 450
FALSE |  |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File | 137 | 760 | 466 | 2023-09-05 | 2026-09-10 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 39 | 530
FALSE |  |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File | 51 | 712 | 322 | 2023-09-05 | 2026-07-02 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 55 | 530
FALSE |  |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File | 688 | 808 | 0 | 2023-10-12 | 2027-01-01 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 99 | 454
FALSE |  |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File | 190 | 703 | 703 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 0 | 19
FALSE |  |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File | 396 | 739 | 554 | 2023-10-18 | 2026-09-25 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 25 | 512
FALSE |  |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File | 512 | 655 | 255 | 2024-03-04 | 2026-10-08 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 61 | 510
FALSE |  |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 378 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 376 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File | 375 | 571 | 554 | 2024-08-01 | 2026-11-10 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 3 | 488
FALSE |  |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File | 366 | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 325
FALSE |  |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File | 366 | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 325
FALSE |  |  | 7388 | subTjNOw9tjXphx2xXzW | Large Test File | 324 | 324 | 324 | 2025-06-18 | 2026-10-02 | 2025-06-18 | 2026-10-02 | Summary | Planned | 0 | 514
FALSE |  |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File | 340 | 276 | 276 | 2025-06-23 | 2026-07-31 | 2024-09-26 | 2026-01-30 | Summary | Planned | 0 | 514
FALSE |  |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File | 145 | 272 | 272 | 2025-06-27 | 2026-07-29 | 2025-06-27 | 2026-01-23 | Summary | Planned | 0 | 24
FALSE |  |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File | 293 | 319 | 319 | 2025-10-07 | 2027-01-01 | 2025-06-24 | 2026-08-14 | Summary | Planned | 0 | 80
FALSE |  |  | 5277 | TgmqG1sR4A60sNmMtPcE | Large Test File | 111 | 193 | 193 | 2025-10-07 | 2026-07-09 | 2024-04-30 | 2024-10-04 | Summary | Planned | 0 | -28
FALSE |  |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File | 105 | 144 | 144 | 2026-01-15 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 0 | 11
FALSE |  |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File | 126 | 126 | 126 | 2026-04-01 | 2026-09-29 | 2026-01-07 | 2026-07-07 | Summary | Planned | 0 | 512
FALSE |  |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  |  | 4538 | aTyUglf0WPX6H8Zd17Iq | Large Test File | 136 | 71 | 71 | 2026-04-20 | 2026-07-31 | 2025-12-18 | 2026-07-03 | Summary | Planned | 0 | 514
FALSE |  |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File | 97 | 127 | 127 | 2026-04-23 | 2026-10-23 | 2025-06-26 | 2025-11-11 | Summary | Planned | 0 | 488
FALSE |  |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File | 77 | 160 | 160 | 2026-05-15 | 2027-01-07 | 2026-04-07 | 2026-07-27 | Summary | Planned | 0 | 450
FALSE |  |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 42 | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  |  | 4140 | Lk7gef35zB3WaxM8Xyxe | Large Test File | 86 | 48 | 48 | 2026-07-06 | 2026-09-10 | 2025-09-11 | 2026-01-13 | Summary | Planned | 0 | 530
FALSE |  |  | 4141 | HGo5Ep3pqhcsiM5K4QjA | Large Test File | 23 | 23 | 23 | 2026-07-06 | 2026-08-05 | 2025-09-11 | 2025-10-13 | Summary | Planned | 0 | 530
FALSE |  |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | 0 | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | 0 | -28
FALSE |  |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 0 | 514
FALSE |  |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | 0 | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 514
FALSE |  |  | 7435 | nSo6tYchIu2Aw4YtE45u | Large Test File | 44 | 44 | 44 | 2026-07-31 | 2026-10-02 | 2026-07-31 | 2026-10-02 | Summary | Planned | 0 | 514
FALSE |  |  | 7436 | Y83lvWkQwfsc3dMGwfVN | Large Test File | 30 | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE |  |  | 7437 | E8EwVgjFQaEPGP66WsCb | Large Test File | 30 | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE |  |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  |  | 7441 | IcgrxiRjEYJLwuugm8N7 | Large Test File | 30 | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 0 | 514
FALSE |  |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 19
FALSE |  |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File | 76 | 106 | 106 | 2026-08-05 | 2027-01-01 | 2026-05-01 | 2026-08-14 | Summary | Planned | 0 | 455
FALSE |  |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 19
FALSE |  |  | 4144 | zaFQ6K5wegGvKt6DGuoz | Large Test File | 63 | 25 | 25 | 2026-08-06 | 2026-09-10 | 2025-10-14 | 2026-01-13 | Summary | Planned | 0 | 530
FALSE |  |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 48 | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 539 | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  |  | 7446 | NnBZUSVumxDXwVdCLN8g | Large Test File | 12 | 12 | 12 | 2026-09-14 | 2026-09-30 | 2026-09-14 | 2026-09-30 | Summary | Planned | 0 | 514
FALSE |  |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  |  | 4590 | 21lrGsmJiPqRYOd4yY3H | Large Test File | 2 | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Summary | Planned | 0 | 514
FALSE |  |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File | 74 | 37 | 37 | 2026-09-18 | 2026-11-10 | 2025-10-08 | 2026-01-23 | Summary | Planned | 0 | 488
FALSE |  |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File | 50 | 32 | 32 | 2026-09-18 | 2026-11-03 | 2025-10-08 | 2025-12-17 | Summary | Planned | 0 | 488
FALSE |  |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | 0 | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 0 | 512
FALSE |  |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 0 | 514
FALSE |  |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | 30 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 0 | 514
FALSE |  |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | 0 | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 0 | 514
FALSE |  |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 0 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  |  | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Large Test File | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Summary | Planned | 0 | 510
FALSE |  |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 0 | 510
FALSE |  |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | 0 | -26
FALSE |  |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 0 | 510
FALSE |  |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | 0 | -26
FALSE |  |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | 0 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | 0 | -26
FALSE |  |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 30 | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  |  | 4059 | sH9kz6O2EFda2hu4x8Kx | Large Test File | 45 | 12 | 12 | 2026-10-26 | 2026-11-10 | 2025-11-12 | 2026-01-16 | Summary | Planned | 0 | 488
FALSE |  |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 15 | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 20 | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  |  | 4054 | WhXMUGkGRid5sulqMW8S | Large Test File | 24 | 5 | 5 | 2026-11-04 | 2026-11-10 | 2025-12-18 | 2026-01-23 | Summary | Planned | 0 | 488
FALSE |  |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 14 | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 6 | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 2 | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 6 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Critical w/High Planned Duration (44d)
Number of critical activities with a duration longer than 44 days.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
Activities (To-Go)
The total number of activities within a grouping.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | 1874 | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 79 | 532
FALSE |  |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | 378 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 30 | 532
FALSE |  |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | 376 | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 30 | 532
FALSE |  |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | 122 | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 512
FALSE |  |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | 42 | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 488
FALSE |  |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | 36 | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 0 | 514
FALSE |  |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | 6 | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | 0 | -28
FALSE |  |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | 5 | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 0 | 530
FALSE |  |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | 5 | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 24
FALSE |  |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | 5 | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | 0 | -28
FALSE |  |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | 12 | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 0 | 530
FALSE |  |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | 10 | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 24
FALSE |  |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -28
FALSE |  |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -28
FALSE |  |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -28
FALSE |  |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | 11 | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 0 | 530
FALSE |  |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | 5 | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 24
FALSE |  |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -28
FALSE |  |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -26
FALSE |  |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | 20 | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -26
FALSE |  |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 496
FALSE |  |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -27
FALSE |  |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | 15 | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 0 | 514
FALSE |  |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | 20 | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 0 | 524
FALSE |  |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | 10 | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 0 | 534
FALSE |  |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 19
FALSE |  |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 463
FALSE |  |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | 10 | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 0 | 530
FALSE |  |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | 10 | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 455
FALSE |  |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | 5 | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 0 | 530
FALSE |  |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | 5 | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 0 | 514
FALSE |  |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | 15 | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 539
FALSE |  |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | 48 | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 0 | 530
FALSE |  |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | 10 | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 0 | 514
FALSE |  |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | 539 | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 0 | 1
FALSE |  |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | 4 | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 0 | 514
FALSE |  |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | 2 | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 0 | 514
FALSE |  |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | 9 | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 455
FALSE |  |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | 1 | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 524
FALSE |  |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | 3 | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 0 | 514
FALSE |  |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | 20 | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 488
FALSE |  |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | 7 | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 0 | 514
FALSE |  |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | 2 | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 0 | 512
FALSE |  |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | 2 | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 0 | 514
FALSE |  |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | 0 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 0 | 514
FALSE |  |  | 6084 | deZM0xh115wln716GUoI | Large Test File | 1 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 514
FALSE |  |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 510
FALSE |  |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | 5 | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 450
FALSE |  |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 455
FALSE |  |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 455
FALSE |  |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | 15 | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 450
FALSE |  |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | 5 | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 0 | 488
FALSE |  |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | 30 | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 0 | 488
FALSE |  |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 455
FALSE |  |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | 15 | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 0 | 488
FALSE |  |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | 20 | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 0 | 488
FALSE |  |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 455
FALSE |  |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | 2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 0 | 488
FALSE |  |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | 14 | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 0 | 488
FALSE |  |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | 6 | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 0 | 488
FALSE |  |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | 2 | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 0 | 488
FALSE |  |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | 5 | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 455
FALSE |  |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | 20 | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 450
FALSE |  |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | 6 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 0 | 488
FALSE |  |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 0 | 488
FALSE |  |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | 2 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 0 | 488
FALSE |  |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | 5 | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 455
FALSE |  |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | 5 | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 455
FALSE |  |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | 5 | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 455
FALSE |  |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | 5 | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 455
FALSE |  |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | 5 | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 0 | 450
FALSE |  |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | 5 | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 455
FALSE |  |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | 5 | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 0 | 450
FALSE |  |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | 5 | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 455
FALSE |  |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | 5 | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 0 | 450
FALSE |  |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | 5 | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 0 | 450
FALSE |  |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | 1 | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 0 | 455
Total Activities
The total number of activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 79 |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File | Aspose.Tasks.Calendar | 2874 | 611 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 0
FALSE |  | 61 |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File | Aspose.Tasks.Calendar | 2874 | 1132 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 0
FALSE |  | 68 |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File | Aspose.Tasks.Calendar | 2873 | 911 | 2017-06-07 | 2028-09-27 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 1
FALSE |  | 84 |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File | Aspose.Tasks.Calendar | 1928 | 315 | 2019-04-01 | 2026-11-10 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 488
FALSE |  | 79 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | Aspose.Tasks.Calendar | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 532
FALSE |  | 82 |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File | Aspose.Tasks.Calendar | 1454 | 263 | 2021-01-04 | 2026-10-05 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 514
FALSE |  | 79 |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File | Aspose.Tasks.Calendar | 1390 | 288 | 2021-04-05 | 2026-10-05 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 514
FALSE |  | 82 |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File | Aspose.Tasks.Calendar | 1198 | 222 | 2022-01-06 | 2026-10-05 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 514
FALSE |  | 76 |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File | Aspose.Tasks.Calendar | 1144 | 274 | 2022-03-07 | 2026-09-16 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 526
FALSE |  | 77 |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File | Aspose.Tasks.Calendar | 1134 | 264 | 2022-04-04 | 2026-09-29 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 512
FALSE |  | 87 |  | 6297 | AqdIsKbIPOfZJkjKYjnG | Large Test File | Aspose.Tasks.Calendar | 928 | 118 | 2022-12-21 | 2026-08-26 | 2022-11-15 | 2026-08-26 | Summary | InProgress | 539
FALSE |  | 83 |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File | Aspose.Tasks.Calendar | 931 | 163 | 2023-01-03 | 2026-09-10 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 530
FALSE |  | 85 |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File | Aspose.Tasks.Calendar | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -26
FALSE |  | 85 |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File | Aspose.Tasks.Calendar | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -26
FALSE |  | 70 |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File | Aspose.Tasks.Calendar | 975 | 288 | 2023-02-23 | 2027-01-07 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 450
FALSE |  | 17 |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File | Aspose.Tasks.Calendar | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 30
FALSE |  | 68 |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File | Aspose.Tasks.Calendar | 972 | 309 | 2023-03-06 | 2027-01-01 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 455
FALSE |  | 79 |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File | Aspose.Tasks.Calendar | 823 | 172 | 2023-08-04 | 2026-11-10 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 488
FALSE |  | 31 |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File | Aspose.Tasks.Calendar | 800 | 552 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 510
FALSE |  | 65 |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File | Aspose.Tasks.Calendar | 800 | 277 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2025-05-30 | Summary | InProgress | -26
FALSE |  | 65 |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File | Aspose.Tasks.Calendar | 860 | 297 | 2023-08-07 | 2027-01-07 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 450
FALSE |  | 39 |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File | Aspose.Tasks.Calendar | 760 | 466 | 2023-09-05 | 2026-09-10 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 530
FALSE |  | 55 |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File | Aspose.Tasks.Calendar | 712 | 322 | 2023-09-05 | 2026-07-02 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 530
FALSE |  | 99 |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File | Aspose.Tasks.Calendar | 808 | 0 | 2023-10-12 | 2027-01-01 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 454
FALSE |  | 0 |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File | Aspose.Tasks.Calendar | 703 | 703 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 19
FALSE |  | 25 |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File | Aspose.Tasks.Calendar | 739 | 554 | 2023-10-18 | 2026-09-25 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 512
FALSE |  | 61 |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File | Aspose.Tasks.Calendar | 655 | 255 | 2024-03-04 | 2026-10-08 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 510
FALSE |  | 30 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 532
FALSE |  | 30 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 532
FALSE |  | 3 |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File | Aspose.Tasks.Calendar | 571 | 554 | 2024-08-01 | 2026-11-10 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 488
FALSE |  | 0 |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File | Aspose.Tasks.Calendar | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 325
FALSE |  | 0 |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File | Aspose.Tasks.Calendar | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 325
FALSE |  | 0 |  | 7388 | subTjNOw9tjXphx2xXzW | Large Test File | Aspose.Tasks.Calendar | 324 | 324 | 2025-06-18 | 2026-10-02 | 2025-06-18 | 2026-10-02 | Summary | Planned | 514
FALSE |  | 0 |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File | Aspose.Tasks.Calendar | 276 | 276 | 2025-06-23 | 2026-07-31 | 2024-09-26 | 2026-01-30 | Summary | Planned | 514
FALSE |  | 0 |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File | Aspose.Tasks.Calendar | 272 | 272 | 2025-06-27 | 2026-07-29 | 2025-06-27 | 2026-01-23 | Summary | Planned | 24
FALSE |  | 0 |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File | Aspose.Tasks.Calendar | 319 | 319 | 2025-10-07 | 2027-01-01 | 2025-06-24 | 2026-08-14 | Summary | Planned | 80
FALSE |  | 0 |  | 5277 | TgmqG1sR4A60sNmMtPcE | Large Test File | Aspose.Tasks.Calendar | 193 | 193 | 2025-10-07 | 2026-07-09 | 2024-04-30 | 2024-10-04 | Summary | Planned | -28
FALSE |  | 0 |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File | Aspose.Tasks.Calendar | 144 | 144 | 2026-01-15 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 11
FALSE |  | 0 |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File | Aspose.Tasks.Calendar | 126 | 126 | 2026-04-01 | 2026-09-29 | 2026-01-07 | 2026-07-07 | Summary | Planned | 512
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE |  | 0 |  | 4538 | aTyUglf0WPX6H8Zd17Iq | Large Test File | Aspose.Tasks.Calendar | 71 | 71 | 2026-04-20 | 2026-07-31 | 2025-12-18 | 2026-07-03 | Summary | Planned | 514
FALSE |  | 0 |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File | Aspose.Tasks.Calendar | 127 | 127 | 2026-04-23 | 2026-10-23 | 2025-06-26 | 2025-11-11 | Summary | Planned | 488
FALSE |  | 0 |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File | Aspose.Tasks.Calendar | 160 | 160 | 2026-05-15 | 2027-01-07 | 2026-04-07 | 2026-07-27 | Summary | Planned | 450
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE |  | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 |  | 4140 | Lk7gef35zB3WaxM8Xyxe | Large Test File | Aspose.Tasks.Calendar | 48 | 48 | 2026-07-06 | 2026-09-10 | 2025-09-11 | 2026-01-13 | Summary | Planned | 530
FALSE |  | 0 |  | 4141 | HGo5Ep3pqhcsiM5K4QjA | Large Test File | Aspose.Tasks.Calendar | 23 | 23 | 2026-07-06 | 2026-08-05 | 2025-09-11 | 2025-10-13 | Summary | Planned | 530
FALSE |  | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE |  | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 514
FALSE |  | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 514
FALSE |  | 0 |  | 7435 | nSo6tYchIu2Aw4YtE45u | Large Test File | Aspose.Tasks.Calendar | 44 | 44 | 2026-07-31 | 2026-10-02 | 2026-07-31 | 2026-10-02 | Summary | Planned | 514
FALSE |  | 0 |  | 7436 | Y83lvWkQwfsc3dMGwfVN | Large Test File | Aspose.Tasks.Calendar | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 514
FALSE |  | 0 |  | 7437 | E8EwVgjFQaEPGP66WsCb | Large Test File | Aspose.Tasks.Calendar | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 514
FALSE |  | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7441 | IcgrxiRjEYJLwuugm8N7 | Large Test File | Aspose.Tasks.Calendar | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 514
FALSE |  | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE |  | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 19
FALSE |  | 0 |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File | Aspose.Tasks.Calendar | 106 | 106 | 2026-08-05 | 2027-01-01 | 2026-05-01 | 2026-08-14 | Summary | Planned | 455
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 19
FALSE |  | 0 |  | 4144 | zaFQ6K5wegGvKt6DGuoz | Large Test File | Aspose.Tasks.Calendar | 25 | 25 | 2026-08-06 | 2026-09-10 | 2025-10-14 | 2026-01-13 | Summary | Planned | 530
FALSE |  | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE |  | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE |  | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE |  | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE |  | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE |  | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE |  | 0 |  | 7446 | NnBZUSVumxDXwVdCLN8g | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-09-14 | 2026-09-30 | 2026-09-14 | 2026-09-30 | Summary | Planned | 514
FALSE |  | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE |  | 0 |  | 4590 | 21lrGsmJiPqRYOd4yY3H | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Summary | Planned | 514
FALSE |  | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE |  | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE |  | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File | Aspose.Tasks.Calendar | 37 | 37 | 2026-09-18 | 2026-11-10 | 2025-10-08 | 2026-01-23 | Summary | Planned | 488
FALSE |  | 0 |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File | Aspose.Tasks.Calendar | 32 | 32 | 2026-09-18 | 2026-11-03 | 2025-10-08 | 2025-12-17 | Summary | Planned | 488
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE |  | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 512
FALSE |  | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE |  | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE |  | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 514
FALSE |  | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 514
FALSE |  | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 514
FALSE |  | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE |  | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE |  | 0 |  | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Summary | Planned | 510
FALSE |  | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE |  | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 510
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE |  | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE |  | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE |  | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE |  | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE |  | 0 |  | 4059 | sH9kz6O2EFda2hu4x8Kx | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-10-26 | 2026-11-10 | 2025-11-12 | 2026-01-16 | Summary | Planned | 488
FALSE |  | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE |  | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE |  | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE |  | 0 |  | 4054 | WhXMUGkGRid5sulqMW8S | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-04 | 2026-11-10 | 2025-12-18 | 2026-01-23 | Summary | Planned | 488
FALSE |  | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE |  | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE |  | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE |  | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE |  | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE |  | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE |  | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE |  | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE |  | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE |  | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
Milestones
Number of milestones within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 79 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | Aspose.Tasks.Calendar | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 532
FALSE |  | 30 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 532
FALSE |  | 30 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 532
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE |  | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE |  | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE |  | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE |  | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE |  | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE |  | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE |  | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE |  | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE |  | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE |  | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE |  | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE |  | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE |  | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE |  | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE |  | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE |  | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE |  | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE |  | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE |  | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE |  | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE |  | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE |  | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE |  | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE |  | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE |  | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE |  | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE |  | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE |  | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE |  | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE |  | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE |  | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
Normal Tasks
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 79 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | Aspose.Tasks.Calendar | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 532
FALSE |  | 30 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 532
FALSE |  | 30 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 532
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE |  | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE |  | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE |  | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE |  | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE |  | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE |  | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE |  | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE |  | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE |  | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE |  | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE |  | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE |  | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE |  | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE |  | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE |  | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE |  | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE |  | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE |  | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE |  | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE |  | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE |  | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE |  | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE |  | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE |  | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE |  | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE |  | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE |  | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE |  | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE |  | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE |  | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE |  | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
Summaries
Number of summary activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 79 |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File | Aspose.Tasks.Calendar | 2874 | 611 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 0
FALSE |  | 61 |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File | Aspose.Tasks.Calendar | 2874 | 1132 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 0
FALSE |  | 68 |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File | Aspose.Tasks.Calendar | 2873 | 911 | 2017-06-07 | 2028-09-27 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 1
FALSE |  | 84 |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File | Aspose.Tasks.Calendar | 1928 | 315 | 2019-04-01 | 2026-11-10 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 488
FALSE |  | 82 |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File | Aspose.Tasks.Calendar | 1454 | 263 | 2021-01-04 | 2026-10-05 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 514
FALSE |  | 79 |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File | Aspose.Tasks.Calendar | 1390 | 288 | 2021-04-05 | 2026-10-05 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 514
FALSE |  | 82 |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File | Aspose.Tasks.Calendar | 1198 | 222 | 2022-01-06 | 2026-10-05 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 514
FALSE |  | 76 |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File | Aspose.Tasks.Calendar | 1144 | 274 | 2022-03-07 | 2026-09-16 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 526
FALSE |  | 77 |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File | Aspose.Tasks.Calendar | 1134 | 264 | 2022-04-04 | 2026-09-29 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 512
FALSE |  | 87 |  | 6297 | AqdIsKbIPOfZJkjKYjnG | Large Test File | Aspose.Tasks.Calendar | 928 | 118 | 2022-12-21 | 2026-08-26 | 2022-11-15 | 2026-08-26 | Summary | InProgress | 539
FALSE |  | 83 |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File | Aspose.Tasks.Calendar | 931 | 163 | 2023-01-03 | 2026-09-10 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 530
FALSE |  | 85 |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File | Aspose.Tasks.Calendar | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -26
FALSE |  | 85 |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File | Aspose.Tasks.Calendar | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -26
FALSE |  | 70 |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File | Aspose.Tasks.Calendar | 975 | 288 | 2023-02-23 | 2027-01-07 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 450
FALSE |  | 17 |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File | Aspose.Tasks.Calendar | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 30
FALSE |  | 68 |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File | Aspose.Tasks.Calendar | 972 | 309 | 2023-03-06 | 2027-01-01 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 455
FALSE |  | 79 |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File | Aspose.Tasks.Calendar | 823 | 172 | 2023-08-04 | 2026-11-10 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 488
FALSE |  | 31 |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File | Aspose.Tasks.Calendar | 800 | 552 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 510
FALSE |  | 65 |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File | Aspose.Tasks.Calendar | 800 | 277 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2025-05-30 | Summary | InProgress | -26
FALSE |  | 65 |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File | Aspose.Tasks.Calendar | 860 | 297 | 2023-08-07 | 2027-01-07 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 450
FALSE |  | 39 |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File | Aspose.Tasks.Calendar | 760 | 466 | 2023-09-05 | 2026-09-10 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 530
FALSE |  | 55 |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File | Aspose.Tasks.Calendar | 712 | 322 | 2023-09-05 | 2026-07-02 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 530
FALSE |  | 99 |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File | Aspose.Tasks.Calendar | 808 | 0 | 2023-10-12 | 2027-01-01 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 454
FALSE |  | 0 |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File | Aspose.Tasks.Calendar | 703 | 703 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 19
FALSE |  | 25 |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File | Aspose.Tasks.Calendar | 739 | 554 | 2023-10-18 | 2026-09-25 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 512
FALSE |  | 61 |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File | Aspose.Tasks.Calendar | 655 | 255 | 2024-03-04 | 2026-10-08 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 510
FALSE |  | 3 |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File | Aspose.Tasks.Calendar | 571 | 554 | 2024-08-01 | 2026-11-10 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 488
FALSE |  | 0 |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File | Aspose.Tasks.Calendar | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 325
FALSE |  | 0 |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File | Aspose.Tasks.Calendar | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 325
FALSE |  | 0 |  | 7388 | subTjNOw9tjXphx2xXzW | Large Test File | Aspose.Tasks.Calendar | 324 | 324 | 2025-06-18 | 2026-10-02 | 2025-06-18 | 2026-10-02 | Summary | Planned | 514
FALSE |  | 0 |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File | Aspose.Tasks.Calendar | 276 | 276 | 2025-06-23 | 2026-07-31 | 2024-09-26 | 2026-01-30 | Summary | Planned | 514
FALSE |  | 0 |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File | Aspose.Tasks.Calendar | 272 | 272 | 2025-06-27 | 2026-07-29 | 2025-06-27 | 2026-01-23 | Summary | Planned | 24
FALSE |  | 0 |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File | Aspose.Tasks.Calendar | 319 | 319 | 2025-10-07 | 2027-01-01 | 2025-06-24 | 2026-08-14 | Summary | Planned | 80
FALSE |  | 0 |  | 5277 | TgmqG1sR4A60sNmMtPcE | Large Test File | Aspose.Tasks.Calendar | 193 | 193 | 2025-10-07 | 2026-07-09 | 2024-04-30 | 2024-10-04 | Summary | Planned | -28
FALSE |  | 0 |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File | Aspose.Tasks.Calendar | 144 | 144 | 2026-01-15 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 11
FALSE |  | 0 |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File | Aspose.Tasks.Calendar | 126 | 126 | 2026-04-01 | 2026-09-29 | 2026-01-07 | 2026-07-07 | Summary | Planned | 512
FALSE |  | 0 |  | 4538 | aTyUglf0WPX6H8Zd17Iq | Large Test File | Aspose.Tasks.Calendar | 71 | 71 | 2026-04-20 | 2026-07-31 | 2025-12-18 | 2026-07-03 | Summary | Planned | 514
FALSE |  | 0 |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File | Aspose.Tasks.Calendar | 127 | 127 | 2026-04-23 | 2026-10-23 | 2025-06-26 | 2025-11-11 | Summary | Planned | 488
FALSE |  | 0 |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File | Aspose.Tasks.Calendar | 160 | 160 | 2026-05-15 | 2027-01-07 | 2026-04-07 | 2026-07-27 | Summary | Planned | 450
FALSE |  | 0 |  | 4140 | Lk7gef35zB3WaxM8Xyxe | Large Test File | Aspose.Tasks.Calendar | 48 | 48 | 2026-07-06 | 2026-09-10 | 2025-09-11 | 2026-01-13 | Summary | Planned | 530
FALSE |  | 0 |  | 4141 | HGo5Ep3pqhcsiM5K4QjA | Large Test File | Aspose.Tasks.Calendar | 23 | 23 | 2026-07-06 | 2026-08-05 | 2025-09-11 | 2025-10-13 | Summary | Planned | 530
FALSE |  | 0 |  | 7435 | nSo6tYchIu2Aw4YtE45u | Large Test File | Aspose.Tasks.Calendar | 44 | 44 | 2026-07-31 | 2026-10-02 | 2026-07-31 | 2026-10-02 | Summary | Planned | 514
FALSE |  | 0 |  | 7436 | Y83lvWkQwfsc3dMGwfVN | Large Test File | Aspose.Tasks.Calendar | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 514
FALSE |  | 0 |  | 7437 | E8EwVgjFQaEPGP66WsCb | Large Test File | Aspose.Tasks.Calendar | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 514
FALSE |  | 0 |  | 7441 | IcgrxiRjEYJLwuugm8N7 | Large Test File | Aspose.Tasks.Calendar | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 514
FALSE |  | 0 |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File | Aspose.Tasks.Calendar | 106 | 106 | 2026-08-05 | 2027-01-01 | 2026-05-01 | 2026-08-14 | Summary | Planned | 455
FALSE |  | 0 |  | 4144 | zaFQ6K5wegGvKt6DGuoz | Large Test File | Aspose.Tasks.Calendar | 25 | 25 | 2026-08-06 | 2026-09-10 | 2025-10-14 | 2026-01-13 | Summary | Planned | 530
FALSE |  | 0 |  | 7446 | NnBZUSVumxDXwVdCLN8g | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-09-14 | 2026-09-30 | 2026-09-14 | 2026-09-30 | Summary | Planned | 514
FALSE |  | 0 |  | 4590 | 21lrGsmJiPqRYOd4yY3H | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Summary | Planned | 514
FALSE |  | 0 |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File | Aspose.Tasks.Calendar | 37 | 37 | 2026-09-18 | 2026-11-10 | 2025-10-08 | 2026-01-23 | Summary | Planned | 488
FALSE |  | 0 |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File | Aspose.Tasks.Calendar | 32 | 32 | 2026-09-18 | 2026-11-03 | 2025-10-08 | 2025-12-17 | Summary | Planned | 488
FALSE |  | 0 |  | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Summary | Planned | 510
FALSE |  | 0 |  | 4059 | sH9kz6O2EFda2hu4x8Kx | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-10-26 | 2026-11-10 | 2025-11-12 | 2026-01-16 | Summary | Planned | 488
FALSE |  | 0 |  | 4054 | WhXMUGkGRid5sulqMW8S | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-04 | 2026-11-10 | 2025-12-18 | 2026-01-23 | Summary | Planned | 488
Total Tasks & Milestones
Total number of regular tasks and milestones in the project schedule.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 79 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | Aspose.Tasks.Calendar | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 532
FALSE |  | 30 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 532
FALSE |  | 30 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 532
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE |  | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE |  | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 514
FALSE |  | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 514
FALSE |  | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE |  | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 19
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 19
FALSE |  | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE |  | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE |  | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE |  | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE |  | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE |  | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE |  | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE |  | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE |  | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE |  | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE |  | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 512
FALSE |  | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE |  | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE |  | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 514
FALSE |  | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 514
FALSE |  | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 514
FALSE |  | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE |  | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE |  | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE |  | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 510
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE |  | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE |  | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE |  | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE |  | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE |  | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE |  | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE |  | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE |  | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE |  | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE |  | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE |  | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE |  | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE |  | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE |  | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE |  | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE |  | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE |  | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
Total Activities (To-Go) - % of Total
The total number of activities within a grouping. Percentage shows total total to-go (planned and in-progress) activities (normal, milestone, summary and LOE) out of total to-go and completed activities.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 79 |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File | Aspose.Tasks.Calendar | 2874 | 611 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 0
FALSE |  | 61 |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File | Aspose.Tasks.Calendar | 2874 | 1132 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 0
FALSE |  | 68 |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File | Aspose.Tasks.Calendar | 2873 | 911 | 2017-06-07 | 2028-09-27 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 1
FALSE |  | 84 |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File | Aspose.Tasks.Calendar | 1928 | 315 | 2019-04-01 | 2026-11-10 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 488
FALSE |  | 79 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | Aspose.Tasks.Calendar | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 532
FALSE |  | 82 |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File | Aspose.Tasks.Calendar | 1454 | 263 | 2021-01-04 | 2026-10-05 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 514
FALSE |  | 79 |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File | Aspose.Tasks.Calendar | 1390 | 288 | 2021-04-05 | 2026-10-05 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 514
FALSE |  | 82 |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File | Aspose.Tasks.Calendar | 1198 | 222 | 2022-01-06 | 2026-10-05 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 514
FALSE |  | 76 |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File | Aspose.Tasks.Calendar | 1144 | 274 | 2022-03-07 | 2026-09-16 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 526
FALSE |  | 77 |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File | Aspose.Tasks.Calendar | 1134 | 264 | 2022-04-04 | 2026-09-29 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 512
FALSE |  | 87 |  | 6297 | AqdIsKbIPOfZJkjKYjnG | Large Test File | Aspose.Tasks.Calendar | 928 | 118 | 2022-12-21 | 2026-08-26 | 2022-11-15 | 2026-08-26 | Summary | InProgress | 539
FALSE |  | 83 |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File | Aspose.Tasks.Calendar | 931 | 163 | 2023-01-03 | 2026-09-10 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 530
FALSE |  | 85 |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File | Aspose.Tasks.Calendar | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -26
FALSE |  | 85 |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File | Aspose.Tasks.Calendar | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -26
FALSE |  | 70 |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File | Aspose.Tasks.Calendar | 975 | 288 | 2023-02-23 | 2027-01-07 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 450
FALSE |  | 17 |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File | Aspose.Tasks.Calendar | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 30
FALSE |  | 68 |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File | Aspose.Tasks.Calendar | 972 | 309 | 2023-03-06 | 2027-01-01 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 455
FALSE |  | 79 |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File | Aspose.Tasks.Calendar | 823 | 172 | 2023-08-04 | 2026-11-10 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 488
FALSE |  | 31 |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File | Aspose.Tasks.Calendar | 800 | 552 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 510
FALSE |  | 65 |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File | Aspose.Tasks.Calendar | 800 | 277 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2025-05-30 | Summary | InProgress | -26
FALSE |  | 65 |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File | Aspose.Tasks.Calendar | 860 | 297 | 2023-08-07 | 2027-01-07 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 450
FALSE |  | 39 |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File | Aspose.Tasks.Calendar | 760 | 466 | 2023-09-05 | 2026-09-10 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 530
FALSE |  | 55 |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File | Aspose.Tasks.Calendar | 712 | 322 | 2023-09-05 | 2026-07-02 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 530
FALSE |  | 99 |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File | Aspose.Tasks.Calendar | 808 | 0 | 2023-10-12 | 2027-01-01 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 454
FALSE |  | 0 |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File | Aspose.Tasks.Calendar | 703 | 703 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 19
FALSE |  | 25 |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File | Aspose.Tasks.Calendar | 739 | 554 | 2023-10-18 | 2026-09-25 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 512
FALSE |  | 61 |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File | Aspose.Tasks.Calendar | 655 | 255 | 2024-03-04 | 2026-10-08 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 510
FALSE |  | 30 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 532
FALSE |  | 30 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 532
FALSE |  | 3 |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File | Aspose.Tasks.Calendar | 571 | 554 | 2024-08-01 | 2026-11-10 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 488
FALSE |  | 0 |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File | Aspose.Tasks.Calendar | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 325
FALSE |  | 0 |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File | Aspose.Tasks.Calendar | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 325
FALSE |  | 0 |  | 7388 | subTjNOw9tjXphx2xXzW | Large Test File | Aspose.Tasks.Calendar | 324 | 324 | 2025-06-18 | 2026-10-02 | 2025-06-18 | 2026-10-02 | Summary | Planned | 514
FALSE |  | 0 |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File | Aspose.Tasks.Calendar | 276 | 276 | 2025-06-23 | 2026-07-31 | 2024-09-26 | 2026-01-30 | Summary | Planned | 514
FALSE |  | 0 |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File | Aspose.Tasks.Calendar | 272 | 272 | 2025-06-27 | 2026-07-29 | 2025-06-27 | 2026-01-23 | Summary | Planned | 24
FALSE |  | 0 |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File | Aspose.Tasks.Calendar | 319 | 319 | 2025-10-07 | 2027-01-01 | 2025-06-24 | 2026-08-14 | Summary | Planned | 80
FALSE |  | 0 |  | 5277 | TgmqG1sR4A60sNmMtPcE | Large Test File | Aspose.Tasks.Calendar | 193 | 193 | 2025-10-07 | 2026-07-09 | 2024-04-30 | 2024-10-04 | Summary | Planned | -28
FALSE |  | 0 |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File | Aspose.Tasks.Calendar | 144 | 144 | 2026-01-15 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 11
FALSE |  | 0 |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File | Aspose.Tasks.Calendar | 126 | 126 | 2026-04-01 | 2026-09-29 | 2026-01-07 | 2026-07-07 | Summary | Planned | 512
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE |  | 0 |  | 4538 | aTyUglf0WPX6H8Zd17Iq | Large Test File | Aspose.Tasks.Calendar | 71 | 71 | 2026-04-20 | 2026-07-31 | 2025-12-18 | 2026-07-03 | Summary | Planned | 514
FALSE |  | 0 |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File | Aspose.Tasks.Calendar | 127 | 127 | 2026-04-23 | 2026-10-23 | 2025-06-26 | 2025-11-11 | Summary | Planned | 488
FALSE |  | 0 |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File | Aspose.Tasks.Calendar | 160 | 160 | 2026-05-15 | 2027-01-07 | 2026-04-07 | 2026-07-27 | Summary | Planned | 450
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE |  | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 |  | 4140 | Lk7gef35zB3WaxM8Xyxe | Large Test File | Aspose.Tasks.Calendar | 48 | 48 | 2026-07-06 | 2026-09-10 | 2025-09-11 | 2026-01-13 | Summary | Planned | 530
FALSE |  | 0 |  | 4141 | HGo5Ep3pqhcsiM5K4QjA | Large Test File | Aspose.Tasks.Calendar | 23 | 23 | 2026-07-06 | 2026-08-05 | 2025-09-11 | 2025-10-13 | Summary | Planned | 530
FALSE |  | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE |  | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 514
FALSE |  | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 514
FALSE |  | 0 |  | 7435 | nSo6tYchIu2Aw4YtE45u | Large Test File | Aspose.Tasks.Calendar | 44 | 44 | 2026-07-31 | 2026-10-02 | 2026-07-31 | 2026-10-02 | Summary | Planned | 514
FALSE |  | 0 |  | 7436 | Y83lvWkQwfsc3dMGwfVN | Large Test File | Aspose.Tasks.Calendar | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 514
FALSE |  | 0 |  | 7437 | E8EwVgjFQaEPGP66WsCb | Large Test File | Aspose.Tasks.Calendar | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 514
FALSE |  | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7441 | IcgrxiRjEYJLwuugm8N7 | Large Test File | Aspose.Tasks.Calendar | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 514
FALSE |  | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE |  | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 19
FALSE |  | 0 |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File | Aspose.Tasks.Calendar | 106 | 106 | 2026-08-05 | 2027-01-01 | 2026-05-01 | 2026-08-14 | Summary | Planned | 455
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 19
FALSE |  | 0 |  | 4144 | zaFQ6K5wegGvKt6DGuoz | Large Test File | Aspose.Tasks.Calendar | 25 | 25 | 2026-08-06 | 2026-09-10 | 2025-10-14 | 2026-01-13 | Summary | Planned | 530
FALSE |  | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE |  | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE |  | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE |  | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE |  | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE |  | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE |  | 0 |  | 7446 | NnBZUSVumxDXwVdCLN8g | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-09-14 | 2026-09-30 | 2026-09-14 | 2026-09-30 | Summary | Planned | 514
FALSE |  | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE |  | 0 |  | 4590 | 21lrGsmJiPqRYOd4yY3H | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Summary | Planned | 514
FALSE |  | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE |  | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE |  | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File | Aspose.Tasks.Calendar | 37 | 37 | 2026-09-18 | 2026-11-10 | 2025-10-08 | 2026-01-23 | Summary | Planned | 488
FALSE |  | 0 |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File | Aspose.Tasks.Calendar | 32 | 32 | 2026-09-18 | 2026-11-03 | 2025-10-08 | 2025-12-17 | Summary | Planned | 488
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE |  | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 512
FALSE |  | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE |  | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE |  | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 514
FALSE |  | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 514
FALSE |  | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 514
FALSE |  | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE |  | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE |  | 0 |  | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Summary | Planned | 510
FALSE |  | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE |  | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 510
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE |  | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE |  | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE |  | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE |  | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE |  | 0 |  | 4059 | sH9kz6O2EFda2hu4x8Kx | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-10-26 | 2026-11-10 | 2025-11-12 | 2026-01-16 | Summary | Planned | 488
FALSE |  | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE |  | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE |  | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE |  | 0 |  | 4054 | WhXMUGkGRid5sulqMW8S | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-04 | 2026-11-10 | 2025-12-18 | 2026-01-23 | Summary | Planned | 488
FALSE |  | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE |  | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE |  | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE |  | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE |  | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE |  | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE |  | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE |  | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE |  | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE |  | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
Tasks & Milestones (To-Go) - % of Total To-Go
The total number of activities within a grouping. Percentage shows total to-go (planned and in-progress) tasks and milestones out of all activities (normal, milestone, summary, and LOE).
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 79 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | Aspose.Tasks.Calendar | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 532
FALSE |  | 30 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 532
FALSE |  | 30 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 532
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE |  | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE |  | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 514
FALSE |  | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 514
FALSE |  | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE |  | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 19
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 19
FALSE |  | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE |  | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE |  | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE |  | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE |  | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE |  | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE |  | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE |  | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE |  | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE |  | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE |  | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 512
FALSE |  | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE |  | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE |  | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 514
FALSE |  | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 514
FALSE |  | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 514
FALSE |  | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE |  | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE |  | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE |  | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 510
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE |  | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE |  | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE |  | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE |  | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE |  | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE |  | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE |  | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE |  | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE |  | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE |  | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE |  | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE |  | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE |  | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE |  | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE |  | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE |  | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE |  | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
Milestones (To-Go)
Number of milestones within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE |  | 0 |  | 196 | kzYOxx4jS6vhIcTyxNFn | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-01-30 | 2026-01-30 | Milestone | Planned | 514
FALSE |  | 0 |  | 7434 | MkjgnYEnwrIrITdXMEl9 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 514
FALSE |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 19
FALSE |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 19
FALSE |  | 0 |  | 180 | 9Vp3PBZnh9TpV8TGBWRG | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-09-25 | 2026-09-25 | 2025-02-07 | 2025-02-11 | Milestone | Planned | 512
FALSE |  | 0 |  | 152 | QJ29ZvAvtEjBcpqHDer1 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-01-29 | 2026-01-29 | Milestone | Planned | 514
FALSE |  | 0 |  | 150 | 7cu6yvdJV8ndF0CYMHk8 | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2025-12-15 | 2026-01-28 | Milestone | Planned | 514
FALSE |  | 0 |  | 7451 | nShmtMdGhMi3SzNeAZjW | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Milestone | Planned | 514
FALSE |  | 0 |  | 155 | 1yu6CrDX9QU5hWE1UWMV | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-10-15 | 2025-10-15 | Milestone | Planned | 510
FALSE |  | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE |  | 0 |  | 5523 | APkwTVep7mUhgmcCl4NB | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 |  | 5527 | Mw5Re8SivA42laH7UhJE | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-09-01 | 2026-09-01 | Milestone | Planned | 510
FALSE |  | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE |  | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26
Normal Tasks (To-Go)
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 79 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File | Aspose.Tasks.Calendar | 1874 | 396 | 2019-04-15 | 2026-09-08 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 532
FALSE |  | 30 |  | 6689 | fEYxMDiPOAwjjU8zha5c | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-25 | Normal | InProgress | 532
FALSE |  | 30 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File | Aspose.Tasks.Calendar | 569 | 396 | 2024-06-03 | 2026-09-08 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 532
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File | Aspose.Tasks.Calendar | 122 | 122 | 2026-04-03 | 2026-09-25 | 2026-01-09 | 2026-07-03 | Normal | Planned | 512
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File | Aspose.Tasks.Calendar | 72 | 72 | 2026-06-05 | 2026-09-17 | 2025-08-08 | 2025-10-07 | Normal | Planned | 488
FALSE |  | 0 |  | 6513 | IG8fHoH3vjERJ6iSB3Rj | Large Test File | Aspose.Tasks.Calendar | 36 | 36 | 2026-06-09 | 2026-07-31 | 2026-05-12 | 2026-07-03 | Normal | Planned | 514
FALSE |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 |  | 4139 | 9SKpfzivi43NDDuHUq0B | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-26 | 2026-07-02 | 2025-09-04 | 2025-09-10 | Normal | Planned | 530
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-06-30 | 2026-07-08 | 2025-12-24 | 2025-12-31 | Normal | Planned | 24
FALSE |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 |  | 4142 | VTqJrDLpWuaSlvRQajcM | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-06 | 2026-07-21 | 2025-09-11 | 2025-09-26 | Normal | Planned | 530
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-08 | 2026-07-22 | 2026-01-02 | 2026-01-15 | Normal | Planned | 24
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 |  | 4143 | UwGhtpl5Mnq9WQrcrXRR | Large Test File | Aspose.Tasks.Calendar | 11 | 11 | 2026-07-22 | 2026-08-05 | 2025-09-29 | 2025-10-13 | Normal | Planned | 530
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-22 | 2026-07-29 | 2026-01-16 | 2026-01-23 | Normal | Planned | 24
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 496
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 |  | 7438 | y2P0mgWq1uFkM4aVxtQJ | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7442 | B8zfbswYxyRxHa21jaE6 | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-07-31 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Normal | Planned | 514
FALSE |  | 0 |  | 7444 | 419IszMaZW6XNIQptprk | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-07-31 | 2026-08-28 | 2026-07-31 | 2026-08-28 | Normal | Planned | 524
FALSE |  | 0 |  | 7445 | oNfFp4VAwKEpoSujTbHZ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-07-31 | 2026-08-14 | 2026-07-31 | 2026-08-14 | Normal | Planned | 534
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 19
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 463
FALSE |  | 0 |  | 4145 | S2ZZUpnRVAnUNmaYAkv9 | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-06 | 2026-08-19 | 2025-10-14 | 2025-10-27 | Normal | Planned | 530
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 455
FALSE |  | 0 |  | 4146 | rTeXGnIwGPt6ES3ynSHq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-20 | 2026-08-26 | 2025-10-28 | 2025-11-03 | Normal | Planned | 530
FALSE |  | 0 |  | 7439 | nsJKxwZOWJc3LdYsNOwr | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-08-21 | 2026-08-28 | 2026-08-21 | 2026-08-28 | Normal | Planned | 514
FALSE |  | 0 |  | 7443 | lvFKaF8Jtq8DkkB0s9nv | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-08-21 | 2026-09-14 | 2026-08-21 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6080 | jFrzSNmYyPDtKSvRlBw2 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 539
FALSE |  | 0 |  | 4147 | hQaW5HIstT5bbsPEBxyQ | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-27 | 2026-09-10 | 2025-11-04 | 2026-01-13 | Normal | Planned | 530
FALSE |  | 0 |  | 7440 | 3ZzL4TktDwncii0hY2dA | Large Test File | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-28 | 2026-09-14 | 2026-08-28 | 2026-09-14 | Normal | Planned | 514
FALSE |  | 0 |  | 6690 | bopLkaAZbmZjIM9EGI6L | Large Test File | Aspose.Tasks.Calendar | 532 | 532 | 2026-09-08 | 2028-09-27 | 2026-09-08 | 2028-09-29 | Normal | Planned | 1
FALSE |  | 0 |  | 7447 | CAsJ3atkVCS14hehUB9Y | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-09-14 | 2026-09-18 | 2026-09-14 | 2026-09-18 | Normal | Planned | 514
FALSE |  | 0 |  | 1570 | 9hmrS48cr19KgrseY4yN | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Normal | Planned | 514
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File | Aspose.Tasks.Calendar | 9 | 9 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 455
FALSE |  | 0 |  | 795 | 85yV4lhIxXIziyB5R2QA | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-09-16 | 2026-09-17 | 2026-08-17 | 2026-08-18 | Normal | Planned | 524
FALSE |  | 0 |  | 7448 | 8tMCh2h8AwE53TPPkfEv | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 | Normal | Planned | 514
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-09-18 | 2026-10-16 | 2025-10-08 | 2025-11-04 | Normal | Planned | 488
FALSE |  | 0 |  | 7449 | LaZxXVdUnGzqswRGUiV5 | Large Test File | Aspose.Tasks.Calendar | 7 | 7 | 2026-09-21 | 2026-09-30 | 2026-09-21 | 2026-09-30 | Normal | Planned | 514
FALSE |  | 0 |  | 5775 | D3NIdGcGrWNhiaQ0dYbY | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-28 | 2026-09-29 | 2026-07-06 | 2026-07-07 | Normal | Planned | 512
FALSE |  | 0 |  | 7450 | F3vtt1T8lz7mQWFPgUKT | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-30 | 2026-10-02 | 2026-09-30 | 2026-10-02 | Normal | Planned | 514
FALSE |  | 0 |  | 844 | 1qfp8o9PQxr9vZvO7S5k | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-02 | 2026-09-02 | Normal | Planned | 514
FALSE |  | 0 |  | 6084 | deZM0xh115wln716GUoI | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-15 | 2026-09-15 | Normal | Planned | 514
FALSE |  | 0 |  | 6082 | YsSSuERf5VIDKO5m8eZo | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Normal | Planned | 510
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-08 | 2026-10-16 | 2026-04-30 | 2026-05-07 | Normal | Planned | 450
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 455
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 455
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File | Aspose.Tasks.Calendar | 15 | 15 | 2026-10-16 | 2026-11-06 | 2026-05-07 | 2026-05-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4049 | kP1jeiEwkYg4HRpUjG4p | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-19 | 2026-10-23 | 2025-11-05 | 2025-11-11 | Normal | Planned | 488
FALSE |  | 0 |  | 4053 | uYiMgxVAxCr7KnHZ9xA2 | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-10-19 | 2026-11-03 | 2025-11-05 | 2025-12-17 | Normal | Planned | 488
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 455
FALSE |  | 0 |  | 4060 | 6S9Iuo5kzbvnNzJK2SoM | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-26 | 2026-10-28 | 2025-11-12 | 2025-12-03 | Normal | Planned | 488
FALSE |  | 0 |  | 4061 | ViM2psfxppAdWr3IoYdq | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-10-29 | 2026-11-02 | 2025-12-04 | 2026-01-02 | Normal | Planned | 488
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 455
FALSE |  | 0 |  | 4062 | RvsEFsErXikPrAOovPaZ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-01-05 | 2026-01-06 | Normal | Planned | 488
FALSE |  | 0 |  | 4055 | dWrJCmOwv1i72p29KBXE | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-11-04 | 2026-11-05 | 2025-12-18 | 2026-01-08 | Normal | Planned | 488
FALSE |  | 0 |  | 4063 | ma6GKJ3GzeKmeF4AshaM | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-11-04 | 2026-11-09 | 2026-01-07 | 2026-01-14 | Normal | Planned | 488
FALSE |  | 0 |  | 4056 | a1SRK7UWhIIMlkKKriy9 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-06 | 2026-11-06 | 2026-01-09 | 2026-01-12 | Normal | Planned | 488
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-06 | 2026-11-13 | 2026-06-25 | 2026-07-02 | Normal | Planned | 455
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File | Aspose.Tasks.Calendar | 20 | 20 | 2026-11-06 | 2026-12-08 | 2026-05-29 | 2026-06-29 | Normal | Planned | 450
FALSE |  | 0 |  | 4057 | NKnvgqAHKv63TOKudyZQ | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-01-13 | 2026-01-21 | Normal | Planned | 488
FALSE |  | 0 |  | 4058 | cbANjhwCBqAluf1RM04K | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-22 | 2026-01-23 | Normal | Planned | 488
FALSE |  | 0 |  | 4064 | OALhjNOvEaqSDAmsS5Il | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-01-15 | 2026-01-16 | Normal | Planned | 488
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-13 | 2026-11-20 | 2026-07-02 | 2026-07-09 | Normal | Planned | 455
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-20 | 2026-11-27 | 2026-07-09 | 2026-07-16 | Normal | Planned | 455
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-27 | 2026-12-04 | 2026-07-16 | 2026-07-23 | Normal | Planned | 455
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-04 | 2026-12-11 | 2026-07-23 | 2026-07-30 | Normal | Planned | 455
FALSE |  | 0 |  | 3925 | hSr4t1vn7GiB6Kp7YK0M | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-08 | 2026-12-15 | 2026-06-29 | 2026-07-06 | Normal | Planned | 450
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-11 | 2026-12-18 | 2026-07-30 | 2026-08-06 | Normal | Planned | 455
FALSE |  | 0 |  | 3926 | vGJMK6sejFbKR6Gom2up | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-15 | 2026-12-22 | 2026-07-06 | 2026-07-13 | Normal | Planned | 450
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-18 | 2026-12-31 | 2026-08-06 | 2026-08-13 | Normal | Planned | 455
FALSE |  | 0 |  | 3927 | 3RLmiC17tI4E2ggNuRe0 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-22 | 2026-12-30 | 2026-07-13 | 2026-07-20 | Normal | Planned | 450
FALSE |  | 0 |  | 3928 | hCBFci3gUopMkWW2dQQj | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-30 | 2027-01-07 | 2026-07-20 | 2026-07-27 | Normal | Planned | 450
FALSE |  | 0 |  | 5325 | D5c4JntP5EU4thbOE4hi | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-12-31 | 2027-01-01 | 2026-08-14 | 2026-08-14 | Normal | Planned | 455
Summaries (To-Go)
Number of summary activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 79 |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File | Aspose.Tasks.Calendar | 2874 | 611 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 0
FALSE |  | 61 |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File | Aspose.Tasks.Calendar | 2874 | 1132 | 2017-06-07 | 2028-09-29 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 0
FALSE |  | 68 |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File | Aspose.Tasks.Calendar | 2873 | 911 | 2017-06-07 | 2028-09-27 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 1
FALSE |  | 84 |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File | Aspose.Tasks.Calendar | 1928 | 315 | 2019-04-01 | 2026-11-10 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 488
FALSE |  | 82 |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File | Aspose.Tasks.Calendar | 1454 | 263 | 2021-01-04 | 2026-10-05 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 514
FALSE |  | 79 |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File | Aspose.Tasks.Calendar | 1390 | 288 | 2021-04-05 | 2026-10-05 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 514
FALSE |  | 82 |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File | Aspose.Tasks.Calendar | 1198 | 222 | 2022-01-06 | 2026-10-05 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 514
FALSE |  | 76 |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File | Aspose.Tasks.Calendar | 1144 | 274 | 2022-03-07 | 2026-09-16 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 526
FALSE |  | 77 |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File | Aspose.Tasks.Calendar | 1134 | 264 | 2022-04-04 | 2026-09-29 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 512
FALSE |  | 87 |  | 6297 | AqdIsKbIPOfZJkjKYjnG | Large Test File | Aspose.Tasks.Calendar | 928 | 118 | 2022-12-21 | 2026-08-26 | 2022-11-15 | 2026-08-26 | Summary | InProgress | 539
FALSE |  | 83 |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File | Aspose.Tasks.Calendar | 931 | 163 | 2023-01-03 | 2026-09-10 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 530
FALSE |  | 85 |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File | Aspose.Tasks.Calendar | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -26
FALSE |  | 85 |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File | Aspose.Tasks.Calendar | 915 | 140 | 2023-02-23 | 2026-10-08 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -26
FALSE |  | 70 |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File | Aspose.Tasks.Calendar | 975 | 288 | 2023-02-23 | 2027-01-07 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 450
FALSE |  | 17 |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File | Aspose.Tasks.Calendar | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 30
FALSE |  | 68 |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File | Aspose.Tasks.Calendar | 972 | 309 | 2023-03-06 | 2027-01-01 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 455
FALSE |  | 79 |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File | Aspose.Tasks.Calendar | 823 | 172 | 2023-08-04 | 2026-11-10 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 488
FALSE |  | 31 |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File | Aspose.Tasks.Calendar | 800 | 552 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 510
FALSE |  | 65 |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File | Aspose.Tasks.Calendar | 800 | 277 | 2023-08-07 | 2026-10-08 | 2023-08-07 | 2025-05-30 | Summary | InProgress | -26
FALSE |  | 65 |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File | Aspose.Tasks.Calendar | 860 | 297 | 2023-08-07 | 2027-01-07 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 450
FALSE |  | 39 |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File | Aspose.Tasks.Calendar | 760 | 466 | 2023-09-05 | 2026-09-10 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 530
FALSE |  | 55 |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File | Aspose.Tasks.Calendar | 712 | 322 | 2023-09-05 | 2026-07-02 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 530
FALSE |  | 99 |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File | Aspose.Tasks.Calendar | 808 | 0 | 2023-10-12 | 2027-01-01 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 454
FALSE |  | 0 |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File | Aspose.Tasks.Calendar | 703 | 703 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 19
FALSE |  | 25 |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File | Aspose.Tasks.Calendar | 739 | 554 | 2023-10-18 | 2026-09-25 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 512
FALSE |  | 61 |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File | Aspose.Tasks.Calendar | 655 | 255 | 2024-03-04 | 2026-10-08 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 510
FALSE |  | 3 |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File | Aspose.Tasks.Calendar | 571 | 554 | 2024-08-01 | 2026-11-10 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 488
FALSE |  | 0 |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File | Aspose.Tasks.Calendar | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 325
FALSE |  | 0 |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File | Aspose.Tasks.Calendar | 391 | 391 | 2025-03-20 | 2026-10-08 | 2025-03-20 | 2026-09-01 | Summary | Planned | 325
FALSE |  | 0 |  | 7388 | subTjNOw9tjXphx2xXzW | Large Test File | Aspose.Tasks.Calendar | 324 | 324 | 2025-06-18 | 2026-10-02 | 2025-06-18 | 2026-10-02 | Summary | Planned | 514
FALSE |  | 0 |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File | Aspose.Tasks.Calendar | 276 | 276 | 2025-06-23 | 2026-07-31 | 2024-09-26 | 2026-01-30 | Summary | Planned | 514
FALSE |  | 0 |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File | Aspose.Tasks.Calendar | 272 | 272 | 2025-06-27 | 2026-07-29 | 2025-06-27 | 2026-01-23 | Summary | Planned | 24
FALSE |  | 0 |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File | Aspose.Tasks.Calendar | 319 | 319 | 2025-10-07 | 2027-01-01 | 2025-06-24 | 2026-08-14 | Summary | Planned | 80
FALSE |  | 0 |  | 5277 | TgmqG1sR4A60sNmMtPcE | Large Test File | Aspose.Tasks.Calendar | 193 | 193 | 2025-10-07 | 2026-07-09 | 2024-04-30 | 2024-10-04 | Summary | Planned | -28
FALSE |  | 0 |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File | Aspose.Tasks.Calendar | 144 | 144 | 2026-01-15 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 11
FALSE |  | 0 |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File | Aspose.Tasks.Calendar | 126 | 126 | 2026-04-01 | 2026-09-29 | 2026-01-07 | 2026-07-07 | Summary | Planned | 512
FALSE |  | 0 |  | 4538 | aTyUglf0WPX6H8Zd17Iq | Large Test File | Aspose.Tasks.Calendar | 71 | 71 | 2026-04-20 | 2026-07-31 | 2025-12-18 | 2026-07-03 | Summary | Planned | 514
FALSE |  | 0 |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File | Aspose.Tasks.Calendar | 127 | 127 | 2026-04-23 | 2026-10-23 | 2025-06-26 | 2025-11-11 | Summary | Planned | 488
FALSE |  | 0 |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File | Aspose.Tasks.Calendar | 160 | 160 | 2026-05-15 | 2027-01-07 | 2026-04-07 | 2026-07-27 | Summary | Planned | 450
FALSE |  | 0 |  | 4140 | Lk7gef35zB3WaxM8Xyxe | Large Test File | Aspose.Tasks.Calendar | 48 | 48 | 2026-07-06 | 2026-09-10 | 2025-09-11 | 2026-01-13 | Summary | Planned | 530
FALSE |  | 0 |  | 4141 | HGo5Ep3pqhcsiM5K4QjA | Large Test File | Aspose.Tasks.Calendar | 23 | 23 | 2026-07-06 | 2026-08-05 | 2025-09-11 | 2025-10-13 | Summary | Planned | 530
FALSE |  | 0 |  | 7435 | nSo6tYchIu2Aw4YtE45u | Large Test File | Aspose.Tasks.Calendar | 44 | 44 | 2026-07-31 | 2026-10-02 | 2026-07-31 | 2026-10-02 | Summary | Planned | 514
FALSE |  | 0 |  | 7436 | Y83lvWkQwfsc3dMGwfVN | Large Test File | Aspose.Tasks.Calendar | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 514
FALSE |  | 0 |  | 7437 | E8EwVgjFQaEPGP66WsCb | Large Test File | Aspose.Tasks.Calendar | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 514
FALSE |  | 0 |  | 7441 | IcgrxiRjEYJLwuugm8N7 | Large Test File | Aspose.Tasks.Calendar | 30 | 30 | 2026-07-31 | 2026-09-14 | 2026-07-31 | 2026-09-14 | Summary | Planned | 514
FALSE |  | 0 |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File | Aspose.Tasks.Calendar | 106 | 106 | 2026-08-05 | 2027-01-01 | 2026-05-01 | 2026-08-14 | Summary | Planned | 455
FALSE |  | 0 |  | 4144 | zaFQ6K5wegGvKt6DGuoz | Large Test File | Aspose.Tasks.Calendar | 25 | 25 | 2026-08-06 | 2026-09-10 | 2025-10-14 | 2026-01-13 | Summary | Planned | 530
FALSE |  | 0 |  | 7446 | NnBZUSVumxDXwVdCLN8g | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-09-14 | 2026-09-30 | 2026-09-14 | 2026-09-30 | Summary | Planned | 514
FALSE |  | 0 |  | 4590 | 21lrGsmJiPqRYOd4yY3H | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-09-14 | 2026-09-16 | 2026-08-14 | 2026-08-17 | Summary | Planned | 514
FALSE |  | 0 |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File | Aspose.Tasks.Calendar | 37 | 37 | 2026-09-18 | 2026-11-10 | 2025-10-08 | 2026-01-23 | Summary | Planned | 488
FALSE |  | 0 |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File | Aspose.Tasks.Calendar | 32 | 32 | 2026-09-18 | 2026-11-03 | 2025-10-08 | 2025-12-17 | Summary | Planned | 488
FALSE |  | 0 |  | 6301 | fAO5ZNKjSUxD4bzFvTE9 | Large Test File | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-08-17 | 2026-08-17 | Summary | Planned | 510
FALSE |  | 0 |  | 4059 | sH9kz6O2EFda2hu4x8Kx | Large Test File | Aspose.Tasks.Calendar | 12 | 12 | 2026-10-26 | 2026-11-10 | 2025-11-12 | 2026-01-16 | Summary | Planned | 488
FALSE |  | 0 |  | 4054 | WhXMUGkGRid5sulqMW8S | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-04 | 2026-11-10 | 2025-12-18 | 2026-01-23 | Summary | Planned | 488
Longest Path (Tasks & Milestones)
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
FALSE |  | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE |  | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE |  | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26
Longest Path (Normal Tasks)
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 5286 | Yb8sH9U5B9gBzfVjcJKN | Large Test File | Aspose.Tasks.Calendar | 6 | 6 | 2026-06-25 | 2026-07-02 | 2024-09-20 | 2024-09-27 | Normal | Planned | -28
FALSE |  | 0 |  | 5287 | bhDhrVJ9ZVKMNyReuPKm | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-02 | 2026-07-09 | 2024-09-27 | 2024-10-04 | Normal | Planned | -28
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -28
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -28
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -28
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -28
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -26
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File | Aspose.Tasks.Calendar | 49 | 49 | 2026-07-30 | 2026-10-08 | 2024-12-26 | 2025-01-24 | Normal | Planned | -26
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -27
Longest Path (Milestones)
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 5288 | RIVzpLwElpoiAIgfwKiL | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-07-09 | 2026-07-09 | 2024-10-04 | 2024-10-04 | Milestone | Planned | -28
FALSE |  | 0 |  | 5746 | 9Uq3Ix5n2BJf2VZJ21kx | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2023-08-07 | 2024-05-31 | Milestone | Planned | -26
FALSE |  | 0 |  | 156 | 0RXSkgYJdrs7AeQvgU3w | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-05-15 | 2025-05-15 | Milestone | Planned | -26
FALSE |  | 0 |  | 157 | DYCfhHgWVvjY4WPSrw6q | Large Test File | Aspose.Tasks.Calendar | 0 | 0 | 2026-10-08 | 2026-10-08 | 2025-06-16 | 2025-06-16 | Milestone | Planned | -26

## Large-Test-File22
Fuse® Analyst Report
Workbook: Large Test File vs Large Test File2 - 4249 Activities
Quick Add Metrics
Created on: 7/15/2026
Created by: dpolitte
Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View | Large Test File2: Detailed View
4. SS/FF Relations
Number of Start to Start (SS) and Finish to Finish (FF) logic links. Should be lower than 10%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
6. High Float
Number of activities with total float greater than 2 months. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
7. Negative Float
Activities that are incomplete and have total float less than 0 working days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
8. High Duration
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
10. Resources
Number of activities that do not have resources/costs assigned
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
11. Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
Remaining Work
Calculation of total remaining work for all activities within a grouping
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Missing Resources
Number of activities that are not carrying resources
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
Resources
Number of activities that are carrying resources
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Negative Planned Cost
Activities that have a negative planned cost.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
Critical
Number of critical activities
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Rem. Critical Duration
The amount of remaining time planned in order to complete all critical normal activities and milestones within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File2 | 3019 | 690 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 77 | 0
FALSE |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File2 | 3019 | 1201 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 60 | 0
FALSE |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File2 | 3019 | 634 | 2017-06-07 | 2029-04-20 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 79 | 0
FALSE |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File2 | 3006 | 876 | 2017-06-07 | 2029-04-03 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 71 | 13
FALSE |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File2 | 2452 | 792 | 2017-06-07 | 2027-02-17 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 68 | 567
FALSE |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File2 | 2632 | 0 | 2017-12-28 | 2028-05-11 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 99 | 245
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File2 | 1996 | 361 | 2019-04-01 | 2027-02-19 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 82 | 565
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 6315 | 2iW64uJmzViIcLEo0dMn | Large Test File2 | 1909 | 422 | 2021-01-04 | 2028-07-10 | 2021-01-04 | 2025-11-07 | Summary | InProgress | 78 | 24
FALSE |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File2 | 2049 | 428 | 2021-04-05 | 2029-04-20 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 79 | 0
FALSE |  | 6317 | NzqiT3qChWGoVO5Oxj9C | Large Test File2 | 1312 | 213 | 2021-08-09 | 2026-10-19 | 2021-07-06 | 2025-09-16 | Summary | InProgress | 84 | 478
FALSE |  | 5362 | 4bsxfawvV6TKTvCq9VoB | Large Test File2 | 1240 | 236 | 2021-08-09 | 2026-07-08 | 2021-07-06 | 2023-10-16 | Summary | InProgress | 81 | 490
FALSE |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File2 | 1857 | 309 | 2022-01-06 | 2029-04-20 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 83 | 0
FALSE |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File2 | 1203 | 297 | 2022-04-04 | 2027-01-12 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 75 | 588
FALSE |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File2 | 1514 | 262 | 2023-01-03 | 2028-12-12 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 83 | 93
FALSE |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File2 | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 83 | -34
FALSE |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File2 | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 83 | -34
FALSE |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File2 | 996 | 304 | 2023-02-23 | 2027-02-08 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 69 | 574
FALSE |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File2 | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 17 | 30
FALSE |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File2 | 975 | 320 | 2023-03-06 | 2027-01-06 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 67 | 597
FALSE |  | 870 | m3oEXpasu7ssfpw9dqLv | Large Test File2 | 1460 | 498 | 2023-03-20 | 2028-12-11 | 2023-03-20 | 2025-06-27 | Summary | InProgress | 66 | 0
FALSE |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File2 | 891 | 191 | 2023-08-04 | 2027-02-19 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 79 | 565
FALSE |  | 5375 | zkXPpJkHw8DPAtspwcmA | Large Test File2 | 800 | 190 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Summary | InProgress | 76 | 478
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File2 | 881 | 310 | 2023-08-07 | 2027-02-08 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 65 | 574
FALSE |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File2 | 1210 | 829 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 31 | 245
FALSE |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File2 | 1210 | 426 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2025-05-30 | Summary | InProgress | 65 | -436
FALSE |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File2 | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 245
FALSE |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File2 | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 245
FALSE |  | 7382 | GJk3wpkfagyrb21gVciV | Large Test File2 | 1339 | 1339 | 2023-08-07 | 2028-11-09 | 2025-02-07 | 2026-03-24 | Summary | Planned | 0 | 28
FALSE |  | 4129 | G6dPcJRrq5zqLYx4Vr0R | Large Test File2 | 1363 | 928 | 2023-08-07 | 2028-12-12 | 2023-08-07 | 2025-06-13 | Summary | InProgress | 32 | 5
FALSE |  | 5753 | ZptYdARXANY2IOcoHhB1 | Large Test File2 | 1128 | 148 | 2023-08-07 | 2028-01-19 | 2023-08-07 | 2024-02-01 | Summary | InProgress | 87 | -80
FALSE |  | 5537 | 9xVQhmyTVkChMoMOy91g | Large Test File2 | 1214 | 637 | 2023-08-21 | 2028-06-01 | 2023-08-16 | 2024-06-11 | Summary | InProgress | 48 | 24
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File2 | 1218 | 743 | 2023-09-05 | 2028-06-20 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 39 | 218
FALSE |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File2 | 1169 | 514 | 2023-09-05 | 2028-04-12 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 56 | 218
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File2 | 702 | 702 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 0 | 20
FALSE |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File2 | 808 | 597 | 2023-10-18 | 2027-01-08 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 26 | 588
FALSE |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File2 | 1093 | 431 | 2024-03-04 | 2028-06-20 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 61 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 4038 | VkrURyJwsSkEVRV6WcXe | Large Test File2 | 483 | 462 | 2024-08-01 | 2026-07-08 | 2024-08-01 | 2025-04-16 | Summary | InProgress | 5 | 565
FALSE |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File2 | 639 | 621 | 2024-08-01 | 2027-02-19 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 3 | 565
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5570 | MuDwSgsBJjDxwFkSMWYJ | Large Test File2 | 819 | 534 | 2024-11-18 | 2028-02-14 | 2024-02-05 | 2024-05-20 | Summary | InProgress | 35 | 45
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 5557 | U376LwOjKfNZoVLUlmMD | Large Test File2 | 749 | 749 | 2025-04-02 | 2028-03-14 | 2024-01-05 | 2024-04-22 | Summary | Planned | 0 | 24
FALSE |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File2 | 343 | 343 | 2025-04-10 | 2026-08-24 | 2025-06-27 | 2026-01-23 | Summary | Planned | 0 | 7
FALSE |  | 5544 | cIc3ARzcdrbXv6maHllr | Large Test File2 | 765 | 765 | 2025-04-15 | 2028-04-19 | 2023-12-06 | 2024-03-25 | Summary | Planned | 0 | 24
FALSE |  | 5583 | gkFBoXdv1oJb2jtBcO5M | Large Test File2 | 790 | 790 | 2025-04-23 | 2028-06-01 | 2024-03-04 | 2024-06-11 | Summary | Planned | 0 | 24
FALSE |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File2 | 345 | 345 | 2025-09-04 | 2027-01-06 | 2025-06-24 | 2026-08-14 | Summary | Planned | 0 | 80
FALSE |  | 5402 | zDUD70mdAG3rcozejCwk | Large Test File2 | 279 | 279 | 2025-09-05 | 2026-10-19 | 2025-08-26 | 2025-09-16 | Summary | Planned | 0 | 478
FALSE |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File2 | 872 | 872 | 2025-09-19 | 2029-02-14 | 2024-09-26 | 2026-01-30 | Summary | Planned | 0 | 8
FALSE |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File2 | 120 | 120 | 2026-02-18 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 0 | -36
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File2 | 160 | 160 | 2026-06-16 | 2027-02-08 | 2026-04-07 | 2026-07-27 | Summary | Planned | 0 | 574
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File2 | 136 | 136 | 2026-06-24 | 2027-01-12 | 2026-01-07 | 2026-07-07 | Summary | Planned | 0 | 588
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7264 | vNqQNKJIEgg8BiBzdWeI | Large Test File2 | 57 | 57 | 2026-07-02 | 2026-09-23 | 2025-04-04 | 2025-06-25 | Summary | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File2 | 145 | 145 | 2026-07-08 | 2027-02-04 | 2025-06-26 | 2025-11-11 | Summary | Planned | 0 | 565
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File2 | 110 | 110 | 2026-08-05 | 2027-01-06 | 2026-05-01 | 2026-08-14 | Summary | Planned | 0 | 597
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File2 | 40 | 40 | 2026-12-23 | 2027-02-19 | 2025-10-08 | 2026-01-23 | Summary | Planned | 0 | 565
FALSE |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File2 | 32 | 32 | 2026-12-23 | 2027-02-09 | 2025-10-08 | 2025-12-17 | Summary | Planned | 0 | 568
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Longest Path
Activities that together form the longest path through to project completion.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Forecast to be Finished
Forecast to be finished before time now
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Project Time Now | Type | Status | Percent Complete
7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 363 | 2019-04-01 | 2019-01-15 | 2026-08-20 | 2025-01-03 | 2025-03-10 | Normal | InProgress | 80
5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 56 | 2023-08-07 | 2024-03-27 | 2026-10-09 | 2024-04-16 | 2025-03-10 | Normal | InProgress | 76
5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 628 | 2023-08-23 | 2023-08-23 | 2027-09-02 | 2023-10-23 | 2025-03-10 | Normal | InProgress | 37
6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 23 | 2024-11-01 | 2024-04-26 | 2027-10-12 | 2024-06-11 | 2025-03-10 | Normal | InProgress | 52
5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 2026-07-02 | 2023-09-12 | 2026-07-08 | 2023-09-20 | 2025-03-10 | Normal | Planned | 0
5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 2026-07-20 | 2024-05-03 | 2026-07-21 | 2024-05-03 | 2025-03-10 | Normal | Planned | 0
5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 2026-07-30 | 2024-12-26 | 2026-10-21 | 2025-01-24 | 2025-03-10 | Normal | Planned | 0
Not Completed
Activities that were planned to be complete by now that are not complete.
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Type | Activity Status
7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 363 | 2019-04-01 | 2019-01-15 | 2026-08-20 | 2025-01-03 | Normal | InProgress
5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 56 | 2023-08-07 | 2024-03-27 | 2026-10-09 | 2024-04-16 | Normal | InProgress
5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 628 | 2023-08-23 | 2023-08-23 | 2027-09-02 | 2023-10-23 | Normal | InProgress
6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 23 | 2024-11-01 | 2024-04-26 | 2027-10-12 | 2024-06-11 | Normal | InProgress
5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 2026-07-02 | 2023-09-12 | 2026-07-08 | 2023-09-20 | Normal | Planned
5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 2026-07-20 | 2024-05-03 | 2026-07-21 | 2024-05-03 | Normal | Planned
5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 2026-07-30 | 2024-12-26 | 2026-10-21 | 2025-01-24 | Normal | Planned
Baseline Finish Compliance
Percentage of those activities forecast to be finished before time now that were finished on time.
Id | Description | Project | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Project Time Now | Type | Status | Percent Complete
7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | 2025-03-10 | Normal | InProgress | 80
5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | 2025-03-10 | Normal | InProgress | 76
5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | 2025-03-10 | Normal | InProgress | 37
6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | 2025-03-10 | Normal | InProgress | 52
5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | 2025-03-10 | Normal | Planned | 0
5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | 2025-03-10 | Normal | Planned | 0
5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | 2025-03-10 | Normal | Planned | 0
Forecast to be Started
Forecast to be started before time now
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Project Time Now | Type | Status | Percent Complete
7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 363 | 2019-04-01 | 2019-01-15 | 2026-08-20 | 2025-01-03 | 2025-03-10 | Normal | InProgress | 80
7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 418 | 2019-04-15 | 2019-04-15 | 2026-11-06 | 2026-09-04 | 2025-03-10 | Normal | InProgress | 78
5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 56 | 2023-08-07 | 2024-03-27 | 2026-10-09 | 2024-04-16 | 2025-03-10 | Normal | InProgress | 76
5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 628 | 2023-08-23 | 2023-08-23 | 2027-09-02 | 2023-10-23 | 2025-03-10 | Normal | InProgress | 37
6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 486 | 2024-06-03 | 2024-06-03 | 2027-02-17 | 2025-11-21 | 2025-03-10 | Normal | InProgress | 26
6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 23 | 2024-11-01 | 2024-04-26 | 2027-10-12 | 2024-06-11 | 2025-03-10 | Normal | InProgress | 52
5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 2026-07-02 | 2023-09-12 | 2026-07-08 | 2023-09-20 | 2025-03-10 | Normal | Planned | 0
5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 2026-07-20 | 2024-05-03 | 2026-07-21 | 2024-05-03 | 2025-03-10 | Normal | Planned | 0
5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 2026-07-30 | 2024-12-26 | 2026-10-21 | 2025-01-24 | 2025-03-10 | Normal | Planned | 0
Started On Time
Activities actually started on time, by their baseline start date.
Id | Description | Project | Start | Baseline Start | Finish | Baseline Finish | Type | Status
7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 2019-04-15 | 2019-04-15 | 2026-11-06 | 2026-09-04 | Normal | InProgress
5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 2023-08-07 | 2024-03-27 | 2026-10-09 | 2024-04-16 | Normal | InProgress
5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 2023-08-23 | 2023-08-23 | 2027-09-02 | 2023-10-23 | Normal | InProgress
6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 2024-06-03 | 2024-06-03 | 2027-02-17 | 2025-11-21 | Normal | InProgress
Started Late
Activities actually started but late, after their baseline start date.
Id | Description | Project | Start | Baseline Start | Finish | Baseline Finish | Type | Status
7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 2019-04-01 | 2019-01-15 | 2026-08-20 | 2025-01-03 | Normal | InProgress
6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 2024-11-01 | 2024-04-26 | 2027-10-12 | 2024-06-11 | Normal | InProgress
Not Started
Activities that were planned to be start by now that are not started.
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Type | Activity Status
5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 2026-07-02 | 2023-09-12 | 2026-07-08 | 2023-09-20 | Normal | Planned
5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 2026-07-20 | 2024-05-03 | 2026-07-21 | 2024-05-03 | Normal | Planned
5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 2026-07-30 | 2024-12-26 | 2026-10-21 | 2025-01-24 | Normal | Planned
Baseline Start Compliance
Percentage of those activities forecast to be started before time now that were started on time.
Id | Description | Project | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Project Time Now | Type | Status | Percent Complete
7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | 2025-03-10 | Normal | InProgress | 80
6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | 2025-03-10 | Normal | InProgress | 52
5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | 2025-03-10 | Normal | Planned | 0
5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | 2025-03-10 | Normal | Planned | 0
5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | 2025-03-10 | Normal | Planned | 0
Started Ahead
Number of activities that started before their planned start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
Started Delayed
Number of activities that started after their planned start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
In-Progress On Schedule
Number of activities that are currently underway and started on time.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
Actually Started
Total number of activities that have started.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
Planned Delayed
Number of activities that are currently planned to start after their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Scheduled to Start
Number of activities that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Scheduled to Finish
Number of activities within that are planned to finish.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Underway
Number of activities that are in-progress.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
Planned
Number of activities that have yet to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Planned Milestones
Number of milestones that are planned but not yet in-progress or complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
Not Completed
Total number of activities that have not been completed.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Negative Float
Number of activities with total float of less than 0 working days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
20 to 30 days float
Total number of activities with positive float of more than 20 and less than or equal to 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
Total Activities
The total number of activities within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File2 | 3019 | 690 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 77 | 0
FALSE |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File2 | 3019 | 1201 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 60 | 0
FALSE |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File2 | 3019 | 634 | 2017-06-07 | 2029-04-20 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 79 | 0
FALSE |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File2 | 3006 | 876 | 2017-06-07 | 2029-04-03 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 71 | 13
FALSE |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File2 | 2452 | 792 | 2017-06-07 | 2027-02-17 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 68 | 567
FALSE |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File2 | 2632 | 0 | 2017-12-28 | 2028-05-11 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 99 | 245
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File2 | 1996 | 361 | 2019-04-01 | 2027-02-19 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 82 | 565
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 6315 | 2iW64uJmzViIcLEo0dMn | Large Test File2 | 1909 | 422 | 2021-01-04 | 2028-07-10 | 2021-01-04 | 2025-11-07 | Summary | InProgress | 78 | 24
FALSE |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File2 | 2049 | 428 | 2021-04-05 | 2029-04-20 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 79 | 0
FALSE |  | 6317 | NzqiT3qChWGoVO5Oxj9C | Large Test File2 | 1312 | 213 | 2021-08-09 | 2026-10-19 | 2021-07-06 | 2025-09-16 | Summary | InProgress | 84 | 478
FALSE |  | 5362 | 4bsxfawvV6TKTvCq9VoB | Large Test File2 | 1240 | 236 | 2021-08-09 | 2026-07-08 | 2021-07-06 | 2023-10-16 | Summary | InProgress | 81 | 490
FALSE |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File2 | 1857 | 309 | 2022-01-06 | 2029-04-20 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 83 | 0
FALSE |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File2 | 1203 | 297 | 2022-04-04 | 2027-01-12 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 75 | 588
FALSE |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File2 | 1514 | 262 | 2023-01-03 | 2028-12-12 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 83 | 93
FALSE |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File2 | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 83 | -34
FALSE |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File2 | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 83 | -34
FALSE |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File2 | 996 | 304 | 2023-02-23 | 2027-02-08 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 69 | 574
FALSE |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File2 | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 17 | 30
FALSE |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File2 | 975 | 320 | 2023-03-06 | 2027-01-06 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 67 | 597
FALSE |  | 870 | m3oEXpasu7ssfpw9dqLv | Large Test File2 | 1460 | 498 | 2023-03-20 | 2028-12-11 | 2023-03-20 | 2025-06-27 | Summary | InProgress | 66 | 0
FALSE |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File2 | 891 | 191 | 2023-08-04 | 2027-02-19 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 79 | 565
FALSE |  | 5375 | zkXPpJkHw8DPAtspwcmA | Large Test File2 | 800 | 190 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Summary | InProgress | 76 | 478
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File2 | 881 | 310 | 2023-08-07 | 2027-02-08 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 65 | 574
FALSE |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File2 | 1210 | 829 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 31 | 245
FALSE |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File2 | 1210 | 426 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2025-05-30 | Summary | InProgress | 65 | -436
FALSE |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File2 | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 245
FALSE |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File2 | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 245
FALSE |  | 7382 | GJk3wpkfagyrb21gVciV | Large Test File2 | 1339 | 1339 | 2023-08-07 | 2028-11-09 | 2025-02-07 | 2026-03-24 | Summary | Planned | 0 | 28
FALSE |  | 4129 | G6dPcJRrq5zqLYx4Vr0R | Large Test File2 | 1363 | 928 | 2023-08-07 | 2028-12-12 | 2023-08-07 | 2025-06-13 | Summary | InProgress | 32 | 5
FALSE |  | 5753 | ZptYdARXANY2IOcoHhB1 | Large Test File2 | 1128 | 148 | 2023-08-07 | 2028-01-19 | 2023-08-07 | 2024-02-01 | Summary | InProgress | 87 | -80
FALSE |  | 5537 | 9xVQhmyTVkChMoMOy91g | Large Test File2 | 1214 | 637 | 2023-08-21 | 2028-06-01 | 2023-08-16 | 2024-06-11 | Summary | InProgress | 48 | 24
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File2 | 1218 | 743 | 2023-09-05 | 2028-06-20 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 39 | 218
FALSE |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File2 | 1169 | 514 | 2023-09-05 | 2028-04-12 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 56 | 218
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File2 | 702 | 702 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 0 | 20
FALSE |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File2 | 808 | 597 | 2023-10-18 | 2027-01-08 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 26 | 588
FALSE |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File2 | 1093 | 431 | 2024-03-04 | 2028-06-20 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 61 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 4038 | VkrURyJwsSkEVRV6WcXe | Large Test File2 | 483 | 462 | 2024-08-01 | 2026-07-08 | 2024-08-01 | 2025-04-16 | Summary | InProgress | 5 | 565
FALSE |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File2 | 639 | 621 | 2024-08-01 | 2027-02-19 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 3 | 565
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5570 | MuDwSgsBJjDxwFkSMWYJ | Large Test File2 | 819 | 534 | 2024-11-18 | 2028-02-14 | 2024-02-05 | 2024-05-20 | Summary | InProgress | 35 | 45
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 5557 | U376LwOjKfNZoVLUlmMD | Large Test File2 | 749 | 749 | 2025-04-02 | 2028-03-14 | 2024-01-05 | 2024-04-22 | Summary | Planned | 0 | 24
FALSE |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File2 | 343 | 343 | 2025-04-10 | 2026-08-24 | 2025-06-27 | 2026-01-23 | Summary | Planned | 0 | 7
FALSE |  | 5544 | cIc3ARzcdrbXv6maHllr | Large Test File2 | 765 | 765 | 2025-04-15 | 2028-04-19 | 2023-12-06 | 2024-03-25 | Summary | Planned | 0 | 24
FALSE |  | 5583 | gkFBoXdv1oJb2jtBcO5M | Large Test File2 | 790 | 790 | 2025-04-23 | 2028-06-01 | 2024-03-04 | 2024-06-11 | Summary | Planned | 0 | 24
FALSE |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File2 | 345 | 345 | 2025-09-04 | 2027-01-06 | 2025-06-24 | 2026-08-14 | Summary | Planned | 0 | 80
FALSE |  | 5402 | zDUD70mdAG3rcozejCwk | Large Test File2 | 279 | 279 | 2025-09-05 | 2026-10-19 | 2025-08-26 | 2025-09-16 | Summary | Planned | 0 | 478
FALSE |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File2 | 872 | 872 | 2025-09-19 | 2029-02-14 | 2024-09-26 | 2026-01-30 | Summary | Planned | 0 | 8
FALSE |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File2 | 120 | 120 | 2026-02-18 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 0 | -36
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File2 | 160 | 160 | 2026-06-16 | 2027-02-08 | 2026-04-07 | 2026-07-27 | Summary | Planned | 0 | 574
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File2 | 136 | 136 | 2026-06-24 | 2027-01-12 | 2026-01-07 | 2026-07-07 | Summary | Planned | 0 | 588
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7264 | vNqQNKJIEgg8BiBzdWeI | Large Test File2 | 57 | 57 | 2026-07-02 | 2026-09-23 | 2025-04-04 | 2025-06-25 | Summary | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File2 | 145 | 145 | 2026-07-08 | 2027-02-04 | 2025-06-26 | 2025-11-11 | Summary | Planned | 0 | 565
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File2 | 110 | 110 | 2026-08-05 | 2027-01-06 | 2026-05-01 | 2026-08-14 | Summary | Planned | 0 | 597
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File2 | 40 | 40 | 2026-12-23 | 2027-02-19 | 2025-10-08 | 2026-01-23 | Summary | Planned | 0 | 565
FALSE |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File2 | 32 | 32 | 2026-12-23 | 2027-02-09 | 2025-10-08 | 2025-12-17 | Summary | Planned | 0 | 568
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Milestones
Number of milestones within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
Normal
Number of normal activities within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Summaries
Number of summary activities within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File2 | 3019 | 690 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 77 | 0
FALSE |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File2 | 3019 | 1201 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 60 | 0
FALSE |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File2 | 3019 | 634 | 2017-06-07 | 2029-04-20 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 79 | 0
FALSE |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File2 | 3006 | 876 | 2017-06-07 | 2029-04-03 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 71 | 13
FALSE |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File2 | 2452 | 792 | 2017-06-07 | 2027-02-17 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 68 | 567
FALSE |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File2 | 2632 | 0 | 2017-12-28 | 2028-05-11 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 99 | 245
FALSE |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File2 | 1996 | 361 | 2019-04-01 | 2027-02-19 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 82 | 565
FALSE |  | 6315 | 2iW64uJmzViIcLEo0dMn | Large Test File2 | 1909 | 422 | 2021-01-04 | 2028-07-10 | 2021-01-04 | 2025-11-07 | Summary | InProgress | 78 | 24
FALSE |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File2 | 2049 | 428 | 2021-04-05 | 2029-04-20 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 79 | 0
FALSE |  | 6317 | NzqiT3qChWGoVO5Oxj9C | Large Test File2 | 1312 | 213 | 2021-08-09 | 2026-10-19 | 2021-07-06 | 2025-09-16 | Summary | InProgress | 84 | 478
FALSE |  | 5362 | 4bsxfawvV6TKTvCq9VoB | Large Test File2 | 1240 | 236 | 2021-08-09 | 2026-07-08 | 2021-07-06 | 2023-10-16 | Summary | InProgress | 81 | 490
FALSE |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File2 | 1857 | 309 | 2022-01-06 | 2029-04-20 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 83 | 0
FALSE |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File2 | 1203 | 297 | 2022-04-04 | 2027-01-12 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 75 | 588
FALSE |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File2 | 1514 | 262 | 2023-01-03 | 2028-12-12 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 83 | 93
FALSE |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File2 | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 83 | -34
FALSE |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File2 | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 83 | -34
FALSE |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File2 | 996 | 304 | 2023-02-23 | 2027-02-08 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 69 | 574
FALSE |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File2 | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 17 | 30
FALSE |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File2 | 975 | 320 | 2023-03-06 | 2027-01-06 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 67 | 597
FALSE |  | 870 | m3oEXpasu7ssfpw9dqLv | Large Test File2 | 1460 | 498 | 2023-03-20 | 2028-12-11 | 2023-03-20 | 2025-06-27 | Summary | InProgress | 66 | 0
FALSE |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File2 | 891 | 191 | 2023-08-04 | 2027-02-19 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 79 | 565
FALSE |  | 5375 | zkXPpJkHw8DPAtspwcmA | Large Test File2 | 800 | 190 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Summary | InProgress | 76 | 478
FALSE |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File2 | 881 | 310 | 2023-08-07 | 2027-02-08 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 65 | 574
FALSE |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File2 | 1210 | 829 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 31 | 245
FALSE |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File2 | 1210 | 426 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2025-05-30 | Summary | InProgress | 65 | -436
FALSE |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File2 | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 245
FALSE |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File2 | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 245
FALSE |  | 7382 | GJk3wpkfagyrb21gVciV | Large Test File2 | 1339 | 1339 | 2023-08-07 | 2028-11-09 | 2025-02-07 | 2026-03-24 | Summary | Planned | 0 | 28
FALSE |  | 4129 | G6dPcJRrq5zqLYx4Vr0R | Large Test File2 | 1363 | 928 | 2023-08-07 | 2028-12-12 | 2023-08-07 | 2025-06-13 | Summary | InProgress | 32 | 5
FALSE |  | 5753 | ZptYdARXANY2IOcoHhB1 | Large Test File2 | 1128 | 148 | 2023-08-07 | 2028-01-19 | 2023-08-07 | 2024-02-01 | Summary | InProgress | 87 | -80
FALSE |  | 5537 | 9xVQhmyTVkChMoMOy91g | Large Test File2 | 1214 | 637 | 2023-08-21 | 2028-06-01 | 2023-08-16 | 2024-06-11 | Summary | InProgress | 48 | 24
FALSE |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File2 | 1218 | 743 | 2023-09-05 | 2028-06-20 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 39 | 218
FALSE |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File2 | 1169 | 514 | 2023-09-05 | 2028-04-12 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 56 | 218
FALSE |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File2 | 702 | 702 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 0 | 20
FALSE |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File2 | 808 | 597 | 2023-10-18 | 2027-01-08 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 26 | 588
FALSE |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File2 | 1093 | 431 | 2024-03-04 | 2028-06-20 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 61 | 218
FALSE |  | 4038 | VkrURyJwsSkEVRV6WcXe | Large Test File2 | 483 | 462 | 2024-08-01 | 2026-07-08 | 2024-08-01 | 2025-04-16 | Summary | InProgress | 5 | 565
FALSE |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File2 | 639 | 621 | 2024-08-01 | 2027-02-19 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 3 | 565
FALSE |  | 5570 | MuDwSgsBJjDxwFkSMWYJ | Large Test File2 | 819 | 534 | 2024-11-18 | 2028-02-14 | 2024-02-05 | 2024-05-20 | Summary | InProgress | 35 | 45
FALSE |  | 5557 | U376LwOjKfNZoVLUlmMD | Large Test File2 | 749 | 749 | 2025-04-02 | 2028-03-14 | 2024-01-05 | 2024-04-22 | Summary | Planned | 0 | 24
FALSE |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File2 | 343 | 343 | 2025-04-10 | 2026-08-24 | 2025-06-27 | 2026-01-23 | Summary | Planned | 0 | 7
FALSE |  | 5544 | cIc3ARzcdrbXv6maHllr | Large Test File2 | 765 | 765 | 2025-04-15 | 2028-04-19 | 2023-12-06 | 2024-03-25 | Summary | Planned | 0 | 24
FALSE |  | 5583 | gkFBoXdv1oJb2jtBcO5M | Large Test File2 | 790 | 790 | 2025-04-23 | 2028-06-01 | 2024-03-04 | 2024-06-11 | Summary | Planned | 0 | 24
FALSE |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File2 | 345 | 345 | 2025-09-04 | 2027-01-06 | 2025-06-24 | 2026-08-14 | Summary | Planned | 0 | 80
FALSE |  | 5402 | zDUD70mdAG3rcozejCwk | Large Test File2 | 279 | 279 | 2025-09-05 | 2026-10-19 | 2025-08-26 | 2025-09-16 | Summary | Planned | 0 | 478
FALSE |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File2 | 872 | 872 | 2025-09-19 | 2029-02-14 | 2024-09-26 | 2026-01-30 | Summary | Planned | 0 | 8
FALSE |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File2 | 120 | 120 | 2026-02-18 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 0 | -36
FALSE |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File2 | 160 | 160 | 2026-06-16 | 2027-02-08 | 2026-04-07 | 2026-07-27 | Summary | Planned | 0 | 574
FALSE |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File2 | 136 | 136 | 2026-06-24 | 2027-01-12 | 2026-01-07 | 2026-07-07 | Summary | Planned | 0 | 588
FALSE |  | 7264 | vNqQNKJIEgg8BiBzdWeI | Large Test File2 | 57 | 57 | 2026-07-02 | 2026-09-23 | 2025-04-04 | 2025-06-25 | Summary | Planned | 0 | 490
FALSE |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File2 | 145 | 145 | 2026-07-08 | 2027-02-04 | 2025-06-26 | 2025-11-11 | Summary | Planned | 0 | 565
FALSE |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File2 | 110 | 110 | 2026-08-05 | 2027-01-06 | 2026-05-01 | 2026-08-14 | Summary | Planned | 0 | 597
FALSE |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File2 | 40 | 40 | 2026-12-23 | 2027-02-19 | 2025-10-08 | 2026-01-23 | Summary | Planned | 0 | 565
FALSE |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File2 | 32 | 32 | 2026-12-23 | 2027-02-09 | 2025-10-08 | 2025-12-17 | Summary | Planned | 0 | 568
Longest Path
Activities that together form the longest path through to project completion.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Critical
Number of critical activities
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Insufficient Detail™
Number of activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Notes | Id | Description | Project | Original Duration | Number of Predecessors | Number of Successors | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 3 | 1 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 3 | 2 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 3 | 1 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 3 | 1 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 3 | 3 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 3 | 2 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 3 | 1 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 7 | 1 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
Longest Path (Normal Tasks)
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 37 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 52 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
Longest Path (Tasks & Milestones)
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 37 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 52 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
Normal Tasks
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 80 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | Aspose.Tasks.Calendar | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 689
FALSE |  | 78 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | Aspose.Tasks.Calendar | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 635
FALSE |  | 76 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | Aspose.Tasks.Calendar | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 478
FALSE |  | 37 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 79 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | Aspose.Tasks.Calendar | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 218
FALSE |  | 26 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | Aspose.Tasks.Calendar | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 567
FALSE |  | 52 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 8 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | Aspose.Tasks.Calendar | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 490
FALSE |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE |  | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE |  | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE |  | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE |  | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE |  | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE |  | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE |  | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE |  | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE |  | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE |  | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
Normal Tasks (To-Go)
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 80 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | Aspose.Tasks.Calendar | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 689
FALSE |  | 78 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | Aspose.Tasks.Calendar | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 635
FALSE |  | 76 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | Aspose.Tasks.Calendar | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 478
FALSE |  | 37 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 79 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | Aspose.Tasks.Calendar | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 218
FALSE |  | 26 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | Aspose.Tasks.Calendar | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 567
FALSE |  | 52 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 8 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | Aspose.Tasks.Calendar | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 490
FALSE |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE |  | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE |  | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE |  | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE |  | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE |  | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE |  | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE |  | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE |  | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE |  | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE |  | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
Critical Tasks (To-Go)
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | TRUE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE | TRUE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Critical Tasks (In Progress)
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | TRUE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | TRUE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
CP - Float Ratio™
Average float divided by average remaining duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Newly Critical Activities
How many remaining activities were added to the critical path this period
Id | Description | Critical | Previous_Critical | Original Duration | Remaining Duration | Start | Finish | Type | Status | Percent Complete | Total Float | Project
5539 | kRsO3PSMDsMxji3dmdNc | TRUE | FALSE | 998 | 628 | 2023-08-23 | 2027-09-02 | Normal | InProgress | 37 | -436 | Large Test File2
6997 | MBGoTUikAECGvIHYk1uV | TRUE | FALSE | 48 | 23 | 2024-11-01 | 2027-10-12 | Normal | InProgress | 52 | 0 | Large Test File2
5308 | JBAsTSNPb9OQmIAmtadV | TRUE | FALSE | 29 | 29 | 2026-05-25 | 2026-07-07 | Normal | Planned | 0 | -36 | Large Test File2
6522 | WYJvDx3FrKALT2lj4FIo | TRUE | FALSE | 2 | 2 | 2026-07-07 | 2026-07-09 | Normal | Planned | 0 | -36 | Large Test File2
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE | FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE | FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE | FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE | FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE | FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE | FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE | FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE | FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE | FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE | FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE | FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE | FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE | FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE | FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE | FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
High Float 44d
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE | FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE | FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE | FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE | FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE | FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE | FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE | FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE | FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE | FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE | FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE | FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE | FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE | FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE | FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE | FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE | FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Zero Days Float
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | TRUE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
Critical Logic Hotspot™
Number of activities with a high number of predecessors as well as a high number of successors.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 3 | TRUE | -34 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
Critical Merge Hotspot
The total number of activities with a high number of predecessor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 3 | 0 | 0 | 0 | TRUE | -34 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
Critical Diverge Hotspot
Number of activities with a high number of successor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Successor Leads | Number of Successor Lags | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 4 | 0 | 1 | TRUE | -436 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 43 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37
FALSE | 1 | 3 | 0 | 0 | TRUE | -36 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0
FALSE | 3 | 3 | 0 | 0 | TRUE | -34 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE | 1 | 4 | 0 | 0 | TRUE | -36 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0
Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
Missing Baseline Starts
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
Missing Baseline Finishes
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
CEI - Total Tasks
The number of tasks forecasted in the previous month's schedule (based on the prior schedule's status date) to be completed in the current month (time between prior schedule's satus date and current schedule's status date).
Excluded | Notes | DRM | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 8.6047 | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 0 | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
CEI - Incomplete Tasks
The number of tasks that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
Longest Path - Critical Activities and Milestones
Activities that together form the longest path through to project completion. (Number of critical activities.)
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | TRUE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE | TRUE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Critical Tasks (To-Go)
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | TRUE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE | TRUE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Critical Tasks (In Progress)
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | TRUE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | TRUE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Float Ratio™
Average float divided by average remaining duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File2 | 3019 | 690 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 77 | 0
FALSE |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File2 | 3019 | 1201 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 60 | 0
FALSE |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File2 | 3019 | 634 | 2017-06-07 | 2029-04-20 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 79 | 0
FALSE |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File2 | 3006 | 876 | 2017-06-07 | 2029-04-03 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 71 | 13
FALSE |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File2 | 2452 | 792 | 2017-06-07 | 2027-02-17 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 68 | 567
FALSE |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File2 | 2632 | 0 | 2017-12-28 | 2028-05-11 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 99 | 245
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File2 | 1996 | 361 | 2019-04-01 | 2027-02-19 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 82 | 565
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 6315 | 2iW64uJmzViIcLEo0dMn | Large Test File2 | 1909 | 422 | 2021-01-04 | 2028-07-10 | 2021-01-04 | 2025-11-07 | Summary | InProgress | 78 | 24
FALSE |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File2 | 2049 | 428 | 2021-04-05 | 2029-04-20 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 79 | 0
FALSE |  | 6317 | NzqiT3qChWGoVO5Oxj9C | Large Test File2 | 1312 | 213 | 2021-08-09 | 2026-10-19 | 2021-07-06 | 2025-09-16 | Summary | InProgress | 84 | 478
FALSE |  | 5362 | 4bsxfawvV6TKTvCq9VoB | Large Test File2 | 1240 | 236 | 2021-08-09 | 2026-07-08 | 2021-07-06 | 2023-10-16 | Summary | InProgress | 81 | 490
FALSE |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File2 | 1857 | 309 | 2022-01-06 | 2029-04-20 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 83 | 0
FALSE |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File2 | 1203 | 297 | 2022-04-04 | 2027-01-12 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 75 | 588
FALSE |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File2 | 1514 | 262 | 2023-01-03 | 2028-12-12 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 83 | 93
FALSE |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File2 | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 83 | -34
FALSE |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File2 | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 83 | -34
FALSE |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File2 | 996 | 304 | 2023-02-23 | 2027-02-08 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 69 | 574
FALSE |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File2 | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 17 | 30
FALSE |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File2 | 975 | 320 | 2023-03-06 | 2027-01-06 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 67 | 597
FALSE |  | 870 | m3oEXpasu7ssfpw9dqLv | Large Test File2 | 1460 | 498 | 2023-03-20 | 2028-12-11 | 2023-03-20 | 2025-06-27 | Summary | InProgress | 66 | 0
FALSE |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File2 | 891 | 191 | 2023-08-04 | 2027-02-19 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 79 | 565
FALSE |  | 5375 | zkXPpJkHw8DPAtspwcmA | Large Test File2 | 800 | 190 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Summary | InProgress | 76 | 478
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File2 | 881 | 310 | 2023-08-07 | 2027-02-08 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 65 | 574
FALSE |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File2 | 1210 | 829 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 31 | 245
FALSE |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File2 | 1210 | 426 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2025-05-30 | Summary | InProgress | 65 | -436
FALSE |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File2 | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 245
FALSE |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File2 | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 245
FALSE |  | 7382 | GJk3wpkfagyrb21gVciV | Large Test File2 | 1339 | 1339 | 2023-08-07 | 2028-11-09 | 2025-02-07 | 2026-03-24 | Summary | Planned | 0 | 28
FALSE |  | 4129 | G6dPcJRrq5zqLYx4Vr0R | Large Test File2 | 1363 | 928 | 2023-08-07 | 2028-12-12 | 2023-08-07 | 2025-06-13 | Summary | InProgress | 32 | 5
FALSE |  | 5753 | ZptYdARXANY2IOcoHhB1 | Large Test File2 | 1128 | 148 | 2023-08-07 | 2028-01-19 | 2023-08-07 | 2024-02-01 | Summary | InProgress | 87 | -80
FALSE |  | 5537 | 9xVQhmyTVkChMoMOy91g | Large Test File2 | 1214 | 637 | 2023-08-21 | 2028-06-01 | 2023-08-16 | 2024-06-11 | Summary | InProgress | 48 | 24
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File2 | 1218 | 743 | 2023-09-05 | 2028-06-20 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 39 | 218
FALSE |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File2 | 1169 | 514 | 2023-09-05 | 2028-04-12 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 56 | 218
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File2 | 702 | 702 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 0 | 20
FALSE |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File2 | 808 | 597 | 2023-10-18 | 2027-01-08 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 26 | 588
FALSE |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File2 | 1093 | 431 | 2024-03-04 | 2028-06-20 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 61 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 4038 | VkrURyJwsSkEVRV6WcXe | Large Test File2 | 483 | 462 | 2024-08-01 | 2026-07-08 | 2024-08-01 | 2025-04-16 | Summary | InProgress | 5 | 565
FALSE |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File2 | 639 | 621 | 2024-08-01 | 2027-02-19 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 3 | 565
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5570 | MuDwSgsBJjDxwFkSMWYJ | Large Test File2 | 819 | 534 | 2024-11-18 | 2028-02-14 | 2024-02-05 | 2024-05-20 | Summary | InProgress | 35 | 45
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 5557 | U376LwOjKfNZoVLUlmMD | Large Test File2 | 749 | 749 | 2025-04-02 | 2028-03-14 | 2024-01-05 | 2024-04-22 | Summary | Planned | 0 | 24
FALSE |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File2 | 343 | 343 | 2025-04-10 | 2026-08-24 | 2025-06-27 | 2026-01-23 | Summary | Planned | 0 | 7
FALSE |  | 5544 | cIc3ARzcdrbXv6maHllr | Large Test File2 | 765 | 765 | 2025-04-15 | 2028-04-19 | 2023-12-06 | 2024-03-25 | Summary | Planned | 0 | 24
FALSE |  | 5583 | gkFBoXdv1oJb2jtBcO5M | Large Test File2 | 790 | 790 | 2025-04-23 | 2028-06-01 | 2024-03-04 | 2024-06-11 | Summary | Planned | 0 | 24
FALSE |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File2 | 345 | 345 | 2025-09-04 | 2027-01-06 | 2025-06-24 | 2026-08-14 | Summary | Planned | 0 | 80
FALSE |  | 5402 | zDUD70mdAG3rcozejCwk | Large Test File2 | 279 | 279 | 2025-09-05 | 2026-10-19 | 2025-08-26 | 2025-09-16 | Summary | Planned | 0 | 478
FALSE |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File2 | 872 | 872 | 2025-09-19 | 2029-02-14 | 2024-09-26 | 2026-01-30 | Summary | Planned | 0 | 8
FALSE |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File2 | 120 | 120 | 2026-02-18 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 0 | -36
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File2 | 160 | 160 | 2026-06-16 | 2027-02-08 | 2026-04-07 | 2026-07-27 | Summary | Planned | 0 | 574
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File2 | 136 | 136 | 2026-06-24 | 2027-01-12 | 2026-01-07 | 2026-07-07 | Summary | Planned | 0 | 588
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7264 | vNqQNKJIEgg8BiBzdWeI | Large Test File2 | 57 | 57 | 2026-07-02 | 2026-09-23 | 2025-04-04 | 2025-06-25 | Summary | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File2 | 145 | 145 | 2026-07-08 | 2027-02-04 | 2025-06-26 | 2025-11-11 | Summary | Planned | 0 | 565
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File2 | 110 | 110 | 2026-08-05 | 2027-01-06 | 2026-05-01 | 2026-08-14 | Summary | Planned | 0 | 597
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File2 | 40 | 40 | 2026-12-23 | 2027-02-19 | 2025-10-08 | 2026-01-23 | Summary | Planned | 0 | 565
FALSE |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File2 | 32 | 32 | 2026-12-23 | 2027-02-09 | 2025-10-08 | 2025-12-17 | Summary | Planned | 0 | 568
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
CP - Float Ratio™
Average float divided by average remaining duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Critical w/High Baseline Duration (44d)
Total number of critical activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Critical | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File2 | 2875 | 3019 | 690 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 77 | 0
FALSE | TRUE |  |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File2 | 2388 | 3019 | 1201 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 60 | 0
FALSE | TRUE |  |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File2 | 1454 | 3019 | 634 | 2017-06-07 | 2029-04-20 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 79 | 0
FALSE | FALSE |  |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File2 | 1125 | 3006 | 876 | 2017-06-07 | 2029-04-03 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 71 | 13
FALSE | FALSE |  |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File2 | 2478 | 2452 | 792 | 2017-06-07 | 2027-02-17 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 68 | 567
FALSE | FALSE |  |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File2 | 688 | 2632 | 0 | 2017-12-28 | 2028-05-11 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 99 | 245
FALSE | FALSE |  |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1518 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE | FALSE |  |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File2 | 1877 | 1996 | 361 | 2019-04-01 | 2027-02-19 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 82 | 565
FALSE | FALSE |  |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1874 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE | FALSE |  |  | 6315 | 2iW64uJmzViIcLEo0dMn | Large Test File2 | 1229 | 1909 | 422 | 2021-01-04 | 2028-07-10 | 2021-01-04 | 2025-11-07 | Summary | InProgress | 78 | 24
FALSE | FALSE |  |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File2 | 1410 | 2049 | 428 | 2021-04-05 | 2029-04-20 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 79 | 0
FALSE | FALSE |  |  | 6317 | NzqiT3qChWGoVO5Oxj9C | Large Test File2 | 1064 | 1312 | 213 | 2021-08-09 | 2026-10-19 | 2021-07-06 | 2025-09-16 | Summary | InProgress | 84 | 478
FALSE | FALSE |  |  | 5362 | 4bsxfawvV6TKTvCq9VoB | Large Test File2 | 580 | 1240 | 236 | 2021-08-09 | 2026-07-08 | 2021-07-06 | 2023-10-16 | Summary | InProgress | 81 | 490
FALSE | TRUE |  |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File2 | 1185 | 1857 | 309 | 2022-01-06 | 2029-04-20 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 83 | 0
FALSE | FALSE |  |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File2 | 1189 | 1203 | 297 | 2022-04-04 | 2027-01-12 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 75 | 588
FALSE | FALSE |  |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File2 | 621 | 1514 | 262 | 2023-01-03 | 2028-12-12 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 83 | 93
FALSE | TRUE |  |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File2 | 516 | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 83 | -34
FALSE | TRUE |  |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File2 | 516 | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 83 | -34
FALSE | FALSE |  |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File2 | 906 | 996 | 304 | 2023-02-23 | 2027-02-08 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 69 | 574
FALSE | FALSE |  |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File2 | 402 | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 17 | 30
FALSE | FALSE |  |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File2 | 873 | 975 | 320 | 2023-03-06 | 2027-01-06 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 67 | 597
FALSE | TRUE |  |  | 870 | m3oEXpasu7ssfpw9dqLv | Large Test File2 | 580 | 1460 | 498 | 2023-03-20 | 2028-12-11 | 2023-03-20 | 2025-06-27 | Summary | InProgress | 66 | 0
FALSE | FALSE |  |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File2 | 632 | 891 | 191 | 2023-08-04 | 2027-02-19 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 79 | 565
FALSE | FALSE |  |  | 5375 | zkXPpJkHw8DPAtspwcmA | Large Test File2 | 15 | 800 | 190 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Summary | InProgress | 76 | 478
FALSE | FALSE |  |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 15 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE | FALSE |  |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File2 | 748 | 881 | 310 | 2023-08-07 | 2027-02-08 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 65 | 574
FALSE | FALSE |  |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File2 | 775 | 1210 | 829 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 31 | 245
FALSE | TRUE |  |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File2 | 462 | 1210 | 426 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2025-05-30 | Summary | InProgress | 65 | -436
FALSE | FALSE |  |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File2 | 366 | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 245
FALSE | FALSE |  |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File2 | 366 | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 245
FALSE | FALSE |  |  | 7382 | GJk3wpkfagyrb21gVciV | Large Test File2 | 281 | 1339 | 1339 | 2023-08-07 | 2028-11-09 | 2025-02-07 | 2026-03-24 | Summary | Planned | 0 | 28
FALSE | FALSE |  |  | 4129 | G6dPcJRrq5zqLYx4Vr0R | Large Test File2 | 472 | 1363 | 928 | 2023-08-07 | 2028-12-12 | 2023-08-07 | 2025-06-13 | Summary | InProgress | 32 | 5
FALSE | TRUE |  |  | 5753 | ZptYdARXANY2IOcoHhB1 | Large Test File2 | 124 | 1128 | 148 | 2023-08-07 | 2028-01-19 | 2023-08-07 | 2024-02-01 | Summary | InProgress | 87 | -80
FALSE | FALSE |  |  | 5537 | 9xVQhmyTVkChMoMOy91g | Large Test File2 | 209 | 1214 | 637 | 2023-08-21 | 2028-06-01 | 2023-08-16 | 2024-06-11 | Summary | InProgress | 48 | 24
FALSE | TRUE |  |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 43 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | FALSE |  |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File2 | 137 | 1218 | 743 | 2023-09-05 | 2028-06-20 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 39 | 218
FALSE | FALSE |  |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File2 | 51 | 1169 | 514 | 2023-09-05 | 2028-04-12 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 56 | 218
FALSE | FALSE |  |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 15 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE | FALSE |  |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File2 | 190 | 702 | 702 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 0 | 20
FALSE | FALSE |  |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File2 | 396 | 808 | 597 | 2023-10-18 | 2027-01-08 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 26 | 588
FALSE | FALSE |  |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File2 | 512 | 1093 | 431 | 2024-03-04 | 2028-06-20 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 61 | 218
FALSE | FALSE |  |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 376 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE | FALSE |  |  | 4038 | VkrURyJwsSkEVRV6WcXe | Large Test File2 | 180 | 483 | 462 | 2024-08-01 | 2026-07-08 | 2024-08-01 | 2025-04-16 | Summary | InProgress | 5 | 565
FALSE | FALSE |  |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File2 | 375 | 639 | 621 | 2024-08-01 | 2027-02-19 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 3 | 565
FALSE | TRUE |  |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 32 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE | FALSE |  |  | 5570 | MuDwSgsBJjDxwFkSMWYJ | Large Test File2 | 76 | 819 | 534 | 2024-11-18 | 2028-02-14 | 2024-02-05 | 2024-05-20 | Summary | InProgress | 35 | 45
FALSE | FALSE |  |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 |  | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE | FALSE |  |  | 5557 | U376LwOjKfNZoVLUlmMD | Large Test File2 | 76 | 749 | 749 | 2025-04-02 | 2028-03-14 | 2024-01-05 | 2024-04-22 | Summary | Planned | 0 | 24
FALSE | FALSE |  |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File2 | 145 | 343 | 343 | 2025-04-10 | 2026-08-24 | 2025-06-27 | 2026-01-23 | Summary | Planned | 0 | 7
FALSE | FALSE |  |  | 5544 | cIc3ARzcdrbXv6maHllr | Large Test File2 | 76 | 765 | 765 | 2025-04-15 | 2028-04-19 | 2023-12-06 | 2024-03-25 | Summary | Planned | 0 | 24
FALSE | FALSE |  |  | 5583 | gkFBoXdv1oJb2jtBcO5M | Large Test File2 | 71 | 790 | 790 | 2025-04-23 | 2028-06-01 | 2024-03-04 | 2024-06-11 | Summary | Planned | 0 | 24
FALSE | FALSE |  |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File2 | 293 | 345 | 345 | 2025-09-04 | 2027-01-06 | 2025-06-24 | 2026-08-14 | Summary | Planned | 0 | 80
FALSE | FALSE |  |  | 5402 | zDUD70mdAG3rcozejCwk | Large Test File2 | 15 | 279 | 279 | 2025-09-05 | 2026-10-19 | 2025-08-26 | 2025-09-16 | Summary | Planned | 0 | 478
FALSE | FALSE |  |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File2 | 340 | 872 | 872 | 2025-09-19 | 2029-02-14 | 2024-09-26 | 2026-01-30 | Summary | Planned | 0 | 8
FALSE | TRUE |  |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File2 | 105 | 120 | 120 | 2026-02-18 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 0 | -36
FALSE | TRUE |  |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 20 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE | FALSE |  |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 20 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE | FALSE |  |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 30 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE | FALSE |  |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File2 | 77 | 160 | 160 | 2026-06-16 | 2027-02-08 | 2026-04-07 | 2026-07-27 | Summary | Planned | 0 | 574
FALSE | FALSE |  |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE | FALSE |  |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File2 | 126 | 136 | 136 | 2026-06-24 | 2027-01-12 | 2026-01-07 | 2026-07-07 | Summary | Planned | 0 | 588
FALSE | FALSE |  |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 122 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE | FALSE |  |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 |  | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE | FALSE |  |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 7 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE | FALSE |  |  | 7264 | vNqQNKJIEgg8BiBzdWeI | Large Test File2 | 57 | 57 | 57 | 2026-07-02 | 2026-09-23 | 2025-04-04 | 2025-06-25 | Summary | Planned | 0 | 490
FALSE | FALSE |  |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 13 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE | TRUE |  |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE | FALSE |  |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File2 | 97 | 145 | 145 | 2026-07-08 | 2027-02-04 | 2025-06-26 | 2025-11-11 | Summary | Planned | 0 | 565
FALSE | FALSE |  |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 20 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE | TRUE |  |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE | FALSE |  |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE | TRUE |  |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE | FALSE |  |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE | TRUE |  |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE | TRUE |  |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE | FALSE |  |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 13 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE | FALSE |  |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 5 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE | TRUE |  |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE | TRUE |  |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | FALSE |  |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE | TRUE |  |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE | FALSE |  |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE | FALSE |  |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE | FALSE |  |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE | FALSE |  |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File2 | 76 | 110 | 110 | 2026-08-05 | 2027-01-06 | 2026-05-01 | 2026-08-14 | Summary | Planned | 0 | 597
FALSE | FALSE |  |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE | FALSE |  |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE | FALSE |  |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 13 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE | FALSE |  |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 10 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE | FALSE |  |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 5 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE | FALSE |  |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 10 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE | FALSE |  |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 42 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE | FALSE |  |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE | FALSE |  |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 9 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE | FALSE |  |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE | FALSE |  |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE | FALSE |  |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 6 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE | FALSE |  |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE | FALSE |  |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 5 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE | FALSE |  |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE | FALSE |  |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 15 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE | FALSE |  |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE | FALSE |  |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 5 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE | FALSE |  |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 5 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE | FALSE |  |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE | FALSE |  |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE | FALSE |  |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 20 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE | FALSE |  |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 5 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE | FALSE |  |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE | FALSE |  |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 20 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE | FALSE |  |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File2 | 74 | 40 | 40 | 2026-12-23 | 2027-02-19 | 2025-10-08 | 2026-01-23 | Summary | Planned | 0 | 565
FALSE | FALSE |  |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File2 | 50 | 32 | 32 | 2026-12-23 | 2027-02-09 | 2025-10-08 | 2025-12-17 | Summary | Planned | 0 | 568
FALSE | FALSE |  |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 20 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE | FALSE |  |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Critical w/High Planned Duration (44d)
Number of critical activities with a duration longer than 44 days.
Excluded | Critical | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 43 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | TRUE |  |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 32 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE | TRUE |  |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
Critical CEI - Total Tasks
The number of tasks forecasted in the previous month's schedule (based on the prior schedule's status date) to be completed in the current month (time between prior schedule's satus date and current schedule's status date).
Excluded | Critical | Created | Notes | DRM | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  |  | 8.6047 | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
Critical CEI - Incomplete Tasks
The number of tasks that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Excluded | Critical | Created | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
Newly Critical Activities
How many remaining activities were added to the critical path this period
Id | Description | Critical | Previous_Critical | Original Duration | Remaining Duration | Start | Finish | Type | Status | Percent Complete | Total Float | Project
5539 | kRsO3PSMDsMxji3dmdNc | TRUE | FALSE | 998 | 628 | 2023-08-23 | 2027-09-02 | Normal | InProgress | 37 | -436 | Large Test File2
6997 | MBGoTUikAECGvIHYk1uV | TRUE | FALSE | 48 | 23 | 2024-11-01 | 2027-10-12 | Normal | InProgress | 52 | 0 | Large Test File2
5308 | JBAsTSNPb9OQmIAmtadV | TRUE | FALSE | 29 | 29 | 2026-05-25 | 2026-07-07 | Normal | Planned | 0 | -36 | Large Test File2
6522 | WYJvDx3FrKALT2lj4FIo | TRUE | FALSE | 2 | 2 | 2026-07-07 | 2026-07-09 | Normal | Planned | 0 | -36 | Large Test File2
Longest Path - Critical Activities and Milestones
Activities that together form the longest path through to project completion. (Number of critical activities.)
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | TRUE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE | TRUE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Critical Tasks (To-Go)
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | TRUE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE | TRUE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Critical Tasks (In Progress)
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | TRUE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE | FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE | FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE | FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE | FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE | FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE | FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE | FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE | FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE | FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE | FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE | FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE | FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE | FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE | FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE | FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
High Float 44d
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE | FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE | FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE | FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE | FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE | FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE | FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE | FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE | FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE | FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE | FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE | FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE | FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE | FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE | FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE | FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE | FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE | FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE | FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE | FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Zero Days Float
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | TRUE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE | TRUE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | TRUE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
CP - Float Ratio™
Average float divided by average remaining duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
20 to 30 days float
Total number of activities with positive float of more than 20 and less than or equal to 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Schedule Baseline Activities
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Scheduled/Baselined to Start
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Scheduled/Baselined to Finish
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Start/ed
Number of activities starting or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
Started Delayed (>30 days)
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0.98024 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 1488 | 2019-04-01 |  | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE | 0.78125 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 25 | 2024-11-01 |  | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
Duration Variance (Original & Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1518 | 1488 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE | 1874 | 1478 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE | 15 | 182 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE | 43 | 370 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | 15 | 63 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE | 376 | 173 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE | 32 | 25 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE | 20 | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE | 122 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE | 13 | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE | 20 | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE | 5 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE | 20 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | 13 | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE | 10 | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE | 5 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE | 42 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE | 9 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE | 5 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE | 15 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE | 5 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE | 5 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE | 20 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE | 5 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE | 20 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE | 20 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
Duration Variance (Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 15 | 182 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE | 43 | 370 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | 15 | 63 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
Scheduled Activities
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Scheduled to Start
Number of activities that are scheduled to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Scheduled to Finish
Number of activities that are scheduled to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Scheduled to Start - Tasks & Milestones
Number of activities and milestones that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Planned Delayed Start - Tasks & Milestones
Number of activities and milestones that are currently planned to start after their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Scheduled to Start - Tasks
Number of activities that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Planned Delayed Start - Tasks
Number of activities that are currently planned to start after their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Planned Delayed Finish - Tasks
Number of planned/future activities that are schedule to slip from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Scheduled to Start - Milestones
Number of milestones that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
Planned Delayed Start - Milestones
Number of milestones that are currently planned to start after their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
Planned Delayed Finish - Milestones
Number of planned/future activities that are schedule to slip from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
Actually Started - Tasks
Total number of activities that have started.
Excluded | Actual Start | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2019-04-01 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE | 2019-04-15 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE | 2023-08-07 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE | 2023-08-23 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | 2023-09-05 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE | 2024-06-03 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE | 2024-11-01 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE | 2024-12-23 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
In-Progress Started Ahead - Tasks
Number of activities that started before their planned start date.
Excluded | Actual Start | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2023-08-07 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE | 2023-09-05 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
In-Progress Started On-Schedule - Tasks
Number of activities that are currently underway and started on time.
Excluded | Actual Start | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2019-04-15 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE | 2023-08-23 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | 2024-06-03 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
In-Progress Started Delayed - Tasks
Number of activities that started after their planned start date.
Excluded | Actual Start | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2019-04-01 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE | 2024-11-01 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
In-Progress Delayed Finish - Tasks
Number of in-progress activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
All Activities w/Successors
The total number of activities within a grouping.
Excluded | Created | Percent Complete | Number of Successors | Number of Successor Leads | Number of Successor Lags | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 80 | 1 | 0 | 0 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | Aspose.Tasks.Calendar | 1518 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 689
FALSE |  | 78 | 1 | 0 | 0 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | Aspose.Tasks.Calendar | 1874 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 635
FALSE |  | 76 | 1 | 0 | 0 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | Aspose.Tasks.Calendar | 15 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 478
FALSE |  | 37 | 4 | 0 | 1 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 43 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 79 | 2 | 0 | 0 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | Aspose.Tasks.Calendar | 15 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 218
FALSE |  | 26 | 1 | 0 | 0 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | Aspose.Tasks.Calendar | 376 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 567
FALSE |  | 52 | 1 | 0 | 0 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 32 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 8 | 1 | 0 | 0 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | Aspose.Tasks.Calendar |  | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 490
FALSE |  | 0 | 1 | 0 | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 20 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 20 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE |  | 0 | 1 | 0 | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 30 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE |  | 0 | 1 | 0 | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE |  | 0 | 2 | 0 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 122 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE |  | 0 | 1 | 0 | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar |  | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE |  | 0 | 2 | 0 | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 7 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 13 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 20 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE |  | 0 | 2 | 0 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 | 1 | 0 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 | 3 | 0 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 | 2 | 0 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 13 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE |  | 0 | 1 | 0 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 | 3 | 0 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 | 1 | 0 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE |  | 0 | 4 | 0 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE |  | 0 | 1 | 0 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE |  | 0 | 1 | 0 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 20
FALSE |  | 0 | 1 | 0 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE |  | 0 | 2 | 0 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 20
FALSE |  | 0 | 1 | 0 | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 13 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE |  | 0 | 2 | 0 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE |  | 0 | 1 | 0 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 10 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE |  | 0 | 2 | 0 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 42 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE |  | 0 | 1 | 0 | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 9 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 6 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE |  | 0 | 1 | 0 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 5 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE |  | 0 | 1 | 0 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 15 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE |  | 0 | 1 | 0 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE |  | 0 | 2 | 0 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 20 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE |  | 0 | 1 | 0 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 20 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE |  | 0 | 1 | 0 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 20 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE |  | 0 | 1 | 0 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
Total # Successors
The total number of successors on all activities within a grouping.
Excluded | Created | Percent Complete | Number of Successors | Number of Successor Leads | Number of Successor Lags | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 80 | 1 | 0 | 0 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | Aspose.Tasks.Calendar | 1518 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 689
FALSE |  | 78 | 1 | 0 | 0 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | Aspose.Tasks.Calendar | 1874 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 635
FALSE |  | 76 | 1 | 0 | 0 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | Aspose.Tasks.Calendar | 15 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 478
FALSE |  | 37 | 4 | 0 | 1 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 43 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 79 | 2 | 0 | 0 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | Aspose.Tasks.Calendar | 15 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 218
FALSE |  | 26 | 1 | 0 | 0 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | Aspose.Tasks.Calendar | 376 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 567
FALSE |  | 52 | 1 | 0 | 0 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 32 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 8 | 1 | 0 | 0 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | Aspose.Tasks.Calendar |  | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 490
FALSE |  | 0 | 1 | 0 | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 20 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 20 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE |  | 0 | 1 | 0 | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 30 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE |  | 0 | 1 | 0 | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE |  | 0 | 2 | 0 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 122 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE |  | 0 | 1 | 0 | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar |  | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE |  | 0 | 2 | 0 | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 7 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 13 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 20 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE |  | 0 | 2 | 0 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 | 1 | 0 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 | 3 | 0 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 | 2 | 0 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 13 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE |  | 0 | 1 | 0 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 | 3 | 0 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 | 1 | 0 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE |  | 0 | 4 | 0 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE |  | 0 | 1 | 0 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE |  | 0 | 1 | 0 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 20
FALSE |  | 0 | 1 | 0 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE |  | 0 | 2 | 0 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 20
FALSE |  | 0 | 1 | 0 | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 13 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE |  | 0 | 2 | 0 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE |  | 0 | 1 | 0 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 10 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE |  | 0 | 2 | 0 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 42 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE |  | 0 | 1 | 0 | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 9 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 6 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE |  | 0 | 1 | 0 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 5 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE |  | 0 | 1 | 0 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 15 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE |  | 0 | 1 | 0 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE |  | 0 | 2 | 0 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 20 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE |  | 0 | 1 | 0 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 20 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE |  | 0 | 1 | 0 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 20 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE |  | 0 | 1 | 0 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
Max # Successors on an Activity
Excluded | Number of Successors | Number of Successor Leads | Number of Successor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 | 0 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE | 1 | 0 | 0 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE | 1 | 0 | 0 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE | 4 | 0 | 1 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | 2 | 0 | 0 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE | 1 | 0 | 0 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE | 1 | 0 | 0 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE | 1 | 0 | 0 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE | 1 | 0 | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE | 1 | 0 | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE | 1 | 0 | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE | 2 | 0 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE | 1 | 0 | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE | 2 | 0 | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE | 1 | 0 | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE | 1 | 0 | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE | 2 | 0 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE | 1 | 0 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE | 3 | 0 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE | 2 | 0 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE | 1 | 0 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE | 1 | 0 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE | 3 | 0 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | 1 | 0 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE | 4 | 0 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE | 1 | 0 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE | 1 | 0 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE | 1 | 0 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE | 2 | 0 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE | 1 | 0 | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE | 1 | 0 | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE | 2 | 0 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE | 1 | 0 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE | 2 | 0 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE | 1 | 0 | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE | 1 | 0 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE | 1 | 0 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE | 1 | 0 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE | 1 | 0 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE | 1 | 0 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE | 2 | 0 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE | 1 | 0 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE | 1 | 0 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE | 1 | 0 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Activities w/Lags on Successor
Total number of activities carrying a lag on the link to their successor activity. This number should not exceed 5%.
Excluded | Number of Successors | Number of Successor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 4 | 1 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
Total# of Successor Lags
Total number of successor relationships with lags in the schedule.
Excluded | Number of Successors | Number of Successor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 4 | 1 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
Max # of Successor Lags on Activity
The max number of successor lags on an activity.
Excluded | Number of Successors | Number of Successor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 4 | 1 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
Diverge Hotspot (Successors >2)
Number of activities with a high number of successor links.
Excluded | Number of Predecessors | Number of Successors | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 4 | 0 | 0 | TRUE | -436 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 43 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37
FALSE | 1 | 3 | 0 | 0 | TRUE | -36 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0
FALSE | 3 | 3 | 0 | 0 | TRUE | -34 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE | 1 | 4 | 0 | 0 | TRUE | -36 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0
Critical Diverge Hotspot
Number of activities with a high number of successor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Successor Leads | Number of Successor Lags | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 4 | 0 | 1 | TRUE | -436 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 43 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37
FALSE | 1 | 3 | 0 | 0 | TRUE | -36 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0
FALSE | 3 | 3 | 0 | 0 | TRUE | -34 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE | 1 | 4 | 0 | 0 | TRUE | -36 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0
Logic Hotspot™
Number of activities with a high number of predecessors as well as a high number of successors.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 3 | TRUE | -34 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
Critical Logic Hotspot™
Number of activities with a high number of predecessors as well as a high number of successors.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 3 | TRUE | -34 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
All Activities w/Predecessors
The total number of activities within a grouping that have predecessors. Includes normal activities and milestones that are planned.
Excluded | Created | Percent Complete | Number of Predecessors | Number of Leads | Number of Lags | Minimum Lag | Maximum Lag | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 20 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 20 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 30 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 122 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar |  | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 7 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 13 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 20 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 13 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 20
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 20
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 13 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 10 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 42 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 9 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE |  | 0 | 7 | 0 | 0 | 0 | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 6 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 5 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 15 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 20 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 20 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 20 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
Total # Predecessors
The total number of successors on all activities within a grouping that have predecessors. Includes normal activities and milestones that are planned.
Excluded | Created | Percent Complete | Number of Predecessors | Number of Leads | Number of Lags | Minimum Lag | Maximum Lag | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 20 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 20 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 30 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 122 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar |  | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 7 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 13 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 20 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 13 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 20
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 20
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 13 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 10 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 42 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 9 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE |  | 0 | 7 | 0 | 0 | 0 | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 6 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 5 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 15 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 20 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 20 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 20 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
Max # Predecessors on an Activity
The max number of predecessor links on an activity. Includes normal activities and milestones that are planned.
Excluded | Number of Predecessors | Number of Leads | Number of Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2 | 0 | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE | 1 | 0 | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE | 1 | 0 | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE | 3 | 0 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE | 1 | 0 | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE | 3 | 0 | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE | 2 | 0 | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE | 1 | 0 | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE | 3 | 0 | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE | 2 | 0 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE | 1 | 0 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE | 1 | 0 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE | 3 | 0 | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE | 1 | 0 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE | 2 | 0 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE | 3 | 0 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | 2 | 0 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE | 1 | 0 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE | 1 | 0 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE | 1 | 0 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE | 1 | 0 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE | 3 | 0 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE | 1 | 0 | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE | 2 | 0 | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE | 1 | 0 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE | 3 | 0 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE | 1 | 0 | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE | 1 | 0 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE | 1 | 0 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE | 7 | 0 | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE | 1 | 0 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE | 2 | 0 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE | 1 | 0 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE | 1 | 0 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE | 1 | 0 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE | 1 | 0 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE | 1 | 0 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Max Predecessor Lag (days)
The largest predecessor lag value for the selected activity grouping.
Excluded | Number of Predecessors | Number of Lags | Minimum Lag | Maximum Lag | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2 | 0 | 0 | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE | 1 | 0 | 0 | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE | 1 | 0 | 0 | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE | 3 | 0 | 0 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE | 1 | 0 | 0 | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE | 3 | 0 | 0 | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE | 2 | 0 | 0 | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE | 1 | 0 | 0 | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE | 3 | 0 | 0 | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE | 2 | 0 | 0 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE | 1 | 0 | 0 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE | 1 | 0 | 0 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE | 3 | 0 | 0 | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE | 1 | 0 | 0 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE | 2 | 0 | 0 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE | 3 | 0 | 0 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | 2 | 0 | 0 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE | 1 | 0 | 0 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE | 1 | 0 | 0 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE | 1 | 0 | 0 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE | 1 | 0 | 0 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE | 1 | 0 | 0 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE | 3 | 0 | 0 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE | 1 | 0 | 0 | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE | 2 | 0 | 0 | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE | 1 | 0 | 0 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE | 3 | 0 | 0 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE | 1 | 0 | 0 | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE | 1 | 0 | 0 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE | 1 | 0 | 0 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE | 7 | 0 | 0 | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE | 1 | 0 | 0 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE | 2 | 0 | 0 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE | 1 | 0 | 0 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE | 1 | 0 | 0 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE | 1 | 0 | 0 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE | 1 | 0 | 0 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE | 1 | 0 | 0 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE | 1 | 0 | 0 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Merge Hotspot (Predecessors >2)
The total number of activities with a high number of predecessor links.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 2 | FALSE | 588 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 122 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0
FALSE | 3 | 2 | FALSE | 490 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 7 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0
FALSE | 3 | 1 | FALSE | 565 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 20 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0
FALSE | 3 | 1 | FALSE | 490 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 13 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0
FALSE | 3 | 3 | TRUE | -34 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE | 3 | 2 | FALSE | 20 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0
FALSE | 3 | 1 | FALSE | 597 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 10 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0
FALSE | 7 | 1 | FALSE | 478 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 6 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0
Critical Merge Hotspot
The total number of activities with a high number of predecessor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 3 | 0 | 0 | 0 | TRUE | -34 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
Logic Hotspot™
Number of activities with a high number of predecessors as well as a high number of successors.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 3 | TRUE | -34 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
Critical Logic Hotspot™
Number of activities with a high number of predecessors as well as a high number of successors.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 3 | TRUE | -34 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
All Activities w/Predecessors
The total number of activities within a grouping that have predecessors. Includes normal activities and milestones that are planned or in-progress.
Excluded | Number of Predecessors | Number of Leads | Number of Lags | Maximum Lag | Minimum Lag | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 20 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 20 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 30 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 122 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar |  | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 7 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 13 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 20 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 13 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 20
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 20
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 13 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 10 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 42 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 9 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE | 7 | 0 | 0 | 0 | 0 |  | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 6 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 5 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 15 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 20 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 20 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 20 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
SS Predecessors
Number of activities with Start-to-Start (SS) logic links.
Excluded | Number of SS Predecessors | Number Of SS Predecessor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2 | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE | 1 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | 1 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FF Predecessors
Number of activities with Finish-to-Finish (FF) logic links.
Excluded | Number of FF Predecessors | Number Of FF Predecessor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE | 1 | 0 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE | 2 | 0 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE | 1 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FS Predecessors
Number of activities with Finish-to-Start (FS) logic links. Should be at least 90%.
Excluded | Number of FS Predecessors | Number Of FS Predecessor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE | 1 | 0 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE | 1 | 0 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE | 1 | 0 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | 1 | 0 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE | 1 | 0 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE | 1 | 0 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE | 1 | 0 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE | 2 | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE | 1 | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE | 1 | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE | 1 | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE | 3 | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE | 1 | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE | 3 | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE | 1 | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE | 3 | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE | 2 | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE | 1 | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE | 1 | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE | 1 | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE | 1 | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE | 1 | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE | 3 | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE | 1 | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE | 2 | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE | 2 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | 1 | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE | 1 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE | 1 | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE | 1 | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE | 1 | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE | 1 | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE | 3 | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE | 1 | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE | 2 | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE | 1 | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE | 2 | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE | 1 | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE | 1 | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE | 1 | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE | 1 | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE | 1 | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE | 7 | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE | 1 | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE | 2 | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE | 1 | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE | 1 | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE | 1 | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE | 1 | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE | 1 | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE | 1 | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE | 1 | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE | 1 | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE | 1 | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE | 1 | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE | 1 | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE | 1 | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE | 1 | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
All Activities w/Successors
The total number of activities within a grouping. Includes normal activities and milestones that are planned or in-progress.
Excluded | Number of Successors | Number of Successor Leads | Number of Successor Lags | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 1 | 0 | 0 |  | 80 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | Aspose.Tasks.Calendar | 1518 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 689
FALSE | 1 | 0 | 0 |  | 78 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | Aspose.Tasks.Calendar | 1874 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 635
FALSE | 1 | 0 | 0 |  | 76 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | Aspose.Tasks.Calendar | 15 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 478
FALSE | 4 | 0 | 1 |  | 37 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 43 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE | 2 | 0 | 0 |  | 79 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | Aspose.Tasks.Calendar | 15 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 218
FALSE | 1 | 0 | 0 |  | 26 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | Aspose.Tasks.Calendar | 376 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 567
FALSE | 1 | 0 | 0 |  | 52 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 32 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE | 1 | 0 | 0 |  | 8 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | Aspose.Tasks.Calendar |  | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 490
FALSE | 1 | 0 | 0 |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 20 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE | 1 | 0 | 0 |  | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 20 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE | 1 | 0 | 0 |  | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 30 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE | 1 | 0 | 0 |  | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE | 2 | 0 | 0 |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 122 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE | 1 | 0 | 0 |  | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar |  | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE | 2 | 0 | 0 |  | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 7 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE | 1 | 0 | 0 |  | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 13 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE | 1 | 0 | 0 |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE | 1 | 0 | 0 |  | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 20 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE | 2 | 0 | 0 |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE | 1 | 0 | 0 |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE | 1 | 0 | 0 |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE | 1 | 0 | 0 |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE | 3 | 0 | 0 |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE | 2 | 0 | 0 |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE | 1 | 0 | 0 |  | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 13 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE | 1 | 0 | 0 |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE | 1 | 0 | 0 |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE | 3 | 0 | 0 |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE | 1 | 0 | 0 |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE | 4 | 0 | 0 |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE | 1 | 0 | 0 |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE | 1 | 0 | 0 |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE | 1 | 0 | 0 |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 20
FALSE | 1 | 0 | 0 |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE | 2 | 0 | 0 |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 20
FALSE | 1 | 0 | 0 |  | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 13 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE | 1 | 0 | 0 |  | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE | 2 | 0 | 0 |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE | 1 | 0 | 0 |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 10 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE | 2 | 0 | 0 |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 42 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE | 1 | 0 | 0 |  | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE | 1 | 0 | 0 |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 9 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE | 1 | 0 | 0 |  | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE | 1 | 0 | 0 |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE | 1 | 0 | 0 |  | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 6 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE | 1 | 0 | 0 |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE | 1 | 0 | 0 |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 5 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE | 1 | 0 | 0 |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE | 1 | 0 | 0 |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 15 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE | 1 | 0 | 0 |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE | 1 | 0 | 0 |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE | 1 | 0 | 0 |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE | 2 | 0 | 0 |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE | 1 | 0 | 0 |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE | 1 | 0 | 0 |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 20 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE | 1 | 0 | 0 |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE | 1 | 0 | 0 |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE | 1 | 0 | 0 |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 20 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE | 1 | 0 | 0 |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 20 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE | 1 | 0 | 0 |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
SS Successors
Number of activities with Start-to-Start (SS) logic links.
Excluded | Number of SS Successors | Number of Successor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 1 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE | 1 | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE | 1 | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE | 1 | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FF Successors
Number of activities with Finish-to-Finish (FF) logic links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FS Successors
Number of activities with Finish-to-Start (FS) logic links. Should be at least 90%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
No Constraints
Number of activities with no constraints.
Excluded | Created | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | None |  | None |  | FALSE | 689 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80
FALSE |  | None |  | None |  | FALSE | 635 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78
FALSE |  | None |  | None |  | FALSE | 478 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76
FALSE |  | None |  | None |  | TRUE | -436 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37
FALSE |  | None |  | None |  | FALSE | 218 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79
FALSE |  | None |  | None |  | FALSE | 567 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26
FALSE |  | None |  | None |  | TRUE | 0 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52
FALSE |  | None |  | None |  | FALSE | 490 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8
FALSE |  | None |  | None |  | TRUE | -36 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 565 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 7 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 648 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 588 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 490 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 490 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 490 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -36 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 565 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -36 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 30 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -36 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 30 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -36 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -36 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 490 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 7 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -34 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -34 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 629 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -36 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 7 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 20 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 20 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 605 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 20 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 490 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 565 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 7 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 565 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 490 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 490 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 478 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 574 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 574 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 574 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 565 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 568 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0
No Constraints
Number of activities with no constraints.
Excluded | Created | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | None |  | None |  | FALSE | 689 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80
FALSE |  | None |  | None |  | FALSE | 635 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78
FALSE |  | None |  | None |  | FALSE | 478 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76
FALSE |  | None |  | None |  | TRUE | -436 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37
FALSE |  | None |  | None |  | FALSE | 218 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79
FALSE |  | None |  | None |  | FALSE | 567 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26
FALSE |  | None |  | None |  | TRUE | 0 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52
FALSE |  | None |  | None |  | FALSE | 490 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8
FALSE |  | None |  | None |  | TRUE | -36 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 565 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 7 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 648 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 588 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 490 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 490 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 490 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -36 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 565 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -36 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 30 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -36 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 30 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -36 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -36 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 490 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 7 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -34 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -34 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 629 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | -36 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 7 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 20 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 20 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 605 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 20 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 490 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 565 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 7 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 565 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 490 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 490 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 478 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 574 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 574 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 574 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 565 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 568 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 597 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0
Tasks & Milestones (To-Go) - % of Total To-Go
The total number of activities within a grouping. Percentage shows total to-go (planned and in-progress) tasks and milestones out of all activities (normal, milestone, summary, and LOE).
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 80 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | Aspose.Tasks.Calendar | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 689
FALSE |  | 78 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | Aspose.Tasks.Calendar | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 635
FALSE |  | 76 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | Aspose.Tasks.Calendar | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 478
FALSE |  | 37 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 79 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | Aspose.Tasks.Calendar | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 218
FALSE |  | 26 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | Aspose.Tasks.Calendar | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 567
FALSE |  | 52 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 8 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | Aspose.Tasks.Calendar | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 490
FALSE |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE |  | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE |  | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE |  | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE |  | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE |  | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 20
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 20
FALSE |  | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE |  | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE |  | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE |  | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE |  | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
High Baseline Duration (44d)
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1518 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1874 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 376 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 122 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
High Planned Duration (44d)
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1518 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1874 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 15 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 43 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 15 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 376 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 32 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 |  | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 122 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 42 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
Insufficient Detail™
Number of activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1518 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1874 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 43 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 376 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
Critical Activities (To-Go)
Number of critical activities
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 43 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 32 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 20 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
Critical w/High Baseline Duration (44d)
Total number of critical activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File2 | 2875 | 3019 | 690 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 77 | 0
FALSE |  |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File2 | 2388 | 3019 | 1201 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 60 | 0
FALSE |  |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File2 | 1454 | 3019 | 634 | 2017-06-07 | 2029-04-20 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 79 | 0
FALSE |  |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File2 | 1125 | 3006 | 876 | 2017-06-07 | 2029-04-03 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 71 | 13
FALSE |  |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File2 | 2478 | 2452 | 792 | 2017-06-07 | 2027-02-17 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 68 | 567
FALSE |  |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File2 | 688 | 2632 | 0 | 2017-12-28 | 2028-05-11 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 99 | 245
FALSE |  |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1518 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File2 | 1877 | 1996 | 361 | 2019-04-01 | 2027-02-19 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 82 | 565
FALSE |  |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1874 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  |  | 6315 | 2iW64uJmzViIcLEo0dMn | Large Test File2 | 1229 | 1909 | 422 | 2021-01-04 | 2028-07-10 | 2021-01-04 | 2025-11-07 | Summary | InProgress | 78 | 24
FALSE |  |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File2 | 1410 | 2049 | 428 | 2021-04-05 | 2029-04-20 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 79 | 0
FALSE |  |  | 6317 | NzqiT3qChWGoVO5Oxj9C | Large Test File2 | 1064 | 1312 | 213 | 2021-08-09 | 2026-10-19 | 2021-07-06 | 2025-09-16 | Summary | InProgress | 84 | 478
FALSE |  |  | 5362 | 4bsxfawvV6TKTvCq9VoB | Large Test File2 | 580 | 1240 | 236 | 2021-08-09 | 2026-07-08 | 2021-07-06 | 2023-10-16 | Summary | InProgress | 81 | 490
FALSE |  |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File2 | 1185 | 1857 | 309 | 2022-01-06 | 2029-04-20 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 83 | 0
FALSE |  |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File2 | 1189 | 1203 | 297 | 2022-04-04 | 2027-01-12 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 75 | 588
FALSE |  |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File2 | 621 | 1514 | 262 | 2023-01-03 | 2028-12-12 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 83 | 93
FALSE |  |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File2 | 516 | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 83 | -34
FALSE |  |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File2 | 516 | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | 83 | -34
FALSE |  |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File2 | 906 | 996 | 304 | 2023-02-23 | 2027-02-08 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 69 | 574
FALSE |  |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File2 | 402 | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 17 | 30
FALSE |  |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File2 | 873 | 975 | 320 | 2023-03-06 | 2027-01-06 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 67 | 597
FALSE |  |  | 870 | m3oEXpasu7ssfpw9dqLv | Large Test File2 | 580 | 1460 | 498 | 2023-03-20 | 2028-12-11 | 2023-03-20 | 2025-06-27 | Summary | InProgress | 66 | 0
FALSE |  |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File2 | 632 | 891 | 191 | 2023-08-04 | 2027-02-19 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 79 | 565
FALSE |  |  | 5375 | zkXPpJkHw8DPAtspwcmA | Large Test File2 | 15 | 800 | 190 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Summary | InProgress | 76 | 478
FALSE |  |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 15 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File2 | 748 | 881 | 310 | 2023-08-07 | 2027-02-08 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 65 | 574
FALSE |  |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File2 | 775 | 1210 | 829 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 31 | 245
FALSE |  |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File2 | 462 | 1210 | 426 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2025-05-30 | Summary | InProgress | 65 | -436
FALSE |  |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File2 | 366 | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 245
FALSE |  |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File2 | 366 | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 0 | 245
FALSE |  |  | 7382 | GJk3wpkfagyrb21gVciV | Large Test File2 | 281 | 1339 | 1339 | 2023-08-07 | 2028-11-09 | 2025-02-07 | 2026-03-24 | Summary | Planned | 0 | 28
FALSE |  |  | 4129 | G6dPcJRrq5zqLYx4Vr0R | Large Test File2 | 472 | 1363 | 928 | 2023-08-07 | 2028-12-12 | 2023-08-07 | 2025-06-13 | Summary | InProgress | 32 | 5
FALSE |  |  | 5753 | ZptYdARXANY2IOcoHhB1 | Large Test File2 | 124 | 1128 | 148 | 2023-08-07 | 2028-01-19 | 2023-08-07 | 2024-02-01 | Summary | InProgress | 87 | -80
FALSE |  |  | 5537 | 9xVQhmyTVkChMoMOy91g | Large Test File2 | 209 | 1214 | 637 | 2023-08-21 | 2028-06-01 | 2023-08-16 | 2024-06-11 | Summary | InProgress | 48 | 24
FALSE |  |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 43 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File2 | 137 | 1218 | 743 | 2023-09-05 | 2028-06-20 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 39 | 218
FALSE |  |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File2 | 51 | 1169 | 514 | 2023-09-05 | 2028-04-12 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 56 | 218
FALSE |  |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 15 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File2 | 190 | 702 | 702 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 0 | 20
FALSE |  |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File2 | 396 | 808 | 597 | 2023-10-18 | 2027-01-08 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 26 | 588
FALSE |  |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File2 | 512 | 1093 | 431 | 2024-03-04 | 2028-06-20 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 61 | 218
FALSE |  |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 376 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  |  | 4038 | VkrURyJwsSkEVRV6WcXe | Large Test File2 | 180 | 483 | 462 | 2024-08-01 | 2026-07-08 | 2024-08-01 | 2025-04-16 | Summary | InProgress | 5 | 565
FALSE |  |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File2 | 375 | 639 | 621 | 2024-08-01 | 2027-02-19 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 3 | 565
FALSE |  |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 32 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  |  | 5570 | MuDwSgsBJjDxwFkSMWYJ | Large Test File2 | 76 | 819 | 534 | 2024-11-18 | 2028-02-14 | 2024-02-05 | 2024-05-20 | Summary | InProgress | 35 | 45
FALSE |  |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 |  | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  |  | 5557 | U376LwOjKfNZoVLUlmMD | Large Test File2 | 76 | 749 | 749 | 2025-04-02 | 2028-03-14 | 2024-01-05 | 2024-04-22 | Summary | Planned | 0 | 24
FALSE |  |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File2 | 145 | 343 | 343 | 2025-04-10 | 2026-08-24 | 2025-06-27 | 2026-01-23 | Summary | Planned | 0 | 7
FALSE |  |  | 5544 | cIc3ARzcdrbXv6maHllr | Large Test File2 | 76 | 765 | 765 | 2025-04-15 | 2028-04-19 | 2023-12-06 | 2024-03-25 | Summary | Planned | 0 | 24
FALSE |  |  | 5583 | gkFBoXdv1oJb2jtBcO5M | Large Test File2 | 71 | 790 | 790 | 2025-04-23 | 2028-06-01 | 2024-03-04 | 2024-06-11 | Summary | Planned | 0 | 24
FALSE |  |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File2 | 293 | 345 | 345 | 2025-09-04 | 2027-01-06 | 2025-06-24 | 2026-08-14 | Summary | Planned | 0 | 80
FALSE |  |  | 5402 | zDUD70mdAG3rcozejCwk | Large Test File2 | 15 | 279 | 279 | 2025-09-05 | 2026-10-19 | 2025-08-26 | 2025-09-16 | Summary | Planned | 0 | 478
FALSE |  |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File2 | 340 | 872 | 872 | 2025-09-19 | 2029-02-14 | 2024-09-26 | 2026-01-30 | Summary | Planned | 0 | 8
FALSE |  |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File2 | 105 | 120 | 120 | 2026-02-18 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | 0 | -36
FALSE |  |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 20 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 20 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 30 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File2 | 77 | 160 | 160 | 2026-06-16 | 2027-02-08 | 2026-04-07 | 2026-07-27 | Summary | Planned | 0 | 574
FALSE |  |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File2 | 126 | 136 | 136 | 2026-06-24 | 2027-01-12 | 2026-01-07 | 2026-07-07 | Summary | Planned | 0 | 588
FALSE |  |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 122 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 |  | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 7 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  |  | 7264 | vNqQNKJIEgg8BiBzdWeI | Large Test File2 | 57 | 57 | 57 | 2026-07-02 | 2026-09-23 | 2025-04-04 | 2025-06-25 | Summary | Planned | 0 | 490
FALSE |  |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 13 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File2 | 97 | 145 | 145 | 2026-07-08 | 2027-02-04 | 2025-06-26 | 2025-11-11 | Summary | Planned | 0 | 565
FALSE |  |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 20 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 13 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 5 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 0 | 20
FALSE |  |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File2 | 76 | 110 | 110 | 2026-08-05 | 2027-01-06 | 2026-05-01 | 2026-08-14 | Summary | Planned | 0 | 597
FALSE |  |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | 0 | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 0 | 20
FALSE |  |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 13 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 10 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 5 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 10 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 42 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 9 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 6 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 5 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 15 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 5 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 5 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 20 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 5 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 20 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File2 | 74 | 40 | 40 | 2026-12-23 | 2027-02-19 | 2025-10-08 | 2026-01-23 | Summary | Planned | 0 | 565
FALSE |  |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File2 | 50 | 32 | 32 | 2026-12-23 | 2027-02-09 | 2025-10-08 | 2025-12-17 | Summary | Planned | 0 | 568
FALSE |  |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 20 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Critical w/High Planned Duration (44d)
Number of critical activities with a duration longer than 44 days.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 43 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 32 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
Critical w/Insufficient Detail™
Number of critical activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 43 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
Activities (To-Go)
The total number of activities within a grouping.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | 1518 | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 80 | 689
FALSE |  |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | 1874 | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 78 | 635
FALSE |  |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | 15 | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 76 | 478
FALSE |  |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | 43 | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | 37 | -436
FALSE |  |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | 15 | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 79 | 218
FALSE |  |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | 376 | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 26 | 567
FALSE |  |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | 32 | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 52 | 0
FALSE |  |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 |  | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 8 | 490
FALSE |  |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | 20 | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | 0 | -36
FALSE |  |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | 20 | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 0 | 565
FALSE |  |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | 30 | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 0 | 7
FALSE |  |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | 9 | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 0 | 648
FALSE |  |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | 122 | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 0 | 588
FALSE |  |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 |  | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 0 | 490
FALSE |  |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | 7 | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 0 | 490
FALSE |  |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | 13 | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 0 | 490
FALSE |  |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | 2 | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | 0 | -36
FALSE |  |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | 20 | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 0 | 565
FALSE |  |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | 5 | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | 0 | -36
FALSE |  |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | 30
FALSE |  |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | 2 | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 0 | -36
FALSE |  |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | 1 | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 0 | 30
FALSE |  |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | 2 | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | 0 | -36
FALSE |  |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | 2 | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | 0 | -36
FALSE |  |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | 13 | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 0 | 490
FALSE |  |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | 5 | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 0 | 7
FALSE |  |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | 4 | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | 0 | -34
FALSE |  |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | 20 | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | 0 | -34
FALSE |  |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | 629
FALSE |  |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | 3 | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 0 | -36
FALSE |  |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | 10 | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 0 | 7
FALSE |  |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | 1 | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 0 | 20
FALSE |  |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | 10 | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 605
FALSE |  |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | 13 | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 0 | 490
FALSE |  |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | 10 | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 0 | 565
FALSE |  |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | 5 | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 0 | 7
FALSE |  |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | 10 | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 0 | 597
FALSE |  |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | 42 | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 0 | 565
FALSE |  |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | 12 | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 0 | 490
FALSE |  |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | 9 | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 0 | 597
FALSE |  |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | 5 | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 0 | 490
FALSE |  |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | 5 | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 0 | 597
FALSE |  |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | 6 | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 0 | 478
FALSE |  |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | 5 | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 0 | 597
FALSE |  |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | 5 | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 0 | 574
FALSE |  |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | 5 | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 0 | 597
FALSE |  |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | 15 | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 0 | 574
FALSE |  |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | 5 | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 0 | 597
FALSE |  |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | 5 | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 0 | 597
FALSE |  |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | 5 | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 0 | 597
FALSE |  |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | 5 | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 0 | 597
FALSE |  |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | 5 | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 0 | 597
FALSE |  |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | 20 | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 0 | 574
FALSE |  |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | 5 | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 0 | 597
FALSE |  |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | 5 | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 0 | 597
FALSE |  |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | 20 | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 565
FALSE |  |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | 20 | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 0 | 568
FALSE |  |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | 5 | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 0 | 597
Total Activities
The total number of activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 77 |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File2 | Aspose.Tasks.Calendar | 3019 | 690 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 0
FALSE |  | 60 |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File2 | Aspose.Tasks.Calendar | 3019 | 1201 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 0
FALSE |  | 79 |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File2 | Aspose.Tasks.Calendar | 3019 | 634 | 2017-06-07 | 2029-04-20 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 0
FALSE |  | 71 |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File2 | Aspose.Tasks.Calendar | 3006 | 876 | 2017-06-07 | 2029-04-03 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 13
FALSE |  | 68 |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File2 | Aspose.Tasks.Calendar | 2452 | 792 | 2017-06-07 | 2027-02-17 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 567
FALSE |  | 99 |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File2 | Aspose.Tasks.Calendar | 2632 | 0 | 2017-12-28 | 2028-05-11 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 245
FALSE |  | 80 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | Aspose.Tasks.Calendar | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 689
FALSE |  | 82 |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File2 | Aspose.Tasks.Calendar | 1996 | 361 | 2019-04-01 | 2027-02-19 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 565
FALSE |  | 78 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | Aspose.Tasks.Calendar | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 635
FALSE |  | 78 |  | 6315 | 2iW64uJmzViIcLEo0dMn | Large Test File2 | Aspose.Tasks.Calendar | 1909 | 422 | 2021-01-04 | 2028-07-10 | 2021-01-04 | 2025-11-07 | Summary | InProgress | 24
FALSE |  | 79 |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File2 | Aspose.Tasks.Calendar | 2049 | 428 | 2021-04-05 | 2029-04-20 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 0
FALSE |  | 84 |  | 6317 | NzqiT3qChWGoVO5Oxj9C | Large Test File2 | Aspose.Tasks.Calendar | 1312 | 213 | 2021-08-09 | 2026-10-19 | 2021-07-06 | 2025-09-16 | Summary | InProgress | 478
FALSE |  | 81 |  | 5362 | 4bsxfawvV6TKTvCq9VoB | Large Test File2 | Aspose.Tasks.Calendar | 1240 | 236 | 2021-08-09 | 2026-07-08 | 2021-07-06 | 2023-10-16 | Summary | InProgress | 490
FALSE |  | 83 |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File2 | Aspose.Tasks.Calendar | 1857 | 309 | 2022-01-06 | 2029-04-20 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 0
FALSE |  | 75 |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File2 | Aspose.Tasks.Calendar | 1203 | 297 | 2022-04-04 | 2027-01-12 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 588
FALSE |  | 83 |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File2 | Aspose.Tasks.Calendar | 1514 | 262 | 2023-01-03 | 2028-12-12 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 93
FALSE |  | 83 |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File2 | Aspose.Tasks.Calendar | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -34
FALSE |  | 83 |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File2 | Aspose.Tasks.Calendar | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -34
FALSE |  | 69 |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File2 | Aspose.Tasks.Calendar | 996 | 304 | 2023-02-23 | 2027-02-08 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 574
FALSE |  | 17 |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File2 | Aspose.Tasks.Calendar | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 30
FALSE |  | 67 |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File2 | Aspose.Tasks.Calendar | 975 | 320 | 2023-03-06 | 2027-01-06 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 597
FALSE |  | 66 |  | 870 | m3oEXpasu7ssfpw9dqLv | Large Test File2 | Aspose.Tasks.Calendar | 1460 | 498 | 2023-03-20 | 2028-12-11 | 2023-03-20 | 2025-06-27 | Summary | InProgress | 0
FALSE |  | 79 |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File2 | Aspose.Tasks.Calendar | 891 | 191 | 2023-08-04 | 2027-02-19 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 565
FALSE |  | 76 |  | 5375 | zkXPpJkHw8DPAtspwcmA | Large Test File2 | Aspose.Tasks.Calendar | 800 | 190 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Summary | InProgress | 478
FALSE |  | 76 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | Aspose.Tasks.Calendar | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 478
FALSE |  | 65 |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File2 | Aspose.Tasks.Calendar | 881 | 310 | 2023-08-07 | 2027-02-08 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 574
FALSE |  | 31 |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 829 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 245
FALSE |  | 65 |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 426 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2025-05-30 | Summary | InProgress | -436
FALSE |  | 0 |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 245
FALSE |  | 0 |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 245
FALSE |  | 0 |  | 7382 | GJk3wpkfagyrb21gVciV | Large Test File2 | Aspose.Tasks.Calendar | 1339 | 1339 | 2023-08-07 | 2028-11-09 | 2025-02-07 | 2026-03-24 | Summary | Planned | 28
FALSE |  | 32 |  | 4129 | G6dPcJRrq5zqLYx4Vr0R | Large Test File2 | Aspose.Tasks.Calendar | 1363 | 928 | 2023-08-07 | 2028-12-12 | 2023-08-07 | 2025-06-13 | Summary | InProgress | 5
FALSE |  | 87 |  | 5753 | ZptYdARXANY2IOcoHhB1 | Large Test File2 | Aspose.Tasks.Calendar | 1128 | 148 | 2023-08-07 | 2028-01-19 | 2023-08-07 | 2024-02-01 | Summary | InProgress | -80
FALSE |  | 48 |  | 5537 | 9xVQhmyTVkChMoMOy91g | Large Test File2 | Aspose.Tasks.Calendar | 1214 | 637 | 2023-08-21 | 2028-06-01 | 2023-08-16 | 2024-06-11 | Summary | InProgress | 24
FALSE |  | 37 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 39 |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File2 | Aspose.Tasks.Calendar | 1218 | 743 | 2023-09-05 | 2028-06-20 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 218
FALSE |  | 56 |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File2 | Aspose.Tasks.Calendar | 1169 | 514 | 2023-09-05 | 2028-04-12 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 218
FALSE |  | 79 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | Aspose.Tasks.Calendar | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 218
FALSE |  | 0 |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File2 | Aspose.Tasks.Calendar | 702 | 702 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 20
FALSE |  | 26 |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File2 | Aspose.Tasks.Calendar | 808 | 597 | 2023-10-18 | 2027-01-08 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 588
FALSE |  | 61 |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File2 | Aspose.Tasks.Calendar | 1093 | 431 | 2024-03-04 | 2028-06-20 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 218
FALSE |  | 26 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | Aspose.Tasks.Calendar | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 567
FALSE |  | 5 |  | 4038 | VkrURyJwsSkEVRV6WcXe | Large Test File2 | Aspose.Tasks.Calendar | 483 | 462 | 2024-08-01 | 2026-07-08 | 2024-08-01 | 2025-04-16 | Summary | InProgress | 565
FALSE |  | 3 |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File2 | Aspose.Tasks.Calendar | 639 | 621 | 2024-08-01 | 2027-02-19 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 565
FALSE |  | 52 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 35 |  | 5570 | MuDwSgsBJjDxwFkSMWYJ | Large Test File2 | Aspose.Tasks.Calendar | 819 | 534 | 2024-11-18 | 2028-02-14 | 2024-02-05 | 2024-05-20 | Summary | InProgress | 45
FALSE |  | 8 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | Aspose.Tasks.Calendar | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 490
FALSE |  | 0 |  | 5557 | U376LwOjKfNZoVLUlmMD | Large Test File2 | Aspose.Tasks.Calendar | 749 | 749 | 2025-04-02 | 2028-03-14 | 2024-01-05 | 2024-04-22 | Summary | Planned | 24
FALSE |  | 0 |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File2 | Aspose.Tasks.Calendar | 343 | 343 | 2025-04-10 | 2026-08-24 | 2025-06-27 | 2026-01-23 | Summary | Planned | 7
FALSE |  | 0 |  | 5544 | cIc3ARzcdrbXv6maHllr | Large Test File2 | Aspose.Tasks.Calendar | 765 | 765 | 2025-04-15 | 2028-04-19 | 2023-12-06 | 2024-03-25 | Summary | Planned | 24
FALSE |  | 0 |  | 5583 | gkFBoXdv1oJb2jtBcO5M | Large Test File2 | Aspose.Tasks.Calendar | 790 | 790 | 2025-04-23 | 2028-06-01 | 2024-03-04 | 2024-06-11 | Summary | Planned | 24
FALSE |  | 0 |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File2 | Aspose.Tasks.Calendar | 345 | 345 | 2025-09-04 | 2027-01-06 | 2025-06-24 | 2026-08-14 | Summary | Planned | 80
FALSE |  | 0 |  | 5402 | zDUD70mdAG3rcozejCwk | Large Test File2 | Aspose.Tasks.Calendar | 279 | 279 | 2025-09-05 | 2026-10-19 | 2025-08-26 | 2025-09-16 | Summary | Planned | 478
FALSE |  | 0 |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File2 | Aspose.Tasks.Calendar | 872 | 872 | 2025-09-19 | 2029-02-14 | 2024-09-26 | 2026-01-30 | Summary | Planned | 8
FALSE |  | 0 |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File2 | Aspose.Tasks.Calendar | 120 | 120 | 2026-02-18 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | -36
FALSE |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE |  | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE |  | 0 |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File2 | Aspose.Tasks.Calendar | 160 | 160 | 2026-06-16 | 2027-02-08 | 2026-04-07 | 2026-07-27 | Summary | Planned | 574
FALSE |  | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE |  | 0 |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File2 | Aspose.Tasks.Calendar | 136 | 136 | 2026-06-24 | 2027-01-12 | 2026-01-07 | 2026-07-07 | Summary | Planned | 588
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE |  | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE |  | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE |  | 0 |  | 7264 | vNqQNKJIEgg8BiBzdWeI | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-02 | 2026-09-23 | 2025-04-04 | 2025-06-25 | Summary | Planned | 490
FALSE |  | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File2 | Aspose.Tasks.Calendar | 145 | 145 | 2026-07-08 | 2027-02-04 | 2025-06-26 | 2025-11-11 | Summary | Planned | 565
FALSE |  | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 20
FALSE |  | 0 |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File2 | Aspose.Tasks.Calendar | 110 | 110 | 2026-08-05 | 2027-01-06 | 2026-05-01 | 2026-08-14 | Summary | Planned | 597
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 20
FALSE |  | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE |  | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE |  | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE |  | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE |  | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE |  | 0 |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File2 | Aspose.Tasks.Calendar | 40 | 40 | 2026-12-23 | 2027-02-19 | 2025-10-08 | 2026-01-23 | Summary | Planned | 565
FALSE |  | 0 |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File2 | Aspose.Tasks.Calendar | 32 | 32 | 2026-12-23 | 2027-02-09 | 2025-10-08 | 2025-12-17 | Summary | Planned | 568
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
Milestones
Number of milestones within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 80 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | Aspose.Tasks.Calendar | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 689
FALSE |  | 78 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | Aspose.Tasks.Calendar | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 635
FALSE |  | 76 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | Aspose.Tasks.Calendar | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 478
FALSE |  | 37 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 79 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | Aspose.Tasks.Calendar | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 218
FALSE |  | 26 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | Aspose.Tasks.Calendar | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 567
FALSE |  | 52 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 8 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | Aspose.Tasks.Calendar | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 490
FALSE |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE |  | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE |  | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE |  | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE |  | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE |  | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE |  | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE |  | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE |  | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE |  | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE |  | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
Normal Tasks
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 80 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | Aspose.Tasks.Calendar | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 689
FALSE |  | 78 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | Aspose.Tasks.Calendar | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 635
FALSE |  | 76 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | Aspose.Tasks.Calendar | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 478
FALSE |  | 37 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 79 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | Aspose.Tasks.Calendar | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 218
FALSE |  | 26 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | Aspose.Tasks.Calendar | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 567
FALSE |  | 52 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 8 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | Aspose.Tasks.Calendar | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 490
FALSE |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE |  | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE |  | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE |  | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE |  | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE |  | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE |  | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE |  | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE |  | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE |  | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE |  | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
Summaries
Number of summary activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 77 |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File2 | Aspose.Tasks.Calendar | 3019 | 690 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 0
FALSE |  | 60 |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File2 | Aspose.Tasks.Calendar | 3019 | 1201 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 0
FALSE |  | 79 |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File2 | Aspose.Tasks.Calendar | 3019 | 634 | 2017-06-07 | 2029-04-20 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 0
FALSE |  | 71 |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File2 | Aspose.Tasks.Calendar | 3006 | 876 | 2017-06-07 | 2029-04-03 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 13
FALSE |  | 68 |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File2 | Aspose.Tasks.Calendar | 2452 | 792 | 2017-06-07 | 2027-02-17 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 567
FALSE |  | 99 |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File2 | Aspose.Tasks.Calendar | 2632 | 0 | 2017-12-28 | 2028-05-11 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 245
FALSE |  | 82 |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File2 | Aspose.Tasks.Calendar | 1996 | 361 | 2019-04-01 | 2027-02-19 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 565
FALSE |  | 78 |  | 6315 | 2iW64uJmzViIcLEo0dMn | Large Test File2 | Aspose.Tasks.Calendar | 1909 | 422 | 2021-01-04 | 2028-07-10 | 2021-01-04 | 2025-11-07 | Summary | InProgress | 24
FALSE |  | 79 |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File2 | Aspose.Tasks.Calendar | 2049 | 428 | 2021-04-05 | 2029-04-20 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 0
FALSE |  | 84 |  | 6317 | NzqiT3qChWGoVO5Oxj9C | Large Test File2 | Aspose.Tasks.Calendar | 1312 | 213 | 2021-08-09 | 2026-10-19 | 2021-07-06 | 2025-09-16 | Summary | InProgress | 478
FALSE |  | 81 |  | 5362 | 4bsxfawvV6TKTvCq9VoB | Large Test File2 | Aspose.Tasks.Calendar | 1240 | 236 | 2021-08-09 | 2026-07-08 | 2021-07-06 | 2023-10-16 | Summary | InProgress | 490
FALSE |  | 83 |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File2 | Aspose.Tasks.Calendar | 1857 | 309 | 2022-01-06 | 2029-04-20 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 0
FALSE |  | 75 |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File2 | Aspose.Tasks.Calendar | 1203 | 297 | 2022-04-04 | 2027-01-12 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 588
FALSE |  | 83 |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File2 | Aspose.Tasks.Calendar | 1514 | 262 | 2023-01-03 | 2028-12-12 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 93
FALSE |  | 83 |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File2 | Aspose.Tasks.Calendar | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -34
FALSE |  | 83 |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File2 | Aspose.Tasks.Calendar | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -34
FALSE |  | 69 |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File2 | Aspose.Tasks.Calendar | 996 | 304 | 2023-02-23 | 2027-02-08 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 574
FALSE |  | 17 |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File2 | Aspose.Tasks.Calendar | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 30
FALSE |  | 67 |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File2 | Aspose.Tasks.Calendar | 975 | 320 | 2023-03-06 | 2027-01-06 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 597
FALSE |  | 66 |  | 870 | m3oEXpasu7ssfpw9dqLv | Large Test File2 | Aspose.Tasks.Calendar | 1460 | 498 | 2023-03-20 | 2028-12-11 | 2023-03-20 | 2025-06-27 | Summary | InProgress | 0
FALSE |  | 79 |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File2 | Aspose.Tasks.Calendar | 891 | 191 | 2023-08-04 | 2027-02-19 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 565
FALSE |  | 76 |  | 5375 | zkXPpJkHw8DPAtspwcmA | Large Test File2 | Aspose.Tasks.Calendar | 800 | 190 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Summary | InProgress | 478
FALSE |  | 65 |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File2 | Aspose.Tasks.Calendar | 881 | 310 | 2023-08-07 | 2027-02-08 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 574
FALSE |  | 31 |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 829 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 245
FALSE |  | 65 |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 426 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2025-05-30 | Summary | InProgress | -436
FALSE |  | 0 |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 245
FALSE |  | 0 |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 245
FALSE |  | 0 |  | 7382 | GJk3wpkfagyrb21gVciV | Large Test File2 | Aspose.Tasks.Calendar | 1339 | 1339 | 2023-08-07 | 2028-11-09 | 2025-02-07 | 2026-03-24 | Summary | Planned | 28
FALSE |  | 32 |  | 4129 | G6dPcJRrq5zqLYx4Vr0R | Large Test File2 | Aspose.Tasks.Calendar | 1363 | 928 | 2023-08-07 | 2028-12-12 | 2023-08-07 | 2025-06-13 | Summary | InProgress | 5
FALSE |  | 87 |  | 5753 | ZptYdARXANY2IOcoHhB1 | Large Test File2 | Aspose.Tasks.Calendar | 1128 | 148 | 2023-08-07 | 2028-01-19 | 2023-08-07 | 2024-02-01 | Summary | InProgress | -80
FALSE |  | 48 |  | 5537 | 9xVQhmyTVkChMoMOy91g | Large Test File2 | Aspose.Tasks.Calendar | 1214 | 637 | 2023-08-21 | 2028-06-01 | 2023-08-16 | 2024-06-11 | Summary | InProgress | 24
FALSE |  | 39 |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File2 | Aspose.Tasks.Calendar | 1218 | 743 | 2023-09-05 | 2028-06-20 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 218
FALSE |  | 56 |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File2 | Aspose.Tasks.Calendar | 1169 | 514 | 2023-09-05 | 2028-04-12 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 218
FALSE |  | 0 |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File2 | Aspose.Tasks.Calendar | 702 | 702 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 20
FALSE |  | 26 |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File2 | Aspose.Tasks.Calendar | 808 | 597 | 2023-10-18 | 2027-01-08 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 588
FALSE |  | 61 |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File2 | Aspose.Tasks.Calendar | 1093 | 431 | 2024-03-04 | 2028-06-20 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 218
FALSE |  | 5 |  | 4038 | VkrURyJwsSkEVRV6WcXe | Large Test File2 | Aspose.Tasks.Calendar | 483 | 462 | 2024-08-01 | 2026-07-08 | 2024-08-01 | 2025-04-16 | Summary | InProgress | 565
FALSE |  | 3 |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File2 | Aspose.Tasks.Calendar | 639 | 621 | 2024-08-01 | 2027-02-19 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 565
FALSE |  | 35 |  | 5570 | MuDwSgsBJjDxwFkSMWYJ | Large Test File2 | Aspose.Tasks.Calendar | 819 | 534 | 2024-11-18 | 2028-02-14 | 2024-02-05 | 2024-05-20 | Summary | InProgress | 45
FALSE |  | 0 |  | 5557 | U376LwOjKfNZoVLUlmMD | Large Test File2 | Aspose.Tasks.Calendar | 749 | 749 | 2025-04-02 | 2028-03-14 | 2024-01-05 | 2024-04-22 | Summary | Planned | 24
FALSE |  | 0 |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File2 | Aspose.Tasks.Calendar | 343 | 343 | 2025-04-10 | 2026-08-24 | 2025-06-27 | 2026-01-23 | Summary | Planned | 7
FALSE |  | 0 |  | 5544 | cIc3ARzcdrbXv6maHllr | Large Test File2 | Aspose.Tasks.Calendar | 765 | 765 | 2025-04-15 | 2028-04-19 | 2023-12-06 | 2024-03-25 | Summary | Planned | 24
FALSE |  | 0 |  | 5583 | gkFBoXdv1oJb2jtBcO5M | Large Test File2 | Aspose.Tasks.Calendar | 790 | 790 | 2025-04-23 | 2028-06-01 | 2024-03-04 | 2024-06-11 | Summary | Planned | 24
FALSE |  | 0 |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File2 | Aspose.Tasks.Calendar | 345 | 345 | 2025-09-04 | 2027-01-06 | 2025-06-24 | 2026-08-14 | Summary | Planned | 80
FALSE |  | 0 |  | 5402 | zDUD70mdAG3rcozejCwk | Large Test File2 | Aspose.Tasks.Calendar | 279 | 279 | 2025-09-05 | 2026-10-19 | 2025-08-26 | 2025-09-16 | Summary | Planned | 478
FALSE |  | 0 |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File2 | Aspose.Tasks.Calendar | 872 | 872 | 2025-09-19 | 2029-02-14 | 2024-09-26 | 2026-01-30 | Summary | Planned | 8
FALSE |  | 0 |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File2 | Aspose.Tasks.Calendar | 120 | 120 | 2026-02-18 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | -36
FALSE |  | 0 |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File2 | Aspose.Tasks.Calendar | 160 | 160 | 2026-06-16 | 2027-02-08 | 2026-04-07 | 2026-07-27 | Summary | Planned | 574
FALSE |  | 0 |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File2 | Aspose.Tasks.Calendar | 136 | 136 | 2026-06-24 | 2027-01-12 | 2026-01-07 | 2026-07-07 | Summary | Planned | 588
FALSE |  | 0 |  | 7264 | vNqQNKJIEgg8BiBzdWeI | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-02 | 2026-09-23 | 2025-04-04 | 2025-06-25 | Summary | Planned | 490
FALSE |  | 0 |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File2 | Aspose.Tasks.Calendar | 145 | 145 | 2026-07-08 | 2027-02-04 | 2025-06-26 | 2025-11-11 | Summary | Planned | 565
FALSE |  | 0 |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File2 | Aspose.Tasks.Calendar | 110 | 110 | 2026-08-05 | 2027-01-06 | 2026-05-01 | 2026-08-14 | Summary | Planned | 597
FALSE |  | 0 |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File2 | Aspose.Tasks.Calendar | 40 | 40 | 2026-12-23 | 2027-02-19 | 2025-10-08 | 2026-01-23 | Summary | Planned | 565
FALSE |  | 0 |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File2 | Aspose.Tasks.Calendar | 32 | 32 | 2026-12-23 | 2027-02-09 | 2025-10-08 | 2025-12-17 | Summary | Planned | 568
Total Tasks & Milestones
Total number of regular tasks and milestones in the project schedule.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 80 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | Aspose.Tasks.Calendar | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 689
FALSE |  | 78 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | Aspose.Tasks.Calendar | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 635
FALSE |  | 76 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | Aspose.Tasks.Calendar | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 478
FALSE |  | 37 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 79 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | Aspose.Tasks.Calendar | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 218
FALSE |  | 26 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | Aspose.Tasks.Calendar | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 567
FALSE |  | 52 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 8 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | Aspose.Tasks.Calendar | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 490
FALSE |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE |  | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE |  | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE |  | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE |  | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE |  | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 20
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 20
FALSE |  | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE |  | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE |  | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE |  | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE |  | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
Total Activities (To-Go) - % of Total
The total number of activities within a grouping. Percentage shows total total to-go (planned and in-progress) activities (normal, milestone, summary and LOE) out of total to-go and completed activities.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 77 |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File2 | Aspose.Tasks.Calendar | 3019 | 690 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 0
FALSE |  | 60 |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File2 | Aspose.Tasks.Calendar | 3019 | 1201 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 0
FALSE |  | 79 |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File2 | Aspose.Tasks.Calendar | 3019 | 634 | 2017-06-07 | 2029-04-20 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 0
FALSE |  | 71 |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File2 | Aspose.Tasks.Calendar | 3006 | 876 | 2017-06-07 | 2029-04-03 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 13
FALSE |  | 68 |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File2 | Aspose.Tasks.Calendar | 2452 | 792 | 2017-06-07 | 2027-02-17 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 567
FALSE |  | 99 |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File2 | Aspose.Tasks.Calendar | 2632 | 0 | 2017-12-28 | 2028-05-11 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 245
FALSE |  | 80 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | Aspose.Tasks.Calendar | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 689
FALSE |  | 82 |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File2 | Aspose.Tasks.Calendar | 1996 | 361 | 2019-04-01 | 2027-02-19 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 565
FALSE |  | 78 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | Aspose.Tasks.Calendar | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 635
FALSE |  | 78 |  | 6315 | 2iW64uJmzViIcLEo0dMn | Large Test File2 | Aspose.Tasks.Calendar | 1909 | 422 | 2021-01-04 | 2028-07-10 | 2021-01-04 | 2025-11-07 | Summary | InProgress | 24
FALSE |  | 79 |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File2 | Aspose.Tasks.Calendar | 2049 | 428 | 2021-04-05 | 2029-04-20 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 0
FALSE |  | 84 |  | 6317 | NzqiT3qChWGoVO5Oxj9C | Large Test File2 | Aspose.Tasks.Calendar | 1312 | 213 | 2021-08-09 | 2026-10-19 | 2021-07-06 | 2025-09-16 | Summary | InProgress | 478
FALSE |  | 81 |  | 5362 | 4bsxfawvV6TKTvCq9VoB | Large Test File2 | Aspose.Tasks.Calendar | 1240 | 236 | 2021-08-09 | 2026-07-08 | 2021-07-06 | 2023-10-16 | Summary | InProgress | 490
FALSE |  | 83 |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File2 | Aspose.Tasks.Calendar | 1857 | 309 | 2022-01-06 | 2029-04-20 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 0
FALSE |  | 75 |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File2 | Aspose.Tasks.Calendar | 1203 | 297 | 2022-04-04 | 2027-01-12 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 588
FALSE |  | 83 |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File2 | Aspose.Tasks.Calendar | 1514 | 262 | 2023-01-03 | 2028-12-12 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 93
FALSE |  | 83 |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File2 | Aspose.Tasks.Calendar | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -34
FALSE |  | 83 |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File2 | Aspose.Tasks.Calendar | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -34
FALSE |  | 69 |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File2 | Aspose.Tasks.Calendar | 996 | 304 | 2023-02-23 | 2027-02-08 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 574
FALSE |  | 17 |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File2 | Aspose.Tasks.Calendar | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 30
FALSE |  | 67 |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File2 | Aspose.Tasks.Calendar | 975 | 320 | 2023-03-06 | 2027-01-06 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 597
FALSE |  | 66 |  | 870 | m3oEXpasu7ssfpw9dqLv | Large Test File2 | Aspose.Tasks.Calendar | 1460 | 498 | 2023-03-20 | 2028-12-11 | 2023-03-20 | 2025-06-27 | Summary | InProgress | 0
FALSE |  | 79 |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File2 | Aspose.Tasks.Calendar | 891 | 191 | 2023-08-04 | 2027-02-19 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 565
FALSE |  | 76 |  | 5375 | zkXPpJkHw8DPAtspwcmA | Large Test File2 | Aspose.Tasks.Calendar | 800 | 190 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Summary | InProgress | 478
FALSE |  | 76 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | Aspose.Tasks.Calendar | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 478
FALSE |  | 65 |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File2 | Aspose.Tasks.Calendar | 881 | 310 | 2023-08-07 | 2027-02-08 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 574
FALSE |  | 31 |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 829 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 245
FALSE |  | 65 |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 426 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2025-05-30 | Summary | InProgress | -436
FALSE |  | 0 |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 245
FALSE |  | 0 |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 245
FALSE |  | 0 |  | 7382 | GJk3wpkfagyrb21gVciV | Large Test File2 | Aspose.Tasks.Calendar | 1339 | 1339 | 2023-08-07 | 2028-11-09 | 2025-02-07 | 2026-03-24 | Summary | Planned | 28
FALSE |  | 32 |  | 4129 | G6dPcJRrq5zqLYx4Vr0R | Large Test File2 | Aspose.Tasks.Calendar | 1363 | 928 | 2023-08-07 | 2028-12-12 | 2023-08-07 | 2025-06-13 | Summary | InProgress | 5
FALSE |  | 87 |  | 5753 | ZptYdARXANY2IOcoHhB1 | Large Test File2 | Aspose.Tasks.Calendar | 1128 | 148 | 2023-08-07 | 2028-01-19 | 2023-08-07 | 2024-02-01 | Summary | InProgress | -80
FALSE |  | 48 |  | 5537 | 9xVQhmyTVkChMoMOy91g | Large Test File2 | Aspose.Tasks.Calendar | 1214 | 637 | 2023-08-21 | 2028-06-01 | 2023-08-16 | 2024-06-11 | Summary | InProgress | 24
FALSE |  | 37 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 39 |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File2 | Aspose.Tasks.Calendar | 1218 | 743 | 2023-09-05 | 2028-06-20 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 218
FALSE |  | 56 |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File2 | Aspose.Tasks.Calendar | 1169 | 514 | 2023-09-05 | 2028-04-12 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 218
FALSE |  | 79 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | Aspose.Tasks.Calendar | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 218
FALSE |  | 0 |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File2 | Aspose.Tasks.Calendar | 702 | 702 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 20
FALSE |  | 26 |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File2 | Aspose.Tasks.Calendar | 808 | 597 | 2023-10-18 | 2027-01-08 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 588
FALSE |  | 61 |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File2 | Aspose.Tasks.Calendar | 1093 | 431 | 2024-03-04 | 2028-06-20 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 218
FALSE |  | 26 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | Aspose.Tasks.Calendar | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 567
FALSE |  | 5 |  | 4038 | VkrURyJwsSkEVRV6WcXe | Large Test File2 | Aspose.Tasks.Calendar | 483 | 462 | 2024-08-01 | 2026-07-08 | 2024-08-01 | 2025-04-16 | Summary | InProgress | 565
FALSE |  | 3 |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File2 | Aspose.Tasks.Calendar | 639 | 621 | 2024-08-01 | 2027-02-19 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 565
FALSE |  | 52 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 35 |  | 5570 | MuDwSgsBJjDxwFkSMWYJ | Large Test File2 | Aspose.Tasks.Calendar | 819 | 534 | 2024-11-18 | 2028-02-14 | 2024-02-05 | 2024-05-20 | Summary | InProgress | 45
FALSE |  | 8 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | Aspose.Tasks.Calendar | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 490
FALSE |  | 0 |  | 5557 | U376LwOjKfNZoVLUlmMD | Large Test File2 | Aspose.Tasks.Calendar | 749 | 749 | 2025-04-02 | 2028-03-14 | 2024-01-05 | 2024-04-22 | Summary | Planned | 24
FALSE |  | 0 |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File2 | Aspose.Tasks.Calendar | 343 | 343 | 2025-04-10 | 2026-08-24 | 2025-06-27 | 2026-01-23 | Summary | Planned | 7
FALSE |  | 0 |  | 5544 | cIc3ARzcdrbXv6maHllr | Large Test File2 | Aspose.Tasks.Calendar | 765 | 765 | 2025-04-15 | 2028-04-19 | 2023-12-06 | 2024-03-25 | Summary | Planned | 24
FALSE |  | 0 |  | 5583 | gkFBoXdv1oJb2jtBcO5M | Large Test File2 | Aspose.Tasks.Calendar | 790 | 790 | 2025-04-23 | 2028-06-01 | 2024-03-04 | 2024-06-11 | Summary | Planned | 24
FALSE |  | 0 |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File2 | Aspose.Tasks.Calendar | 345 | 345 | 2025-09-04 | 2027-01-06 | 2025-06-24 | 2026-08-14 | Summary | Planned | 80
FALSE |  | 0 |  | 5402 | zDUD70mdAG3rcozejCwk | Large Test File2 | Aspose.Tasks.Calendar | 279 | 279 | 2025-09-05 | 2026-10-19 | 2025-08-26 | 2025-09-16 | Summary | Planned | 478
FALSE |  | 0 |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File2 | Aspose.Tasks.Calendar | 872 | 872 | 2025-09-19 | 2029-02-14 | 2024-09-26 | 2026-01-30 | Summary | Planned | 8
FALSE |  | 0 |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File2 | Aspose.Tasks.Calendar | 120 | 120 | 2026-02-18 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | -36
FALSE |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE |  | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE |  | 0 |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File2 | Aspose.Tasks.Calendar | 160 | 160 | 2026-06-16 | 2027-02-08 | 2026-04-07 | 2026-07-27 | Summary | Planned | 574
FALSE |  | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE |  | 0 |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File2 | Aspose.Tasks.Calendar | 136 | 136 | 2026-06-24 | 2027-01-12 | 2026-01-07 | 2026-07-07 | Summary | Planned | 588
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE |  | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE |  | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE |  | 0 |  | 7264 | vNqQNKJIEgg8BiBzdWeI | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-02 | 2026-09-23 | 2025-04-04 | 2025-06-25 | Summary | Planned | 490
FALSE |  | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File2 | Aspose.Tasks.Calendar | 145 | 145 | 2026-07-08 | 2027-02-04 | 2025-06-26 | 2025-11-11 | Summary | Planned | 565
FALSE |  | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 20
FALSE |  | 0 |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File2 | Aspose.Tasks.Calendar | 110 | 110 | 2026-08-05 | 2027-01-06 | 2026-05-01 | 2026-08-14 | Summary | Planned | 597
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 20
FALSE |  | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE |  | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE |  | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE |  | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE |  | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE |  | 0 |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File2 | Aspose.Tasks.Calendar | 40 | 40 | 2026-12-23 | 2027-02-19 | 2025-10-08 | 2026-01-23 | Summary | Planned | 565
FALSE |  | 0 |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File2 | Aspose.Tasks.Calendar | 32 | 32 | 2026-12-23 | 2027-02-09 | 2025-10-08 | 2025-12-17 | Summary | Planned | 568
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
Tasks & Milestones (To-Go) - % of Total To-Go
The total number of activities within a grouping. Percentage shows total to-go (planned and in-progress) tasks and milestones out of all activities (normal, milestone, summary, and LOE).
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 80 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | Aspose.Tasks.Calendar | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 689
FALSE |  | 78 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | Aspose.Tasks.Calendar | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 635
FALSE |  | 76 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | Aspose.Tasks.Calendar | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 478
FALSE |  | 37 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 79 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | Aspose.Tasks.Calendar | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 218
FALSE |  | 26 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | Aspose.Tasks.Calendar | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 567
FALSE |  | 52 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 8 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | Aspose.Tasks.Calendar | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 490
FALSE |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE |  | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE |  | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE |  | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE |  | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE |  | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 20
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 20
FALSE |  | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE |  | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE |  | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE |  | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE |  | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
Milestones (To-Go)
Number of milestones within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 168 | MT1CsCIMkhjJER6f3fjG | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2025-10-08 | 2025-10-08 | Milestone | Planned | 20
FALSE |  | 0 |  | 5312 | mmXMEY1kphvE51vXPbq6 | Large Test File2 | Aspose.Tasks.Calendar | 0 | 0 | 2026-08-05 | 2026-08-05 | 2026-05-01 | 2026-05-01 | Milestone | Planned | 20
Normal Tasks (To-Go)
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 80 |  | 7378 | YjoFZZooPnFRzsk2Ba2E | Large Test File2 | Aspose.Tasks.Calendar | 1851 | 363 | 2019-04-01 | 2026-08-20 | 2019-01-15 | 2025-01-03 | Normal | InProgress | 689
FALSE |  | 78 |  | 7376 | FfEUU5kpALOu6FlmjosD | Large Test File2 | Aspose.Tasks.Calendar | 1896 | 418 | 2019-04-15 | 2026-11-06 | 2019-04-15 | 2026-09-04 | Normal | InProgress | 635
FALSE |  | 76 |  | 5376 | zSTdFwWI5FOaluV37lYS | Large Test File2 | Aspose.Tasks.Calendar | 238 | 56 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Normal | InProgress | 478
FALSE |  | 37 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 79 |  | 4136 | bllhlvXmXgF1yFG9Nwfe | Large Test File2 | Aspose.Tasks.Calendar | 79 | 16 | 2023-09-05 | 2028-02-25 | 2025-06-30 | 2025-07-21 | Normal | InProgress | 218
FALSE |  | 26 |  | 6691 | xLErpFHjPEH3ifHRbBMY | Large Test File2 | Aspose.Tasks.Calendar | 659 | 486 | 2024-06-03 | 2027-02-17 | 2024-06-03 | 2025-11-21 | Normal | InProgress | 567
FALSE |  | 52 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 8 |  | 7260 | DPsh83rHAyIaiD8XYnO0 | Large Test File2 | Aspose.Tasks.Calendar | 359 | 329 | 2024-12-23 | 2026-07-01 |  |  | Normal | InProgress | 490
FALSE |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 |  | 6623 | BVU87KMg9Rhzc6j5yKVh | Large Test File2 | Aspose.Tasks.Calendar | 19 | 19 | 2026-06-09 | 2026-07-08 | 2025-03-20 | 2025-04-16 | Normal | Planned | 565
FALSE |  | 0 |  | 3914 | e7efPn2W4IFyilt2hNai | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-06-16 | 2026-07-24 | 2025-11-11 | 2025-12-23 | Normal | Planned | 7
FALSE |  | 0 |  | 3920 | mBVNyTIN7rvKyNQxzyxZ | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-06-18 | 2026-07-01 | 2026-04-08 | 2026-04-21 | Normal | Planned | 648
FALSE |  | 0 |  | 6435 | Ql00ScpYzqtI9PQP57zu | Large Test File2 | Aspose.Tasks.Calendar | 133 | 133 | 2026-06-26 | 2027-01-08 | 2026-01-09 | 2026-07-03 | Normal | Planned | 588
FALSE |  | 0 |  | 7261 | isfym7y8CMuc9Vq3Mbcl | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-01 | 2026-07-02 |  |  | Normal | Planned | 490
FALSE |  | 0 |  | 5368 | NKJL1ZJN3KgUArkbA4qS | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-02 | 2026-07-08 | 2023-09-12 | 2023-09-20 | Normal | Planned | 490
FALSE |  | 0 |  | 7265 | uNFJkQaxxZ7oOYaM8QxX | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-07-02 | 2026-07-23 | 2025-04-04 | 2025-04-23 | Normal | Planned | 490
FALSE |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 |  | 4045 | mDphgqAAxA2RnvA52x8A | Large Test File2 | Aspose.Tasks.Calendar | 24 | 24 | 2026-07-08 | 2026-08-11 | 2025-06-26 | 2025-07-24 | Normal | Planned | 565
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 |  | 5310 | RMnJ5j2lLGlokfxLAfSa | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | 30
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 |  | 5225 | b44Ij1WE7Qrra8bO7ZTN | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-07-20 | 2026-07-21 | 2024-05-03 | 2024-05-03 | Normal | Planned | 30
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 |  | 7266 | y7TR6NxR4uOKxinxsnEt | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-07-23 | 2026-08-11 | 2025-04-24 | 2025-05-12 | Normal | Planned | 490
FALSE |  | 0 |  | 3915 | jOX8xbQ5VzQq8YZ9EVJS | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-07-24 | 2026-08-03 | 2025-12-24 | 2025-12-31 | Normal | Planned | 7
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 |  | 3921 | jEuseC90wYhkn0V4svXs | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | 629
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
FALSE |  | 0 |  | 3916 | xcLTkuiw0V5a2mOSGmcP | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-03 | 2026-08-14 | 2026-01-02 | 2026-01-15 | Normal | Planned | 7
FALSE |  | 0 |  | 6881 | XekYY8n1P4vELtk4BUks | Large Test File2 | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-04 | 2026-08-05 | 2025-12-16 | 2025-12-17 | Normal | Planned | 20
FALSE |  | 0 |  | 5314 | SRtjKDi8lC5PBWdNdIAU | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-08-05 | 2026-08-19 | 2026-05-01 | 2026-05-15 | Normal | Planned | 605
FALSE |  | 0 |  | 7267 | f0BUmD79ZhKqjjzrwXUq | Large Test File2 | Aspose.Tasks.Calendar | 14 | 14 | 2026-08-11 | 2026-08-28 | 2025-05-13 | 2025-05-30 | Normal | Planned | 490
FALSE |  | 0 |  | 4046 | 5HyQBVwuqRdeW1HhaSOP | Large Test File2 | Aspose.Tasks.Calendar | 11 | 11 | 2026-08-11 | 2026-08-27 | 2025-07-25 | 2025-08-07 | Normal | Planned | 565
FALSE |  | 0 |  | 3917 | hmttcJptV92JIo4OpANW | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-08-14 | 2026-08-24 | 2026-01-16 | 2026-01-23 | Normal | Planned | 7
FALSE |  | 0 |  | 5316 | LCfcLPfxTjnSY0dCrjlE | Large Test File2 | Aspose.Tasks.Calendar | 9 | 9 | 2026-08-19 | 2026-09-16 | 2026-05-01 | 2026-05-15 | Normal | Planned | 597
FALSE |  | 0 |  | 4047 | WZVyPUJ7ZWyAZGgKP4Y9 | Large Test File2 | Aspose.Tasks.Calendar | 80 | 80 | 2026-08-27 | 2026-12-23 | 2025-08-08 | 2025-10-07 | Normal | Planned | 565
FALSE |  | 0 |  | 7268 | sP1zO7OhzT9CUKqdzecJ | Large Test File2 | Aspose.Tasks.Calendar | 12 | 12 | 2026-08-28 | 2026-09-16 | 2025-06-02 | 2025-06-17 | Normal | Planned | 490
FALSE |  | 0 |  | 5317 | pw6YyMXR7oeqsrtIHdqo | Large Test File2 | Aspose.Tasks.Calendar | 10 | 10 | 2026-09-16 | 2026-10-09 | 2026-05-15 | 2026-05-28 | Normal | Planned | 597
FALSE |  | 0 |  | 7269 | 7v5GPnNw6yREyKfoeMiZ | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-09-16 | 2026-09-23 | 2025-06-18 | 2025-06-25 | Normal | Planned | 490
FALSE |  | 0 |  | 6467 | n3qEWBmgcrCNzbacKk03 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-16 | 2026-05-28 | 2026-06-04 | Normal | Planned | 597
FALSE |  | 0 |  | 5404 | UrewlDJ3J2c8Ueci7p9E | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-09 | 2026-10-19 | 2025-09-09 | 2025-09-16 | Normal | Planned | 478
FALSE |  | 0 |  | 6468 | BqsEZH5IWCI59bWKml0D | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-16 | 2026-10-23 | 2026-06-04 | 2026-06-11 | Normal | Planned | 597
FALSE |  | 0 |  | 3922 | yD55zWPn8USsNa4i8nCC | Large Test File2 | Aspose.Tasks.Calendar | 7 | 7 | 2026-10-21 | 2026-10-30 | 2026-04-30 | 2026-05-07 | Normal | Planned | 574
FALSE |  | 0 |  | 6469 | TtC6fzAb8zClFAVfKkP8 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-23 | 2026-10-30 | 2026-06-11 | 2026-06-18 | Normal | Planned | 597
FALSE |  | 0 |  | 3923 | FwZ3BvPGTUfvQ1CE4iRh | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-10-30 | 2026-12-03 | 2026-05-07 | 2026-05-29 | Normal | Planned | 574
FALSE |  | 0 |  | 6470 | UrgnPc0HjVwpN7twGsWX | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-10-30 | 2026-11-06 | 2026-06-18 | 2026-06-25 | Normal | Planned | 597
FALSE |  | 0 |  | 5318 | KMG5hXAC4X2MZPfyVOSc | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-06 | 2026-11-16 | 2026-06-25 | 2026-07-02 | Normal | Planned | 597
FALSE |  | 0 |  | 5319 | mDGXCmTQB2ITo8MYwlYq | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-11-16 | 2026-11-24 | 2026-07-02 | 2026-07-09 | Normal | Planned | 597
FALSE |  | 0 |  | 5320 | hu6UActfLD0rLfdNqC55 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-11-24 | 2026-12-01 | 2026-07-09 | 2026-07-16 | Normal | Planned | 597
FALSE |  | 0 |  | 5321 | pG9QTaeiPcJe7Bm3iI1s | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-01 | 2026-12-08 | 2026-07-16 | 2026-07-23 | Normal | Planned | 597
FALSE |  | 0 |  | 3924 | N1CigBiMQE2J41ZAMkt0 | Large Test File2 | Aspose.Tasks.Calendar | 22 | 22 | 2026-12-03 | 2027-01-06 | 2026-05-29 | 2026-06-29 | Normal | Planned | 574
FALSE |  | 0 |  | 5322 | oNpYocgOFdrRcJiQE0H5 | Large Test File2 | Aspose.Tasks.Calendar | 6 | 6 | 2026-12-08 | 2026-12-16 | 2026-07-23 | 2026-07-30 | Normal | Planned | 597
FALSE |  | 0 |  | 5323 | Tt5dEbDabBigq84Eat5c | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-16 | 2026-12-23 | 2026-07-30 | 2026-08-06 | Normal | Planned | 597
FALSE |  | 0 |  | 4048 | ybbKhm9jdtNbVzABGZ8L | Large Test File2 | Aspose.Tasks.Calendar | 25 | 25 | 2026-12-23 | 2027-01-29 | 2025-10-08 | 2025-11-04 | Normal | Planned | 565
FALSE |  | 0 |  | 4052 | JSSXcLTdD9VQNM766DgK | Large Test File2 | Aspose.Tasks.Calendar | 21 | 21 | 2026-12-23 | 2027-01-22 | 2025-10-08 | 2025-11-04 | Normal | Planned | 568
FALSE |  | 0 |  | 5324 | INz2wzhVzgQCZLXqwTZc | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-12-23 | 2027-01-05 | 2026-08-06 | 2026-08-13 | Normal | Planned | 597
Summaries (To-Go)
Number of summary activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 77 |  | 1249 | v1zgYyoO7UpynPZXt29g | Large Test File2 | Aspose.Tasks.Calendar | 3019 | 690 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2028-09-29 | Summary | InProgress | 0
FALSE |  | 60 |  | 147 | DEZpxiHWY7fkyvQEaEGc | Large Test File2 | Aspose.Tasks.Calendar | 3019 | 1201 | 2017-06-07 | 2029-04-20 | 2017-06-07 | 2026-11-09 | Summary | InProgress | 0
FALSE |  | 79 |  | 6274 | 2SmU2FGkRqKGvY5bRkVZ | Large Test File2 | Aspose.Tasks.Calendar | 3019 | 634 | 2017-06-07 | 2029-04-20 | 2021-01-04 | 2026-10-02 | Summary | InProgress | 0
FALSE |  | 71 |  | 6279 | p7EJXT1muDSglD2OZLFH | Large Test File2 | Aspose.Tasks.Calendar | 3006 | 876 | 2017-06-07 | 2029-04-03 | 2022-03-07 | 2026-08-17 | Summary | InProgress | 13
FALSE |  | 68 |  | 6688 | aKOlgm9Tw9oPXF0YCFLp | Large Test File2 | Aspose.Tasks.Calendar | 2452 | 792 | 2017-06-07 | 2027-02-17 | 2019-01-15 | 2028-09-29 | Summary | InProgress | 567
FALSE |  | 99 |  | 7131 | XTX9Wl5SzTxAD1rtsh9U | Large Test File2 | Aspose.Tasks.Calendar | 2632 | 0 | 2017-12-28 | 2028-05-11 | 2023-10-12 | 2026-06-30 | Summary | InProgress | 245
FALSE |  | 82 |  | 6271 | Q6QswYSvhipRUbZBXuiu | Large Test File2 | Aspose.Tasks.Calendar | 1996 | 361 | 2019-04-01 | 2027-02-19 | 2019-04-01 | 2026-08-26 | Summary | InProgress | 565
FALSE |  | 78 |  | 6315 | 2iW64uJmzViIcLEo0dMn | Large Test File2 | Aspose.Tasks.Calendar | 1909 | 422 | 2021-01-04 | 2028-07-10 | 2021-01-04 | 2025-11-07 | Summary | InProgress | 24
FALSE |  | 79 |  | 6275 | OL3lkJGtK3tkk0d4SBRn | Large Test File2 | Aspose.Tasks.Calendar | 2049 | 428 | 2021-04-05 | 2029-04-20 | 2021-03-08 | 2026-10-02 | Summary | InProgress | 0
FALSE |  | 84 |  | 6317 | NzqiT3qChWGoVO5Oxj9C | Large Test File2 | Aspose.Tasks.Calendar | 1312 | 213 | 2021-08-09 | 2026-10-19 | 2021-07-06 | 2025-09-16 | Summary | InProgress | 478
FALSE |  | 81 |  | 5362 | 4bsxfawvV6TKTvCq9VoB | Large Test File2 | Aspose.Tasks.Calendar | 1240 | 236 | 2021-08-09 | 2026-07-08 | 2021-07-06 | 2023-10-16 | Summary | InProgress | 490
FALSE |  | 83 |  | 6296 | SlR21lje1Tex9DLMlAM1 | Large Test File2 | Aspose.Tasks.Calendar | 1857 | 309 | 2022-01-06 | 2029-04-20 | 2022-01-06 | 2026-09-15 | Summary | InProgress | 0
FALSE |  | 75 |  | 6277 | moVS9Ou3GclDwNSW1OnS | Large Test File2 | Aspose.Tasks.Calendar | 1203 | 297 | 2022-04-04 | 2027-01-12 | 2021-10-21 | 2026-07-07 | Summary | InProgress | 588
FALSE |  | 83 |  | 6294 | Jtjxi70STISSeVqV8OJy | Large Test File2 | Aspose.Tasks.Calendar | 1514 | 262 | 2023-01-03 | 2028-12-12 | 2023-08-03 | 2026-01-13 | Summary | InProgress | 93
FALSE |  | 83 |  | 6290 | VuOK0YK760zOpXaJ9U7h | Large Test File2 | Aspose.Tasks.Calendar | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -34
FALSE |  | 83 |  | 4537 | FhESv2GOKRYErv6rS2Ko | Large Test File2 | Aspose.Tasks.Calendar | 923 | 158 | 2023-02-23 | 2026-10-21 | 2023-01-13 | 2025-01-24 | Summary | InProgress | -34
FALSE |  | 69 |  | 6270 | Wwp4MRWhcV55WleZhe1f | Large Test File2 | Aspose.Tasks.Calendar | 996 | 304 | 2023-02-23 | 2027-02-08 | 2023-01-13 | 2026-08-14 | Summary | InProgress | 574
FALSE |  | 17 |  | 5212 | ZlVhXj8OyAxr3mrFsaoQ | Large Test File2 | Aspose.Tasks.Calendar | 855 | 707 | 2023-03-06 | 2026-07-21 | 2023-03-06 | 2024-10-04 | Summary | InProgress | 30
FALSE |  | 67 |  | 6318 | cM5VCGnPiK1mfNJo8YLF | Large Test File2 | Aspose.Tasks.Calendar | 975 | 320 | 2023-03-06 | 2027-01-06 | 2023-03-06 | 2026-08-14 | Summary | InProgress | 597
FALSE |  | 66 |  | 870 | m3oEXpasu7ssfpw9dqLv | Large Test File2 | Aspose.Tasks.Calendar | 1460 | 498 | 2023-03-20 | 2028-12-11 | 2023-03-20 | 2025-06-27 | Summary | InProgress | 0
FALSE |  | 79 |  | 6293 | WhUcOZjaj9TDZe74ojmh | Large Test File2 | Aspose.Tasks.Calendar | 891 | 191 | 2023-08-04 | 2027-02-19 | 2023-07-28 | 2026-01-23 | Summary | InProgress | 565
FALSE |  | 76 |  | 5375 | zkXPpJkHw8DPAtspwcmA | Large Test File2 | Aspose.Tasks.Calendar | 800 | 190 | 2023-08-07 | 2026-10-09 | 2024-03-27 | 2024-04-16 | Summary | InProgress | 478
FALSE |  | 65 |  | 6291 | 7X6NK9qir9GRz5m7bXmK | Large Test File2 | Aspose.Tasks.Calendar | 881 | 310 | 2023-08-07 | 2027-02-08 | 2023-08-07 | 2026-07-27 | Summary | InProgress | 574
FALSE |  | 31 |  | 6273 | ljz6i2ltFwqcRU3btDx0 | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 829 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2026-09-01 | Summary | InProgress | 245
FALSE |  | 65 |  | 1639 | mkPE1mMWzawwUBF3KKzV | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 426 | 2023-08-07 | 2028-05-11 | 2023-08-07 | 2025-05-30 | Summary | InProgress | -436
FALSE |  | 0 |  | 6313 | 8HYxn50EKf1DU0fX0MF7 | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 245
FALSE |  | 0 |  | 5516 | dd6fm1lW4tBXPtNV5RGW | Large Test File2 | Aspose.Tasks.Calendar | 1210 | 1210 | 2023-08-07 | 2028-05-11 | 2025-03-20 | 2026-09-01 | Summary | Planned | 245
FALSE |  | 0 |  | 7382 | GJk3wpkfagyrb21gVciV | Large Test File2 | Aspose.Tasks.Calendar | 1339 | 1339 | 2023-08-07 | 2028-11-09 | 2025-02-07 | 2026-03-24 | Summary | Planned | 28
FALSE |  | 32 |  | 4129 | G6dPcJRrq5zqLYx4Vr0R | Large Test File2 | Aspose.Tasks.Calendar | 1363 | 928 | 2023-08-07 | 2028-12-12 | 2023-08-07 | 2025-06-13 | Summary | InProgress | 5
FALSE |  | 87 |  | 5753 | ZptYdARXANY2IOcoHhB1 | Large Test File2 | Aspose.Tasks.Calendar | 1128 | 148 | 2023-08-07 | 2028-01-19 | 2023-08-07 | 2024-02-01 | Summary | InProgress | -80
FALSE |  | 48 |  | 5537 | 9xVQhmyTVkChMoMOy91g | Large Test File2 | Aspose.Tasks.Calendar | 1214 | 637 | 2023-08-21 | 2028-06-01 | 2023-08-16 | 2024-06-11 | Summary | InProgress | 24
FALSE |  | 39 |  | 4134 | 86JmjjOtZxj7XQRp3CQF | Large Test File2 | Aspose.Tasks.Calendar | 1218 | 743 | 2023-09-05 | 2028-06-20 | 2025-06-30 | 2026-01-13 | Summary | InProgress | 218
FALSE |  | 56 |  | 4135 | 0voiyAtBe9AzaXfs8cVF | Large Test File2 | Aspose.Tasks.Calendar | 1169 | 514 | 2023-09-05 | 2028-04-12 | 2025-06-30 | 2025-09-10 | Summary | InProgress | 218
FALSE |  | 0 |  | 160 | gFTVv5U5XORyz5ZEYbdN | Large Test File2 | Aspose.Tasks.Calendar | 702 | 702 | 2023-10-18 | 2026-08-05 | 2023-10-31 | 2024-08-06 | Summary | InProgress | 20
FALSE |  | 26 |  | 179 | jSOjvYE1qiHOKdcV2ixu | Large Test File2 | Aspose.Tasks.Calendar | 808 | 597 | 2023-10-18 | 2027-01-08 | 2023-09-05 | 2025-03-28 | Summary | InProgress | 588
FALSE |  | 61 |  | 158 | D5C8AUNeoI4YKF3PggKx | Large Test File2 | Aspose.Tasks.Calendar | 1093 | 431 | 2024-03-04 | 2028-06-20 | 2023-12-13 | 2025-12-17 | Summary | InProgress | 218
FALSE |  | 5 |  | 4038 | VkrURyJwsSkEVRV6WcXe | Large Test File2 | Aspose.Tasks.Calendar | 483 | 462 | 2024-08-01 | 2026-07-08 | 2024-08-01 | 2025-04-16 | Summary | InProgress | 565
FALSE |  | 3 |  | 4037 | hMBnPD0NfYpjSqEpRMYY | Large Test File2 | Aspose.Tasks.Calendar | 639 | 621 | 2024-08-01 | 2027-02-19 | 2024-08-01 | 2026-01-23 | Summary | InProgress | 565
FALSE |  | 35 |  | 5570 | MuDwSgsBJjDxwFkSMWYJ | Large Test File2 | Aspose.Tasks.Calendar | 819 | 534 | 2024-11-18 | 2028-02-14 | 2024-02-05 | 2024-05-20 | Summary | InProgress | 45
FALSE |  | 0 |  | 5557 | U376LwOjKfNZoVLUlmMD | Large Test File2 | Aspose.Tasks.Calendar | 749 | 749 | 2025-04-02 | 2028-03-14 | 2024-01-05 | 2024-04-22 | Summary | Planned | 24
FALSE |  | 0 |  | 3907 | pFYLZycbgH4KMn6pLhBU | Large Test File2 | Aspose.Tasks.Calendar | 343 | 343 | 2025-04-10 | 2026-08-24 | 2025-06-27 | 2026-01-23 | Summary | Planned | 7
FALSE |  | 0 |  | 5544 | cIc3ARzcdrbXv6maHllr | Large Test File2 | Aspose.Tasks.Calendar | 765 | 765 | 2025-04-15 | 2028-04-19 | 2023-12-06 | 2024-03-25 | Summary | Planned | 24
FALSE |  | 0 |  | 5583 | gkFBoXdv1oJb2jtBcO5M | Large Test File2 | Aspose.Tasks.Calendar | 790 | 790 | 2025-04-23 | 2028-06-01 | 2024-03-04 | 2024-06-11 | Summary | Planned | 24
FALSE |  | 0 |  | 5289 | tqKGxL2oceRufkd47wnf | Large Test File2 | Aspose.Tasks.Calendar | 345 | 345 | 2025-09-04 | 2027-01-06 | 2025-06-24 | 2026-08-14 | Summary | Planned | 80
FALSE |  | 0 |  | 5402 | zDUD70mdAG3rcozejCwk | Large Test File2 | Aspose.Tasks.Calendar | 279 | 279 | 2025-09-05 | 2026-10-19 | 2025-08-26 | 2025-09-16 | Summary | Planned | 478
FALSE |  | 0 |  | 195 | jWoM7YMyhsN7uWtVDNIl | Large Test File2 | Aspose.Tasks.Calendar | 872 | 872 | 2025-09-19 | 2029-02-14 | 2024-09-26 | 2026-01-30 | Summary | Planned | 8
FALSE |  | 0 |  | 6321 | KAyzIHlSkkFZqIIdJ9JD | Large Test File2 | Aspose.Tasks.Calendar | 120 | 120 | 2026-02-18 | 2026-08-05 | 2025-12-04 | 2026-05-01 | Summary | Planned | -36
FALSE |  | 0 |  | 3918 | VKkEEklTkhlAtqntT93x | Large Test File2 | Aspose.Tasks.Calendar | 160 | 160 | 2026-06-16 | 2027-02-08 | 2026-04-07 | 2026-07-27 | Summary | Planned | 574
FALSE |  | 0 |  | 5785 | xIbBdattr1YLWDiqGWPC | Large Test File2 | Aspose.Tasks.Calendar | 136 | 136 | 2026-06-24 | 2027-01-12 | 2026-01-07 | 2026-07-07 | Summary | Planned | 588
FALSE |  | 0 |  | 7264 | vNqQNKJIEgg8BiBzdWeI | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-02 | 2026-09-23 | 2025-04-04 | 2025-06-25 | Summary | Planned | 490
FALSE |  | 0 |  | 4043 | XbXkjxtfHUxhg4CK1elt | Large Test File2 | Aspose.Tasks.Calendar | 145 | 145 | 2026-07-08 | 2027-02-04 | 2025-06-26 | 2025-11-11 | Summary | Planned | 565
FALSE |  | 0 |  | 5313 | 3y8KKUl940HiJi7UFKFT | Large Test File2 | Aspose.Tasks.Calendar | 110 | 110 | 2026-08-05 | 2027-01-06 | 2026-05-01 | 2026-08-14 | Summary | Planned | 597
FALSE |  | 0 |  | 4050 | jQIHIDf5FTnJxQysEvnn | Large Test File2 | Aspose.Tasks.Calendar | 40 | 40 | 2026-12-23 | 2027-02-19 | 2025-10-08 | 2026-01-23 | Summary | Planned | 565
FALSE |  | 0 |  | 4051 | bizigDTezGi1mMHxJ1gi | Large Test File2 | Aspose.Tasks.Calendar | 32 | 32 | 2026-12-23 | 2027-02-09 | 2025-10-08 | 2025-12-17 | Summary | Planned | 568
Longest Path (Tasks & Milestones)
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 37 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 52 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36
Longest Path (Normal Tasks)
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 37 |  | 5539 | kRsO3PSMDsMxji3dmdNc | Large Test File2 | Aspose.Tasks.Calendar | 998 | 628 | 2023-08-23 | 2027-09-02 | 2023-08-23 | 2023-10-23 | Normal | InProgress | -436
FALSE |  | 52 |  | 6997 | MBGoTUikAECGvIHYk1uV | Large Test File2 | Aspose.Tasks.Calendar | 48 | 23 | 2024-11-01 | 2027-10-12 | 2024-04-26 | 2024-06-11 | Normal | InProgress | 0
FALSE |  | 0 |  | 5308 | JBAsTSNPb9OQmIAmtadV | Large Test File2 | Aspose.Tasks.Calendar | 29 | 29 | 2026-05-25 | 2026-07-07 | 2026-03-05 | 2026-04-02 | Normal | Planned | -36
FALSE |  | 0 |  | 6522 | WYJvDx3FrKALT2lj4FIo | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-07 | 2026-07-09 | 2026-04-02 | 2026-04-06 | Normal | Planned | -36
FALSE |  | 0 |  | 5309 | xRRT514kq8kwyv7njrs5 | Large Test File2 | Aspose.Tasks.Calendar | 5 | 5 | 2026-07-09 | 2026-07-16 | 2026-04-06 | 2026-04-13 | Normal | Planned | -36
FALSE |  | 0 |  | 6523 | TvM5XBX3OaVljTSOZ4e2 | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-16 | 2026-07-20 | 2026-04-13 | 2026-04-15 | Normal | Planned | -36
FALSE |  | 0 |  | 5311 | BowxNbb4uXSnAk8z8ZkC | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-20 | 2026-07-22 | 2026-04-15 | 2026-04-17 | Normal | Planned | -36
FALSE |  | 0 |  | 6524 | cvaJgvK8KpGYV8ykH12h | Large Test File2 | Aspose.Tasks.Calendar | 2 | 2 | 2026-07-22 | 2026-07-24 | 2026-04-17 | 2026-04-21 | Normal | Planned | -36
FALSE |  | 0 |  | 6880 | ZuauWvCPNW7n2NMscMO2 | Large Test File2 | Aspose.Tasks.Calendar | 4 | 4 | 2026-07-24 | 2026-07-30 | 2025-12-05 | 2025-12-11 | Normal | Planned | -34
FALSE |  | 0 |  | 5855 | ufnWeMCBRu1ZyXfLmzt1 | Large Test File2 | Aspose.Tasks.Calendar | 57 | 57 | 2026-07-30 | 2026-10-21 | 2024-12-26 | 2025-01-24 | Normal | Planned | -34
FALSE |  | 0 |  | 6525 | GtEwLNkefPtnncnl90X4 | Large Test File2 | Aspose.Tasks.Calendar | 3 | 3 | 2026-07-30 | 2026-08-04 | 2026-04-27 | 2026-04-30 | Normal | Planned | -36

## Phase Analysis
Fuse® Analyst Report
Workbook: Large Test File vs Large Test File2 - 4249 Activities
Quick Add Metrics
Created on: 7/15/2026
Created by: dpolitte
Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
|  | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Phase Analyzer | Status Date | 2025-02-07 | 2025-02-07 | 2025-02-07 | 2025-02-07 | 2025-02-07 | 2025-02-07
Phase Analyzer | WBS | 1 | 1 | 1 | 1 | 1 | 1
Phase Analyzer | New Activity - Created (Snapshot) | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | New Activity - Already Finished (Snapshot) - check/compare | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | New Activity - Finished in Status Period (Snapshot) - check/compare | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Specific Task Start | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Specific Task Finish | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Score | 100 | 100 | 100 | 100 | 100 | 100
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
|  | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Phase Analyzer | Status Date
Phase Analyzer | WBS
Phase Analyzer | New Activity - Created (Snapshot)
Phase Analyzer | New Activity - Already Finished (Snapshot) - check/compare
Phase Analyzer | New Activity - Finished in Status Period (Snapshot) - check/compare
Phase Analyzer | Specific Task Start
Phase Analyzer | Specific Task Finish
Phase Analyzer | Score