## Program-Summary
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program Summary
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
NASA_Quick Library
|  | Quick Add Metrics | Schedule Errors | Schedule Warnings | Critical Path | BEI - Incomplete Activities Analysis | Control Milestone Dates | Margin Date | Margin Duration | Status - Characteristics (GRAPH 1) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - BEI vs CP% (GRAPH 7)
Ribbons | Project2 | 100 | 97 | 62 | 0 | 100 | 100 | 100 | 100 | 100 | 90 | 72 | 0 | 100 | 100 | 100
Ribbons | Project5_TAMPERED | 100 | 96 | 69 | 24 | 100 | 100 | 100 | 100 | 100 | 86 | 67 | 0 | 100 | 100 | 100
NASA Metrics
|  | Status & Quality | Performance | Schedule Errors | Schedule Warnings | Critical Path
Ribbons | Project2 | 59 | 67.1071 | 97 | 62 | 0
Ribbons | Project5_TAMPERED | 59.5714 | 66.1429 | 96 | 69 | 24
Advanced
Baseline Compliance
Ribbons | Project2 | 6
Ribbons | Project5_TAMPERED | 6
Industry Standards
|  | Schedule Execution Metrics (SEM) | Half Step Delay Analysis
Ribbons | Project2 | 71 | 0
Ribbons | Project5_TAMPERED | 60 | 0

## Program-Summary-2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program Summary 2
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
|  | NASA_Quick Library | [14 empty] | NASA Metrics |  |  | Status & Quality | [7 empty] | Performance | [26 empty] | Baseline Execution Index (BEI) |  | Hit or Miss Index (HMI) |  | Current Execution Index (CEI) |  | Advanced | [20 empty] | Industry Standards
|  | Quick Add Metrics | Schedule Errors | Schedule Warnings | Critical Path | BEI - Incomplete Activities Analysis | Control Milestone Dates | Margin Date | Margin Duration | Status - Characteristics (GRAPH 1) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - BEI vs CP% (GRAPH 7) | Schedule Errors | Schedule Warnings | Critical Path | Status - Characteristics | Status - New Activities (Snapshot) | Quality - Construction | Quality - Duration | Quality - Constraints | Quality - Logic | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Successors | Performance - Completed | Performance - In-Progress | Performance - Planned/Future | Performance - Baseline Compliance | Performance - Float | Performance - Critical Path | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline_Additional Metrics | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Incomplete - Old & New | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Values Adjusted | DRM | Tracking Dates | Margin Duration | Margin Date | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | BEI, HMI, CEI - Values | BEI, HMI, CEI - Critical Path | BEI - Tasks | BEI - Milestones | HMI - Tasks | HMI - Milestones | CEI - Tasks | CEI - Milestones | Baseline Compliance | [20 empty] | Schedule Execution Metrics (SEM) | Half Step Delay Analysis
Ribbons | Project2 | 100 | 97 | 62 | 0 | 100 | 100 | 100 | 100 | 100 | 90 | 72 | 0 | 100 | 100 | 100 | 97 | 62 | 0 | 100 | N/A | 100 | 0 | 26 | 70 | 28 | 89 | 0 | 0 | 0 | 96 | 69 | 0 | 90 | 90 | 90 | 72 | 0 | 0 | 100 | 100 | 0 | 0 | 100 | 100 | 100 | N/A | 100 | 100 | 100 | 100 | 72 | N/A | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 6 | [20 empty] | 71 | 0
Ribbons | Project5_TAMPERED | 100 | 96 | 69 | 24 | 100 | 100 | 100 | 100 | 100 | 86 | 67 | 0 | 100 | 100 | 100 | 96 | 69 | 24 | 100 | N/A | 100 | 0 | 31 | 65 | 33 | 88 | 0 | 0 | 0 | 91 | 69 | 0 | 86 | 86 | 86 | 67 | 0 | 0 | 100 | 100 | 0 | 0 | 100 | 100 | 100 | N/A | 100 | 100 | 100 | 100 | 67 | N/A | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 6 | [20 empty] | 60 | 0
|  | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7) | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - New Activities (Snapshot) | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | DRM | DRM | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis
|  | Status Date | Specific Task Start | Specific Task Finish | Wrong Status - Actual Starts | Wrong Status - Actual Finishes | Invalid Forecast Dates | Expected Finish But Still In-Progress | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | High Float 44d | Zero Days Float | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Riding Data Date | Deadlines | High Float 10% | Negative Float | Tasks & Milestones (To Go) | Milestones (To-Go) | Normal Tasks (To-Go) | Normal Tasks (To-Go, In Progress) | Critical Path (Tasks & Milestones) | Critical Path (Milestones) | Critical Path (Normal Tasks) | Critical Path (Normal In Progress) | Critical Milestone-to-Task Ratio (To-Go) | Negative Float | Zero Days Float | Near-Critical (<10 Days Float) | CP Logic Density™ | Critical CEI - Value Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | Status Date | Milestone #1 - 100 | Float Milestone #1 - 100 | Milestone #2 - 101 | Float to Milestone #2 - 101 | Milestone #3 - 102 | Float to Milestone #3 - 102 | Milestone #4 - 103 | Float to Milestone #4 - 103 | Milestone #5 - 104 | Float to Milestone #5 - 104 | New Activities Since Previous Status Date | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Critical Milestones (To-Go) | Critical Normal Tasks (To-Go) | Riding Data Date | Baselined to Start | Scheduled to Start | Actual Starts | Baselined to Finish | Scheduled to Finish | Actual Finishes | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Current Baseline to Start & Started (BL Plan) | Future Baseline to Start & Started (Early Starts) | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Finish & Finished (BL Plan) | Future Baseline to Finish & Finished (Early Finishes) | Past Baseline to Finish & Finished (Workoff Burden) | Current Baseline to Finish & Not Finished (Incompletes) | Past Baseline to Start & Not Started (Workoff Burden) (SEM07) | Future Baseline to Start & Already Delayed (Workoff Burden) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Duration Ratio Metric (DRM) | DRM Graph | Baselined to Start | Scheduled to Start | Baselined to Finish | Scheduled to Finish | BEI - Value Activities | Tasks & Milestones (To-Go) - % of Total To-Go | Critical Path To-Go | Wrong Status | Invalid Forecast Dates | Expected Finish | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Riding Data Date | Deadlines | Longest Path (Normal Tasks) | Longest Path (Tasks & Milestones) | Critical Milestone-to-Task Ratio (To-Go) | Critical Milestones (To-Go) | Longest Path (Milestones) | Normal Tasks | Normal Tasks (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Zero Days Float | Negative Float | CP Logic Density™ | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Riding Data Date | Status Date | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Summary-to-Task Ratio (To-Go) | Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | Manual Tasks (To-Go) | Critical Tasks and Milestones (To-Go) | Wrong Status (To-Go) | Invalid Forecast Dates | Missing WBS (To-Go) | All Activities (To Go) | Tasks & Milestones (To-Go) - % of Total To-Go | Estimated Duration | Milestones with Duration>0 | Activities with Duration=0 | Avg. Original Duration | Avg. Remaining Duration | High Baseline Duration (44d) | High Planned Duration (44d) | Insufficient Detail™ | Critical Activities (To-Go) | Avg. Critical Original Duration | Avg. Critical Remaining Duration | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical w/Insufficient Detail™ | Activities (To-Go) | Total Constraints | Start No Earlier Than | Start No Later Than | Finish No Earlier Than | Finish No Later Than | Hard Constraints | Must Start On | Must Finish On | As Late As Possible | Deadlines | Mandatory Start | Mandatory Finish | Open Ends with Constraints | Open Ends w/o Constraints | Unsatisfied Constraints | No Constraints | No Constraints | Logic Density™ | Logic Density™ - Predecessors | Logic Density™ - Successors | Summary Links | All Activities w/Predecessors | SS Predecessors | SF Predecessors | FF Predecessors | FS Predecessors | All Activities w/Successors | SS Successors | FF Successors | SF Successors | FS Successors | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Logic Density™ - Predecessors | All Activities w/Predecessors | Total # Predecessors | Activities Missing Predecessors | Activities w/Leads on Predecessor | Total # Predecessor Leads | Max # Predecessor Leads on an Activity | Activities w/Lags on Predecessor | Total # Predecessor Lags | Max # of Predecessor Lags on an Activity | Min Predecessor Lag (days) | Max Predecessor Lag (days) | Hidden Duration (Planned) | Critical w/Hidden Duration (Planned) | Merge Hotspot (Predecessors >2) | Merge Hotspot w/Predecessor Lags | Merge Hotspot w/Predecessor Lags & Low Total Float | Critical Merge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Logic Density™ - Successors | All Activities w/Successors | Activities Missing Successors | Total # Successors | Activities w/Leads on Successor | Total# of Successor Leads | Max # of Successor Leads on Activity | Activities w/Lags on Successor | Total# of Successor Lags | Max # of Successor Lags on Activity | Diverge Hotspot (Successors >2) | Diverge Hotspot w/Successor Lags | Diverge Hotspot w/Successor Lags & Low Total Float | Critical Diverge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Actually Finished - Tasks & Milestones | Completed Ahead - Tasks & Milestones | Completed On-Schedule - Tasks & Milestones | Completed Delayed - Tasks & Milestones | Avg Days Finished Early - Tasks & Milestones | Avg Days Finished Late - Tasks & Milestones | Avg Finish Variance - Tasks & Milestones | Actually Finished - Tasks | Completed Ahead - Tasks | Completed On-Schedule - Tasks | Completed Delayed - Tasks | Accelerated Durations Early/On-Schedule - Tasks | Accelerated Durations Late - Tasks | Extended Durations - Tasks | Actually Finished - Milestones | Completed Ahead - Milestones | Completed On-Schedule - Milestones | Completed Delayed - Milestones | Actually Started - Tasks | In-Progress Started Ahead - Tasks | In-Progress Started On-Schedule - Tasks | In-Progress Started Delayed - Tasks | In-Progress Delayed Finish - Tasks | Avg Days Started Early | Avg Days Started Late | Avg Start Variance | Expected Finish | In-Progress Schedule Overrun - Tasks & Milestones | Scheduled to Start - Tasks & Milestones | Planned Ahead Start - Tasks & Milestones | Planned On Schedule Start - Tasks & Milestones | Planned Delayed Start - Tasks & Milestones | Riding Data Date - Tasks & Milestones | Planned Schedule Overrun - Tasks & Milestones | Scheduled to Start - Tasks | Planned Ahead Start - Tasks | Planned On Schedule Start - Tasks | Planned Delayed Start - Tasks | Planned Delayed Finish - Tasks | Scheduled to Start - Milestones | Planned Ahead Start - Milestones | Planned On Schedule Start - Milestones | Planned Delayed Start - Milestones | Planned Delayed Finish - Milestones | Schedule Baseline Activities | Scheduled/Baselined to Start | Scheduled/Baselined to Finish | Start/ed | Finish/ed | Start Variance (Phase) | Start Compliance™ (Phase) | Finish Variance (Phase) | Finish Compliance™ (Phase) | Started Delayed (>30 days) | Completed Delayed (>30 days) | SPI(t) | Scheduled Activities | Scheduled to Start | Scheduled to Finish | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Critical Milestone-to-Task Ratio (To-Go) | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | Logic Density™ | CP Logic Density™ | Critical w/Missing Logic | Critical w/Hard Constraints | Zero Days Float | Negative Float | Critical LOE | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical with Predecessor Lag | Critical with Successor Lag | Critical with Hard Constraints | Negative Float with Predecessor Lag | Negative Float with Successor Lag | Critical CEI - Value Tasks | Critical CEI - Total Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Baselined to Start | Scheduled to Start | Actual Starts | Baselined to Finish | Scheduled to Finish | Actual Finishes | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Baselined to Start | Scheduled to Start | Actual Starts | Current Baselined to Start & Started | Past Baselined to Start & Started | Future Baseline to Start & Started | Baselined to Finish | Scheduled to Finish | Actual Finishes | Current Baselined to Finish & Finished | Past Baselined to Finish & Finished | Future Baselined to Finish & Finished | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Baselined to Start - To Time Now | Scheduled to Start - To Time Now | Started | Started Late | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | BEI - Value Task Starts | Baselined to Finish - To Time Now | Scheduled to Finish - To Time Now | Finished | Finished Late | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | BEI - Value Task Finishes | Started - Future | Not Baselined to Start | BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Started | Current Baseline to Start & Started Past (Early Starts) | Current Baseline to Start & Started Future (Late Starts) | Current Baseline to Start & Not Started (Incomplete) | Baselined to Start - Check | Future Baseline to Start & Started (Early Starts) | Past Baseline to Finish & Finished - Check | Current Baseline to Finish & Finished - Check | Current Baseline to Finish & Finished Past - Check | Current Baseline to Finish & Finished Future - Check | Current Baseline to Finish & Not Finished - Check | Baselined to Finish - Check | Future Baseline to Finish & Finished - Check | Workoff Burden (Snapshot_Phase) (SEM01) | Workoff Burden - Starts To-Go (Total) (SEM07) | Past Baseline to Start & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Start & AlreadyDelayed (Workoff Burden) (SEM07) | Workoff Burden - Finishes To-Go (Total) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Current Baseline to Start & Started (BL Plan) | Future Baseline to Start & Started (Early Starts) | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Finish & Finished (BL Plan) | Future Baseline to Finish & Finished (Early Finishes) | Past Baseline to Finish & Finished (Workoff Burden) | Current Baseline to Finish & Not Finished (Incompletes) | Past Baseline to Start & Not Started (Workoff Burden) (SEM07) | Future Baseline to Start & Already Delayed (Workoff Burden) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Baselined to Start | Scheduled to Start | Started - Scheduled | Started - Baseline Comparison | BEI - Value Task Starts | HMI - Value Task Starts | CEI - Value Task Starts | Baselined to Finish | Scheduled to Finish | Finished | BEI - Value Task Finishes | HMI - Value Task Finishes | CEI - Value Task Finishes | Status Date | Started (incl. Future Baseline Starts) - Scheduled | Started (incl. Future Baseline Starts) - Baseline Comparison | Started Late (from Baseline) | Finished (incl. Future Baseline Finishes) - Scheduled | Finished (incl. Future Baseline Finishes) - Baseline Comparison | Finished Late | Completed Ahead | Completed Delayed | Completed On-Schedule | Accelerated | Days Variance | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Variance | Actually Finished | Took Longer than Planned | Took Less Than Planned | Completed (w/Baseline Duration) | Completed (w/o Baseline Duration) | Completed (w/Baseline Dur=0) | Baseline-to-Date Completed Tasks | Missed Durations | Missed Durations & Late Actual Finish | Completed Ahead | Completed Delayed | Completed On-Schedule | Accelerated | Days Variance | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Variance | Actually Finished | Took Longer than Planned | Took Less Than Planned | Completed (w/Baseline Duration) | Completed (w/o Baseline Duration) | Completed (w/Baseline Dur=0) | Baseline-to-Date Completed Tasks | Missed Durations | Missed Durations & Late Actual Finish | Baselined Tasks | Baselined to Start - TOTAL | Complete Task Starts - Cumulative | Incomplete Task Starts - Cumulative (in work) | Old Incomplete Task Starts in Status Period | Baselined to Finish | Complete Task Finishes - Cumulative (in work) | Incomplete Task Finishes - Cumulative | Old Incomplete Task Finishes in Status Period | Old Completed Task Finishes in Status Period | BEI - Value Tasks | BEI - Total Tasks | BEI - Incomplete Tasks | HMI - Value Tasks | HMI - Total Tasks | HMI - Incomplete Tasks | CEI - Value Tasks | CEI - Total Tasks | CEI - Incomplete Tasks | BEI - Complete Milestones | HMI - Complete Tasks | CEI - Complete Tasks | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Incomplete Milestones | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | BEI - Value Tasks (adjusted) | HMI - Value Tasks (adjusted) | CEI - Value Tasks (adjusted) | BEI - Value Milestones (adjusted) | HMI - Value Milestones (adjusted) | CEI - Value Milestones (adjusted) | Status Date | Total Activities - DRM | Total Activities - DRM Graph | Status Date | Milestone #1 - 5158 | Float Milestone #1 - 5158 | Milestone #2 - 4786 | Float to Milestone #2 - 4786 | Milestone #3 - 102 | Float to Milestone #3 - 102 | Milestone #4 - 103 | Float to Milestone #4 - 103 | Milestone #5 - 104 | Float to Milestone #5 - 105 | New Activities Since Previous Status Date | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | BEI - Value Tasks | HMI - Value Tasks | CEI - Value Tasks | BEI - Value Milestones | HMI - Value Milestones | CEI - Value Milestones | BEI - Value Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - CP Tasks - Planned Cumulative | BEI - CP Value Tasks | HMI - Value Tasks | HMI - Complete Tasks | HMI - Incomplete Tasks | HMI - CP Tasks - Planned to be Completed this Month | HMI - CP Value Tasks | CEI - Value Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - CP Tasks - Planned to be Completed this Month | CEI - CP Value Tasks | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | Time Now | Forecast to be Finished | Completed On Time | Completed Late | Not Completed | Baseline Finish Compliance | Forecast to be Started | Started On Time | Started Late | Not Started | Baseline Start Compliance | Completed Activities (1) | Workoff Burden (SEM01) | BRI Current (SEM02) | BRI Cumulative (SEM03) | BPI Current (SEM04) | BEI Current (SEM05) | BEI Cumulative (SEM06) | TC-BEI (SEM07) | FRI Current (SEM08) | Delta (BEI vs TC-BEI) (SEM09) | Time Now (HSD01) | Label (HSD02) | Forecast to be Started but not Started yet (HSD03) | Started Late (HSD04) | Forecast to be Finished but not Finished yet (HSD05) | Finished Late (HSD06) | Total days delay in the half step (Days) (HSD06) | Total days delay in the full update (Days) (HSD07) | Total days ahead in the half step (Days) (HSD08) | Total days ahead in the full update (Days) (HSD09) | Cumulative Finish Impact (Days) (HSD10) | Net Finish Impact (Days) (HSD10) | Project Finish (HSD20)
|  | 2026-08-27 | 2027-09-24 | 2027-10-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 44 | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 99 | 0 | 99 | 2 | 4 | 0 | 4 | 0 | N/A | 0 | 4 | 5 | 3 | N/A | N/A | N/A | 1 | 34 | 0.59 | 46 | 27 | 19 | 2026-08-27 | 2027-09-24 | 19 | 2027-07-16 | 36 | 2027-08-20 | 35 | 2027-09-23 | 35 | 2027-09-24 | 55 | 0 | 2026-08-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 144 | 0 | 126 | 18 | 0 | 0 | 126 | 27 | 0 | 27 | 113 | 99 | 0 | 99 | 14 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 0 | 126 | 126 | 29 | 126 | 126 | 27 | 8 | 4 | 6 | 7 | 6 | 5 | 0.6 | 0.59 | 0 | 0.05 | 0.4 | 0.44 | 1.24 | 1.24 | 1.24 | 1.24 | 97 | 99 | 97 | 1.24 | 29 | N/A | 0 | 97 | 27 | 0 | 0 | 99 | 19 | 78 | 19 | 80 | 27 | 27 | 99 | 99 | 99 | 99 | 0.59 | 99 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 41 | 44 | 4 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | N/A | 0 | 0 | 126 | 99 | 4 | 0 | 4 | 0 | 3 | 1 | 34 | 2026-08-27 | 144 | 0 | 126 | 18 | 0 | 0 | 126 | 27 | 0 | 27 | 113 | 99 | 0 | 99 | 14 | 0 | 0 | 4 | 4 | 0 | 0 | 2026-08-27 | 113 | 99 | 1:07 | N/A | N/A | 0 | 4 | 0 | 0 | 0 | 99 | 99 | 0 | 0 | 0 | 10 | 9 | 0 | 0 | 0 | 4 | 8 | 8 | 0 | 0 | 0 | 99 | 3 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 5 | 0 | 96 | 96 | 2.86 | 1.48 | 1.37 | 0 | 97 | 0 | 0 | 0 | 99 | 94 | 0 | 0 | 0 | 94 | 5 | 0 | 5 | 0 | 0 | 1.49 | 97 | 145 | 0 | 0 | N/A | N/A | 1 | 1 | 1 | 0 | 5 | 1 | 0 | 10 | 0 | N/A | 1 | 1 | 0 | 1.37 | 94 | 5 | 136 | 0 | N/A | N/A | 1 | 1 | 1 | 11 | 0 | N/A | 0 | 1 | 0 | 27 | 0 | 9 | 18 | 0 | 39 | 26 | 27 | 0 | 9 | 18 | 0 | 2 | 7 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 2 | 0 | 85 | 85 | 0 | 0 | 97 | 0 | 0 | 97 | 0 | 0 | 97 | 0 | 0 | 97 | 97 | 0 | 0 | 0 | 0 | 0 | 126 | 99 | 99 | 29 | 27 | 0 | 100% | 0 | 100% | 10 | 11 | 0.91 | 126 | 99 | 99 | 4 | 0 | 4 | 0 | N/A | 41 | 44 | 4 | 0 | 4 | 0 | 4 | 0 | N/A | N/A | 2.81 | 3 | 1 | 1 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | N/A | 0 | N/A | N/A | 1 | 34 | 126 | 126 | 29 | 126 | 126 | 27 | 8 | 4 | 6 | 7 | 6 | 5 | 126 | 126 | 29 | 29 | 0 | 0 | 126 | 126 | 27 | 27 | 0 | 0 | 8 | 4 | 6 | 7 | 6 | 5 | 48 | 48 | 29 | 18 | 8 | 4 | 6 | 0.6 | 46 | 46 | 27 | 18 | 7 | 6 | 5 | 0.59 | 0 | 0 | 0.6 | 0.59 | 0 | 0.05 | 0.4 | 0.44 | 1.24 | 1.24 | 1.24 | 1.24 | 97 | 99 | 97 | 1.24 | 0 | 29 | 0 | 0 | 97 | 126 | N/A | 0 | 27 | 0 | 0 | 99 | 126 | 0 | 6 | 97 | 19 | 78 | 99 | 19 | 80 | 29 | N/A | 0 | 97 | 27 | 0 | 0 | 99 | 19 | 78 | 19 | 80 | 48 | 48 | 29 | 29 | 0.6 | 0 | 0.46 | 46 | 46 | 27 | 0.59 | 0.05 | 0.44 | 2026-08-27 | 29 | 29 | 18 | 27 | 27 | 18 | 0 | 18 | 9 | 0 | 705 | 0 | 705 | 0 | 39 | 26 | 27 | 7 | 6 | 27 | 0 | 0 | 27 | 7 | 7 | 0 | 18 | 9 | 0 | 705 | 0 | 705 | 0 | 39 | 26 | 27 | 7 | 6 | 27 | 0 | 0 | 27 | 7 | 7 | 126 | 126 | 29 | 19 | N/A | 126 | 27 | 19 | N/A | N/A | 0.59 | 46 | 19 | 0.05 | 19 | 18 | 0.44 | 16 | 9 | N/A | 1 | 7 | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | 0.59 | 0.05 | 0.44 | N/A | N/A | N/A | 2026-08-27 | 27 | 27 | 2026-08-27 | N/A | N/A | N/A | N/A | 2027-08-20 | 35 | 2027-09-09 | 35 | 2027-10-22 | 35 | 0 | 2026-08-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0.6 | 0.59 | 0 | 0.05 | 0.4 | 0.44 | 1.24 | 1.24 | 1.24 | 1.24 | 97 | 99 | 97 | 1.24 | 0.59 | 0.05 | 0.44 | N/A | N/A | N/A | 0.59 | 27 | 19 | 14 | 0 | 0.05 | 1 | 18 | 10 | 0 | 0.44 | 7 | 9 | 9 | 0.44 | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0.05 | 19 | 1 | N/A | 18 | 0.05 | 1 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 0.44 | 16 | 7 | 9 | 0.44 | 7 | 0 | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 2026-08-27 | 46 | 9 | 18 | 19 | 20% | 48 | 11 | 18 | 19 | 25% | 27 | 2 | 0 | 0.59 | 0 | 0.67 | 0.59 | 1.24 | 0 | -0.61 | 2026-08-27 | N/A | 19 | 18 | 19 | 18 | N/A | 9646 | N/A | 0 | -9646 | -134 | 2028-01-26
[5 empty] | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  | 44% | 4% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 41% | 0% | 79% | 0% | 100% | 2% | 4% | 0% | 100% | 0% |  | 0% | 4% | 5% |  |  | 44% | 56% | 25% | 24% |  |  | 59% | 41% | [21 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 0% | 88% | 13% | 0% | 0% | 88% | 21% | ( N/A ) | 21% | 78% | 88% | 0% | 88% | 12% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 0% | [6 empty] | 44% | 22% | 33% | 39% | 33% | 28% | [33 empty] | 88% | 4% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  | 41% | 44% | 4% | 0% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 0 | ( N/A ) | 0% | 88% | 88% | 4% | 0% | 4% | 0% |  | 1% | 24% |  |  | 0% | 88% | 13% | 0% | 0% | 88% | 21% | ( N/A ) | 21% | 78% | 88% | 0% | 88% | 12% | 0% | 0% | 100% | 100% | 0% | 0% |  | 78% | 88% | 0.14 | 0 | 0 | 0% | 4% | 0% | 0% | 0% | 100% | 88% | 0% | ( N/A ) | 0% |  |  | 0% | 0% | 0% | 4% |  |  | 0% | 0% | 0% | 79% | 3% | 2% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 5% | 0% | 97% | 97% |  |  |  | 0% | 100% | 0% | 0% | 0% | 100% | 95% | 0% | 0% | 0% | 95% | 5% | 0% | 5% | 0% | 0% |  | 100% |  | 0% | 0% |  |  | 1% |  |  |  |  | 1% | 0% | 10% | 0% | ( N/A ) | 1% | 1% | 0% |  | 100% | 5% |  | 0% |  |  | 1% |  |  | 11% | 0% | ( N/A ) | 0% | 1% | 0% | 21% | 0% | 33% | 67% |  |  |  | 21% | 0% | 33% | 67% | 0% | 2% | 6% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | 2% | 0% | 0% | 100% | 100% |  |  |  | 0% | 0% | 77% | 0% | 0% | 100% | 0% | 0% | 77% | 0% | 0% | 100% | 100% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | 100% |  |  |  |  | 0% |  | 0% |  | 56% | 61% |  | 100% | 79% | 79% | 4% | ( N/A ) | 4% | 0% | 0 | 41% | 44% | 4% | 0% | 4% | ( N/A ) | 4% | 0% | 0 | 0 |  |  | 5% | 1% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  |  | 44% | 56% | 1% | 24% | [6 empty] | 44% | 22% | 33% | 39% | 33% | 28% | [12 empty] | 44% | 22% | 33% | 39% | 33% | 28% | 38% | 38% |  |  | 44% | 22% | 33% |  | 37% | 37% |  |  | 39% | 33% | 28% |  |  | 0% | [28 empty] | 86% | [19 empty] | 100% | 60% | 60% | [10 empty] | 23% | 23% | N/A | 21% | 21% |  | 0% | 67% | 33% | 0% | 2611% | 0% | 2611% |  |  |  | 21% | 26% | 22% | 21% | 0% | 0% | 59% | 26% | 26% | 0% | 67% | 33% | 0% | 2611% | 0% | 2611% |  |  |  | 21% | 26% | 22% | 21% | 0% | 0% | 59% | 26% | 26% |  |  | 60% | 40% |  |  | 59% | 59% |  |  |  |  | 41% |  |  | 95% |  |  | 56% | N/A | 5% | 44% |  |  | N/A | N/A |  |  | N/A | N/A |  |  | N/A | N/A | [58 empty] | 59% | 41% |  |  |  | 5% | 95% |  |  |  | 44% | 56% |  |  |  |  | 59% | 41% |  | 59% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | 5% | 0% | 95% |  | 5% |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  | 44% | 56% |  | 44% |  |  |  |  | N/A | N/A |  | N/A |  |  |  | 37% | 20% | 39% | 41% |  | 38% | 23% | 38% | 40% |  |  | 100% | [10 empty] | 15% | 38% | 15% | 39%

## NASA_Quick-Library
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick Library
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
NASA_Quick Library
|  | Quick Add Metrics | Schedule Errors | Schedule Warnings | Critical Path | BEI - Incomplete Activities Analysis | Control Milestone Dates | Margin Date | Margin Duration | Status - Characteristics (GRAPH 1) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - BEI vs CP% (GRAPH 7)
Ribbons | Project2 | 100 | 97 | 62 | 0 | 100 | 100 | 100 | 100 | 100 | 90 | 72 | 0 | 100 | 100 | 100
Ribbons | Project5_TAMPERED | 100 | 96 | 69 | 24 | 100 | 100 | 100 | 100 | 100 | 86 | 67 | 0 | 100 | 100 | 100
|  | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics
|  | Status Date | Specific Task Start | Specific Task Finish | Score
Ribbons | Project2 | 2026-05-24 | 2027-06-17 | 2027-07-14 | 100
Ribbons
Ribbons | Project5_TAMPERED | 2026-08-27 | 2027-09-24 | 2027-10-21 | 100
Ribbons
|  | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors
|  | Wrong Status - Actual Starts | Wrong Status - Actual Finishes | Invalid Forecast Dates | Expected Finish But Still In-Progress | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | Score
Ribbons | Project2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-24 | 97
Ribbons |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Ribbons | Project5_TAMPERED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 96
Ribbons |  | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 1% | 0% | 0%
|  | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings
|  | High Float 44d | Zero Days Float | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Riding Data Date | Deadlines | High Float 10% | Negative Float | Score
Ribbons | Project2 | 44 | 41 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 39 | 0 | 62
Ribbons |  | 42% | 39% | 1% | 2% | 3% | 0% | 8% | 0% | 0% | 0% | 37% | 0%
Ribbons | Project5_TAMPERED | 44 | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 69
Ribbons |  | 44% | 4% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 41% | 0%
|  | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path
|  | Tasks & Milestones (To Go) | Milestones (To-Go) | Normal Tasks (To-Go) | Normal Tasks (To-Go, In Progress) | Critical Path (Tasks & Milestones) | Critical Path (Milestones) | Critical Path (Normal Tasks) | Critical Path (Normal In Progress) | Critical Milestone-to-Task Ratio (To-Go) | Negative Float | Zero Days Float | Near-Critical (<10 Days Float) | CP Logic Density™ | Critical CEI - Value Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Score
Ribbons | Project2 | 106 | 0 | 106 | 3 | 41 | 0 | 41 | 1 | N/A | 0 | 41 | 50 | 3.2 | N/A | N/A | N/A | 0 | 0 | 0
Ribbons |  | 84% | 0% | 100% | 3% | 39% | 0% | 100% | 2% |  | 0% | 39% | 47% |  |  | N/A | N/A | 0% | 0%
Ribbons | Project5_TAMPERED | 99 | 0 | 99 | 2 | 4 | 0 | 4 | 0 | N/A | 0 | 4 | 5 | 3 | N/A | N/A | N/A | 1 | 34 | 24
Ribbons |  | 79% | 0% | 100% | 2% | 4% | 0% | 100% | 0% |  | 0% | 4% | 5% |  |  | 44% | 56% | 25% | 24%
|  | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis
|  | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | Score
Ribbons | Project2 | 0.74 | 27 | 20 | 7 | 100
Ribbons |  |  |  | 74% | 26%
Ribbons | Project5_TAMPERED | 0.59 | 46 | 27 | 19 | 100
Ribbons |  |  |  | 59% | 41%
|  | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates
|  | Status Date | Milestone #1 - 100 | Float Milestone #1 - 100 | Milestone #2 - 101 | Float to Milestone #2 - 101 | Milestone #3 - 102 | Float to Milestone #3 - 102 | Milestone #4 - 103 | Float to Milestone #4 - 103 | Milestone #5 - 104 | Float to Milestone #5 - 104 | New Activities Since Previous Status Date | Score
Ribbons | Project2 | 2026-05-24 | 2027-06-17 | 0 | 2027-04-08 | 15 | 2027-05-13 | 10 | 2027-06-16 | 10 | 2027-06-17 | 30 | 0 | 100
Ribbons
Ribbons | Project5_TAMPERED | 2026-08-27 | 2027-09-24 | 19 | 2027-07-16 | 36 | 2027-08-20 | 35 | 2027-09-23 | 35 | 2027-09-24 | 55 | 0 | 100
Ribbons
|  | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date
|  | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
Ribbons | Project2 | 2026-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons
Ribbons | Project5_TAMPERED | 2026-08-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons
|  | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration
|  | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
Ribbons | Project2 | 2026-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Ribbons | Project5_TAMPERED | 2026-08-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1)
|  | Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Critical Milestones (To-Go) | Critical Normal Tasks (To-Go) | Riding Data Date | Score
Ribbons | Project2 | 2026-05-24 | 144 | 0 | 126 | 18 | 0 | 0 | 126 | 20 | 0 | 20 | 122 | 106 | 0 | 106 | 16 | 0 | 0 | 41 | 41 | 0 | 0 | 41 | 0 | 100
Ribbons |  |  |  | 0% | 88% | 13% | 0% | 0% | 88% | 16% | ( N/A ) | 16% | 85% | 87% | 0% | 87% | 13% | 0% | 0% | 87% | 87% | 0% | 0% | 100% | 0%
Ribbons | Project5_TAMPERED | 2026-08-27 | 144 | 0 | 126 | 18 | 0 | 0 | 126 | 27 | 0 | 27 | 113 | 99 | 0 | 99 | 14 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 0 | 100
Ribbons |  |  |  | 0% | 88% | 13% | 0% | 0% | 88% | 21% | ( N/A ) | 21% | 78% | 88% | 0% | 88% | 12% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 0%
|  | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project)
|  | Baselined to Start | Scheduled to Start | Actual Starts | Baselined to Finish | Scheduled to Finish | Actual Finishes | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Score
Ribbons | Project2 | 126 | 126 | 23 | 126 | 126 | 20 | 8 | 4 | 0 | 6 | 5 | 0 | 90
Ribbons | [7 empty] | 67% | 33% | 0% | 55% | 45% | 0%
Ribbons | Project5_TAMPERED | 126 | 126 | 29 | 126 | 126 | 27 | 8 | 4 | 6 | 7 | 6 | 5 | 86
Ribbons | [7 empty] | 44% | 22% | 33% | 39% | 33% | 28%
|  | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon)
|  | BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Score
Ribbons | Project2 | 0.79 | 0.74 | N/A | N/A | N/A | N/A | 1.06 | 1.07 | 1.06 | 1.07 | 103 | 106 | 103 | 1.06 | 72
Ribbons
Ribbons | Project5_TAMPERED | 0.6 | 0.59 | 0 | 0.05 | 0.4 | 0.44 | 1.24 | 1.24 | 1.24 | 1.24 | 97 | 99 | 97 | 1.24 | 67
Ribbons
|  | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4)
|  | Current Baseline to Start & Started (BL Plan) | Future Baseline to Start & Started (Early Starts) | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Finish & Finished (BL Plan) | Future Baseline to Finish & Finished (Early Finishes) | Past Baseline to Finish & Finished (Workoff Burden) | Current Baseline to Finish & Not Finished (Incompletes) | Past Baseline to Start & Not Started (Workoff Burden) (SEM07) | Future Baseline to Start & Already Delayed (Workoff Burden) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Score
Ribbons | Project2 | 23 | N/A | 0 | 103 | 20 | 0 | 0 | 106 | 6 | 97 | 7 | 99 | 0
Ribbons
Ribbons | Project5_TAMPERED | 29 | N/A | 0 | 97 | 27 | 0 | 0 | 99 | 19 | 78 | 19 | 80 | 0
Ribbons
|  | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Duration Ratio (GRAPH 5, Project)
|  | Duration Ratio Metric (DRM) | DRM Graph | Score
Ribbons | Project2 | 20 | 20 | 100
Ribbons
Ribbons | Project5_TAMPERED | 27 | 27 | 100
Ribbons
|  | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6)
|  | Baselined to Start | Scheduled to Start | Baselined to Finish | Scheduled to Finish | Score
Ribbons | Project2 | 106 | 106 | 106 | 106 | 100
Ribbons
Ribbons | Project5_TAMPERED | 99 | 99 | 99 | 99 | 100
Ribbons
|  | Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7)
|  | BEI - Value Activities | Tasks & Milestones (To-Go) - % of Total To-Go | Critical Path To-Go | Score
Ribbons | Project2 | 0.74 | 106 | 41 | 100
Ribbons |  |  | 87% | 39%
Ribbons | Project5_TAMPERED | 0.59 | 99 | 4 | 100
Ribbons |  |  | 88% | 4%

## NASA_Quick-Library-Quick-Add-M
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick-Library -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics
Status Date | Specific Task Start | Specific Task Finish | Score
2026-08-27 | 2027-09-24 | 2027-10-21 | 100
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Project Time Now Date) for the schedule.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Specific Task Start | Specific Task Start | 2027-09-24 |  | 2027-06-17
Provides the start date of a specific task.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Specific Task Finish | Specific Task Finish | 2027-10-21 |  | 2027-07-14
Provides the finish date of a specific task.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19

## NASA_Quick-Library-Schedule-Er
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick-Library -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors
Wrong Status - Actual Starts | Wrong Status - Actual Finishes | Invalid Forecast Dates | Expected Finish But Still In-Progress | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | Score
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 96
0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 1% | 0% | 0%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Wrong Status - Actual Starts | Wrong Status - Actual Starts | 0 | 0% | 0 | 0%
Number of activity starts that have been statused into the future.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Wrong Status - Actual Finishes | Wrong Status - Actual Finishes | 0 | 0% | 0 | 0%
Number of activity finishes that have been statused into the future.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Invalid Forecast Dates | Invalid Forecast Dates | 0 | 0% | 0 | 0%
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Expected Finish But Still In-Progress | Expected Finish But Still In-Progress | 0 | 0% | 0 | 0%
In-progress activities that are 100% complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missing WBS | Missing WBS | 0 | 0% | 0 | 0%
Number of activities that are missing WBS values.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestones with Duration>0 | Milestones with Duration>0 | 0 |  | 0
Milestones with a duration greater than 0 days.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Activities with Duration=0 | Activities with Duration=0 | 0 | 0% | 0 | 0%
Activities that have an original duration of 0 days.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Estimated Duration | Estimated Duration | 0 | 0% | 0 | 0%
Tasks with estimated duration in Microsoft Project.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missing Logic | Missing Logic | 5 | 5% | 4 | 4%
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Percent Complete | Total Float | Status
FALSE |  | FALSE | None | 1 | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | 0 | 184 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | 0 | 89 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 20 | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | 0 | 28 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | 0 | 38 | Planned
FALSE |  | TRUE | None | 2 | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | 0 | 0 | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missing Predecessors | Missing Predecessors | 0 | 0% | 0 | 0%
Number of activities that are missing a predecessor.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missing Successors | Missing Successors | 5 | 5% | 4 | 4%
Number of normal activities that are missing a successor.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | FALSE | None | 1 | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | FALSE | None | 1 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | FALSE | None | 1 | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 20 | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | FALSE | None | 1 | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | TRUE | None | 2 | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Open Start | Open Start | 0 | 0% | 0 | 0%
Activities where only the predecessor(s) are either Finish-to-Finish or Start-to-Finish resulting in an open start to the activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Open Finish | Open Finish | 0 | 0% | 0 | 0%
Activities where the only successors(s) are either Start-to-Finish or Start-to-Start resulting in an open finish to the activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Unsatisfied Constraints | Unsatisfied Constraints | 0 | 0% | 0 | 0%
Activities where the constraint date cannot be met
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Summary Links | Summary Links | 0 | 0% | 0 | 0%
Number of summary activities that have logic links.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Hard Constraints | Hard Constraints | 1 | 1% | 0 | 0%
Number of activities with hard or two-way constraints.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical w/Hidden Duration | Critical w/Hidden Duration | 0 | 0% | 0 | 0%
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of its original duration
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.

## NASA_Quick-Library-Schedule-Wa
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick-Library -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings
High Float 44d | Zero Days Float | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Riding Data Date | Deadlines | High Float 10% | Negative Float | Score
44 | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 69
44% | 4% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 41% | 0%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
High Float 44d | High Float 44d | 44 | 44% | 44 | 42%
Number of activities with total float greater than 2 months. This number should not exceed 10%.
Excluded | Critical | Project Remaining Duration | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | FALSE | 369 | 275 | 204 | 71 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93
FALSE | FALSE | 369 | 275 | 204 | 71 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0
FALSE | FALSE | 369 | 275 | 203 | 72 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0
FALSE | FALSE | 369 | 275 | 202 | 73 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0
FALSE | FALSE | 369 | 256 | 202 | 54 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0
FALSE | FALSE | 369 | 256 | 202 | 54 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0
FALSE | FALSE | 369 | 256 | 202 | 54 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0
FALSE | FALSE | 369 | 256 | 202 | 54 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0
FALSE | FALSE | 369 | 56 | 35 | 21 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0
FALSE | FALSE | 369 | 156 | 144 | 12 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0
FALSE | FALSE | 369 | 156 | 144 | 12 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0
FALSE | FALSE | 369 | 95 | 73 | 22 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE | FALSE | 369 | 100 | 78 | 22 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE | FALSE | 369 | 100 | 78 | 22 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE | FALSE | 369 | 95 | 73 | 22 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE | FALSE | 369 | 95 | 73 | 22 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE | FALSE | 369 | 184 | 144 | 40 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE | FALSE | 369 | 156 | 151 | 5 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0
FALSE | FALSE | 369 | 95 | 73 | 22 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE | FALSE | 369 | 95 | 73 | 22 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0
FALSE | FALSE | 369 | 94 | 73 | 21 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE | FALSE | 369 | 184 | 144 | 40 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0
FALSE | FALSE | 369 | 118 | 93 | 25 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 369 | 94 | 73 | 21 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 369 | 124 | 114 | 10 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 369 | 184 | 144 | 40 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0
FALSE | FALSE | 369 | 118 | 93 | 25 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0
FALSE | FALSE | 369 | 118 | 93 | 25 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0
FALSE | FALSE | 369 | 115 | 90 | 25 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0
FALSE | FALSE | 369 | 82 | 61 | 21 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0
FALSE | FALSE | 369 | 80 | 59 | 21 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0
FALSE | FALSE | 369 | 115 | 90 | 25 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0
FALSE | FALSE | 369 | 80 | 59 | 21 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE | FALSE | 369 | 80 | 59 | 21 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
FALSE | FALSE | 369 | 80 | 59 | 21 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0
FALSE | FALSE | 369 | 80 | 59 | 21 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0
FALSE | FALSE | 369 | 70 | 45 | 25 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0
FALSE | FALSE | 369 | 82 | 71 | 11 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE | FALSE | 369 | 51 | 30 | 21 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0
FALSE | FALSE | 369 | 70 | 45 | 25 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE | FALSE | 369 | 81 | 56 | 25 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0
FALSE | FALSE | 369 | 81 | 56 | 25 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0
FALSE | FALSE | 369 | 89 | 64 | 25 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 369 | 55 | 30 | 25 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Zero Days Float | Zero Days Float | 4 | 4% | 41 | 39%
Total number of activities with 0 days float. This number should not exceed 15%.
Excluded | Critical | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | TRUE | 0 | 17 | -17 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Hidden Duration (Planned) | Hidden Duration (Planned) | 1 | 1% | 1 | 1%
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of their original durations.
Excluded | Number of Predecessors | Number of Lags | Minimum Lag | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 1 | 5 | 5 | FALSE | 80 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Logic Hotspot™ | Critical Logic Hotspot™ | 0 | 0% | 1 | 2%
Number of critical activities with a high number of predecessors as well as a high number of successors (>2).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Merge Hotspot | Critical Merge Hotspot | 1 | 1% | 3 | 3%
The total number of activities with a high number of predecessor links (>2) that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 1 | 0 | 0 | 0 | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Merge Hotspot w/Predecessor Lags | Merge Hotspot w/Predecessor Lags | 0 | 0% | 0 | 0%
Number of activities with a high number of predecessor links and lags on the predecessor relationships.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Diverge Hotspot | Critical Diverge Hotspot | 0 | 0% | 8 | 8%
Number of activities with a high number of successor links (>2) that are also critical.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Diverge Hotspot w/Successor Lags | Diverge Hotspot w/Successor Lags | 0 | 0% | 0 | 0%
Number of activities with a high number of successor links and critical.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Riding Data Date | Riding Data Date | 0 | 0% | 0 | 0%
Number of planned activities that have a start date that is the same as the project data date (Time Now)
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Deadlines | Deadlines | 0 | 0% | 0 | 0%
A Deadline is entered as a target finish date for a task (activity), but it functions more like a monitoring tool than a constraint.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
High Float 10% | High Float 10% | 41 | 41% | 39 | 37%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.

## NASA_Quick-Library-Critical-Pa
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick-Library -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path
Tasks & Milestones (To Go) | Milestones (To-Go) | Normal Tasks (To-Go) | Normal Tasks (To-Go, In Progress) | Critical Path (Tasks & Milestones) | Critical Path (Milestones) | Critical Path (Normal Tasks) | Critical Path (Normal In Progress) | Critical Milestone-to-Task Ratio (To-Go) | Negative Float | Zero Days Float | Near-Critical (<10 Days Float) | CP Logic Density™ | Critical CEI - Value Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Score
99 | 0 | 99 | 2 | 4 | 0 | 4 | 0 | N/A | 0 | 4 | 5 | 3 | N/A | N/A | N/A | 1 | 34 | 24
79% | 0% | 100% | 2% | 4% | 0% | 100% | 0% |  | 0% | 4% | 5% |  |  | 44% | 56% | 25% | 24%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Tasks & Milestones (To Go) | Tasks & Milestones (To Go) | 99 | 79% | 106 | 84%
Remaining tasks and milestones in the schedule.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 275 | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress
FALSE |  | FALSE | 19 | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress
FALSE |  | FALSE | 275 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned
FALSE |  | FALSE | 275 | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned
FALSE |  | FALSE | 275 | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned
FALSE |  | FALSE | 256 | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned
FALSE |  | FALSE | 256 | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned
FALSE |  | FALSE | 256 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned
FALSE |  | FALSE | 256 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 56 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 156 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned
FALSE |  | FALSE | 156 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 95 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 100 | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 100 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 95 | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 95 | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 184 | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned
FALSE |  | FALSE | 156 | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 95 | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned
FALSE |  | FALSE | 30 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned
FALSE |  | FALSE | 95 | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | FALSE | 94 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 184 | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned
FALSE |  | FALSE | 118 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 94 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 124 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 184 | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned
FALSE |  | FALSE | 118 | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned
FALSE |  | FALSE | 118 | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned
FALSE |  | FALSE | 82 | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned
FALSE |  | FALSE | 80 | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned
FALSE |  | FALSE | 80 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned
FALSE |  | FALSE | 80 | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned
FALSE |  | FALSE | 80 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned
FALSE |  | FALSE | 80 | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned
FALSE |  | FALSE | 39 | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 36 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned
FALSE |  | FALSE | 82 | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned
FALSE |  | FALSE | 51 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 35 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned
FALSE |  | FALSE | 36 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 35 | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 89 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned
FALSE |  | FALSE | 36 | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned
FALSE |  | FALSE | 38 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned
FALSE |  | FALSE | 38 | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned
FALSE |  | FALSE | 35 | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 28 | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned
FALSE |  | FALSE | 32 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 35 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 32 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned
FALSE |  | FALSE | 38 | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | FALSE | 1 | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestones (To-Go) | Milestones (To-Go) | 0 | 0% | 0 | 0%
Number of milestones to-go. Includes % of to-go activities that are milestones (vs. normal activities).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Normal Tasks (To-Go) | Normal Tasks (To-Go) | 99 | 100% | 106 | 100%
Number of normal activities to-go. Includes % of to-go activities that are normal activities (vs. milestones).
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 275 | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress
FALSE |  | FALSE | 19 | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress
FALSE |  | FALSE | 275 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned
FALSE |  | FALSE | 275 | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned
FALSE |  | FALSE | 275 | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned
FALSE |  | FALSE | 256 | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned
FALSE |  | FALSE | 256 | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned
FALSE |  | FALSE | 256 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned
FALSE |  | FALSE | 256 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 56 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 156 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned
FALSE |  | FALSE | 156 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 95 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 100 | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 100 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 95 | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 95 | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 184 | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned
FALSE |  | FALSE | 156 | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 95 | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned
FALSE |  | FALSE | 30 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned
FALSE |  | FALSE | 95 | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | FALSE | 94 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 184 | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned
FALSE |  | FALSE | 118 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 94 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 124 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 184 | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned
FALSE |  | FALSE | 118 | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned
FALSE |  | FALSE | 118 | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned
FALSE |  | FALSE | 82 | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned
FALSE |  | FALSE | 80 | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned
FALSE |  | FALSE | 80 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned
FALSE |  | FALSE | 80 | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned
FALSE |  | FALSE | 80 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned
FALSE |  | FALSE | 80 | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned
FALSE |  | FALSE | 39 | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 36 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned
FALSE |  | FALSE | 82 | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned
FALSE |  | FALSE | 51 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 35 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned
FALSE |  | FALSE | 36 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 35 | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 89 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned
FALSE |  | FALSE | 36 | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned
FALSE |  | FALSE | 38 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned
FALSE |  | FALSE | 38 | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned
FALSE |  | FALSE | 35 | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 28 | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned
FALSE |  | FALSE | 32 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 35 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 32 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned
FALSE |  | FALSE | 38 | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | FALSE | 1 | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Normal Tasks (To-Go, In Progress) | Normal Tasks (To-Go, In Progress) | 2 | 2% | 3 | 3%
Number of normal, in-progress to-go activities. Includes % of to-go activities that are normal, in-progress activities.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 275 | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress
FALSE |  | FALSE | 19 | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress
FALSE |  | FALSE | 275 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned
FALSE |  | FALSE | 275 | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned
FALSE |  | FALSE | 275 | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned
FALSE |  | FALSE | 256 | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned
FALSE |  | FALSE | 256 | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned
FALSE |  | FALSE | 256 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned
FALSE |  | FALSE | 256 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 56 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 156 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned
FALSE |  | FALSE | 156 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 95 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 100 | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 100 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 95 | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 95 | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 184 | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned
FALSE |  | FALSE | 156 | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 95 | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned
FALSE |  | FALSE | 30 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned
FALSE |  | FALSE | 95 | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | FALSE | 94 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 184 | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned
FALSE |  | FALSE | 118 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 94 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 124 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 184 | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned
FALSE |  | FALSE | 118 | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned
FALSE |  | FALSE | 118 | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned
FALSE |  | FALSE | 82 | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned
FALSE |  | FALSE | 80 | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned
FALSE |  | FALSE | 80 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned
FALSE |  | FALSE | 80 | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned
FALSE |  | FALSE | 80 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned
FALSE |  | FALSE | 80 | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned
FALSE |  | FALSE | 39 | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 36 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned
FALSE |  | FALSE | 82 | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned
FALSE |  | FALSE | 51 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 35 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned
FALSE |  | FALSE | 36 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 35 | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 89 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned
FALSE |  | FALSE | 36 | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned
FALSE |  | FALSE | 38 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned
FALSE |  | FALSE | 38 | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned
FALSE |  | FALSE | 35 | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 28 | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned
FALSE |  | FALSE | 32 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 35 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 32 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned
FALSE |  | FALSE | 38 | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
FALSE |  | FALSE | 19 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | FALSE | 1 | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Path (Tasks & Milestones) | Critical Path (Tasks & Milestones) | 4 | 4% | 41 | 39%
Normal activities and milestones that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Path (Milestones) | Critical Path (Milestones) | 0 | 0% | 0 | 0%
Activities that together form the longest path through to project completion.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Path (Normal Tasks) | Critical Path (Normal Tasks) | 4 | 100% | 41 | 100%
Activities that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Path (Normal In Progress) | Critical Path (Normal In Progress) | 0 | 0% | 1 | 2%
Number of critical, in-progress activities.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | N/A |  | N/A
Ratio of the number of milestones to the number of normal activities. Ideally, milestones should make up 5% to 10% of the activities in the schedule.
Excluded | Created | Critical | Total Float | Type | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Status | Percent Complete
FALSE |  | TRUE | 0 | Normal |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Zero Days Float | Zero Days Float | 4 | 4% | 41 | 39%
Total number of activities with 0 days float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Near-Critical (<10 Days Float) | Near-Critical (<10 Days Float) | 5 | 5% | 50 | 47%
Total number of activities with less than 10 days of float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | FALSE | 1 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CP Logic Density™ | CP Logic Density™ | 3 |  | 3.2
The average number of logic links per activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical CEI - Value Tasks | Critical CEI - Value Tasks | N/A |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical CEI - Complete Tasks | Critical CEI - Complete Tasks | N/A | 44% | N/A
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical CEI - Incomplete Tasks | Critical CEI - Incomplete Tasks | N/A | 56% | N/A
The number of tasks that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Newly Critical Activities | Newly Critical Activities | 1 | 25% | 0 | 0%
Number of remaining activities that were added to the critical path this period (i.e., not critical in the last period).
Excluded | Created | Critical | Total Float | Previous_Critical | Notes | Id | Description | Original Duration | Remaining Duration | Start | Finish | Type | Status | Percent Complete | Project
FALSE |  | TRUE | 0 | FALSE |  | 131 | Set HVAC trim and test and balance system | 20 | 20 | 2027-12-10 | 2028-01-06 | Normal | Planned | 0 | Project5_TAMPERED
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Activities No Longer Critical | Activities No Longer Critical | 34 | 24% | 0 | 0%
Number of activities that were previously critical but are no longer on the critical path this period.
Excluded | Created | Critical | Total Float | Previous_Critical | Id | Description | Original Duration | Remaining Duration | Start | Finish | Type | Status | Percent Complete | Project
FALSE |  | FALSE | 19 | TRUE | 35 | Form column piers and spread foundations | 25 | 16 | 2026-08-17 | 2026-09-18 | Normal | InProgress | 36 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 38 | Set reinforcing and anchor bolts | 4 | 4 | 2026-09-21 | 2026-09-24 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 39 | Pour column piers and foundations | 21 | 21 | 2026-09-25 | 2026-10-23 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 42 | Cure piers and foundations | 7 | 7 | 2026-10-26 | 2026-11-03 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 44 | Strip column piers and foundation forms | 3 | 3 | 2026-11-04 | 2026-11-06 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | 10 | 10 | 2026-11-09 | 2026-11-20 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 49 | Erect steel columns, beams and joist - 3rd floor and roof | 17 | 17 | 2026-11-23 | 2026-12-15 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | 10 | 10 | 2026-12-16 | 2026-12-29 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 52 | Install stairs and miscellaneous iron railing | 10 | 10 | 2026-12-30 | 2027-01-12 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 53 | Touch-up paint on steel | 5 | 5 | 2027-01-13 | 2027-01-19 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 55 | Form 2nd floor including all floor openings | 17 | 17 | 2027-01-20 | 2027-02-11 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 57 | Pour 2nd floor slab | 4 | 4 | 2027-02-12 | 2027-02-17 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 58 | Cure 2nd floor slab | 7 | 7 | 2027-02-18 | 2027-02-26 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 60 | Form 3rd floor including all floor openings | 5 | 5 | 2027-03-01 | 2027-03-05 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 5 | 5 | 2027-03-01 | 2027-03-05 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 62 | Pour 3rd floor slab | 4 | 4 | 2027-03-08 | 2027-03-11 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 63 | Cure 3rd floor slab | 7 | 7 | 2027-03-12 | 2027-03-22 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 65 | Form roof slab including all floor openings | 5 | 5 | 2027-03-23 | 2027-03-29 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 5 | 5 | 2027-03-23 | 2027-03-29 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 67 | Pour roof slab | 4 | 4 | 2027-03-30 | 2027-04-02 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 68 | Cure roof slab | 7 | 7 | 2027-04-05 | 2027-04-13 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 69 | Strip forms from roof slab | 2 | 2 | 2027-04-14 | 2027-04-15 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 78 | Install exterior sheathing and metal studs | 15 | 15 | 2027-04-16 | 2027-05-06 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 82 | Install exterior masonry work | 25 | 25 | 2027-05-07 | 2027-06-10 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 94 | Install window wall aluminum and glass | 25 | 25 | 2027-06-11 | 2027-07-15 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 95 | Install interior stud walls and drywall | 25 | 25 | 2027-07-16 | 2027-08-19 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 96 | Install interior doors and hardware | 10 | 10 | 2027-09-10 | 2027-09-23 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 100 | Paint walls and woodwork | 20 | 20 | 2027-09-24 | 2027-10-21 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 28 | TRUE | 106 | Install building carpet | 41 | 41 | 2027-10-22 | 2027-12-17 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 135 | Remove debris from building and do final clean-up | 4 | 4 | 2027-11-29 | 2027-12-02 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 138 | Complete elevator inspection and certification | 3 | 3 | 2027-12-03 | 2027-12-07 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 139 | Perform architect's inspection | 1 | 1 | 2027-12-08 | 2027-12-08 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 140 | Perform local building agency inspection | 1 | 1 | 2027-12-09 | 2027-12-09 | Normal | Planned | 0 | Project5_TAMPERED
FALSE |  | FALSE | 19 | TRUE | 141 | Perform Fire Marshal's inspection | 1 | 1 | 2027-12-10 | 2027-12-10 | Normal | Planned | 0 | Project5_TAMPERED

## NASA_Quick-Library-BEI---Incom
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick-Library -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis
BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | Score
0.59 | 46 | 27 | 19 | 100
|  | 59% | 41%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Tasks | BEI - Value Tasks | 0.59 |  | 0.74
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Total Tasks | BEI - Total Tasks | 46 |  | 27
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Complete Tasks | BEI - Complete Tasks | 27 | 59% | 20 | 74%
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Incomplete Tasks | BEI - Incomplete Tasks | 19 | 41% | 7 | 26%
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19

## NASA_Quick-Library-Control-Mil
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick-Library -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates
Status Date | Milestone #1 - 100 | Float Milestone #1 - 100 | Milestone #2 - 101 | Float to Milestone #2 - 101 | Milestone #3 - 102 | Float to Milestone #3 - 102 | Milestone #4 - 103 | Float to Milestone #4 - 103 | Milestone #5 - 104 | Float to Milestone #5 - 104 | New Activities Since Previous Status Date | Score
2026-08-27 | 2027-09-24 | 19 | 2027-07-16 | 36 | 2027-08-20 | 35 | 2027-09-23 | 35 | 2027-09-24 | 55 | 0 | 100
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestone #1 - 100 | Milestone #1 - 100 | 2027-09-24 |  | 2027-06-17
Tracks the milestone start date across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Float Milestone #1 - 100 | Float Milestone #1 - 100 | 19 |  | 0
Tracks the milestone's total float across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestone #2 - 101 | Milestone #2 - 101 | 2027-07-16 |  | 2027-04-08
Tracks the milestone start date across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Float to Milestone #2 - 101 | Float to Milestone #2 - 101 | 36 |  | 15
Tracks the milestone's total float across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestone #3 - 102 | Milestone #3 - 102 | 2027-08-20 |  | 2027-05-13
Tracks the milestone start date across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Float to Milestone #3 - 102 | Float to Milestone #3 - 102 | 35 |  | 10
Tracks the milestone's total float across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestone #4 - 103 | Milestone #4 - 103 | 2027-09-23 |  | 2027-06-16
Tracks the milestone start date across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Float to Milestone #4 - 103 | Float to Milestone #4 - 103 | 35 |  | 10
Tracks the milestone's total float across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestone #5 - 104 | Milestone #5 - 104 | 2027-09-24 |  | 2027-06-17
Tracks the milestone start date across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Float to Milestone #5 - 104 | Float to Milestone #5 - 104 | 55 |  | 30
Tracks the milestone's total float across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
New Activities Since Previous Status Date | New Activities Since Previous Status Date | 0 |  | 0

## NASA_Quick-Library-Margin-Date
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick-Library -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date
Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
2026-08-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #1 | Margin - Margin Task Name #1 | N/A |  | N/A
Tracks the margin activity start date across multiple schedule status updates.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #2 | Margin - Margin Task Name #2 | N/A |  | N/A
Tracks the margin activity start date across multiple schedule status updates.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #3 | Margin - Margin Task Name #3 | N/A |  | N/A
Tracks the margin activity start date across multiple schedule status updates.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #4 | Margin - Margin Task Name #4 | N/A |  | N/A
Tracks the margin activity start date across multiple schedule status updates.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #5 | Margin - Margin Task Name #5 | N/A |  | N/A
Tracks the margin activity start date across multiple schedule status updates.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #6 | Margin - Margin Task Name #6 | N/A |  | N/A
Tracks the margin activity start date across multiple schedule status updates.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #7 | Margin - Margin Task Name #7 | N/A |  | N/A
Tracks the margin activity start date across multiple schedule status updates.

## NASA_Quick-Library-Margin-Dura
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick-Library -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration
Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
2026-08-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100
| N/A | N/A | N/A | N/A | N/A | N/A | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #1 | Margin - Margin Task Name #1 | N/A |  | N/A
Tracks the margin activity's remaining duration across multiple schedule status updates.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #2 | Margin - Margin Task Name #2 | N/A |  | N/A
Tracks the margin activity's remaining duration across multiple schedule status updates.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #3 | Margin - Margin Task Name #3 | N/A |  | N/A
Tracks the margin activity's remaining duration across multiple schedule status updates.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #4 | Margin - Margin Task Name #4 | N/A |  | N/A
Tracks the margin activity's remaining duration across multiple schedule status updates.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #5 | Margin - Margin Task Name #5 | N/A |  | N/A
Tracks the margin activity's remaining duration across multiple schedule status updates.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #6 | Margin - Margin Task Name #6 | N/A |  | N/A
Tracks the margin activity's remaining duration across multiple schedule status updates.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #7 | Margin - Margin Task Name #7 | N/A |  | N/A
Tracks the margin activity's remaining duration across multiple schedule status updates.

## NASA_Quick-Library-Status---Ch
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick-Library -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1)
Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Critical Milestones (To-Go) | Critical Normal Tasks (To-Go) | Riding Data Date | Score
2026-08-27 | 144 | 0 | 126 | 18 | 0 | 0 | 126 | 27 | 0 | 27 | 113 | 99 | 0 | 99 | 14 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 0 | 100
|  | 0% | 88% | 13% | 0% | 0% | 88% | 21% | ( N/A ) | 21% | 78% | 88% | 0% | 88% | 12% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 0%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total Activities | Total Activities | 144 |  | 144
The total number of activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 2 | General Conditions | Project5_TAMPERED | Standard | 46 | 0 | 2026-03-02 | 2026-05-04 | 2026-03-02 | 2026-04-01 | Summary | Complete | 0
FALSE |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | Standard | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | Standard | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE |  | 100 |  | 18 | Mobilize on Site | Project5_TAMPERED | Standard | 17 | 0 | 2026-03-05 | 2026-03-27 | 2026-03-05 | 2026-03-18 | Summary | Complete | 0
FALSE |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 10 | Long Lead Procurement | Project5_TAMPERED | Standard | 76 | 0 | 2026-03-06 | 2026-06-19 | 2026-03-06 | 2026-06-11 | Summary | Complete | 0
FALSE |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | Standard | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | Standard | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | Standard | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | Standard | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE |  | 100 |  | 24 | Site Grading and Utilities | Project5_TAMPERED | Standard | 85 | 0 | 2026-04-06 | 2026-07-31 | 2026-03-19 | 2026-05-06 | Summary | Complete | 0
FALSE |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | Standard | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | Standard | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | Standard | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | Standard | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | Standard | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | Standard | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | Standard | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | Standard | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE |  | 28 |  | 32 | Foundations | Project5_TAMPERED | Standard | 92 | 66 | 2026-08-03 | 2026-12-08 | 2026-05-07 | 2026-07-08 | Summary | InProgress | 256
FALSE |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | Standard | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 47 | Steel Erection | Project5_TAMPERED | Standard | 74 | 74 | 2026-11-09 | 2027-02-18 | 2026-06-23 | 2026-08-31 | Summary | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 54 | Form and Pour Concrete - Floors and Roof | Project5_TAMPERED | Standard | 89 | 89 | 2026-12-16 | 2027-04-19 | 2026-07-07 | 2026-11-04 | Summary | Planned | 44
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 79 | Masonry Work | Project5_TAMPERED | Standard | 86 | 86 | 2027-02-19 | 2027-06-18 | 2026-09-01 | 2027-01-05 | Summary | Planned | 74
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 110 | Elevators | Project5_TAMPERED | Standard | 40 | 40 | 2027-03-19 | 2027-05-13 | 2026-09-29 | 2026-11-23 | Summary | Planned | 184
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 126 | Heating and Ventilating - AC | Project5_TAMPERED | Standard | 210 | 210 | 2027-03-19 | 2028-01-06 | 2026-09-29 | 2027-06-16 | Summary | Planned | 14
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 77 | Carpentry Work | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Summary | Planned | 19
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 119 | Electrical | Project5_TAMPERED | Standard | 140 | 140 | 2027-04-20 | 2027-11-01 | 2026-11-05 | 2027-05-19 | Summary | Planned | 38
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 87 | Roofing | Project5_TAMPERED | Standard | 33 | 33 | 2027-06-11 | 2027-07-27 | 2026-12-29 | 2027-02-11 | Summary | Planned | 80
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 93 | Window wall and store front closures | Project5_TAMPERED | Standard | 75 | 75 | 2027-06-11 | 2027-09-23 | 2026-12-29 | 2027-04-12 | Summary | Planned | 19
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 114 | Plumbing | Project5_TAMPERED | Standard | 100 | 100 | 2027-06-18 | 2027-11-04 | 2027-01-05 | 2027-05-24 | Summary | Planned | 35
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 98 | Building Finishes | Project5_TAMPERED | Standard | 111 | 111 | 2027-07-16 | 2027-12-17 | 2027-02-02 | 2027-06-07 | Summary | Planned | 28
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 132 | Final Clean-up and Occupancy | Project5_TAMPERED | Standard | 76 | 76 | 2027-08-20 | 2027-12-03 | 2027-03-09 | 2027-06-14 | Summary | Planned | 38
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 137 | Complete Final Inspections | Project5_TAMPERED | Standard | 6 | 6 | 2027-12-03 | 2027-12-10 | 2027-06-14 | 2027-06-21 | Summary | Planned | 19
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestones | Milestones | 0 | 0% | 0 | 0%
Number of milestones within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | Standard | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | Standard | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | Standard | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | Standard | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | Standard | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | Standard | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | Standard | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | Standard | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | Standard | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | Standard | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | Standard | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | Standard | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | Standard | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | Standard | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | Standard | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Normal Tasks | Normal Tasks | 126 | 88% | 126 | 88%
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | Standard | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | Standard | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | Standard | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | Standard | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | Standard | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | Standard | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | Standard | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | Standard | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | Standard | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | Standard | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | Standard | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | Standard | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | Standard | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | Standard | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | Standard | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Summaries | Summaries | 18 | 13% | 18 | 13%
Number of summary activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 2 | General Conditions | Project5_TAMPERED | Standard | 46 | 0 | 2026-03-02 | 2026-05-04 | 2026-03-02 | 2026-04-01 | Summary | Complete | 0
FALSE |  | 100 |  | 18 | Mobilize on Site | Project5_TAMPERED | Standard | 17 | 0 | 2026-03-05 | 2026-03-27 | 2026-03-05 | 2026-03-18 | Summary | Complete | 0
FALSE |  | 100 |  | 10 | Long Lead Procurement | Project5_TAMPERED | Standard | 76 | 0 | 2026-03-06 | 2026-06-19 | 2026-03-06 | 2026-06-11 | Summary | Complete | 0
FALSE |  | 100 |  | 24 | Site Grading and Utilities | Project5_TAMPERED | Standard | 85 | 0 | 2026-04-06 | 2026-07-31 | 2026-03-19 | 2026-05-06 | Summary | Complete | 0
FALSE |  | 28 |  | 32 | Foundations | Project5_TAMPERED | Standard | 92 | 66 | 2026-08-03 | 2026-12-08 | 2026-05-07 | 2026-07-08 | Summary | InProgress | 256
FALSE |  | 0 |  | 47 | Steel Erection | Project5_TAMPERED | Standard | 74 | 74 | 2026-11-09 | 2027-02-18 | 2026-06-23 | 2026-08-31 | Summary | Planned | 19
FALSE |  | 0 |  | 54 | Form and Pour Concrete - Floors and Roof | Project5_TAMPERED | Standard | 89 | 89 | 2026-12-16 | 2027-04-19 | 2026-07-07 | 2026-11-04 | Summary | Planned | 44
FALSE |  | 0 |  | 79 | Masonry Work | Project5_TAMPERED | Standard | 86 | 86 | 2027-02-19 | 2027-06-18 | 2026-09-01 | 2027-01-05 | Summary | Planned | 74
FALSE |  | 0 |  | 110 | Elevators | Project5_TAMPERED | Standard | 40 | 40 | 2027-03-19 | 2027-05-13 | 2026-09-29 | 2026-11-23 | Summary | Planned | 184
FALSE |  | 0 |  | 126 | Heating and Ventilating - AC | Project5_TAMPERED | Standard | 210 | 210 | 2027-03-19 | 2028-01-06 | 2026-09-29 | 2027-06-16 | Summary | Planned | 14
FALSE |  | 0 |  | 77 | Carpentry Work | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Summary | Planned | 19
FALSE |  | 0 |  | 119 | Electrical | Project5_TAMPERED | Standard | 140 | 140 | 2027-04-20 | 2027-11-01 | 2026-11-05 | 2027-05-19 | Summary | Planned | 38
FALSE |  | 0 |  | 87 | Roofing | Project5_TAMPERED | Standard | 33 | 33 | 2027-06-11 | 2027-07-27 | 2026-12-29 | 2027-02-11 | Summary | Planned | 80
FALSE |  | 0 |  | 93 | Window wall and store front closures | Project5_TAMPERED | Standard | 75 | 75 | 2027-06-11 | 2027-09-23 | 2026-12-29 | 2027-04-12 | Summary | Planned | 19
FALSE |  | 0 |  | 114 | Plumbing | Project5_TAMPERED | Standard | 100 | 100 | 2027-06-18 | 2027-11-04 | 2027-01-05 | 2027-05-24 | Summary | Planned | 35
FALSE |  | 0 |  | 98 | Building Finishes | Project5_TAMPERED | Standard | 111 | 111 | 2027-07-16 | 2027-12-17 | 2027-02-02 | 2027-06-07 | Summary | Planned | 28
FALSE |  | 0 |  | 132 | Final Clean-up and Occupancy | Project5_TAMPERED | Standard | 76 | 76 | 2027-08-20 | 2027-12-03 | 2027-03-09 | 2027-06-14 | Summary | Planned | 38
FALSE |  | 0 |  | 137 | Complete Final Inspections | Project5_TAMPERED | Standard | 6 | 6 | 2027-12-03 | 2027-12-10 | 2027-06-14 | 2027-06-21 | Summary | Planned | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Hammocks | Hammocks | 0 | 0% | 0 | 0%
Number of hammocks within a grouping.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Recurring Normal Tasks | Recurring Normal Tasks | 0 | 0% | 0 | 0%
Tasks marked as recurring.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total Tasks & Milestones | Total Tasks & Milestones | 126 | 88% | 126 | 88%
Total number of regular tasks and milestones in the project schedule.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | Standard | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | Standard | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | Standard | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | Standard | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | Standard | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | Standard | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | Standard | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | Standard | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | Standard | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | Standard | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | Standard | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | Standard | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | Standard | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | Standard | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | Standard | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Tasks & Milestones | Completed Tasks & Milestones | 27 | 21% | 20 | 16%
Total number of completed tasks and milestones
Excluded | DRM | Baseline Duration | Actual Duration | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 1 | 3 | 3 |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE | 1 | 4 | 4 |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | Standard | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE | 1 | 1 | 1 |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | Standard | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE | 1.6 | 10 | 16 |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | Standard | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE | 1 | 3 | 3 |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE | 3.3333 | 3 | 10 |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | Standard | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE | 1 | 60 | 60 |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | Standard | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE | 2.3 | 10 | 23 |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | Standard | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE | 1 | 3 | 3 |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | Standard | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | Standard | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE | 1 | 5 | 5 |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | Standard | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE | 2 | 10 | 20 |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | Standard | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE | 4.3 | 10 | 43 |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | Standard | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE | 1.9 | 10 | 19 |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | Standard | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 0.9 | 10 | 9 |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | Standard | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE | 4 | 5 | 20 |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | Standard | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE | 0.5 | 10 | 5 |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | Standard | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Milestones | Completed Milestones | 0 |  | 0
Total number of completed milestones.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Tasks | Completed Tasks | 27 | 21% | 20 | 16%
Total number of completed tasks
Excluded | DRM | Baseline Duration | Actual Duration | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 1 | 3 | 3 |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE | 1 | 4 | 4 |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | Standard | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE | 1 | 1 | 1 |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | Standard | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE | 1.6 | 10 | 16 |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | Standard | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE | 1 | 3 | 3 |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE | 3.3333 | 3 | 10 |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | Standard | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE | 1 | 60 | 60 |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | Standard | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE | 2.3 | 10 | 23 |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | Standard | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE | 1 | 3 | 3 |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | Standard | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | Standard | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE | 1 | 5 | 5 |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | Standard | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE | 2 | 10 | 20 |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | Standard | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE | 4.3 | 10 | 43 |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | Standard | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE | 1.9 | 10 | 19 |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | Standard | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 0.9 | 10 | 9 |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | Standard | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE | 4 | 5 | 20 |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | Standard | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE | 0.5 | 10 | 5 |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | Standard | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total Activities (To-Go) - % of Total | Total Activities (To-Go) - % of Total | 113 | 78% | 122 | 85%
The total number of activities within a grouping. Percentage shows total total to-go (planned and in-progress) activities (normal, milestone, summary and LOE) out of total to-go and completed activities.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 28 |  | 32 | Foundations | Project5_TAMPERED | Standard | 92 | 66 | 2026-08-03 | 2026-12-08 | 2026-05-07 | 2026-07-08 | Summary | InProgress | 256
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 47 | Steel Erection | Project5_TAMPERED | Standard | 74 | 74 | 2026-11-09 | 2027-02-18 | 2026-06-23 | 2026-08-31 | Summary | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 54 | Form and Pour Concrete - Floors and Roof | Project5_TAMPERED | Standard | 89 | 89 | 2026-12-16 | 2027-04-19 | 2026-07-07 | 2026-11-04 | Summary | Planned | 44
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 79 | Masonry Work | Project5_TAMPERED | Standard | 86 | 86 | 2027-02-19 | 2027-06-18 | 2026-09-01 | 2027-01-05 | Summary | Planned | 74
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 110 | Elevators | Project5_TAMPERED | Standard | 40 | 40 | 2027-03-19 | 2027-05-13 | 2026-09-29 | 2026-11-23 | Summary | Planned | 184
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 126 | Heating and Ventilating - AC | Project5_TAMPERED | Standard | 210 | 210 | 2027-03-19 | 2028-01-06 | 2026-09-29 | 2027-06-16 | Summary | Planned | 14
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 77 | Carpentry Work | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Summary | Planned | 19
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 119 | Electrical | Project5_TAMPERED | Standard | 140 | 140 | 2027-04-20 | 2027-11-01 | 2026-11-05 | 2027-05-19 | Summary | Planned | 38
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 87 | Roofing | Project5_TAMPERED | Standard | 33 | 33 | 2027-06-11 | 2027-07-27 | 2026-12-29 | 2027-02-11 | Summary | Planned | 80
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 93 | Window wall and store front closures | Project5_TAMPERED | Standard | 75 | 75 | 2027-06-11 | 2027-09-23 | 2026-12-29 | 2027-04-12 | Summary | Planned | 19
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 114 | Plumbing | Project5_TAMPERED | Standard | 100 | 100 | 2027-06-18 | 2027-11-04 | 2027-01-05 | 2027-05-24 | Summary | Planned | 35
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 98 | Building Finishes | Project5_TAMPERED | Standard | 111 | 111 | 2027-07-16 | 2027-12-17 | 2027-02-02 | 2027-06-07 | Summary | Planned | 28
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 132 | Final Clean-up and Occupancy | Project5_TAMPERED | Standard | 76 | 76 | 2027-08-20 | 2027-12-03 | 2027-03-09 | 2027-06-14 | Summary | Planned | 38
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 137 | Complete Final Inspections | Project5_TAMPERED | Standard | 6 | 6 | 2027-12-03 | 2027-12-10 | 2027-06-14 | 2027-06-21 | Summary | Planned | 19
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Tasks & Milestones (To-Go) - % of Total To-Go | Tasks & Milestones (To-Go) - % of Total To-Go | 99 | 88% | 106 | 87%
The total number of activities within a grouping. Percentage shows total to-go (planned and in-progress) tasks and milestones out of all activities (normal, milestone, summary, and LOE).
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestones (To-Go) | Milestones (To-Go) | 0 | 0% | 0 | 0%
Number of milestones within a grouping.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Normal Tasks (To-Go) | Normal Tasks (To-Go) | 99 | 88% | 106 | 87%
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Summaries (To-Go) | Summaries (To-Go) | 14 | 12% | 16 | 13%
Number of summary activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 28 |  | 32 | Foundations | Project5_TAMPERED | Standard | 92 | 66 | 2026-08-03 | 2026-12-08 | 2026-05-07 | 2026-07-08 | Summary | InProgress | 256
FALSE |  | 0 |  | 47 | Steel Erection | Project5_TAMPERED | Standard | 74 | 74 | 2026-11-09 | 2027-02-18 | 2026-06-23 | 2026-08-31 | Summary | Planned | 19
FALSE |  | 0 |  | 54 | Form and Pour Concrete - Floors and Roof | Project5_TAMPERED | Standard | 89 | 89 | 2026-12-16 | 2027-04-19 | 2026-07-07 | 2026-11-04 | Summary | Planned | 44
FALSE |  | 0 |  | 79 | Masonry Work | Project5_TAMPERED | Standard | 86 | 86 | 2027-02-19 | 2027-06-18 | 2026-09-01 | 2027-01-05 | Summary | Planned | 74
FALSE |  | 0 |  | 110 | Elevators | Project5_TAMPERED | Standard | 40 | 40 | 2027-03-19 | 2027-05-13 | 2026-09-29 | 2026-11-23 | Summary | Planned | 184
FALSE |  | 0 |  | 126 | Heating and Ventilating - AC | Project5_TAMPERED | Standard | 210 | 210 | 2027-03-19 | 2028-01-06 | 2026-09-29 | 2027-06-16 | Summary | Planned | 14
FALSE |  | 0 |  | 77 | Carpentry Work | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Summary | Planned | 19
FALSE |  | 0 |  | 119 | Electrical | Project5_TAMPERED | Standard | 140 | 140 | 2027-04-20 | 2027-11-01 | 2026-11-05 | 2027-05-19 | Summary | Planned | 38
FALSE |  | 0 |  | 87 | Roofing | Project5_TAMPERED | Standard | 33 | 33 | 2027-06-11 | 2027-07-27 | 2026-12-29 | 2027-02-11 | Summary | Planned | 80
FALSE |  | 0 |  | 93 | Window wall and store front closures | Project5_TAMPERED | Standard | 75 | 75 | 2027-06-11 | 2027-09-23 | 2026-12-29 | 2027-04-12 | Summary | Planned | 19
FALSE |  | 0 |  | 114 | Plumbing | Project5_TAMPERED | Standard | 100 | 100 | 2027-06-18 | 2027-11-04 | 2027-01-05 | 2027-05-24 | Summary | Planned | 35
FALSE |  | 0 |  | 98 | Building Finishes | Project5_TAMPERED | Standard | 111 | 111 | 2027-07-16 | 2027-12-17 | 2027-02-02 | 2027-06-07 | Summary | Planned | 28
FALSE |  | 0 |  | 132 | Final Clean-up and Occupancy | Project5_TAMPERED | Standard | 76 | 76 | 2027-08-20 | 2027-12-03 | 2027-03-09 | 2027-06-14 | Summary | Planned | 38
FALSE |  | 0 |  | 137 | Complete Final Inspections | Project5_TAMPERED | Standard | 6 | 6 | 2027-12-03 | 2027-12-10 | 2027-06-14 | 2027-06-21 | Summary | Planned | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Hammocks (To-Go) | Hammocks (To-Go) | 0 | 0% | 0 | 0%
Number of level of effort (hammocks) within a grouping.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Recurring Tasks (To-Go) | Recurring Tasks (To-Go) | 0 | 0% | 0 | 0%
Tasks marked recurring that are in progress or planned (future).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Longest Path (Tasks & Milestones) | Longest Path (Tasks & Milestones) | 4 | 100% | 41 | 87%
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Longest Path (Normal Tasks) | Longest Path (Normal Tasks) | 4 | 100% | 41 | 87%
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Longest Path (Milestones) | Longest Path (Milestones) | 0 | 0% | 0 | 0%
Activities that together form the longest path through to project completion.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Milestones (To-Go) | Critical Milestones (To-Go) | 0 | 0% | 0 | 0%
Number of critical milestones to-go.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Normal Tasks (To-Go) | Critical Normal Tasks (To-Go) | 4 | 100% | 41 | 100%
Number of critical activities to-go.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Riding Data Date | Riding Data Date | 0 | 0% | 0 | 0%
Number of planned activities that have a start date that is the same as the project data date (Time Now)

## NASA_Quick-Library-Performance
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick-Library -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project)
Baselined to Start | Scheduled to Start | Actual Starts | Baselined to Finish | Scheduled to Finish | Actual Finishes | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Score
126 | 126 | 29 | 126 | 126 | 27 | 8 | 4 | 6 | 7 | 6 | 5 | 86
[6 empty] | 44% | 22% | 33% | 39% | 33% | 28%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Start | Baselined to Start | 126 |  | 126
Number of activities that are baselined to start.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Start | Scheduled to Start | 126 |  | 126
Number of activities that are scheduled/planned to start.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Actual Starts | Actual Starts | 29 |  | 23
Number of activities that have started in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Finish | Baselined to Finish | 126 |  | 126
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Finish | Scheduled to Finish | 126 |  | 126
Number of activities within that are planned to finish.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Actual Finishes | Actual Finishes | 27 |  | 20
Number of activities that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Delayed (<=30 days) | Started Delayed (<=30 days) | 8 | 44% | 8 | 67%
Number of activities that finished up to 30 days after their baselined finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Delayed (Between 31 to 60 days) | Started Delayed (Between 31 to 60 days) | 4 | 22% | 4 | 33%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Delayed (>60 days) | Started Delayed (>60 days) | 6 | 33% | 0 | 0%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed (<=30 days) | Completed Delayed (<=30 days) | 7 | 39% | 6 | 55%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed (Between 31 to 60 days) | Completed Delayed (Between 31 to 60 days) | 6 | 33% | 5 | 45%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed (>60 days) | Completed Delayed (>60 days) | 5 | 28% | 0 | 0%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0

## NASA_Quick-Library-Performance2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick-Library -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon)
BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Score
0.6 | 0.59 | 0 | 0.05 | 0.4 | 0.44 | 1.24 | 1.24 | 1.24 | 1.24 | 97 | 99 | 97 | 1.24 | 67
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Task Starts - Cumulative | BEI - Value Task Starts - Cumulative | 0.6 |  | 0.79
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Task Finishes - Cumulative | BEI - Value Task Finishes - Cumulative | 0.59 |  | 0.74
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Task Starts - by Status Dates | HMI - Value Task Starts - by Status Dates | 0 |  | N/A
Hit or Miss Index (HMI) calculation for task starts. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Task Finishes - by Status Dates | HMI - Value Task Finishes - by Status Dates | 0.05 |  | N/A
Hit or Miss Index (HMI) calculation for task finishes. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Task Starts - by Status Dates | CEI - Value Task Starts - by Status Dates | 0.4 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Task Finishes - by Status Dates | CEI - Value Task Finishes - by Status Dates | 0.44 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
FEI - Value Task Starts - Cumulative | FEI - Value Task Starts - Cumulative | 1.24 |  | 1.06
Future Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline for activities that have not yet started.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
FEI - Value Task Finish - Cumulative | FEI - Value Task Finish - Cumulative | 1.24 |  | 1.07
Future Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline for activities that have not yet started.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - BEI - Value Task Starts - Cumulative | To Go - BEI - Value Task Starts - Cumulative | 1.24 |  | 1.06
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - BEI - Value Task Finishes - Cumulative | To Go - BEI - Value Task Finishes - Cumulative | 1.24 |  | 1.07
To-Complete Baseline Execution Index (TC-BEI)
Id | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
34 | Excavate elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-05-22 |  | 2026-08-28 | Normal | InProgress
35 | Form column piers and spread foundations | Project5_TAMPERED | 2026-08-27 | 2026-05-26 |  | 2026-09-18 | Normal | InProgress
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - Planned Task Starts - Count | To Go - Planned Task Starts - Count | 97 |  | 103
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - BEI - Task Finishes - Count | To Go - BEI - Task Finishes - Count | 99 |  | 106
To-Complete Baseline Execution Index (TC-BEI)
Id | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
34 | Excavate elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-05-22 |  | 2026-08-28 | Normal | InProgress
35 | Form column piers and spread foundations | Project5_TAMPERED | 2026-08-27 | 2026-05-26 |  | 2026-09-18 | Normal | InProgress
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - Baselined Task Starts - Count | To Go - Baselined Task Starts - Count | 97 |  | 103
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - BEI - Value Task Starts - Cumulative | To Go - BEI - Value Task Starts - Cumulative | 1.24 |  | 1.06
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned

## NASA_Quick-Library-Performance3
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick-Library -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4)
Current Baseline to Start & Started (BL Plan) | Future Baseline to Start & Started (Early Starts) | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Finish & Finished (BL Plan) | Future Baseline to Finish & Finished (Early Finishes) | Past Baseline to Finish & Finished (Workoff Burden) | Current Baseline to Finish & Not Finished (Incompletes) | Past Baseline to Start & Not Started (Workoff Burden) (SEM07) | Future Baseline to Start & Already Delayed (Workoff Burden) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Score
29 | N/A | 0 | 97 | 27 | 0 | 0 | 99 | 19 | 78 | 19 | 80 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Start & Started (BL Plan) | Current Baseline to Start & Started (BL Plan) | 29 |  | 23
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Future Baseline to Start & Started (Early Starts) | Future Baseline to Start & Started (Early Starts) | N/A |  | N/A
Number of activities that have started in the current period with baseline start dates in the past (before current period).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Past Baseline to Start & Started (Workoff Burden) | Past Baseline to Start & Started (Workoff Burden) | 0 |  | 0
Number of activities that have started in the current period with baseline start dates in the past (before current period).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Start & Not Started (Incompletes) | 97 |  | 103
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Finish & Finished (BL Plan) | Current Baseline to Finish & Finished (BL Plan) | 27 |  | 20
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Future Baseline to Finish & Finished (Early Finishes) | Future Baseline to Finish & Finished (Early Finishes) | 0 |  | 0
Number of activities finishing or that have finished in the current period.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Past Baseline to Finish & Finished (Workoff Burden) | Past Baseline to Finish & Finished (Workoff Burden) | 0 |  | 0
Number of that have finished in the current period with baseline finish dates in the past (before current period).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Finish & Not Finished (Incompletes) | Current Baseline to Finish & Not Finished (Incompletes) | 99 |  | 106
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Past Baseline to Start & Not Started (Workoff Burden) | Past Baseline to Start & Not Started (Workoff Burden) | 19 |  | 6
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Future Baseline to Start & Already Delayed (Workoff Burden) | Future Baseline to Start & Already Delayed (Workoff Burden) | 78 |  | 97
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Past Baseline to Finish & Not Finished (Workoff Burden) | Past Baseline to Finish & Not Finished (Workoff Burden) | 19 |  | 7
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
34 | 2026-05-21 | 2026-08-10 | 2026-08-10 | Excavate elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-05-22 |  | 2026-08-28 | Normal | InProgress
35 | 2026-05-21 | 2026-08-17 | 2026-08-17 | Form column piers and spread foundations | Project5_TAMPERED | 2026-08-27 | 2026-05-26 |  | 2026-09-18 | Normal | InProgress
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Future Baseline to Finish & Already Delayed (Workoff Burden) | Future Baseline to Finish & Already Delayed (Workoff Burden) | 80 |  | 99
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned

## NASA_Quick-Library-Performance4
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick-Library -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Duration Ratio (GRAPH 5, Project) | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Duration Ratio (GRAPH 5, Project)
Duration Ratio Metric (DRM) | DRM Graph | Score
27 | 27 | 100
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Duration Ratio Metric (DRM) | Duration Ratio Metric (DRM) | 27 |  | 20
Duration Ratio Metric compares the actual time a task or project phase took (Actual Duration) to the time it was originally planned or expected to take (Baseline Duration). The result is a ratio that quantifies schedule performance. Duration Ratio = ActualDuration/BaselineDuration
Excluded | Notes | Id | Description | Baseline Duration | Actual Duration | DRM | Project | Original Duration | Remaining Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | 3 | 3 | 1 | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | 4 | 4 | 1 | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | 1 | 1 | 1 | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | 2 | 2 | 1 | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | 2 | 2 | 1 | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | 10 | 16 | 1.6 | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | 3 | 3 | 1 | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | 3 | 10 | 3.3333 | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | 2 | 2 | 1 | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | 2 | 2 | 1 | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | 2 | 2 | 1 | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | 60 | 60 | 1 | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | 2 | 2 | 1 | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | 10 | 23 | 2.3 | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | 3 | 3 | 1 | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | 2 | 2 | 1 | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | 5 | 5 | 1 | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | 10 | 20 | 2 | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | 10 | 43 | 4.3 | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | 10 | 19 | 1.9 | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | 10 | 10 | 1 | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | 10 | 9 | 0.9 | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | 10 | 10 | 1 | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | 10 | 10 | 1 | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | 10 | 10 | 1 | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | 5 | 20 | 4 | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | 10 | 5 | 0.5 | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
DRM Graph | DRM Graph | 27 |  | 20
The total number of activities within a grouping.
Id | Description | Baseline Duration | Actual Duration | DRM
3 | Receive notice to proceed and sign contract | 3 | 3 | 1
7 | Obtain building permits | 4 | 4 | 1
9 | Submit monthly requests for payment | 1 | 1 | 1
19 | Install temporary power | 2 | 2 | 1
20 | Install temporary water service | 2 | 2 | 1
11 | Submit shop drawings and order long lead items - steel | 10 | 16 | 1.6
21 | Set up site office | 3 | 3 | 1
22 | Set line and grade benchmarks | 3 | 10 | 3.3333
4 | Submit bond and insurance documents | 2 | 2 | 1
23 | Prepare site - lay down yard and temporary fencing | 2 | 2 | 1
5 | Prepare and submit project schedule | 2 | 2 | 1
17 | Detail, fabricate and deliver steel | 60 | 60 | 1
6 | Prepare and submit schedule of values | 2 | 2 | 1
8 | Submit preliminary shop drawings | 10 | 23 | 2.3
25 | Clear and grub site | 3 | 3 | 1
26 | Stone site access and temporary parking area | 2 | 2 | 1
27 | Rough grade site (cut and fill) | 5 | 5 | 1
28 | Install storm drainage | 10 | 20 | 2
29 | Install exterior fire line and building fire riser | 10 | 43 | 4.3
12 | Submit shop drawings and order long lead items - roofing | 10 | 19 | 1.9
13 | Submit shop drawings and order long lead items - elevator | 10 | 10 | 1
14 | Submit shop drawings and order long lead items - plumbing | 10 | 9 | 0.9
16 | Submit shop drawings and order long lead items - HVAC | 10 | 10 | 1
15 | Submit shop drawings and order long lead items - electric | 10 | 10 | 1
30 | Perform final site grading | 10 | 10 | 1
31 | Erect building batter boards and layout building | 5 | 20 | 4
33 | Excavate foundations | 10 | 5 | 0.5

## NASA_Quick-Library-Performance5
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick-Library -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6)
Baselined to Start | Scheduled to Start | Baselined to Finish | Scheduled to Finish | Score
99 | 99 | 99 | 99 | 100
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Start | Baselined to Start | 99 |  | 106
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Start | Scheduled to Start | 99 |  | 106
Number of activities that are planned to start.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Finish | Baselined to Finish | 99 |  | 106
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Finish | Scheduled to Finish | 99 |  | 106
Number of activities within that are planned to finish.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0

## NASA_Quick-Library-Performance6
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA_Quick-Library -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7)
BEI - Value Activities | Tasks & Milestones (To-Go) - % of Total To-Go | Critical Path To-Go | Score
0.59 | 99 | 4 | 100
| 88% | 4%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Activities | BEI - Value Activities | 0.59 |  | 0.74
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Tasks & Milestones (To-Go) - % of Total To-Go | Tasks & Milestones (To-Go) - % of Total To-Go | 99 | 88% | 106 | 87%
The total number of activities within a grouping. Percentage shows total to-go (planned and in-progress) tasks and milestones out of all activities (normal, milestone, summary, and LOE).
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Path To-Go | Critical Path To-Go | 4 | 4% | 41 | 39%
Normal activities and milestones that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned

## NASA-Metrics
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA Metrics
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
NASA Metrics
|  | Status & Quality | Performance | Schedule Errors | Schedule Warnings | Critical Path
Ribbons | Project2 | 59 | 67.1071 | 97 | 62 | 0
Ribbons | Project5_TAMPERED | 59.5714 | 66.1429 | 96 | 69 | 24
Status & Quality
|  | Status - Characteristics | Status - New Activities (Snapshot) | Quality - Construction | Quality - Duration | Quality - Constraints | Quality - Logic | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Successors
Ribbons | Project2 | 100 | N/A | 100 | 0 | 26 | 70 | 28 | 89
Ribbons | Project5_TAMPERED | 100 | N/A | 100 | 0 | 31 | 65 | 33 | 88
Performance
|  | Performance - Completed | Performance - In-Progress | Performance - Planned/Future | Performance - Baseline Compliance | Performance - Float | Performance - Critical Path | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline_Additional Metrics | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Incomplete - Old & New | Baseline Execution Index (BEI) | Hit or Miss Index (HMI) | Current Execution Index (CEI) | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Values Adjusted | DRM | Tracking Dates | Margin Duration | Margin Date | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | BEI, HMI, CEI - Values | BEI, HMI, CEI - Critical Path
Ribbons | Project2 | 0 | 0 | 0 | 96 | 69 | 0 | 90 | 90 | 90 | 72 | 0 | 0 | 100 | 100 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | N/A | 100 | 100 | 100 | 100 | 72 | N/A | 100
Ribbons | Project5_TAMPERED | 0 | 0 | 0 | 91 | 69 | 0 | 86 | 86 | 86 | 67 | 0 | 0 | 100 | 100 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | N/A | 100 | 100 | 100 | 100 | 67 | N/A | 100
|  | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors
|  | Wrong Status | Invalid Forecast Dates | Expected Finish | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | Score
Ribbons | Project2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-24 | 97
Ribbons |  | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Ribbons | Project5_TAMPERED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 96
Ribbons |  | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 1% | 0% | 0%
|  | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings
|  | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Riding Data Date | Deadlines | Score
Ribbons | Project2 | 39 | 44 | 41 | 0 | 1 | 1 | 3 | 0 | 8 | 0 | 0 | 0 | 62
Ribbons |  | 37% | 42% | 39% | 0% | 1% | 2% | 3% | 0% | 8% | 0% | 0% | 0%
Ribbons | Project5_TAMPERED | 41 | 44 | 4 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 69
Ribbons |  | 41% | 44% | 4% | 0% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | 0%
|  | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path
|  | Longest Path (Normal Tasks) | Longest Path (Tasks & Milestones) | Critical Milestone-to-Task Ratio (To-Go) | Critical Milestones (To-Go) | Longest Path (Milestones) | Normal Tasks | Normal Tasks (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Zero Days Float | Negative Float | CP Logic Density™ | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Score
Ribbons | Project2 | 41 | 41 | N/A | 0 | 0 | 126 | 106 | 41 | 1 | 41 | 0 | 3.2 | 0 | 0 | 0
Ribbons |  | 87% | 87% | 0 | ( N/A ) | 0% | 88% | 87% | 39% | 2% | 39% | 0% |  | 0% | 0%
Ribbons | Project5_TAMPERED | 4 | 4 | N/A | 0 | 0 | 126 | 99 | 4 | 0 | 4 | 0 | 3 | 1 | 34 | 24
Ribbons |  | 100% | 100% | 0 | ( N/A ) | 0% | 88% | 88% | 4% | 0% | 4% | 0% |  | 1% | 24%

## NASA-Metrics-Status---Quality
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA Metrics Status & Quality
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Status & Quality
|  | Status - Characteristics | Status - New Activities (Snapshot) | Quality - Construction | Quality - Duration | Quality - Constraints | Quality - Logic | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Successors
Ribbons | Project2 | 100 | N/A | 100 | 0 | 26 | 70 | 28 | 89
Ribbons | Project5_TAMPERED | 100 | N/A | 100 | 0 | 31 | 65 | 33 | 88
|  | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics
|  | Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Riding Data Date | Score
Ribbons | Project2 | 2026-05-24 | 144 | 0 | 126 | 18 | 0 | 0 | 126 | 20 | 0 | 20 | 122 | 106 | 0 | 106 | 16 | 0 | 0 | 41 | 41 | 0 | 0 | 100
Ribbons |  |  |  | 0% | 88% | 13% | 0% | 0% | 88% | 16% | ( N/A ) | 16% | 85% | 87% | 0% | 87% | 13% | 0% | 0% | 87% | 87% | 0% | 0%
Ribbons | Project5_TAMPERED | 2026-08-27 | 144 | 0 | 126 | 18 | 0 | 0 | 126 | 27 | 0 | 27 | 113 | 99 | 0 | 99 | 14 | 0 | 0 | 4 | 4 | 0 | 0 | 100
Ribbons |  |  |  | 0% | 88% | 13% | 0% | 0% | 88% | 21% | ( N/A ) | 21% | 78% | 88% | 0% | 88% | 12% | 0% | 0% | 100% | 100% | 0% | 0%
|  | Status - New Activities (Snapshot) | Status - New Activities (Snapshot)
|  | Status Date | Score
Ribbons | Project2 | 2026-05-24 | N/A
Ribbons
Ribbons | Project5_TAMPERED | 2026-08-27 | N/A
Ribbons
|  | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction
|  | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Summary-to-Task Ratio (To-Go) | Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | Manual Tasks (To-Go) | Critical Tasks and Milestones (To-Go) | Wrong Status (To-Go) | Invalid Forecast Dates | Missing WBS (To-Go) | All Activities (To Go) | Score
Ribbons | Project2 | 122 | 106 | 1:07 | N/A | N/A | 0 | 41 | 0 | 0 | 0 | 106 | 100
Ribbons |  | 85% | 87% | 0.15 | 0 | 0 | 0% | 39% | 0% | 0% | 0% | 100%
Ribbons | Project5_TAMPERED | 113 | 99 | 1:07 | N/A | N/A | 0 | 4 | 0 | 0 | 0 | 99 | 100
Ribbons |  | 78% | 88% | 0.14 | 0 | 0 | 0% | 4% | 0% | 0% | 0% | 100%
|  | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration
|  | Tasks & Milestones (To-Go) - % of Total To-Go | Estimated Duration | Milestones with Duration>0 | Activities with Duration=0 | Avg. Original Duration | Avg. Remaining Duration | High Baseline Duration (44d) | High Planned Duration (44d) | Insufficient Detail™ | Critical Activities (To-Go) | Avg. Critical Original Duration | Avg. Critical Remaining Duration | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical w/Insufficient Detail™ | Activities (To-Go) | Score
Ribbons | Project2 | 106 | 0 | 0 | 0 | 9 | 9 | 1 | 1 | 1 | 41 | 9 | 8 | 0 | 0 | 0 | 106 | 0
Ribbons |  | 87% | 0% | ( N/A ) | 0% |  |  | 1% | 1% | 1% | 39% |  |  | 0% | 0% | 0% | 84%
Ribbons | Project5_TAMPERED | 99 | 0 | 0 | 0 | 10 | 9 | 0 | 0 | 0 | 4 | 8 | 8 | 0 | 0 | 0 | 99 | 0
Ribbons |  | 88% | 0% | ( N/A ) | 0% |  |  | 0% | 0% | 0% | 4% |  |  | 0% | 0% | 0% | 79%
|  | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints
|  | Total Constraints | Start No Earlier Than | Start No Later Than | Finish No Earlier Than | Finish No Later Than | Hard Constraints | Must Start On | Must Finish On | As Late As Possible | Deadlines | Mandatory Start | Mandatory Finish | Open Ends with Constraints | Open Ends w/o Constraints | Unsatisfied Constraints | No Constraints | No Constraints | Score
Ribbons | Project2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 105 | 105 | 26
Ribbons |  | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4% | 0% | 99% | 99%
Ribbons | Project5_TAMPERED | 3 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 5 | 0 | 96 | 96 | 31
Ribbons |  | 3% | 2% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 5% | 0% | 97% | 97%
|  | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic
|  | Logic Density™ | Logic Density™ - Predecessors | Logic Density™ - Successors | Summary Links | All Activities w/Predecessors | SS Predecessors | SF Predecessors | FF Predecessors | FS Predecessors | All Activities w/Successors | SS Successors | FF Successors | SF Successors | FS Successors | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Score
Ribbons | Project2 | 2.81 | 1.45 | 1.36 | 0 | 103 | 0 | 0 | 1 | 106 | 102 | 0 | 0 | 0 | 102 | 4 | 0 | 4 | 0 | 0 | 70
Ribbons |  |  |  |  | 0% | 100% | 0% | 0% | 1% | 100% | 96% | 0% | 0% | 0% | 96% | 4% | 0% | 4% | 0% | 0%
Ribbons | Project5_TAMPERED | 2.86 | 1.48 | 1.37 | 0 | 97 | 0 | 0 | 0 | 99 | 94 | 0 | 0 | 0 | 94 | 5 | 0 | 5 | 0 | 0 | 65
Ribbons |  |  |  |  | 0% | 100% | 0% | 0% | 0% | 100% | 95% | 0% | 0% | 0% | 95% | 5% | 0% | 5% | 0% | 0%
|  | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors
|  | Logic Density™ - Predecessors | All Activities w/Predecessors | Total # Predecessors | Activities Missing Predecessors | Activities w/Leads on Predecessor | Total # Predecessor Leads | Max # Predecessor Leads on an Activity | Activities w/Lags on Predecessor | Total # Predecessor Lags | Max # of Predecessor Lags on an Activity | Min Predecessor Lag (days) | Max Predecessor Lag (days) | Hidden Duration (Planned) | Critical w/Hidden Duration (Planned) | Merge Hotspot (Predecessors >2) | Merge Hotspot w/Predecessor Lags | Merge Hotspot w/Predecessor Lags & Low Total Float | Critical Merge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Score
Ribbons | Project2 | 1.47 | 103 | 151 | 0 | 0 | N/A | N/A | 2 | 2 | 1 | 0 | 5 | 1 | 0 | 10 | 0 | 0 | 3 | 1 | 1 | 28
Ribbons |  |  | 100% |  | 0% | 0% |  |  | 2% |  |  |  |  | 1% | 0% | 10% | 0% | 0% | 3% | 1% | 2%
Ribbons | Project5_TAMPERED | 1.49 | 97 | 145 | 0 | 0 | N/A | N/A | 1 | 1 | 1 | 0 | 5 | 1 | 0 | 10 | 0 | N/A | 1 | 1 | 0 | 33
Ribbons |  |  | 100% |  | 0% | 0% |  |  | 1% |  |  |  |  | 1% | 0% | 10% | 0% | ( N/A ) | 1% | 1% | 0%
|  | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors
|  | Logic Density™ - Successors | All Activities w/Successors | Activities Missing Successors | Total # Successors | Activities w/Leads on Successor | Total# of Successor Leads | Max # of Successor Leads on Activity | Activities w/Lags on Successor | Total# of Successor Lags | Max # of Successor Lags on Activity | Diverge Hotspot (Successors >2) | Diverge Hotspot w/Successor Lags | Diverge Hotspot w/Successor Lags & Low Total Float | Critical Diverge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Score
Ribbons | Project2 | 1.36 | 102 | 4 | 144 | 0 | N/A | N/A | 1 | 1 | 1 | 11 | 0 | 0 | 8 | 1 | 1 | 89
Ribbons |  |  | 100% | 4% |  | 0% |  |  | 1% |  |  | 10% | 0% | 0% | 8% | 1% | 2%
Ribbons | Project5_TAMPERED | 1.37 | 94 | 5 | 136 | 0 | N/A | N/A | 1 | 1 | 1 | 11 | 0 | N/A | 0 | 1 | 0 | 88
Ribbons |  |  | 100% | 5% |  | 0% |  |  | 1% |  |  | 11% | 0% | ( N/A ) | 0% | 1% | 0%

## NASA-Metrics-Status---Quality-
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics
Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Riding Data Date | Score
2026-08-27 | 144 | 0 | 126 | 18 | 0 | 0 | 126 | 27 | 0 | 27 | 113 | 99 | 0 | 99 | 14 | 0 | 0 | 4 | 4 | 0 | 0 | 100
|  | 0% | 88% | 13% | 0% | 0% | 88% | 21% | ( N/A ) | 21% | 78% | 88% | 0% | 88% | 12% | 0% | 0% | 100% | 100% | 0% | 0%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total Activities | Total Activities | 144 |  | 144
The total number of activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 2 | General Conditions | Project5_TAMPERED | Standard | 46 | 0 | 2026-03-02 | 2026-05-04 | 2026-03-02 | 2026-04-01 | Summary | Complete | 0
FALSE |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | Standard | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | Standard | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE |  | 100 |  | 18 | Mobilize on Site | Project5_TAMPERED | Standard | 17 | 0 | 2026-03-05 | 2026-03-27 | 2026-03-05 | 2026-03-18 | Summary | Complete | 0
FALSE |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 10 | Long Lead Procurement | Project5_TAMPERED | Standard | 76 | 0 | 2026-03-06 | 2026-06-19 | 2026-03-06 | 2026-06-11 | Summary | Complete | 0
FALSE |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | Standard | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | Standard | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | Standard | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | Standard | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE |  | 100 |  | 24 | Site Grading and Utilities | Project5_TAMPERED | Standard | 85 | 0 | 2026-04-06 | 2026-07-31 | 2026-03-19 | 2026-05-06 | Summary | Complete | 0
FALSE |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | Standard | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | Standard | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | Standard | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | Standard | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | Standard | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | Standard | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | Standard | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | Standard | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE |  | 28 |  | 32 | Foundations | Project5_TAMPERED | Standard | 92 | 66 | 2026-08-03 | 2026-12-08 | 2026-05-07 | 2026-07-08 | Summary | InProgress | 256
FALSE |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | Standard | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 47 | Steel Erection | Project5_TAMPERED | Standard | 74 | 74 | 2026-11-09 | 2027-02-18 | 2026-06-23 | 2026-08-31 | Summary | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 54 | Form and Pour Concrete - Floors and Roof | Project5_TAMPERED | Standard | 89 | 89 | 2026-12-16 | 2027-04-19 | 2026-07-07 | 2026-11-04 | Summary | Planned | 44
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 79 | Masonry Work | Project5_TAMPERED | Standard | 86 | 86 | 2027-02-19 | 2027-06-18 | 2026-09-01 | 2027-01-05 | Summary | Planned | 74
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 110 | Elevators | Project5_TAMPERED | Standard | 40 | 40 | 2027-03-19 | 2027-05-13 | 2026-09-29 | 2026-11-23 | Summary | Planned | 184
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 126 | Heating and Ventilating - AC | Project5_TAMPERED | Standard | 210 | 210 | 2027-03-19 | 2028-01-06 | 2026-09-29 | 2027-06-16 | Summary | Planned | 14
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 77 | Carpentry Work | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Summary | Planned | 19
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 119 | Electrical | Project5_TAMPERED | Standard | 140 | 140 | 2027-04-20 | 2027-11-01 | 2026-11-05 | 2027-05-19 | Summary | Planned | 38
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 87 | Roofing | Project5_TAMPERED | Standard | 33 | 33 | 2027-06-11 | 2027-07-27 | 2026-12-29 | 2027-02-11 | Summary | Planned | 80
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 93 | Window wall and store front closures | Project5_TAMPERED | Standard | 75 | 75 | 2027-06-11 | 2027-09-23 | 2026-12-29 | 2027-04-12 | Summary | Planned | 19
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 114 | Plumbing | Project5_TAMPERED | Standard | 100 | 100 | 2027-06-18 | 2027-11-04 | 2027-01-05 | 2027-05-24 | Summary | Planned | 35
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 98 | Building Finishes | Project5_TAMPERED | Standard | 111 | 111 | 2027-07-16 | 2027-12-17 | 2027-02-02 | 2027-06-07 | Summary | Planned | 28
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 132 | Final Clean-up and Occupancy | Project5_TAMPERED | Standard | 76 | 76 | 2027-08-20 | 2027-12-03 | 2027-03-09 | 2027-06-14 | Summary | Planned | 38
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 137 | Complete Final Inspections | Project5_TAMPERED | Standard | 6 | 6 | 2027-12-03 | 2027-12-10 | 2027-06-14 | 2027-06-21 | Summary | Planned | 19
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestones | Milestones | 0 | 0% | 0 | 0%
Number of milestones within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | Standard | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | Standard | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | Standard | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | Standard | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | Standard | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | Standard | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | Standard | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | Standard | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | Standard | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | Standard | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | Standard | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | Standard | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | Standard | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | Standard | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | Standard | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Normal Tasks | Normal Tasks | 126 | 88% | 126 | 88%
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | Standard | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | Standard | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | Standard | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | Standard | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | Standard | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | Standard | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | Standard | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | Standard | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | Standard | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | Standard | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | Standard | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | Standard | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | Standard | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | Standard | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | Standard | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Summaries | Summaries | 18 | 13% | 18 | 13%
Number of summary activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 2 | General Conditions | Project5_TAMPERED | Standard | 46 | 0 | 2026-03-02 | 2026-05-04 | 2026-03-02 | 2026-04-01 | Summary | Complete | 0
FALSE |  | 100 |  | 18 | Mobilize on Site | Project5_TAMPERED | Standard | 17 | 0 | 2026-03-05 | 2026-03-27 | 2026-03-05 | 2026-03-18 | Summary | Complete | 0
FALSE |  | 100 |  | 10 | Long Lead Procurement | Project5_TAMPERED | Standard | 76 | 0 | 2026-03-06 | 2026-06-19 | 2026-03-06 | 2026-06-11 | Summary | Complete | 0
FALSE |  | 100 |  | 24 | Site Grading and Utilities | Project5_TAMPERED | Standard | 85 | 0 | 2026-04-06 | 2026-07-31 | 2026-03-19 | 2026-05-06 | Summary | Complete | 0
FALSE |  | 28 |  | 32 | Foundations | Project5_TAMPERED | Standard | 92 | 66 | 2026-08-03 | 2026-12-08 | 2026-05-07 | 2026-07-08 | Summary | InProgress | 256
FALSE |  | 0 |  | 47 | Steel Erection | Project5_TAMPERED | Standard | 74 | 74 | 2026-11-09 | 2027-02-18 | 2026-06-23 | 2026-08-31 | Summary | Planned | 19
FALSE |  | 0 |  | 54 | Form and Pour Concrete - Floors and Roof | Project5_TAMPERED | Standard | 89 | 89 | 2026-12-16 | 2027-04-19 | 2026-07-07 | 2026-11-04 | Summary | Planned | 44
FALSE |  | 0 |  | 79 | Masonry Work | Project5_TAMPERED | Standard | 86 | 86 | 2027-02-19 | 2027-06-18 | 2026-09-01 | 2027-01-05 | Summary | Planned | 74
FALSE |  | 0 |  | 110 | Elevators | Project5_TAMPERED | Standard | 40 | 40 | 2027-03-19 | 2027-05-13 | 2026-09-29 | 2026-11-23 | Summary | Planned | 184
FALSE |  | 0 |  | 126 | Heating and Ventilating - AC | Project5_TAMPERED | Standard | 210 | 210 | 2027-03-19 | 2028-01-06 | 2026-09-29 | 2027-06-16 | Summary | Planned | 14
FALSE |  | 0 |  | 77 | Carpentry Work | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Summary | Planned | 19
FALSE |  | 0 |  | 119 | Electrical | Project5_TAMPERED | Standard | 140 | 140 | 2027-04-20 | 2027-11-01 | 2026-11-05 | 2027-05-19 | Summary | Planned | 38
FALSE |  | 0 |  | 87 | Roofing | Project5_TAMPERED | Standard | 33 | 33 | 2027-06-11 | 2027-07-27 | 2026-12-29 | 2027-02-11 | Summary | Planned | 80
FALSE |  | 0 |  | 93 | Window wall and store front closures | Project5_TAMPERED | Standard | 75 | 75 | 2027-06-11 | 2027-09-23 | 2026-12-29 | 2027-04-12 | Summary | Planned | 19
FALSE |  | 0 |  | 114 | Plumbing | Project5_TAMPERED | Standard | 100 | 100 | 2027-06-18 | 2027-11-04 | 2027-01-05 | 2027-05-24 | Summary | Planned | 35
FALSE |  | 0 |  | 98 | Building Finishes | Project5_TAMPERED | Standard | 111 | 111 | 2027-07-16 | 2027-12-17 | 2027-02-02 | 2027-06-07 | Summary | Planned | 28
FALSE |  | 0 |  | 132 | Final Clean-up and Occupancy | Project5_TAMPERED | Standard | 76 | 76 | 2027-08-20 | 2027-12-03 | 2027-03-09 | 2027-06-14 | Summary | Planned | 38
FALSE |  | 0 |  | 137 | Complete Final Inspections | Project5_TAMPERED | Standard | 6 | 6 | 2027-12-03 | 2027-12-10 | 2027-06-14 | 2027-06-21 | Summary | Planned | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Hammocks | Hammocks | 0 | 0% | 0 | 0%
Number of hammocks within a grouping.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Recurring Normal Tasks | Recurring Normal Tasks | 0 | 0% | 0 | 0%
Tasks marked as recurring.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total Tasks & Milestones | Total Tasks & Milestones | 126 | 88% | 126 | 88%
Total number of regular tasks and milestones in the project schedule.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | Standard | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | Standard | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | Standard | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | Standard | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | Standard | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | Standard | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | Standard | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | Standard | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | Standard | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | Standard | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | Standard | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | Standard | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | Standard | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | Standard | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | Standard | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Tasks & Milestones | Completed Tasks & Milestones | 27 | 21% | 20 | 16%
Total number of completed tasks and milestones
Excluded | DRM | Baseline Duration | Actual Duration | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 1 | 3 | 3 |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE | 1 | 4 | 4 |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | Standard | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE | 1 | 1 | 1 |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | Standard | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE | 1.6 | 10 | 16 |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | Standard | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE | 1 | 3 | 3 |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE | 3.3333 | 3 | 10 |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | Standard | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE | 1 | 60 | 60 |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | Standard | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE | 2.3 | 10 | 23 |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | Standard | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE | 1 | 3 | 3 |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | Standard | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | Standard | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE | 1 | 5 | 5 |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | Standard | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE | 2 | 10 | 20 |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | Standard | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE | 4.3 | 10 | 43 |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | Standard | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE | 1.9 | 10 | 19 |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | Standard | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 0.9 | 10 | 9 |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | Standard | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE | 4 | 5 | 20 |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | Standard | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE | 0.5 | 10 | 5 |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | Standard | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Milestones | Completed Milestones | 0 |  | 0
Total number of completed milestones.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Tasks | Completed Tasks | 27 | 21% | 20 | 16%
Total number of completed tasks
Excluded | DRM | Baseline Duration | Actual Duration | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 1 | 3 | 3 |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE | 1 | 4 | 4 |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | Standard | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE | 1 | 1 | 1 |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | Standard | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE | 1.6 | 10 | 16 |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | Standard | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE | 1 | 3 | 3 |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE | 3.3333 | 3 | 10 |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | Standard | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE | 1 | 60 | 60 |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | Standard | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE | 2.3 | 10 | 23 |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | Standard | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE | 1 | 3 | 3 |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | Standard | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE | 1 | 2 | 2 |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | Standard | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE | 1 | 5 | 5 |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | Standard | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE | 2 | 10 | 20 |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | Standard | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE | 4.3 | 10 | 43 |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | Standard | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE | 1.9 | 10 | 19 |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | Standard | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 0.9 | 10 | 9 |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | Standard | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE | 1 | 10 | 10 |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE | 4 | 5 | 20 |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | Standard | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE | 0.5 | 10 | 5 |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | Standard | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total Activities (To-Go) - % of Total | Total Activities (To-Go) - % of Total | 113 | 78% | 122 | 85%
The total number of activities within a grouping. Percentage shows total total to-go (planned and in-progress) activities (normal, milestone, summary and LOE) out of total to-go and completed activities.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 28 |  | 32 | Foundations | Project5_TAMPERED | Standard | 92 | 66 | 2026-08-03 | 2026-12-08 | 2026-05-07 | 2026-07-08 | Summary | InProgress | 256
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 47 | Steel Erection | Project5_TAMPERED | Standard | 74 | 74 | 2026-11-09 | 2027-02-18 | 2026-06-23 | 2026-08-31 | Summary | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 54 | Form and Pour Concrete - Floors and Roof | Project5_TAMPERED | Standard | 89 | 89 | 2026-12-16 | 2027-04-19 | 2026-07-07 | 2026-11-04 | Summary | Planned | 44
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 79 | Masonry Work | Project5_TAMPERED | Standard | 86 | 86 | 2027-02-19 | 2027-06-18 | 2026-09-01 | 2027-01-05 | Summary | Planned | 74
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 110 | Elevators | Project5_TAMPERED | Standard | 40 | 40 | 2027-03-19 | 2027-05-13 | 2026-09-29 | 2026-11-23 | Summary | Planned | 184
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 126 | Heating and Ventilating - AC | Project5_TAMPERED | Standard | 210 | 210 | 2027-03-19 | 2028-01-06 | 2026-09-29 | 2027-06-16 | Summary | Planned | 14
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 77 | Carpentry Work | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Summary | Planned | 19
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 119 | Electrical | Project5_TAMPERED | Standard | 140 | 140 | 2027-04-20 | 2027-11-01 | 2026-11-05 | 2027-05-19 | Summary | Planned | 38
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 87 | Roofing | Project5_TAMPERED | Standard | 33 | 33 | 2027-06-11 | 2027-07-27 | 2026-12-29 | 2027-02-11 | Summary | Planned | 80
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 93 | Window wall and store front closures | Project5_TAMPERED | Standard | 75 | 75 | 2027-06-11 | 2027-09-23 | 2026-12-29 | 2027-04-12 | Summary | Planned | 19
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 114 | Plumbing | Project5_TAMPERED | Standard | 100 | 100 | 2027-06-18 | 2027-11-04 | 2027-01-05 | 2027-05-24 | Summary | Planned | 35
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 98 | Building Finishes | Project5_TAMPERED | Standard | 111 | 111 | 2027-07-16 | 2027-12-17 | 2027-02-02 | 2027-06-07 | Summary | Planned | 28
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 132 | Final Clean-up and Occupancy | Project5_TAMPERED | Standard | 76 | 76 | 2027-08-20 | 2027-12-03 | 2027-03-09 | 2027-06-14 | Summary | Planned | 38
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 137 | Complete Final Inspections | Project5_TAMPERED | Standard | 6 | 6 | 2027-12-03 | 2027-12-10 | 2027-06-14 | 2027-06-21 | Summary | Planned | 19
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Tasks & Milestones (To-Go) - % of Total To-Go | Tasks & Milestones (To-Go) - % of Total To-Go | 99 | 88% | 106 | 87%
The total number of activities within a grouping. Percentage shows total to-go (planned and in-progress) tasks and milestones out of all activities (normal, milestone, summary, and LOE).
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestones (To-Go) | Milestones (To-Go) | 0 | 0% | 0 | 0%
Number of milestones within a grouping.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Normal Tasks (To-Go) | Normal Tasks (To-Go) | 99 | 88% | 106 | 87%
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Summaries (To-Go) | Summaries (To-Go) | 14 | 12% | 16 | 13%
Number of summary activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 28 |  | 32 | Foundations | Project5_TAMPERED | Standard | 92 | 66 | 2026-08-03 | 2026-12-08 | 2026-05-07 | 2026-07-08 | Summary | InProgress | 256
FALSE |  | 0 |  | 47 | Steel Erection | Project5_TAMPERED | Standard | 74 | 74 | 2026-11-09 | 2027-02-18 | 2026-06-23 | 2026-08-31 | Summary | Planned | 19
FALSE |  | 0 |  | 54 | Form and Pour Concrete - Floors and Roof | Project5_TAMPERED | Standard | 89 | 89 | 2026-12-16 | 2027-04-19 | 2026-07-07 | 2026-11-04 | Summary | Planned | 44
FALSE |  | 0 |  | 79 | Masonry Work | Project5_TAMPERED | Standard | 86 | 86 | 2027-02-19 | 2027-06-18 | 2026-09-01 | 2027-01-05 | Summary | Planned | 74
FALSE |  | 0 |  | 110 | Elevators | Project5_TAMPERED | Standard | 40 | 40 | 2027-03-19 | 2027-05-13 | 2026-09-29 | 2026-11-23 | Summary | Planned | 184
FALSE |  | 0 |  | 126 | Heating and Ventilating - AC | Project5_TAMPERED | Standard | 210 | 210 | 2027-03-19 | 2028-01-06 | 2026-09-29 | 2027-06-16 | Summary | Planned | 14
FALSE |  | 0 |  | 77 | Carpentry Work | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Summary | Planned | 19
FALSE |  | 0 |  | 119 | Electrical | Project5_TAMPERED | Standard | 140 | 140 | 2027-04-20 | 2027-11-01 | 2026-11-05 | 2027-05-19 | Summary | Planned | 38
FALSE |  | 0 |  | 87 | Roofing | Project5_TAMPERED | Standard | 33 | 33 | 2027-06-11 | 2027-07-27 | 2026-12-29 | 2027-02-11 | Summary | Planned | 80
FALSE |  | 0 |  | 93 | Window wall and store front closures | Project5_TAMPERED | Standard | 75 | 75 | 2027-06-11 | 2027-09-23 | 2026-12-29 | 2027-04-12 | Summary | Planned | 19
FALSE |  | 0 |  | 114 | Plumbing | Project5_TAMPERED | Standard | 100 | 100 | 2027-06-18 | 2027-11-04 | 2027-01-05 | 2027-05-24 | Summary | Planned | 35
FALSE |  | 0 |  | 98 | Building Finishes | Project5_TAMPERED | Standard | 111 | 111 | 2027-07-16 | 2027-12-17 | 2027-02-02 | 2027-06-07 | Summary | Planned | 28
FALSE |  | 0 |  | 132 | Final Clean-up and Occupancy | Project5_TAMPERED | Standard | 76 | 76 | 2027-08-20 | 2027-12-03 | 2027-03-09 | 2027-06-14 | Summary | Planned | 38
FALSE |  | 0 |  | 137 | Complete Final Inspections | Project5_TAMPERED | Standard | 6 | 6 | 2027-12-03 | 2027-12-10 | 2027-06-14 | 2027-06-21 | Summary | Planned | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Hammocks (To-Go) | Hammocks (To-Go) | 0 | 0% | 0 | 0%
Number of hammocks within a grouping.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Recurring Tasks (To-Go) | Recurring Tasks (To-Go) | 0 | 0% | 0 | 0%
Tasks marked recurring that are in progress or planned (future).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Longest Path (Tasks & Milestones) | Longest Path (Tasks & Milestones) | 4 | 100% | 41 | 87%
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Longest Path (Normal Tasks) | Longest Path (Normal Tasks) | 4 | 100% | 41 | 87%
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Longest Path (Milestones) | Longest Path (Milestones) | 0 | 0% | 0 | 0%
Activities that together form the longest path through to project completion.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Riding Data Date | Riding Data Date | 0 | 0% | 0 | 0%
Number of planned activities that have a start date that is the same as the project data date (Time Now)

## NASA-Metrics-Status---Quality-2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Status - New Activities (Snapshot) | Status - New Activities (Snapshot)
Status Date | Score
2026-08-27 | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Status---Quality-3
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction
Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Summary-to-Task Ratio (To-Go) | Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | Manual Tasks (To-Go) | Critical Tasks and Milestones (To-Go) | Wrong Status (To-Go) | Invalid Forecast Dates | Missing WBS (To-Go) | All Activities (To Go) | Score
113 | 99 | 1:07 | N/A | N/A | 0 | 4 | 0 | 0 | 0 | 99 | 100
78% | 88% | 0.14 | 0 | 0 | 0% | 4% | 0% | 0% | 0% | 100%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total Activities (To-Go) - % of Total | Total Activities (To-Go) - % of Total | 113 | 78% | 122 | 85%
The total number of activities within a grouping. Percentage shows total total to-go (planned and in-progress) activities (normal, milestone, summary and LOE) out of total to-go and completed activities.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 28 |  | 32 | Foundations | Project5_TAMPERED | Standard | 92 | 66 | 2026-08-03 | 2026-12-08 | 2026-05-07 | 2026-07-08 | Summary | InProgress | 256
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 47 | Steel Erection | Project5_TAMPERED | Standard | 74 | 74 | 2026-11-09 | 2027-02-18 | 2026-06-23 | 2026-08-31 | Summary | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 54 | Form and Pour Concrete - Floors and Roof | Project5_TAMPERED | Standard | 89 | 89 | 2026-12-16 | 2027-04-19 | 2026-07-07 | 2026-11-04 | Summary | Planned | 44
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 79 | Masonry Work | Project5_TAMPERED | Standard | 86 | 86 | 2027-02-19 | 2027-06-18 | 2026-09-01 | 2027-01-05 | Summary | Planned | 74
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 110 | Elevators | Project5_TAMPERED | Standard | 40 | 40 | 2027-03-19 | 2027-05-13 | 2026-09-29 | 2026-11-23 | Summary | Planned | 184
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 126 | Heating and Ventilating - AC | Project5_TAMPERED | Standard | 210 | 210 | 2027-03-19 | 2028-01-06 | 2026-09-29 | 2027-06-16 | Summary | Planned | 14
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 77 | Carpentry Work | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Summary | Planned | 19
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 119 | Electrical | Project5_TAMPERED | Standard | 140 | 140 | 2027-04-20 | 2027-11-01 | 2026-11-05 | 2027-05-19 | Summary | Planned | 38
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 87 | Roofing | Project5_TAMPERED | Standard | 33 | 33 | 2027-06-11 | 2027-07-27 | 2026-12-29 | 2027-02-11 | Summary | Planned | 80
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 93 | Window wall and store front closures | Project5_TAMPERED | Standard | 75 | 75 | 2027-06-11 | 2027-09-23 | 2026-12-29 | 2027-04-12 | Summary | Planned | 19
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 114 | Plumbing | Project5_TAMPERED | Standard | 100 | 100 | 2027-06-18 | 2027-11-04 | 2027-01-05 | 2027-05-24 | Summary | Planned | 35
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 98 | Building Finishes | Project5_TAMPERED | Standard | 111 | 111 | 2027-07-16 | 2027-12-17 | 2027-02-02 | 2027-06-07 | Summary | Planned | 28
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 132 | Final Clean-up and Occupancy | Project5_TAMPERED | Standard | 76 | 76 | 2027-08-20 | 2027-12-03 | 2027-03-09 | 2027-06-14 | Summary | Planned | 38
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 137 | Complete Final Inspections | Project5_TAMPERED | Standard | 6 | 6 | 2027-12-03 | 2027-12-10 | 2027-06-14 | 2027-06-21 | Summary | Planned | 19
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Tasks & Milestones (To-Go) - % of Total To-Go | Tasks & Milestones (To-Go) - % of Total To-Go | 99 | 88% | 106 | 87%
The total number of activities within a grouping. Percentage shows total to-go (planned and in-progress) tasks and milestones out of all activities (normal, milestone, summary, and LOE).
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Summary-to-Task Ratio (To-Go) | Summary-to-Task Ratio (To-Go) | 1:07 | 0.14 | 1:07 | 0.15
Ratio of the number of summary to the number of normal activities. Should not be less than 1:20.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestone-to-Task Ratio (To-Go) | Milestone-to-Task Ratio (To-Go) | N/A | 0 | N/A | 0
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | N/A | 0 | N/A | 0
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Manual Tasks (To-Go) | Manual Tasks (To-Go) | 0 | 0% | 0 | 0%
Tasks marked for manual calculation in Microsoft Project 2010 and higher
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Tasks and Milestones (To-Go) | Critical Tasks and Milestones (To-Go) | 4 | 4% | 41 | 39%
Number of critical activities to-go.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Wrong Status (To-Go) | Wrong Status (To-Go) | 0 | 0% | 0 | 0%
Number of activities that have been statused into the future.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Invalid Forecast Dates | Invalid Forecast Dates | 0 | 0% | 0 | 0%
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missing WBS (To-Go) | Missing WBS (To-Go) | 0 | 0% | 0 | 0%
Number of activities that are missing WBS values.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
All Activities (To Go) | All Activities (To Go) | 99 | 100% | 106 | 100%
The total number of activities within a grouping that have predecessors.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0

## NASA-Metrics-Status---Quality-4
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration
Tasks & Milestones (To-Go) - % of Total To-Go | Estimated Duration | Milestones with Duration>0 | Activities with Duration=0 | Avg. Original Duration | Avg. Remaining Duration | High Baseline Duration (44d) | High Planned Duration (44d) | Insufficient Detail™ | Critical Activities (To-Go) | Avg. Critical Original Duration | Avg. Critical Remaining Duration | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical w/Insufficient Detail™ | Activities (To-Go) | Score
99 | 0 | 0 | 0 | 10 | 9 | 0 | 0 | 0 | 4 | 8 | 8 | 0 | 0 | 0 | 99 | 0
88% | 0% | ( N/A ) | 0% |  |  | 0% | 0% | 0% | 4% |  |  | 0% | 0% | 0% | 79%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Tasks & Milestones (To-Go) - % of Total To-Go | Tasks & Milestones (To-Go) - % of Total To-Go | 99 | 88% | 106 | 87%
The total number of activities within a grouping. Percentage shows total to-go (planned and in-progress) tasks and milestones out of all activities (normal, milestone, summary, and LOE).
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Estimated Duration | Estimated Duration | 0 | 0% | 0 | 0%
Tasks with estimated duration in Microsoft Project. This condition occurs when an original duration has not been entered by the user.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestones with Duration>0 | Milestones with Duration>0 | 0 |  | 0
Milestones with a duration greater than 0 days.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Activities with Duration=0 | Activities with Duration=0 | 0 | 0% | 0 | 0%
Activities that have an original duration of 0 days.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg. Original Duration | Avg. Original Duration | 10 |  | 9
Average planned or original duration of all normal activities and milestones within a grouping.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg. Remaining Duration | Avg. Remaining Duration | 9 |  | 9
Average remaining duration of all normal activities and milestones within a grouping.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
High Baseline Duration (44d) | High Baseline Duration (44d) | 0 | 0% | 1 | 1%
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
High Planned Duration (44d) | High Planned Duration (44d) | 0 | 0% | 1 | 1%
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Insufficient Detail™ | Insufficient Detail™ | 0 | 0% | 1 | 1%
Number of activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Activities (To-Go) | Critical Activities (To-Go) | 4 | 4% | 41 | 39%
Number of critical activities
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg. Critical Original Duration | Avg. Critical Original Duration | 8 |  | 9
Average planned or original duration of all critical activities within a grouping.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg. Critical Remaining Duration | Avg. Critical Remaining Duration | 8 |  | 8
Average remaining duration of all normal activities and milestones within a grouping.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical w/High Baseline Duration (44d) | Critical w/High Baseline Duration (44d) | 0 | 0% | 0 | 0%
Total number of critical activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 2 | General Conditions | Project5_TAMPERED | 23 | 46 | 0 | 2026-03-02 | 2026-05-04 | 2026-03-02 | 2026-04-01 | Summary | Complete | 100 | 0
FALSE |  |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  |  | 18 | Mobilize on Site | Project5_TAMPERED | 10 | 17 | 0 | 2026-03-05 | 2026-03-27 | 2026-03-05 | 2026-03-18 | Summary | Complete | 100 | 0
FALSE |  |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  |  | 10 | Long Lead Procurement | Project5_TAMPERED | 70 | 76 | 0 | 2026-03-06 | 2026-06-19 | 2026-03-06 | 2026-06-11 | Summary | Complete | 100 | 0
FALSE |  |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 10 | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  |  | 21 | Set up site office | Project5_TAMPERED | 3 | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 3 | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 10 | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  |  | 24 | Site Grading and Utilities | Project5_TAMPERED | 35 | 85 | 0 | 2026-04-06 | 2026-07-31 | 2026-03-19 | 2026-05-06 | Summary | Complete | 100 | 0
FALSE |  |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  |  | 28 | Install storm drainage | Project5_TAMPERED | 10 | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 10 | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 10 | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 10 | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 5 | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  |  | 32 | Foundations | Project5_TAMPERED | 45 | 92 | 66 | 2026-08-03 | 2026-12-08 | 2026-05-07 | 2026-07-08 | Summary | InProgress | 28 | 256
FALSE |  |  | 33 | Excavate foundations | Project5_TAMPERED | 10 | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  |  | 34 | Excavate elevator pit | Project5_TAMPERED | 2 | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 4 | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 5 | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  |  | 47 | Steel Erection | Project5_TAMPERED | 50 | 74 | 74 | 2026-11-09 | 2027-02-18 | 2026-06-23 | 2026-08-31 | Summary | Planned | 0 | 19
FALSE |  |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 10 | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  |  | 54 | Form and Pour Concrete - Floors and Roof | Project5_TAMPERED | 87 | 89 | 89 | 2026-12-16 | 2027-04-19 | 2026-07-07 | 2026-11-04 | Summary | Planned | 0 | 44
FALSE |  |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 10 | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 5 | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  |  | 79 | Masonry Work | Project5_TAMPERED | 91 | 86 | 86 | 2027-02-19 | 2027-06-18 | 2026-09-01 | 2027-01-05 | Summary | Planned | 0 | 74
FALSE |  |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  |  | 110 | Elevators | Project5_TAMPERED | 40 | 40 | 40 | 2027-03-19 | 2027-05-13 | 2026-09-29 | 2026-11-23 | Summary | Planned | 0 | 184
FALSE |  |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  |  | 126 | Heating and Ventilating - AC | Project5_TAMPERED | 187 | 210 | 210 | 2027-03-19 | 2028-01-06 | 2026-09-29 | 2027-06-16 | Summary | Planned | 0 | 14
FALSE |  |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  |  | 77 | Carpentry Work | Project5_TAMPERED | 15 | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Summary | Planned | 0 | 19
FALSE |  |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  |  | 119 | Electrical | Project5_TAMPERED | 140 | 140 | 140 | 2027-04-20 | 2027-11-01 | 2026-11-05 | 2027-05-19 | Summary | Planned | 0 | 38
FALSE |  |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  |  | 87 | Roofing | Project5_TAMPERED | 33 | 33 | 33 | 2027-06-11 | 2027-07-27 | 2026-12-29 | 2027-02-11 | Summary | Planned | 0 | 80
FALSE |  |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  |  | 93 | Window wall and store front closures | Project5_TAMPERED | 75 | 75 | 75 | 2027-06-11 | 2027-09-23 | 2026-12-29 | 2027-04-12 | Summary | Planned | 0 | 19
FALSE |  |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  |  | 114 | Plumbing | Project5_TAMPERED | 100 | 100 | 100 | 2027-06-18 | 2027-11-04 | 2027-01-05 | 2027-05-24 | Summary | Planned | 0 | 35
FALSE |  |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  |  | 98 | Building Finishes | Project5_TAMPERED | 90 | 111 | 111 | 2027-07-16 | 2027-12-17 | 2027-02-02 | 2027-06-07 | Summary | Planned | 0 | 28
FALSE |  |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  |  | 132 | Final Clean-up and Occupancy | Project5_TAMPERED | 70 | 76 | 76 | 2027-08-20 | 2027-12-03 | 2027-03-09 | 2027-06-14 | Summary | Planned | 0 | 38
FALSE |  |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  |  | 106 | Install building carpet | Project5_TAMPERED | 20 | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  |  | 107 | Install hardware and accessories | Project5_TAMPERED | 15 | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  |  | 137 | Complete Final Inspections | Project5_TAMPERED | 6 | 6 | 6 | 2027-12-03 | 2027-12-10 | 2027-06-14 | 2027-06-21 | Summary | Planned | 0 | 19
FALSE |  |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical w/High Planned Duration (44d) | Critical w/High Planned Duration (44d) | 0 | 0% | 0 | 0%
Number of critical activities with a duration longer than 44 days.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical w/Insufficient Detail™ | Critical w/Insufficient Detail™ | 0 | 0% | 0 | 0%
Number of critical activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Activities (To-Go) | Activities (To-Go) | 99 | 79% | 106 | 84%
The total number of activities within a grouping.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 10 | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  |  | 21 | Set up site office | Project5_TAMPERED | 3 | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 3 | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 10 | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  |  | 28 | Install storm drainage | Project5_TAMPERED | 10 | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 10 | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 10 | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 10 | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 5 | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  |  | 33 | Excavate foundations | Project5_TAMPERED | 10 | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  |  | 34 | Excavate elevator pit | Project5_TAMPERED | 2 | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 4 | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 5 | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 10 | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 10 | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 5 | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  |  | 106 | Install building carpet | Project5_TAMPERED | 20 | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  |  | 107 | Install hardware and accessories | Project5_TAMPERED | 15 | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0

## NASA-Metrics-Status---Quality-5
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints
Total Constraints | Start No Earlier Than | Start No Later Than | Finish No Earlier Than | Finish No Later Than | Hard Constraints | Must Start On | Must Finish On | As Late As Possible | Deadlines | Mandatory Start | Mandatory Finish | Open Ends with Constraints | Open Ends w/o Constraints | Unsatisfied Constraints | No Constraints | No Constraints | Score
3 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 5 | 0 | 96 | 96 | 31
3% | 2% | 0% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 1% | 0% | 0% | 5% | 0% | 97% | 97%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total Constraints | Total Constraints | 3 | 3% | 1 | 1%
Number of activities with certain constraint types.
Excluded | Created | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | StartOnOrAfter | 2026-08-10 | None |  | FALSE | 275 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93
FALSE |  | StartOnOrAfter | 2026-08-17 | None |  | FALSE | 19 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36
FALSE |  | MandatoryStart | 2027-12-10 | None |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Start No Earlier Than | Start No Earlier Than | 2 | 2% | 1 | 1%
Number of activities with a soft (one-way) constraint that forces the activity to start on or after a given date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Start No Later Than | Start No Later Than | 0 | 0% | 0 | 0%
Number of activities with a soft (one-way) constraint that forces the activity to start on or before a given date.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Finish No Earlier Than | Finish No Earlier Than | 0 | 0% | 0 | 0%
Number of activities with a soft (one-way) constraint that forces the activity to finish on or after a specific date
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Finish No Later Than | Finish No Later Than | 0 | 0% | 0 | 0%
Number of activities with a soft (one-way) constraint that forces the activity to finish on or before a specific date
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Hard Constraints | Hard Constraints | 1 | 1% | 0 | 0%
Number of activities with hard or two-way constraints.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Must Start On | Must Start On | 0 | 0% | 0 | 0%
Number of activities with a hard (two-way) constraint that forces the activity to start on a specific date but does not override CPM Calculations.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Must Finish On | Must Finish On | 0 | 0% | 0 | 0%
Number of activities with a hard (two-way) constraint that forces the activity to finish on a specific date but does not override CPM Calculations.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
As Late As Possible | As Late As Possible | 0 | 0% | 0 | 0%
Number of activities with a soft (one-way) constraint that forces the activity to start as late as possible without impacting the Early or Late dates.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Deadlines | Deadlines | 0 | 0% | 0 | 0%
Number of activities with a hard (two-way) constraint that forces the activity to finish on a specific date, overriding CPM calculations.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Mandatory Start | Mandatory Start | 1 | 1% | 0 | 0%
Number of activities with a hard (two-way) constraint that forces the activity to start on a specific date, overriding CPM calculations.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Mandatory Finish | Mandatory Finish | 0 | 0% | 0 | 0%
Number of activities with a hard (two-way) constraint that forces the activity to finish on a specific date, overriding CPM calculations.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Open Ends with Constraints | Open Ends with Constraints | 0 | 0% | 0 | 0%
Activities where missing logic is accounted for through the use of a constraint.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Open Ends w/o Constraints | Open Ends w/o Constraints | 5 | 5% | 4 | 4%
Activities that are missing logic without any type of supporting constraint.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Unsatisfied Constraints | Unsatisfied Constraints | 0 | 0% | 0 | 0%
Activities where the constraint date cannot be met
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
No Constraints | No Constraints | 96 | 97% | 105 | 99%
Number of activities with no constraints.
Excluded | Created | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | None |  | None |  | FALSE | 275 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 275 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 275 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 256 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 256 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 256 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 256 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 56 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 156 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 156 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 95 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 100 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 100 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 95 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 95 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 184 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 156 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 95 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 30 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 95 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 94 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 184 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 118 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 94 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 124 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 184 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 118 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 118 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 115 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 82 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 80 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 115 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 80 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 80 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 80 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 80 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 39 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 36 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 70 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 82 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 51 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 70 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 29 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 35 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 81 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 81 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 36 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 35 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 89 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 55 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 36 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 38 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 38 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 35 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 28 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 32 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 35 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 32 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 38 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 1 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
No Constraints | No Constraints | 96 | 97% | 105 | 99%
Number of activities with no constraints.
Excluded | Created | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | None |  | None |  | FALSE | 275 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 275 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 275 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 256 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 256 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 256 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 256 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 56 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 156 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 156 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 95 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 100 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 100 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 95 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 95 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 184 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 156 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 95 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 30 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 95 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 94 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 184 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 118 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 94 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 124 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 184 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 118 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 118 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 115 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 82 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 80 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 115 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 80 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 80 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 80 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 80 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 39 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 36 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 70 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 82 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 51 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 70 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 29 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 35 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 81 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 81 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 36 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 35 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 89 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 55 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 36 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 38 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 38 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 35 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 28 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 32 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 35 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 32 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 38 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 19 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 1 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0

## NASA-Metrics-Status---Quality-6
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic
Logic Density™ | Logic Density™ - Predecessors | Logic Density™ - Successors | Summary Links | All Activities w/Predecessors | SS Predecessors | SF Predecessors | FF Predecessors | FS Predecessors | All Activities w/Successors | SS Successors | FF Successors | SF Successors | FS Successors | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Score
2.86 | 1.48 | 1.37 | 0 | 97 | 0 | 0 | 0 | 99 | 94 | 0 | 0 | 0 | 94 | 5 | 0 | 5 | 0 | 0 | 65
|  |  | 0% | 100% | 0% | 0% | 0% | 100% | 95% | 0% | 0% | 0% | 95% | 5% | 0% | 5% | 0% | 0%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Logic Density™ | Logic Density™ | 2.86 |  | 2.81
The average number of logic links per activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Logic Density™ - Predecessors | Logic Density™ - Predecessors | 1.48 |  | 1.45
The average number of predecessor logic links per activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Logic Density™ - Successors | Logic Density™ - Successors | 1.37 |  | 1.36
The average number of successor logic links per activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Summary Links | Summary Links | 0 | 0% | 0 | 0%
Number of summary activities that have logic links.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
All Activities w/Predecessors | All Activities w/Predecessors | 97 | 100% | 103 | 100%
The total number of activities within a grouping that have predecessors. Includes normal activities and milestones that are planned or in-progress.
Excluded | Number of Predecessors | Number of Leads | Number of Lags | Maximum Lag | Minimum Lag | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 5 | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE | 5 | 0 | 0 | 0 | 0 |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE | 4 | 0 | 0 | 0 | 0 |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE | 1 | 0 | 1 | 5 | 5 |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 20 | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 15 | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE | 7 | 0 | 0 | 0 | 0 |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
SS Predecessors | SS Predecessors | 0 | 0% | 0 | 0%
Number of activities with Start-to-Start (SS) logic links.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
SF Predecessors | SF Predecessors | 0 | 0% | 0 | 0%
Number of activities with Start-to-Finish (SF) logic links.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
FF Predecessors | FF Predecessors | 0 | 0% | 1 | 1%
Number of activities with Finish-to-Finish (FF) logic links.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
FS Predecessors | FS Predecessors | 99 | 100% | 106 | 100%
Number of activities with Finish-to-Start (FS) logic links. Should be at least 90%.
Excluded | Number of FS Predecessors | Number Of FS Predecessor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 1 | 0 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 1 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 1 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 1 | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 1 | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 2 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 2 | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 1 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 1 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 1 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 1 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 2 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 1 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 1 | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 5 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 2 | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 2 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 1 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 2 | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 1 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 1 | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 1 | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 3 | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 2 | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 1 | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 4 | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 1 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 2 | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 1 | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 2 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 2 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 2 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 1 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 1 | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 1 | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 1 | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 1 | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 1 | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 1 | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 1 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 3 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 1 | 1 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 1 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 1 | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 1 | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 1 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 1 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 3 | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 1 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 3 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 2 | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 2 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 1 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 1 | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 2 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 1 | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 2 | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 1 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 2 | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 2 | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 2 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 2 | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 1 | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 1 | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 1 | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 3 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 1 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 7 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 1 | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 3 | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 1 | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 3 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 2 | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 1 | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 2 | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
All Activities w/Successors | All Activities w/Successors | 94 | 95% | 102 | 96%
The total number of activities within a grouping. Includes normal activities and milestones that are planned or in-progress.
Excluded | Number of Successors | Number of Successor Leads | Number of Successor Lags | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 1 | 0 | 0 |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 2 | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE | 1 | 0 | 0 |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 4 | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE | 1 | 0 | 0 |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE | 1 | 0 | 0 |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 5 | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE | 1 | 0 | 0 |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE | 5 | 0 | 0 |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE | 2 | 0 | 0 |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE | 1 | 0 | 0 |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE | 1 | 0 | 0 |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE | 2 | 0 | 0 |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE | 1 | 0 | 0 |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE | 1 | 0 | 0 |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE | 3 | 0 | 0 |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE | 2 | 0 | 0 |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE | 1 | 0 | 0 |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE | 4 | 0 | 0 |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE | 1 | 0 | 0 |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE | 1 | 0 | 0 |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE | 3 | 0 | 0 |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE | 1 | 0 | 0 |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE | 1 | 0 | 0 |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE | 1 | 0 | 0 |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE | 1 | 0 | 0 |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE | 1 | 0 | 0 |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE | 1 | 0 | 0 |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE | 1 | 0 | 0 |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE | 3 | 0 | 0 |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE | 1 | 0 | 0 |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE | 2 | 0 | 0 |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE | 1 | 0 | 0 |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE | 1 | 0 | 0 |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE | 5 | 0 | 0 |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE | 1 | 0 | 0 |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE | 1 | 0 | 0 |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE | 1 | 0 | 0 |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE | 6 | 0 | 0 |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE | 1 | 0 | 0 |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE | 1 | 0 | 1 |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE | 1 | 0 | 0 |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE | 1 | 0 | 0 |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE | 1 | 0 | 0 |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE | 5 | 0 | 0 |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE | 2 | 0 | 0 |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE | 1 | 0 | 0 |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE | 1 | 0 | 0 |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE | 1 | 0 | 0 |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE | 1 | 0 | 0 |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE | 1 | 0 | 0 |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE | 1 | 0 | 0 |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE | 1 | 0 | 0 |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE | 1 | 0 | 0 |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE | 2 | 0 | 0 |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE | 1 | 0 | 0 |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE | 4 | 0 | 0 |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE | 4 | 0 | 0 |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE | 1 | 0 | 0 |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE | 1 | 0 | 0 |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE | 1 | 0 | 0 |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE | 1 | 0 | 0 |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE | 1 | 0 | 0 |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 15 | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE | 2 | 0 | 0 |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE | 1 | 0 | 0 |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE | 1 | 0 | 0 |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE | 3 | 0 | 0 |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE | 1 | 0 | 0 |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE | 2 | 0 | 0 |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE | 1 | 0 | 0 |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
SS Successors | SS Successors | 0 | 0% | 0 | 0%
Number of activities with Start-to-Start (SS) logic links.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
FF Successors | FF Successors | 0 | 0% | 0 | 0%
Number of activities with Finish-to-Finish (FF) logic links.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
SF Successors | SF Successors | 0 | 0% | 0 | 0%
Number of activities with Start-to-Finish (SF) logic links.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
FS Successors | FS Successors | 94 | 95% | 102 | 96%
Number of activities with Finish-to-Start (FS) logic links. Should be at least 90%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missing Logic | Missing Logic | 5 | 5% | 4 | 4%
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Number of Predecessors | Number of Successors | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 1 | 0 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 1 | 0 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 1 | 0 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 2 | 0 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missing Predecessors | Missing Predecessors | 0 | 0% | 0 | 0%
Number of activities that are missing a predecessor.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missing Successors | Missing Successors | 5 | 5% | 4 | 4%
Number of normal activities that are missing a successor.
Excluded | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 1 | 0 |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 1 | 0 |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 1 | 0 |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 2 | 0 |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Open Start | Open Start | 0 | 0% | 0 | 0%
Activities where only the predecessor(s) are either Finish-to-Finish or Start-to-Finish resulting in an open start to the activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Open Finish | Open Finish | 0 | 0% | 0 | 0%
Activities where the only successors(s) are either Start-to-Finish or Start-to-Start resulting in an open finish to the activity.

## NASA-Metrics-Status---Quality-7
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors
Logic Density™ - Predecessors | All Activities w/Predecessors | Total # Predecessors | Activities Missing Predecessors | Activities w/Leads on Predecessor | Total # Predecessor Leads | Max # Predecessor Leads on an Activity | Activities w/Lags on Predecessor | Total # Predecessor Lags | Max # of Predecessor Lags on an Activity | Min Predecessor Lag (days) | Max Predecessor Lag (days) | Hidden Duration (Planned) | Critical w/Hidden Duration (Planned) | Merge Hotspot (Predecessors >2) | Merge Hotspot w/Predecessor Lags | Merge Hotspot w/Predecessor Lags & Low Total Float | Critical Merge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Score
1.49 | 97 | 145 | 0 | 0 | N/A | N/A | 1 | 1 | 1 | 0 | 5 | 1 | 0 | 10 | 0 | N/A | 1 | 1 | 0 | 33
| 100% |  | 0% | 0% |  |  | 1% |  |  |  |  | 1% | 0% | 10% | 0% | ( N/A ) | 1% | 1% | 0%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Logic Density™ - Predecessors | Logic Density™ - Predecessors | 1.49 |  | 1.47
The average number of predecessor logic links per activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
All Activities w/Predecessors | All Activities w/Predecessors | 97 | 100% | 103 | 100%
The total number of activities within a grouping that have predecessors. Includes normal activities and milestones that are planned.
Excluded | Created | Percent Complete | Number of Predecessors | Number of Leads | Number of Lags | Minimum Lag | Maximum Lag | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 5 | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 | 5 | 0 | 0 | 0 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 | 4 | 0 | 0 | 0 | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 1 | 5 | 5 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 20 | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 15 | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 | 7 | 0 | 0 | 0 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total # Predecessors | Total # Predecessors | 145 |  | 151
The total number of successors on all activities within a grouping that have predecessors. Includes normal activities and milestones that are planned.
Excluded | Created | Percent Complete | Number of Predecessors | Number of Leads | Number of Lags | Minimum Lag | Maximum Lag | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 5 | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 | 5 | 0 | 0 | 0 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 | 4 | 0 | 0 | 0 | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 1 | 5 | 5 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 20 | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 15 | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 | 7 | 0 | 0 | 0 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Activities Missing Predecessors | Activities Missing Predecessors | 0 | 0% | 0 | 0%
Number of activities that are missing a predecessor.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Activities w/Leads on Predecessor | Activities w/Leads on Predecessor | 0 | 0% | 0 | 0%
Total number of activities carrying a lead (negative lag) on the link to their predecessor activity. This number should not exceed 5%.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total # Predecessor Leads | Total # Predecessor Leads | N/A |  | N/A
Total number of predecessor relationships with leads (negative lag) in the schedule
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Max # Predecessor Leads on an Activity | Max # Predecessor Leads on an Activity | N/A |  | N/A
The max number of predecessor leads (negative lag) on an activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Activities w/Lags on Predecessor | Activities w/Lags on Predecessor | 1 | 1% | 2 | 2%
Total number of activities carrying a lag on the link to their predecessor activity. This number should not exceed 5%.
Excluded | Number of Predecessors | Number of Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 1 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total # Predecessor Lags | Total # Predecessor Lags | 1 |  | 2
Total number of predecessor relationships with lags in the schedule.
Excluded | Number of Predecessors | Number of Lags | Minimum Lag | Maximum Lag | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 1 | 5 | 5 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Max # of Predecessor Lags on an Activity | Max # of Predecessor Lags on an Activity | 1 |  | 1
The max number of predecessor lags on an activity.
Excluded | Number of Predecessors | Number of Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 1 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Min Predecessor Lag (days) | Min Predecessor Lag (days) | 0 |  | 0
The smallest predecessor lag value for the selected activity grouping.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Max Predecessor Lag (days) | Max Predecessor Lag (days) | 5 |  | 5
The largest predecessor lag value for the selected activity grouping.
Excluded | Number of Predecessors | Number of Lags | Minimum Lag | Maximum Lag | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 | 0 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 1 | 0 | 0 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 1 | 0 | 0 | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 1 | 0 | 0 | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 2 | 0 | 0 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 2 | 0 | 0 | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 1 | 0 | 0 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 1 | 0 | 0 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 1 | 0 | 0 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 1 | 0 | 0 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 2 | 0 | 0 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 1 | 0 | 0 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 1 | 0 | 0 | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 5 | 0 | 0 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 2 | 0 | 0 | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 2 | 0 | 0 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 1 | 0 | 0 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 2 | 0 | 0 | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 1 | 0 | 0 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 1 | 0 | 0 | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 1 | 0 | 0 | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 3 | 0 | 0 | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 2 | 0 | 0 | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 1 | 0 | 0 | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 4 | 0 | 0 | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 1 | 0 | 0 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 2 | 0 | 0 | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 1 | 0 | 0 | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 2 | 0 | 0 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 2 | 0 | 0 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 2 | 0 | 0 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 1 | 0 | 0 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 1 | 0 | 0 | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 1 | 0 | 0 | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 1 | 0 | 0 | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 1 | 0 | 0 | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 1 | 0 | 0 | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 1 | 0 | 0 | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 1 | 0 | 0 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 3 | 0 | 0 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 1 | 1 | 5 | 5 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 1 | 0 | 0 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 1 | 0 | 0 | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 1 | 0 | 0 | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 1 | 0 | 0 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 1 | 0 | 0 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 3 | 0 | 0 | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 1 | 0 | 0 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 3 | 0 | 0 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 2 | 0 | 0 | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 2 | 0 | 0 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 1 | 0 | 0 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 1 | 0 | 0 | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 2 | 0 | 0 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 1 | 0 | 0 | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 2 | 0 | 0 | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 1 | 0 | 0 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 2 | 0 | 0 | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 2 | 0 | 0 | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 2 | 0 | 0 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 2 | 0 | 0 | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 1 | 0 | 0 | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 1 | 0 | 0 | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 1 | 0 | 0 | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 3 | 0 | 0 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 1 | 0 | 0 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 7 | 0 | 0 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 1 | 0 | 0 | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 3 | 0 | 0 | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 1 | 0 | 0 | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 3 | 0 | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 2 | 0 | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 1 | 0 | 0 | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 2 | 0 | 0 | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Hidden Duration (Planned) | Hidden Duration (Planned) | 1 | 1% | 1 | 1%
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of its original duration
Excluded | Number of Predecessors | Number of Lags | Minimum Lag | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 1 | 5 | 5 | FALSE | 80 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical w/Hidden Duration (Planned) | Critical w/Hidden Duration (Planned) | 0 | 0% | 0 | 0%
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of its original duration
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Merge Hotspot (Predecessors >2) | Merge Hotspot (Predecessors >2) | 10 | 10% | 10 | 10%
The total number of activities with a high number of predecessor links.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 5 | 1 | FALSE | 19 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 5 | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0
FALSE | 3 | 1 | FALSE | 184 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE | 4 | 1 | FALSE | 95 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE | 3 | 1 | FALSE | 80 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE | 3 | 1 | FALSE | 82 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE | 3 | 1 | FALSE | 70 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE | 3 | 1 | FALSE | 35 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE | 7 | 3 | FALSE | 19 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0
FALSE | 3 | 1 | FALSE | 19 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0
FALSE | 3 | 1 | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Merge Hotspot w/Predecessor Lags | Merge Hotspot w/Predecessor Lags | 0 | 0% | 0 | 0%
Number of activities with a high number of predecessor links with lags on the predecessor relationships.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Merge Hotspot w/Predecessor Lags & Low Total Float | Merge Hotspot w/Predecessor Lags & Low Total Float | N/A |  | 0 | 0%
Number of activities with a high number of predecessor links with lags on the predecessor relationships and low total float.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Merge Hotspot | Critical Merge Hotspot | 1 | 1% | 3 | 3%
The total number of activities with a high number of predecessor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 1 | 0 | 0 | 0 | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Logic Hotspot™ | Logic Hotspot™ | 1 | 1% | 1 | 1%
Number of activities with a high number of predecessors as well as a high number of successors.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 7 | 3 | FALSE | 19 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Logic Hotspot™ | Critical Logic Hotspot™ | 0 | 0% | 1 | 2%
Number of activities with a high number of predecessors as well as a high number of successors.

## NASA-Metrics-Status---Quality-8
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors
Logic Density™ - Successors | All Activities w/Successors | Activities Missing Successors | Total # Successors | Activities w/Leads on Successor | Total# of Successor Leads | Max # of Successor Leads on Activity | Activities w/Lags on Successor | Total# of Successor Lags | Max # of Successor Lags on Activity | Diverge Hotspot (Successors >2) | Diverge Hotspot w/Successor Lags | Diverge Hotspot w/Successor Lags & Low Total Float | Critical Diverge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Score
1.37 | 94 | 5 | 136 | 0 | N/A | N/A | 1 | 1 | 1 | 11 | 0 | N/A | 0 | 1 | 0 | 88
| 100% | 5% |  | 0% |  |  | 1% |  |  | 11% | 0% | ( N/A ) | 0% | 1% | 0%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Logic Density™ - Successors | Logic Density™ - Successors | 1.37 |  | 1.36
The average number of successor logic links per activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
All Activities w/Successors | All Activities w/Successors | 94 | 100% | 102 | 100%
The total number of activities within a grouping.
Excluded | Created | Percent Complete | Number of Successors | Number of Successor Leads | Number of Successor Lags | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 93 | 1 | 0 | 0 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 2 | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 | 1 | 0 | 0 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 4 | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 | 1 | 0 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 | 1 | 0 | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 5 | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 | 1 | 0 | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 | 5 | 0 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 | 2 | 0 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 | 1 | 0 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 | 1 | 0 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 | 2 | 0 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 | 1 | 0 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 | 1 | 0 | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 | 3 | 0 | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 | 1 | 0 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 | 4 | 0 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 | 1 | 0 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 | 3 | 0 | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 | 1 | 0 | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 | 1 | 0 | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 | 1 | 0 | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 | 3 | 0 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 | 1 | 0 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 | 2 | 0 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 | 1 | 0 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 | 1 | 0 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 | 5 | 0 | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 | 1 | 0 | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 | 1 | 0 | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 | 1 | 0 | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 | 6 | 0 | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 | 1 | 0 | 1 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 | 5 | 0 | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 | 2 | 0 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 | 1 | 0 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 | 1 | 0 | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 | 1 | 0 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 | 1 | 0 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 | 1 | 0 | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 | 1 | 0 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 | 1 | 0 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 | 1 | 0 | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 | 2 | 0 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 | 1 | 0 | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 | 4 | 0 | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 | 4 | 0 | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 | 1 | 0 | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 | 1 | 0 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 | 1 | 0 | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 15 | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 | 1 | 0 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 | 1 | 0 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 | 3 | 0 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 | 1 | 0 | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Activities Missing Successors | Activities Missing Successors | 5 | 5% | 4 | 4%
Number of activities that are missing a successor.
Excluded | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0 |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total # Successors | Total # Successors | 136 |  | 144
The total number of successors on all activities within a grouping.
Excluded | Created | Percent Complete | Number of Successors | Number of Successor Leads | Number of Successor Lags | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 93 | 1 | 0 | 0 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 2 | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 | 1 | 0 | 0 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 4 | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 | 1 | 0 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 | 1 | 0 | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 5 | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 | 1 | 0 | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 | 5 | 0 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 | 2 | 0 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 | 1 | 0 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 | 1 | 0 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 | 2 | 0 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 | 1 | 0 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 | 1 | 0 | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 | 3 | 0 | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 | 1 | 0 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 | 4 | 0 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 | 1 | 0 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 | 3 | 0 | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 | 1 | 0 | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 | 1 | 0 | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 | 1 | 0 | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 | 1 | 0 | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 | 3 | 0 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 | 1 | 0 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 | 2 | 0 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 | 1 | 0 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 | 1 | 0 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 | 5 | 0 | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 | 1 | 0 | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 | 1 | 0 | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 | 1 | 0 | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 | 6 | 0 | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 | 1 | 0 | 1 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 | 1 | 0 | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 | 5 | 0 | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 | 2 | 0 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 | 1 | 0 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 | 1 | 0 | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 | 1 | 0 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 | 1 | 0 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 | 1 | 0 | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 | 1 | 0 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 | 1 | 0 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 | 1 | 0 | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 | 2 | 0 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 | 1 | 0 | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 | 4 | 0 | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 | 4 | 0 | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 | 1 | 0 | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 | 1 | 0 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 | 1 | 0 | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 15 | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 | 1 | 0 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 | 1 | 0 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 | 3 | 0 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 | 1 | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 | 2 | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 | 1 | 0 | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Activities w/Leads on Successor | Activities w/Leads on Successor | 0 | 0% | 0 | 0%
Total number of activities carrying a lead (negative lag) on the link to their successor activity. This number should not exceed 5%.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total# of Successor Leads | Total# of Successor Leads | N/A |  | N/A
Total number of successor relationships with leads in the schedule.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Max # of Successor Leads on Activity | Max # of Successor Leads on Activity | N/A |  | N/A
The max number of successor leads (negative lag) on an activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Activities w/Lags on Successor | Activities w/Lags on Successor | 1 | 1% | 1 | 1%
Total number of activities carrying a lag on the link to their successor activity. This number should not exceed 5%.
Excluded | Number of Successors | Number of Successor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 1 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total# of Successor Lags | Total# of Successor Lags | 1 |  | 1
Total number of successor relationships with lags in the schedule.
Excluded | Number of Successors | Number of Successor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 1 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Max # of Successor Lags on Activity | Max # of Successor Lags on Activity | 1 |  | 1
The max number of successor lags on an activity.
Excluded | Number of Successors | Number of Successor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 1 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Diverge Hotspot (Successors >2) | Diverge Hotspot (Successors >2) | 11 | 11% | 11 | 10%
Number of activities with a high number of successor links.
Excluded | Number of Predecessors | Number of Successors | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 2 | 5 | 0 | 0 | FALSE | 19 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0
FALSE | 1 | 3 | 0 | 0 | FALSE | 19 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0
FALSE | 1 | 4 | 0 | 0 | FALSE | 95 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE | 1 | 3 | 0 | 0 | FALSE | 19 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0
FALSE | 1 | 3 | 0 | 0 | FALSE | 94 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE | 1 | 5 | 0 | 0 | FALSE | 19 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0
FALSE | 1 | 6 | 0 | 0 | FALSE | 19 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0
FALSE | 1 | 5 | 0 | 0 | FALSE | 19 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0
FALSE | 2 | 4 | 0 | 0 | FALSE | 35 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE | 2 | 4 | 0 | 0 | FALSE | 19 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0
FALSE | 7 | 3 | 0 | 0 | FALSE | 19 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Diverge Hotspot w/Successor Lags | Diverge Hotspot w/Successor Lags | 0 | 0% | 0 | 0%
Number of activities with a high number of successor links and critical.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Diverge Hotspot w/Successor Lags & Low Total Float | Diverge Hotspot w/Successor Lags & Low Total Float | N/A |  | 0 | 0%
Number of activities with a high number of successor links.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Diverge Hotspot | Critical Diverge Hotspot | 0 | 0% | 8 | 8%
Number of activities with a high number of successor links that are also critical.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Logic Hotspot™ | Logic Hotspot™ | 1 | 1% | 1 | 1%
Number of activities with a high number of predecessors as well as a high number of successors.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 7 | 3 | FALSE | 19 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Logic Hotspot™ | Critical Logic Hotspot™ | 0 | 0% | 1 | 2%
Number of activities with a high number of predecessors as well as a high number of successors.

## NASA-Metrics-Performance
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA Metrics Performance
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Performance
|  | Performance - Completed | Performance - In-Progress | Performance - Planned/Future | Performance - Baseline Compliance | Performance - Float | Performance - Critical Path | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline_Additional Metrics | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Incomplete - Old & New | Baseline Execution Index (BEI) | Hit or Miss Index (HMI) | Current Execution Index (CEI) | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Values Adjusted | DRM | Tracking Dates | Margin Duration | Margin Date | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | BEI, HMI, CEI - Values | BEI, HMI, CEI - Critical Path
Ribbons | Project2 | 0 | 0 | 0 | 96 | 69 | 0 | 90 | 90 | 90 | 72 | 0 | 0 | 100 | 100 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | N/A | 100 | 100 | 100 | 100 | 72 | N/A | 100
Ribbons | Project5_TAMPERED | 0 | 0 | 0 | 91 | 69 | 0 | 86 | 86 | 86 | 67 | 0 | 0 | 100 | 100 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | N/A | 100 | 100 | 100 | 100 | 67 | N/A | 100
|  | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed
|  | Actually Finished - Tasks & Milestones | Completed Ahead - Tasks & Milestones | Completed On-Schedule - Tasks & Milestones | Completed Delayed - Tasks & Milestones | Avg Days Finished Early - Tasks & Milestones | Avg Days Finished Late - Tasks & Milestones | Avg Finish Variance - Tasks & Milestones | Actually Finished - Tasks | Completed Ahead - Tasks | Completed On-Schedule - Tasks | Completed Delayed - Tasks | Accelerated Durations Early/On-Schedule - Tasks | Accelerated Durations Late - Tasks | Extended Durations - Tasks | Actually Finished - Milestones | Completed Ahead - Milestones | Completed On-Schedule - Milestones | Completed Delayed - Milestones | Score
Ribbons | Project2 | 20 | 0 | 9 | 11 | 0 | 25 | 14 | 20 | 0 | 9 | 11 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0
Ribbons |  | 16% | 0% | 45% | 55% |  |  |  | 16% | 0% | 45% | 55% | 0% | 1% | 3% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Ribbons | Project5_TAMPERED | 27 | 0 | 9 | 18 | 0 | 39 | 26 | 27 | 0 | 9 | 18 | 0 | 2 | 7 | 0 | 0 | 0 | 0 | 0
Ribbons |  | 21% | 0% | 33% | 67% |  |  |  | 21% | 0% | 33% | 67% | 0% | 2% | 6% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
|  | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress
|  | Actually Started - Tasks | In-Progress Started Ahead - Tasks | In-Progress Started On-Schedule - Tasks | In-Progress Started Delayed - Tasks | In-Progress Delayed Finish - Tasks | Avg Days Started Early | Avg Days Started Late | Avg Start Variance | Expected Finish | In-Progress Schedule Overrun - Tasks & Milestones | Score
Ribbons | Project2 | 3 | 0 | 0 | 3 | 3 | 0 | 24 | 24 | 0 | 0 | 0
Ribbons |  | 2% | 0% | 0% | 100% | 100% |  |  |  | 0% | 0%
Ribbons | Project5_TAMPERED | 2 | 0 | 0 | 2 | 2 | 0 | 85 | 85 | 0 | 0 | 0
Ribbons |  | 2% | 0% | 0% | 100% | 100% |  |  |  | 0% | 0%
|  | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future
|  | Scheduled to Start - Tasks & Milestones | Planned Ahead Start - Tasks & Milestones | Planned On Schedule Start - Tasks & Milestones | Planned Delayed Start - Tasks & Milestones | Riding Data Date - Tasks & Milestones | Planned Schedule Overrun - Tasks & Milestones | Scheduled to Start - Tasks | Planned Ahead Start - Tasks | Planned On Schedule Start - Tasks | Planned Delayed Start - Tasks | Planned Delayed Finish - Tasks | Scheduled to Start - Milestones | Planned Ahead Start - Milestones | Planned On Schedule Start - Milestones | Planned Delayed Start - Milestones | Planned Delayed Finish - Milestones | Score
Ribbons | Project2 | 103 | 0 | 0 | 103 | 0 | 0 | 103 | 0 | 0 | 103 | 103 | 0 | 0 | 0 | 0 | 0 | 0
Ribbons |  | 82% | 0% | 0% | 100% | 0% | 0% | 82% | 0% | 0% | 100% | 100% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Ribbons | Project5_TAMPERED | 97 | 0 | 0 | 97 | 0 | 0 | 97 | 0 | 0 | 97 | 97 | 0 | 0 | 0 | 0 | 0 | 0
Ribbons |  | 77% | 0% | 0% | 100% | 0% | 0% | 77% | 0% | 0% | 100% | 100% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
|  | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance
|  | Schedule Baseline Activities | Scheduled/Baselined to Start | Scheduled/Baselined to Finish | Start/ed | Finish/ed | Start Variance (Phase) | Start Compliance™ (Phase) | Finish Variance (Phase) | Finish Compliance™ (Phase) | Started Delayed (>30 days) | Completed Delayed (>30 days) | SPI(t) | Scheduled Activities | Scheduled to Start | Scheduled to Finish | Score
Ribbons | Project2 | 126 | 106 | 106 | 23 | 20 | 0 | 100% | 0 | 100% | 4 | 5 | 0.83 | 126 | 106 | 106 | 96
Ribbons |  | 100% |  |  |  |  | 0% |  | 0% |  | 33% | 45% |  | 100% | 84% | 84%
Ribbons | Project5_TAMPERED | 126 | 99 | 99 | 29 | 27 | 0 | 100% | 0 | 100% | 10 | 11 | 0.91 | 126 | 99 | 99 | 91
Ribbons |  | 100% |  |  |  |  | 0% |  | 0% |  | 56% | 61% |  | 100% | 79% | 79%
|  | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float
|  | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Critical Milestone-to-Task Ratio (To-Go) | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Score
Ribbons | Project2 | 41 | 0 | 41 | 1 | N/A | 39 | 44 | 41 | 0 | 69
Ribbons |  | 39% | ( N/A ) | 39% | 2% | 0 | 37% | 42% | 39% | 0%
Ribbons | Project5_TAMPERED | 4 | 0 | 4 | 0 | N/A | 41 | 44 | 4 | 0 | 69
Ribbons |  | 4% | ( N/A ) | 4% | 0% | 0 | 41% | 44% | 4% | 0%
|  | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path
|  | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | Logic Density™ | CP Logic Density™ | Critical w/Missing Logic | Critical w/Hard Constraints | Zero Days Float | Negative Float | Critical LOE | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical with Predecessor Lag | Critical with Successor Lag | Critical with Hard Constraints | Negative Float with Predecessor Lag | Negative Float with Successor Lag | Critical CEI - Value Tasks | Critical CEI - Total Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Score
Ribbons | Project2 | 41 | 0 | 41 | 1 | N/A | N/A | 2.79 | 3.2 | 1 | 0 | 41 | 0 | N/A | 0 | 0 | 1 | 1 | 0 | 1 | 1 | N/A | 0 | N/A | N/A | 0 | 0 | 0
Ribbons |  | 39% | ( N/A ) | 39% | 2% | 0 | 0 |  |  | 4% | 0% | 39% | 0% | 0% | 0% | 0% | 2% | 2% | 0% | 2% | 2% |  |  | N/A | N/A | 0% | 0%
Ribbons | Project5_TAMPERED | 4 | 0 | 4 | 0 | N/A | N/A | 2.81 | 3 | 1 | 1 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | N/A | 0 | N/A | N/A | 1 | 34 | 0
Ribbons |  | 4% | ( N/A ) | 4% | 0% | 0 | 0 |  |  | 5% | 1% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  |  | 44% | 56% | 1% | 24%
|  | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH)
|  | Baselined to Start | Scheduled to Start | Actual Starts | Baselined to Finish | Scheduled to Finish | Actual Finishes | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Score
Ribbons | Project2 | 126 | 126 | 23 | 126 | 126 | 20 | 8 | 4 | 0 | 6 | 5 | 0 | 90
Ribbons | [7 empty] | 67% | 33% | 0% | 55% | 45% | 0%
Ribbons | Project5_TAMPERED | 126 | 126 | 29 | 126 | 126 | 27 | 8 | 4 | 6 | 7 | 6 | 5 | 86
Ribbons | [7 empty] | 44% | 22% | 33% | 39% | 33% | 28%
|  | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics)
|  | Baselined to Start | Scheduled to Start | Actual Starts | Current Baselined to Start & Started | Past Baselined to Start & Started | Future Baseline to Start & Started | Baselined to Finish | Scheduled to Finish | Actual Finishes | Current Baselined to Finish & Finished | Past Baselined to Finish & Finished | Future Baselined to Finish & Finished | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Score
Ribbons | Project2 | 126 | 126 | 23 | 23 | 0 | 0 | 126 | 126 | 20 | 20 | 0 | 0 | 8 | 4 | 0 | 6 | 5 | 0 | 90
Ribbons | [13 empty] | 67% | 33% | 0% | 55% | 45% | 0%
Ribbons | Project5_TAMPERED | 126 | 126 | 29 | 29 | 0 | 0 | 126 | 126 | 27 | 27 | 0 | 0 | 8 | 4 | 6 | 7 | 6 | 5 | 86
Ribbons | [13 empty] | 44% | 22% | 33% | 39% | 33% | 28%
|  | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now
|  | Baselined to Start - To Time Now | Scheduled to Start - To Time Now | Started | Started Late | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | BEI - Value Task Starts | Baselined to Finish - To Time Now | Scheduled to Finish - To Time Now | Finished | Finished Late | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | BEI - Value Task Finishes | Started - Future | Not Baselined to Start | Score
Ribbons | Project2 | 29 | 29 | 23 | 12 | 8 | 4 | 0 | 0.79 | 27 | 27 | 20 | 11 | 6 | 5 | 0 | 0.74 | 0 | 0 | 90
Ribbons |  | 23% | 23% |  |  | 67% | 33% | 0% |  | 21% | 21% |  |  | 55% | 45% | 0% |  |  | 0%
Ribbons | Project5_TAMPERED | 48 | 48 | 29 | 18 | 8 | 4 | 6 | 0.6 | 46 | 46 | 27 | 18 | 7 | 6 | 5 | 0.59 | 0 | 0 | 86
Ribbons |  | 38% | 38% |  |  | 44% | 22% | 33% |  | 37% | 37% |  |  | 39% | 33% | 28% |  |  | 0%
|  | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH)
|  | BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Score
Ribbons | Project2 | 0.79 | 0.74 | N/A | N/A | N/A | N/A | 1.06 | 1.07 | 1.06 | 1.07 | 103 | 106 | 103 | 1.06 | 72
Ribbons
Ribbons | Project5_TAMPERED | 0.6 | 0.59 | 0 | 0.05 | 0.4 | 0.44 | 1.24 | 1.24 | 1.24 | 1.24 | 97 | 99 | 97 | 1.24 | 67
Ribbons
|  | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics)
|  | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Started | Current Baseline to Start & Started Past (Early Starts) | Current Baseline to Start & Started Future (Late Starts) | Current Baseline to Start & Not Started (Incomplete) | Baselined to Start - Check | Future Baseline to Start & Started (Early Starts) | Past Baseline to Finish & Finished - Check | Current Baseline to Finish & Finished - Check | Current Baseline to Finish & Finished Past - Check | Current Baseline to Finish & Finished Future - Check | Current Baseline to Finish & Not Finished - Check | Baselined to Finish - Check | Future Baseline to Finish & Finished - Check | Workoff Burden (Snapshot_Phase) (SEM01) | Workoff Burden - Starts To-Go (Total) (SEM07) | Past Baseline to Start & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Start & AlreadyDelayed (Workoff Burden) (SEM07) | Workoff Burden - Finishes To-Go (Total) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Score
Ribbons | Project2 | 0 | 23 | 0 | 0 | 103 | 126 | N/A | 0 | 20 | 0 | 0 | 106 | 126 | 0 | 0 | 103 | 6 | 97 | 106 | 7 | 99 | 0
Ribbons | [15 empty] | 0%
Ribbons | Project5_TAMPERED | 0 | 29 | 0 | 0 | 97 | 126 | N/A | 0 | 27 | 0 | 0 | 99 | 126 | 0 | 6 | 97 | 19 | 78 | 99 | 19 | 80 | 0
Ribbons | [15 empty] | 86%
|  | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH)
|  | Current Baseline to Start & Started (BL Plan) | Future Baseline to Start & Started (Early Starts) | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Finish & Finished (BL Plan) | Future Baseline to Finish & Finished (Early Finishes) | Past Baseline to Finish & Finished (Workoff Burden) | Current Baseline to Finish & Not Finished (Incompletes) | Past Baseline to Start & Not Started (Workoff Burden) (SEM07) | Future Baseline to Start & Already Delayed (Workoff Burden) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Score
Ribbons | Project2 | 23 | N/A | 0 | 103 | 20 | 0 | 0 | 106 | 6 | 97 | 7 | 99 | 0
Ribbons
Ribbons | Project5_TAMPERED | 29 | N/A | 0 | 97 | 27 | 0 | 0 | 99 | 19 | 78 | 19 | 80 | 0
Ribbons
|  | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now
|  | Baselined to Start | Scheduled to Start | Started - Scheduled | Started - Baseline Comparison | BEI - Value Task Starts | HMI - Value Task Starts | CEI - Value Task Starts | Baselined to Finish | Scheduled to Finish | Finished | BEI - Value Task Finishes | HMI - Value Task Finishes | CEI - Value Task Finishes | Status Date | Score
Ribbons | Project2 | 29 | 29 | 23 | 23 | 0.79 | N/A | N/A | 27 | 27 | 20 | 0.74 | N/A | N/A | 2026-05-24 | 100
Ribbons |  |  | 100% | 79% | 79%
Ribbons | Project5_TAMPERED | 48 | 48 | 29 | 29 | 0.6 | 0 | 0.46 | 46 | 46 | 27 | 0.59 | 0.05 | 0.44 | 2026-08-27 | 100
Ribbons |  |  | 100% | 60% | 60%
|  | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics
|  | Started (incl. Future Baseline Starts) - Scheduled | Started (incl. Future Baseline Starts) - Baseline Comparison | Started Late (from Baseline) | Finished (incl. Future Baseline Finishes) - Scheduled | Finished (incl. Future Baseline Finishes) - Baseline Comparison | Finished Late | Score
Ribbons | Project2 | 23 | 23 | 12 | 20 | 20 | 11 | 100
Ribbons |  | 18% | 18% | N/A | 16% | 16%
Ribbons | Project5_TAMPERED | 29 | 29 | 18 | 27 | 27 | 18 | 100
Ribbons |  | 23% | 23% | N/A | 21% | 21%
|  | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST
|  | Completed Ahead | Completed Delayed | Completed On-Schedule | Accelerated | Days Variance | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Variance | Actually Finished | Took Longer than Planned | Took Less Than Planned | Completed (w/Baseline Duration) | Completed (w/o Baseline Duration) | Completed (w/Baseline Dur=0) | Baseline-to-Date Completed Tasks | Missed Durations | Missed Durations & Late Actual Finish | Score
Ribbons | Project2 | 0 | 11 | 9 | 0 | 277 | 0 | 277 | 0 | 25 | 14 | 20 | 4 | 2 | 20 | 0 | 0 | 20 | 4 | 4 | 0
Ribbons |  | 0% | 55% | 45% | 0% | 1385% | 0% | 1385% |  |  |  | 16% | 20% | 10% | 16% | 0% | 0% | 74% | 20% | 20%
Ribbons | Project5_TAMPERED | 0 | 18 | 9 | 0 | 705 | 0 | 705 | 0 | 39 | 26 | 27 | 7 | 6 | 27 | 0 | 0 | 27 | 7 | 7 | 0
Ribbons |  | 0% | 67% | 33% | 0% | 2611% | 0% | 2611% |  |  |  | 21% | 26% | 22% | 21% | 0% | 0% | 59% | 26% | 26%
|  | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST
|  | Completed Ahead | Completed Delayed | Completed On-Schedule | Accelerated | Days Variance | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Variance | Actually Finished | Took Longer than Planned | Took Less Than Planned | Completed (w/Baseline Duration) | Completed (w/o Baseline Duration) | Completed (w/Baseline Dur=0) | Baseline-to-Date Completed Tasks | Missed Durations | Missed Durations & Late Actual Finish | Score
Ribbons | Project2 | 0 | 11 | 9 | 0 | 277 | 0 | 277 | 0 | 25 | 14 | 20 | 4 | 2 | 20 | 0 | 0 | 20 | 4 | 4 | 0
Ribbons |  | 0% | 55% | 45% | 0% | 1385% | 0% | 1385% |  |  |  | 16% | 20% | 10% | 16% | 0% | 0% | 74% | 20% | 20%
Ribbons | Project5_TAMPERED | 0 | 18 | 9 | 0 | 705 | 0 | 705 | 0 | 39 | 26 | 27 | 7 | 6 | 27 | 0 | 0 | 27 | 7 | 7 | 0
Ribbons |  | 0% | 67% | 33% | 0% | 2611% | 0% | 2611% |  |  |  | 21% | 26% | 22% | 21% | 0% | 0% | 59% | 26% | 26%
|  | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New
|  | Baselined Tasks | Baselined to Start - TOTAL | Complete Task Starts - Cumulative | Incomplete Task Starts - Cumulative (in work) | Old Incomplete Task Starts in Status Period | Baselined to Finish | Complete Task Finishes - Cumulative (in work) | Incomplete Task Finishes - Cumulative | Old Incomplete Task Finishes in Status Period | Old Completed Task Finishes in Status Period | Score
Ribbons | Project2 | 126 | 126 | 23 | 6 | N/A | 126 | 20 | 7 | N/A | N/A | 100
Ribbons |  |  |  | 79% | 21% |  |  | 74% | 74%
Ribbons | Project5_TAMPERED | 126 | 126 | 29 | 19 | N/A | 126 | 27 | 19 | N/A | N/A | 100
Ribbons |  |  |  | 60% | 40% |  |  | 59% | 59%
Baseline Execution Index (BEI)
|  | BEI - Tasks | BEI - Milestones
Ribbons | Project2 | 100 | 100
Ribbons | Project5_TAMPERED | 100 | 100
Hit or Miss Index (HMI)
|  | HMI - Tasks | HMI - Milestones
Ribbons | Project2 | 100 | 100
Ribbons | Project5_TAMPERED | 100 | 100
Current Execution Index (CEI)
|  | CEI - Tasks | CEI - Milestones
Ribbons | Project2 | 100 | 100
Ribbons | Project5_TAMPERED | 100 | 100
|  | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks
|  | BEI - Value Tasks | BEI - Total Tasks | BEI - Incomplete Tasks | HMI - Value Tasks | HMI - Total Tasks | HMI - Incomplete Tasks | CEI - Value Tasks | CEI - Total Tasks | CEI - Incomplete Tasks | BEI - Complete Milestones | HMI - Complete Tasks | CEI - Complete Tasks | Score
Ribbons | Project2 | 0.74 | 27 | 7 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 100
Ribbons |  |  |  | 26% |  |  | N/A |  |  | N/A | N/A | N/A | N/A
Ribbons | Project5_TAMPERED | 0.59 | 46 | 19 | 0.05 | 19 | 18 | 0.44 | 16 | 9 | N/A | 1 | 7 | 100
Ribbons |  |  |  | 41% |  |  | 95% |  |  | 56% | N/A | 5% | 44%
|  | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones
|  | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Incomplete Milestones | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | Score
Ribbons | Project2 | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | 100
Ribbons |  |  |  | N/A | N/A |  |  | N/A | N/A |  |  | N/A | N/A
Ribbons | Project5_TAMPERED | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | 100
Ribbons |  |  |  | N/A | N/A |  |  | N/A | N/A |  |  | N/A | N/A
|  | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted
|  | BEI - Value Tasks (adjusted) | HMI - Value Tasks (adjusted) | CEI - Value Tasks (adjusted) | BEI - Value Milestones (adjusted) | HMI - Value Milestones (adjusted) | CEI - Value Milestones (adjusted) | Status Date | Score
Ribbons | Project2 | 0.74 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A
Ribbons
Ribbons | Project5_TAMPERED | 0.59 | 0.05 | 0.44 | N/A | N/A | N/A | 2026-08-27 | N/A
Ribbons
|  | DRM | DRM | DRM
|  | Total Activities - DRM | Total Activities - DRM Graph | Score
Ribbons | Project2 | 20 | 20 | 100
Ribbons
Ribbons | Project5_TAMPERED | 27 | 27 | 100
Ribbons
|  | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates
|  | Status Date | Milestone #1 - 5158 | Float Milestone #1 - 5158 | Milestone #2 - 4786 | Float to Milestone #2 - 4786 | Milestone #3 - 102 | Float to Milestone #3 - 102 | Milestone #4 - 103 | Float to Milestone #4 - 103 | Milestone #5 - 104 | Float to Milestone #5 - 105 | New Activities Since Previous Status Date | Score
Ribbons | Project2 | 2026-05-24 | N/A | N/A | N/A | N/A | 2027-05-13 | 10 | 2027-06-02 | 10 | 2027-07-15 | 10 | 0 | 100
Ribbons
Ribbons | Project5_TAMPERED | 2026-08-27 | N/A | N/A | N/A | N/A | 2027-08-20 | 35 | 2027-09-09 | 35 | 2027-10-22 | 35 | 0 | 100
Ribbons
|  | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration
|  | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
Ribbons | Project2 | 2026-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons
Ribbons | Project5_TAMPERED | 2026-08-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons
|  | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date
|  | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
Ribbons | Project2 | 2026-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons
Ribbons | Project5_TAMPERED | 2026-08-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons
|  | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon)
|  | BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Score
Ribbons | Project2 | 0.79 | 0.74 | N/A | N/A | N/A | N/A | 1.06 | 1.07 | 1.06 | 1.07 | 103 | 106 | 103 | 1.06 | 72
Ribbons
Ribbons | Project5_TAMPERED | 0.6 | 0.59 | 0 | 0.05 | 0.4 | 0.44 | 1.24 | 1.24 | 1.24 | 1.24 | 97 | 99 | 97 | 1.24 | 67
Ribbons
|  | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values
|  | BEI - Value Tasks | HMI - Value Tasks | CEI - Value Tasks | BEI - Value Milestones | HMI - Value Milestones | CEI - Value Milestones | Score
Ribbons | Project2 | 0.74 | N/A | N/A | N/A | N/A | N/A | N/A
Ribbons
Ribbons | Project5_TAMPERED | 0.59 | 0.05 | 0.44 | N/A | N/A | N/A | N/A
Ribbons
|  | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path
|  | BEI - Value Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - CP Tasks - Planned Cumulative | BEI - CP Value Tasks | HMI - Value Tasks | HMI - Complete Tasks | HMI - Incomplete Tasks | HMI - CP Tasks - Planned to be Completed this Month | HMI - CP Value Tasks | CEI - Value Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - CP Tasks - Planned to be Completed this Month | CEI - CP Value Tasks | Score
Ribbons | Project2 | 0.74 | 20 | 7 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons |  |  | 74% | 26% |  |  |  | N/A | N/A |  |  |  | N/A | N/A
Ribbons | Project5_TAMPERED | 0.59 | 27 | 19 | 14 | 0 | 0.05 | 1 | 18 | 10 | 0 | 0.44 | 7 | 9 | 9 | 0.44 | 100
Ribbons |  |  | 59% | 41% |  |  |  | 5% | 95% |  |  |  | 44% | 56%

## NASA-Metrics-Performance-Perfo
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed
Actually Finished - Tasks & Milestones | Completed Ahead - Tasks & Milestones | Completed On-Schedule - Tasks & Milestones | Completed Delayed - Tasks & Milestones | Avg Days Finished Early - Tasks & Milestones | Avg Days Finished Late - Tasks & Milestones | Avg Finish Variance - Tasks & Milestones | Actually Finished - Tasks | Completed Ahead - Tasks | Completed On-Schedule - Tasks | Completed Delayed - Tasks | Accelerated Durations Early/On-Schedule - Tasks | Accelerated Durations Late - Tasks | Extended Durations - Tasks | Actually Finished - Milestones | Completed Ahead - Milestones | Completed On-Schedule - Milestones | Completed Delayed - Milestones | Score
27 | 0 | 9 | 18 | 0 | 39 | 26 | 27 | 0 | 9 | 18 | 0 | 2 | 7 | 0 | 0 | 0 | 0 | 0
21% | 0% | 33% | 67% |  |  |  | 21% | 0% | 33% | 67% | 0% | 2% | 6% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Actually Finished - Tasks & Milestones | Actually Finished - Tasks & Milestones | 27 | 21% | 20 | 16%
Number of activities and miletones that have finished.
Excluded | DRM | Actual Finish | % | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 2026-03-04 | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-10 | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-05 | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-06 | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-06 | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 | 2026-03-27 | 1 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-11 | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 | 2026-03-25 | 1 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-26 | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-27 | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-30 | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-06-19 | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-01 | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 | 2026-05-04 | 1 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-08 | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-14 | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-21 | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 | 2026-05-19 | 1 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 | 2026-06-19 | 1 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 | 2026-05-29 | 1 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-05-18 | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 | 2026-05-15 | 1 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-05-18 | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-06-19 | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-07-03 | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 | 2026-07-31 | 1 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 | 2026-08-07 | 1 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Ahead - Tasks & Milestones | Completed Ahead - Tasks & Milestones | 0 | 0% | 0 | 0%
Number of activities and milestones that finished before their planned finish date
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed On-Schedule - Tasks & Milestones | Completed On-Schedule - Tasks & Milestones | 9 | 33% | 9 | 45%
Number of activities and milestones that completed on time.
Excluded | DRM | Actual Finish | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 2026-03-04 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-10 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-05 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-06 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-06 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-11 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-26 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-30 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-01 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed - Tasks & Milestones | Completed Delayed - Tasks & Milestones | 18 | 67% | 11 | 55%
Number of activities and milestones that finished after their planned finish date.
Excluded | DRM | Actual Finish | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.6 | 2026-03-27 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 3.3333 | 2026-03-25 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-27 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-06-19 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 2.3 | 2026-05-04 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-08 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-14 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-21 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 | 2026-05-19 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 | 2026-06-19 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 | 2026-05-29 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-05-18 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 | 2026-05-15 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-05-18 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-06-19 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-07-03 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 | 2026-07-31 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 | 2026-08-07 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg Days Finished Early - Tasks & Milestones | Avg Days Finished Early - Tasks & Milestones | 0 |  | 0
Average number of days that all activities within a grouping finished early (before the baseline start date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg Days Finished Late - Tasks & Milestones | Avg Days Finished Late - Tasks & Milestones | 39 |  | 25
Average number of days that all activities within a grouping finished late (after the baseline start date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg Finish Variance - Tasks & Milestones | Avg Finish Variance - Tasks & Milestones | 26 |  | 14
Average variance (in days) between activities that finished early and those that finished late.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Actually Finished - Tasks | Actually Finished - Tasks | 27 | 21% | 20 | 16%
Number of normal activities that have finished.
Excluded | DRM | Actual Finish | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 2026-03-04 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-10 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-05 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-06 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-06 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 | 2026-03-27 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-11 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 | 2026-03-25 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-26 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-27 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-30 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-06-19 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-01 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 | 2026-05-04 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-08 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-14 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-21 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 | 2026-05-19 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 | 2026-06-19 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 | 2026-05-29 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-05-18 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 | 2026-05-15 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-05-18 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-06-19 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-07-03 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 | 2026-07-31 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 | 2026-08-07 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Ahead - Tasks | Completed Ahead - Tasks | 0 | 0% | 0 | 0%
Number of activities that finished before their planned finish date
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed On-Schedule - Tasks | Completed On-Schedule - Tasks | 9 | 33% | 9 | 45%
Number of activities that completed on time.
Excluded | DRM | Actual Finish | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 2026-03-04 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-10 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-05 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-06 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-06 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-11 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-26 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-30 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-01 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed - Tasks | Completed Delayed - Tasks | 18 | 67% | 11 | 55%
Number of activities that finished after their planned finish date.
Excluded | DRM | Actual Finish | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.6 | 2026-03-27 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 3.3333 | 2026-03-25 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-03-27 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-06-19 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 2.3 | 2026-05-04 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-08 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-14 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-04-21 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 | 2026-05-19 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 | 2026-06-19 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 | 2026-05-29 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-05-18 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 | 2026-05-15 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-05-18 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-06-19 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-07-03 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 | 2026-07-31 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 | 2026-08-07 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Accelerated Durations Early/On-Schedule - Tasks | Accelerated Durations Early/On-Schedule - Tasks | 0 | 0% | 0 | 0%
Number of activities that started after their planned start date but finished before or on their planned finish date.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Accelerated Durations Late - Tasks | Accelerated Durations Late - Tasks | 2 | 2% | 1 | 1%
Number of activities that started after their planned start date and reduced their durations, but still finished late.
Excluded | DRM | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Actual Start | Actual Finish | Type | Status | Percent Complete | Total Float
FALSE | 0.9 | 10 | 9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | 2026-05-05 | 2026-05-15 | Normal | Complete | 100 | 0
FALSE | 0.5 | 10 | 5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | 2026-08-03 | 2026-08-07 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Extended Durations - Tasks | Extended Durations - Tasks | 7 | 6% | 4 | 3%
Number of activities with actual durations greater than their baseline durations.
Excluded | DRM | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Actual Start | Actual Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.6 | 10 | 16 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | 2026-03-06 | 2026-03-27 | Normal | Complete | 100 | 0
FALSE | 3.3333 | 3 | 10 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | 2026-03-12 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 2.3 | 10 | 23 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | 2026-04-02 | 2026-05-04 | Normal | Complete | 100 | 0
FALSE | 2 | 10 | 20 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | 2026-04-22 | 2026-05-19 | Normal | Complete | 100 | 0
FALSE | 4.3 | 10 | 43 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | 2026-04-22 | 2026-06-19 | Normal | Complete | 100 | 0
FALSE | 1.9 | 10 | 19 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | 2026-05-05 | 2026-05-29 | Normal | Complete | 100 | 0
FALSE | 4 | 5 | 20 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | 2026-07-06 | 2026-07-31 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Actually Finished - Milestones | Actually Finished - Milestones | 0 |  | 0
Number of milestones that have finished.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Ahead - Milestones | Completed Ahead - Milestones | 0 |  | 0
Number of milestones that finished before their planned finish date
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed On-Schedule - Milestones | Completed On-Schedule - Milestones | 0 |  | 0
Number of milestones that completed on time.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed - Milestones | Completed Delayed - Milestones | 0 |  | 0
Number of milestones that finished after their planned finish date.

## NASA-Metrics-Performance-Perfo2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress
Actually Started - Tasks | In-Progress Started Ahead - Tasks | In-Progress Started On-Schedule - Tasks | In-Progress Started Delayed - Tasks | In-Progress Delayed Finish - Tasks | Avg Days Started Early | Avg Days Started Late | Avg Start Variance | Expected Finish | In-Progress Schedule Overrun - Tasks & Milestones | Score
2 | 0 | 0 | 2 | 2 | 0 | 85 | 85 | 0 | 0 | 0
2% | 0% | 0% | 100% | 100% |  |  |  | 0% | 0%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Actually Started - Tasks | Actually Started - Tasks | 2 | 2% | 3 | 2%
Total number of activities that have started.
Excluded | Actual Start | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2026-08-10 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2026-08-17 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
In-Progress Started Ahead - Tasks | In-Progress Started Ahead - Tasks | 0 | 0% | 0 | 0%
Number of activities that started before their planned start date.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
In-Progress Started On-Schedule - Tasks | In-Progress Started On-Schedule - Tasks | 0 | 0% | 0 | 0%
Number of activities that are currently underway and started on time.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
In-Progress Started Delayed - Tasks | In-Progress Started Delayed - Tasks | 2 | 100% | 3 | 100%
Number of activities that started after their planned start date.
Excluded | Actual Start | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2026-08-10 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2026-08-17 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
In-Progress Delayed Finish - Tasks | In-Progress Delayed Finish - Tasks | 2 | 100% | 3 | 100%
Number of in-progress activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg Days Started Early | Avg Days Started Early | 0 |  | 0
Average number of days that all activities within a grouping started early (before the baseline start date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg Days Started Late | Avg Days Started Late | 85 |  | 24
Average number of days that all activities within a grouping started late (after the baseline start date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg Start Variance | Avg Start Variance | 85 |  | 24
A calculation of the average variance between total days started early and total days started late.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Expected Finish | Expected Finish | 0 | 0% | 0 | 0%
In-progress activities that are 100% complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
In-Progress Schedule Overrun - Tasks & Milestones | In-Progress Schedule Overrun - Tasks & Milestones | 0 | 0% | 0 | 0%
Number of activities where the remaining duration is greater than the original duration

## NASA-Metrics-Performance-Perfo3
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future
Scheduled to Start - Tasks & Milestones | Planned Ahead Start - Tasks & Milestones | Planned On Schedule Start - Tasks & Milestones | Planned Delayed Start - Tasks & Milestones | Riding Data Date - Tasks & Milestones | Planned Schedule Overrun - Tasks & Milestones | Scheduled to Start - Tasks | Planned Ahead Start - Tasks | Planned On Schedule Start - Tasks | Planned Delayed Start - Tasks | Planned Delayed Finish - Tasks | Scheduled to Start - Milestones | Planned Ahead Start - Milestones | Planned On Schedule Start - Milestones | Planned Delayed Start - Milestones | Planned Delayed Finish - Milestones | Score
97 | 0 | 0 | 97 | 0 | 0 | 97 | 0 | 0 | 97 | 97 | 0 | 0 | 0 | 0 | 0 | 0
77% | 0% | 0% | 100% | 0% | 0% | 77% | 0% | 0% | 100% | 100% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Start - Tasks & Milestones | Scheduled to Start - Tasks & Milestones | 97 | 77% | 103 | 82%
Number of activities and milestones that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Planned Ahead Start - Tasks & Milestones | Planned Ahead Start - Tasks & Milestones | 0 | 0% | 0 | 0%
Number of activities and milestines that are currently planned to start before their baseline start date.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Planned On Schedule Start - Tasks & Milestones | Planned On Schedule Start - Tasks & Milestones | 0 | 0% | 0 | 0%
Number of activities and milestones that are planned to start on time.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Planned Delayed Start - Tasks & Milestones | Planned Delayed Start - Tasks & Milestones | 97 | 100% | 103 | 100%
Number of activities and milestones that are currently planned to start after their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Riding Data Date - Tasks & Milestones | Riding Data Date - Tasks & Milestones | 0 | 0% | 0 | 0%
Number of planned activities that have a start date that is the same as the project data date (Time Now)
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Planned Schedule Overrun - Tasks & Milestones | Planned Schedule Overrun - Tasks & Milestones | 0 | 0% | 0 | 0%
Number of activities where the remaining duration is greater than the original duration
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Start - Tasks | Scheduled to Start - Tasks | 97 | 77% | 103 | 82%
Number of activities that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Planned Ahead Start - Tasks | Planned Ahead Start - Tasks | 0 | 0% | 0 | 0%
Number of activities that are currently planned to start before their baseline start date.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Planned On Schedule Start - Tasks | Planned On Schedule Start - Tasks | 0 | 0% | 0 | 0%
Number of activities that are planned to start on time.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Planned Delayed Start - Tasks | Planned Delayed Start - Tasks | 97 | 100% | 103 | 100%
Number of activities that are currently planned to start after their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Planned Delayed Finish - Tasks | Planned Delayed Finish - Tasks | 97 | 100% | 103 | 100%
Number of planned/future activities that are schedule to slip from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Start - Milestones | Scheduled to Start - Milestones | 0 |  | 0
Number of milestones that are planned to start.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Planned Ahead Start - Milestones | Planned Ahead Start - Milestones | 0 |  | 0
Number of milestones that are currently planned to start before their baseline start date.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Planned On Schedule Start - Milestones | Planned On Schedule Start - Milestones | 0 |  | 0
Number of milestones that are planned to start on time.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Planned Delayed Start - Milestones | Planned Delayed Start - Milestones | 0 |  | 0
Number of milestones that are currently planned to start after their baseline start date.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Planned Delayed Finish - Milestones | Planned Delayed Finish - Milestones | 0 |  | 0
Number of planned/future activities that are schedule to slip from their baseline dates

## NASA-Metrics-Performance-Perfo4
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance
Schedule Baseline Activities | Scheduled/Baselined to Start | Scheduled/Baselined to Finish | Start/ed | Finish/ed | Start Variance (Phase) | Start Compliance™ (Phase) | Finish Variance (Phase) | Finish Compliance™ (Phase) | Started Delayed (>30 days) | Completed Delayed (>30 days) | SPI(t) | Scheduled Activities | Scheduled to Start | Scheduled to Finish | Score
126 | 99 | 99 | 29 | 27 | 0 | 100% | 0 | 100% | 10 | 11 | 0.91 | 126 | 99 | 99 | 91
100% |  |  |  |  | 0% |  | 0% |  | 56% | 61% |  | 100% | 79% | 79%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Schedule Baseline Activities | Schedule Baseline Activities | 126 | 100% | 126 | 100%
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled/Baselined to Start | Scheduled/Baselined to Start | 99 |  | 106
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled/Baselined to Finish | Scheduled/Baselined to Finish | 99 |  | 106
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Start/ed | Start/ed | 29 |  | 23
Number of activities starting or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Finish/ed | Finish/ed | 27 |  | 20
Number of activities finishing or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Start Variance (Phase) | Start Variance (Phase) | 0 | 0% | 0 | 0%
Number of activities starting or that have started outside of the expected baselined period.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Start Compliance™ (Phase) | Start Compliance™ (Phase) | 100% |  | 100%
A calculation of activity start date compliance with baselined start dates.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Finish Variance (Phase) | Finish Variance (Phase) | 0 | 0% | 0 | 0%
Number of activities finishing or that have finished outside the expected baselined period.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Finish Compliance™ (Phase) | Finish Compliance™ (Phase) | 100% |  | 100%
A calculation of activity finish date compliance with baselined finish dates.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Delayed (>30 days) | Started Delayed (>30 days) | 10 | 56% | 4 | 33%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed (>30 days) | Completed Delayed (>30 days) | 11 | 61% | 5 | 45%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
SPI(t) | SPI(t) | 0.91 |  | 0.83
Ratio showing the performance of the activity relative to the baseline.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled Activities | Scheduled Activities | 126 | 100% | 126 | 100%
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Start | Scheduled to Start | 99 | 79% | 106 | 84%
Number of activities that are scheduled to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Finish | Scheduled to Finish | 99 | 79% | 106 | 84%
Number of activities that are scheduled to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0

## NASA-Metrics-Performance-Perfo5
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float
Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Critical Milestone-to-Task Ratio (To-Go) | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Score
4 | 0 | 4 | 0 | N/A | 41 | 44 | 4 | 0 | 69
4% | ( N/A ) | 4% | 0% | 0 | 41% | 44% | 4% | 0%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Longest Path - Critical Activities and Milestones | Longest Path - Critical Activities and Milestones | 4 | 4% | 41 | 39%
Activities that together form the longest path through to project completion. (Number of critical activities.)
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Milestones (To-Go) | Critical Milestones (To-Go) | 0 |  | 0
Number of critical milestones to-go.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Tasks (To-Go) | Critical Tasks (To-Go) | 4 | 4% | 41 | 39%
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Tasks (In Progress) | Critical Tasks (In Progress) | 0 | 0% | 1 | 2%
Number of critical activities to-go.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | N/A | 0 | N/A | 0
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
High Float 10% | High Float 10% | 41 | 41% | 39 | 37%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
High Float 44d | High Float 44d | 44 | 44% | 44 | 42%
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Zero Days Float | Zero Days Float | 4 | 4% | 41 | 39%
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.

## NASA-Metrics-Performance-Perfo6
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path
Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | Logic Density™ | CP Logic Density™ | Critical w/Missing Logic | Critical w/Hard Constraints | Zero Days Float | Negative Float | Critical LOE | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical with Predecessor Lag | Critical with Successor Lag | Critical with Hard Constraints | Negative Float with Predecessor Lag | Negative Float with Successor Lag | Critical CEI - Value Tasks | Critical CEI - Total Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Score
4 | 0 | 4 | 0 | N/A | N/A | 2.81 | 3 | 1 | 1 | 4 | 0 | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | N/A | 0 | N/A | N/A | 1 | 34 | 0
4% | ( N/A ) | 4% | 0% | 0 | 0 |  |  | 5% | 1% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  |  | 44% | 56% | 1% | 24%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Longest Path - Critical Activities and Milestones | Longest Path - Critical Activities and Milestones | 4 | 4% | 41 | 39%
Activities that together form the longest path through to project completion. (Number of critical activities.)
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Milestones (To-Go) | Critical Milestones (To-Go) | 0 |  | 0
Number of critical milestones to-go.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Tasks (To-Go) | Critical Tasks (To-Go) | 4 | 4% | 41 | 39%
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Tasks (In Progress) | Critical Tasks (In Progress) | 0 | 0% | 1 | 2%
Number of critical activities to-go.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestone-to-Task Ratio (To-Go) | Milestone-to-Task Ratio (To-Go) | N/A | 0 | N/A | 0
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | N/A | 0 | N/A | 0
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Logic Density™ | Logic Density™ | 2.81 |  | 2.79
The average number of logic links per activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CP Logic Density™ | CP Logic Density™ | 3 |  | 3.2
The average number of logic links per activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical w/Missing Logic | Critical w/Missing Logic | 1 | 5% | 1 | 4%
Total number of critical activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Number of Predecessors | Number of Successors | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 2 | 0 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical w/Hard Constraints | Critical w/Hard Constraints | 1 | 1% | 0 | 0%
Number of critical activities with hard or two-way constraints.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Zero Days Float | Zero Days Float | 4 | 4% | 41 | 39%
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical LOE | Critical LOE | N/A | 0% | N/A | 0%
Critical Level Of Effort or Hammock Tasks
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical w/High Baseline Duration (44d) | Critical w/High Baseline Duration (44d) | 0 | 0% | 0 | 0%
Total number of critical activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Critical | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  |  | 2 | General Conditions | Project5_TAMPERED | 23 | 46 | 0 | 2026-03-02 | 2026-05-04 | 2026-03-02 | 2026-04-01 | Summary | Complete | 100 | 0
FALSE | FALSE |  |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 18 | Mobilize on Site | Project5_TAMPERED | 10 | 17 | 0 | 2026-03-05 | 2026-03-27 | 2026-03-05 | 2026-03-18 | Summary | Complete | 100 | 0
FALSE | FALSE |  |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 10 | Long Lead Procurement | Project5_TAMPERED | 70 | 76 | 0 | 2026-03-06 | 2026-06-19 | 2026-03-06 | 2026-06-11 | Summary | Complete | 100 | 0
FALSE | FALSE |  |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 10 | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 21 | Set up site office | Project5_TAMPERED | 3 | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 3 | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 10 | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 24 | Site Grading and Utilities | Project5_TAMPERED | 35 | 85 | 0 | 2026-04-06 | 2026-07-31 | 2026-03-19 | 2026-05-06 | Summary | Complete | 100 | 0
FALSE | FALSE |  |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 28 | Install storm drainage | Project5_TAMPERED | 10 | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 10 | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 10 | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 10 | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 5 | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 32 | Foundations | Project5_TAMPERED | 45 | 92 | 66 | 2026-08-03 | 2026-12-08 | 2026-05-07 | 2026-07-08 | Summary | InProgress | 28 | 256
FALSE | FALSE |  |  | 33 | Excavate foundations | Project5_TAMPERED | 10 | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 34 | Excavate elevator pit | Project5_TAMPERED | 2 | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | FALSE |  |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 4 | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | FALSE |  |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | FALSE |  |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | FALSE |  |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 5 | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | FALSE |  |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 47 | Steel Erection | Project5_TAMPERED | 50 | 74 | 74 | 2026-11-09 | 2027-02-18 | 2026-06-23 | 2026-08-31 | Summary | Planned | 0 | 19
FALSE | FALSE |  |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | FALSE |  |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 10 | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | FALSE |  |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | FALSE |  |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | FALSE |  |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 54 | Form and Pour Concrete - Floors and Roof | Project5_TAMPERED | 87 | 89 | 89 | 2026-12-16 | 2027-04-19 | 2026-07-07 | 2026-11-04 | Summary | Planned | 0 | 44
FALSE | FALSE |  |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | FALSE |  |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 10 | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | FALSE |  |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 5 | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 79 | Masonry Work | Project5_TAMPERED | 91 | 86 | 86 | 2027-02-19 | 2027-06-18 | 2026-09-01 | 2027-01-05 | Summary | Planned | 0 | 74
FALSE | FALSE |  |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | FALSE |  |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | FALSE |  |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | FALSE |  |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | FALSE |  |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | FALSE |  |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | FALSE |  |  | 110 | Elevators | Project5_TAMPERED | 40 | 40 | 40 | 2027-03-19 | 2027-05-13 | 2026-09-29 | 2026-11-23 | Summary | Planned | 0 | 184
FALSE | FALSE |  |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | FALSE |  |  | 126 | Heating and Ventilating - AC | Project5_TAMPERED | 187 | 210 | 210 | 2027-03-19 | 2028-01-06 | 2026-09-29 | 2027-06-16 | Summary | Planned | 0 | 14
FALSE | FALSE |  |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | FALSE |  |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | FALSE |  |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | FALSE |  |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | FALSE |  |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | FALSE |  |  | 77 | Carpentry Work | Project5_TAMPERED | 15 | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Summary | Planned | 0 | 19
FALSE | FALSE |  |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | FALSE |  |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | FALSE |  |  | 119 | Electrical | Project5_TAMPERED | 140 | 140 | 140 | 2027-04-20 | 2027-11-01 | 2026-11-05 | 2027-05-19 | Summary | Planned | 0 | 38
FALSE | FALSE |  |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | FALSE |  |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | FALSE |  |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | FALSE |  |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | FALSE |  |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | FALSE |  |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | FALSE |  |  | 87 | Roofing | Project5_TAMPERED | 33 | 33 | 33 | 2027-06-11 | 2027-07-27 | 2026-12-29 | 2027-02-11 | Summary | Planned | 0 | 80
FALSE | FALSE |  |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | FALSE |  |  | 93 | Window wall and store front closures | Project5_TAMPERED | 75 | 75 | 75 | 2027-06-11 | 2027-09-23 | 2026-12-29 | 2027-04-12 | Summary | Planned | 0 | 19
FALSE | FALSE |  |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | FALSE |  |  | 114 | Plumbing | Project5_TAMPERED | 100 | 100 | 100 | 2027-06-18 | 2027-11-04 | 2027-01-05 | 2027-05-24 | Summary | Planned | 0 | 35
FALSE | FALSE |  |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | FALSE |  |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | FALSE |  |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | FALSE |  |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | FALSE |  |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | FALSE |  |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | FALSE |  |  | 98 | Building Finishes | Project5_TAMPERED | 90 | 111 | 111 | 2027-07-16 | 2027-12-17 | 2027-02-02 | 2027-06-07 | Summary | Planned | 0 | 28
FALSE | FALSE |  |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | FALSE |  |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | FALSE |  |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | FALSE |  |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | FALSE |  |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | FALSE |  |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | FALSE |  |  | 132 | Final Clean-up and Occupancy | Project5_TAMPERED | 70 | 76 | 76 | 2027-08-20 | 2027-12-03 | 2027-03-09 | 2027-06-14 | Summary | Planned | 0 | 38
FALSE | FALSE |  |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | FALSE |  |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | FALSE |  |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | FALSE |  |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | FALSE |  |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | FALSE |  |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | FALSE |  |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | FALSE |  |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | FALSE |  |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | FALSE |  |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | FALSE |  |  | 106 | Install building carpet | Project5_TAMPERED | 20 | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | FALSE |  |  | 107 | Install hardware and accessories | Project5_TAMPERED | 15 | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | FALSE |  |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | FALSE |  |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | FALSE |  |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | FALSE |  |  | 137 | Complete Final Inspections | Project5_TAMPERED | 6 | 6 | 6 | 2027-12-03 | 2027-12-10 | 2027-06-14 | 2027-06-21 | Summary | Planned | 0 | 19
FALSE | FALSE |  |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | FALSE |  |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | TRUE |  |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | TRUE |  |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | TRUE |  |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical w/High Planned Duration (44d) | Critical w/High Planned Duration (44d) | 0 | 0% | 0 | 0%
Number of critical activities with a duration longer than 44 days.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical with Predecessor Lag | Critical with Predecessor Lag | 0 | 0% | 1 | 2%
Number of critical activities and milestones with lags.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical with Successor Lag | Critical with Successor Lag | 0 | 0% | 1 | 2%
Number of critical activities and milestones with lags.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical with Hard Constraints | Critical with Hard Constraints | 1 | 1% | 0 | 0%
Number of activities with hard or two-way constraints.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Negative Float with Predecessor Lag | Negative Float with Predecessor Lag | 0 | 0% | 1 | 2%
Number of critical activities and milestones with lags.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Negative Float with Successor Lag | Negative Float with Successor Lag | 0 | 0% | 1 | 2%
Number of critical activities and milestones with lags.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical CEI - Value Tasks | Critical CEI - Value Tasks | N/A |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical CEI - Total Tasks | Critical CEI - Total Tasks | 0 |  | 0
The number of tasks forecasted in the previous month's schedule (based on the prior schedule's status date) to be completed in the current month (time between prior schedule's satus date and current schedule's status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical CEI - Complete Tasks | Critical CEI - Complete Tasks | N/A | 44% | N/A
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical CEI - Incomplete Tasks | Critical CEI - Incomplete Tasks | N/A | 56% | N/A
The number of tasks that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Newly Critical Activities | Newly Critical Activities | 1 | 1% | 0 | 0%
How many remaining activities were added to the critical path this period
Id | Description | Critical | Previous_Critical | Original Duration | Remaining Duration | Start | Finish | Type | Status | Percent Complete | Total Float | Project
131 | Set HVAC trim and test and balance system | TRUE | FALSE | 20 | 20 | 2027-12-10 | 2028-01-06 | Normal | Planned | 0 | 0 | Project5_TAMPERED
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Activities No Longer Critical | Activities No Longer Critical | 34 | 24% | 0 | 0%
How many remaining activities are no longer on the critical path this period.
Id | Description | Critical | Previous_Critical | Original Duration | Remaining Duration | Start | Finish | Type | Status | Percent Complete | Total Float | Project
35 | Form column piers and spread foundations | FALSE | TRUE | 25 | 16 | 2026-08-17 | 2026-09-18 | Normal | InProgress | 36 | 19 | Project5_TAMPERED
38 | Set reinforcing and anchor bolts | FALSE | TRUE | 4 | 4 | 2026-09-21 | 2026-09-24 | Normal | Planned | 0 | 19 | Project5_TAMPERED
39 | Pour column piers and foundations | FALSE | TRUE | 21 | 21 | 2026-09-25 | 2026-10-23 | Normal | Planned | 0 | 19 | Project5_TAMPERED
42 | Cure piers and foundations | FALSE | TRUE | 7 | 7 | 2026-10-26 | 2026-11-03 | Normal | Planned | 0 | 19 | Project5_TAMPERED
44 | Strip column piers and foundation forms | FALSE | TRUE | 3 | 3 | 2026-11-04 | 2026-11-06 | Normal | Planned | 0 | 19 | Project5_TAMPERED
48 | Erect steel columns, beams and joist - 1st and 2nd floors | FALSE | TRUE | 10 | 10 | 2026-11-09 | 2026-11-20 | Normal | Planned | 0 | 19 | Project5_TAMPERED
49 | Erect steel columns, beams and joist - 3rd floor and roof | FALSE | TRUE | 17 | 17 | 2026-11-23 | 2026-12-15 | Normal | Planned | 0 | 19 | Project5_TAMPERED
51 | Install miscellaneous iron and bracing - 3rd floor and roof | FALSE | TRUE | 10 | 10 | 2026-12-16 | 2026-12-29 | Normal | Planned | 0 | 19 | Project5_TAMPERED
52 | Install stairs and miscellaneous iron railing | FALSE | TRUE | 10 | 10 | 2026-12-30 | 2027-01-12 | Normal | Planned | 0 | 19 | Project5_TAMPERED
53 | Touch-up paint on steel | FALSE | TRUE | 5 | 5 | 2027-01-13 | 2027-01-19 | Normal | Planned | 0 | 19 | Project5_TAMPERED
55 | Form 2nd floor including all floor openings | FALSE | TRUE | 17 | 17 | 2027-01-20 | 2027-02-11 | Normal | Planned | 0 | 19 | Project5_TAMPERED
57 | Pour 2nd floor slab | FALSE | TRUE | 4 | 4 | 2027-02-12 | 2027-02-17 | Normal | Planned | 0 | 19 | Project5_TAMPERED
58 | Cure 2nd floor slab | FALSE | TRUE | 7 | 7 | 2027-02-18 | 2027-02-26 | Normal | Planned | 0 | 19 | Project5_TAMPERED
60 | Form 3rd floor including all floor openings | FALSE | TRUE | 5 | 5 | 2027-03-01 | 2027-03-05 | Normal | Planned | 0 | 19 | Project5_TAMPERED
61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | FALSE | TRUE | 5 | 5 | 2027-03-01 | 2027-03-05 | Normal | Planned | 0 | 19 | Project5_TAMPERED
62 | Pour 3rd floor slab | FALSE | TRUE | 4 | 4 | 2027-03-08 | 2027-03-11 | Normal | Planned | 0 | 19 | Project5_TAMPERED
63 | Cure 3rd floor slab | FALSE | TRUE | 7 | 7 | 2027-03-12 | 2027-03-22 | Normal | Planned | 0 | 19 | Project5_TAMPERED
65 | Form roof slab including all floor openings | FALSE | TRUE | 5 | 5 | 2027-03-23 | 2027-03-29 | Normal | Planned | 0 | 19 | Project5_TAMPERED
66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | FALSE | TRUE | 5 | 5 | 2027-03-23 | 2027-03-29 | Normal | Planned | 0 | 19 | Project5_TAMPERED
67 | Pour roof slab | FALSE | TRUE | 4 | 4 | 2027-03-30 | 2027-04-02 | Normal | Planned | 0 | 19 | Project5_TAMPERED
68 | Cure roof slab | FALSE | TRUE | 7 | 7 | 2027-04-05 | 2027-04-13 | Normal | Planned | 0 | 19 | Project5_TAMPERED
69 | Strip forms from roof slab | FALSE | TRUE | 2 | 2 | 2027-04-14 | 2027-04-15 | Normal | Planned | 0 | 19 | Project5_TAMPERED
78 | Install exterior sheathing and metal studs | FALSE | TRUE | 15 | 15 | 2027-04-16 | 2027-05-06 | Normal | Planned | 0 | 19 | Project5_TAMPERED
82 | Install exterior masonry work | FALSE | TRUE | 25 | 25 | 2027-05-07 | 2027-06-10 | Normal | Planned | 0 | 19 | Project5_TAMPERED
94 | Install window wall aluminum and glass | FALSE | TRUE | 25 | 25 | 2027-06-11 | 2027-07-15 | Normal | Planned | 0 | 19 | Project5_TAMPERED
95 | Install interior stud walls and drywall | FALSE | TRUE | 25 | 25 | 2027-07-16 | 2027-08-19 | Normal | Planned | 0 | 19 | Project5_TAMPERED
96 | Install interior doors and hardware | FALSE | TRUE | 10 | 10 | 2027-09-10 | 2027-09-23 | Normal | Planned | 0 | 19 | Project5_TAMPERED
100 | Paint walls and woodwork | FALSE | TRUE | 20 | 20 | 2027-09-24 | 2027-10-21 | Normal | Planned | 0 | 19 | Project5_TAMPERED
106 | Install building carpet | FALSE | TRUE | 41 | 41 | 2027-10-22 | 2027-12-17 | Normal | Planned | 0 | 28 | Project5_TAMPERED
135 | Remove debris from building and do final clean-up | FALSE | TRUE | 4 | 4 | 2027-11-29 | 2027-12-02 | Normal | Planned | 0 | 19 | Project5_TAMPERED
138 | Complete elevator inspection and certification | FALSE | TRUE | 3 | 3 | 2027-12-03 | 2027-12-07 | Normal | Planned | 0 | 19 | Project5_TAMPERED
139 | Perform architect's inspection | FALSE | TRUE | 1 | 1 | 2027-12-08 | 2027-12-08 | Normal | Planned | 0 | 19 | Project5_TAMPERED
140 | Perform local building agency inspection | FALSE | TRUE | 1 | 1 | 2027-12-09 | 2027-12-09 | Normal | Planned | 0 | 19 | Project5_TAMPERED
141 | Perform Fire Marshal's inspection | FALSE | TRUE | 1 | 1 | 2027-12-10 | 2027-12-10 | Normal | Planned | 0 | 19 | Project5_TAMPERED

## NASA-Metrics-Performance-Perfo7
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH)
Baselined to Start | Scheduled to Start | Actual Starts | Baselined to Finish | Scheduled to Finish | Actual Finishes | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Score
126 | 126 | 29 | 126 | 126 | 27 | 8 | 4 | 6 | 7 | 6 | 5 | 86
[6 empty] | 44% | 22% | 33% | 39% | 33% | 28%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Start | Baselined to Start | 126 |  | 126
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Start | Scheduled to Start | 126 |  | 126
Number of activities that are planned to start.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Actual Starts | Actual Starts | 29 |  | 23
Number of activities that have started in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Finish | Baselined to Finish | 126 |  | 126
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Finish | Scheduled to Finish | 126 |  | 126
Number of activities within that are planned to finish.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Actual Finishes | Actual Finishes | 27 |  | 20
Number of activities that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Delayed (<=30 days) | Started Delayed (<=30 days) | 8 | 44% | 8 | 67%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Delayed (Between 31 to 60 days) | Started Delayed (Between 31 to 60 days) | 4 | 22% | 4 | 33%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Delayed (>60 days) | Started Delayed (>60 days) | 6 | 33% | 0 | 0%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed (<=30 days) | Completed Delayed (<=30 days) | 7 | 39% | 6 | 55%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed (Between 31 to 60 days) | Completed Delayed (Between 31 to 60 days) | 6 | 33% | 5 | 45%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed (>60 days) | Completed Delayed (>60 days) | 5 | 28% | 0 | 0%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0

## NASA-Metrics-Performance-Perfo8
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics)
Baselined to Start | Scheduled to Start | Actual Starts | Current Baselined to Start & Started | Past Baselined to Start & Started | Future Baseline to Start & Started | Baselined to Finish | Scheduled to Finish | Actual Finishes | Current Baselined to Finish & Finished | Past Baselined to Finish & Finished | Future Baselined to Finish & Finished | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Score
126 | 126 | 29 | 29 | 0 | 0 | 126 | 126 | 27 | 27 | 0 | 0 | 8 | 4 | 6 | 7 | 6 | 5 | 86
[12 empty] | 44% | 22% | 33% | 39% | 33% | 28%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Start | Baselined to Start | 126 |  | 126
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Start | Scheduled to Start | 126 |  | 126
Number of activities that are planned to start.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Actual Starts | Actual Starts | 29 |  | 23
Number of activities that have started in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baselined to Start & Started | Current Baselined to Start & Started | 29 |  | 23
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Past Baselined to Start & Started | Past Baselined to Start & Started | 0 |  | 0
Number of activities that have started in the current period with baseline start dates in the past (before current period).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Future Baseline to Start & Started | Future Baseline to Start & Started | 0 |  | 0
Number of activities that have started in the current period no matter their baseline start date.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Finish | Baselined to Finish | 126 |  | 126
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Finish | Scheduled to Finish | 126 |  | 126
Number of activities within that are planned to finish.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Actual Finishes | Actual Finishes | 27 |  | 20
Number of activities that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baselined to Finish & Finished | Current Baselined to Finish & Finished | 27 |  | 20
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Past Baselined to Finish & Finished | Past Baselined to Finish & Finished | 0 |  | 0
Number of that have finished in the current period with baseline finish dates in the past (before current period).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Future Baselined to Finish & Finished | Future Baselined to Finish & Finished | 0 |  | 0
Number of activities finishing or that have finished in the current period.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Delayed (<=30 days) | Started Delayed (<=30 days) | 8 | 44% | 8 | 67%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Delayed (Between 31 to 60 days) | Started Delayed (Between 31 to 60 days) | 4 | 22% | 4 | 33%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Delayed (>60 days) | Started Delayed (>60 days) | 6 | 33% | 0 | 0%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed (<=30 days) | Completed Delayed (<=30 days) | 7 | 39% | 6 | 55%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed (Between 31 to 60 days) | Completed Delayed (Between 31 to 60 days) | 6 | 33% | 5 | 45%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed (>60 days) | Completed Delayed (>60 days) | 5 | 28% | 0 | 0%
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0

## NASA-Metrics-Performance-Perfo9
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now
Baselined to Start - To Time Now | Scheduled to Start - To Time Now | Started | Started Late | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | BEI - Value Task Starts | Baselined to Finish - To Time Now | Scheduled to Finish - To Time Now | Finished | Finished Late | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | BEI - Value Task Finishes | Started - Future | Not Baselined to Start | Score
48 | 48 | 29 | 18 | 8 | 4 | 6 | 0.6 | 46 | 46 | 27 | 18 | 7 | 6 | 5 | 0.59 | 0 | 0 | 86
38% | 38% |  |  | 44% | 22% | 33% |  | 37% | 37% |  |  | 39% | 33% | 28% |  |  | 0%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Start - To Time Now | Baselined to Start - To Time Now | 48 | 38% | 29 | 23%
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Start - To Time Now | Scheduled to Start - To Time Now | 48 | 38% | 29 | 23%
Number of activities that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started | Started | 29 |  | 23
Number of activities starting or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Late | Started Late | 18 |  | 12
Number of activities finishing or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Delayed (<=30 days) | Started Delayed (<=30 days) | 8 | 44% | 8 | 67%
Number of activities that finished after their planned finish date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Delayed (Between 31 to 60 days) | Started Delayed (Between 31 to 60 days) | 4 | 22% | 4 | 33%
Number of activities that finished after their planned finish date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Delayed (>60 days) | Started Delayed (>60 days) | 6 | 33% | 0 | 0%
Number of activities that finished after their planned finish date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Task Starts | BEI - Value Task Starts | 0.6 |  | 0.79
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Finish - To Time Now | Baselined to Finish - To Time Now | 46 | 37% | 27 | 21%
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Finish - To Time Now | Scheduled to Finish - To Time Now | 46 | 37% | 27 | 21%
Number of activities within that are planned to finish.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Finished | Finished | 27 |  | 20
Number of activities finishing or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Finished Late | Finished Late | 18 |  | 11
Number of activities finishing or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed (<=30 days) | Completed Delayed (<=30 days) | 7 | 39% | 6 | 55%
Number of activities that finished after their planned finish date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed (Between 31 to 60 days) | Completed Delayed (Between 31 to 60 days) | 6 | 33% | 5 | 45%
Number of activities that finished after their planned finish date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed (>60 days) | Completed Delayed (>60 days) | 5 | 28% | 0 | 0%
Number of activities that finished after their planned finish date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Task Finishes | BEI - Value Task Finishes | 0.59 |  | 0.74
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started - Future | Started - Future | 0 |  | 0
Number of activities starting or that were baselined to start in the future, but have alread started
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Not Baselined to Start | Not Baselined to Start | 0 | 0% | 0 | 0%
Number of activities that are scheduled/baselined to start or that have started in the current period.

## NASA-Metrics-Performance-Perf10
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH)
BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Score
0.6 | 0.59 | 0 | 0.05 | 0.4 | 0.44 | 1.24 | 1.24 | 1.24 | 1.24 | 97 | 99 | 97 | 1.24 | 67
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Task Starts - Cumulative | BEI - Value Task Starts - Cumulative | 0.6 |  | 0.79
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Task Finishes - Cumulative | BEI - Value Task Finishes - Cumulative | 0.59 |  | 0.74
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Task Starts - by Status Dates | HMI - Value Task Starts - by Status Dates | 0 |  | N/A
Hit or Miss Index (HMI) calculation for task starts. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Task Finishes - by Status Dates | HMI - Value Task Finishes - by Status Dates | 0.05 |  | N/A
Hit or Miss Index (HMI) calculation for task finishes. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Task Starts - by Status Dates | CEI - Value Task Starts - by Status Dates | 0.4 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Task Finishes - by Status Dates | CEI - Value Task Finishes - by Status Dates | 0.44 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
FEI - Value Task Starts - Cumulative | FEI - Value Task Starts - Cumulative | 1.24 |  | 1.06
Future Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline for activities that have not yet started.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
FEI - Value Task Finish - Cumulative | FEI - Value Task Finish - Cumulative | 1.24 |  | 1.07
Future Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline for activities that have not yet started.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - BEI - Value Task Starts - Cumulative | To Go - BEI - Value Task Starts - Cumulative | 1.24 |  | 1.06
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - BEI - Value Task Finishes - Cumulative | To Go - BEI - Value Task Finishes - Cumulative | 1.24 |  | 1.07
To-Complete Baseline Execution Index (TC-BEI)
Id | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
34 | Excavate elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-05-22 |  | 2026-08-28 | Normal | InProgress
35 | Form column piers and spread foundations | Project5_TAMPERED | 2026-08-27 | 2026-05-26 |  | 2026-09-18 | Normal | InProgress
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - Planned Task Starts - Count | To Go - Planned Task Starts - Count | 97 |  | 103
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - BEI - Task Finishes - Count | To Go - BEI - Task Finishes - Count | 99 |  | 106
To-Complete Baseline Execution Index (TC-BEI)
Id | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
34 | Excavate elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-05-22 |  | 2026-08-28 | Normal | InProgress
35 | Form column piers and spread foundations | Project5_TAMPERED | 2026-08-27 | 2026-05-26 |  | 2026-09-18 | Normal | InProgress
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - Baselined Task Starts - Count | To Go - Baselined Task Starts - Count | 97 |  | 103
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - BEI - Value Task Starts - Cumulative | To Go - BEI - Value Task Starts - Cumulative | 1.24 |  | 1.06
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned

## NASA-Metrics-Performance-Perf11
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics)
Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Started | Current Baseline to Start & Started Past (Early Starts) | Current Baseline to Start & Started Future (Late Starts) | Current Baseline to Start & Not Started (Incomplete) | Baselined to Start - Check | Future Baseline to Start & Started (Early Starts) | Past Baseline to Finish & Finished - Check | Current Baseline to Finish & Finished - Check | Current Baseline to Finish & Finished Past - Check | Current Baseline to Finish & Finished Future - Check | Current Baseline to Finish & Not Finished - Check | Baselined to Finish - Check | Future Baseline to Finish & Finished - Check | Workoff Burden (Snapshot_Phase) (SEM01) | Workoff Burden - Starts To-Go (Total) (SEM07) | Past Baseline to Start & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Start & AlreadyDelayed (Workoff Burden) (SEM07) | Workoff Burden - Finishes To-Go (Total) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Score
0 | 29 | 0 | 0 | 97 | 126 | N/A | 0 | 27 | 0 | 0 | 99 | 126 | 0 | 6 | 97 | 19 | 78 | 99 | 19 | 80 | 0
86%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Past Baseline to Start & Started (Workoff Burden) | Past Baseline to Start & Started (Workoff Burden) | 0 |  | 0
Number of activities that have started in the current period with baseline start dates in the past (before current period).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Start & Started | Current Baseline to Start & Started | 29 |  | 23
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Start & Started Past (Early Starts) | Current Baseline to Start & Started Past (Early Starts) | 0 |  | 0
Number of activities that have started in the current period no matter their baseline start date.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Start & Started Future (Late Starts) | Current Baseline to Start & Started Future (Late Starts) | 0 |  | 0
Number of activities that have started in the current period no matter their baseline start date.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Start & Not Started (Incomplete) | Current Baseline to Start & Not Started (Incomplete) | 97 |  | 103
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Start - Check | Baselined to Start - Check | 126 |  | 126
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Future Baseline to Start & Started (Early Starts) | Future Baseline to Start & Started (Early Starts) | N/A |  | N/A
Number of activities that have started in the current period with baseline start dates in the past (before current period).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Past Baseline to Finish & Finished - Check | Past Baseline to Finish & Finished - Check | 0 |  | 0
Number of that have finished in the current period with baseline finish dates in the past (before current period).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Finish & Finished - Check | Current Baseline to Finish & Finished - Check | 27 |  | 20
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Finish & Finished Past - Check | Current Baseline to Finish & Finished Past - Check | 0 |  | 0
Number of activities finishing or that have finished in the current period.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Finish & Finished Future - Check | Current Baseline to Finish & Finished Future - Check | 0 |  | 0
Number of activities finishing or that have finished in the current period.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Finish & Not Finished - Check | Current Baseline to Finish & Not Finished - Check | 99 |  | 106
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Finish - Check | Baselined to Finish - Check | 126 |  | 126
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Future Baseline to Finish & Finished - Check | Future Baseline to Finish & Finished - Check | 0 |  | 0
Number of activities finishing or that have finished in the current period.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Workoff Burden (Snapshot_Phase) | Workoff Burden (Snapshot_Phase) | 6 | 86% | 0 | 0%
Workoff 30 Day Window
Id | Description | Project | Baseline Finish | ProjectTimeNowMinus30Days | Actual Finish | Project Time Now | Type
29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 2026-04-15 | 2026-07-28 | 2026-06-19 | 2026-08-27 | Normal
12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 2026-04-07 | 2026-07-28 | 2026-05-29 | 2026-08-27 | Normal
15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 2026-04-07 | 2026-07-28 | 2026-06-19 | 2026-08-27 | Normal
30 | Perform final site grading | Project5_TAMPERED | 2026-04-29 | 2026-07-28 | 2026-07-03 | 2026-08-27 | Normal
31 | Erect building batter boards and layout building | Project5_TAMPERED | 2026-05-06 | 2026-07-28 | 2026-07-31 | 2026-08-27 | Normal
33 | Excavate foundations | Project5_TAMPERED | 2026-05-20 | 2026-07-28 | 2026-08-07 | 2026-08-27 | Normal
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Workoff Burden - Starts To-Go (Total) | Workoff Burden - Starts To-Go (Total) | 97 |  | 103
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Past Baseline to Start & Not Finished (Workoff Burden) | Past Baseline to Start & Not Finished (Workoff Burden) | 19 |  | 6
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Future Baseline to Start & AlreadyDelayed (Workoff Burden) | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | 78 |  | 97
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Workoff Burden - Finishes To-Go (Total) | Workoff Burden - Finishes To-Go (Total) | 99 |  | 106
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
34 | 2026-05-21 | 2026-08-10 | 2026-08-10 | Excavate elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-05-22 |  | 2026-08-28 | Normal | InProgress
35 | 2026-05-21 | 2026-08-17 | 2026-08-17 | Form column piers and spread foundations | Project5_TAMPERED | 2026-08-27 | 2026-05-26 |  | 2026-09-18 | Normal | InProgress
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Past Baseline to Finish & Not Finished (Workoff Burden) | Past Baseline to Finish & Not Finished (Workoff Burden) | 19 |  | 7
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
34 | 2026-05-21 | 2026-08-10 | 2026-08-10 | Excavate elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-05-22 |  | 2026-08-28 | Normal | InProgress
35 | 2026-05-21 | 2026-08-17 | 2026-08-17 | Form column piers and spread foundations | Project5_TAMPERED | 2026-08-27 | 2026-05-26 |  | 2026-09-18 | Normal | InProgress
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Future Baseline to Finish & Already Delayed (Workoff Burden) | Future Baseline to Finish & Already Delayed (Workoff Burden) | 80 |  | 99
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned

## NASA-Metrics-Performance-Perf12
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH)
Current Baseline to Start & Started (BL Plan) | Future Baseline to Start & Started (Early Starts) | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Finish & Finished (BL Plan) | Future Baseline to Finish & Finished (Early Finishes) | Past Baseline to Finish & Finished (Workoff Burden) | Current Baseline to Finish & Not Finished (Incompletes) | Past Baseline to Start & Not Started (Workoff Burden) (SEM07) | Future Baseline to Start & Already Delayed (Workoff Burden) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Score
29 | N/A | 0 | 97 | 27 | 0 | 0 | 99 | 19 | 78 | 19 | 80 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Start & Started (BL Plan) | Current Baseline to Start & Started (BL Plan) | 29 |  | 23
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Future Baseline to Start & Started (Early Starts) | Future Baseline to Start & Started (Early Starts) | N/A |  | N/A
Number of activities that have started in the current period with baseline start dates in the past (before current period).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Past Baseline to Start & Started (Workoff Burden) | Past Baseline to Start & Started (Workoff Burden) | 0 |  | 0
Number of activities that have started in the current period with baseline start dates in the past (before current period).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Start & Not Started (Incompletes) | 97 |  | 103
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Finish & Finished (BL Plan) | Current Baseline to Finish & Finished (BL Plan) | 27 |  | 20
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Future Baseline to Finish & Finished (Early Finishes) | Future Baseline to Finish & Finished (Early Finishes) | 0 |  | 0
Number of activities finishing or that have finished in the current period.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Past Baseline to Finish & Finished (Workoff Burden) | Past Baseline to Finish & Finished (Workoff Burden) | 0 |  | 0
Number of that have finished in the current period with baseline finish dates in the past (before current period).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Current Baseline to Finish & Not Finished (Incompletes) | Current Baseline to Finish & Not Finished (Incompletes) | 99 |  | 106
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Past Baseline to Start & Not Started (Workoff Burden) | Past Baseline to Start & Not Started (Workoff Burden) | 19 |  | 6
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Future Baseline to Start & Already Delayed (Workoff Burden) | Future Baseline to Start & Already Delayed (Workoff Burden) | 78 |  | 97
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Past Baseline to Finish & Not Finished (Workoff Burden) | Past Baseline to Finish & Not Finished (Workoff Burden) | 19 |  | 7
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
34 | 2026-05-21 | 2026-08-10 | 2026-08-10 | Excavate elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-05-22 |  | 2026-08-28 | Normal | InProgress
35 | 2026-05-21 | 2026-08-17 | 2026-08-17 | Form column piers and spread foundations | Project5_TAMPERED | 2026-08-27 | 2026-05-26 |  | 2026-09-18 | Normal | InProgress
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Future Baseline to Finish & Already Delayed (Workoff Burden) | Future Baseline to Finish & Already Delayed (Workoff Burden) | 80 |  | 99
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned

## NASA-Metrics-Performance-Perf13
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now
Baselined to Start | Scheduled to Start | Started - Scheduled | Started - Baseline Comparison | BEI - Value Task Starts | HMI - Value Task Starts | CEI - Value Task Starts | Baselined to Finish | Scheduled to Finish | Finished | BEI - Value Task Finishes | HMI - Value Task Finishes | CEI - Value Task Finishes | Status Date | Score
48 | 48 | 29 | 29 | 0.6 | 0 | 0.46 | 46 | 46 | 27 | 0.59 | 0.05 | 0.44 | 2026-08-27 | 100
| 100% | 60% | 60%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Start | Baselined to Start | 48 |  | 29
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Start | Scheduled to Start | 48 | 100% | 29 | 100%
Number of activities that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started - Scheduled | Started - Scheduled | 29 | 60% | 23 | 79%
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started - Baseline Comparison | Started - Baseline Comparison | 29 | 60% | 23 | 79%
Number of activities baselined in the current period that have started (at any time).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Task Starts | BEI - Value Task Starts | 0.6 |  | 0.79
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Task Starts | HMI - Value Task Starts | 0 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Task Starts | CEI - Value Task Starts | 0.46 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Finish | Baselined to Finish | 46 |  | 27
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Scheduled to Finish | Scheduled to Finish | 46 |  | 27
Number of activities within that are planned to finish.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Finished | Finished | 27 |  | 20
Number of activities finishing or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Task Finishes | BEI - Value Task Finishes | 0.59 |  | 0.74
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Task Finishes | HMI - Value Task Finishes | 0.05 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Task Finishes | CEI - Value Task Finishes | 0.44 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Performance-Perf14
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics
Started (incl. Future Baseline Starts) - Scheduled | Started (incl. Future Baseline Starts) - Baseline Comparison | Started Late (from Baseline) | Finished (incl. Future Baseline Finishes) - Scheduled | Finished (incl. Future Baseline Finishes) - Baseline Comparison | Finished Late | Score
29 | 29 | 18 | 27 | 27 | 18 | 100
23% | 23% | N/A | 21% | 21%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started (incl. Future Baseline Starts) - Scheduled | Started (incl. Future Baseline Starts) - Scheduled | 29 | 23% | 23 | 18%
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started (incl. Future Baseline Starts) - Baseline Comparison | Started (incl. Future Baseline Starts) - Baseline Comparison | 29 | 23% | 23 | 18%
Number of activities baselined in the current period that have started (at any time).
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Late (from Baseline) | Started Late (from Baseline) | 18 |  | 12
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Finished (incl. Future Baseline Finishes) - Scheduled | Finished (incl. Future Baseline Finishes) - Scheduled | 27 | 21% | 20 | 16%
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Finished (incl. Future Baseline Finishes) - Baseline Comparison | Finished (incl. Future Baseline Finishes) - Baseline Comparison | 27 | 21% | 20 | 16%
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Finished Late | Finished Late | 18 |  | 11
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0

## NASA-Metrics-Performance-Perf15
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST
Completed Ahead | Completed Delayed | Completed On-Schedule | Accelerated | Days Variance | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Variance | Actually Finished | Took Longer than Planned | Took Less Than Planned | Completed (w/Baseline Duration) | Completed (w/o Baseline Duration) | Completed (w/Baseline Dur=0) | Baseline-to-Date Completed Tasks | Missed Durations | Missed Durations & Late Actual Finish | Score
0 | 18 | 9 | 0 | 705 | 0 | 705 | 0 | 39 | 26 | 27 | 7 | 6 | 27 | 0 | 0 | 27 | 7 | 7 | 0
0% | 67% | 33% | 0% | 2611% | 0% | 2611% |  |  |  | 21% | 26% | 22% | 21% | 0% | 0% | 59% | 26% | 26%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Ahead | Completed Ahead | 0 | 0% | 0 | 0%
Number of activities that finished before their planned finish date
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed | Completed Delayed | 18 | 67% | 11 | 55%
Number of activities that finished after their planned finish date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed On-Schedule | Completed On-Schedule | 9 | 33% | 9 | 45%
Number of activities that completed on time.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Accelerated | Accelerated | 0 | 0% | 0 | 0%
Number of activities that started after their planned start date but finished before or on their planned finish date.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Days Variance | Days Variance | 705 | 2611% | 277 | 1385%
Total variance (in days) between activities that started early and those that started late.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Days Early | Days Early | 0 | 0% | 0 | 0%
A calculation of the total number of days saved by activities that finished early.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Days Late | Days Late | 705 | 2611% | 277 | 1385%
A calculation of the total number of days lost by activities that started late.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg Days Early | Avg Days Early | 0 |  | 0
Average number of days that all activities within a grouping finished early (before the baseline start date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg Days Late | Avg Days Late | 39 |  | 25
Average number of days that all activities within a grouping finished late (after the baseline start date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg Variance | Avg Variance | 26 |  | 14
Average variance (in days) between activities that started early and those that started late.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Actually Finished | Actually Finished | 27 | 21% | 20 | 16%
Number of activities that have finished.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Took Longer than Planned | Took Longer than Planned | 7 | 26% | 4 | 20%
Number of activities that took longer than forecasted.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Took Less Than Planned | Took Less Than Planned | 6 | 22% | 2 | 10%
Number of activities that took less than forecasted.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed (w/Baseline Duration) | Completed (w/Baseline Duration) | 27 | 21% | 20 | 16%
Total number of completed activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed (w/o Baseline Duration) | Completed (w/o Baseline Duration) | 0 | 0% | 0 | 0%
Total number of completed activities.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed (w/Baseline Dur=0) | Completed (w/Baseline Dur=0) | 0 | 0% | 0 | 0%
Total number of completed activities.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baseline-to-Date Completed Tasks | Baseline-to-Date Completed Tasks | 27 | 59% | 20 | 74%
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missed Durations | Missed Durations | 7 | 26% | 4 | 20%
Number of activities that have slipped from their baseline duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missed Durations & Late Actual Finish | Missed Durations & Late Actual Finish | 7 | 26% | 4 | 20%
Number of activities that have slipped from their baseline duration and finish date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0

## NASA-Metrics-Performance-Perf16
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST
Completed Ahead | Completed Delayed | Completed On-Schedule | Accelerated | Days Variance | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Variance | Actually Finished | Took Longer than Planned | Took Less Than Planned | Completed (w/Baseline Duration) | Completed (w/o Baseline Duration) | Completed (w/Baseline Dur=0) | Baseline-to-Date Completed Tasks | Missed Durations | Missed Durations & Late Actual Finish | Score
0 | 18 | 9 | 0 | 705 | 0 | 705 | 0 | 39 | 26 | 27 | 7 | 6 | 27 | 0 | 0 | 27 | 7 | 7 | 0
0% | 67% | 33% | 0% | 2611% | 0% | 2611% |  |  |  | 21% | 26% | 22% | 21% | 0% | 0% | 59% | 26% | 26%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Ahead | Completed Ahead | 0 | 0% | 0 | 0%
Number of activities that finished before their planned finish date
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Delayed | Completed Delayed | 18 | 67% | 11 | 55%
Number of activities that finished after their planned finish date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed On-Schedule | Completed On-Schedule | 9 | 33% | 9 | 45%
Number of activities that completed on time.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Accelerated | Accelerated | 0 | 0% | 0 | 0%
Number of activities that started after their planned start date but finished before or on their planned finish date.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Days Variance | Days Variance | 705 | 2611% | 277 | 1385%
Total variance (in days) between activities that started early and those that started late.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Days Early | Days Early | 0 | 0% | 0 | 0%
A calculation of the total number of days saved by activities that finished early.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Days Late | Days Late | 705 | 2611% | 277 | 1385%
A calculation of the total number of days lost by activities that started late.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg Days Early | Avg Days Early | 0 |  | 0
Average number of days that all activities within a grouping finished early (before the baseline start date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg Days Late | Avg Days Late | 39 |  | 25
Average number of days that all activities within a grouping finished late (after the baseline start date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Avg Variance | Avg Variance | 26 |  | 14
Average variance (in days) between activities that started early and those that started late.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Actually Finished | Actually Finished | 27 | 21% | 20 | 16%
Number of activities that have finished.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Took Longer than Planned | Took Longer than Planned | 7 | 26% | 4 | 20%
Number of activities that took longer than forecasted.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Took Less Than Planned | Took Less Than Planned | 6 | 22% | 2 | 10%
Number of activities that took less than forecasted.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed (w/Baseline Duration) | Completed (w/Baseline Duration) | 27 | 21% | 20 | 16%
Total number of completed activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed (w/o Baseline Duration) | Completed (w/o Baseline Duration) | 0 | 0% | 0 | 0%
Total number of completed activities.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed (w/Baseline Dur=0) | Completed (w/Baseline Dur=0) | 0 | 0% | 0 | 0%
Total number of completed activities.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baseline-to-Date Completed Tasks | Baseline-to-Date Completed Tasks | 27 | 59% | 20 | 74%
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missed Durations | Missed Durations | 7 | 26% | 4 | 20%
Number of activities that have slipped from their baseline duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missed Durations & Late Actual Finish | Missed Durations & Late Actual Finish | 7 | 26% | 4 | 20%
Number of activities that have slipped from their baseline duration and finish date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0

## NASA-Metrics-Performance-Perf17
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New
Baselined Tasks | Baselined to Start - TOTAL | Complete Task Starts - Cumulative | Incomplete Task Starts - Cumulative (in work) | Old Incomplete Task Starts in Status Period | Baselined to Finish | Complete Task Finishes - Cumulative (in work) | Incomplete Task Finishes - Cumulative | Old Incomplete Task Finishes in Status Period | Old Completed Task Finishes in Status Period | Score
126 | 126 | 29 | 19 | N/A | 126 | 27 | 19 | N/A | N/A | 100
|  | 60% | 40% |  |  | 59% | 59%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined Tasks | Baselined Tasks | 126 |  | 126
The total number of baselined tasks.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Actual Duration | Start | Finish | Actual Start | Baseline Start | Baseline Finish | Actual Finish | Type | Status | Total Float
FALSE |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | Standard | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-02 | 2026-03-04 | 2026-03-04 | Normal | Complete | 0
FALSE |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | Standard | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-05 | 2026-03-10 | 2026-03-10 | Normal | Complete | 0
FALSE |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | Standard | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | Standard | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-05 | 2026-03-06 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | Standard | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-05 | 2026-03-06 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | Standard | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-06 | 2026-03-19 | 2026-03-27 | Normal | Complete | 0
FALSE |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | Standard | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-09 | 2026-03-11 | 2026-03-11 | Normal | Complete | 0
FALSE |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | Standard | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-12 | 2026-03-16 | 2026-03-25 | Normal | Complete | 0
FALSE |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | Standard | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-25 | 2026-03-26 | 2026-03-26 | Normal | Complete | 0
FALSE |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | Standard | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-17 | 2026-03-18 | 2026-03-27 | Normal | Complete | 0
FALSE |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | Standard | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-27 | 2026-03-30 | 2026-03-30 | Normal | Complete | 0
FALSE |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | Standard | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-03-20 | 2026-06-11 | 2026-06-19 | Normal | Complete | 0
FALSE |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | Standard | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | Standard | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-03-11 | 2026-03-24 | 2026-05-04 | Normal | Complete | 0
FALSE |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | Standard | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-03-19 | 2026-03-23 | 2026-04-08 | Normal | Complete | 0
FALSE |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | Standard | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-03-24 | 2026-03-25 | 2026-04-14 | Normal | Complete | 0
FALSE |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | Standard | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-03-26 | 2026-04-01 | 2026-04-21 | Normal | Complete | 0
FALSE |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | Standard | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-04-02 | 2026-04-15 | 2026-05-19 | Normal | Complete | 0
FALSE |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | Standard | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-04-02 | 2026-04-15 | 2026-06-19 | Normal | Complete | 0
FALSE |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | Standard | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-03-25 | 2026-04-07 | 2026-05-29 | Normal | Complete | 0
FALSE |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | Standard | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-03-25 | 2026-04-07 | 2026-05-18 | Normal | Complete | 0
FALSE |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | Standard | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-03-25 | 2026-04-07 | 2026-05-15 | Normal | Complete | 0
FALSE |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | Standard | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-03-25 | 2026-04-07 | 2026-05-18 | Normal | Complete | 0
FALSE |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | Standard | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-03-25 | 2026-04-07 | 2026-06-19 | Normal | Complete | 0
FALSE |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | Standard | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-04-16 | 2026-04-29 | 2026-07-03 | Normal | Complete | 0
FALSE |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | Standard | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-04-30 | 2026-05-06 | 2026-07-31 | Normal | Complete | 0
FALSE |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | Standard | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-05-07 | 2026-05-20 | 2026-08-07 | Normal | Complete | 0
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 14 | 2026-08-10 | 2026-08-28 | 2026-08-10 | 2026-05-21 | 2026-05-22 |  | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 9 | 2026-08-17 | 2026-09-18 | 2026-08-17 | 2026-05-21 | 2026-05-26 |  | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 0 | 2026-08-31 | 2026-09-03 |  | 2026-05-25 | 2026-05-28 |  | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 0 | 2026-09-21 | 2026-09-24 |  | 2026-05-27 | 2026-06-01 |  | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 0 | 2026-09-25 | 2026-09-30 |  | 2026-06-02 | 2026-06-05 |  | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 0 | 2026-09-25 | 2026-10-23 |  | 2026-06-02 | 2026-06-08 |  | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 0 | 2026-10-26 | 2026-10-26 |  | 2026-06-09 | 2026-06-09 |  | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 0 | 2026-10-26 | 2026-11-03 |  | 2026-06-09 | 2026-06-17 |  | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 0 | 2026-11-04 | 2026-11-06 |  | 2026-06-18 | 2026-06-22 |  | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2026-11-09 | 2026-11-20 |  | 2026-06-23 | 2026-07-06 |  | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 0 | 2026-11-23 | 2026-12-01 |  | 2026-06-23 | 2026-07-01 |  | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 0 | 2026-11-23 | 2026-12-15 |  | 2026-07-07 | 2026-07-20 |  | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 0 | 2026-12-02 | 2026-12-02 |  | 2026-07-02 | 2026-07-02 |  | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 0 | 2026-12-03 | 2026-12-07 |  | 2026-07-03 | 2026-07-07 |  | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 0 | 2026-12-08 | 2026-12-08 |  | 2026-07-08 | 2026-07-08 |  | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2026-12-16 | 2026-12-29 |  | 2026-07-21 | 2026-08-03 |  | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 0 | 2026-12-16 | 2026-12-22 |  | 2026-07-07 | 2026-07-13 |  | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2026-12-30 | 2027-01-12 |  | 2026-08-04 | 2026-08-17 |  | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 0 | 2027-01-13 | 2027-02-18 |  | 2026-08-18 | 2026-08-31 |  | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 0 | 2027-01-13 | 2027-01-19 |  | 2026-08-18 | 2026-08-24 |  | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 0 | 2027-01-20 | 2027-02-11 |  | 2026-08-25 | 2026-08-31 |  | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 0 | 2027-02-12 | 2027-02-17 |  | 2026-09-01 | 2026-09-04 |  | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 0 | 2027-02-18 | 2027-02-26 |  | 2026-09-07 | 2026-09-15 |  | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 0 | 2027-02-19 | 2027-03-18 |  | 2026-09-01 | 2026-09-28 |  | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 0 | 2027-03-01 | 2027-03-05 |  | 2026-09-16 | 2026-09-22 |  | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 0 | 2027-03-01 | 2027-03-05 |  | 2026-09-16 | 2026-09-22 |  | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 0 | 2027-03-08 | 2027-03-09 |  | 2026-09-23 | 2026-09-24 |  | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 0 | 2027-03-08 | 2027-03-11 |  | 2026-09-23 | 2026-09-28 |  | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 0 | 2027-03-10 | 2027-03-15 |  | 2026-09-25 | 2026-09-30 |  | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 0 | 2027-03-10 | 2027-03-15 |  | 2026-09-25 | 2026-09-30 |  | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 0 | 2027-03-12 | 2027-03-22 |  | 2026-09-29 | 2026-10-07 |  | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 0 | 2027-03-16 | 2027-03-22 |  | 2026-10-01 | 2026-10-07 |  | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 0 | 2027-03-16 | 2027-03-22 |  | 2026-10-01 | 2026-10-07 |  | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 0 | 2027-03-19 | 2027-04-15 |  | 2026-09-29 | 2026-10-26 |  | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2027-03-19 | 2027-04-01 |  | 2026-09-29 | 2026-10-12 |  | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 0 | 2027-03-23 | 2027-03-29 |  | 2026-10-08 | 2026-10-14 |  | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 0 | 2027-03-23 | 2027-03-29 |  | 2026-10-08 | 2026-10-14 |  | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 0 | 2027-03-23 | 2027-03-26 |  | 2026-10-08 | 2026-10-13 |  | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 0 | 2027-03-30 | 2027-03-31 |  | 2026-10-15 | 2026-10-16 |  | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 0 | 2027-03-30 | 2027-04-02 |  | 2026-10-15 | 2026-10-20 |  | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 0 | 2027-04-01 | 2027-04-09 |  | 2026-10-19 | 2026-10-27 |  | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 0 | 2027-04-05 | 2027-04-13 |  | 2026-10-21 | 2026-10-29 |  | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 0 | 2027-04-14 | 2027-04-15 |  | 2026-10-30 | 2026-11-02 |  | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 0 | 2027-04-16 | 2027-04-19 |  | 2026-11-03 | 2026-11-04 |  | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 0 | 2027-04-16 | 2027-05-06 |  | 2026-11-03 | 2026-11-23 |  | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2027-04-16 | 2027-04-29 |  | 2026-10-27 | 2026-11-09 |  | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 0 | 2027-04-20 | 2027-05-17 |  | 2026-11-05 | 2026-12-02 |  | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 0 | 2027-04-20 | 2027-05-17 |  | 2026-11-05 | 2026-12-02 |  | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 0 | 2027-04-20 | 2027-05-17 |  | 2026-11-05 | 2026-12-02 |  | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2027-04-30 | 2027-05-13 |  | 2026-11-10 | 2026-11-23 |  | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 0 | 2027-05-07 | 2027-06-10 |  | 2026-11-24 | 2026-12-28 |  | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2027-05-18 | 2027-05-31 |  | 2026-12-03 | 2026-12-16 |  | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 0 | 2027-06-01 | 2027-06-07 |  | 2026-12-17 | 2026-12-23 |  | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 0 | 2027-06-11 | 2027-06-17 |  | 2026-12-29 | 2027-01-04 |  | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 0 | 2027-06-11 | 2027-06-16 |  | 2026-12-29 | 2027-01-01 |  | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 0 | 2027-06-11 | 2027-07-15 |  | 2026-12-29 | 2027-02-01 |  | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 0 | 2027-06-17 | 2027-06-18 |  | 2027-01-04 | 2027-01-05 |  | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2027-06-18 | 2027-07-01 |  | 2027-01-05 | 2027-01-18 |  | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 0 | 2027-06-21 | 2027-06-22 |  | 2027-01-06 | 2027-01-07 |  | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 0 | 2027-06-30 | 2027-07-06 |  | 2027-01-15 | 2027-01-21 |  | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 0 | 2027-07-07 | 2027-07-13 |  | 2027-01-22 | 2027-01-28 |  | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2027-07-14 | 2027-07-27 |  | 2027-01-29 | 2027-02-11 |  | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 0 | 2027-07-16 | 2027-08-19 |  | 2027-02-02 | 2027-03-08 |  | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 0 | 2027-07-16 | 2027-08-05 |  | 2027-02-02 | 2027-02-22 |  | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 0 | 2027-07-16 | 2027-08-05 |  | 2027-02-02 | 2027-02-22 |  | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 0 | 2027-07-16 | 2027-08-12 |  | 2027-02-02 | 2027-03-01 |  | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 0 | 2027-07-28 | 2027-08-17 |  | 2027-02-12 | 2027-03-04 |  | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 0 | 2027-08-06 | 2027-09-02 |  | 2027-02-23 | 2027-03-22 |  | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 0 | 2027-08-13 | 2027-09-02 |  | 2027-03-02 | 2027-03-22 |  | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 0 | 2027-08-20 | 2027-09-09 |  | 2027-03-09 | 2027-03-29 |  | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 0 | 2027-08-20 | 2027-09-09 |  | 2027-03-09 | 2027-03-29 |  | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 0 | 2027-08-20 | 2027-08-26 |  | 2027-03-09 | 2027-03-15 |  | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 0 | 2027-08-27 | 2027-09-01 |  | 2027-03-16 | 2027-03-19 |  | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 0 | 2027-09-03 | 2027-09-23 |  | 2027-03-23 | 2027-04-12 |  | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2027-09-10 | 2027-09-23 |  | 2027-03-30 | 2027-04-12 |  | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2027-09-10 | 2027-09-23 |  | 2027-03-30 | 2027-04-12 |  | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2027-09-10 | 2027-09-23 |  | 2027-03-30 | 2027-04-12 |  | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 0 | 2027-09-24 | 2027-10-21 |  | 2027-04-13 | 2027-05-10 |  | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2027-09-24 | 2027-10-07 |  | 2027-04-13 | 2027-04-26 |  | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 0 | 2027-09-24 | 2027-10-14 |  | 2027-04-13 | 2027-05-03 |  | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 0 | 2027-10-15 | 2027-10-18 |  | 2027-05-18 | 2027-05-19 |  | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2027-10-19 | 2027-11-01 |  | 2027-05-04 | 2027-05-17 |  | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2027-10-22 | 2027-11-04 |  | 2027-05-11 | 2027-05-24 |  | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 0 | 2027-10-22 | 2027-12-17 |  | 2027-05-11 | 2027-06-07 |  | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 0 | 2027-10-22 | 2027-11-26 |  | 2027-05-11 | 2027-05-31 |  | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2027-10-22 | 2027-11-04 |  | 2027-05-11 | 2027-05-24 |  | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2027-10-22 | 2027-11-04 |  | 2027-05-11 | 2027-05-24 |  | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2027-11-05 | 2027-11-18 |  | 2027-05-25 | 2027-06-07 |  | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 0 | 2027-11-29 | 2027-12-02 |  | 2027-06-08 | 2027-06-11 |  | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 0 | 2027-12-03 | 2027-12-03 |  | 2027-06-14 | 2027-06-14 |  | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 0 | 2027-12-03 | 2027-12-07 |  | 2027-06-14 | 2027-06-16 |  | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 0 | 2027-12-08 | 2027-12-08 |  | 2027-06-17 | 2027-06-17 |  | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 0 | 2027-12-09 | 2027-12-09 |  | 2027-06-18 | 2027-06-18 |  | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 0 | 2027-12-10 | 2028-01-06 |  | 2027-05-20 | 2027-06-16 |  | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 0 | 2027-12-10 | 2027-12-10 |  | 2027-06-21 | 2027-06-21 |  | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 0 | 2028-01-07 | 2028-01-20 |  | 2027-06-22 | 2027-07-05 |  | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 0 | 2028-01-21 | 2028-01-24 |  | 2027-07-06 | 2027-07-07 |  | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 0 | 2028-01-25 | 2028-01-25 |  | 2027-07-08 | 2027-07-08 |  | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 0 | 2028-01-26 | 2028-01-26 |  | 2027-07-09 | 2027-07-09 |  | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Start - TOTAL | Baselined to Start - TOTAL | 126 |  | 126
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Created | Actual Start | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 2026-03-02 | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE |  | 2026-03-05 | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE |  | 2026-03-05 | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE |  | 2026-03-05 | 100 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 2026-03-05 | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 2026-03-06 | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE |  | 2026-03-09 | 100 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE |  | 2026-03-12 | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE |  | 2026-03-25 | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE |  | 2026-03-26 | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE |  | 2026-03-27 | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE |  | 2026-03-30 | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE |  | 2026-03-31 | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 2026-04-02 | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE |  | 2026-04-06 | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE |  | 2026-04-13 | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE |  | 2026-04-15 | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 2026-04-22 | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 2026-04-22 | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 2026-05-05 | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 2026-05-05 | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 2026-05-05 | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 2026-05-05 | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 2026-06-08 | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 2026-06-22 | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE |  | 2026-07-06 | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE |  | 2026-08-03 | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
FALSE |  | 2026-08-10 | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 2026-08-17 | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Complete Task Starts - Cumulative | Complete Task Starts - Cumulative | 29 | 60% | 23 | 79%
The total number (cumulative) of tasks that were baselined to start and started.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Start | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Incomplete Task Starts - Cumulative (in work) | Incomplete Task Starts - Cumulative (in work) | 19 | 40% | 6 | 21%
The total number (cumulative) of tasks that were baselined to start but did not start.
Excluded | Created | Actual Start | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Old Incomplete Task Starts in Status Period | Old Incomplete Task Starts in Status Period | N/A |  | N/A
The total number (cumulative) of tasks were created prior to the current status period and baselined to start but did not start.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baselined to Finish | Baselined to Finish | 126 |  | 126
Number of activities that are baselined to finish or that have finished in the current period.
Excluded | Created | Percent Complete | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE |  | 100 | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE |  | 100 | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE |  | 100 | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
FALSE |  | 93 | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Complete Task Finishes - Cumulative (in work) | Complete Task Finishes - Cumulative (in work) | 27 | 59% | 20 | 74%
The total number (cumulative) of tasks that were baselined to finish and finshed.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Incomplete Task Finishes - Cumulative | Incomplete Task Finishes - Cumulative | 19 | 59% | 7 | 74%
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Old Incomplete Task Finishes in Status Period | Old Incomplete Task Finishes in Status Period | N/A |  | N/A
The total number (cumulative) of tasks that were created prior to the current status period and baselined to complete but did not complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Old Completed Task Finishes in Status Period | Old Completed Task Finishes in Status Period | N/A |  | N/A
The total number (cumulative) of tasks that were were created prior to the current status period and baselined to complete and completed.

## NASA-Metrics-Performance-Basel
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA Metrics Performance Baseline Execution Index (BEI)
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Baseline Execution Index (BEI)
|  | BEI - Tasks | BEI - Milestones
Ribbons | Project2 | 100 | 100
Ribbons | Project5_TAMPERED | 100 | 100
|  | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks
|  | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | Score
Ribbons | Project2 | 0.74 | 27 | 20 | 7 | 0.74 | 20 | N/A | 2026-05-24 | 100
Ribbons |  |  |  | 74% | 26% |  | 74%
Ribbons | Project5_TAMPERED | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | 100
Ribbons |  |  |  | 59% | 41% |  | 59%
|  | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones
|  | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | Score
Ribbons | Project2 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 100
Ribbons |  |  |  | N/A | N/A |  | N/A
Ribbons | Project5_TAMPERED | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 100
Ribbons |  |  |  | N/A | N/A |  | N/A

## NASA-Metrics-Performance-Basel2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance-Basel -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks
BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | Score
0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | 100
|  | 59% | 41% |  | 59%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Tasks | BEI - Value Tasks | 0.59 |  | 0.74
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Total Tasks | BEI - Total Tasks | 46 |  | 27
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Complete Tasks | BEI - Complete Tasks | 27 | 59% | 20 | 74%
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Incomplete Tasks | BEI - Incomplete Tasks | 19 | 41% | 7 | 26%
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Tasks (adjusted) | BEI - Value Tasks (adjusted) | 0.59 |  | 0.74
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline. Takes credit for future-baselined activities that are complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Complete Tasks (adjusted) | BEI - Complete Tasks (adjusted) | 27 | 59% | 20 | 74%
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Complete Future Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | N/A |  | N/A
The total number tasks that are baselined to complete in the future and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Performance-Basel3
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance-Basel -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones
BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | Score
N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 100
|  | N/A | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Milestones | BEI - Value Milestones | N/A |  | N/A
Baseline Execution Index (BEI) calculation for milestones. A cumulative measure of IMS milestone performance against the baseline.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Total Milestones | BEI - Total Milestones | 0 |  | 0
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Complete Milestones | BEI - Complete Milestones | N/A |  | N/A
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Incomplete Milestones | BEI - Incomplete Milestones | N/A |  | N/A
The total number (cumulative) of milestones that were baselined to complete but did not complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Milestones (adjusted) | BEI - Value Milestones (adjusted) | N/A |  | N/A
Baseline Execution Index (BEI) calculation for milestones. A cumulative measure of IMS milestone performance against the baseline. Takes credit for future-baselined milestones that are complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Complete Milestones (adjusted) | BEI - Complete Milestones (adjusted) | N/A |  | N/A
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined milestones that are complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Complete Future Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | N/A |  | N/A
The total number of milestones that are baselined to complete in the future and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined milestones that are complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Performance-Hit-o
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA Metrics Performance Hit or Miss Index (HMI)
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hit or Miss Index (HMI)
|  | HMI - Tasks | HMI - Milestones
Ribbons | Project2 | 100 | 100
Ribbons | Project5_TAMPERED | 100 | 100
|  | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks
|  | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Score
Ribbons | Project2 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons |  |  |  | N/A | N/A | N/A |  | N/A
Ribbons | Project5_TAMPERED | 0.05 | 19 | 1 | N/A | 18 | 0.05 | 1 | N/A | 100
Ribbons |  |  |  | 5% | 0% | 95% |  | 5%
|  | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones
|  | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Score
Ribbons | Project2 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons |  |  |  | N/A | N/A | N/A |  | N/A
Ribbons | Project5_TAMPERED | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons |  |  |  | N/A | N/A | N/A |  | N/A

## NASA-Metrics-Performance-Hit-o2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance-Hit-o -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks
HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Score
0.05 | 19 | 1 | N/A | 18 | 0.05 | 1 | N/A | 100
|  | 5% | 0% | 95% |  | 5%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Tasks | HMI - Value Tasks | 0.05 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Total Tasks | HMI - Total Tasks | 19 |  | 0
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Complete Tasks | HMI - Complete Tasks | 1 | 5% | N/A
The total number of tasks that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Completed Early Tasks | HMI - Completed Early Tasks | N/A | 0% | N/A
The total number of tasks that were baselined to complete within the current status period and actually completed before the current status period (i.e., from previous IMS status date to current IMS status date). Calculates tasks that are missing from the HMI Value calculation because they were completed early.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Incomplete Tasks | HMI - Incomplete Tasks | 18 | 95% | N/A
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Tasks (adjusted) | HMI - Value Tasks (adjusted) | 0.05 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month). Gives credit for tasks baselined in the future that completed during the given status period.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Complete Tasks (adjusted) | HMI - Complete Tasks (adjusted) | 1 | 5% | N/A
The total number of tasks that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date). Gives credit for tasks baselined in the future that completed during the given status period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Complete Future Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | N/A |  | N/A
The total number of tasks that were baselined to complete in the future and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date). Gives credit for tasks baselined in the future that completed during the given status period.

## NASA-Metrics-Performance-Hit-o3
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance-Hit-o -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones
HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Score
N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 100
|  | N/A | N/A | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Milestones | HMI - Value Milestones | N/A |  | N/A
Hit or Miss Index (HMI) calculation for milestones. A monthly measure of IMS milestone performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Total Milestones | HMI - Total Milestones | 0 |  | 0
The total number of milestones baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Complete Milestones | HMI - Complete Milestones | N/A |  | N/A
The total number of milestones that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Completed Early Milestones | HMI - Completed Early Milestones | N/A |  | N/A
The total number of milestones that were baselined to complete within the current status period and actually completed before the current status period (i.e., from previous IMS status date to current IMS status date). Calculates milestones that are missing from the HMI Value calculation because they were completed early.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Incomplete Milestones | HMI - Incomplete Milestones | N/A |  | N/A
The total number of milestones that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Milestones (adjusted) | HMI - Value Milestones (adjusted) | N/A |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS milestone performance against the baseline for a given status period (e.g., within a month). Gives credit for milestones baselined in the future that completed during the given status period.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Complete Milestones (adjusted) | HMI - Complete Milestones (adjusted) | N/A |  | N/A
The total number of milestones that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date). Gives credit for milestones baselined in the future that completed during the given status period.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Complete Future Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | N/A |  | N/A
The total number of milestones that were baselined to complete in the future and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date). Gives credit for milestones baselined in the future that completed during the given status period.

## NASA-Metrics-Performance-Curre
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA Metrics Performance Current Execution Index (CEI)
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Current Execution Index (CEI)
|  | CEI - Tasks | CEI - Milestones
Ribbons | Project2 | 100 | 100
Ribbons | Project5_TAMPERED | 100 | 100
|  | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks
|  | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | Score
Ribbons | Project2 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 100
Ribbons |  |  |  | N/A | N/A |  | N/A
Ribbons | Project5_TAMPERED | 0.44 | 16 | 7 | 9 | 0.44 | 7 | 0 | 2026-08-27 | 100
Ribbons |  |  |  | 44% | 56% |  | 44%
|  | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones
|  | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | Score
Ribbons | Project2 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 100
Ribbons |  |  |  | N/A | N/A |  | N/A
Ribbons | Project5_TAMPERED | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 100
Ribbons |  |  |  | N/A | N/A |  | N/A

## NASA-Metrics-Performance-Curre2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance-Curre -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks
CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | Score
0.44 | 16 | 7 | 9 | 0.44 | 7 | 0 | 2026-08-27 | 100
|  | 44% | 56% |  | 44%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Tasks | CEI - Value Tasks | 0.44 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Total Tasks | CEI - Total Tasks | 16 |  | 0
The number of tasks forecasted in the previous month's schedule (based on the prior schedule's status date) to be completed in the current month (time between prior schedule's satus date and current schedule's status date).
Excluded | Notes | DRM | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1 | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 4.3 | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 1.9 | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 1 | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 1 | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 4 | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 0.5 | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 7 | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 2.25 | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 0 | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 0 | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 0 | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 0 | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 0 | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 0 | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 0 | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Complete Tasks | CEI - Complete Tasks | 7 | 44% | N/A
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Excluded | Notes | DRM | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1 | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 4.3 | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 1.9 | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 1 | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 1 | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 4 | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 0.5 | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Incomplete Tasks | CEI - Incomplete Tasks | 9 | 56% | N/A
The number of tasks that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Tasks (adjusted) | CEI - Value Tasks (adjusted) | 0.44 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast. Takes credit for future-planned activities that were completed within the measured timeframe.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Complete Tasks (adjusted) | CEI - Complete Tasks (adjusted) | 7 | 44% | N/A
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date). Takes credit for future-planned activities that were completed within the measured timeframe.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Complete Future Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | 0 |  | N/A
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the future per the previous month's schedule forecast (based on the prior schedule's status date). Takes credit for future-planned activities that were completed within the measured timeframe.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Performance-Curre3
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance-Curre -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones
CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | Score
N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 100
|  | N/A | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Milestones | CEI - Value Milestones | N/A |  | N/A
Current Execution Index (CEI) calculation for milestones. A monthly measure of schedule milestone performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Total Milestones | CEI - Total Milestones | 0 |  | 0
The number of milestones forecasted in the previous month's schedule (based on the prior schedule's status date) to be completed in the current month (time between prior schedule's satus date and current schedule's status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Complete Milestones | CEI - Complete Milestones | N/A |  | N/A
The number of activities completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Incomplete Milestones | CEI - Incomplete Milestones | N/A |  | N/A
The number of milestones that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Milestones (adjusted) | CEI - Value Milestones (adjusted) | N/A |  | N/A
Current Execution Index (CEI) calculation for milestones. A monthly measure of schedule milestone performance against the monthly forecast. Takes credit for future-planned milestones that were completed within the measured timeframe.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Complete Milestones (adjusted) | CEI - Complete Milestones (adjusted) | N/A |  | N/A
The number of activities completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date). Takes credit for future-planned milestones that were completed within the measured timeframe.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Complete Future Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | N/A |  | N/A
The number of milestones completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the future per the previous month's schedule forecast (based on the prior schedule's status date). Takes credit for future-planned milestones that were completed within the measured timeframe.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Performance-BEI--
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks
BEI - Value Tasks | BEI - Total Tasks | BEI - Incomplete Tasks | HMI - Value Tasks | HMI - Total Tasks | HMI - Incomplete Tasks | CEI - Value Tasks | CEI - Total Tasks | CEI - Incomplete Tasks | BEI - Complete Milestones | HMI - Complete Tasks | CEI - Complete Tasks | Score
0.59 | 46 | 19 | 0.05 | 19 | 18 | 0.44 | 16 | 9 | N/A | 1 | 7 | 100
|  | 41% |  |  | 95% |  |  | 56% | N/A | 5% | 44%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Tasks | BEI - Value Tasks | 0.59 |  | 0.74
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Total Tasks | BEI - Total Tasks | 46 |  | 27
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Incomplete Tasks | BEI - Incomplete Tasks | 19 | 41% | 7 | 26%
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Tasks | HMI - Value Tasks | 0.05 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Total Tasks | HMI - Total Tasks | 19 |  | 0
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Incomplete Tasks | HMI - Incomplete Tasks | 18 | 95% | N/A
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Tasks | CEI - Value Tasks | 0.44 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Total Tasks | CEI - Total Tasks | 16 |  | 0
The number of tasks forecasted in the previous month's schedule (based on the prior schedule's status date) to be completed in the current month (time between prior schedule's satus date and current schedule's status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Incomplete Tasks | CEI - Incomplete Tasks | 9 | 56% | N/A
The number of tasks that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Complete Milestones | BEI - Complete Milestones | N/A |  | N/A
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Complete Tasks | HMI - Complete Tasks | 1 | 5% | N/A
The total number of tasks that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Complete Tasks | CEI - Complete Tasks | 7 | 44% | N/A
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Excluded | Notes | DRM | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1 | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 4.3 | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 1.9 | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 1 | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 1 | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 4 | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 0.5 | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0

## NASA-Metrics-Performance-BEI--2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones
BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Incomplete Milestones | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | Score
N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | 100
|  | N/A | N/A |  |  | N/A | N/A |  |  | N/A | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Milestones | BEI - Value Milestones | N/A |  | N/A
Baseline Execution Index (BEI) calculation for milestones. A cumulative measure of IMS milestone performance against the baseline.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Total Milestones | BEI - Total Milestones | 0 |  | 0
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Complete Milestones | BEI - Complete Milestones | N/A |  | N/A
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Incomplete Milestones | BEI - Incomplete Milestones | N/A |  | N/A
The total number (cumulative) of milestones that were baselined to complete but did not complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Milestones | HMI - Value Milestones | N/A |  | N/A
Hit or Miss Index (HMI) calculation for milestones. A monthly measure of IMS milestone performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Total Milestones | HMI - Total Milestones | 0 |  | 0
The total number of milestones baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Complete Milestones | HMI - Complete Milestones | N/A |  | N/A
The total number of milestones that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Incomplete Milestones | HMI - Incomplete Milestones | N/A |  | N/A
The total number of milestones that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Milestones | CEI - Value Milestones | N/A |  | N/A
Current Execution Index (CEI) calculation for milestones. A monthly measure of schedule milestone performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Total Milestones | CEI - Total Milestones | 0 |  | 0
The number of milestones forecasted in the previous month's schedule (based on the prior schedule's status date) to be completed in the current month (time between prior schedule's satus date and current schedule's status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Complete Milestones | CEI - Complete Milestones | N/A |  | N/A
The number of activities completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Incomplete Milestones | CEI - Incomplete Milestones | N/A |  | N/A
The number of milestones that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.

## NASA-Metrics-Performance-BEI--3
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted
BEI - Value Tasks (adjusted) | HMI - Value Tasks (adjusted) | CEI - Value Tasks (adjusted) | BEI - Value Milestones (adjusted) | HMI - Value Milestones (adjusted) | CEI - Value Milestones (adjusted) | Status Date | Score
0.59 | 0.05 | 0.44 | N/A | N/A | N/A | 2026-08-27 | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Tasks (adjusted) | BEI - Value Tasks (adjusted) | 0.59 |  | 0.74
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline. Takes credit for future-baselined activities that are complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Tasks (adjusted) | HMI - Value Tasks (adjusted) | 0.05 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month). Gives credit for tasks baselined in the future that completed during the given status period.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Tasks (adjusted) | CEI - Value Tasks (adjusted) | 0.44 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast. Takes credit for future-planned activities that were completed within the measured timeframe.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Milestones (adjusted) | BEI - Value Milestones (adjusted) | N/A |  | N/A
Baseline Execution Index (BEI) calculation for milestones. A cumulative measure of IMS milestone performance against the baseline. Takes credit for future-baselined milestones that are complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Milestones (adjusted) | HMI - Value Milestones (adjusted) | N/A |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS milestone performance against the baseline for a given status period (e.g., within a month). Gives credit for milestones baselined in the future that completed during the given status period.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Milestones (adjusted) | CEI - Value Milestones (adjusted) | N/A |  | N/A
Current Execution Index (CEI) calculation for milestones. A monthly measure of schedule milestone performance against the monthly forecast. Takes credit for future-planned milestones that were completed within the measured timeframe.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Performance-DRM
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
DRM | DRM | DRM
Total Activities - DRM | Total Activities - DRM Graph | Score
27 | 27 | 100
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total Activities - DRM | Total Activities - DRM | 27 |  | 20
The total number of activities within a grouping.
Excluded | Notes | Id | Description | Baseline Duration | Actual Duration | DRM | Project | Actual Start | Actual Finish | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | 3 | 3 | 1 | Project5_TAMPERED | 2026-03-02 | 2026-03-04 | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | 4 | 4 | 1 | Project5_TAMPERED | 2026-03-05 | 2026-03-10 | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | 1 | 1 | 1 | Project5_TAMPERED | 2026-03-05 | 2026-03-05 | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | 2 | 2 | 1 | Project5_TAMPERED | 2026-03-05 | 2026-03-06 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | 2 | 2 | 1 | Project5_TAMPERED | 2026-03-05 | 2026-03-06 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | 10 | 16 | 1.6 | Project5_TAMPERED | 2026-03-06 | 2026-03-27 | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | 3 | 3 | 1 | Project5_TAMPERED | 2026-03-09 | 2026-03-11 | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | 3 | 10 | 3.3333 | Project5_TAMPERED | 2026-03-12 | 2026-03-25 | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | 2 | 2 | 1 | Project5_TAMPERED | 2026-03-25 | 2026-03-26 | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | 2 | 2 | 1 | Project5_TAMPERED | 2026-03-26 | 2026-03-27 | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | 2 | 2 | 1 | Project5_TAMPERED | 2026-03-27 | 2026-03-30 | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | 60 | 60 | 1 | Project5_TAMPERED | 2026-03-30 | 2026-06-19 | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | 2 | 2 | 1 | Project5_TAMPERED | 2026-03-31 | 2026-04-01 | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | 10 | 23 | 2.3 | Project5_TAMPERED | 2026-04-02 | 2026-05-04 | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | 3 | 3 | 1 | Project5_TAMPERED | 2026-04-06 | 2026-04-08 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | 2 | 2 | 1 | Project5_TAMPERED | 2026-04-13 | 2026-04-14 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | 5 | 5 | 1 | Project5_TAMPERED | 2026-04-15 | 2026-04-21 | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | 10 | 20 | 2 | Project5_TAMPERED | 2026-04-22 | 2026-05-19 | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | 10 | 43 | 4.3 | Project5_TAMPERED | 2026-04-22 | 2026-06-19 | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | 10 | 19 | 1.9 | Project5_TAMPERED | 2026-05-05 | 2026-05-29 | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | 10 | 10 | 1 | Project5_TAMPERED | 2026-05-05 | 2026-05-18 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | 10 | 9 | 0.9 | Project5_TAMPERED | 2026-05-05 | 2026-05-15 | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | 10 | 10 | 1 | Project5_TAMPERED | 2026-05-05 | 2026-05-18 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | 10 | 10 | 1 | Project5_TAMPERED | 2026-06-08 | 2026-06-19 | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | 10 | 10 | 1 | Project5_TAMPERED | 2026-06-22 | 2026-07-03 | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | 5 | 20 | 4 | Project5_TAMPERED | 2026-07-06 | 2026-07-31 | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | 10 | 5 | 0.5 | Project5_TAMPERED | 2026-08-03 | 2026-08-07 | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total Activities - DRM Graph | Total Activities - DRM Graph | 27 |  | 20
The total number of activities within a grouping.
Id | Description | Baseline Duration | Actual Duration | DRM
3 | Receive notice to proceed and sign contract | 3 | 3 | 1
7 | Obtain building permits | 4 | 4 | 1
9 | Submit monthly requests for payment | 1 | 1 | 1
19 | Install temporary power | 2 | 2 | 1
20 | Install temporary water service | 2 | 2 | 1
11 | Submit shop drawings and order long lead items - steel | 10 | 16 | 1.6
21 | Set up site office | 3 | 3 | 1
22 | Set line and grade benchmarks | 3 | 10 | 3.3333
4 | Submit bond and insurance documents | 2 | 2 | 1
23 | Prepare site - lay down yard and temporary fencing | 2 | 2 | 1
5 | Prepare and submit project schedule | 2 | 2 | 1
17 | Detail, fabricate and deliver steel | 60 | 60 | 1
6 | Prepare and submit schedule of values | 2 | 2 | 1
8 | Submit preliminary shop drawings | 10 | 23 | 2.3
25 | Clear and grub site | 3 | 3 | 1
26 | Stone site access and temporary parking area | 2 | 2 | 1
27 | Rough grade site (cut and fill) | 5 | 5 | 1
28 | Install storm drainage | 10 | 20 | 2
29 | Install exterior fire line and building fire riser | 10 | 43 | 4.3
12 | Submit shop drawings and order long lead items - roofing | 10 | 19 | 1.9
13 | Submit shop drawings and order long lead items - elevator | 10 | 10 | 1
14 | Submit shop drawings and order long lead items - plumbing | 10 | 9 | 0.9
16 | Submit shop drawings and order long lead items - HVAC | 10 | 10 | 1
15 | Submit shop drawings and order long lead items - electric | 10 | 10 | 1
30 | Perform final site grading | 10 | 10 | 1
31 | Erect building batter boards and layout building | 5 | 20 | 4
33 | Excavate foundations | 10 | 5 | 0.5

## NASA-Metrics-Performance-Track
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates
Status Date | Milestone #1 - 5158 | Float Milestone #1 - 5158 | Milestone #2 - 4786 | Float to Milestone #2 - 4786 | Milestone #3 - 102 | Float to Milestone #3 - 102 | Milestone #4 - 103 | Float to Milestone #4 - 103 | Milestone #5 - 104 | Float to Milestone #5 - 105 | New Activities Since Previous Status Date | Score
2026-08-27 | N/A | N/A | N/A | N/A | 2027-08-20 | 35 | 2027-09-09 | 35 | 2027-10-22 | 35 | 0 | 100
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestone #1 - 5158 | Milestone #1 - 5158 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Float Milestone #1 - 5158 | Float Milestone #1 - 5158 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestone #2 - 4786 | Milestone #2 - 4786 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Float to Milestone #2 - 4786 | Float to Milestone #2 - 4786 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestone #3 - 102 | Milestone #3 - 102 | 2027-08-20 |  | 2027-05-13
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Float to Milestone #3 - 102 | Float to Milestone #3 - 102 | 35 |  | 10
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestone #4 - 103 | Milestone #4 - 103 | 2027-09-09 |  | 2027-06-02
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Float to Milestone #4 - 103 | Float to Milestone #4 - 103 | 35 |  | 10
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestone #5 - 104 | Milestone #5 - 104 | 2027-10-22 |  | 2027-07-15
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Float to Milestone #5 - 105 | Float to Milestone #5 - 105 | 35 |  | 10
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
New Activities Since Previous Status Date | New Activities Since Previous Status Date | 0 |  | 0

## NASA-Metrics-Performance-Margi
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration
Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
2026-08-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #1 | Margin - Margin Task Name #1 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #2 | Margin - Margin Task Name #2 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #3 | Margin - Margin Task Name #3 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #4 | Margin - Margin Task Name #4 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #5 | Margin - Margin Task Name #5 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #6 | Margin - Margin Task Name #6 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #7 | Margin - Margin Task Name #7 | N/A |  | N/A

## NASA-Metrics-Performance-Margi2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date
Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
2026-08-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #1 | Margin - Margin Task Name #1 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #2 | Margin - Margin Task Name #2 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #3 | Margin - Margin Task Name #3 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #4 | Margin - Margin Task Name #4 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #5 | Margin - Margin Task Name #5 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #6 | Margin - Margin Task Name #6 | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Margin - Margin Task Name #7 | Margin - Margin Task Name #7 | N/A |  | N/A

## NASA-Metrics-Performance-Perf18
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon)
BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Score
0.6 | 0.59 | 0 | 0.05 | 0.4 | 0.44 | 1.24 | 1.24 | 1.24 | 1.24 | 97 | 99 | 97 | 1.24 | 67
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Task Starts - Cumulative | BEI - Value Task Starts - Cumulative | 0.6 |  | 0.79
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Task Finishes - Cumulative | BEI - Value Task Finishes - Cumulative | 0.59 |  | 0.74
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE | 1 |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 4 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE | 1 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 1 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE | 1 |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1 |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 16 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 3 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE | 3.3333 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 10 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE | 1 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE | 1 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-26 | 2026-03-27 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE | 1 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE | 1 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 60 | 2026-03-30 | 2026-06-19 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | 1 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2.3 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 23 | 2026-04-02 | 2026-05-04 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE | 1 |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2 | 2026-04-13 | 2026-04-14 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE | 1 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 5 | 2026-04-15 | 2026-04-21 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE | 2 |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 20 | 2026-04-22 | 2026-05-19 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 4.3 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 43 | 2026-04-22 | 2026-06-19 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | 1.9 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 19 | 2026-05-05 | 2026-05-29 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 0.9 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 9 | 2026-05-05 | 2026-05-15 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 10 | 2026-05-05 | 2026-05-18 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-08 | 2026-06-19 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | 1 |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 10 | 2026-06-22 | 2026-07-03 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | 4 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 20 | 2026-07-06 | 2026-07-31 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | 0.5 |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 5 | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Task Starts - by Status Dates | HMI - Value Task Starts - by Status Dates | 0 |  | N/A
Hit or Miss Index (HMI) calculation for task starts. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Task Finishes - by Status Dates | HMI - Value Task Finishes - by Status Dates | 0.05 |  | N/A
Hit or Miss Index (HMI) calculation for task finishes. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Task Starts - by Status Dates | CEI - Value Task Starts - by Status Dates | 0.4 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Task Finishes - by Status Dates | CEI - Value Task Finishes - by Status Dates | 0.44 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
FEI - Value Task Starts - Cumulative | FEI - Value Task Starts - Cumulative | 1.24 |  | 1.06
Future Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline for activities that have not yet started.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
FEI - Value Task Finish - Cumulative | FEI - Value Task Finish - Cumulative | 1.24 |  | 1.07
Future Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline for activities that have not yet started.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 7 |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 14 | 2026-08-10 |  | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | 2.25 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 9 | 2026-08-17 |  | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 0 |  |  | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 0 |  |  | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 0 |  |  | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 0 |  |  | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | 0 |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE | 0 |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 0 |  |  | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 0 |  |  | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 0 |  |  | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 0 |  |  | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 0 |  |  | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 0 |  |  | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 0 |  |  | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 0 |  |  | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 0 |  |  | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 0 |  |  | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 0 |  |  | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - BEI - Value Task Starts - Cumulative | To Go - BEI - Value Task Starts - Cumulative | 1.24 |  | 1.06
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - BEI - Value Task Finishes - Cumulative | To Go - BEI - Value Task Finishes - Cumulative | 1.24 |  | 1.07
To-Complete Baseline Execution Index (TC-BEI)
Id | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
34 | Excavate elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-05-22 |  | 2026-08-28 | Normal | InProgress
35 | Form column piers and spread foundations | Project5_TAMPERED | 2026-08-27 | 2026-05-26 |  | 2026-09-18 | Normal | InProgress
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - Planned Task Starts - Count | To Go - Planned Task Starts - Count | 97 |  | 103
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - BEI - Task Finishes - Count | To Go - BEI - Task Finishes - Count | 99 |  | 106
To-Complete Baseline Execution Index (TC-BEI)
Id | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
34 | Excavate elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-05-22 |  | 2026-08-28 | Normal | InProgress
35 | Form column piers and spread foundations | Project5_TAMPERED | 2026-08-27 | 2026-05-26 |  | 2026-09-18 | Normal | InProgress
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - Baselined Task Starts - Count | To Go - Baselined Task Starts - Count | 97 |  | 103
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
To Go - BEI - Value Task Starts - Cumulative | To Go - BEI - Value Task Starts - Cumulative | 1.24 |  | 1.06
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
36 | 2026-05-25 | 2026-08-31 |  | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | 2026-05-27 | 2026-09-21 |  | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | 2026-06-02 | 2026-09-25 |  | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | 2026-06-02 | 2026-09-25 |  | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | 2026-06-09 | 2026-10-26 |  | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | 2026-06-09 | 2026-10-26 |  | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | 2026-06-18 | 2026-11-04 |  | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | 2026-06-23 | 2026-11-09 |  | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | 2026-06-23 | 2026-11-23 |  | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | 2026-07-07 | 2026-11-23 |  | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | 2026-07-02 | 2026-12-02 |  | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | 2026-07-03 | 2026-12-03 |  | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | 2026-07-08 | 2026-12-08 |  | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | 2026-07-21 | 2026-12-16 |  | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | 2026-07-07 | 2026-12-16 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | 2026-08-04 | 2026-12-30 |  | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | 2026-08-18 | 2027-01-13 |  | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | 2026-08-18 | 2027-01-13 |  | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | 2026-08-25 | 2027-01-20 |  | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | 2026-09-01 | 2027-02-12 |  | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | 2026-09-07 | 2027-02-18 |  | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | 2026-09-01 | 2027-02-19 |  | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | 2026-09-16 | 2027-03-01 |  | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | 2026-09-16 | 2027-03-01 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | 2026-09-23 | 2027-03-08 |  | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | 2026-09-23 | 2027-03-08 |  | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | 2026-09-25 | 2027-03-10 |  | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | 2026-09-25 | 2027-03-10 |  | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | 2026-09-29 | 2027-03-12 |  | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | 2026-10-01 | 2027-03-16 |  | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | 2026-10-01 | 2027-03-16 |  | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | 2026-09-29 | 2027-03-19 |  | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | 2026-09-29 | 2027-03-19 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | 2026-10-08 | 2027-03-23 |  | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | 2026-10-08 | 2027-03-23 |  | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | 2026-10-08 | 2027-03-23 |  | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | 2026-10-15 | 2027-03-30 |  | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | 2026-10-15 | 2027-03-30 |  | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | 2026-10-19 | 2027-04-01 |  | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | 2026-10-21 | 2027-04-05 |  | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | 2026-10-30 | 2027-04-14 |  | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | 2026-11-03 | 2027-04-16 |  | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | 2026-11-03 | 2027-04-16 |  | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | 2026-10-27 | 2027-04-16 |  | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | 2026-11-05 | 2027-04-20 |  | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | 2026-11-05 | 2027-04-20 |  | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | 2026-11-05 | 2027-04-20 |  | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | 2026-11-10 | 2027-04-30 |  | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | 2026-11-24 | 2027-05-07 |  | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | 2026-12-03 | 2027-05-18 |  | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | 2026-12-17 | 2027-06-01 |  | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | 2026-12-29 | 2027-06-11 |  | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | 2026-12-29 | 2027-06-11 |  | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | 2026-12-29 | 2027-06-11 |  | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | 2027-01-04 | 2027-06-17 |  | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | 2027-01-05 | 2027-06-18 |  | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | 2027-01-06 | 2027-06-21 |  | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | 2027-01-15 | 2027-06-30 |  | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | 2027-01-22 | 2027-07-07 |  | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | 2027-01-29 | 2027-07-14 |  | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | 2027-02-02 | 2027-07-16 |  | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | 2027-02-02 | 2027-07-16 |  | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | 2027-02-02 | 2027-07-16 |  | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | 2027-02-02 | 2027-07-16 |  | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | 2027-02-12 | 2027-07-28 |  | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | 2027-02-23 | 2027-08-06 |  | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | 2027-03-02 | 2027-08-13 |  | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | 2027-03-09 | 2027-08-20 |  | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | 2027-03-09 | 2027-08-20 |  | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | 2027-03-09 | 2027-08-20 |  | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | 2027-03-16 | 2027-08-27 |  | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | 2027-03-23 | 2027-09-03 |  | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | 2027-03-30 | 2027-09-10 |  | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | 2027-03-30 | 2027-09-10 |  | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | 2027-03-30 | 2027-09-10 |  | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | 2027-04-13 | 2027-09-24 |  | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | 2027-04-13 | 2027-09-24 |  | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | 2027-04-13 | 2027-09-24 |  | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | 2027-05-18 | 2027-10-15 |  | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | 2027-05-04 | 2027-10-19 |  | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | 2027-05-11 | 2027-10-22 |  | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | 2027-05-11 | 2027-10-22 |  | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | 2027-05-11 | 2027-10-22 |  | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | 2027-05-11 | 2027-10-22 |  | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | 2027-05-11 | 2027-10-22 |  | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | 2027-05-25 | 2027-11-05 |  | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | 2027-06-08 | 2027-11-29 |  | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | 2027-06-14 | 2027-12-03 |  | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | 2027-06-14 | 2027-12-03 |  | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | 2027-06-17 | 2027-12-08 |  | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | 2027-06-18 | 2027-12-09 |  | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | 2027-05-20 | 2027-12-10 |  | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | 2027-06-21 | 2027-12-10 |  | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | 2027-06-22 | 2028-01-07 |  | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | 2027-07-06 | 2028-01-21 |  | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | 2027-07-08 | 2028-01-25 |  | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | 2027-07-09 | 2028-01-26 |  | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned

## NASA-Metrics-Performance-BEI--4
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values
BEI - Value Tasks | HMI - Value Tasks | CEI - Value Tasks | BEI - Value Milestones | HMI - Value Milestones | CEI - Value Milestones | Score
0.59 | 0.05 | 0.44 | N/A | N/A | N/A | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Tasks | BEI - Value Tasks | 0.59 |  | 0.74
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Tasks | HMI - Value Tasks | 0.05 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Tasks | CEI - Value Tasks | 0.44 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Milestones | BEI - Value Milestones | N/A |  | N/A
Baseline Execution Index (BEI) calculation for milestones. A cumulative measure of IMS milestone performance against the baseline.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Milestones | HMI - Value Milestones | N/A |  | N/A
Hit or Miss Index (HMI) calculation for milestones. A monthly measure of IMS milestone performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Milestones | CEI - Value Milestones | N/A |  | N/A
Current Execution Index (CEI) calculation for milestones. A monthly measure of schedule milestone performance against the monthly forecast.

## NASA-Metrics-Performance-BEI--5
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path
BEI - Value Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - CP Tasks - Planned Cumulative | BEI - CP Value Tasks | HMI - Value Tasks | HMI - Complete Tasks | HMI - Incomplete Tasks | HMI - CP Tasks - Planned to be Completed this Month | HMI - CP Value Tasks | CEI - Value Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - CP Tasks - Planned to be Completed this Month | CEI - CP Value Tasks | Score
0.59 | 27 | 19 | 14 | 0 | 0.05 | 1 | 18 | 10 | 0 | 0.44 | 7 | 9 | 9 | 0.44 | 100
| 59% | 41% |  |  |  | 5% | 95% |  |  |  | 44% | 56%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Value Tasks | BEI - Value Tasks | 0.59 |  | 0.74
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Complete Tasks | BEI - Complete Tasks | 27 | 59% | 20 | 74%
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - Incomplete Tasks | BEI - Incomplete Tasks | 19 | 41% | 7 | 26%
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Previous_Critical | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | TRUE | FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | TRUE | FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | TRUE | FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | TRUE | FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | FALSE | FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | TRUE | FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | FALSE | FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | FALSE | FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | FALSE | FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | TRUE | FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | FALSE | FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | TRUE | FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - CP Tasks - Planned Cumulative | BEI - CP Tasks - Planned Cumulative | 14 |  | 0
Excluded | Previous_Critical | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE | FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | TRUE | FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI - CP Value Tasks | BEI - CP Value Tasks | 0 |  | N/A
Excluded | Previous_Critical | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE | FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Value Tasks | HMI - Value Tasks | 0.05 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Complete Tasks | HMI - Complete Tasks | 1 | 5% | N/A
The total number of tasks that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - Incomplete Tasks | HMI - Incomplete Tasks | 18 | 95% | N/A
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - CP Tasks - Planned to be Completed this Month | HMI - CP Tasks - Planned to be Completed this Month | 10 |  | N/A
Excluded | Previous_Critical | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE | FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | TRUE | FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
HMI - CP Value Tasks | HMI - CP Value Tasks | 0 |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Value Tasks | CEI - Value Tasks | 0.44 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Complete Tasks | CEI - Complete Tasks | 7 | 44% | N/A
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Excluded | Previous_Critical | Critical | Notes | DRM | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE | FALSE |  | 1 | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 4.3 | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | FALSE | FALSE |  | 1.9 | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | FALSE | FALSE |  | 1 | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 1 | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 4 | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 0.5 | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - Incomplete Tasks | CEI - Incomplete Tasks | 9 | 56% | N/A
The number of tasks that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Excluded | Previous_Critical | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | TRUE | FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | TRUE | FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | TRUE | FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | TRUE | FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - CP Tasks - Planned to be Completed this Month | CEI - CP Tasks - Planned to be Completed this Month | 9 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Excluded | Previous_Critical | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE | FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE | TRUE | FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE | TRUE | FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CEI - CP Value Tasks | CEI - CP Value Tasks | 0.44 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Excluded | Previous_Critical | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE | FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE | TRUE | FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0

## NASA-Metrics-Schedule-Errors
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors
Wrong Status | Invalid Forecast Dates | Expected Finish | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | Score
0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 96
0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 1% | 0% | 0%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Wrong Status | Wrong Status | 0 | 0% | 0 | 0%
Number of activities that have been statused into the future.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Invalid Forecast Dates | Invalid Forecast Dates | 0 | 0% | 0 | 0%
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Expected Finish | Expected Finish | 0 | 0% | 0 | 0%
In-progress activities that are 100% complete.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missing WBS | Missing WBS | 0 | 0% | 0 | 0%
Number of activities that are missing WBS values.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Milestones with Duration>0 | Milestones with Duration>0 | 0 |  | 0
Milestones with a duration greater than 0 days.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Activities with Duration=0 | Activities with Duration=0 | 0 | 0% | 0 | 0%
Activities that have an original duration of 0 days.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Estimated Duration | Estimated Duration | 0 | 0% | 0 | 0%
Tasks with estimated duration in Microsoft Project. This condition occurs when an original duration has not been entered by the user.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missing Logic | Missing Logic | 5 | 5% | 4 | 4%
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | None | TRUE | 2 | 0 |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missing Predecessors | Missing Predecessors | 0 | 0% | 0 | 0%
Number of activities that are missing a predecessor.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Missing Successors | Missing Successors | 5 | 5% | 4 | 4%
Number of normal activities that are missing a successor.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE | None | TRUE | 2 | 0 |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Open Start | Open Start | 0 | 0% | 0 | 0%
Activities where only the predecessor(s) are either Finish-to-Finish or Start-to-Finish resulting in an open start to the activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Open Finish | Open Finish | 0 | 0% | 0 | 0%
Activities where the only successors(s) are either Start-to-Finish or Start-to-Start resulting in an open finish to the activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Unsatisfied Constraints | Unsatisfied Constraints | 0 | 0% | 0 | 0%
Activities where the constraint date cannot be met
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Summary Links | Summary Links | 0 | 0% | 0 | 0%
Number of summary activities that have logic links.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Hard Constraints | Hard Constraints | 1 | 1% | 0 | 0%
Number of activities with hard or two-way constraints.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical w/Hidden Duration | Critical w/Hidden Duration | 0 | 0% | 0 | 0%
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of its original duration
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Status Date | Status Date | 2026-08-27 |  | 2026-05-24
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Schedule-Warnings
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings
High Float 10% | High Float 44d | Zero Days Float | Negative Float | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Riding Data Date | Deadlines | Score
41 | 44 | 4 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 69
41% | 44% | 4% | 0% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | 0%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
High Float 10% | High Float 10% | 41 | 41% | 39 | 37%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
High Float 44d | High Float 44d | 44 | 44% | 44 | 42%
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE | FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE | FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE | FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE | FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE | FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE | FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE | FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE | FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE | FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE | FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE | FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE | FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE | FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE | FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE | FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE | FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE | FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE | FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE | FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE | FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE | FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE | FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Zero Days Float | Zero Days Float | 4 | 4% | 41 | 39%
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Hidden Duration (Planned) | Hidden Duration (Planned) | 1 | 1% | 1 | 1%
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of its original duration
Excluded | Number of Predecessors | Number of Lags | Minimum Lag | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 1 | 5 | 5 | FALSE | 80 |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Logic Hotspot™ | Critical Logic Hotspot™ | 0 | 0% | 1 | 2%
Number of activities with a high number of predecessors as well as a high number of successors.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Merge Hotspot | Critical Merge Hotspot | 1 | 1% | 3 | 3%
The total number of activities with a high number of predecessor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 1 | 0 | 0 | 0 | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Merge Hotspot w/Predecessor Lags | Merge Hotspot w/Predecessor Lags | 0 | 0% | 0 | 0%
Number of activities with a high number of predecessor links with lags on the predecessor relationships.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Diverge Hotspot | Critical Diverge Hotspot | 0 | 0% | 8 | 8%
Number of activities with a high number of successor links that are also critical.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Diverge Hotspot w/Successor Lags | Diverge Hotspot w/Successor Lags | 0 | 0% | 0 | 0%
Number of activities with a high number of successor links and critical.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Riding Data Date | Riding Data Date | 0 | 0% | 0 | 0%
Number of planned activities that have a start date that is the same as the project data date (Time Now)
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Deadlines | Deadlines | 0 | 0% | 0 | 0%
Number of activities with a hard (two-way) constraint that forces the activity to finish on a specific date, overriding CPM calculations.

## NASA-Metrics-Critical-Path
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | NASA-Metrics -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path
Longest Path (Normal Tasks) | Longest Path (Tasks & Milestones) | Critical Milestone-to-Task Ratio (To-Go) | Critical Milestones (To-Go) | Longest Path (Milestones) | Normal Tasks | Normal Tasks (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Zero Days Float | Negative Float | CP Logic Density™ | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Score
4 | 4 | N/A | 0 | 0 | 126 | 99 | 4 | 0 | 4 | 0 | 3 | 1 | 34 | 24
100% | 100% | 0 | ( N/A ) | 0% | 88% | 88% | 4% | 0% | 4% | 0% |  | 1% | 24%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Longest Path (Normal Tasks) | Longest Path (Normal Tasks) | 4 | 100% | 41 | 87%
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Longest Path (Tasks & Milestones) | Longest Path (Tasks & Milestones) | 4 | 100% | 41 | 87%
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | N/A | 0 | N/A | 0
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Milestones (To-Go) | Critical Milestones (To-Go) | 0 |  | 0
Number of critical milestones to-go.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Longest Path (Milestones) | Longest Path (Milestones) | 0 | 0% | 0 | 0%
Activities that together form the longest path through to project completion.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Normal Tasks | Normal Tasks | 126 | 88% | 126 | 88%
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0
FALSE |  | 100 |  | 7 | Obtain building permits | Project5_TAMPERED | Standard | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0
FALSE |  | 100 |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | Standard | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0
FALSE |  | 100 |  | 19 | Install temporary power | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 20 | Install temporary water service | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0
FALSE |  | 100 |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | Standard | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 0
FALSE |  | 100 |  | 21 | Set up site office | Project5_TAMPERED | Standard | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0
FALSE |  | 100 |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | Standard | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 0
FALSE |  | 100 |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0
FALSE |  | 100 |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 0
FALSE |  | 100 |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0
FALSE |  | 100 |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | Standard | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 0
FALSE |  | 100 |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | Standard | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | Standard | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 0
FALSE |  | 100 |  | 25 | Clear and grub site | Project5_TAMPERED | Standard | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 0
FALSE |  | 100 |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | Standard | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 0
FALSE |  | 100 |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | Standard | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 0
FALSE |  | 100 |  | 28 | Install storm drainage | Project5_TAMPERED | Standard | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | Standard | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 0
FALSE |  | 100 |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | Standard | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | Standard | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | Standard | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 0
FALSE |  | 100 |  | 30 | Perform final site grading | Project5_TAMPERED | Standard | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 0
FALSE |  | 100 |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | Standard | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 0
FALSE |  | 100 |  | 33 | Excavate foundations | Project5_TAMPERED | Standard | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 0
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Normal Tasks (To-Go) | Normal Tasks (To-Go) | 99 | 88% | 106 | 87%
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 93 |  | 34 | Excavate elevator pit | Project5_TAMPERED | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 275
FALSE |  | 36 |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 19
FALSE |  | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 275
FALSE |  | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 19
FALSE |  | 0 |  | 37 | Form elevator pit walls | Project5_TAMPERED | Standard | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 275
FALSE |  | 0 |  | 39 | Pour column piers and foundations | Project5_TAMPERED | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 19
FALSE |  | 0 |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 275
FALSE |  | 0 |  | 42 | Cure piers and foundations | Project5_TAMPERED | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 19
FALSE |  | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 19
FALSE |  | 0 |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 256
FALSE |  | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 19
FALSE |  | 0 |  | 43 | Strip wall forms | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 256
FALSE |  | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 256
FALSE |  | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 256
FALSE |  | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 19
FALSE |  | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 56
FALSE |  | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 19
FALSE |  | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | Standard | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 156
FALSE |  | 0 |  | 53 | Touch-up paint on steel | Project5_TAMPERED | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 19
FALSE |  | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 19
FALSE |  | 0 |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 19
FALSE |  | 0 |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 19
FALSE |  | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | Standard | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 156
FALSE |  | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 19
FALSE |  | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 95
FALSE |  | 0 |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 19
FALSE |  | 0 |  | 70 | Form 1st floor | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 100
FALSE |  | 0 |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 19
FALSE |  | 0 |  | 71 | Install electrical underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 72 | Install plumbing underground | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 95
FALSE |  | 0 |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | Standard | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 184
FALSE |  | 0 |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 156
FALSE |  | 0 |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 19
FALSE |  | 0 |  | 74 | Pour 1st floor slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 95
FALSE |  | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 30
FALSE |  | 0 |  | 67 | Pour roof slab | Project5_TAMPERED | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 19
FALSE |  | 0 |  | 75 | Cure 1st floor slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 95
FALSE |  | 0 |  | 68 | Cure roof slab | Project5_TAMPERED | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 19
FALSE |  | 0 |  | 69 | Strip forms from roof slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 19
FALSE |  | 0 |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | Standard | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 94
FALSE |  | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 19
FALSE |  | 0 |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 184
FALSE |  | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 118
FALSE |  | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 94
FALSE |  | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 124
FALSE |  | 0 |  | 113 | Test and align doors and equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 184
FALSE |  | 0 |  | 82 | Install exterior masonry work | Project5_TAMPERED | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 19
FALSE |  | 0 |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | Standard | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 118
FALSE |  | 0 |  | 86 | Clean toilet room tile | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 118
FALSE |  | 0 |  | 85 | Clean masonry | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 115
FALSE |  | 0 |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 82
FALSE |  | 0 |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 19
FALSE |  | 0 |  | 83 | Install roof drains | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 80
FALSE |  | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 115
FALSE |  | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | Standard | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 80
FALSE |  | 0 |  | 90 | Install seamless roofing material | Project5_TAMPERED | Standard | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 80
FALSE |  | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | Standard | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 80
FALSE |  | 0 |  | 92 | Set rooftop equipment | Project5_TAMPERED | Standard | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 80
FALSE |  | 0 |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 19
FALSE |  | 0 |  | 97 | Install store front doors and hardware | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 39
FALSE |  | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 36
FALSE |  | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 70
FALSE |  | 0 |  | 130 | Install duct in building chase | Project5_TAMPERED | Standard | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 82
FALSE |  | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | Standard | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 51
FALSE |  | 0 |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 70
FALSE |  | 0 |  | 99 | Install millwork and wood trim | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 29
FALSE |  | 0 |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 35
FALSE |  | 0 |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 81
FALSE |  | 0 |  | 134 | Clean hard tile floors | Project5_TAMPERED | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 81
FALSE |  | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 36
FALSE |  | 0 |  | 96 | Install interior doors and hardware | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 19
FALSE |  | 0 |  | 103 | Install ceiling grid | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 35
FALSE |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 89
FALSE |  | 0 |  | 100 | Paint walls and woodwork | Project5_TAMPERED | Standard | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 19
FALSE |  | 0 |  | 104 | Install ceiling tile | Project5_TAMPERED | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 55
FALSE |  | 0 |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | Standard | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 36
FALSE |  | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | Standard | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 38
FALSE |  | 0 |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 38
FALSE |  | 0 |  | 105 | Hang wallpaper | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 106 | Install building carpet | Project5_TAMPERED | Standard | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 28
FALSE |  | 0 |  | 107 | Install hardware and accessories | Project5_TAMPERED | Standard | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 19
FALSE |  | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 32
FALSE |  | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 35
FALSE |  | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | Standard | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 32
FALSE |  | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | Standard | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 19
FALSE |  | 0 |  | 136 | Substantial completion date | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 38
FALSE |  | 0 |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | Standard | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 19
FALSE |  | 0 |  | 139 | Perform architect's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 19
FALSE |  | 0 |  | 140 | Perform local building agency inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 19
FALSE |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | Standard | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 19
FALSE |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 1
FALSE |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Issue final request for payment | Project5_TAMPERED | Standard | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Tasks (To-Go) | Critical Tasks (To-Go) | 4 | 4% | 41 | 39%
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Critical Tasks (In Progress) | Critical Tasks (In Progress) | 0 | 0% | 1 | 2%
Number of critical activities to-go.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Zero Days Float | Zero Days Float | 4 | 4% | 41 | 39%
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
CP Logic Density™ | CP Logic Density™ | 3 |  | 3.2
The average number of logic links per activity.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Newly Critical Activities | Newly Critical Activities | 1 | 1% | 0 | 0%
How many remaining activities were added to the critical path this period
Id | Description | Critical | Previous_Critical | Original Duration | Remaining Duration | Start | Finish | Type | Status | Percent Complete | Total Float | Project
131 | Set HVAC trim and test and balance system | TRUE | FALSE | 20 | 20 | 2027-12-10 | 2028-01-06 | Normal | Planned | 0 | 0 | Project5_TAMPERED
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Activities No Longer Critical | Activities No Longer Critical | 34 | 24% | 0 | 0%
How many remaining activities are no longer on the critical path this period.
Id | Description | Critical | Previous_Critical | Original Duration | Remaining Duration | Start | Finish | Type | Status | Percent Complete | Total Float | Project
35 | Form column piers and spread foundations | FALSE | TRUE | 25 | 16 | 2026-08-17 | 2026-09-18 | Normal | InProgress | 36 | 19 | Project5_TAMPERED
38 | Set reinforcing and anchor bolts | FALSE | TRUE | 4 | 4 | 2026-09-21 | 2026-09-24 | Normal | Planned | 0 | 19 | Project5_TAMPERED
39 | Pour column piers and foundations | FALSE | TRUE | 21 | 21 | 2026-09-25 | 2026-10-23 | Normal | Planned | 0 | 19 | Project5_TAMPERED
42 | Cure piers and foundations | FALSE | TRUE | 7 | 7 | 2026-10-26 | 2026-11-03 | Normal | Planned | 0 | 19 | Project5_TAMPERED
44 | Strip column piers and foundation forms | FALSE | TRUE | 3 | 3 | 2026-11-04 | 2026-11-06 | Normal | Planned | 0 | 19 | Project5_TAMPERED
48 | Erect steel columns, beams and joist - 1st and 2nd floors | FALSE | TRUE | 10 | 10 | 2026-11-09 | 2026-11-20 | Normal | Planned | 0 | 19 | Project5_TAMPERED
49 | Erect steel columns, beams and joist - 3rd floor and roof | FALSE | TRUE | 17 | 17 | 2026-11-23 | 2026-12-15 | Normal | Planned | 0 | 19 | Project5_TAMPERED
51 | Install miscellaneous iron and bracing - 3rd floor and roof | FALSE | TRUE | 10 | 10 | 2026-12-16 | 2026-12-29 | Normal | Planned | 0 | 19 | Project5_TAMPERED
52 | Install stairs and miscellaneous iron railing | FALSE | TRUE | 10 | 10 | 2026-12-30 | 2027-01-12 | Normal | Planned | 0 | 19 | Project5_TAMPERED
53 | Touch-up paint on steel | FALSE | TRUE | 5 | 5 | 2027-01-13 | 2027-01-19 | Normal | Planned | 0 | 19 | Project5_TAMPERED
55 | Form 2nd floor including all floor openings | FALSE | TRUE | 17 | 17 | 2027-01-20 | 2027-02-11 | Normal | Planned | 0 | 19 | Project5_TAMPERED
57 | Pour 2nd floor slab | FALSE | TRUE | 4 | 4 | 2027-02-12 | 2027-02-17 | Normal | Planned | 0 | 19 | Project5_TAMPERED
58 | Cure 2nd floor slab | FALSE | TRUE | 7 | 7 | 2027-02-18 | 2027-02-26 | Normal | Planned | 0 | 19 | Project5_TAMPERED
60 | Form 3rd floor including all floor openings | FALSE | TRUE | 5 | 5 | 2027-03-01 | 2027-03-05 | Normal | Planned | 0 | 19 | Project5_TAMPERED
61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | FALSE | TRUE | 5 | 5 | 2027-03-01 | 2027-03-05 | Normal | Planned | 0 | 19 | Project5_TAMPERED
62 | Pour 3rd floor slab | FALSE | TRUE | 4 | 4 | 2027-03-08 | 2027-03-11 | Normal | Planned | 0 | 19 | Project5_TAMPERED
63 | Cure 3rd floor slab | FALSE | TRUE | 7 | 7 | 2027-03-12 | 2027-03-22 | Normal | Planned | 0 | 19 | Project5_TAMPERED
65 | Form roof slab including all floor openings | FALSE | TRUE | 5 | 5 | 2027-03-23 | 2027-03-29 | Normal | Planned | 0 | 19 | Project5_TAMPERED
66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | FALSE | TRUE | 5 | 5 | 2027-03-23 | 2027-03-29 | Normal | Planned | 0 | 19 | Project5_TAMPERED
67 | Pour roof slab | FALSE | TRUE | 4 | 4 | 2027-03-30 | 2027-04-02 | Normal | Planned | 0 | 19 | Project5_TAMPERED
68 | Cure roof slab | FALSE | TRUE | 7 | 7 | 2027-04-05 | 2027-04-13 | Normal | Planned | 0 | 19 | Project5_TAMPERED
69 | Strip forms from roof slab | FALSE | TRUE | 2 | 2 | 2027-04-14 | 2027-04-15 | Normal | Planned | 0 | 19 | Project5_TAMPERED
78 | Install exterior sheathing and metal studs | FALSE | TRUE | 15 | 15 | 2027-04-16 | 2027-05-06 | Normal | Planned | 0 | 19 | Project5_TAMPERED
82 | Install exterior masonry work | FALSE | TRUE | 25 | 25 | 2027-05-07 | 2027-06-10 | Normal | Planned | 0 | 19 | Project5_TAMPERED
94 | Install window wall aluminum and glass | FALSE | TRUE | 25 | 25 | 2027-06-11 | 2027-07-15 | Normal | Planned | 0 | 19 | Project5_TAMPERED
95 | Install interior stud walls and drywall | FALSE | TRUE | 25 | 25 | 2027-07-16 | 2027-08-19 | Normal | Planned | 0 | 19 | Project5_TAMPERED
96 | Install interior doors and hardware | FALSE | TRUE | 10 | 10 | 2027-09-10 | 2027-09-23 | Normal | Planned | 0 | 19 | Project5_TAMPERED
100 | Paint walls and woodwork | FALSE | TRUE | 20 | 20 | 2027-09-24 | 2027-10-21 | Normal | Planned | 0 | 19 | Project5_TAMPERED
106 | Install building carpet | FALSE | TRUE | 41 | 41 | 2027-10-22 | 2027-12-17 | Normal | Planned | 0 | 28 | Project5_TAMPERED
135 | Remove debris from building and do final clean-up | FALSE | TRUE | 4 | 4 | 2027-11-29 | 2027-12-02 | Normal | Planned | 0 | 19 | Project5_TAMPERED
138 | Complete elevator inspection and certification | FALSE | TRUE | 3 | 3 | 2027-12-03 | 2027-12-07 | Normal | Planned | 0 | 19 | Project5_TAMPERED
139 | Perform architect's inspection | FALSE | TRUE | 1 | 1 | 2027-12-08 | 2027-12-08 | Normal | Planned | 0 | 19 | Project5_TAMPERED
140 | Perform local building agency inspection | FALSE | TRUE | 1 | 1 | 2027-12-09 | 2027-12-09 | Normal | Planned | 0 | 19 | Project5_TAMPERED
141 | Perform Fire Marshal's inspection | FALSE | TRUE | 1 | 1 | 2027-12-10 | 2027-12-10 | Normal | Planned | 0 | 19 | Project5_TAMPERED

## Advanced
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | Advanced
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Advanced
Baseline Compliance
Ribbons | Project2 | 6
Ribbons | Project5_TAMPERED | 6
|  | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance
|  | Time Now | Forecast to be Finished | Completed On Time | Completed Late | Not Completed | Baseline Finish Compliance | Forecast to be Started | Started On Time | Started Late | Not Started | Baseline Start Compliance | Score
Ribbons | Project2 | 2026-05-24 | 27 | 9 | 11 | 7 | 33% | 29 | 11 | 12 | 6 | 41% | 6
Ribbons |  |  | 21% | 33% | 41% | 26% |  | 23% | 38% | 41% | 21%
Ribbons | Project5_TAMPERED | 2026-08-27 | 46 | 9 | 18 | 19 | 20% | 48 | 11 | 18 | 19 | 25% | 6
Ribbons |  |  | 37% | 20% | 39% | 41% |  | 38% | 23% | 38% | 40%

## Advanced-Baseline-Compliance
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | Advanced -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance
Time Now | Forecast to be Finished | Completed On Time | Completed Late | Not Completed | Baseline Finish Compliance | Forecast to be Started | Started On Time | Started Late | Not Started | Baseline Start Compliance | Score
2026-08-27 | 46 | 9 | 18 | 19 | 20% | 48 | 11 | 18 | 19 | 25% | 6
| 37% | 20% | 39% | 41% |  | 38% | 23% | 38% | 40%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Time Now | Time Now | 2026-08-27 |  | 2026-05-24
Current Project Time Now
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Forecast to be Finished | Forecast to be Finished | 46 | 37% | 27 | 21%
Forecast to be finished before time now
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Project Time Now | Type | Status | Percent Complete
3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 0 | 2026-03-02 | 2026-03-02 | 2026-03-04 | 2026-03-04 | 2026-08-27 | Normal | Complete | 100
7 | Obtain building permits | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-05 | 2026-03-10 | 2026-03-10 | 2026-08-27 | Normal | Complete | 100
9 | Submit monthly requests for payment | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-08-27 | Normal | Complete | 100
19 | Install temporary power | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-08-27 | Normal | Complete | 100
20 | Install temporary water service | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-08-27 | Normal | Complete | 100
11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 0 | 2026-03-06 | 2026-03-06 | 2026-03-27 | 2026-03-19 | 2026-08-27 | Normal | Complete | 100
21 | Set up site office | Project5_TAMPERED | 0 | 2026-03-09 | 2026-03-09 | 2026-03-11 | 2026-03-11 | 2026-08-27 | Normal | Complete | 100
22 | Set line and grade benchmarks | Project5_TAMPERED | 0 | 2026-03-12 | 2026-03-12 | 2026-03-25 | 2026-03-16 | 2026-08-27 | Normal | Complete | 100
4 | Submit bond and insurance documents | Project5_TAMPERED | 0 | 2026-03-25 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 2026-08-27 | Normal | Complete | 100
23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 0 | 2026-03-26 | 2026-03-17 | 2026-03-27 | 2026-03-18 | 2026-08-27 | Normal | Complete | 100
5 | Prepare and submit project schedule | Project5_TAMPERED | 0 | 2026-03-27 | 2026-03-27 | 2026-03-30 | 2026-03-30 | 2026-08-27 | Normal | Complete | 100
17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 0 | 2026-03-30 | 2026-03-20 | 2026-06-19 | 2026-06-11 | 2026-08-27 | Normal | Complete | 100
6 | Prepare and submit schedule of values | Project5_TAMPERED | 0 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-08-27 | Normal | Complete | 100
8 | Submit preliminary shop drawings | Project5_TAMPERED | 0 | 2026-04-02 | 2026-03-11 | 2026-05-04 | 2026-03-24 | 2026-08-27 | Normal | Complete | 100
25 | Clear and grub site | Project5_TAMPERED | 0 | 2026-04-06 | 2026-03-19 | 2026-04-08 | 2026-03-23 | 2026-08-27 | Normal | Complete | 100
26 | Stone site access and temporary parking area | Project5_TAMPERED | 0 | 2026-04-13 | 2026-03-24 | 2026-04-14 | 2026-03-25 | 2026-08-27 | Normal | Complete | 100
27 | Rough grade site (cut and fill) | Project5_TAMPERED | 0 | 2026-04-15 | 2026-03-26 | 2026-04-21 | 2026-04-01 | 2026-08-27 | Normal | Complete | 100
28 | Install storm drainage | Project5_TAMPERED | 0 | 2026-04-22 | 2026-04-02 | 2026-05-19 | 2026-04-15 | 2026-08-27 | Normal | Complete | 100
29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 0 | 2026-04-22 | 2026-04-02 | 2026-06-19 | 2026-04-15 | 2026-08-27 | Normal | Complete | 100
12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 0 | 2026-05-05 | 2026-03-25 | 2026-05-29 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 0 | 2026-05-05 | 2026-03-25 | 2026-05-18 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 0 | 2026-05-05 | 2026-03-25 | 2026-05-15 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 0 | 2026-05-05 | 2026-03-25 | 2026-05-18 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 0 | 2026-06-08 | 2026-03-25 | 2026-06-19 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
30 | Perform final site grading | Project5_TAMPERED | 0 | 2026-06-22 | 2026-04-16 | 2026-07-03 | 2026-04-29 | 2026-08-27 | Normal | Complete | 100
31 | Erect building batter boards and layout building | Project5_TAMPERED | 0 | 2026-07-06 | 2026-04-30 | 2026-07-31 | 2026-05-06 | 2026-08-27 | Normal | Complete | 100
33 | Excavate foundations | Project5_TAMPERED | 0 | 2026-08-03 | 2026-05-07 | 2026-08-07 | 2026-05-20 | 2026-08-27 | Normal | Complete | 100
34 | Excavate elevator pit | Project5_TAMPERED | 1 | 2026-08-10 | 2026-05-21 | 2026-08-28 | 2026-05-22 | 2026-08-27 | Normal | InProgress | 93
35 | Form column piers and spread foundations | Project5_TAMPERED | 16 | 2026-08-17 | 2026-05-21 | 2026-09-18 | 2026-05-26 | 2026-08-27 | Normal | InProgress | 36
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 2026-08-31 | 2026-05-25 | 2026-09-03 | 2026-05-28 | 2026-08-27 | Normal | Planned | 0
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 2026-09-21 | 2026-05-27 | 2026-09-24 | 2026-06-01 | 2026-08-27 | Normal | Planned | 0
37 | Form elevator pit walls | Project5_TAMPERED | 4 | 2026-09-25 | 2026-06-02 | 2026-09-30 | 2026-06-05 | 2026-08-27 | Normal | Planned | 0
39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 2026-09-25 | 2026-06-02 | 2026-10-23 | 2026-06-08 | 2026-08-27 | Normal | Planned | 0
40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 2026-10-26 | 2026-06-09 | 2026-10-26 | 2026-06-09 | 2026-08-27 | Normal | Planned | 0
42 | Cure piers and foundations | Project5_TAMPERED | 7 | 2026-10-26 | 2026-06-09 | 2026-11-03 | 2026-06-17 | 2026-08-27 | Normal | Planned | 0
44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 2026-11-04 | 2026-06-18 | 2026-11-06 | 2026-06-22 | 2026-08-27 | Normal | Planned | 0
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 2026-11-09 | 2026-06-23 | 2026-11-20 | 2026-07-06 | 2026-08-27 | Normal | Planned | 0
41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 2026-11-23 | 2026-06-23 | 2026-12-01 | 2026-07-01 | 2026-08-27 | Normal | Planned | 0
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 2026-11-23 | 2026-07-07 | 2026-12-15 | 2026-07-20 | 2026-08-27 | Normal | Planned | 0
43 | Strip wall forms | Project5_TAMPERED | 1 | 2026-12-02 | 2026-07-02 | 2026-12-02 | 2026-07-02 | 2026-08-27 | Normal | Planned | 0
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 2026-12-03 | 2026-07-03 | 2026-12-07 | 2026-07-07 | 2026-08-27 | Normal | Planned | 0
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 2026-12-08 | 2026-07-08 | 2026-12-08 | 2026-07-08 | 2026-08-27 | Normal | Planned | 0
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 2026-12-16 | 2026-07-21 | 2026-12-29 | 2026-08-03 | 2026-08-27 | Normal | Planned | 0
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2026-12-16 | 2026-07-07 | 2026-12-22 | 2026-07-13 | 2026-08-27 | Normal | Planned | 0
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 2026-12-30 | 2026-08-04 | 2027-01-12 | 2026-08-17 | 2026-08-27 | Normal | Planned | 0
53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 2027-01-13 | 2026-08-18 | 2027-01-19 | 2026-08-24 | 2026-08-27 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed On Time | Completed On Time | 9 | 20% | 9 | 33%
Activities actually completed on time, by their baseline finish date.
Id | Description | Project | Start | Baseline Start | Finish | Baseline Finish | Type | Status
3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 2026-03-02 | 2026-03-02 | 2026-03-04 | 2026-03-04 | Normal | Complete
7 | Obtain building permits | Project5_TAMPERED | 2026-03-05 | 2026-03-05 | 2026-03-10 | 2026-03-10 | Normal | Complete
9 | Submit monthly requests for payment | Project5_TAMPERED | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete
19 | Install temporary power | Project5_TAMPERED | 2026-03-05 | 2026-03-05 | 2026-03-06 | 2026-03-06 | Normal | Complete
20 | Install temporary water service | Project5_TAMPERED | 2026-03-05 | 2026-03-05 | 2026-03-06 | 2026-03-06 | Normal | Complete
21 | Set up site office | Project5_TAMPERED | 2026-03-09 | 2026-03-09 | 2026-03-11 | 2026-03-11 | Normal | Complete
4 | Submit bond and insurance documents | Project5_TAMPERED | 2026-03-25 | 2026-03-25 | 2026-03-26 | 2026-03-26 | Normal | Complete
5 | Prepare and submit project schedule | Project5_TAMPERED | 2026-03-27 | 2026-03-27 | 2026-03-30 | 2026-03-30 | Normal | Complete
6 | Prepare and submit schedule of values | Project5_TAMPERED | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | Normal | Complete
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Late | Completed Late | 18 | 39% | 11 | 41%
Activities actually completed but late, after their baseline finish date.
Id | Description | Project | Start | Baseline Start | Finish | Baseline Finish | Type | Status
11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 2026-03-06 | 2026-03-06 | 2026-03-27 | 2026-03-19 | Normal | Complete
22 | Set line and grade benchmarks | Project5_TAMPERED | 2026-03-12 | 2026-03-12 | 2026-03-25 | 2026-03-16 | Normal | Complete
23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2026-03-26 | 2026-03-17 | 2026-03-27 | 2026-03-18 | Normal | Complete
17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 2026-03-30 | 2026-03-20 | 2026-06-19 | 2026-06-11 | Normal | Complete
8 | Submit preliminary shop drawings | Project5_TAMPERED | 2026-04-02 | 2026-03-11 | 2026-05-04 | 2026-03-24 | Normal | Complete
25 | Clear and grub site | Project5_TAMPERED | 2026-04-06 | 2026-03-19 | 2026-04-08 | 2026-03-23 | Normal | Complete
26 | Stone site access and temporary parking area | Project5_TAMPERED | 2026-04-13 | 2026-03-24 | 2026-04-14 | 2026-03-25 | Normal | Complete
27 | Rough grade site (cut and fill) | Project5_TAMPERED | 2026-04-15 | 2026-03-26 | 2026-04-21 | 2026-04-01 | Normal | Complete
28 | Install storm drainage | Project5_TAMPERED | 2026-04-22 | 2026-04-02 | 2026-05-19 | 2026-04-15 | Normal | Complete
29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 2026-04-22 | 2026-04-02 | 2026-06-19 | 2026-04-15 | Normal | Complete
12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 2026-05-05 | 2026-03-25 | 2026-05-29 | 2026-04-07 | Normal | Complete
13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 2026-05-05 | 2026-03-25 | 2026-05-18 | 2026-04-07 | Normal | Complete
14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 2026-05-05 | 2026-03-25 | 2026-05-15 | 2026-04-07 | Normal | Complete
16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 2026-05-05 | 2026-03-25 | 2026-05-18 | 2026-04-07 | Normal | Complete
15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 2026-06-08 | 2026-03-25 | 2026-06-19 | 2026-04-07 | Normal | Complete
30 | Perform final site grading | Project5_TAMPERED | 2026-06-22 | 2026-04-16 | 2026-07-03 | 2026-04-29 | Normal | Complete
31 | Erect building batter boards and layout building | Project5_TAMPERED | 2026-07-06 | 2026-04-30 | 2026-07-31 | 2026-05-06 | Normal | Complete
33 | Excavate foundations | Project5_TAMPERED | 2026-08-03 | 2026-05-07 | 2026-08-07 | 2026-05-20 | Normal | Complete
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Not Completed | Not Completed | 19 | 41% | 7 | 26%
Activities that were planned to be complete by now that are not complete.
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Type | Activity Status
34 | Excavate elevator pit | Project5_TAMPERED | 1 | 2026-08-10 | 2026-05-21 | 2026-08-28 | 2026-05-22 | Normal | InProgress
35 | Form column piers and spread foundations | Project5_TAMPERED | 16 | 2026-08-17 | 2026-05-21 | 2026-09-18 | 2026-05-26 | Normal | InProgress
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 2026-08-31 | 2026-05-25 | 2026-09-03 | 2026-05-28 | Normal | Planned
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 2026-09-21 | 2026-05-27 | 2026-09-24 | 2026-06-01 | Normal | Planned
37 | Form elevator pit walls | Project5_TAMPERED | 4 | 2026-09-25 | 2026-06-02 | 2026-09-30 | 2026-06-05 | Normal | Planned
39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 2026-09-25 | 2026-06-02 | 2026-10-23 | 2026-06-08 | Normal | Planned
40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 2026-10-26 | 2026-06-09 | 2026-10-26 | 2026-06-09 | Normal | Planned
42 | Cure piers and foundations | Project5_TAMPERED | 7 | 2026-10-26 | 2026-06-09 | 2026-11-03 | 2026-06-17 | Normal | Planned
44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 2026-11-04 | 2026-06-18 | 2026-11-06 | 2026-06-22 | Normal | Planned
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 2026-11-09 | 2026-06-23 | 2026-11-20 | 2026-07-06 | Normal | Planned
41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 2026-11-23 | 2026-06-23 | 2026-12-01 | 2026-07-01 | Normal | Planned
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 2026-11-23 | 2026-07-07 | 2026-12-15 | 2026-07-20 | Normal | Planned
43 | Strip wall forms | Project5_TAMPERED | 1 | 2026-12-02 | 2026-07-02 | 2026-12-02 | 2026-07-02 | Normal | Planned
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 2026-12-03 | 2026-07-03 | 2026-12-07 | 2026-07-07 | Normal | Planned
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 2026-12-08 | 2026-07-08 | 2026-12-08 | 2026-07-08 | Normal | Planned
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 2026-12-16 | 2026-07-21 | 2026-12-29 | 2026-08-03 | Normal | Planned
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2026-12-16 | 2026-07-07 | 2026-12-22 | 2026-07-13 | Normal | Planned
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 2026-12-30 | 2026-08-04 | 2027-01-12 | 2026-08-17 | Normal | Planned
53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 2027-01-13 | 2026-08-18 | 2027-01-19 | 2026-08-24 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baseline Finish Compliance | Baseline Finish Compliance | 20% |  | 33%
Percentage of those activities forecast to be finished before time now that were finished on time.
Id | Description | Project | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Project Time Now | Type | Status | Percent Complete
11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | 2026-08-27 | Normal | Complete | 100
22 | Set line and grade benchmarks | Project5_TAMPERED | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | 2026-08-27 | Normal | Complete | 100
23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | 2026-08-27 | Normal | Complete | 100
17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | 2026-08-27 | Normal | Complete | 100
8 | Submit preliminary shop drawings | Project5_TAMPERED | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | 2026-08-27 | Normal | Complete | 100
25 | Clear and grub site | Project5_TAMPERED | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | 2026-08-27 | Normal | Complete | 100
26 | Stone site access and temporary parking area | Project5_TAMPERED | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | 2026-08-27 | Normal | Complete | 100
27 | Rough grade site (cut and fill) | Project5_TAMPERED | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | 2026-08-27 | Normal | Complete | 100
28 | Install storm drainage | Project5_TAMPERED | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | 2026-08-27 | Normal | Complete | 100
29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | 2026-08-27 | Normal | Complete | 100
12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
30 | Perform final site grading | Project5_TAMPERED | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | 2026-08-27 | Normal | Complete | 100
31 | Erect building batter boards and layout building | Project5_TAMPERED | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | 2026-08-27 | Normal | Complete | 100
33 | Excavate foundations | Project5_TAMPERED | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | 2026-08-27 | Normal | Complete | 100
34 | Excavate elevator pit | Project5_TAMPERED | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | 2026-08-27 | Normal | InProgress | 93
35 | Form column piers and spread foundations | Project5_TAMPERED | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | 2026-08-27 | Normal | InProgress | 36
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | 2026-08-27 | Normal | Planned | 0
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | 2026-08-27 | Normal | Planned | 0
37 | Form elevator pit walls | Project5_TAMPERED | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | 2026-08-27 | Normal | Planned | 0
39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | 2026-08-27 | Normal | Planned | 0
40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | 2026-08-27 | Normal | Planned | 0
42 | Cure piers and foundations | Project5_TAMPERED | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | 2026-08-27 | Normal | Planned | 0
44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | 2026-08-27 | Normal | Planned | 0
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | 2026-08-27 | Normal | Planned | 0
41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | 2026-08-27 | Normal | Planned | 0
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | 2026-08-27 | Normal | Planned | 0
43 | Strip wall forms | Project5_TAMPERED | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | 2026-08-27 | Normal | Planned | 0
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | 2026-08-27 | Normal | Planned | 0
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | 2026-08-27 | Normal | Planned | 0
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | 2026-08-27 | Normal | Planned | 0
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | 2026-08-27 | Normal | Planned | 0
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | 2026-08-27 | Normal | Planned | 0
53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | 2026-08-27 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Forecast to be Started | Forecast to be Started | 48 | 38% | 29 | 23%
Forecast to be started before time now
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Project Time Now | Type | Status | Percent Complete
3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 0 | 2026-03-02 | 2026-03-02 | 2026-03-04 | 2026-03-04 | 2026-08-27 | Normal | Complete | 100
7 | Obtain building permits | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-05 | 2026-03-10 | 2026-03-10 | 2026-08-27 | Normal | Complete | 100
9 | Submit monthly requests for payment | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-08-27 | Normal | Complete | 100
19 | Install temporary power | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-08-27 | Normal | Complete | 100
20 | Install temporary water service | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-05 | 2026-03-06 | 2026-03-06 | 2026-08-27 | Normal | Complete | 100
11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 0 | 2026-03-06 | 2026-03-06 | 2026-03-27 | 2026-03-19 | 2026-08-27 | Normal | Complete | 100
21 | Set up site office | Project5_TAMPERED | 0 | 2026-03-09 | 2026-03-09 | 2026-03-11 | 2026-03-11 | 2026-08-27 | Normal | Complete | 100
22 | Set line and grade benchmarks | Project5_TAMPERED | 0 | 2026-03-12 | 2026-03-12 | 2026-03-25 | 2026-03-16 | 2026-08-27 | Normal | Complete | 100
4 | Submit bond and insurance documents | Project5_TAMPERED | 0 | 2026-03-25 | 2026-03-25 | 2026-03-26 | 2026-03-26 | 2026-08-27 | Normal | Complete | 100
23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 0 | 2026-03-26 | 2026-03-17 | 2026-03-27 | 2026-03-18 | 2026-08-27 | Normal | Complete | 100
5 | Prepare and submit project schedule | Project5_TAMPERED | 0 | 2026-03-27 | 2026-03-27 | 2026-03-30 | 2026-03-30 | 2026-08-27 | Normal | Complete | 100
17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 0 | 2026-03-30 | 2026-03-20 | 2026-06-19 | 2026-06-11 | 2026-08-27 | Normal | Complete | 100
6 | Prepare and submit schedule of values | Project5_TAMPERED | 0 | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | 2026-08-27 | Normal | Complete | 100
8 | Submit preliminary shop drawings | Project5_TAMPERED | 0 | 2026-04-02 | 2026-03-11 | 2026-05-04 | 2026-03-24 | 2026-08-27 | Normal | Complete | 100
25 | Clear and grub site | Project5_TAMPERED | 0 | 2026-04-06 | 2026-03-19 | 2026-04-08 | 2026-03-23 | 2026-08-27 | Normal | Complete | 100
26 | Stone site access and temporary parking area | Project5_TAMPERED | 0 | 2026-04-13 | 2026-03-24 | 2026-04-14 | 2026-03-25 | 2026-08-27 | Normal | Complete | 100
27 | Rough grade site (cut and fill) | Project5_TAMPERED | 0 | 2026-04-15 | 2026-03-26 | 2026-04-21 | 2026-04-01 | 2026-08-27 | Normal | Complete | 100
28 | Install storm drainage | Project5_TAMPERED | 0 | 2026-04-22 | 2026-04-02 | 2026-05-19 | 2026-04-15 | 2026-08-27 | Normal | Complete | 100
29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 0 | 2026-04-22 | 2026-04-02 | 2026-06-19 | 2026-04-15 | 2026-08-27 | Normal | Complete | 100
12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 0 | 2026-05-05 | 2026-03-25 | 2026-05-29 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 0 | 2026-05-05 | 2026-03-25 | 2026-05-18 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 0 | 2026-05-05 | 2026-03-25 | 2026-05-15 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 0 | 2026-05-05 | 2026-03-25 | 2026-05-18 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 0 | 2026-06-08 | 2026-03-25 | 2026-06-19 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
30 | Perform final site grading | Project5_TAMPERED | 0 | 2026-06-22 | 2026-04-16 | 2026-07-03 | 2026-04-29 | 2026-08-27 | Normal | Complete | 100
31 | Erect building batter boards and layout building | Project5_TAMPERED | 0 | 2026-07-06 | 2026-04-30 | 2026-07-31 | 2026-05-06 | 2026-08-27 | Normal | Complete | 100
33 | Excavate foundations | Project5_TAMPERED | 0 | 2026-08-03 | 2026-05-07 | 2026-08-07 | 2026-05-20 | 2026-08-27 | Normal | Complete | 100
34 | Excavate elevator pit | Project5_TAMPERED | 1 | 2026-08-10 | 2026-05-21 | 2026-08-28 | 2026-05-22 | 2026-08-27 | Normal | InProgress | 93
35 | Form column piers and spread foundations | Project5_TAMPERED | 16 | 2026-08-17 | 2026-05-21 | 2026-09-18 | 2026-05-26 | 2026-08-27 | Normal | InProgress | 36
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 2026-08-31 | 2026-05-25 | 2026-09-03 | 2026-05-28 | 2026-08-27 | Normal | Planned | 0
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 2026-09-21 | 2026-05-27 | 2026-09-24 | 2026-06-01 | 2026-08-27 | Normal | Planned | 0
37 | Form elevator pit walls | Project5_TAMPERED | 4 | 2026-09-25 | 2026-06-02 | 2026-09-30 | 2026-06-05 | 2026-08-27 | Normal | Planned | 0
39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 2026-09-25 | 2026-06-02 | 2026-10-23 | 2026-06-08 | 2026-08-27 | Normal | Planned | 0
40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 2026-10-26 | 2026-06-09 | 2026-10-26 | 2026-06-09 | 2026-08-27 | Normal | Planned | 0
42 | Cure piers and foundations | Project5_TAMPERED | 7 | 2026-10-26 | 2026-06-09 | 2026-11-03 | 2026-06-17 | 2026-08-27 | Normal | Planned | 0
44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 2026-11-04 | 2026-06-18 | 2026-11-06 | 2026-06-22 | 2026-08-27 | Normal | Planned | 0
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 2026-11-09 | 2026-06-23 | 2026-11-20 | 2026-07-06 | 2026-08-27 | Normal | Planned | 0
41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 2026-11-23 | 2026-06-23 | 2026-12-01 | 2026-07-01 | 2026-08-27 | Normal | Planned | 0
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 2026-11-23 | 2026-07-07 | 2026-12-15 | 2026-07-20 | 2026-08-27 | Normal | Planned | 0
43 | Strip wall forms | Project5_TAMPERED | 1 | 2026-12-02 | 2026-07-02 | 2026-12-02 | 2026-07-02 | 2026-08-27 | Normal | Planned | 0
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 2026-12-03 | 2026-07-03 | 2026-12-07 | 2026-07-07 | 2026-08-27 | Normal | Planned | 0
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 2026-12-08 | 2026-07-08 | 2026-12-08 | 2026-07-08 | 2026-08-27 | Normal | Planned | 0
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 2026-12-16 | 2026-07-21 | 2026-12-29 | 2026-08-03 | 2026-08-27 | Normal | Planned | 0
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2026-12-16 | 2026-07-07 | 2026-12-22 | 2026-07-13 | 2026-08-27 | Normal | Planned | 0
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 2026-12-30 | 2026-08-04 | 2027-01-12 | 2026-08-17 | 2026-08-27 | Normal | Planned | 0
50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 2027-01-13 | 2026-08-18 | 2027-02-18 | 2026-08-31 | 2026-08-27 | Normal | Planned | 0
53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 2027-01-13 | 2026-08-18 | 2027-01-19 | 2026-08-24 | 2026-08-27 | Normal | Planned | 0
55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 2027-01-20 | 2026-08-25 | 2027-02-11 | 2026-08-31 | 2026-08-27 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started On Time | Started On Time | 11 | 23% | 11 | 38%
Activities actually started on time, by their baseline start date.
Id | Description | Project | Start | Baseline Start | Finish | Baseline Finish | Type | Status
3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 2026-03-02 | 2026-03-02 | 2026-03-04 | 2026-03-04 | Normal | Complete
7 | Obtain building permits | Project5_TAMPERED | 2026-03-05 | 2026-03-05 | 2026-03-10 | 2026-03-10 | Normal | Complete
9 | Submit monthly requests for payment | Project5_TAMPERED | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete
19 | Install temporary power | Project5_TAMPERED | 2026-03-05 | 2026-03-05 | 2026-03-06 | 2026-03-06 | Normal | Complete
20 | Install temporary water service | Project5_TAMPERED | 2026-03-05 | 2026-03-05 | 2026-03-06 | 2026-03-06 | Normal | Complete
11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 2026-03-06 | 2026-03-06 | 2026-03-27 | 2026-03-19 | Normal | Complete
21 | Set up site office | Project5_TAMPERED | 2026-03-09 | 2026-03-09 | 2026-03-11 | 2026-03-11 | Normal | Complete
22 | Set line and grade benchmarks | Project5_TAMPERED | 2026-03-12 | 2026-03-12 | 2026-03-25 | 2026-03-16 | Normal | Complete
4 | Submit bond and insurance documents | Project5_TAMPERED | 2026-03-25 | 2026-03-25 | 2026-03-26 | 2026-03-26 | Normal | Complete
5 | Prepare and submit project schedule | Project5_TAMPERED | 2026-03-27 | 2026-03-27 | 2026-03-30 | 2026-03-30 | Normal | Complete
6 | Prepare and submit schedule of values | Project5_TAMPERED | 2026-03-31 | 2026-03-31 | 2026-04-01 | 2026-04-01 | Normal | Complete
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Late | Started Late | 18 | 38% | 12 | 41%
Activities actually started but late, after their baseline start date.
Id | Description | Project | Start | Baseline Start | Finish | Baseline Finish | Type | Status
23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2026-03-26 | 2026-03-17 | 2026-03-27 | 2026-03-18 | Normal | Complete
17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 2026-03-30 | 2026-03-20 | 2026-06-19 | 2026-06-11 | Normal | Complete
8 | Submit preliminary shop drawings | Project5_TAMPERED | 2026-04-02 | 2026-03-11 | 2026-05-04 | 2026-03-24 | Normal | Complete
25 | Clear and grub site | Project5_TAMPERED | 2026-04-06 | 2026-03-19 | 2026-04-08 | 2026-03-23 | Normal | Complete
26 | Stone site access and temporary parking area | Project5_TAMPERED | 2026-04-13 | 2026-03-24 | 2026-04-14 | 2026-03-25 | Normal | Complete
27 | Rough grade site (cut and fill) | Project5_TAMPERED | 2026-04-15 | 2026-03-26 | 2026-04-21 | 2026-04-01 | Normal | Complete
28 | Install storm drainage | Project5_TAMPERED | 2026-04-22 | 2026-04-02 | 2026-05-19 | 2026-04-15 | Normal | Complete
29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 2026-04-22 | 2026-04-02 | 2026-06-19 | 2026-04-15 | Normal | Complete
12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 2026-05-05 | 2026-03-25 | 2026-05-29 | 2026-04-07 | Normal | Complete
13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 2026-05-05 | 2026-03-25 | 2026-05-18 | 2026-04-07 | Normal | Complete
14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 2026-05-05 | 2026-03-25 | 2026-05-15 | 2026-04-07 | Normal | Complete
16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 2026-05-05 | 2026-03-25 | 2026-05-18 | 2026-04-07 | Normal | Complete
15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 2026-06-08 | 2026-03-25 | 2026-06-19 | 2026-04-07 | Normal | Complete
30 | Perform final site grading | Project5_TAMPERED | 2026-06-22 | 2026-04-16 | 2026-07-03 | 2026-04-29 | Normal | Complete
31 | Erect building batter boards and layout building | Project5_TAMPERED | 2026-07-06 | 2026-04-30 | 2026-07-31 | 2026-05-06 | Normal | Complete
33 | Excavate foundations | Project5_TAMPERED | 2026-08-03 | 2026-05-07 | 2026-08-07 | 2026-05-20 | Normal | Complete
34 | Excavate elevator pit | Project5_TAMPERED | 2026-08-10 | 2026-05-21 | 2026-08-28 | 2026-05-22 | Normal | InProgress
35 | Form column piers and spread foundations | Project5_TAMPERED | 2026-08-17 | 2026-05-21 | 2026-09-18 | 2026-05-26 | Normal | InProgress
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Not Started | Not Started | 19 | 40% | 6 | 21%
Activities that were planned to be start by now that are not started.
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Type | Activity Status
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 2026-08-31 | 2026-05-25 | 2026-09-03 | 2026-05-28 | Normal | Planned
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 2026-09-21 | 2026-05-27 | 2026-09-24 | 2026-06-01 | Normal | Planned
37 | Form elevator pit walls | Project5_TAMPERED | 4 | 2026-09-25 | 2026-06-02 | 2026-09-30 | 2026-06-05 | Normal | Planned
39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 2026-09-25 | 2026-06-02 | 2026-10-23 | 2026-06-08 | Normal | Planned
40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 2026-10-26 | 2026-06-09 | 2026-10-26 | 2026-06-09 | Normal | Planned
42 | Cure piers and foundations | Project5_TAMPERED | 7 | 2026-10-26 | 2026-06-09 | 2026-11-03 | 2026-06-17 | Normal | Planned
44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 2026-11-04 | 2026-06-18 | 2026-11-06 | 2026-06-22 | Normal | Planned
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 2026-11-09 | 2026-06-23 | 2026-11-20 | 2026-07-06 | Normal | Planned
41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 2026-11-23 | 2026-06-23 | 2026-12-01 | 2026-07-01 | Normal | Planned
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 2026-11-23 | 2026-07-07 | 2026-12-15 | 2026-07-20 | Normal | Planned
43 | Strip wall forms | Project5_TAMPERED | 1 | 2026-12-02 | 2026-07-02 | 2026-12-02 | 2026-07-02 | Normal | Planned
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 2026-12-03 | 2026-07-03 | 2026-12-07 | 2026-07-07 | Normal | Planned
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 2026-12-08 | 2026-07-08 | 2026-12-08 | 2026-07-08 | Normal | Planned
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 2026-12-16 | 2026-07-21 | 2026-12-29 | 2026-08-03 | Normal | Planned
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2026-12-16 | 2026-07-07 | 2026-12-22 | 2026-07-13 | Normal | Planned
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 2026-12-30 | 2026-08-04 | 2027-01-12 | 2026-08-17 | Normal | Planned
50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 2027-01-13 | 2026-08-18 | 2027-02-18 | 2026-08-31 | Normal | Planned
53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 2027-01-13 | 2026-08-18 | 2027-01-19 | 2026-08-24 | Normal | Planned
55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 2027-01-20 | 2026-08-25 | 2027-02-11 | 2026-08-31 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Baseline Start Compliance | Baseline Start Compliance | 25% |  | 41%
Percentage of those activities forecast to be started before time now that were started on time.
Id | Description | Project | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Project Time Now | Type | Status | Percent Complete
23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | 2026-08-27 | Normal | Complete | 100
17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | 2026-08-27 | Normal | Complete | 100
8 | Submit preliminary shop drawings | Project5_TAMPERED | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | 2026-08-27 | Normal | Complete | 100
25 | Clear and grub site | Project5_TAMPERED | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | 2026-08-27 | Normal | Complete | 100
26 | Stone site access and temporary parking area | Project5_TAMPERED | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | 2026-08-27 | Normal | Complete | 100
27 | Rough grade site (cut and fill) | Project5_TAMPERED | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | 2026-08-27 | Normal | Complete | 100
28 | Install storm drainage | Project5_TAMPERED | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | 2026-08-27 | Normal | Complete | 100
29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | 2026-08-27 | Normal | Complete | 100
12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | 2026-08-27 | Normal | Complete | 100
30 | Perform final site grading | Project5_TAMPERED | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | 2026-08-27 | Normal | Complete | 100
31 | Erect building batter boards and layout building | Project5_TAMPERED | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | 2026-08-27 | Normal | Complete | 100
33 | Excavate foundations | Project5_TAMPERED | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | 2026-08-27 | Normal | Complete | 100
34 | Excavate elevator pit | Project5_TAMPERED | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | 2026-08-27 | Normal | InProgress | 93
35 | Form column piers and spread foundations | Project5_TAMPERED | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | 2026-08-27 | Normal | InProgress | 36
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | 2026-08-27 | Normal | Planned | 0
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | 2026-08-27 | Normal | Planned | 0
37 | Form elevator pit walls | Project5_TAMPERED | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | 2026-08-27 | Normal | Planned | 0
39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | 2026-08-27 | Normal | Planned | 0
40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | 2026-08-27 | Normal | Planned | 0
42 | Cure piers and foundations | Project5_TAMPERED | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | 2026-08-27 | Normal | Planned | 0
44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | 2026-08-27 | Normal | Planned | 0
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | 2026-08-27 | Normal | Planned | 0
41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | 2026-08-27 | Normal | Planned | 0
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | 2026-08-27 | Normal | Planned | 0
43 | Strip wall forms | Project5_TAMPERED | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | 2026-08-27 | Normal | Planned | 0
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | 2026-08-27 | Normal | Planned | 0
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | 2026-08-27 | Normal | Planned | 0
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | 2026-08-27 | Normal | Planned | 0
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | 2026-08-27 | Normal | Planned | 0
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | 2026-08-27 | Normal | Planned | 0
50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | 2026-08-27 | Normal | Planned | 0
53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | 2026-08-27 | Normal | Planned | 0
55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | 2026-08-27 | Normal | Planned | 0

## Industry-Standards
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | Industry Standards
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Industry Standards
|  | Schedule Execution Metrics (SEM) | Half Step Delay Analysis
Ribbons | Project2 | 71 | 0
Ribbons | Project5_TAMPERED | 60 | 0
|  | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM)
|  | Completed Activities (1) | Workoff Burden (SEM01) | BRI Current (SEM02) | BRI Cumulative (SEM03) | BPI Current (SEM04) | BEI Current (SEM05) | BEI Cumulative (SEM06) | TC-BEI (SEM07) | FRI Current (SEM08) | Delta (BEI vs TC-BEI) (SEM09) | Score
Ribbons | Project2 | 20 | 5 | 0 | 0.74 | 0 | 1.25 | 0.74 | 1.07 | N/A | -0.34 | 71
Ribbons |  |  | 100%
Ribbons | Project5_TAMPERED | 27 | 2 | 0 | 0.59 | 0 | 0.67 | 0.59 | 1.24 | 0 | -0.61 | 60
Ribbons |  |  | 100%
|  | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis
|  | Time Now (HSD01) | Label (HSD02) | Forecast to be Started but not Started yet (HSD03) | Started Late (HSD04) | Forecast to be Finished but not Finished yet (HSD05) | Finished Late (HSD06) | Total days delay in the half step (Days) (HSD06) | Total days delay in the full update (Days) (HSD07) | Total days ahead in the half step (Days) (HSD08) | Total days ahead in the full update (Days) (HSD09) | Cumulative Finish Impact (Days) (HSD10) | Net Finish Impact (Days) (HSD10) | Project Finish (HSD20) | Score
Ribbons | Project2 | 2026-05-24 | N/A | 6 | 12 | 7 | 11 | N/A | 0 | N/A | 0 | 0 | 0 | 2027-09-14 | 0
Ribbons |  |  |  | 5% | 41% | 6% | 41%
Ribbons | Project5_TAMPERED | 2026-08-27 | N/A | 19 | 18 | 19 | 18 | N/A | 9646 | N/A | 0 | -9646 | -134 | 2028-01-26 | 0
Ribbons |  |  |  | 15% | 38% | 15% | 39%

## Industry-Standards-Schedule-Ex
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | Industry-Standards -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM)
Completed Activities (1) | Workoff Burden (SEM01) | BRI Current (SEM02) | BRI Cumulative (SEM03) | BPI Current (SEM04) | BEI Current (SEM05) | BEI Cumulative (SEM06) | TC-BEI (SEM07) | FRI Current (SEM08) | Delta (BEI vs TC-BEI) (SEM09) | Score
27 | 2 | 0 | 0.59 | 0 | 0.67 | 0.59 | 1.24 | 0 | -0.61 | 60
100%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Completed Activities | Completed Activities | 27 |  | 20
Total count of completed activities to date.
Id | Description | Project | ProjectTimeNowMinus30Days | Baseline Finish | Actual Finish | Project Time Now | Type
3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 2026-07-28 | 2026-03-04 | 2026-03-04 | 2026-08-27 | Normal
7 | Obtain building permits | Project5_TAMPERED | 2026-07-28 | 2026-03-10 | 2026-03-10 | 2026-08-27 | Normal
9 | Submit monthly requests for payment | Project5_TAMPERED | 2026-07-28 | 2026-03-05 | 2026-03-05 | 2026-08-27 | Normal
19 | Install temporary power | Project5_TAMPERED | 2026-07-28 | 2026-03-06 | 2026-03-06 | 2026-08-27 | Normal
20 | Install temporary water service | Project5_TAMPERED | 2026-07-28 | 2026-03-06 | 2026-03-06 | 2026-08-27 | Normal
11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 2026-07-28 | 2026-03-19 | 2026-03-27 | 2026-08-27 | Normal
21 | Set up site office | Project5_TAMPERED | 2026-07-28 | 2026-03-11 | 2026-03-11 | 2026-08-27 | Normal
22 | Set line and grade benchmarks | Project5_TAMPERED | 2026-07-28 | 2026-03-16 | 2026-03-25 | 2026-08-27 | Normal
4 | Submit bond and insurance documents | Project5_TAMPERED | 2026-07-28 | 2026-03-26 | 2026-03-26 | 2026-08-27 | Normal
23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2026-07-28 | 2026-03-18 | 2026-03-27 | 2026-08-27 | Normal
5 | Prepare and submit project schedule | Project5_TAMPERED | 2026-07-28 | 2026-03-30 | 2026-03-30 | 2026-08-27 | Normal
17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 2026-07-28 | 2026-06-11 | 2026-06-19 | 2026-08-27 | Normal
6 | Prepare and submit schedule of values | Project5_TAMPERED | 2026-07-28 | 2026-04-01 | 2026-04-01 | 2026-08-27 | Normal
8 | Submit preliminary shop drawings | Project5_TAMPERED | 2026-07-28 | 2026-03-24 | 2026-05-04 | 2026-08-27 | Normal
25 | Clear and grub site | Project5_TAMPERED | 2026-07-28 | 2026-03-23 | 2026-04-08 | 2026-08-27 | Normal
26 | Stone site access and temporary parking area | Project5_TAMPERED | 2026-07-28 | 2026-03-25 | 2026-04-14 | 2026-08-27 | Normal
27 | Rough grade site (cut and fill) | Project5_TAMPERED | 2026-07-28 | 2026-04-01 | 2026-04-21 | 2026-08-27 | Normal
28 | Install storm drainage | Project5_TAMPERED | 2026-07-28 | 2026-04-15 | 2026-05-19 | 2026-08-27 | Normal
29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 2026-07-28 | 2026-04-15 | 2026-06-19 | 2026-08-27 | Normal
12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 2026-07-28 | 2026-04-07 | 2026-05-29 | 2026-08-27 | Normal
13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 2026-07-28 | 2026-04-07 | 2026-05-18 | 2026-08-27 | Normal
14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 2026-07-28 | 2026-04-07 | 2026-05-15 | 2026-08-27 | Normal
16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 2026-07-28 | 2026-04-07 | 2026-05-18 | 2026-08-27 | Normal
15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 2026-07-28 | 2026-04-07 | 2026-06-19 | 2026-08-27 | Normal
30 | Perform final site grading | Project5_TAMPERED | 2026-07-28 | 2026-04-29 | 2026-07-03 | 2026-08-27 | Normal
31 | Erect building batter boards and layout building | Project5_TAMPERED | 2026-07-28 | 2026-05-06 | 2026-07-31 | 2026-08-27 | Normal
33 | Excavate foundations | Project5_TAMPERED | 2026-07-28 | 2026-05-20 | 2026-08-07 | 2026-08-27 | Normal
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Workoff Burden | Workoff Burden | 2 | 100% | 5 | 100%
Workoff 30 Day Window
Id | Description | Project | Baseline Finish | ProjectTimeNowMinus30Days | Actual Finish | Project Time Now | Type
31 | Erect building batter boards and layout building | Project5_TAMPERED | 2026-05-06 | 2026-07-28 | 2026-07-31 | 2026-08-27 | Normal
33 | Excavate foundations | Project5_TAMPERED | 2026-05-20 | 2026-07-28 | 2026-08-07 | 2026-08-27 | Normal
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BRI Current | BRI Current | 0 |  | 0
Current Baseline Realism Index (BRI) - Is the contractor executing the plan?
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BRI Cumulative | BRI Cumulative | 0.59 |  | 0.74
Current Baseline Realism Index (BRI) - Is the contractor executing the plan?
Id | Description | Project | Baseline Finish | Finish | Actual Finish | Project Time Now | Type | Status
3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-08-27 | Normal | Complete
7 | Obtain building permits | Project5_TAMPERED | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-08-27 | Normal | Complete
9 | Submit monthly requests for payment | Project5_TAMPERED | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-08-27 | Normal | Complete
19 | Install temporary power | Project5_TAMPERED | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-08-27 | Normal | Complete
20 | Install temporary water service | Project5_TAMPERED | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-08-27 | Normal | Complete
11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 2026-03-19 | 2026-03-27 | 2026-03-27 | 2026-08-27 | Normal | Complete
21 | Set up site office | Project5_TAMPERED | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-08-27 | Normal | Complete
22 | Set line and grade benchmarks | Project5_TAMPERED | 2026-03-16 | 2026-03-25 | 2026-03-25 | 2026-08-27 | Normal | Complete
4 | Submit bond and insurance documents | Project5_TAMPERED | 2026-03-26 | 2026-03-26 | 2026-03-26 | 2026-08-27 | Normal | Complete
23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2026-03-18 | 2026-03-27 | 2026-03-27 | 2026-08-27 | Normal | Complete
5 | Prepare and submit project schedule | Project5_TAMPERED | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-08-27 | Normal | Complete
17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 2026-06-11 | 2026-06-19 | 2026-06-19 | 2026-08-27 | Normal | Complete
6 | Prepare and submit schedule of values | Project5_TAMPERED | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-08-27 | Normal | Complete
8 | Submit preliminary shop drawings | Project5_TAMPERED | 2026-03-24 | 2026-05-04 | 2026-05-04 | 2026-08-27 | Normal | Complete
25 | Clear and grub site | Project5_TAMPERED | 2026-03-23 | 2026-04-08 | 2026-04-08 | 2026-08-27 | Normal | Complete
26 | Stone site access and temporary parking area | Project5_TAMPERED | 2026-03-25 | 2026-04-14 | 2026-04-14 | 2026-08-27 | Normal | Complete
27 | Rough grade site (cut and fill) | Project5_TAMPERED | 2026-04-01 | 2026-04-21 | 2026-04-21 | 2026-08-27 | Normal | Complete
28 | Install storm drainage | Project5_TAMPERED | 2026-04-15 | 2026-05-19 | 2026-05-19 | 2026-08-27 | Normal | Complete
29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 2026-04-15 | 2026-06-19 | 2026-06-19 | 2026-08-27 | Normal | Complete
12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 2026-04-07 | 2026-05-29 | 2026-05-29 | 2026-08-27 | Normal | Complete
13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 2026-04-07 | 2026-05-18 | 2026-05-18 | 2026-08-27 | Normal | Complete
14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 2026-04-07 | 2026-05-15 | 2026-05-15 | 2026-08-27 | Normal | Complete
16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 2026-04-07 | 2026-05-18 | 2026-05-18 | 2026-08-27 | Normal | Complete
15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 2026-04-07 | 2026-06-19 | 2026-06-19 | 2026-08-27 | Normal | Complete
30 | Perform final site grading | Project5_TAMPERED | 2026-04-29 | 2026-07-03 | 2026-07-03 | 2026-08-27 | Normal | Complete
31 | Erect building batter boards and layout building | Project5_TAMPERED | 2026-05-06 | 2026-07-31 | 2026-07-31 | 2026-08-27 | Normal | Complete
33 | Excavate foundations | Project5_TAMPERED | 2026-05-20 | 2026-08-07 | 2026-08-07 | 2026-08-27 | Normal | Complete
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BPI Current | BPI Current | 0 |  | 0
Current Baseline Progress Index (BPI) - Is the contractor keeping up with planned work?
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI Current | BEI Current | 0.67 |  | 1.25
Current Baseline Execution Index (BEI)
Id | Description | Project | ProjectTimeNowMinus30Days | Baseline Finish | Actual Finish | Project Time Now | Type | Status
31 | Erect building batter boards and layout building | Project5_TAMPERED | 2026-07-28 | 2026-05-06 | 2026-07-31 | 2026-08-27 | Normal | Complete
33 | Excavate foundations | Project5_TAMPERED | 2026-07-28 | 2026-05-20 | 2026-08-07 | 2026-08-27 | Normal | Complete
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-07-28 | 2026-08-03 |  | 2026-08-27 | Normal | Planned
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-07-28 | 2026-08-17 |  | 2026-08-27 | Normal | Planned
53 | Touch-up paint on steel | Project5_TAMPERED | 2026-07-28 | 2026-08-24 |  | 2026-08-27 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
BEI Cumulative | BEI Cumulative | 0.59 |  | 0.74
Cumulative Baseline Execution Index (BEI)
Id | Description | Project | ProjectTimeNowMinus30Days | Baseline Finish | Actual Finish | Project Time Now | Type | Status
3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 2026-07-28 | 2026-03-04 | 2026-03-04 | 2026-08-27 | Normal | Complete
7 | Obtain building permits | Project5_TAMPERED | 2026-07-28 | 2026-03-10 | 2026-03-10 | 2026-08-27 | Normal | Complete
9 | Submit monthly requests for payment | Project5_TAMPERED | 2026-07-28 | 2026-03-05 | 2026-03-05 | 2026-08-27 | Normal | Complete
19 | Install temporary power | Project5_TAMPERED | 2026-07-28 | 2026-03-06 | 2026-03-06 | 2026-08-27 | Normal | Complete
20 | Install temporary water service | Project5_TAMPERED | 2026-07-28 | 2026-03-06 | 2026-03-06 | 2026-08-27 | Normal | Complete
11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 2026-07-28 | 2026-03-19 | 2026-03-27 | 2026-08-27 | Normal | Complete
21 | Set up site office | Project5_TAMPERED | 2026-07-28 | 2026-03-11 | 2026-03-11 | 2026-08-27 | Normal | Complete
22 | Set line and grade benchmarks | Project5_TAMPERED | 2026-07-28 | 2026-03-16 | 2026-03-25 | 2026-08-27 | Normal | Complete
4 | Submit bond and insurance documents | Project5_TAMPERED | 2026-07-28 | 2026-03-26 | 2026-03-26 | 2026-08-27 | Normal | Complete
23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2026-07-28 | 2026-03-18 | 2026-03-27 | 2026-08-27 | Normal | Complete
5 | Prepare and submit project schedule | Project5_TAMPERED | 2026-07-28 | 2026-03-30 | 2026-03-30 | 2026-08-27 | Normal | Complete
17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 2026-07-28 | 2026-06-11 | 2026-06-19 | 2026-08-27 | Normal | Complete
6 | Prepare and submit schedule of values | Project5_TAMPERED | 2026-07-28 | 2026-04-01 | 2026-04-01 | 2026-08-27 | Normal | Complete
8 | Submit preliminary shop drawings | Project5_TAMPERED | 2026-07-28 | 2026-03-24 | 2026-05-04 | 2026-08-27 | Normal | Complete
25 | Clear and grub site | Project5_TAMPERED | 2026-07-28 | 2026-03-23 | 2026-04-08 | 2026-08-27 | Normal | Complete
26 | Stone site access and temporary parking area | Project5_TAMPERED | 2026-07-28 | 2026-03-25 | 2026-04-14 | 2026-08-27 | Normal | Complete
27 | Rough grade site (cut and fill) | Project5_TAMPERED | 2026-07-28 | 2026-04-01 | 2026-04-21 | 2026-08-27 | Normal | Complete
28 | Install storm drainage | Project5_TAMPERED | 2026-07-28 | 2026-04-15 | 2026-05-19 | 2026-08-27 | Normal | Complete
29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 2026-07-28 | 2026-04-15 | 2026-06-19 | 2026-08-27 | Normal | Complete
12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 2026-07-28 | 2026-04-07 | 2026-05-29 | 2026-08-27 | Normal | Complete
13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 2026-07-28 | 2026-04-07 | 2026-05-18 | 2026-08-27 | Normal | Complete
14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 2026-07-28 | 2026-04-07 | 2026-05-15 | 2026-08-27 | Normal | Complete
16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 2026-07-28 | 2026-04-07 | 2026-05-18 | 2026-08-27 | Normal | Complete
15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 2026-07-28 | 2026-04-07 | 2026-06-19 | 2026-08-27 | Normal | Complete
30 | Perform final site grading | Project5_TAMPERED | 2026-07-28 | 2026-04-29 | 2026-07-03 | 2026-08-27 | Normal | Complete
31 | Erect building batter boards and layout building | Project5_TAMPERED | 2026-07-28 | 2026-05-06 | 2026-07-31 | 2026-08-27 | Normal | Complete
33 | Excavate foundations | Project5_TAMPERED | 2026-07-28 | 2026-05-20 | 2026-08-07 | 2026-08-27 | Normal | Complete
34 | Excavate elevator pit | Project5_TAMPERED | 2026-07-28 | 2026-05-22 |  | 2026-08-27 | Normal | InProgress
35 | Form column piers and spread foundations | Project5_TAMPERED | 2026-07-28 | 2026-05-26 |  | 2026-08-27 | Normal | InProgress
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-07-28 | 2026-05-28 |  | 2026-08-27 | Normal | Planned
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-07-28 | 2026-06-01 |  | 2026-08-27 | Normal | Planned
37 | Form elevator pit walls | Project5_TAMPERED | 2026-07-28 | 2026-06-05 |  | 2026-08-27 | Normal | Planned
39 | Pour column piers and foundations | Project5_TAMPERED | 2026-07-28 | 2026-06-08 |  | 2026-08-27 | Normal | Planned
40 | Pour concrete elevator walls | Project5_TAMPERED | 2026-07-28 | 2026-06-09 |  | 2026-08-27 | Normal | Planned
42 | Cure piers and foundations | Project5_TAMPERED | 2026-07-28 | 2026-06-17 |  | 2026-08-27 | Normal | Planned
44 | Strip column piers and foundation forms | Project5_TAMPERED | 2026-07-28 | 2026-06-22 |  | 2026-08-27 | Normal | Planned
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-07-28 | 2026-07-06 |  | 2026-08-27 | Normal | Planned
41 | Cure elevator wall concrete | Project5_TAMPERED | 2026-07-28 | 2026-07-01 |  | 2026-08-27 | Normal | Planned
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-07-28 | 2026-07-20 |  | 2026-08-27 | Normal | Planned
43 | Strip wall forms | Project5_TAMPERED | 2026-07-28 | 2026-07-02 |  | 2026-08-27 | Normal | Planned
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-07-28 | 2026-07-07 |  | 2026-08-27 | Normal | Planned
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-07-28 | 2026-07-08 |  | 2026-08-27 | Normal | Planned
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-07-28 | 2026-08-03 |  | 2026-08-27 | Normal | Planned
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-07-28 | 2026-07-13 |  | 2026-08-27 | Normal | Planned
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-07-28 | 2026-08-17 |  | 2026-08-27 | Normal | Planned
53 | Touch-up paint on steel | Project5_TAMPERED | 2026-07-28 | 2026-08-24 |  | 2026-08-27 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
TC-BEI | TC-BEI | 1.24 |  | 1.07
To-Complete Baseline Execution Index (TC-BEI)
Id | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
34 | Excavate elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-05-22 |  | 2026-08-28 | Normal | InProgress
35 | Form column piers and spread foundations | Project5_TAMPERED | 2026-08-27 | 2026-05-26 |  | 2026-09-18 | Normal | InProgress
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-27 | 2026-05-28 |  | 2026-09-03 | Normal | Planned
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-27 | 2026-06-01 |  | 2026-09-24 | Normal | Planned
37 | Form elevator pit walls | Project5_TAMPERED | 2026-08-27 | 2026-06-05 |  | 2026-09-30 | Normal | Planned
39 | Pour column piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-08 |  | 2026-10-23 | Normal | Planned
40 | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-27 | 2026-06-09 |  | 2026-10-26 | Normal | Planned
42 | Cure piers and foundations | Project5_TAMPERED | 2026-08-27 | 2026-06-17 |  | 2026-11-03 | Normal | Planned
44 | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-27 | 2026-06-22 |  | 2026-11-06 | Normal | Planned
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-07-06 |  | 2026-11-20 | Normal | Planned
41 | Cure elevator wall concrete | Project5_TAMPERED | 2026-08-27 | 2026-07-01 |  | 2026-12-01 | Normal | Planned
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-07-20 |  | 2026-12-15 | Normal | Planned
43 | Strip wall forms | Project5_TAMPERED | 2026-08-27 | 2026-07-02 |  | 2026-12-02 | Normal | Planned
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-07 |  | 2026-12-07 | Normal | Planned
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 2026-08-27 | 2026-07-08 |  | 2026-12-08 | Normal | Planned
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 2026-08-27 | 2026-08-03 |  | 2026-12-29 | Normal | Planned
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-07-13 |  | 2026-12-22 | Normal | Planned
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 2026-08-27 | 2026-08-17 |  | 2027-01-12 | Normal | Planned
50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-18 | Normal | Planned
53 | Touch-up paint on steel | Project5_TAMPERED | 2026-08-27 | 2026-08-24 |  | 2027-01-19 | Normal | Planned
55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-08-31 |  | 2027-02-11 | Normal | Planned
57 | Pour 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-04 |  | 2027-02-17 | Normal | Planned
58 | Cure 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-15 |  | 2027-02-26 | Normal | Planned
81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-18 | Normal | Planned
60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-09-22 |  | 2027-03-05 | Normal | Planned
59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-24 |  | 2027-03-09 | Normal | Planned
62 | Pour 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-09-28 |  | 2027-03-11 | Normal | Planned
70 | Form 1st floor | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
73 | Install rebar and in-floor utilities | Project5_TAMPERED | 2026-08-27 | 2026-09-30 |  | 2027-03-15 | Normal | Planned
63 | Cure 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
71 | Install electrical underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
72 | Install plumbing underground | Project5_TAMPERED | 2026-08-27 | 2026-10-07 |  | 2027-03-22 | Normal | Planned
111 | Set elevator equipment in shafts | Project5_TAMPERED | 2026-08-27 | 2026-10-26 |  | 2027-04-15 | Normal | Planned
127 | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-10-12 |  | 2027-04-01 | Normal | Planned
65 | Form roof slab including all floor openings | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 2026-08-27 | 2026-10-14 |  | 2027-03-29 | Normal | Planned
74 | Pour 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-13 |  | 2027-03-26 | Normal | Planned
64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-16 |  | 2027-03-31 | Normal | Planned
67 | Pour roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-20 |  | 2027-04-02 | Normal | Planned
75 | Cure 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-10-27 |  | 2027-04-09 | Normal | Planned
68 | Cure roof slab | Project5_TAMPERED | 2026-08-27 | 2026-10-29 |  | 2027-04-13 | Normal | Planned
69 | Strip forms from roof slab | Project5_TAMPERED | 2026-08-27 | 2026-11-02 |  | 2027-04-15 | Normal | Planned
76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2026-08-27 | 2026-11-04 |  | 2027-04-19 | Normal | Planned
78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-06 | Normal | Planned
112 | Set equipment in mechanical room | Project5_TAMPERED | 2026-08-27 | 2026-11-09 |  | 2027-04-29 | Normal | Planned
80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 2026-08-27 | 2026-12-02 |  | 2027-05-17 | Normal | Planned
113 | Test and align doors and equipment | Project5_TAMPERED | 2026-08-27 | 2026-11-23 |  | 2027-05-13 | Normal | Planned
82 | Install exterior masonry work | Project5_TAMPERED | 2026-08-27 | 2026-12-28 |  | 2027-06-10 | Normal | Planned
84 | Install tile in toilet rooms | Project5_TAMPERED | 2026-08-27 | 2026-12-16 |  | 2027-05-31 | Normal | Planned
86 | Clean toilet room tile | Project5_TAMPERED | 2026-08-27 | 2026-12-23 |  | 2027-06-07 | Normal | Planned
85 | Clean masonry | Project5_TAMPERED | 2026-08-27 | 2027-01-04 |  | 2027-06-17 | Normal | Planned
88 | Install flashing at parapet walls | Project5_TAMPERED | 2026-08-27 | 2027-01-01 |  | 2027-06-16 | Normal | Planned
94 | Install window wall aluminum and glass | Project5_TAMPERED | 2026-08-27 | 2027-02-01 |  | 2027-07-15 | Normal | Planned
83 | Install roof drains | Project5_TAMPERED | 2026-08-27 | 2027-01-05 |  | 2027-06-18 | Normal | Planned
116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 2026-08-27 | 2027-01-18 |  | 2027-07-01 | Normal | Planned
89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2026-08-27 | 2027-01-07 |  | 2027-06-22 | Normal | Planned
90 | Install seamless roofing material | Project5_TAMPERED | 2026-08-27 | 2027-01-21 |  | 2027-07-06 | Normal | Planned
91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 2026-08-27 | 2027-01-28 |  | 2027-07-13 | Normal | Planned
92 | Set rooftop equipment | Project5_TAMPERED | 2026-08-27 | 2027-02-11 |  | 2027-07-27 | Normal | Planned
95 | Install interior stud walls and drywall | Project5_TAMPERED | 2026-08-27 | 2027-03-08 |  | 2027-08-19 | Normal | Planned
97 | Install store front doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-02-22 |  | 2027-08-05 | Normal | Planned
115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-01 |  | 2027-08-12 | Normal | Planned
130 | Install duct in building chase | Project5_TAMPERED | 2026-08-27 | 2027-03-04 |  | 2027-08-17 | Normal | Planned
121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
117 | Set plumbing fixtures and trim | Project5_TAMPERED | 2026-08-27 | 2027-03-22 |  | 2027-09-02 | Normal | Planned
99 | Install millwork and wood trim | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
102 | Install duct in ceiling plenum space | Project5_TAMPERED | 2026-08-27 | 2027-03-29 |  | 2027-09-09 | Normal | Planned
133 | Install hard tile flooring in common areas | Project5_TAMPERED | 2026-08-27 | 2027-03-15 |  | 2027-08-26 | Normal | Planned
134 | Clean hard tile floors | Project5_TAMPERED | 2026-08-27 | 2027-03-19 |  | 2027-09-01 | Normal | Planned
122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
96 | Install interior doors and hardware | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
103 | Install ceiling grid | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 2026-08-27 | 2027-04-12 |  | 2027-09-23 | Normal | Planned
100 | Paint walls and woodwork | Project5_TAMPERED | 2026-08-27 | 2027-05-10 |  | 2027-10-21 | Normal | Planned
104 | Install ceiling tile | Project5_TAMPERED | 2026-08-27 | 2027-04-26 |  | 2027-10-07 | Normal | Planned
123 | Install and terminate electrical devices | Project5_TAMPERED | 2026-08-27 | 2027-05-03 |  | 2027-10-14 | Normal | Planned
124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2026-08-27 | 2027-05-19 |  | 2027-10-18 | Normal | Planned
125 | Install light fixtures - test and clean | Project5_TAMPERED | 2026-08-27 | 2027-05-17 |  | 2027-11-01 | Normal | Planned
105 | Hang wallpaper | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
106 | Install building carpet | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-12-17 | Normal | Planned
107 | Install hardware and accessories | Project5_TAMPERED | 2026-08-27 | 2027-05-31 |  | 2027-11-26 | Normal | Planned
108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 2026-08-27 | 2027-05-24 |  | 2027-11-04 | Normal | Planned
109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 2026-08-27 | 2027-06-07 |  | 2027-11-18 | Normal | Planned
135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 2026-08-27 | 2027-06-11 |  | 2027-12-02 | Normal | Planned
136 | Substantial completion date | Project5_TAMPERED | 2026-08-27 | 2027-06-14 |  | 2027-12-03 | Normal | Planned
138 | Complete elevator inspection and certification | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2027-12-07 | Normal | Planned
139 | Perform architect's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-17 |  | 2027-12-08 | Normal | Planned
140 | Perform local building agency inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-18 |  | 2027-12-09 | Normal | Planned
131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 2026-08-27 | 2027-06-16 |  | 2028-01-06 | Normal | Planned
141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 2026-08-27 | 2027-06-21 |  | 2027-12-10 | Normal | Planned
142 | Complete punch list items from all inspections | Project5_TAMPERED | 2026-08-27 | 2027-07-05 |  | 2028-01-20 | Normal | Planned
143 | Obtain certificate of occupancy | Project5_TAMPERED | 2026-08-27 | 2027-07-07 |  | 2028-01-24 | Normal | Planned
144 | Issue final completion documents including warranties | Project5_TAMPERED | 2026-08-27 | 2027-07-08 |  | 2028-01-25 | Normal | Planned
145 | Issue final request for payment | Project5_TAMPERED | 2026-08-27 | 2027-07-09 |  | 2028-01-26 | Normal | Planned
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
FRI Current | FRI Current | 0 |  | N/A
Forecast Realism Index (FRI)
Id | Description | Project | PreviousFinish | Finish | Actual Finish | Project Time Now | Type | Status | ProjectTimeNowMinus30Days
34 | Excavate elevator pit | Project5_TAMPERED | 2026-07-28 | 2026-08-28 |  | 2026-08-27 | Normal | InProgress | 2026-07-28
35 | Form column piers and spread foundations | Project5_TAMPERED | 2026-07-30 | 2026-09-18 |  | 2026-08-27 | Normal | InProgress | 2026-07-28
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 2026-08-03 | 2026-09-03 |  | 2026-08-27 | Normal | Planned | 2026-07-28
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 2026-08-05 | 2026-09-24 |  | 2026-08-27 | Normal | Planned | 2026-07-28
37 | Form elevator pit walls | Project5_TAMPERED | 2026-08-11 | 2026-09-30 |  | 2026-08-27 | Normal | Planned | 2026-07-28
39 | Pour column piers and foundations | Project5_TAMPERED | 2026-08-12 | 2026-10-23 |  | 2026-08-27 | Normal | Planned | 2026-07-28
40 | Pour concrete elevator walls | Project5_TAMPERED | 2026-08-13 | 2026-10-26 |  | 2026-08-27 | Normal | Planned | 2026-07-28
42 | Cure piers and foundations | Project5_TAMPERED | 2026-08-21 | 2026-11-03 |  | 2026-08-27 | Normal | Planned | 2026-07-28
44 | Strip column piers and foundation forms | Project5_TAMPERED | 2026-08-26 | 2026-11-06 |  | 2026-08-27 | Normal | Planned | 2026-07-28
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Delta (BEI vs TC-BEI) | Delta (BEI vs TC-BEI) | -0.61 |  | -0.34
Change in efficiency needed to achieve the forecast

## Industry-Standards-Half-Step-D
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities | P-P5 - 288 Activities
Program-Summary -> | Industry-Standards -> | Project5_TAMPERED: Detailed View
Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026 | Created on: 6/21/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis
Time Now (HSD01) | Label (HSD02) | Forecast to be Started but not Started yet (HSD03) | Started Late (HSD04) | Forecast to be Finished but not Finished yet (HSD05) | Finished Late (HSD06) | Total days delay in the half step (Days) (HSD06) | Total days delay in the full update (Days) (HSD07) | Total days ahead in the half step (Days) (HSD08) | Total days ahead in the full update (Days) (HSD09) | Cumulative Finish Impact (Days) (HSD10) | Net Finish Impact (Days) (HSD10) | Project Finish (HSD20) | Score
2026-08-27 | N/A | 19 | 18 | 19 | 18 | N/A | 9646 | N/A | 0 | -9646 | -134 | 2028-01-26 | 0
|  | 15% | 38% | 15% | 39%
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Time Now | Time Now | 2026-08-27 |  | 2026-05-24
Current Project Time Now
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Label | Label | N/A |  | N/A
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Forecast to be Started but not Started yet | Forecast to be Started but not Started yet | 19 | 15% | 6 | 5%
Forecast to be started before time now
Id | Description | Project | Remaining Duration | Start | Baseline Start | Actual Start | Project Time Now | Type | Status | Percent Complete
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 2026-08-31 | 2026-05-25 |  | 2026-08-27 | Normal | Planned | 0
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 2026-09-21 | 2026-05-27 |  | 2026-08-27 | Normal | Planned | 0
37 | Form elevator pit walls | Project5_TAMPERED | 4 | 2026-09-25 | 2026-06-02 |  | 2026-08-27 | Normal | Planned | 0
39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 2026-09-25 | 2026-06-02 |  | 2026-08-27 | Normal | Planned | 0
40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 2026-10-26 | 2026-06-09 |  | 2026-08-27 | Normal | Planned | 0
42 | Cure piers and foundations | Project5_TAMPERED | 7 | 2026-10-26 | 2026-06-09 |  | 2026-08-27 | Normal | Planned | 0
44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 2026-11-04 | 2026-06-18 |  | 2026-08-27 | Normal | Planned | 0
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 2026-11-09 | 2026-06-23 |  | 2026-08-27 | Normal | Planned | 0
41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 2026-11-23 | 2026-06-23 |  | 2026-08-27 | Normal | Planned | 0
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 2026-11-23 | 2026-07-07 |  | 2026-08-27 | Normal | Planned | 0
43 | Strip wall forms | Project5_TAMPERED | 1 | 2026-12-02 | 2026-07-02 |  | 2026-08-27 | Normal | Planned | 0
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 2026-12-03 | 2026-07-03 |  | 2026-08-27 | Normal | Planned | 0
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 2026-12-08 | 2026-07-08 |  | 2026-08-27 | Normal | Planned | 0
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 2026-12-16 | 2026-07-21 |  | 2026-08-27 | Normal | Planned | 0
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2026-12-16 | 2026-07-07 |  | 2026-08-27 | Normal | Planned | 0
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 2026-12-30 | 2026-08-04 |  | 2026-08-27 | Normal | Planned | 0
50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 2027-01-13 | 2026-08-18 |  | 2026-08-27 | Normal | Planned | 0
53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 2027-01-13 | 2026-08-18 |  | 2026-08-27 | Normal | Planned | 0
55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 2027-01-20 | 2026-08-25 |  | 2026-08-27 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Started Late | Started Late | 18 | 38% | 12 | 41%
Activities actually started but late, after their baseline start date.
Id | Description | Project | Baseline Start | Start | StartDelay | Type | Status
23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2026-03-17 | 2026-03-26 | 9 | Normal | Complete
17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 2026-03-20 | 2026-03-30 | 10 | Normal | Complete
8 | Submit preliminary shop drawings | Project5_TAMPERED | 2026-03-11 | 2026-04-02 | 22 | Normal | Complete
25 | Clear and grub site | Project5_TAMPERED | 2026-03-19 | 2026-04-06 | 18 | Normal | Complete
26 | Stone site access and temporary parking area | Project5_TAMPERED | 2026-03-24 | 2026-04-13 | 20 | Normal | Complete
27 | Rough grade site (cut and fill) | Project5_TAMPERED | 2026-03-26 | 2026-04-15 | 20 | Normal | Complete
28 | Install storm drainage | Project5_TAMPERED | 2026-04-02 | 2026-04-22 | 20 | Normal | Complete
29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 2026-04-02 | 2026-04-22 | 20 | Normal | Complete
12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 2026-03-25 | 2026-05-05 | 41 | Normal | Complete
13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 2026-03-25 | 2026-05-05 | 41 | Normal | Complete
14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 2026-03-25 | 2026-05-05 | 41 | Normal | Complete
16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 2026-03-25 | 2026-05-05 | 41 | Normal | Complete
15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 2026-03-25 | 2026-06-08 | 75 | Normal | Complete
30 | Perform final site grading | Project5_TAMPERED | 2026-04-16 | 2026-06-22 | 67 | Normal | Complete
31 | Erect building batter boards and layout building | Project5_TAMPERED | 2026-04-30 | 2026-07-06 | 67 | Normal | Complete
33 | Excavate foundations | Project5_TAMPERED | 2026-05-07 | 2026-08-03 | 88 | Normal | Complete
34 | Excavate elevator pit | Project5_TAMPERED | 2026-05-21 | 2026-08-10 | 81 | Normal | InProgress
35 | Form column piers and spread foundations | Project5_TAMPERED | 2026-05-21 | 2026-08-17 | 88 | Normal | InProgress
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Forecast to be Finished but not Finished yet | Forecast to be Finished but not Finished yet | 19 | 15% | 7 | 6%
Forecast to be finished before time now
Id | Description | Project | Remaining Duration | Finish | Baseline Finish | Project Time Now | Type | Status | Percent Complete
34 | Excavate elevator pit | Project5_TAMPERED | 1 | 2026-08-28 | 2026-05-22 | 2026-08-27 | Normal | InProgress | 93
35 | Form column piers and spread foundations | Project5_TAMPERED | 16 | 2026-09-18 | 2026-05-26 | 2026-08-27 | Normal | InProgress | 36
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 2026-09-03 | 2026-05-28 | 2026-08-27 | Normal | Planned | 0
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 2026-09-24 | 2026-06-01 | 2026-08-27 | Normal | Planned | 0
37 | Form elevator pit walls | Project5_TAMPERED | 4 | 2026-09-30 | 2026-06-05 | 2026-08-27 | Normal | Planned | 0
39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 2026-10-23 | 2026-06-08 | 2026-08-27 | Normal | Planned | 0
40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 2026-10-26 | 2026-06-09 | 2026-08-27 | Normal | Planned | 0
42 | Cure piers and foundations | Project5_TAMPERED | 7 | 2026-11-03 | 2026-06-17 | 2026-08-27 | Normal | Planned | 0
44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 2026-11-06 | 2026-06-22 | 2026-08-27 | Normal | Planned | 0
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 2026-11-20 | 2026-07-06 | 2026-08-27 | Normal | Planned | 0
41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 2026-12-01 | 2026-07-01 | 2026-08-27 | Normal | Planned | 0
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 2026-12-15 | 2026-07-20 | 2026-08-27 | Normal | Planned | 0
43 | Strip wall forms | Project5_TAMPERED | 1 | 2026-12-02 | 2026-07-02 | 2026-08-27 | Normal | Planned | 0
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 2026-12-07 | 2026-07-07 | 2026-08-27 | Normal | Planned | 0
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 2026-12-08 | 2026-07-08 | 2026-08-27 | Normal | Planned | 0
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 2026-12-29 | 2026-08-03 | 2026-08-27 | Normal | Planned | 0
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2026-12-22 | 2026-07-13 | 2026-08-27 | Normal | Planned | 0
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 2027-01-12 | 2026-08-17 | 2026-08-27 | Normal | Planned | 0
53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 2027-01-19 | 2026-08-24 | 2026-08-27 | Normal | Planned | 0
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Finished Late | Finished Late | 18 | 39% | 11 | 41%
Activities actually completed but late, after their baseline finish date.
Id | Description | Project | Baseline Finish | Finish | FinishDelay | Type | Status
11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 2026-03-19 | 2026-03-27 | 8 | Normal | Complete
22 | Set line and grade benchmarks | Project5_TAMPERED | 2026-03-16 | 2026-03-25 | 9 | Normal | Complete
23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2026-03-18 | 2026-03-27 | 9 | Normal | Complete
17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 2026-06-11 | 2026-06-19 | 8 | Normal | Complete
8 | Submit preliminary shop drawings | Project5_TAMPERED | 2026-03-24 | 2026-05-04 | 41 | Normal | Complete
25 | Clear and grub site | Project5_TAMPERED | 2026-03-23 | 2026-04-08 | 16 | Normal | Complete
26 | Stone site access and temporary parking area | Project5_TAMPERED | 2026-03-25 | 2026-04-14 | 20 | Normal | Complete
27 | Rough grade site (cut and fill) | Project5_TAMPERED | 2026-04-01 | 2026-04-21 | 20 | Normal | Complete
28 | Install storm drainage | Project5_TAMPERED | 2026-04-15 | 2026-05-19 | 34 | Normal | Complete
29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 2026-04-15 | 2026-06-19 | 65 | Normal | Complete
12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 2026-04-07 | 2026-05-29 | 52 | Normal | Complete
13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 2026-04-07 | 2026-05-18 | 41 | Normal | Complete
14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 2026-04-07 | 2026-05-15 | 38 | Normal | Complete
16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 2026-04-07 | 2026-05-18 | 41 | Normal | Complete
15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 2026-04-07 | 2026-06-19 | 73 | Normal | Complete
30 | Perform final site grading | Project5_TAMPERED | 2026-04-29 | 2026-07-03 | 65 | Normal | Complete
31 | Erect building batter boards and layout building | Project5_TAMPERED | 2026-05-06 | 2026-07-31 | 86 | Normal | Complete
33 | Excavate foundations | Project5_TAMPERED | 2026-05-20 | 2026-08-07 | 79 | Normal | Complete
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total days delay in the half step (Days) | Total days delay in the half step (Days) | N/A |  | N/A
The total number of days activities are delayed due to the progress update in the half step.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total days delay in the full update (Days) | Total days delay in the full update (Days) | 9646 |  | 0
The total number of days activities are delayed due to the updated information on the fully updated schedule.
Id | Description | Project | Remaining Duration | PreviousFinish | Finish | DelayDays | Type | Status | FullStepLabel
31 | Erect building batter boards and layout building | Project5_TAMPERED | 0 | 2026-07-10 | 2026-07-31 | 21 | Normal | Complete | Compared to previous snapshot
33 | Excavate foundations | Project5_TAMPERED | 0 | 2026-07-24 | 2026-08-07 | 14 | Normal | Complete | Compared to previous snapshot
34 | Excavate elevator pit | Project5_TAMPERED | 1 | 2026-07-28 | 2026-08-28 | 31 | Normal | InProgress | Compared to previous snapshot
35 | Form column piers and spread foundations | Project5_TAMPERED | 16 | 2026-07-30 | 2026-09-18 | 50 | Normal | InProgress | Compared to previous snapshot
36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 2026-08-03 | 2026-09-03 | 31 | Normal | Planned | Compared to previous snapshot
38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 2026-08-05 | 2026-09-24 | 50 | Normal | Planned | Compared to previous snapshot
37 | Form elevator pit walls | Project5_TAMPERED | 4 | 2026-08-11 | 2026-09-30 | 50 | Normal | Planned | Compared to previous snapshot
39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 2026-08-12 | 2026-10-23 | 72 | Normal | Planned | Compared to previous snapshot
40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 2026-08-13 | 2026-10-26 | 74 | Normal | Planned | Compared to previous snapshot
42 | Cure piers and foundations | Project5_TAMPERED | 7 | 2026-08-21 | 2026-11-03 | 74 | Normal | Planned | Compared to previous snapshot
44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 2026-08-26 | 2026-11-06 | 72 | Normal | Planned | Compared to previous snapshot
48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 2026-09-09 | 2026-11-20 | 72 | Normal | Planned | Compared to previous snapshot
41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 2026-09-04 | 2026-12-01 | 88 | Normal | Planned | Compared to previous snapshot
49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 2026-09-23 | 2026-12-15 | 83 | Normal | Planned | Compared to previous snapshot
43 | Strip wall forms | Project5_TAMPERED | 1 | 2026-09-07 | 2026-12-02 | 86 | Normal | Planned | Compared to previous snapshot
45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 2026-09-10 | 2026-12-07 | 88 | Normal | Planned | Compared to previous snapshot
46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 2026-09-11 | 2026-12-08 | 88 | Normal | Planned | Compared to previous snapshot
51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 2026-10-07 | 2026-12-29 | 83 | Normal | Planned | Compared to previous snapshot
56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2026-09-16 | 2026-12-22 | 97 | Normal | Planned | Compared to previous snapshot
52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 2026-10-21 | 2027-01-12 | 83 | Normal | Planned | Compared to previous snapshot
50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 2026-11-04 | 2027-02-18 | 106 | Normal | Planned | Compared to previous snapshot
53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 2026-10-28 | 2027-01-19 | 83 | Normal | Planned | Compared to previous snapshot
55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 2026-11-04 | 2027-02-11 | 99 | Normal | Planned | Compared to previous snapshot
57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 2026-11-10 | 2027-02-17 | 99 | Normal | Planned | Compared to previous snapshot
58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 2026-11-19 | 2027-02-26 | 99 | Normal | Planned | Compared to previous snapshot
81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 2026-12-02 | 2027-03-18 | 106 | Normal | Planned | Compared to previous snapshot
60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 2026-11-26 | 2027-03-05 | 99 | Normal | Planned | Compared to previous snapshot
61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2026-11-26 | 2027-03-05 | 99 | Normal | Planned | Compared to previous snapshot
59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2026-11-30 | 2027-03-09 | 99 | Normal | Planned | Compared to previous snapshot
62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 2026-12-02 | 2027-03-11 | 99 | Normal | Planned | Compared to previous snapshot
70 | Form 1st floor | Project5_TAMPERED | 4 | 2026-12-04 | 2027-03-15 | 101 | Normal | Planned | Compared to previous snapshot
73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 2026-12-04 | 2027-03-15 | 101 | Normal | Planned | Compared to previous snapshot
63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 2026-12-11 | 2027-03-22 | 101 | Normal | Planned | Compared to previous snapshot
71 | Install electrical underground | Project5_TAMPERED | 5 | 2026-12-11 | 2027-03-22 | 101 | Normal | Planned | Compared to previous snapshot
72 | Install plumbing underground | Project5_TAMPERED | 5 | 2026-12-11 | 2027-03-22 | 101 | Normal | Planned | Compared to previous snapshot
111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 2026-12-30 | 2027-04-15 | 106 | Normal | Planned | Compared to previous snapshot
127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 2026-12-16 | 2027-04-01 | 106 | Normal | Planned | Compared to previous snapshot
65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 2026-12-18 | 2027-03-29 | 101 | Normal | Planned | Compared to previous snapshot
66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2026-12-18 | 2027-03-29 | 101 | Normal | Planned | Compared to previous snapshot
74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 2026-12-17 | 2027-03-26 | 99 | Normal | Planned | Compared to previous snapshot
64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2026-12-22 | 2027-03-31 | 99 | Normal | Planned | Compared to previous snapshot
67 | Pour roof slab | Project5_TAMPERED | 4 | 2026-12-24 | 2027-04-02 | 99 | Normal | Planned | Compared to previous snapshot
75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 2026-12-31 | 2027-04-09 | 99 | Normal | Planned | Compared to previous snapshot
68 | Cure roof slab | Project5_TAMPERED | 7 | 2027-01-04 | 2027-04-13 | 99 | Normal | Planned | Compared to previous snapshot
69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2027-01-06 | 2027-04-15 | 99 | Normal | Planned | Compared to previous snapshot
76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2027-01-08 | 2027-04-19 | 101 | Normal | Planned | Compared to previous snapshot
78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 2027-01-27 | 2027-05-06 | 99 | Normal | Planned | Compared to previous snapshot
112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 2027-01-13 | 2027-04-29 | 106 | Normal | Planned | Compared to previous snapshot
80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 2027-02-05 | 2027-05-17 | 101 | Normal | Planned | Compared to previous snapshot
120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 2027-02-05 | 2027-05-17 | 101 | Normal | Planned | Compared to previous snapshot
128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 2027-02-05 | 2027-05-17 | 101 | Normal | Planned | Compared to previous snapshot
113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 2027-01-27 | 2027-05-13 | 106 | Normal | Planned | Compared to previous snapshot
82 | Install exterior masonry work | Project5_TAMPERED | 25 | 2027-03-03 | 2027-06-10 | 99 | Normal | Planned | Compared to previous snapshot
84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 2027-02-19 | 2027-05-31 | 101 | Normal | Planned | Compared to previous snapshot
86 | Clean toilet room tile | Project5_TAMPERED | 5 | 2027-02-26 | 2027-06-07 | 101 | Normal | Planned | Compared to previous snapshot
85 | Clean masonry | Project5_TAMPERED | 5 | 2027-03-10 | 2027-06-17 | 99 | Normal | Planned | Compared to previous snapshot
88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 2027-03-09 | 2027-06-16 | 99 | Normal | Planned | Compared to previous snapshot
94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 2027-04-07 | 2027-07-15 | 99 | Normal | Planned | Compared to previous snapshot
83 | Install roof drains | Project5_TAMPERED | 2 | 2027-03-11 | 2027-06-18 | 99 | Normal | Planned | Compared to previous snapshot
116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 2027-03-24 | 2027-07-01 | 99 | Normal | Planned | Compared to previous snapshot
89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2027-03-15 | 2027-06-22 | 99 | Normal | Planned | Compared to previous snapshot
90 | Install seamless roofing material | Project5_TAMPERED | 5 | 2027-03-29 | 2027-07-06 | 99 | Normal | Planned | Compared to previous snapshot
91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 2027-04-05 | 2027-07-13 | 99 | Normal | Planned | Compared to previous snapshot
92 | Set rooftop equipment | Project5_TAMPERED | 10 | 2027-04-19 | 2027-07-27 | 99 | Normal | Planned | Compared to previous snapshot
95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 2027-05-12 | 2027-08-19 | 99 | Normal | Planned | Compared to previous snapshot
97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 2027-04-28 | 2027-08-05 | 99 | Normal | Planned | Compared to previous snapshot
101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 2027-04-28 | 2027-08-05 | 99 | Normal | Planned | Compared to previous snapshot
115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 2027-05-05 | 2027-08-12 | 99 | Normal | Planned | Compared to previous snapshot
130 | Install duct in building chase | Project5_TAMPERED | 15 | 2027-05-10 | 2027-08-17 | 99 | Normal | Planned | Compared to previous snapshot
121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 2027-05-26 | 2027-09-02 | 99 | Normal | Planned | Compared to previous snapshot
117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 2027-05-26 | 2027-09-02 | 99 | Normal | Planned | Compared to previous snapshot
99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 2027-06-02 | 2027-09-09 | 99 | Normal | Planned | Compared to previous snapshot
102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 2027-06-02 | 2027-09-09 | 99 | Normal | Planned | Compared to previous snapshot
133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 2027-05-19 | 2027-08-26 | 99 | Normal | Planned | Compared to previous snapshot
134 | Clean hard tile floors | Project5_TAMPERED | 4 | 2027-05-25 | 2027-09-01 | 99 | Normal | Planned | Compared to previous snapshot
122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 2027-06-16 | 2027-09-23 | 99 | Normal | Planned | Compared to previous snapshot
96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 2027-06-16 | 2027-09-23 | 99 | Normal | Planned | Compared to previous snapshot
103 | Install ceiling grid | Project5_TAMPERED | 10 | 2027-06-16 | 2027-09-23 | 99 | Normal | Planned | Compared to previous snapshot
129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 2027-06-16 | 2027-09-23 | 99 | Normal | Planned | Compared to previous snapshot
100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 2027-07-14 | 2027-10-21 | 99 | Normal | Planned | Compared to previous snapshot
104 | Install ceiling tile | Project5_TAMPERED | 10 | 2027-06-30 | 2027-10-07 | 99 | Normal | Planned | Compared to previous snapshot
123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 2027-07-07 | 2027-10-14 | 99 | Normal | Planned | Compared to previous snapshot
124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2027-07-23 | 2027-10-18 | 87 | Normal | Planned | Compared to previous snapshot
125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 2027-07-21 | 2027-11-01 | 103 | Normal | Planned | Compared to previous snapshot
105 | Hang wallpaper | Project5_TAMPERED | 10 | 2027-07-28 | 2027-11-04 | 99 | Normal | Planned | Compared to previous snapshot
106 | Install building carpet | Project5_TAMPERED | 41 | 2027-08-11 | 2027-12-17 | 128 | Normal | Planned | Compared to previous snapshot
107 | Install hardware and accessories | Project5_TAMPERED | 26 | 2027-08-04 | 2027-11-26 | 114 | Normal | Planned | Compared to previous snapshot
108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 2027-07-28 | 2027-11-04 | 99 | Normal | Planned | Compared to previous snapshot
118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 2027-07-28 | 2027-11-04 | 99 | Normal | Planned | Compared to previous snapshot
109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 2027-08-11 | 2027-11-18 | 99 | Normal | Planned | Compared to previous snapshot
135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 2027-08-17 | 2027-12-02 | 107 | Normal | Planned | Compared to previous snapshot
136 | Substantial completion date | Project5_TAMPERED | 1 | 2027-08-18 | 2027-12-03 | 107 | Normal | Planned | Compared to previous snapshot
138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 2027-08-20 | 2027-12-07 | 109 | Normal | Planned | Compared to previous snapshot
139 | Perform architect's inspection | Project5_TAMPERED | 1 | 2027-08-23 | 2027-12-08 | 107 | Normal | Planned | Compared to previous snapshot
140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 2027-08-24 | 2027-12-09 | 107 | Normal | Planned | Compared to previous snapshot
131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 2027-08-20 | 2028-01-06 | 139 | Normal | Planned | Compared to previous snapshot
141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 2027-08-25 | 2027-12-10 | 107 | Normal | Planned | Compared to previous snapshot
142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 2027-09-08 | 2028-01-20 | 134 | Normal | Planned | Compared to previous snapshot
143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2027-09-10 | 2028-01-24 | 136 | Normal | Planned | Compared to previous snapshot
144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 2027-09-13 | 2028-01-25 | 134 | Normal | Planned | Compared to previous snapshot
145 | Issue final request for payment | Project5_TAMPERED | 1 | 2027-09-14 | 2028-01-26 | 134 | Normal | Planned | Compared to previous snapshot
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total days ahead in the half step (Days) | Total days ahead in the half step (Days) | N/A |  | N/A
The number of days an activity is ahead due to progress on the half step scenario
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Total days ahead in the full update (Days) | Total days ahead in the full update (Days) | 0 |  | 0
The total number of days activities are ahead due to the updated information on the fully updated schedule.
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Cumulative Finish Impact (Days) | Cumulative Finish Impact (Days) | -9646 |  | 0
Sum of the finish delays - the finish acceleration in days
Excluded | Notes | Id | Description | Project | Remaining Duration | Start | Finish | Type | Status | AccelerationDays | DelayDays
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 0 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 0 | 2026-03-06 | 2026-03-27 | Normal | Complete | 0 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 0 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 0 | 2026-03-12 | 2026-03-25 | Normal | Complete | 0 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 0 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 0 | 2026-03-26 | 2026-03-27 | Normal | Complete | 0 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 0 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 0 | 2026-03-30 | 2026-06-19 | Normal | Complete | 0 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 0 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 0 | 2026-04-02 | 2026-05-04 | Normal | Complete | 0 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 0 | 2026-04-06 | 2026-04-08 | Normal | Complete | 0 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 0 | 2026-04-13 | 2026-04-14 | Normal | Complete | 0 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 0 | 2026-04-15 | 2026-04-21 | Normal | Complete | 0 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 0 | 2026-04-22 | 2026-05-19 | Normal | Complete | 0 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 0 | 2026-04-22 | 2026-06-19 | Normal | Complete | 0 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-29 | Normal | Complete | 0 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-18 | Normal | Complete | 0 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-15 | Normal | Complete | 0 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-18 | Normal | Complete | 0 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 0 | 2026-06-08 | 2026-06-19 | Normal | Complete | 0 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 0 | 2026-06-22 | 2026-07-03 | Normal | Complete | 0 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 0 | 2026-07-06 | 2026-07-31 | Normal | Complete | 0 | 21
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 0 | 2026-08-03 | 2026-08-07 | Normal | Complete | 0 | 14
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 1 | 2026-08-10 | 2026-08-28 | Normal | InProgress | 0 | 31
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 16 | 2026-08-17 | 2026-09-18 | Normal | InProgress | 0 | 50
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 2026-08-31 | 2026-09-03 | Normal | Planned | 0 | 31
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 2026-09-21 | 2026-09-24 | Normal | Planned | 0 | 50
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 50
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 2026-09-25 | 2026-10-23 | Normal | Planned | 0 | 72
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 74
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 2026-10-26 | 2026-11-03 | Normal | Planned | 0 | 74
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 2026-11-04 | 2026-11-06 | Normal | Planned | 0 | 72
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 2026-11-09 | 2026-11-20 | Normal | Planned | 0 | 72
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 2026-11-23 | 2026-12-01 | Normal | Planned | 0 | 88
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 2026-11-23 | 2026-12-15 | Normal | Planned | 0 | 83
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 2026-12-02 | 2026-12-02 | Normal | Planned | 0 | 86
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 2026-12-03 | 2026-12-07 | Normal | Planned | 0 | 88
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 2026-12-08 | 2026-12-08 | Normal | Planned | 0 | 88
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 2026-12-16 | 2026-12-29 | Normal | Planned | 0 | 83
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2026-12-16 | 2026-12-22 | Normal | Planned | 0 | 97
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 2026-12-30 | 2027-01-12 | Normal | Planned | 0 | 83
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 2027-01-13 | 2027-02-18 | Normal | Planned | 0 | 106
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 2027-01-13 | 2027-01-19 | Normal | Planned | 0 | 83
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 2027-01-20 | 2027-02-11 | Normal | Planned | 0 | 99
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 2027-02-12 | 2027-02-17 | Normal | Planned | 0 | 99
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 2027-02-18 | 2027-02-26 | Normal | Planned | 0 | 99
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 2027-02-19 | 2027-03-18 | Normal | Planned | 0 | 106
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 2027-03-01 | 2027-03-05 | Normal | Planned | 0 | 99
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2027-03-01 | 2027-03-05 | Normal | Planned | 0 | 99
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2027-03-08 | 2027-03-09 | Normal | Planned | 0 | 99
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 2027-03-08 | 2027-03-11 | Normal | Planned | 0 | 99
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 2027-03-10 | 2027-03-15 | Normal | Planned | 0 | 101
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 2027-03-10 | 2027-03-15 | Normal | Planned | 0 | 101
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 2027-03-12 | 2027-03-22 | Normal | Planned | 0 | 101
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 2027-03-16 | 2027-03-22 | Normal | Planned | 0 | 101
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 2027-03-16 | 2027-03-22 | Normal | Planned | 0 | 101
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 2027-03-19 | 2027-04-15 | Normal | Planned | 0 | 106
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 2027-03-19 | 2027-04-01 | Normal | Planned | 0 | 106
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 2027-03-23 | 2027-03-29 | Normal | Planned | 0 | 101
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2027-03-23 | 2027-03-29 | Normal | Planned | 0 | 101
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 2027-03-23 | 2027-03-26 | Normal | Planned | 0 | 99
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2027-03-30 | 2027-03-31 | Normal | Planned | 0 | 99
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 2027-03-30 | 2027-04-02 | Normal | Planned | 0 | 99
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 2027-04-01 | 2027-04-09 | Normal | Planned | 0 | 99
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 2027-04-05 | 2027-04-13 | Normal | Planned | 0 | 99
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2027-04-14 | 2027-04-15 | Normal | Planned | 0 | 99
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2027-04-16 | 2027-04-19 | Normal | Planned | 0 | 101
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 2027-04-16 | 2027-05-06 | Normal | Planned | 0 | 99
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 2027-04-16 | 2027-04-29 | Normal | Planned | 0 | 106
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 2027-04-20 | 2027-05-17 | Normal | Planned | 0 | 101
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 2027-04-20 | 2027-05-17 | Normal | Planned | 0 | 101
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 2027-04-20 | 2027-05-17 | Normal | Planned | 0 | 101
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 2027-04-30 | 2027-05-13 | Normal | Planned | 0 | 106
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 2027-05-07 | 2027-06-10 | Normal | Planned | 0 | 99
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 2027-05-18 | 2027-05-31 | Normal | Planned | 0 | 101
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 2027-06-01 | 2027-06-07 | Normal | Planned | 0 | 101
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 2027-06-11 | 2027-06-17 | Normal | Planned | 0 | 99
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 2027-06-11 | 2027-06-16 | Normal | Planned | 0 | 99
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 2027-06-11 | 2027-07-15 | Normal | Planned | 0 | 99
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2027-06-17 | 2027-06-18 | Normal | Planned | 0 | 99
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 2027-06-18 | 2027-07-01 | Normal | Planned | 0 | 99
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2027-06-21 | 2027-06-22 | Normal | Planned | 0 | 99
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 2027-06-30 | 2027-07-06 | Normal | Planned | 0 | 99
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 2027-07-07 | 2027-07-13 | Normal | Planned | 0 | 99
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 2027-07-14 | 2027-07-27 | Normal | Planned | 0 | 99
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 2027-07-16 | 2027-08-19 | Normal | Planned | 0 | 99
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 2027-07-16 | 2027-08-05 | Normal | Planned | 0 | 99
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 2027-07-16 | 2027-08-05 | Normal | Planned | 0 | 99
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 2027-07-16 | 2027-08-12 | Normal | Planned | 0 | 99
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 2027-07-28 | 2027-08-17 | Normal | Planned | 0 | 99
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 2027-08-06 | 2027-09-02 | Normal | Planned | 0 | 99
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 2027-08-13 | 2027-09-02 | Normal | Planned | 0 | 99
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 2027-08-20 | 2027-09-09 | Normal | Planned | 0 | 99
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 2027-08-20 | 2027-09-09 | Normal | Planned | 0 | 99
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 2027-08-20 | 2027-08-26 | Normal | Planned | 0 | 99
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 2027-08-27 | 2027-09-01 | Normal | Planned | 0 | 99
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 2027-09-03 | 2027-09-23 | Normal | Planned | 0 | 99
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 2027-09-10 | 2027-09-23 | Normal | Planned | 0 | 99
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 2027-09-10 | 2027-09-23 | Normal | Planned | 0 | 99
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 2027-09-10 | 2027-09-23 | Normal | Planned | 0 | 99
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 2027-09-24 | 2027-10-21 | Normal | Planned | 0 | 99
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 2027-09-24 | 2027-10-07 | Normal | Planned | 0 | 99
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 2027-09-24 | 2027-10-14 | Normal | Planned | 0 | 99
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2027-10-15 | 2027-10-18 | Normal | Planned | 0 | 87
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 2027-10-19 | 2027-11-01 | Normal | Planned | 0 | 103
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 2027-10-22 | 2027-11-04 | Normal | Planned | 0 | 99
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 2027-10-22 | 2027-12-17 | Normal | Planned | 0 | 128
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 2027-10-22 | 2027-11-26 | Normal | Planned | 0 | 114
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 2027-10-22 | 2027-11-04 | Normal | Planned | 0 | 99
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 2027-10-22 | 2027-11-04 | Normal | Planned | 0 | 99
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 2027-11-05 | 2027-11-18 | Normal | Planned | 0 | 99
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 2027-11-29 | 2027-12-02 | Normal | Planned | 0 | 107
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 2027-12-03 | 2027-12-03 | Normal | Planned | 0 | 107
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 2027-12-03 | 2027-12-07 | Normal | Planned | 0 | 109
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 2027-12-08 | 2027-12-08 | Normal | Planned | 0 | 107
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 2027-12-09 | 2027-12-09 | Normal | Planned | 0 | 107
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 2027-12-10 | 2028-01-06 | Normal | Planned | 0 | 139
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 2027-12-10 | 2027-12-10 | Normal | Planned | 0 | 107
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 2028-01-07 | 2028-01-20 | Normal | Planned | 0 | 134
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2028-01-21 | 2028-01-24 | Normal | Planned | 0 | 136
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 2028-01-25 | 2028-01-25 | Normal | Planned | 0 | 134
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 2028-01-26 | 2028-01-26 | Normal | Planned | 0 | 134
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Net Finish Impact (Days) | Net Finish Impact (Days) | -134 |  | 0
Finish delay to the project
Excluded | Notes | Id | Description | Project | Remaining Duration | Start | Finish | Type | Status | AccelerationDays | DelayDays
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 0 | 2026-03-02 | 2026-03-04 | Normal | Complete | 0 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-10 | Normal | Complete | 0 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-05 | Normal | Complete | 0 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 0 | 2026-03-05 | 2026-03-06 | Normal | Complete | 0 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 0 | 2026-03-06 | 2026-03-27 | Normal | Complete | 0 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 0 | 2026-03-09 | 2026-03-11 | Normal | Complete | 0 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 0 | 2026-03-12 | 2026-03-25 | Normal | Complete | 0 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 0 | 2026-03-25 | 2026-03-26 | Normal | Complete | 0 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 0 | 2026-03-26 | 2026-03-27 | Normal | Complete | 0 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 0 | 2026-03-27 | 2026-03-30 | Normal | Complete | 0 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 0 | 2026-03-30 | 2026-06-19 | Normal | Complete | 0 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 0 | 2026-03-31 | 2026-04-01 | Normal | Complete | 0 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 0 | 2026-04-02 | 2026-05-04 | Normal | Complete | 0 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 0 | 2026-04-06 | 2026-04-08 | Normal | Complete | 0 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 0 | 2026-04-13 | 2026-04-14 | Normal | Complete | 0 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 0 | 2026-04-15 | 2026-04-21 | Normal | Complete | 0 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 0 | 2026-04-22 | 2026-05-19 | Normal | Complete | 0 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 0 | 2026-04-22 | 2026-06-19 | Normal | Complete | 0 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-29 | Normal | Complete | 0 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-18 | Normal | Complete | 0 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-15 | Normal | Complete | 0 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 0 | 2026-05-05 | 2026-05-18 | Normal | Complete | 0 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 0 | 2026-06-08 | 2026-06-19 | Normal | Complete | 0 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 0 | 2026-06-22 | 2026-07-03 | Normal | Complete | 0 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 0 | 2026-07-06 | 2026-07-31 | Normal | Complete | 0 | 21
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 0 | 2026-08-03 | 2026-08-07 | Normal | Complete | 0 | 14
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 1 | 2026-08-10 | 2026-08-28 | Normal | InProgress | 0 | 31
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 16 | 2026-08-17 | 2026-09-18 | Normal | InProgress | 0 | 50
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 2026-08-31 | 2026-09-03 | Normal | Planned | 0 | 31
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 2026-09-21 | 2026-09-24 | Normal | Planned | 0 | 50
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 50
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 2026-09-25 | 2026-10-23 | Normal | Planned | 0 | 72
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 74
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 2026-10-26 | 2026-11-03 | Normal | Planned | 0 | 74
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 2026-11-04 | 2026-11-06 | Normal | Planned | 0 | 72
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 2026-11-09 | 2026-11-20 | Normal | Planned | 0 | 72
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 2026-11-23 | 2026-12-01 | Normal | Planned | 0 | 88
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 2026-11-23 | 2026-12-15 | Normal | Planned | 0 | 83
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 2026-12-02 | 2026-12-02 | Normal | Planned | 0 | 86
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 2026-12-03 | 2026-12-07 | Normal | Planned | 0 | 88
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 2026-12-08 | 2026-12-08 | Normal | Planned | 0 | 88
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 2026-12-16 | 2026-12-29 | Normal | Planned | 0 | 83
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2026-12-16 | 2026-12-22 | Normal | Planned | 0 | 97
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 2026-12-30 | 2027-01-12 | Normal | Planned | 0 | 83
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 2027-01-13 | 2027-02-18 | Normal | Planned | 0 | 106
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 2027-01-13 | 2027-01-19 | Normal | Planned | 0 | 83
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 2027-01-20 | 2027-02-11 | Normal | Planned | 0 | 99
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 2027-02-12 | 2027-02-17 | Normal | Planned | 0 | 99
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 2027-02-18 | 2027-02-26 | Normal | Planned | 0 | 99
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 2027-02-19 | 2027-03-18 | Normal | Planned | 0 | 106
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 2027-03-01 | 2027-03-05 | Normal | Planned | 0 | 99
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2027-03-01 | 2027-03-05 | Normal | Planned | 0 | 99
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2027-03-08 | 2027-03-09 | Normal | Planned | 0 | 99
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 2027-03-08 | 2027-03-11 | Normal | Planned | 0 | 99
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 2027-03-10 | 2027-03-15 | Normal | Planned | 0 | 101
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 2027-03-10 | 2027-03-15 | Normal | Planned | 0 | 101
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 2027-03-12 | 2027-03-22 | Normal | Planned | 0 | 101
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 2027-03-16 | 2027-03-22 | Normal | Planned | 0 | 101
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 2027-03-16 | 2027-03-22 | Normal | Planned | 0 | 101
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 2027-03-19 | 2027-04-15 | Normal | Planned | 0 | 106
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 2027-03-19 | 2027-04-01 | Normal | Planned | 0 | 106
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 2027-03-23 | 2027-03-29 | Normal | Planned | 0 | 101
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 2027-03-23 | 2027-03-29 | Normal | Planned | 0 | 101
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 2027-03-23 | 2027-03-26 | Normal | Planned | 0 | 99
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2027-03-30 | 2027-03-31 | Normal | Planned | 0 | 99
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 2027-03-30 | 2027-04-02 | Normal | Planned | 0 | 99
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 2027-04-01 | 2027-04-09 | Normal | Planned | 0 | 99
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 2027-04-05 | 2027-04-13 | Normal | Planned | 0 | 99
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2027-04-14 | 2027-04-15 | Normal | Planned | 0 | 99
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2027-04-16 | 2027-04-19 | Normal | Planned | 0 | 101
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 2027-04-16 | 2027-05-06 | Normal | Planned | 0 | 99
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 2027-04-16 | 2027-04-29 | Normal | Planned | 0 | 106
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 2027-04-20 | 2027-05-17 | Normal | Planned | 0 | 101
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 2027-04-20 | 2027-05-17 | Normal | Planned | 0 | 101
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 2027-04-20 | 2027-05-17 | Normal | Planned | 0 | 101
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 2027-04-30 | 2027-05-13 | Normal | Planned | 0 | 106
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 2027-05-07 | 2027-06-10 | Normal | Planned | 0 | 99
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 2027-05-18 | 2027-05-31 | Normal | Planned | 0 | 101
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 2027-06-01 | 2027-06-07 | Normal | Planned | 0 | 101
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 2027-06-11 | 2027-06-17 | Normal | Planned | 0 | 99
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 2027-06-11 | 2027-06-16 | Normal | Planned | 0 | 99
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 2027-06-11 | 2027-07-15 | Normal | Planned | 0 | 99
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2027-06-17 | 2027-06-18 | Normal | Planned | 0 | 99
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 2027-06-18 | 2027-07-01 | Normal | Planned | 0 | 99
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2027-06-21 | 2027-06-22 | Normal | Planned | 0 | 99
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 2027-06-30 | 2027-07-06 | Normal | Planned | 0 | 99
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 2027-07-07 | 2027-07-13 | Normal | Planned | 0 | 99
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 2027-07-14 | 2027-07-27 | Normal | Planned | 0 | 99
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 2027-07-16 | 2027-08-19 | Normal | Planned | 0 | 99
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 2027-07-16 | 2027-08-05 | Normal | Planned | 0 | 99
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 2027-07-16 | 2027-08-05 | Normal | Planned | 0 | 99
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 2027-07-16 | 2027-08-12 | Normal | Planned | 0 | 99
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 2027-07-28 | 2027-08-17 | Normal | Planned | 0 | 99
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 2027-08-06 | 2027-09-02 | Normal | Planned | 0 | 99
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 2027-08-13 | 2027-09-02 | Normal | Planned | 0 | 99
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 2027-08-20 | 2027-09-09 | Normal | Planned | 0 | 99
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 2027-08-20 | 2027-09-09 | Normal | Planned | 0 | 99
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 2027-08-20 | 2027-08-26 | Normal | Planned | 0 | 99
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 2027-08-27 | 2027-09-01 | Normal | Planned | 0 | 99
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 2027-09-03 | 2027-09-23 | Normal | Planned | 0 | 99
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 2027-09-10 | 2027-09-23 | Normal | Planned | 0 | 99
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 2027-09-10 | 2027-09-23 | Normal | Planned | 0 | 99
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 2027-09-10 | 2027-09-23 | Normal | Planned | 0 | 99
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 2027-09-24 | 2027-10-21 | Normal | Planned | 0 | 99
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 2027-09-24 | 2027-10-07 | Normal | Planned | 0 | 99
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 2027-09-24 | 2027-10-14 | Normal | Planned | 0 | 99
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2027-10-15 | 2027-10-18 | Normal | Planned | 0 | 87
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 2027-10-19 | 2027-11-01 | Normal | Planned | 0 | 103
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 2027-10-22 | 2027-11-04 | Normal | Planned | 0 | 99
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 2027-10-22 | 2027-12-17 | Normal | Planned | 0 | 128
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 2027-10-22 | 2027-11-26 | Normal | Planned | 0 | 114
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 2027-10-22 | 2027-11-04 | Normal | Planned | 0 | 99
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 2027-10-22 | 2027-11-04 | Normal | Planned | 0 | 99
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 2027-11-05 | 2027-11-18 | Normal | Planned | 0 | 99
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 2027-11-29 | 2027-12-02 | Normal | Planned | 0 | 107
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 2027-12-03 | 2027-12-03 | Normal | Planned | 0 | 107
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 2027-12-03 | 2027-12-07 | Normal | Planned | 0 | 109
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 2027-12-08 | 2027-12-08 | Normal | Planned | 0 | 107
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 2027-12-09 | 2027-12-09 | Normal | Planned | 0 | 107
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 2027-12-10 | 2028-01-06 | Normal | Planned | 0 | 139
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 2027-12-10 | 2027-12-10 | Normal | Planned | 0 | 107
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 2028-01-07 | 2028-01-20 | Normal | Planned | 0 | 134
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2028-01-21 | 2028-01-24 | Normal | Planned | 0 | 136
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 2028-01-25 | 2028-01-25 | Normal | Planned | 0 | 134
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 2028-01-26 | 2028-01-26 | Normal | Planned | 0 | 134
Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Current Period (Time Now: 8/27/2026) | Project2 (Time Now: 5/24/2026) | Project2 (Time Now: 5/24/2026)
Project Finish | Project Finish | 2028-01-26 |  | 2027-09-14