## Ribbon View
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
|  | 2025-12-28 | 2025-12-28 | 2026-01-04 | 2026-01-04 | 2026-01-11 | 2026-01-11 | 2026-01-18 | 2026-01-18 | 2026-01-25 | 2026-01-25 | 2026-02-01 | 2026-02-01 | 2026-02-08 | 2026-02-08 | 2026-02-15 | 2026-02-15 | 2026-02-22 | 2026-02-22 | 2026-03-01 | 2026-03-01 | 2026-03-08 | 2026-03-08 | 2026-03-15 | 2026-03-15 | 2026-03-22 | 2026-03-22 | 2026-03-29 | 2026-03-29 | 2026-04-05 | 2026-04-05 | 2026-04-12 | 2026-04-12 | 2026-04-19 | 2026-04-19 | 2026-04-26 | 2026-04-26 | 2026-05-03 | 2026-05-03 | 2026-05-10 | 2026-05-10 | 2026-05-17 | 2026-05-17 | 2026-05-24 | 2026-05-24 | 2026-05-31 | 2026-05-31 | 2026-06-07 | 2026-06-07 | 2026-06-14 | 2026-06-14 | 2026-06-21 | 2026-06-21 | 2026-06-28 | 2026-06-28 | 2026-07-05 | 2026-07-05 | 2026-07-12 | 2026-07-12 | 2026-07-19 | 2026-07-19 | 2026-07-26 | 2026-07-26 | 2026-08-02 | 2026-08-02 | 2026-08-09 | 2026-08-09 | 2026-08-16 | 2026-08-16 | 2026-08-23 | 2026-08-23 | 2026-08-30 | 2026-08-30 | 2026-09-06 | 2026-09-06 | 2026-09-13 | 2026-09-13 | 2026-09-20 | 2026-09-20 | 2026-09-27 | 2026-09-27 | 2026-10-04 | 2026-10-04 | 2026-10-11 | 2026-10-11 | 2026-10-18 | 2026-10-18 | 2026-10-25 | 2026-10-25 | 2026-11-01 | 2026-11-01 | 2026-11-08 | 2026-11-08 | 2026-11-15 | 2026-11-15 | 2026-11-22 | 2026-11-22 | 2026-11-29 | 2026-11-29 | 2026-12-06 | 2026-12-06 | 2026-12-13 | 2026-12-13 | 2026-12-20 | 2026-12-20 | 2026-12-27 | 2026-12-27 | 2027-01-03 | 2027-01-03 | 2027-01-10 | 2027-01-10 | 2027-01-17 | 2027-01-17 | 2027-01-24 | 2027-01-24 | 2027-01-31 | 2027-01-31 | 2027-02-07 | 2027-02-07 | 2027-02-14 | 2027-02-14 | 2027-02-21 | 2027-02-21 | 2027-02-28 | 2027-02-28 | 2027-03-07 | 2027-03-07 | 2027-03-14 | 2027-03-14 | 2027-03-21 | 2027-03-21 | 2027-03-28 | 2027-03-28 | 2027-04-04 | 2027-04-04 | 2027-04-11 | 2027-04-11 | 2027-04-18 | 2027-04-18 | 2027-04-25 | 2027-04-25 | 2027-05-02 | 2027-05-02 | 2027-05-09 | 2027-05-09 | 2027-05-16 | 2027-05-16 | 2027-05-23 | 2027-05-23 | 2027-05-30 | 2027-05-30 | 2027-06-06 | 2027-06-06 | 2027-06-13 | 2027-06-13 | 2027-06-20 | 2027-06-20 | 2027-06-27 | 2027-06-27 | 2027-07-04 | 2027-07-04 | 2027-07-11 | 2027-07-11 | 2027-07-18 | 2027-07-18 | 2027-07-25 | 2027-07-25 | 2027-08-01 | 2027-08-01 | 2027-08-08 | 2027-08-08 | 2027-08-15 | 2027-08-15 | 2027-08-22 | 2027-08-22 | 2027-08-29 | 2027-08-29 | 2027-09-05 | 2027-09-05 | 2027-09-12 | 2027-09-12 | 2027-09-19 | 2027-09-19 | 2027-09-26 | 2027-09-26 | 2027-10-03 | 2027-10-03 | 2027-10-10 | 2027-10-10 | 2027-10-17 | 2027-10-17 | 2027-10-24 | 2027-10-24 | 2027-10-31 | 2027-10-31 | 2027-11-07 | 2027-11-07 | 2027-11-14 | 2027-11-14 | 2027-11-21 | 2027-11-21 | 2027-11-28 | 2027-11-28 | 2027-12-05 | 2027-12-05 | 2027-12-12 | 2027-12-12 | 2027-12-19 | 2027-12-19 | 2027-12-26 | 2027-12-26 | 2028-01-02 | 2028-01-02 | 2028-01-09 | 2028-01-09 | 2028-01-16 | 2028-01-16 | 2028-01-23 | 2028-01-23 | 2028-01-30 | 2028-01-30 | 2028-02-06 | 2028-02-06 | 2028-02-13 | 2028-02-13 | 2028-02-20 | 2028-02-20 | 2028-02-27 | 2028-02-27 | 2028-03-05 | 2028-03-05 | 2028-03-12 | 2028-03-12 | 2028-03-19 | 2028-03-19 | 2028-03-26 | 2028-03-26 | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Early Finishes | Late Finishes | Total Activities | Milestones | Normal | Summaries | Hammocks | Milestone Ratio | Detail Level | Missing WBS | Longest Path | Riding Data Date | Activities per million | Original Duration | Remaining Duration | Rem. Critical Duration | Rem. Non-Critical Duration | Avg. Original Duration | Avg. Remaining Duration | Ribbon Length | Schedule Overrun | Lags | Leads | Minimum Lag | Maximum Lag | Hidden Duration | Constraint | As Late As Possible | Finish On Or After | Finish On Or Before | Must Finish On | Mandatory Finish | Must Start On | Mandatory Start | Start And Finish | Start On Or After | Start On Or Before | Late Constraints | Early Constraints | Free Float Constraints | Total Float Constraints | Soft Constraints | Hard Constraints | Unsatisfied Constraints | Critical | Non-Critical | Negative Float | Zero Days Float | 0 to 20 Days Float | 20 to 30 days float | More than 30 days float | High Float | Avg Float | Max Float | Float Ratio™ | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Status Date | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Status Date | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | New Activity - Created | New Activity - Already Finished | New Activity - Finished in Status Period | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | Score
Ribbons | Project2 | [236 empty] | 4 | 0 | 2 | 1 | 0 | 0 | 44 | 0 | 1 | 0 | 0 | 0 | 18 | ✓ | 1 | 0.74 | 126 | 126 | 144 | 0 | 126 | 18 | 0 | N/A | 1:07 | 0 | 41 | 0 | N/A | 1128 | 920 | 335 | 585 | 9 | 9 | 561 | 0 | 2 | 0 | 0 | 5 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 41 | 65 | 0 | 41 | 18 | 2 | 45 | 44 | 48 | 263 | 5.58 | 0.74 | 27 | 20 | 7 | 0.74 | 20 | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 12
Ribbons | Project2 | [236 empty] | 4% | 0% | 1% | 1% | 0% | 0% | 42% | 0% | 1% | 0% | 0% | 0% | 67% | [5 empty] | 100% | 0% | 88% | 13% | 0% | 0 | 0.14 | 0% | 39% | 0% |  | 281% | 269% | 98% | 171% |  |  |  | 0% | 2% | 0% |  |  | 1% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2% | 0% | 0% | 2% | 0% | 0% | 2% | 0% | 0% | 39% | 61% | 0% | 39% | 17% | 2% | 42% | 42% | [5 empty] | 74% | 26% |  | 74% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A
Ribbons | Project5_TAMPERED | [236 empty] | 5 | 0 | 1 | 0 | 0 | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 37 | ✓ | 1 | 0.59 | 126 | 126 | 144 | 0 | 126 | 18 | 0 | N/A | 1:07 | 0 | 4 | 0 | N/A | 1256 | 935 | 32 | 903 | 10 | 9 | 695 | 0 | 2 | 0 | 0 | 5 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 5 | 0 | 0 | 5 | 0 | 1 | 5 | 1 | 0 | 4 | 95 | 0 | 4 | 35 | 3 | 57 | 44 | 71 | 275 | 7.52 | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0.05 | 19 | 1 | N/A | 18 | 0.05 | 1 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0.44 | 16 | 7 | 9 | 0.44 | 7 | 0 | 2026-08-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 12
Ribbons | Project5_TAMPERED | [236 empty] | 5% | 0% | 1% | 0% | 0% | 1% | 44% | 0% | 0% | 0% | 0% | 0% | 80% | [5 empty] | 100% | 0% | 88% | 13% | 0% | 0 | 0.14 | 0% | 4% | 0% |  | 312% | 273% | 9% | 264% |  |  |  | 0% | 2% | 0% |  |  | 1% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 4% | 0% | 0% | 4% | 0% | 1% | 4% | 1% | 0% | 4% | 96% | 0% | 4% | 35% | 3% | 58% | 44% | [5 empty] | 59% | 41% |  | 59% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | 5% | 0% | 95% |  | 5% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | 44% | 56% |  | 44% | [7 empty] | N/A | N/A |  | N/A
Phase Analyzer | Critical | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 1 | 50% | 1 | 50% | 1 | 33% | 1 | 33% | 1 | 33% | 1 | 33% | 1 | 50% | 1 | 33% | 1 | 33% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 2 | 50% | 2 | 50% | 2 | 50% | 1 | 100% | 2 | 67% | 1 | 50% | 2 | 33% | 1 | 50% | 2 | 100% | 1 | 100% | 2 | 100% | 1 | 100% | 2 | 67% | 2 | 67% | 2 | 50% | 2 | 67% | 3 | 75% | 3 | 60% | 2 | 25% | 1 | 20% | 2 | 40% | 2 | 40% | 1 | 25% | 3 | 60% | 1 | 17% | 1 | 20% | 2 | 33% | 1 | 25% | 1 | 50% | 1 | 50% | 1 | 50% | 2 | 50% | 1 | 17% | 1 | 33% | 1 | 33% | 1 | 33% | 2 | 29% | 1 | 20% | 1 | 17% | 1 | 17% | 1 | 20% | 1 | 14% | 0 | 0% | 0 | 0% | 1 | 17% | 1 | 25% | 2 | 29% | 1 | 33% | 1 | 33% | 1 | 33% | 2 | 29% | 1 | 14% | 1 | 14% | 1 | 25% | 2 | 50% | 2 | 50% | 4 | 100% | 1 | 100% | 1 | 50% | 2 | 100% | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A )
Phase Analyzer | Non-Critical | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 50% | 1 | 50% | 2 | 67% | 2 | 67% | 2 | 67% | 2 | 67% | 1 | 50% | 2 | 67% | 2 | 67% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2 | 50% | 2 | 50% | 2 | 50% | 0 | 0% | 1 | 33% | 1 | 50% | 4 | 67% | 1 | 50% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 1 | 33% | 1 | 33% | 2 | 50% | 1 | 33% | 1 | 25% | 2 | 40% | 6 | 75% | 4 | 80% | 3 | 60% | 3 | 60% | 3 | 75% | 2 | 40% | 5 | 83% | 4 | 80% | 4 | 67% | 3 | 75% | 1 | 50% | 1 | 50% | 1 | 50% | 2 | 50% | 5 | 83% | 2 | 67% | 2 | 67% | 2 | 67% | 5 | 71% | 4 | 80% | 5 | 83% | 5 | 83% | 4 | 80% | 6 | 86% | 6 | 100% | 6 | 100% | 5 | 83% | 3 | 75% | 5 | 71% | 2 | 67% | 2 | 67% | 2 | 67% | 5 | 71% | 6 | 86% | 6 | 86% | 3 | 75% | 2 | 50% | 2 | 50% | 0 | 0% | 0 | 0% | 1 | 50% | 0 | 0% | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A )
Phase Analyzer | Negative Float | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | 0% | 0 | ( N/A ) | 0 | ( N/A ) | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A )
Phase Analyzer | Zero Days Float | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | 0% | 0 | ( N/A ) | 0 | ( N/A ) | 1 | 33% | 0 | ( N/A ) | 1 | 100% | 1 | 100% | 0 | ( N/A ) | 1 | 100% | 1 | 50% | 1 | 50% | 1 | 33% | 1 | 100% | 1 | 100% | 0 | 0% | 1 | 25% | 0 | 0% | 1 | 100% | 0 | ( N/A ) | 1 | 100% | 0 | ( N/A ) | 1 | 100% | 1 | 100% | 1 | 50% | 1 | 100% | 1 | 100% | 2 | 100% | 1 | 20% | 1 | 33% | 2 | 50% | 1 | 50% | 0 | 0% | 2 | 67% | 0 | 0% | 0 | ( N/A ) | 1 | 50% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 1 | 50% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 1 | 50% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 1 | 25% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 1 | 50% | 2 | 50% | 3 | 100% | 0 | ( N/A ) | 1 | 50% | 2 | 100% | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A )
Phase Analyzer | 0 to 20 Days Float | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | 0% | 0 | ( N/A ) | 0 | ( N/A ) | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 1 | 50% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 2 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2 | 100% | 0 | ( N/A ) | 2 | 50% | 0 | ( N/A ) | 0 | 0% | 1 | 100% | 0 | 0% | 2 | 100% | 3 | 100% | 1 | 100% | 1 | 50% | 2 | 50% | 0 | 0% | 0 | ( N/A ) | 1 | 50% | 0 | 0% | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A )
Phase Analyzer | 20 to 30 days float | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | 0% | 0 | ( N/A ) | 0 | ( N/A ) | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 1 | 33% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | ( N/A ) | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A )
Phase Analyzer | More than 30 days float | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 1 | 100% | 0 | ( N/A ) | 0 | ( N/A ) | 2 | 67% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 1 | 50% | 1 | 50% | 2 | 67% | 0 | 0% | 0 | 0% | 1 | 100% | 3 | 75% | 1 | 100% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 1 | 50% | 0 | 0% | 0 | 0% | 0 | 0% | 4 | 80% | 2 | 67% | 2 | 50% | 0 | 0% | 2 | 100% | 1 | 33% | 1 | 100% | 0 | ( N/A ) | 1 | 50% | 3 | 100% | 0 | ( N/A ) | 1 | 100% | 1 | 100% | 0 | 0% | 3 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 50% | 0 | ( N/A ) | 1 | 100% | 0 | 0% | 1 | 100% | 1 | 50% | 1 | 100% | 2 | 67% | 0 | 0% | 0 | ( N/A ) | 1 | 25% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A )
Phase Analyzer | High Float | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 1 | 100% | 0 | ( N/A ) | 0 | ( N/A ) | 2 | 67% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 1 | 50% | 1 | 50% | 2 | 67% | 0 | 0% | 0 | 0% | 1 | 100% | 3 | 75% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 1 | 50% | 0 | 0% | 0 | 0% | 0 | 0% | 4 | 80% | 2 | 67% | 2 | 50% | 0 | 0% | 2 | 100% | 1 | 33% | 1 | 100% | 0 | ( N/A ) | 1 | 50% | 3 | 100% | 0 | ( N/A ) | 1 | 100% | 1 | 100% | 0 | 0% | 3 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 50% | 0 | ( N/A ) | 1 | 100% | 0 | 0% | 1 | 100% | 1 | 50% | 1 | 100% | 2 | 67% | 0 | 0% | 0 | ( N/A ) | 1 | 25% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | ( N/A )
Phase Analyzer | Avg Float | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 263 |  | N/A |  | N/A |  | 47 |  | N/A |  | 0 |  | 0 |  | N/A |  | 0 |  | 102 |  | 102 |  | 135 |  | 0 |  | 0 |  | 202 |  | 152 |  | 35 |  | 0 |  | N/A |  | 0 |  | N/A |  | 0 |  | 0 |  | 72 |  | 0 |  | 0 |  | 0 |  | 75 |  | 49 |  | 56 |  | 6 |  | 109 |  | 24 |  | 144 |  | N/A |  | 72 |  | 93 |  | N/A |  | 93 |  | 93 |  | 0 |  | 70 |  | 59 |  | 90 |  | 59 |  | 30 |  | N/A |  | 59 |  | 18 |  | 45 |  | 36 |  | 56 |  | 44 |  | 10 |  | N/A |  | 22 |  | N/A |  | 30 |  | 15 |  | 0 |  | 16 |  | 9 |  | 5 |  | 4 |  | 9 |  | 0 |  | N/A |  | 1 |  | 0 |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | Max Float | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 263 |  | N/A |  | N/A |  | 93 |  | N/A |  | 0 |  | 0 |  | N/A |  | 0 |  | 204 |  | 204 |  | 203 |  | 0 |  | 0 |  | 202 |  | 202 |  | 35 |  | 0 |  | N/A |  | 0 |  | N/A |  | 0 |  | 0 |  | 144 |  | 0 |  | 0 |  | 0 |  | 144 |  | 73 |  | 151 |  | 11 |  | 144 |  | 73 |  | 144 |  | N/A |  | 144 |  | 114 |  | N/A |  | 93 |  | 93 |  | 0 |  | 90 |  | 59 |  | 90 |  | 59 |  | 59 |  | N/A |  | 59 |  | 20 |  | 45 |  | 71 |  | 56 |  | 56 |  | 10 |  | N/A |  | 64 |  | N/A |  | 30 |  | 15 |  | 0 |  | 17 |  | 10 |  | 5 |  | 7 |  | 19 |  | 0 |  | N/A |  | 1 |  | 0 |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | Float Ratio™ | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 17.53 |  | 0 |  | 0 |  | 9.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 20.4 |  | 25.5 |  | 50.63 |  | 0 |  | 0 |  | 20.2 |  | 50.5 |  | 4.38 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 14.4 |  | 0 |  | 0 |  | 0 |  | 17.76 |  | 5.84 |  | 10.18 |  | 0.73 |  | 15.5 |  | 6.08 |  | 5.76 |  | 0 |  | 6.26 |  | 14 |  | 0 |  | 9.3 |  | 9.3 |  | 0 |  | 14 |  | 5.36 |  | 7.5 |  | 5.9 |  | 3.69 |  | 0 |  | 2.36 |  | 1.52 |  | 2.25 |  | 3.55 |  | 2.24 |  | 6.55 |  | 1.18 |  | 0 |  | 4.94 |  | 0 |  | 2.31 |  | 1.5 |  | 0 |  | 1.07 |  | 1.04 |  | 0.28 |  | 0.54 |  | 3.27 |  | 0 |  | 0 |  | 0.2 |  | 0 |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | BEI - Value Tasks | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0.8 |  | 0.75 |  | N/A |  | 0.5 |  | 0.5 |  | N/A |  | 0.25 |  | 0 |  | 0 |  | 0.33 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | N/A |  | 0 |  | N/A |  | 0 |  | 0 |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | BEI - Total Tasks | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 8 |  | 4 |  | 6 |  | 8 |  | 6 |  | 10 |  | 4 |  | 0 |  | 2 |  | 2 |  | 0 |  | 4 |  | 2 |  | 2 |  | 3 |  | 1 |  | 1 |  | 2 |  | 3 |  | 1 |  | 1 |  | 0 |  | 1 |  | 0 |  | 1 |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Phase Analyzer | BEI - Complete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 8 | 100% | 4 | 100% | 6 | 100% | 8 | 100% | 6 | 100% | 8 | 80% | 3 | 75% | N/A | N/A | 1 | 50% | 1 | 50% | N/A | N/A | 1 | 25% | 0 | 0% | 0 | 0% | 1 | 33% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | N/A | N/A | 0 | 0% | N/A | N/A | 0 | 0% | 0 | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Incomplete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2 | 20% | 1 | 25% | N/A | N/A | 1 | 50% | 1 | 50% | N/A | N/A | 3 | 75% | 2 | 100% | 2 | 100% | 2 | 67% | 1 | 100% | 1 | 100% | 2 | 100% | 3 | 100% | 1 | 100% | 1 | 100% | N/A | N/A | 1 | 100% | N/A | N/A | 1 | 100% | 1 | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Value Tasks (adjusted) | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0.8 |  | 0.75 |  | N/A |  | 0.5 |  | 0.5 |  | N/A |  | 0.25 |  | 0 |  | 0 |  | 0.33 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | N/A |  | 0 |  | N/A |  | 0 |  | 0 |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | BEI - Complete Tasks (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 8 | 100% | 4 | 100% | 6 | 100% | 8 | 100% | 6 | 100% | 8 | 80% | 3 | 75% | N/A | N/A | 1 | 50% | 1 | 50% | N/A | N/A | 1 | 25% | 0 | 0% | 0 | 0% | 1 | 33% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | N/A | N/A | 0 | 0% | N/A | N/A | 0 | 0% | 0 | 0% | 0 | N/A | N/A | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Complete Future Tasks (adjusted) | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | Status Date | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | BEI - Value Milestones | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | BEI - Total Milestones | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Phase Analyzer | BEI - Complete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Incomplete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Value Milestones (adjusted) | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | BEI - Complete Milestones (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Complete Future Milestones (adjusted) | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | Status Date | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | HMI - Value Tasks | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 0 |  | 0 |  | 0.33 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | N/A |  | 0 |  | N/A |  | 0 |  | 0 |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | HMI - Total Tasks | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2 |  | 2 |  | 3 |  | 1 |  | 1 |  | 2 |  | 3 |  | 1 |  | 1 |  | 0 |  | 1 |  | 0 |  | 1 |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Phase Analyzer | HMI - Complete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | N/A | 0% | 1 | 33% | N/A | 0% | N/A | 0% | N/A | 0% | N/A | 0% | N/A | 0% | N/A | 0% | N/A | N/A | N/A | 0% | N/A | N/A | N/A | 0% | N/A | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Completed Early Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | N/A | 0% | N/A | 0% | N/A | 0% | N/A | 0% | N/A | 0% | N/A | 0% | N/A | 0% | N/A | 0% | N/A | N/A | N/A | 0% | N/A | N/A | N/A | 0% | N/A | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Incomplete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 | 100% | 2 | 100% | 2 | 67% | 1 | 100% | 1 | 100% | 2 | 100% | 3 | 100% | 1 | 100% | 1 | 100% | N/A | N/A | 1 | 100% | N/A | N/A | 1 | 100% | 1 | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Value Tasks (adjusted) | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 0 |  | 0 |  | 0.33 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | N/A |  | 0 |  | N/A |  | 0 |  | 0 |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | HMI - Complete Tasks (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | N/A | 0% | 1 | 33% | N/A | 0% | N/A | 0% | N/A | 0% | N/A | 0% | N/A | 0% | N/A | 0% | N/A | N/A | N/A | 0% | N/A | N/A | N/A | 0% | N/A | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Complete Future Tasks (adjusted) | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | Status Date | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | HMI - Value Milestones | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | HMI - Total Milestones | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Phase Analyzer | HMI - Complete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Completed Early Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Incomplete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Value Milestones (adjusted) | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | HMI - Complete Milestones (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Complete Future Milestones (adjusted) | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | Status Date | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | CEI - Value Tasks | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | CEI - Total Tasks | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Phase Analyzer | CEI - Complete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Incomplete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Value Tasks (adjusted) | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | CEI - Complete Tasks (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Complete Future Tasks (adjusted) | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | Status Date | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | New Activity - Created | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Phase Analyzer | New Activity - Already Finished | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | New Activity - Finished in Status Period | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | CEI - Value Milestones | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | CEI - Total Milestones | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Phase Analyzer | CEI - Complete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Incomplete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Value Milestones (adjusted) | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | CEI - Complete Milestones (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Complete Future Milestones (adjusted) | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Phase Analyzer | Status Date | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | 2026-05-24 |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A

## Ribbon Analysis
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Early Finishes | Late Finishes | Total Activities | Milestones | Normal | Summaries | Hammocks | Milestone Ratio | Detail Level | Missing WBS | Longest Path | Riding Data Date | Activities per million | Original Duration | Remaining Duration | Rem. Critical Duration | Rem. Non-Critical Duration | Avg. Original Duration | Avg. Remaining Duration | Ribbon Length | Schedule Overrun | Lags | Leads | Minimum Lag | Maximum Lag | Hidden Duration | Constraint | As Late As Possible | Finish On Or After | Finish On Or Before | Must Finish On | Mandatory Finish | Must Start On | Mandatory Start | Start And Finish | Start On Or After | Start On Or Before | Late Constraints | Early Constraints | Free Float Constraints | Total Float Constraints | Soft Constraints | Hard Constraints | Unsatisfied Constraints | Critical | Non-Critical | Negative Float | Zero Days Float | 0 to 20 Days Float | 20 to 30 days float | More than 30 days float | High Float | Avg Float | Max Float | Float Ratio™ | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Status Date | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Status Date | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | New Activity - Created | New Activity - Already Finished | New Activity - Finished in Status Period | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | Score
Ribbons | Project2 | 4 | 0 | 2 | 1 | 0 | 0 | 44 | 0 | 1 | 0 | 0 | 0 | 18 | ✓ | 1 | 0.74 | 126 | 126 | 144 | 0 | 126 | 18 | 0 | N/A | 1:07 | 0 | 41 | 0 | N/A | 1128 | 920 | 335 | 585 | 9 | 9 | 561 | 0 | 2 | 0 | 0 | 5 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 41 | 65 | 0 | 41 | 18 | 2 | 45 | 44 | 48 | 263 | 5.58 | 0.74 | 27 | 20 | 7 | 0.74 | 20 | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 12
Ribbons | Project5_TAMPERED | 5 | 0 | 1 | 0 | 0 | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 37 | ✓ | 1 | 0.59 | 126 | 126 | 144 | 0 | 126 | 18 | 0 | N/A | 1:07 | 0 | 4 | 0 | N/A | 1256 | 935 | 32 | 903 | 10 | 9 | 695 | 0 | 2 | 0 | 0 | 5 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 5 | 0 | 0 | 5 | 0 | 1 | 5 | 1 | 0 | 4 | 95 | 0 | 4 | 35 | 3 | 57 | 44 | 71 | 275 | 7.52 | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0.05 | 19 | 1 | N/A | 18 | 0.05 | 1 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0.44 | 16 | 7 | 9 | 0.44 | 7 | 0 | 2026-08-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 12
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Early Finishes | Late Finishes | Total Activities | Milestones | Normal | Summaries | Hammocks | Milestone Ratio | Detail Level | Missing WBS | Longest Path | Riding Data Date | Activities per million | Original Duration | Remaining Duration | Rem. Critical Duration | Rem. Non-Critical Duration | Avg. Original Duration | Avg. Remaining Duration | Ribbon Length | Schedule Overrun | Lags | Leads | Minimum Lag | Maximum Lag | Hidden Duration | Constraint | As Late As Possible | Finish On Or After | Finish On Or Before | Must Finish On | Mandatory Finish | Must Start On | Mandatory Start | Start And Finish | Start On Or After | Start On Or Before | Late Constraints | Early Constraints | Free Float Constraints | Total Float Constraints | Soft Constraints | Hard Constraints | Unsatisfied Constraints | Critical | Non-Critical | Negative Float | Zero Days Float | 0 to 20 Days Float | 20 to 30 days float | More than 30 days float | High Float | Avg Float | Max Float | Float Ratio™ | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Status Date | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Status Date | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | New Activity - Created | New Activity - Already Finished | New Activity - Finished in Status Period | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | Score
Ribbons | Project2 | 4% | 0% | 1% | 1% | 0% | 0% | 42% | 0% | 1% | 0% | 0% | 0% | 67% | [5 empty] | 100% | 0% | 88% | 13% | 0% | 0 | 0.14 | 0% | 39% | 0% |  | 281% | 269% | 98% | 171% |  |  |  | 0% | 2% | 0% |  |  | 1% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2% | 0% | 0% | 2% | 0% | 0% | 2% | 0% | 0% | 39% | 61% | 0% | 39% | 17% | 2% | 42% | 42% | [5 empty] | 74% | 26% |  | 74% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A
Ribbons | Project5_TAMPERED | 5% | 0% | 1% | 0% | 0% | 1% | 44% | 0% | 0% | 0% | 0% | 0% | 80% | [5 empty] | 100% | 0% | 88% | 13% | 0% | 0 | 0.14 | 0% | 4% | 0% |  | 312% | 273% | 9% | 264% |  |  |  | 0% | 2% | 0% |  |  | 1% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 4% | 0% | 0% | 4% | 0% | 1% | 4% | 1% | 0% | 4% | 96% | 0% | 4% | 35% | 3% | 58% | 44% | [5 empty] | 59% | 41% |  | 59% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | 5% | 0% | 95% |  | 5% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | 44% | 56% |  | 44% | [7 empty] | N/A | N/A |  | N/A

## Project21
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View | Project2: Detailed View
1. Logic
Number of activities that are missing a predecessor, a successor or both. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 64
FALSE |  | 131 | Set HVAC trim and test and balance system | Project2 | 20 | 20 | 2027-07-26 | 2027-08-20 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 17
FALSE |  | 136 | Substantial completion date | Project2 | 1 | 1 | 2027-08-18 | 2027-08-18 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 19
FALSE |  | 145 | Issue final request for payment | Project2 | 1 | 1 | 2027-09-14 | 2027-09-14 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
3. Lags
Number of lags in the schedule.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59
4. SS/FF Relations
Number of Start to Start (SS) and Finish to Finish (FF) logic links. Should be lower than 10%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
6. High Float
Number of activities with total float greater than 2 months. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project2 | 4 | 4 | 2026-07-29 | 2026-08-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 204
FALSE |  | 37 | Form elevator pit walls | Project2 | 4 | 4 | 2026-08-06 | 2026-08-11 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 203
FALSE |  | 40 | Pour concrete elevator walls | Project2 | 1 | 1 | 2026-08-13 | 2026-08-13 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 202
FALSE |  | 41 | Cure elevator wall concrete | Project2 | 7 | 7 | 2026-08-27 | 2026-09-04 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 202
FALSE |  | 43 | Strip wall forms | Project2 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 202
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project2 | 3 | 3 | 2026-09-08 | 2026-09-10 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 202
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 202
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project2 | 10 | 10 | 2026-10-22 | 2026-11-04 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 144
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144
FALSE |  | 59 | Strip forms from 2nd floor slab | Project2 | 2 | 2 | 2026-11-27 | 2026-11-30 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 73
FALSE |  | 70 | Form 1st floor | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 73 | Install rebar and in-floor utilities | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144
FALSE |  | 127 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-03 | 2026-12-16 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 151
FALSE |  | 71 | Install electrical underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 72 | Install plumbing underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 74 | Pour 1st floor slab | Project2 | 4 | 4 | 2026-12-14 | 2026-12-17 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 73
FALSE |  | 75 | Cure 1st floor slab | Project2 | 7 | 7 | 2026-12-23 | 2026-12-31 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 73
FALSE |  | 112 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-31 | 2027-01-13 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 144
FALSE |  | 76 | Strip forms from 1st floor slab | Project2 | 2 | 2 | 2027-01-07 | 2027-01-08 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 73
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 93
FALSE |  | 120 | Rough-in electrical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 73
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 114
FALSE |  | 113 | Test and align doors and equipment | Project2 | 10 | 10 | 2027-01-14 | 2027-01-27 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 144
FALSE |  | 84 | Install tile in toilet rooms | Project2 | 10 | 10 | 2027-02-08 | 2027-02-19 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 93
FALSE |  | 86 | Clean toilet room tile | Project2 | 5 | 5 | 2027-02-22 | 2027-02-26 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 93
FALSE |  | 85 | Clean masonry | Project2 | 5 | 5 | 2027-03-04 | 2027-03-10 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 90
FALSE |  | 88 | Install flashing at parapet walls | Project2 | 4 | 4 | 2027-03-04 | 2027-03-09 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 61
FALSE |  | 83 | Install roof drains | Project2 | 2 | 2 | 2027-03-10 | 2027-03-11 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 59
FALSE |  | 116 | Tie-in fire line riser and set valves | Project2 | 10 | 10 | 2027-03-11 | 2027-03-24 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 90
FALSE |  | 89 | Pour lightweight concrete roof fill | Project2 | 2 | 2 | 2027-03-12 | 2027-03-15 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 59
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59
FALSE |  | 91 | Spread stone ballast on seamless roof | Project2 | 5 | 5 | 2027-03-30 | 2027-04-05 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 59
FALSE |  | 92 | Set rooftop equipment | Project2 | 10 | 10 | 2027-04-06 | 2027-04-19 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 59
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45
FALSE |  | 130 | Install duct in building chase | Project2 | 15 | 15 | 2027-04-20 | 2027-05-10 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 71
FALSE |  | 117 | Set plumbing fixtures and trim | Project2 | 15 | 15 | 2027-05-06 | 2027-05-26 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 45
FALSE |  | 133 | Install hard tile flooring in common areas | Project2 | 5 | 5 | 2027-05-13 | 2027-05-19 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 56
FALSE |  | 134 | Clean hard tile floors | Project2 | 4 | 4 | 2027-05-20 | 2027-05-25 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 56
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 64
8. High Duration
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
11. Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project2 | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project2 | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project2 | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project2 | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project2 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project2 | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project2 | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project2 | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project2 | 5 | 5 | 2026-07-06 | 2026-07-10 | 2026-04-30 | 2026-05-06 | Normal | Planned | 0 | 0
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
Total Activities
The total number of activities within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 2 | General Conditions | Project2 | 46 | 0 | 2026-03-02 | 2026-05-04 | 2026-03-02 | 2026-04-01 | Summary | Complete | 100 | 0
FALSE |  | 3 | Receive notice to proceed and sign contract | Project2 | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project2 | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project2 | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 18 | Mobilize on Site | Project2 | 17 | 0 | 2026-03-05 | 2026-03-27 | 2026-03-05 | 2026-03-18 | Summary | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 10 | Long Lead Procurement | Project2 | 76 | 20 | 2026-03-06 | 2026-06-19 | 2026-03-06 | 2026-06-11 | Summary | InProgress | 74 | 248
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project2 | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project2 | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project2 | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project2 | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project2 | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project2 | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 6 | Prepare and submit schedule of values | Project2 | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project2 | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 24 | Site Grading and Utilities | Project2 | 70 | 28 | 2026-04-06 | 2026-07-10 | 2026-03-19 | 2026-05-06 | Summary | InProgress | 60 | 0
FALSE |  | 25 | Clear and grub site | Project2 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project2 | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project2 | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project2 | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project2 | 5 | 5 | 2026-07-06 | 2026-07-10 | 2026-04-30 | 2026-05-06 | Normal | Planned | 0 | 0
FALSE |  | 32 | Foundations | Project2 | 45 | 45 | 2026-07-13 | 2026-09-11 | 2026-05-07 | 2026-07-08 | Summary | Planned | 0 | 0
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
FALSE |  | 35 | Form column piers and spread foundations | Project2 | 4 | 4 | 2026-07-27 | 2026-07-30 | 2026-05-21 | 2026-05-26 | Normal | Planned | 0 | 0
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project2 | 4 | 4 | 2026-07-29 | 2026-08-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 204
FALSE |  | 38 | Set reinforcing and anchor bolts | Project2 | 4 | 4 | 2026-07-31 | 2026-08-05 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 0
FALSE |  | 37 | Form elevator pit walls | Project2 | 4 | 4 | 2026-08-06 | 2026-08-11 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 203
FALSE |  | 39 | Pour column piers and foundations | Project2 | 5 | 5 | 2026-08-06 | 2026-08-12 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 0
FALSE |  | 40 | Pour concrete elevator walls | Project2 | 1 | 1 | 2026-08-13 | 2026-08-13 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 202
FALSE |  | 42 | Cure piers and foundations | Project2 | 7 | 7 | 2026-08-13 | 2026-08-21 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 0
FALSE |  | 44 | Strip column piers and foundation forms | Project2 | 3 | 3 | 2026-08-24 | 2026-08-26 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 0
FALSE |  | 41 | Cure elevator wall concrete | Project2 | 7 | 7 | 2026-08-27 | 2026-09-04 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 202
FALSE |  | 47 | Steel Erection | Project2 | 50 | 50 | 2026-08-27 | 2026-11-04 | 2026-06-23 | 2026-08-31 | Summary | Planned | 0 | 0
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project2 | 10 | 10 | 2026-08-27 | 2026-09-09 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 0
FALSE |  | 43 | Strip wall forms | Project2 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 202
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project2 | 3 | 3 | 2026-09-08 | 2026-09-10 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 202
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-10 | 2026-09-23 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 0
FALSE |  | 54 | Form and Pour Concrete - Floors and Roof | Project2 | 87 | 87 | 2026-09-10 | 2027-01-08 | 2026-07-07 | 2026-11-04 | Summary | Planned | 0 | 35
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-09-10 | 2026-09-16 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 35
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 202
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-24 | 2026-10-07 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 0
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project2 | 10 | 10 | 2026-10-08 | 2026-10-21 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project2 | 10 | 10 | 2026-10-22 | 2026-11-04 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 144
FALSE |  | 53 | Touch-up paint on steel | Project2 | 5 | 5 | 2026-10-22 | 2026-10-28 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 55 | Form 2nd floor including all floor openings | Project2 | 5 | 5 | 2026-10-29 | 2026-11-04 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 0
FALSE |  | 57 | Pour 2nd floor slab | Project2 | 4 | 4 | 2026-11-05 | 2026-11-10 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 79 | Masonry Work | Project2 | 91 | 91 | 2026-11-05 | 2027-03-11 | 2026-09-01 | 2027-01-05 | Summary | Planned | 0 | 60
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144
FALSE |  | 58 | Cure 2nd floor slab | Project2 | 7 | 7 | 2026-11-11 | 2026-11-19 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 60 | Form 3rd floor including all floor openings | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 59 | Strip forms from 2nd floor slab | Project2 | 2 | 2 | 2026-11-27 | 2026-11-30 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 73
FALSE |  | 62 | Pour 3rd floor slab | Project2 | 4 | 4 | 2026-11-27 | 2026-12-02 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 70 | Form 1st floor | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 73 | Install rebar and in-floor utilities | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 63 | Cure 3rd floor slab | Project2 | 7 | 7 | 2026-12-03 | 2026-12-11 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 110 | Elevators | Project2 | 40 | 40 | 2026-12-03 | 2027-01-27 | 2026-09-29 | 2026-11-23 | Summary | Planned | 0 | 144
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144
FALSE |  | 126 | Heating and Ventilating - AC | Project2 | 187 | 187 | 2026-12-03 | 2027-08-20 | 2026-09-29 | 2027-06-16 | Summary | Planned | 0 | 17
FALSE |  | 127 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-03 | 2026-12-16 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 151
FALSE |  | 71 | Install electrical underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 72 | Install plumbing underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 65 | Form roof slab including all floor openings | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 74 | Pour 1st floor slab | Project2 | 4 | 4 | 2026-12-14 | 2026-12-17 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 73
FALSE |  | 64 | Strip forms from 3rd floor slab | Project2 | 2 | 2 | 2026-12-21 | 2026-12-22 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 11
FALSE |  | 67 | Pour roof slab | Project2 | 4 | 4 | 2026-12-21 | 2026-12-24 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 0
FALSE |  | 75 | Cure 1st floor slab | Project2 | 7 | 7 | 2026-12-23 | 2026-12-31 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 73
FALSE |  | 68 | Cure roof slab | Project2 | 7 | 7 | 2026-12-25 | 2027-01-04 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 112 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-31 | 2027-01-13 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 144
FALSE |  | 69 | Strip forms from roof slab | Project2 | 2 | 2 | 2027-01-05 | 2027-01-06 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 76 | Strip forms from 1st floor slab | Project2 | 2 | 2 | 2027-01-07 | 2027-01-08 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 73
FALSE |  | 77 | Carpentry Work | Project2 | 15 | 15 | 2027-01-07 | 2027-01-27 | 2026-11-03 | 2026-11-23 | Summary | Planned | 0 | 0
FALSE |  | 78 | Install exterior sheathing and metal studs | Project2 | 15 | 15 | 2027-01-07 | 2027-01-27 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 0
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 93
FALSE |  | 119 | Electrical | Project2 | 140 | 140 | 2027-01-11 | 2027-07-23 | 2026-11-05 | 2027-05-19 | Summary | Planned | 0 | 17
FALSE |  | 120 | Rough-in electrical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 73
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 114
FALSE |  | 113 | Test and align doors and equipment | Project2 | 10 | 10 | 2027-01-14 | 2027-01-27 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 144
FALSE |  | 82 | Install exterior masonry work | Project2 | 25 | 25 | 2027-01-28 | 2027-03-03 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 0
FALSE |  | 84 | Install tile in toilet rooms | Project2 | 10 | 10 | 2027-02-08 | 2027-02-19 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 93
FALSE |  | 86 | Clean toilet room tile | Project2 | 5 | 5 | 2027-02-22 | 2027-02-26 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 93
FALSE |  | 85 | Clean masonry | Project2 | 5 | 5 | 2027-03-04 | 2027-03-10 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 90
FALSE |  | 87 | Roofing | Project2 | 33 | 33 | 2027-03-04 | 2027-04-19 | 2026-12-29 | 2027-02-11 | Summary | Planned | 0 | 59
FALSE |  | 88 | Install flashing at parapet walls | Project2 | 4 | 4 | 2027-03-04 | 2027-03-09 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 61
FALSE |  | 93 | Window wall and store front closures | Project2 | 75 | 75 | 2027-03-04 | 2027-06-16 | 2026-12-29 | 2027-04-12 | Summary | Planned | 0 | 0
FALSE |  | 94 | Install window wall aluminum and glass | Project2 | 25 | 25 | 2027-03-04 | 2027-04-07 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 0
FALSE |  | 83 | Install roof drains | Project2 | 2 | 2 | 2027-03-10 | 2027-03-11 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 59
FALSE |  | 114 | Plumbing | Project2 | 100 | 100 | 2027-03-11 | 2027-07-28 | 2027-01-05 | 2027-05-24 | Summary | Planned | 0 | 10
FALSE |  | 116 | Tie-in fire line riser and set valves | Project2 | 10 | 10 | 2027-03-11 | 2027-03-24 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 90
FALSE |  | 89 | Pour lightweight concrete roof fill | Project2 | 2 | 2 | 2027-03-12 | 2027-03-15 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 59
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59
FALSE |  | 91 | Spread stone ballast on seamless roof | Project2 | 5 | 5 | 2027-03-30 | 2027-04-05 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 59
FALSE |  | 92 | Set rooftop equipment | Project2 | 10 | 10 | 2027-04-06 | 2027-04-19 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 59
FALSE |  | 95 | Install interior stud walls and drywall | Project2 | 25 | 25 | 2027-04-08 | 2027-05-12 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 0
FALSE |  | 97 | Install store front doors and hardware | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 20
FALSE |  | 98 | Building Finishes | Project2 | 90 | 90 | 2027-04-08 | 2027-08-11 | 2027-02-02 | 2027-06-07 | Summary | Planned | 0 | 7
FALSE |  | 101 | Install conduit at ceiling plenum space | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 15
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45
FALSE |  | 130 | Install duct in building chase | Project2 | 15 | 15 | 2027-04-20 | 2027-05-10 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 71
FALSE |  | 121 | Rough-in electrical in drywall walls | Project2 | 20 | 20 | 2027-04-29 | 2027-05-26 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 30
FALSE |  | 117 | Set plumbing fixtures and trim | Project2 | 15 | 15 | 2027-05-06 | 2027-05-26 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 45
FALSE |  | 99 | Install millwork and wood trim | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 102 | Install duct in ceiling plenum space | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 132 | Final Clean-up and Occupancy | Project2 | 70 | 70 | 2027-05-13 | 2027-08-18 | 2027-03-09 | 2027-06-14 | Summary | Planned | 0 | 19
FALSE |  | 133 | Install hard tile flooring in common areas | Project2 | 5 | 5 | 2027-05-13 | 2027-05-19 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 56
FALSE |  | 134 | Clean hard tile floors | Project2 | 4 | 4 | 2027-05-20 | 2027-05-25 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 56
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project2 | 15 | 15 | 2027-05-27 | 2027-06-16 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 15
FALSE |  | 96 | Install interior doors and hardware | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 0
FALSE |  | 103 | Install ceiling grid | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 10
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 64
FALSE |  | 100 | Paint walls and woodwork | Project2 | 20 | 20 | 2027-06-17 | 2027-07-14 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 0
FALSE |  | 104 | Install ceiling tile | Project2 | 10 | 10 | 2027-06-17 | 2027-06-30 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 30
FALSE |  | 123 | Install and terminate electrical devices | Project2 | 15 | 15 | 2027-06-17 | 2027-07-07 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 15
FALSE |  | 125 | Install light fixtures - test and clean | Project2 | 10 | 10 | 2027-07-08 | 2027-07-21 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 15
FALSE |  | 105 | Hang wallpaper | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 106 | Install building carpet | Project2 | 20 | 20 | 2027-07-15 | 2027-08-11 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 0
FALSE |  | 107 | Install hardware and accessories | Project2 | 15 | 15 | 2027-07-15 | 2027-08-04 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 5
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 7
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project2 | 2 | 2 | 2027-07-22 | 2027-07-23 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 17
FALSE |  | 131 | Set HVAC trim and test and balance system | Project2 | 20 | 20 | 2027-07-26 | 2027-08-20 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 17
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project2 | 10 | 10 | 2027-07-29 | 2027-08-11 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 7
FALSE |  | 135 | Remove debris from building and do final clean-up | Project2 | 4 | 4 | 2027-08-12 | 2027-08-17 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 0
FALSE |  | 136 | Substantial completion date | Project2 | 1 | 1 | 2027-08-18 | 2027-08-18 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 19
FALSE |  | 137 | Complete Final Inspections | Project2 | 6 | 6 | 2027-08-18 | 2027-08-25 | 2027-06-14 | 2027-06-21 | Summary | Planned | 0 | 0
FALSE |  | 138 | Complete elevator inspection and certification | Project2 | 3 | 3 | 2027-08-18 | 2027-08-20 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 139 | Perform architect's inspection | Project2 | 1 | 1 | 2027-08-23 | 2027-08-23 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 0
FALSE |  | 140 | Perform local building agency inspection | Project2 | 1 | 1 | 2027-08-24 | 2027-08-24 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project2 | 1 | 1 | 2027-08-25 | 2027-08-25 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project2 | 10 | 10 | 2027-08-26 | 2027-09-08 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project2 | 2 | 2 | 2027-09-09 | 2027-09-10 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project2 | 1 | 1 | 2027-09-13 | 2027-09-13 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project2 | 1 | 1 | 2027-09-14 | 2027-09-14 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Normal
Number of normal activities within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project2 | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project2 | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project2 | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project2 | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project2 | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project2 | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project2 | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project2 | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project2 | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 6 | Prepare and submit schedule of values | Project2 | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project2 | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project2 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project2 | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project2 | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project2 | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project2 | 5 | 5 | 2026-07-06 | 2026-07-10 | 2026-04-30 | 2026-05-06 | Normal | Planned | 0 | 0
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
FALSE |  | 35 | Form column piers and spread foundations | Project2 | 4 | 4 | 2026-07-27 | 2026-07-30 | 2026-05-21 | 2026-05-26 | Normal | Planned | 0 | 0
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project2 | 4 | 4 | 2026-07-29 | 2026-08-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 204
FALSE |  | 38 | Set reinforcing and anchor bolts | Project2 | 4 | 4 | 2026-07-31 | 2026-08-05 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 0
FALSE |  | 37 | Form elevator pit walls | Project2 | 4 | 4 | 2026-08-06 | 2026-08-11 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 203
FALSE |  | 39 | Pour column piers and foundations | Project2 | 5 | 5 | 2026-08-06 | 2026-08-12 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 0
FALSE |  | 40 | Pour concrete elevator walls | Project2 | 1 | 1 | 2026-08-13 | 2026-08-13 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 202
FALSE |  | 42 | Cure piers and foundations | Project2 | 7 | 7 | 2026-08-13 | 2026-08-21 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 0
FALSE |  | 44 | Strip column piers and foundation forms | Project2 | 3 | 3 | 2026-08-24 | 2026-08-26 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 0
FALSE |  | 41 | Cure elevator wall concrete | Project2 | 7 | 7 | 2026-08-27 | 2026-09-04 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 202
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project2 | 10 | 10 | 2026-08-27 | 2026-09-09 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 0
FALSE |  | 43 | Strip wall forms | Project2 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 202
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project2 | 3 | 3 | 2026-09-08 | 2026-09-10 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 202
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-10 | 2026-09-23 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 0
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-09-10 | 2026-09-16 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 35
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 202
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-24 | 2026-10-07 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 0
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project2 | 10 | 10 | 2026-10-08 | 2026-10-21 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project2 | 10 | 10 | 2026-10-22 | 2026-11-04 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 144
FALSE |  | 53 | Touch-up paint on steel | Project2 | 5 | 5 | 2026-10-22 | 2026-10-28 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 55 | Form 2nd floor including all floor openings | Project2 | 5 | 5 | 2026-10-29 | 2026-11-04 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 0
FALSE |  | 57 | Pour 2nd floor slab | Project2 | 4 | 4 | 2026-11-05 | 2026-11-10 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144
FALSE |  | 58 | Cure 2nd floor slab | Project2 | 7 | 7 | 2026-11-11 | 2026-11-19 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 60 | Form 3rd floor including all floor openings | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 59 | Strip forms from 2nd floor slab | Project2 | 2 | 2 | 2026-11-27 | 2026-11-30 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 73
FALSE |  | 62 | Pour 3rd floor slab | Project2 | 4 | 4 | 2026-11-27 | 2026-12-02 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 70 | Form 1st floor | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 73 | Install rebar and in-floor utilities | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 63 | Cure 3rd floor slab | Project2 | 7 | 7 | 2026-12-03 | 2026-12-11 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144
FALSE |  | 127 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-03 | 2026-12-16 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 151
FALSE |  | 71 | Install electrical underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 72 | Install plumbing underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 65 | Form roof slab including all floor openings | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 74 | Pour 1st floor slab | Project2 | 4 | 4 | 2026-12-14 | 2026-12-17 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 73
FALSE |  | 64 | Strip forms from 3rd floor slab | Project2 | 2 | 2 | 2026-12-21 | 2026-12-22 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 11
FALSE |  | 67 | Pour roof slab | Project2 | 4 | 4 | 2026-12-21 | 2026-12-24 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 0
FALSE |  | 75 | Cure 1st floor slab | Project2 | 7 | 7 | 2026-12-23 | 2026-12-31 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 73
FALSE |  | 68 | Cure roof slab | Project2 | 7 | 7 | 2026-12-25 | 2027-01-04 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 112 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-31 | 2027-01-13 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 144
FALSE |  | 69 | Strip forms from roof slab | Project2 | 2 | 2 | 2027-01-05 | 2027-01-06 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 76 | Strip forms from 1st floor slab | Project2 | 2 | 2 | 2027-01-07 | 2027-01-08 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 73
FALSE |  | 78 | Install exterior sheathing and metal studs | Project2 | 15 | 15 | 2027-01-07 | 2027-01-27 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 0
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 93
FALSE |  | 120 | Rough-in electrical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 73
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 114
FALSE |  | 113 | Test and align doors and equipment | Project2 | 10 | 10 | 2027-01-14 | 2027-01-27 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 144
FALSE |  | 82 | Install exterior masonry work | Project2 | 25 | 25 | 2027-01-28 | 2027-03-03 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 0
FALSE |  | 84 | Install tile in toilet rooms | Project2 | 10 | 10 | 2027-02-08 | 2027-02-19 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 93
FALSE |  | 86 | Clean toilet room tile | Project2 | 5 | 5 | 2027-02-22 | 2027-02-26 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 93
FALSE |  | 85 | Clean masonry | Project2 | 5 | 5 | 2027-03-04 | 2027-03-10 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 90
FALSE |  | 88 | Install flashing at parapet walls | Project2 | 4 | 4 | 2027-03-04 | 2027-03-09 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 61
FALSE |  | 94 | Install window wall aluminum and glass | Project2 | 25 | 25 | 2027-03-04 | 2027-04-07 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 0
FALSE |  | 83 | Install roof drains | Project2 | 2 | 2 | 2027-03-10 | 2027-03-11 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 59
FALSE |  | 116 | Tie-in fire line riser and set valves | Project2 | 10 | 10 | 2027-03-11 | 2027-03-24 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 90
FALSE |  | 89 | Pour lightweight concrete roof fill | Project2 | 2 | 2 | 2027-03-12 | 2027-03-15 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 59
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59
FALSE |  | 91 | Spread stone ballast on seamless roof | Project2 | 5 | 5 | 2027-03-30 | 2027-04-05 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 59
FALSE |  | 92 | Set rooftop equipment | Project2 | 10 | 10 | 2027-04-06 | 2027-04-19 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 59
FALSE |  | 95 | Install interior stud walls and drywall | Project2 | 25 | 25 | 2027-04-08 | 2027-05-12 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 0
FALSE |  | 97 | Install store front doors and hardware | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 20
FALSE |  | 101 | Install conduit at ceiling plenum space | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 15
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45
FALSE |  | 130 | Install duct in building chase | Project2 | 15 | 15 | 2027-04-20 | 2027-05-10 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 71
FALSE |  | 121 | Rough-in electrical in drywall walls | Project2 | 20 | 20 | 2027-04-29 | 2027-05-26 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 30
FALSE |  | 117 | Set plumbing fixtures and trim | Project2 | 15 | 15 | 2027-05-06 | 2027-05-26 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 45
FALSE |  | 99 | Install millwork and wood trim | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 102 | Install duct in ceiling plenum space | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 133 | Install hard tile flooring in common areas | Project2 | 5 | 5 | 2027-05-13 | 2027-05-19 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 56
FALSE |  | 134 | Clean hard tile floors | Project2 | 4 | 4 | 2027-05-20 | 2027-05-25 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 56
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project2 | 15 | 15 | 2027-05-27 | 2027-06-16 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 15
FALSE |  | 96 | Install interior doors and hardware | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 0
FALSE |  | 103 | Install ceiling grid | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 10
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 64
FALSE |  | 100 | Paint walls and woodwork | Project2 | 20 | 20 | 2027-06-17 | 2027-07-14 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 0
FALSE |  | 104 | Install ceiling tile | Project2 | 10 | 10 | 2027-06-17 | 2027-06-30 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 30
FALSE |  | 123 | Install and terminate electrical devices | Project2 | 15 | 15 | 2027-06-17 | 2027-07-07 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 15
FALSE |  | 125 | Install light fixtures - test and clean | Project2 | 10 | 10 | 2027-07-08 | 2027-07-21 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 15
FALSE |  | 105 | Hang wallpaper | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 106 | Install building carpet | Project2 | 20 | 20 | 2027-07-15 | 2027-08-11 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 0
FALSE |  | 107 | Install hardware and accessories | Project2 | 15 | 15 | 2027-07-15 | 2027-08-04 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 5
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 7
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project2 | 2 | 2 | 2027-07-22 | 2027-07-23 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 17
FALSE |  | 131 | Set HVAC trim and test and balance system | Project2 | 20 | 20 | 2027-07-26 | 2027-08-20 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 17
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project2 | 10 | 10 | 2027-07-29 | 2027-08-11 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 7
FALSE |  | 135 | Remove debris from building and do final clean-up | Project2 | 4 | 4 | 2027-08-12 | 2027-08-17 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 0
FALSE |  | 136 | Substantial completion date | Project2 | 1 | 1 | 2027-08-18 | 2027-08-18 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 19
FALSE |  | 138 | Complete elevator inspection and certification | Project2 | 3 | 3 | 2027-08-18 | 2027-08-20 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 139 | Perform architect's inspection | Project2 | 1 | 1 | 2027-08-23 | 2027-08-23 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 0
FALSE |  | 140 | Perform local building agency inspection | Project2 | 1 | 1 | 2027-08-24 | 2027-08-24 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project2 | 1 | 1 | 2027-08-25 | 2027-08-25 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project2 | 10 | 10 | 2027-08-26 | 2027-09-08 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project2 | 2 | 2 | 2027-09-09 | 2027-09-10 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project2 | 1 | 1 | 2027-09-13 | 2027-09-13 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project2 | 1 | 1 | 2027-09-14 | 2027-09-14 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Summaries
Number of summary activities within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 2 | General Conditions | Project2 | 46 | 0 | 2026-03-02 | 2026-05-04 | 2026-03-02 | 2026-04-01 | Summary | Complete | 100 | 0
FALSE |  | 18 | Mobilize on Site | Project2 | 17 | 0 | 2026-03-05 | 2026-03-27 | 2026-03-05 | 2026-03-18 | Summary | Complete | 100 | 0
FALSE |  | 10 | Long Lead Procurement | Project2 | 76 | 20 | 2026-03-06 | 2026-06-19 | 2026-03-06 | 2026-06-11 | Summary | InProgress | 74 | 248
FALSE |  | 24 | Site Grading and Utilities | Project2 | 70 | 28 | 2026-04-06 | 2026-07-10 | 2026-03-19 | 2026-05-06 | Summary | InProgress | 60 | 0
FALSE |  | 32 | Foundations | Project2 | 45 | 45 | 2026-07-13 | 2026-09-11 | 2026-05-07 | 2026-07-08 | Summary | Planned | 0 | 0
FALSE |  | 47 | Steel Erection | Project2 | 50 | 50 | 2026-08-27 | 2026-11-04 | 2026-06-23 | 2026-08-31 | Summary | Planned | 0 | 0
FALSE |  | 54 | Form and Pour Concrete - Floors and Roof | Project2 | 87 | 87 | 2026-09-10 | 2027-01-08 | 2026-07-07 | 2026-11-04 | Summary | Planned | 0 | 35
FALSE |  | 79 | Masonry Work | Project2 | 91 | 91 | 2026-11-05 | 2027-03-11 | 2026-09-01 | 2027-01-05 | Summary | Planned | 0 | 60
FALSE |  | 110 | Elevators | Project2 | 40 | 40 | 2026-12-03 | 2027-01-27 | 2026-09-29 | 2026-11-23 | Summary | Planned | 0 | 144
FALSE |  | 126 | Heating and Ventilating - AC | Project2 | 187 | 187 | 2026-12-03 | 2027-08-20 | 2026-09-29 | 2027-06-16 | Summary | Planned | 0 | 17
FALSE |  | 77 | Carpentry Work | Project2 | 15 | 15 | 2027-01-07 | 2027-01-27 | 2026-11-03 | 2026-11-23 | Summary | Planned | 0 | 0
FALSE |  | 119 | Electrical | Project2 | 140 | 140 | 2027-01-11 | 2027-07-23 | 2026-11-05 | 2027-05-19 | Summary | Planned | 0 | 17
FALSE |  | 87 | Roofing | Project2 | 33 | 33 | 2027-03-04 | 2027-04-19 | 2026-12-29 | 2027-02-11 | Summary | Planned | 0 | 59
FALSE |  | 93 | Window wall and store front closures | Project2 | 75 | 75 | 2027-03-04 | 2027-06-16 | 2026-12-29 | 2027-04-12 | Summary | Planned | 0 | 0
FALSE |  | 114 | Plumbing | Project2 | 100 | 100 | 2027-03-11 | 2027-07-28 | 2027-01-05 | 2027-05-24 | Summary | Planned | 0 | 10
FALSE |  | 98 | Building Finishes | Project2 | 90 | 90 | 2027-04-08 | 2027-08-11 | 2027-02-02 | 2027-06-07 | Summary | Planned | 0 | 7
FALSE |  | 132 | Final Clean-up and Occupancy | Project2 | 70 | 70 | 2027-05-13 | 2027-08-18 | 2027-03-09 | 2027-06-14 | Summary | Planned | 0 | 19
FALSE |  | 137 | Complete Final Inspections | Project2 | 6 | 6 | 2027-08-18 | 2027-08-25 | 2027-06-14 | 2027-06-21 | Summary | Planned | 0 | 0
Longest Path
Activities that together form the longest path through to project completion.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project2 | 5 | 5 | 2026-07-06 | 2026-07-10 | 2026-04-30 | 2026-05-06 | Normal | Planned | 0 | 0
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
FALSE |  | 35 | Form column piers and spread foundations | Project2 | 4 | 4 | 2026-07-27 | 2026-07-30 | 2026-05-21 | 2026-05-26 | Normal | Planned | 0 | 0
FALSE |  | 38 | Set reinforcing and anchor bolts | Project2 | 4 | 4 | 2026-07-31 | 2026-08-05 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 0
FALSE |  | 39 | Pour column piers and foundations | Project2 | 5 | 5 | 2026-08-06 | 2026-08-12 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 0
FALSE |  | 42 | Cure piers and foundations | Project2 | 7 | 7 | 2026-08-13 | 2026-08-21 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 0
FALSE |  | 44 | Strip column piers and foundation forms | Project2 | 3 | 3 | 2026-08-24 | 2026-08-26 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 0
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project2 | 10 | 10 | 2026-08-27 | 2026-09-09 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 0
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-10 | 2026-09-23 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 0
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-24 | 2026-10-07 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 0
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project2 | 10 | 10 | 2026-10-08 | 2026-10-21 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 53 | Touch-up paint on steel | Project2 | 5 | 5 | 2026-10-22 | 2026-10-28 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 55 | Form 2nd floor including all floor openings | Project2 | 5 | 5 | 2026-10-29 | 2026-11-04 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 0
FALSE |  | 57 | Pour 2nd floor slab | Project2 | 4 | 4 | 2026-11-05 | 2026-11-10 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 58 | Cure 2nd floor slab | Project2 | 7 | 7 | 2026-11-11 | 2026-11-19 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 60 | Form 3rd floor including all floor openings | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 62 | Pour 3rd floor slab | Project2 | 4 | 4 | 2026-11-27 | 2026-12-02 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 63 | Cure 3rd floor slab | Project2 | 7 | 7 | 2026-12-03 | 2026-12-11 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 65 | Form roof slab including all floor openings | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 67 | Pour roof slab | Project2 | 4 | 4 | 2026-12-21 | 2026-12-24 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 0
FALSE |  | 68 | Cure roof slab | Project2 | 7 | 7 | 2026-12-25 | 2027-01-04 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 69 | Strip forms from roof slab | Project2 | 2 | 2 | 2027-01-05 | 2027-01-06 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 78 | Install exterior sheathing and metal studs | Project2 | 15 | 15 | 2027-01-07 | 2027-01-27 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 0
FALSE |  | 82 | Install exterior masonry work | Project2 | 25 | 25 | 2027-01-28 | 2027-03-03 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 0
FALSE |  | 94 | Install window wall aluminum and glass | Project2 | 25 | 25 | 2027-03-04 | 2027-04-07 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 0
FALSE |  | 95 | Install interior stud walls and drywall | Project2 | 25 | 25 | 2027-04-08 | 2027-05-12 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 0
FALSE |  | 96 | Install interior doors and hardware | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 0
FALSE |  | 100 | Paint walls and woodwork | Project2 | 20 | 20 | 2027-06-17 | 2027-07-14 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 0
FALSE |  | 106 | Install building carpet | Project2 | 20 | 20 | 2027-07-15 | 2027-08-11 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 0
FALSE |  | 135 | Remove debris from building and do final clean-up | Project2 | 4 | 4 | 2027-08-12 | 2027-08-17 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 0
FALSE |  | 138 | Complete elevator inspection and certification | Project2 | 3 | 3 | 2027-08-18 | 2027-08-20 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 139 | Perform architect's inspection | Project2 | 1 | 1 | 2027-08-23 | 2027-08-23 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 0
FALSE |  | 140 | Perform local building agency inspection | Project2 | 1 | 1 | 2027-08-24 | 2027-08-24 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project2 | 1 | 1 | 2027-08-25 | 2027-08-25 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project2 | 10 | 10 | 2027-08-26 | 2027-09-08 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 144 | Issue final completion documents including warranties | Project2 | 1 | 1 | 2027-09-13 | 2027-09-13 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project2 | 1 | 1 | 2027-09-14 | 2027-09-14 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Rem. Critical Duration
The amount of remaining time planned in order to complete all critical normal activities and milestones within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project2 | 5 | 5 | 2026-07-06 | 2026-07-10 | 2026-04-30 | 2026-05-06 | Normal | Planned | 0 | 0
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
FALSE |  | 35 | Form column piers and spread foundations | Project2 | 4 | 4 | 2026-07-27 | 2026-07-30 | 2026-05-21 | 2026-05-26 | Normal | Planned | 0 | 0
FALSE |  | 38 | Set reinforcing and anchor bolts | Project2 | 4 | 4 | 2026-07-31 | 2026-08-05 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 0
FALSE |  | 39 | Pour column piers and foundations | Project2 | 5 | 5 | 2026-08-06 | 2026-08-12 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 0
FALSE |  | 42 | Cure piers and foundations | Project2 | 7 | 7 | 2026-08-13 | 2026-08-21 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 0
FALSE |  | 44 | Strip column piers and foundation forms | Project2 | 3 | 3 | 2026-08-24 | 2026-08-26 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 0
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project2 | 10 | 10 | 2026-08-27 | 2026-09-09 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 0
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-10 | 2026-09-23 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 0
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-24 | 2026-10-07 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 0
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project2 | 10 | 10 | 2026-10-08 | 2026-10-21 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 53 | Touch-up paint on steel | Project2 | 5 | 5 | 2026-10-22 | 2026-10-28 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 55 | Form 2nd floor including all floor openings | Project2 | 5 | 5 | 2026-10-29 | 2026-11-04 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 0
FALSE |  | 57 | Pour 2nd floor slab | Project2 | 4 | 4 | 2026-11-05 | 2026-11-10 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 58 | Cure 2nd floor slab | Project2 | 7 | 7 | 2026-11-11 | 2026-11-19 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 60 | Form 3rd floor including all floor openings | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 62 | Pour 3rd floor slab | Project2 | 4 | 4 | 2026-11-27 | 2026-12-02 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 63 | Cure 3rd floor slab | Project2 | 7 | 7 | 2026-12-03 | 2026-12-11 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 65 | Form roof slab including all floor openings | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 67 | Pour roof slab | Project2 | 4 | 4 | 2026-12-21 | 2026-12-24 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 0
FALSE |  | 68 | Cure roof slab | Project2 | 7 | 7 | 2026-12-25 | 2027-01-04 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 69 | Strip forms from roof slab | Project2 | 2 | 2 | 2027-01-05 | 2027-01-06 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 78 | Install exterior sheathing and metal studs | Project2 | 15 | 15 | 2027-01-07 | 2027-01-27 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 0
FALSE |  | 82 | Install exterior masonry work | Project2 | 25 | 25 | 2027-01-28 | 2027-03-03 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 0
FALSE |  | 94 | Install window wall aluminum and glass | Project2 | 25 | 25 | 2027-03-04 | 2027-04-07 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 0
FALSE |  | 95 | Install interior stud walls and drywall | Project2 | 25 | 25 | 2027-04-08 | 2027-05-12 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 0
FALSE |  | 96 | Install interior doors and hardware | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 0
FALSE |  | 100 | Paint walls and woodwork | Project2 | 20 | 20 | 2027-06-17 | 2027-07-14 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 0
FALSE |  | 106 | Install building carpet | Project2 | 20 | 20 | 2027-07-15 | 2027-08-11 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 0
FALSE |  | 135 | Remove debris from building and do final clean-up | Project2 | 4 | 4 | 2027-08-12 | 2027-08-17 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 0
FALSE |  | 138 | Complete elevator inspection and certification | Project2 | 3 | 3 | 2027-08-18 | 2027-08-20 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 139 | Perform architect's inspection | Project2 | 1 | 1 | 2027-08-23 | 2027-08-23 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 0
FALSE |  | 140 | Perform local building agency inspection | Project2 | 1 | 1 | 2027-08-24 | 2027-08-24 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project2 | 1 | 1 | 2027-08-25 | 2027-08-25 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project2 | 10 | 10 | 2027-08-26 | 2027-09-08 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 144 | Issue final completion documents including warranties | Project2 | 1 | 1 | 2027-09-13 | 2027-09-13 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project2 | 1 | 1 | 2027-09-14 | 2027-09-14 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Rem. Non-Critical Duration
The amount of remaining time planned in order to complete all non-critical normal activities and milestones within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project2 | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project2 | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project2 | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project2 | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project2 | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project2 | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project2 | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project2 | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project2 | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 6 | Prepare and submit schedule of values | Project2 | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project2 | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project2 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project2 | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project2 | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project2 | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project2 | 4 | 4 | 2026-07-29 | 2026-08-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 204
FALSE |  | 37 | Form elevator pit walls | Project2 | 4 | 4 | 2026-08-06 | 2026-08-11 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 203
FALSE |  | 40 | Pour concrete elevator walls | Project2 | 1 | 1 | 2026-08-13 | 2026-08-13 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 202
FALSE |  | 41 | Cure elevator wall concrete | Project2 | 7 | 7 | 2026-08-27 | 2026-09-04 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 202
FALSE |  | 43 | Strip wall forms | Project2 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 202
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project2 | 3 | 3 | 2026-09-08 | 2026-09-10 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 202
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-09-10 | 2026-09-16 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 35
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 202
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project2 | 10 | 10 | 2026-10-22 | 2026-11-04 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 144
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144
FALSE |  | 59 | Strip forms from 2nd floor slab | Project2 | 2 | 2 | 2026-11-27 | 2026-11-30 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 73
FALSE |  | 70 | Form 1st floor | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 73 | Install rebar and in-floor utilities | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144
FALSE |  | 127 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-03 | 2026-12-16 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 151
FALSE |  | 71 | Install electrical underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 72 | Install plumbing underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 74 | Pour 1st floor slab | Project2 | 4 | 4 | 2026-12-14 | 2026-12-17 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 73
FALSE |  | 64 | Strip forms from 3rd floor slab | Project2 | 2 | 2 | 2026-12-21 | 2026-12-22 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 11
FALSE |  | 75 | Cure 1st floor slab | Project2 | 7 | 7 | 2026-12-23 | 2026-12-31 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 73
FALSE |  | 112 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-31 | 2027-01-13 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 144
FALSE |  | 76 | Strip forms from 1st floor slab | Project2 | 2 | 2 | 2027-01-07 | 2027-01-08 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 73
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 93
FALSE |  | 120 | Rough-in electrical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 73
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 114
FALSE |  | 113 | Test and align doors and equipment | Project2 | 10 | 10 | 2027-01-14 | 2027-01-27 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 144
FALSE |  | 84 | Install tile in toilet rooms | Project2 | 10 | 10 | 2027-02-08 | 2027-02-19 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 93
FALSE |  | 86 | Clean toilet room tile | Project2 | 5 | 5 | 2027-02-22 | 2027-02-26 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 93
FALSE |  | 85 | Clean masonry | Project2 | 5 | 5 | 2027-03-04 | 2027-03-10 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 90
FALSE |  | 88 | Install flashing at parapet walls | Project2 | 4 | 4 | 2027-03-04 | 2027-03-09 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 61
FALSE |  | 83 | Install roof drains | Project2 | 2 | 2 | 2027-03-10 | 2027-03-11 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 59
FALSE |  | 116 | Tie-in fire line riser and set valves | Project2 | 10 | 10 | 2027-03-11 | 2027-03-24 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 90
FALSE |  | 89 | Pour lightweight concrete roof fill | Project2 | 2 | 2 | 2027-03-12 | 2027-03-15 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 59
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59
FALSE |  | 91 | Spread stone ballast on seamless roof | Project2 | 5 | 5 | 2027-03-30 | 2027-04-05 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 59
FALSE |  | 92 | Set rooftop equipment | Project2 | 10 | 10 | 2027-04-06 | 2027-04-19 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 59
FALSE |  | 97 | Install store front doors and hardware | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 20
FALSE |  | 101 | Install conduit at ceiling plenum space | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 15
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45
FALSE |  | 130 | Install duct in building chase | Project2 | 15 | 15 | 2027-04-20 | 2027-05-10 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 71
FALSE |  | 121 | Rough-in electrical in drywall walls | Project2 | 20 | 20 | 2027-04-29 | 2027-05-26 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 30
FALSE |  | 117 | Set plumbing fixtures and trim | Project2 | 15 | 15 | 2027-05-06 | 2027-05-26 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 45
FALSE |  | 99 | Install millwork and wood trim | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 102 | Install duct in ceiling plenum space | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 133 | Install hard tile flooring in common areas | Project2 | 5 | 5 | 2027-05-13 | 2027-05-19 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 56
FALSE |  | 134 | Clean hard tile floors | Project2 | 4 | 4 | 2027-05-20 | 2027-05-25 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 56
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project2 | 15 | 15 | 2027-05-27 | 2027-06-16 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 15
FALSE |  | 103 | Install ceiling grid | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 10
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 64
FALSE |  | 104 | Install ceiling tile | Project2 | 10 | 10 | 2027-06-17 | 2027-06-30 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 30
FALSE |  | 123 | Install and terminate electrical devices | Project2 | 15 | 15 | 2027-06-17 | 2027-07-07 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 15
FALSE |  | 125 | Install light fixtures - test and clean | Project2 | 10 | 10 | 2027-07-08 | 2027-07-21 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 15
FALSE |  | 105 | Hang wallpaper | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 107 | Install hardware and accessories | Project2 | 15 | 15 | 2027-07-15 | 2027-08-04 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 5
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 7
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project2 | 2 | 2 | 2027-07-22 | 2027-07-23 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 17
FALSE |  | 131 | Set HVAC trim and test and balance system | Project2 | 20 | 20 | 2027-07-26 | 2027-08-20 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 17
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project2 | 10 | 10 | 2027-07-29 | 2027-08-11 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 7
FALSE |  | 136 | Substantial completion date | Project2 | 1 | 1 | 2027-08-18 | 2027-08-18 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 19
FALSE |  | 143 | Obtain certificate of occupancy | Project2 | 2 | 2 | 2027-09-09 | 2027-09-10 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
Lags
Total number of activities with positive lags.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59
Minimum Lag
The smallest successor lag value for the selected activity grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project2 | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project2 | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project2 | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project2 | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project2 | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project2 | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project2 | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project2 | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project2 | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 6 | Prepare and submit schedule of values | Project2 | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project2 | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project2 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project2 | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project2 | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project2 | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project2 | 5 | 5 | 2026-07-06 | 2026-07-10 | 2026-04-30 | 2026-05-06 | Normal | Planned | 0 | 0
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
FALSE |  | 35 | Form column piers and spread foundations | Project2 | 4 | 4 | 2026-07-27 | 2026-07-30 | 2026-05-21 | 2026-05-26 | Normal | Planned | 0 | 0
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project2 | 4 | 4 | 2026-07-29 | 2026-08-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 204
FALSE |  | 38 | Set reinforcing and anchor bolts | Project2 | 4 | 4 | 2026-07-31 | 2026-08-05 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 0
FALSE |  | 37 | Form elevator pit walls | Project2 | 4 | 4 | 2026-08-06 | 2026-08-11 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 203
FALSE |  | 39 | Pour column piers and foundations | Project2 | 5 | 5 | 2026-08-06 | 2026-08-12 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 0
FALSE |  | 40 | Pour concrete elevator walls | Project2 | 1 | 1 | 2026-08-13 | 2026-08-13 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 202
FALSE |  | 42 | Cure piers and foundations | Project2 | 7 | 7 | 2026-08-13 | 2026-08-21 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 0
FALSE |  | 44 | Strip column piers and foundation forms | Project2 | 3 | 3 | 2026-08-24 | 2026-08-26 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 0
FALSE |  | 41 | Cure elevator wall concrete | Project2 | 7 | 7 | 2026-08-27 | 2026-09-04 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 202
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project2 | 10 | 10 | 2026-08-27 | 2026-09-09 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 0
FALSE |  | 43 | Strip wall forms | Project2 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 202
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project2 | 3 | 3 | 2026-09-08 | 2026-09-10 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 202
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-10 | 2026-09-23 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 0
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-09-10 | 2026-09-16 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 35
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 202
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-24 | 2026-10-07 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 0
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project2 | 10 | 10 | 2026-10-08 | 2026-10-21 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project2 | 10 | 10 | 2026-10-22 | 2026-11-04 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 144
FALSE |  | 53 | Touch-up paint on steel | Project2 | 5 | 5 | 2026-10-22 | 2026-10-28 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 55 | Form 2nd floor including all floor openings | Project2 | 5 | 5 | 2026-10-29 | 2026-11-04 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 0
FALSE |  | 57 | Pour 2nd floor slab | Project2 | 4 | 4 | 2026-11-05 | 2026-11-10 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144
FALSE |  | 58 | Cure 2nd floor slab | Project2 | 7 | 7 | 2026-11-11 | 2026-11-19 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 60 | Form 3rd floor including all floor openings | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 59 | Strip forms from 2nd floor slab | Project2 | 2 | 2 | 2026-11-27 | 2026-11-30 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 73
FALSE |  | 62 | Pour 3rd floor slab | Project2 | 4 | 4 | 2026-11-27 | 2026-12-02 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 70 | Form 1st floor | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 73 | Install rebar and in-floor utilities | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 63 | Cure 3rd floor slab | Project2 | 7 | 7 | 2026-12-03 | 2026-12-11 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144
FALSE |  | 127 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-03 | 2026-12-16 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 151
FALSE |  | 71 | Install electrical underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 72 | Install plumbing underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 65 | Form roof slab including all floor openings | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 74 | Pour 1st floor slab | Project2 | 4 | 4 | 2026-12-14 | 2026-12-17 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 73
FALSE |  | 64 | Strip forms from 3rd floor slab | Project2 | 2 | 2 | 2026-12-21 | 2026-12-22 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 11
FALSE |  | 67 | Pour roof slab | Project2 | 4 | 4 | 2026-12-21 | 2026-12-24 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 0
FALSE |  | 75 | Cure 1st floor slab | Project2 | 7 | 7 | 2026-12-23 | 2026-12-31 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 73
FALSE |  | 68 | Cure roof slab | Project2 | 7 | 7 | 2026-12-25 | 2027-01-04 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 112 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-31 | 2027-01-13 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 144
FALSE |  | 69 | Strip forms from roof slab | Project2 | 2 | 2 | 2027-01-05 | 2027-01-06 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 76 | Strip forms from 1st floor slab | Project2 | 2 | 2 | 2027-01-07 | 2027-01-08 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 73
FALSE |  | 78 | Install exterior sheathing and metal studs | Project2 | 15 | 15 | 2027-01-07 | 2027-01-27 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 0
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 93
FALSE |  | 120 | Rough-in electrical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 73
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 114
FALSE |  | 113 | Test and align doors and equipment | Project2 | 10 | 10 | 2027-01-14 | 2027-01-27 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 144
FALSE |  | 82 | Install exterior masonry work | Project2 | 25 | 25 | 2027-01-28 | 2027-03-03 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 0
FALSE |  | 84 | Install tile in toilet rooms | Project2 | 10 | 10 | 2027-02-08 | 2027-02-19 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 93
FALSE |  | 86 | Clean toilet room tile | Project2 | 5 | 5 | 2027-02-22 | 2027-02-26 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 93
FALSE |  | 85 | Clean masonry | Project2 | 5 | 5 | 2027-03-04 | 2027-03-10 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 90
FALSE |  | 88 | Install flashing at parapet walls | Project2 | 4 | 4 | 2027-03-04 | 2027-03-09 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 61
FALSE |  | 94 | Install window wall aluminum and glass | Project2 | 25 | 25 | 2027-03-04 | 2027-04-07 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 0
FALSE |  | 83 | Install roof drains | Project2 | 2 | 2 | 2027-03-10 | 2027-03-11 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 59
FALSE |  | 116 | Tie-in fire line riser and set valves | Project2 | 10 | 10 | 2027-03-11 | 2027-03-24 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 90
FALSE |  | 89 | Pour lightweight concrete roof fill | Project2 | 2 | 2 | 2027-03-12 | 2027-03-15 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 59
FALSE |  | 91 | Spread stone ballast on seamless roof | Project2 | 5 | 5 | 2027-03-30 | 2027-04-05 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 59
FALSE |  | 92 | Set rooftop equipment | Project2 | 10 | 10 | 2027-04-06 | 2027-04-19 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 59
FALSE |  | 95 | Install interior stud walls and drywall | Project2 | 25 | 25 | 2027-04-08 | 2027-05-12 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 0
FALSE |  | 97 | Install store front doors and hardware | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 20
FALSE |  | 101 | Install conduit at ceiling plenum space | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 15
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45
FALSE |  | 130 | Install duct in building chase | Project2 | 15 | 15 | 2027-04-20 | 2027-05-10 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 71
FALSE |  | 121 | Rough-in electrical in drywall walls | Project2 | 20 | 20 | 2027-04-29 | 2027-05-26 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 30
FALSE |  | 117 | Set plumbing fixtures and trim | Project2 | 15 | 15 | 2027-05-06 | 2027-05-26 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 45
FALSE |  | 99 | Install millwork and wood trim | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 102 | Install duct in ceiling plenum space | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 133 | Install hard tile flooring in common areas | Project2 | 5 | 5 | 2027-05-13 | 2027-05-19 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 56
FALSE |  | 134 | Clean hard tile floors | Project2 | 4 | 4 | 2027-05-20 | 2027-05-25 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 56
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project2 | 15 | 15 | 2027-05-27 | 2027-06-16 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 15
FALSE |  | 96 | Install interior doors and hardware | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 0
FALSE |  | 103 | Install ceiling grid | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 10
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 64
FALSE |  | 100 | Paint walls and woodwork | Project2 | 20 | 20 | 2027-06-17 | 2027-07-14 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 0
FALSE |  | 104 | Install ceiling tile | Project2 | 10 | 10 | 2027-06-17 | 2027-06-30 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 30
FALSE |  | 123 | Install and terminate electrical devices | Project2 | 15 | 15 | 2027-06-17 | 2027-07-07 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 15
FALSE |  | 125 | Install light fixtures - test and clean | Project2 | 10 | 10 | 2027-07-08 | 2027-07-21 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 15
FALSE |  | 105 | Hang wallpaper | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 106 | Install building carpet | Project2 | 20 | 20 | 2027-07-15 | 2027-08-11 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 0
FALSE |  | 107 | Install hardware and accessories | Project2 | 15 | 15 | 2027-07-15 | 2027-08-04 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 5
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 7
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project2 | 2 | 2 | 2027-07-22 | 2027-07-23 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 17
FALSE |  | 131 | Set HVAC trim and test and balance system | Project2 | 20 | 20 | 2027-07-26 | 2027-08-20 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 17
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project2 | 10 | 10 | 2027-07-29 | 2027-08-11 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 7
FALSE |  | 135 | Remove debris from building and do final clean-up | Project2 | 4 | 4 | 2027-08-12 | 2027-08-17 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 0
FALSE |  | 136 | Substantial completion date | Project2 | 1 | 1 | 2027-08-18 | 2027-08-18 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 19
FALSE |  | 138 | Complete elevator inspection and certification | Project2 | 3 | 3 | 2027-08-18 | 2027-08-20 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 139 | Perform architect's inspection | Project2 | 1 | 1 | 2027-08-23 | 2027-08-23 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 0
FALSE |  | 140 | Perform local building agency inspection | Project2 | 1 | 1 | 2027-08-24 | 2027-08-24 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project2 | 1 | 1 | 2027-08-25 | 2027-08-25 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project2 | 10 | 10 | 2027-08-26 | 2027-09-08 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project2 | 2 | 2 | 2027-09-09 | 2027-09-10 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project2 | 1 | 1 | 2027-09-13 | 2027-09-13 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project2 | 1 | 1 | 2027-09-14 | 2027-09-14 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Maximum Lag
The largest successor lag value for the selected activity grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59
Hidden Duration
Number of activities that contain a lag that is bigger than 35% of its original duration
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59
Constraint
Number of activities with a constraint of any kind applied. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 25 | Clear and grub site | Project2 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
Start On Or After
Number of activities with a soft (one-way) constraint that forces the activity to start on or after a given date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 25 | Clear and grub site | Project2 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
Early Constraints
Number of activities with a soft (one-way) constraint that forces the activity to start or finish on or after a given date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 25 | Clear and grub site | Project2 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
Soft Constraints
Number of activities with soft or one-way constraints.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 25 | Clear and grub site | Project2 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project2 | 5 | 5 | 2026-07-06 | 2026-07-10 | 2026-04-30 | 2026-05-06 | Normal | Planned | 0 | 0
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
FALSE |  | 35 | Form column piers and spread foundations | Project2 | 4 | 4 | 2026-07-27 | 2026-07-30 | 2026-05-21 | 2026-05-26 | Normal | Planned | 0 | 0
FALSE |  | 38 | Set reinforcing and anchor bolts | Project2 | 4 | 4 | 2026-07-31 | 2026-08-05 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 0
FALSE |  | 39 | Pour column piers and foundations | Project2 | 5 | 5 | 2026-08-06 | 2026-08-12 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 0
FALSE |  | 42 | Cure piers and foundations | Project2 | 7 | 7 | 2026-08-13 | 2026-08-21 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 0
FALSE |  | 44 | Strip column piers and foundation forms | Project2 | 3 | 3 | 2026-08-24 | 2026-08-26 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 0
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project2 | 10 | 10 | 2026-08-27 | 2026-09-09 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 0
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-10 | 2026-09-23 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 0
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-24 | 2026-10-07 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 0
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project2 | 10 | 10 | 2026-10-08 | 2026-10-21 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 53 | Touch-up paint on steel | Project2 | 5 | 5 | 2026-10-22 | 2026-10-28 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 55 | Form 2nd floor including all floor openings | Project2 | 5 | 5 | 2026-10-29 | 2026-11-04 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 0
FALSE |  | 57 | Pour 2nd floor slab | Project2 | 4 | 4 | 2026-11-05 | 2026-11-10 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 58 | Cure 2nd floor slab | Project2 | 7 | 7 | 2026-11-11 | 2026-11-19 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 60 | Form 3rd floor including all floor openings | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 62 | Pour 3rd floor slab | Project2 | 4 | 4 | 2026-11-27 | 2026-12-02 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 63 | Cure 3rd floor slab | Project2 | 7 | 7 | 2026-12-03 | 2026-12-11 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 65 | Form roof slab including all floor openings | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 67 | Pour roof slab | Project2 | 4 | 4 | 2026-12-21 | 2026-12-24 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 0
FALSE |  | 68 | Cure roof slab | Project2 | 7 | 7 | 2026-12-25 | 2027-01-04 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 69 | Strip forms from roof slab | Project2 | 2 | 2 | 2027-01-05 | 2027-01-06 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 78 | Install exterior sheathing and metal studs | Project2 | 15 | 15 | 2027-01-07 | 2027-01-27 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 0
FALSE |  | 82 | Install exterior masonry work | Project2 | 25 | 25 | 2027-01-28 | 2027-03-03 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 0
FALSE |  | 94 | Install window wall aluminum and glass | Project2 | 25 | 25 | 2027-03-04 | 2027-04-07 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 0
FALSE |  | 95 | Install interior stud walls and drywall | Project2 | 25 | 25 | 2027-04-08 | 2027-05-12 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 0
FALSE |  | 96 | Install interior doors and hardware | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 0
FALSE |  | 100 | Paint walls and woodwork | Project2 | 20 | 20 | 2027-06-17 | 2027-07-14 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 0
FALSE |  | 106 | Install building carpet | Project2 | 20 | 20 | 2027-07-15 | 2027-08-11 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 0
FALSE |  | 135 | Remove debris from building and do final clean-up | Project2 | 4 | 4 | 2027-08-12 | 2027-08-17 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 0
FALSE |  | 138 | Complete elevator inspection and certification | Project2 | 3 | 3 | 2027-08-18 | 2027-08-20 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 139 | Perform architect's inspection | Project2 | 1 | 1 | 2027-08-23 | 2027-08-23 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 0
FALSE |  | 140 | Perform local building agency inspection | Project2 | 1 | 1 | 2027-08-24 | 2027-08-24 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project2 | 1 | 1 | 2027-08-25 | 2027-08-25 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project2 | 10 | 10 | 2027-08-26 | 2027-09-08 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 144 | Issue final completion documents including warranties | Project2 | 1 | 1 | 2027-09-13 | 2027-09-13 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project2 | 1 | 1 | 2027-09-14 | 2027-09-14 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project2 | 4 | 4 | 2026-07-29 | 2026-08-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 204
FALSE |  | 37 | Form elevator pit walls | Project2 | 4 | 4 | 2026-08-06 | 2026-08-11 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 203
FALSE |  | 40 | Pour concrete elevator walls | Project2 | 1 | 1 | 2026-08-13 | 2026-08-13 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 202
FALSE |  | 41 | Cure elevator wall concrete | Project2 | 7 | 7 | 2026-08-27 | 2026-09-04 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 202
FALSE |  | 43 | Strip wall forms | Project2 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 202
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project2 | 3 | 3 | 2026-09-08 | 2026-09-10 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 202
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-09-10 | 2026-09-16 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 35
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 202
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project2 | 10 | 10 | 2026-10-22 | 2026-11-04 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 144
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144
FALSE |  | 59 | Strip forms from 2nd floor slab | Project2 | 2 | 2 | 2026-11-27 | 2026-11-30 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 73
FALSE |  | 70 | Form 1st floor | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 73 | Install rebar and in-floor utilities | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144
FALSE |  | 127 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-03 | 2026-12-16 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 151
FALSE |  | 71 | Install electrical underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 72 | Install plumbing underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 74 | Pour 1st floor slab | Project2 | 4 | 4 | 2026-12-14 | 2026-12-17 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 73
FALSE |  | 64 | Strip forms from 3rd floor slab | Project2 | 2 | 2 | 2026-12-21 | 2026-12-22 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 11
FALSE |  | 75 | Cure 1st floor slab | Project2 | 7 | 7 | 2026-12-23 | 2026-12-31 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 73
FALSE |  | 112 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-31 | 2027-01-13 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 144
FALSE |  | 76 | Strip forms from 1st floor slab | Project2 | 2 | 2 | 2027-01-07 | 2027-01-08 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 73
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 93
FALSE |  | 120 | Rough-in electrical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 73
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 114
FALSE |  | 113 | Test and align doors and equipment | Project2 | 10 | 10 | 2027-01-14 | 2027-01-27 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 144
FALSE |  | 84 | Install tile in toilet rooms | Project2 | 10 | 10 | 2027-02-08 | 2027-02-19 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 93
FALSE |  | 86 | Clean toilet room tile | Project2 | 5 | 5 | 2027-02-22 | 2027-02-26 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 93
FALSE |  | 85 | Clean masonry | Project2 | 5 | 5 | 2027-03-04 | 2027-03-10 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 90
FALSE |  | 88 | Install flashing at parapet walls | Project2 | 4 | 4 | 2027-03-04 | 2027-03-09 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 61
FALSE |  | 83 | Install roof drains | Project2 | 2 | 2 | 2027-03-10 | 2027-03-11 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 59
FALSE |  | 116 | Tie-in fire line riser and set valves | Project2 | 10 | 10 | 2027-03-11 | 2027-03-24 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 90
FALSE |  | 89 | Pour lightweight concrete roof fill | Project2 | 2 | 2 | 2027-03-12 | 2027-03-15 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 59
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59
FALSE |  | 91 | Spread stone ballast on seamless roof | Project2 | 5 | 5 | 2027-03-30 | 2027-04-05 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 59
FALSE |  | 92 | Set rooftop equipment | Project2 | 10 | 10 | 2027-04-06 | 2027-04-19 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 59
FALSE |  | 97 | Install store front doors and hardware | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 20
FALSE |  | 101 | Install conduit at ceiling plenum space | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 15
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45
FALSE |  | 130 | Install duct in building chase | Project2 | 15 | 15 | 2027-04-20 | 2027-05-10 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 71
FALSE |  | 121 | Rough-in electrical in drywall walls | Project2 | 20 | 20 | 2027-04-29 | 2027-05-26 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 30
FALSE |  | 117 | Set plumbing fixtures and trim | Project2 | 15 | 15 | 2027-05-06 | 2027-05-26 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 45
FALSE |  | 99 | Install millwork and wood trim | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 102 | Install duct in ceiling plenum space | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 133 | Install hard tile flooring in common areas | Project2 | 5 | 5 | 2027-05-13 | 2027-05-19 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 56
FALSE |  | 134 | Clean hard tile floors | Project2 | 4 | 4 | 2027-05-20 | 2027-05-25 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 56
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project2 | 15 | 15 | 2027-05-27 | 2027-06-16 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 15
FALSE |  | 103 | Install ceiling grid | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 10
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 64
FALSE |  | 104 | Install ceiling tile | Project2 | 10 | 10 | 2027-06-17 | 2027-06-30 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 30
FALSE |  | 123 | Install and terminate electrical devices | Project2 | 15 | 15 | 2027-06-17 | 2027-07-07 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 15
FALSE |  | 125 | Install light fixtures - test and clean | Project2 | 10 | 10 | 2027-07-08 | 2027-07-21 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 15
FALSE |  | 105 | Hang wallpaper | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 107 | Install hardware and accessories | Project2 | 15 | 15 | 2027-07-15 | 2027-08-04 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 5
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 7
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project2 | 2 | 2 | 2027-07-22 | 2027-07-23 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 17
FALSE |  | 131 | Set HVAC trim and test and balance system | Project2 | 20 | 20 | 2027-07-26 | 2027-08-20 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 17
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project2 | 10 | 10 | 2027-07-29 | 2027-08-11 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 7
FALSE |  | 136 | Substantial completion date | Project2 | 1 | 1 | 2027-08-18 | 2027-08-18 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 19
FALSE |  | 143 | Obtain certificate of occupancy | Project2 | 2 | 2 | 2027-09-09 | 2027-09-10 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project2 | 5 | 5 | 2026-07-06 | 2026-07-10 | 2026-04-30 | 2026-05-06 | Normal | Planned | 0 | 0
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
FALSE |  | 35 | Form column piers and spread foundations | Project2 | 4 | 4 | 2026-07-27 | 2026-07-30 | 2026-05-21 | 2026-05-26 | Normal | Planned | 0 | 0
FALSE |  | 38 | Set reinforcing and anchor bolts | Project2 | 4 | 4 | 2026-07-31 | 2026-08-05 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 0
FALSE |  | 39 | Pour column piers and foundations | Project2 | 5 | 5 | 2026-08-06 | 2026-08-12 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 0
FALSE |  | 42 | Cure piers and foundations | Project2 | 7 | 7 | 2026-08-13 | 2026-08-21 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 0
FALSE |  | 44 | Strip column piers and foundation forms | Project2 | 3 | 3 | 2026-08-24 | 2026-08-26 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 0
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project2 | 10 | 10 | 2026-08-27 | 2026-09-09 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 0
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-10 | 2026-09-23 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 0
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-24 | 2026-10-07 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 0
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project2 | 10 | 10 | 2026-10-08 | 2026-10-21 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 53 | Touch-up paint on steel | Project2 | 5 | 5 | 2026-10-22 | 2026-10-28 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 55 | Form 2nd floor including all floor openings | Project2 | 5 | 5 | 2026-10-29 | 2026-11-04 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 0
FALSE |  | 57 | Pour 2nd floor slab | Project2 | 4 | 4 | 2026-11-05 | 2026-11-10 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 58 | Cure 2nd floor slab | Project2 | 7 | 7 | 2026-11-11 | 2026-11-19 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 60 | Form 3rd floor including all floor openings | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 62 | Pour 3rd floor slab | Project2 | 4 | 4 | 2026-11-27 | 2026-12-02 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 63 | Cure 3rd floor slab | Project2 | 7 | 7 | 2026-12-03 | 2026-12-11 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 65 | Form roof slab including all floor openings | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 67 | Pour roof slab | Project2 | 4 | 4 | 2026-12-21 | 2026-12-24 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 0
FALSE |  | 68 | Cure roof slab | Project2 | 7 | 7 | 2026-12-25 | 2027-01-04 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 69 | Strip forms from roof slab | Project2 | 2 | 2 | 2027-01-05 | 2027-01-06 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 78 | Install exterior sheathing and metal studs | Project2 | 15 | 15 | 2027-01-07 | 2027-01-27 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 0
FALSE |  | 82 | Install exterior masonry work | Project2 | 25 | 25 | 2027-01-28 | 2027-03-03 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 0
FALSE |  | 94 | Install window wall aluminum and glass | Project2 | 25 | 25 | 2027-03-04 | 2027-04-07 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 0
FALSE |  | 95 | Install interior stud walls and drywall | Project2 | 25 | 25 | 2027-04-08 | 2027-05-12 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 0
FALSE |  | 96 | Install interior doors and hardware | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 0
FALSE |  | 100 | Paint walls and woodwork | Project2 | 20 | 20 | 2027-06-17 | 2027-07-14 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 0
FALSE |  | 106 | Install building carpet | Project2 | 20 | 20 | 2027-07-15 | 2027-08-11 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 0
FALSE |  | 135 | Remove debris from building and do final clean-up | Project2 | 4 | 4 | 2027-08-12 | 2027-08-17 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 0
FALSE |  | 138 | Complete elevator inspection and certification | Project2 | 3 | 3 | 2027-08-18 | 2027-08-20 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 139 | Perform architect's inspection | Project2 | 1 | 1 | 2027-08-23 | 2027-08-23 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 0
FALSE |  | 140 | Perform local building agency inspection | Project2 | 1 | 1 | 2027-08-24 | 2027-08-24 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project2 | 1 | 1 | 2027-08-25 | 2027-08-25 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project2 | 10 | 10 | 2027-08-26 | 2027-09-08 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 144 | Issue final completion documents including warranties | Project2 | 1 | 1 | 2027-09-13 | 2027-09-13 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project2 | 1 | 1 | 2027-09-14 | 2027-09-14 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 64 | Strip forms from 3rd floor slab | Project2 | 2 | 2 | 2026-12-21 | 2026-12-22 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 11
FALSE |  | 97 | Install store front doors and hardware | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 20
FALSE |  | 101 | Install conduit at ceiling plenum space | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 15
FALSE |  | 99 | Install millwork and wood trim | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 102 | Install duct in ceiling plenum space | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project2 | 15 | 15 | 2027-05-27 | 2027-06-16 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 15
FALSE |  | 103 | Install ceiling grid | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 10
FALSE |  | 123 | Install and terminate electrical devices | Project2 | 15 | 15 | 2027-06-17 | 2027-07-07 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 15
FALSE |  | 125 | Install light fixtures - test and clean | Project2 | 10 | 10 | 2027-07-08 | 2027-07-21 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 15
FALSE |  | 105 | Hang wallpaper | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 107 | Install hardware and accessories | Project2 | 15 | 15 | 2027-07-15 | 2027-08-04 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 5
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 7
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project2 | 2 | 2 | 2027-07-22 | 2027-07-23 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 17
FALSE |  | 131 | Set HVAC trim and test and balance system | Project2 | 20 | 20 | 2027-07-26 | 2027-08-20 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 17
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project2 | 10 | 10 | 2027-07-29 | 2027-08-11 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 7
FALSE |  | 136 | Substantial completion date | Project2 | 1 | 1 | 2027-08-18 | 2027-08-18 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 19
FALSE |  | 143 | Obtain certificate of occupancy | Project2 | 2 | 2 | 2027-09-09 | 2027-09-10 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
20 to 30 days float
Total number of activities with positive float of more than 20 and less than or equal to 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 121 | Rough-in electrical in drywall walls | Project2 | 20 | 20 | 2027-04-29 | 2027-05-26 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 30
FALSE |  | 104 | Install ceiling tile | Project2 | 10 | 10 | 2027-06-17 | 2027-06-30 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 30
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project2 | 4 | 4 | 2026-07-29 | 2026-08-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 204
FALSE |  | 37 | Form elevator pit walls | Project2 | 4 | 4 | 2026-08-06 | 2026-08-11 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 203
FALSE |  | 40 | Pour concrete elevator walls | Project2 | 1 | 1 | 2026-08-13 | 2026-08-13 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 202
FALSE |  | 41 | Cure elevator wall concrete | Project2 | 7 | 7 | 2026-08-27 | 2026-09-04 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 202
FALSE |  | 43 | Strip wall forms | Project2 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 202
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project2 | 3 | 3 | 2026-09-08 | 2026-09-10 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 202
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-09-10 | 2026-09-16 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 35
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 202
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project2 | 10 | 10 | 2026-10-22 | 2026-11-04 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 144
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144
FALSE |  | 59 | Strip forms from 2nd floor slab | Project2 | 2 | 2 | 2026-11-27 | 2026-11-30 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 73
FALSE |  | 70 | Form 1st floor | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 73 | Install rebar and in-floor utilities | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144
FALSE |  | 127 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-03 | 2026-12-16 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 151
FALSE |  | 71 | Install electrical underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 72 | Install plumbing underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 74 | Pour 1st floor slab | Project2 | 4 | 4 | 2026-12-14 | 2026-12-17 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 73
FALSE |  | 75 | Cure 1st floor slab | Project2 | 7 | 7 | 2026-12-23 | 2026-12-31 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 73
FALSE |  | 112 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-31 | 2027-01-13 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 144
FALSE |  | 76 | Strip forms from 1st floor slab | Project2 | 2 | 2 | 2027-01-07 | 2027-01-08 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 73
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 93
FALSE |  | 120 | Rough-in electrical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 73
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 114
FALSE |  | 113 | Test and align doors and equipment | Project2 | 10 | 10 | 2027-01-14 | 2027-01-27 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 144
FALSE |  | 84 | Install tile in toilet rooms | Project2 | 10 | 10 | 2027-02-08 | 2027-02-19 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 93
FALSE |  | 86 | Clean toilet room tile | Project2 | 5 | 5 | 2027-02-22 | 2027-02-26 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 93
FALSE |  | 85 | Clean masonry | Project2 | 5 | 5 | 2027-03-04 | 2027-03-10 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 90
FALSE |  | 88 | Install flashing at parapet walls | Project2 | 4 | 4 | 2027-03-04 | 2027-03-09 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 61
FALSE |  | 83 | Install roof drains | Project2 | 2 | 2 | 2027-03-10 | 2027-03-11 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 59
FALSE |  | 116 | Tie-in fire line riser and set valves | Project2 | 10 | 10 | 2027-03-11 | 2027-03-24 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 90
FALSE |  | 89 | Pour lightweight concrete roof fill | Project2 | 2 | 2 | 2027-03-12 | 2027-03-15 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 59
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59
FALSE |  | 91 | Spread stone ballast on seamless roof | Project2 | 5 | 5 | 2027-03-30 | 2027-04-05 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 59
FALSE |  | 92 | Set rooftop equipment | Project2 | 10 | 10 | 2027-04-06 | 2027-04-19 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 59
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45
FALSE |  | 130 | Install duct in building chase | Project2 | 15 | 15 | 2027-04-20 | 2027-05-10 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 71
FALSE |  | 117 | Set plumbing fixtures and trim | Project2 | 15 | 15 | 2027-05-06 | 2027-05-26 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 45
FALSE |  | 133 | Install hard tile flooring in common areas | Project2 | 5 | 5 | 2027-05-13 | 2027-05-19 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 56
FALSE |  | 134 | Clean hard tile floors | Project2 | 4 | 4 | 2027-05-20 | 2027-05-25 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 56
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 64
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project2 | 4 | 4 | 2026-07-29 | 2026-08-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 204
FALSE |  | 37 | Form elevator pit walls | Project2 | 4 | 4 | 2026-08-06 | 2026-08-11 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 203
FALSE |  | 40 | Pour concrete elevator walls | Project2 | 1 | 1 | 2026-08-13 | 2026-08-13 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 202
FALSE |  | 41 | Cure elevator wall concrete | Project2 | 7 | 7 | 2026-08-27 | 2026-09-04 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 202
FALSE |  | 43 | Strip wall forms | Project2 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 202
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project2 | 3 | 3 | 2026-09-08 | 2026-09-10 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 202
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 202
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project2 | 10 | 10 | 2026-10-22 | 2026-11-04 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 144
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144
FALSE |  | 59 | Strip forms from 2nd floor slab | Project2 | 2 | 2 | 2026-11-27 | 2026-11-30 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 73
FALSE |  | 70 | Form 1st floor | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 73 | Install rebar and in-floor utilities | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144
FALSE |  | 127 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-03 | 2026-12-16 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 151
FALSE |  | 71 | Install electrical underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 72 | Install plumbing underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 74 | Pour 1st floor slab | Project2 | 4 | 4 | 2026-12-14 | 2026-12-17 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 73
FALSE |  | 75 | Cure 1st floor slab | Project2 | 7 | 7 | 2026-12-23 | 2026-12-31 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 73
FALSE |  | 112 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-31 | 2027-01-13 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 144
FALSE |  | 76 | Strip forms from 1st floor slab | Project2 | 2 | 2 | 2027-01-07 | 2027-01-08 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 73
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 93
FALSE |  | 120 | Rough-in electrical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 73
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 114
FALSE |  | 113 | Test and align doors and equipment | Project2 | 10 | 10 | 2027-01-14 | 2027-01-27 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 144
FALSE |  | 84 | Install tile in toilet rooms | Project2 | 10 | 10 | 2027-02-08 | 2027-02-19 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 93
FALSE |  | 86 | Clean toilet room tile | Project2 | 5 | 5 | 2027-02-22 | 2027-02-26 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 93
FALSE |  | 85 | Clean masonry | Project2 | 5 | 5 | 2027-03-04 | 2027-03-10 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 90
FALSE |  | 88 | Install flashing at parapet walls | Project2 | 4 | 4 | 2027-03-04 | 2027-03-09 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 61
FALSE |  | 83 | Install roof drains | Project2 | 2 | 2 | 2027-03-10 | 2027-03-11 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 59
FALSE |  | 116 | Tie-in fire line riser and set valves | Project2 | 10 | 10 | 2027-03-11 | 2027-03-24 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 90
FALSE |  | 89 | Pour lightweight concrete roof fill | Project2 | 2 | 2 | 2027-03-12 | 2027-03-15 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 59
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59
FALSE |  | 91 | Spread stone ballast on seamless roof | Project2 | 5 | 5 | 2027-03-30 | 2027-04-05 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 59
FALSE |  | 92 | Set rooftop equipment | Project2 | 10 | 10 | 2027-04-06 | 2027-04-19 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 59
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45
FALSE |  | 130 | Install duct in building chase | Project2 | 15 | 15 | 2027-04-20 | 2027-05-10 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 71
FALSE |  | 117 | Set plumbing fixtures and trim | Project2 | 15 | 15 | 2027-05-06 | 2027-05-26 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 45
FALSE |  | 133 | Install hard tile flooring in common areas | Project2 | 5 | 5 | 2027-05-13 | 2027-05-19 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 56
FALSE |  | 134 | Clean hard tile floors | Project2 | 4 | 4 | 2027-05-20 | 2027-05-25 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 56
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 64
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project2 | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project2 | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project2 | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project2 | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project2 | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project2 | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project2 | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project2 | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project2 | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project2 | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project2 | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project2 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project2 | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project2 | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project2 | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project2 | 5 | 5 | 2026-07-06 | 2026-07-10 | 2026-04-30 | 2026-05-06 | Normal | Planned | 0 | 0
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project2 | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project2 | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project2 | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project2 | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project2 | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project2 | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project2 | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project2 | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project2 | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project2 | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project2 | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project2 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project2 | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project2 | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project2 | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project2 | 5 | 5 | 2026-07-06 | 2026-07-10 | 2026-04-30 | 2026-05-06 | Normal | Planned | 0 | 0
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project2 | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project2 | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project2 | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project2 | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project2 | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project2 | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project2 | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project2 | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project2 | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project2 | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project2 | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project2 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project2 | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project2 | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project2 | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0

## Project5_TAMPERED2
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View | Project5_TAMPERED: Detailed View
1. Logic
Number of activities that are missing a predecessor, a successor or both. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
3. Lags
Number of lags in the schedule.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
5. Hard Constraint
Number of activities with hard or two-way constraints. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
6. High Float
Number of activities with total float greater than 2 months. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
11. Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
Total Activities
The total number of activities within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 2 | General Conditions | Project5_TAMPERED | 46 | 0 | 2026-03-02 | 2026-05-04 | 2026-03-02 | 2026-04-01 | Summary | Complete | 100 | 0
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 18 | Mobilize on Site | Project5_TAMPERED | 17 | 0 | 2026-03-05 | 2026-03-27 | 2026-03-05 | 2026-03-18 | Summary | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 10 | Long Lead Procurement | Project5_TAMPERED | 76 | 0 | 2026-03-06 | 2026-06-19 | 2026-03-06 | 2026-06-11 | Summary | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 24 | Site Grading and Utilities | Project5_TAMPERED | 85 | 0 | 2026-04-06 | 2026-07-31 | 2026-03-19 | 2026-05-06 | Summary | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 32 | Foundations | Project5_TAMPERED | 92 | 66 | 2026-08-03 | 2026-12-08 | 2026-05-07 | 2026-07-08 | Summary | InProgress | 28 | 256
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 47 | Steel Erection | Project5_TAMPERED | 74 | 74 | 2026-11-09 | 2027-02-18 | 2026-06-23 | 2026-08-31 | Summary | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 54 | Form and Pour Concrete - Floors and Roof | Project5_TAMPERED | 89 | 89 | 2026-12-16 | 2027-04-19 | 2026-07-07 | 2026-11-04 | Summary | Planned | 0 | 44
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 79 | Masonry Work | Project5_TAMPERED | 86 | 86 | 2027-02-19 | 2027-06-18 | 2026-09-01 | 2027-01-05 | Summary | Planned | 0 | 74
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 110 | Elevators | Project5_TAMPERED | 40 | 40 | 2027-03-19 | 2027-05-13 | 2026-09-29 | 2026-11-23 | Summary | Planned | 0 | 184
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 126 | Heating and Ventilating - AC | Project5_TAMPERED | 210 | 210 | 2027-03-19 | 2028-01-06 | 2026-09-29 | 2027-06-16 | Summary | Planned | 0 | 14
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 77 | Carpentry Work | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Summary | Planned | 0 | 19
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 119 | Electrical | Project5_TAMPERED | 140 | 140 | 2027-04-20 | 2027-11-01 | 2026-11-05 | 2027-05-19 | Summary | Planned | 0 | 38
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 87 | Roofing | Project5_TAMPERED | 33 | 33 | 2027-06-11 | 2027-07-27 | 2026-12-29 | 2027-02-11 | Summary | Planned | 0 | 80
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 93 | Window wall and store front closures | Project5_TAMPERED | 75 | 75 | 2027-06-11 | 2027-09-23 | 2026-12-29 | 2027-04-12 | Summary | Planned | 0 | 19
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 114 | Plumbing | Project5_TAMPERED | 100 | 100 | 2027-06-18 | 2027-11-04 | 2027-01-05 | 2027-05-24 | Summary | Planned | 0 | 35
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 98 | Building Finishes | Project5_TAMPERED | 111 | 111 | 2027-07-16 | 2027-12-17 | 2027-02-02 | 2027-06-07 | Summary | Planned | 0 | 28
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 132 | Final Clean-up and Occupancy | Project5_TAMPERED | 76 | 76 | 2027-08-20 | 2027-12-03 | 2027-03-09 | 2027-06-14 | Summary | Planned | 0 | 38
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 137 | Complete Final Inspections | Project5_TAMPERED | 6 | 6 | 2027-12-03 | 2027-12-10 | 2027-06-14 | 2027-06-21 | Summary | Planned | 0 | 19
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Normal
Number of normal activities within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Summaries
Number of summary activities within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 2 | General Conditions | Project5_TAMPERED | 46 | 0 | 2026-03-02 | 2026-05-04 | 2026-03-02 | 2026-04-01 | Summary | Complete | 100 | 0
FALSE |  | 18 | Mobilize on Site | Project5_TAMPERED | 17 | 0 | 2026-03-05 | 2026-03-27 | 2026-03-05 | 2026-03-18 | Summary | Complete | 100 | 0
FALSE |  | 10 | Long Lead Procurement | Project5_TAMPERED | 76 | 0 | 2026-03-06 | 2026-06-19 | 2026-03-06 | 2026-06-11 | Summary | Complete | 100 | 0
FALSE |  | 24 | Site Grading and Utilities | Project5_TAMPERED | 85 | 0 | 2026-04-06 | 2026-07-31 | 2026-03-19 | 2026-05-06 | Summary | Complete | 100 | 0
FALSE |  | 32 | Foundations | Project5_TAMPERED | 92 | 66 | 2026-08-03 | 2026-12-08 | 2026-05-07 | 2026-07-08 | Summary | InProgress | 28 | 256
FALSE |  | 47 | Steel Erection | Project5_TAMPERED | 74 | 74 | 2026-11-09 | 2027-02-18 | 2026-06-23 | 2026-08-31 | Summary | Planned | 0 | 19
FALSE |  | 54 | Form and Pour Concrete - Floors and Roof | Project5_TAMPERED | 89 | 89 | 2026-12-16 | 2027-04-19 | 2026-07-07 | 2026-11-04 | Summary | Planned | 0 | 44
FALSE |  | 79 | Masonry Work | Project5_TAMPERED | 86 | 86 | 2027-02-19 | 2027-06-18 | 2026-09-01 | 2027-01-05 | Summary | Planned | 0 | 74
FALSE |  | 110 | Elevators | Project5_TAMPERED | 40 | 40 | 2027-03-19 | 2027-05-13 | 2026-09-29 | 2026-11-23 | Summary | Planned | 0 | 184
FALSE |  | 126 | Heating and Ventilating - AC | Project5_TAMPERED | 210 | 210 | 2027-03-19 | 2028-01-06 | 2026-09-29 | 2027-06-16 | Summary | Planned | 0 | 14
FALSE |  | 77 | Carpentry Work | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Summary | Planned | 0 | 19
FALSE |  | 119 | Electrical | Project5_TAMPERED | 140 | 140 | 2027-04-20 | 2027-11-01 | 2026-11-05 | 2027-05-19 | Summary | Planned | 0 | 38
FALSE |  | 87 | Roofing | Project5_TAMPERED | 33 | 33 | 2027-06-11 | 2027-07-27 | 2026-12-29 | 2027-02-11 | Summary | Planned | 0 | 80
FALSE |  | 93 | Window wall and store front closures | Project5_TAMPERED | 75 | 75 | 2027-06-11 | 2027-09-23 | 2026-12-29 | 2027-04-12 | Summary | Planned | 0 | 19
FALSE |  | 114 | Plumbing | Project5_TAMPERED | 100 | 100 | 2027-06-18 | 2027-11-04 | 2027-01-05 | 2027-05-24 | Summary | Planned | 0 | 35
FALSE |  | 98 | Building Finishes | Project5_TAMPERED | 111 | 111 | 2027-07-16 | 2027-12-17 | 2027-02-02 | 2027-06-07 | Summary | Planned | 0 | 28
FALSE |  | 132 | Final Clean-up and Occupancy | Project5_TAMPERED | 76 | 76 | 2027-08-20 | 2027-12-03 | 2027-03-09 | 2027-06-14 | Summary | Planned | 0 | 38
FALSE |  | 137 | Complete Final Inspections | Project5_TAMPERED | 6 | 6 | 2027-12-03 | 2027-12-10 | 2027-06-14 | 2027-06-21 | Summary | Planned | 0 | 19
Longest Path
Activities that together form the longest path through to project completion.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Rem. Critical Duration
The amount of remaining time planned in order to complete all critical normal activities and milestones within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Rem. Non-Critical Duration
The amount of remaining time planned in order to complete all non-critical normal activities and milestones within a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
Lags
Total number of activities with positive lags.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
Minimum Lag
The smallest successor lag value for the selected activity grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Maximum Lag
The largest successor lag value for the selected activity grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
Hidden Duration
Number of activities that contain a lag that is bigger than 35% of its original duration
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
Constraint
Number of activities with a constraint of any kind applied. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Mandatory Start
Number of activities with a hard (two-way) constraint that forces the activity to start on a specific date, overriding CPM calculations.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Start On Or After
Number of activities with a soft (one-way) constraint that forces the activity to start on or after a given date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Early Constraints
Number of activities with a soft (one-way) constraint that forces the activity to start or finish on or after a given date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Total Float Constraints
Number of activities with both a mandatory start and finish constraint applied.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Soft Constraints
Number of activities with soft or one-way constraints.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
Hard Constraints
Number of activities with hard or two-way constraints.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_TAMPERED | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project5_TAMPERED | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 144 | Issue final completion documents including warranties | Project5_TAMPERED | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project5_TAMPERED | 1 | 1 | 2028-01-26 | 2028-01-26 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_TAMPERED | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 19
FALSE |  | 57 | Pour 2nd floor slab | Project5_TAMPERED | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 19
FALSE |  | 58 | Cure 2nd floor slab | Project5_TAMPERED | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 19
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 19
FALSE |  | 62 | Pour 3rd floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 19
FALSE |  | 63 | Cure 3rd floor slab | Project5_TAMPERED | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 19
FALSE |  | 65 | Form roof slab including all floor openings | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 19
FALSE |  | 67 | Pour roof slab | Project5_TAMPERED | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 19
FALSE |  | 68 | Cure roof slab | Project5_TAMPERED | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 19
FALSE |  | 69 | Strip forms from roof slab | Project5_TAMPERED | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 19
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_TAMPERED | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 19
FALSE |  | 82 | Install exterior masonry work | Project5_TAMPERED | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 19
FALSE |  | 94 | Install window wall aluminum and glass | Project5_TAMPERED | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 19
FALSE |  | 95 | Install interior stud walls and drywall | Project5_TAMPERED | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 19
FALSE |  | 96 | Install interior doors and hardware | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 19
FALSE |  | 100 | Paint walls and woodwork | Project5_TAMPERED | 20 | 20 | 2027-09-24 | 2027-10-21 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 19
FALSE |  | 107 | Install hardware and accessories | Project5_TAMPERED | 26 | 26 | 2027-10-22 | 2027-11-26 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 19
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_TAMPERED | 4 | 4 | 2027-11-29 | 2027-12-02 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 19
FALSE |  | 138 | Complete elevator inspection and certification | Project5_TAMPERED | 3 | 3 | 2027-12-03 | 2027-12-07 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 19
FALSE |  | 139 | Perform architect's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-08 | 2027-12-08 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 19
FALSE |  | 140 | Perform local building agency inspection | Project5_TAMPERED | 1 | 1 | 2027-12-09 | 2027-12-09 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 19
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_TAMPERED | 1 | 1 | 2027-12-10 | 2027-12-10 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 19
FALSE |  | 143 | Obtain certificate of occupancy | Project5_TAMPERED | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
20 to 30 days float
Total number of activities with positive float of more than 20 and less than or equal to 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-30 | 2027-03-31 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 30
FALSE |  | 99 | Install millwork and wood trim | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 106 | Install building carpet | Project5_TAMPERED | 41 | 41 | 2027-10-22 | 2027-12-17 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 28
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 97 | Install store front doors and hardware | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 39
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 36
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_TAMPERED | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 35
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_TAMPERED | 15 | 15 | 2027-09-03 | 2027-09-23 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 36
FALSE |  | 103 | Install ceiling grid | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 35
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 123 | Install and terminate electrical devices | Project5_TAMPERED | 15 | 15 | 2027-09-24 | 2027-10-14 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 36
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_TAMPERED | 2 | 2 | 2027-10-15 | 2027-10-18 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 38
FALSE |  | 125 | Install light fixtures - test and clean | Project5_TAMPERED | 10 | 10 | 2027-10-19 | 2027-11-01 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 38
FALSE |  | 105 | Hang wallpaper | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 32
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_TAMPERED | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 35
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_TAMPERED | 10 | 10 | 2027-11-05 | 2027-11-18 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 32
FALSE |  | 136 | Substantial completion date | Project5_TAMPERED | 1 | 1 | 2027-12-03 | 2027-12-03 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 38
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_TAMPERED | 27 | 27 | 2027-01-13 | 2027-02-18 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 156
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_TAMPERED | 20 | 20 | 2027-02-19 | 2027-03-18 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 156
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_TAMPERED | 2 | 2 | 2027-03-08 | 2027-03-09 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 95
FALSE |  | 70 | Form 1st floor | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_TAMPERED | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 100
FALSE |  | 71 | Install electrical underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 72 | Install plumbing underground | Project5_TAMPERED | 5 | 5 | 2027-03-16 | 2027-03-22 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 95
FALSE |  | 111 | Set elevator equipment in shafts | Project5_TAMPERED | 20 | 20 | 2027-03-19 | 2027-04-15 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 184
FALSE |  | 127 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-03-19 | 2027-04-01 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 156
FALSE |  | 74 | Pour 1st floor slab | Project5_TAMPERED | 4 | 4 | 2027-03-23 | 2027-03-26 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 95
FALSE |  | 75 | Cure 1st floor slab | Project5_TAMPERED | 7 | 7 | 2027-04-01 | 2027-04-09 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 95
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_TAMPERED | 2 | 2 | 2027-04-16 | 2027-04-19 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 94
FALSE |  | 112 | Set equipment in mechanical room | Project5_TAMPERED | 10 | 10 | 2027-04-16 | 2027-04-29 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 184
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 118
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 94
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_TAMPERED | 20 | 20 | 2027-04-20 | 2027-05-17 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 124
FALSE |  | 113 | Test and align doors and equipment | Project5_TAMPERED | 10 | 10 | 2027-04-30 | 2027-05-13 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 184
FALSE |  | 84 | Install tile in toilet rooms | Project5_TAMPERED | 10 | 10 | 2027-05-18 | 2027-05-31 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 118
FALSE |  | 86 | Clean toilet room tile | Project5_TAMPERED | 5 | 5 | 2027-06-01 | 2027-06-07 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 118
FALSE |  | 85 | Clean masonry | Project5_TAMPERED | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_TAMPERED | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 82
FALSE |  | 83 | Install roof drains | Project5_TAMPERED | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 80
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_TAMPERED | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_TAMPERED | 2 | 2 | 2027-06-21 | 2027-06-22 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 80
FALSE |  | 90 | Install seamless roofing material | Project5_TAMPERED | 5 | 5 | 2027-06-30 | 2027-07-06 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 80
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_TAMPERED | 5 | 5 | 2027-07-07 | 2027-07-13 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 80
FALSE |  | 92 | Set rooftop equipment | Project5_TAMPERED | 10 | 10 | 2027-07-14 | 2027-07-27 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 80
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 130 | Install duct in building chase | Project5_TAMPERED | 15 | 15 | 2027-07-28 | 2027-08-17 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 82
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_TAMPERED | 20 | 20 | 2027-08-06 | 2027-09-02 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 51
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_TAMPERED | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_TAMPERED | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 134 | Clean hard tile floors | Project5_TAMPERED | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_TAMPERED | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 89
FALSE |  | 104 | Install ceiling tile | Project5_TAMPERED | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
HMI - Total Tasks
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
HMI - Complete Tasks
The total number of tasks that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
HMI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
HMI - Complete Tasks (adjusted)
The total number of tasks that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date). Gives credit for tasks baselined in the future that completed during the given status period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
CEI - Total Tasks
The number of tasks forecasted in the previous month's schedule (based on the prior schedule's status date) to be completed in the current month (time between prior schedule's satus date and current schedule's status date).
Excluded | Notes | DRM | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1 | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 4.3 | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 1.9 | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 1 | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 1 | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 4 | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 0.5 | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 7 | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 2.25 | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 0 | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 0 | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 0 | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 0 | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 0 | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 0 | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 0 | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
CEI - Complete Tasks
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Excluded | Notes | DRM | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1 | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 4.3 | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 1.9 | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 1 | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 1 | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 4 | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 0.5 | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
CEI - Incomplete Tasks
The number of tasks that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
CEI - Complete Tasks (adjusted)
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date). Takes credit for future-planned activities that were completed within the measured timeframe.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0

## Phase Analysis
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
 | time axis 2025-12-28 to 2028-03-26
Phase Analyzer | Critical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 4 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | Non-Critical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 1 | 1 | 4 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 1 | 2 | 6 | 4 | 3 | 3 | 3 | 2 | 5 | 4 | 4 | 3 | 1 | 1 | 1 | 2 | 5 | 2 | 2 | 2 | 5 | 4 | 5 | 5 | 4 | 6 | 6 | 6 | 5 | 3 | 5 | 2 | 2 | 2 | 5 | 6 | 6 | 3 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | Negative Float | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | Zero Days Float | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | 0 to 20 Days Float | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 1 | 0 | 2 | 3 | 1 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | 20 to 30 days float | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | More than 30 days float | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 2 | 1 | 1 | 0 | 1 | 3 | 0 | 1 | 1 | 0 | 3 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | High Float | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 2 | 1 | 1 | 0 | 1 | 3 | 0 | 1 | 1 | 0 | 3 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | Avg Float | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 263 | N/A | N/A | 47 | N/A | 0 | 0 | N/A | 0 | 102 | 102 | 135 | 0 | 0 | 202 | 152 | 35 | 0 | N/A | 0 | N/A | 0 | 0 | 72 | 0 | 0 | 0 | 75 | 49 | 56 | 6 | 109 | 24 | 144 | N/A | 72 | 93 | N/A | 93 | 93 | 0 | 70 | 59 | 90 | 59 | 30 | N/A | 59 | 18 | 45 | 36 | 56 | 44 | 10 | N/A | 22 | N/A | 30 | 15 | 0 | 16 | 9 | 5 | 4 | 9 | 0 | N/A | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Max Float | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 263 | N/A | N/A | 93 | N/A | 0 | 0 | N/A | 0 | 204 | 204 | 203 | 0 | 0 | 202 | 202 | 35 | 0 | N/A | 0 | N/A | 0 | 0 | 144 | 0 | 0 | 0 | 144 | 73 | 151 | 11 | 144 | 73 | 144 | N/A | 144 | 114 | N/A | 93 | 93 | 0 | 90 | 59 | 90 | 59 | 59 | N/A | 59 | 20 | 45 | 71 | 56 | 56 | 10 | N/A | 64 | N/A | 30 | 15 | 0 | 17 | 10 | 5 | 7 | 19 | 0 | N/A | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Float Ratio™ | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 17.53 | 0 | 0 | 9.4 | 0 | 0 | 0 | 0 | 0 | 20.4 | 25.5 | 50.63 | 0 | 0 | 20.2 | 50.5 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 14.4 | 0 | 0 | 0 | 17.76 | 5.84 | 10.18 | 0.73 | 15.5 | 6.08 | 5.76 | 0 | 6.26 | 14 | 0 | 9.3 | 9.3 | 0 | 14 | 5.36 | 7.5 | 5.9 | 3.69 | 0 | 2.36 | 1.52 | 2.25 | 3.55 | 2.24 | 6.55 | 1.18 | 0 | 4.94 | 0 | 2.31 | 1.5 | 0 | 1.07 | 1.04 | 0.28 | 0.54 | 3.27 | 0 | 0 | 0.2 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Value Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.75 | N/A | 0.5 | 0.5 | N/A | 0.25 | 0 | 0 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Total Tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 6 | 8 | 6 | 10 | 4 | 0 | 2 | 2 | 0 | 4 | 2 | 2 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | BEI - Complete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 8 | 4 | 6 | 8 | 6 | 8 | 3 | N/A | 1 | 1 | N/A | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Incomplete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 2 | 1 | N/A | 1 | 1 | N/A | 3 | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | N/A | 1 | N/A | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Value Tasks (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 1 | 1 | 1 | 1 | 0.8 | 0.75 | N/A | 0.5 | 0.5 | N/A | 0.25 | 0 | 0 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Complete Tasks (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 8 | 4 | 6 | 8 | 6 | 8 | 3 | N/A | 1 | 1 | N/A | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Complete Future Tasks (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Status Date | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Value Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Total Milestones | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | BEI - Complete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Incomplete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Value Milestones (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Complete Milestones (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Complete Future Milestones (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Status Date | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Value Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Total Tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 1 | 1 | 2 | 3 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | HMI - Complete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Completed Early Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Incomplete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 1 | N/A | 1 | N/A | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Value Tasks (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Complete Tasks (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Complete Future Tasks (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Status Date | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Value Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Total Milestones | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | HMI - Complete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Completed Early Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Incomplete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Value Milestones (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Complete Milestones (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Complete Future Milestones (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Status Date | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Value Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Total Tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | CEI - Complete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Incomplete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Value Tasks (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Complete Tasks (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Complete Future Tasks (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Status Date | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | New Activity - Created | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | New Activity - Already Finished | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | New Activity - Finished in Status Period | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Value Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Total Milestones | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | CEI - Complete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Incomplete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Value Milestones (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Complete Milestones (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Complete Future Milestones (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Status Date | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | 2026-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
 | time axis 2025-12-28 to 2028-03-26
Phase Analyzer | Critical | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 50% | 50% | 33% | 33% | 33% | 33% | 50% | 33% | 33% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 50% | 100% | 67% | 50% | 33% | 50% | 100% | 100% | 100% | 100% | 67% | 67% | 50% | 67% | 75% | 60% | 25% | 20% | 40% | 40% | 25% | 60% | 17% | 20% | 33% | 25% | 50% | 50% | 50% | 50% | 17% | 33% | 33% | 33% | 29% | 20% | 17% | 17% | 20% | 14% | 0% | 0% | 17% | 25% | 29% | 33% | 33% | 33% | 29% | 14% | 14% | 25% | 50% | 50% | 100% | 100% | 50% | 100% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Phase Analyzer | Non-Critical | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | 100% | 100% | 100% | 50% | 50% | 67% | 67% | 67% | 67% | 50% | 67% | 67% | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 0% | 33% | 50% | 67% | 50% | 0% | 0% | 0% | 0% | 33% | 33% | 50% | 33% | 25% | 40% | 75% | 80% | 60% | 60% | 75% | 40% | 83% | 80% | 67% | 75% | 50% | 50% | 50% | 50% | 83% | 67% | 67% | 67% | 71% | 80% | 83% | 83% | 80% | 86% | 100% | 100% | 83% | 75% | 71% | 67% | 67% | 67% | 71% | 86% | 86% | 75% | 50% | 50% | 0% | 0% | 50% | 0% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Phase Analyzer | Negative Float | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | ( N/A ) | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Phase Analyzer | Zero Days Float | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 33% | ( N/A ) | 100% | 100% | ( N/A ) | 100% | 50% | 50% | 33% | 100% | 100% | 0% | 25% | 0% | 100% | ( N/A ) | 100% | ( N/A ) | 100% | 100% | 50% | 100% | 100% | 100% | 20% | 33% | 50% | 50% | 0% | 67% | 0% | ( N/A ) | 50% | 0% | ( N/A ) | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 50% | ( N/A ) | 0% | 0% | 0% | 50% | 0% | 0% | 0% | ( N/A ) | 25% | ( N/A ) | 0% | 0% | 100% | 0% | 0% | 0% | 50% | 50% | 100% | ( N/A ) | 50% | 100% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Phase Analyzer | 0 to 20 Days Float | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | ( N/A ) | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 100% | 0% | 0% | 0% | 0% | 100% | ( N/A ) | 50% | ( N/A ) | 0% | 100% | 0% | 100% | 100% | 100% | 50% | 50% | 0% | ( N/A ) | 50% | 0% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Phase Analyzer | 20 to 30 days float | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | ( N/A ) | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 33% | 0% | ( N/A ) | 0% | ( N/A ) | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Phase Analyzer | More than 30 days float | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | 100% | ( N/A ) | ( N/A ) | 67% | ( N/A ) | 0% | 0% | ( N/A ) | 0% | 50% | 50% | 67% | 0% | 0% | 100% | 75% | 100% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 50% | 0% | 0% | 0% | 80% | 67% | 50% | 0% | 100% | 33% | 100% | ( N/A ) | 50% | 100% | ( N/A ) | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 50% | ( N/A ) | 100% | 0% | 100% | 50% | 100% | 67% | 0% | ( N/A ) | 25% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Phase Analyzer | High Float | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | 100% | ( N/A ) | ( N/A ) | 67% | ( N/A ) | 0% | 0% | ( N/A ) | 0% | 50% | 50% | 67% | 0% | 0% | 100% | 75% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 50% | 0% | 0% | 0% | 80% | 67% | 50% | 0% | 100% | 33% | 100% | ( N/A ) | 50% | 100% | ( N/A ) | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 50% | ( N/A ) | 100% | 0% | 100% | 50% | 100% | 67% | 0% | ( N/A ) | 25% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A )
Phase Analyzer | Avg Float
Phase Analyzer | Max Float
Phase Analyzer | Float Ratio™
Phase Analyzer | BEI - Value Tasks | bar: 2026-03-01 to 2026-04-12; 2026-04-26 to 2026-05-03; 2026-05-17 to 2026-07-19; 2026-08-02; 2026-08-16 to 2026-08-23
Phase Analyzer | BEI - Total Tasks
Phase Analyzer | BEI - Complete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 80% | 75% | N/A | 50% | 50% | N/A | 25% | 0% | 0% | 33% | 0% | 0% | 0% | 0% | 0% | 0% | N/A | 0% | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Incomplete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | 0% | 0% | 0% | 20% | 25% | N/A | 50% | 50% | N/A | 75% | 100% | 100% | 67% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | N/A | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Value Tasks (adjusted) | bar: 2026-03-01 to 2026-04-12; 2026-04-26 to 2026-05-03; 2026-05-17 to 2026-07-19; 2026-08-02; 2026-08-16 to 2026-08-23
Phase Analyzer | BEI - Complete Tasks (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 80% | 75% | N/A | 50% | 50% | N/A | 25% | 0% | 0% | 33% | 0% | 0% | 0% | 0% | 0% | 0% | N/A | 0% | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Complete Future Tasks (adjusted)
Phase Analyzer | Status Date
Phase Analyzer | BEI - Value Milestones
Phase Analyzer | BEI - Total Milestones
Phase Analyzer | BEI - Complete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Incomplete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Value Milestones (adjusted)
Phase Analyzer | BEI - Complete Milestones (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | BEI - Complete Future Milestones (adjusted)
Phase Analyzer | Status Date
Phase Analyzer | HMI - Value Tasks | bar: 2026-05-24 to 2026-07-19; 2026-08-02; 2026-08-16 to 2026-08-23
Phase Analyzer | HMI - Total Tasks
Phase Analyzer | HMI - Complete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | 33% | 0% | 0% | 0% | 0% | 0% | 0% | N/A | 0% | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Completed Early Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | N/A | 0% | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Incomplete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100% | 100% | 67% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | N/A | 100% | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Value Tasks (adjusted) | bar: 2026-05-24 to 2026-07-19; 2026-08-02; 2026-08-16 to 2026-08-23
Phase Analyzer | HMI - Complete Tasks (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0% | 0% | 33% | 0% | 0% | 0% | 0% | 0% | 0% | N/A | 0% | N/A | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Complete Future Tasks (adjusted)
Phase Analyzer | Status Date
Phase Analyzer | HMI - Value Milestones
Phase Analyzer | HMI - Total Milestones
Phase Analyzer | HMI - Complete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Completed Early Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Incomplete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Value Milestones (adjusted)
Phase Analyzer | HMI - Complete Milestones (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | HMI - Complete Future Milestones (adjusted)
Phase Analyzer | Status Date
Phase Analyzer | CEI - Value Tasks
Phase Analyzer | CEI - Total Tasks
Phase Analyzer | CEI - Complete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Incomplete Tasks | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Value Tasks (adjusted)
Phase Analyzer | CEI - Complete Tasks (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Complete Future Tasks (adjusted)
Phase Analyzer | Status Date
Phase Analyzer | New Activity - Created
Phase Analyzer | New Activity - Already Finished
Phase Analyzer | New Activity - Finished in Status Period
Phase Analyzer | CEI - Value Milestones
Phase Analyzer | CEI - Total Milestones
Phase Analyzer | CEI - Complete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Incomplete Milestones | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Value Milestones (adjusted)
Phase Analyzer | CEI - Complete Milestones (adjusted) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | CEI - Complete Future Milestones (adjusted)
Phase Analyzer | Status Date

## 3-1-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
3/1/2026: Detailed View | 3/1/2026: Detailed View | 3/1/2026: Detailed View | 3/1/2026: Detailed View
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project2 | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project2 | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project2 | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project2 | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project2 | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project2 | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project2 | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_TAMPERED | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_TAMPERED | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_TAMPERED | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0

## 3-8-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
3/8/2026: Detailed View | 3/8/2026: Detailed View | 3/8/2026: Detailed View | 3/8/2026: Detailed View
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7 | Obtain building permits | Project2 | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project2 | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7 | Obtain building permits | Project2 | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project2 | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7 | Obtain building permits | Project2 | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project2 | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_TAMPERED | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_TAMPERED | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0

## 3-15-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
3/15/2026: Detailed View | 3/15/2026: Detailed View | 3/15/2026: Detailed View | 3/15/2026: Detailed View
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project2 | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project2 | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project2 | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project2 | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project2 | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project2 | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project2 | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project2 | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project2 | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_TAMPERED | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_TAMPERED | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_TAMPERED | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0

## 3-22-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
3/22/2026: Detailed View | 3/22/2026: Detailed View | 3/22/2026: Detailed View | 3/22/2026: Detailed View
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 4 | Submit bond and insurance documents | Project2 | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project2 | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project2 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 4 | Submit bond and insurance documents | Project2 | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project2 | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project2 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 4 | Submit bond and insurance documents | Project2 | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project2 | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project2 | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project2 | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_TAMPERED | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_TAMPERED | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_TAMPERED | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_TAMPERED | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0

## 3-29-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
3/29/2026: Detailed View | 3/29/2026: Detailed View | 3/29/2026: Detailed View | 3/29/2026: Detailed View | 3/29/2026: Detailed View
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5 | Prepare and submit project schedule | Project2 | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project2 | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project2 | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5 | Prepare and submit project schedule | Project2 | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project2 | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project2 | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 5 | Prepare and submit project schedule | Project2 | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project2 | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project2 | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_TAMPERED | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_TAMPERED | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_TAMPERED | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0

## 4-5-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
4/5/2026: Detailed View | 4/5/2026: Detailed View | 4/5/2026: Detailed View | 4/5/2026: Detailed View | 4/5/2026: Detailed View | 4/5/2026: Detailed View
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project2 | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project2 | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project2 | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project2 | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_TAMPERED | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_TAMPERED | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_TAMPERED | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_TAMPERED | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0

## 4-12-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
4/12/2026: Detailed View | 4/12/2026: Detailed View | 4/12/2026: Detailed View | 4/12/2026: Detailed View | 4/12/2026: Detailed View | 4/12/2026: Detailed View
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 28 | Install storm drainage | Project2 | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 28 | Install storm drainage | Project2 | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 28 | Install storm drainage | Project2 | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_TAMPERED | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_TAMPERED | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0

## 4-19-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
4/19/2026: Detailed View | 4/19/2026: Detailed View | 4/19/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48

## 4-26-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
4/26/2026: Detailed View | 4/26/2026: Detailed View | 4/26/2026: Detailed View | 4/26/2026: Detailed View | 4/26/2026: Detailed View | 4/26/2026: Detailed View | 4/26/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project5_TAMPERED | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0

## 5-3-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
5/3/2026: Detailed View | 5/3/2026: Detailed View | 5/3/2026: Detailed View | 5/3/2026: Detailed View | 5/3/2026: Detailed View | 5/3/2026: Detailed View | 5/3/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 31 | Erect building batter boards and layout building | Project2 | 5 | 5 | 2026-07-06 | 2026-07-10 | 2026-04-30 | 2026-05-06 | Normal | Planned | 0 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 31 | Erect building batter boards and layout building | Project2 | 5 | 5 | 2026-07-06 | 2026-07-10 | 2026-04-30 | 2026-05-06 | Normal | Planned | 0 | 0
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 31 | Erect building batter boards and layout building | Project5_TAMPERED | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0

## 5-10-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
5/10/2026: Detailed View | 5/10/2026: Detailed View | 5/10/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263

## 5-17-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
5/17/2026: Detailed View | 5/17/2026: Detailed View | 5/17/2026: Detailed View | 5/17/2026: Detailed View | 5/17/2026: Detailed View | 5/17/2026: Detailed View | 5/17/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
FALSE |  | 34 | Excavate elevator pit | Project5_TAMPERED | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 275
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 33 | Excavate foundations | Project5_TAMPERED | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0

## 5-24-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
5/24/2026: Detailed View | 5/24/2026: Detailed View | 5/24/2026: Detailed View | 5/24/2026: Detailed View | 5/24/2026: Detailed View | 5/24/2026: Detailed View | 5/24/2026: Detailed View | 5/24/2026: Detailed View | 5/24/2026: Detailed View | 5/24/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project2 | 19 | 5 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | InProgress | 74 | 263
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
HMI - Total Tasks
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275
HMI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 35 | Form column piers and spread foundations | Project5_TAMPERED | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 19
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_TAMPERED | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 275

## 5-31-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
5/31/2026: Detailed View | 5/31/2026: Detailed View | 5/31/2026: Detailed View | 5/31/2026: Detailed View | 5/31/2026: Detailed View | 5/31/2026: Detailed View | 5/31/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
HMI - Total Tasks
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19
HMI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 37 | Form elevator pit walls | Project5_TAMPERED | 4 | 4 | 2026-09-25 | 2026-09-30 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 275
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_TAMPERED | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 19

## 6-7-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
6/7/2026: Detailed View | 6/7/2026: Detailed View | 6/7/2026: Detailed View | 6/7/2026: Detailed View | 6/7/2026: Detailed View | 6/7/2026: Detailed View | 6/7/2026: Detailed View | 6/7/2026: Detailed View | 6/7/2026: Detailed View | 6/7/2026: Detailed View | 6/7/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
HMI - Total Tasks
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
HMI - Complete Tasks
The total number of tasks that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
HMI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 39 | Pour column piers and foundations | Project5_TAMPERED | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 19
FALSE |  | 40 | Pour concrete elevator walls | Project5_TAMPERED | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 275
HMI - Complete Tasks (adjusted)
The total number of tasks that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date). Gives credit for tasks baselined in the future that completed during the given status period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_TAMPERED | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0

## 6-14-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
6/14/2026: Detailed View | 6/14/2026: Detailed View | 6/14/2026: Detailed View | 6/14/2026: Detailed View | 6/14/2026: Detailed View | 6/14/2026: Detailed View | 6/14/2026: Detailed View | 6/14/2026: Detailed View | 6/14/2026: Detailed View | 6/14/2026: Detailed View | 6/14/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 29 | Install exterior fire line and building fire riser | Project2 | 43 | 20 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | InProgress | 53 | 0
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 17 | Detail, fabricate and deliver steel | Project2 | 60 | 20 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | InProgress | 67 | 48
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project2 | 10 | 10 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Planned | 0 | 93
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
HMI - Total Tasks
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19
HMI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 42 | Cure piers and foundations | Project5_TAMPERED | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 19

## 6-21-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
6/21/2026: Detailed View | 6/21/2026: Detailed View | 6/21/2026: Detailed View | 6/21/2026: Detailed View | 6/21/2026: Detailed View | 6/21/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
HMI - Total Tasks
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19
HMI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 44 | Strip column piers and foundation forms | Project5_TAMPERED | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 19

## 6-28-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
6/28/2026: Detailed View | 6/28/2026: Detailed View | 6/28/2026: Detailed View | 6/28/2026: Detailed View | 6/28/2026: Detailed View | 6/28/2026: Detailed View | 6/28/2026: Detailed View | 6/28/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project2 | 10 | 10 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Planned | 0 | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
HMI - Total Tasks
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256
HMI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 41 | Cure elevator wall concrete | Project5_TAMPERED | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 256
FALSE |  | 43 | Strip wall forms | Project5_TAMPERED | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 256

## 7-5-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
7/5/2026: Detailed View | 7/5/2026: Detailed View | 7/5/2026: Detailed View | 7/5/2026: Detailed View | 7/5/2026: Detailed View | 7/5/2026: Detailed View | 7/5/2026: Detailed View | 7/5/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 31 | Erect building batter boards and layout building | Project2 | 5 | 5 | 2026-07-06 | 2026-07-10 | 2026-04-30 | 2026-05-06 | Normal | Planned | 0 | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 31 | Erect building batter boards and layout building | Project2 | 5 | 5 | 2026-07-06 | 2026-07-10 | 2026-04-30 | 2026-05-06 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 31 | Erect building batter boards and layout building | Project2 | 5 | 5 | 2026-07-06 | 2026-07-10 | 2026-04-30 | 2026-05-06 | Normal | Planned | 0 | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
HMI - Total Tasks
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19
HMI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_TAMPERED | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 256
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_TAMPERED | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 256
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_TAMPERED | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 19

## 7-12-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
7/12/2026: Detailed View | 7/12/2026: Detailed View | 7/12/2026: Detailed View | 7/12/2026: Detailed View | 7/12/2026: Detailed View | 7/12/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
HMI - Total Tasks
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56
HMI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_TAMPERED | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 56

## 7-19-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
7/19/2026: Detailed View | 7/19/2026: Detailed View | 7/19/2026: Detailed View | 7/19/2026: Detailed View | 7/19/2026: Detailed View | 7/19/2026: Detailed View | 7/19/2026: Detailed View | 7/19/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 33 | Excavate foundations | Project2 | 10 | 10 | 2026-07-13 | 2026-07-24 | 2026-05-07 | 2026-05-20 | Normal | Planned | 0 | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
HMI - Total Tasks
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19
HMI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_TAMPERED | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 19

## 7-26-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
7/26/2026: Detailed View | 7/26/2026: Detailed View | 7/26/2026: Detailed View | 7/26/2026: Detailed View | 7/26/2026: Detailed View | 7/26/2026: Detailed View | 7/26/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 35 | Form column piers and spread foundations | Project2 | 4 | 4 | 2026-07-27 | 2026-07-30 | 2026-05-21 | 2026-05-26 | Normal | Planned | 0 | 0
FALSE |  | 38 | Set reinforcing and anchor bolts | Project2 | 4 | 4 | 2026-07-31 | 2026-08-05 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project2 | 4 | 4 | 2026-07-29 | 2026-08-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 204
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 35 | Form column piers and spread foundations | Project2 | 4 | 4 | 2026-07-27 | 2026-07-30 | 2026-05-21 | 2026-05-26 | Normal | Planned | 0 | 0
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project2 | 2 | 2 | 2026-07-27 | 2026-07-28 | 2026-05-21 | 2026-05-22 | Normal | Planned | 0 | 204

## 8-2-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
8/2/2026: Detailed View | 8/2/2026: Detailed View | 8/2/2026: Detailed View | 8/2/2026: Detailed View | 8/2/2026: Detailed View | 8/2/2026: Detailed View | 8/2/2026: Detailed View | 8/2/2026: Detailed View | 8/2/2026: Detailed View | 8/2/2026: Detailed View | 8/2/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 38 | Set reinforcing and anchor bolts | Project2 | 4 | 4 | 2026-07-31 | 2026-08-05 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 0
FALSE |  | 39 | Pour column piers and foundations | Project2 | 5 | 5 | 2026-08-06 | 2026-08-12 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project2 | 4 | 4 | 2026-07-29 | 2026-08-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 204
FALSE |  | 37 | Form elevator pit walls | Project2 | 4 | 4 | 2026-08-06 | 2026-08-11 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 203
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 38 | Set reinforcing and anchor bolts | Project2 | 4 | 4 | 2026-07-31 | 2026-08-05 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 0
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project2 | 4 | 4 | 2026-07-29 | 2026-08-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 204
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project2 | 4 | 4 | 2026-07-29 | 2026-08-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 204
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project2 | 4 | 4 | 2026-07-29 | 2026-08-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 204
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
HMI - Total Tasks
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19
HMI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_TAMPERED | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 19

## 8-9-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
8/9/2026: Detailed View | 8/9/2026: Detailed View | 8/9/2026: Detailed View | 8/9/2026: Detailed View | 8/9/2026: Detailed View | 8/9/2026: Detailed View | 8/9/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 39 | Pour column piers and foundations | Project2 | 5 | 5 | 2026-08-06 | 2026-08-12 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 0
FALSE |  | 42 | Cure piers and foundations | Project2 | 7 | 7 | 2026-08-13 | 2026-08-21 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 37 | Form elevator pit walls | Project2 | 4 | 4 | 2026-08-06 | 2026-08-11 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 203
FALSE |  | 40 | Pour concrete elevator walls | Project2 | 1 | 1 | 2026-08-13 | 2026-08-13 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 202
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 39 | Pour column piers and foundations | Project2 | 5 | 5 | 2026-08-06 | 2026-08-12 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 0
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 37 | Form elevator pit walls | Project2 | 4 | 4 | 2026-08-06 | 2026-08-11 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 203
FALSE |  | 40 | Pour concrete elevator walls | Project2 | 1 | 1 | 2026-08-13 | 2026-08-13 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 202
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 37 | Form elevator pit walls | Project2 | 4 | 4 | 2026-08-06 | 2026-08-11 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 203
FALSE |  | 40 | Pour concrete elevator walls | Project2 | 1 | 1 | 2026-08-13 | 2026-08-13 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 202
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 37 | Form elevator pit walls | Project2 | 4 | 4 | 2026-08-06 | 2026-08-11 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 203

## 8-16-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
8/16/2026: Detailed View | 8/16/2026: Detailed View | 8/16/2026: Detailed View | 8/16/2026: Detailed View | 8/16/2026: Detailed View | 8/16/2026: Detailed View | 8/16/2026: Detailed View | 8/16/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 42 | Cure piers and foundations | Project2 | 7 | 7 | 2026-08-13 | 2026-08-21 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 42 | Cure piers and foundations | Project2 | 7 | 7 | 2026-08-13 | 2026-08-21 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 42 | Cure piers and foundations | Project2 | 7 | 7 | 2026-08-13 | 2026-08-21 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
HMI - Total Tasks
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19
HMI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_TAMPERED | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 19

## 8-23-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
8/23/2026: Detailed View | 8/23/2026: Detailed View | 8/23/2026: Detailed View | 8/23/2026: Detailed View | 8/23/2026: Detailed View | 8/23/2026: Detailed View | 8/23/2026: Detailed View | 8/23/2026: Detailed View | 8/23/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 44 | Strip column piers and foundation forms | Project2 | 3 | 3 | 2026-08-24 | 2026-08-26 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 0
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project2 | 10 | 10 | 2026-08-27 | 2026-09-09 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 41 | Cure elevator wall concrete | Project2 | 7 | 7 | 2026-08-27 | 2026-09-04 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 202
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 44 | Strip column piers and foundation forms | Project2 | 3 | 3 | 2026-08-24 | 2026-08-26 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 44 | Strip column piers and foundation forms | Project2 | 3 | 3 | 2026-08-24 | 2026-08-26 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
HMI - Total Tasks
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19
HMI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 53 | Touch-up paint on steel | Project5_TAMPERED | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 19

## 8-30-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
8/30/2026: Detailed View | 8/30/2026: Detailed View | 8/30/2026: Detailed View | 8/30/2026: Detailed View | 8/30/2026: Detailed View | 8/30/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project2 | 10 | 10 | 2026-08-27 | 2026-09-09 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 41 | Cure elevator wall concrete | Project2 | 7 | 7 | 2026-08-27 | 2026-09-04 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 202
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 41 | Cure elevator wall concrete | Project2 | 7 | 7 | 2026-08-27 | 2026-09-04 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 202
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 41 | Cure elevator wall concrete | Project2 | 7 | 7 | 2026-08-27 | 2026-09-04 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 202
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 41 | Cure elevator wall concrete | Project2 | 7 | 7 | 2026-08-27 | 2026-09-04 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 202

## 9-6-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
9/6/2026: Detailed View | 9/6/2026: Detailed View | 9/6/2026: Detailed View | 9/6/2026: Detailed View | 9/6/2026: Detailed View | 9/6/2026: Detailed View | 9/6/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project2 | 10 | 10 | 2026-08-27 | 2026-09-09 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 0
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-10 | 2026-09-23 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 43 | Strip wall forms | Project2 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 202
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project2 | 3 | 3 | 2026-09-08 | 2026-09-10 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 202
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-09-10 | 2026-09-16 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 35
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 202
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project2 | 10 | 10 | 2026-08-27 | 2026-09-09 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 0
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 43 | Strip wall forms | Project2 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 202
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project2 | 3 | 3 | 2026-09-08 | 2026-09-10 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 202
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 202
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 43 | Strip wall forms | Project2 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 202
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project2 | 3 | 3 | 2026-09-08 | 2026-09-10 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 202
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 202
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 43 | Strip wall forms | Project2 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 202
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project2 | 3 | 3 | 2026-09-08 | 2026-09-10 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 202
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 202

## 9-13-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
9/13/2026: Detailed View | 9/13/2026: Detailed View | 9/13/2026: Detailed View | 9/13/2026: Detailed View | 9/13/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-10 | 2026-09-23 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-09-10 | 2026-09-16 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 35
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-09-10 | 2026-09-16 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 35
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-09-10 | 2026-09-16 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 35

## 9-20-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
9/20/2026: Detailed View | 9/20/2026: Detailed View | 9/20/2026: Detailed View | 9/20/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-10 | 2026-09-23 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 0
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-24 | 2026-10-07 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-10 | 2026-09-23 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-10 | 2026-09-23 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 0

## 9-27-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
9/27/2026: Detailed View | 9/27/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-24 | 2026-10-07 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 0

## 10-4-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
10/4/2026: Detailed View | 10/4/2026: Detailed View | 10/4/2026: Detailed View | 10/4/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-24 | 2026-10-07 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 0
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project2 | 10 | 10 | 2026-10-08 | 2026-10-21 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-24 | 2026-10-07 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project2 | 10 | 10 | 2026-09-24 | 2026-10-07 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 0

## 10-11-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
10/11/2026: Detailed View | 10/11/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project2 | 10 | 10 | 2026-10-08 | 2026-10-21 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 0

## 10-18-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
10/18/2026: Detailed View | 10/18/2026: Detailed View | 10/18/2026: Detailed View | 10/18/2026: Detailed View | 10/18/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project2 | 10 | 10 | 2026-10-08 | 2026-10-21 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 53 | Touch-up paint on steel | Project2 | 5 | 5 | 2026-10-22 | 2026-10-28 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project2 | 10 | 10 | 2026-10-22 | 2026-11-04 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 144
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project2 | 10 | 10 | 2026-10-08 | 2026-10-21 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project2 | 10 | 10 | 2026-10-08 | 2026-10-21 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 0

## 10-25-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
10/25/2026: Detailed View | 10/25/2026: Detailed View | 10/25/2026: Detailed View | 10/25/2026: Detailed View | 10/25/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 53 | Touch-up paint on steel | Project2 | 5 | 5 | 2026-10-22 | 2026-10-28 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 55 | Form 2nd floor including all floor openings | Project2 | 5 | 5 | 2026-10-29 | 2026-11-04 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project2 | 10 | 10 | 2026-10-22 | 2026-11-04 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 144
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 53 | Touch-up paint on steel | Project2 | 5 | 5 | 2026-10-22 | 2026-10-28 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 53 | Touch-up paint on steel | Project2 | 5 | 5 | 2026-10-22 | 2026-10-28 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 0

## 11-1-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
11/1/2026: Detailed View | 11/1/2026: Detailed View | 11/1/2026: Detailed View | 11/1/2026: Detailed View | 11/1/2026: Detailed View | 11/1/2026: Detailed View | 11/1/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 55 | Form 2nd floor including all floor openings | Project2 | 5 | 5 | 2026-10-29 | 2026-11-04 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 0
FALSE |  | 57 | Pour 2nd floor slab | Project2 | 4 | 4 | 2026-11-05 | 2026-11-10 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project2 | 10 | 10 | 2026-10-22 | 2026-11-04 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 144
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 55 | Form 2nd floor including all floor openings | Project2 | 5 | 5 | 2026-10-29 | 2026-11-04 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 0
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project2 | 10 | 10 | 2026-10-22 | 2026-11-04 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 144
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project2 | 10 | 10 | 2026-10-22 | 2026-11-04 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 144
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project2 | 10 | 10 | 2026-10-22 | 2026-11-04 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 144

## 11-8-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
11/8/2026: Detailed View | 11/8/2026: Detailed View | 11/8/2026: Detailed View | 11/8/2026: Detailed View | 11/8/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 57 | Pour 2nd floor slab | Project2 | 4 | 4 | 2026-11-05 | 2026-11-10 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 58 | Cure 2nd floor slab | Project2 | 7 | 7 | 2026-11-11 | 2026-11-19 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 57 | Pour 2nd floor slab | Project2 | 4 | 4 | 2026-11-05 | 2026-11-10 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 57 | Pour 2nd floor slab | Project2 | 4 | 4 | 2026-11-05 | 2026-11-10 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 0

## 11-15-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
11/15/2026: Detailed View | 11/15/2026: Detailed View | 11/15/2026: Detailed View | 11/15/2026: Detailed View | 11/15/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 58 | Cure 2nd floor slab | Project2 | 7 | 7 | 2026-11-11 | 2026-11-19 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 60 | Form 3rd floor including all floor openings | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 58 | Cure 2nd floor slab | Project2 | 7 | 7 | 2026-11-11 | 2026-11-19 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 58 | Cure 2nd floor slab | Project2 | 7 | 7 | 2026-11-11 | 2026-11-19 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 0

## 11-22-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
11/22/2026: Detailed View | 11/22/2026: Detailed View | 11/22/2026: Detailed View | 11/22/2026: Detailed View | 11/22/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 60 | Form 3rd floor including all floor openings | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 62 | Pour 3rd floor slab | Project2 | 4 | 4 | 2026-11-27 | 2026-12-02 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144
FALSE |  | 59 | Strip forms from 2nd floor slab | Project2 | 2 | 2 | 2026-11-27 | 2026-11-30 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 73
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 60 | Form 3rd floor including all floor openings | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 60 | Form 3rd floor including all floor openings | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-11-20 | 2026-11-26 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 0

## 11-29-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
11/29/2026: Detailed View | 11/29/2026: Detailed View | 11/29/2026: Detailed View | 11/29/2026: Detailed View | 11/29/2026: Detailed View | 11/29/2026: Detailed View | 11/29/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 62 | Pour 3rd floor slab | Project2 | 4 | 4 | 2026-11-27 | 2026-12-02 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 63 | Cure 3rd floor slab | Project2 | 7 | 7 | 2026-12-03 | 2026-12-11 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144
FALSE |  | 59 | Strip forms from 2nd floor slab | Project2 | 2 | 2 | 2026-11-27 | 2026-11-30 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 73
FALSE |  | 70 | Form 1st floor | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 73 | Install rebar and in-floor utilities | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144
FALSE |  | 127 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-03 | 2026-12-16 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 151
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 62 | Pour 3rd floor slab | Project2 | 4 | 4 | 2026-11-27 | 2026-12-02 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 0
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144
FALSE |  | 59 | Strip forms from 2nd floor slab | Project2 | 2 | 2 | 2026-11-27 | 2026-11-30 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 73
FALSE |  | 70 | Form 1st floor | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 73 | Install rebar and in-floor utilities | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144
FALSE |  | 59 | Strip forms from 2nd floor slab | Project2 | 2 | 2 | 2026-11-27 | 2026-11-30 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 73
FALSE |  | 70 | Form 1st floor | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
FALSE |  | 73 | Install rebar and in-floor utilities | Project2 | 4 | 4 | 2026-12-01 | 2026-12-04 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 78
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project2 | 20 | 20 | 2026-11-05 | 2026-12-02 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 144

## 12-6-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
12/6/2026: Detailed View | 12/6/2026: Detailed View | 12/6/2026: Detailed View | 12/6/2026: Detailed View | 12/6/2026: Detailed View | 12/6/2026: Detailed View | 12/6/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 63 | Cure 3rd floor slab | Project2 | 7 | 7 | 2026-12-03 | 2026-12-11 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144
FALSE |  | 127 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-03 | 2026-12-16 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 151
FALSE |  | 71 | Install electrical underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 72 | Install plumbing underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 63 | Cure 3rd floor slab | Project2 | 7 | 7 | 2026-12-03 | 2026-12-11 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 0
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 71 | Install electrical underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 72 | Install plumbing underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 71 | Install electrical underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 72 | Install plumbing underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 71 | Install electrical underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73
FALSE |  | 72 | Install plumbing underground | Project2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 73

## 12-13-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
12/13/2026: Detailed View | 12/13/2026: Detailed View | 12/13/2026: Detailed View | 12/13/2026: Detailed View | 12/13/2026: Detailed View | 12/13/2026: Detailed View | 12/13/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 65 | Form roof slab including all floor openings | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144
FALSE |  | 127 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-03 | 2026-12-16 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 151
FALSE |  | 74 | Pour 1st floor slab | Project2 | 4 | 4 | 2026-12-14 | 2026-12-17 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 73
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 65 | Form roof slab including all floor openings | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project2 | 5 | 5 | 2026-12-14 | 2026-12-18 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 0
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 127 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-03 | 2026-12-16 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 151
FALSE |  | 74 | Pour 1st floor slab | Project2 | 4 | 4 | 2026-12-14 | 2026-12-17 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 73
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 127 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-03 | 2026-12-16 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 151
FALSE |  | 74 | Pour 1st floor slab | Project2 | 4 | 4 | 2026-12-14 | 2026-12-17 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 73
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 127 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-03 | 2026-12-16 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 151

## 12-20-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
12/20/2026: Detailed View | 12/20/2026: Detailed View | 12/20/2026: Detailed View | 12/20/2026: Detailed View | 12/20/2026: Detailed View | 12/20/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 67 | Pour roof slab | Project2 | 4 | 4 | 2026-12-21 | 2026-12-24 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 0
FALSE |  | 68 | Cure roof slab | Project2 | 7 | 7 | 2026-12-25 | 2027-01-04 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144
FALSE |  | 64 | Strip forms from 3rd floor slab | Project2 | 2 | 2 | 2026-12-21 | 2026-12-22 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 11
FALSE |  | 75 | Cure 1st floor slab | Project2 | 7 | 7 | 2026-12-23 | 2026-12-31 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 73
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 67 | Pour roof slab | Project2 | 4 | 4 | 2026-12-21 | 2026-12-24 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 0
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 64 | Strip forms from 3rd floor slab | Project2 | 2 | 2 | 2026-12-21 | 2026-12-22 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 11
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 64 | Strip forms from 3rd floor slab | Project2 | 2 | 2 | 2026-12-21 | 2026-12-22 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 11

## 12-27-2026 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
12/27/2026: Detailed View | 12/27/2026: Detailed View | 12/27/2026: Detailed View | 12/27/2026: Detailed View | 12/27/2026: Detailed View | 12/27/2026: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 68 | Cure roof slab | Project2 | 7 | 7 | 2026-12-25 | 2027-01-04 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144
FALSE |  | 75 | Cure 1st floor slab | Project2 | 7 | 7 | 2026-12-23 | 2026-12-31 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 73
FALSE |  | 112 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-31 | 2027-01-13 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 144
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144
FALSE |  | 75 | Cure 1st floor slab | Project2 | 7 | 7 | 2026-12-23 | 2026-12-31 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 73
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144
FALSE |  | 75 | Cure 1st floor slab | Project2 | 7 | 7 | 2026-12-23 | 2026-12-31 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 73
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 111 | Set elevator equipment in shafts | Project2 | 20 | 20 | 2026-12-03 | 2026-12-30 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 144

## 1-3-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
1/3/2027: Detailed View | 1/3/2027: Detailed View | 1/3/2027: Detailed View | 1/3/2027: Detailed View | 1/3/2027: Detailed View | 1/3/2027: Detailed View | 1/3/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 68 | Cure roof slab | Project2 | 7 | 7 | 2026-12-25 | 2027-01-04 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 69 | Strip forms from roof slab | Project2 | 2 | 2 | 2027-01-05 | 2027-01-06 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 78 | Install exterior sheathing and metal studs | Project2 | 15 | 15 | 2027-01-07 | 2027-01-27 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 112 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-31 | 2027-01-13 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 144
FALSE |  | 76 | Strip forms from 1st floor slab | Project2 | 2 | 2 | 2027-01-07 | 2027-01-08 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 73
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 68 | Cure roof slab | Project2 | 7 | 7 | 2026-12-25 | 2027-01-04 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 69 | Strip forms from roof slab | Project2 | 2 | 2 | 2027-01-05 | 2027-01-06 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 76 | Strip forms from 1st floor slab | Project2 | 2 | 2 | 2027-01-07 | 2027-01-08 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 73
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 76 | Strip forms from 1st floor slab | Project2 | 2 | 2 | 2027-01-07 | 2027-01-08 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 73
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 76 | Strip forms from 1st floor slab | Project2 | 2 | 2 | 2027-01-07 | 2027-01-08 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 73

## 1-10-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
1/10/2027: Detailed View | 1/10/2027: Detailed View | 1/10/2027: Detailed View | 1/10/2027: Detailed View | 1/10/2027: Detailed View | 1/10/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 78 | Install exterior sheathing and metal studs | Project2 | 15 | 15 | 2027-01-07 | 2027-01-27 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 112 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-31 | 2027-01-13 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 144
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 93
FALSE |  | 120 | Rough-in electrical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 73
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 114
FALSE |  | 113 | Test and align doors and equipment | Project2 | 10 | 10 | 2027-01-14 | 2027-01-27 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 144
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 112 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-31 | 2027-01-13 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 144
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 112 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-31 | 2027-01-13 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 144
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 112 | Set equipment in mechanical room | Project2 | 10 | 10 | 2026-12-31 | 2027-01-13 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 144

## 1-17-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
1/17/2027: Detailed View | 1/17/2027: Detailed View | 1/17/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 78 | Install exterior sheathing and metal studs | Project2 | 15 | 15 | 2027-01-07 | 2027-01-27 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 93
FALSE |  | 120 | Rough-in electrical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 73
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 114
FALSE |  | 113 | Test and align doors and equipment | Project2 | 10 | 10 | 2027-01-14 | 2027-01-27 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 144

## 1-24-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
1/24/2027: Detailed View | 1/24/2027: Detailed View | 1/24/2027: Detailed View | 1/24/2027: Detailed View | 1/24/2027: Detailed View | 1/24/2027: Detailed View | 1/24/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 78 | Install exterior sheathing and metal studs | Project2 | 15 | 15 | 2027-01-07 | 2027-01-27 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 0
FALSE |  | 82 | Install exterior masonry work | Project2 | 25 | 25 | 2027-01-28 | 2027-03-03 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 93
FALSE |  | 120 | Rough-in electrical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 73
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 114
FALSE |  | 113 | Test and align doors and equipment | Project2 | 10 | 10 | 2027-01-14 | 2027-01-27 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 144
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 78 | Install exterior sheathing and metal studs | Project2 | 15 | 15 | 2027-01-07 | 2027-01-27 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 0
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 113 | Test and align doors and equipment | Project2 | 10 | 10 | 2027-01-14 | 2027-01-27 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 144
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 113 | Test and align doors and equipment | Project2 | 10 | 10 | 2027-01-14 | 2027-01-27 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 144
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 113 | Test and align doors and equipment | Project2 | 10 | 10 | 2027-01-14 | 2027-01-27 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 144

## 1-31-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
1/31/2027: Detailed View | 1/31/2027: Detailed View | 1/31/2027: Detailed View | 1/31/2027: Detailed View | 1/31/2027: Detailed View | 1/31/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 82 | Install exterior masonry work | Project2 | 25 | 25 | 2027-01-28 | 2027-03-03 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 93
FALSE |  | 120 | Rough-in electrical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 73
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 114
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 93
FALSE |  | 120 | Rough-in electrical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 73
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 114
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 93
FALSE |  | 120 | Rough-in electrical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 73
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 114
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project2 | 20 | 20 | 2027-01-11 | 2027-02-05 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 114

## 2-7-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
2/7/2027: Detailed View | 2/7/2027: Detailed View | 2/7/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 82 | Install exterior masonry work | Project2 | 25 | 25 | 2027-01-28 | 2027-03-03 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 84 | Install tile in toilet rooms | Project2 | 10 | 10 | 2027-02-08 | 2027-02-19 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 93

## 2-14-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
2/14/2027: Detailed View | 2/14/2027: Detailed View | 2/14/2027: Detailed View | 2/14/2027: Detailed View | 2/14/2027: Detailed View | 2/14/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 82 | Install exterior masonry work | Project2 | 25 | 25 | 2027-01-28 | 2027-03-03 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 84 | Install tile in toilet rooms | Project2 | 10 | 10 | 2027-02-08 | 2027-02-19 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 93
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 84 | Install tile in toilet rooms | Project2 | 10 | 10 | 2027-02-08 | 2027-02-19 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 93
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 84 | Install tile in toilet rooms | Project2 | 10 | 10 | 2027-02-08 | 2027-02-19 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 93
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 84 | Install tile in toilet rooms | Project2 | 10 | 10 | 2027-02-08 | 2027-02-19 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 93

## 2-21-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
2/21/2027: Detailed View | 2/21/2027: Detailed View | 2/21/2027: Detailed View | 2/21/2027: Detailed View | 2/21/2027: Detailed View | 2/21/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 82 | Install exterior masonry work | Project2 | 25 | 25 | 2027-01-28 | 2027-03-03 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 86 | Clean toilet room tile | Project2 | 5 | 5 | 2027-02-22 | 2027-02-26 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 93
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 86 | Clean toilet room tile | Project2 | 5 | 5 | 2027-02-22 | 2027-02-26 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 93
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 86 | Clean toilet room tile | Project2 | 5 | 5 | 2027-02-22 | 2027-02-26 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 93
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 86 | Clean toilet room tile | Project2 | 5 | 5 | 2027-02-22 | 2027-02-26 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 93

## 2-28-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
2/28/2027: Detailed View | 2/28/2027: Detailed View | 2/28/2027: Detailed View | 2/28/2027: Detailed View | 2/28/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 82 | Install exterior masonry work | Project2 | 25 | 25 | 2027-01-28 | 2027-03-03 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 0
FALSE |  | 94 | Install window wall aluminum and glass | Project2 | 25 | 25 | 2027-03-04 | 2027-04-07 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 85 | Clean masonry | Project2 | 5 | 5 | 2027-03-04 | 2027-03-10 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 90
FALSE |  | 88 | Install flashing at parapet walls | Project2 | 4 | 4 | 2027-03-04 | 2027-03-09 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 61
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 82 | Install exterior masonry work | Project2 | 25 | 25 | 2027-01-28 | 2027-03-03 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 82 | Install exterior masonry work | Project2 | 25 | 25 | 2027-01-28 | 2027-03-03 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 0

## 3-7-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
3/7/2027: Detailed View | 3/7/2027: Detailed View | 3/7/2027: Detailed View | 3/7/2027: Detailed View | 3/7/2027: Detailed View | 3/7/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Install window wall aluminum and glass | Project2 | 25 | 25 | 2027-03-04 | 2027-04-07 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 85 | Clean masonry | Project2 | 5 | 5 | 2027-03-04 | 2027-03-10 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 90
FALSE |  | 88 | Install flashing at parapet walls | Project2 | 4 | 4 | 2027-03-04 | 2027-03-09 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 61
FALSE |  | 83 | Install roof drains | Project2 | 2 | 2 | 2027-03-10 | 2027-03-11 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 59
FALSE |  | 116 | Tie-in fire line riser and set valves | Project2 | 10 | 10 | 2027-03-11 | 2027-03-24 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 90
FALSE |  | 89 | Pour lightweight concrete roof fill | Project2 | 2 | 2 | 2027-03-12 | 2027-03-15 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 59
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 85 | Clean masonry | Project2 | 5 | 5 | 2027-03-04 | 2027-03-10 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 90
FALSE |  | 88 | Install flashing at parapet walls | Project2 | 4 | 4 | 2027-03-04 | 2027-03-09 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 61
FALSE |  | 83 | Install roof drains | Project2 | 2 | 2 | 2027-03-10 | 2027-03-11 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 59
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 85 | Clean masonry | Project2 | 5 | 5 | 2027-03-04 | 2027-03-10 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 90
FALSE |  | 88 | Install flashing at parapet walls | Project2 | 4 | 4 | 2027-03-04 | 2027-03-09 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 61
FALSE |  | 83 | Install roof drains | Project2 | 2 | 2 | 2027-03-10 | 2027-03-11 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 59
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 85 | Clean masonry | Project2 | 5 | 5 | 2027-03-04 | 2027-03-10 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 90

## 3-14-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
3/14/2027: Detailed View | 3/14/2027: Detailed View | 3/14/2027: Detailed View | 3/14/2027: Detailed View | 3/14/2027: Detailed View | 3/14/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Install window wall aluminum and glass | Project2 | 25 | 25 | 2027-03-04 | 2027-04-07 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 116 | Tie-in fire line riser and set valves | Project2 | 10 | 10 | 2027-03-11 | 2027-03-24 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 90
FALSE |  | 89 | Pour lightweight concrete roof fill | Project2 | 2 | 2 | 2027-03-12 | 2027-03-15 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 59
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 89 | Pour lightweight concrete roof fill | Project2 | 2 | 2 | 2027-03-12 | 2027-03-15 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 59
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 89 | Pour lightweight concrete roof fill | Project2 | 2 | 2 | 2027-03-12 | 2027-03-15 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 59
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 89 | Pour lightweight concrete roof fill | Project2 | 2 | 2 | 2027-03-12 | 2027-03-15 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 59

## 3-21-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
3/21/2027: Detailed View | 3/21/2027: Detailed View | 3/21/2027: Detailed View | 3/21/2027: Detailed View | 3/21/2027: Detailed View | 3/21/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Install window wall aluminum and glass | Project2 | 25 | 25 | 2027-03-04 | 2027-04-07 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 116 | Tie-in fire line riser and set valves | Project2 | 10 | 10 | 2027-03-11 | 2027-03-24 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 90
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 116 | Tie-in fire line riser and set valves | Project2 | 10 | 10 | 2027-03-11 | 2027-03-24 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 90
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 116 | Tie-in fire line riser and set valves | Project2 | 10 | 10 | 2027-03-11 | 2027-03-24 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 90
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 116 | Tie-in fire line riser and set valves | Project2 | 10 | 10 | 2027-03-11 | 2027-03-24 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 90

## 3-28-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
3/28/2027: Detailed View | 3/28/2027: Detailed View | 3/28/2027: Detailed View | 3/28/2027: Detailed View | 3/28/2027: Detailed View | 3/28/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Install window wall aluminum and glass | Project2 | 25 | 25 | 2027-03-04 | 2027-04-07 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59
FALSE |  | 91 | Spread stone ballast on seamless roof | Project2 | 5 | 5 | 2027-03-30 | 2027-04-05 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 59
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 90 | Install seamless roofing material | Project2 | 5 | 5 | 2027-03-23 | 2027-03-29 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 59

## 4-4-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
4/4/2027: Detailed View | 4/4/2027: Detailed View | 4/4/2027: Detailed View | 4/4/2027: Detailed View | 4/4/2027: Detailed View | 4/4/2027: Detailed View | 4/4/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Install window wall aluminum and glass | Project2 | 25 | 25 | 2027-03-04 | 2027-04-07 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 0
FALSE |  | 95 | Install interior stud walls and drywall | Project2 | 25 | 25 | 2027-04-08 | 2027-05-12 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 91 | Spread stone ballast on seamless roof | Project2 | 5 | 5 | 2027-03-30 | 2027-04-05 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 59
FALSE |  | 92 | Set rooftop equipment | Project2 | 10 | 10 | 2027-04-06 | 2027-04-19 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 59
FALSE |  | 97 | Install store front doors and hardware | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 20
FALSE |  | 101 | Install conduit at ceiling plenum space | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 15
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Install window wall aluminum and glass | Project2 | 25 | 25 | 2027-03-04 | 2027-04-07 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 0
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 91 | Spread stone ballast on seamless roof | Project2 | 5 | 5 | 2027-03-30 | 2027-04-05 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 59
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 91 | Spread stone ballast on seamless roof | Project2 | 5 | 5 | 2027-03-30 | 2027-04-05 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 59
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 91 | Spread stone ballast on seamless roof | Project2 | 5 | 5 | 2027-03-30 | 2027-04-05 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 59

## 4-11-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
4/11/2027: Detailed View | 4/11/2027: Detailed View | 4/11/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Install interior stud walls and drywall | Project2 | 25 | 25 | 2027-04-08 | 2027-05-12 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 92 | Set rooftop equipment | Project2 | 10 | 10 | 2027-04-06 | 2027-04-19 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 59
FALSE |  | 97 | Install store front doors and hardware | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 20
FALSE |  | 101 | Install conduit at ceiling plenum space | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 15
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45

## 4-18-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
4/18/2027: Detailed View | 4/18/2027: Detailed View | 4/18/2027: Detailed View | 4/18/2027: Detailed View | 4/18/2027: Detailed View | 4/18/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Install interior stud walls and drywall | Project2 | 25 | 25 | 2027-04-08 | 2027-05-12 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 92 | Set rooftop equipment | Project2 | 10 | 10 | 2027-04-06 | 2027-04-19 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 59
FALSE |  | 97 | Install store front doors and hardware | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 20
FALSE |  | 101 | Install conduit at ceiling plenum space | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 15
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45
FALSE |  | 130 | Install duct in building chase | Project2 | 15 | 15 | 2027-04-20 | 2027-05-10 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 71
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 92 | Set rooftop equipment | Project2 | 10 | 10 | 2027-04-06 | 2027-04-19 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 59
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 92 | Set rooftop equipment | Project2 | 10 | 10 | 2027-04-06 | 2027-04-19 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 59
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 92 | Set rooftop equipment | Project2 | 10 | 10 | 2027-04-06 | 2027-04-19 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 59

## 4-25-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
4/25/2027: Detailed View | 4/25/2027: Detailed View | 4/25/2027: Detailed View | 4/25/2027: Detailed View | 4/25/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Install interior stud walls and drywall | Project2 | 25 | 25 | 2027-04-08 | 2027-05-12 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Install store front doors and hardware | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 20
FALSE |  | 101 | Install conduit at ceiling plenum space | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 15
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45
FALSE |  | 130 | Install duct in building chase | Project2 | 15 | 15 | 2027-04-20 | 2027-05-10 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 71
FALSE |  | 121 | Rough-in electrical in drywall walls | Project2 | 20 | 20 | 2027-04-29 | 2027-05-26 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 30
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Install store front doors and hardware | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 20
FALSE |  | 101 | Install conduit at ceiling plenum space | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 15
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Install store front doors and hardware | Project2 | 15 | 15 | 2027-04-08 | 2027-04-28 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 20

## 5-2-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
5/2/2027: Detailed View | 5/2/2027: Detailed View | 5/2/2027: Detailed View | 5/2/2027: Detailed View | 5/2/2027: Detailed View | 5/2/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Install interior stud walls and drywall | Project2 | 25 | 25 | 2027-04-08 | 2027-05-12 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45
FALSE |  | 130 | Install duct in building chase | Project2 | 15 | 15 | 2027-04-20 | 2027-05-10 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 71
FALSE |  | 121 | Rough-in electrical in drywall walls | Project2 | 20 | 20 | 2027-04-29 | 2027-05-26 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 30
FALSE |  | 117 | Set plumbing fixtures and trim | Project2 | 15 | 15 | 2027-05-06 | 2027-05-26 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 45
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project2 | 20 | 20 | 2027-04-08 | 2027-05-05 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 45

## 5-9-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
5/9/2027: Detailed View | 5/9/2027: Detailed View | 5/9/2027: Detailed View | 5/9/2027: Detailed View | 5/9/2027: Detailed View | 5/9/2027: Detailed View | 5/9/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Install interior stud walls and drywall | Project2 | 25 | 25 | 2027-04-08 | 2027-05-12 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 130 | Install duct in building chase | Project2 | 15 | 15 | 2027-04-20 | 2027-05-10 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 71
FALSE |  | 121 | Rough-in electrical in drywall walls | Project2 | 20 | 20 | 2027-04-29 | 2027-05-26 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 30
FALSE |  | 117 | Set plumbing fixtures and trim | Project2 | 15 | 15 | 2027-05-06 | 2027-05-26 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 45
FALSE |  | 99 | Install millwork and wood trim | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 102 | Install duct in ceiling plenum space | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 133 | Install hard tile flooring in common areas | Project2 | 5 | 5 | 2027-05-13 | 2027-05-19 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 56
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Install interior stud walls and drywall | Project2 | 25 | 25 | 2027-04-08 | 2027-05-12 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 0
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 130 | Install duct in building chase | Project2 | 15 | 15 | 2027-04-20 | 2027-05-10 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 71
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 130 | Install duct in building chase | Project2 | 15 | 15 | 2027-04-20 | 2027-05-10 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 71
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 130 | Install duct in building chase | Project2 | 15 | 15 | 2027-04-20 | 2027-05-10 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 71

## 5-16-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
5/16/2027: Detailed View | 5/16/2027: Detailed View | 5/16/2027: Detailed View | 5/16/2027: Detailed View | 5/16/2027: Detailed View
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 121 | Rough-in electrical in drywall walls | Project2 | 20 | 20 | 2027-04-29 | 2027-05-26 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 30
FALSE |  | 117 | Set plumbing fixtures and trim | Project2 | 15 | 15 | 2027-05-06 | 2027-05-26 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 45
FALSE |  | 99 | Install millwork and wood trim | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 102 | Install duct in ceiling plenum space | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 133 | Install hard tile flooring in common areas | Project2 | 5 | 5 | 2027-05-13 | 2027-05-19 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 56
FALSE |  | 134 | Clean hard tile floors | Project2 | 4 | 4 | 2027-05-20 | 2027-05-25 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 56
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 133 | Install hard tile flooring in common areas | Project2 | 5 | 5 | 2027-05-13 | 2027-05-19 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 56
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 133 | Install hard tile flooring in common areas | Project2 | 5 | 5 | 2027-05-13 | 2027-05-19 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 56
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 133 | Install hard tile flooring in common areas | Project2 | 5 | 5 | 2027-05-13 | 2027-05-19 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 56

## 5-23-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
5/23/2027: Detailed View | 5/23/2027: Detailed View | 5/23/2027: Detailed View | 5/23/2027: Detailed View | 5/23/2027: Detailed View | 5/23/2027: Detailed View
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 121 | Rough-in electrical in drywall walls | Project2 | 20 | 20 | 2027-04-29 | 2027-05-26 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 30
FALSE |  | 117 | Set plumbing fixtures and trim | Project2 | 15 | 15 | 2027-05-06 | 2027-05-26 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 45
FALSE |  | 99 | Install millwork and wood trim | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 102 | Install duct in ceiling plenum space | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 134 | Clean hard tile floors | Project2 | 4 | 4 | 2027-05-20 | 2027-05-25 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 56
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project2 | 15 | 15 | 2027-05-27 | 2027-06-16 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 15
20 to 30 days float
Total number of activities with positive float of more than 20 and less than or equal to 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 121 | Rough-in electrical in drywall walls | Project2 | 20 | 20 | 2027-04-29 | 2027-05-26 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 30
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 117 | Set plumbing fixtures and trim | Project2 | 15 | 15 | 2027-05-06 | 2027-05-26 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 45
FALSE |  | 134 | Clean hard tile floors | Project2 | 4 | 4 | 2027-05-20 | 2027-05-25 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 56
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 117 | Set plumbing fixtures and trim | Project2 | 15 | 15 | 2027-05-06 | 2027-05-26 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 45
FALSE |  | 134 | Clean hard tile floors | Project2 | 4 | 4 | 2027-05-20 | 2027-05-25 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 56
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 134 | Clean hard tile floors | Project2 | 4 | 4 | 2027-05-20 | 2027-05-25 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 56

## 5-30-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
5/30/2027: Detailed View | 5/30/2027: Detailed View | 5/30/2027: Detailed View | 5/30/2027: Detailed View | 5/30/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 96 | Install interior doors and hardware | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 99 | Install millwork and wood trim | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 102 | Install duct in ceiling plenum space | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project2 | 15 | 15 | 2027-05-27 | 2027-06-16 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 15
FALSE |  | 103 | Install ceiling grid | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 10
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 64
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 99 | Install millwork and wood trim | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 102 | Install duct in ceiling plenum space | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 99 | Install millwork and wood trim | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10
FALSE |  | 102 | Install duct in ceiling plenum space | Project2 | 15 | 15 | 2027-05-13 | 2027-06-02 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 10

## 6-6-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
6/6/2027: Detailed View | 6/6/2027: Detailed View | 6/6/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 96 | Install interior doors and hardware | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project2 | 15 | 15 | 2027-05-27 | 2027-06-16 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 15
FALSE |  | 103 | Install ceiling grid | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 10
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 64

## 6-13-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
6/13/2027: Detailed View | 6/13/2027: Detailed View | 6/13/2027: Detailed View | 6/13/2027: Detailed View | 6/13/2027: Detailed View | 6/13/2027: Detailed View | 6/13/2027: Detailed View | 6/13/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 96 | Install interior doors and hardware | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 0
FALSE |  | 100 | Paint walls and woodwork | Project2 | 20 | 20 | 2027-06-17 | 2027-07-14 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project2 | 15 | 15 | 2027-05-27 | 2027-06-16 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 15
FALSE |  | 103 | Install ceiling grid | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 10
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 64
FALSE |  | 104 | Install ceiling tile | Project2 | 10 | 10 | 2027-06-17 | 2027-06-30 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 30
FALSE |  | 123 | Install and terminate electrical devices | Project2 | 15 | 15 | 2027-06-17 | 2027-07-07 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 15
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 96 | Install interior doors and hardware | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 0
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project2 | 15 | 15 | 2027-05-27 | 2027-06-16 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 15
FALSE |  | 103 | Install ceiling grid | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 10
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 64
High Float
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 64
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project2 | 10 | 10 | 2027-06-03 | 2027-06-16 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 64

## 6-20-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
6/20/2027: Detailed View | 6/20/2027: Detailed View | 6/20/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 100 | Paint walls and woodwork | Project2 | 20 | 20 | 2027-06-17 | 2027-07-14 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 104 | Install ceiling tile | Project2 | 10 | 10 | 2027-06-17 | 2027-06-30 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 30
FALSE |  | 123 | Install and terminate electrical devices | Project2 | 15 | 15 | 2027-06-17 | 2027-07-07 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 15

## 6-27-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
6/27/2027: Detailed View | 6/27/2027: Detailed View | 6/27/2027: Detailed View | 6/27/2027: Detailed View | 6/27/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 100 | Paint walls and woodwork | Project2 | 20 | 20 | 2027-06-17 | 2027-07-14 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 104 | Install ceiling tile | Project2 | 10 | 10 | 2027-06-17 | 2027-06-30 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 30
FALSE |  | 123 | Install and terminate electrical devices | Project2 | 15 | 15 | 2027-06-17 | 2027-07-07 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 15
20 to 30 days float
Total number of activities with positive float of more than 20 and less than or equal to 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 104 | Install ceiling tile | Project2 | 10 | 10 | 2027-06-17 | 2027-06-30 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 30
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 104 | Install ceiling tile | Project2 | 10 | 10 | 2027-06-17 | 2027-06-30 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 30

## 7-4-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
7/4/2027: Detailed View | 7/4/2027: Detailed View | 7/4/2027: Detailed View | 7/4/2027: Detailed View | 7/4/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 100 | Paint walls and woodwork | Project2 | 20 | 20 | 2027-06-17 | 2027-07-14 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 123 | Install and terminate electrical devices | Project2 | 15 | 15 | 2027-06-17 | 2027-07-07 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 15
FALSE |  | 125 | Install light fixtures - test and clean | Project2 | 10 | 10 | 2027-07-08 | 2027-07-21 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 15
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 123 | Install and terminate electrical devices | Project2 | 15 | 15 | 2027-06-17 | 2027-07-07 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 15
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 123 | Install and terminate electrical devices | Project2 | 15 | 15 | 2027-06-17 | 2027-07-07 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 15

## 7-11-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
7/11/2027: Detailed View | 7/11/2027: Detailed View | 7/11/2027: Detailed View | 7/11/2027: Detailed View | 7/11/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 100 | Paint walls and woodwork | Project2 | 20 | 20 | 2027-06-17 | 2027-07-14 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 0
FALSE |  | 106 | Install building carpet | Project2 | 20 | 20 | 2027-07-15 | 2027-08-11 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 125 | Install light fixtures - test and clean | Project2 | 10 | 10 | 2027-07-08 | 2027-07-21 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 15
FALSE |  | 105 | Hang wallpaper | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 107 | Install hardware and accessories | Project2 | 15 | 15 | 2027-07-15 | 2027-08-04 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 5
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 7
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 100 | Paint walls and woodwork | Project2 | 20 | 20 | 2027-06-17 | 2027-07-14 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 100 | Paint walls and woodwork | Project2 | 20 | 20 | 2027-06-17 | 2027-07-14 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 0

## 7-18-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
7/18/2027: Detailed View | 7/18/2027: Detailed View | 7/18/2027: Detailed View | 7/18/2027: Detailed View | 7/18/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 106 | Install building carpet | Project2 | 20 | 20 | 2027-07-15 | 2027-08-11 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 125 | Install light fixtures - test and clean | Project2 | 10 | 10 | 2027-07-08 | 2027-07-21 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 15
FALSE |  | 105 | Hang wallpaper | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 107 | Install hardware and accessories | Project2 | 15 | 15 | 2027-07-15 | 2027-08-04 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 5
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 7
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project2 | 2 | 2 | 2027-07-22 | 2027-07-23 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 17
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 125 | Install light fixtures - test and clean | Project2 | 10 | 10 | 2027-07-08 | 2027-07-21 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 15
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project2 | 2 | 2 | 2027-07-22 | 2027-07-23 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 17
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project2 | 2 | 2 | 2027-07-22 | 2027-07-23 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 17

## 7-25-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
7/25/2027: Detailed View | 7/25/2027: Detailed View | 7/25/2027: Detailed View | 7/25/2027: Detailed View | 7/25/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 106 | Install building carpet | Project2 | 20 | 20 | 2027-07-15 | 2027-08-11 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 105 | Hang wallpaper | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 107 | Install hardware and accessories | Project2 | 15 | 15 | 2027-07-15 | 2027-08-04 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 5
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 7
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 131 | Set HVAC trim and test and balance system | Project2 | 20 | 20 | 2027-07-26 | 2027-08-20 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 17
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project2 | 10 | 10 | 2027-07-29 | 2027-08-11 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 7
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 105 | Hang wallpaper | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 7
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 105 | Hang wallpaper | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project2 | 10 | 10 | 2027-07-15 | 2027-07-28 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 10

## 8-1-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
8/1/2027: Detailed View | 8/1/2027: Detailed View | 8/1/2027: Detailed View | 8/1/2027: Detailed View | 8/1/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 106 | Install building carpet | Project2 | 20 | 20 | 2027-07-15 | 2027-08-11 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 107 | Install hardware and accessories | Project2 | 15 | 15 | 2027-07-15 | 2027-08-04 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 5
FALSE |  | 131 | Set HVAC trim and test and balance system | Project2 | 20 | 20 | 2027-07-26 | 2027-08-20 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 17
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project2 | 10 | 10 | 2027-07-29 | 2027-08-11 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 7
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 107 | Install hardware and accessories | Project2 | 15 | 15 | 2027-07-15 | 2027-08-04 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 5
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 107 | Install hardware and accessories | Project2 | 15 | 15 | 2027-07-15 | 2027-08-04 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 5

## 8-8-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
8/8/2027: Detailed View | 8/8/2027: Detailed View | 8/8/2027: Detailed View | 8/8/2027: Detailed View | 8/8/2027: Detailed View | 8/8/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 106 | Install building carpet | Project2 | 20 | 20 | 2027-07-15 | 2027-08-11 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 0
FALSE |  | 135 | Remove debris from building and do final clean-up | Project2 | 4 | 4 | 2027-08-12 | 2027-08-17 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project2 | 20 | 20 | 2027-07-26 | 2027-08-20 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 17
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project2 | 10 | 10 | 2027-07-29 | 2027-08-11 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 7
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 106 | Install building carpet | Project2 | 20 | 20 | 2027-07-15 | 2027-08-11 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 0
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project2 | 10 | 10 | 2027-07-29 | 2027-08-11 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 7
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project2 | 10 | 10 | 2027-07-29 | 2027-08-11 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 7

## 8-15-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
8/15/2027: Detailed View | 8/15/2027: Detailed View | 8/15/2027: Detailed View | 8/15/2027: Detailed View | 8/15/2027: Detailed View | 8/15/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 135 | Remove debris from building and do final clean-up | Project2 | 4 | 4 | 2027-08-12 | 2027-08-17 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 0
FALSE |  | 138 | Complete elevator inspection and certification | Project2 | 3 | 3 | 2027-08-18 | 2027-08-20 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project2 | 20 | 20 | 2027-07-26 | 2027-08-20 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 17
FALSE |  | 136 | Substantial completion date | Project2 | 1 | 1 | 2027-08-18 | 2027-08-18 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 19
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 135 | Remove debris from building and do final clean-up | Project2 | 4 | 4 | 2027-08-12 | 2027-08-17 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 0
FALSE |  | 138 | Complete elevator inspection and certification | Project2 | 3 | 3 | 2027-08-18 | 2027-08-20 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 0
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project2 | 20 | 20 | 2027-07-26 | 2027-08-20 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 17
FALSE |  | 136 | Substantial completion date | Project2 | 1 | 1 | 2027-08-18 | 2027-08-18 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 19
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 136 | Substantial completion date | Project2 | 1 | 1 | 2027-08-18 | 2027-08-18 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 19

## 8-22-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
8/22/2027: Detailed View | 8/22/2027: Detailed View | 8/22/2027: Detailed View | 8/22/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 139 | Perform architect's inspection | Project2 | 1 | 1 | 2027-08-23 | 2027-08-23 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 0
FALSE |  | 140 | Perform local building agency inspection | Project2 | 1 | 1 | 2027-08-24 | 2027-08-24 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project2 | 1 | 1 | 2027-08-25 | 2027-08-25 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project2 | 10 | 10 | 2027-08-26 | 2027-09-08 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 139 | Perform architect's inspection | Project2 | 1 | 1 | 2027-08-23 | 2027-08-23 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 0
FALSE |  | 140 | Perform local building agency inspection | Project2 | 1 | 1 | 2027-08-24 | 2027-08-24 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project2 | 1 | 1 | 2027-08-25 | 2027-08-25 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 139 | Perform architect's inspection | Project2 | 1 | 1 | 2027-08-23 | 2027-08-23 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 0
FALSE |  | 140 | Perform local building agency inspection | Project2 | 1 | 1 | 2027-08-24 | 2027-08-24 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 0
FALSE |  | 141 | Perform Fire Marshal's inspection | Project2 | 1 | 1 | 2027-08-25 | 2027-08-25 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 0

## 8-29-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
8/29/2027: Detailed View | 8/29/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 142 | Complete punch list items from all inspections | Project2 | 10 | 10 | 2027-08-26 | 2027-09-08 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0

## 9-5-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
9/5/2027: Detailed View | 9/5/2027: Detailed View | 9/5/2027: Detailed View | 9/5/2027: Detailed View | 9/5/2027: Detailed View | 9/5/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 142 | Complete punch list items from all inspections | Project2 | 10 | 10 | 2027-08-26 | 2027-09-08 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 143 | Obtain certificate of occupancy | Project2 | 2 | 2 | 2027-09-09 | 2027-09-10 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 142 | Complete punch list items from all inspections | Project2 | 10 | 10 | 2027-08-26 | 2027-09-08 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 143 | Obtain certificate of occupancy | Project2 | 2 | 2 | 2027-09-09 | 2027-09-10 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 143 | Obtain certificate of occupancy | Project2 | 2 | 2 | 2027-09-09 | 2027-09-10 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 1

## 9-12-2027 Details
Fuse® Analyst Report
Workbook: P-P5 - 288 Activities
Quick Add Metrics
Created on: 6/21/2026
Created by: dpolitte
9/12/2027: Detailed View | 9/12/2027: Detailed View | 9/12/2027: Detailed View | 9/12/2027: Detailed View
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 144 | Issue final completion documents including warranties | Project2 | 1 | 1 | 2027-09-13 | 2027-09-13 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project2 | 1 | 1 | 2027-09-14 | 2027-09-14 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 144 | Issue final completion documents including warranties | Project2 | 1 | 1 | 2027-09-13 | 2027-09-13 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project2 | 1 | 1 | 2027-09-14 | 2027-09-14 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 144 | Issue final completion documents including warranties | Project2 | 1 | 1 | 2027-09-13 | 2027-09-13 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 0
FALSE |  | 145 | Issue final request for payment | Project2 | 1 | 1 | 2027-09-14 | 2027-09-14 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0