## Ribbon View
Fuse® Analyst Report
Workbook: Hard_File_update vs update2_Fuse - 282 Activities
Quick Add Metrics
Created on: 7/9/2026
Created by: dpolitte
Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
|  | 2026-07-01 | 2026-07-01 | 2026-08-01 | 2026-08-01 | 2026-09-01 | 2026-09-01 | 2026-10-01 | 2026-10-01 | 2026-11-01 | 2026-11-01 | Status Date | Missing Logic | Logic Density™ | Critical | Hard Constraints | Negative Float | Insufficient Detail™ | Number of Lags | Number of Leads | Merge Hotspot | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Avg Float | Max Float | CV | SV | SPI | CPI | EAC | EAC(CPI) | EAC(Composite) | TCPI(BAC) | TCPI(EAC) | TCPI(EAC) to CPI | PV (BCWS) | EV (BCWP) | AC (ACWP) | %Schedule | %Spent | %Complete | %Spent (EAC) | VAC | BAC | EAC | AC (ACWP) | %Spent | %Spent (EAC) | VAC | BAC | SV(t) | SPI(t) | Overrun | $ Cost Underrun | $ Cost Overrun | $ Total Cost | $ Actual Cost | $ Remaining Cost | $ Cost Discrepancy | $ Budget Cost | $ Cost per Day | Negative Planned Cost | Negative Actual Cost | Score
Ribbons | Hard_File_updated | [10 empty] | 2026-08-11 | 10 | 2.05 | 33 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 9 | ✓ | 1 | 0.55 | 7 | 54 | -4000 | 800 | 1.05 | 0.81 | 137400 | 165162 | 158288 | 1.04 | 1 | 0.19 | 16000 | 16800 | 20800 | 12% | 16% | 13% | 15% | -4000 | 133400 | 1325 | 416 | 33% | 31% | -80 | 1245 | 51 | 0.8 | 2 | N/A | 14000 | 137400 | 20800 | 116600 | 4000 | 133400 | 864 | 0 | 0 | 0
Ribbons | Hard_File_updated | [11 empty] | 9% |  | 32% | 0% | 0% | 2% | 0% | 0% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 4% | 0% | 0% | 0% | 0% | 3% | 82% | [5 empty] | -24% | 5% | [15 empty] | -3% | [5 empty] | -6% |  |  |  | 2% | 0% | 10% | 100% | 15% | 85% | 3% | 100% |  | 0% | 0%
Ribbons | Hard_File_updated2 | [10 empty] | 2026-09-10 | 9 | 2.07 | 53 | 0 | 53 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 43 | 0 | 30 | 0 | 1 | 33 | ✓ | 0.93 | 0.59 | 9 | 62 | -14405 | -14540 | 0.77 | 0.78 | 146859 | 172063 | 203647 | 1.21 | 1.01 | 0.24 | 64240 | 49700 | 64105 | 48% | 48% | 37% | 44% | -13459 | 133400 | 1399 | 753 | 60% | 54% | -154 | 1245 | -73 | 1.14 | 6 | 7446 | 36613 | 146859 | 63763 | 83096 | 13459 | 133400 | 907 | 0 | 0 | 1
Ribbons | Hard_File_updated2 | [11 empty] | 8% |  | 70% | 0% | 70% | 2% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 3% | 74% | 0% | 52% | 0% | 2% | 75% | [5 empty] | -29% | -23% | [15 empty] | -10% | [5 empty] | -12% |  |  |  | 5% | 5% | 25% | 107% | 43% | 57% | 10% | 100% |  | 0% | 0%
Phase Analyzer | Status Date | 2026-07-01: 2026-08-11; 2026-08-01: 2026-08-11; 2026-09-01: 2026-08-11; 2026-10-01: 2026-08-11; 2026-11-01: 2026-08-11
Phase Analyzer | WBS | 2026-07-01: 2; 2026-08-01: 2; 2026-09-01: 6; 2026-10-01: 6; 2026-11-01: 8
Phase Analyzer | New Activity - Created (Snapshot) | 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0; 2026-11-01: 0
Phase Analyzer | New Activity - Already Finished (Snapshot) - check/compare | 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0; 2026-11-01: 0
Phase Analyzer | New Activity - Finished in Status Period (Snapshot) - check/compare | 2026-07-01: N/A; 2026-08-01: N/A; 2026-09-01: N/A; 2026-10-01: N/A; 2026-11-01: N/A
Phase Analyzer | Specific Task Start | 2026-07-01: N/A; 2026-08-01: N/A; 2026-09-01: N/A; 2026-10-01: N/A; 2026-11-01: N/A
Phase Analyzer | Specific Task Finish | 2026-07-01: N/A; 2026-08-01: N/A; 2026-09-01: N/A; 2026-10-01: N/A; 2026-11-01: N/A
Phase Analyzer | Score | 2026-07-01: 100; 2026-08-01: 100; 2026-09-01: 100; 2026-10-01: 100; 2026-11-01: 100

## Ribbon Analysis
Fuse® Analyst Report
Workbook: Hard_File_update vs update2_Fuse - 282 Activities
Quick Add Metrics
Created on: 7/9/2026
Created by: dpolitte
Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Status Date | Missing Logic | Logic Density™ | Critical | Hard Constraints | Negative Float | Insufficient Detail™ | Number of Lags | Number of Leads | Merge Hotspot | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Avg Float | Max Float | CV | SV | SPI | CPI | EAC | EAC(CPI) | EAC(Composite) | TCPI(BAC) | TCPI(EAC) | TCPI(EAC) to CPI | PV (BCWS) | EV (BCWP) | AC (ACWP) | %Schedule | %Spent | %Complete | %Spent (EAC) | VAC | BAC | EAC | AC (ACWP) | %Spent | %Spent (EAC) | VAC | BAC | SV(t) | SPI(t) | Overrun | $ Cost Underrun | $ Cost Overrun | $ Total Cost | $ Actual Cost | $ Remaining Cost | $ Cost Discrepancy | $ Budget Cost | $ Cost per Day | Negative Planned Cost | Negative Actual Cost | Score
Ribbons | Hard_File_updated | 2026-08-11 | 10 | 2.05 | 33 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 9 | ✓ | 1 | 0.55 | 7 | 54 | -4000 | 800 | 1.05 | 0.81 | 137400 | 165162 | 158288 | 1.04 | 1 | 0.19 | 16000 | 16800 | 20800 | 12% | 16% | 13% | 15% | -4000 | 133400 | 1325 | 416 | 33% | 31% | -80 | 1245 | 51 | 0.8 | 2 | N/A | 14000 | 137400 | 20800 | 116600 | 4000 | 133400 | 864 | 0 | 0 | 0
Ribbons | Hard_File_updated2 | 2026-09-10 | 9 | 2.07 | 53 | 0 | 53 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 43 | 0 | 30 | 0 | 1 | 33 | ✓ | 0.93 | 0.59 | 9 | 62 | -14405 | -14540 | 0.77 | 0.78 | 146859 | 172063 | 203647 | 1.21 | 1.01 | 0.24 | 64240 | 49700 | 64105 | 48% | 48% | 37% | 44% | -13459 | 133400 | 1399 | 753 | 60% | 54% | -154 | 1245 | -73 | 1.14 | 6 | 7446 | 36613 | 146859 | 63763 | 83096 | 13459 | 133400 | 907 | 0 | 0 | 1
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Status Date | Missing Logic | Logic Density™ | Critical | Hard Constraints | Negative Float | Insufficient Detail™ | Number of Lags | Number of Leads | Merge Hotspot | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Avg Float | Max Float | CV | SV | SPI | CPI | EAC | EAC(CPI) | EAC(Composite) | TCPI(BAC) | TCPI(EAC) | TCPI(EAC) to CPI | PV (BCWS) | EV (BCWP) | AC (ACWP) | %Schedule | %Spent | %Complete | %Spent (EAC) | VAC | BAC | EAC | AC (ACWP) | %Spent | %Spent (EAC) | VAC | BAC | SV(t) | SPI(t) | Overrun | $ Cost Underrun | $ Cost Overrun | $ Total Cost | $ Actual Cost | $ Remaining Cost | $ Cost Discrepancy | $ Budget Cost | $ Cost per Day | Negative Planned Cost | Negative Actual Cost | Score
Ribbons | Hard_File_updated |  | 9% |  | 32% | 0% | 0% | 2% | 0% | 0% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 4% | 0% | 0% | 0% | 0% | 3% | 82% | [5 empty] | -24% | 5% | [15 empty] | -3% | [5 empty] | -6% |  |  |  | 2% | 0% | 10% | 100% | 15% | 85% | 3% | 100% |  | 0% | 0%
Ribbons | Hard_File_updated2 |  | 8% |  | 70% | 0% | 70% | 2% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 3% | 74% | 0% | 52% | 0% | 2% | 75% | [5 empty] | -29% | -23% | [15 empty] | -10% | [5 empty] | -12% |  |  |  | 5% | 5% | 25% | 107% | 43% | 57% | 10% | 100% |  | 0% | 0%

## Hard_File_updated1
Fuse® Analyst Report
Workbook: Hard_File_update vs update2_Fuse - 282 Activities
Quick Add Metrics
Created on: 7/9/2026
Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Number of Predecessors | Number of Successors | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 0 | 1 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 1 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 1 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 1 | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 1 | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 1 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 1 | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 1 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Critical
Number of critical activities
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Insufficient Detail™
Number of activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Notes | Id | Description | Project | Original Duration | Number of Predecessors | Number of Successors | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 3 | 1 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
1. Logic
Number of activities that are missing a predecessor, a successor or both. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
6. High Float
Number of activities with total float greater than 2 months. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
10. Resources
Number of activities that do not have resources/costs assigned
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
11. Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
Overrun
Number of activities where total cost is greater than budgeted cost.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
$ Cost Overrun
A currency measure of the difference between total budgeted cost and total cost of all over-budget activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
$ Actual Cost
A currency measure of the actual amount paid or incurred, as opposed to estimated cost or standard cost.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
$ Cost Discrepancy
A currency measure of the difference between budgeted and current cost.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0

## Hard_File_updated22
Fuse® Analyst Report
Workbook: Hard_File_update vs update2_Fuse - 282 Activities
Quick Add Metrics
Created on: 7/9/2026
Created by: dpolitte
Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Number of Predecessors | Number of Successors | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated2 | 0 | 0 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 1 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 1 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 1 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 1 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 1 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 1 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 1 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Critical
Number of critical activities
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Insufficient Detail™
Number of activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Notes | Id | Description | Project | Original Duration | Number of Predecessors | Number of Successors | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 3 | 1 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
6. High Float
Number of activities with total float greater than 2 months. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
7. Negative Float
Activities that are incomplete and have total float less than 0 working days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
9. Invalid Forecast Dates
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
10. Resources
Number of activities that do not have resources/costs assigned
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
11. Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
Overrun
Number of activities where total cost is greater than budgeted cost.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
$ Cost Underrun
A currency measure of the difference between total budgeted cost and total cost of all under-budget activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
$ Cost Overrun
A currency measure of the difference between total budgeted cost and total cost of all over-budget activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
$ Actual Cost
A currency measure of the actual amount paid or incurred, as opposed to estimated cost or standard cost.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated2 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
$ Cost Discrepancy
A currency measure of the difference between budgeted and current cost.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2

## Phase Analysis
Fuse® Analyst Report
Workbook: Hard_File_update vs update2_Fuse - 282 Activities
Quick Add Metrics
Created on: 7/9/2026
Created by: dpolitte
Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line | Time Line
|  | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01
Phase Analyzer | Status Date | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-11
Phase Analyzer | WBS | 2 | 2 | 6 | 6 | 8
Phase Analyzer | New Activity - Created (Snapshot) | 0 | 0 | 0 | 0 | 0
Phase Analyzer | New Activity - Already Finished (Snapshot) - check/compare | 0 | 0 | 0 | 0 | 0
Phase Analyzer | New Activity - Finished in Status Period (Snapshot) - check/compare | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Specific Task Start | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Specific Task Finish | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Score | 100 | 100 | 100 | 100 | 100
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line | Time Line
|  | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01
Phase Analyzer | Status Date
Phase Analyzer | WBS
Phase Analyzer | New Activity - Created (Snapshot)
Phase Analyzer | New Activity - Already Finished (Snapshot) - check/compare
Phase Analyzer | New Activity - Finished in Status Period (Snapshot) - check/compare
Phase Analyzer | Specific Task Start
Phase Analyzer | Specific Task Finish
Phase Analyzer | Score